## Notice to Proceed
As Of February 12, 2010
Row | State | County | Urban Area | Cong. District | Project # | Project Description | Improvement Type | Proceed Date | Work Start Date | Estimated Completion Date | Total ARRA Obligations | Length (Miles)
1 | Alabama | MADISON | HUNTSVILLE | 05 | 0001537 | This project constructs the mainline of US-231/431 with overpasses at Max Luther and Sparkman Drive. The mainline will be four and six lanes with a concrete median divider for approximately 1 mile. | New Construction | 08/10/2009 | 08/30/2009 | 06/01/2011 | 21866586.41 | 1.03
2 | Alabama | HOUSTON | DOTHAN | 02 | 0001538 | This project will upgrade the bridge rails to current safety standards for bridges with inventory number 006900 and 006901 over Big Creek on US Highway 231 in Houston County | Pavement Improvement | 05/13/2009 | 06/25/2009 | 04/01/2010 | 195000 | 0
3 | Alabama | HOUSTON | DOTHAN | 02 | 0001539 | This project involve the repaving of approximately 6 miles of US Highway 231 from the Florida State line to just north of County Road 93 (Smithville Road) south of Dothan | Pavement Improvement | 05/13/2009 | 06/18/2009 | 04/01/2010 | 2850120.19 | 6.082
4 | Alabama | RUSSELL | COLUMBUS (GA) | 03 | 0001546 | This project involves the repaving of 10 miles of US Highway 431 from Old Seale Highway to just south of US Highway 280 in Russell County | Pavement Improvement | 09/25/2009 | 11/06/2009 | 07/01/2010 | 4541092.12 | 10.33
5 | Alabama | CHAMBERS |  | 03 | 0001553 | This project will improve the curves along SR-1(US-431) from one mile south of SR-147 to south of Sturkie and provide new traffic stripe. | Safety/Traffic Management | 10/22/2009 | 12/11/2009 |  | 229544.17 | 2
6 | Alabama | CLEBURNE |  | 03 | 0001554 | SR-1 (US-431) SAFETY IMPROVEMENTS IN CURVES AT MP 211.9, MP 213.7 AND MP 219.3 TO 220.2 | Safety/Traffic Management | 01/07/2010 |  |  | 1113140.91 | 0
7 | Alabama | COLBERT | FLORENCE | 05 | 0002534 | This project involves the repaving and 2 foot safety widening for about 4 miles of US Highway 72 from west of Cane Creek to east of Dry in Colbert County | Pavement Improvement | 05/15/2009 | 07/02/2009 | 04/10/2010 | 1659387.98 | 3.673
8 | Alabama | LIMESTONE |  | 05 | 0003544 | This project involves the repaving and widening of about 3 miles of US Highway 31 from just south of Cactus Street to Interstate 65 near Athens | Pavement Improvement | 05/04/2009 | 06/22/2009 | 04/01/2010 | 1395000 | 2.655
9 | Alabama | BALDWIN |  | 01 | 0003546 | This project involves the repaving of aproximately 7 miles of the Gulf Shores Parkway from Stapleton to the Bay Minette south city limits | Pavement Improvement | 05/13/2009 | 06/24/2009 | 04/01/2010 | 2997585.19 | 7.38
10 | Alabama | BUTLER |  | 02 | 0003550 | This project involves the repaving and 2 foot widening of approximately 5 miles of US Highway 31 from the Conecuh County line to a bout a mile north of Persimmon Creek of Butler County | Pavement Improvement | 07/23/2009 | 09/16/2009 | 05/01/2010 | 2255932.06 | 5.215
11 | Alabama | LOWNDES |  | 02 | 0003551 | This project involves the repaving and 2 foot widening of approximately 10 miles of US Highway 31 near Fort Deposit from the Junction of State Highway 185 to the Montgomery County line | Pavement Improvement | 08/13/2009 | 09/30/2009 | 06/01/2010 | 3407833.03 | 9.637
12 | Alabama | CONECUH |  | 02 | 0003552 | This project involves the repaving of about 12 miles of US Highway 31 from US Highway 84 to the Butler County Line in Conecuh County | Pavement Improvement | 08/13/2009 | 09/15/2009 | 06/01/2010 | 2579722.58 | 12.127
13 | Alabama | CLARKE |  | 01 | 0005526 | This project involves the repaving of approximately 5 miles of State Highway 5 in Clarke County from US Highway 43 to the Wilcox County Line north of Thomasville | Pavement Improvement | 05/01/2009 | 07/07/2009 | 04/01/2010 | 1619174.16 | 4.795
14 | Alabama | AUTAUGA | MONTGOMERY | 02 | 0006538 | This project involves the repaving and 2 foot widening of 12 miles of US Highway 82 from just west of County Road 40 to State Highway 206 in Pratville | Pavement Improvement | 08/14/2009 | 08/31/2009 | 06/01/2010 | 3850345.25 | 12
15 | Alabama | TUSCALOOSA | TUSCALOOSA | 07 | 0007519 | This project involves the repaving of US Highway 11 from the Greene County Line to just south of the Warrior River Bridge in the Fosters. The project also include the repaving of Holly Springs Road f | Pavement Improvement | 09/16/2009 | 10/13/2009 | 07/01/2010 | 4194899.73 | 9.826
16 | Alabama | GREENE |  | 07 | 0007520 | This project invovles the repaving and widening of 10 miles US Highway 11 from north of Greentrack Road to Tuscaloosa County Line near Knoxville | Pavement Improvement | 09/15/2009 | 10/20/2009 | 07/01/2010 | 3463826.99 | 9.634
17 | Alabama | MACON |  | 03 | 0008554 | This project involves the repaving and widening of 9 miles of US Highway 80 in Macon County from near the junction of State Highway 186 to the Lee County line | Pavement Improvement | 08/14/2009 | 09/29/2009 | 06/01/2010 | 2698634.49 | 9.03
18 | Alabama | MONTGOMERY |  | 03 | 0009509 | This project will add two additional lanes to the existing two lanes to provide a four-lane facility on US Highway 331 from approximately one-half mile south of State Highway 94 to the end of the pres | Pavement Widening | 11/18/2009 |  |  | 18869375.36 | 4.21
19 | Alabama | WILCOX |  | 07 | 0010520 | This project involves the repaving of 2 miles of State Highway 10 (Camden Bypass) from State Highway 28 to State Highway 28 in Camden. Wilcox County | Pavement Improvement | 08/04/2009 | 09/04/2009 | 06/01/2010 | 631951.38 | 1.964
20 | Alabama | CRENSHAW |  | 02 | 0010521 | This project involves the repaving and widening for 10 miles of State Highway 10 from the Butler County line to US Highway 331 in Crenshaw County | Pavement Improvement | 08/12/2009 | 09/04/2009 | 06/01/2010 | 3252048.79 | 9.872
21 | Alabama | LAUDERDALE |  | 05 | 0013503 | This project will add two additional lanes to the existing two lanes to ultimately provide a four-lane facility from the end of the present four-lane at Killen to State Highway 64. This project will | Pavement Improvement | 12/02/2009 | 12/15/2009 |  | 10060231.81 | 5.066
22 | Alabama | BULLOCK |  | 02 | 0015515 | This project involves the repaving of a mile of US Highway 29 from State Highway 197 to US Highway 82 in Union Springs | Pavement Improvement | 09/10/2009 | 09/28/2009 | 07/01/2010 | 435883.86 | 1.01
23 | Alabama | ESCAMBIA |  | 01 | 0015516 | This project involves the repaving of over 11 miles of US Highway 29 from 1 mile south of Maye Creek to just south of Smith Creek in Escambia County | Pavement Improvement | 01/26/2010 |  |  | 2053006.16 | 11.42
24 | Alabama | LEE | AUBURN-OPELIKA | 03 | 0015517 | This project involves the repaving of about 2 miles of US Highway 29 from the Macon County Line to Sand Hill Road in Lee County | Pavement Improvement | 07/29/2009 | 09/16/2009 | 05/01/2010 | 913000 | 1.86
25 | Alabama | CHOCTAW |  | 07 | 0017525 | This project involves the repaving and widening of approximately 4 miles of State Highway 17 in Chocktaw County from about 1 mile south of County Road 18 to just north of County Road 28 east of Needha | Pavement Improvement | 07/29/2009 | 08/30/2009 | 05/01/2010 | 1278321.13 | 3.571
26 | Alabama | CHOCTAW |  | 07 | 0017526 | This project involves the repaving of 5 miles of State Highway 17 (Mulberry Avenue) from just north of County Road 28 to north of the Butler city limits in Choctaw County | Pavement Improvement | 07/29/2009 | 09/10/2009 | 05/01/2010 | 1288681.05 | 5.541
27 | Alabama | LAMAR |  | 04 | 0017528 | This project involves the repaving of approximately 8 miles of State Highway 17 from about a mile north of County Road 29 to County Road 30 in Sulligent | Pavement Improvement | 09/11/2009 | 11/13/2009 | 07/01/2010 | 6356216.29 | 8.3
28 | Alabama | MARION |  | 04 | 0017529 | This project involves the repaving of approximately 7 miles of State Highway 17 from the Lamar County line to State Highway 4 south of Hamilton in Marion County | Pavement Improvement | 05/04/2009 | 07/06/2009 | 04/01/2010 | 1770059.52 | 7.191
29 | Alabama | SUMTER |  | 07 | 0017530 | This project involves the repaving of 6 miles of State Highway 17 from State Highway 28 to County Road 24 in Sumter County | Pavement Improvement | 09/14/2009 |  | 07/01/2010 | 2721996.1 | 5.97
30 | Alabama | WASHINGTON |  | 01 | 0017531 | This project involves the repaving of 9 miles of State Highway 17 from about 2 miles south of County Road 20 To State Highway 56 in Chatom | Pavement Improvement | 09/28/2009 |  | 07/01/2010 | 2957542.17 | 9.042
31 | Alabama | PICKENS |  | 04 | 0017532 | This project involves the repaving of 2.5 miles of State Highway 17 from the Carrollton south city limits to just north of the north city limits in Pickens County | Pavement Improvement | 09/21/2009 | 10/13/2009 | 07/01/2010 | 2095405.03 | 2.4
32 | Alabama | LAUDERDALE |  | 05 | 0020510 | This project involves the repaving of approximately 8 miles of State Highway 20 from the Tennessee State line to south of County Road 22 at the Natchez Trace Parkway in Lauderdale County | Pavement Improvement | 09/23/2009 | 10/09/2009 | 07/01/2010 | 1980526.45 | 7.84
33 | Alabama | MONROE |  | 01 | 0021522 | This project involves the repaving of approximately 6 miles of State Highway 21 in Monroe County from the north end of the Litte River Bridge at the Escambia County line to County Road 8 north of Uria | Pavement Improvement | 08/17/2009 | 09/29/2009 | 06/01/2010 | 2193633.16 | 6.245
34 | Alabama | MONROE |  | 01 | 0021523 | This project involves the repaving of approximately 6 miles of State Highway 21 from north of County Road 8 to south of County Road 10 in Monroe County | Pavement Improvement | 08/17/2009 | 09/29/2009 | 06/01/2010 | 2171063.85 | 6.425
35 | Alabama | ESCAMBIA |  | 01 | 0021527 | This project involves the repaving of South Main Street in the town of Atmore from the Florida State line to about 1 mile north | Pavement Improvement | 08/18/2009 | 09/30/2009 | 06/01/2010 | 325434.98 | 0.968
36 | Alabama | CALHOUN |  | 03 | 0021528 | This project involves the repaving of 5 miles of Jacksonville State University Highway from Maxwellborn Road to near Foothills Drive in the town of Piedmont | Pavement Improvement | 09/15/2009 | 01/04/2010 | 07/01/2010 | 1786569.53 | 4.76
37 | Alabama | DALLAS |  | 07 | 0022509 | This project involves the repaving and 2 foot widening of approximately 19 miles of State Highway 22 from State Highway 5 to State Highway 219 in Dallas County southwest of Selma | Pavement Improvement | 08/04/2009 | 09/14/2009 | 06/01/2010 | 4095666.24 | 19.181
38 | Alabama | HALE |  | 07 | 0025520 | This project involves repaving and widening fro about 5 miles of State Highway 25 in Hale County from County Road 29 to the Bibb County line | Pavement Improvement | 08/19/2009 | 10/15/2009 | 06/01/2010 | 1811864.63 | 4.534
39 | Alabama | DALE |  | 02 | 0027504 | This project involves the repaving and widening of approximately 10 miles of State Highway 27 in Dale County from east of County Road 59 to the Henry County line | Pavement Improvement | 01/20/2010 |  |  | 2754292.17 | 9.591
40 | Alabama | COFFEE |  | 02 | 0027505 | This project involves the repaving and widening of approximately 5 miles of State Highway 27 northeast of Enterprise from Indego Place to the Dale County line | Pavement Improvement | 08/04/2009 | 09/30/2009 | 06/01/2010 | 1605503.37 | 5.217
41 | Alabama | WINSTON |  | 04 | 0033502 | This project involves the repaving of 5 miles of State Highway 24 from County Road 460 to near County Road 320 in Lawrence County | Pavement Improvement | 08/18/2009 | 08/31/2009 | 06/01/2010 | 1600500.71 | 4.945
42 | Alabama | JACKSON |  | 05 | 0035509 | This project involves the repaving and 2 foot safety widening for approximately 13 miles of State Highway 35 from State Highway 79 westerly through Woodville to US Highway 72 in Jackson County | Pavement Improvement | 05/04/2009 | 06/29/2009 | 04/01/2010 | 1500000 | 13.29
43 | Alabama | SHELBY | BIRMINGHAM | 06 | 0038522 | This project involves the repaving of over 6 miles of US-280 from Hugh Daniel Drive to Old US 280 Highway | Pavement Improvement | 05/14/2009 | 06/15/2009 | 04/01/2010 | 6551704.45 | 6.25
44 | Alabama | CLAY |  | 03 | 0049502 | This project involves the repaving of about 8 miles of State Highway 49 fromt the Tallapoosa County line to State Highway 77 near the town of Ashland | Pavement Improvement | 07/21/2009 | 09/11/2009 | 05/01/2010 | 2409572.53 | 7.334
45 | Alabama | TALLAPOOSA |  | 03 | 0049503 | This project involves the resurfacing and traffic stripe at various sites on SR-49. | Safety/Traffic Management | 01/07/2010 |  |  | 723703.78 | 0
46 | Alabama | BARBOUR |  | 02 | 0051503 | This project involves the repaving and and widening of approximately 10 miles of State Highway 51 in Barbour County from just South of State Highway 239 to the Bullock County line | Pavement Improvement | 08/07/2009 | 09/23/2009 | 06/01/2010 | 2934528.24 | 10.325
47 | Alabama | DALE |  | 02 | 0051504 | This project involves the repaving and widening of 3 miles of State Highway 51 in Dale County from the Coffee County line to US Highway 231 | Pavement Improvement | 01/20/2010 |  |  | 1008604.6 | 3.107
48 | Alabama | DALE |  | 02 | 0053537 | This project will upgrade the bridge rails to current safety standards for bridges with inventory numbers 005532 and 005533 over Little Claybank Creek and bridges with inventory numbers 005571 and 009 | Bridge Improvement | 05/04/2009 | 06/05/2009 | 04/01/2010 | 155000 | 6.39
49 | Alabama | DALE |  | 02 | 0053538 | This project involves the repaving of about 6.5 miles of US Higway 231 from just south of State Highway 27 north to County Road 2 in Ozark | Pavement Improvement | 05/04/2009 | 06/30/2009 | 04/01/2010 | 2768226.13 | 6.39
50 | Alabama | ST CLAIR |  | 06 | 0053543 | This project involves the repaving of 7.5 miles of US Highway 231 from just north of Interstate 20 to a couple miles north of Wattsville in Ashville. | Pavement Improvement | 07/16/2009 | 08/22/2009 | 05/01/2010 | 1600829.13 | 7.51
51 | Alabama | BUTLER |  | 02 | 0055505 | This project involves the repaving of a little over 1 mile of State Highway 55 from the Conecuh County Line to US Highway 31 in McKenzie | Pavement Improvement | 07/23/2009 | 09/02/2009 | 05/01/2010 | 546999.66 | 1.169
52 | Alabama | MARENGO |  | 07 | 0069521 | This project involves the widening of approximately 12 miles of State Highway 69 in Marengo County from US Highway 43 to the Hale County line | Pavement Improvement | 07/23/2009 | 08/25/2009 | 05/01/2010 | 920953.49 | 11.643
53 | Alabama | FRANKLIN |  | 04 | 0069523 | This project involves the repaving of about 4 miles of State Highway 69 from Interstate 65 in Good Hope to the US Highway 31 intersection in Cullman | Pavement Improvement | 07/22/2009 | 09/01/2009 | 05/01/2010 | 1280340.48 | 3.7
54 | Alabama | HALE |  | 07 | 0069525 | This project involves the repaving and extension of culvert pipes to improve roadside safety along 2 milesof State Highway 69 from the Marengo County line to US Highway 80 in Hale County | Pavement Improvement | 07/23/2009 | 08/22/2009 | 05/01/2010 | 486659.58 | 1.994
55 | Alabama | MARENGO |  | 07 | 0069529 | This project involves the repaving of about 12 miles of State Highway 69 in Marengo County from US Highway 43 to the Hale County line | Pavement Improvement | 07/23/2009 | 08/30/2009 | 05/01/2010 | 2904189.23 | 11.643
56 | Alabama | BLOUNT |  | 04 | 0075515 | This project involves the repaving of aprroximately 4 miles of State Highway 75 from from Brooks Lane (County Road 363) in Allgood to 2nd Street (County Road 58) in Oneonta | Pavement Improvement | 09/15/2009 | 10/02/2009 | 07/01/2010 | 1730844.36 | 3.57
57 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 0079510 | This project involvesthe repaving of approximately 5 miles of State Highway 79 (Pinson Valley Parkway) from Winewood Road to State Highway 151 just west of Pinson in Jefferson County | Pavement Improvement | 07/21/2009 | 09/02/2009 | 05/01/2010 | 2399825.05 | 5.2
58 | Alabama | PIKE |  | 02 | 0093501 | This project involves the repaving of about 2 miles of State Highway 93 from Us Highway 231 to the North city limits of Brundidge | Pavement Improvement | 08/10/2009 | 09/02/2009 | 06/01/2010 | 840752.4 | 2.25
59 | Alabama | MONTGOMERY | MONTGOMERY | 03 | 0097503 | This project involves the repaving and 2 foot widening of approximately 1 mile State Highway 97 from Crenshaw County line to north of US Highway 31 near Letohatchee | Pavement Improvement | 08/13/2009 | 09/22/2009 | 06/01/2010 | 569032.16 | 1.187
60 | Alabama | WALKER |  | 04 | 0102530 | This project involves the repaving of about 7 miles of State Highway 102 from the Fayette County Line to the intersection with Old Birmingham Highway in Walker County | Pavement Improvement | 12/29/2009 |  |  | 1055859.86 | 6.896
61 | Alabama | GENEVA |  | 02 | 0103508 | This project involves the repaving and widening of 9 miles of State Highway 103 from the Florida State line to State Highway 52 in Slocomb | Pavement Improvement | 11/16/2009 | 12/04/2009 |  | 2513466.31 | 8.933
62 | Alabama | COOSA |  | 03 | 0115503 | This project involves the repaving of about 3 miles of State Highway 115 from State Highway 9 to US Highway 280 | Pavement Improvement | 07/08/2009 | 09/02/2009 | 05/01/2010 | 1163764.15 | 3.19
63 | Alabama | JACKSON |  | 05 | 0117505 | This project involves the repaving of State Highway 117 in Jackson County from the intersection with State Highway 71 north for about 6 miles. | Pavement Improvement | 01/19/2010 |  |  | 1556825.03 | 5.73
64 | Alabama | WALKER |  | 04 | 0118508 | This project involves the repaving of about 4 miles of US Highway 78 in Carbon Hill from 4th Street to Ripley Loop Road. | Pavement Improvement | 09/25/2009 | 10/09/2009 | 07/01/2010 | 1351912.76 | 3.676
65 | Alabama | AUTAUGA |  | 02 | 0123200 | This project involves the repaving of approximatley 3 miles of Autauga County Road 37 from Autauga County Road 24 to the Chilton County Line and is located North of Billingsley, Alabama. | Pavement Improvement | 01/14/2010 |  |  | 265000 | 0
66 | Alabama | WALKER |  | 04 | 0124500 | This project involves the repaving of approximately 10 miles of Old Birmingham Highway from US Highway 78 south to the intersection with State Highway 69 in Walker County. | Pavement Improvement | 12/29/2009 |  |  | 1818990.69 | 10.896
67 | Alabama | FAYETTE |  | 04 | 0129502 | This project involves the repaving of approximately 7 miles of State Highway 129 from US Highway 43 to County Road 49 in Hubbertville | Pavement Improvement | 08/10/2009 | 08/27/2009 | 06/01/2010 | 1679635.45 | 7.26
68 | Alabama | BIBB |  | 06 | 0139502 | This project involves the repaving of 7 miles of State Highway 139 from Six Mile Creek to just north of the Shelby County line | Pavement Improvement | 09/10/2009 | 10/08/2009 | 07/01/2010 | 2128141.35 | 7.104
69 | Alabama | TALLADEGA |  | 03 | 0148500 | This project involves the repaving and 2 foot widening of about 2 miles of State Highway 148 from State Highway 21 to the east city limits of Sylacauga | Pavement Improvement | 07/23/2009 | 09/06/2009 | 05/01/2010 | 623949.72 | 1.78
70 | Alabama | CHILTON |  | 06 | 0155500 | This project involves the repaving and widening of 4 miles of State Highway 155 in Chilton County from near County Road 33 to the Shelby County line | Pavement Improvement | 08/18/2009 | 09/03/2009 | 06/01/2010 | 1675952.78 | 4.076
71 | Alabama | COLBERT | FLORENCE | 05 | 0157514 | This project involves the repaving and the upgrade of bridge rails to current safety standards along State Highway 157 from the lawrence County Line to State Highway 20 in Colbert County | Pavement Improvement | 09/15/2009 | 09/30/2009 | 07/01/2010 | 3612416.49 | 7.495
72 | Alabama | PERRY |  | 07 | 0175500 | This project involves the repaving and widening of State Highway 175 from State Highway 14 near Heiberger to State Highway 5 in Perry County | Pavement Improvement | 09/11/2009 |  | 07/01/2010 | 1730838.95 | 5.382
73 | Alabama | MOBILE | MOBILE | 01 | 0188501 | This project involves the repaving of about 9 miles of State Highway 188 from Franklin Creek to Oddfellows Cemetery in Baldwin County | Pavement Improvement | 01/26/2010 |  |  | 1478347.69 | 8.67
74 | Alabama | CALHOUN | ANNISTON | 03 | 0192901 | This project provides for grading the road so it can be paved to a four lane roadway from 1500' South of Lake Yahoo to SR-1 (US-431) in Anniston. The project will be partial base and pave wih a bridge | New Construction | 09/21/2009 | 10/09/2009 | 07/01/2011 | 37189383.68 | 2.56
75 | Alabama | GENEVA |  | 02 | 0196500 | This project involves the repaving of Magnolia Avenue from State Highway 52 to State Highway 27 in Geneva | Pavement Improvement | 01/19/2010 |  |  | 638815.99 | 1.69
76 | Alabama | BARBOUR |  | 02 | 0198500 | This project involves the repaving and widening of approximately 2 miles of State Highway 198 in Barbour County from just east of State Highway 239 to State Highway 30 | Pavement Improvement | 12/29/2009 |  |  | 580466.81 | 1.61
77 | Alabama | MOBILE | MOBILE | 01 | 0213502 | This project involves the repaving and widening of about 3 miles of State Highway 213 (Shelton Beach Road) from State Highway 158 (Industrial Parkway) to US Highway 43 (Saraland Boulevard) in Saraland | Pavement Improvement | 07/22/2009 | 08/28/2009 | 05/01/2010 | 653739.91 | 2.88
78 | Alabama | BULLOCK |  | 02 | 0223501 | This project involves the repaving and 2 foot widening of a bout a mile of State Highway 223 (Baskin Street) from the Bullock County High School to the junction of US Highway 82 in Union Springs | Pavement Improvement | 09/10/2009 | 09/28/2009 | 07/01/2010 | 390602.39 | 0.75
79 | Alabama | FRANKLIN |  | 04 | 0241501 | This project involves the repaving of about a mile of State Highway 241 from just south of the Marion County line to State Highway 237 in Franklin County | Pavement Improvement | 07/30/2009 | 08/28/2009 | 05/01/2010 | 703021.14 | 1.024
80 | Alabama | LOWNDES |  | 02 | 0263501 | This project involves the repaving and 2 foot widening of approximately 9 miles of State Highway 263 from the Butler County line to State Highway 21 | Pavement Improvement | 01/26/2010 |  |  | 3106388.17 | 8.48
81 | Alabama | CHEROKEE |  | 03 | 0273500 | The project involves the repaving and widening of approximately 16 miles of State Highway 273 from State Highway 68 in Leesburg to State Highway 35 near Blanche | Pavement Improvement | 08/12/2009 |  | 06/01/2010 | 4016700.1 | 15.836
82 | Alabama | BULLOCK |  | 02 | 0621200 | This project will completely rebuild the pavement structure (full depth reclamation) down to the subgrade, then the pavement will be widened and repaved approximately 8 miles of Bullock County Road 2 | Pavement Improvement | 10/22/2009 | 11/18/2009 |  | 265000 | 0
83 | Alabama | CHAMBERS |  | 03 | 0928200 | This project will completely rebuild the pavement structure (full depth reclamation) down to the subgrade, then the pavement will be repaved approximately 5 miles of County Road 267 in Chambers County | Pavement Improvement | 07/27/2009 | 09/02/2009 | 05/01/2011 | 265000 | 0
84 | Alabama | CHEROKEE |  | 03 | 1006201 | "This project involves the repaving of approximately 4 miles of Cherokee County Road 71 (Centre Rd.) from 0.6 miles north of Cherokee County Road 59 ( to the Terrapin Creek Bridge south of Centre | Pavement Improvement | 12/29/2009 |  |  | 265000 | 0
85 | Alabama | COLBERT | FLORENCE | 05 | 1709200 | This project involves the repaving of County Road 57 from County Road 61 to the Joe Wheeler Highway (State Highway 20) in Tuscumbia | Pavement Improvement | 08/19/2009 | 09/30/2009 | 06/26/2010 | 330972.08 | 0
86 | Alabama | COLBERT | FLORENCE | 05 | 1717200 | This project involves the repaving of 1 mile of River Road from County Road 48 to Brick School Road in Muscle Shoals | Pavement Improvement | 10/13/2009 |  |  | 135105.43 | 0
87 | Alabama | CONECUH |  | 02 | 1818202 | "This project involves the repaving of approximately 4 miles of Conecuh County Road 23 from U.S. Highway 31(N. Jackson Street) northwesterly to Interstate 65 (I-65) north of Castleberry | Pavement Improvement | 11/09/2009 |  |  | 265000 | 0
88 | Alabama | COFFEE |  | 02 | 1E34600 | This project involves the repaving of County Road 709 in Enterprise from State Highway 167 to State Highway 134 | Pavement Improvement | 09/11/2009 | 10/12/2009 | 07/01/2010 | 265000 | 0
89 | Alabama | ELMORE |  | 02 | 2601201 | PAVE SHOULDERS & TRAFFIC EDGE STRIPE ON CR-4 (RIFLE RANGE ROAD) FROM CR-8 (REDLAND RD) TO CR-234 (MITCHELL CREEK RD),ECP 26-08-09 | Pavement Improvement | 01/26/2010 |  |  | 297933.3 | 0
90 | Alabama | ESCAMBIA |  | 01 | 2710200 | "This project involves the widening and repaving of approximately 5 miles of Escambia County Road 17 (Stanley Rd.) from Escambia County Road 27 (Robinsonville Rd.) to Alabama Highway Route 113 | Pavement Improvement | 01/05/2010 |  |  | 265000 | 0
91 | Alabama | GENEVA |  | 02 | 3131200 | "This project involves the repaving and widening of approximately 3 miles of Geneva County Road 4 (Goathill Road) from Alabama State Highway 87 to Geneva County Road 120 (Ausley Road) West of Geneva | Other | 11/09/2009 |  |  | 265000 | 0
92 | Alabama | HENRY |  | 02 | 3408200 | "This project involves the widening and repaving of Henry County Road 99 from Henry County Road 41 to Henry County Road 107 in Abbeville | Pavement Improvement | 08/21/2009 | 09/09/2009 | 06/01/2010 | 265000 | 0
93 | Alabama | HOUSTON |  | 02 | 3500214 | This project will replace the bridge with inventory number 003313 over Cedar Creek on East Cook Road (County Road 438) about a half north of Ed Tolar Road in Houston County | Bridge Replacement | 07/14/2009 | 08/01/2009 | 05/01/2010 | 265000 | 0
94 | Alabama | LAMAR |  | 04 | 3804200 | "This project involves the repaving of approximately 10 miles of Lamar County Road 49 & 20 (Pickens St.) from the Northern Right of Way of the Luxapallila Railroad in Kennedy | Pavement Improvement | 11/04/2009 |  |  | 265000 | 0
95 | Alabama | LAWRENCE |  | 05 | 4000219 | The project involves the replacement of a bridge with the inventory number 003222 on County Road 129 over Pool Creek in Lawrence County | Bridge Replacement | 09/14/2009 | 10/28/2009 | 07/31/2010 | 111054.29 | 0
96 | Alabama | LAWRENCE |  | 05 | 4000220 | "This project will replace the bridge for Sandy Creek on Lawrence County Road 150. The bridge has an inventory number of 002345 and wil be replace by a bridge culvert that has 3 barrels that are 10 f | Pavement Improvement | 11/06/2009 |  |  | 153945.71 | 0
97 | Alabama | MACON |  | 03 | 4424203 | RESURFACE CR-54 FROM EAST NOTASULGA CITY LIMITS TO CR-53-MCP 44-123-09 | Pavement Improvement | 01/19/2010 |  |  | 265000 | 0
98 | Alabama | MORGAN | DECATUR | 04 | 5218200 | This project involves the repaving of South Seneca Drive From the Trinity town limits to Deanna Bridge Highway | Pavement Improvement | 07/01/2009 | 07/02/2009 |  | 55906.97 | 0
99 | Alabama | MORGAN | DECATUR | 04 | 5222200 | This project involves the repaving of less than a mile of Indian Hills Road from Lincoya Circle to Ben Poole Road in the city of Decatur | Pavement Improvement | 07/18/2009 | 07/19/2009 |  | 84137 | 0
100 | Alabama | PERRY |  | 07 | 5303200 | This project involves the repaving of about 7 miles of County Road 12 from 2 miles east of State Highway 183 to State Highway 5 in Perry County | Pavement Improvement | 10/13/2009 |  |  | 265000 | 0
101 | Alabama | PICKENS |  | 07 | 5422200 | FULL DEPTH RECLAMATION, RESURFACING, & STRIPING ON CR-85 FROM THE SUMTER CO. LINE TO SR-17 - PCP 54-06-05 | Pavement Improvement | 12/29/2009 |  |  | 265000 | 0
102 | Alabama | PIKE |  | 02 | 5505202 | This project involves the repaving of County Road 2276 from the Crenshaw County line to County Road 2290 and also the repaving of County Road 2290 from County Road 2276 to County Road 2262 near Hender | Pavement Improvement | 07/16/2009 | 08/15/2009 | 05/01/2010 | 265000 | 0
103 | Alabama | RANDOLPH |  | 03 | 5605200 | This project involves the widening and repaving of Randolph County Road 82 from the Meadows Bridge (Little Tallapoosa River) to Randolph County Road 87. | Pavement Improvement | 09/28/2009 | 10/22/2009 | 07/31/2010 | 265000 | 0
104 | Alabama | RUSSELL |  | 03 | 5704200 | This project will relocate and replace a bridge on Russell County Road 4 over Weolustee Creek north of Pitttsview | Pavement Improvement | 09/30/2009 | 10/09/2009 |  | 265000 | 0
105 | Alabama | SUMTER |  | 07 | 6020200 | "This project involves the repaving and extending the culvert pipes to improve the roadside safety of approximately 2 miles of Sumter County Road 27 from the Mississippi State line south to Sumter Co | Pavement Improvement | 10/16/2009 |  |  | 265000 | 0
106 | Alabama | TALLAPOOSA |  | 03 | 6233200 | "This project includes widening and repaving of approximately 7 milles of Tallapoosa County Road 44 (Dudleyville Road) from Tallapoosa County Road 32 (Denver Road) to the Chambers County Line | Pavement Improvement | 01/07/2010 |  |  | 265000 | 0
107 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 7005600 | This project will realign 3 intersections in the City of Hoover and replace the existing signals. The realignments will improve driver's sight distance and visibility. | Pavement Improvement | 12/15/2009 |  | 07/01/2010 | 1878317.89 | 0
108 | Alabama | JEFFERSON | BIRMINGHAM | 07 | 7045601 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Improvement | 11/12/2009 |  |  | 2624716.25 | 0
109 | Alabama | JEFFERSON | BIRMINGHAM | 07 | 7229601 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Widening | 11/09/2009 |  |  | 2900626.44 | 0
110 | Alabama | MOBILE | MOBILE | 01 | 7548600 | This project involves the repaving about a mile of Springhill Avenue from McGregor Avenue to Intersate 65 in the city of Mobile | Pavement Improvement | 08/27/2009 | 09/03/2009 | 07/01/2010 | 312513.08 | 0
111 | Alabama | MOBILE | MOBILE | 01 | 7548601 | This project involves the repaving of less than a mile of Springhill Avenue from Interstate 65 to Moffet Road in the city of Mobile | Pavement Improvement | 08/27/2009 | 09/03/2009 | 07/01/2010 | 124363.53 | 0
112 | Alabama | MOBILE | MOBILE | 01 | 7573600 | This project involves traffic stripe, markings, legends and pavement markers on CR-41 (Celeste Road) from SR-13 (US-43) in Saraland to Lafitte Road. | Safety/Traffic Management | 12/30/2009 |  |  | 136752.25 | 0
113 | Alabama | MOBILE | MOBILE | 01 | 7615600 | Mobile County will widen the existing 20 eet width pavement of Half Mile Road 2 feet on each side and then resurface with asphalt the entire 24 feet width from Beverly Road eastwardly approximately 2 | Pavement Improvement | 07/24/2009 | 08/29/2009 | 05/01/2010 | 265000 | 0
114 | Alabama | ETOWAH | GADSDEN | 04 | 8104600 | This project constructs a new 4 lane roadway approximately 1 mile long between the intersections of Steel Station / Sutton Bridge Roads to I-759. | Pavement Improvement | 12/15/2009 |  |  | 2138433 | 0
115 | Alabama | MORGAN | DECATUR | 05 | 9229600 | This project involves the repaving of Austinville Road SW from Carridale Street to 14 th Street SW and 14th Street SW to Central Parkway in the city of Decatur | Pavement Improvement | 07/08/2009 | 07/09/2009 |  | 138860 | 0
116 | Alabama | HOUSTON | DOTHAN | 02 | 9412601 | This project involves the repaving of Westgate Parkway from US Highway 84 to US Highway 231 in the city of Dothan | Pavement Improvement | 07/01/2009 | 07/01/2009 |  | 644000 | 0
117 | Alabama | HOUSTON | DOTHAN | 02 | 9441604 | This project involves the resurfacing of South Brannon Stand Road (CR-59) from 0.06 mile north of SR-52 to 0.30 mile north of CR-40 (Fortner Street). | Pavement Improvement | 01/13/2010 |  |  | 303268.56 | 0
118 | Alabama | MOBILE, BALDWIN |  | 01 | CN09208 | "This project will repair badly deteriorated pavements at 16 sites located throughout Mobile and Baldwin Counties. The sites are located on various state | Pavement Improvement | 07/27/2009 | 08/29/2009 | 05/01/2010 | 755598.08 | 0
119 | Alabama | ELMORE | MONTGOMERY | 02 | CN09908 | This project involves the repaving of the Coosa River Parkway from West Bridge Street to US Highway 231 and the repaving of West Bridge Street from the Coosa River Parkway to North Bridge Street in We | Pavement Improvement | 07/30/2009 | 09/01/2009 | 05/01/2010 | 1207835.61 | 3.459
120 | Alabama | LAUDERDALE |  | 05 | CN10201 | "This project involves the repaving of two different roads. Site 1 is South of Lovelace Crossroads and includes approximately 2 miles of Lauderdale County Road 6 from Lauderdale County Road 219 to Ala | Pavement Improvement | 12/28/2009 |  |  | 265000 | 0
121 | Alabama | HOUSTON | DOTHAN | 02 | CN10204 | This project involves the resurfacing of CR-26 (Jordon Avenue) from North ROW SR-12 (US-84) to 0.22 mile east of Glen Lawrence Int. | Pavement Improvement | 01/13/2010 |  |  | 289828.56 | 0
122 | Alabama | ETOWAH | GADSDEN | 04 | I059342 | Reconstructs a portion of existing concrete Interstate 59 near Gadsden by placing a layer of asphalt on the existing roadway and then placing an 11 inch layer of concrete pavement on the asphalt layer | Pavement Improvement | 05/14/2009 | 06/15/2009 | 04/01/2011 | 47525423.51 | 10.913
123 | Alabama | MADISON | HUNTSVILLE | 05 | PE09909 | This project involves the repaving various streets in the city of Huntsville | Other | 07/08/2009 | 07/09/2009 |  | 64974 | 0
124 | Alabama | MADISON | HUNTSVILLE | 05 | PE09910 | This project involves the repaving various streets in the city of Huntsville | Other | 07/08/2009 | 07/09/2009 |  | 150726 | 0
125 | Alabama | LAUDERDALE | FLORENCE | 05 | PE09912 | This project involves the repaving at three differenct sites in Florence. Site #1 is the repaving of about a 1 mile section of Hermitage Drive from Royal Avenue to Helton Drive. Site # 2 is the repa | Other | 08/01/2009 | 08/02/2009 |  | 48985 | 0
126 | Alabama | MORGAN | DECATUR | 04 | PE09913 | This project involves the repaving of 8th Street SE from 16th Avenue to Point Mallard Drive and Point Mallard Drive to Point Mallard Circle in the city of Decatur | Other | 07/17/2009 | 07/18/2009 |  | 21510 | 0
127 | Alabama | MORGAN | DECATUR | 04 | PE09915 | "This project involves the repaving of approximately 4 miles of Morgan County Road 41 (Danville Road) from Morgan County Road 191 (Chapel Hill Rd.) to 2nd Street SW in Decatur | Other | 07/17/2009 | 07/18/2009 |  | 19188 | 0
128 | Alabama | BARBOUR |  | 02 | TE09946 | This Project involves streetscaping on Main Street in Louisville, Alabama. Barbour County | Transportation Enhancements | 01/20/2010 |  |  | 314995 | 0
129 | Alaska | NORTHWEST ARCTIC |  | 00 | 0002109 | This project will reconstruct and pave approximately 4,400 lineal feet of Shore Avenue between Lake Street and Crowley Dock Road including armoring the tidewater side of the road for protection agains | Pavement Improvement | 06/17/2009 | 06/01/2009 | 10/01/2011 | 6500000 | 1.077
130 | Alaska | SKAGWAY-HOONAH-ANGN |  | 00 | 0003053 | Construct a deepwater dock connected to the mainland with a causeway that has two driving lanes and a bicycle/pedestrian lane. The causeway will be capable of handling a variety of seagoing vessels t | Bridge Improvement | 04/16/2009 | 04/27/2009 | 12/01/2010 | 7700000 | 0.185
131 | Alaska | VALDEZ - CORDOVA |  | 00 | 000S684 | The project will re-pave 7.1 miles of bike and pedestrian path alongside the Richardson Highway between Meals Avenue in downtown Valdez and River Road at the Robe River Subdivision. | Transportation Enhancements | 07/24/2009 | 06/03/2009 | 10/01/2009 | 954770 | 7.6
132 | Alaska | VALDEZ - CORDOVA |  | 00 | 000S685 | Repave 0.95 miles of Blueberry Lake Road in Valdez at the access to the Blueberry Lake Campground. Pave 1,900 feet of roadway within the Blueberry Lake Campground. | Pavement Improvement | 07/27/2009 | 06/03/2009 | 10/01/2009 | 1045762 | 0.95
133 | Alaska | KENAI PENINSULA |  | 00 | 0221054 | The project will resurface the driving lanes and shoulder of 16.75 miles of the Sterling Highway between Kalifornsky Beach Road and South Coho Loop Road in the Kenai Peninsula Borough. The project wi | Pavement Improvement | 07/17/2009 | 05/26/2009 | 06/30/2010 | 6756419 | 17
134 | Alaska | KODIAK ISLAND |  | 00 | 0391014 | Resurface 6.4 miles of urban roadway in the City of Kodiak. The project will include replacement of the waterproof membrane on the Buskin River bridge, paint striping, installation of pedestrian cros | Pavement Improvement | 08/06/2009 | 06/02/2009 | 10/01/2009 | 6635651 | 6.95
135 | Alaska | VALDEZ - CORDOVA |  | 00 | 0750011 | This project will construct a new wayside in the vicinity of Milepost 7 of the Denali Highway. The project includes paved parking, a vault toilet,, litter barrel, table and bench. The project will r | Transportation Enhancements | 09/03/2009 |  | 07/15/2010 | 441283 | 0
136 | Alaska | JUNEAU |  | 00 | 0933027 | This project will widen and straighten Glacier Highway to a paved width of 30 feet for 4.6 miles between the Amalga Harbor Road and the kayak launch at Eagle Beach. The project will include culvert r | Pavement Improvement | 07/23/2009 | 05/27/2009 | 12/01/2010 | 11273789 | 4.597
137 | Alaska | JUNEAU |  | 00 | 0933036 | The project will rehabilitate and resurface 4.52 miles of driving lanes on Glacier Highway in Juneau, between the Mendenhall Loop road and the Auke Bay Ferry Terminal, not including a segment between | Pavement Improvement | 08/03/2009 | 05/27/2009 | 06/30/2010 | 3416667 | 4.474
138 | Alaska | HAINES |  | 00 | 0956032 | This project will rebuild 0.59 miles of highway between the intersections of Front Street and Union Street including removal and replacement of asphalt, grading and adding material to the subgrade as | Pavement Improvement | 08/12/2009 | 10/19/2009 | 06/30/2010 | 2175989 | 0.59
139 | Alaska | MATANUSKA-SUSITNA |  | 00 | 0A15026 | This project will resurface 5.8 miles of the Glenn Highway between mileposts 34-42 and replace or repair guardrails including the energy-absorbing, collapsable ends of the guardrails. The project wil | Pavement Improvement | 07/16/2009 | 06/04/2009 | 10/01/2009 | 2037579 | 8
140 | Alaska | MATANUSKA-SUSITNA | ANCHORAGE | 00 | 0A16039 | This project will resurface 15.188 miles of driving lanes, and all ramps and bridges, on the Glenn Highway between Hiland Road and Artillery Road interchanges. Replace or repair guardrails including | Pavement Improvement | 06/12/2009 | 05/26/2002 | 10/01/2009 | 13149213 | 34
141 | Alaska | MATANUSKA-SUSITNA |  | 00 | 0A41022 | Rehabilitate the driving surface and widen the shoulders of 11.1 miles of roadway on the Parks Highway between Willow Creek and the Kashwitna River including 3 passing zones for northbound traffic an | Pavement Improvement | 10/20/2009 | 10/21/2009 | 09/30/2011 | 25175000 | 11
142 | Arizona | YUMA | YUMA (CA) | 7 | 008A204 | The Arizona Department of Transportation proposes to construct a Chain Link Fence project in Yuma County along I-8; US-95 (16th St) to Araby Rd in YUMA. | Other | 10/08/2009 |  |  | 321253 | 6.25
143 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 010B205 | The Arizona Department of Transportation proposes to reconstruct a traffic interchange in Pima County along I-10, from Cienega Creek (milepost 288.4) to Marsh Station (milepost 290.5). Work will incl | Pavement Widening | 07/27/2009 |  |  | 27635071 | 6.099
144 | Arizona | PINAL |  | 1 | 010D204 | The Arizona Department of Transportation proposes to complete a freeway widening project in Pinal County along I-10 from the Town of Picacho to the Picacho Peak traffic interchange. Work will include | Pavement Improvement | 07/29/2009 |  |  | 17294637.35 | 5.699
145 | Arizona | PIMA |  | 8 | 010E201 | The Arizona Department of Transportation proposes to reconstruct a traffic interchange in Pima County along I-10, from Cienega Creek (milepost 288.4) to Marsh Station (milepost 290.5). Work will incl | Pavement Widening | 07/27/2009 | 07/27/2009 | 09/18/2009 | 10122297 | 2.1
146 | Arizona | PIMA |  | 8 | 010E203 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Pima County along I-10, from Rita Rd to Houghton Rd east of TUCSON a total of 4 miles. | Pavement Improvement | 07/08/2009 |  |  | 3274959.18 | 4
147 | Arizona | PIMA |  | 8 | 010E204 | The Arizona Department of Transportation proposes to replace barbed wire fence in Pima County along I-10; from Vail Rd to Pima/Cochise County Line. | Other | 10/05/2009 |  |  | 202793 | 16.8
148 | Arizona | COCHISE |  | 8 | 010F201 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Cochise County along I-10 (EB), from East Benson to Johnson Rd (milepost 307.68 to milepost 321.60) to | Pavement Improvement | 06/08/2009 |  |  | 7316659 | 14.97
149 | Arizona | COCHISE |  | 8 | 010F203 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Cochise County along I-10 (east bound); from Luzena to Bowie. | Pavement Improvement | 07/29/2009 |  |  | 1486257 | 4.9
150 | Arizona | MARICOPA |  | 3 | 017A207 | The Arizona Department of Transportation proposes to construct a Freeway Widening project in Maricopa County along I-17; SR-74 to Anthem Way in PHOENIX to include Major widening along 5 miles to provi | Pavement Widening | 06/30/2009 |  |  | 13994094 | 4.809
151 | Arizona | MARICOPA |  | 3 | 017A210 | The Arizona Department of Transportation proposes to construct a Right-of-way fence replacement project in Maricopa County along Interstate 17 (South Bound); from Table Mesa Interchange to Rock Spring | Other | 06/30/2009 |  |  | 109158.14 | 6
152 | Arizona | SANTA CRUZ |  | 7, 8 | 019A202 | The Arizona Department of Transportation proposes to replace barbed wire fence in Santa Cruz County along I-19; from Rio Rico Rd to Chaves Siding Road north of NOGALES. | Other | 11/04/2009 |  |  | 371785 | 13.2
153 | Arizona | MOHAVE |  | 2 | 040A208 | The Arizona Department of Transportation proposes to replace barb wire fence in Mohave County along Interstate 40; California State Line to Oatman Hwy Interchange to include Safety. | Other | 08/28/2009 |  |  | 205600.17 | 44
154 | Arizona | MOHAVE |  | 2 | 040B205 | The Arizona Department of Transportation proposes to construct a fence replacement project in Mohave County along Interstate 40; Railroad Ave to Rattlesnake Wash in Kingman, AZ, to include chain link | Other | 06/23/2009 |  |  | 507115.78 | 3
155 | Arizona | COCONINO |  | 1 | 040C202 | The Arizona Department of Transportation proposes to replace barb wire fence in Coconino County along Interstate 40 from State Route 64 (milepost (MP) 166) to Volunteer Wash (MP 188). | Other | 08/10/2009 |  |  | 344894 | 22
156 | Arizona | COCONINO |  | 1 | 040C203 | The Arizona Department of Transportation proposes to construct a pavement preservation project in Coconino County along Interstate 40 from milepost (MP) 150 to MP 190.8. | Pavement Improvement | 08/04/2009 |  |  | 581676 | 40.8
157 | Arizona | COCONINO |  | 1 | 040D018 | The Arizona Department of Transportation proposes to reconstruct the roadway and alleviate steep grades in Coconino County along Interstate 40 westbound near Walnut Canyon (milepost 205) east of Flag | Pavement Improvement | 06/01/2009 | 06/01/2009 | 05/11/2010 | 7533237 | 3.97
158 | Arizona | APACHE |  | 1 | 040E201 | The Arizona Department of Transportation proposes to construct features that will protect the Dead River Bridge (Bridge #565) in Apache County along Interstate 40 (Eastbound) from the effects of high | Bridge Improvement | 06/25/2009 |  |  | 151765 | 0.829
159 | Arizona | APACHE |  | 1 | 040E202 | The Arizona Department of Transportation proposes a bridge rehabilitation project in Apache County along Interstate 40 at the Black Creek west of Houck, AZ; project also includes high water protectiv | Bridge Improvement | 06/08/2009 |  |  | 446667 | 0.1
160 | Arizona | MARICOPA |  | 2 | 060A204 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Maricopa County along US 60, from MP 107.6 to MP 110.2 in WICKENBURG to include Micro Seal. | Pavement Improvement | 08/24/2009 |  |  | 370011.92 | 2.6
161 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 060B200 | The proposed widen roadway project is located in Maricopa County within the City of Peoria on US 60. The project begins at MP 148.5 and extends to MP 150.3 for a total length of approximately 1.8 mil | Pavement Widening | 06/03/2009 | 06/03/2009 | 06/11/2009 | 8046826.32 | 2.889
162 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 060B201 | The Arizona Department of Transportation proposes to construct a Roadway Widening project in Maricopa County along US-60 (Grand Av); SR-303L to 99th Av to include Road Widening. | Pavement Widening | 11/30/2009 |  |  | 24112061 | 10.14
163 | Arizona | PINAL | PHOENIX, AZ | 6 | 060C201 | The Arizona Department of Transportation proposes to construct a Gateway graphics project in Pinal County along US 60 at Tomahawk Rd in APACHE JUNCTION (Graphics) to include Gateway graphics. | Transportation Enhancements | 10/05/2009 |  |  | 349339.19 | 0.2
164 | Arizona | PINAL | PHOENIX, AZ | 6 | 060C202 | The Arizona Department of Transportation proposes to construct a Transportation Enhancement project in Pinal County along US-60 at Goldfield Rd in APACHE JUNCTION to include Gateway graphics. | Transportation Enhancements | 10/05/2009 |  |  | 361715.74 | 0
165 | Arizona | GILA |  | 1 | 060D201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along US-60, Miami City Limits to McMillan Wash. | Pavement Improvement | 06/25/2009 |  |  | 6325864 | 8.289
166 | Arizona | GILA |  | 1 | 060E202 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along US-60, from Timber Mountain (MP 278.8) to Seneca (MP 286.4). | Pavement Improvement | 05/28/2009 |  |  | 3652653.74 | 7.779
167 | Arizona | YAVAPAI |  | 1 | 069A206 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Yavapai County along SR-69, I-17 to Big Bug Creek. | Pavement Improvement | 06/10/2009 |  |  | 2524105.4 | 4.8
168 | Arizona | GRAHAM |  | 1 | 070A202 | The Arizona Department of Transportation proposes to construct a traffic intersection improvement project in Graham County on US-70 @ 8th Avenue in SAFFORD to include pavement and signal improvements. | Pavement Improvement | 08/03/2009 |  |  | 210664 | 0.159
169 | Arizona | GILA |  | 1 | 073A200 | The Arizona Department of Transportation proposes to construct a Replace Barb Wire Fence project in Gila County along SR 73; Cedar Creek to Canyon Day to include Safety. | Other | 09/08/2009 |  |  | 324586.89 | 11.6
170 | Arizona | MARICOPA |  | 2 | 074A200 | The Arizona Department of Transportation proposes to construct a Widen Roadway project in Maricopa County along SR-74; MP 19 - New River Rd to include new construction of passing lanes on both eastbou | Pavement Widening | 11/02/2009 |  |  | 2440925 | 3.12
171 | Arizona | GREENLEE |  | 1 | 075A001 | The Arizona Department of Transportation proposes to construct a transportation enhancement project in Greenlee County along SR 75 in York Valley to include pathways, railings, and retaining walls. | Transportation Enhancements | 10/27/2009 |  |  | 270508 | 0.5
172 | Arizona | COCHISE |  | 8 | 080A201 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Cochise County along SR-80 through TOMBSTONE. | Pavement Improvement | 06/30/2009 |  |  | 784285.57 | 1.19
173 | Arizona | COCHISE |  | 8 | 080A202 | The Arizona Department of Transportation proposes to replace fence in Cochise County along SR-80; from Double Adobe Road to the Town of Douglas. | Other | 06/16/2009 |  |  | 413660.6 | 14
174 | Arizona | SANTA CRUZ |  | 8 | 083A201 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Santa Cruz County along SR-83, near Sonoita from milepost 31.6 to milepost 43.5, a total of 11.9 miles. | Pavement Improvement | 06/16/2009 |  |  | 2365274.63 | 11.86
175 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 085B200 | The Arizona Department of Transportation proposes to construct a Widen Roadway project in Maricopa County along SR-85; Southern Ave to I-10. | Pavement Widening | 10/06/2009 |  |  | 11147270.09 | 1.919
176 | Arizona | PIMA |  | 7 | 086A008 | The Arizona Department of Transportation proposes to construct a shoulder widening project in Pima County along SR-86 west Sells from milepost 73.9 to milepost 77.4. | Pavement Improvement | 07/28/2009 |  |  | 2167459.61 | 3.7
177 | Arizona | PIMA | TUCSON | 7 | 086A203 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Pima County along SR-86, from Kinney Road to La Cholla Blvd in TUCSON, a total of 3.1 miles. | Pavement Improvement | 08/05/2009 |  |  | 2528446.98 | 3.099
178 | Arizona | PIMA | TUCSON | 7 | 086A204 | The Arizona Department of Transportation proposes to perform a bridge deck rehabilitation project in Pima County on SR-86 at the Santa Cruz River in TUCSON. Work will include repair of deteriorating | Bridge Improvement | 07/08/2009 |  |  | 350000 | 0.069
179 | Arizona | PIMA |  | 7 | 086A205 | The Arizona Department of Transportation proposes to complete the widening of SR-86 in Pima County across Brawley Wash west of TUCSON from milepost 145.69 to milepost 148.3. | Pavement Improvement | 08/03/2009 |  |  | 1660928.59 | 2.56
180 | Arizona | GILA |  | 1 | 087C002 | The Arizona Department of Transportation proposes to construct a Shoulder Widening project in Gila County along SR-87, PAYSON to PINE. | Pavement Improvement | 05/22/2009 |  |  | 4646791.59 | 2.4
181 | Arizona | GILA |  | 1 | 087C201 | The Arizona Department of Transportation proposes to construct a Replace Barb Wire Fence project in Gila County along SR 87; PAYSON to PINE. | Other | 08/18/2009 |  |  | 385111 | 12.2
182 | Arizona | COCONINO | FLAGSTAFF | 1 | 089C200 | The Arizona Department of Transportation proposes to construct a pavement preservation project in Coconino County along US 89; Townsend (milepost (MP) 420) to Fernwood (MP 426) north of Flagstaff, AZ. | Pavement Improvement | 05/22/2009 |  |  | 4783750.62 | 5.449
183 | Arizona | MOHAVE |  | 2 | 093B201 | The Arizona Department of Transportation proposes to construct new southbound travel lanes, creating a divided highway, in Mohave County along US 93, from milepost (MP) 104.1 to MP 106 (Ranch Rd Secti | New Construction | 07/28/2009 | 11/13/2009 | 02/11/2010 | 7157709 | 2.95
184 | Arizona | YUMA | YUMA (CA) | 7 | 095A201 | The Arizona Department of Transportation proposes to construct a widening project in Yuma County along US 95 (16th Street), I-8 to Palms Ave. | Pavement Widening | 08/18/2009 | 09/08/2009 |  | 11349523.66 | 0.71
185 | Arizona | LA PAZ |  | 7 | 095B200 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in La Paz County along US-95, from Peligro (MP 63) to Clarks (MP 80). | Pavement Improvement | 09/28/2009 |  |  | 9039982 | 17
186 | Arizona | YUMA |  | 7 | 095B202 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Yuma County along US 95, from MP 44.3 to MP 312.7. | Pavement Improvement | 08/24/2009 |  |  | 502307.5 | 9.7
187 | Arizona | LA PAZ |  | 7 | 095C203 | The Arizona Department of Transportation proposes to construct a Passing Lanes project in La Paz County along SR 95 South of Bouse Wash. | Pavement Improvement | 06/30/2009 |  |  | 1684770.2 | 2.81
188 | Arizona | PIMA | TUCSON | 8 | 0RV0201 | The Town of Oro Valley will perform a pavement preservation project on the following roadways: LaCholla, First, Lamber, Moor,Tan in the Town of Oro Valley. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 2020936 | 0
189 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 101A204 | The Arizona Department of Transportation proposes to widen Union Hills Road Traffic Interchange in Maricopa County along SR-101L (Aqua Fria Frwy) @ Beardsley Rd/Union Hills Dr in GLENDALE. | New Bridge Construction | 10/26/2009 | 10/26/2009 | 01/01/2012 | 8239577 | 1.66
190 | Arizona | COCONINO |  | 1 | 160A001 | The Arizona Department of Transportation proposes a pavement preservation project in Coconino County along US 160, from the junction of US 89 and US 160 to Van's Trading Post; west of Tuba City, AZ - | Pavement Improvement | 06/01/2009 |  |  | 3588895 | 9.04
191 | Arizona | NAVAJO |  | 1 | 160A200 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County along US 160, in Kayenta, AZ to Navajo Route 59 - 12.5 miles | Pavement Widening | 05/26/2009 |  |  | 7003779 | 12.5
192 | Arizona | NAVAJO |  | 1 | 160B200 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County along US 160; from Navajo Route 59 to Dennehotso - 14 miles. | Pavement Improvement | 05/26/2009 |  |  | 3815548 | 14
193 | Arizona | NAVAJO |  | 1 | 180B202 | The Arizona Department of Transportation proposes to replace barb wire fence in Navajo County along US 180, east of Holbrook, AZ; from milepost (MP) 307.3 to 324.9, near the Petrified Forest Road. | Other | 08/05/2009 |  |  | 579716.79 | 17.6
194 | Arizona | COCHISE | PHOENIX, AZ | 8 | 191A200 | The Arizona Department of Transportation proposes to construct an intersection improvement project in Cochise County along US-191 @ High Street in Sunsites (MP 48.36 to MP 48.94 to include Widen Roadw | Pavement Improvement | 06/16/2009 |  |  | 484868.83 | 0.579
195 | Arizona | GREENLEE |  | 1 | 191C202 | The Arizona Department of Transportation proposes an intersection improvement project in Greenlee County along US 191 at Black Hills Rd (Back County Byway) at milepost 159.5. | Pavement Improvement | 07/24/2009 |  |  | 715888.89 | 0.699
196 | Arizona | GREENLEE |  | 1 | 191C203 | The Arizona Department of Transportation proposes to construct a drainage improvement project in Greenlee County along US-191 (Coronado Trail) at milepost 175 to include Lower Coronado Drainage Improv | Other | 09/28/2009 |  |  | 409630.3 | 9
197 | Arizona | APACHE |  | 1 | 191E202 | The Arizona Department of Transportation proposes a pavement preservation project in Apache County along US 191, from milepost (MP) 427 to MP 436 south of Chinle, AZ. | Pavement Improvement | 06/16/2009 |  |  | 3171048.9 | 8.329
198 | Arizona | NAVAJO |  | 1 | 260C003 | The Arizona Department of Transportation proposes to construct a Transportation Enhancement project in Navajo County along SR-260; Porter Mtn. Rd to Woodland Rd in PINETOP/LAKESIDE to include Pedestri | Other | 10/28/2009 |  |  | 627151 | 0.6
199 | Arizona | NAVAJO |  | 1 | 277A201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Navajo County along SR 277, from MP 305.7 to 312.7. | Pavement Improvement | 08/05/2009 |  |  | 350575.03 | 6.909
200 | Arizona | STATEWIDE |  | 7, 8 | 999A238 | The Arizona Department of Transportation proposes to implement a Pavement Micro Seal project Statewide in various Counties in Southeast Arizona. | Pavement Improvement | 08/24/2009 |  |  | 1193435.5 | 14.9
201 | Arizona | STATEWIDE |  | 1 | 999A239 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County at various locations. | Pavement Improvement | 08/03/2009 |  |  | 709240.92 | 14.53
202 | Arizona | GILA |  | 1 | 999A242 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along Globe District Chip Seals to include Chip Seal. | Pavement Improvement | 07/29/2009 |  |  | 573572.04 | 11.2
203 | Arizona | PINAL |  | 6 | APJ0200 | The City of Apache Junction, AZ will perform Pavement Preservation along Ironwood Drive from US 60 (Superstition Frwy) to Southern Ave. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 2185330 | 6
204 | Arizona | MARICOPA |  | 4 | APJ0201 | The City of Apache Junction AZ will perform Design and Reconstruction of Pavement along Ironwood Drive from Southern Ave to 16th Ave. | Other | 06/15/2009 |  |  | 20000 | 0
205 | Arizona | MARICOPA | PHOENIX, AZ | 7 | AVN0206 | The City of Avondale will perform a Preliminary engineering, design and construction along Dysart Rd; I-10 to Indian School Rd in AVONDALE. | Pavement Improvement | 06/23/2009 | 06/23/2009 |  | 2166201.52 | 2.5
206 | Arizona | MARICOPA | PHOENIX, AZ | 7 | AVN0207 | The City of Avondale will perform a Preliminary engineering, design and construction for along Dysart Rd; Van Buren St to I-10 in AVONDALE. | Other | 06/23/2009 | 06/23/2009 |  | 48698.43 | 0.5
207 | Arizona | MARICOPA | PHOENIX, AZ | 7 | BKY0202 | The Town of Buckeye will perform a Pre-engineering/Design and Pavement Rehabilitation and Preservation along Various Locations on Functionally Classified Roads in BUCKEYE. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 1460066 | 3.5
208 | Arizona | MOHAVE |  | 2 | BUL0200 | Bullhead City will perform a pavement preservation project of existing deteriorating asphalt pavement along Miracle Mile in Bullhead City, AZ. | Pavement Improvement | 07/02/2009 | 07/02/2009 |  | 500000 | 2.6
209 | Arizona | COCONINO |  | 1 | CCN0204 | The Coconino County will perform a pavement preservation along Lake Mary Road south of Flagstaff, AZ. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 679486 | 0
210 | Arizona | COCONINO | FLAGSTAFF | 1 | CCN0205 | The Coconino County will perform a pavement preservation project along State Route B40 (Old US 66), from I-40 to City Limits, west of Flagstaff, AZ. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 961128 | 0
211 | Arizona | MARICOPA | PHOENIX, AZ | 3 | CFE0201 | The Town of Carefree, AZ will perform Design and construction of repair and restoration of Cave Creek Road from Scopa Trail to Carefree Eastern Border. | Pavement Improvement | 07/01/2009 | 07/01/2009 |  | 588340 | 4
212 | Arizona | MARICOPA | PHOENIX, AZ | 6 | CHN0025 | The City of Chandler, AZ will perform Intersection and Capacity Improvement along Chandler Blvd at Dobson Rd, and on Dobson Rd from Chandler Blvd to Frye Rd. | Pavement Widening | 08/24/2009 | 08/24/2009 |  | 2288700 | 0.5
213 | Arizona | MARICOPA | PHOENIX, AZ | 6 | CHN0211 | The City of Chandler will perform Design and reconstruction of pavement along Price Road; Germann Road to Queen Creek Road in CHANDLER. | Pavement Improvement | 06/30/2009 | 06/30/2009 |  | 3678899 | 1
214 | Arizona | PINAL |  | 1 | CSG0200 | The City of Casa Grande will install intersection traffic signals at the following intersection Peart Road / McCartney Road and Peart Road / Korsten Road in Casa Grande. | Other | 06/18/2009 | 06/18/2009 | 10/16/2009 | 20000 | 0
215 | Arizona | MARICOPA | PHOENIX, AZ | 3 | CVK0201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project along Cave Creek Road from Spur Crossing to the Cave Creek Town Limits in CAVE CREEK, AZ. | Pavement Improvement | 09/09/2009 | 09/09/2009 |  | 614813 | 1.5
216 | Arizona | COCHISE |  | 8 | DGS0005 | The City of Douglas will perform a transportation enhancement project which will include a shared use pathway with ADA ramps over a railroad bridge along Paseo de la Amistad. | Transportation Enhancements | 12/29/2009 | 12/29/2009 |  | 690479 | 0.2
217 | Arizona | APACHE |  | 1 | EGR0200 | The City of Eager will perform a Pavement Preservation along Main Street; from US-60 to SR-260 in EAGER. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 857375 | 1.6
218 | Arizona | MARICOPA | PHOENIX, AZ | 2 | ELM0202 | The City of El Mirage will perform a Pre-Engineer/Design and Mill and Replace Existing Pavement along Various Locations on Functionally Classified Roadways. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 826349.83 | 1.5
219 | Arizona | COCONINO | FLAGSTAFF | 1 | FLA0006 | The City of Flagstaff will perform a improvements along State Route B40 in downtown Flagstaff, AZ; the project includes pathway and landscaping improvements. | Transportation Enhancements | 09/14/2009 | 09/14/2009 |  | 613298 | 0
220 | Arizona | MARICOPA | PHOENIX, AZ | 5 | FTH0203 | The City of Fountain Hills will be add a for 3rd (westbound) lane, bike lane, sidewalk, and turn pockets on Shea Blvd., from Palisades Blvd. to Fountain Hills Blvd. | Other | 07/06/2009 | 07/06/2009 |  | 1126700 | 1
221 | Arizona | MARICOPA | PHOENIX, AZ | 5 | FTM0201 | The City of Fountain Hills will perform pre-engineer and design work, and then construct various pavement rehabilitation projects in Ft. McDowell on functionally classified roadways. | Other | 07/20/2009 |  |  | 45087 | 0
222 | Arizona | MARICOPA | PHOENIX, AZ | 7 | GBD0200 | The City of Gila Bend will construct Pedestrian and Landscape Improvements along Various Locations along SR-85 (Pima St) in GILA BEND. | Transportation Enhancements | 09/10/2009 | 09/10/2009 |  | 242497 | 0
223 | Arizona | MARICOPA | PHOENIX, AZ | 7 | GBD0201 | The City of Gila Bend will perform a Design and Construct Signage Improvements along Various Locations along SR-85 (Pima St) in GILA BEND. | Other | 06/11/2009 |  |  | 1650 | 0
224 | Arizona | MARICOPA | PHOENIX, AZ | 7 | GBD0203 | The City of Gila Bend will design and construct a carpool lane and transit park & ride lot at the Gila Bend Airport on SR85. | Other | 09/10/2009 | 09/10/2009 |  | 300000 | 0
225 | Arizona | MARICOPA | PHOENIX, AZ | 2 | GDY0202 | The City of Goodyear will perform a Pre-Engineer/Design to mill, patch and replace pavement along Various Locations on Functionally Classified Roads in GOODYEAR. | Pavement Improvement | 06/23/2009 | 06/23/2009 |  | 782415 | 2.5
226 | Arizona | GILA |  | 1 | GGI0005 | The Gila County, will perform a Bridge Rehabilitation along Ice House, Bridge and Ice House Wash Bridge and Approaches in GLOBE. | Other | 06/18/2009 | 06/18/2009 |  | 65136 | 0
227 | Arizona | MARICOPA | PHOENIX, AZ | 6 | GIL0015 | The City of Gilbert will construct Pedestrian bridges across a major Canal within the City. | Transportation Enhancements | 10/21/2009 |  |  | 270000 | 0
228 | Arizona | MARICOPA | PHOENIX, AZ | 6 | GIL0203 | The City of Gilbert, AZ will perform Design and Construction of Chip Seal Overlays on various arterial roadways in GILBERT. | Pavement Improvement | 07/06/2009 | 07/06/2009 |  | 5306313 | 15
229 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0211 | The City of Glendale, will perform a Pre-Engineer/Design for pavement overlay along Glendale Ave; 51st Ave to 66th Ave in GLENDALE. | Other | 06/12/2009 | 06/12/2009 |  | 89923 | 2
230 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0212 | The City of Glendale will perform a Pre-Engineer/Design and construct pavement surface treatment along Litchfield Rd; Missouri to Northern Ave in GLENDALE. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 517144 | 2
231 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0214 | The City of Glendale will Install thermoplastic pavement markings along 25 Miles on Arterial Streets in GLENDALE. | Pavement Widening | 06/12/2009 | 06/12/2009 |  | 338973 | 25
232 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0215 | The City of Glendale will install wireless communication devices along Camelback Rd from 47th Ave to 83rd Ave to improve communication with traffic signals. | Other | 06/12/2009 | 06/12/2009 |  | 13332 | 4.5
233 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0216 | The City of Glendale will install wireless communication devices along Bethany Home Rd from 63rd Ave to 83rd Ave to improve communication with traffic signals. | Other | 06/23/2009 | 06/23/2009 |  | 13332 | 2.5
234 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0217 | The City of Glendale will install CCTV cameras at various locations on their functionally classified roadways to improve traffic operations and management. | Other | 06/23/2009 | 06/23/2009 |  | 13282 | 0
235 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0218 | The City of Glendale will modernize traffic signals at various locations on functionally classified roadways to improve traffic operations and management. | Other | 06/23/2009 | 06/23/2009 |  | 13512 | 0
236 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0219 | The City of Glendale will install new traffic signal cabinets and controllers at various locations on functionally classified roadways to improve traffic operations and management. | Other | 06/23/2009 | 06/23/2009 |  | 13605 | 0
237 | Arizona | MARICOPA | PHOENIX, AZ | 7 | GRI0200 | ADOT will perform Design and Construction of Pavement Rehab projects along Various Locations on Functionally Classified Roads within Gila River Indian Community. | Pavement Improvement | 06/23/2009 | 06/23/2009 |  | 561349 | 1.5
238 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GUA0200 | The Town of Guadalupe AZ will perform Replacement of existing street lights to improve safety along Various Roadways in GUADALUPE, AZ | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 634022 | 0
239 | Arizona | PIMA | TUCSON | 7 | IT00200 | The Tohono O'odham Indian Reservation will perform a pavement preservation project along San Xavier Road from Mission to Los Reales on the Tohono O'odham Nation. | Pavement Improvement | 07/09/2009 | 07/09/2009 |  | 2500000 | 0
240 | Arizona | MOHAVE |  | 2 | KNG0202 | The City of Kingman will perform a pavement preservation project along Bank Street Kingman, AZ. | Other | 06/12/2009 | 06/12/2009 |  | 34294 | 0.5
241 | Arizona | MOHAVE |  | 2 | LHV0003 | The Lake Havasu City will construct a shared use pathway along Magnolia Drive to Acoma Boulevard (Multi-Use Path) in Lake Havasu City, AZ. | Transportation Enhancements | 08/11/2009 | 01/04/2010 |  | 638305 | 0.5
242 | Arizona | MOHAVE |  | 2 | LHV0200 | The Lake Havasu City will install traffic signals at the intersection of South Palo Verde and Acoma in Lake Havasu City, AZ. | Pavement Improvement | 09/09/2009 | 09/09/2009 |  | 264000 | 0
243 | Arizona | LA PAZ |  | 7 | LLA0201 | The LaPaz County will perform a Pavement Preservation project along Salome Road, from US 60 to MP 5.5. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 600000 | 5.5
244 | Arizona | MARICOPA | PHOENIX, AZ | 4 | LPK0201 | The City of Litchfield Park will perform a Pre-Engineer/Design to mill and replace pavement resurfacing/ reconstruction along Various Locations on Functionally Classified Roads in LITCHFIELD PARK. | Pavement Improvement | 06/23/2009 | 06/23/2009 |  | 613958 | 0.7
245 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0209 | The City of Mesa, AZ will perform Design and Construction of Pavement Preservation and Americans with Disabilities Act (ADA) upgrades along Various Roadways. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 1610892 | 7.5
246 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0210 | The City of Mesa, AZ will perform Design and construction of mill and replace pavement along Various Roadways. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 970728 | 3.5
247 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0211 | The City of Mesa proposes a pavement preservation project and American with Disabilities Act upgrades in various locations in Mesa, AZ. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 2559279 | 2
248 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0212 | City of Mesa, AZ proposes a pavement preservation project and upgrades to the American with Disabilities Act features in various locations in Mesa, Arizona. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 2333311 | 2
249 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0213 | City of Mesa, AZ proposes a pavement preservation project with Americans with Disabilities Act improvements in various locations in Mesa, Arizona. | Pavement Improvement | 08/06/2009 | 08/06/2009 |  | 3310569 | 3
250 | Arizona | MOHAVE |  | 2 | MM00001 | The Mohave County will construct a shared use pathway along the Mohave Wash Pathway (County) from Gordon Drive to Bank Street in Kingman, AZ. | Transportation Enhancements | 11/20/2009 |  |  | 698368 | 0
251 | Arizona | MOHAVE |  | 2 | MM00200 | The Mohave County will construct a shared use pathway along Mohave Wash Pathway (County) from Bank Street to Northern Avenue in Kingman, AZ. | Transportation Enhancements | 11/20/2009 |  |  | 440000 | 0.6
252 | Arizona | MOHAVE |  | 2 | MM00203 | The Mohave County will perform a pavement preservation project along Northern Avenue in Kingman, AZ. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 500000 | 1.5
253 | Arizona | MARICOPA |  | 5 | MMA0201 | Maricopa County, AZ will construct Paved shoulders and add bike lanes along Bush Highway from Usery Pass Rd to Steward Mountain Rd northwest of MESA AZ. | Other | 10/05/2009 | 10/05/2009 |  | 750000 | 4.6
254 | Arizona | MARICOPA | PHOENIX, AZ | 3 | MMA0210 | Maricopa County, will perform Pre-Engineer/Design and construct Asphalt Rubber Overlay along Various Locations on Functionally Classified Roadways in MARICOPA COUNTY. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 6469193 | 31.1
255 | Arizona | PIMA | TUCSON | 8 | MRN0202 | The City of Marana will perform various pavement preservation projects: Rattlesnake Pass (2.5 miles); Tangerine Road, I-10 to Thornydale Road; Moore Road, I-10 to Sandario Road; Sandario Road, Trico R | Pavement Improvement | 06/22/2009 | 06/22/2009 |  | 3191974 | 7.9
256 | Arizona | NAVAJO |  | 1 | NNA0200 | The Navajo County will perform a pavement preservation project along Bourdon Ranch Road from milepost (MP) 6.5 to MP 10.1 in Navajo County. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 662007 | 3.5
257 | Arizona | PIMA | TUCSON | 2 | PAS0201 | The Pascua Yaqui Tribe will perform a pavement preservation project along Calle Torim and Ignacio. | Pavement Improvement | 07/14/2009 | 07/14/2009 |  | 462793 | 2.6
258 | Arizona | MARICOPA | PHOENIX, AZ | 2 | PE00205 | Major Arterial mill, overlay and re-striping to 5 general purpose lanes and bike lanes along Beardsley Rd; Lake Pleasant Rd to 83rd Av in PEORIA. | Pavement Widening | 06/08/2009 | 06/08/2009 |  | 2042695 | 2.4
259 | Arizona | MARICOPA | PHOENIX, AZ | 2 | PE00206 | The City of Peoria will Widen the Beardsley Rd Connection: SR-101L (Agua Fria Fwy) to Beardsley Rd at 83rd Av/Lake Pleasant Pkwy in PEORIA, which will include Advance constructing the Beardsley Road | New Construction | 06/08/2009 | 06/08/2009 |  | 1937971 | 2
260 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0209 | The City of Phoenix, AZ will perform Design & Construction of Intersection Improvements along 7th St at McDowell Rd in PHOENIX. | Other | 07/01/2009 | 07/01/2009 | 09/09/2009 | 1000000 | 0
261 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0229 | The City of Phoenix, AZ will perform Design & Construction of Removal/Replacement of Existing Americans with Disabilities Act (ADA) Ramps or Construction of New ADA Ramps along Various Locations in PH | Pavement Improvement | 07/07/2009 | 07/07/2009 |  | 1750000 | 0
262 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0230 | The City of Phoenix, AZ will perform Design & Construction of Removal/Replacement of Existing Americans with Disabilities (ADA) Ramps or Construction of New ADA Ramps along Various Locations in PHOENI | Pavement Improvement | 07/07/2009 | 07/07/2009 |  | 1750000 | 0
263 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0231 | The City of Phoenix, AZ will perform Design & Construction of Bridge Deck Rehabilitations along 11 Locations in PHOENIX. | Bridge Improvement | 07/08/2009 | 07/08/2009 |  | 2250000 | 0
264 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0232 | The City of Phoenix, AZ will perform Design & Construction of Bridge Joint Rehabilitations along 6 Locations in PHOENIX. | Bridge Improvement | 07/08/2009 | 07/08/2009 |  | 1250000 | 0
265 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0233 | The City of Phoenix will design, procure, and install CCTV along various corridors to improve traffic operations and management. | Safety/Traffic Management | 07/08/2009 | 07/08/2009 |  | 1000000 | 0
266 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0234 | The City of Phoenix will design, procure and install a fiber optic backbone system along various corridors to improve traffic operations and management. | Safety/Traffic Management | 07/08/2009 | 07/08/2009 |  | 1500000 | 0
267 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0235 | The City of Phoenix will design, procure, and install wireless communications devices along various corridors to improve communications facilitating better traffic operations and management. | Safety/Traffic Management | 07/09/2009 | 07/09/2009 |  | 500000 | 0
268 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0236 | The City of Phoenix will perform an inventory, procure, and install traffic control signs along various corridors to aid in the control and management of traffic. | Safety/Traffic Management | 07/09/2009 | 07/09/2009 |  | 3000000 | 0
269 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0237 | The City of Phoenix will perform a Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (North Area). | Pavement Improvement | 07/09/2009 | 07/09/2009 |  | 7136181 | 16
270 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0238 | The City of Phoenix, will perform Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (Central Area). | Pavement Improvement | 07/09/2009 | 07/09/2009 |  | 7150000 | 16
271 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0239 | The City of Phoenix, will perform Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (South Area). | Pavement Improvement | 07/09/2009 | 07/09/2009 |  | 7150000 | 16
272 | Arizona | PIMA | TUCSON | 7 | PPM0161 | The Pima County will perform a transportation enhancement project which consists of new paved shoulders, shared use driveway improvements, and access ramps near the Hohokam Middle School in Pima Count | Other | 10/20/2009 | 10/20/2009 |  | 575000 | 1
273 | Arizona | PIMA | TUCSON | 7 | PPM0214 | The Pima County will perform pavement preservation projects in various locations throughout Pima County. | Pavement Improvement | 06/22/2009 | 06/22/2009 |  | 6750590 | 0
274 | Arizona | PIMA | TUCSON | 7 | PPM0215 | Pima County will complete bridge deck repairs from along Sabino Canyon Rd and Tanque Verde Creek in PIMA COUNTY. | Bridge Improvement | 06/22/2009 | 06/22/2009 |  | 600000 | 43
275 | Arizona | YAVAPAI |  | 1 | PRV0004 | The City of Prescott Valley will perform a Transportation Enhancement project along Bison Lane in PRESCOTT VALLEY to include a shared use pathway. | Other | 08/24/2009 | 08/24/2009 |  | 661180 | 0.6
276 | Arizona | YAVAPAI | FLAGSTAFF | 1 | PRV0203 | The City of Prescott Valley will perform a Pavement Preservation along Glassford Hill Road in PRESCOTT VALLEY to include Overlay/ 3" AC. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 1574160 | 0
277 | Arizona | MARICOPA | PHOENIX, AZ | 3 | PVY0202 | The Town of Paradise Valley, AZ will perform Design and construction of pavement resurfacing along Various Roadways in PARADISE VALLEY. | Other | 08/11/2009 | 08/11/2009 |  | 129037 | 3.7
278 | Arizona | MARICOPA | PHOENIX, AZ | 6 | QCR0205 | The City of Queen Creek, AZ will perform Design and construction of roadway resurfacing and shoulder paving along Various Locations on Rittenhouse Rd in QUEEN CREEK. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 1033098 | 1.7
279 | Arizona | PIMA |  | 7 | SAH0201 | The Town of Sahuarita will perform a pavement preservation project in Rancho Sahuarita: La Villita to 2 miles north and Traffic signals & signage reflectivity upgrades and Duval Mine Rd: La Canada to | Pavement Improvement | 07/01/2009 | 07/01/2009 |  | 1864080 | 2.6
280 | Arizona | MARICOPA | PHOENIX, AZ | 5 | SCT0203 | The City of Scottsdale, AZ will construct a Shared use pathway along Arizona Canal (Sun Circle Trail) at Goldwater Blvd in SCOTTSDALE. | Transportation Enhancements | 09/09/2009 | 12/07/2009 |  | 600000 | 0.1
281 | Arizona | MARICOPA | PHOENIX, AZ | 5 | SCT0206 | The City of Scottsdale will upgraded traffic controllers and cabinets at various locations in the southern area of Scottsdale to improve traffic operations and management. | Safety/Traffic Management | 08/05/2009 | 08/05/2009 |  | 439633 | 0
282 | Arizona | MARICOPA | PHOENIX, AZ | 5 | SCT0209 | The City of Scottsdale, will perform Pavement Preservation along Various Roadways in the City of Scottsdale. | Pavement Improvement | 09/09/2009 | 09/09/2009 |  | 4600000 | 10.5
283 | Arizona | NAVAJO |  | 1 | SLW0201 | The Navajo County will perform a Pavement Preservation along Penrod Road in SHOW LOW. | Other | 07/01/2009 | 07/01/2009 |  | 56608 | 4.1
284 | Arizona | MARICOPA | PHOENIX, AZ | 5 | SRI0200 | The Salt River Pima-Maricopa Indian Community, will Design & Construct Pavement Preservation/Chip-Seal along Various Locations on Functionally Classified Roads within Salt River Pima - Maricopa Indian | Pavement Improvement | 08/03/2009 | 08/03/2009 |  | 653910 | 2
285 | Arizona | PIMA | TUCSON | 7 | STC0200 | The City of South Tucson will perform a pavement preservation project along 29th Street; from 12th Avenue to the Union Pacific Railroad in SOUTH TUCSON. | Pavement Improvement | 06/23/2009 | 06/23/2009 |  | 580660 | 0.5
286 | Arizona | GILA |  | 1 | SUP0200 | The Town of Superior will perform a Pavement Preservation along Main Street. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 648994 | 1
287 | Arizona | MARICOPA | PHOENIX, AZ | 2 | SUR0208 | The City of Surprise will perform a Pre-Engineer/Design and construct pavement Reconstruction and ITS Conduit Installation along Bell Rd; Parkview to West City Limit in SURPRISE. | Pavement Improvement | 06/22/2009 | 06/22/2009 |  | 2933374 | 4.3
288 | Arizona | PIMA |  | 8 | SVS0200 | The City of Sierra Vista will complete transportation enhancement along Snyder Boulevard multi-use path, Avenida del Sol to SR-92 in SIERRA VISTA to include pathways, landscaping, and irrigation. | Other | 08/31/2009 | 09/21/2009 |  | 650000 | 0.5
289 | Arizona | COCHISE |  | 8 | SVS0204 | The City of Sierra Vista will perform widening, signal upgrades, drainage, improvements, curb, sidewalk, multi-use pathways on South side along Charleston Road. | Other | 06/11/2009 | 06/11/2009 |  | 2195079 | 1.2
290 | Arizona | GRAHAM |  | 1 | THR0200 | The Town of Thatcher will perform a 2 inch asphalt overlay along Reay Lane in the Town of Thatcher. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 600001 | 2
291 | Arizona | MARICOPA | PHOENIX, AZ | 5 | TMP0211 | The City of Tempe, AZ will Construct a replacement bridge over the Western Canal along Baseline Rd (Kyrene Rd to Union Pacific Railroad) in TEMPE. | Bridge Replacement | 08/11/2009 | 08/11/2009 |  | 4362619 | 0.2
292 | Arizona | PIMA | TUCSON | 7 | TUC0051 | The City of Tucson will install, repair or replace deteriorated sidewalks/driveways along South Fourth Avenue in TUCSON. | Other | 09/14/2009 | 09/14/2009 |  | 514000 | 0.5
293 | Arizona | PIMA | TUCSON | 7 | TUC0073 | The City of Tucson will perform a transportation enhancement project along Fourth Avenue between 17th and 22nd Streets in Tucson to include construction of sidewalks and driveways to meet ADA standard | Transportation Enhancements | 08/12/2009 | 08/12/2009 |  | 467000 | 0
294 | Arizona | PIMA | TUCSON | 7 | TUC0231 | The City of Tucson will perform pavement preservation projects at various locations within the City of Tucson. | Other | 06/18/2009 | 06/18/2009 |  | 173480 | 0
295 | Arizona | PIMA | TUCSON | 7 | TUC0232 | The City of Tucson will complete various pavement preservation projects within the City of Tucson. | New Construction | 09/03/2009 | 09/03/2009 |  | 6000000 | 0
296 | Arizona | MARICOPA | PHOENIX, AZ | 2 | WBG0200 | The Town of Wickenburg, will perform a Pavement Preservation project along North Vulture Mine Rd; from US 60 to Northern Town Limits in WICKENBURG to include Mill and Replace. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 644140.49 | 1.6
297 | Arizona | MARICOPA | PHOENIX, AZ | 2 | YTN0200 | The Town of Youngtown will perform a Pre-Engineer/Design to construct, mill and replace pavement resurfacing along Peoria Ave; 111th Ave to 115th Av in YOUNGTOWN. | Other | 06/12/2009 | 06/12/2009 |  | 72908 | 0
298 | Arizona | YUMA | YUMA (CA) | 7 | YUM0200 | The City of Yuma will perform a Transportation Enhancement project in YUMA to include Construction of an interpretative plaza, complete with retaining walls. | Other | 08/01/2009 | 07/20/2009 |  | 750000 | 0.2
299 | Arizona | YUMA | YUMA (CA) | 7 | YYU0200 | The Yuma County will perform a round-about construction project along Avenue E @ Juan Sanchez Blvd within the New San Luis II POE in YUMA COUNTY. | Pavement Improvement | 09/10/2009 | 09/10/2009 |  | 932000 | 2
300 | Arizona | YAVAPAI |  | 1 | YYV0202 | The Yavapai County will perform a Cold in place recycle; reconstruction along Cornville Rd; from Aspaas Rd to Beaverhead Flat Rd in YAVAPAI COUNTY. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 788542 | 3.8
301 | Arkansas | LAWRENCE |  | 01 | ARR1001 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT THE EMBANKMENT AND BRIDGES FOR 9.89 MILES OF THE NEW LOCATION OF HIGHWAY 67 BETWEEN HIGHWAY 230 AND HIGHWAY 63, SOUTH OF HOXIE IN LAWRENCE COUNTY. WORK INC | New Construction | 06/22/2009 | 07/15/2009 | 12/31/2012 | 21094279 | 9.89
302 | Arkansas | PULASKI |  | 02 | ARR1003 | THE PURPOSE OF THIS PROJECT IS TO REPLACE FOUR EXISTING BRIDGE STRUCTURES, RECONSTRUCT APPROACHES ON I-430 AND CONSTRUCT WIDENING TO THE I-630 LOOP RAMP CONNECTIONS AT THE I-430/I-630 INTERCHANGE IN | Bridge Improvement | 07/17/2009 | 07/20/2009 | 11/15/2010 | 15991380 | 0.1
303 | Arkansas | ST FRANCIS |  | 01 | ARR1004 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.30 MILES OF HIGHWAY 1 BETWEEN THE CITIES OF CALDWELL AND COLT IN ST. FRANCIS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE | Pavement Improvement | 06/15/2009 | 07/07/2009 | 08/21/2009 | 1674685 | 4.3
304 | Arkansas | PHILLIPS |  | 01 | ARR1005 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.36 MILES OF HIGHWAY 49B BETWEEN HIGHWAY 49 AND HIGHWAY 242 IN THE CITY OF HELENA-WEST HELENA, PHILLIPS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, | Pavement Improvement | 06/03/2009 | 07/02/2009 | 07/15/2009 | 391184 | 1.36
305 | Arkansas | MONROE |  | 01 | ARR1006 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.45 MILES OF HIGHWAY 49 FROM HIGHWAY 241 NORTH IN THE VICINITY OF THE CITY OF RICH IN MONROE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, MAINTENANCE | Pavement Improvement | 04/22/2009 | 06/19/2009 | 07/09/2009 | 580419 | 2.45
306 | Arkansas | CRITTENDEN |  | 01 | ARR1007 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 9.63 MILES OF HIGHWAY 79 IN CRITTENDEN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELL | Pavement Improvement | 04/20/2009 | 04/22/2009 | 07/15/2009 | 2139531 | 9.63
307 | Arkansas | LINCOLN |  | 04 | ARR1008 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.39 MILES OF HIGHWAY 425 NORTH AND SOUTH OF STAR CITY IN LINCOLN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, P | Pavement Improvement | 04/17/2009 | 05/04/2009 | 07/06/2009 | 1253938 | 5.39
308 | Arkansas | CHICOT |  | 04 | ARR1010 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.75 MILES OF HIGHWAY 65 BETWEEN THE CITY OF LAKE VILLAGE AND THE CITY OF MCMILLAN CORNER IN CHICOT COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD | Pavement Improvement | 06/03/2009 | 06/30/2009 | 09/14/2009 | 1175262 | 3.75
309 | Arkansas | ASHLEY |  | 04 | ARR1011 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 6.09 MILES OF HIGHWAY 82 EAST OF THE CITY OF CROSSETT IN ASHLEY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUTTERS, MAINTENAN | Pavement Improvement | 06/15/2009 | 06/16/2009 | 09/14/2009 | 1864060 | 6.09
310 | Arkansas | ARKANSAS |  | 01 | ARR1012 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.11 MILES OF SELECTED SECTIONS OF HIGHWAY 79 BETWEEN HIGHWAY 79C AND HIGHWAY 165 NEAR THE CITY OF STUTTGART IN ARKANSAS COUNTY. WORK INCLUDES PAVEMENT | Pavement Improvement | 04/17/2009 | 05/22/2009 | 07/01/2009 | 682688 | 3.11
311 | Arkansas | PIKE |  | 04 | ARR1013 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.06 MILES OF HIGHWAY 70 FROM THE CITY OF KIRBY EAST IN PIKE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEME | Pavement Improvement | 04/22/2009 | 04/30/2009 | 08/10/2009 | 1082860 | 3.06
312 | Arkansas | NEVADA |  | 04 | ARR1014 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.02 MILES OF HIGHWAY 67 FROM THE CITY OF PRESCOTT SOUTH IN NEVADA COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUTTERS, MAINTE | Pavement Improvement | 06/15/2009 | 06/15/2009 | 09/14/2009 | 1017964 | 3.02
313 | Arkansas | HEMPSTEAD |  | 04 | ARR1015 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.67 MILES OF HIGHWAY 278 BETWEEN HAZEL STREET AND GREENWOOD STREET IN THE CITY OF HOPE, HEMPSTEAD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD M | Pavement Improvement | 06/08/2009 | 06/08/2009 | 09/14/2009 | 335086 | 1.67
314 | Arkansas | LITTLE RIVER |  | 04 | ARR1016 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.41 MILES OF HIGHWAY 71 BETWEEN THE CITIES OF ASHDOWN AND WILTON IN LITTLE RIVER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENAN | Pavement Improvement | 04/27/2009 | 04/27/2009 | 07/24/2009 | 1021455 | 3.41
315 | Arkansas | SEVIER |  | 04 | ARR1017 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.01 MILES OF HIGHWAY 70 FROM THE CITY OF DEQUEEN WEST IN SEVIER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PA | Pavement Improvement | 06/08/2009 | 06/08/2009 | 08/20/2009 | 368943 | 1.01
316 | Arkansas | LAFAYETTE |  | 04 | ARR1018 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.08 MILES OF HIGHWAY 82 EAST AND WEST OF THE RED RIVER IN MILLER AND LAFAYETTE COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH | Pavement Improvement | 04/27/2009 | 05/21/2009 | 08/10/2009 | 609665 | 2.08
317 | Arkansas | HEMPSTEAD |  | 04 | ARR1019 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.45 MILES OF HIGHWAY 278 FROM THE CITY OF OZAN WEST IN HEMPSTEAD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, P | Pavement Improvement | 06/08/2009 | 08/18/2009 | 09/14/2009 | 885084 | 5.45
318 | Arkansas | WASHINGTON |  | 03 | ARR1020 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.78 MILES OF HIGHWAY 412 BETWEEN HIGHWAY 112 AND INTERSTATE 540 IN THE CITY OF SPRINGDALE, WASHINGTON COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, CO | Pavement Improvement | 04/23/2009 | 05/26/2009 | 07/08/2009 | 570814 | 1.78
319 | Arkansas | FRANKLIN |  | 03 | ARR1021 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.09 MILES OF HIGHWAY 22 FROM CHARLESTON EAST IN FRANKLIN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROSION C | Pavement Improvement | 06/15/2009 | 07/27/2009 | 09/14/2009 | 684500 | 3.09
320 | Arkansas | LOGAN |  | 04 | ARR1022 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.77 MILES OF HIGHWAY 22 BETWEEN THE CITIES OF SUBIACO AND MIDWAY IN LOGAN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF T | Pavement Improvement | 04/17/2009 | 04/23/2009 | 05/28/2009 | 691491 | 2.77
321 | Arkansas | SHARP |  | 04 | ARR1023 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.47 MILES OF HIGHWAY 71 SOUTH OF THE CITY OF WALDRON IN SCOTT COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROS | Pavement Improvement | 06/15/2009 | 07/07/2009 | 08/07/2009 | 805350 | 3.47
322 | Arkansas | SEBASTIAN |  | 03 | ARR1024 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.74 MILES OF HIGHWAY 22 FROM INTERSTATE 540 EAST IN THE CITY OF FORT SMITH, SEBASTIAN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAIN | Pavement Improvement | 06/08/2009 | 06/24/2009 | 09/07/2009 | 1069701 | 2.74
323 | Arkansas | POLK |  | 04 | ARR1025 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.65 MILES OF HIGHWAY 71 SOUTH AND NORTH OF HIGHWAY 8 IN THE CITY OF MENA, POLK COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE | Pavement Improvement | 04/27/2009 | 05/29/2009 | 06/24/2009 | 581777 | 1.65
324 | Arkansas | CRAWFORD |  | 03 | ARR1026 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.00 MILES OF HIGHWAY 64 FROM ALMA EAST IN CRAWFORD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROSION CONTROL | Pavement Improvement | 04/20/2009 | 04/20/2009 | 07/24/2009 | 524121 | 2
325 | Arkansas | WHITE |  | 02 | ARR1027 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.67 MILES OF HIGHWAY 167 NORTH OF THE CITY OF BALD KNOB IN WHITE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, P | Pavement Improvement | 06/08/2009 | 07/27/2009 | 09/01/2009 | 1132854 | 3.67
326 | Arkansas | STONE |  | 01 | ARR1028 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.57 MILES OF HIGHWAY 14 EAST OF THE CITY OF MOUNTAIN HOME IN STONE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 04/17/2009 | 05/04/2009 | 05/19/2009 | 438853 | 1.57
327 | Arkansas | WHITE |  | 02 | ARR1029 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.88 MILES OF HIGHWAY 167 FROM THE JACKSON COUNTY LINE NORTH IN WHITE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFI | Pavement Improvement | 06/08/2009 | 07/09/2009 | 09/14/2009 | 862415 | 2.88
328 | Arkansas | WHITE, INDEPENDENCE |  | 01,02 | ARR1030 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.64 MILES OF HIGHWAY 167 FROM THE CITY OF PLEASANT PLAINS SOUTH IN INDEPENDENCE AND WHITE COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING | Pavement Improvement | 04/17/2009 | 05/28/2009 | 06/01/2009 | 862046 | 2.64
329 | Arkansas | CLEBURNE |  | 01 | ARR1031 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.66 MILES OF HIGHWAY 25 FROM GREERS FERRY DAM SOUTH IN THE VICINITY OF THE CITY OF HEBER SPRINGS IN CLEBURNE COUNTY. WORK INCLUDES PAVEMENT REHABILITAT | Pavement Improvement | 04/22/2009 | 07/15/2009 | 08/10/2009 | 667833 | 2.66
330 | Arkansas | INDEPENDENCE |  | 01 | ARR1032 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.14 MILES OF HIGHWAY 69 FROM THE BLACK RIVER WEST IN INDEPENDENCE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 06/03/2009 | 07/06/2009 | 09/14/2009 | 245794 | 1.14
331 | Arkansas | PULASKI |  | 02 | ARR1033 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.10 MILES OF INTERSTATE 40 BETWEEN INTERSTATE 30 AND HIGHWAY 67 IN THE CITY OF NORTH LITTLE ROCK, PULASKI COUNTY. WORK INCLUDES CONCRETE PAVEMENT PATCH | Pavement Improvement | 08/04/2009 | 08/17/2009 | 11/13/2009 | 1709583 | 1.1
332 | Arkansas | LONOKE |  | 01 | ARR1034 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.80 MILES OF HIGHWAY 70 FROM THE PULASKI COUNTY LINE EAST IN LONOKE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, TRENCHING AND SHOULDER PREPARATION, | Pavement Improvement | 04/28/2009 | 04/28/2009 | 06/30/2009 | 467972 | 2.8
333 | Arkansas | HOT SPRING |  | 04 | ARR1035 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.20 MILES OF HIGHWAY 67 FROM THE CITY OF GLEN ROSE SOUTH IN HOT SPRING COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, TRENCHING AND SHOULDER PREPARATIO | Pavement Improvement | 04/17/2009 | 05/05/2009 | 06/17/2009 | 264789 | 1.2
334 | Arkansas | PRAIRIE |  | 01 | ARR1036 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.40 MILES OF HIGHWAY 70 BETWEEN HAZEN AND DEVALLS BLUFF IN PRAIRIE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 04/22/2009 | 04/22/2009 | 06/17/2009 | 993892 | 5.4
335 | Arkansas | LONOKE, PULASKI |  | 02 | ARR1037 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.25 MILES OF HIGHWAY 165 BETWEEN THE CITIES OF NORTH LITTLE ROCK AND SCOTT IN LONOKE AND PULASKI COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD | Pavement Improvement | 06/01/2009 | 06/08/2009 | 09/14/2009 | 1153688 | 7.25
336 | Arkansas | OUACHITA |  | 04 | ARR1038 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.60 MILES OF HIGHWAY 79 BETWEEN THE CITIES OF CAMDEN AND EAST CAMDEN IN OUACHITA COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH | Pavement Improvement | 06/03/2009 | 06/22/2009 | 09/14/2009 | 1313310 | 2.6
337 | Arkansas | DALLAS |  | 04 | ARR1039 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.61 MILES OF HIGHWAY 79 IN DALLAS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEO | Pavement Improvement | 04/17/2009 | 05/07/2009 | 06/24/2009 | 1124559 | 3.61
338 | Arkansas | CLEVELAND |  | 04 | ARR1040 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 9.50 MILES OF HIGHWAY 79 BETWEEN THE CITIES OF KINGLAND AND RISON IN CLEVELAND COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUT | Pavement Improvement | 06/03/2009 | 06/11/2009 | 08/21/2009 | 1360655 | 9.5
339 | Arkansas | CALHOUN |  | 04 | ARR1041 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.12 MILES OF HIGHWAY 167 FROM THE CITY OF HAMPTON SOUTH IN CALHOUN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 04/17/2009 | 05/05/2009 | 06/09/2009 | 1026517 | 4.12
340 | Arkansas | VAN BUREN |  | 02 | ARR1042 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.87 MILES OF HIGHWAY 65 NORTH OF THE CITY OF CLINTON IN VAN BUREN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 06/08/2009 | 08/10/2009 | 09/14/2009 | 1748105 | 5.87
341 | Arkansas | FAULKNER |  | 02 | ARR1043 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.68 MILES OF HIGHWAY 65 NORTH AND SOUTH OF HIGHWAY 25 IN THE CITY OF GREENBRIER, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 04/22/2009 | 07/02/2009 | 08/03/2009 | 794592 | 2.68
342 | Arkansas | YELL |  | 02 | ARR1044 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.90 MILES OF HIGHWAY 10 EAST AND WEST OF THE CITY OF MICKLES IN YELL COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFI | Pavement Improvement | 04/17/2009 | 04/27/2009 | 07/07/2009 | 977943 | 5.9
343 | Arkansas | POPE |  | 03 | ARR1045 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.64 MILES OF HIGHWAY 7 BETWEEN J STREET AND HIGHWAY 326 IN THE CITY OF RUSSELLVILLE, POPE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 06/04/2009 | 09/04/2009 | 09/14/2009 | 467309 | 1.64
344 | Arkansas | FAULKNER |  | 02 | ARR1046 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 0.37 MILE OF HIGHWAY 65 BETWEEN THE INTERSTATE 40 OFF AND ON RAMPS IN THE CITY OF CONWAY, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD M | Pavement Improvement | 04/22/2009 | 07/02/2009 | 08/05/2009 | 196872 | 0.37
345 | Arkansas | BENTON |  | 03 | ARR1047 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE HIGHWAY 412 FROM HIGHWAY 59 IN THE CITY OF SILOAM SPRINGS TO THE EAST 5.45 MILES IN BENTON COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 06/01/2009 | 06/22/2009 | 08/27/2009 | 2030641 | 5.45
346 | Arkansas | BOONE |  | 03 | ARR1048 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.40 MILES OF HIGHWAY 65 FROM THE MISSOURI STATE LINE SOUTH IN BOONE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC | Pavement Improvement | 04/22/2009 | 05/04/2009 | 07/28/2009 | 2940266 | 7.4
347 | Arkansas | GREENE |  | 01 | ARR1052 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.79 MILES OF HIGHWAY 412 BETWEEN REYNOLDS ROAD AND HIGHWAY 49B IN THE CITY OF PARAGOULD, GREENE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MIL | Pavement Improvement | 06/08/2009 | 08/19/2009 | 09/14/2009 | 770949 | 1.79
348 | Arkansas | MISSISSIPPI |  | 01 | ARR1053 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 0.84 MILE OF HIGHWAY 18 FROM INTERSTATE 55 WEST IN THE CITY OF BLYTHEVILLE, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAI | Pavement Improvement | 04/27/2009 | 04/27/2009 | 05/28/2009 | 348065 | 0.84
349 | Arkansas | CLAY |  | 01 | ARR1054 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.10 MILES OF HIGHWAY 67 BETWEEN HIGHWAY 328 NORTH OF CORNING AND THE MISSOURI STATE LINE IN CLAY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MI | Pavement Improvement | 06/08/2009 | 07/15/2009 | 09/14/2009 | 1098919 | 4.1
350 | Arkansas | MISSISSIPPI |  | 01 | ARR1055 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.10 MILES OF HIGHWAY 140 WEST AND EAST OF HIGHWAY 119Y IN THE CITY OF OSCEOLA, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 04/27/2009 | 05/15/2009 | 06/09/2009 | 452888 | 1.1
351 | Arkansas | LAWRENCE |  | 01 | ARR1056 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE A 0.26 MILE SECTION OF HIGHWAY 412 BETWEEN HIGHWAY 67B NORTH AND HIGHWAY 67B SOUTH IN THE CITY OF WALNUT RIDGE, LAWRENCE COUNTY. WORK INCLUDES PAVEMENT | Pavement Improvement | 06/01/2009 | 08/11/2009 | 09/14/2009 | 125418 | 0.26
352 | Arkansas | RANDOLPH |  | 01 | ARR1057 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.05 MILES OF HIGHWAY 67 FROM HIGHWAY 90 NORTH IN THE THE CITY OF POCAHONTAS, RANDOLPH COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAIN | Pavement Improvement | 04/17/2009 | 05/14/2009 | 08/03/2009 | 174441 | 1.05
353 | Arkansas | POINSETT |  | 01 | ARR1058 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.14 MILES OF HIGHWAY 63 FROM THE CRAIGHEAD COUNTY LINE TO HIGHWAY 69 WEST OF THE CITY OF TRUMANN IN POINSETT COUNTY. WORK INCLUDES PAVEMENT REHABILITAT | Pavement Improvement | 06/01/2009 | 06/04/2009 | 09/14/2009 | 673482 | 2.14
354 | Arkansas | CRAIGHEAD |  | 01 | ARR1059 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.59 MILES OF HIGHWAY 63 BETWEEN HIGHWAY 91 AND HIGHWAY 226 IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK INCLUDES CONCRETE PAVEMENT GRINDING AND P | Pavement Improvement | 05/08/2009 | 06/04/2009 | 10/30/2009 | 1180866 | 3.59
355 | Arkansas | GARLAND |  | 04 | ARR1060 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 0.37 MILE OF HIGHWAY 128 FROM SHADY GROVE ROAD TO NORTH OF HIGHWAY 270 IN THE CITY OF HOT SPRINGS, GARLAND COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADW | Pavement Widening | 09/23/2009 | 10/27/2009 |  | 1583907 | 0.37
356 | Arkansas | GRANT |  | 04 | ARR1061 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.1 MILES OF HIGHWAY 167 BETWEEN NORTH MILLERVILLE AND THE SHERIDAN BYPASS IN GRANT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN | Pavement Widening | 09/18/2009 | 09/24/2009 |  | 8819100 | 4.1
357 | Arkansas | SEBASTIAN |  | 03 | ARR1063 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT FOUR MAIN LANE BRIDGES AS PART OF THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49) BETWEEN TAYLOR AVENUE AND HIGHWAY 22 NEAR FT. CHAFFEE IN SEBASTIAN C | New Bridge Construction | 07/06/2009 | 07/09/2009 | 12/30/2010 | 11693084 | 0.33
358 | Arkansas | SEBASTIAN |  | 03 | ARR1064 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 2.69 MILES OF GRADING AND STRUCTURES OF THE NEW LOCATION HIGHWAY 71 BETWEEN CO ROAD 8 AND CUSTER BLVD. NEAR FORT CHAFFEE IN SEBASTIAN COUNTY. WORK WILL INC | New Construction | 10/16/2009 | 10/15/2009 |  | 10730011 | 2.69
359 | Arkansas | MILLER |  | 04 | ARR1065 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 1.77 MILES OF EMBANKMENT AND MINOR DRAINAGE STRUCTURES FOR THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49) BETWEEN COUNTY ROAD 2 AND DODDRIDGE, SOUTH | New Construction | 08/21/2009 | 09/03/2009 | 06/25/2011 | 6685747 | 1.77
360 | Arkansas | CRAIGHEAD |  | 01 | ARR1066 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 141 AND PARKER ROAD IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK ITEMS INCLUDE TRAFFIC SI | Safety/Traffic Management | 06/08/2009 | 10/20/2009 | 12/18/2009 | 83737 | 0
361 | Arkansas | ARKANSAS |  | 01 | ARR1067 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT APPROXIMATELY 1.30 MILES OF COUNTY ROADS 33 AND 43 NEAR THE CITY OF ALMYRA IN ARKANSAS COUNTY. WORK WILL INCLUDE RECONSTRUCTING THE EXISTING ROADWAY, PAV | Pavement Improvement | 06/15/2009 | 06/26/2009 | 08/14/2009 | 159875 | 1.3
362 | Arkansas | PULASKI |  | 02 | ARR2006 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT TWO CONCRETE. BOX CULVERTS AND APPROACHES ON 0.360 MILE OF COUNTY ROAD 67 IN THE VICINITY OF SHERWOOD IN PULASKI COUNTY. WORK INCLUDES CLEARING AND GRUBBI | Bridge Replacement | 09/17/2009 | 09/17/2009 |  | 770372 | 0.36
363 | Arkansas | BENTON |  | 03 | ARR2008 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A BRIDGE AND APPROACHES ON APPROXIMATELY 0.47 MILE OF COUNTY ROAD 9 NEAR SILOAM SPRINGS IN BENTON COUNTY. WORK WILL INCLUDE CLEARING, GRADING, DRAINAGE IMP | Bridge Replacement | 11/20/2009 |  |  | 1319151 | 0.46
364 | Arkansas | BRADLEY |  | 04 | ARR2009 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT ONE CONCRETE BOX CULVERT AND APPROACHES ON 0.80 MILE OF COUNTY ROAD 2 IN THE VICINITY OF HERMITAGE IN BRADLEY COUNTY. WORK INCLUDES CLEARING AND GRUBBING, | Pavement Improvement | 08/12/2009 | 08/20/2009 | 12/18/2009 | 319946 | 0.8
365 | Arkansas | RANDOLPH |  | 01 | ARR2010 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT ONE BRIDGE LENGTH STRUCTURE AND APPROACHES ON 0.492 MILE OF COUNTY ROAD 48 NEAR POCAHONTAS IN RANDOLPH COUNTY. WORK INCLUDES GRADING, DRAINAGE IMPROVEMENTS, | Bridge Replacement | 06/22/2009 | 07/09/2009 | 12/22/2010 | 1693838 | 0.49
366 | Arkansas | CLARK |  | 01 | ARR2011 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT TWO BRIDGE LENGTH STRUCTURES AND APPROACHES ON 0.72 MILE OF COUNTY ROAD 38 NEAR ASH FLAT IN SHARP COUNTY. WORK WILL INCLUDE EARTHWORK, DRAINAGE IMPROVEMENT | Pavement Improvement | 07/14/2009 | 07/16/2009 | 12/22/2010 | 985359 | 0.72
367 | Arkansas | ST FRANCIS |  | 01 | ARR2012 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 1 AND HIGHWAY 306 IN THE CITY OF COLT IN ST. FRANCIS COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 11/06/2009 | 11/30/2009 |  | 127341 | 0
368 | Arkansas | WASHINGTON |  | 03 | ARR2013 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 16 AND HIGHWAY 74 IN THE CITY OF ELKINS IN WASHINGTON COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 11/06/2009 |  |  | 65247 | 0
369 | Arkansas | CLARK |  | 04 | ARR2014 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL THREE TRAFFIC SIGNALS ON HIGHWAY 67 AT THE INTERSECTIONS OF HENDERSON STREET, HIGHWAY 51 WEST/PINE STREET AND HIGHWAY 51 EAST/CADDO STREET IN TH | Safety/Traffic Management | 11/13/2009 |  |  | 203370 | 0
370 | Arkansas | FAULKNER |  | 02 | ARR2016 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 64, ROOSTER ROAD AND LOWER RIDGE ROAD NEAR THE CITY OF CONWAY IN FAULKNER COUNTY. WORK ITEMS IN | Pavement Improvement | 08/19/2009 | 09/14/2009 | 02/05/2010 | 74500 | 0
371 | Arkansas | HEMPSTEAD |  | 04 | ARR2018 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 278, HIGHWAY 29 AND SHOVER ROAD IN THE CITY OF HOPE IN HEMPSTEAD COUNTY. WORK ITEMS INCLUDE TRA | Transportation Enhancements | 12/31/2009 |  |  | 113093 | 0
372 | Arkansas | LINCOLN, DESHA |  | 04 | ARR2031 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 5.39 MILES OF HIGHWAY 65 NORTH AND SOUTH OF THE CITY OF GOULD IN LINCOLN AND DESHA COUNTIES. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, DRAINAGE IMPROVEM | Pavement Widening | 09/18/2009 | 12/10/2009 |  | 15776865 | 5.39
373 | Arkansas | UNION |  | 04 | ARR2043 | THE PURPOSE OF THIS PROJECT IS TO PROVIDE 3.22 MILES OF BASE AND SURFACING TO COMPLETE WIDENING HIGHWAY 167 BETWEEN CHAMPAGNOLLE ROAD AND HIGHWAY 7 SOUTH IN THE CITY OF EL DORADO, UNION COUNTY. WORK | New Construction | 11/09/2009 | 12/04/2009 |  | 552587 | 3.22
374 | Arkansas | WASHINGTON, BENTON |  | 03 | ARR2050 | THE PURPOSE OF THIS PROJECT IS TO WIDEN RAMPS AND ADD AUXILIARY LANES AT FOUR INTERCHANGES IN BENTON AND WASHINGTON COUNTIES. IMPROVEMENTS AT A FIFTH INTERCHANGE (PORTER RD.) IN WASHINGTON COUNTY INV | Pavement Widening | 09/29/2009 | 10/12/2009 |  | 2013305 | 0.1
375 | Arkansas | FAULKNER | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2052 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A RAILROAD OVERPASS BRIDGE WITH APPROACH EMBANKMENTS ON SALEM ROAD IN THE CITY OF CONWAY, FAULKNER COUNTY. WORK INCLUDES CONSTRUCTING THE RAILROAD OVERPASS | New Bridge Construction | 09/30/2009 | 09/30/2009 |  | 2360595 | 0.31
376 | Arkansas | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2056 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 0.851 MILE OF HIGHWAY 107 IN PULASKI COUNTY. WORK INCLUDES GRADING, MINOR DRAINAGE STRUCTURES, PAVING, STORM DRAINS, EROSION CONTROL ITEMS, MAINTENANCE OF TRAF | Pavement Widening | 11/12/2009 | 11/12/2009 |  | 2669342 | 0.85
377 | Arkansas | GRANT |  | 04 | ARR2057 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.91 MILES OF HIGHWAY 167 BETWEEN THE SALINE RIVER AND NORTH MILLERVILLE IN GRANT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN 11 | Bridge Replacement | 11/13/2009 | 12/01/2009 |  | 7244745 | 4.91
378 | California | COLUSA, SACRAMENTO, PLACER | SACRAMENTO | 2,4,5 | 000C303 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In Colusa, Placer and Sacramento Counties, at various locations. | Pavement Improvement | 09/18/2009 | 09/18/2009 | 11/01/2010 | 6246659 | 1
379 | California | YOLO, SACRAMENTO, PLACER | SACRAMENTO | 2,4,5 | 000C304 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In Sacramento, El Dorado, Yolo and Placer counties, at various locations. | Safety/Traffic Management | 06/02/2009 | 07/27/2009 | 06/01/2011 | 1810921 | 1
380 | California | TEHAMA, PLUMAS |  | 4 | 000C305 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Tehama and Plumas Counties, as Various Locations. | Pavement Improvement | 06/26/2009 | 07/06/2009 | 12/01/2010 | 2629087 | 1
381 | California | KINGS |  | 20 | 000C306 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Kern and King Counties near Avenal and Devils Den (Sunflower Valley) on State Ro | Pavement Improvement | 07/02/2009 | 07/09/2009 | 12/01/2009 | 3891487 | 1
382 | California | LOS ANGELES | LOS ANGELES, CA | 27,28 | 0053014 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Sun Valley and Sylmar, from Hollywood Way to north of San Fer | Pavement Improvement | 10/12/2009 | 10/22/2009 | 12/01/2010 | 11254618 | 4.9
383 | California | KERN |  | 22 | 0054182 | This is a Safety project by the California Department of Transportation. The project is described as: Near Grapevine, at various locations. | Pavement Improvement | 07/15/2009 | 09/08/2009 | 02/01/2011 | 1651958 | 3.8
384 | California | TEHAMA |  | 2 | 0058336 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In and near Red Bluff, from 5.3 miles south of Adobe Road Overcr | Pavement Improvement | 07/08/2009 | 08/24/2009 | 12/01/2010 | 34239790 | 3.4
385 | California | RIVERSIDE |  | 44 | 0155152 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Riverside County in and near Corona, from Temescal Canyon Road to 0.4 mile south | Pavement Improvement | 06/15/2009 | 06/29/2009 | 12/01/2009 | 851045 | 5
386 | California | SOLANO | SAN FRANCISCO-OAKLAND, CA | 10 | 0802356 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Fairfield, from 0.4 mile west of Route 12 to 0.8 mile east of | Pavement Improvement | 04/28/2009 | 05/18/2009 | 12/01/2009 | 19570134 | 4.7
387 | California | LOS ANGELES | LOS ANGELES, CA | 26,29 | 2101795 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Los Angeles County in and near Pasadena, from State Route 2-A | Pavement Improvement | 09/16/2009 | 11/09/2009 | 05/01/2011 | 341883 | 5.4
388 | California | SANTA CLARA | SAN FRANCISCO-OAKLAND, CA | 15 | 2801119 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In San Jose, from Cypress Avenue Pedestrian Overcrossing to Tant | Pavement Improvement | 07/29/2009 | 09/09/2009 | 01/01/2011 | 11594095 | 2.7
389 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 2801122 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In San Mateo County from Santa Clara County line to San Francisco County | Safety/Traffic Management | 09/17/2009 |  | 10/01/2010 | 1814073 | 27.4
390 | California | LOS ANGELES | LOS ANGELES, CA | 27,28,30,36 | 4053015 | This is a Design-Build Contract project by the California Department of Transportation. The project is described as: Widen NB I-405 for HOV Lane | Safety/Traffic Management | 06/02/2009 | 06/02/2009 | 04/01/2013 | 189900000 | 10.2
391 | California | SACRAMENTO | SACRAMENTO | 5 | 5002138 | This is a Pavement Restoration and Rehabilitation project by the City of Sacramento. The project is described as: Rehabilitate various roadways in Sacramento. | Pavement Improvement | 08/26/2009 |  | 12/01/2010 | 5746013 | 1
392 | California | SANTA CLARA | SAN JOSE, CA | 11,14,15,16 | 5005096 | This is a Pavement Restoration and Rehabilitation project by the City of San Jose. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/06/2009 |  | 08/01/2010 | 9302466 | 8.65
393 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5006569 | This is a Pavement Restoration and Rehabilitation project by the City of Los Angeles. The project is described as: LAX HOSPITALITY ZONE STREET AND SIDEWALK REHABILITATION - PHASE II : THIS PROJECT WI | Pavement Improvement | 07/06/2009 |  | 12/01/2010 | 7000000 | 3.85
394 | California | LOS ANGELES | LOS ANGELES, CA | 25,27 | 5006571 | This is a Facilities for Pedestrians and Bicycles project by the City of Los Angeles. The project is described as: COMMERCE AVE PEDESTRIAN IMPROVEMENTS: THIS IS A PILOT PROJECT TO INSTALL GREEN SIDEW | Pavement Improvement | 07/06/2009 |  | 02/01/2010 | 900000 | 0.5
395 | California | LOS ANGELES | LOS ANGELES, CA | 29,31,32,33,34 | 5006577 | This is a Pavement Resurfacing project by the City of Los Angeles. The project is described as: CITY OF LOS ANGELES NORTH CENTRAL REGION RESURFACING PROJECT- PHASE II: THIS PROJECT WILL RESURFACE AND | Pavement Improvement | 07/01/2009 |  | 09/01/2010 | 7275000 | 14
396 | California | LOS ANGELES | LOS ANGELES, CA | 27,30 | 5006578 | This is a Pavement Resurfacing project by the City of Los Angeles. The project is described as: CITY OF LOS ANGELES WEST VALLEY REGION RESURFACING PROJECT - PHASE II: THIS PROJECT WILL RESURFACE AND | Pavement Improvement | 07/01/2009 |  | 09/01/2010 | 7275000 | 18
397 | California | LOS ANGELES | LOS ANGELES, CA | 25,27,28 | 5006579 | This is a Pavement Resurfacing project by the City of Los Angeles. The project is described as: CITY OF LOS ANGELES EAST VALLEY REGION RESURFACING PROJECTS - PHASE II: THIS PROJECT WILL RESURFACE AND | Pavement Improvement | 07/01/2009 |  | 09/01/2010 | 7275000 | 16
398 | California | LOS ANGELES | LOS ANGELES, CA | 35,36,37,39,46 | 5006580 | This is a Pavement Resurfacing project by the City of Los Angeles. The project is described as: CITY OF LOS ANGELES BAY HARBOR REGION RESURFACING PROJECTS - PHASE II: THIS PROJECT WILL RESURFACE AND | Pavement Improvement | 07/01/2009 |  | 09/01/2010 | 7275000 | 16.5
399 | California | LOS ANGELES | LOS ANGELES, CA | 35,36,37,39,46 | 5006595 | This is a Pavement Resurfacing project by the City of Los Angeles. The project is described as: CITY OF LOS ANGELES BAY HARBOR REGION RESURFACING PROJECTS - PHASE I: THIS PROJECT WILL RESURFACE AND R | Pavement Improvement | 07/01/2009 |  | 09/01/2011 | 15588000 | 10.25
400 | California | SAN JOAQUIN | STOCKTON | 18 | 5008087 | This is a Pavement Restoration and Rehabilitation project by the City of Stockton. The project is described as: Rehabilitation of 24 streets in the City of Stockton. | Pavement Improvement | 10/01/2009 |  | 09/01/2009 | 6141391 | 14
401 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5014032 | This is a Pavement Restoration and Rehabilitation project by the City of Alameda. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/07/2009 |  | 09/01/2009 | 1304000 | 1.04
402 | California | EL DORADO | SACRAMENTO | 4 | 5015013 | This is a Pavement Resurfacing project by the City of Placerville. The project is described as: Cold Springs Road, from Placerville City Limit to Sleepy Hollow Road: Rehabilitate roadways. | Pavement Improvement | 11/16/2009 |  | 11/01/2009 | 650000 | 0.8
403 | California | HUMBOLDT |  | 1 | 5017023 | This is a Pavement Resurfacing project by the City of Eureka. The project is described as: Street grind, patch and overlay. | Pavement Improvement | 10/29/2009 |  | 10/01/2009 | 665129 | 3.53
404 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5019022 | This is a Pavement Restoration and Rehabilitation project by the City of Santa Clara. The project is described as: Rehabilitate local street. | Pavement Improvement | 11/02/2009 |  | 08/01/2009 | 962000 | 4.8
405 | California | SONOMA | SANTA ROSA | 6 | 5022044 | This is a Pavement Restoration and Rehabilitation project by the City of Petaluma. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/10/2009 |  | 11/01/2009 | 1109000 | 1.01
406 | California | CONTRA COSTA | CONCORD | 7,10 | 5024023 | This is a Pavement Restoration and Rehabilitation project by the City of Martinez. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/14/2009 |  | 11/01/2009 | 850000 | 4.2
407 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5025045 | This is a Pavement Restoration and Rehabilitation project by the City of Santa Cruz. The project is described as: Road repairs: Morrissey Blvd from Soquel Ave to Fairmount. | Pavement Improvement | 08/18/2009 |  | 10/01/2010 | 451000 | 0.2
408 | California | VENTURA | OXNARD-VENTURA | 23 | 5026043 | This is a Pavement Restoration and Rehabilitation project by the City of San Buena Ventura. The project is described as: Street Rehab. Olive Street Phase I. | Pavement Improvement | 01/05/2010 |  | 11/01/2009 | 530943 | 1
409 | California | SONOMA | SANTA ROSA | 1,6 | 5027014 | This is a Pavement Restoration and Rehabilitation project by the City of Healdsburg. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/08/2009 |  | 08/01/2009 | 500000 | 2.47
410 | California | SONOMA | SANTA ROSA | 1,6 | 5028053 | This is a Pavement Restoration and Rehabilitation project by the City of Santa Rosa. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/30/2009 |  | 10/01/2009 | 3696000 | 2.1
411 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5029020 | This is a Pavement Restoration and Rehabilitation project by the Redwood City. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/08/2009 |  | 12/01/2009 | 736000 | 1.5
412 | California | SOLANO | VALLEJO | 1,7 | 5030048 | This is a Facilities for Pedestrians and Bicycles project by the City of Vallejo. The project is described as: Pedestrian Enhancements. | Transportation Enhancements | 12/14/2009 |  | 02/01/2011 | 2138000 | 0.85
413 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5031018 | This is a Pavement Restoration and Rehabilitation project by the City of Watsonville. The project is described as: Road repairs: various roadways. | Pavement Improvement | 08/13/2009 |  | 10/01/2010 | 1200000 | 10
414 | California | SANTA CLARA | SAN JOSE, CA | 11,15,16 | 5034020 | This is a Pavement Restoration and Rehabilitation project by the City of Gilroy. The project is described as: Rehabilitate local street. | Transportation Enhancements | 01/18/2010 |  | 02/01/2010 | 663000 | 9.4
415 | California | SONOMA |  | 1 | 5039021 | This is a Pavement Restoration and Rehabilitation project by the City of Cloverdale. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/25/2009 |  | 08/01/2009 | 500000 | 1.6
416 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,13 | 5041033 | This is a Pavement Restoration and Rehabilitation project by the City of San Leandro. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/17/2009 |  | 11/01/2009 | 1338000 | 0.65
417 | California | NAPA | SAN FRANCISCO-OAKLAND, CA | 1 | 5042049 | This is a Pavement Restoration and Rehabilitation project by the City of Napa. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/04/2009 |  | 10/01/2009 | 1600000 | 1.4
418 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5043030 | This is a Pavement Restoration and Rehabilitation project by the City of San Rafael. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/23/2009 |  | 08/01/2009 | 1188000 | 3.33
419 | California | TULARE | VISALIA | 21 | 5044051 | This is a Traffic Management Engineering project by the City of Visalia. The project is described as: Widening of Ben Maddox Bridge over SR-198 from 5-8 lanes (2 thru lanes each direction plus dual l | Bridge Improvement | 12/28/2009 |  | 12/01/2010 | 6400000 | 0.79
420 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5045023 | This is a Pavement Resurfacing project by the City of Salinas. The project is described as: Reconstruct between Natividad and North Sanborn Roads. | Pavement Improvement | 08/31/2009 |  | 12/01/2009 | 2956000 | 1
421 | California | YOLO |  | 2 | 5046029 | This is a Pavement Restoration and Rehabilitation project by the City of Woodland. The project is described as: CR 102, from East Beamer St to Hanson Way: Rehabilitate roadway.. | Pavement Improvement | 09/21/2009 |  | 10/01/2009 | 655725 | 1
422 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,13 | 5050036 | This is a Pavement Restoration and Rehabilitation project by the City of Hayward. The project is described as: Rehabilitate local street. | Pavement Improvement | 07/24/2009 |  | 03/01/2010 | 2037000 | 3.88
423 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 10,11 | 5053018 | This is a Pavement Restoration and Rehabilitation project by the City of Livermore. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/10/2009 |  | 09/01/2009 | 1479000 | 1.13
424 | California | SOLANO |  | 3,10 | 5056016 | This is a Pavement Restoration and Rehabilitation project by the City of Dixon. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/19/2009 |  | 08/01/2009 | 300000 | 0.52
425 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 7,9,10 | 5057032 | This is a Pavement Restoration and Rehabilitation project by the City of Berkeley. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/18/2009 |  | 12/01/2009 | 1619000 | 0.56
426 | California | RIVERSIDE | SAN BERNARDINO-RIVERSIDE | 44 | 5058079 | This is a Landscaping and Other Scenic Beautification project by the County of Riverside. The project is described as: Install median landscaping. | Transportation Enhancements | 12/21/2009 |  | 05/01/2010 | 348000 | 1
427 | California | ORANGE | LOS ANGELES, CA | 47 | 5063131 | This is a Pavement Reconstruction, No Added Capacity project by the City of Santa Ana. The project is described as: Roadway Rehabilitation Non-capacity Adding . | Pavement Improvement | 01/04/2010 |  | 06/01/2011 | 980000 | 0.4
428 | California | SANTA CLARA | SAN JOSE, CA | 14,15,16 | 5067014 | This is a Traffic Management Engineering project by the City of Los Gatos. The project is described as: Intersection improvements and signal upgrade. | Safety/Traffic Management | 07/20/2009 |  | 09/01/2009 | 453295 | 0.25
429 | California | SANTA BARBARA | LOMPOC | 24 | 5080021 | This is a Pavement Resurfacing project by the City of Lompoc. The project is described as: Street pavement rehabilitation and overlays on V Street, College Avenue, 7th Street, O Street, and North Ave | Pavement Improvement | 09/21/2009 |  | 10/01/2009 | 682161 | 2.7
430 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5086029 | This is a Pavement Resurfacing project by the City of Monterey. The project is described as: Reconstruct between Fremont and Elorado. | Pavement Improvement | 08/31/2009 |  | 12/01/2009 | 602716 | 1
431 | California | MONTEREY |  | 17 | 5086030 | This is a Safety project by the City of Monterey. The project is described as: Del Monte/Figueroa; Traffic signal modifications and curb return/ADA/new bike lane improvements, safety lighting, and o | Safety/Traffic Management | 01/04/2010 |  | 12/01/2009 | 375000 | 1
432 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5087027 | This is a Facilities for Pedestrians and Bicycles project by the City of Pacific Grove. The project is described as: Sidewalk and storm drain improvements. | Transportation Enhancements | 11/10/2009 |  | 12/01/2009 | 303000 | 1
433 | California | KINGS | HANFORD | 20 | 5091037 | This is a Pavement Resurfacing project by the City of Hanford. The project is described as: City of Hanford, Hanford-Armona Road, From 11th Avenue to Greenbriar Dr; Rehabilitate Roadway. | Pavement Improvement | 10/12/2009 |  | 08/01/2009 | 825000 | 1
434 | California | LOS ANGELES | LOS ANGELES, CA | 36 | 5093013 | This is a Pavement Resurfacing project by the City of Redondo Beach. The project is described as: PRIORITY 1 INGLEWOOD AVE STREET RESURFACING FROM ARTESIA BLVD TO MANHATTAN BEACH BLVD, INCLUDES STREE | Pavement Improvement | 10/12/2009 |  | 09/01/2009 | 1058000 | 1
435 | California | SOLANO | VACAVILLE | 3,7,10 | 5094049 | This is a Facilities for Pedestrians and Bicycles project by the City of Vacaville. The project is described as: Pedestrian Enhancements. | Safety/Traffic Management | 06/12/2009 |  | 08/01/2009 | 260000 | 0.27
436 | California | PLACER | SACRAMENTO | 4 | 5095013 | This is a Pavement Restoration and Rehabilitation project by the City of Rocklin. The project is described as: Rehabilitate Sunset Boulevard from Blue Oaks Blvd to Atherton Road.. | Pavement Improvement | 09/14/2009 |  |  | 1289206 | 1
437 | California | SANTA CLARA | SAN JOSE, CA | 14 | 5100011 | This is a Pavement Restoration and Rehabilitation project by the City of Palo Alto. The project is described as: Rehabilitate local street. | Pavement Improvement | 11/10/2009 |  | 10/01/2009 | 580000 | 0.6
438 | California | SANTA CLARA | SAN JOSE, CA | 14 | 5100012 | This is a Pavement Restoration and Rehabilitation project by the City of Palo Alto. The project is described as: Rehabilitate local street. | Pavement Improvement | 12/04/2009 |  | 10/01/2009 | 505000 | 1.7
439 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,10,11,13 | 5101022 | This is a Pavement Restoration and Rehabilitation project by the City of Pleasanton. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/15/2009 |  | 09/01/2009 | 1216711 | 1.2
440 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5102034 | This is a Pavement Restoration and Rehabilitation project by the City of San Mateo. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/17/2009 |  | 11/01/2009 | 1196775 | 4
441 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5107021 | This is a Pavement Resurfacing project by the City of Santa Monica. The project is described as: SANTA MONICA BLVD RESURFACING PROJECT PHASE II - MAINTENANCE AND REPAIR TO THE EXISTING ASPHALT STREET | Pavement Improvement | 01/05/2010 |  | 06/01/2010 | 882288 | 0.7
442 | California | KERN | BAKERSFIELD | 22 | 5109153 | This is a Pavement Reconstruction, No Added Capacity project by the City of Bakersfield. The project is described as: Hughes Lane: White Lane to Planz Rd; Wible Road: White Lane to Pacheco Road; Wils | Other | 09/02/2009 |  | 11/01/2009 | 2040374 | 1.56
443 | California | KERN | BAKERSFIELD | 22 | 5109154 | This is a Pavement Reconstruction, No Added Capacity project by the City of Bakersfield. The project is described as: Mt. Vernon Ave: State Route 178 to University Ave; Resurfacing, Reconstruction. | Other | 09/03/2009 |  | 11/01/2009 | 1772000 | 0.7
444 | California | YOLO |  | 2 | 5110027 | This is a Safety project by the City of Winters. The project is described as: Grant Ave.(SR128), east of Railroad Ave., between Dutton St and Morgan St.: widen to accommodate a continuous left turn l | Pavement Improvement | 09/01/2009 |  | 01/01/2010 | 357118 | 1
445 | California | LOS ANGELES | LOS ANGELES, CA | 32 | 5112010 | This is a Pavement Reconstruction, No Added Capacity project by the City of Azusa. The project is described as: RECONSTRUCTION OF FOOTHILL BLVD. FROM TODD AVE. TO ORANGE AVE. (3,716 FEET.) THE COMBIN | Pavement Improvement | 09/23/2009 |  | 07/01/2009 | 1431000 | 0.7
446 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5113010 | This is a Pavement Restoration and Rehabilitation project by the City of Mill Valley. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/22/2009 |  | 08/01/2009 | 335000 | 0.36
447 | California | SONOMA | SANTA ROSA | 1,6 | 5114014 | This is a Pavement Restoration and Rehabilitation project by the City of Sonoma. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/28/2009 |  | 09/01/2009 | 500000 | 0.53
448 | California | KINGS |  | 20 | 5115019 | This is a Pavement Resurfacing project by the City of Lemoore. The project is described as: City of Lemoore, Hanford-Armona Road, From 19th Ave. to SR 41; Overlay Roadway. | Pavement Improvement | 10/19/2009 |  | 08/01/2009 | 435000 | 1
449 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7 | 5117008 | This is a Pavement Restoration and Rehabilitation project by the City of Hercules. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/29/2009 |  | 12/01/2009 | 671000 | 0.83
450 | California | LOS ANGELES | LOS ANGELES, CA | 32 | 5118014 | This is a Pavement Resurfacing project by the City of Covina. The project is described as: STREET OVERLAYS - CITYWIDE. | Pavement Improvement | 12/02/2009 |  | 12/01/2009 | 1136300 | 2.65
451 | California | VENTURA | OXNARD-VENTURA | 24 | 5121017 | This is a Pavement Resurfacing project by the City of Santa Paula. The project is described as: 8th Street from Harvard to Santa Paula Street. | Pavement Improvement | 10/14/2009 |  | 12/01/2009 | 254000 | 1
452 | California | SONOMA | SANTA ROSA | 6 | 5123014 | This is a Pavement Restoration and Rehabilitation project by the City of Sebastopol. The project is described as: Rehabilitate local street. | Pavement Improvement | 11/10/2009 |  | 10/01/2009 | 595023 | 0.83
453 | California | SANTA CLARA | SAN JOSE, CA | 14 | 5124027 | This is a Pavement Restoration and Rehabilitation project by the City of Mountain View. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/05/2009 |  | 10/01/2009 | 724815 | 0.86
454 | California | INYO |  | 25 | 5125022 | This is a Pavement Reconstruction, No Added Capacity project by the City of Bishop. The project is described as: Replace asphalt paving, cross gutters & ramps. Install new water and sewer mains.. | Pavement Improvement | 08/28/2009 |  | 11/01/2009 | 349998 | 0.2
455 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5126010 | This is a Facilities for Pedestrians and Bicycles project by the City of Pinole. The project is described as: Pedestrian Enhancements. | Pavement Improvement | 10/22/2009 |  | 10/01/2009 | 214000 | 1
456 | California | CONTRA COSTA | ANTIOCH-PITTSBURGH | 7,10 | 5127023 | This is a Pavement Restoration and Rehabilitation project by the City of Pittsburg. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/25/2009 |  | 08/01/2009 | 1103000 | 1.02
457 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5135036 | This is a Pavement Restoration and Rehabilitation project by the City of Concord. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/03/2009 |  | 12/01/2009 | 1270000 | 1.2
458 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5137037 | This is a Pavement Restoration and Rehabilitation project by the City of Richmond. The project is described as: Rehabilitate local street and add bicycle lane. | Pavement Improvement | 02/01/2010 |  | 06/01/2010 | 1578000 | 0.8
459 | California | BUTTE |  | 2 | 5142030 | This is a Pavement Resurfacing project by the City of Oroville. The project is described as: Roadway Rehabilitation / Overlays. | Pavement Improvement | 08/28/2009 |  | 10/01/2009 | 1095000 | 2
460 | California | LOS ANGELES | LOS ANGELES, CA | 28 | 5149005 | This is a Pavement Restoration and Rehabilitation project by the City of La Verne. The project is described as: COMPLETE REHABILITATION OF 1.3 MILE LENGTH OF GOLDEN HILLS ROAD FROM SAN DIMAS CANYON T | Pavement Improvement | 09/14/2009 |  | 06/01/2009 | 800000 | 1.3
461 | California | ORANGE | MISSION VIEJO | 48 | 5151024 | This is a Pavement Resurfacing project by the City of Newport Beach. The project is described as: Pavement rehab. from 44th St. to 22nd St.. | Pavement Improvement | 11/09/2009 |  | 01/01/2010 | 1083924 | 0.95
462 | California | SANTA CLARA | SAN JOSE, CA | 11,15,16 | 5152019 | This is a Pavement Restoration and Rehabilitation project by the City of Morgan Hill. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/09/2009 |  | 05/01/2009 | 556000 | 0.6
463 | California | SAN JOAQUIN | LODI | 11 | 5154036 | This is a Pavement Restoration and Rehabilitation project by the City of Lodi. The project is described as: Enhancement of existing roadway. | Pavement Improvement | 11/11/2009 |  | 02/01/2010 | 2295960 | 0.62
464 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5159014 | This is a Pavement Restoration and Rehabilitation project by the City of San Anselmo. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/20/2009 |  | 09/01/2009 | 267000 | 0.3
465 | California | SUTTER | YUBA CITY | 2 | 5163019 | This is a Facilities for Pedestrians and Bicycles project by the Yuba City. The project is described as: In Yuba City, from Plumas to Shasta, construct signal-phasing modifications, street reconstruc | Pavement Improvement | 08/10/2009 |  | 12/01/2009 | 1900000 | 1
466 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5164016 | This is a Pavement Resurfacing project by the City of Inglewood. The project is described as: MANCHESTER BOULEVARD CORRIDOR ROADWAY IMPROVEMENT PROJECT. TO PRESERVE AND REHABILITATE THE EXISTING ROA | Pavement Improvement | 11/02/2009 |  | 12/01/2010 | 3200000 | 2.45
467 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5166022 | This is a Pavement Restoration and Rehabilitation project by the City of Larkspur. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/08/2009 |  | 08/01/2009 | 236000 | 0.49
468 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5171016 | This is a Pavement Restoration and Rehabilitation project by the City of Burlingame. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/13/2009 |  | 08/01/2009 | 551000 | 1.2
469 | California | IMPERIAL |  | 51 | 5174007 | This is a Pavement Resurfacing project by the County of Imperial. The project is described as: Street Improvements of Rehabilitation and Reconstruction along West side of Holt Avenue between Ninth an | Pavement Improvement | 01/04/2010 |  | 11/01/2009 | 346000 | 0.11
470 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5177022 | This is a Pavement Restoration and Rehabilitation project by the City of South San Francisco. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/10/2009 |  | 09/01/2009 | 816451 | 0.85
471 | California | GLENN |  | 4 | 5185005 | This is a Pavement Resurfacing project by the City of Orland. The project is described as: Road maintenance. | Pavement Improvement | 10/05/2009 |  | 12/01/2009 | 661000 | 1.07
472 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5191004 | This is a Pavement Restoration and Rehabilitation project by the City of Hillsborough. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/29/2009 |  | 10/01/2009 | 392000 | 2.3
473 | California | SAN JOAQUIN | TRACY | 11 | 5192028 | This is a Pavement Reconstruction, No Added Capacity project by the City of Tracy. The project is described as: Reconstruct roadway between Carlton Avenue and 11th Street. | Pavement Improvement | 10/08/2009 |  | 06/01/2010 | 1614306 | 0.5
474 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5202014 | This is a Pavement Restoration and Rehabilitation project by the City of San Fernando. The project is described as: ECONOMIC STIMULUS PROJECT- NORTH BRAND BOULEVARD STREET IMPROVEMENT BETWEEN TRUMAN | Pavement Improvement | 10/19/2009 |  | 09/01/2009 | 745000 | 0.58
475 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5204011 | This is a Pavement Restoration and Rehabilitation project by the City of Glendora. The project is described as: GRAND AVENUE PAVING PROJECT FROM ARROW HIGHWAY TO FOOTHILL BOULEVARD. GRIND AND PAVE A | Pavement Improvement | 12/16/2009 |  | 09/01/2009 | 1537000 | 2
476 | California | FRESNO | FRESNO | 21 | 5208090 | This is a New Construction Roadway project by the City of Clovis. The project is described as: Temperance Ave.: Between Gould Canal and Gettysburg; widen from 2 LU to 4 LD.. | Pavement Widening | 10/21/2009 |  | 10/01/2009 | 400000 | 0.75
477 | California | LOS ANGELES | LOS ANGELES, CA | 36 | 5212003 | This is a Pavement Resurfacing project by the City of Manhattan Beach. The project is described as: AVIATION BLVD. RESURFACING (MARINE AVE. TO MANHATTAN BEACH BLVD.) --- COLD MILL AND ASPHALT OVERLAY | Pavement Improvement | 12/03/2009 |  | 12/01/2009 | 464000 | 0.5
478 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5213032 | This is a Pavement Restoration and Rehabilitation project by the City of Sunnyvale. The project is described as: Rehabilitate local street. | Bridge Improvement | 08/19/2009 |  | 11/01/2009 | 2745000 | 0.3
479 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5221009 | This is a Pavement Resurfacing project by the City of Beverly Hills. The project is described as: RESURFACING OF APPROXIMATELY 8.1 MILES OF PRINCIPAL ARTERIAL AND MAJOR COLLECTOR STREETS WITHIN THE C | Pavement Improvement | 10/26/2009 |  | 12/01/2009 | 1059000 | 1.1
480 | California | VENTURA | OXNARD-VENTURA | 24 | 5222018 | This is a Pavement Resurfacing project by the City of Fillmore. The project is described as: Edge Grinding & Rubberized Asphalt. | Pavement Improvement | 01/10/2010 |  | 12/01/2009 | 400000 | 0.82
481 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5225022 | This is a Pavement Restoration and Rehabilitation project by the City of Walnut Creek. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/09/2009 |  | 10/01/2009 | 1446000 | 0.83
482 | California | KERN | BAKERSFIELD | 20 | 5227036 | This is a Pavement Resurfacing project by the City of Delano. The project is described as: 11th Ave from Albany St to High St, 9th Ave from High St to Randolph St, Norwalk St from Co. Line Rd to Ceci | Pavement Improvement | 01/07/2010 |  | 02/01/2010 | 934745 | 3.42
483 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5232009 | This is a Pavement Restoration and Rehabilitation project by the City of Corte Madera. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/21/2009 |  | 09/01/2009 | 174000 | 0.77
484 | California | YOLO | SACRAMENTO | 2 | 5238048 | This is a Pavement Restoration and Rehabilitation project by the City of Davis. The project is described as: In Yolo County, rehabilitate various roadways.. | Pavement Improvement | 08/17/2009 |  | 11/01/2009 | 732903 | 1
485 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5239014 | This is a Pavement Restoration and Rehabilitation project by the City of El Cerrito. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/21/2009 |  | 12/01/2009 | 678000 | 1.5
486 | California | SAN JOAQUIN | STOCKTON | 11 | 5242021 | This is a Pavement Restoration and Rehabilitation project by the City of Manteca. The project is described as: Rehabilitation of 9 streets in the City of Manteca. | Pavement Improvement | 10/16/2009 |  | 09/01/2009 | 1356058 | 4
487 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5247015 | This is a Facilities for Pedestrians and Bicycles project by the City of Montebello. The project is described as: NEIGHBORHOOD CITYWIDE SIDEWALK REHABILITATION: REMOVAL AND REPLACEMENT OF CONCRETE SI | Transportation Enhancements | 12/01/2009 |  | 12/01/2009 | 1575904 | 0.7
488 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5248006 | This is a Safety project by the City of Soledad. The project is described as: Install new traffic signal at Oak & Front Streets. | Safety/Traffic Management | 06/22/2009 |  | 12/01/2009 | 544891 | 0.12
489 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5253014 | This is a Facilities for Pedestrians and Bicycles project by the City of Hawthorne. The project is described as: THE PURPOSE OF THE ALTERATIONS IS TO ENHANCE PUBLIC SAFETY ON A RAILROAD CROSSING ON B | Pavement Improvement | 11/02/2009 |  | 12/01/2009 | 35000 | 0.1
490 | California | MERCED |  | 18 | 5254012 | This is a Pavement Resurfacing project by the City of Atwater. The project is described as: Shaffer Road - AC Overlay and Partial reconstruction. | Pavement Improvement | 12/14/2009 |  | 10/01/2009 | 568723 | 0.7
491 | California | MERCED |  | 18 | 5256009 | This is a Pavement Resurfacing project by the City of Livingston. The project is described as: Project involves road grinding, replacement of asphalt concrete, crack sealing of road, slurry seal, rep | Pavement Improvement | 10/02/2009 |  | 02/01/2010 | 550803 | 2.62
492 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5261006 | This is a Pavement Restoration and Rehabilitation project by the City of Atherton. The project is described as: Rehabilitate local street. | Pavement Improvement | 07/27/2009 |  | 09/01/2009 | 468000 | 0.5
493 | California | LOS ANGELES |  | 37 | 5262004 | This is a Pavement Resurfacing project by the City of Signal Hill. The project is described as: GRIND AND OVERLAY APPROXIMATELY 12 LANE MILES OF DETERIORATING PAVEMENT ON A MAJOR ARTERIAL USED BY COM | Pavement Improvement | 09/14/2009 |  | 07/01/2010 | 500000 | 1.5
494 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5264003 | This is a Pavement Restoration and Rehabilitation project by the City of Colma. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/11/2009 |  | 09/01/2009 | 131000 | 0.5
495 | California | LOS ANGELES |  | 34 | 5265011 | This is a Pavement Restoration and Rehabilitation project by the City of Maywood. The project is described as: ATLANTIC BLVD. SOUTH: PROJECT INCLUDES REMOVAL AND REPLACEMENT OF AC PAVEMENT, RECONSTRU | Pavement Improvement | 09/21/2009 |  | 12/01/2009 | 638385 | 0.3
496 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5267013 | This is a Pavement Restoration and Rehabilitation project by the City of San Carlos. The project is described as: Rehabilitate local street. | Transportation Enhancements | 09/28/2009 |  | 12/01/2009 | 559000 | 0.75
497 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5268015 | This is a Pavement Restoration and Rehabilitation project by the City of Belmont. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/31/2009 |  | 09/01/2009 | 464000 | 0.8
498 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5273020 | This is a Pavement Restoration and Rehabilitation project by the City of Menlo Park. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/03/2009 |  | 08/01/2009 | 635000 | 1.3
499 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5276022 | This is a Pavement Restoration and Rehabilitation project by the City of Gardena. The project is described as: WESTERN AVENUE STREET IMPROVEMENT - REDONDO BEACH BLVD. TO EL SEGUNDO BLVD.. | Pavement Improvement | 12/14/2009 |  | 12/01/2009 | 1000000 | 2
500 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5276023 | This is a Pavement Restoration and Rehabilitation project by the City of Gardena. The project is described as: 135TH STREET IMPROVEMENT - CRENSHAW BLVD. TO VERMONT AVE.. | Pavement Improvement | 12/14/2009 |  | 12/01/2009 | 811000 | 2
501 | California | RIVERSIDE | INDIA-COACHELLA | 45 | 5282027 | This is a Landscaping and Other Scenic Beautification project by the City of Palm Springs. The project is described as: Install landscaping, gateway park, pedestrian walkway. | Transportation Enhancements | 11/09/2009 |  | 03/01/2010 | 1850000 | 0.25
502 | California | LOS ANGELES | LOS ANGELES, CA | 46 | 5283006 | This is a Pavement Restoration and Rehabilitation project by the City of Palos Verdes Estates. The project is described as: PALOS VERDES DRIVE WEST AT BLUFF COVE ROADWAY STABILIZATION PROJECT FOR ECO | Pavement Improvement | 11/09/2009 |  | 09/01/2009 | 500000 | 0.05
503 | California | SAN JOAQUIN |  | 11 | 5286012 | This is a Traffic Management Engineering project by the City of Ripon. The project is described as: Enhancement of existing roundabout. | Pavement Improvement | 11/24/2009 |  | 03/01/2010 | 202131 | 1
504 | California | KERN |  | 20 | 5287026 | This is a Pavement Reconstruction, No Added Capacity project by the City of Wasco. The project is described as: Poso Dr: State Route 43 to Griffith Ave; Reconstruction. | Pavement Improvement | 10/14/2009 |  | 04/01/2010 | 937195 | 0.4
505 | California | SACRAMENTO | SACRAMENTO | 3 | 5288028 | This is a Pavement Restoration and Rehabilitation project by the City of Folsom. The project is described as: Oak Avenue Parkway, from Blue Ravine Road to East Bidwell Street: Rehabilitate roadway.. | Pavement Improvement | 10/05/2009 |  | 12/01/2009 | 1380477 | 1
506 | California | SACRAMENTO |  | 3 | 5293012 | This is a Pavement Restoration and Rehabilitation project by the City of Galt. The project is described as: In Galt, Rehabilitate roadways.. | Pavement Improvement | 08/11/2009 |  | 11/01/2009 | 416140 | 1
507 | California | MONTEREY |  | 17 | 5296003 | This is a Pavement Resurfacing project by the City of Gonzales. The project is described as: Reconstruct from southerly city limits to 4th Street including sidewalk and bike lanes. | Pavement Improvement | 08/12/2009 |  | 12/01/2009 | 171893 | 1
508 | California | SUTTER |  | 2 | 5297006 | This is a Pavement Restoration and Rehabilitation project by the City of Live Oak. The project is described as: Rehabilitate Apricot St: N St-Broadway. | Pavement Improvement | 10/12/2009 |  | 12/01/2009 | 205639 | 1
509 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5299011 | This is a Pavement Restoration and Rehabilitation project by the City of Millbrae. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/31/2009 |  | 08/01/2009 | 382000 | 0.5
510 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10,11 | 5300008 | This is a Pavement Restoration and Rehabilitation project by the City of Brentwood. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/31/2009 |  | 12/01/2009 | 1074000 | 1
511 | California | FRESNO |  | 21 | 5301007 | This is a Pavement Reconstruction, No Added Capacity project by the City of Orange Cove. The project is described as: Center Street: Between Adams and Park; reconstruction.. | Pavement Improvement | 09/21/2009 |  | 11/01/2009 | 200866 | 0.5
512 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7 | 5303013 | This is a Pavement Restoration and Rehabilitation project by the City of San Pablo. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/28/2009 |  | 12/01/2009 | 694000 | 0.85
513 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5304007 | This is a Pavement Restoration and Rehabilitation project by the City of Capitola. The project is described as: Road repairs : Capitola Road to Clares. | Pavement Improvement | 08/07/2009 |  | 10/01/2010 | 230000 | 0.3
514 | California | SANTA CLARA | SAN JOSE, CA | 14,15,16 | 5306018 | This is a Pavement Restoration and Rehabilitation project by the City of Campbell. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/21/2009 |  | 12/01/2009 | 594000 | 0.42
515 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5309013 | This is a Pavement Restoration and Rehabilitation project by the City of Los Altos. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/12/2009 |  | 12/01/2009 | 253000 | 2
516 | California | ORANGE | LOS ANGELES, CA | 46 | 5312071 | This is a Landscaping and Other Scenic Beautification project by the City of Costa Mesa. The project is described as: Landscape and beautification at Fairview Road/I405 Interchange. | Transportation Enhancements | 11/02/2009 |  | 12/01/2010 | 500000 | 2.3
517 | California | SANTA CLARA | SAN JOSE, CA | 11,15,16 | 5314007 | This is a Pavement Restoration and Rehabilitation project by the City of Milpitas. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/01/2009 |  | 10/01/2009 | 1136000 | 0.6
518 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5315006 | This is a Pavement Resurfacing project by the City of Lakewood. The project is described as: BLOOMFIELD AVENUE IMPROVEMENTS FROM SOUTH CITY LIMIT TO DEL AMO BOULEVARD - RESURFACE PAVEMENT, CONCRETE R | Pavement Improvement | 09/08/2009 |  | 09/01/2009 | 610000 | 0.89
519 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5316006 | This is a Pavement Resurfacing project by the City of Seaside. The project is described as: Reconstruct between south city limits and Broadway Ave. | Pavement Improvement | 09/10/2009 |  | 12/01/2009 | 669839 | 1
520 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5318025 | This is a Pavement Restoration and Rehabilitation project by the City of Cupertino. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/05/2009 |  | 12/01/2009 | 707000 | 0.81
521 | California | SHASTA |  | 2 | 5321015 | This is a Pavement Resurfacing project by the City of Anderson. The project is described as: 2.95 miles of Preventative Maintenance on major local streets. | Pavement Improvement | 09/03/2009 |  | 09/01/2009 | 421000 | 2.94
522 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 11,13 | 5322035 | This is a Pavement Restoration and Rehabilitation project by the City of Fremont. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/24/2009 |  | 12/01/2010 | 5907000 | 4.28
523 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5324005 | This is a Pavement Restoration and Rehabilitation project by the City of Los Altos Hills. The project is described as: Rehabilitate local street. | Pavement Improvement | 07/16/2009 |  | 08/01/2009 | 316000 | 1.8
524 | California | LOS ANGELES |  | 38 | 5331011 | This is a Pavement Reconstruction, No Added Capacity project by the City of La Puente. The project is described as: HACIENDA BLVD. RECONSTRUCTION: RECONSTRUCTION AND/OR OVERLAY OF ROADWAY PAVEMENT AN | Pavement Improvement | 10/19/2009 |  | 12/01/2009 | 1000000 | 0.9
525 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5332014 | This is a Pavement Restoration and Rehabilitation project by the City of Saratoga. The project is described as: Rehabilitate local street. | Pavement Improvement | 11/09/2009 |  | 09/01/2009 | 714000 | 1.3
526 | California | ORANGE | LOS ANGELES, CA | 40,46 | 5338041 | This is a Pavement Resurfacing project by the City of Westminster. The project is described as: Brookhurst St Improvements from Hazard Avenue to Bolsa Avenue. | Pavement Improvement | 11/02/2009 |  | 12/01/2009 | 813214 | 0.5
527 | California | SANTA CLARA | SAN JOSE, CA | 14 | 5339001 | This is a Pavement Restoration and Rehabilitation project by the City of Monte Sereno. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/10/2009 |  | 09/01/2009 | 94000 | 0.5
528 | California | KERN | BAKERSFIELD | 20 | 5343002 | This is a Pavement Reconstruction, No Added Capacity project by the City of McFarland. The project is described as: W. Perkins Ave: 50 ft east of 3rd St to 320 ft east of 3rd St and Intersection of W | Pavement Improvement | 11/13/2009 |  | 10/01/2009 | 507524 | 0.05
529 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5347032 | This is a Pavement Restoration and Rehabilitation project by the City of Norwalk. The project is described as: REHABILITATE FRONT STREET FROM SAN ANTONIO DRIVE TO ROSECRANS AVENUE.. | Pavement Improvement | 01/04/2010 |  | 12/01/2009 | 398665 | 0.77
530 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5350016 | This is a Pavement Restoration and Rehabilitation project by the City of Pacifica. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/21/2009 |  | 08/01/2009 | 677000 | 2
531 | California | LOS ANGELES | LOS ANGELES, CA | 42 | 5353005 | This is a Pavement Restoration and Rehabilitation project by the City of Walnut. The project is described as: Nogales Street from southerly city limit to Amar. Rehabilitate pavement section and repl | Pavement Improvement | 12/14/2009 |  | 07/01/2010 | 951000 | 0.5
532 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5355021 | This is a Facilities for Pedestrians and Bicycles project by the City of Artesia. The project is described as: SOUTH STREET PEDESTRIAN BIKEWAY AND TRANSIT IMPROVEMENTS. PROJECT PROPOSES TO INSTALL L | Transportation Enhancements | 11/09/2009 |  | 09/01/2009 | 402866 | 0.5
533 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5357005 | This is a Pavement Restoration and Rehabilitation project by the City of Half Moon Bay. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/07/2009 |  | 09/01/2009 | 210000 | 0.5
534 | California | SAN LUIS OBISPO | SAN LUIS OBISPO | 23 | 5359015 | This is a Landscaping and Other Scenic Beautification project by the City of Grover Beach. The project is described as: Fourth Street to the Railroad Tracks (Improve and upgrade landscape, with inter | Transportation Enhancements | 12/22/2009 |  | 10/01/2009 | 856000 | 0.17
535 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5360008 | This is a Pavement Restoration and Rehabilitation project by the City of Lawndale. The project is described as: THE PROJECT WILL MAKE VARIOUS STREET IMPROVEMENTS TO ROSECRANS AVENUE FROM INGLEWOOD AV | Pavement Improvement | 12/01/2009 |  | 12/01/2009 | 987000 | 1
536 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5361022 | This is a Pavement Restoration and Rehabilitation project by the City of Novato. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/19/2009 |  | 10/01/2009 | 1062000 | 6
537 | California | LOS ANGELES |  | 34 | 5362014 | This is a Pavement Reconstruction, No Added Capacity project by the City of Commerce. The project is described as: THIS PROJECT IS AT THE INTERSECTION OF GARFIELD AVENUE AND SLAUSON AVENUE AND IMPROV | Pavement Improvement | 09/28/2009 |  | 12/01/2014 | 500000 | 0.1
538 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5364005 | This is a Pavement Restoration and Rehabilitation project by the City of La Mirada. The project is described as: Stage Road from Alondra Boulevard to east City Limit. Selective Reconstruction of Cur | Pavement Improvement | 02/01/2010 |  | 10/01/2009 | 843751 | 0.8
539 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5365003 | This is a Safety project by the Temple City. The project is described as: NEW TRAFFIC SIGNAL ON TEMPLE CITY BLVD. AT ELLIS LANE: INSTALLATION OF A NEW SIGNAL. COMPONENTS INCLUDE POLES, SIGNAL HEADS, | Safety/Traffic Management | 01/22/2010 |  | 03/01/2010 | 176000 | 1
540 | California | LOS ANGELES |  | 26 | 5367006 | This is a Pavement Restoration and Rehabilitation project by the City of San Dimas. The project is described as: SAN DIMAS AVENUE RECONSTRUCTION, REHABILITATION AND LANDSCAPE MEDIAN. | Pavement Improvement | 10/26/2009 |  | 09/01/2009 | 1085000 | 0.7
541 | California | LOS ANGELES | LOS ANGELES, CA | 34 | 5373013 | This is a Pavement Resurfacing project by the City of Bell Gardens. The project is described as: CITYWIDE STREET OVERLAY: RECYCLED ASPHALT CONCRETE OVERLAY OF STREETS.. | Pavement Improvement | 09/16/2009 |  | 10/01/2009 | 745800 | 0.7
542 | California | CONTRA COSTA | CONCORD | 7,10 | 5375021 | This is a Pavement Restoration and Rehabilitation project by the City of Pleasant Hill. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/19/2009 |  | 12/01/2009 | 842000 | 0.71
543 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5376008 | This is a Pavement Restoration and Rehabilitation project by the City of Brisbane. The project is described as: Rehabilitate local street. | Pavement Improvement | 07/13/2009 |  | 10/01/2009 | 131000 | 0.1
544 | California | LOS ANGELES | LOS ANGELES, CA | 25 | 5378019 | This is a Pavement Restoration and Rehabilitation project by the City of Palmdale. The project is described as: 2009 ARTERIAL REHABILITATION AND RECONSTRUCTION PROGRAM. | Pavement Improvement | 09/16/2009 |  | 10/01/2009 | 4324000 | 24.58
545 | California | SONOMA | SANTA ROSA | 6 | 5379017 | This is a Pavement Restoration and Rehabilitation project by the City of Rohnert Park. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/13/2009 |  | 11/01/2009 | 869000 | 3.21
546 | California | SONOMA | SANTA ROSA | 6 | 5383007 | This is a Pavement Restoration and Rehabilitation project by the City of Cotati. The project is described as: Rehabilitate local street. | Pavement Improvement | 11/09/2009 |  | 10/01/2009 | 500000 | 0.34
547 | California | CONTRA COSTA | CONCORD | 7,10 | 5386009 | This is a Pavement Restoration and Rehabilitation project by the City of Clayton. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/18/2009 |  | 09/01/2009 | 554000 | 1.1
548 | California | LOS ANGELES |  | 39 | 5387009 | This is a Pavement Resurfacing project by the City of Hawaiian Gardens. The project is described as: NORWALK BOULEVARD FROM CENTRALIA STREET TO SOUTH CITY LIMIT - RESURFACE PAVEMENT, NEW SIDEWALK, CO | Pavement Improvement | 10/05/2009 |  | 09/01/2009 | 428060 | 0.56
549 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5388008 | This is a Pavement Restoration and Rehabilitation project by the City of Tiburon. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/21/2009 |  | 07/01/2009 | 204000 | 1
550 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5390004 | This is a Pavement Restoration and Rehabilitation project by the City of Portola Valley. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/18/2009 |  | 11/01/2009 | 196000 | 0.6
551 | California | VENTURA | OXNARD-VENTURA | 24 | 5393020 | This is a Pavement Restoration and Rehabilitation project by the City of Camarillo. The project is described as: Annual Pavement Rehab at Various Location. | Pavement Improvement | 11/23/2009 |  | 12/01/2009 | 1099966 | 2.45
552 | California | LOS ANGELES | LOS ANGELES, CA | 37 | 5403014 | This is a Landscaping and Other Scenic Beautification project by the City of Carson. The project is described as: BROADWAY IMPROVEMENTS FROM 168TH ST. TO NORTH CITY LIMIT (ALONDRA BLVD). CONSTRUCT RA | Pavement Improvement | 11/02/2009 |  | 12/01/2009 | 2000000 | 0.4
553 | California | CONTRA COSTA | CONCORD | 7,10 | 5404020 | This is a Pavement Restoration and Rehabilitation project by the City of Lafayette. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/04/2009 |  | 10/01/2009 | 744000 | 2.25
554 | California | VENTURA | OXNARD-VENTURA | 24 | 5405050 | This is a Pavement Reconstruction, No Added Capacity project by the City of Simi Valley. The project is described as: Reconstruction Moorpark Road from Santa Rosa Rd to Calle Contento. | Pavement Improvement | 08/03/2009 |  | 10/01/2009 | 1080532 | 2.35
555 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5409015 | This is a Pavement Restoration and Rehabilitation project by the Foster City. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/14/2009 |  | 10/01/2009 | 440000 | 0.5
556 | California | LOS ANGELES |  | 36 | 5413010 | This is a Pavement Restoration and Rehabilitation project by the City of Rancho Palos Verdes. The project is described as: STREET IMPROVEMENTS ON HAWTHORNE BLVD FROM INDIAN PEAK ROAD TO VERDE RIDGE R | Pavement Improvement | 10/19/2009 |  | 09/01/2009 | 1262000 | 4.47
557 | California | CONTRA COSTA | CONCORD | 10 | 5415010 | This is a Pavement Restoration and Rehabilitation project by the City of Moraga. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/15/2009 |  | 11/01/2009 | 609000 | 1.1
558 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5417015 | This is a Pavement Resurfacing project by the City of La Canada Flintridge. The project is described as: RESURFACING OF VARIOUS CITY STREETS.. | Pavement Improvement | 10/15/2009 |  | 09/01/2009 | 964700 | 2.16
559 | California | LOS ANGELES | LOS ANGELES, CA | 22,25 | 5419020 | This is a Pavement Reconstruction, No Added Capacity project by the City of Lancaster. The project is described as: RECONSTRUCTION OF THE NORTH HALF OF AVENUE K FROM 50TH TO 52ND STREETS WEST AND THE | Pavement Improvement | 10/19/2009 |  | 01/01/2010 | 325033 | 0.5
560 | California | LOS ANGELES | LOS ANGELES, CA | 22,25 | 5419021 | This is a Pavement Resurfacing project by the City of Lancaster. The project is described as: 2008 STREET REHABILITATION - PHASE II SHALL PERFORM FULL DEPTH RECLAMATION, COLD IN PLACE RECYCLING, CENT | Pavement Improvement | 09/21/2009 |  | 01/01/2010 | 3172000 | 3.8
561 | California | LOS ANGELES | LOS ANGELES, CA | 42 | 5422002 | This is a Pavement Restoration and Rehabilitation project by the City of La Habra Heights. The project is described as: REHABILITATION OF ROADWAY, RESTORATION OF STREET SHOULDER, HAZARD ELIMINATION A | Pavement Improvement | 01/04/2010 |  | 12/01/2009 | 500000 | 4.16
562 | California | BUTTE |  | 2 | 5425020 | This is a Pavement Resurfacing project by the City of Paradise. The project is described as: Roadway Rehabilitation / Overlays. | Pavement Improvement | 09/25/2009 |  | 12/01/2010 | 1498962 | 5.1
563 | California | LAKE |  | 1 | 5427019 | This is a Pavement Resurfacing project by the City of Clearlake. The project is described as: Lakeshore Drive to Old Highway 53/Between Rumsey Road and Woodland Drive. | Pavement Improvement | 09/10/2009 |  | 09/01/2009 | 813600 | 1.37
564 | California | CONTRA COSTA | CONCORD | 10,11 | 5434018 | This is a Pavement Restoration and Rehabilitation project by the City of Danville. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/08/2009 |  | 09/01/2010 | 971000 | 2.1
565 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5435016 | This is a Bridge Rehabilitation, Added Capacity project by the City of Agoura Hills. The project is described as: WIDENING OF THE REYES ADOBE ROAD OVERCROSSING OF THE 101 FREEWAY FROM 3 LANES TO 6 LA | Pavement Widening | 09/11/2009 |  | 08/01/2010 | 690000 | 0.2
566 | California | CONTRA COSTA | CONCORD | 10,11 | 5437022 | This is a Pavement Restoration and Rehabilitation project by the City of San Ramon. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/01/2009 |  | 06/01/2010 | 1122000 | 0.88
567 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5438008 | This is a Pavement Restoration and Rehabilitation project by the City of East Palo Alto. The project is described as: Rehabilitate local street. | Pavement Improvement | 11/06/2009 |  | 06/01/2010 | 421000 | 1.9
568 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5440008 | This is a Pavement Restoration and Rehabilitation project by the City of West Hollywood. The project is described as: SUNSET BLVD FROM WEST CITY BOUNDARY (WEST OF CORY AVE) TO EAST CITY BOUNDARY (EAS | Pavement Improvement | 01/11/2010 |  | 12/01/2010 | 1105000 | 1.7
569 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5444013 | This is a Pavement Restoration and Rehabilitation project by the City of Orinda. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/17/2009 |  | 12/01/2009 | 694000 | 0.9
570 | California | LOS ANGELES | LOS ANGELES, CA | 25 | 5450047 | This is a Safety project by the City of Santa Clarita. The project is described as: TRAFFIC CIRCULATION AND SAFETY IMPROVEMENTS AT NEWHALL AVENUE AND SIERRA HIGHWAY. | Pavement Improvement | 10/12/2009 |  | 09/01/2009 | 282101 | 0.2
571 | California | ORANGE | MISSION VIEJO | 42 | 5451026 | This is a Pavement Resurfacing project by the City of Mission Viejo. The project is described as: Overlay of Portions of Alicia, Trabuco and Olympiad. | Pavement Improvement | 01/04/2010 |  | 12/01/2009 | 898537 | 2.2
572 | California | LOS ANGELES | LOS ANGELES, CA | 42 | 5455013 | This is a Pavement Resurfacing project by the City of Diamond Bar. The project is described as: PREVENTIVE STREET MAINTENANCE PROGRAM - APPROXIMATELY 10 MILES OF ARTERIAL ROADWAY SLURRY, CHIP SEAL, | Pavement Improvement | 09/23/2009 |  | 12/01/2009 | 1763586 | 10
573 | California | RIVERSIDE | STATEWIDE | 45 | 5464029 | This is a Pavement Reconstruction, Added Capacity project by the City of Murrieta. The project is described as: Replace Diamond IC with partial Cloverleaf IC. | Bridge Improvement | 12/21/2009 |  | 04/01/2011 | 9999452 | 1.1
574 | California | ORANGE | MISSION VIEJO | 48 | 5468013 | This is a Pavement Restoration and Rehabilitation project by the City of Laguna Hills. The project is described as: Pavement Rehabilitation. | Pavement Improvement | 12/07/2009 |  | 06/01/2010 | 500000 | 0.72
575 | California | ORANGE | MISSION VIEJO | 48 | 5469013 | This is a Pavement Resurfacing project by the City of Lake Forest. The project is described as: Trabuco Road Rehabilitation - Lake Forest Dr to South City Limit. | Pavement Improvement | 11/30/2009 |  | 12/01/2010 | 749310 | 1.1
576 | California | NAPA | STATEWIDE | 1,7 | 5470007 | This is a Pavement Restoration and Rehabilitation project by the City of American Canyon. The project is described as: Rehabilitate local street. | Pavement Improvement | 11/02/2009 |  | 09/01/2009 | 320000 | 0.5
577 | California | SONOMA | SANTA ROSA | 1,6 | 5472012 | This is a Pavement Restoration and Rehabilitation project by the City of Windsor. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/25/2009 |  | 10/01/2009 | 596432 | 0.75
578 | California | SHASTA |  | 2 | 5474013 | This is a Pavement Resurfacing project by the City of Shasta Lake. The project is described as: 1.51miles of Preventative Maintenance on major local streets. | Pavement Improvement | 10/07/2009 |  | 09/01/2009 | 409000 | 1.51
579 | California | SACRAMENTO | SACRAMENTO | 3 | 5475022 | This is a Pavement Resurfacing project by the City of Citrus Heights. The project is described as: Fair Oaks Blvd., between Oak Avenue and Old Auburn Road: Minor reconstruction, overlay and re-stripe | Pavement Improvement | 09/08/2009 |  | 11/01/2009 | 1404058 | 1
580 | California | ORANGE | MISSION VIEJO | 48 | 5476007 | This is a Pavement Reconstruction, No Added Capacity project by the City of Laguna Woods. The project is described as: The project involves reconstruction of failed pavement areas, cold milling AC pa | Pavement Improvement | 10/12/2009 |  | 06/01/2010 | 500000 | 1.3
581 | California | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10,11 | 5477003 | This is a Pavement Restoration and Rehabilitation project by the City of Oakley. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/28/2009 |  | 09/01/2009 | 402000 | 1.3
582 | California | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10,11 | 5477004 | This is a Pavement Restoration and Rehabilitation project by the City of Oakley. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/28/2009 |  | 09/01/2009 | 403000 | 0.98
583 | California | SACRAMENTO | SACRAMENTO | 3 | 5479019 | This is a Traffic Management Engineering project by the City of Elk Grove. The project is described as: Install ITS components throughout Elk Grove. | Safety/Traffic Management | 10/26/2009 |  | 12/01/2009 | 1000000 | 1
584 | California | SANTA BARBARA | SANTA BARBARA | 23 | 5481007 | This is a Traffic Management Engineering project by the City of Goleta. The project is described as: Asphalt overlay (grind and replace) on various Federal Aid streets within the City of Goleta . | Pavement Improvement | 11/19/2009 |  | 06/01/2010 | 1270736 | 1.7
585 | California | SACRAMENTO | SACRAMENTO | 3 | 5482007 | This is a New Construction Roadway project by the City of Rancho Cordova. The project is described as: International Dr extension and bike/pedestrian bridge. | New Construction | 10/20/2009 |  | 12/01/2011 | 1050000 | 1
586 | California | DEL NORTE |  | 1 | 5901034 | This is a Pavement Restoration and Rehabilitation project by the County of Del Norte. The project is described as: Rehabilitate Oceanview Dr.: Mouth of Smith River Rd. to 1100 ft. S. of Spyglass. | Pavement Improvement | 08/19/2009 |  | 09/01/2009 | 245000 | 1.4
587 | California | DEL NORTE |  | 1 | 5901036 | This is a Pavement Restoration and Rehabilitation project by the County of Del Norte. The project is described as: Rehabilitation of Pebble Beach Dr. from Hemlock Ave. to Washington Blvd.. | Pavement Improvement | 08/19/2009 |  | 09/01/2009 | 200000 | 0.86
588 | California | SISKIYOU |  | 2 | 5902060 | This is a Pavement Resurfacing project by the County of Siskiyou. The project is described as: Near Hornbrook Rehab Copco Rd. | Pavement Improvement | 08/18/2009 |  | 11/01/2009 | 1002340 | 3.2
589 | California | HUMBOLDT |  | 1 | 5904097 | This is a Pavement Resurfacing project by the County of Humboldt. The project is described as: Rehabilitation and paving. | Pavement Improvement | 10/23/2009 |  | 10/01/2009 | 630600 | 1.02
590 | California | HUMBOLDT |  | 1 | 5904098 | This is a Pavement Resurfacing project by the County of Humboldt. The project is described as: Rehabilitation and paving. | Pavement Improvement | 11/06/2009 |  | 10/01/2009 | 630000 | 0.76
591 | California | SHASTA |  | 2 | 5906096 | This is a Pavement Resurfacing project by the County of Shasta. The project is described as: 37.7 miles of Preventative Maintenance on major local streets. | Pavement Improvement | 07/31/2009 |  | 09/01/2009 | 2819000 | 42.15
592 | California | SHASTA | REDDING | 2 | 5906097 | This is a Facilities for Pedestrians and Bicycles project by the County of Shasta. The project is described as: Construct East Redding Bike Lanes Phase 1. | Transportation Enhancements | 01/14/2010 |  | 12/01/2009 | 680217 | 2.19
593 | California | LASSEN |  | 4 | 5907055 | This is a Pavement Resurfacing project by the County of Lassen. The project is described as: Asphalt Concrete Overlay and shoulder backing. | Pavement Improvement | 09/15/2009 |  | 11/01/2009 | 777240 | 3.5
594 | California | TEHAMA |  | 2 | 5908083 | This is a Pavement Resurfacing project by the County of Tehama. The project is described as: Overlay of San Benito Avenue. | Pavement Improvement | 10/12/2009 |  | 09/01/2009 | 1170000 | 4.1
595 | California | BUTTE |  | 2 | 5912082 | This is a Pavement Resurfacing project by the County of Butte. The project is described as: Roadway Overlay. | Pavement Improvement | 10/19/2009 |  | 12/01/2009 | 660000 | 3.3
596 | California | SIERRA |  | 4 | 5913045 | This is a Scenic or Historic Highway Programs project by the County of Sierra. The project is described as: Multimodal travel information facility- visitor center Highway 49. | Transportation Enhancements | 09/28/2009 |  | 10/01/2009 | 93000 | 0
597 | California | YUBA |  | 2 | 5916079 | This is a Pavement Restoration and Rehabilitation project by the County of Yuba. The project is described as: La Porte Road from Challenge Cutoff Road to west Butte County Line and from east Butte Co | Pavement Improvement | 07/01/2009 |  | 10/01/2009 | 995038 | 1
598 | California | NEVADA |  | 4 | 5917059 | This is a Pavement Restoration and Rehabilitation project by the County of Nevada. The project is described as: Hirschdale Rd. from I-80 Exit to bridge over Truckee River & Glenshire Dr. from Hirschd | Pavement Improvement | 09/21/2009 |  | 10/01/2009 | 250000 | 1.5
599 | California | SUTTER |  | 2 | 5918072 | This is a Pavement Restoration and Rehabilitation project by the County of Sutter. The project is described as: In Sutter County, rehabilitate various roadways.. | Pavement Improvement | 10/13/2009 |  | 08/01/2009 | 651463 | 1
600 | California | NAPA |  | 1 | 5921045 | This is a Pavement Restoration and Rehabilitation project by the County of Napa. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/19/2009 |  | 09/01/2009 | 775000 | 3.8
601 | California | YOLO | SACRAMENTO | 1,2 | 5922084 | This is a Facilities for Pedestrians and Bicycles project by the County of Yolo. The project is described as: Bikeways and rehabilitation: CR 99, 29, 99D. | Transportation Enhancements | 08/06/2009 |  | 12/01/2011 | 368568 | 1
602 | California | SOLANO |  | 7,10 | 5923088 | This is a Pavement Restoration and Rehabilitation project by the County of Solano. The project is described as: Rehabilitate local street. | Pavement Improvement | 06/25/2009 |  | 09/01/2009 | 2000000 | 10.4
603 | California | SACRAMENTO | SACRAMENTO | 3 | 5924159 | This is a Pavement Restoration and Rehabilitation project by the County of Sacramento. The project is described as: In Sacramento County, rehabilitate various roadways. . | Pavement Improvement | 08/21/2009 |  | 11/01/2009 | 10565338 | 1
604 | California | EL DORADO |  | 4 | 5925069 | This is a Pavement Resurfacing project by the County of El Dorado. The project is described as: Forni Rd from Ray Lawyer Dr to Placerville Dr: rehabilitate roadways. | Pavement Improvement | 08/24/2009 |  | 11/01/2009 | 648187 | 0.7
605 | California | EL DORADO |  | 4 | 5925073 | This is a Pavement Resurfacing project by the County of El Dorado. The project is described as: Malcolm Dixon Rd from Salmon Falls Rd to Green Valley Rd: rehabilitate roadways. | Pavement Improvement | 10/06/2009 |  | 11/01/2009 | 439255 | 2.04
606 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5927068 | This is a Pavement Restoration and Rehabilitation project by the County of Marin. The project is described as: Rehabilitate local street. | Pavement Improvement | 10/05/2009 |  | 09/01/2009 | 2097410 | 3.99
607 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5928091 | This is a Pavement Restoration and Rehabilitation project by the County of Contra Costa. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/17/2009 |  | 11/01/2009 | 2762000 | 5.1
608 | California | SAN JOAQUIN |  | 11 | 5929197 | This is a Pavement Resurfacing project by the County of San Joaquin. The project is described as: Resurface roadway between Jack Tone Road and State Route 120. | Pavement Improvement | 10/02/2009 |  | 12/01/2009 | 892700 | 3.4
609 | California | SAN JOAQUIN | STATEWIDE | 11,18 | 5929200 | This is a Pavement Resurfacing project by the County of San Joaquin. The project is described as: Rubberized chip seal of 10 roadways in San Joaquin County. | Pavement Improvement | 10/05/2009 |  | 04/01/2010 | 4168169 | 30
610 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,13 | 5933098 | This is a Pavement Restoration and Rehabilitation project by the County of Alameda. The project is described as: Rehabilitate local street. | Pavement Improvement | 12/11/2009 |  | 12/01/2009 | 2200000 | 1.65
611 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8,12 | 5934147 | This is a Pavement Restoration and Rehabilitation project by the City of San Francisco. The project is described as: Rehabilitate local street. | Pavement Improvement | 08/19/2009 |  | 02/01/2010 | 2066000 | 0.7
612 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5935054 | This is a Pavement Restoration and Rehabilitation project by the County of San Mateo. The project is described as: Rehabilitate local street. | Pavement Improvement | 09/25/2009 |  | 10/01/2009 | 1726000 | 4
613 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5936076 | This is a Pavement Restoration and Rehabilitation project by the County of Santa Cruz. The project is described as: Road repairs: various roadways. | Pavement Improvement | 07/21/2009 |  | 10/01/2010 | 2433875 | 4.8
614 | California | SANTA CLARA | SAN JOSE, CA | 11,14,15,16 | 5937132 | This is a Pavement Restoration and Rehabilitation project by the County of Santa Clara. The project is described as: Rehabilitate local street. | Pavement Improvement | 07/14/2009 |  | 09/01/2009 | 3054000 | 2.7
615 | California | MADERA |  | 19 | 5941072 | This is a Pavement Restoration and Rehabilitation project by the County of Madera. The project is described as: Avenue 15 - Road 29 to Road 35 alignment. | Pavement Improvement | 10/21/2009 |  | 09/01/2009 | 1868824 | 6
616 | California | SAN BENITO |  | 17 | 5943048 | This is a Pavement Resurfacing project by the County of San Benito. The project is described as: On Southside Road from Union Road to Southside Bridge, Roadway Rehabilitation.. | Pavement Improvement | 09/08/2009 |  | 08/01/2009 | 851092 | 3
617 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5944095 | This is a Pavement Resurfacing project by the County of Monterey. The project is described as: Overlay Espinosa Road between MP .04 and MP 4.72. | Safety/Traffic Management | 08/10/2009 |  | 12/01/2009 | 2108638 | 4.68
618 | California | INYO |  | 25 | 5948069 | This is a Pavement Reconstruction, No Added Capacity project by the County of Inyo. The project is described as: Reconstruct approx 0.5 mi of Barlow and 0.1 miles of Saniger install traffic striping, | Pavement Improvement | 10/01/2009 |  | 07/01/2010 | 1018000 | 2.9
619 | California | SANTA BARBARA |  | 23,24 | 5951124 | This is a Pavement Resurfacing project by the County of Santa Barbara. The project is described as: AC Overlay Various Streets and Roads. | Pavement Improvement | 06/24/2009 |  | 11/01/2009 | 1715803 | 5
620 | California | SANTA BARBARA |  | 23,24 | 5951125 | This is a Bridge Rehabilitation, No Added Capacity project by the County of Santa Barbara. The project is described as: Seal Cracks in the Bridge decks in Santa Barbara County. | Bridge Improvement | 06/24/2009 |  | 11/01/2009 | 300000 | 1
621 | California | VENTURA | OXNARD-VENTURA | 23,24 | 5952134 | This is a Safety project by the City of Oxnard. The project is described as: Add new through right-turn lane in both directions on Rose; add new left-turn lane on Rose SB; lengthen existing turn lane | Pavement Widening | 07/20/2009 |  | 10/01/2009 | 210000 | 0.13
622 | California | VENTURA | OXNARD-VENTURA | 50 | 5952139 | This is a Pavement Restoration and Rehabilitation project by the County of Ventura. The project is described as: On system roads - Phase A various locations. | Pavement Improvement | 08/13/2009 |  | 12/01/2009 | 2335171 | 10.34
623 | California | LOS ANGELES | LOS ANGELES, CA | 36,38 | 5953595 | This is a Traffic Management Engineering project by the County of Los Angeles. The project is described as: TRAFFIC SIGNAL UPGRADES AT WHITTIER BOULEVARD ET. AL.. | Safety/Traffic Management | 10/06/2009 |  | 09/01/2010 | 206821 | 1
624 | California | LOS ANGELES | LOS ANGELES, CA | 34 | 5953617 | This is a Pavement Resurfacing project by the County of Los Angeles. The project is described as: FIRESTONE BL, ET AL ROADWAY RESURFACING. | Pavement Improvement | 11/18/2009 |  | 02/01/2010 | 1713500 | 2.63
625 | California | SAN BERNARDINO | STATEWIDE | 43 | 6053080 | This is a Pavement Reconstruction, Added Capacity project by the County of San Bernardino. The project is described as: HOV and lane addition to relieve traffic congestion. | Safety/Traffic Management | 10/19/2009 |  | 09/01/2013 | 128116032 | 2.5
626 | California | SAN DIEGO | SAN DIEGO, CA | 52 | 6066067 | This is a Transit project by the San Diego Association of Governments. The project is described as: Pedestrian/disabled user facility improvements. | Transportation Enhancements | 01/11/2010 |  | 11/01/2011 | 4002427 | 0
627 | California | SANTA CRUZ | SANTA CRUZ | 17 | 6149062 | This is a Traffic Management Engineering project by the Santa Cruz County Regional Transportation Commission. The project is described as: Motorist aide tow trucks to remove incidents.. | Safety/Traffic Management | 07/13/2009 |  | 06/01/2012 | 180000 | 7.03
628 | California | SANTA CLARA | SAN JOSE, CA | 15 | 6264042 | This is a Traffic Management Engineering project by the Santa Clara Valley Transportation Authority. The project is described as: In Milpitas: implement roadway pricing on the carpool lane to carpool | Other | 07/08/2009 |  | 09/01/2010 | 2700000 | 4.17
629 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8 | 6328030 | This is a Facilities for Pedestrians and Bicycles project by the San Francisco, MTA/Parking & Traffic. The project is described as: Pedestrian Enhancements. | Transportation Enhancements | 12/01/2009 |  | 06/01/2011 | 632295 | 1
630 | California | SAN DIEGO | SAN DIEGO, CA | 50 | 8051608 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Chula Vista, from north of H Street to north of Route 54; als | Pavement Improvement | 07/24/2009 | 10/05/2009 | 08/01/2010 | 8525838 | 0.9
631 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9 | 8801058 | This is a Bridge Rehabilitation, No Added Capacity project by the California Department of Transportation. The project is described as: In Oakland, at Fruitvale Avenue Bridge #33-0041. | Pavement Improvement | 06/25/2009 | 07/20/2009 | 06/01/2012 | 9412019 | 0.3
632 | California | SONOMA |  | 6 | P001540 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Sonoma County near Fort Ross, from 2.5 miles south of Fort Ross Road to Timber C | Pavement Improvement | 09/10/2009 | 09/14/2009 | 09/01/2010 | 524169 | 7.9
633 | California | ORANGE | LOS ANGELES, CA | 48 | P001541 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in and near Laguna Beach, from Dana Point/Laguna Beach City limits | Pavement Improvement | 09/09/2009 | 09/09/2009 | 06/01/2010 | 2309355 | 9.5
634 | California | KERN |  | 22 | P014065 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Kern County near Mojave, from South Junction State Route 58 to 5 miles north of | Pavement Improvement | 06/28/2009 | 07/02/2009 | 10/01/2009 | 5129627 | 24.5
635 | California | SAN BERNARDINO |  | 41 | P018037 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County, from 0.1 mile west of Route 18/330 Separation to Lakeview | Pavement Improvement | 06/25/2009 | 07/24/2009 | 12/01/2009 | 1360611 | 7.5
636 | California | SAN BERNARDINO |  | 41 | P018038 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County near Big Bear City, from Snubbing Post Grade Road to 0.6 m | Pavement Improvement | 06/23/2009 | 06/19/2009 | 12/01/2009 | 859022 | 10
637 | California | COLUSA |  | 2 | P020150 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In Williams, from 0.3 mile east to 0.6 mile west of Route 5. | Pavement Improvement | 09/09/2009 | 10/06/2009 | 10/01/2010 | 7088950 | 0.9
638 | California | YUBA |  | 2 | P020151 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Yuba County near Marysville, from 0.2 miles west of Spring Valley Road to 0.1 mi | Pavement Improvement | 08/13/2009 | 08/13/2009 | 10/01/2010 | 1227430 | 3.2
639 | California | ALAMEDA, CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 9 | P024030 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: Construct a 2-lane tunnel | Pavement Improvement | 11/20/2009 | 01/13/2010 | 05/01/2014 | 192357000 | 2.2
640 | California | NAPA |  | 1 | P029105 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Napa County near Calistoga, from 0.2 miles north of Silverado Trail to Lake Coun | Pavement Improvement | 07/21/2009 | 08/19/2009 | 06/01/2010 | 673891 | 10.5
641 | California | MERCED |  | 18 | P033068 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Merced County in and near Dos Palos, from Fresno County Line to State Route 152; | Pavement Improvement | 06/25/2009 | 07/10/2009 | 12/01/2009 | 1182595 | 19.9
642 | California | VENTURA | OXNARD-VENTURA | 37 | P034004 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Ventura County in and near Camarillo, from Daily Drive to State Route 118. | Pavement Improvement | 07/16/2009 | 07/17/2009 | 05/01/2011 | 1436883 | 4
643 | California | PLUMAS |  | 4 | P036086 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Plumas County about 6 miles east of Chester, from 0.8 mile west to 1.2 miles eas | Pavement Improvement | 06/12/2009 | 08/15/2009 | 12/01/2010 | 1739616 | 1.7
644 | California | ORANGE | LOS ANGELES, CA | 39 | P039021 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In La Habra, from Route 90 to Los Angeles County Line; also on R | Pavement Improvement | 07/17/2009 | 09/21/2009 | 07/01/2011 | 5634488 | 4
645 | California | FRESNO | FRESNO | 20,21 | P041110 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In Fresno - At McKinley Avenue and Shields Avenue | Pavement Improvement | 08/11/2009 |  | 11/01/2011 | 2954313 | 1.4
646 | California | SAN LUIS OBISPO |  | 22 | P046042 | This is a Safety project by the California Department of Transportation. The project is described as: Near Shandon - at the Shandon Rest Area - rehabilitate Safety Roadside Rest Area | Safety/Traffic Management | 08/13/2009 | 10/06/2009 | 03/01/2012 | 4730488 | 0
647 | California | EL DORADO |  | 4 | P049143 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near El Dorado, from Ore Court Road to China Hill Road. | Pavement Improvement | 07/07/2009 | 07/07/2009 | 09/01/2011 | 6868710 | 1
648 | California | SIERRA |  | 4 | P049144 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Sierra County on State Route 49 near Sierraville and Loyalton, from South Juncti | Pavement Improvement | 07/09/2009 | 07/27/2009 | 10/01/2010 | 901956 | 17
649 | California | TUOLUMNE |  | 4 | P049145 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Tuolumne County in and near Sonora, from 0.2 mile south of Pesce Way to Calavera | Pavement Improvement | 07/02/2009 | 07/20/2009 | 12/01/2009 | 1274809 | 9.1
650 | California | ORANGE | LOS ANGELES, CA | 39,47 | P057053 | This is a Safety project by the California Department of Transportation. The project is described as: In Orange, Anaheim and Fullerton, from West Orangewood Avenue to the Los Angeles County line at v | Pavement Improvement | 08/05/2009 | 08/05/2009 | 07/01/2011 | 2968914 | 11
651 | California | SAN BERNARDINO |  | 41 | P062026 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County, from 4.9 miles west to 0.9 miles west of Rio Mesa Drive. | Pavement Improvement | 08/14/2009 | 08/14/2009 | 12/01/2009 | 903988 | 4
652 | California | ORANGE | LOS ANGELES, CA | 48 | P073086 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in Laguna Niguel, Laguna Hills, Aliso Viejo, Laguna Beach and Irvi | Pavement Improvement | 08/05/2009 | 08/19/2009 | 12/01/2010 | 8790626 | 12.5
653 | California | RIVERSIDE |  | 45 | P078108 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Palo Verde, on 32nd Avenue west of South Randalls Avenue Brid | Pavement Improvement | 08/04/2009 | 09/17/2009 | 05/01/2011 | 1608437 | 0.2
654 | California | AMADOR | STOCKTON | 4 | P088052 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Amador County in and near Barton, from 0.1 mile west of Wagon Wheel Drive to 0.1 | Pavement Improvement | 06/25/2009 | 07/06/2009 | 12/01/2009 | 995691 | 5.7
655 | California | AMADOR |  | 4 | P088053 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Amador County near Plasse, from 2 miles west of Tragedy Springs Road to 0.3 mile | Pavement Improvement | 07/10/2009 | 07/10/2009 | 12/01/2009 | 490501 | 6.1
656 | California | EL DORADO |  | 4 | P089094 | This is a Mitigation of Water Pollution due to Highway Runoff project by the California Department of Transportation. The project is described as: Near Meyers, from Alpine County Line to Route 50. | Pavement Improvement | 07/01/2009 | 09/01/2009 | 01/01/2011 | 16425073 | 8.6
657 | California | RIVERSIDE, ORANGE | LOS ANGELES, CA | 42,44 | P091127 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Orange County add one lane on eastbound SR-91 from SR-241 to | Pavement Improvement | 09/16/2009 | 11/10/2009 | 11/01/2011 | 47887635 | 5.9
658 | California | RIVERSIDE |  | 45 | P095020 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: Near Blythe, from 0.4 mile north of Wiley Hill Log Cabin to 0 | Pavement Improvement | 06/26/2009 |  | 02/01/2010 | 2639700 | 8.3
659 | California | BUTTE |  | 2,4 | P099519 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: SR 99 Near Biggs - Rio Bonito to SR 162. | Pavement Improvement | 07/07/2009 | 08/01/2009 | 01/01/2011 | 11436484 | 4.6
660 | California | SUTTER |  | 2 | P099520 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Sutter County, SR 99 near East Nicholas, from Sacramento County | Pavement Improvement | 07/23/2009 | 07/06/2009 | 10/01/2010 | 12195645 | 8.7
661 | California | MERCED | MERCED | 18 | P099521 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: In Merced County, from north of V Street to Black Rascal Bridge #3 | Pavement Improvement | 10/22/2009 | 10/22/2009 | 04/01/2012 | 29805432 | 1.5
662 | California | LOS ANGELES | LOS ANGELES, CA | 29 | P134035 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Los Angeles County in Burbank, Glendale and Los Angeles, from Bob Hope Drive Und | Pavement Improvement | 08/06/2009 | 09/03/2009 | 05/01/2011 | 1511500 | 6.4
663 | California | LASSEN |  | 4 | P139019 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Lassen County about 40 miles north of Susanville, from 7.0 miles north of Califo | Pavement Improvement | 07/14/2009 | 07/27/2009 | 12/01/2010 | 1555196 | 13
664 | California | MADERA |  | 18,19 | P145029 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: Near Madera, from Avenue 5 1/2 to Avenue 11 1/2. | Pavement Improvement | 06/20/2009 | 06/20/2009 | 05/01/2011 | 10674715 | 6.1
665 | California | FRESNO |  | 21 | P180053 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near Centerville, from Temperance Avenue to Academy Avenue (Qual | Pavement Improvement | 09/21/2009 | 11/30/2009 | 05/01/2012 | 18369261 | 6.2
666 | California | MENDOCINO |  | 1 | P222001 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Ukiah, at Russian River Bridge #10-80. | Bridge Replacement | 10/15/2009 | 10/15/2009 | 09/01/2012 | 7903106 | 0.01
667 | California | RIVERSIDE |  | 45 | P243002 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Riverside County near Idyllwild, from 1.1 miles north of State Routes 74/243 Sep | Pavement Improvement | 07/15/2009 | 07/29/2009 | 12/01/2009 | 1933265 | 12.2
668 | California | MODOC |  | 4 | P395224 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Modoc County near Alturas, from the Lassen/Modoc County Line to Alturas Overhead | Pavement Improvement | 07/17/2009 | 08/13/2009 | 12/01/2010 | 2358462 | 20.8
669 | California | SAN BERNARDINO |  | 25 | P395225 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County on US Highway 395 near Kramer Junction, from Federal Priso | Pavement Improvement | 06/26/2009 | 07/10/2009 | 12/01/2009 | 1530677 | 6
670 | California | MONO |  | 25 | P395226 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Mono County near Hilton Creek, from 0.1 mile north of Crooked Creek Bridge to 0. | Pavement Improvement | 07/03/2009 | 07/23/2009 | 12/01/2009 | 3273458 | 23.5
671 | California | LOS ANGELES | LOS ANGELES, CA | 34,39 | P710014 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Los Angeles from 0.3 mile south of Firestone Blvd to 0.2 mile | Pavement Improvement | 09/23/2009 | 11/16/2009 | 01/01/2014 | 52602457 | 2.7
672 | California | MONTEREY |  | 17 | Q101151 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near Salinas, from Central Avenue to Gould Avenue at various loc | Pavement Improvement | 08/14/2009 | 08/31/2009 | 07/01/2010 | 5942549 | 36.9
673 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 4 | Q101152 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Mateo County in South San Francisco and Brisbane, from Oyster Point Boulevar | Pavement Improvement | 08/14/2009 | 08/19/2009 | 12/01/2010 | 3134512 | 3.1
674 | California | MARIN | STATEWIDE | 6 | Q101155 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Construct HOV lanes and bike path | Transportation Enhancements | 10/16/2007 | 08/15/2007 | 10/01/2009 | 2401200 | 1.86
675 | California | SANTA CLARA |  | 10,14 | S035007 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Santa Clara County near Los Gatos, from Black Road to the State Route 35 separat | Pavement Improvement | 07/21/2009 | 08/19/2009 | 09/01/2010 | 1421222 | 6.42
676 | California | KERN | BAKERSFIELD | 22 | S204004 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: In Bakersfield, at Chester Avenue Bridge #50-183. | Bridge Replacement | 07/03/2009 | 08/24/2009 | 08/01/2012 | 15231775 | 1
677 | California | FRESNO |  | 20 | X019021 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Fresno County on Route 33 near Harris Ranch, from I-5 to 1.7 miles north of Harl | Pavement Improvement | 06/18/2009 | 07/06/2009 | 10/01/2009 | 1519610 | 1
678 | California | VENTURA, LOS ANGELES |  | 23,24 | X037145 | This is a Safety project by the California Department of Transportation. The project is described as: In Ventura County in and near Oxnard from Wood Road to Mobil Pier Road and in routes 23,33,101,11 | Safety/Traffic Management | 10/15/2009 | 01/01/2010 | 12/01/2011 | 1197345 | 1
679 | California | LOS ANGELES | LOS ANGELES, CA | 30 | X037146 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles County in Santa Monica from Lincoln Blvd to Palasades pedestrian overcrossing and | Safety/Traffic Management | 10/15/2009 | 11/09/2009 | 07/01/2011 | 1343812 | 1
680 | California | LOS ANGELES | LOS ANGELES, CA | 34,38,39 | X037147 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles County from Santa Fe Springs to Los Angeles from Valley-View Avenue to Soto Street | Safety/Traffic Management | 09/01/2009 |  | 08/01/2011 | 1472796 | 1
681 | California | LOS ANGELES | LOS ANGELES, CA | 35,66,37 | X037148 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles and Long Beach, on various routes. | Safety/Traffic Management | 09/01/2009 | 10/17/2009 | 07/01/2011 | 1136232 | 1
682 | California | MONTEREY |  | 17 | X053022 | This is a Safety project by the California Department of Transportation. The project is described as: Pacific Grove to Castroville, south of Route 1 to Tembladero Slough; also on Route 68 east of Fai | Safety/Traffic Management | 06/29/2009 | 06/29/2009 | 07/01/2010 | 1872022 | 17.1
683 | Colorado | MESA |  | 3 | 0063031 | Enhancement Project: constructs bike and pedestrian trail in Fruita along US 6 | Transportation Enhancements | 09/21/2009 |  |  | 433399 | 0.63
684 | Colorado | EAGLE |  | 2 | 006A043 | Enhancement Project: constructs bike and pedestrian trail to connect Town of Minutrn to Dowd Junction ECO trail | Transportation Enhancements | 09/21/2009 | 09/22/2009 |  | 375000 | 0.42
685 | Colorado | SUMMIT |  | 2 | 0091032 | Widens SH 9 to two lanes in each direction and constructs a new pedestrian bridge and a retaining wall. The project will also relocate a bike path and improve drainage north of Breckenridge in Summit | Pavement Widening | 06/04/2009 | 06/04/2009 | 01/13/2010 | 8994331 | 1.55
686 | Colorado | RIO BLANCO |  | 3 | 0131055 | Reconstructs five miles of SH 13 in asphalt, adds eight-foot shoulders and climbing and passing lanes at Rio Blanco Hill in Rio Blanco County. The improvements will enhance recreational bicycling in t | Pavement Widening | 07/17/2009 | 07/17/2009 | 10/01/2010 | 10439448 | 5.29
687 | Colorado | JACKSON |  | 03,04 | 0141020 | Asphalt resurfacing of SH 14 east and est of Cameron Pass in Larimer and Jackson counties. | Pavement Improvement | 06/04/2009 | 06/09/2009 | 11/18/2009 | 5478898 | 13.39
688 | Colorado | CHAFFEE |  | 5 | 0242045 | Resurfaces 12.5 miles of US 24/US 285, north of Johnson Village in Chaffee County, in asphalt. | Pavement Improvement | 05/19/2009 | 07/13/2009 | 10/14/2009 | 3714986 | 12.68
689 | Colorado | EL PASO |  | 5 | 0243076 | Replaces a structurally deficient bridge over Falcon Creek in Falcon in El Paso County and improves drainage. | Bridge Replacement | 09/16/2009 | 09/16/2009 | 07/01/2010 | 3463203 | 0.8
690 | Colorado | LAS ANIMAS | PUEBLO | 3 | 0251335 | Constructs the Purgatoire River Pedestrian Trail, adds street lights, parking lot paving, curb and gutter, drainage inlets, landscaping and sidewalk along I-25 in Trinidad. | Pavement Improvement | 06/16/2009 | 05/29/2009 | 07/03/2011 | 7044806 | 3
691 | Colorado | DENVER | DENVER, CO | 1 | 0252402 | Resurfaces approximately three miles of I-25 in Denver from 6th Avenue to 23rd Avenue, in asphalt. | Pavement Improvement | 04/28/2009 | 06/14/2009 | 11/04/2009 | 4190706 | 2
692 | Colorado | LARIMER | FORT COLLINS | 4 | 0253206 | Improves five miles of roadway surface on I-25 from the Crossroads Interchange at Loveland to SH 392, the Windsor Interchange. | Pavement Improvement | 07/01/2009 | 07/05/2009 | 10/19/2009 | 6859424 | 4.012
693 | Colorado | LARIMER | FORT COLLINS | 4 | 0253207 | Constructs roundabouts on Crossroads at the I-25 and Crossroads, Loveland interchange to improve mobility and safety. | Safety/Traffic Management | 08/31/2009 | 08/31/2009 |  | 3000000 | 0.95
694 | Colorado | WELD |  | 4 | 0342050 | Installs a traffic signal at the intersection of US 34 and Weld County Road 49, west of Kersey. | Safety/Traffic Management | 08/03/2009 | 08/08/2009 | 10/03/2009 | 462227 | 0.2
695 | Colorado | LARIMER |  | 02,04 | 0361089 | Chip seals 22 miles of US 36 between Lyons and Estes Park to improve the roadway surface condition. | Pavement Improvement | 06/22/2009 | 07/20/2009 | 08/24/2009 | 1652568 | 21.77
696 | Colorado | BOULDER | BOULDER | 2 | 0361090 | Installs a new traffic signal at the intersection of US 36 and Broadway in Boulder. | Safety/Traffic Management | 07/02/2009 | 08/03/2009 | 10/13/2009 | 386913 | 0.27
697 | Colorado | CHAFFEE |  | 5 | 050A009 | Enhancement Project: constructs curb, gutter, sidewalk, and ADA ramps in Salida on US 50 | Transportation Enhancements | 09/03/2009 | 09/18/2009 | 12/17/2009 | 491470 | 0.766
698 | Colorado | BOULDER | BOULDER | 2 | 052A031 | Replaces the bridge over Boulder Creek on SH 52 at the Boulder - Weld County Line. | Bridge Replacement | 07/16/2009 | 08/31/2009 | 07/21/2010 | 4978205 | 0.511
699 | Colorado | WELD |  | 4 | 060A013 | Installs a new traffic signal at the intersection of the I-25 exit ramps and frontage roads with SH 60 (Johnstown Exit).. | Safety/Traffic Management | 07/09/2009 | 08/03/2009 | 09/28/2009 | 493383 | 0.17
700 | Colorado | SAN MIGUEL |  | 3 | 062A013 | Resurface a total of 21.5 miles of SH 62, Dallas Divide in in Ouray and San Migel counties between Placerville and Ridgway, in asphalt and repair embankments. Project includes some work on US 550 at R | Pavement Improvement | 05/12/2009 | 05/12/2009 | 10/02/2009 | 4000000 | 24.9
701 | Colorado | MESA | GRAND JUNCTION | 3 | 0701197 | Improves safety by widening the acceleration and deceleration lanes at this interchange on I-70 at the Palisade exit in Mesa County. The improvements will upgrade the interchange to current design sta | Pavement Improvement | 06/22/2009 | 09/21/2009 | 11/24/2009 | 1552173 | 1
702 | Colorado | SUMMIT |  | 2 | 0702283 | Resurfaces 14 miles of I-70 from milepost 190 to 204 as well as the right lane of eastbound I-70 between milepost 180 and 190. Numerous bridges along the I-70 corridor will also be rehabilitated by r | Pavement Improvement | 05/05/2009 | 05/05/2009 | 11/08/2009 | 8000000 | 24
703 | Colorado | JEFFERSON | DENVER, CO | 7 | 0703350 | Repairs and replaces concrete slabs on I-70 between Kipling Street and Wadsworth Blvd in Wheatridge. | Pavement Improvement | 04/21/2009 | 05/19/2009 | 08/09/2009 | 1793405 | 2.07
704 | Colorado | EAGLE | DENVER, CO | 2 | 0703353 | Installs various truck parking management components (electronic signs, closed-circuit cameras, power and communications systems), to provide notification during inclement weather. along I-70 between | Safety/Traffic Management | 06/22/2009 | 06/22/2009 | 10/29/2009 | 2014974 | 54.44
705 | Colorado | ADAMS | DENVER, CO | 7 | 0704217 | Installs cable guardrailin the median of I-70 between Pena Blvd and Tower Road in Aurora to prevent crossover accidents. | Safety/Traffic Management | 06/22/2009 | 07/13/2009 | 09/07/2009 | 294430 | 2.18
706 | Colorado | ADAMS | DENVER, CO | 7 | 0761200 | Construct two roundabouts on 96th Avenue at the ramps to I-76 in Commerce City. | Safety/Traffic Management | 05/21/2009 | 06/22/2009 | 12/18/2009 | 2222733 | 0.04
707 | Colorado | ADAMS | DENVER, CO | 7 | 0761201 | Replaces two bridges on I-76 over the Union Pacific Railroad and SH 224 in Commerce City. | Bridge Replacement | 06/02/2009 | 07/06/2009 | 02/03/2011 | 10876514 | 1.043
708 | Colorado | SEDGWICK |  | 4 | 0762045 | Reconstructs 11 miles of eastbound I-76 in concrete between Sedgwick and the Nebraska state line. | Pavement Improvement | 07/10/2009 | 07/13/2009 | 01/23/2010 | 15570336 | 19.49
709 | Colorado | GARFIELD |  | 3 | 0821087 | This safety improvement project at the I-70 interchange with US 6 and SH 82 in Glenwood Springs will upgrade traffic signals and improve ramp width and length to benefit both pedestrians and vehicle | Other | 09/03/2009 | 08/03/2009 | 11/24/2009 | 2500000 | 3.02
710 | Colorado | DOUGLAS | DENVER, CO | 6 | 0852095 | Widens one mile of US 85 to two lanes in each directions with shoulders and a raised median with controlled access on US 85 between Titan Road and Cook Ranch Road in Douglas County. | Pavement Widening | 08/17/2009 | 08/17/2009 | 05/03/2010 | 5400000 | 7.48
711 | Colorado | ARAPAHOE | DENVER, CO | 6 | 088A026 | Replaces the asphalt surface on SH 88, Belleview Avenue, between Santa Fe Drive and Federal Blvd in Littleton. | Pavement Improvement | 04/28/2009 | 05/18/2009 | 06/29/2009 | 431702 | 0.9
712 | Colorado | DELTA |  | 3 | 092A022 | Reconstructs five miles of SH 92 in asphalt and adds passing lanes and shoulders to improve recreational bicycling between Austin and Hotchkiss in Delta County. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 10/30/2010 | 9677646 | 4.1
713 | Colorado | RIO GRANDE |  | 3 | 1602122 | Resurfaces three miles of US 160 west of Del Norte in Rio Grande County, in asphalt. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 07/21/2009 | 1468886 | 3.32
714 | Colorado | ALAMOSA |  | 3 | 1603027 | Resurfaces six miles of US 160 east of Alamosa in asphalt. | Pavement Improvement | 06/12/2009 | 07/13/2009 | 09/07/2009 | 2773893 | 6.755
715 | Colorado | LA PLATA |  | 3 | 160A010 | Constructs a new eastbound on-ramp as part of an already scheduled project that will widen US 160 to four lanes and relocate a traffic signal due to the widening east of Durango. | New Construction | 09/03/2009 | 09/03/2009 | 04/21/2010 | 3919600 | 1.49
716 | Colorado | DOUGLAS | DENVER, CO | 6 | 177A006 | Resurface in asphalt, SH 177, University Avenue in Centennial, from C-470 to Arapahoe. | Pavement Improvement | 05/12/2009 | 05/26/2009 | 08/08/2009 | 1559083 | 2
717 | Colorado | ARAPAHOE | DENVER, CO | 7 | 2254078 | Phase 1 of project to reconstruct the I-225 / Colfax interchange in Aurora to rebuild the southbound ramp from Colfax to I-225 | Pavement Widening | 11/23/2009 | 11/30/2009 | 05/07/2010 | 1077890 | 0.096
718 | Colorado | WELD | FORT COLLINS | 4 | 257A007 | Installs a new traffic signal at the intersection fo SH 257 and Garden drive in Windsor. | Safety/Traffic Management | 07/16/2009 | 08/10/2009 | 10/05/2009 | 344070 | 0.16
719 | Colorado | SAGUACHE |  | 3 | 2852016 | Resurfaces eight miles of US 285, south of Saguache, in asphalt. | Pavement Improvement | 06/12/2009 | 06/12/2009 | 08/29/2009 | 3660211 | 9.48
720 | Colorado | JEFFERSON | DENVER, CO | 6 | 2854117 | Constructs a grade-separated interchange at Elk Creek Road, new frontage roads and a wildlife crossing underpass. When complete, Elk Creek Rd. will run under US 285. THe project is located in Jefferso | Pavement Widening | 08/26/2009 | 08/26/2009 | 12/08/2010 | 8400000 | 0.664
721 | Colorado | BACA |  | 4 | 2871032 | This project will reconstruct US 287 in concrete and improve drainage and shoulder embankments south of Springfield in Baca County. | Pavement Improvement | 10/07/2009 | 10/12/2009 | 10/03/2010 | 13688257 | 8.3
722 | Colorado | MESA |  | 3 | 340A015 | Installs two new traffic signals west of the I-70 interchange on SH 240 in Fruitia in Mesa County.and makes intersection safety improvements for pedestrians and vehicles. | Pavement Widening | 09/21/2009 |  |  | 1628248 | 0.89
723 | Colorado | DOUGLAS | DENVER, CO | 6 | 4701118 | Repairs or replaces concrete slabs on C-470 and resurfaces C-470 in asphalt between Santa Fe Drive and I-25 in Douglas County. Rehabilitates the C-470 bike path between I-70 and I-25 in Jefferson, Ara | Pavement Improvement | 06/16/2009 | 07/09/2009 | 08/12/2010 | 31465789 | 9.243
724 | Colorado | WELD | FORT COLLINS | 4 | C030035 | Resurfaces Weld County Road 74 from Weld County Road 13 to SH 357 in asphalt. | Pavement Improvement | 08/24/2009 | 08/24/2009 |  | 625000 | 0
725 | Colorado | LARIMER | FORT COLLINS | 4 | C060049 | Enhancement Project: Constructs a bicycle/pedestrian underpass under SH 392 in Windsor. | Transportation Enhancements | 07/28/2009 | 08/12/2009 |  | 600000 | 0.369
726 | Colorado | LARIMER | FORT COLLINS | 4 | C060050 | Resurfaces Larimer County Road 17 between Berthoud and Fort Collins in asphalt. | Pavement Improvement | 07/28/2009 | 08/03/2009 | 10/19/2009 | 3485000 | 0
727 | Colorado | ARAPAHOE | DENVER, CO | 6 | C100028 | Enhancement Project: Construct an extension to the bicycle and pedestrain bridge over I-25 south of Dry Creek Road to extend over Inverness Drive in Arapahoe County. | Transportation Enhancements | 07/30/2009 | 11/18/2009 | 07/19/2010 | 708947 | 0
728 | Colorado | STATEWIDE |  | 04 | HQ00023 | Provides on the job training to construction workers to develop construction skills | Other | 09/15/2009 | 09/15/2009 |  | 250000 | 0
729 | Colorado | JEFFERSON | DENVER, CO | 02,07 | M040017 | Enhancement Project: Construct a bicycle and pedestrian trail on the south side of the West 86th Parkway in Arvada to connect the exisitng trails. | Transportation Enhancements | 10/13/2009 | 10/22/2009 | 12/21/2009 | 300000 | 0
730 | Colorado | LA PLATA |  | 3 | M065003 | Enhancement Project: constructs sidewalks along US 160 business route in Bayfield | Transportation Enhancements | 08/20/2009 | 08/24/2009 | 10/13/2009 | 200000 | 0.11
731 | Colorado | BOULDER | STATEWIDE | 2 | M110065 | Enhancement Project: constructs pedestrian access ramps at various intersections in Boulder to meet Americans with Disability (ADA) requirements. | Transportation Enhancements | 09/08/2009 | 09/14/2009 |  | 757624 | 0
732 | Colorado | WELD | FORT COLLINS | 4 | M190003 | Resurfaces in asphalt 4th Avenue(Weld County Road 74) in Severance 2.5 miles west of Weld County Road 25 | Pavement Improvement | 09/28/2009 | 09/28/2009 |  | 838000 | 0
733 | Colorado | EL PASO | COLORADO SPRINGS | 5 | M240121 | Widens Woodmen Rd. and constructs a new interchange at Academy Blvd.in Colorado Springs including construction of sidewalks and a bike path. | Pavement Widening | 09/18/2009 | 09/24/2009 | 11/15/2011 | 35031818 | 0
734 | Colorado | DENVER | DENVER, CO | 1 | M320064 | Enhancement Project: Striping and singage on various designated bikeways on the streets of Denver. | Transportation Enhancements | 10/22/2009 | 10/26/2009 | 06/30/2010 | 250000 | 0
735 | Colorado | ADAMS | DENVER, CO | 2 | M356024 | Enhancement Project: replace existing 4' sidewalks with 8' sidewalks to serve as a bike and pedestrain train on Bradburn Blvd from 73rd Avenue to Turnpike Drive in Westminster. | Transportation Enhancements | 07/23/2009 | 07/27/2009 | 09/30/2009 | 260000 | 0
736 | Colorado | WELD | BOULDER | 2 | M400004 | Enhancement Project: Construct bike pathes on the north and south sides of Leon Wurl Parkway in Erie from Bonanza Drive east to I-25. | Transportation Enhancements | 10/12/2009 | 10/19/2009 |  | 607066 | 0
737 | Colorado | LARIMER |  | 4 | M405013 | Enhancement Project: constructs Fall River Trail/Path in Estes Park | Transportation Enhancements | 10/05/2009 | 10/08/2009 | 12/15/2009 | 140012 | 0.73
738 | Colorado | WELD | FORT COLLINS | 4 | M415012 | Resurfaces 37th Street in Evans in asphalt | Pavement Improvement | 09/08/2009 | 09/08/2009 | 10/16/2009 | 354000 | 0
739 | Colorado | GARFIELD |  | 3 | M535004 | Enhancement Project: constructs a pedestrian bridge over I-70 along Devereux Rd in Glenwood Springs | Transportation Enhancements | 09/11/2009 | 09/15/2009 | 06/01/2010 | 50200 | 0
740 | Colorado | LARIMER | FORT COLLINS | 4 | M830047 | Intersection improvements at SH 34 and Wilson in Loveland. | Safety/Traffic Management | 09/14/2009 | 09/14/2009 |  | 250000 | 0
741 | Colorado | BOULDER | BOULDER | 2 | M835002 | Enhancement Project: streetscape enhancements and recostruction of Main Street (US 36) in Lyons between 3rd and 5th Avenues to include paving, curb and gutter, landscaping and pedestrian amenities. | Transportation Enhancements | 09/28/2009 | 10/12/2009 | 12/09/2009 | 689000 | 0.294
742 | Colorado | BOULDER | BOULDER | 2 | M935001 | Enhancement Project: Construct sidewalks on SH 119 between Eldora and @nd in Nederland to connect to the RTD parking. | Transportation Enhancements | 09/08/2009 |  |  | 385000 | 2
743 | Colorado | LINCOLN |  | 4 | R100157 | The project will ireconstruct to concrete pavement 8.7 miles of US 40/US 287 (mileposts 413-422 approximately) south of Hugo in Lincloln County. | Pavement Improvement | 06/02/2009 | 06/02/2009 | 03/17/2010 | 12248750 | 8.7
744 | Colorado | ADAMS | DENVER, CO | 02,06 | R600340 | Installs ramp metering systems on I-25, US 36, and C470 in various locations | Safety/Traffic Management | 05/19/2009 | 06/01/2009 | 08/11/2009 | 333489 | 0.18
745 | Colorado | BOULDER | DENVER, CO | 02,07 | R600343 | Replaces traffic signals at the intersection of US6, SH 58 and SH 93 in Golden and at the SH 128 and Simms intersection in Broomfield. | Safety/Traffic Management | 06/04/2009 | 07/20/2009 | 10/28/2009 | 886979 | 4.38
746 | Colorado | JEFFERSON | DENVER, CO | 7 | R600346 | Resurface in asphalt approximately three miles of US 40, Colfax Avenue, between Kipling Street and Sheridan Blvd in Lakewood. | Pavement Improvement | 05/01/2009 | 06/01/2009 | 09/09/2009 | 3337195 | 2.829
747 | Connecticut | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 0001315 | The project involves the reconstruction and lengthening of the existing AMTRAK bridge over Route 1, as well as the rehabilitation of a portion of Route 1 in the Town of Branford | Bridge Replacement | 08/13/2009 | 08/13/2009 | 03/09/2014 | 70815491 | 0
748 | Connecticut | HARTFORD | SPRINGFIELD-CHICOPEE-HOLYOKE (MA) | 01 | 0005105 | This project will extend the life of the bridge along Route 5 over Interstate 91 in the Town of Enfield by replacing the existing deteriorated deck, bridge supports, and piers. | Bridge Improvement | 06/22/2009 | 06/22/2009 | 12/13/2010 | 6657600 | 0
749 | Connecticut | STATEWIDE |  | 01,02,03,04,05 | 000R418 | The State of Connecticut will replace overhead sign supports on multiple state highways | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 12/01/2010 | 5975600 | 0
750 | Connecticut | HARTFORD |  | 01 | 000R430 | The State of Connecticut will install and revise traffic control signals at various intersections throughout District 1 | Safety/Traffic Management | 07/27/2009 | 07/27/2009 | 08/10/2010 | 1362070 | 0
751 | Connecticut | STATEWIDE |  | 02 | 000R442 | The State of Connecticut will install and revise traffic control signals at various intersections in District 2 to improve safety | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 09/01/2010 | 328970 | 0
752 | Connecticut | STATEWIDE |  | 02 | 000R444 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 to improve safety | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 09/01/2010 | 1872080 | 0
753 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 000R447 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 to improve safety | Safety/Traffic Management | 08/10/2009 | 08/03/2009 | 05/17/2010 | 186176 | 0.01
754 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 000R449 | The State of Connecticut will install and revise traffic control signals at various intersections in District 3 | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 05/17/2010 | 339748 | 0
755 | Connecticut | STATEWIDE |  | 05,01 | 000R453 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 4 | Safety/Traffic Management | 12/11/2009 | 05/04/2010 | 07/14/2009 | 788940 | 0
756 | Connecticut | STATEWIDE |  | 03,04 | 000R514 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 05/17/2010 | 1073963 | 0
757 | Connecticut | STATEWIDE |  | 05,01 | 000R538 | This project consists of the replacement of bridge deck joints within District 4 | Bridge Improvement | 07/24/2009 | 08/03/2009 | 01/26/2010 | 5734200 | 32.26
758 | Connecticut | NEW HAVEN | WATERBURY | 03 | 000R596 | This project consists of pavement milling and resurfacing of the travel lanes, new line striping, rumble strips, and NOVACHIPTM Surface treatment that provides improved skid, wear, and rutting resiste | Pavement Improvement | 10/16/2009 | 10/16/2009 | 05/17/2010 | 3932474 | 5.88
759 | Connecticut | STATEWIDE |  | 01,02,03,04,05 | 000R597 | The State of Connecticut will conduct crack sealing and crack filling along major highways including Route 8, I-84, I-91, I-95, and I-384. This effort will help extend the lifetime of the pavements o | Pavement Improvement | 10/01/2009 | 10/01/2009 | 11/14/2009 | 2204907 | 22.27
760 | Connecticut | STATEWIDE |  | 01 | 000R598 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists through District 1. | Safety/Traffic Management | 08/31/2009 | 09/08/2009 | 09/30/2009 | 189000 | 0
761 | Connecticut | STATEWIDE |  | 02 | 000R599 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 2. | Safety/Traffic Management | 09/01/2009 | 10/05/2009 | 10/19/2009 | 189000 | 0
762 | Connecticut | STATEWIDE |  | 03, 04 | 000R600 | The State of Connecticut will install epoxy pavement markings and Interstae lines for safey of motorists through District 3. | Safety/Traffic Management | 09/01/2009 | 09/20/2009 | 10/14/2009 | 245000 | 0
763 | Connecticut | STATEWIDE |  | 05, 01 | 000R601 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 4 | Safety/Traffic Management | 09/02/2009 | 09/08/2009 | 05/17/2010 | 77000 | 0
764 | Connecticut | STATEWIDE |  | 01 | 000R604 | The State of Connecticut will install epoxy pavement markings and Interste lines for safety of motorists throughout District 1. | Safety/Traffic Management | 10/16/2009 | 10/25/2009 | 11/10/2009 | 368000 | 0
765 | Connecticut | STATEWIDE |  | 02 | 000R605 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 2. | Safety/Traffic Management | 10/06/2009 | 10/19/2009 | 11/04/2009 | 464000 | 0
766 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0015103 | This project will provide for median deck repairs on the bridge carrying Route 15 (Merritt Parkway) over Reservoir Avenue in the Town of Trumbull | Bridge Improvement | 06/15/2009 | 06/18/2009 | 07/29/2011 | 1299200 | 0
767 | Connecticut | NEW HAVEN |  | 02 | 0032184 | The State of Connecticut will resurface Route 2 in Eastbound and Westbound directions from Colchester to Lebanon | Pavement Improvement | 10/28/2009 | 10/28/2009 | 11/11/2009 | 3802792 | 0.02
768 | Connecticut | WINDHAM |  | 02 | 0089118 | This project involves the reconstruction of the existing bridge superstructure, including new steel girders and a concrete deck. Additional improvements to the approach pavement and drainage will als | Bridge Improvement | 07/03/2009 | 07/13/2009 | 08/03/2010 | 1272600 | 0
769 | Connecticut | HARTFORD | HARTFORD | 01 | 0091103 | Pavement preservation will be conducted by the State of Connecticut along Interstate 91 from West Street in the Town of Rocky Hill to Route 3 in the Town of Wethersfield. Scope of work includes resur | Pavement Improvement | 10/01/2009 | 10/14/2009 | 11/18/2009 | 4748987 | 4.08
770 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150192 | This project involves the resurfacing of the pavement, along with other bridge and safety improvements, along a section of Route 15 (Merritt Parkway) from Congress Street to Morehouse Highway | Pavement Improvement | 06/15/2009 | 06/18/2009 | 07/29/2011 | 25328500 | 44.06
771 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150193 | This project will provide for the replacement of the existing Route 15 (Merritt Parkway) bridge over the Mill River in the Town of Fairfield. | Bridge Replacement | 06/15/2009 | 06/18/2009 | 07/29/2011 | 11202400 | 0.02
772 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150194 | This project involves the resurfacing of the pavement, along with other bridge and safety improvements, along a section of Route 15 (Merritt Parkway) from Morehouse Highway to Route 8 | Pavement Improvement | 06/15/2009 | 06/18/2009 | 07/29/2011 | 32914900 | 10.73
773 | Connecticut | MIDDLESEX | MERIDEN-NEW HAVEN | 02 | 0952111 | This project consists of replacing the bridge deck joints on the Baldwin Bridge on I95 over the Connecticut River | Bridge Improvement | 07/27/2009 | 07/27/2009 | 11/17/2009 | 2851300 | 0
774 | Connecticut | HARTFORD | HARTFORD | 01 | 1076120 | In the Town of Manchester, a new traffic control signal will be installed at the interesection of Slater Street and the Best Buy driveways to improve safety and traffic flow to and from exisiting stor | Safety/Traffic Management | 09/08/2009 | 04/01/2010 | 05/15/2010 | 252300 | 0
775 | Connecticut | HARTFORD | HARTFORD | 01 | 1076124 | In the Town of Manchester, pavement preservation will be conducted along Buckland Hills Road by repaving from Buckland Street eastward to Deming Street. | Pavement Improvement | 11/05/2009 | 04/01/2010 | 06/29/2010 | 2509498 | 0
776 | Connecticut | FAIRFIELD | DANBURY (NY) | 05 | 1090103 | In the Town of New Fairfield, the park and ride lot will be repaved for an improved surface. | Pavement Improvement | 10/13/2009 | 10/13/2009 | 10/21/2009 | 220000 | 4.25
777 | Connecticut | HARTFORD | HARTFORD | 01 | 1118003 | In the Town of Rocky Hill, pavement preservation will be conducted along Old Main Street by repaving from Glastonbury Avenue extending 50 feet south of the bridge over Goff Brook | Pavement Improvement | 07/29/2009 | 08/10/2009 | 11/07/2009 | 1262839 | 0
778 | Connecticut | HARTFORD | HARTFORD | 01 | 1132104 | In the Town of South Windsor, beginning at the Manchester Town Line and extending north, approximately 4400 feet of Buckland Road will be resurfaced. | Pavement Improvement | 10/02/2009 | 10/02/2009 | 12/30/2009 | 1137602 | 0
779 | Connecticut | HARTFORD | HARTFORD | 01 | 1164106 | In the Town of Windsor, pavement preservation will be conducted by along Day Hill Road by milling and paving from Blue Hills Avenue to Great Pond Drive. This will include new drainage and curbing. | Pavement Improvement | 09/28/2009 | 10/01/2009 | 12/29/2009 | 891700 | 0
780 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 6158006 | This project will provide rehabilitation of th existing Hales Road bridge over Metro North RR in the Town of Westport. Construction will include complete replacement of the bridge superstructure and | Bridge Improvement | 08/28/2009 | 09/28/2009 | 07/28/2010 | 4192758 | 0
781 | Connecticut | NEW LONDON | NEW LONDON-NORWICH | 02 | H018012 | This project will provide for streetscape type improvements along Route 1 in the Town of Stonington from the Mystic Bridge easterly to Willow Street. The work includes new curbing, sidewalks, decorti | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 05/01/2010 | 905760 | 0.11
782 | Connecticut | LITCHFIELD |  | 01 | PEDS124 | In the City of Torrington, the Still River Greenway multi-use path will be extended 1.8 miles from Princewoods Road north to Harris Drive. | Transportation Enhancements | 07/07/2009 | 07/07/2009 | 11/11/2009 | 900000 | 0
783 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009009 | This project will remove and replace hot-mix surface, hot mix patching, and profile improvements at one location in New Castle County. | Pavement Improvement | 05/20/2009 | 05/20/2009 | 10/01/2009 | 4223809.38 | 4.94
784 | Delaware | SUSSEX |  | 00 | 2009010 | This project will remove and replace hot-mix surface, hot-mix patching, and curb ramp upgrades at two locations in Sussex County. | Pavement Improvement | 06/03/2009 | 06/08/2009 | 10/01/2009 | 1049790.94 | 3.519
785 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009011 | This project replaces the concrete median barrier on I-95 between SR 7 interchange and SR 72 overpass. | Pavement Improvement | 08/13/2009 | 08/13/2009 | 01/01/2010 | 1712689.38 | 4.89
786 | Delaware | SUSSEX, KENT |  | 00 | 2009012 | This project will improve the long-term condition of the roadway by paving and rehabilitating at various locations | Pavement Improvement | 04/24/2009 | 04/24/2009 | 06/01/2010 | 7726403.72 | 1
787 | Delaware | NEW CASTLE |  | 00 | 2009014 | This project will improve the long-term condition of the roadway by milling, hot-mix patching, and overlaying at 2 locations in New Castle County. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 11/01/2009 | 1240215.51 | 2.63
788 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009015 | This project will improve the long-term condition of the roadway by milling, hot-mix patching and overlaying at 4 locations in Wilmington. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 12/01/2009 | 3513768.31 | 1
789 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009016 | This project will improve the long-term condition of the roadway by milling, patching and overlayin at 3 locations in New Castle County. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 1289897.07 | 1
790 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009018 | This project involves the rehabilitation of interstate bridges 1-800, 1-831, 1-802, 1-809, 1-811, 1-815, 1-819N, 1-826N and 1-826S. This work includes: replacing expansion joints, joint seals, compre | Bridge Improvement | 05/04/2009 | 05/04/2009 | 04/10/2010 | 2797509.35 | 1
791 | Delaware | SUSSEX |  | 00 | 2009019 | This project involves the Boardwalk restoration - approximately 52,795 square foot section from the Henlopen Hotel to Rehoboth Avenue and the 24,300 square foot section from Laurel Street to Prospect | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 06/01/2010 | 5585854.53 | 0.05
792 | Delaware | STATEWIDE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009020 | This project involves various intersections with different scope of works, variously involving new signal installations, reconstruction of aging infrastructure, pedestrian signal enhancements, upgrade | Other | 04/21/2009 | 04/21/2009 | 08/01/2009 | 1554380.95 | 1
793 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009021 | This project will complete an over 4 mile loop recreational trail and will be a segment in an overall cross-county greenway trail system. | Transportation Enhancements | 05/18/2009 | 05/18/2009 | 11/01/2009 | 925803.47 | 0.05
794 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009022 | This project in the New Castle Industrial Track Rail Trail covers 4.75 miles of corridor running north from Delaware Street in New Castle, across Boulden Boulevard, then crossing the the Christina Riv | Transportation Enhancements | 08/31/2009 | 08/31/2009 | 12/01/2009 | 996274.64 | 0.51
795 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009023 | This project includes miscellaneous work at Bridge 1-701, 703, 703A, 704 and 705. Work includes the replacement of bearings, expansion joints, painting of structural steel, repair of spalled concrete | Other | 05/04/2009 | 05/04/2009 | 12/01/2010 | 134734.73 | 1
796 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009024 | This project involves the rehabilwork at Bridge 1-792 and 829. Work includes the replacement of bearings, expansion joints, painting of structural steel, repair of spalled concrete and replacement of | Other | 04/28/2009 | 04/28/2009 | 12/01/2010 | 176065.92 | 1
797 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009025 | This project involves the rehabilitation of interstate bridges 1-804, 1-805, 1-810, 1-811 and 1-812. This work includes cleaning and painting the steel beams,diaphragms and bearings. | Bridge Improvement | 05/08/2009 | 05/08/2009 | 04/01/2010 | 2353419.3 | 1
798 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009026 | This streetscape improvement project is along Old Lancaster Pike from Valley Road to Errickson Drive. Improvements include; new sidewalks, upgrades to curb ramps, drainage modifications, decrotive cro | Transportation Enhancements | 05/07/2009 | 05/07/2009 | 12/01/2010 | 2880690.94 | 0.38
799 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009027 | This streetscape improvement project is along Old Lancaster Pike from Valley Road to Errickson Drive. Improvements include; new sidewalks, upgrades to curb ramps, drainage modifications, decrotive cro | Transportation Enhancements | 09/29/2009 | 09/29/2009 | 09/04/2010 | 1976610.33 | 0.65
800 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009028 | This project will replace non-standard guardrail, guardrail components and end treatments as required for all state-maintained roads in New Castle County. | Safety/Traffic Management | 10/21/2009 | 10/21/2009 | 08/30/2012 | 630798.38 | 1
801 | Delaware | STATEWIDE |  | 00 | 2009029 | This project will repaint existing pavement markings statewide. | Safety/Traffic Management | 08/31/2009 | 08/31/2009 | 06/01/2010 | 1190717.54 | 107.41
802 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009030 | This project involves the rehabilitation of interstate bridges 1-676, 1- 717, 1-719, 1-720, 1-738, 1-739 and 1-740. Work includes the replacement of bearings, expansion seal and/or joints, painting of | Bridge Improvement | 05/04/2009 | 05/04/2009 | 09/01/2010 | 4956394.73 | 1
803 | Delaware | KENT | DOVER | 00 | 2009031 | This project will build the first phase of a DART Dover Transit Center on five acres on Water Street between Queen and West Streets. | Other | 12/08/2009 | 12/08/2009 | 03/08/2011 | 3602365 | 0.11
804 | Delaware | KENT | DOVER | 00 | K356011 | This project improves saftey by channelizing the median at the intersection of SR 10 and Sorghum Mill Road to accommodate eastbound and westbound SR 10 left-turns. | Safety/Traffic Management | 06/17/2009 | 07/20/2009 | 11/01/2009 | 275339.17 | 0.15
805 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | N056038 | This project entails constructing two highway speed EZ Pass Lanes in both the Northbound and Southbound directions of the Newark Toll Plaza located on I-95 near the DE/MD State Line. | Other | 04/17/2009 | 04/17/2009 | 12/01/2011 | 3000000 | 2.6
806 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | N059036 | This project will mill and resurface southbound I-95 from the Wilmington Viaduct to just south of the SR 141 interchange. | Pavement Improvement | 04/24/2009 | 04/24/2009 | 12/01/2009 | 2670441.6 | 2.83
807 | Delaware | NEW CASTLE |  | 00 | N438002 | This project will expand the park & ride on along SR 299, west of SR 1. | Other | 06/05/2009 | 06/05/2009 | 01/01/2010 | 932672.49 | 0.29
808 | Delaware | SUSSEX |  | 00 | S020003 | This project will involve hot-mix patching and 3 1/2" overlay at one location in Sussex County. | Pavement Improvement | 07/08/2009 | 07/20/2009 | 10/01/2009 | 1625878.26 | 5.09
809 | Delaware | SUSSEX |  | 00 | S584003 | This project improves the railroad crossing at SR 404 and Newton Road by installing automatic gates, updating the cantilever lights and controller, and replace pre-cast concrete surface. | Other | 06/08/2009 |  | 04/01/2010 | 362333.6 | 1
810 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 1108027 | REPLACEMENT OF THE NEW YORK AVENUE BRIDGE WHICH CROSSES OVER METRO, AMTRACK AND CSX RAILROAD TRACKS | Bridge Improvement | 09/22/2009 |  |  | 36623004.7 | 0.1
811 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 1300015 | CONSTRUCTION WILL INCLUDE SIDEWALK, CURB AND GUTTER, PAVING T, NEW STREETLIGHTS, TRAFFIC SIGNALS, SAFETY IMPROVEMENTS AND LANDSCAPING ALONG PENNSYLVANIA AVENUE FROM THE SOUSA BRIDGE TO SOUTHERN AVENUE | Pavement Improvement | 11/18/2009 |  |  | 18392820.99 | 1.4
812 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 3000050 | THIS PROJECT IS MAINLY TO REPAVE THE ROADWAY; ALSO MINOR IMPROVEMENTS WILL BE DONE ALONG VARIOUS ROADWAYS WITHIN THE HISTORIC DUPONT CIRCLE BUSINESS DISTRICT | Pavement Improvement | 11/12/2009 |  |  | 5383959.4 | 0.48
813 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 3105006 | RECONSTRUCT/RESURFACE ROADWAY, SIDEWALK, CURB, GUTTER AND WHEELCHAIR RAMPS. UPGRADE STREETLIGHT AND TRAFFIC SIGNALS. REPLACE WATER MAIN AND LANDSCAPING .ALONG 18TH STREET, FROM FLORIDA AVENUE TO MASSA | Pavement Improvement | 11/15/2009 |  |  | 5526764.7 | 0.53
814 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 3207003 | REPLACEMENT OF THE EASTERN AVENUE BRIDGE THAT CROSSES OVER KENNILWORTH AVENUE | Bridge Improvement | 11/13/2009 |  |  | 4499569.75 | 0.1
815 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 3207004 | REPLACEMENT OF THE EASTERN AVENUE BRIDGE THAT CROSSES OVER KENNILWORTH AVENUE | Pavement Improvement | 11/13/2009 |  |  | 5162691 | 0.1
816 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888323 | THE WORK WILL INCLUDE UPGRADING OF STREETLIGHTS, WHEELCHAIR RAMPS, PLANTING TREES AS WELL AS REPAIRING SIDEWALKS AND GUTTERS AND AND REPAVING THE ROADWAY. THIS WORK WILL OCCUR ALONG 25 BLOCKS OF TH | Safety/Traffic Management | 08/10/2009 | 09/17/2009 |  | 8330809.13 | 1.36
817 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888327 | INSTALL BATTERY BACKUP POWER SUPPLY FOR CRITICAL TRAFFIC LIGHTS THROUGHOUT THE CITY TO PROVIDE UP TO 8 HOURS OF POWER. | Safety/Traffic Management | 01/01/2010 |  |  | 1751131.58 | 0
818 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888328 | REPAVING OF SECTIONS OF THE INTERSTATE HIGHWAY IN DC | Pavement Improvement | 04/24/2009 | 04/24/2009 |  | 1000000 | 14.14
819 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888329 | IMPROVE STREETLIGHTS ALONG THE DALECARLIA PARKWAY AND BLADENSBURG ROAD | Safety/Traffic Management | 04/24/2009 | 04/24/2009 |  | 4845806.11 | 12.64
820 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888332 | IMPROVE PEDESTRIAN FACILITIES THAT SERVICE NEIGHBORHOOD SCHOOLS | Transportation Enhancements | 01/07/2010 | 01/07/2010 |  | 2593767.6 | 0
821 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA001 | "This Okaloosa County project will improve safety at the existing intersection of State Road 85 South and State Road 123, near the Northwest Florida Regional airport, by providing a flyover ramp for m | Pavement Widening | 12/05/2000 | 07/01/2009 |  | 29568927 | 1.241
822 | Florida | SANTA ROSA | PENSACOLA | 01 | ARRA002 | This Santa Rosa County project will widen the existing two-lane roadway to four with bike lanes and sidewalks to improve safety and relieve congestion. | Pavement Widening | 07/20/2009 | 07/20/2009 |  | 6926150 | 0.984
823 | Florida | BAY | PANAMA CITY | 02 | ARRA004 | Bay County is building a new bridge over Grand Lagoon for vehicles and pedestrians to improve safety and relieve congestion on Thomas Drive in Panama City Beach. | Bridge Improvement | 09/28/2009 | 09/28/2009 |  | 13502328 | 0.822
824 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA005 | Barrier walls and culverts will be installed on this Leon County safety improvement project to allow wildlife to pass under the road and improve driver safety along this roadway. | Transportation Enhancements | 08/18/2009 | 08/18/2009 |  | 3281480 | 1.074
825 | Florida | FRANKLIN |  | 02 | ARRA006 | "Franklin County will construct approximately 2,500 feet of five-foot wide sidewalk along Bluff Road in Apalachicola to improve pedestrian safety." | Transportation Enhancements | 11/16/2009 |  |  | 171522 | 0.737
826 | Florida | MARTIN | FORT PIERCE-STUART | 16,23 | ARRA010 | FDOT will build a new high level bridge over the south fork of the St. Lucie River and the Okeechobee Waterway between Palm City and Stuart to ease congestion and provide faster evacuation from the co | New Bridge Construction | 10/14/2009 |  |  | 72288911 | 1.42
827 | Florida | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17,19,20,21,22,23 | ARRA013 | The City of Deerfield Beach will improve access to the west entrance of the Deerfield Beach train station that serves Tri-Rail (commuter) and Amtrak customers by building a sidewalk and a pedestrian p | Transportation Enhancements | 12/14/2009 |  |  | 359765 | 0
828 | Florida | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17,19,20,21,22,23 | ARRA014 | "The City of Pembroke Pines will build new sidewalks at several locations along Pembroke Road and 196th Avenue to provide pedestrian access between major roads, subdivisions , schools, shops and to pr | Transportation Enhancements | 12/07/2009 |  |  | 526915 | 0.986
829 | Florida | INDIAN RIVER | VERO BEACH | 15 | ARRA018 | Indian River County will plant additional landscaping to enhance the median of 58th Avenue for 3.05 miles from Oslo Road to 16th Avenue in southern Indian River County. | Transportation Enhancements | 12/15/2009 | 12/21/2009 |  | 277648 | 3.05
830 | Florida | ST LUCIE | FORT PIERCE-STUART | 16,23 | ARRA020 | The City of Port St. Lucie will add 0.6 miles of sidewalk to improve pedestrian safety on the east side of California Boulevard from Heatherwood Boulevard to Fairway Isles. | Transportation Enhancements | 12/29/2009 |  |  | 73189 | 0.611
831 | Florida | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16,19,22,23 | ARRA031 | "FDOT will build a new four-lane bridge between Hillsboro Boulevard/ State Road 810 in Deerfield Beach (Broward County) and S.W. 18th Street in Boca Raton (Palm Beach County), crossing over local stre | Pavement Widening | 10/29/2009 | 11/19/2009 |  | 2574095 | 0.234
832 | Florida | MARTIN | FORT PIERCE-STUART | 16,23 | ARRA034 | Martin County is replacing the deteriorating pavement on one mile of Baker Road from U.S. 1 to Savannah Road in northeastern Martin County. | Pavement Improvement | 10/12/2009 | 10/12/2009 |  | 250000 | 1.011
833 | Florida | MARTIN | FORT PIERCE-STUART | 16,23 | ARRA035 | Martin County will improve nine miles of County Road 609 from State Road 710 north of Indiantown north to County Road 714 by replacing aging pavement. | Pavement Improvement | 11/30/2009 | 11/30/2009 |  | 2100000 | 9
834 | Florida | INDIAN RIVER | VERO BEACH | 15 | ARRA036 | FDOT will resurface County Road 507 from the Fellsmere city limits north 3.09 miles to the Indian River/Brevard County line to extend the life of the road. | Pavement Improvement | 11/23/2009 | 11/23/2009 |  | 651192 | 3.094
835 | Florida | PASCO |  | 05,09 | ARRA037 | "In Pasco County, this project widens 2.8 miles of U.S. 41 from the existing two lanes to a four-lane divided road with medians and turn lanes to reduce congestion." | Pavement Widening | 07/01/2009 | 07/15/2009 |  | 14652500 | 2.841
836 | Florida | ALACHUA |  | 03,06 | ARRA038 | "In the City of Alachua, in northern Alachua County, a sidewalk and bike lane will be built along Northwest County Road 235A from U.S. 441 to Santa Fe High School which will improve the safety of stud | Transportation Enhancements | 08/20/2009 | 08/20/2009 |  | 69218 | 1
837 | Florida | ALACHUA |  | 03,06 | ARRA039 | "In Alachua County, a concrete sidewalk will be built along the north side of Southwest Eighth Avenue between Southwest 75th Street (Tower Road) and end of the road which will provide a safer place fo | Transportation Enhancements | 08/20/2009 | 08/20/2009 |  | 92087 | 1
838 | Florida | LEVY |  | 05,06 | ARRA040 | "In Levy County, bike lanes will be built along both sides of State Road 320 from Manatee Springs State Park to U.S. 19 to improve recreational options for campers at the state park as well as provide | Transportation Enhancements | 08/20/2009 | 08/20/2009 |  | 1615626 | 5.784
839 | Florida | PUTNAM |  | 03,07 | ARRA041 | "In Bradford County, a 12-foot wide, 4-mile long multi-use trail will be built along the old abandoned railroad line along State Road 100 from the Clay County line to County Road 315 to provide recrea | Transportation Enhancements | 10/12/2009 | 10/12/2009 |  | 1165046 | 4.366
840 | Florida | ALACHUA | GAINESVILLE | 03,06 | ARRA042 | "In Gainesville, an off-road bicycle path will be built on the abandoned railroad property alongside West Sixth Street from Southeast Second Avenue to Northwest 16th Avenue for recreation and those wh | Transportation Enhancements | 08/04/2009 | 08/04/2009 |  | 1000000 | 0
841 | Florida | ALACHUA | GAINESVILLE | 03,06 | ARRA043 | "In Gainesville, Northeast Eighth Avenue will be repaved between North Main Street (State Road 329) and Northeast Boulevard to improve the road surface." | Pavement Improvement | 08/04/2009 | 08/04/2009 |  | 113575 | 0.311
842 | Florida | ALACHUA |  | 03,06 | ARRA045 | "To promote economic development in the western area of Alachua County, a southbound turn lane will be added to U.S. 41 just south of Newberry onto Southwest 30th Avenue." | Safety/Traffic Management | 08/20/2009 | 08/20/2009 |  | 439124 | 0.001
843 | Florida | ALACHUA | GAINESVILLE | 03,06 | ARRA046 | "In Gainesville, North Main Street (County Road 329) will be reconstructed from four to two lanes with a center turn between Northwest Eighth and 16th avenues which will increase safety. It will also | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 951007 | 1.681
844 | Florida | STATEWIDE |  | 17,18,20,21,25 | ARRA047 | "Cash toll collections will be replaced with all-electronic tolling on a 21-mile segment of Florida?s Turnpike located between State Road 836 in Miami and County Line Road in Miramar.? The project wil | Pavement Improvement | 09/30/2009 | 09/30/2009 |  | 22000000 | 12
845 | Florida | ALACHUA |  | 03,06 | ARRA048 | Southwest 122nd Street in Alachua County will be resurfaced and a five-foot paved shoulder added south of Archer Road (State Road 24) to Southwest 89th Avenue which will improve safety. | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 393385 | 0.343
846 | Florida | BAKER |  | 04 | ARRA049 | "In Glen St. Mary, County Road 125 will be resurfaced from U.S. 90 to Glen Haven Lane and the culverts will be upgraded to make the roadway a safer route to drive." | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 596688 | 1.556
847 | Florida | BRADFORD |  | 06 | ARRA050 | "In Bradford County, Northwest County Road 229 between State Road 16 and Northwest 55th Avenue will be repaved to improve the road surface." | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 704488 | 2
848 | Florida | CLAY |  | 03,06 | ARRA051 | "In St. Johns County, County Road 214 will be resurfaced between State Road 100 and County Road 315C to improve the ride." | Pavement Improvement | 08/07/2009 | 08/07/2009 |  | 1466596 | 6.584
849 | Florida | COLUMBIA |  | 04 | ARRA052 | "In western Columbia County, County Road 250 (Lake Jeffery Road) will be widened from 10 to 12-foot lanes and resurfaced from Interstate 75 to the Suwannee County line to improve the road surface." | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 1134339 | 2.9
850 | Florida | COLUMBIA |  | 04 | ARRA053 | "In Lake City, County Road 129 (Northwest Lake Jeffery Road) will be resurfaced between U.S. 90 and the CSX Railroad and a crosswalk added at Parkview Baptist Church to provide additional safety on a | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 394801 | 0.664
851 | Florida | DIXIE |  | 02 | ARRA054 | "In Cross City, the intersection of U.S. 19 (State Road 55) and County Road 351A will be improved by widening the intersection to allow log trucks and larger vehicles to safely turn. The road also wil | Safety/Traffic Management | 08/20/2009 | 08/20/2009 |  | 415337 | 0.1
852 | Florida | MADISON |  | 04 | ARRA055 | "In Madison County, County Road 53 between Interstate 10 and Southeast Roger Sink Road will be resurfaced to improve the ride." | Pavement Improvement | 08/04/2009 | 08/04/2009 | 10/13/2009 | 867199 | 1.899
853 | Florida | PUTNAM |  | 03,07 | ARRA056 | St. Johns Avenue will be resurfaced between State Road 19 and Palm Avenue which will improve the roadway for traffic headed toward downtown Palatka. | Pavement Improvement | 08/04/2009 | 08/04/2009 |  | 285439 | 1.176
854 | Florida | PUTNAM |  | 03,07 | ARRA058 | "In Pomona Park in southern Putnam County, a new concrete sidewalk will be built between U.S. 17 and Cisco Road to provide a safer path for pedestrians." | Transportation Enhancements | 08/04/2009 | 08/04/2009 | 11/30/2009 | 136772 | 3.835
855 | Florida | PUTNAM |  | 03,07 | ARRA059 | "In Putnam County, two culverts will be replaced on Silver Lake Drive over Devall Branch and Two Mile Creek with new concrete culverts to improve the drainage in the area." | Pavement Improvement | 08/04/2009 | 08/04/2009 |  | 453008 | 3.44
856 | Florida | PUTNAM |  | 03,07 | ARRA060 | "In western Putnam County, a concrete sidewalk and asphalt bike path will be built along a section of County Road 315 to improve safety for pedestrians and bicyclists." | Transportation Enhancements | 08/04/2009 | 08/04/2009 |  | 333013 | 2.082
857 | Florida | SUWANNEE |  | 02 | ARRA061 | "A two mile section of County Road 252 in eastern Suwannee County, between the Columbia County line and County Road 137, will be widened from 10 to 12-foot lanes and repaved to improve the road surfac | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 854162 | 1.915
858 | Florida | ST JOHNS |  | 07 | ARRA062 | "In St. Johns County, West King Street (County Road 214) between County Road 13 and 13A will have several culverts or pipes replaced and extended to help with drainage issues." | Pavement Improvement | 11/23/2009 | 11/23/2009 |  | 342033 | 3.946
859 | Florida | ST JOHNS |  | 07 | ARRA063 | "In St. Johns County, West King Street (County 214) will be widened to improve safety and the road resurfaced between County 13 and 13A to improve the ride." | Pavement Improvement | 11/23/2009 | 11/23/2009 |  | 729621 | 7.891
860 | Florida | GILCHRIST |  | 06 | ARRA064 | "In Gilchrist County, County Road 341 will be repaved between State Road 26 and the Levy County line to improve the road surface." | Pavement Improvement | 08/04/2009 | 08/04/2009 | 10/30/2009 | 267983 | 1.482
861 | Florida | HAMILTON |  | 04 | ARRA065 | "In Hamilton County, County Road 135 between White Springs and Southeast 177th Court will be repaved to improve the road surface.." | Pavement Improvement | 08/04/2009 | 08/04/2009 | 10/30/2009 | 804796 | 2.9
862 | Florida | LAFAYETTE |  | 02 | ARRA066 | "In Lafayette County, County Road 354 from U.S. 27 to County Road 361 will be repaved to improve the road surface." | Pavement Improvement | 08/04/2009 | 08/04/2009 | 10/14/2009 | 504250 | 2.707
863 | Florida | LEVY |  | 05,06 | ARRA067 | "In Levy County, County Road 40 will be repaved between Park Street in Inglis and the Marion County line to improve the road surface and make it safer." | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 800053 | 7.413
864 | Florida | NASSAU |  | 04 | ARRA068 | "In Nassau County, County Road 2 will be resurfaced between County Road 121 and the Georgia line and the Agricultural Inspection Station ramps will be repaved to improve safety for motorists." | Pavement Improvement | 08/20/2009 | 08/20/2009 | 11/13/2009 | 338015 | 1.381
865 | Florida | PUTNAM |  | 03,07 | ARRA069 | "In Crescent City in southern Putnam County, a new concrete sidewalk will be built along East Grand Rondo from Central Street to County Road 308 to provide a safer route for pedestrians." | Transportation Enhancements | 08/04/2009 | 08/04/2009 | 11/30/2009 | 91669 | 0.1
866 | Florida | TAYLOR |  | 02 | ARRA070 | "In Taylor County, County Road 14 will be resurfaced between U.S. 221 in Shady Grove and the Madison County line to provide a safer road." | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 996525 | 3.063
867 | Florida | UNION |  | 04 | ARRA071 | County Road 231 in Union County will be resurfaced between the Department of Corrections Reception and Medical Center and the Bradford County line to improve the ride. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 09/17/2009 | 463222 | 1.009
868 | Florida | CLAY | JACKSONVILLE | 03,06 | ARRA072 | "In Clay County, Peoria Road (County Road 224A) will be widened to provide a center turn lane from College Drive (County Road 224) to Moody Road to improve traffic flow. An intersection improvement wi | Safety/Traffic Management | 08/04/2009 | 08/04/2009 |  | 829429 | 0.241
869 | Florida | CLAY | JACKSONVILLE | 03,06 | ARRA073 | "In Orange Park, an additional right turn lane will be added to Kingsley Avenue at U.S. 17 to increase the amount of traffic that can turn onto U.S. 17." | Safety/Traffic Management | 08/07/2009 | 08/07/2009 |  | 390148 | 0.001
870 | Florida | CLAY | JACKSONVILLE | 03,06 | ARRA074 | Four lanes on Knight Boxx Road (County Road 220B) in Orange Park in Clay County will be resurfaced from Blanding Boulevard (State Road 21) to County Road 220 to provide a safer ride. | Pavement Improvement | 08/07/2009 | 08/07/2009 |  | 479970 | 1.206
871 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA075 | "In Jacksonville, for Alta Drive and New Berlin Road, the existing pavement will be resurfaced and paved shoulders added to improve the road surface between Zoo Parkway (State Road 105) and State Road | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 4240787 | 2.012
872 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA076 | Ninth Street in Jacksonville Beach will be improved by repairing the existing drainage system and resurfacing between Osceola Avenue and First Street. | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 4177278 | 1.5
873 | Florida | NASSAU | JACKSONVILLE | 04 | ARRA077 | "In Fernandina Beach, North 14th Street will be resurfaced between Atlantic Avenue and Pogy Place. The bridge railing will be replaced at Egans Creek Bridge to make the crossing safer for motorists, p | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 520379 | 1.76
874 | Florida | NASSAU | JACKSONVILLE | 04 | ARRA078 | North Eighth Street in Fernandina Beach between Dade Street and the Port of Fernandina will be repaved to improve the road surface. | Pavement Improvement | 08/20/2009 | 08/20/2009 |  | 68619 | 0.464
875 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA079 | "In St. Augustine, West King Street or County Road 214 will be resurfaced between County Road 13 and Palmer Avenue to provide a safer road." | Pavement Improvement | 11/23/2009 | 11/23/2009 |  | 1505182 | 14.979
876 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA080 | "To improve capacity and safety at the Interstate 95/State Road 207 interchange in St. Johns County, the northbound and southbound ramps will be widened and a turn lane will be added for westbound tra | Safety/Traffic Management | 07/22/2009 | 07/22/2009 |  | 628914 | 0.001
877 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA081 | "In St. Augustine, concrete sidewalks will be provided along Del Monte, Varella and Durbin Creek Boulevard to increase safety for pedestrians." | Transportation Enhancements | 08/20/2009 | 08/20/2009 |  | 396926 | 5.968
878 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA082 | "North of St. Augustine, a new traffic signal system along County Road 210 and Racetrack Road between U.S. 1 and County Road 16A will improve traffic flow along county roads." | Safety/Traffic Management | 08/20/2009 | 08/20/2009 |  | 313387 | 16.16
879 | Florida | CITRUS |  | 05 | ARRA083 | "In Citrus County, a new multi-use path is being built along U.S. 19 in Crystal River between NW 19th Street and W. State Park Street to provide an area for both bicyclists and pedestrians to travel s | Transportation Enhancements | 09/04/2009 | 09/14/2009 | 11/30/2009 | 170000 | 0.477
880 | Florida | CITRUS |  | 05 | ARRA084 | "In Citrus County, this project repaves 2.4 miles of Fort Island Trail from North Palm Springs Terrace to U.S. 19/Suncoast Boulevard to improve the road surface." | Pavement Improvement | 11/09/2009 | 12/14/2009 |  | 328560 | 1.461
881 | Florida | CITRUS |  | 05 | ARRA085 | "In Citrus County, this project repaves 1.5 miles of Ozello Trail from U.S. 19 to Winterset Avenue to improve the road surface." | Pavement Improvement | 11/09/2009 | 11/30/2009 |  | 180711 | 1.455
882 | Florida | CITRUS |  | 05 | ARRA086 | "In Citrus County, to enhance the ride ability of the roadway, this project resurfaces 2.7 miles of Croft Ave. from State Road 44 to north of Harley Street." | Pavement Improvement | 11/09/2009 | 11/11/2009 |  | 388134 | 2.726
883 | Florida | CITRUS |  | 05 | ARRA087 | "In Citrus County, this project repaves one mile of Turner Camp Road from Ella Avenue to Twin Lakes Drive to improve the road surface." | Pavement Improvement | 11/12/2009 | 11/18/2009 |  | 149100 | 1.53
884 | Florida | CITRUS |  | 05 | ARRA088 | "In Citrus County, this project repaves six miles of Cardinal Street from U.S. 19 to County Road 491 (Lecanto Highway) to improve the road surface." | Pavement Improvement | 11/09/2009 |  |  | 709410 | 6.151
885 | Florida | CITRUS |  | 05 | ARRA089 | "In Citrus County, this project resurfaces 2.5 miles of County Road 491 from State Road 44 to County Road 486 due to the poor condition of the road." | Pavement Improvement | 11/09/2009 | 11/22/2009 |  | 503100 | 2.515
886 | Florida | CITRUS |  | 05 | ARRA091 | "In Citrus County, due to the poor condition of the road, this project resurfaces 6.8 miles of County Road 491 from Pine Ridge Boulevard to State Road 200." | Pavement Improvement | 11/09/2009 |  |  | 777534 | 7.018
887 | Florida | CITRUS |  | 05 | ARRA094 | "In Citrus County, this project repaves 5.6 miles of County Road 480 (Stagecoach Road) from County Road 491 (Lecanto Highway) to County Road 581 (Pleasant Grove Road) to improve the road surface." | Pavement Improvement | 11/09/2009 | 11/10/2009 |  | 1042656 | 5.722
888 | Florida | CITRUS |  | 05 | ARRA095 | "In Citrus County, this project adds a new traffic signal and a right turn lane on State Road 44 at the Citrus County Landfill to ease access and minimize backups at the entrance to the landfill." | Pavement Improvement | 09/15/2009 |  |  | 579953 | 0.577
889 | Florida | CITRUS |  | 05 | ARRA096 | "In Citrus County, this project repaves 2.4 miles of Grover Cleveland Boulevard from Tedna Terrace to County Road 491 to improve the road surface." | Pavement Improvement | 11/09/2009 | 12/17/2009 |  | 259860 | 2.403
890 | Florida | CITRUS |  | 05 | ARRA097 | "In Citrus County, this project repaves 1.6 miles of Halls River Road from the Halls River Bridge to Fishbowl Drive to improve the road surface." | Pavement Improvement | 11/09/2009 | 12/14/2009 |  | 121292 | 1.067
891 | Florida | HERNANDO |  | 05 | ARRA099 | "In eastern Hernando County, this project resurfaces 1.8 miles of Cortez Blvd (State Road 50) between U.S. 98 and the railroad tracks to the east to provide a safer ride." | Pavement Improvement | 08/05/2009 | 08/31/2009 | 11/09/2009 | 737444 | 1.844
892 | Florida | INDIAN RIVER | VERO BEACH | 15 | ARRA100 | FDOT will resurface 3.5 miles of 20th Avenue from Oslo Road to State Road 60 in Vero Beach to extend the life of the road. | Pavement Improvement | 12/12/2009 |  |  | 2276803 | 5.583
893 | Florida | HERNANDO |  | 05 | ARRA101 | "In Hernando County, this project repaves 2.2 miles of Mariner Boulevard from Maderia Street to Augustine Road to improve the road surface." | Pavement Improvement | 11/12/2009 |  |  | 814015 | 2.204
894 | Florida | HERNANDO |  | 05 | ARRA102 | "In Hernando County, this project repaves 0.6 miles of Spring Hill Drive from Pinehurst Drive to Deltona Boulevard to improve the road surface." | Pavement Improvement | 10/05/2009 | 10/08/2009 | 12/07/2009 | 281586 | 0.657
895 | Florida | HERNANDO |  | 05 | ARRA103 | "In Hernando County, this project repaves 1.5 miles of Deltona Boulevard from State Road 50 to Northcliffe Boulevard to improve the road surface." | Pavement Improvement | 10/15/2009 | 10/15/2009 | 12/04/2009 | 251664 | 1.489
896 | Florida | HERNANDO |  | 05 | ARRA105 | "In Hernando County, this project repaves 2.8 miles of Spring Hill Drive from Mariner Boulevard to Deltona Boulevard to improve the road surface." | Pavement Improvement | 11/12/2009 | 11/30/2009 |  | 893110 | 3.038
897 | Florida | HERNANDO |  | 05 | ARRA106 | "In Hernando County, due to the poor condition of the road, this project replaces 2.1 miles of the asphalt surface on Burwell Rd. (County Road 575) and widens the 10-foot lanes to 12-foot lanes from S | Pavement Improvement | 10/22/2009 | 10/22/2009 | 11/16/2009 | 279563 | 2.049
898 | Florida | HERNANDO |  | 05 | ARRA107 | "In Hernando County, due to the poor condition of the road, this project resurfaces 3.8 miles of Citrus Way and widens the 11-foot lanes to 12-foot lanes from Ft. Dade Avenue to south of Centralia Roa | Pavement Improvement | 11/12/2009 |  |  | 762757 | 3.826
899 | Florida | HERNANDO |  | 05 | ARRA108 | "In Hernando County, this project repaves 1.4 miles of Yontz Road from U.S. 98 to Howell Avenue to improve the road surface." | Pavement Improvement | 11/12/2009 | 12/15/2009 |  | 276140 | 1.433
900 | Florida | HERNANDO |  | 05 | ARRA109 | "In Hernando County, this project repaves one mile of North Avenue from Howell Avenue to Ponce de Leon Boulevard to improve the road surface." | Pavement Improvement | 11/12/2009 |  |  | 241465 | 0.743
901 | Florida | HERNANDO |  | 05 | ARRA110 | "In Hernando County, 20 miles of the asphalt surface of the Suncoast Trail is being replaced due to the poor condition of the trail." | Transportation Enhancements | 08/31/2009 | 09/21/2009 |  | 759000 | 0
902 | Florida | HILLSBOROUGH | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,11,12 | ARRA113 | "In Hillsborough County, this project will add new lighting, landscaping and brick sidewalks for safety purposes on 56th Street from Temple Heights Road to east of 98th Avenue." | Transportation Enhancements | 10/19/2009 | 11/23/2009 |  | 348298 | 0.146
903 | Florida | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,10,11 | ARRA129 | "In Pinellas County, this project converts the existing southbound lane of East Avenue to a trail for pedestrians and bicyclists to travel safely between Drew Street and Turner Street." | Transportation Enhancements | 10/19/2009 | 10/19/2009 |  | 313596 | 0.001
904 | Florida | ST LUCIE | FORT PIERCE-STUART | 16,23 | ARRA135 | "FDOT is widening 4.35 miles of State Road 70 in western St. Lucie County to a four-lane, divided highway and adding shoulders for safety on this major cross-state business and evacuation route." | Pavement Widening | 07/27/2009 | 09/08/2009 |  | 15734857 | 4.356
905 | Florida | BROWARD | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,19,20,21,22,23 | ARRA136 | "FDOT will build a new four-lane bridge between Hillsboro Boulevard/ State Road 810 in Deerfield Beach (Broward County) and S.W. 18th Street in Boca Raton (Palm Beach County), crossing over local stre | Pavement Widening | 10/29/2009 | 11/19/2009 |  | 38349338 | 0.46
906 | Florida | GULF |  | 02 | ARRA137 | This pedestrian safety project includes sidewalk and landscape improvements in the City of Port St. Joe in Gulf County. | Transportation Enhancements | 10/23/2009 | 11/09/2009 |  | 343118 | 0.297
907 | Florida | HOLMES |  | 01 | ARRA138 | This project will repair the existing sidewalk and construct additional sidewalk near Bonifay Middle School to improve pedestrian safety in Holmes County. | Transportation Enhancements | 07/29/2009 | 07/29/2009 | 11/20/2009 | 89882 | 0.239
908 | Florida | WASHINGTON |  | 01 | ARRA139 | The City of Chipley will construct approximately 900 feet of five-foot wide sidewalk along State Road 77 to improve pedestrian safety in Washington County. | Transportation Enhancements | 10/06/2009 | 11/30/2009 |  | 80000 | 0.172
909 | Florida | GADSDEN |  | 02 | ARRA140 | Five-foot wide sidewalks along various streets within the city limits of Midway will be constructed to improve pedestrian safety in Gadsden County. | Transportation Enhancements | 08/18/2009 | 08/18/2009 |  | 465033 | 1.35
910 | Florida | GADSDEN | TALLAHASSEE | 02 | ARRA141 | A five-foot wide sidewalk along State Road 267 in the City of Quincy has been constructed to improve pedestrian safety in Gadsden County. | Transportation Enhancements | 08/18/2009 | 08/18/2009 | 11/02/2009 | 79110 | 0.272
911 | Florida | FRANKLIN |  | 02 | ARRA142 | "Franklin County will construct approximately 1,600 feet of five-foot wide sidewalk along Franklin Boulevard to improve pedestrian safety." | Transportation Enhancements | 11/03/2009 |  |  | 133057 | 0.139
912 | Florida | JACKSON |  | 02 | ARRA143 | Jackson County will construct a five-foot wide sidewalk along Riverforest Road to improve pedestrian safety. | Transportation Enhancements | 10/15/2009 |  |  | 85755 | 0.538
913 | Florida | COLLIER | NAPLES | 14,25 | ARRA144 | Build a second two-lane bridge next to the existing Jolley Bridge to give drivers a four-lane bridge that connects Marco Island to U.S. 41 and reduces congestion during heavy travel times. | New Bridge Construction | 09/10/2009 | 09/21/2009 |  | 27657755 | 0.783
914 | Florida | POLK | LAKELAND | 05,12,15 | ARRA145 | Construct a new two-lane road to provide a direct connection between State Road 33 and the Pace Road Interchange at the Polk Parkway for easy access to the new University of South Florida Polytechnic | New Construction | 12/29/2009 |  |  | 37049661 | 0
915 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA147 | "Construct Metro Extension (State Road 739), a new six-lane road that connects U.S. 41 and Six Mile Cypress Parkway in Lee County and relieves heavy traffic on U.S. 41. It will also serve as an altern | New Construction | 04/29/2009 | 07/25/2009 |  | 34333780 | 2.772
916 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA148 | Widen U.S. 301 in Sarasota from four to six lanes to relieve roadway congestion. Improvements to drainage and sidewalks will also enhance safety in the area. | Pavement Widening | 09/02/2009 | 09/16/2009 |  | 9709352 | 2.007
917 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA149 | Install communications devices at 88 intersections throughout Manatee County and connect them to the Manatee Traffic Management Center to improve traffic congestion and emergency response times. | Safety/Traffic Management | 09/30/2009 | 10/13/2009 |  | 6106640 | 0
918 | Florida | CHARLOTTE |  | 13,14,16 | ARRA151 | "Replace the old Cape Haze Drive bridge over Amberjack Cove Waterway in Charlotte County with a new bridge with wider lanes, shoulders and sidewalks." | Pavement Improvement | 09/09/2009 | 11/02/2009 |  | 1067407 | 0.073
919 | Florida | CHARLOTTE |  | 13,14,16 | ARRA152 | "Construct intersection improvements at State Road 776/Coliseum Boulevard in Charlotte County, including new turn lanes and traffic signals to move traffic more efficiently through this area." | Pavement Improvement | 09/29/2009 | 09/29/2009 |  | 549480 | 0.207
920 | Florida | CHARLOTTE |  | 13,14,16 | ARRA153 | Add two new right turn lanes on Veterans Boulevard to improve traffic flow at the Murdock Circle intersection in Charlotte County. | Pavement Improvement | 09/29/2009 | 09/29/2009 |  | 230509 | 0.01
921 | Florida | CHARLOTTE |  | 13,14,16 | ARRA154 | Lengthen the left turn lane on State Road 776 at the Oriole Boulevard intersection to improve traffic movement through the intersection in Charlotte County. | Pavement Improvement | 09/29/2009 | 09/29/2009 |  | 99882 | 0.172
922 | Florida | DE SOTO |  | 13 | ARRA155 | Pave five miles of County Road 760 from County Road 769 to U.S. 17 in Desoto County to improve the road surface. | Pavement Improvement | 09/16/2009 | 10/24/2009 |  | 1436442 | 3.17
923 | Florida | GLADES |  | 16 | ARRA156 | Pave County Road 720 in Glades County from the Hendry County line to five miles west to improve the road surface. | Pavement Improvement | 09/15/2009 | 11/25/2009 |  | 2301359 | 5
924 | Florida | HARDEE |  | 13 | ARRA157 | Resurface Main Street (County Road 664) in the city of Bowling Green from Doc Coil Road to east of U.S.17 to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 09/21/2009 | 10/24/2009 |  | 743793 | 3.5
925 | Florida | HENDRY |  | 16,23 | ARRA158 | Pave County Road 832 in Hendry County from State Road 29 to nine miles east to improve the road surface. | Pavement Improvement | 07/28/2009 | 09/15/2009 |  | 1587304 | 9
926 | Florida | HIGHLANDS |  | 16 | ARRA159 | Resurface Memorial Drive (County Road 17A) in Highlands County from Sebring Parkway to Manatee Drive to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 09/15/2009 | 10/20/2009 |  | 380105 | 2.268
927 | Florida | HIGHLANDS |  | 16 | ARRA160 | Resurface County Road 621 in Highlands County from U.S. 27 to Crocket Road to improve the surface of this heavily traveled road. | Pavement Improvement | 09/15/2009 | 09/21/2009 |  | 205558 | 0.6
928 | Florida | HARDEE |  | 13 | ARRA161 | Add sidewalks along West Main Street from Booker T. Washington Avenue to Chester Avenue in the City of Bowling Green to improve safety. | Transportation Enhancements | 09/21/2009 |  |  | 85238 | 0
929 | Florida | DE SOTO |  | 13 | ARRA162 | "Construct a sidewalk along Dr. Martin Luther King, Jr. Street from Booker T. Washington Avenue to U.S. 17 to enhance safety for bicyclists and pedestrians." | Transportation Enhancements | 09/16/2009 | 11/22/2009 | 11/23/2009 | 87008 | 0
930 | Florida | HENDRY |  | 16,23 | ARRA163 | Construct a new sidewalk along State Road 29 from the RV park to the post office in the Felda community in Hendry County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 09/09/2009 | 09/28/2009 |  | 431911 | 2.077
931 | Florida | OKEECHOBEE |  | 16 | ARRA164 | "Add sidewalks along Southwest 7th Avenue, Southwest 9th Street and Southwest 11th Avenue in the City of Okeechobee to improve pedestrian safety." | Transportation Enhancements | 09/21/2009 |  |  | 166276 | 0
932 | Florida | POLK |  | 05,12,15 | ARRA165 | "Design and build a 12-foot wide paved trail between State Road 17 and 4th Street as an extension of the existing Lake Wales Trail, improving the connectivity of walking trails in Polk County." | Transportation Enhancements | 09/10/2009 | 12/07/2009 |  | 142042 | 0
933 | Florida | POLK |  | 05,12,15 | ARRA166 | Build a 12-foot wide paved trail connecting the existing Fort Fraser Trail just south of the University of South Florida/Polk State College to the Circle B Bar Reserve located on S.R. 540 to improve t | Transportation Enhancements | 09/10/2009 | 09/29/2009 |  | 525918 | 0
934 | Florida | COLLIER | NAPLES | 14,25 | ARRA168 | "Construct a paved pathway along Bald Eagle Drive on Marco Island to connect the town center, residential areas, and schools and give walkers and bicyclists a recreational route for exercise." | Transportation Enhancements | 08/19/2009 | 08/24/2009 |  | 380719 | 1.185
935 | Florida | HIGHLANDS |  | 16 | ARRA169 | Resurface Kenilworth Boulevard from Lakeview Drive to Persimmon Avenue to improve the surface of this heavily traveled road in Highlands County. | Pavement Improvement | 09/15/2009 | 10/20/2009 |  | 156905 | 0.4
936 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA170 | Add landscaping along State Road 789 through the coastal city of Long Boat Key to enhance the roadway features of this beach community. | Transportation Enhancements | 09/30/2009 | 10/22/2009 |  | 321987 | 4.557
937 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA171 | Add landscaping along State Road 789 through the coastal city of Bradenton Beach to enhance the roadway features of this beach community. | Transportation Enhancements | 09/30/2009 | 10/22/2009 |  | 178013 | 0.902
938 | Florida | HIGHLANDS |  | 16 | ARRA172 | Resurface County Road 17 (S. Main Street) in the town of Lake Placid from Poinsettia Street to West Interlake Boulevard to improve the surface of this heavily traveled road. | Pavement Improvement | 09/15/2009 | 09/21/2009 |  | 205921 | 0.499
939 | Florida | MANATEE |  | 11,13 | ARRA173 | Add sidewalks along Gulf Front Park from Palm Avenue to Willow Avenue in the City of Anna Maria to improve safety. | Transportation Enhancements | 09/16/2009 | 11/09/2009 | 12/03/2009 | 19458 | 0
940 | Florida | HIGHLANDS |  | 16 | ARRA174 | Resurface Home Avenue from Sebring Parkway to State Road 17 (North Gate Drive) to improve the surface of this heavily traveled road in Highlands County. | Pavement Improvement | 09/15/2009 | 10/20/2009 |  | 52165 | 0.168
941 | Florida | MANATEE |  | 11,13 | ARRA176 | Add sidewalks along North Bay Boulevard from Hibiscus Street to North Shore Drive in the City of Anna Maria to improve safety. | Transportation Enhancements | 09/16/2009 | 11/09/2009 | 12/12/2009 | 42716 | 0
942 | Florida | MANATEE |  | 11,13 | ARRA177 | Add sidewalks along Gulf Drive from Spring Avenue to Pine Avenue in the City of Anna Maria to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 11/09/2009 | 12/03/2009 | 6973 | 0
943 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA178 | Replace a short bridge in Lee County on Cortez Boulevard near Fort Myers High School with a new bridge that has sidewalks. | Pavement Improvement | 10/28/2009 | 12/06/2009 |  | 247843 | 0
944 | Florida | MANATEE |  | 11,13 | ARRA179 | Add sidewalks along North and South Gulf Drive from 57th Street to 84th Street in the City of Holmes Beach to improve safety. | Transportation Enhancements | 09/16/2009 | 09/29/2009 | 11/11/2009 | 9998 | 1.203
945 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA180 | "Construct a new culvert on Carrel Road to replace an older, rough-riding surface." | Pavement Improvement | 11/23/2009 | 11/23/2009 |  | 94960 | 0
946 | Florida | MANATEE |  | 11,13 | ARRA181 | Add sidewalks along Holmes Boulevard from 54th Street to 66th Street in the City of Holmes Beach to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 09/28/2009 | 11/05/2009 | 22942 | 0
947 | Florida | MANATEE |  | 11,13 | ARRA182 | Add sidewalks along Palm Drive from 66th Street to 85th Street in the City of Holmes Beach to improve safety. | Transportation Enhancements | 09/16/2009 | 09/29/2009 | 11/11/2009 | 10445 | 0
948 | Florida | MANATEE |  | 11,13 | ARRA183 | Add sidewalks along 85th Street from Gulf Drive to Marina Drive in the City of Holmes Beach to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 09/29/2009 | 11/11/2009 | 11341 | 0
949 | Florida | MANATEE |  | 11,13 | ARRA184 | Add sidewalks along 21st Avenue from 26th Street West to 27th Street West in Bradenton to improve safety. | Transportation Enhancements | 09/16/2009 | 09/30/2009 | 11/10/2009 | 8922 | 0
950 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA185 | Add sidewalks along 27th Street from 22nd Avenue West to 23rd Avenue West in Bradenton to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 09/30/2009 | 11/10/2009 | 25553 | 0
951 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA186 | Add sidewalks along 23nd Avenue from 26th Street West to 27th Street West in Bradenton to improve safety. | Transportation Enhancements | 09/16/2009 | 09/30/2009 | 11/10/2009 | 8491 | 0
952 | Florida | MANATEE |  | 11,13 | ARRA187 | Add sidewalks along 21st Avenue from 30th Street West to 34th Street West in Bradenton to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 09/30/2009 | 11/10/2009 | 53496 | 0
953 | Florida | HIGHLANDS |  | 16 | ARRA189 | Add sidewalks along Thunderbird Road from Lotus Avenue to Red Pine Drive in the City of Sebring to improve pedestrian safety. | Transportation Enhancements | 09/15/2009 |  |  | 115031 | 0
954 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA194 | Construct a left turn on Homestead Road South in Lee County at the Milwaukee Boulevard to move traffic more efficiently though the intersection. | Safety/Traffic Management | 09/17/2009 | 09/17/2009 |  | 70579 | 0.2
955 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA195 | Rehabilitate the Crescent Avenue bridge and the North Bay Boulevard bridge in the coastal city of Anna Maria Island to extend the use of the bridges by many years. | Pavement Improvement | 09/22/2009 | 10/13/2009 |  | 490590 | 0
956 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA196 | Resurface Pine Avenue in the city of Anna Maria from Gulf Drive to Bay Boulevard to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 09/16/2009 | 11/09/2009 |  | 95773 | 0.504
957 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA197 | Resurface Gulf Drive in the city of Anna Maria from Willow Avenue to Pine Avenue to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 09/16/2009 | 11/09/2009 |  | 136214 | 0.276
958 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA199 | Add landscaping and sidewalks along State Road 789/Gulf Drive from south of 2nd Street to north of 5th Street to improve the safety and enhance the roadway features of this beach community. | Transportation Enhancements | 09/30/2009 | 10/22/2009 |  | 341204 | 0.371
959 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA200 | Add pedestrian crosswalks to the intersections of East Bay Drive and Gulf Drive in the city of Holmes Beach to improve safety. | Transportation Enhancements | 09/16/2009 | 11/16/2009 | 12/12/2009 | 23521 | 0.002
960 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA201 | "Beach Boulevard, (U.S. 90/State Road 212) in Duval County will be widened from four to six lanes for 1? miles between Hodges Boulevard and San Pablo Road in order to complete the six-lane section bet | Pavement Widening | 06/10/2009 | 06/10/2009 |  | 15209245 | 2.76
961 | Florida | CLAY |  | 03,06 | ARRA202 | "In Clay County, a new overpass for Plantation Oaks Boulevard traffic will separate the higher speed and volume of traffic on State Road 23, making it safer and more efficient." | Pavement Widening | 06/16/2009 | 06/16/2009 | 10/01/2009 | 8405228 | 0.1
962 | Florida | NASSAU |  | 04 | ARRA203 | "In Nassau County, State Road A1A (State Road 200) will be widened from two to four lanes for six miles between Griffin and Stratton roads to improve traffic flow within the corridor." | Pavement Widening | 06/16/2009 | 06/16/2009 |  | 29791163 | 7.89
963 | Florida | CHARLOTTE |  | 13,14,16 | ARRA204 | Lengthen two left turn lanes on southbound U.S. 41 in Charlotte County to improve traffic flow at the Midway Boulevard intersection. | Pavement Improvement | 09/30/2009 |  |  | 165765 | 0.1
964 | Florida | CHARLOTTE |  | 13,14,16 | ARRA205 | Add a left turn lane at Murdock Circle westbound at U.S. 41 to improve traffic movement in this area. | Pavement Improvement | 09/30/2009 |  |  | 180803 | 0.1
965 | Florida | MARION | OCALA | 03,05,06,08 | ARRA208 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/06/2009 | 11/30/2009 |  | 335281 | 1.517
966 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA209 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 01/11/2010 | 01/21/2010 |  | 182075 | 2.291
967 | Florida | MARION | OCALA | 03,05,06,08 | ARRA214 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/06/2009 | 11/10/2009 |  | 47971 | 0.839
968 | Florida | MARION | OCALA | 03,05,06,08 | ARRA216 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/10/2009 | 11/16/2009 |  | 139256 | 0.922
969 | Florida | MARION | OCALA | 03,05,06,08 | ARRA218 | This turn lane project in the City of Ocala will improve safety and traffic flow and reduce traffic congestion at intersections. | Safety/Traffic Management | 12/03/2009 | 12/07/2009 |  | 1152877 | 1.058
970 | Florida | MARION | OCALA | 03,05,06,08 | ARRA219 | This repaving project in Marion County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/05/2009 | 11/09/2009 |  | 980253 | 3.363
971 | Florida | MARION | OCALA | 03,05,06,08 | ARRA222 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/06/2009 | 11/10/2009 |  | 97672 | 0.707
972 | Florida | MARION | OCALA | 03,05,06,08 | ARRA224 | This repaving project in Marion County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 12/14/2009 | 12/14/2009 |  | 4837445 | 10.849
973 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA225 | This resurfacing project in the City of Satellite Beach will improve the condition of the existing pavement and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 12/16/2009 | 12/21/2009 |  | 137098 | 0.275
974 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA226 | This resurfacing project in the City of Titusville will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 11/16/2009 | 12/07/2009 |  | 131399 | 0.285
975 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA231 | This repaving project in the City of Palm Bay will improve the road surface. | Pavement Improvement | 11/17/2009 | 11/17/2009 |  | 698396 | 1.251
976 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA232 | This resurfacing project in the City of Titusville will improve the condition of the existing pavement as well as provide better guardrails. | Pavement Improvement | 11/16/2009 | 12/07/2009 |  | 225850 | 0.68
977 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA237 | This resurfacing project in Lake County will improve the condition of the pavement and enhance safety by upgrading pedestrian crossings. | Pavement Improvement | 01/18/2010 |  |  | 156704 | 1.269
978 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA243 | "This project in the City of Cocoa Beach will resurface the road, improve storm water drainage, fix sidewalks and upgrade pedestrian crossings." | Pavement Improvement | 10/22/2009 | 11/02/2009 |  | 262282 | 0.409
979 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA248 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 01/11/2010 | 01/21/2010 |  | 617617 | 4.896
980 | Florida | LAKE | LADY LAKE | 03,05,06,08 | ARRA249 | This resurfacing project in Lake County will fix the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 01/11/2010 | 01/21/2010 |  | 127208 | 0.3
981 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA251 | This resurfacing project in Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 11/24/2009 | 12/07/2009 |  | 880639 | 2.16
982 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA252 | This resurfacing project in the City of Oviedo will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 12/11/2009 | 12/11/2009 |  | 996399 | 1.791
983 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA254 | The Rinehart Road project in the City of Lake Mary includes resurfacing which will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 11/19/2009 | 11/20/2009 |  | 711850 | 2.09
984 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA255 | The Howell Branch Road resurfacing project in Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 11/02/2009 | 11/02/2009 |  | 505154 | 0.745
985 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA257 | The State Road 419 project in the City of Winter Springs will provide turn lanes to reduce traffic congestion. | Pavement Improvement | 12/01/2009 | 12/01/2009 |  | 534000 | 0.001
986 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA275 | The Riverside Drive resurfacing project in the City of New Smyrna Beach will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 11/19/2009 | 11/23/2009 |  | 295459 | 0.839
987 | Florida | HILLSBOROUGH | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,11,12 | ARRA279 | The I-4/Selmon Expressway Connector is a new toll road that will connect Interstate 4 to the Selmon Expressway and provide commercial trucks direct access to the Port of Tampa improving the efficient | New Construction | 07/01/2009 | 07/08/2009 |  | 105004102 | 0.913
988 | Florida | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,10,11 | ARRA280 | "In Pinellas County, to reduce congestion, this project removes the traffic signals on U.S. 19 between Whitney Road and State Road 60 and replaces them with two new interchanges at Belleair Road and S | Pavement Widening | 06/29/2009 | 08/20/2009 |  | 44990142 | 2.643
989 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA281 | "This project widens Interstate 95 from Malabar Road to Palm Bay Road in Brevard County, making this section of I-95 three lanes in both directions." | Pavement Widening | 10/01/2009 | 10/01/2009 |  | 21156663 | 4.173
990 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA282 | "The U.S. 27 project will add two new lanes, making this a six-lane, divided highway from just north of Lake Louisa Road to Cluster Oaks Drive in the City of Clermont." | Pavement Widening | 10/14/2009 | 10/09/2009 |  | 20433560 | 3.837
991 | Florida | MARION | OCALA | 03,05,06,08 | ARRA283 | "This project will transform Baseline Road, which is primarily a two-lane highway, into a four-lane, divided highway near Ocala in Marion County." | Pavement Widening | 09/11/2009 | 09/11/2009 |  | 26554924 | 5.704
992 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA284 | The State Road 50 project in the City of Winter Garden will widen this roadway more than three miles to a six-lane divided roadway. | Pavement Widening | 09/23/2009 | 09/23/2009 |  | 19868356 | 3.056
993 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA285 | "The State Road 434 project in the City of Altamonte Springs will make this section of the road a six-lane, divided highway, which is consistent to the rest of State Road 434 in this area." | Pavement Widening | 09/30/2009 | 09/30/2009 |  | 4697089 | 0.713
994 | Florida | OKEECHOBEE |  | 16 | ARRA290 | Replace the bridge at 43rd Avenue in the city of Okeechobee to improve the safety of motorists. | Pavement Improvement | 09/21/2009 | 10/24/2009 |  | 1201547 | 0
995 | Florida | MARION | OCALA | 03,05,06,08 | ARRA307 | This sidewalk project in Marion County will provide a safer environment for pedestrians and will upgrade pedestrian crossings. | Transportation Enhancements | 10/16/2009 | 10/26/2009 |  | 456707 | 0
996 | Florida | MARION | OCALA | 03,05,06,08 | ARRA308 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrians. | Pavement Improvement | 11/06/2009 | 11/30/2009 |  | 988939 | 1.02
997 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA310 | The Cross Seminole County Trail project will repair the Howell Creek Trestle Bridge which is a vital part of the Seminole County trail system. | Transportation Enhancements | 12/07/2009 | 12/07/2009 |  | 450866 | 0
998 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA312 | This State Road 434 project in the City of Winter Springs will provide safer conditions for making right turns at this intersection. | Pavement Improvement | 12/01/2009 | 12/01/2009 |  | 169461 | 0.064
999 | Florida | SUMTER |  | 05 | ARRA313 | This repaving project in Osceola County will improve the road surface and upgrade pedestrian crossings. | Pavement Improvement | 11/24/2009 | 01/11/2010 |  | 661988 | 3.785
1000 | Florida | SUMTER |  | 05 | ARRA314 | This sidewalk project in Marion County will provide a safer environment for pedestrians and bicyclists as well as upgraded pedestrian crossings. | Pavement Improvement | 11/24/2009 | 01/11/2010 |  | 1020860 | 7.425
1001 | Florida | MIAMI-DADE | MIAMI-HIALEAH, FL | 17,18,20,21,25 | ARRA319 | This project reconstructs almost three miles of the US 1 corridor known as the 18-mile stretch between Florida City and Key Largo. | Pavement Improvement | 09/03/2009 | 09/28/2009 |  | 18362727 | 2.86
1002 | Florida | MONROE |  | 18,25 | ARRA323 | This project will provide maintenance and repairs to the Palm Drive Bridge in Monroe County. The project will replace the bridge deck and railings. | Bridge Improvement | 11/19/2009 | 11/30/2009 |  | 296620 | 0.013
1003 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA331 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Transportation Enhancements | 12/01/2009 |  |  | 162000 | 0
1004 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA332 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Transportation Enhancements | 12/01/2009 |  |  | 220000 | 0
1005 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA354 | The Village of Biscayne Park will construct median curbs and an irrigation system. The project will enhance pedestrian safety. | Transportation Enhancements | 09/16/2009 | 10/15/2009 | 12/19/2009 | 74073 | 0.527
1006 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA355 | The Village of El Portal will resurface and enhance drainage at intersections. The project will enhance roadway safety for the traveling public. | Pavement Improvement | 09/16/2009 |  |  | 56641 | 0.261
1007 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA356 | "The City of Virginia Gardens will construct new drainage inlets at intersections, and perform pavement resurfacing and restriping. This project will enhance safety for the traveling public." | Pavement Improvement | 09/16/2009 |  |  | 39364 | 0.3
1008 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA357 | Larger drainage pipes will be installed under US 29 in the Town of Century as part of an overall community drainage improvement project in Escambia County. | Pavement Improvement | 08/18/2009 | 08/18/2009 |  | 498123 | 0.134
1009 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA361 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists. | Safety/Traffic Management | 11/12/2009 | 11/12/2009 |  | 186000 | 0
1010 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA362 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists and pedestrians. | Safety/Traffic Management | 11/30/2009 | 12/07/2009 |  | 150000 | 0
1011 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA364 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 10/19/2009 | 10/19/2009 |  | 105000 | 0.26
1012 | Florida | JACKSON |  | 02 | ARRA370 | The City of Marianna will repave Milton Avenue to improve the road surface and driving quality in Jackson County. | Pavement Improvement | 12/03/2009 | 12/18/2009 |  | 306898 | 0.086
1013 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA373 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 11/30/2009 | 11/30/2009 |  | 283000 | 0.513
1014 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA374 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 11/30/2009 | 11/30/2009 |  | 362000 | 0.786
1015 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA381 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 09/28/2009 |  |  | 185000 | 1.028
1016 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA397 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses a | Pavement Improvement | 11/30/2009 | 11/30/2009 |  | 236429 | 0.311
1017 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA400 | This Leon County project will add a left turn lane and a traffic signal on Meridian Road at Bannerman Road to improve traffic operations and safety. | Safety/Traffic Management | 08/03/2009 | 08/03/2009 |  | 889431 | 0.325
1018 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA401 | The City of Homestead will install streetlight poles. Streetlights along the corridor will enhance the safety of all roadway users. | Safety/Traffic Management | 12/01/2009 | 12/07/2009 |  | 1345064 | 6.127
1019 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA409 | "The City of South Miami will enhance sections of Sunset Drive by resurfacing, reconstructing sidewalks, upgrading drainage, and installing median landscaping and irrigation. This project will create | Pavement Improvement | 11/30/2009 | 11/30/2009 |  | 253166 | 0.219
1020 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA440 | This project will repave the existing roadway and repair existing pavement markings. This project will enhance safety and mobility. | Pavement Improvement | 10/06/2009 |  |  | 322621 | 0.501
1021 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA441 | The City of West Miami will construct four traffic-calming devices at various locations. This project will reduce the speed of traffic and improve pedestrian safety. | Safety/Traffic Management | 09/14/2009 | 10/20/2009 |  | 38540 | 0.013
1022 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA442 | The City of West Miami will construct four traffic-calming devices at various locations. This project will reduce the speed of traffic and improve pedestrian safety. | Safety/Traffic Management | 09/14/2009 | 10/14/2009 |  | 39163 | 0.13
1023 | Florida | MIAMI-DADE | MIAMI-HIALEAH, FL | 17,18,20,21,25 | ARRA444 | This project will repave the existing roadway and repair existing pavement markings. This project will enhance safety and mobility. | Transportation Enhancements | 10/06/2009 | 11/18/2009 |  | 180725 | 0.47
1024 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA446 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 11/23/2009 | 11/23/2009 |  | 88184 | 1
1025 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA447 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 11/23/2009 | 11/23/2009 |  | 30000 | 1.174
1026 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA448 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 11/23/2009 | 11/23/2009 |  | 30000 | 0.504
1027 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA457 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 10/19/2009 | 10/19/2009 |  | 155000 | 1.014
1028 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA458 | The City of Fort Walton Beach will repave Memorial Parkway to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 12/10/2009 | 12/10/2009 |  | 726114 | 1.304
1029 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA459 | The City of Fort Walton Beach will repave Bay Drive Southeast to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 12/10/2009 | 12/10/2009 |  | 179160 | 1.191
1030 | Florida | CALHOUN |  | 02 | ARRA460 | This safety project will provide roadway striping on city streets in the City of Blountstown to provide safer travel on roads that have little or no existing striping in Calhoun County. | Safety/Traffic Management | 12/15/2009 |  |  | 80384 | 3.125
1031 | Florida | HOLMES |  | 01 | ARRA464 | This safety project will provide roadway striping on rural roads in Holmes County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 11/06/2009 | 11/12/2009 |  | 547609 | 16.647
1032 | Florida | LIBERTY |  | 02 | ARRA465 | Liberty County will install guardrail at several locations on county roads to improve the safety of the traveling public. | Safety/Traffic Management | 11/17/2009 | 11/30/2009 |  | 266006 | 0
1033 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA467 | Okaloosa County will replace drainage pipes and existing failing pavement on Hollywood Boulevard in Fort Walton Beach to improve the road surface and driving quality. | Pavement Improvement | 11/19/2009 | 12/01/2009 |  | 1271467 | 0.187
1034 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA468 | "The City of Destin will add bus stops, public parking and landscaping, improve sidewalks, and replace existing failing pavement on Scenic Highway to improve pedestrian safety and travel in Okaloosa C | Pavement Improvement | 10/06/2009 | 10/19/2009 |  | 760955 | 0.771
1035 | Florida | WAKULLA |  | 02 | ARRA469 | This safety project will provide roadway striping on rural roads in Wakulla County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 10/13/2009 | 11/02/2009 | 11/18/2009 | 200000 | 19.785
1036 | Florida | WASHINGTON |  | 01 | ARRA471 | This safety project will provide roadway striping on rural roads in Washington County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 11/04/2009 |  |  | 458424 | 11.46
1037 | Florida | WASHINGTON |  | 01 | ARRA472 | Washington County will repave State Park Road to improve the road surface and driving quality. | Pavement Improvement | 12/07/2009 | 12/17/2009 |  | 261576 | 1.035
1038 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA479 | This project will repave approximately 0.9 miles of Harbor Drive to improve the ride for the users of this roadway. | Pavement Improvement | 10/19/2009 | 10/19/2009 |  | 108566 | 0.912
1039 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA480 | This project will install lighting along approximately 0.4 mile of the project corridor providing better visibility to the users of this roadway. | Safety/Traffic Management | 10/19/2009 | 10/19/2009 |  | 153021 | 0.497
1040 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA495 | The project will repave the existing roadway. This project will enhance mobility for users of this roadway. | Pavement Improvement | 12/25/2009 |  |  | 165365 | 1.331
1041 | Florida | CALHOUN |  | 02 | ARRA501 | Guardrail will be installed on several county roads in Calhoun County to improve the safety of the traveling public. | Safety/Traffic Management | 07/29/2009 | 07/29/2009 | 10/30/2009 | 157367 | 6.302
1042 | Florida | CALHOUN |  | 02 | ARRA502 | This safety project will provide roadway striping on rural roads in Calhoun County to provide safer travel on roads that had little or no existing striping. | Safety/Traffic Management | 07/29/2009 | 07/29/2009 | 10/15/2009 | 233840 | 9.656
1043 | Florida | WAKULLA |  | 02 | ARRA503 | Crosswalks and sidewalks were constructed along State Road 363 to improve pedestrian safety in the City of St. Marks. | Transportation Enhancements | 08/18/2009 | 08/18/2009 | 10/14/2009 | 37785 | 0.097
1044 | Florida | GADSDEN |  | 02 | ARRA504 | Five-foot wide sidewalks along various streets within the city limits of Gretna will be constructed to improve pedestrian safety in Gadsden County . | Transportation Enhancements | 08/18/2009 | 08/18/2009 |  | 348058 | 0.777
1045 | Florida | HOLMES |  | 01 | ARRA505 | This pedestrian safety project in Holmes County will include the construction of a 600-foot sidewalk in the Town of Noma. | Other | 07/29/2009 | 07/29/2009 |  | 52558 | 0.117
1046 | Florida | HOLMES |  | 01 | ARRA506 | This pedestrian safety project in Holmes County will include the construction of a 900-foot sidewalk in the Town of Esto. | Transportation Enhancements | 07/29/2009 | 07/29/2009 |  | 76942 | 0.336
1047 | Florida | JEFFERSON |  | 02,04 | ARRA507 | Existing deficient pavement on North Salt Road in Jefferson County will be replaced to improve the road surface and driving quality. | Safety/Traffic Management | 08/18/2009 | 08/18/2009 |  | 730552 | 4.889
1048 | Florida | JACKSON |  | 02 | ARRA508 | A five-foot wide sidewalk along State Road 69 will be constructed in the City of Grand Ridge to improve pedestrian safety in Jackson County. | Transportation Enhancements | 07/29/2009 | 07/29/2009 | 12/23/2009 | 134870 | 0.255
1049 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA509 | A five-foot wide sidewalk along State Road 285 has been constructed in the City of Niceville to improve pedestrian safety in Okaloosa County. | Transportation Enhancements | 07/29/2009 | 07/29/2009 | 10/19/2009 | 163692 | 0.858
1050 | Florida | WALTON | FORT WALTON BEACH | 01,02 | ARRA510 | A five-foot wide sidewalk along 19th Street will be constructed in the City of DeFuniak Springs to improve pedestrian safety in Walton County. | Transportation Enhancements | 07/29/2009 | 07/29/2009 |  | 164311 | 2.196
1051 | Florida | JACKSON |  | 02 | ARRA512 | The City of Marianna in Jackson County will repave College Street to improve the road surface and driving quality. | Pavement Improvement | 10/19/2009 |  |  | 314931 | 0.589
1052 | Florida | WALTON | FORT WALTON BEACH | 01,02 | ARRA513 | The City of Freeport will construct a five-foot wide sidewalk along State Road 20 to improve pedestrian safety in Walton County. | Transportation Enhancements | 11/09/2009 | 11/09/2009 | 12/31/2009 | 110000 | 0.114
1053 | Florida | WAKULLA | TALLAHASSEE | 02 | ARRA514 | This project will improve safety for motorists by providing a left turn lane onto Russell Drive north of the City of Crawfordville. | Pavement Widening | 08/18/2009 | 08/18/2009 | 12/17/2009 | 200191 | 0.214
1054 | Florida | JACKSON |  | 02 | ARRA515 | This Jackson County project consists of installing sidewalk along Caverns Road to increase pedestrian safety to Marianna High School. | Transportation Enhancements | 10/15/2009 |  |  | 507379 | 1.631
1055 | Florida | JACKSON |  | 02 | ARRA516 | This Jackson County project consists of restriping cross-walks and replacing failing sidewalks to improve pedestrian safety in the City of Marianna. | Safety/Traffic Management | 10/15/2009 |  |  | 216184 | 0.068
1056 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA521 | The City of Fort Walton Beach will repave Country Club Avenue to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 12/10/2009 | 12/10/2009 |  | 163980 | 0.85
1057 | Florida | GADSDEN | TALLAHASSEE | 02 | ARRA522 | Gadsden County will repave Glades Road to improve the road surface and driving quality. | Pavement Improvement | 12/14/2009 | 12/24/2009 |  | 574383 | 1.84
1058 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA525 | Leon County will repair the existing sidewalk and construct additional sidewalk along Perkins Road to improve pedestrian safety in the City of Tallahassee. | Transportation Enhancements | 11/23/2009 |  |  | 97738 | 0.076
1059 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA527 | Okaloosa County will construct a five-foot sidewalk along Brookmeade Drive to improve pedestrian safety in the City of Crestview. | Transportation Enhancements | 12/16/2009 | 12/21/2009 |  | 110000 | 0.373
1060 | Florida | FRANKLIN |  | 02 | ARRA528 | "Franklin County will construct approximately 2,700 feet of five-foot wide sidewalk along Pine Avenue to improve pedestrian safety." | Transportation Enhancements | 11/03/2009 | 11/03/2009 |  | 176412 | 0.227
1061 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA529 | Escambia County will repave Dog Track Road to improve the road surface and driving quality. | Pavement Improvement | 10/13/2009 | 10/13/2009 |  | 256347 | 1.125
1062 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA530 | Escambia County will repave Old Palafox Road from East Roberts Boulevard to Nine Mile Road to improve the road surface and driving quality in the City of Pensacola. | Pavement Improvement | 10/13/2009 | 10/13/2009 |  | 858684 | 2.182
1063 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA531 | Escambia County will repave Old Palafox Road from Memory Lane to Nine Mile Road to improve the road surface and driving quality in the City of Pensacola. | Pavement Improvement | 10/29/2009 | 10/30/2009 |  | 1923650 | 4.342
1064 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA532 | Escambia County will repave Copter Road to improve the road surface and driving quality. | Pavement Improvement | 10/13/2009 | 10/13/2009 |  | 246433 | 0.428
1065 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA533 | "Along with pedestrian safety improvements, Escambia County will repave ""W"" Street to improve the road surface and driving quality." | Pavement Improvement | 10/13/2009 | 10/13/2009 |  | 2527424 | 3.081
1066 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA534 | Escambia County will repave Dog Track Road from Blue Angel Parkway to US 98 to improve the road surface and driving quality. | Pavement Improvement | 10/13/2009 | 10/13/2009 |  | 871927 | 2.084
1067 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA535 | Escambia County will repave East Johnson Avenue to improve the road surface and driving quality. | Pavement Improvement | 10/13/2009 | 10/13/2009 |  | 243267 | 0.845
1068 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA537 | Escambia County will construct a five-foot wide sidewalk along Broad Street to improve pedestrian safety. | Transportation Enhancements | 10/13/2009 | 10/13/2009 |  | 143690 | 0.468
1069 | Florida | MANATEE |  | 11,13 | ARRA538 | Add Sidewalks along Gulf Front Park from Maple Street to Oak Street in the City of Anna Maria to improve safety for pedestrians in the area. | Transportation Enhancements | 09/16/2009 | 11/09/2009 | 12/03/2009 | 6981 | 0
1070 | Florida | LIBERTY |  | 02 | ARRA541 | Liberty County will construct approximately one mile of sidewalk along County Road 12 leading to Tolar Elementary School to improve pedestrian safety in the City of Bristol. | Transportation Enhancements | 12/02/2009 | 12/07/2009 |  | 220000 | 0.809
1071 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA543 | Add a new sidewalk along Cape Coral Parkway from Agualinda Boulevard to 16th Place in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 11/17/2009 | 11/23/2009 |  | 115000 | 0.846
1072 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA545 | Add a new sidewalk along Nicholas Parkway from State Road 78 to Santa Barbara Boulevard in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 11/17/2009 |  |  | 350000 | 1.344
1073 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA546 | Add a new sidewalk along Beach Parkway from Surfside Boulevard to Chiquita Boulevard in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 11/17/2009 |  |  | 505000 | 1.935
1074 | Florida | LEE |  | 14 | ARRA555 | Widen Interstate 75 from Colonial Boulevard to State Road 82 in Southwest Florida from four to six lanes to move daily traffic and commerce more efficiently. | Pavement Widening | 12/15/2009 | 12/21/2009 |  | 11186431 | 1.536
1075 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA559 | RESURFACING HABEN BLVD FROM US 301 TO US 41 (0001.044 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 01/21/2010 |  |  | 850023 | 1.044
1076 | Georgia | MUSCOGEE | COLUMBUS (AL) | 2, 3 | 0000099 | This is an enhancement project in Muscogee County. The project construction consists of the construction of a 10 to 12 foot multi use trail beginning at Columbus State University and extending northe | Transportation Enhancements | 09/23/2009 | 09/28/2009 | 03/26/2015 | 663681 | 12
1077 | Georgia | LANIER |  | 1 | 0000310 | This is a safety improvment project in Lanier County on SR 11/US 129. The project will realign on new location SR 11/US 129 and SR 31, 122/ US 221 to create two 90 degree intersections with SR 37 to | Pavement Widening | 07/27/2009 | 08/03/2009 | 06/30/2010 | 1610924.53 | 1.05
1078 | Georgia | DOUGLAS | ATLANTA | 13 | 0000424 | This project consists of reconstructing the existing intersection of SR 5 and Rose Avenue, located just north of I-20 in Douglas County. The existing intersection has an undesirable scissor-type confi | Safety/Traffic Management | 07/27/2009 | 08/18/2009 | 02/28/2011 | 2465582.05 | 0.2
1079 | Georgia | GORDON |  | 9 | 0000683 | This project is a bridge replacement project is Gordon and Murray counties. The bridge is located on County Road 134/County Line Road over Polecat Creek on the Gordon and Murray county line. Also, t | Bridge Replacement | 07/27/2009 | 09/17/2009 | 05/31/2013 | 1439870.03 | 0.61
1080 | Georgia | NEWTON | ATLANTA | 8 | 0000842 | This project is an intersection improvement project in Newton County. This project will widen SR 162/Salem Road 6 ft. symmetrically to provide a north bound left turn lane. In addition, County Road | Safety/Traffic Management | 11/03/2009 | 11/17/2009 | 12/31/2010 | 959526.39 | 0.32
1081 | Georgia | MILLER |  | 2 | 0001361 | This project is a bridge replacement project in Miller County. The construction proposes to construct a new 160' x 44' concrete bridge on SR 91 over Dry Creek at the existing bridge site. The roadway | Bridge Replacement | 10/23/2009 | 11/05/2009 | 11/30/2010 | 2086863.35 | 0.32
1082 | Georgia | TATTNALL |  | 12 | 0001364 | This project is a bridge replacement on S.R. 56/Nail Bridge @ the Ohoopee River, 2 miles west of Reidsville in Tattnall County. The project length is 0.41 miles. | Bridge Replacement | 07/28/2009 | 08/31/2009 | 09/30/2010 | 2831014.42 | 0.41
1083 | Georgia | CLAY |  | 2 | 0001369 | This project will replace the structurally deficient bridge in Clay County on County Road 76 over Drag Nasty Creek with a new 180' x 28' reinforced concrete bridge. The existing approaches consist of | Bridge Replacement | 07/06/2009 | 07/31/2009 | 02/28/2010 | 1201513.85 | 0.32
1084 | Georgia | GLYNN | BRUNSWICK | 1 | 0001558 | This project is the construction of safety turn lanes on SR 520 in Brantley and Glynn Counties. The project begins just west of the Brantley/Glynn County Line at its intersection with County Road 580 | Safety/Traffic Management | 11/23/2009 |  | 12/31/2010 | 6011380.22 | 11.41
1085 | Georgia | BARTOW | ATLANTA | 11 | 0001574 | "This project is a safety improvement located on SR 3/US 41 in Bartow County. The project begins approximately at the Cobb/Bartow County line and extends north to the SR 293 Connector in Bartow Count | Safety/Traffic Management | 08/18/2009 | 09/16/2009 | 05/31/2011 | 12826646.94 | 15.15
1086 | Georgia | FLOYD | ROME | 11 | 0001575 | This project is a safety improvement that will construct turn lanes on SR 53 in Floyd County. The project will construct left and right turn lanes at fifteen intersections and four median crossovers | Safety/Traffic Management | 11/30/2009 |  | 09/30/2011 | 9138206.83 | 9.93
1087 | Georgia | DE KALB | ATLANTA | 4 | 0002406 | This is a sidewalk construction project in Dekalb County. This project includes construction of sidewalks on both sides of SR 12/US 278/Covington Highway from SR 154/Memorial Drive to County Road 518 | Transportation Enhancements | 07/27/2009 | 08/25/2009 | 08/31/2010 | 870414.3 | 1.58
1088 | Georgia | HENRY | ATLANTA | 13, 3 | 0002638 | This project is a roadway widening project in Henry County. The project is located on Eagle's Landing Parkway, 0.4 miles east of the I-75 interchange in Henry County. This project will continue the | Pavement Widening | 08/31/2009 | 09/29/2009 | 02/27/2012 | 23370448.45 | 2.6
1089 | Georgia | CANDLER |  | 12 | 0002734 | This is a bridge replacement project in Candler County. The project is a bridge replacement on County Road 203/Glisson Road at Wolfe Creek. The existing bridge was constructed in 1955 and is structu | Bridge Replacement | 08/26/2009 | 11/18/2009 | 09/30/2011 | 1207275.12 | 0.49
1090 | Georgia | CANDLER |  | 12 | 0002841 | This project is a bridge replacement in Candler County. The project will replace the bridge on County Road 223/Portal Highway at Little Stocking Head Creek, 5 miles north of Metter. The existing bri | Bridge Replacement | 07/28/2009 | 09/21/2009 | 12/31/2010 | 928868.6 | 0.35
1091 | Georgia | CANDLER |  | 12 | 0002842 | This project will replace two bridges in Bulloch and Candler counties. The project will replace the bridge on County Road 223/Portal Highway at Big Branch and the bridge on County Road 223/Portal Hig | Bridge Replacement | 07/28/2009 | 09/21/2009 | 12/31/2010 | 2288929.57 | 0.78
1092 | Georgia | FULTON | ATLANTA | 6 | 0003769 | This project is an intersection improvement in Fulton County. The project will reconstruct the intersection on County Road 85/Kimball Bridge Road at County Road 103/Waters Road. The construction wil | Pavement Improvement | 12/01/2009 |  | 06/03/2015 | 849092.42 | 0.2
1093 | Georgia | GWINNETT | ATLANTA | 7 | 0004456 | This is a new roadway construction project in Gwinnett County. This proposed project will connect to the existing intersection of McGinnis Ferry Road and Satellite Boulevard, with only minor improvem | New Construction | 09/03/2009 | 09/11/2009 | 09/30/2011 | 21888586.22 | 2.67
1094 | Georgia | CLINCH |  | 1 | 0006534 | This project is a transportation enhancement in Clinch County. The historic Homerville Railroad Depot, also known as Station 11, will be restored to its original architectural style to the extent pos | Transportation Enhancements | 10/08/2009 | 11/09/2009 | 04/10/2015 | 500000 | 0
1095 | Georgia | MUSCOGEE | COLUMBUS (AL) | 2 | 0006597 | This project is a transportation enhancement in Columbus, Muscogee County. This project consists of streetscape improvements on Veterans Pkwy SR 1/US 27 beginning at 8th Street and extending northerl | Transportation Enhancements | 11/12/2009 |  | 05/15/2015 | 1250000 | 0.65
1096 | Georgia | PIKE |  | 3 | 0006600 | "This project constructs a walking trail in Molena, in Pike County. Construction includes the aesthetic revitalization of a portion of Georgia Highway 109 east of the Georgia Highway 18 intersection. | Transportation Enhancements | 09/29/2009 | 10/21/2009 | 04/01/2015 | 97307 | 0.1
1097 | Georgia | GWINNETT | ATLANTA | 4, 7 | 0006825 | The proposed project along Buford Highway in Gwinnett County will upgrade signal equipment and install fiber optic interconnect to allow for Intelligent Transporation Systems (ITS). Installation of IT | Safety/Traffic Management | 09/18/2009 |  | 10/28/2011 | 2402881.44 | 11.01
1098 | Georgia | GWINNETT | ATLANTA | 7 | 0006829 | This project, in Gwinnett County, includes the design of fiber optic communications cable and closed-circuit television (CCTV) cameras along Sugarloaf Parkway from Peachtree Industrial Boulevard in Du | Safety/Traffic Management | 09/18/2009 |  | 10/28/2011 | 1586642.07 | 12.3
1099 | Georgia | DE KALB | ATLANTA | 4, 5 | 0007130 | This project is a transportation enhancement in Dekalb County. The project will construct streetscape designs and intersection improvements along SR 154/Memorial Drive from SR 155/Candler Road to Mou | Transportation Enhancements | 07/23/2009 | 09/28/2009 | 05/31/2012 | 4539202.25 | 3.4
1100 | Georgia | DE KALB | ATLANTA | 4 | 0007131 | This project is the construction of intersection and pedestrian safety improvements in DeKalb County. This project is on SR 10/Memorial Drive and begins at Woodcroft Road and ends at Goldsmith Road. | Transportation Enhancements | 12/22/2009 |  | 12/31/2011 | 3136464.75 | 3.47
1101 | Georgia | DECATUR |  | 2 | 0008113 | This project provides streetscape improvements in downtown Bainbridge in Decatur County. The Bainbridge Central Business District is well defined on the north by Calhoun Street and on the south by Sh | Transportation Enhancements | 09/29/2009 | 11/09/2009 | 04/01/2015 | 591411.23 | 0.36
1102 | Georgia | DE KALB | ATLANTA | 3, 4 | 0008119 | This project is a transportation enhancement in DeKalb and Rockdale Counties. This project involves clearing, grading, and installing a 10' to 12' wide concrete trail from MLK High School on Snapfinge | Transportation Enhancements | 01/18/2010 |  |  | 633418.65 | 1.6
1103 | Georgia | FAYETTE | ATLANTA | 3 | 0008126 | The project will provide pedestrian improvements within the City of Fayetteville in Fayette County along Lee Street. This will include construction of a 5 foot sidewalk with a 2 foot grass buffer and | Transportation Enhancements | 09/23/2009 |  | 03/26/2015 | 337500 | 0.59
1104 | Georgia | HARALSON |  | 11 | 0008157 | This project is a transportation enhancement in the City of Buchanan in Haralson County. The project will construct sidewalks, curb and gutter, seatwalls, lighting, street furniture and landscaping a | Transportation Enhancements | 10/09/2009 |  | 04/11/2015 | 438000 | 0.2
1105 | Georgia | HENRY | ATLANTA | 3 | 0008159 | This project is a transportation enhancement in Henry County. The proposed project will provide a trailhead facility. The project will be constructed on two city owned parcels adjacent to Cleveland | Transportation Enhancements | 10/01/2009 |  | 04/03/2015 | 241204.1 | 0.91
1106 | Georgia | MUSCOGEE | COLUMBUS (AL) | 2 | 0008185 | This is a transportation enhancement project in Muscogee County. This project will provide streetscape and beautification along SR 1/Veteran's Parkway in Columbus from 10th Street to SR 22 Spur. The | Transportation Enhancements | 11/12/2009 |  | 05/15/2015 | 1250000 | 0.4
1107 | Georgia | PAULDING | ATLANTA | 11 | 0008188 | The project will provide a trailhead facility adjacent to downtown Dallas in Paulding County, on an approximate 1 acre site at the intersection of South Main Street and Hardee Street. The trailhead w | Transportation Enhancements | 09/17/2009 |  | 03/20/2015 | 625000 | 0.06
1108 | Georgia | SCHLEY |  | 2 | 0008198 | This project is a transportation enhancement in Schley County. The project will construct sidewalks on three locations in Ellaville: 1) east side of Hill Street between West Buena Vista Street and | Transportation Enhancements | 10/08/2009 |  | 04/10/2015 | 66997.38 | 0.64
1109 | Georgia | STATEWIDE | ATLANTA | 5, 6, 7, 4, 13, 11, 9, 3 | 0009312 | "This project is a planning study in the Atlanta Metropolitan Area. This study will develop a ""Strategic Regional Thoroughfare Plan"" for counties within the Atlanta MPO area. The planning study wi | Other | 01/07/2010 |  | 03/31/2011 | 1000000 | 0
1110 | Georgia | GWINNETT | ATLANTA | 7 | 0009344 | This project is an intersection improvement in Gwinnett County. The purpose of this project is to improve the operating characteristics of the intersection of SR 8 (Lawrenceville Highway) and Pleasan | Safety/Traffic Management | 08/28/2009 | 09/16/2009 | 06/30/2011 | 9328483.55 | 0.21
1111 | Georgia | GWINNETT | ATLANTA | 4, 7 | 0009345 | The project is an intersection improvement in Gwinnett County. This project will improve the operation characteristics of the intersection of SR 8 (Lawrenceville Highway) and Beaver Ruin Road/Arcado | Safety/Traffic Management | 08/05/2009 | 08/05/2009 | 06/30/2011 | 6227012.29 | 1.1
1112 | Georgia | CATOOSA | CHATTANOOGA (TN) | 9 | 0009346 | This project is a safety intersection improvement project in Catoosa County. This project consists of reconstructing the existing left turns lanes on SR 2 from a Type A median crossover to a Type B. | Safety/Traffic Management | 07/27/2009 | 08/26/2009 | 09/30/2010 | 1531013.32 | 0.22
1113 | Georgia | COBB | ATLANTA | 6 | 0009349 | This project will modify the interchange of SR 120/Roswell Road and SR 120 Alternate (formerly SR 120 Loop) in Cobb County. This project is located in the City of Marietta. The proposed project will | Pavement Improvement | 08/18/2009 | 09/01/2009 | 06/30/2011 | 7907591.75 | 0.75
1114 | Georgia | COBB | ATLANTA | 11 | 0009350 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 809/Corner Road. The construction will con | Pavement Improvement | 08/19/2009 | 09/24/2009 | 04/30/2011 | 1242339.86 | 1.6
1115 | Georgia | GWINNETT | ATLANTA | 7 | 0009351 | This project is a road widening construction project in Gwinnett County. The project will widen and reconstruct the existing two lanes of SR 20 to accommodate 4 lanes beginning approximately 800 feet | Pavement Improvement | 09/08/2009 | 10/28/2009 | 12/31/2011 | 13281562.16 | 2.65
1116 | Georgia | COBB | ATLANTA | 11 | 0009352 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 784/Hadaway Road. The construction will co | Pavement Improvement | 08/19/2009 | 09/24/2009 | 04/30/2011 | 956562.38 | 0.4
1117 | Georgia | COBB | ATLANTA | 11 | 0009353 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 55/Mars Hill Church Road. The construction | Pavement Improvement | 08/19/2009 | 09/24/2009 | 04/30/2011 | 884562.14 | 0.4
1118 | Georgia | FAYETTE | ATLANTA | 3 | 0009355 | This project will upgrade existing traffic signal equipment and pedestrian facilities for S.R. 314 and S.R. 54 at various intersections in Fayette County. The intersections are as follows: 1) SR 3 | Safety/Traffic Management | 07/20/2009 | 10/26/2009 | 02/28/2010 | 175877.47 | 1.2
1119 | Georgia | FULTON | ATLANTA | 6 | 0009358 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations on SR 961/Old Alabama Road in the City of Roswell, Fulton County. The intersections are | Safety/Traffic Management | 07/17/2009 | 10/12/2009 | 07/31/2010 | 766858.65 | 3
1120 | Georgia | DE KALB | ATLANTA | 4, 6 | 0009359 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations in DeKalb County on Chamblee Tucker Road, Clairmont Road, & New Peachtree Road. The int | Safety/Traffic Management | 07/20/2009 | 09/22/2009 | 05/31/2010 | 1161968.65 | 0
1121 | Georgia | DE KALB | ATLANTA | 4 | 0009360 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations on Briarcliff Road & Shallowford Road in Dekalb County. The intersections are as follow | Safety/Traffic Management | 07/20/2009 | 11/04/2009 | 07/31/2010 | 892693.87 | 1.8
1122 | Georgia | DE KALB | ATLANTA | 4, 6 | 0009361 | This project will upgrade the existing traffic signal equipment and pedestrian facilities at various locations on Chamblee Dunwoody Road and NorthShallowford Road in DeKalb County. The intersections | Safety/Traffic Management | 07/20/2009 |  | 12/31/2010 | 1855080.7 | 0
1123 | Georgia | DE KALB | ATLANTA | 4 | 0009362 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at 21 locations on LaVista Rd, Northlake Pkwy, & Henderson Mill Rd in Dekalb County at the following intersec | Safety/Traffic Management | 07/20/2009 |  | 12/31/2010 | 1984055.69 | 0
1124 | Georgia | COBB | ATLANTA | 13 | 0009363 | This project consists of the upgrade of the traffic signals at 4 locations on SR 139/Mableton Parkway and 1 location on County Road 2570/Old Alabama Road in Cobb County. Pedestrian improvements will | Safety/Traffic Management | 07/20/2009 | 11/02/2009 | 07/31/2010 | 453645.6 | 1.9
1125 | Georgia | COLUMBIA | AUGUSTA (SC) | 10 | 0009365 | This project is the replacement of the existing bridge over Euchee Creek on SR 223, 2.2 miles northwest of Grovetown, in Columbia County. The project will widen and correct the structural deficiencie | Bridge Replacement | 11/02/2009 |  | 12/31/2010 | 2397388.95 | 0.22
1126 | Georgia | ATKINSON |  | 1 | 0009366 | This project is located approximately four miles northwest of Pearson, Georgia in Atkinson County. This project will construct a bridge replacement over Pudding Creek along County Road 42/Antioch Chur | Bridge Replacement | 07/28/2009 | 08/10/2009 | 06/30/2010 | 1528744.92 | 0.43
1127 | Georgia | FULTON | ATLANTA | 6 | 0009367 | This project is a bridge replacement on CR 85/Kimball Bridge Road two miles southeast of Alpharetta in Fulton County. The project is 0.554 miles long, consisting of removal of the existing Big Creek B | Bridge Replacement | 12/04/2009 |  | 09/30/2011 | 4491923.44 | 0.2
1128 | Georgia | COWETA | ATLANTA | 3 | 0009419 | This project is an intersection improvement in Coweta County. The project will realign the intersection of SR 16/Wells Street at County Road 157/Broad Street & Luther Bailey Road. The project will c | Safety/Traffic Management | 10/06/2009 | 10/15/2009 | 09/30/2010 | 1017617.62 | 0.38
1129 | Georgia | COFFEE |  | 1 | 0009421 | This project will replace the structurally deficient bridge on SR 135/US 221 over Tiger Creek in Coffee County. The existing 108 X 24' bridge was constructed in 1947 and will be replaced with a new 1 | Bridge Replacement | 09/24/2009 | 10/29/2009 | 08/31/2010 | 1332580.3 | 0.3
1130 | Georgia | PIERCE |  | 1 | 0009422 | This is an intersection improvement project in Pierce County. This project will realign the intersection of SR 203/Strickland Street and County Road 309/Old Alma Road and with County Road 236 to impr | Pavement Improvement | 09/28/2009 |  | 06/30/2010 | 1067196.42 | 0.36
1131 | Georgia | FAYETTE | ATLANTA | 3 | 0009452 | This project is the construction of the widening and improvement of SR 74 in Fayette County, from SR 85 to Cooper Circle Road (approximately 1.85 miles south of Crosstown Drive) for a total length of | Pavement Widening | 10/26/2009 | 11/17/2009 | 12/31/2011 | 21538931.42 | 3
1132 | Georgia | TROUP |  | 3 | 0009453 | This project will construct phase two of the South LaGrange Loop, a new roadway in Troup County. The roadway will be a bypass around the southern portion of the City of LaGrange. The limits extend f | New Construction | 11/06/2009 | 11/23/2009 | 12/31/2011 | 22927146.25 | 4.15
1133 | Georgia | COOK |  | 1 | 0011061 | This project is a bridge replacement in Cook County. This project will replace the structurally deficient bridge on SR 7/US 41 over Giddens Mill Creek with a new reinforced concrete bridge. The exis | Bridge Replacement | 09/24/2009 | 09/24/2009 | 09/30/2010 | 2215295.17 | 0.209
1134 | Georgia | PIKE |  | 3 | 0051034 | This project is a safety intersection improvement in Pike County. The purpose of this project is to improve the safety and operation by realigning the intersection of SR 18/SR 109 and SR 74. Current | Pavement Improvement | 09/30/2009 | 10/29/2009 | 07/31/2010 | 1401078.13 | 0.52
1135 | Georgia | CHEROKEE | ATLANTA | 6 | 0057017 | This is a bridge replacement project in Cherokee County. This project will replace a narrow and structurally deficient bridge on Howell Bridge Road (CR 107) over Sharp Mountain Creek, 2 miles southwe | Bridge Replacement | 10/26/2009 |  | 12/31/2010 | 1497991.35 | 0.13
1136 | Georgia | COLQUITT |  | 8 | 0071028 | This project will replace the structurally deficient bridge on CR 186/Hagin Still Road over the Ochlockonee River in Colquitt County. The bridge is located southeast of the city of Doerun. The 140'x | Bridge Replacement | 09/24/2009 | 09/28/2009 | 08/31/2010 | 1279473.46 | 0.23
1137 | Georgia | DOUGHERTY | ALBANY | 2 | 0133005 | This project is a roadway widening in Dougherty County. This project widens and reconstructs SR 234/Gillionville Road from Eight Mile Road to Lockett Station Road. The existing two lane roadway wil | Pavement Widening | 08/19/2009 | 09/25/2009 | 09/30/2011 | 8348399.01 | 4.34
1138 | Georgia | WILKINSON |  | 8 | 0540019 | This project is the construction of the North Gordon Bypass, a new roadway, from SR 57 at the Twiggs/Wilkinson County Line to SR 243 at Lake Tchucoloako. The total length of project is 7.2 miles. The | New Construction | 09/01/2009 | 10/26/2009 | 07/31/2012 | 36239872.37 | 7.2
1139 | Georgia | CHATHAM | SAVANNAH | 12 | 0641049 | This is a bridge replacement project in Chatham County. This project will replace the US 17/SR 25 bridge over Norfolk Southern Railroad approximately 5.5 miles north of Savannah in Port Wentworth. T | Bridge Replacement | 07/27/2009 | 07/28/2009 | 05/31/2012 | 4231018.62 | 0.46
1140 | Georgia | BIBB | MACON | 8 | 0661036 | This project will construct auxiliary lanes on SR 87 in Bibb County. The project will reconstruct SR 87/US 23 from an existing four-lane roadway with a 40-ft depressed median with rural shoulders to | Pavement Improvement | 09/24/2009 | 11/12/2009 | 04/30/2011 | 9140469.98 | 2.12
1141 | Georgia | GWINNETT | ATLANTA | 7 | 0852176 | This project is the construction of an Advanced Traffic Management System along Interstate 85 in Gwinnett County. The proposed project involves the installation of fiber optic cable and High Density | Safety/Traffic Management | 09/18/2009 |  | 10/31/2010 | 2164670.45 | 4.91
1142 | Georgia | GWINNETT | ATLANTA | 7 | 0998001 | This project will rehabilitate and improve the safety at the bridge over I-85 and widening of SR 324 approaching the bridge in Gwinett County. | Bridge Replacement | 09/04/2009 | 10/02/2009 | 05/31/2012 | 12413620.07 | 1.6
1143 | Georgia | CLAYTON | ATLANTA | 13, 5 | 6751001 | This project will install the NaviGAtor system along I-675 from I-75 to I-285 in Clayton, Dekalb and henry Counties. Included in the project will be two changeable message signs, vehicle detection co | Safety/Traffic Management | 08/18/2009 | 08/18/2009 | 12/31/2010 | 1894362.88 | 10.7
1144 | Georgia | DOUGLAS | ATLANTA | 13 | 7532950 | This project is a bridge replacement in Douglas County. The proposed project consists of replacing the existing structurally deficient bridge (48.43 Suff. Rating) along County Road 815/Anneewakee Roa | Bridge Replacement | 09/24/2009 | 10/23/2009 | 12/31/2010 | 2051456.6 | 0.419
1145 | Georgia | DE KALB | ATLANTA | 4 | 9014024 | This project is a culvert replacement in Dekalb County. The proposed project will replace the existing box culvert and wooden pedestrian bridge on SR 155/Candler Road at Shoal Creek with a larger con | Bridge Replacement | 09/23/2009 | 11/12/2009 | 12/31/2010 | 1308637.48 | 0.26
1146 | Georgia | DOUGLAS | ATLANTA | 13 | 9398001 | This project is the construction of intersection improvements on Kings Highway at Central Church Road in Douglas County. The project will provide a separate left turn bay for westbound movements onto | Safety/Traffic Management | 09/18/2009 | 11/12/2009 | 04/30/2011 | 778753.72 | 0.33
1147 | Georgia | ROCKDALE | ATLANTA | 4 | M003836 | This is a maintenance construction project in Rockdale County. This project is the milling and resurfacing of SR 162 from the Newton County Line to County Road 666/Dogwood Drive. This section of SR | Pavement Improvement | 07/17/2009 | 08/13/2009 | 05/31/2010 | 594191.33 | 2.39
1148 | Georgia | JACKSON |  | 10 | M003862 | This project is a maintenance construction project in Jackson County. This project is the resurfacing of SR 82. This section of SR 82 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 07/20/2009 |  | 05/31/2010 | 1009579.73 | 6.2
1149 | Georgia | QUITMAN |  | 2 | M003896 | This project is a maintenance construction project in Quitman and Randolph Counties. This project is the milling and resurfacing of SR 50. This section of SR 50 needs resurfacing because the existing | Pavement Improvement | 06/19/2009 |  | 03/31/2010 | 2542654.65 | 11.26
1150 | Georgia | COFFEE |  | 1 | M003897 | This is a maintenance construction project in Coffee County. This project is the milling and resurfacing of SR 31/US 441 from SR 135 to City Street 787/McNeal Drive. This section of SR 31 needs resur | Pavement Improvement | 07/06/2009 | 08/26/2009 | 04/30/2010 | 665267.93 | 2.4
1151 | Georgia | DOUGHERTY | ALBANY | 2 | M003898 | This project is a maintenance construction project in Dougherty County. The project is the milling and resurfacing of SR 133 from SR 91 to the Lee County Line. This section of SR 133 needs resurfacin | Pavement Improvement | 06/19/2009 | 07/30/2009 | 01/31/2010 | 224974.26 | 1.07
1152 | Georgia | MADISON |  | 10 | M003906 | This is a maintenance construction project in Madison County. The project is the resurfacing of SR 98 from SR 8/US 29 to SR 72. Ths section of SR 98 needs resurfacing because the existing pavement is | Pavement Improvement | 06/25/2009 | 07/25/2009 | 03/31/2010 | 825383.1 | 7.4
1153 | Georgia | TOWNS |  | 10 | M003907 | This is a maintenance construction project in Towns County. The project is the milling and rsurfacing of SR 75 from SR 2 to the North carolina State Line. This section of SR 75 needs resurfacing beca | Pavement Improvement | 06/19/2009 | 08/17/2009 | 03/31/2010 | 498265.27 | 3.4
1154 | Georgia | HALL | GAINESVILLE | 9 | M003908 | This is a maintenance construction project in Hall County. The project is the resurfacing of SR 283 from SR 60 to SR 52/Dahlonega Highway. This section of SR 283 needs resurfacing because the existin | Pavement Improvement | 06/25/2009 | 08/24/2009 | 04/30/2010 | 1289894.36 | 9.3
1155 | Georgia | MONTGOMERY |  | 1, 12 | M003909 | This project is a maintenance construction project in Jeff Davis and Montgomery Counties. This project is the resurfacing of SR 135. This section of SR 135 needs resurfacing because the existing pave | Pavement Improvement | 07/17/2009 |  | 05/31/2010 | 3147915.33 | 18.57
1156 | Georgia | CHATHAM | SAVANNAH | 12 | M003910 | This project is a maintenance construction project in Chatham County. This project is the milling and resurfacing of SR 307. This section of SR 307 needs resurfacing because the existing pavement is | Pavement Improvement | 06/30/2009 |  | 04/30/2010 | 1311565.27 | 5.94
1157 | Georgia | CHATHAM | SAVANNAH | 12 | M003911 | This project is a maintenance construction project in Chatham County. This project is the milling and resurfacing of SR 30. This section of SR 30 needs resurfacing because the existing pavement is de | Pavement Improvement | 06/30/2009 |  | 04/30/2010 | 182427.84 | 0.98
1158 | Georgia | BACON |  | 1 | M003914 | This project is a maintenance construction project in Bacon County. This project is the milling and resurfacing of SR 32. This section of SR 32 needs resurfacing because the existing pavement is dete | Pavement Improvement | 06/30/2009 |  | 03/31/2010 | 1152581.33 | 4.56
1159 | Georgia | CHARLTON |  | 1 | M003916 | This is a maintenance construction project in Charlton County. The project is the resurfacing of SR 4/US 1 from north of SR 4 to the Ware County Line. This section of SR 4 needs resurfacing because t | Pavement Improvement | 06/25/2009 | 07/13/2009 | 04/30/2010 | 4132510.48 | 11.73
1160 | Georgia | CHARLTON |  | 1 | M003917 | This is a maintenance construction project in Charlton County. This project is the resurfacing of SR 40 Connector from SR 40 to SR 4. This section of SR 40 Connector needs resurfacing because the exis | Pavement Improvement | 06/25/2009 | 07/13/2009 | 04/30/2010 | 197452.66 | 1.33
1161 | Georgia | WALKER |  | 9 | M003920 | This project is a maintenance construction project in Walker County. This project is the milling and resurfacing of SR 1 Businesss. This section of SR 1 Business needs resurfacing because the existin | Pavement Improvement | 07/06/2009 | 09/10/2009 | 04/30/2010 | 721762.53 | 3.34
1162 | Georgia | BARTOW |  | 11 | M003921 | This is a maintenance construction project in Bartow County. This project is the milling and resurfacing of SR 3 from south of Peachtree Street to north of MLK Jr. Drive in Cartersville. This sectio | Pavement Improvement | 06/25/2009 | 08/18/2009 | 04/30/2010 | 745586.75 | 1.63
1163 | Georgia | CHEROKEE | ATLANTA | 6 | M003923 | This project is a maintenance construction project in Cherokee County. This project is the resurfacing on SR 140. This section of SR 140 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 06/25/2009 | 09/08/2009 | 03/31/2010 | 1762634.82 | 10.61
1164 | Georgia | SUMTER |  | 2 | M003932 | This is a maintenance construction project in Sumter County. This project is the milling and resurfacing of SR 27 West from SR 27 to SR 3/US 19 in Americus. This section of SR 27 West needs resurfaci | Pavement Improvement | 06/25/2009 | 08/02/2009 | 12/31/2009 | 593223.49 | 2.13
1165 | Georgia | SUMTER |  | 2 | M003933 | This is a maintenance construction project in Sumter County. This project is the milling and resurfacing of SR 27 from SR 3/US 19 to SR 27 West/SR 30 in Americus. This section of SR 27 needs resurfac | Pavement Improvement | 06/25/2009 | 08/02/2009 | 12/31/2009 | 616798.09 | 2.136
1166 | Georgia | RICHMOND | AUGUSTA (SC) | 12 | M003935 | This project is a maintenance construction project in Richmond County. This project is the milling and resurfacing of SR 28. This section of SR 28 needs resurfacing because the existing pavement is d | Pavement Improvement | 10/26/2009 |  | 06/30/2010 | 1295804.9 | 2.72
1167 | Georgia | DODGE |  | 8 | M003938 | This is a maintenance construction project in Dodge County. This project is the milling and resurfacing of SR 117 from south of Front Street to Sugar Creek Bridge. This section of SR 117 needs resurf | Pavement Improvement | 06/22/2009 | 07/09/2009 | 03/31/2010 | 2273844.08 | 13.62
1168 | Georgia | JEFFERSON |  | 12 | M003941 | This project is a maintenance construction project in Jefferson County. This project is the milling and resurfacing of SR 4. This section of SR 4 needs resurfacing because the existing pavement is de | Pavement Improvement | 10/26/2009 |  | 08/31/2010 | 3438984.42 | 13.61
1169 | Georgia | FULTON | ATLANTA | 6 | M003942 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 9 from the Chattahoochee River to Marietta Highway. This section of SR 9 needs resurfaci | Pavement Improvement | 06/25/2009 | 08/02/2009 | 04/30/2010 | 296263.38 | 1.21
1170 | Georgia | FULTON | ATLANTA | 5 | M003943 | This is a maintenance construction project in Clayton and Fulton Counties. This project is the milling and resurfacing of SR 3/US 19 from Interstate 285 to City Street 3096/Cleveland Avenue. This sec | Pavement Improvement | 06/26/2009 | 07/07/2009 | 03/31/2010 | 937841.23 | 4.17
1171 | Georgia | FULTON | ATLANTA | 6 | M003945 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 9 from Abernathy Road to the Chattahoochee River. This section of SR 9 needs resurfacing | Pavement Improvement | 06/25/2009 | 08/02/2009 | 04/30/2010 | 1558771.05 | 5.2
1172 | Georgia | DE KALB | ATLANTA | 4, 7 | M003946 | This project is a maintenance construction project in DeKalb and Gwinnett Counties. This project is the milling and resurfacing of SR 10. This section of SR 10 needs resurfacing because the existing | Pavement Improvement | 08/14/2009 |  | 06/30/2010 | 2953476.64 | 3.83
1173 | Georgia | FULTON | ATLANTA | 13 | M003947 | This project is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 14 Spur. This section of SR 14 Spur needs resurfacing because the existing pavem | Pavement Improvement | 08/07/2009 |  | 06/30/2010 | 894468.65 | 1.61
1174 | Georgia | FULTON | ATLANTA | 5 | M003948 | This is a maintenance construction project in Fulton County. This project is the resurfacing of SR 139 from West Whitehall Street to County Road 4176/Cascade Avenue. This section of SR 139 needs resu | Pavement Improvement | 06/19/2009 | 08/11/2009 | 03/31/2010 | 515323.56 | 1.21
1175 | Georgia | FULTON | ATLANTA | 5 | M003949 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 54 from north of I-285 to University Avenue. This section of SR 54 needs resurfacing bec | Pavement Improvement | 08/07/2009 | 09/01/2009 | 06/30/2010 | 1249406.17 | 5.87
1176 | Georgia | FULTON | ATLANTA | 13 | M003950 | This project is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 92. This section of SR 92 needs resurfacing because the existing pavement is det | Pavement Improvement | 06/25/2009 | 09/23/2009 | 03/31/2010 | 941806.6 | 3.83
1177 | Georgia | HALL | GAINESVILLE | 9 | M003957 | This project is a maintenance construction project in Hall County. This project is the resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 06/25/2009 | 09/10/2009 | 04/30/2010 | 1190457.2 | 3
1178 | Georgia | DAWSON |  | 9 | M003958 | This project is a maintenance construction project in Dawson County. This project is the resurfacing of SR 53. This section of SR 53 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 06/25/2009 | 11/19/2009 | 03/31/2010 | 1242103.96 | 6.8
1179 | Georgia | HABERSHAM |  | 10 | M003959 | This project is a maintenance construction project in Habersham County. This project is the resurfacing of SR 384. This section of SR 384 needs resurfacing because the existing pavement is deteriorat | Pavement Improvement | 06/25/2009 | 11/02/2009 | 03/31/2010 | 645925.17 | 4.2
1180 | Georgia | FRANKLIN |  | 10 | M003960 | This is a maintenance construction project in Franklin County. This project is the resurfacing of SR 51 from SR 59 to County Road 168/Hale Crossing Road. This section of SR 51 needs resurfacing becau | Pavement Improvement | 06/25/2009 | 08/25/2009 | 03/31/2010 | 1045067.2 | 9.9
1181 | Georgia | WHITE |  | 10, 9 | M003961 | This is a maintenance construction project in Habersham and White Counties. The project is the resurfacing of SR 356 from SR 17 in White County to SR 197 in Habersham County. This section of SR 356 n | Pavement Improvement | 06/25/2009 | 07/20/2009 | 04/30/2010 | 1804857.39 | 10.83
1182 | Georgia | FORSYTH | ATLANTA | 9 | M003964 | This project is a maintenance construction project in Forsyth County. This project is the milling and resurfacing of SR 9. This section of SR 9 needs resurfacing because the existing pavement is dete | Pavement Improvement | 06/25/2009 | 09/30/2009 | 03/31/2010 | 1996234.06 | 9.8
1183 | Georgia | STEPHENS |  | 10 | M003965 | This project is a maintenance construction project in Banks, Franklin and Stephens Counties. This project is the resurfacing of SR 63. This section of SR 63 needs resurfacing because the existing pav | Pavement Improvement | 07/21/2009 | 09/08/2009 | 05/31/2010 | 1911803.7 | 12.63
1184 | Georgia | BANKS |  | 10 | M003966 | This project is a maintenance construction project in Banks County. This project is the resurfacing of SR 164. This section of SR 164 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 06/25/2009 | 11/04/2009 | 04/30/2010 | 794418.78 | 4.8
1185 | Georgia | CHEROKEE | ATLANTA | 11, 6 | M003967 | This is an Interstate 575 maintenance construction project in Cobb and Cherokee Counties. This project is the milling and resurfacing of I-575/SR 417 from I-75 in Cobb County to the Etowah River in C | Pavement Improvement | 06/25/2009 | 07/13/2009 | 05/31/2010 | 19601134.47 | 19.79
1186 | Georgia | MARION |  | 2 | M003968 | This is a maintenance construction project in Marion County. This project is the milling and resurfacing of SR 137 from City Street 505/McDuffie Street to the Taylor County line. This section of SR 1 | Pavement Improvement | 06/25/2009 | 09/09/2009 | 04/30/2010 | 1407634.2 | 10.53
1187 | Georgia | CRAWFORD |  | 2 | M003969 | This is a maintenance construction project in Crawford and Peach Counties. The project is the milling and resurfacing of SR 7 from SR 96 in Peach County to SR 22/US 80 in Crawford County. This sectio | Pavement Improvement | 07/17/2009 | 08/06/2009 | 04/30/2010 | 2363595.66 | 14.37
1188 | Georgia | SCHLEY |  | 2 | M003970 | This project is a maintenance construction project in Schley and Sumter Counties. This project is the milling and resurfacing of SR 153. This section of SR 153 needs resurfacing because the existing | Pavement Improvement | 06/25/2009 |  | 04/30/2010 | 1433599.39 | 8.1
1189 | Georgia | HENRY | ATLANTA | 3 | M003971 | This is a maintenance construction project in Henry County. This project is the milling and resurfacing of SR 155 from the Spalding County line to SR 20/SR 81. This section of SR 155 needs resurfacin | Pavement Improvement | 06/25/2009 | 08/04/2009 | 04/30/2010 | 2069902.16 | 8.8
1190 | Georgia | JASPER |  | 8 | M003972 | This project is a maintenance construction project in Jasper County. This project is the milling and resurfacing of SR 83. This section of SR 83 needs resurfacing because the existing pavement is dete | Pavement Improvement | 06/25/2009 | 08/31/2009 | 04/30/2010 | 1960212.75 | 12.79
1191 | Georgia | RICHMOND | AUGUSTA (SC) | 10, 12 | M003973 | This project is a maintenance construction project in Richmond County. This project is the milling and resurfacing of SR 4. This section of SR 4 needs resurfacing because the existing pavement is det | Pavement Improvement | 08/20/2009 | 10/20/2009 | 06/30/2010 | 4028596.8 | 10.2
1192 | Georgia | JASPER |  | 8 | M003974 | This is a maintenance construction project in Jasper County. This project is the milling and resurfacing of SR 16 from the Butts County line to SR 11 South. This section of SR 16 needs resurfacing be | Pavement Improvement | 06/25/2009 | 08/03/2009 | 04/30/2010 | 1532619.83 | 8.95
1193 | Georgia | PUTNAM |  | 10 | M003975 | This project is a maintenance construction project in Putnam County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is dete | Pavement Improvement | 06/19/2009 | 09/28/2009 | 04/30/2010 | 1787960.7 | 8.3
1194 | Georgia | TWIGGS |  | 8 | M003976 | This project is a maintenance construction project in Bleckley, Laurens and Twiggs Counties. This project is the concrete slab replacement of I-16/SR 404. This slab replacement of I-16 is needed becau | Pavement Improvement | 11/19/2009 |  | 05/31/2011 | 22597976.74 | 15.32
1195 | Georgia | WARE |  | 1 | M003978 | This is a maintenance construction project in Ware County. This project is the milling and resurfacing of SR 4 Business/US 1 from south of County Road 341/Short Street to north of County Road 255/Smi | Pavement Improvement | 06/25/2009 | 07/20/2009 | 04/30/2010 | 1064995.62 | 5.79
1196 | Georgia | EFFINGHAM |  | 12 | M003979 | This project is a maintenance construction project in Effingham County. This project is the resurfacing of SR 17. This section of SR 17 needs resurfacing because the existing pavement is deterioratin | Pavement Improvement | 06/30/2009 | 09/15/2009 | 04/30/2010 | 741328.89 | 4.12
1197 | Georgia | CHARLTON |  | 1 | M003980 | This project is a maintenance construction project in Brantley and Charlton Counties. This project is the resurfacing of SR 23. This section of SR 23 needs resurfacing because the existing pavement is | Pavement Improvement | 07/06/2009 |  | 04/30/2010 | 3681244.89 | 23.15
1198 | Georgia | BRYAN |  | 1 | M003981 | This project is a maintenance construction project in Bryan County. This project is the resurfacing of SR 25. This section of SR 25 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 08/20/2009 | 11/19/2009 | 06/30/2010 | 1623997.7 | 4.28
1199 | Georgia | ROCKDALE | ATLANTA | 4 | M003983 | This is a maintenance construction project in Rockdale County. This project is the resurfacing of SR 20 from County Road 435/Sigman Road to SR 138. This section of SR 20 needs resurfacing because the | Pavement Improvement | 06/25/2009 | 07/08/2009 | 04/30/2010 | 292742.36 | 1.34
1200 | Georgia | ROCKDALE | ATLANTA | 3, 4 | M003984 | This project is a maintenance construction project in Rockdale County. This project is the resurfacing of SR 20. This section of SR 20 needs resurfacing because the existing pavement is deteriorating | Pavement Improvement | 08/07/2009 | 09/08/2009 | 06/30/2010 | 2169087.78 | 6.99
1201 | Georgia | DE KALB | ATLANTA | 4 | M003985 | This project is a maintenance construction project in DeKalb County. This project is the resurfacing of SR 236/LaVista Road. This section of SR 236 needs resurfacing because the existing pavement is | Pavement Improvement | 08/17/2009 | 09/08/2009 | 06/30/2010 | 976902.07 | 2.4
1202 | Georgia | COBB | ATLANTA | 11 | M003986 | This project is a maintenance construction project in Cobb County. This project is the resurfacing of SR 360. This section of SR 360 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 08/07/2009 |  | 06/30/2010 | 501006.53 | 2.97
1203 | Georgia | WEBSTER |  | 2 | M003989 | This project is a maintenance construction project in Marion and Webster Counties. This project is the resurfacing of SR 41. This section of SR 41 needs resurfacing because the existing pavement is d | Pavement Improvement | 07/20/2009 |  | 05/31/2010 | 1817639.78 | 12.57
1204 | Georgia | TAYLOR |  | 2 | M003990 | This project is a maintenance construction project in Crawford and Taylor Counties. This project is the resurfacing of SR 128. This section of SR 128 needs resurfacing because the existing pavement i | Pavement Improvement | 06/25/2009 |  | 04/30/2010 | 2088691.24 | 14.09
1205 | Georgia | HARRIS |  | 3 | M003991 | This is a maintenance construction project in Harris County. This project is the resurfacing of SR 18 from SR 219 to SR 1/US 27. This section of SR 18 needs resurfacing because the existing pavement | Pavement Improvement | 06/25/2009 | 08/06/2009 | 04/30/2010 | 1763681.6 | 11.48
1206 | Georgia | GREENE |  | 10 | M003992 | This is a maintenance construction project in Greene County. The project is the resurfacing of SR 44 from the Putnam County line to SR 12. This section of SR 44 needs resurfacing because the existing | Pavement Improvement | 06/19/2009 | 08/11/2009 | 04/30/2010 | 2465038.45 | 11.45
1207 | Georgia | RICHMOND | AUGUSTA (SC) | 12 | M003993 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 56 Spur. This section of SR 56 Spur needs resurfacing because the existing pavement is det | Pavement Improvement | 11/30/2009 |  | 09/30/2010 | 3576406.9 | 6.58
1208 | Georgia | BRYAN |  | 1 | M004000 | This project is a maintenance construction project in Bryan County. This project is the resurfacing of SR 30/US 280. This section of SR 30 needs resurfacing because the existing pavement is deteriora | Pavement Improvement | 07/20/2009 | 09/16/2009 | 05/31/2010 | 2039028.08 | 8.85
1209 | Georgia | WHEELER |  | 1, 12 | M004001 | This project is a maintenance construction project in Montgomery and Wheeler Counties. This project is the resurfacing of SR 30. This section of SR 30 needs resurfacing because the existing pavement | Pavement Improvement | 07/17/2009 | 10/09/2009 | 05/31/2010 | 1904208.01 | 11.52
1210 | Georgia | WHEELER |  | 1 | M004003 | This project is a maintenance construction project in Wheeler County. This project is the resurfacing of SR 126. This section of SR 126 needs resurfacing because the existing pavement is deterioratin | Pavement Improvement | 07/20/2009 |  | 05/31/2010 | 1795111.71 | 12.09
1211 | Georgia | WILKES |  | 10 | M004006 | This project is a maintenance construction project in Lincoln and Wilkes Counties. This project is the resurfacing of SR 47. This section of SR 47 needs resurfacing because the existing pavement is d | Pavement Improvement | 09/21/2009 |  | 07/31/2010 | 2458228.56 | 15.69
1212 | Georgia | RICHMOND | AUGUSTA (SC) | 10 | M004012 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 104. This section of SR 104 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 151609.12 | 0.45
1213 | Georgia | RICHMOND | AUGUSTA (SC) | 10 | M004013 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 104 East. This section of SR 104 East needs resurfacing because the existing pavement is d | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 144882.58 | 0.44
1214 | Georgia | FRANKLIN |  | 10 | M004014 | This projects provides maintenance construction on I-85 in Franklin and Hart Counties. This project is the milling and resurfacing of I-85/SR 403 from south of SR 17 in Franklin County to the South C | Pavement Improvement | 09/03/2009 |  | 07/31/2010 | 6116052.98 | 7.12
1215 | Georgia | HALL | GAINESVILLE | 9 | M004015 | This project is a maintenance construction project in Hall County. This project is the removal of selected concrete slabs on SR 365. The reason for removal and replacement of the selected concrete sl | Pavement Improvement | 07/29/2009 | 11/12/2009 | 05/31/2010 | 2273178.2 | 7.97
1216 | Georgia | HOUSTON | WARNER ROBINS | 8 | M004021 | This project is a maintenance construction project in Houston County. This project is the resurfacing of SR 11 Business. This section of SR 11 Business needs resurfacing because the existing pavement | Pavement Improvement | 08/17/2009 |  | 04/30/2010 | 850102.43 | 4.5
1217 | Georgia | PULASKI |  | 8 | M004025 | This project is a maintenance construction project in Pulaski County. This project is the resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 11/23/2009 |  | 09/30/2010 | 1689883.06 | 10.58
1218 | Georgia | MERIWETHER |  | 3 | M004027 | This project is a maintenance construction project in Meriwether County. This project is the resurfacing of SR 85. This section of SR 85 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 12/04/2009 |  | 09/30/2010 | 1712474.03 | 11.1
1219 | Georgia | DOOLY |  | 2 | M004028 | This project is a maintenance construction project in Dooly County. This project is the resurfacing of SR 27. This section of SR 27 needs resurfacing because the existing pavement is deteriorating. S | Pavement Improvement | 11/23/2009 |  | 09/30/2010 | 1863860.66 | 11.76
1220 | Georgia | FAYETTE | ATLANTA | 3 | M004029 | This project is a maintenance construction project in Fayette County. This project is the resurfacing of SR 85. This section of SR 85 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 11/19/2009 |  | 09/30/2010 | 2125652.41 | 9.88
1221 | Georgia | BIBB | MACON | 8 | M004030 | This project is a maintenance construction project in Bibb County. This project is the milling and resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deter | Pavement Improvement | 11/19/2009 |  | 08/31/2010 | 1272250 | 5.33
1222 | Georgia | COWETA | ATLANTA | 3 | M004031 | This project is a maintenance construction project in Coweta County. This project is the resurfacing of SR 154. This section of SR 154 needs resurfacing because the existing pavement is deteriorating | Pavement Improvement | 11/24/2009 |  | 09/30/2010 | 1622334.38 | 8.36
1223 | Georgia | UPSON |  | 3 | M004032 | This project is a maintenance construction project in Lamar and Upson Counties. This project is the resurfacing of SR 36. This section of SR 36 needs resurfacing because the existing pavement is dete | Pavement Improvement | 11/19/2009 |  | 09/30/2010 | 2538255 | 15.03
1224 | Georgia | LAMAR |  | 3, 8 | M004033 | This project is a maintenance construction project in Lamar and Monroe Counties. This project is the resurfacing of SR 7. This section of SR 7 needs resurfacing because the existing pavement is deter | Pavement Improvement | 11/19/2009 |  | 09/30/2010 | 2262804.83 | 15
1225 | Georgia | BRANTLEY |  | 1 | M004040 | This project is a maintenance construction project in Brantley County. This project is the resurfacing of SR 520. This section of SR 520 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 08/07/2009 |  | 06/30/2010 | 979733.41 | 3.5
1226 | Hawaii | HONOLULU | HONOLULU | 1 | 0001036 | Install and Upgrade traffic signals, including ADA improvements, signs, markings and interconnects (Komo Mai St & Hoomalu St, Waiakamilo Rd & McNeil St, N Beretania St & Aala St, Kiluea Ave, Lanikuha | Safety/Traffic Management | 12/21/2009 |  | 08/03/2011 | 3670845.6 | 0
1227 | Hawaii | HONOLULU |  | 1 | 0011250 | Upgrade the Farrington Highway and Makakilo Separation structures over the H-1 freeway to better resist earthquake damage. (Farrington Hwy Separation) | Bridge Improvement | 07/13/2009 | 07/13/2009 | 01/04/2010 | 865200 | 0
1228 | Hawaii | HONOLULU | HONOLULU | 1 | 0011262 | Install longitudinal dowels into concrete sections, repair and smoothen concrete pavement at two major locations on the Interstate Route H-1 freeway from MP 2.4 to 3.46 and MP 24.9 to 26.4. | Pavement Improvement | 01/29/2010 |  | 03/15/2011 | 6350000 | 0
1229 | Hawaii | HAWAII |  | 2 | 0192059 | Remove and dispose of lead-based paint and rust from steel members and paint them. Work also includes repairing/replacing steel members that need repair work. (Kukaiau Bridge MP33.6, Kuwaikahi Bridge | Bridge Improvement | 09/08/2009 | 09/08/2009 | 04/07/2011 | 4301949.3 | 14.2
1230 | Hawaii | MAUI |  | 2 | 0311011 | Extend the life of the pavement and provide a smooth surface in areas that are starting to show distress by removal of the top layer and repaving. | Pavement Improvement | 08/31/2009 | 10/30/2009 | 02/23/2010 | 2979480 | 0
1231 | Hawaii | MAUI |  | 2 | 0360010 | Extending the life of the pavement and provide a smooth surface in areas that are starting to show distress by providing a surface seal. | Pavement Improvement | 08/26/2009 | 09/18/2009 | 10/29/2009 | 619301 | 3.32
1232 | Hawaii | MAUI |  | 2 | 0460014 | Resurface and reconstruct damaged areas of the pavement. Safety (including guardrail and shoulder improvements) and ADA improvements could be included. | Pavement Improvement | 08/26/2009 | 09/21/2009 | 10/22/2009 | 2688406 | 1.96
1233 | Hawaii | MAUI |  | 2 | 0470006 | Extend the life of the pavement and provide a smooth surface in areas that are starting to show distress by removal of the top pavement layer and repaving. | Pavement Improvement | 08/26/2009 | 10/30/2009 | 10/29/2009 | 1061781 | 5.79
1234 | Hawaii | MAUI |  | 2 | 0480003 | Resurface and reconstruct damaged areas of the pavement. Safety (including guardrail and shoulder improvements) on Farrington Avenue (2.44 miles) and Puupeela Avenue (1.21 miles) | Pavement Improvement | 12/10/2009 |  | 03/16/2009 | 5403802 | 3.65
1235 | Hawaii | KAUAI |  | 2 | 0561052 | Reconstruct weakened pavement areas, cold plane, resurface, adjust utility boxes, & install guardrails, pavement markings, & traffic signs on Kuhio Hwy, Rte 56, between MP 9.0 and MP 10.0. | Pavement Improvement | 07/20/2009 | 07/24/2009 | 10/13/2009 | 1021416 | 1
1236 | Hawaii | KAUAI |  | 2 | 0583001 | Reconstruct weakened pavement areas, remove existing surface and repave, adjust utilities, and install guardrails, pavement markings, and traffic signs on Maalo Road, Route 583 | Pavement Improvement | 07/20/2009 | 07/30/2009 | 09/29/2009 | 729083 | 1
1237 | Hawaii | HONOLULU | HONOLULU | 2 | 0831042 | Replace existing South Punaluu Stream Bridge with new concrete bridge. | Bridge Replacement | 08/26/2009 | 08/26/2009 | 09/01/2011 | 15298509.74 | 0
1238 | Hawaii | MAUI |  | 2 | 3405002 | Reconstruction and beautification of Market Street from Kahawai Street to Makuhau Road. Install drainage system, street lights, landscaping and irrigation. | Pavement Improvement | 11/27/2009 |  | 12/01/2010 | 2421989.55 | 0.17
1239 | Idaho | IDAHO |  | 1 | 4110137 | This project will add a climbing lane up the Whitebird Grade by widening 2.6 miles of US-95 in Idaho County. | Pavement Widening | 03/03/2009 | 03/03/2009 | 09/30/2011 | 4129008 | 2.619
1240 | Idaho | IDAHO |  | 1 | 4110138 | This project includes the complete removal and replacement of pavement and base on 12 miles of US-95 north of Grangeville in Idaho County. | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 6132936 | 9.059
1241 | Idaho | KOOTENAI |  | 1 | 5110137 | This project is to reconstruct the last 3.2 mile segment of US-95 in the City of Hayden in Kootenai County | Pavement Widening | 06/02/2009 | 06/02/2009 | 09/30/2011 | 8811426 | 4.46
1242 | Idaho | BANNOCK | POCATELLO | 2 | 7261100 | This project will repair or replace critical elements of the Custer Street Bridge in Bannock County. Improvements to the bridge deck and girders will extend the surface life of the structure and maint | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 306398 | 0
1243 | Idaho | GEM |  | 1 | 8001100 | This project will reconstruct and overlay 0.1 miles of Main Street and provide handicap accessible sidewalks in the City of Emmett, Gem County. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 753475 | 0.129
1244 | Idaho | BONNER |  | 1 | A001222 | This project will replace the Dover Bridge, an aging and deficient bridge, on US-95 in Bonner County. | New Bridge Construction | 04/22/2009 | 04/22/2009 | 09/30/2011 | 28407097 | 1.66
1245 | Idaho | BANNOCK |  | 2 | A007806 | This project will upgrade 31 miles of Southbound I-15 in Bannock County by laying an asphalt overlay, seal coat, and fog coat over the existing pavement. The project will also include deck repair at f | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 3276248 | 5
1246 | Idaho | BANNOCK |  | 2 | A007840 | This project will upgrade 31 miles of Northbound I-15 in Bannock County by laying an asphalt overlay, seal coat, and fog coat over the existing pavement. The project will also include deck repair at f | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 3532285 | 5
1247 | Idaho | FREMONT |  | 2 | A008624 | This project will add passing lanes in a mountainous area near Henry's Lake by widening 6.4 miles of US-20. | Pavement Widening | 04/22/2009 | 04/22/2009 | 09/30/2011 | 2405627 | 6.37
1248 | Idaho | CANYON, PAYETTE |  | 1 | A008955 | This project will repair the concrete pavement to provide a smooth driving surface on 5 miles of I-84 in Payette and Canyon Counties The project also includes repair and replacement of deficient guar | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 9917089 | 5.03
1249 | Idaho | JEFFERSON |  | 2 | A009387 | This project will reconstruct 1.7 miles of SH-48 in Rigby including new curb & gutter and handicap accessible sidewalks to the high school. | Pavement Widening | 04/22/2009 | 04/22/2009 | 09/30/2011 | 3661836 | 1.71
1250 | Idaho | LEWIS, IDAHO |  | 1 | A009795 | This project will repair the bridge deck and seal the driving surface on the bridge crossing Lawyers Creek on US-95 on the county line between Idaho and Lewis County. | Bridge Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 140729 | 0.173
1251 | Idaho | CLEARWATER |  | 1 | A009796 | This project will repair the bridge deck and preserve the driving surface with skid resistance aggregate and epoxy on State Highway 7 in the City of Orofino in Clearwater County. | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 265534 | 0.049
1252 | Idaho | CLEARWATER |  | 1 | A009797 | This project will repair the bridge deck and seal the driving surface on the bridge crossing the North Fork Clearwater River on State Highway 7 in Clearwater County. | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 61284 | 0
1253 | Idaho | ADA |  | 1 | A010489 | This project consists of constructing continuous sidewalk, to be in complliance with the Americans with Disabilities Act, on the east and west sides of a 0.3 mile section of West 8th Street in the Cit | Transportation Enhancements | 05/28/2009 | 05/28/2009 | 09/30/2011 | 147294 | 0.454
1254 | Idaho | ADA | BOISE CITY | 1 | A010537 | This project takes place at 7 locations throughout Ada County and will overlay a total of 11 miles of existing roadways including handicap accessible sidewalk ramps. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 2992775 | 12.51
1255 | Idaho | BANNOCK | POCATELLO | 2 | A010584 | This project will add one additional lane by widening 1.2 miles of congested urban interstate from the Chubbuck Interchange on I-86 to the Pocatello Creek Interchange on I-15 in Bannock County. | Pavement Improvement | 04/22/2009 | 04/22/2009 | 09/30/2011 | 10138499 | 1.2
1256 | Idaho | TWIN FALLS |  | 2 | A010917 | This project will eliminate traffic congestion in Twin Falls by constructing a new 5.1 mile long, 4-lane US-93 bypass, around the west side of the city. | New Construction | 04/22/2009 | 04/22/2009 | 09/30/2011 | 22045265 | 5.07
1257 | Idaho | LATAH |  | 1 | A011031 | This project will add passing lanes in the Moscow Mountain area by widening 1.3 miles of US 95 in Latah County. | Pavement Widening | 04/22/2009 | 04/22/2009 | 09/30/2011 | 3606204 | 1.338
1258 | Idaho | LATAH |  | 1 | A011558 | This project will add a thin lift overlay on 6.2 miles of State Highway 9 in Latah County. | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 1594109 | 6.222
1259 | Idaho | CANYON |  | 1 | A011584 | This project is to realign and reconstruct the west leg of the intersection of Franklin and 21st Avenue in the City of Caldwell in Canyon County. The project includes curb, gutter and handicap accecs | Pavement Widening | 12/30/2009 | 01/05/2010 | 09/30/2011 | 1273513 | 0.132
1260 | Idaho | BONNEVILLE, JEFFERSON |  | 2 | A011673 | This project will improve user operating conditions on an 8.5 mile segment of I-15 in Bonneville County by leveling the pavement, adding a plantmix overlay, and finishing with a seal coat and fog coat | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 1598530 | 8.475
1261 | Idaho | KOOTENAI | COEUR D ALENE | 1 | A011867 | This project will widen and completely reconstruct 0.5 miles of Hanley Avenue between Government Way and a new roundabout on 4th Street in the City of Dalton Gardens in Kootenai County. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 680971 | 0.49
1262 | Idaho | BANNOCK | POCATELLO | 2 | A011918 | This project will remove and replace existing bridge joints on Gould Street Bridge in the City of Pocatello and improve pavement markings along the roadway. | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 326168 | 0.229
1263 | Idaho | BONNEVILLE | IDAHO FALLS | 2 | A011920 | This project will seal coat the existing pavement and provide a skid resistant surface on 5.6 miles of local streets throughout Idaho Falls. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 09/30/2011 | 721474 | 5.598
1264 | Idaho | ADA |  | 1 | A011922 | This project takes place at 16 locations throughout Ada County and will overlay a total of 20 miles of existing roadways to improve operating conditions, preserve structural capacity, and extend the u | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 3948778 | 20.38
1265 | Idaho | ADA |  | 1 | A011924 | This project will improve the network for pedestrians throughout Ada County by improving existing sidewalks, pedestrian ramps, and curb & gutter sections at up to 122 intersections within the cities o | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 484218 | 0
1266 | Idaho | ADA | BOISE CITY | 2 | A011926 | This project will improve the network for pedestrians within Downtown Boise by improving existing sidewalks, pedestrian ramps, and curb and gutter sections at up to 49 intersections so they are in con | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 524260 | 0
1267 | Idaho | ADA | BOISE CITY | 1 | A011932 | This project will provde aesthetically pleasing landscaping to the newly constructed Ten Mile Interchange on I-84 in Canyon County. | Transportation Enhancements | 06/16/2009 | 06/16/2009 | 09/30/2011 | 1035759 | 1
1268 | Idaho | BOUNDARY |  | 1 | A011935 | This project will overlay 3 miles of Deep Creek Loop, a two lane roadway, in Boundary County to provide a safer traveling surface and prolong the life of the asphalt. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 498000 | 10.557
1269 | Idaho | SHOSHONE |  | 1 | A011936 | This project will overlay the existing pavement to improve roadway surface smoothness and will provide stormwater drainage pathways on 0.8 mile of Nine Mile Road in Shoshone County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 472498 | 2.273
1270 | Idaho | BENEWAH |  | 1 | A011937 | This project will pave the existing gravel roadway on 1.3 miles of the Benewah Creek Road corridor in Benewah County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 470542 | 1.64
1271 | Idaho | SHOSHONE |  | 1 | A011938 | This project will include repair of the existing pavement with a new pavement overlay on a 0.5 mile long segment in the City of Wallace in Shoshone County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 308167 | 0.912
1272 | Idaho | CLEARWATER |  | 1 | A011939 | This project includes a pavement seal coat on 14 miles of Cavendish Road in Clearwater County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 494963 | 14.345
1273 | Idaho | CLEARWATER |  | 1 | A011940 | This project will pave on top of existing gravel roadway on 0.8 miles of Musselshell Road in Clearwater County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 498085 | 1.5
1274 | Idaho | CLEARWATER |  | 1 | A011941 | This project will increase the life of the pavement on 2.6 miles of roadway in the City of Orofino in Clearwater County by adding asphalt leveling and a seal coat to provide skid resistance. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 221598 | 6.3
1275 | Idaho | IDAHO |  | 1 | A011942 | This project will remove and replace the pavement and aggregate base on 0.7 mile of local road in the City of Cottonwood, Idaho County, to improve the driving surface and extend the life of the pavem | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 500000 | 0.722
1276 | Idaho | PAYETTE |  | 1 | A011943 | This project will improve traffic flow and pedestrian safety near local schools in the City of Fruitland in Payette County with a pavement overlay, installing handicap accessible sidewalks, and improv | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 500000 | 1.108
1277 | Idaho | CANYON |  | 1 | A011944 | This project in Canyon County will repair the existing pavement and add a new asphalt overlay on a 1.5 mile segment of Notus Road from State Highway 19 to Red Top Road. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 500000 | 2
1278 | Idaho | GEM |  | 1 | A011945 | This project consists of an asphalt overlay on a 4 mile segment of the Ola Highway in Gem County to increase pavement longevity, improve the ride quality, and provide a safer road surface for the trav | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 495000 | 7
1279 | Idaho | ADAMS |  | 1 | A011946 | This project will overlay 1.6 miles and sealcoat 1.2 miles of Indian Valley Road in Adams County to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 457268 | 7.07
1280 | Idaho | LINCOLN |  | 2 | A011947 | This project will overlay 1.7 miles and sealcoat 2.9 miles of 600 West Road in Lincoln County to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 527112 | 4.561
1281 | Idaho | CASSIA |  | 2 | A011948 | This project will remove and recycle the existing pavement and gravel base on 1.2 miles of Old Highway 81 South Road in Cassia County to provide a safe and durable driving surface. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 500000 | 3.468
1282 | Idaho | TWIN FALLS |  | 2 | A011949 | This project will improve 0.2 mile of Center Street in the City of Kimberly, Twin Falls County, by removing the deteriorated roadway, constructing a new base, and laying new pavement. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 349510 | 0.37
1283 | Idaho | CAMAS |  | 2 | A011950 | This project in the City of Fairfield, Camas County, will repair areas of distressed pavement, install an overlay, and perform minor storm drainage improvements at intersections along 0.6 mile of Sold | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 451355 | 0.61
1284 | Idaho | BANNOCK | POCATELLO | 2 | A011951 | This project will remove and recycle the existing pavement and gravel base on a 1.2 mile segment of Mink Creek Road in Bannock County and will include both minor widening and an overlay. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 507740 | 1.933
1285 | Idaho | CARIBOU |  | 2 | A011952 | This project will improve the roadway and increase safety by adding new pedestrian crossing lights, replacing drainage structures, and adding a pavement overlay on 0.4 mile of local road in the City o | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 376547 | 0.426
1286 | Idaho | POWER |  | 2 | A011953 | This project will remove and recycle the existing pavement and gravel base on a 1 mile section of South Pleasant Valley Road in Power County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 499000 | 2.029
1287 | Idaho | BANNOCK |  | 2 | A011954 | This project will repair and overlay 0.4 mile of local roadway pavement and provide a new pedestrian crossing with crossing lights to improve user operating conditions on East Main Street in the City | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 289733 | 0.419
1288 | Idaho | FREMONT |  | 2 | A011955 | This project will seal coat the existing pavement and provide a skid resistant surface on a 4.5 mile segment of the Teton Highway in Fremont County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 269405 | 4.543
1289 | Idaho | CUSTER |  | 2 | A011956 | This project in Custor County will repair a 3.1 mile segment of Trail Creek Road and extend the pavement life by adding a thin overlay to the pavement. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 593627 | 2
1290 | Idaho | FREMONT |  | 2 | A011957 | This project will repair and overlay 0.5 mile of pavement on Main Street in City of St.Anthony, Fremont County and will include minor drainage improvements, replacement of traffic signal detection loo | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 588221 | 1.41
1291 | Idaho | CLARK |  | 2 | A011958 | This project will replace the asphalt gutter with a concrete gutter and will overlay the roadway to improve user operating conditions on a 0.5 mile segment of Main Street in the City of Dubois, Clark | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 373171 | 0.865
1292 | Idaho | STATEWIDE |  | 2 | A011960 | This project will provide for curation and management of artifacts including consolidation of the Hatwaii archaeological collection. This project will develop public outreach on archaeological displa | Transportation Enhancements | 06/16/2009 | 06/16/2009 | 09/30/2011 | 162960 | 0
1293 | Idaho | BOISE |  | 1 | A011961 | This project is to construct a wildlife/game crossing under US-21 in Boise County. | New Bridge Construction | 06/16/2009 | 06/16/2009 | 09/30/2011 | 613890 | 0
1294 | Idaho | STATEWIDE |  | 2 | A011964 | This project will construct 940 handicap ramps in Districts 1, 2, & 3 in accordance with the requirements of the Americans with Disabilities Act. It will be split into five separate projects for cons | Other | 06/16/2009 | 06/16/2009 | 09/30/2011 | 198811 | 0
1295 | Idaho | KOOTENAI |  | 2 | A011976 | This project is to repair 10 structures on Interstate 90 between Post Falls and the Washington State border in Kootenai County. These structures will have the top of the deck removed and replaced with | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 5828317 | 4.6
1296 | Idaho | KOOTENAI |  | 1 | A011979 | This project will construct 89 handicap ramps in the Coeur D'Alene area of District 1, in Benewah, Kootenai and Shoshone Counties, in accordance with the requirements of the Americans with Disabilitie | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 533422 | 0
1297 | Idaho | BONNER |  | 1 | A011980 | This project will construct 90 handicap ramps in the Sandpoint area of District 1, in Bonner County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 510608 | 0
1298 | Idaho | LATAH |  | 1 | A011981 | This project will construct 132 handicap ramps in the northern area of District 2, in Latah County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 783294 | 0
1299 | Idaho | IDAHO |  | 1 | A011982 | This project will construct 80 handicap ramps in the southern area of District 2, in Idaho County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 431301 | 0
1300 | Idaho | CANYON, GEM, PAYETTE, ADA |  | 1,2 | A011983 | This project will construct 127 handicap ramps in District 3, in Canyon, Gem, & Payette Counties, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 826750 | 0
1301 | Idaho | ADA | BOISE CITY | 2 | C009818 | This project, in the City of Boise, the existing I-84 Vista Interchange will be reconstructed into a Single Point Urban Interchange. | Pavement Widening | 04/22/2009 | 04/22/2009 | 09/30/2011 | 24029318 | 1.2
1302 | Illinois | WHITESIDE |  | 14 | 000S617 | This project will extend the pavement life by resurfacing a section of US 30 near the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 05/11/2009 | 05/26/2009 | 08/30/2009 | 884511 | 2.33
1303 | Illinois | WINNEBAGO | ROCKFORD | 16 | 000S618 | This project will extend the pavement life by resurfacing a section of US 20 Business Route in the city of Freeport (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/26/2009 | 10/30/2009 | 518841 | 1.35
1304 | Illinois | HENRY |  | 14 | 000S619 | This project will extend the pavement life by resurfacing 12 miles of US 6 between the cities of Geneseo and Atkinson (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/26/2009 | 10/30/2009 | 2777902 | 29.28
1305 | Illinois | STEPHENSON |  | 16 | 000S620 | This project will extend the pavement life by resurfacing sections of US 20 and IL 26 near the city of Freeport (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 05/26/2009 | 09/30/2009 | 1880580 | 5.15
1306 | Illinois | WINNEBAGO | ROCKFORD | 16 | 000S628 | This project will extend the pavement life by resurfacing a section of IL 2 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 04/30/2009 | 05/26/2009 | 10/30/2009 | 1443568 | 31.81
1307 | Illinois | STATEWIDE |  | 15,17,18,19 | 000S630 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 7 (Southeast Illinois). | Safety/Traffic Management | 04/28/2009 | 06/22/2009 | 12/30/2009 | 745277.15 | 0
1308 | Illinois | STATEWIDE |  | 1,2,3,4,5,6,7,8,9,10,11,13,14 | 000S631 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 1 (Northeast Illinois). | Safety/Traffic Management | 04/23/2009 | 05/12/2009 | 07/30/2010 | 868439 | 0
1309 | Illinois | STATEWIDE |  | 11,14,15 | 000S633 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 3 (East-Central Illinois). | Safety/Traffic Management | 07/30/2009 | 08/10/2009 | 07/30/2010 | 520518 | 0
1310 | Illinois | STATEWIDE |  | 17,18 | 000S634 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout District 4 (West-Central Illinois) | Safety/Traffic Management | 05/06/2009 | 07/27/2009 | 07/30/2010 | 539506 | 0
1311 | Illinois | STATEWIDE |  | 15,17,18,19 | 000S637 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 7 (Southeast Illinois). | Safety/Traffic Management | 05/06/2009 | 07/28/2009 | 07/30/2010 | 353667 | 0
1312 | Illinois | STATEWIDE |  | 12,15,19 | 000S639 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 9 (Southern Illinois). | Safety/Traffic Management | 05/06/2009 | 08/31/2009 | 07/30/2010 | 477700 | 0
1313 | Illinois | STATEWIDE |  | 1,2,3,4,5,6,7,8,9,10,11,13,14 | 000S640 | This project consists of improving safety by upgrading guardrail terminals to current standard throughout IDOT District 1 (Northeast Illinois). | Safety/Traffic Management | 04/30/2009 | 06/23/2009 | 11/30/2009 | 817871 | 0
1314 | Illinois | STATEWIDE |  | 17,18 | 000S644 | This project consists of improving safety by upgrading guardrail terminals to current standard throughout District 4 (West-Central Illinois) | Safety/Traffic Management | 04/28/2009 | 07/27/2009 | 12/30/2009 | 731656 | 0
1315 | Illinois | STATEWIDE |  | 12,15,19 | 000S645 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 9 (Southern Illinois). | Safety/Traffic Management | 04/28/2009 | 05/21/2009 | 12/30/2009 | 684183 | 0
1316 | Illinois | MONTGOMERY |  | 19 | 000S646 | This project will extend the pavement life by resurfacing various streets in Nokomis, Il in Montgomery County (West-Central Illinois). | Pavement Improvement | 04/30/2009 | 05/26/2009 | 08/30/2009 | 943915 | 3.27
1317 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 000S647 | This project will extend the pavement life by resurfacing DesPlaines Avenue from 26th to 31st Street in the Village of Riverside in Cook County. (Northeastern Illinois). | Pavement Improvement | 04/28/2009 | 05/18/2009 | 08/30/2009 | 317814 | 0.51
1318 | Illinois | STATEWIDE |  | 11,14,15 | 000S648 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 3 (East-Central Illinois). | Safety/Traffic Management | 07/30/2009 | 08/24/2009 | 12/30/2009 | 1044653 | 0
1319 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,2,3,13 | 000S649 | This project will extend the pavement life by resurfacing numerous roadway sections in Southern Cook County (Northeastern Illinois) | Pavement Improvement | 06/01/2009 | 06/23/2009 | 09/30/2009 | 854514 | 0
1320 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 3,4,5,7 | 000S650 | This project will extend the pavement life by resurfacing numerous roadway sections in Central Cook County (Northeastern Illinois) | Pavement Improvement | 06/01/2009 | 06/29/2009 | 11/30/2009 | 1805948 | 0
1321 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 6,8,9,10 | 000S651 | This project will extend the pavement life by resurfacing numerous roadway sections in Northern Cook County (Northeastern Illinois) | Pavement Improvement | 06/01/2009 | 06/05/2009 | 10/30/2009 | 1071800 | 0
1322 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 2,11,13 | 000S652 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Kane County (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/22/2009 | 09/30/2009 | 500310 | 0
1323 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 000S653 | This project will extend the pavement life by resurfacing numerous roadway sections in Will County (Northeastern Illinois). | Pavement Improvement | 06/02/2009 | 06/15/2009 | 10/30/2009 | 1595801 | 0
1324 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 6,13,14 | 000S654 | This project will extend the pavement life by resurfacing numerous roadway sections in DuPage County (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/15/2009 | 11/30/2009 | 2555070 | 0
1325 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 8,16 | 000S655 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout McHenry County (Northeastern Illinois). | Pavement Improvement | 06/02/2009 | 06/09/2009 | 09/30/2009 | 693261 | 0
1326 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 8,10 | 000S656 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Lake County (Northeastern Illinois). | Pavement Improvement | 06/02/2009 | 06/12/2009 | 11/30/2009 | 2695773 | 0
1327 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 8,10 | 000S657 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Lake County (Northeastern Illinois). | Pavement Improvement | 07/30/2009 | 08/12/2009 | 11/30/2009 | 1947778 | 0
1328 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 000S658 | This project will substantially improve the roadway, traffic congestion and safety by constructing a new interchange to replace the old interchange in Troy, Illinois (Southwest Illinois) | Pavement Improvement | 08/05/2009 | 08/17/2009 | 07/30/2012 | 23503491 | 0.01
1329 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 000S659 | This project will improve safety and operations by removal of old ramp structures and extention of existing ramps and other roadway improvements on I-94/90 from Hubbard's Cave to I-290 in the City of | Pavement Improvement | 05/20/2009 | 06/15/2009 | 11/30/2009 | 9163712 | 1.18
1330 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 000S660 | This project will extend the pavement life by milling, patching and resurfacing 2 miles of Dempster Street from US 41 to McCormick Blvd in Skokie and Chicago Avenue to Judson Avenue in Evanston in Coo | Pavement Improvement | 06/01/2009 | 06/14/2009 | 11/30/2009 | 1664820 | 2.07
1331 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 000S662 | This project will extend the pavement life by resurfacing 3.04 miles of Touhy Ave from Northwest highway to Central Avenue in the Village of Niles and Cities of Chicago and Park Ridge in Cook County, | Pavement Improvement | 06/01/2009 | 06/12/2009 | 09/30/2009 | 2221718 | 3.18
1332 | Illinois | MCDONOUGH |  | 17 | 000S680 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on CH 23 over Jack Creek at Toulon which is approximately 30 miles northwest of the City of | Pavement Improvement | 07/30/2009 | 08/10/2009 | 11/30/2009 | 1992761 | 10.57
1333 | Illinois | HENDERSON |  | 17 | 000S681 | This project will extend the pavement life by providing for surface improvements at 2 locations on US Route 34 near the City of Gulfport and the Mississippi River (West-Central Illinois) | Pavement Improvement | 08/11/2009 | 08/13/2009 | 09/30/2009 | 605379 | 4.38
1334 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 000S685 | This project will extend the pavement life by resurfacing 3.0 miles on US Route 6 in Channahon and Rockdale (Northeast Illinois). | Pavement Improvement | 10/29/2009 |  | 08/30/2010 | 1727000 | 3.09
1335 | Illinois | FULTON |  | 17 | 0022070 | This project will extend the pavement life by providing for 7.21 miles pavement repairs and resurfacing on Illinois Route 78 approximately 20 miles west of Peoria (West-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/11/2009 | 09/30/2009 | 2080718 | 7.54
1336 | Illinois | PEORIA |  | 18 | 0022071 | This project will extend the pavement life by providing for 3.06 miles of pavement repairs and resurfacing on Ilinois Route 78 west of Peoria (West-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/08/2009 | 08/30/2009 | 1073761 | 3.06
1337 | Illinois | FULTON |  | 17 | 0022072 | This project will extend the pavement life by providing for 9.2 miles of pavement repairs and resurfacing on Illinois Route 78 aproximately 20 miles west of Peoria (West-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/01/2009 | 09/30/2009 | 1679288 | 9.19
1338 | Illinois | STARK |  | 18 | 0022075 | This project will extend the pavement life by resurfacing 9.7 miles of Illinois Route 78 approximately 20 miles northwest of Peoria (West-Central Illinois) | Pavement Improvement | 07/30/2009 | 08/03/2009 | 12/30/2009 | 2467077 | 19.36
1339 | Illinois | CLINTON |  | 19 | 0027038 | This project will substantially improve the roadway by constructing a new bridge over Lost Creek on Sand Ridge Road near Ferrin, Illinois (Southwest Illinois) | Bridge Replacement | 07/27/2009 | 09/14/2009 | 10/30/2009 | 50000 | 0.2
1340 | Illinois | BOONE |  | 16 | 0032106 | This project will extend the pavement life by resurfacing sections of Poplar Grove Road in Boone County (Northwest Illinois). | Pavement Improvement | 09/15/2009 | 10/01/2009 | 10/30/2009 | 398954 | 10.78
1341 | Illinois | DE WITT |  | 15 | 0039028 | Preliminary engineering for the prepaation of a sign inventory in DeWitt county, 09-00000-00-SG | Other | 08/10/2009 | 08/10/2009 | 10/30/2009 | 33300 | 0
1342 | Illinois | DOUGLAS |  | 15 | 0041093 | This project consists of providing engineering design for a future township bridge improvement over the Kaskaskia River (East-Central Illinois). | Other | 09/30/2009 |  | 07/30/2010 | 63525 | 0
1343 | Illinois | DOUGLAS |  | 15 | 0041094 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE OVER SCATTERING FORK, SECTION 07-03122-01-EG | Other | 09/30/2009 | 10/01/2009 | 07/30/2010 | 20000 | 0.01
1344 | Illinois | DOUGLAS |  | 15 | 0041095 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE OVER THE KASKASKIA RIVER NEAR FLICKLIN, SECTION 09-05123-01EG | Other | 09/30/2009 |  | 07/30/2010 | 107005 | 0
1345 | Illinois | DOUGLAS |  | 15 | 0041096 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE CARRYING TR 218 OVER BRUSHY FORK, DOUGLAS COUNTY SECTION 07-08119-01-EG | Other | 09/30/2009 | 10/05/2009 | 02/28/2010 | 33309 | 0.02
1346 | Illinois | KANKAKEE |  | 11 | 0041130 | This project will extend the pavement life by resurfacing 7.9 miles of IL 17 in western Kankakee County (East-Central Illinois). | Pavement Improvement | 04/23/2009 | 05/26/2009 | 08/30/2009 | 1744277.41 | 8.1
1347 | Illinois | JO DAVIESS |  | 16 | 0065104 | This project will extend the pavement life by resurfacing 5.3 miles on Stagecoach Trail near the city of Warren (Northwest Illinois). | Pavement Improvement | 10/27/2009 |  | 12/30/2010 | 375743 | 9.34
1348 | Illinois | SANGAMON |  | 18 | 0067079 | This project will extend the pavement life by milling and resurfacing a portion of Jefferson Street in the City of Springfield (West-Central Illinois). | Pavement Improvement | 04/23/2009 | 04/30/2009 | 09/30/2009 | 836640 | 2.06
1349 | Illinois | CASS |  | 18 | 0067080 | This project will substantially improve the roadway by reconstructing two box culverts and repairing another one on Illinois Route 125 near Bluff Springs (West-Central Illinois) | Pavement Improvement | 05/04/2009 | 05/05/2009 | 05/30/2010 | 2094836 | 2.7
1350 | Illinois | IROQUOIS |  | 15 | 0071115 | This project will extend pavement life by resurfacing 4.2 miles of IL 54 near the city of Thawville (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 07/20/2009 | 10/30/2009 | 880320.15 | 4.57
1351 | Illinois | LOGAN |  | 18 | 0071116 | This project will extend the pavement life by resurfacing a portion of Illinois Route 54 northeast of Mt. Pulaski in Logan County (West-Central Illinois). | Pavement Improvement | 04/23/2009 | 05/14/2009 | 09/30/2009 | 1465825 | 6.89
1352 | Illinois | CARROLL |  | 16 | 0077103 | This project will extend the pavement life by resurfacing sections of County Highways 4 and 25 in Carroll County (Northwest Illinois). | Pavement Improvement | 09/11/2009 | 09/24/2009 | 10/30/2009 | 309728 | 20.56
1353 | Illinois | EDGAR |  | 15 | 0091071 | This project will extend the pavement life by resurfacing 4.5 miles of Illinois 16 approximately 25 miles southeast of Champaign (East-Central Illinois) | Pavement Improvement | 12/08/2009 |  | 08/30/2010 | 2074959 | 29.06
1354 | Illinois | KNOX |  | 17 | 0095126 | This project will substantially improve the roadway by constructing a new bridge over Finch Creek on County Highway 16 east of Galesburg (West-Central Illinois) | Bridge Replacement | 08/03/2009 | 08/17/2009 | 11/30/2009 | 255000 | 0.02
1355 | Illinois | KNOX |  | 17 | 0095133 | This project will substantially improve the roadway by constructing a new bridge over Swab Run Creek in eastern Knox County, approximately 20 miles southeast of Galesburg (West-Central Illinois) | Bridge Replacement | 12/17/2009 |  | 06/30/2010 | 181490 | 0.01
1356 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 00D1691 | This project will substantially improve mobility by constructing a new prefabricated pedestrian bridge over Buffalo Creek & construct a 0.14 mile shared use path between Dundee Road & Glendale Rd in t | Transportation Enhancements | 09/15/2009 | 10/05/2009 | 12/30/2009 | 368060 | 0
1357 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 00D1701 | This project will provide for pedestrain safety by improving the sidewalk, pedestrain lighting and signage adjacent to Roosevelt Road in Westchester, (Northeastern Illinois) | Transportation Enhancements | 09/10/2009 | 09/17/2009 | 11/30/2009 | 268960 | 0.7
1358 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 9 | 00D1795 | This project consists of a safety and traffic enhancement by installing 1.63 miles of new lighting and streetscape improvements on Miner Street, Oakton Street and Lee Street corridors in Des Plaines, | Transportation Enhancements | 12/10/2009 |  | 10/30/2010 | 800000 | 0
1359 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 00D2131 | This project consists of a substantial transportation improvement by construction of a new concrete bicycle and pedestrian path and other associated improvements between the cities of Rock Island and | Transportation Enhancements | 11/18/2009 |  | 05/30/2009 | 446000 | 0
1360 | Illinois | STEPHENSON |  | 16 | 00D2139 | This project will substantially improve pedestrian safety by constructing a new pedestrian bridge over the Pecatonic River in the city of Freeport and repair of a timber bridge in Stephenson County (N | Transportation Enhancements | 12/22/2009 |  | 10/30/2011 | 1928000 | 0
1361 | Illinois | MACON |  | 17 | 00D7036 | This project will provide landscaping for the Farm Progress Grounds in Decatur (Southeast Illinois). | Transportation Enhancements | 10/29/2009 |  | 05/30/2010 | 74400 | 0
1362 | Illinois | SALINE |  | 19 | 00D9096 | LAND ACQUISITION FOR THE CONSTRUCTION OF A BIKE/PED TRAIL TO CONNECT ELDORADO TO HARRISBURG, SECTION 06-00082-00-BT | Transportation Enhancements | 09/14/2009 |  | 10/30/2009 | 22500 | 0
1363 | Illinois | MCLEAN |  | 15 | 0113029 | This project will provide for pedestrian safety by constructing a 1.13 mile multi-use bike trail in Chenoa, approximately 25 miles north of Bloomington (East-Central Illinois) | Transportation Enhancements | 08/04/2009 | 08/07/2009 | 10/30/2009 | 25000 | 0
1364 | Illinois | POPE |  | 19 | 0132130 | This project will extend the pavement life by milling, patching and resurfacing 3.61 miles of IL145 in Pope county, Illinois (Southern Illinois). | Pavement Improvement | 06/02/2009 | 07/01/2009 | 08/30/2009 | 992628 | 3.75
1365 | Illinois | PEORIA |  | 18 | 0143050 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on County Highway 15 over Spoon River approximately 30 miles northwest of Peoria (West-Centr | Bridge Improvement | 09/08/2009 | 09/28/2009 | 07/30/2010 | 379741 | 0.02
1366 | Illinois | PULASKI |  | 12 | 0153030 | This project will substantially improve the roadway by constructing a new bridge over Pulaski Slough on Morris Road in Pulaski County, Illinois (Southern Illinois Illinois) | Bridge Replacement | 08/27/2009 | 09/21/2009 | 10/30/2009 | 157081 | 0.02
1367 | Illinois | SANGAMON |  | 18 | 0167058 | This project will extend the pavement life by resurfacing a portion of a Sangamon County road near Springfield (West-Central Illinois). | Pavement Improvement | 10/14/2009 | 10/12/2009 | 03/30/2010 | 1775000 | 11.2
1368 | Illinois | LA SALLE |  | 11 | 0169103 | This project will extend the pavement life by resurfacing 3.6 miles of US 52 near the city of Troy Grove (East-Central Illinois). | Pavement Improvement | 04/23/2009 | 05/27/2009 | 09/30/2009 | 682587.86 | 3.63
1369 | Illinois | DE KALB |  | 14 | 0174118 | This project will substantially improve the roadway by constructing a new bridge over Big Indian Creek on County Highway 6 in Dekalb County (East-Central Illinois). | Bridge Replacement | 07/30/2009 | 08/10/2009 | 12/30/2009 | 314054 | 10.02
1370 | Illinois | STARK |  | 18 | 0175023 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on CH 23 over Jack Creek at Toulon which is approximately 30 miles northwest of the City of | Bridge Replacement | 09/15/2009 | 09/16/2009 | 10/30/2009 | 184642 | 0.01
1371 | Illinois | TAZEWELL | PEORIA | 18 | 0179032 | This project will enhance safety by widening the pavement to accommodate left and right turn lanes into Tazewell County facilities on Illinois Route 9 approximately 10 miles south of Peoria (West-Cent | Pavement Improvement | 12/14/2009 |  | 07/30/2010 | 420000 | 0.01
1372 | Illinois | LEE |  | 14 | 0185103 | This project will extend the pavement life by resurfacing sections of Ambot Road and Walton Road in Lee County (Northwest Illinois). | Pavement Improvement | 12/09/2009 |  | 07/30/2010 | 433493 | 5.85
1373 | Illinois | WARREN |  |  | 0187038 | This project consists of a safety and traffic enhancement by upgrading roadway signs throughout Warren County (West-Central Illinois) | Safety/Traffic Management | 12/14/2009 |  | 11/30/2010 | 299940 | 0
1374 | Illinois | BUREAU |  | 18 | 0188120 | This project will extend pavement life by resurfacing 2 miles of County Highway 8 in Bureau County (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 09/08/2009 | 09/30/2009 | 292800 | 4
1375 | Illinois | OGLE |  | 16 | 0189108 | This project will extend the pavement life by resurfacing sections of Freeport Road in Ogle County (Northwest Illinois). | Pavement Improvement | 07/30/2009 | 08/24/2009 | 09/30/2009 | 574019 | 21.47
1376 | Illinois | WINNEBAGO |  | 16 | 0201027 | This project consists of improving safety by upgrading guardrail to current standards throughout Winnebago County (Northwest Illinois). | Safety/Traffic Management | 10/29/2009 | 12/02/2009 | 12/30/2009 | 328676 | 0
1377 | Illinois | MERCER |  | 17 | 0206116 | Preliminary engineering for drainage improvements along Knoxville Road from CH 20 to the Henry county line, Mercer county 06-00094-05-EG | Other | 10/27/2009 | 10/27/2009 | 03/30/2010 | 67683 | 1.31
1378 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 2 | 0209003 | This item provides construction engineering service for inspection and oversight for the improvement of I-94 from Martin Luther King Drive to 159th Street in Chicago, Cook County. | Other | 04/30/2009 | 04/30/2009 | 07/30/2011 | 2750000 | 9
1379 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 4,6,7 | 0209004 | This item provides design engineering services for the development of plans and specifications for the construction of I-290 from Thorndale Ave to Grand Ave; I-290 from I-88 to I-94/90 and I-355 from | Other | 05/18/2009 | 05/18/2009 | 05/30/2011 | 5100000 | 14
1380 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1 | 0209005 | This item provides construction engineering service for inspection and oversight of the project on I-57 to replace 7 bridge decks in Cook and Will Counties (Northeast Illinois) | Other | 05/15/2009 | 05/15/2009 | 02/28/2010 | 1300000 | 0
1381 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 7 | 0209006 | This item provides construction engineering service for inspection and oversight of the ramp modification project on I-94/90 from Hubbard's Cave to I-290 and the bridge deck replacement project at 26t | Other | 05/07/2009 | 05/07/2009 | 02/28/2011 | 1189458 | 0
1382 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 5 | 0209007 | This item provides construction engineering service for inspection and oversight of the project for bridge improvement I-90/94 in Chicago (Northeast Illinois) | Other | 05/11/2009 | 05/11/2009 | 12/30/2010 | 702536 | 0
1383 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0209008 | This item provides construction engineering service for inspection and oversight of the project to resurface 159th Street in Homer Glen (Northeast Illinois) | Other | 06/02/2009 | 06/02/2009 | 02/28/2010 | 1100000 | 15
1384 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 2 | 0209009 | This item provides construction engineering service for inspection and oversight of the project to resurface Burnham Avenue in Calumet City (Northeast Illinois) | Other | 05/05/2009 | 05/05/2009 | 02/28/2010 | 605580 | 0
1385 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0209010 | This item provides construction engineering service for inspection and oversight of the project to resurface Lemont Road in Lemont (Northeast Illinois) | Other | 04/30/2009 | 04/30/2009 | 12/30/2012 | 1000000 | 0
1386 | Illinois | STATEWIDE |  | 1,2,3,4,5,6,7,8,9,10,11,13,14,16 | 0209013 | This item provides preliminary engineering services for the development of projects in the District 1 area (Northeast Illinois) | Other | 06/02/2009 | 06/02/2009 | 12/30/2011 | 4000000 | 0
1387 | Illinois | STATEWIDE |  | 14,16,17 | 0209014 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 05/15/2009 | 05/15/2009 | 12/30/2012 | 400000 | 0
1388 | Illinois | STATEWIDE |  | 14,16,17 | 0209015 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 05/15/2009 | 05/15/2009 | 12/30/2012 | 300000 | 0
1389 | Illinois | STATEWIDE |  | 14,16,17 | 0209016 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 05/12/2009 | 05/12/2009 | 12/30/2012 | 300000 | 0
1390 | Illinois | STATEWIDE |  | 17,18 | 0209017 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 4 (West-Central Illinois). | Other | 06/02/2009 | 06/02/2009 | 12/30/2011 | 1700000 | 0
1391 | Illinois | STATEWIDE |  | 11,15 | 0209018 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 5 (East-Central Illinois). | Other | 05/18/2009 | 05/18/2009 | 12/30/2012 | 500000 | 0
1392 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 0209019 | This project will ensure quality infrastructure by providing engineering oversight during construction of a highway interchange on Interstate 55/70 in Madison County (Southwest Illinois). | Other | 06/25/2009 | 06/25/2009 | 05/30/2012 | 2500000 | 0
1393 | Illinois | STATEWIDE |  | 12,17,19 | 0209020 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 05/20/2009 | 05/20/2009 | 05/30/2012 | 500000 | 0
1394 | Illinois | STATEWIDE |  | 12,17,19 | 0209021 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 06/11/2009 | 06/11/2009 | 05/30/2012 | 500000 | 0
1395 | Illinois | STATEWIDE |  | 12,19,17 | 0209022 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 05/15/2009 | 05/15/2009 | 05/30/2012 | 500000 | 0
1396 | Illinois | STATEWIDE |  | 12,17,19 | 0209023 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 05/15/2009 | 05/15/2009 | 05/30/2012 | 500000 | 0
1397 | Illinois | STATEWIDE |  | 12,15,19 | 0209024 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 05/18/2009 | 05/18/2009 | 12/30/2011 | 300000 | 0
1398 | Illinois | STATEWIDE |  | 12,19 | 0209025 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 05/18/2009 | 05/18/2009 | 05/30/2011 | 300000 | 0
1399 | Illinois | STATEWIDE |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19 | 0209026 | This project provides Quality Assurance on pavement resurfacing on projects statewide in Illinois | Other | 05/29/2009 | 05/29/2009 | 05/30/2012 | 300000 | 0
1400 | Illinois | TAZEWELL | PEORIA | 17,18 | 0209027 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 4 (West-Central Illinois). | Other | 06/26/2009 | 06/26/2009 | 12/30/2011 | 1600000 | 0
1401 | Illinois | BUREAU |  | 11 | 0242114 | This project will extend pavement life by providing a surface treatment on 9.5 miles of County Highway 16 in Bureau County (East-Central Illinois). | Pavement Improvement | 09/09/2009 | 09/09/2009 | 09/30/2009 | 128800 | 28.38
1402 | Illinois | BUREAU |  | 11 | 0244101 | This project will extend pavement life by providing a surface treatment on 7.8 miles of County Highway 9 in Bureau County (East-Central Illinois). | Pavement Improvement | 09/09/2009 | 09/15/2009 | 09/30/2009 | 83792 | 12.78
1403 | Illinois | KENDALL |  | 14 | 0281101 | This project will extend the pavement life by resurfacing a section of County Highway 19 in Kendall County (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 10/05/2009 | 10/30/2009 | 361760 | 3.05
1404 | Illinois | MCLEAN |  | 15 | 0294108 | This project will extend the pavement life by providing for 13.05 miles of pavement removal and resurfacing on Old U.S. Route 66 north of Bloomington (East-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/26/2009 | 10/30/2009 | 3062469.26 | 16.77
1405 | Illinois | LIVINGSTON, GRUNDY |  | 11 | 0298103 | This project will extend pavement life by resurfacing 7 miles of Old US 66 between the cities of Dwight and Gardener (East-Central Illinois). | Pavement Improvement | 05/11/2009 | 06/15/2009 | 10/30/2009 | 2107029 | 14.28
1406 | Illinois | STEPHENSON |  | 16 | 0301058 | This project will extend the pavement life by resurfacing a section of US 20 in western Stephenson County (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 07/27/2009 | 11/30/2009 | 1733973 | 5.86
1407 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0303042 | This project will extend the pavement life by resurfacing 5.21 miles on IL 173 from Lake County Line to US 12 in the Villages of Fox Lake and Richmond (Northeastern Illinois) | Pavement Improvement | 04/30/2009 | 05/18/2009 | 08/30/2009 | 1953958 | 5.46
1408 | Illinois | WINNEBAGO | ROCKFORD | 16 | 0303043 | This project will extend the pavement life by resurfacing a section of IL 251 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 04/23/2009 | 05/26/2009 | 10/30/2009 | 610289 | 2.21
1409 | Illinois | WINNEBAGO | ROCKFORD | 16 | 0303044 | This project will extend the pavement life by resurfacing sections of IL 251 in the city of Loves Park (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/11/2009 | 09/30/2009 | 1138543 | 3.18
1410 | Illinois | JERSEY |  | 17 | 0304042 | This project will extend the pavement life by milling, patching and resurfacing Grafton, Illinois (Southwest Illinios). | Pavement Improvement | 05/11/2009 | 05/26/2009 | 11/30/2009 | 2683927 | 8.36
1411 | Illinois | JERSEY, MADISON | ST. LOUIS (MO)-IL | 19 | 0304043 | This project will extend the pavement life by milling, patching and resurfacing near Alton, Illinois (Southwest Illinios). | Pavement Improvement | 05/04/2009 | 05/26/2009 | 11/30/2009 | 2090483 | 6.56
1412 | Illinois | MCHENRY |  | 16 | 0305041 | This project will extend the pavement life by milling, patching, resurfacing and striping 2.34 miles on US 14 from Bunker Hill Rd to Park Lane Dr in unincorporated McHenry | Pavement Improvement | 05/06/2009 | 05/26/2009 | 09/30/2009 | 684447 | 2.35
1413 | Illinois | ROCK ISLAND |  | 17 | 0308035 | This project will extend the pavement life by resurfacing 4.4 miles of IL 81 near the city of Cambridge (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/27/2009 | 06/30/2010 | 4449013 | 4.41
1414 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 0310130 | Construction of two new structures carrying IL Route 255 over Humbert Road in Godfrey, IL (Southwest Illinois) | Pavement Widening | 07/16/2009 | 09/14/2009 | 07/30/2011 | 4885715 | 0.77
1415 | Illinois | SCHUYLER |  | 18 | 0310131 | This project will extend the pavement life by resurfacing a portion of US Route 67 near Rushville (West-Central Illinois). | Pavement Improvement | 04/17/2009 | 04/23/2009 | 10/30/2009 | 3659256 | 9.86
1416 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0310132 | This project will extend the pavement life by resurfacing 3.5 miles of US 67 near the city of Milan (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/20/2009 | 10/30/2009 | 3636748 | 3.48
1417 | Illinois | CASS |  | 18 | 0310134 | This project will extend the pavement life by resurfacing and updating guardrail to a portion of US Route 67 from Beardstown to 3 miles north of Meredosia (West-Central Illinois). | Pavement Improvement | 05/04/2009 | 05/04/2009 | 09/30/2009 | 2477887 | 9.96
1418 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0311037 | This project will extend the pavement life by resurfacing 4.1 miles on US Route 34 in the City of Downers Grove (Northeast Illinois). | Pavement Improvement | 04/28/2009 | 05/01/2009 | 10/30/2009 | 2657532.54 | 3.37
1419 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0311039 | This project will extend the pavement life by resurfacing 2.09 miles on US Route 34 in Napreville (Northeast Illinois). | Pavement Improvement | 10/16/2009 |  | 07/30/2010 | 1420192 | 4.3
1420 | Illinois | MCDONOUGH |  | 17 | 0315055 | This project will extend the pavement life by providing surface improvements on a 0.57 mile section of U.S. Route 136 in Macomb (West-Central Illinois) | Pavement Improvement | 07/30/2009 | 08/10/2009 | 11/30/2009 | 604296 | 1.14
1421 | Illinois | OGLE |  | 16 | 0316035 | This project will extend the pavement life by resurfacing a section of US 52 and IL 26 near the city of Polo (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 05/18/2009 | 07/30/2009 | 388076 | 1.27
1422 | Illinois | MCLEAN |  | 11 | 0317080 | This project will extend the pavement life by providing for 7.3 miles of pavement repairs and resurfacing on U.S. Route 24 north of Bloomington (East-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/04/2009 | 08/30/2009 | 1688139 | 7.28
1423 | Illinois | DOUGLAS, PIATT |  | 15 | 0323026 | This project will extend the pavement life by providing for 9.6 miles of pavement removal and resurfacing on U.S. Route 36 south of Champaign (East-Central Illinois) | Pavement Improvement | 04/23/2009 | 05/06/2009 | 09/30/2009 | 2570726 | 9.78
1424 | Illinois | GRUNDY |  | 11 | 0326077 | This project will extend the pavement life by resurfacing 10.9 miles of IL 47 near the city of Mazon (East-Central Illinois). | Pavement Improvement | 06/08/2009 | 08/17/2009 | 10/30/2009 | 2355686.09 | 11.02
1425 | Illinois | LIVINGSTON, GRUNDY |  | 11 | 0326078 | This project will extend the pavement life by resurfacing 15.6 miles of IL 47 between the cities of Dwight and Saunemin (East-Central Illinois). | Pavement Improvement | 06/02/2009 | 06/08/2009 | 05/30/2010 | 3938465 | 15.49
1426 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0326079 | This project will extend the pavement life by milling, patching, resurfacing and striping 3.55 miles on US 30/IL 47 from US 30/IL 56 to Kendall County lines in the Village of Sugar Grove (Northeaster | Pavement Improvement | 05/18/2009 | 05/26/2009 | 08/30/2009 | 2153935 | 4.01
1427 | Illinois | MARION |  | 19 | 0327043 | This project consists of 2.61 miles of resurfacing which will extend the pavement life by milling, patching and resurfacing in Marion County, Illinois (Southwest Illinios). | Pavement Improvement | 05/04/2009 | 05/13/2009 | 09/30/2009 | 806813.32 | 2.72
1428 | Illinois | WILL |  | 11 | 0330050 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on us Route 45 over Forked Creek 2.1 miles south of Manhattan Monee Road (Northeast Illinoi | Bridge Improvement | 05/11/2009 | 07/13/2009 | 09/30/2009 | 248217 | 0.01
1429 | Illinois | WILL |  | 11 | 0330051 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 45/52 over south Branch of Forked Creek 0.5 miles south of Joliet Road near Pe | Bridge Improvement | 05/11/2009 | 07/13/2009 | 09/30/2009 | 237759 | 0.01
1430 | Illinois | KANKAKEE |  | 11 | 0330052 | This project will extend the pavement life by resurfacing a section of IL 17 near the city of Aroma (East-Central Illinois). | Pavement Improvement | 06/01/2009 | 08/03/2009 | 09/30/2009 | 3022561 | 4.3
1431 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 04 | 0330053 | This project will extend the pavement life by resurfacing 1.66 miles of Mannheim Rd in theVillages of Hillside, Melrose Park, and Stone Park, (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/08/2009 | 10/30/2009 | 1538505 | 1.43
1432 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0330054 | This project will extend the pavement life by resurfacing 1.22 miles of US 12/45 from Prospect Avenue to Walnut Avenue in the City of DesPlaines in Cook County. (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/15/2009 | 09/30/2009 | 811241 | 1.14
1433 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0330055 | This project will extend the pavement life by resurfacing 1.20 miles of US 12/45 from US 12 (Rand Rd) to Walnut Avenue within the City of DesPlaines in Cook County. (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/15/2009 | 09/30/2009 | 989731 | 3.21
1434 | Illinois | SALINE |  | 19 | 0331048 | This project will substantially improve mobility by constructing a new four lane roadway and new bridge over west Harrisburg drainage ditch which will rerout a protion of IL13 around Harrisburg, Illin | New Construction | 06/01/2009 | 07/13/2009 | 08/30/2011 | 14121445 | 5.5
1435 | Illinois | JACKSON |  | 12 | 0331050 | This project will substantially improve the roadway by constructing a new bridge over Mud Creek on IL 13 in Jackson County, Illinois (Southern Illinois) | Bridge Replacement | 10/22/2009 | 11/02/2009 | 10/30/2011 | 1865416 | 0.04
1436 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0332091 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on IL 1 over Trim Creek 1 mile south of Beecher (Northeast Illinois). | Pavement Improvement | 05/11/2009 | 06/23/2009 | 08/30/2009 | 540685 | 0.01
1437 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0334018 | This project will extend the pavement life by milling, patching and resurfacing 1.13 miles on US Rt. 12 (Main St) from Wisconsin State Line to IL 73 (Kenosha Rd) in the Village of Richmond (Northeaste | Pavement Improvement | 06/01/2009 | 06/22/2009 | 09/30/2009 | 523886 | 1.12
1438 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 0335011 | This project will extend the pavement life by resurfacing 3.91 miles on IL 176 between Nish Rd and IL 31in the Villages of Crystal Lake and Prairie Grove (Northeastern Illinois) | Pavement Improvement | 04/28/2009 | 05/11/2009 | 08/30/2009 | 1313266 | 3.89
1439 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0335012 | This project will extend the pavement life by milling, patching, resurfacing and striping 1.44 miles on IL 60 from IL 21(Milwaukee Ave) to west of I-94(Tri-State Tollway) in the Villages of Libertyvil | Pavement Improvement | 06/01/2009 | 06/19/2009 | 11/30/2009 | 1145733 | 1.7
1440 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0335013 | This project will extend the pavement life by milling, patching and resurfacing 2.96 miles on IL Rt 176 and IL 60/83 from west of Thorngate Dr to IL 60/83 and from IL 176 to Midlothian Rd in Mundelein | Pavement Improvement | 10/23/2009 |  | 06/30/2010 | 1216778 | 5.96
1441 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0338036 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL 59 at four structures in West Chicago (Northeast Illinois). | Bridge Improvement | 05/04/2009 | 06/01/2009 | 10/30/2009 | 1071811.74 | 1.99
1442 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0338037 | This project will improve safety and traffic operations by reconstructing the intersection of IL 59 and US Route 30 in Plainfield (Northeast Illinois) | Pavement Improvement | 06/16/2009 | 06/19/2009 | 05/30/2011 | 7903048 | 0.01
1443 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0338038 | This project will extend the pavement life by resurfacing 5.80 miles on IL 59 in West Chicago (Northeast Illinois). | Pavement Improvement | 10/28/2009 |  | 08/30/2010 | 3881214 | 12.58
1444 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0338039 | This project will extend the pavement life by milling, patching and resurfacing 2.45 miles on IL Rt 59/Hough street from IL 22 to Lake-Cook Rd in Barrington (Northeastern Illinois). | Pavement Improvement | 10/27/2009 |  | 07/30/2010 | 1115283 | 5
1445 | Illinois | FORD |  | 15 | 0340103 | This project will substantially improve the roadway by constructing new bridges over creeks on County Highway 26 southwest of the city of Paxton (East-Central Illinois). | Bridge Replacement | 09/08/2009 | 09/23/2009 | 05/30/2010 | 319891 | 0.02
1446 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 0341045 | This project will extend the pavement life by resurfacing 1.43 miles of Touhy Avenue (IL 72) from Lee Street to the DesPlaines River Road in the Villages of Des Plaines and Rosemont in Cook County. (N | Pavement Improvement | 04/23/2009 | 05/12/2009 | 08/30/2009 | 1435199 | 1.7
1447 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0341046 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL 72 over I-90 in Gilberts in Northeastern Illinois | Bridge Improvement | 06/01/2009 | 06/08/2009 | 09/30/2009 | 670892 | 0.01
1448 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0341047 | This project will extend the pavement life by milling, patching and resurfacing 0.98 miles of Il 72 in the Village of Hoffman Estates in Cook County. (Northeastern Illinois). | Pavement Improvement | 08/07/2009 | 08/14/2009 | 10/30/2009 | 1348458 | 2.12
1449 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0347021 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on Il 38 over Kress Creek in West Chicago (Northeast Illinois). | Bridge Improvement | 05/04/2009 | 05/26/2009 | 08/30/2009 | 397956 | 0.01
1450 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0348042 | This project will extend the bridge life by partial and full depth patching of the bridge deck, bridge deck overlay, joint repair, and making other roadway improvements to the IL 43 bridge over Stoney | Bridge Improvement | 06/01/2009 | 06/22/2009 | 10/30/2009 | 693923.83 | 0.01
1451 | Illinois | KENDALL |  | 14 | 0349013 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on US Rt. 30 over River St in Montgomery (Northeastern Illinois) | Bridge Improvement | 04/23/2009 | 06/25/2009 | 08/30/2009 | 476279 | 0.02
1452 | Illinois | KENDALL, KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0349014 | This project will extend the pavement life by milling, resurfacing and striping 2.78 miles on US Rt.30 from IL Rt 47 to Orchard Rd in the Village of Montgomery (Northeastern Illinois) | Pavement Improvement | 05/18/2009 | 05/26/2009 | 08/30/2009 | 1064533 | 3.54
1453 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0350029 | This project will extend the pavement life by resurfacing 1.69 miles of IL 50 (Cicero Avenue) from IL 19 (Irving Road) to I-94 in the City of Chicago. | Pavement Improvement | 04/23/2009 | 05/11/2009 | 09/30/2009 | 1648211 | 3.06
1454 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0350030 | This project will extend the pavement life by resurfacing 2.92 miles of US 41/IL 50 from Foster Street to Touhy Avenue in Lincolnwood in Cook County (Northeastern Illinois). | Pavement Improvement | 04/30/2009 | 05/18/2009 | 10/30/2009 | 2513174 | 2.91
1455 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0350031 | This project will extend pavement life by resurfacing 0.847 miles of US 41 from Old Orchard Road to Central Avenue in the Villages of Skokie and Wilmette in Cook County (Northeastern Illinois). | Pavement Improvement | 05/04/2009 | 05/26/2009 | 08/30/2009 | 650391 | 0.82
1456 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0350032 | This project will extend the life of the pavement by resurfacing 1.512 miles of Cicero Avenue (IL 50) from 34th Street to 46th Street and drainage improvements at IL 50 under I-55 within Cicero & Chic | Pavement Improvement | 07/27/2009 | 09/15/2009 | 10/30/2009 | 1594542 | 1.46
1457 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0351018 | This project will substantially improve the roadway by reconstructing 1.92 miles of US 6 (159th street) from I-294 (Tri-State Tollway) to IL 1 (Halsted Street) in Harvey and Markham in Cook County. (N | Pavement Improvement | 06/11/2009 | 06/12/2009 | 07/30/2011 | 17864123 | 2.33
1458 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0351019 | This project will extend the pavement life by resurfacing 4.78 miles on IL 7 in Homer Glen (Northeast Illinois). | Pavement Improvement | 05/21/2009 | 06/09/2009 | 11/30/2009 | 1650012 | 5.02
1459 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0351020 | This project will extend the pavement life by milling, patching and resurfacing 2.59 miles of US 6 / IL 7 (159th St) from Will-Cook Rd to US 45 in the Village of Orland Park in Cook County. (Northeas | Pavement Improvement | 05/21/2009 | 06/09/2009 | 10/30/2009 | 1260167 | 2.98
1460 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0352010 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL Rt 137 over Des Plaines River in Libertyville (Northeastern Illinois) | Bridge Improvement | 04/30/2009 | 05/06/2009 | 09/30/2009 | 606126 | 0.01
1461 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0352012 | This project will extend the pavement life by milling, patching, resurfacing, curb and gutter 2.52 miles on IL 137 from Martin Luther King Dr to west of US Rt. 41 in the Village of North Chicago (Nort | Pavement Improvement | 06/01/2009 | 06/23/2009 | 10/30/2009 | 3037064 | 2.51
1462 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0353014 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on US 30 over IL 394 in the Village of Ford Heights in Cook County. (Northeastern Illinois). | Bridge Improvement | 09/08/2009 |  | 11/30/2010 | 3441424 | 0.02
1463 | Illinois | WOODFORD |  | 18 | 0358102 | This project will substantially improve the roadway by replacing multiple drainage structures on and reconstructing 2.26 miles of County Highway 1 approximately 25 miles northeast of Peoria (West-Cent | Pavement Improvement | 07/24/2009 | 08/17/2009 | 12/30/2009 | 466776 | 6
1464 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0360010 | This project will extend the pavement life by milling, patching and resurfacing 1.95 miles on IL 25 (Dundee ave) from I-90(Northwest Tollway) to IL 72(Higgins Rd) in the Villages of Dundee and Elgin ( | Pavement Improvement | 06/11/2009 | 06/18/2009 | 11/30/2009 | 1752233 | 2.03
1465 | Illinois | WOODFORD |  | 18 | 0367105 | Thie project will extend the pavement life by resurfacing a 2.5 mile section of County Highway 23 east of Peoria (West-Central Illinois) | Pavement Improvement | 12/03/2009 |  | 06/30/2010 | 302173 | 3.12
1466 | Illinois | MARSHALL |  | 18 | 0369106 | This project will extend the pavement life by resurfacing 2 miles of County Highway 1 in Marshall County, approximately 25 miles northeast of Peoria (West-Central Illinois) | Pavement Improvement | 12/09/2009 |  | 05/30/2010 | 267610 | 2
1467 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0370007 | This project will extend the pavement life by resurfacing 1.52 miles Western Avenue from 87th to 99th Street. (Northeastern Illinois). | Pavement Improvement | 04/28/2009 | 04/28/2009 | 10/30/2009 | 1478278 | 1.46
1468 | Illinois | PEORIA |  | 18 | 0386105 | This project will extend the pavement life by resurfacing 3.3 miles of Kickapoo-Edwards Road just west of Peoria (West-Central Illinois) | Pavement Improvement | 12/03/2009 |  | 05/30/2010 | 129720 | 3.27
1469 | Illinois | LEE |  | 11 | 0391018 | This project will extend the pavement life by patching 19 miles of Interstate 39 trhough Lee County (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 05/26/2009 | 08/30/2009 | 1214302.19 | 19.23
1470 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0391026 | This project will extend the bridge life by deck patching, placement of permanent protective shielding and other roadway improvements on 39th Street (Perhing Road) over S. Racine Avenue and Norfolk an | Bridge Improvement | 04/28/2009 | 05/26/2009 | 08/30/2009 | 234471.51 | 0.01
1471 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 0392007 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 26th Street and Frontage Road B over the Franklin Connector which connects Stevenson Expr | Bridge Improvement | 04/23/2009 | 07/20/2009 | 11/30/2010 | 5620248 | 0.02
1472 | Illinois | HANCOCK |  | 17 | 0428103 | This project will extend the pavement life by resurfacing a portion Hancock County Highway 11 from Basco, IL to five miles west of Basco (West-Central Illinois). | Pavement Improvement | 09/10/2009 | 09/18/2009 | 12/30/2009 | 476459 | 10
1473 | Illinois | TAZEWELL |  | 18 | 0467106 | This project will extend the pavement life by resurfacing 3 miles of Allentown Rd approximately 10 miles southeast of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 |  | 06/30/2010 | 446000 | 2.84
1474 | Illinois | TAZEWELL |  | 18 | 0468102 | This project will extend the pavement life by resurfacing 7 blocks of Minier Avenue in Minier, southeast of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 |  | 05/30/2010 | 155000 | 0.6
1475 | Illinois | TAZEWELL |  | 18 | 0470107 | This project will extend the pavement life by providing for 1.4 miles of resurfacing on Dee Mack Road east of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 |  | 05/30/2010 | 320000 | 3
1476 | Illinois | MCLEAN |  | 15 | 0478106 | This project will substantially improve 0.74 mile of County Highway 29 by providing new concrete pavement and other roadway improvements north of Bloomington (East-Central Illinois) | Pavement Improvement | 07/24/2009 | 08/06/2009 | 01/30/2010 | 1066520 | 0.02
1477 | Illinois | MCLEAN |  | 11 | 0494102 | This project will extend the pavement life by providing for 2.42 miles pavement repairs and resurfacing on Horse Farm Road in LeRoy, southeast of Bloomington (East-Central Illinois) | Pavement Improvement | 09/08/2009 | 09/14/2009 | 11/30/2009 | 510000 | 4.84
1478 | Illinois | VERMILION |  | 15 | 0496106 | This project will substantially improve the roadway by constructing a new bridge on County Highway 14 over the Middle Branch approximately 50 miles northeast of Champaign (East-Central Illinois) | Bridge Replacement | 12/07/2009 |  | 09/30/2010 | 505094 | 0.01
1479 | Illinois | VERMILION |  | 15 | 0513103 | This project will extend the pavement life with 10.4 miles of pavement repairs on Chicago Street approximately 20 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 04/23/2009 | 06/11/2009 | 09/30/2009 | 844802.75 | 9.72
1480 | Illinois | BOONE |  | 16 | 0525115 | This project will extend the pavement life by resurfacing 5.4 miles of US 20 near the city of Belvidere (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/11/2009 | 10/30/2009 | 1776768 | 5.45
1481 | Illinois | CHAMPAIGN |  | 15 | 0531108 | This project will substantially improve the roadway by reconstructing and widening County Highway 18 south of Champaign (East-Central Illinois) | Pavement Improvement | 12/10/2009 |  | 10/30/2010 | 597211 | 4.97
1482 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0535001 | This project will extend the pavement life by milling, patching anfd resurfacing 6.59 miles on IL 60/83 between IL Rt 20(Belvidere Rd) and IL 176 in the Villages of Mundelein, Ivanhoe, Volo and Round | Pavement Improvement | 06/01/2009 | 06/20/2009 | 05/30/2010 | 2369279 | 6.88
1483 | Illinois | PIATT |  | 15 | 0535102 | This project will extend the pavement life by resurfacing a section of Shady Rest Road approximately 15 miles west of Champaign (East-Central Illinois) | Pavement Improvement | 12/22/2009 |  | 08/30/2010 | 276697 | 1.56
1484 | Illinois | DE WITT |  | 15 | 0543105 | This project will substantially improve the roadway by constructing a new bridge on Parnell Road over Salt Creek approximately 25 miles south of Bloomington (East-Central Illinois) | Bridge Improvement | 12/14/2009 |  | 08/30/2010 | 166700 | 0.01
1485 | Illinois | MACON |  | 18 | 0548103 | This project will substantially improve the roadway by replacing a new bridge over Lake Fork Creek on County Highway 58 west of Maroa (West-Central Illinois) | Bridge Replacement | 12/14/2009 |  | 06/30/2010 | 328230 | 0.01
1486 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0556233 | This project will address noise issues with the construction of noise walls along I-55 in Romeoville and Planfield (Northeast Illinois) | Transportation Enhancements | 09/14/2009 |  | 05/30/2011 | 8546818 | 6.57
1487 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0556234 | This project will address noise issues with the construction of noise walls along I-55 in Joliet and Planfield (Northeast Illinois) | Transportation Enhancements | 10/07/2009 | 10/17/2009 | 05/30/2011 | 8162557.2 | 7.93
1488 | Illinois | LEE |  | 14 | 0561029 | This project will substantially improve the roadway by constructing new bridges over creeks on IL 2 near Sauk Valley College (Northwest Illinois). | Bridge Replacement | 12/08/2009 |  | 11/30/2010 | 1959538 | 0.02
1489 | Illinois | WHITESIDE |  | 16 | 0565003 | This project will extend the pavement life by resurfacing 2.9 miles of IL 136 near the city of Fulton (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 05/18/2009 | 10/30/2009 | 1406753 | 3.21
1490 | Illinois | DE KALB |  | 14 | 0567098 | This project will extend the pavement life by resurfacing 5.3 miles of IL 38 east of the city of Dekalb (East-Central Illinois). | Pavement Improvement | 06/01/2009 | 07/06/2009 | 09/30/2009 | 1910450 | 10.6
1491 | Illinois | MASON |  | 18 | 0567115 | This project will extend the pavement life by providing a surface treatment on a section of County Highway 20 near Forest City in Mason County (West-Central Illinois). | Pavement Improvement | 08/27/2009 | 09/08/2009 | 09/30/2009 | 229661 | 3.83
1492 | Illinois | DE KALB |  | 14 | 0567126 | This project will extend the pavement life by resurfacing 2.2 miles of IL 38 in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 08/11/2009 | 08/31/2009 | 07/30/2010 | 1911991 | 4.34
1493 | Illinois | FRANKLIN |  | 12 | 0572149 | This project will extend the pavement life by milling, rubblizing, patching and resurfacing 8.68 miles of Interstate 57 in Franklin County Illinois (Southern Illinios). | Pavement Improvement | 04/28/2009 | 07/13/2009 | 08/30/2009 | 9197918 | 8.68
1494 | Illinois | COLES |  | 15 | 0574128 | This project will extend the pavement life by resurfacing a portion of Interstate 57 from south of Arcola to Mattoon (Southeast Illinois). | Pavement Improvement | 05/20/2009 | 06/09/2009 | 08/30/2010 | 20723530 | 10.87
1495 | Illinois | COOK |  | 01 | 0577277 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 112th Place over I-57 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 06/01/2009 | 06/04/2009 | 11/30/2009 | 2558918 | 0.01
1496 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577278 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 103rd Street over I-57 in Chicago. (Northeastern Illinois). | Bridge Improvement | 05/04/2009 | 06/01/2009 | 11/30/2009 | 2049614 | 0.01
1497 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0577279 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on North Peotone/Joliet Road over I-57in Peotone (Northeast Illinois). | Bridge Improvement | 05/11/2009 | 07/20/2009 | 09/30/2009 | 426191 | 0.01
1498 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0577280 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the 115th Street over I-57 in Chicago, Cook County. (Northeastern Illinois). | Bridge Improvement | 04/23/2009 | 05/11/2009 | 11/30/2009 | 2906045 | 0.01
1499 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577281 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 125th Street over I-57 in Calumet Township. (Northeastern Illinois). | Bridge Improvement | 04/28/2009 | 05/24/2009 | 11/30/2009 | 1622798 | 0.01
1500 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577282 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 111th Street over I-57 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 06/01/2009 | 04/01/2010 | 09/30/2010 | 2687295 | 0.01
1501 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577283 | This project will extend the bridge life by repairing the bridge deck and new deck overlay to 0.06 miles of the 167th Street bridge over I-57 in the Cities of Oark Park and Country Club Hills in Cook | Bridge Improvement | 06/22/2009 | 07/17/2009 | 10/30/2009 | 677916 | 0.01
1502 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0577285 | This project will extend the pavement life by milling, patching and resurfacing 7.2 miles of I-57 from the Will Co Line to 175th St in the Villages of Country Cub Hills, Matteson, Bremen, and Richton | Pavement Improvement | 10/23/2009 |  | 08/30/2010 | 11790438 | 14.48
1503 | Illinois | BUREAU |  | 11 | 0587024 | This project will extend the pavement life by resurfacing 6.2 miles of IL 92 between the cities of Ohio and Walnut (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 06/01/2009 | 08/30/2009 | 1872317.64 | 5.91
1504 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 0592052 | This project will extend the pavement life by milling, patching and resurfacing 1.78 miles in St. Clair County, IL (Southwest Illinois) | Pavement Improvement | 05/11/2009 | 05/15/2009 | 10/30/2009 | 948710 | 1.78
1505 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0607078 | This project will extend the pavement life by resurfacing 1.11 miles on US Routes 52/30/6 in Joliet (Northeast Illinois). | Pavement Improvement | 05/11/2009 | 05/21/2009 | 08/30/2009 | 820699 | 1.16
1506 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0607079 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 30 over Hickory Creek in Joliet (Northeast Illinois). | Bridge Improvement | 05/11/2009 | 06/15/2009 | 09/30/2009 | 328811 | 0.01
1507 | Illinois | HENRY |  | 14 | 0611014 | This project will extend the pavement life by resurfacing 4 miles of IL 92 in the city of Rock Island (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/08/2009 | 08/30/2009 | 648677.93 | 2.34
1508 | Illinois | HENRY |  | 17 | 0611015 | This project will extend the pavement life by resurfacing a section of IL 81 near the city of Andover (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/11/2009 | 08/30/2009 | 392099 | 0.72
1509 | Illinois | MASON |  | 18 | 0614030 | This project will extend the pavement life by milling, patching, and resurfacing a portion of Illinois Route 78 from Havana to Saidora (West-Central Illinois). | Pavement Improvement | 04/30/2009 | 05/08/2009 | 11/30/2009 | 5659417 | 13.61
1510 | Illinois | MCDONOUGH |  | 17 | 0618003 | This project will extend pavement life by providing for 6.8 miles of surface improvements on IL Rte. 41 east of the City of Macomb which is approximately 50 miles west of the City of Peoria (West-Cent | Pavement Improvement | 07/30/2009 | 08/13/2009 | 11/30/2009 | 1576276 | 12.68
1511 | Illinois | FULTON |  | 17 | 0630006 | This project will extend the pavement life by providing for 4.84 miles of pavement repairs and resurfacing on IL Route 100 near the City of Bryant which is approximately 35 miles southwest of the Cit | Pavement Improvement | 04/28/2009 | 05/04/2009 | 08/30/2009 | 912884 | 4.97
1512 | Illinois | WILL |  | 11 | 0631015 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on IL 102 over Rayns Creek southeast of Wilmington (Northeast Illinois). | Bridge Improvement | 04/28/2009 | 06/08/2009 | 09/30/2009 | 247865 | 0.01
1513 | Illinois | HENRY |  | 14 | 0638010 | This project will extend the pavement life by resurfacing a section of US 6 in the city of Geneseo (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/26/2009 | 08/30/2009 | 705730 | 2.29
1514 | Illinois | HENRY |  | 14 | 0638013 | This project will substantially improve the roadway by constructing a new bridge over Hennepin Canal on IL 82 near the city of Geneseo (Northwest Illinois). | Bridge Replacement | 12/08/2009 |  | 11/30/2010 | 1512229 | 0.02
1515 | Illinois | COLES |  | 15 | 0642123 | This project will substantially improve the roadway by constructing a new section of roadway near Mattoon (Southeast Illinois). | New Construction | 07/22/2009 | 08/10/2009 | 02/28/2010 | 307906 | 2.26
1516 | Illinois | STARK |  | 18 | 0643204 | This project will extend the pavement life by providing for 3.4 miles of pavement repair and resurfacing on IL Route 17 at Toulon which is approximately 30 miles northwest of the City of Peoria ( West | Pavement Improvement | 07/30/2009 | 08/03/2009 | 09/30/2009 | 514445 | 6.94
1517 | Illinois | WHITESIDE |  | 17 | 0646069 | This project will extend the pavement life by resurfacing a section of IL 40 in the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 09/08/2009 | 11/30/2009 | 1174527 | 1.25
1518 | Illinois | MARSHALL, STARK |  | 18 | 0646070 | This project will extend the pavement life by providing for 4.43 miles of pavement repair and resurfacing on IL Route 40 and IL Route 17 approximately 25 miles north of the City of Peoria (West-Centra | Pavement Improvement | 07/30/2009 | 08/10/2009 | 10/30/2009 | 1167478.32 | 8.07
1519 | Illinois | LA SALLE, PUTNAM |  | 11 | 0653028 | This project will extend the pavement life by resurfacing 6.5 miles of IL 18 between the cities of Magnolia and Lostant (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 06/22/2009 | 09/30/2009 | 1284918 | 12.13
1520 | Illinois | WARREN |  | 17 | 0665013 | This project will extend the pavement life by providing for 5.08 miles of pavement repair and resurfacing along IL Route 116 near the City of Roseville which is approximately 60 miles west of the City | Pavement Improvement | 07/27/2009 | 08/10/2009 | 10/30/2009 | 1117435 | 10.12
1521 | Illinois | KNOX, FULTON |  | 17 | 0665014 | This project provides for 8.3 miles of pavement repairs and resurfacing, extending the pavement life, on Illinois Route 116 near the City of St. Augustine which is approximately 40 miles west of the C | Pavement Improvement | 07/27/2009 | 08/17/2009 | 11/30/2009 | 2479861 | 7.84
1522 | Illinois | WOODFORD |  | 18 | 0673024 | This project will extend the pavement life by resurfacing of 5.90 miles of IL Routes 116 and 117 near the west city limits of the City of Roanoke which is approximately 20 mile east of the City of Peo | Pavement Improvement | 04/28/2009 | 05/07/2009 | 10/30/2009 | 2231572 | 6.12
1523 | Illinois | COLES |  | 15 | 0674111 | This project will substantially improve the roadway by replacing a box culvert on Fish Hatchery Road near Paradise (Southeast Illinois). | Bridge Improvement | 05/21/2009 | 06/17/2009 | 07/30/2009 | 162702.01 | 0.01
1524 | Illinois | EDGAR |  | 15 | 0678106 | This project will substantially improve the roadway by reconstructing and resurfacing a section of County Highway 21, approximately 50 miles southeast of Champaign (East-Central Illinois) | Pavement Improvement | 12/17/2009 |  | 06/30/2010 | 336991 | 2.71
1525 | Illinois | LIVINGSTON |  | 15 | 0681037 | This project wil substantially improve the roadway by reconstructing a section of IL 116 in the village of Cullom. | Pavement Improvement | 04/30/2009 | 06/22/2009 | 05/30/2010 | 2835182 | 0.89
1526 | Illinois | HANCOCK |  | 17 | 0685028 | This project will extend the pavement life by resurfacing a portion of Illinois Route 9 in Hancock County from Dallas City to LaHarpe (West-Central Illinois). | Pavement Improvement | 04/28/2009 | 05/11/2009 | 10/30/2009 | 3754839 | 13.28
1527 | Illinois | VERMILION |  | 15 | 0697030 | This project will extend the life of the roadway by providing for 6.5 miles of pavement repairs, resurfacing, and bridge deck repairs on Illinois Route 9 in Vermilion County at the Indiana border (Eas | Pavement Improvement | 05/15/2009 | 06/15/2009 | 10/30/2009 | 2075000 | 6.62
1528 | Illinois | JASPER |  | 19 | 0704138 | This project will substantially improve the roadway by reconstructing a section of County Highway 6 near Gila in Jasper County (Southeast Illinois). | Pavement Improvement | 08/03/2009 | 08/11/2009 | 10/30/2009 | 299807 | 3.5
1529 | Illinois | CHAMPAIGN |  | 15 | 0709024 | This project will extend the pavement life by providing for 3.8 miles of pavement repairs and resurfacing on U.S. Route 136 north of Champaign (East-Central Illinois) | Pavement Improvement | 05/04/2009 | 05/29/2009 | 08/30/2009 | 970051 | 3.8
1530 | Illinois | VERMILION |  | 15 | 0711010 | This project will extend the life of the roadway by providing for 7.6 miles of pavement repairs, resurfacing, and culvert replacement on Illinois Route 119 in Vermilion County at the Indian border (Ea | Pavement Improvement | 05/06/2009 | 05/18/2009 | 10/30/2009 | 1969464 | 7.78
1531 | Illinois | EFFINGHAM |  | 19 | 0711108 | This project will extend the pavement life by adding new shoulders and resurfacing a portion of County Highway 25 south of Altamont (Southeast Illinois) | Pavement Improvement | 09/16/2009 | 10/07/2009 | 12/30/2009 | 361611 | 8
1532 | Illinois | FAYETTE |  | 19 | 0712106 | This project will substantially improve the roadway by replacing and repairing several culverts on County Highway 24 in Fayette County (Southeast Illinois). | Bridge Improvement | 08/24/2009 | 09/08/2009 | 12/30/2009 | 410144 | 6.24
1533 | Illinois | SHELBY |  | 19 | 0713111 | This project will substantially improve the roadway by reconstructing a section of Michigan and Logan Streets by providing new concrete pavement and other roadway improvements in Tower Hill (Southeast | Pavement Improvement | 12/10/2009 |  | 08/30/2010 | 487714 | 0.82
1534 | Illinois | MONTGOMERY |  | 19 | 0721219 | This project will substantially improve the roadway by reconstructing a new bridge over East Fork of Shoal Creek on County Highway 8 near Filmore (West-Central Illinois) . | Bridge Replacement | 12/14/2009 |  | 08/30/2010 | 461786 | 0.01
1535 | Illinois | FRANKLIN |  | 12 | 0726058 | This project will extend the pavement life by milling, patching and resurfacing 6.58 miles of IL 148 in Franklin County, Illinois (Southern Illinios). | Pavement Improvement | 04/28/2009 | 06/08/2009 | 09/30/2009 | 2518216 | 13.45
1536 | Illinois | WINNEBAGO | ROCKFORD | 16 | 0734042 | This project will extend the pavement life by resurfacing a section of IL 251 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/26/2009 | 08/30/2009 | 398389 | 0.63
1537 | Illinois | MACON |  | 17 | 0741094 | This project will extend the pavement life by resurfacing a portion of Illinois Route 105 through the City of Decatur (Southeast Illinois). | Pavement Improvement | 04/30/2009 | 05/27/2009 | 10/30/2009 | 2396468 | 3.05
1538 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0741096 | This project will extend the structural life by completing repairs on the viaducts carrying Interstate 74 over IL 92 in the city of Moline (Northwest Illinois). | Bridge Improvement | 04/30/2009 | 05/11/2009 | 08/30/2009 | 756407.74 | 0.02
1539 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0741097 | This project will extend the pavement life by resurfacing a section of Interstate 74 and completing bridge repairs on several structures in the city of Moline (Northwest Illinois). | Pavement Improvement | 04/30/2009 | 05/11/2009 | 10/30/2010 | 10811308 | 5.73
1540 | Illinois | PIATT |  | 15 | 0741098 | This project will extend the pavement life by providing for 12.6 miles of pavement repairs and resurfacing on Illinois Route 105 west of Decatur (East-Central Illinois) | Pavement Improvement | 04/30/2009 | 05/20/2009 | 10/30/2009 | 2960360 | 12.66
1541 | Illinois | HENRY |  | 17 | 0742127 | This project will substantially improve the roadway by constructing new bridges over Opheim Road on Interstate 74 and other roadway improvements north of the city of Woodhull (Northwest Illinois). | Bridge Improvement | 12/08/2009 |  | 11/30/2010 | 3537468 | 0.59
1542 | Illinois | MCLEAN |  | 11 | 0744238 | This project will extend the pavement life by providing for 4.24 miles of pavement repairs and resurfacing on Interstate 74 in Bloomington (East-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/04/2009 | 08/30/2010 | 8232987 | 4.61
1543 | Illinois | PEORIA |  | 18 | 0744239 | This project will extend the pavement life by providing for 6.12 miles of pavement removal and resurfacing on a section of Interstate 74 approximately 7 miles west of the City of Peoria (West-Central | Pavement Improvement | 04/28/2009 | 05/04/2009 | 11/30/2009 | 7969384.99 | 5.72
1544 | Illinois | TAZEWELL |  | 18 | 0744240 | This project will extend the pavement life by providing for 6.41 miles of pavement repairs, resurfacing, and other improvements to Interstate 74 just east of Peoria (West-Central Illinois) | Pavement Improvement | 05/11/2009 | 05/26/2009 | 11/30/2009 | 8138828 | 6.73
1545 | Illinois | ADAMS |  | 18 | 0745079 | This project will extend the pavement life by resurfacing a portion of Illinois Route 104 to the east from Quincy (West-Central Illinois). | Pavement Improvement | 04/28/2009 | 05/18/2009 | 11/30/2009 | 4637785.19 | 3.42
1546 | Illinois | CHAMPAIGN, PIATT |  | 15 | 0745158 | This project will extend the pavement life by providing for 4.6 miles of pavement repairs, resurfacing, safety improvements on Interstate 74 west of Champaign (East-Central Champaign) | Pavement Improvement | 05/06/2009 | 05/28/2009 | 10/30/2009 | 3421383 | 10.95
1547 | Illinois | MORGAN |  | 18 | 0753036 | This project will extend the pavement life by resurfacing a portion of Illinois Route 104 near Waverly (West-Central Illinois). | Pavement Improvement | 04/30/2009 | 07/27/2009 | 11/30/2009 | 2141301 | 2.1
1548 | Illinois | CALHOUN |  | 17 | 0754113 | This project will extend the pavement life by milling, patching and resurfacing of County Highway 1 from the Village of Hardin city limits to Lincoln Valley Road in Calhoun County, Illinois (Southwest | Pavement Improvement | 12/29/2009 |  | 05/30/2010 | 157888 | 0.64
1549 | Illinois | SHELBY |  | 19 | 0766005 | This project will extend the pavement life by resurfacing a portion of Illinois Route 32 west of Oblong (Southeast Illinois). | Pavement Improvement | 04/23/2009 | 04/30/2009 | 10/30/2009 | 2100201 | 13
1550 | Illinois | CUMBERLAND |  | 15 | 0773008 | This project will extend the pavement life by resurfacing a portion of Illinois Route 121 in Greenup (Southeast Illinois). | Pavement Improvement | 04/23/2009 | 05/18/2009 | 09/30/2009 | 1464670 | 5.18
1551 | Illinois | BOND |  | 19 | 0777114 | This project will extend the pavement life by resurfacing Sorento Road from New Douglas road to Crane Road in Sorento, Illinois (Southwest Illinois). | Pavement Improvement | 11/03/2009 |  | 05/30/2010 | 215000 | 5.65
1552 | Illinois | CRAWFORD |  | 15 | 0781030 | This project will extend the pavement life by resurfacing a portion of Illinois Route 33 west of Oblong (Southeast Illinois). | Pavement Improvement | 05/11/2009 | 05/26/2009 | 07/30/2010 | 5815236 | 2.52
1553 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 0788004 | This project will substantially improve the roadway by reconstructing a section of Illinois Route 3 by providing new pavement and other roadway improvements in Venice (Southwest Illinois). | New Construction | 06/16/2009 | 07/06/2009 | 08/30/2011 | 3470924 | 0.63
1554 | Illinois | CLAY |  | 19 | 0801230 | Preliminary engineering for a structure replacement over Laws Creek east of Ingram in Clay County. Section 09-00082-00-BR | Other | 06/19/2009 | 06/22/2009 | 10/30/2009 | 47000 | 0
1555 | Illinois | BUREAU |  | 11 | 0802064 | This project will extend the pavement life by resurfacing 7.5 miles of Interstate 80 near the city of Seatonville (East-Central Illinois). | Pavement Improvement | 05/21/2009 | 06/08/2009 | 10/30/2009 | 3980030 | 7.36
1556 | Illinois | LA SALLE |  | 11 | 0803130 | This project will extend the pavement life by resurfacing 30 miles of Interstate 80 in LaSalle County (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 05/17/2009 | 08/30/2009 | 1188102 | 29.99
1557 | Illinois | GRUNDY |  | 11 | 0803131 | This project will extend the pavement life by providing a surface treatment on 6.3 miles of Interstate 80 in western Grundy County (East-Central Illinois). | Pavement Improvement | 05/11/2009 | 06/15/2009 | 07/30/2009 | 1414141 | 6.3
1558 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0805071 | This project will extend the pavement life by resurfacing 6.125 miles of I-80 from 80th Ave to I-290 in the Tinley Park, Country Club Hills, and Hazel Crest. (Northeastern Illinois). | Pavement Improvement | 10/27/2009 |  | 08/30/2010 | 15769000 | 13.11
1559 | Illinois | CHAMPAIGN |  | 15 | 0836028 | This project will extend the pavement life by providing for 5.7 miles of pavement removal and resurfacing on Illinois Route 49 southeast of Champaign (East-Central Illinois) | Pavement Improvement | 05/06/2009 | 05/11/2009 | 08/30/2009 | 1099137 | 5.98
1560 | Illinois | WILL |  | 11 | 0840061 | This project will extend the pavement life by resurfacing 3.33 miles on IL 50north of Peotone (Northeast Illinois). | Pavement Improvement | 04/28/2009 | 05/05/2009 | 09/30/2009 | 1574903 | 4.11
1561 | Illinois | IROQUOIS |  | 15 | 0840062 | This project will extend the pavement life by resurfacing 10.7 miles of IL 49 near the city of Crescent City (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 06/08/2009 | 10/30/2009 | 2185660 | 10.8
1562 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0840063 | This project will extend the pavement life by resurfacing 2.06 miles on IL 50 in Monee/Peotone (Northeast Illinois). | Pavement Improvement | 10/16/2009 |  | 06/30/2010 | 907356 | 1.91
1563 | Illinois | GRUNDY |  | 11 | 0846019 | This project will extend the pavement life by resurfacing 6.4 miles of IL 53 near the city of Gardener (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 06/13/2009 | 10/30/2009 | 1797640 | 6.3
1564 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0852011 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 52 over Jackson Creek 4 miles southeast of IL 53 (Northeast Illinois). | Pavement Improvement | 04/28/2009 | 06/09/2009 | 08/30/2009 | 309740 | 0.01
1565 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0856025 | This project will extend the pavement life by resurfacing 2.65 miles on IL 7 in Joliet and Crest Hill (Northeast Illinois). | Pavement Improvement | 10/23/2009 |  | 07/30/2010 | 1739465 | 6.81
1566 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0866007 | This project will substantially improve the roadway by resurfacing 4.41 miles, widening, installing traffic signals and drainage improvements on IL 83 from Wisconsin State line to Petite Lake Rd in th | Pavement Improvement | 08/24/2009 | 09/08/2009 | 05/30/2011 | 13436001 | 9.24
1567 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 0870011 | This project will extend the pavement life by resurfacing 1.06 miles on IL 53 in the City of Lombard (Northeast Illinois). | Pavement Improvement | 04/30/2009 | 05/18/2009 | 08/30/2009 | 503716 | 0.99
1568 | Illinois | WHITE |  | 19 | 0877013 | This project will substantially improve the roadway by constructing a new bridge over a tributary of Can Creek on IL 141 in White County, Illinois (Southern Illinois) | Bridge Replacement | 12/10/2009 |  | 11/30/2010 | 785603 | 0.2
1569 | Illinois | WHITESIDE |  | 17 | 0881018 | This project will extend the pavement life by resurfacing 7.9 miles of Interstate 88 near the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 05/11/2009 | 05/26/2009 | 10/30/2009 | 4382273 | 8.45
1570 | Illinois | JOHNSON |  | 19 | 0885040 | This project will extend the pavement life by milling, patching and resurfacing 8.46 miles of IL 146 in Johnson County, Illinois (Southern Illinios). | Pavement Improvement | 06/02/2009 | 06/25/2009 | 08/30/2009 | 1549794 | 8.78
1571 | Illinois | WHITE |  | 15 | 0887108 | Grade slopes and place riprap to prevent erosion for 0.55 miles on County Highway 7 in White County, Illinois (Southern Illinois) | Pavement Improvement | 09/09/2009 | 10/08/2009 | 10/30/2009 | 300757 | 2
1572 | Illinois | WHITE |  | 15 | 0887109 | Grade slopes and place riprap to prevent erosion for 0.26 miles on County Highway 7 in White County, Illinois (Southern Illinois) | Pavement Improvement | 12/10/2009 | 12/15/2009 | 05/30/2010 | 66757 | 0.45
1573 | Illinois | GALLATIN |  | 15 | 0888122 | This project will extend the pavement life by resurfacing 4.48 of County Highway 3 in Gallatin Coutny, Illinois (Southern Illinois). | Pavement Improvement | 07/30/2009 | 11/09/2009 | 10/30/2009 | 190041 | 9
1574 | Illinois | SALINE |  | 19 | 0898107 | This project will extend the pavement life by resurfacing Harco Road from IL 13 to Brushy Creek Road in Saline County (Southern Illinois). | Pavement Improvement | 12/17/2009 |  | 07/30/2010 | 286154 | 4.39
1575 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0904117 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the Sayre Avenue Bridge over I-90 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 04/23/2009 | 06/08/2009 | 09/30/2010 | 2747690 | 0.01
1576 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0904118 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the Central Avenue Bridge over I-90 in the City of Chicago, Cook County. (Northeastern Il | Bridge Improvement | 04/28/2009 | 05/18/2009 | 11/30/2009 | 2664706 | 0.01
1577 | Illinois | JACKSON |  | 12 | 0915102 | This project will extend the pavement life by milling, patching and resurfacing 1.57 miles of Grand Tower Road in Jackson County, Illinois (Southern Illinios). | Pavement Improvement | 07/30/2009 | 08/27/2009 | 10/30/2009 | 382828 | 1.59
1578 | Illinois | MASSAC |  | 19 | 0931110 | This project will extend the pavement life by resurfacing 1.35 miles of County Highway 11 in Massac County, Illinois (Southern Illinois). | Pavement Improvement | 09/10/2009 | 10/05/2009 | 10/30/2009 | 176112 | 2.7
1579 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0943416 | This project will extend the pavement life by resurfacing 6.97 miles of I-94 (Bishop Ford Expressway) from Martin Luther King Drive to 130th Street (south of Dolton Avenue) in Chicago in Cook County. | Pavement Improvement | 05/07/2009 | 05/18/2009 | 08/30/2010 | 13664922 | 5.26
1580 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0943417 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on I-94 over the Little Calumet River and Greenwood Ave. Additionally, the project will sub | Pavement Improvement | 04/29/2009 | 05/11/2009 | 05/30/2010 | 13162234 | 4.29
1581 | Illinois | ALEXANDER |  | 12 | 0946107 | This project will extend the pavement life by resurfacing 3.99 miles of Miller City Road in Alexander County, Illinois (Southern Illinois). | Pavement Improvement | 07/30/2009 | 09/09/2009 | 10/30/2009 | 184896 | 8
1582 | Illinois | WHITESIDE |  | 17 | 1225115 | This project will extend the pavement life by resurfacing sections of Albany Road in western Whiteside County (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 10/12/2009 | 11/30/2009 | 505781 | 9.18
1583 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 1238009 | This project will extend the pavement life by resurfacing 2.83 miles on IL 176 from Midlothian to IL 21 in the Villages of Libertyville and Mundelein (Northeastern Illinois) | Pavement Improvement | 10/21/2009 |  | 07/30/2010 | 1120577 | 7.28
1584 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 1238010 | This project will extend the pavement life by resurfacing 1.17 miles on IL 176 from IL Rt. 21 to St. Mary's Rd in the Village of Libertyville (Northeastern Illinois). This project will also improve b | Pavement Improvement | 10/23/2009 |  | 08/30/2010 | 858704 | 2.92
1585 | Illinois | LAKE, COOK, MCHENRY |  | 08 | 1270004 | This project will extend the pavement life by milling, patching and resurfacing 4.25 miles on Lake-cook Rd from Kane, McHenry, cook county line to Old Hart Rd in Barrington Hills (Northeastern Illinoi | Pavement Improvement | 12/07/2009 |  | 06/30/2010 | 944906 | 9.06
1586 | Illinois | KANKAKEE |  | 11 | 1299109 | This project will extend pavement life by resurfacing a section of County Highway 7 in northern Kankakee County (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 09/14/2009 | 09/30/2009 | 431841 | 6.56
1587 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1319001 | This project will extend the pavement life by 1.45 miles of resurfacing of Ballard Rd from Rand Rd easterly to Greenwood Ave in the Villages of DesPlaines, Glenview, Niles, Park Ridge, Cook County (No | Pavement Improvement | 10/28/2009 |  | 06/30/2010 | 753728 | 3.78
1588 | Illinois | KANKAKEE |  | 11 | 1323114 | This project will extend the pavement life by resurfacing 7 miles of IL 115 near the city of Kankakee (East-Central Illinois). | Pavement Improvement | 04/23/2009 | 06/08/2009 | 10/30/2009 | 1380976 | 9.8
1589 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1332015 | This project will extend the pavement life by resurfacing 3.27 miles of IL 43 (Oakton St) from South DesPlaines Road to US 14 (Caldwell Ave) in Park Ridge & Niles in Cook County. (Northeastern Illinoi | Pavement Improvement | 06/01/2009 | 06/11/2009 | 11/30/2009 | 3091049.58 | 3.27
1590 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1340009 | This project will extend the pavement life by resurfacing 0.8 miles of Touhy Ave from IL50 to US41 and from Lawndale Ave to Kimball Ave in Village of Lincolnwood, Cook County (Northeastern Illinois). | Pavement Improvement | 10/28/2009 |  | 06/30/2010 | 623114 | 2.26
1591 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 1363004 | This project will extend the pavement life by resurfacing 0.98 miles of Gunnison St. from IL 43 (Harlem Ave) to Nagle Ave in Chicago and the Village of Harwood Heights in Cook County (Northeastern Ill | Pavement Improvement | 11/03/2009 |  | 06/30/2010 | 825660 | 2
1592 | Illinois | PEORIA | PEORIA | 18 | 1380106 | This project will extend the pavement life by providing for 3.4 miles of pavement repairs and resurfacing of Illinois Route 91 just north of Peoria (West-Central Illinois). | Pavement Improvement | 07/30/2009 | 08/17/2009 | 11/30/2009 | 1240430 | 6.98
1593 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 04 | 1395003 | This project will extend the pavement life by resurfacing 1.40 miles of Chicago Avenue from Lake St to Thatcher Rd in Melrose Park & Maywood in Cook County. (Northeastern Illinois). | Pavement Improvement | 04/23/2009 | 05/04/2009 | 08/30/2009 | 690675.76 | 1.47
1594 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1459004 | This project will extend the pavement life by resurfacing 2.95 miles of 26th Street from IL 43 to IL 50 in Berwyn & Cicero in Cook County. (Northeastern Illinois). | Pavement Improvement | 04/28/2009 | 05/18/2009 | 09/30/2009 | 1198907 | 3.11
1595 | Illinois | TAZEWELL |  | 18 | 1464103 | This project wil extend the pavement life by providing for 0.41 mile of pavement removal and resurfacing on Locast Street in Delavan, south of Peoria (West-Central Illinois). | Pavement Improvement | 09/14/2009 |  | 09/30/2009 | 125000 | 0.68
1596 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1467006 | This project will extend the pavement life by milling, patching and resurfacing 0.55 miles on 31st Street from IL 171 to DesPlaines Avenue and also on 31st St. from Golfview Rd to IL 171 in the Villag | Pavement Improvement | 04/28/2009 | 05/25/2009 | 07/30/2009 | 265914 | 0.27
1597 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1467007 | This project will extend the pavement life by milling, patching and resurfacing 3.61 miles of 31st St from Wolf Rd to IL 171 in the Villages of Westchester, Brookfield, LaGrange Park. (Northeastern I | Pavement Improvement | 09/09/2009 | 11/07/2009 | 07/30/2010 | 1762647 | 7.38
1598 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 1488004 | This project will extend the pavement life with 2.58 miles of milling, resurfacing, patching, curb & gutter, pavement marking & detector loops on 47th St from DuPage County line to East Ave, Cook Coun | Pavement Improvement | 10/21/2009 |  | 08/30/2010 | 1284808 | 6.06
1599 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 1527012 | This project will substantially improve the roadway network by constructing four new bridges and rehabilitation of an existing bridge. Two of the new bridges are located at IL Rt 25/Dunham and IL Rt 2 | New Construction | 07/27/2009 | 08/18/2009 | 05/30/2011 | 1100000 | 0
1600 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1566002 | This project will extend the life of the pavement by surface removal, pavement patching, guardrail removal and replacement, pavement marking on 2.46 miles of 95th st from IL 171 (Archer Ave) to US 45 | Pavement Improvement | 05/06/2009 | 05/18/2009 | 08/30/2009 | 780519 | 2.54
1601 | Illinois | MASON |  | 18 | 1595103 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE CARRING CH19 OVER SLEEPY HOLLOW DITCH, PHASE I AND II, MASON COUNTY SECTION 08-00035-01-BR | Other | 11/06/2009 | 11/06/2009 | 07/30/2010 | 26681 | 0.01
1602 | Illinois | MORGAN |  | 18 | 1614104 | This project will extend the pavement life by resurfacing a portion of County Highway 32 in Morgan County and adding lighting at an intersection for a safety improvement near Jacksonville (West-Centra | Pavement Improvement | 09/08/2009 | 09/08/2009 | 11/30/2009 | 328970 | 3.89
1603 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 1618001 | This project will extend the life of the pavement by resurfacing 0.72 miles of 175th Street from Governor's Highway to the intersection of 175th Street and Dixie Hwy in the Village of Homewood in Cook | Pavement Improvement | 05/06/2009 | 07/15/2009 | 08/30/2009 | 309819 | 0.75
1604 | Illinois | ADAMS |  | 17 | 1721002 | This project will extend the pavement life by patching and resurfacing a portion Interstate 172 around Quincy, Illinois (West-Central Illinois). | Pavement Improvement | 05/04/2009 | 05/12/2009 | 08/30/2010 | 14473005 | 9.41
1605 | Illinois | CLINTON |  | 19 | 1784105 | This project will extend the pavement life by milling, patching and resurfacing 5.5 miles of County Highway 5 near Centralia, Illinois (Southwest Illinios). | Pavement Improvement | 08/12/2009 | 10/01/2009 | 10/30/2009 | 70000 | 11.04
1606 | Illinois | MARION |  | 19 | 1790103 | This project will extend the pavement life by milling, patching and resurfacing County Highway 32 from Jefferson Road to I-57 in Marion County, Illinois (Southwest Illinios). | Pavement Improvement | 08/05/2009 | 08/17/2009 | 10/30/2009 | 367987 | 4.53
1607 | Illinois | WABASH |  | 19 | 1819107 | This project will extend the pavement life by resurfacing a portion of Goodson Orchard Road in Wabash County (Southeast Illinois). | Pavement Improvement | 01/04/2010 |  | 06/30/2010 | 147866 | 3.25
1608 | Illinois | MONROE |  | 12 | 1858103 | This project will extend the pavement life by providing a surface treatment on 2.18 miles of County Highway 12 from IL156 to County Highway 6 near Valmeyer, Illinois (Southwest Illinois) | Pavement Improvement | 08/25/2009 | 08/31/2009 | 09/30/2009 | 149789 | 4.18
1609 | Illinois | RANDOLPH |  | 12 | 1870108 | This project will extend the pavement life by resurfacing Wine Hill Road from Welge Road to County Highway 5 near Steelville, Illinois (Southwest Illinois). | Pavement Improvement | 12/14/2009 |  | 06/30/2010 | 405449 | 2.92
1610 | Illinois | WILLIAMSON |  | 12 | 1887106 | This project will extend the pavement life by resurfacing Saraville Road from Crab Orchard road to Ewing Road in Williamson County, Illinois (Southern Illinois). | Pavement Improvement | 12/17/2009 |  | 06/30/2010 | 391904 | 2.8
1611 | Illinois | JACKSON |  | 12 | 1908001 | This project will extend the pavement life by milling, patching and resurfacing 7.8 miles of IL 151 in Jackson County, Illinois (Southern Illinios). | Pavement Improvement | 04/28/2009 | 05/12/2009 | 10/30/2009 | 2143872 | 7.84
1612 | Illinois | MARSHALL |  | 18 | 2370114 | This project will extend the pavement life by providing for 7.0 miles of removal and replacement of roadway surface on IL Route 26 near the City of Lacon which is approximately 25 miles north of the C | Pavement Improvement | 04/28/2009 | 06/12/2009 | 08/30/2009 | 1390284.14 | 7.01
1613 | Illinois | ADAMS |  | 17 | 2592102 | This project will extend the pavement life by resurfacing six miles of Adams County Highway near Loraine (West-Central Illinois). | Pavement Improvement | 07/30/2009 | 08/24/2009 | 10/30/2009 | 527967 | 12
1614 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 2612002 | This project will extend the bridge life by adding a new deck overlay, new joints, repairing the backwall of the north abutment and making other roadway improvements on Lemont Road over Des Plaines Ri | Bridge Improvement | 04/28/2009 | 05/28/2009 | 11/30/2009 | 4475086.74 | 0.01
1615 | Illinois | MOULTRIE |  | 15 | 2660101 | This project will substantially improve the roadway by reconstructing a section of County Highway 19 near Sullivan in Moultrie County (Southeast Illinois). | Pavement Improvement | 09/09/2009 | 09/16/2009 | 10/30/2009 | 262058 | 2.54
1616 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2697005 | This project will extend the bridge life by bridge deck patching and overlay on Willow Springs Road over the DesPlaines River and I&M Canal in the Village of Willow Springs in Cook County. (Northeaste | Bridge Improvement | 06/01/2009 | 06/15/2009 | 11/30/2009 | 4390092 | 0.01
1617 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 2706103 | This project will extend the pavement life by milling, patching and resurfacing 1.63 miles on IL Rt 43 (Waukegan Rd) from IL Rt 60 to Gage Lane in the Villages of Lake Forest and Lake Bluff (Northeast | Pavement Improvement | 10/23/2009 |  | 07/30/2010 | 956788 | 3.3
1618 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 2710010 | This project will extend the pavement life by resurfacing 1.05 miles of DesPlaines River Rd from Touhy Ave to Devon Ave in the City of DesPlaines and Village of Rosemont in Cook County. (Northeastern | Pavement Improvement | 06/02/2009 | 07/09/2009 | 09/30/2009 | 728513 | 1.32
1619 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 2711016 | This project will extend the pavement life by resurfacing 3.24 miles on IL Rt 131 from IL Rt 120 to just south of IL Rt 137 in the City of North Chicago (Northeastern Illinois) | Pavement Improvement | 05/06/2009 | 05/18/2009 | 09/30/2009 | 2673893 | 3.09
1620 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 2714010 | This project will extend the pavement life by resurfacing 0.55 miles of 25th Avenue from Belmont Ave to Addison Street in the Village of Franklin Park in Cook County. (Northeasern Illinois). | Pavement Improvement | 06/01/2009 | 10/13/2009 | 08/30/2009 | 376231 | 0.5
1621 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2719001 | This project will extend the pavement life by milling, patching and resurfacing 0.74 miles of East Avenue between 47th and 55th Streets in Summit (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/25/2009 | 09/30/2009 | 420852 | 1
1622 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 2759003 | This project will extend the pavement life by resurfacing 1.29 miles of DesPlaines Avenue from Randolph Street to Roosevelt Road in Forrest Park in Cook Co. (Northeastern Illinois). | Pavement Improvement | 04/28/2009 | 05/04/2009 | 09/30/2009 | 1000006 | 1.34
1623 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2759004 | This project will extend pavement life by resurfacing 1.038 miles of Des Plaines Avenue from Roosevelt Road to Cermak Road within the Village of Forest Park in Cook County (Northeastern Illinois). | Pavement Improvement | 10/28/2009 |  | 06/30/2010 | 767571 | 2.14
1624 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 2831002 | This project will extend the bridge life by making full depth deck repairs, structural repairs, deck overlay, and other roadway improvements to the Kedzie Avenue bridge over the Cal-Sag Channel in Rob | Bridge Improvement | 10/23/2009 |  | 08/30/2010 | 1297860 | 0.02
1625 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 2843006 | This project will extend the life of the pavement by resurfacing 1.07 miles of Dixie Highway just north of 183rd Street to Governor's Highway in Village of Homewood, Cook County (Northeastern Illinois | Pavement Improvement | 06/02/2009 | 07/02/2009 | 10/30/2009 | 573542 | 1.08
1626 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 2907002 | This project will extend the pavement life by resurfacing 1.15 miles of State Street from 60th Street to 69th Street within the City of Chicago in Cook County. (Northeastern, Illinois). | Pavement Improvement | 10/16/2009 |  | 07/30/2010 | 1074300 | 1.44
1627 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 2943016 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements to the Burnham Avenue bridge over State Street, Indiana Harbor Beltway and CSX Railroad and | Bridge Improvement | 05/04/2009 | 05/06/2009 | 10/30/2009 | 3770183 | 0.01
1628 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 3523006 | This project will extend the pavement life by milling, patching and resurfacing 2.6 miles on US 12 from 3rd Avenue to US 12/45 and along Rand Rd from Des Plaines River Road to Lundgren Ave in Des Plai | Pavement Improvement | 06/02/2009 | 06/13/2009 | 10/30/2009 | 1908170 | 1.25
1629 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 3592005 | This project will extend the pavement life by milling, patching and resurfacing 0.94 mile of Brainard Avenue from Burnham Ave to the Indiana State line in the Village of Burnham in Cook County. (North | Pavement Improvement | 06/01/2009 | 06/23/2009 | 09/30/2009 | 386526 | 1.08
1630 | Illinois | CASS |  | 18 | 5002021 | This project will extend the pavement life by resurfacing a portion of Cass County Highway 7 from western edge of Beardstown for five miles to the west (West-Central Illinois). | Pavement Improvement | 09/15/2009 | 10/19/2009 | 11/30/2009 | 170449 | 1.46
1631 | Illinois | BOONE |  | 16 | 5004010 | This project will extend the pavement life by resurfacing a section of Newburg Road and other roadway improvements in the city of Belvidere (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/23/2009 | 11/30/2009 | 500000 | 5.6
1632 | Illinois | FULTON |  | 17 | 5007022 | This project will extend the pavement life by providing for pavement repairs and resurfacing on Elm Street and Walnut Street in the City of Canton, approximately 25 miles southwest of Peoria (West-Cen | Pavement Improvement | 09/08/2009 | 09/18/2009 | 10/30/2009 | 315000 | 2.25
1633 | Illinois | FULTON |  | 17 | 5007023 | This project will provide for pedestrian safety by constructing 6 blocks of new concrete sidewalk along the north side of Ash Street in the City of Canton, approximately 25 miles southwest of Peoria ( | Safety/Traffic Management | 09/22/2009 | 09/22/2009 | 12/30/2009 | 147428 | 1.29
1634 | Illinois | JACKSON |  | 12 | 5008024 | This project will substantially improve mobility by constructing the missing section that connects Marion Street together by providing new concrete pavement, curb and gutter and sidewalk in the city o | New Construction | 09/10/2009 | 09/23/2009 | 12/30/2009 | 319253 | 0
1635 | Illinois | JACKSON |  | 12 | 5008025 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Carbondale, Illinois (Southern Illinois). | Pavement Improvement | 07/30/2009 | 08/03/2009 | 11/30/2009 | 455000 | 0.62
1636 | Illinois | WHITE |  | 19 | 5010010 | This project will extend the pavement life by resurfacing numerous roadway sections in the village of Carmi, Illinois (Southern Illinois). | Pavement Improvement | 10/27/2009 |  | 12/30/2009 | 164004 | 0.74
1637 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011263 | This project will extend the pavement life by resurfacing and repair broken curb and gutter on Lindenthal Ave. from Washington st. to Poplar St. in the City of Highland, IL (Southwest Illinois). | Pavement Improvement | 08/03/2009 | 08/24/2009 | 09/30/2009 | 201250 | 0.44
1638 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011267 | Preliminary engineering for the milling and resurfacing of Madison Ave. in Edwardsville. Section 09-00099-00-RS | Other | 06/18/2009 | 06/22/2009 | 10/30/2009 | 34000 | 1
1639 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011269 | Resurface FAU 9002 (Fosterburg Rd) from 100' north of Stutz Lane to Drexelius Rd & culvert repair in Alton | Pavement Improvement | 12/28/2009 |  |  | 369000 | 0.5
1640 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011270 | This project will extend the pavement life by milling, patching and resurfacing .25 miles of Ostle Dr. from Newport Dr. to Waverly Dr. in Collinsville, Illinois (Southwest Illinios). | Pavement Improvement | 09/23/2009 | 09/23/2009 | 05/30/2010 | 165000 | 0.27
1641 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011271 | This project will extend the pavement life by milling, patching and resurfacing Main St. from Shamrock Ave. to Lakeside Ave. in the city of East Alton, Illinois (Southwest Illinios). | Pavement Improvement | 09/23/2009 | 09/23/2009 | 06/30/2010 | 400000 | 0.5
1642 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011274 | This project will extend the pavement life by resurfacing Maryville Road from St. Clair Ave. to Terminal Ave. in Granite City, Illinois (Southwest Illinois). | Pavement Improvement | 12/29/2009 |  | 06/30/2010 | 400000 | 0.46
1643 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011276 | Preliminary engineering for the resurfacing of West Main Street (Glen Carbonn Road) in the village of Glen Carbon. Section 09-00018-01-RS | Other | 06/18/2009 | 06/22/2009 | 10/30/2009 | 26900 | 1
1644 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011277 | Project consists of concrete pavement widening, construction of concrete curb and gutter and installation of storm sewer along Frank Scott Parkway West from Belleville West Parkway to Concordia Church | Pavement Improvement | 09/10/2009 | 09/21/2009 | 05/30/2010 | 640000 | 4.12
1645 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011279 | Construct new sidewalk, Replace broken sidewalk and upgrade sidewalk/street crossings to accommodate those with disabilities along Monroe St. from St. Louis St. to Marner Park in the city of Lebanon, | Safety/Traffic Management | 09/14/2009 | 10/05/2009 | 03/30/2010 | 334400 | 1.47
1646 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011290 | This project will extend the pavement life by milling, patching and resurfacing Pontoon Rd from Breckenridge Ln. to IL111 in Pontoon Beach, Illinois(Southwest Illinios). | Pavement Improvement | 08/25/2009 | 08/25/2009 | 12/30/2009 | 279500 | 1.55
1647 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011292 | This project will extend the pavement life by milling, patching and resurfacing .44 miles of Frontage Road from Harvestyme Lane to clara Dr. in Troy, Illinois (Northwest Illinios). | Pavement Improvement | 10/29/2009 |  | 05/30/2010 | 134750 | 0.54
1648 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011293 | This project will extend the pavement life by resurfacing 6th street from IL 143 to Rohm Place in the city of Wood River, Illinois(Southwest Illinois). | Pavement Improvement | 12/22/2009 |  | 05/30/2010 | 255300 | 0.59
1649 | Illinois | CLINTON |  | 19 | 5012017 | This project will extend the pavement life by resurfacing Brookside Ave. from 15th street to 17th street in Wamac, Illinois (Southwest Illinois). | Pavement Improvement | 11/18/2009 |  | 05/30/2010 | 41880 | 0.13
1650 | Illinois | COLES |  | 15 | 5013016 | This project will extend the pavement life by resurfacing numerous roadway sections in the City of Charleston (Southeast Illinois). | Pavement Improvement | 09/10/2009 | 10/21/2009 | 11/30/2009 | 340000 | 0
1651 | Illinois | DE WITT |  | 15 | 5015004 | This project will extend the pavement life by resurfacing 5 blocks of Washington Street in Clinton, approximately 25 miles south of Bloomington (East-Central Illinois) | Pavement Improvement | 10/15/2009 |  | 08/30/2010 | 226405 | 0.31
1652 | Illinois | VERMILION |  | 15 | 5016037 | This project will extend the pavement life by resurfacing a section of Denmark Road in Danville, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 12/10/2009 |  | 07/30/2010 | 700000 | 2.88
1653 | Illinois | VERMILION |  | 15 | 5016038 | This project will substantially improve Voorhees Street by constructing a new bridge over the CSX railroad and providing 0.8 mile of resurfacing in Danville, approximately 30 miles east of Champaign ( | Pavement Improvement | 12/14/2009 |  | 10/30/2010 | 700000 | 1
1654 | Illinois | VERMILION |  | 15 | 5016039 | This project will extend the pavement life by resurfacing 0.8 mile of Main Street in Westville, approximately 35 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 01/08/2010 |  | 06/30/2010 | 217531 | 0.99
1655 | Illinois | DE KALB |  | 14 | 5017040 | This project will extend the pavement life by resurfacing a section of Fairview Drive in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 08/12/2009 | 09/03/2009 | 10/30/2009 | 750000 | 2.92
1656 | Illinois | PERRY |  | 12 | 5019007 | This project will extend the pavement life by milling, patching and resurfacing 0.55 miles of Cole Street from Division St. to Line St. in the city of DuQuoin, Illinois (Southern Illinois). | Pavement Improvement | 10/22/2009 | 11/16/2009 | 12/30/2010 | 201632 | 0.52
1657 | Illinois | EFFINGHAM |  | 19 | 5021025 | This project will substantially improve the roadway by constructing a section of Veterans Drive by providing new concrete pavement in Effingham (Southeast Illinois). | Pavement Improvement | 12/17/2009 |  | 09/30/2010 | 374589 | 0.1
1658 | Illinois | STEPHENSON |  | 16 | 5024026 | This project will extend the pavement life and complete other roadway improvements by resurfacing and sidewalk improvements to numerous sections of streets in the city of Freeport (Northwest Illinois) | Pavement Improvement | 10/07/2009 | 10/13/2009 | 06/30/2009 | 799842 | 2.62
1659 | Illinois | KNOX |  | 17 | 5025043 | This project will substantially improve the roadway by reconstructing and providing additional roadway improvements for a 1/4 mile section of Carl Sandburg Drive in the City of Galesburg (West-Central | Pavement Improvement | 07/27/2009 | 07/30/2009 | 10/30/2009 | 249852 | 0.72
1660 | Illinois | KNOX |  | 17 | 5025044 | This project will improve a section of Knox Street by providing a new surface, sidewalks, and drainage improvements in the City of Galesburg (West-Central Illinois) | Pavement Improvement | 08/05/2009 | 08/05/2009 | 11/30/2009 | 471959 | 1.34
1661 | Illinois | KNOX |  | 17 | 5025046 | This project will improve a 1/2 mile section of South Seminary Street by providing a new surface, sidewalks, and drainage improvements in the City of Galesburg (West-Central Illinois) | Pavement Improvement | 10/20/2009 | 10/30/2009 | 12/30/2009 | 279099 | 1.02
1662 | Illinois | HENRY |  | 14 | 5026011 | This project will extend the pavement life by providing a surface treatment on numerous roadway sections in the city of Geneseo (Northwest Illinois). | Pavement Improvement | 08/27/2009 | 09/24/2009 | 10/30/2009 | 196006 | 0
1663 | Illinois | VERMILION |  | 15 | 5031008 | This project will extend the pavement life by resurfacing 0.8 mile of North Market Street in Hoopeston, approximately 50 miles northeast of Champaign (East-Central Illinois) | Pavement Improvement | 12/28/2009 |  | 09/30/2010 | 180428 | 0.87
1664 | Illinois | MORGAN |  | 18 | 5032028 | This project will extend the pavement life by resurfacing a portion of the Village of South Jacksonville's East Vandalia Road (West-Central Illinois). | Pavement Improvement | 09/10/2009 | 10/27/2009 | 10/30/2009 | 105111 | 0.88
1665 | Illinois | LA SALLE |  | 11 | 5036025 | This project will extend the pavement life by resurfacing a section of Richard Moyle Sr. Highway in the city of Oglesby (East-Central Illinois). | Pavement Improvement | 09/09/2009 | 09/09/2009 | 09/30/2009 | 110313 | 2.06
1666 | Illinois | LA SALLE |  | 11 | 5036026 | This project will extend the pavement life and improve pedestrian safety by resurfacing and reconstructing sidewalks for numerous roadway sections in the city of Peru (East-Central Illinois). | Pavement Improvement | 09/15/2009 | 10/01/2009 | 12/30/2009 | 297500 | 1.66
1667 | Illinois | MCDONOUGH |  | 17 | 5040009 | This project will substantially improve the roadway by reconstructing a section of Ward Street with new concrete pavement and other roadway improvements in the City of Macomb which is approximately 60 | Pavement Improvement | 08/03/2009 | 08/19/2009 | 08/30/2020 | 376800 | 1.02
1668 | Illinois | MCDONOUGH |  | 17 | 5040010 | This project will substantially improve the roadway by reconstructing a section of Ward Street with new concrete pavement and other roadway improvements, including sidewalk, in the City of Macomb appr | Pavement Improvement | 10/23/2009 |  | 08/30/2010 | 229517 | 0.26
1669 | Illinois | WILLIAMSON |  | 12 | 5041022 | LAND ACQUISITION FOR THE WIDENING OF MORGAN AVE. FROM CORBON ST. TO NORTH RUSSELL ST IN MARION, SECTION 08-00105-00-FP | Other | 08/26/2009 |  | 10/30/2009 | 90000 | 0
1670 | Illinois | MASSAC |  | 19 | 5045008 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Metropolis, Illinois (Southern Illinois). | Pavement Improvement | 09/09/2009 | 10/05/2009 | 10/30/2009 | 196066 | 0
1671 | Illinois | WARREN |  | 17 | 5046007 | This project will extend the pavement life by resurfacing 0.60 mile of North Main Street in Monmouth, west of Galesburg (West-Central Illinois) | Pavement Improvement | 09/09/2009 | 09/21/2009 | 12/30/2009 | 297669 | 1.1
1672 | Illinois | GRUNDY |  | 11 | 5047008 | This project will extend the pavement life and complete other roadway improvements by resurfacing numerous roadway sections in the city of Morris (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 09/28/2009 | 10/30/2009 | 360796 | 0
1673 | Illinois | WABASH |  | 15 | 5048020 | This project will extend the pavement life by resurfacing a portion of 3rd Street in Mt. Carmel (Southeast Illinois). | Pavement Improvement | 10/16/2009 | 10/26/2009 | 12/30/2009 | 241438 | 0.95
1674 | Illinois | JACKSON |  | 12 | 5050013 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Murphysboro, Illinois (Southern Illinois). | Pavement Improvement | 12/10/2009 |  | 06/30/2010 | 262974 | 0.7
1675 | Illinois | HENRY |  | 17 | 5053012 | This project will extend the pavement life and improve pedestrian safety by resurfacing numerous roadway sections and construction of sidewalks in the city of Kewanee (Northwest Illinois). | Pavement Improvement | 10/16/2009 |  | 05/30/2010 | 391527 | 1.14
1676 | Illinois | EDGAR |  | 15 | 5054008 | This project will extend the pavement life by resurfacing 1 block of Crawford Street in Paris, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 10/14/2009 |  | 05/30/2010 | 47395 | 0.14
1677 | Illinois | EDGAR |  | 15 | 5054009 | This project will extend the pavement life by resurfacing 4 blocks of Wood Street and Court Street in Parkis, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 12/09/2009 |  | 06/30/2010 | 227164 | 0.25
1678 | Illinois | KENDALL |  | 14 | 5055001 | This project will extend pavement life by resurfacing a section of Center Street in the city of Plano (East-Central Illinois). | Pavement Improvement | 10/16/2009 | 04/10/2010 | 05/30/2010 | 323440 | 1.21
1679 | Illinois | LIVINGSTON |  | 15 | 5056017 | This project will extend pavement life by resurfacing a section of Deerfield Road in the city of Pontiac (East-Central Illinois). | Pavement Improvement | 09/15/2009 | 10/01/2009 | 12/30/2009 | 358860 | 2.02
1680 | Illinois | BUREAU |  |  | 5057006 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Princeton (East-Central Illinois). | Pavement Improvement | 10/08/2009 |  | 07/30/2010 | 226889 | 0
1681 | Illinois | CHAMPAIGN |  | 15 | 5059013 | This project will extend the pavement life by resurfacing approximately 1.5 miles of Flessner Avenue and Pacesetter Drive in Rantoul, north of Champaign (East-Central Illinois) | Pavement Improvement | 12/16/2009 |  | 06/30/2010 | 390741 | 1.47
1682 | Illinois | CRAWFORD |  | 15 | 5060008 | This project will substantially improve the roadway by constructing a section of North Allen Street by providing new concrete pavement and other roadway improvements in Robinson (Southeast Illinois). | Pavement Improvement | 12/17/2009 |  | 08/30/2010 | 206350 | 0.08
1683 | Illinois | MARION |  | 19 | 5064014 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Salem, Illinois (Southwest Illinois). | Pavement Improvement | 09/14/2009 | 09/14/2009 | 09/30/2009 | 239230 | 0
1684 | Illinois | BUREAU |  | 18 | 5065006 | This project will extend the pavement life and improve pedestrian safety by resurfacing and reconstructing sidewalks for a section of St. Paul Street in the city of Spring Valley (East-Central Illinoi | Pavement Improvement | 07/24/2009 | 08/01/2009 | 10/30/2009 | 163278 | 0.38
1685 | Illinois | LA SALLE |  | 11 | 5066014 | This project will extend the pavement life by resurfacing a section of Oakley Avenue in the city of Streator (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 10/05/2009 | 12/30/2009 | 437897 | 1.52
1686 | Illinois | ROCK ISLAND |  | 17 | 5074082 | This project will extend the pavement life by resurfacing a section of First Street in the city of Coal Valley (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/28/2009 | 10/30/2009 | 174439 | 2.2
1687 | Illinois | UNION |  | 12 | 5080004 | This project will extend the pavement life by milling, patching and resurfacing 0.7 miles ofHeacock Street in the village of Jonesboro, Illinois (Southern Illinios). | Pavement Improvement | 10/22/2009 | 11/02/2009 | 12/30/2010 | 211402 | 0.73
1688 | Illinois | SANGAMON |  | 19 | 5082008 | LAND ACQUISITION FOR THE RECONSTRUCTION OF GORDON DRIVE FROM RAMBLEWOOD TO MAU DRIVE IN CHATHAM, SECTION 06-00028-00-WR | Other | 09/29/2009 |  | 11/30/2009 | 58000 | 0.53
1689 | Illinois | KANKAKEE |  | 15 | 5092004 | This project wil substantially improve the roadway by reconstructing a section of Burns Road West in the city of Bourbonnais. | New Construction | 08/04/2009 | 09/14/2009 | 07/30/2010 | 2111598 | 2.02
1690 | Illinois | PEORIA | PEORIA | 18 | 5093139 | This project consists of providing engineering design for a future highway improvement on Northmoor Road in the city of Peoria (West-Central Illinois). | Other | 07/16/2009 | 07/16/2009 | 09/30/2009 | 173272 | 0
1691 | Illinois | TAZEWELL | PEORIA | 18 | 5093140 | This project will extend the pavement life by removing existing pavement and resurfacing 0.91 mile of Parkway Drive in Pekin, just south of Peoria (West-Central Illinois) | Pavement Improvement | 10/28/2009 |  | 12/30/2009 | 432276 | 2.3
1692 | Illinois | TAZEWELL | PEORIA | 18 | 5093141 | This project will extend the pavement life by providing for pavement removal and resurfacing on North Main Street in Morton, just east of Peoria (West-Central Illinois) | Pavement Improvement | 10/28/2009 |  | 07/30/2010 | 212838 | 0.62
1693 | Illinois | PEORIA | PEORIA | 18 | 5093142 | This project will extend the pavement life by provide for pavement removal and resurfacing of a 0.51 mile section of Heading Avenue in West Peoria (West-Central Illinois) | Pavement Improvement | 09/25/2009 | 09/29/2009 | 09/30/2009 | 60800 | 1.04
1694 | Illinois | PEORIA | PEORIA | 18 | 5093143 | This project will extend the pavement life by resurfacing a 0.5 mile section of Garfield Avenue in Bartonville, just south of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 |  | 06/30/2010 | 80564 | 0.49
1695 | Illinois | PEORIA | PEORIA | 18 | 5093144 | This project will extend the pavement life by providing for 0.39 mile of pavement removal and resurfacing on North Prospect Road in Peoria (West-Central Illinois) | Pavement Improvement | 09/25/2009 | 10/05/2009 | 10/30/2009 | 84714 | 0.94
1696 | Illinois | TAZEWELL | PEORIA | 18 | 5093145 | This project will extend the pavement life by providing for 0.38 mile of pavement removal and resurfacing on Fischer Avenue just south of Peoria (West-Central Illinois) | Pavement Improvement | 09/14/2009 | 09/23/2009 | 09/30/2009 | 69558 | 0.8
1697 | Illinois | TAZEWELL | PEORIA | 18 | 5093146 | This project will extend the pavement life by providing for 0.64 mile of pavement removal and resurfacing on Highview Road in East Peoria (West-Central Illinois) | Pavement Improvement | 08/04/2009 | 09/01/2009 | 09/30/2009 | 294083 | 1.16
1698 | Illinois | TAZEWELL | PEORIA | 18 | 5093147 | This project will extend the pavement life by providing for 3 blocks of pavement repairs and resurfacing in South Pekin, just south of Peoria (West-Central Illinois) | Pavement Improvement | 10/28/2009 |  | 12/30/2009 | 106397 | 2.98
1699 | Illinois | TAZEWELL | PEORIA | 18 | 5093148 | This project will extend the pavement life by resurfacing 1 mile of Hillcrest Drive and Wilmor Road in the City of Washington, east of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 |  | 05/30/2010 | 168113 | 1.13
1700 | Illinois | DE KALB |  | 16 | 5094001 | This project will extend the pavement life by resurfacing numerous streets in the city of Genoa (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 09/28/2009 | 11/30/2009 | 162552 | 1.78
1701 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099087 | This project will extend the pavement life by resurfacing a section of West Riverside Boulevard in the city of Rockford (Northwest Illinois). | Pavement Improvement | 12/15/2009 |  | 08/30/2010 | 439000 | 0.44
1702 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099088 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Rockford (Northwest Illinois). | Pavement Improvement | 10/29/2009 |  | 06/30/2010 | 926000 | 2.13
1703 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099090 | This project will extend the pavement life by resurfacing a section of Mill Road in the city of Cherry Valley (Northwest Illinois). | Pavement Improvement | 12/15/2009 |  | 05/30/2010 | 48250 | 0.18
1704 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099092 | This project will extend the pavement life by resurfacing a section of Westfield Road in the city of Winnebago (Northwest Illinois). | Pavement Improvement | 09/15/2009 | 09/21/2009 | 10/30/2009 | 66750 | 1
1705 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099094 | This project will extend the pavement life by resurfacing a section of McDonald Road in the city of Roscoe (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/14/2009 | 09/30/2009 | 131194 | 1
1706 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099095 | This project will extend the pavement life by resurfacing sections of Windsor Road and Riverside Boulevard in the city of Loves Park (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/21/2009 | 10/30/2009 | 530000 | 1.02
1707 | Illinois | MACON |  | 17 | 5169042 | This project will extend the bridge life by repairing various bridge piers and making other bridge improvements on Garfield Bridge in the City of Decatur (Southeast Illinois). | Bridge Improvement | 08/03/2009 | 08/10/2009 | 11/30/2009 | 720000 | 0.02
1708 | Illinois | MACON |  | 17 | 5169043 | This project will substantially improve the roadway by constructing a new section of Fletcher Park Boulevard by providing new concrete pavement in Mt.Zion (Southeast Illinois). | New Construction | 12/14/2009 |  | 10/30/2010 | 1229600 | 0.57
1709 | Illinois | CHAMPAIGN |  | 15 | 5181040 | This project will substantially improve the roadway by widening 1.5 miles of Windsor Road in Urbana to 4 lanes and providing for other roadway and safety improvements (East-Central Illinois) | Pavement Widening | 06/05/2009 | 07/13/2009 | 06/30/2011 | 2150000 | 2.71
1710 | Illinois | CHAMPAIGN |  | 15 | 5181044 | This project will substantially improve the north leg of the 1st Street and Windsor Street intersection with concrete widening and other roadway improvements in Champaign (East-Central Illinois) | Pavement Improvement | 08/04/2009 | 08/20/2009 | 11/30/2009 | 750000 | 1.52
1711 | Illinois | CHAMPAIGN |  | 15 | 5181045 | This project consists of providing engineering design for a future highway improvement on Prospect Avenue in the city of Savoy (East-Central Illinois). | Other | 08/26/2009 | 08/26/2009 | 08/30/2010 | 305000 | 0
1712 | Illinois | CHAMPAIGN |  | 15 | 5181046 | This project will extend the pavement life by resurfacing 1.25 miles of Kirby Avenue in Champaign (East-Central Illinois) | Pavement Improvement | 12/10/2009 |  | 08/30/2010 | 939794 | 1.07
1713 | Illinois | MCLEAN |  | 11 | 5227046 | This project will substantially improve the roadway by reconstructing, widening, and adding other roadway improvements to 0.5 mile of Hamilton Road in Bloomington. | Pavement Improvement | 12/15/2009 |  | 06/30/2011 | 834472 | 0.1
1714 | Illinois | MCLEAN |  | 15 | 5227050 | This project will provide safety enhancements by installing traffic signals at the intersection of Hershey Road and College Avenue in Bloomington (East-Central Illinois) | Safety/Traffic Management | 12/10/2009 |  | 04/30/2010 | 200000 | 0.01
1715 | Illinois | MCLEAN |  | 15 | 5227051 | This project will extend the pavement life by resurfacing 1 mile of Ireland Grove Road in Bloomington (East-Central Illinois) | Pavement Improvement | 12/03/2009 |  | 10/30/2010 | 420000 | 0.93
1716 | Illinois | MCLEAN |  | 11 | 5227053 | This project will substantially improve 1 block of Virginia Avenue by reconstructing the roadway with concrete pavement, adding other roadway improvements, and replacing the structure over Sugar Creek | Bridge Replacement | 12/14/2009 |  | 10/30/2010 | 1414977 | 0.01
1717 | Illinois | WINNEBAGO |  | 16 | 5291011 | This project will extend the pavement life by resurfacing a section of East Union Street in the city of Rockton (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/10/2009 | 10/30/2009 | 497697 | 1.77
1718 | Illinois | HENRY | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5789005 | This project will extend the pavement life by resurfacing a section of US 6 near the city of Colona (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/07/2009 | 08/30/2009 | 318797 | 1.06
1719 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,3,4,7 | 6000284 | This project will extend the pavement life by resurfacing numerous roadway sections in the Far South area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 07/09/2009 | 08/03/2009 | 12/30/2009 | 5819055 | 5
1720 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,3,4,7 | 6000285 | This project will extend the pavement life by resurfacing numerous roadway sections in the South area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 07/08/2009 | 08/03/2009 | 12/30/2009 | 11528315 | 11
1721 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,3,4,7 | 6000286 | This project will extend the pavement life by resurfacing numerous roadway sections in the Central area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 07/08/2009 | 07/07/2009 | 12/30/2009 | 7026785 | 6
1722 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,3,4,7 | 6000287 | This project will extend the pavement life by resurfacing numerous roadway sections in the North area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 07/01/2009 | 07/07/2009 | 12/30/2009 | 10101000 | 9
1723 | Illinois | LA SALLE |  | 11 | 6120001 | This project will extend the pavement life by resurfacing a section of IL 178 near the city of Utica (East-Central Illinois). | Pavement Improvement | 04/23/2009 | 05/21/2009 | 08/30/2009 | 301406 | 0.78
1724 | Illinois | KANKAKEE |  | 11 | 6176002 | This project will substantially improve the roadway by reconstructing a section of Armour Road in the city of Bourbonnais (East-Central Illinois). | Pavement Improvement | 06/01/2009 | 07/01/2009 | 07/30/2010 | 3799108 | 1.25
1725 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 8003322 | This project will substantially improve the roadway by reconstructing Cemetary Rd between Washington St and Tri-State Parkway in the Village of Gurnee (Northeastern Illinois) | Pavement Improvement | 09/15/2009 | 11/01/2009 | 06/30/2010 | 7218540 | 2.94
1726 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 8003593 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to Madison Street in Villa Park (Northeast Illinois). | Safety/Traffic Management | 10/19/2009 |  | 06/30/2010 | 260479 | 0.9
1727 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 8003870 | This project will substantially improve the roadway by reconstructing a section of Wilmot Rd between Gordon Terrace and Deerfield Rd in the Village of Deerfield (Northeastern Illinois) by widening the | Pavement Improvement | 06/12/2009 | 08/01/2009 | 11/30/2009 | 1445773 | 2
1728 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 8003888 | This project will provide for pedestrian/bicycle safety by constructing a new shared use path adjacent to Washington Street in Naperville (Northeast Illinois). | Transportation Enhancements | 08/18/2009 | 08/31/2009 | 05/30/2010 | 1623500 | 0
1729 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003067 | This project will extend the life of the pavement by resurfacing Lawndale Ave from 47th St to Ogden Ave in Lyons in Cook County. | Pavement Improvement | 12/07/2009 |  | 06/30/2010 | 600000 | 0.73
1730 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003176 | This project will extend the pavement life by resurfacing 0.99 miles of East Ave from Cermak Rd to Roosevelt Rd in Berwyn. (Northeastern Illinois). | Pavement Improvement | 12/10/2009 |  | 04/30/2010 | 720000 | 0.97
1731 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003193 | This project will extend the pavement life by resurfacing, pavement markings, removing and replacing curb, gutter and sidewalks to assist persons with disabilities. This project is located on Deaan St | Pavement Improvement | 08/07/2009 | 09/21/2009 | 09/30/2009 | 313727 | 1.34
1732 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003199 | This project will extend the pavement life by milling, patching and resurfacing Wilson St from Randall Rd to Raddant Rd in the city of Batavia (Northeastern Illinois) | Pavement Improvement | 07/15/2009 | 07/15/2009 | 08/30/2009 | 1100130 | 5.14
1733 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003218 | This project will extend the pavement life by resurfacing 0.51 miles of 63rd Street from LaGrange Rd to East Ave in Hodgkins in Cook County. (Northeastern Illinois). | Pavement Improvement | 01/08/2010 |  | 05/30/2010 | 400000 | 0.52
1734 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003224 | This project will extend the pavement life by milling, patching, resurfacing and striping McDonald Rd from Burlington Rd to Kendall Rd in the village of Campton Hills (Northeastern Illinois) | Pavement Improvement | 07/01/2009 | 08/24/2009 | 08/30/2009 | 391000 | 2.97
1735 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003225 | This project will extend the pavement life by milling, patching, resurfacing and striping on Summit St from Dundee Ave to Hiawatha Drive in the city of Elgin (Northeastern Illinois) | Pavement Improvement | 08/26/2009 | 09/21/2009 | 12/30/2009 | 933840 | 1.2
1736 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003252 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Farnsworth Ave from Reckinger Rd to Molitor Rd in the City of Aurora (Northeastern Illinois) | Pavement Improvement | 07/09/2009 | 08/24/2009 | 10/30/2009 | 637000 | 1.22
1737 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003292 | This project will extend the pavement life by resurfacing Blackhawk Trail from Plainfield Rd. to Wolf Rd. in the village of Indian Head Park, Cook County (Northeastern Illinois). | Pavement Improvement | 09/22/2009 | 10/07/2009 | 11/30/2009 | 350000 | 1.72
1738 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003299 | This project will extend the pavement life by resurfacing, installing relief sewer, patching, curb & gutter, sidewalks, water main replacement on Sheridan Rd. from South Blvd to Main St. in the city o | Pavement Improvement | 08/27/2009 | 09/10/2009 | 06/30/2010 | 1320000 | 1.22
1739 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003301 | This project will extend the pavement life by resurfacing and side walk repairs to accommodate people with disabilties on Washington St from Williams St to Main St in in the Village of Carpentersville | Pavement Improvement | 09/08/2009 |  | 10/30/2009 | 160000 | 0.84
1740 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003302 | This project will extend the pavement life by resurfacing 1.11 miles of Prairie Ave from 47th St to Burlington Ave, curb & gutter replacement, patching & sanitary sewer replacement all located in the | Pavement Improvement | 12/10/2009 |  | 06/30/2010 | 930000 | 1.12
1741 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003303 | This project will extend the pavement life by resurfacing 0.53 miles of Brainard Ave. from Harding Ave. to 31st St. in LaGrange Park, Cook County (Northeastern Illinois). | Pavement Improvement | 08/07/2009 | 09/01/2009 | 10/30/2009 | 366000 | 1
1742 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003304 | This project will extemd the pavement life by resurfacing 0.68 miles of Irving Park Rd. from Madison Dr. to Bartlett Rd. in the village of Streamwood, Cook County (Northeastern Illinois). | Pavement Improvement | 09/09/2009 | 09/28/2009 | 11/30/2009 | 465000 | 1.68
1743 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003305 | This project will extend the pavement life by resurfacing 0.7 miles of 10th St./Wilmette Ave. from Sheridan Road to Lake Avenue in Wilmette, Cook County (Northeastern Illinois). | Pavement Improvement | 12/10/2009 |  | 06/30/2010 | 360000 | 0.7
1744 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003306 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Sundown Rd from McLean Bvld to IL 31 in the Village of South Elgin (Northeastern Illinois) | Pavement Improvement | 10/16/2009 |  | 06/30/2010 | 976000 | 0.99
1745 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 17 | 9003307 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements and repairs to the structure carrying Old Willow Road over the Middle Fork of the north bran | Bridge Improvement | 12/22/2009 |  | 06/30/2010 | 100000 | 0.01
1746 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003309 | This project will extend the pavement life by resurfacing 1.47 miles of Overlook Drive from Waukegan Road to Golf Road, in the Village of Golf in Cook County (Northeastern Illinois). | Pavement Improvement | 09/10/2009 | 11/07/2009 | 12/30/2009 | 252000 | 1.72
1747 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003311 | This project will extend the pavement life by resurfacing on Bull Valley Rd from Shelby Court to Valley Hill Rd in the Village of Bull Valley (Northeastern Illinois) | Pavement Improvement | 10/16/2009 |  | 12/30/2009 | 262105 | 5.06
1748 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003315 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on Algonquin Rd between Plum Tree Rd and US 14 in the Village of F | Pavement Improvement | 10/16/2009 |  | 06/30/2010 | 262105 | 0.85
1749 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003316 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement of 1.22 miles onKaneville Rd from Randall Rd to IL Rt 38 in the Village of Geneva(Northeastern Il | Pavement Improvement | 12/14/2009 |  | 06/30/2010 | 1064509 | 2.5
1750 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003317 | This project will extend the pavement life by resurfacing on Wondermere Rd from Greenwood Rd to Thompson Rd in the Village of Greenwood (Northeastern Illinois) | Pavement Improvement | 09/15/2009 | 09/22/2009 | 10/30/2009 | 262105 | 3.33
1751 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003318 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on State St from IL Rt 72 to north of Keyes Ave in Hampshire (Nort | Pavement Improvement | 12/16/2009 |  | 06/30/2010 | 659972 | 1.6
1752 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003319 | This project will extend the pavement life by resurfacing 0.44 miles of 9th Ave from Roosevelt Rd to Bataan Drive in the Village of Maywood in Cook County (Northeastern Illinois). | Pavement Improvement | 10/08/2009 |  | 05/30/2010 | 561900 | 1.32
1753 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003320 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings and detector loop replacement on Douglas Rd between Montgomery Rd a | Pavement Improvement | 12/16/2009 |  | 06/30/2010 | 800773 | 1.34
1754 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003321 | This project will extend the pavement life by resurfacing Lehigh Ave from Oakton Street to Lincoln Avenue in the Village of Morton Grove in Cook County (Northeastern Illinois). | Pavement Improvement | 10/29/2009 |  | 05/30/2010 | 328000 | 0.78
1755 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003322 | This project will extend the pavement life by resurfacing Montrose Ave from east of Cumberland Ave to Canfield Ave in the Village of Norridge in Cook County (Northeastern Illinois). | Pavement Improvement | 09/21/2009 | 11/01/2009 | 12/30/2009 | 368200 | 0.49
1756 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003323 | This project will extend the pavement life by resurfacing on Prairie St from west of US Rt 30/IL Rt 47 to Gordon Rd in the Village of Sugar Grove (Northeastern Illinois) | Pavement Improvement | 12/07/2009 | 12/07/2009 | 06/30/2010 | 536036 | 3.84
1757 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003324 | This project will extend the pavement life by resurfacing 0.51 miles of Westchester Blvd from Canterbury St to Roosevelt Rd in the Village of Westchester in Cook County (Northeastern Illinois). | Pavement Improvement | 10/08/2009 | 11/01/2009 | 05/30/2010 | 532235 | 1.53
1758 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003326 | This project will extend the pavement life by resurfacing 1.2 miles of Central Rd from Huber Lane to Harlem Avenue in Glenview in Cook County (Northeastern Illinois). | Pavement Improvement | 09/08/2009 | 10/05/2009 | 12/30/2009 | 720000 | 2.88
1759 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003327 | This project will extend the pavement life by resurfacing Division St. from 25th Ave to 14th Ave in Melrose Park in Cook County (Northeastern Illinois). | Pavement Improvement | 12/07/2009 |  | 06/30/2010 | 548540 | 1.01
1760 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003329 | This project will extend the life of the pavement by resurfacing 0.90 miles of Dundee Ave from Lake Cook Rd. to IL Route 59 in Barrington, Cook County (Northeastern Illinois). | Pavement Improvement | 10/29/2009 |  | 05/30/2010 | 330000 | 0.9
1761 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003345 | This project will extend the life of the pavement by resurfacing N. Oak Ave from W Bartlett Ave to US 20 & resurfacing W. Bartlett Ave from IL 59 to Western Ave, Cook County (Northeastern Illinois). | Pavement Improvement | 12/14/2009 |  | 07/30/2010 | 1435000 | 0.95
1762 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003349 | This project will extend the life of the pavement by resurfacing Thatcher Ave. from Central Ave. to Chicago Ave. in the village of River Forest, Cook County (Northeastern Illinois). | Pavement Improvement | 08/07/2009 | 09/01/2009 | 10/30/2009 | 428200 | 0.98
1763 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003352 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on Ringwood Rd between Spring Grove Rd and Johnsburg Rd in the vill | Pavement Improvement | 10/26/2009 |  | 06/30/2010 | 262105 | 2.44
1764 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003353 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 0.90 miles on Ridge Rd between Deerwood Trail and IL Rt 120 in t | Pavement Improvement | 10/27/2009 | 10/27/2009 | 06/30/2010 | 262105 | 2.88
1765 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003354 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 1.27 miles on Valley View Rd between Crystal Lake Rd and IL Rt 1 | Pavement Improvement | 09/09/2009 | 09/28/2009 | 10/30/2009 | 262105 | 3.9
1766 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003355 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 1.40 miles on Ringwood Rd between McCullom Lake Rd and Devonshir | Pavement Improvement | 10/27/2009 | 10/27/2009 | 06/30/2010 | 262105 | 6.28
1767 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003356 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of on East Wonder Lake Rd between McCullom Lake Rd and Burnard Mill | Pavement Improvement | 12/10/2009 |  | 05/30/2010 | 262105 | 1.61
1768 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003357 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Huntington Dr North from Stonegate Rd to Hanson Rd in the Village of Algonquin (Northeastern I | Pavement Improvement | 09/08/2009 | 09/21/2009 | 10/30/2009 | 262105 | 2.07
1769 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003358 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement including handicap ramps on 1.0 mile on Kreutzer Rd from Smith Rd to Northwestern Railroad tracks | Pavement Improvement | 09/14/2009 | 09/24/2009 | 10/30/2009 | 262105 | 0.88
1770 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003359 | This project will extend the life of the pavement by resurfacing Fullerton Ave. from Webster St. to 76th Ave. in Elmwood Park, Cook County (Northeastern Illinois). | Pavement Improvement | 08/07/2009 | 09/01/2009 | 10/30/2009 | 303000 | 1
1771 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003361 | This project will extend the pavement life by resurfacing 0.81 miles on 135th Street in Romeoville (Northeast Illinois). | Pavement Improvement | 12/08/2009 |  | 06/30/2010 | 415000 | 2.02
1772 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003362 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to Rathje Road in Peotone (Northeast Illinois). | Safety/Traffic Management | 12/17/2009 |  | 05/30/2010 | 58000 | 0.23
1773 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003363 | This project will extend the pavement life by resurfacing on Sauk Trail in Frankfort (Northeast Illinois). | Pavement Improvement | 12/08/2009 |  | 06/30/2010 | 190000 | 1
1774 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003364 | This project will extend the pavement life by resurfacing 99th St. from Oak Park Avenue to Ridgeland Avenue in Chicago Ridge in Cook County (Northeastern Illinois). | Pavement Improvement | 08/19/2009 | 10/03/2009 | 12/30/2009 | 500000 | 0.28
1775 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003368 | This project will extend the life of the pavement by resurfacing Green Bay Rd. from Park Ave to Scott Ave in Glencoe in Cook County (Northeastern Illinois). | Pavement Improvement | 12/10/2009 |  | 06/30/2010 | 608000 | 1.28
1776 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003369 | This project will extend the pavement life by resurfacing on Barreville Rd from north village limits to Ames Rd in the Village of Prairie Grove (Northeastern Illinois) | Pavement Improvement | 12/28/2009 |  | 01/30/2010 | 262105 | 0.72
1777 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003370 | This project will improve safety by lighting 0.5 miles of US Route 30 in Mokena (Northeast Illinois) | Safety/Traffic Management | 11/19/2009 |  | 05/30/2010 | 260000 | 0.02
1778 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003371 | This project will extend the pavement life by resurfacing 0.5 miles on Gaylord Road in Crest Hill (Northeast Illinois). | Pavement Improvement | 09/08/2009 | 09/11/2009 | 10/30/2009 | 211000 | 1.53
1779 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003373 | This project will extend the pavement life by resurfacing on 151st Street in Homer Glen (Northeast Illinois). | Pavement Improvement | 09/08/2009 | 09/28/2009 | 10/30/2009 | 366000 | 2
1780 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003374 | This project will extend the life of the pavement by resurfacing 0.80 miles of Tower Road from Hibbard Road to Sheridan Road excluding Green Bay Road & Sheridan Road intersections, minor curb repair a | Pavement Improvement | 10/29/2009 |  | 05/30/2009 | 420000 | 0.49
1781 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003376 | This project will extend the life of the pavement by resurfacing 0.97 miles of Main St. from IL 50 to Crawford Avenue in Skokie in Cook County (Northeastern Illinois). | Pavement Improvement | 12/28/2009 |  | 06/30/2010 | 760000 | 1
1782 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003377 | This project will improve mobility and safety by installing traffic signals & interconnections at the intersection of 127th St & Timberline Drive in Lemont in Cook County (Northeastern Illinois). | Safety/Traffic Management | 12/08/2009 |  | 06/30/2010 | 300000 | 0.01
1783 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003378 | This project will provide for pedestrian safety by removal & replacement of existing sidewalk with ADA ramps, and new curb & gutter along Roberts Road from 97th st to 111th St. and along 111th St from | Safety/Traffic Management | 10/29/2009 |  | 06/30/2010 | 363000 | 5.15
1784 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003380 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to IL 59 in Naperville (Northeast Illinois). | Safety/Traffic Management | 01/04/2010 |  | 07/30/2010 | 900000 | 3.16
1785 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003382 | This project will extend the life of the pavement by resurfacing 0.28 miles of Franklin Ave from Ruby St to Rose St / 25th St in Franklin Park in Cook County (Northeastern Illinois). | Pavement Improvement | 09/21/2009 | 09/21/2009 | 05/30/2010 | 503000 | 0.54
1786 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003383 | This project will extend the pavement life by resurfacing on Drauden Road in Plainfield (Northeast Illinois). | Pavement Improvement | 12/08/2009 |  | 05/30/2010 | 210000 | 0.99
1787 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003389 | This project will extend the pavement life by resurfacing 1.10 miles on Thomas Dillon Drive in Channahon (Northeast Illinois). | Pavement Improvement | 10/23/2009 |  | 12/30/2009 | 189000 | 1.12
1788 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003396 | This project will extend the pavement life by resurfacing on Wallin Drive in Plainfield (Northeast Illinois). | Pavement Improvement | 12/08/2009 |  | 05/30/2010 | 280000 | 1.01
1789 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003419 | This project consists of improving safety and traffic enhancement by 0.78 miles of traffic signal modernization on US Rt 14 from Dole Ave to Devonshire Lane/Kieth Ave in Crystal Lake (Northeastern Ill | Safety/Traffic Management | 12/03/2009 |  | 07/30/2010 | 262105 | 0.77
1790 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003420 | This project will extend the pavement life with 3.0 miles of concrete pavement patching, asphalt overlay, shoulder rehabilitation, new pipe underdrains, sidewalk removal & replacement on E. Frontage R | Pavement Improvement | 09/21/2009 | 10/01/2009 | 07/30/2010 | 3780000 | 6.32
1791 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003424 | This project will extend the pavement life by resurfacing numerous roadway sections in DuPage County (Northeastern Illinois). | Pavement Improvement | 12/08/2009 |  | 07/30/2010 | 531535 | 1.1
1792 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003436 | This project will extend the pavement life by resurfacing 0.91 miles on Boughton Road in Bolingbrook (Northeast Illinois). | Pavement Improvement | 10/01/2009 | 10/12/2009 | 12/30/2009 | 660000 | 3.21
1793 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003440 | This project will extend the pavement life by resurfacing on Shick Road in Bloomingdale (Northeast Illinois). | Pavement Improvement | 10/29/2009 |  | 07/30/2010 | 1482917 | 0.93
1794 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003445 | This project will substantially extend the pavement life by resurfacing, landscaping and improve safety and traffic enhancement by upgrading pavement markings of on Raffel Rd from Il Rt 120 Banford R | Pavement Improvement | 12/10/2009 |  | 06/30/2010 | 262105 | 0.25
1795 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003449 | This project will extend the pavement life by milling, patching and resurfacing 0.48 miles on Garfield St from McKinley St to Old Orchard Rd in Harvard (Northeastern Illinois). | Pavement Improvement | 12/07/2009 | 12/07/2009 | 03/30/2010 | 262105 | 0.45
1796 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003466 | This project will extend the pavement life by resurfacing 3.65 miles on River Road near Wilmington (Northeast Illinois). | Pavement Improvement | 12/28/2009 |  | 07/30/2010 | 1260000 | 3.7
1797 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003515 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to County Line Road in Burr Ridge (Northeast Illinois). | Safety/Traffic Management | 01/08/2010 |  | 06/30/2010 | 84200 | 0.4
1798 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 9251010 | This project will extend the pavement life by milling, patching and resurfacing in Belleville, Illinois (Southwestwest Illinios). | Pavement Improvement | 05/11/2009 | 06/03/2009 | 08/30/2009 | 170311.96 | 0.7
1799 | Indiana | DUBOIS |  | 09 | 0003610 | This project will add turn lanes, widen the intersection, and install a new signal at SR 56 and Dubois County Rd 500W. | Safety/Traffic Management | 06/18/2009 |  | 06/30/2010 | 104062.22 | 0.123
1800 | Indiana | ELKHART |  | 03 | 0013180 | This project will improve drainage by replacing the structure on SR 15 over a branch of Preston Miles' ditch in Elkhart County. | Pavement Improvement | 06/18/2009 | 07/14/2009 | 10/23/2009 | 1115122.65 | 0.175
1801 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0014130 | This project will improve drainage by replacing the structure on US 41 over Jane Feddeler Ditch in Lake County. | Pavement Improvement | 05/13/2009 | 06/24/2009 | 08/31/2009 | 576957.31 | 0.175
1802 | Indiana | HENRY |  | 06 | 0101426 | This project will improve the surface and rebuild sections of the bridge on SR 109 over I-70 in Henry County. | Bridge Improvement | 07/15/2009 | 07/15/2009 | 10/29/2010 | 1773465.75 | 0.175
1803 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0101500 | This project will improve drainage by replacing the structure on US 6 over Kiefer Ditch in Elkhart County. | Pavement Improvement | 09/09/2009 |  | 10/01/2010 | 531512.95 | 0.175
1804 | Indiana | NOBLE |  | 03 | 0101530 | This project will add turn lanes and imrpove the intersection at US 33 and SR 109 in Noble County. | Pavement Widening | 06/22/2009 | 08/31/2009 | 11/20/2009 | 388892.85 | 0.095
1805 | Indiana | GIBSON |  | 08 | 0173058 | This project will plant wildflowers and native vegetation along US 41at US 41 and Gibson County Road 550. | Transportation Enhancements | 07/21/2009 | 08/24/2009 | 08/01/2010 | 94456.25 | 0.681
1806 | Indiana | WHITE |  | 04 | 0200067 | This project will improve drainage by replacing the structure over Swygman ditch on US 24 in White County. | Safety/Traffic Management | 11/17/2009 |  | 04/30/2010 | 58620.56 | 0.175
1807 | Indiana | WHITE |  | 04 | 0200071 | This project will improve drainage by replacing the structure on US 24 over Winters ditch in White County. | Safety/Traffic Management | 11/17/2009 |  | 04/30/2010 | 93622.54 | 0.175
1808 | Indiana | UNION |  | 06 | 0200195 | This project will repair and restore the pavement and replace signs on US 27 from the Ohio State line north 3.6 miles in Union county. | Safety/Traffic Management | 04/15/2009 | 08/05/2009 | 02/10/2012 | 29179.07 | 2.891
1809 | Indiana | FOUNTAIN |  | 08 | 0200364 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Safety/Traffic Management | 06/17/2009 | 07/16/2009 | 08/31/2010 | 37743.16 | 0.175
1810 | Indiana | SHELBY, JOHNSON |  | 05,04,06 | 0200539 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | Safety/Traffic Management | 05/12/2009 | 07/22/2009 | 07/11/2011 | 26276.41 | 6.222
1811 | Indiana | STATEWIDE |  | 05,04,07 | 0200606 | This project will extend the traffic management system of closed circuit TV used for traffic management in Indianapolis. | Safety/Traffic Management | 06/11/2009 |  | 11/15/2010 | 3592423.77 | 2.564
1812 | Indiana | ALLEN |  | 03 | 0200884 | This project will add lanes to SR 1 from I-69 in Allen County to Tonkel Road. | Pavement Widening | 06/01/2009 | 07/15/2009 | 08/13/2011 | 396605.83 | 0.089
1813 | Indiana | ADAMS |  | 06 | 0200890 | US 27 - Over Swartz Ditch, 2.98 miles N of SR 218 (500' S of CR 300S) | Pavement Improvement | 01/21/2010 |  | 10/30/2010 | 769264.51 | 0.175
1814 | Indiana | WELLS |  | 06 | 0200894 | This project will improve drainage by replacing the structure on SR 301 over Vera Cruz Sewer in Wells County. | Pavement Improvement | 08/20/2009 |  | 08/21/2010 | 240955.15 | 0.175
1815 | Indiana | WABASH |  | 05 | 0200919 | This project will improve drainage by replacing the structure on SR 13 over Sharp ditch in Wabash County. | Pavement Improvement | 04/17/2009 | 06/10/2009 | 08/28/2009 | 422863.65 | 0.175
1816 | Indiana | ALLEN |  | 03 | 0200932 | SR 101 - Bridge over Maumee River, 1.08 miles N of US 24 | Bridge Improvement | 12/11/2009 |  | 08/21/2010 | 846966.05 | 0.175
1817 | Indiana | DE KALB |  | 03 | 0200934 | I-69 - CR 11A over I-69, 2.8 miles S of SR 8 | Bridge Improvement | 11/18/2009 |  | 11/30/2010 | 3484281.13 | 0.175
1818 | Indiana | BENTON |  | 01 | 0201203 | This project will improve the surface and rebuild sections of the bridge on US 41 over KB&S Railroad and US 52 in Benton County. | Bridge Replacement | 04/29/2009 | 05/11/2009 | 11/25/2009 | 1738096.18 | 0.175
1819 | Indiana | BENTON |  | 01 | 0201204 | This project will improve the surface and rebuild sections of the bridge on US 41 over KB&S Railroad and US 52 in Benton County. | Bridge Replacement | 04/29/2009 | 05/11/2009 | 11/25/2009 | 1153115.9 | 0.175
1820 | Indiana | CLINTON |  | 04 | 0201213 | This project will improve the surface and rebuild sections of the bridge on SR 75 over Kilmore Creek in Clinton County. | Bridge Improvement | 05/27/2009 | 06/15/2009 | 10/07/2009 | 438235.02 | 0.175
1821 | Indiana | OHIO |  | 09 | 0201245 | This project will improve the surface and rebuild sections of the bridge on SR 56 over Laughery Creek in Ohio County. | Bridge Improvement | 05/16/2009 | 07/31/2009 | 08/01/2011 | 5184952.26 | 0.175
1822 | Indiana | DUBOIS |  | 09 | 0242029 | This project will add turn lanes, widen the intersection, and install a new signal at SR 56 and Dubois County Rd 500W. | Pavement Widening | 06/18/2009 |  | 06/30/2010 | 639905.85 | 0.123
1823 | Indiana | DE KALB, ALLEN | FORT WAYNE | 03 | 0300084 | This project will improve sections and extend the life of I-69 from 0.86 miles North of SR 1 to 9.87 miles North of SR 1 with a pavement surface overlay. | Pavement Improvement | 08/18/2009 | 08/24/2009 | 11/12/2009 | 2476953.36 | 3.344
1824 | Indiana | DE KALB |  | 03 | 0300092 | This project will improve safety and extend the life of the bridge(s) on County Road 68 over I-69 in DeKalb County. | Bridge Improvement | 04/02/2009 | 04/13/2009 | 09/04/2009 | 453609.98 | 0.11
1825 | Indiana | DE KALB |  | 03 | 0300093 | This project will improve safety and extend the life of the bridge(s) on County Road 60 over I-69 in DeKalb County. | Bridge Improvement | 04/02/2009 | 04/13/2009 | 09/04/2009 | 366395.3 | 0.175
1826 | Indiana | STEUBEN |  | 03 | 0300942 | This project will rebuild the US 20 and I-69 interchange in Steuben county to improve traffic flow. | Pavement Widening | 06/01/2009 | 06/12/2009 | 10/15/2010 | 3676824.73 | 0.49
1827 | Indiana | MARSHALL |  | 02 | 0301057 | This project will improve safety and extend the life of the bridge(s) on SR 10 over Clarence Baker Ditch in Marshall County. | Bridge Improvement | 04/17/2009 | 06/08/2009 | 11/22/2009 | 243247.58 | 0.175
1828 | Indiana | PARKE |  | 08 | 0322001 | This project will improve drainage by repairing pipes in Parke County 3 miles South of SR 234. | Pavement Improvement | 07/22/2009 | 09/11/2009 | 08/30/2010 | 679684.15 | 0.13
1829 | Indiana | JEFFERSON |  | 09 | 0400133 | This project will replace and restore the pavement on Michigan Road in Jefferson County near the Town of Madison. | Pavement Improvement | 07/15/2009 | 09/09/2009 | 06/07/2010 | 1233716 | 0.175
1830 | Indiana | MONROE | BLOOMINGTON | 09 | 0400322 | This project will improve the surface and rebuild sections of the bridge on SR 37 over the abandoned Railroad, 3.5 miles South of SR 45 in Monroe County. | Bridge Improvement | 05/13/2009 | 06/12/2009 | 06/26/2010 | 697938.5 | 0.175
1831 | Indiana | MONROE | BLOOMINGTON | 09 | 0400324 | This project will improve the surface and rebuild sections of the bridge on SR 37 over the abandoned Railroad, 3.5 miles South of SR 45 in Monroe County. | Bridge Improvement | 05/13/2009 | 06/12/2009 | 06/26/2010 | 671638.17 | 0.175
1832 | Indiana | OWEN |  | 08 | 0400568 | This project will correct a slide condition along SR 243 south of the Owen / Putnam County line. | Pavement Improvement | 07/22/2009 | 09/24/2009 | 09/30/2010 | 472233.66 | 0.081
1833 | Indiana | GRANT, HUNTINGTON |  | 05 | 0400614 | This project will improve sections and extend the life of I-69 from 1.84 mi S of Huntington Co Ln to 1.55 mi South of SR 124 with a pavement surface overlay. | Pavement Improvement | 07/07/2009 | 08/12/2009 | 10/24/2009 | 2117715.38 | 5.471
1834 | Indiana | TIPPECANOE |  | 04 | 0400997 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 1288872.55 | 0.175
1835 | Indiana | TIPPECANOE |  | 04 | 0400999 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 624811.28 | 0.109
1836 | Indiana | TIPPECANOE |  | 04 | 0401000 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 1193676.61 | 0.109
1837 | Indiana | TIPPECANOE, BENTON |  | 01,04 | 0401007 | This project will improve sections and extend the life of SR 52 with a pavement surface overlay. | Pavement Improvement | 03/24/2009 | 04/15/2009 | 11/24/2009 | 3823682.05 | 4.592
1838 | Indiana | JACKSON |  | 09 | 0401139 | This project will improve the surface and rebuild sections of the bridge on SR 258 over White River in Jackson County. | Bridge Improvement | 06/05/2009 | 06/08/2009 | 10/16/2009 | 996973.79 | 0.175
1839 | Indiana | DE KALB, ALLEN | FORT WAYNE | 03 | 0401216 | This project will improve drainage by repairing pipes on I-69 from 0.86 miles North of SR 1 to 9.87 miles North of SR 1 in Allen and Dekalb Counties. | Pavement Improvement | 08/18/2009 | 08/24/2009 | 11/12/2009 | 976353.5 | 3.344
1840 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0401287 | This project will beautify the roadside by planting native grasses and wildflowers along US 52 near the SR 443 bridge and Happy Hollow Road in West Lafayette. | Transportation Enhancements | 06/09/2009 | 07/01/2009 | 09/30/2011 | 44866 | 0.175
1841 | Indiana | LAWRENCE |  | 04 | 0426013 | This project will improve sections and extend the life of US 50 from SR 37 to "E" St. in Bedford with a pavement surface overlay. | Pavement Improvement | 03/23/2009 | 04/20/2009 | 08/29/2009 | 1139545.5 | 1.787
1842 | Indiana | KNOX |  | 08 | 0431065 | This project will plant wildflowers and native vegetation along SR 67 south of Bruceville in Knox County. | Transportation Enhancements | 07/21/2009 | 08/24/2009 | 08/01/2010 | 37869.1 | 0.286
1843 | Indiana | ALLEN |  | 03 | 0452010 | This project will add lanes to SR 1 from I-69 in Allen County to Tonkel Road. | Pavement Widening | 06/01/2009 | 07/15/2009 | 08/13/2011 | 11814314.43 | 1.873
1844 | Indiana | STARKE |  | 02 | 0500283 | This project will improve sections and extend the life of SR 39 in Starke County with a pavement surface overlay. | Pavement Improvement | 08/18/2009 |  | 11/15/2009 | 1341695.75 | 7.115
1845 | Indiana | TIPPECANOE |  | 04 | 0500597 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 24555851.35 | 0.109
1846 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0500819 | This project will improve the bike and pedestrian facilities on Tracy Trail at Summerfield Park. | Transportation Enhancements | 12/16/2009 |  | 10/29/2010 | 854400 | 0.175
1847 | Indiana | VANDERBURGH | EVANSVILLE (KY) | 08 | 0500938 | This project will plant wildflowers and native vegetation along I-164 at I-164 and SR 62 in Vanderburgh County. | Transportation Enhancements | 07/21/2009 | 08/21/2009 | 08/01/2010 | 59674.25 | 0.176
1848 | Indiana | CLAY |  | 08 | 0600085 | This project will improve sections and extend the life of SR 246 from SR 159 to SR 157 in Clay County with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 05/11/2009 | 06/30/2009 | 833355.51 | 3.736
1849 | Indiana | DELAWARE | MUNCIE | 06 | 0600233 | This project will improve sections and extend the life of Sr 3 with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 06/02/2009 | 08/07/2009 | 1318336.68 | 5.31
1850 | Indiana | HOWARD | KOKOMO | 05 | 0600338 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Construction | 06/01/2009 | 07/10/2009 | 06/15/2011 | 8764930.32 | 0.175
1851 | Indiana | HOWARD | KOKOMO | 05 | 0600566 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Bridge Construction | 06/01/2009 | 07/10/2009 | 06/15/2011 | 1734801.49 | 0.175
1852 | Indiana | MONROE | BLOOMINGTON | 04,09 | 0600605 | This project will improve sections and extend the life of SR 48 from Curry Pike to E of SR 37 in Bloomington with a pavement surface overlay. | Pavement Improvement | 04/15/2009 | 05/08/2009 | 08/19/2009 | 534251.7 | 0.597
1853 | Indiana | MARION | INDIANAPOLIS | 04 | 0600651 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | New Construction | 05/26/2009 | 06/23/2009 | 11/15/2010 | 9069603.35 | 0.114
1854 | Indiana | MARION | INDIANAPOLIS | 04 | 0600653 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | Bridge Replacement | 05/26/2009 | 06/23/2009 | 11/15/2010 | 2431747.71 | 0.07
1855 | Indiana | MARION | INDIANAPOLIS | 04 | 0600654 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | Bridge Replacement | 05/26/2009 | 06/23/2009 | 11/15/2010 | 2457379.37 | 0.094
1856 | Indiana | MONTGOMERY |  | 04 | 0600803 | This project will improve drainage by replacing the structure on US 231, 3 miles South of the South junction with SR 32 in Montgomery County. | Pavement Improvement | 03/24/2009 | 05/18/2009 | 06/13/2009 | 54455 | 0.199
1857 | Indiana | SHELBY, JOHNSON |  | 05,06,04 | 0684011 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | Pavement Widening | 05/12/2009 | 07/22/2009 | 07/11/2011 | 13306723.99 | 6.222
1858 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710031 | This project will improve sections and extend the life of US 20 in East Chicago with a pavement surface overlay. | Pavement Improvement | 06/17/2009 | 07/21/2009 | 09/30/2009 | 1659673.58 | 1.272
1859 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710034 | This project will improve the pavement on SR 149 from the junstion of SR 130 to the junction of US 20. | Pavement Improvement | 04/08/2009 | 05/04/2009 | 11/13/2009 | 1362731.25 | 4.065
1860 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0710040 | This project will improve sections and extend the life of SR-23 from SR 4 to Olive Street in St Joseph County with a pavement surface overlay. | Pavement Improvement | 06/05/2009 | 08/14/2009 | 11/01/2009 | 1593244.25 | 6.955
1861 | Indiana | PULASKI |  | 02 | 0710042 | This project will improve sections and extend the life of US 35 from SR 14 to SR 10 in Pulaski County with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 05/18/2009 | 10/16/2009 | 1407322.75 | 7.964
1862 | Indiana | CASS |  | 02 | 0710043 | This project will improve sections and extend the life of US 24 from the north junction with US 35 to the south junction with US 35 and on SR 29 from US 24 to Burlington Ave. near Logansport in Cass C | Pavement Improvement | 03/23/2009 | 05/11/2009 | 07/31/2009 | 1651219.54 | 1.62
1863 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710053 | This project will improve sections and extend the life of US 30 in Lake County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/02/2009 | 11/15/2009 | 3324753.79 | 3.736
1864 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710054 | This project will improve sections and extend the life of US 41 from US 231 to 77th Ave with a pavement surface overlay. | Pavement Improvement | 08/27/2009 | 09/04/2009 | 10/31/2009 | 1812338.2 | 3.76
1865 | Indiana | LAKE |  | 01 | 0710058 | This project will improve sections and extend the life of SR 53 from 93rd Ave to South of 73rd Ave with a pavement surface overlay. | Pavement Improvement | 05/13/2009 | 08/03/2009 | 10/16/2009 | 1148579.81 | 2.409
1866 | Indiana | LAWRENCE |  | 04 | 0710074 | This project will stop erosion and correct a slide occurring on the west side of US 50 south of the East Fork White River Bridge in lawrence County. | Safety/Traffic Management | 06/04/2009 | 07/23/2009 | 08/14/2009 | 162684 | 0.175
1867 | Indiana | ALLEN |  | 03 | 0710107 | This project will improve safety and extend the life of the bridge(s) on Hursh Road over I-69 in Allen County. | Bridge Improvement | 04/02/2009 | 04/13/2009 | 09/04/2009 | 326970.52 | 0.175
1868 | Indiana | JASPER |  | 01 | 0710115 | I 65 - From 2.12 miles N of US 231 to 3.29 miles S of SR 14 | Pavement Improvement | 09/15/2009 | 10/22/2009 | 08/20/2010 | 3009802.03 | 9.137
1869 | Indiana | HUNTINGTON |  | 05 | 0710141 | This project will improve safety and extend the life of the bridge(s) on I-69 over Wabash River in Huntington County. | Bridge Improvement | 05/13/2009 | 07/07/2009 | 10/31/2009 | 1452773.4 | 0.175
1870 | Indiana | DE KALB |  | 03 | 0710144 | This project will install new cable barrier along I-69 in Dekalb County. | Safety/Traffic Management | 05/16/2009 | 08/05/2009 | 10/31/2009 | 378654.37 | 2.851
1871 | Indiana | VIGO, HENDRICKS, MORGAN |  | 08 | 0710147 | This project will install new cable barrier on I-70 in Vigo, Henfricks, and Morgan Counties. | Safety/Traffic Management | 06/10/2009 | 07/23/2009 | 10/29/2009 | 1157982.31 | 4.511
1872 | Indiana | HENDRICKS, MARION |  | 04,07 | 0710148 | This project will install new cable barrier along I-74 in Hendricks and Marion Counties. | Safety/Traffic Management | 04/29/2009 | 06/04/2009 | 07/31/2009 | 560763.13 | 3.467
1873 | Indiana | CLARK, SHELBY, JOHNSON, JACKSON |  | 05,06,04,09 | 0710150 | This project will install new guardrail along I-65 in Johnson and Shelby Counties. | Safety/Traffic Management | 06/15/2009 | 06/26/2009 | 10/31/2009 | 3843690.33 | 14.633
1874 | Indiana | FLOYD |  | 09 | 0710151 | This project will install new guardrail along I-64 in Floyd County. | Safety/Traffic Management | 06/15/2009 | 06/26/2009 | 10/31/2009 | 360552.55 | 1.923
1875 | Indiana | CLARK, FLOYD |  | 09 | 0710152 | This project will install new guardrail along I-265 in Clark and Floyd Counties. | Safety/Traffic Management | 06/15/2009 | 06/26/2009 | 10/31/2009 | 545978.63 | 5.672
1876 | Indiana | MARION | INDIANAPOLIS | 07 | 0710163 | This project will improve sections and extend the life of I-465 with a pavement surface overlay from 3.23 miles North of I-74 to 5.12 miles North of I-74. | Pavement Improvement | 06/16/2009 | 07/30/2009 | 11/15/2009 | 1500500 | 0.576
1877 | Indiana | SWITZERLAND |  | 09 | 0710169 | This project will improve sections and extend the life of SR 56 from Oday Road to Rio Vista Lane with a pavement surface overlay. | Pavement Improvement | 10/07/2009 |  | 08/13/2010 | 2230135.96 | 9.504
1878 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0710203 | Parkside School sidewalk project. This is a 2006 SRTS project. | Safety/Traffic Management | 11/30/2009 |  | 06/19/2010 | 167101.57 | 0.01
1879 | Indiana | GREENE |  | 08 | 0710285 | SR 157 - From 0.61 mile N of N jct with US 231 to the jct with SR 48 | Pavement Improvement | 10/14/2009 | 10/21/2009 | 11/15/2009 | 551438.9 | 2.387
1880 | Indiana | DAVIESS, KNOX |  | 08 | 0710390 | This project will improve sections and extend the life of SR 58 from SR 67 to SR 57 in Knox and Daviess Counties with a pavement surface overlay. | Pavement Improvement | 03/23/2009 | 07/08/2009 | 09/20/2009 | 886582.9 | 4.701
1881 | Indiana | MONTGOMERY |  | 04 | 0710394 | This project will improve sections and extend the life of US 231 from just north of US 136 in Crawfordsville to 1/2 mile north of I-74 in Montgomery County with a pavement surface overlay. | Pavement Improvement | 06/03/2009 | 06/23/2009 | 10/27/2009 | 3436551.55 | 3.129
1882 | Indiana | SCOTT, JACKSON |  | 09 | 0710432 | This project will improve sections and extend the life of US 31 from SR 56 to SR 250 in Jackson and Scott Counties with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 04/03/2009 | 11/16/2009 | 1632948.2 | 6.231
1883 | Indiana | STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01,02 | 0710470 | This project will install new signal loop detectors to improve traffic flow at 5 intersection along US 30 in Northwest Indiana | Safety/Traffic Management | 04/14/2009 |  | 11/14/2009 | 369390.8 | 0
1884 | Indiana | HANCOCK, MADISON |  | 05,06 | 0710492 | This project will improve sections and extend the life of SR 9 in Hancock and Madison Counties with a pavement surface overlay. | Pavement Improvement | 06/02/2009 |  | 08/28/2009 | 1556750 | 2.991
1885 | Indiana | JENNINGS |  | 09 | 0710502 | This project will improve sections and extend the life of SR 3 from South junction with SR 7 South of Vernon to US 50 with a pavement surface overlay. | Pavement Improvement | 05/13/2009 | 06/20/2009 | 08/31/2009 | 561483.58 | 1.351
1886 | Indiana | STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01,02 | 0710510 | This project will install new signal loop detectors to improve traffic flow at 5 intersection along US 30 in Northwest Indiana | Safety/Traffic Management | 04/29/2009 | 05/18/2009 | 08/31/2009 | 283823.5 | 0
1887 | Indiana | HANCOCK |  | 05 | 0710541 | This project will improve sections and extend the life of US 40 with a pavement surface overlay. | Pavement Improvement | 06/02/2009 | 06/27/2009 | 08/07/2009 | 820500 | 3.143
1888 | Indiana | MIAMI |  | 05 | 0710581 | This project will improve the surface and rebuild sections of the bridge on US 31 over the abandoned CSX Railroad, 1 miles South of US 50 in Ohio County. | Bridge Replacement | 04/17/2009 | 04/22/2009 | 06/26/2010 | 308238.35 | 0.175
1889 | Indiana | MIAMI |  | 05 | 0710582 | This project will improve the surface and rebuild sections of the bridge on US 31 over the abandoned CSX Railroad, 1 miles South of US 50 in Ohio County. | Bridge Replacement | 04/17/2009 | 04/22/2009 | 06/26/2010 | 729284.5 | 0.175
1890 | Indiana | CLINTON, BOONE |  | 04 | 0710622 | This project will improve sections and extend the life of I-65 with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 04/20/2009 | 10/31/2009 | 4275408.99 | 4.081
1891 | Indiana | LAWRENCE |  | 04 | 0710650 | This project will patch deteriorated pavement areas and seal cracks on SR 37 near Mitchell. | Pavement Improvement | 03/31/2009 | 05/05/2009 | 09/18/2009 | 398921.08 | 6.086
1892 | Indiana | JOHNSON | INDIANAPOLIS | 06,04 | 0710670 | This project will improve sections and extend the life of US 31 with a pavement surface overlay. | Pavement Improvement | 08/18/2009 |  | 08/13/2010 | 1726896.26 | 4.797
1893 | Indiana | WASHINGTON |  | 09 | 0710694 | This project will improve sections and extend the life of SR 56 in Washington County with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 04/02/2009 | 08/01/2009 | 1045317.3 | 6.148
1894 | Indiana | KNOX |  | 08 | 0710700 | US 50 - 6.08 miles W of SR 241 to 1.88 miles E of SR 241 | Pavement Improvement | 10/23/2009 |  | 08/28/2010 | 731062.9 | 4.692
1895 | Indiana | LAWRENCE |  | 04 | 0710823 | This project will improve sections and extend the life of SR 54 from SR 58 to SR 37 with a pavement surface overlay. | Pavement Improvement | 07/07/2009 |  | 11/01/2010 | 650211.09 | 3.64
1896 | Indiana | WARRICK |  | 08 | 0710824 | This project will improve sections and extend the life of SR 61 from 0.8 Mi. N of SR 62 to S of SR 68 in Warrick County with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 04/28/2009 | 12/18/2009 | 1654900 | 6.73
1897 | Indiana | STEUBEN |  | 03 | 0710833 | This project will improve sections and extend the life of SR 1 in Steuben County with a pavement surface overlay. | Pavement Improvement | 06/05/2009 | 08/19/2009 | 10/31/2009 | 1451671.15 | 5.026
1898 | Indiana | PIKE |  | 08 | 0710835 | This project will improve sections and extend the life of SR 56 from South junction with SR 61 to SR 257 with a pavement surface overlay. | Pavement Improvement | 06/16/2009 | 09/08/2009 | 06/30/2010 | 1297838.15 | 4.125
1899 | Indiana | HARRISON | LOUISVILLE (KY)-IN | 09 | 0710884 | This project will extend the bridge life by repainting bridge beams at I-64 over Blue River and Blue Road in Harrison County. | Bridge Improvement | 06/19/2009 |  | 06/28/2010 | 446999.59 | 0.175
1900 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0710886 | This project will improve sections and extend the life of SR 19 near the I-80/I-90 Toll Road with a pavement surface overlay. | Pavement Improvement | 06/05/2009 | 07/16/2009 | 10/02/2009 | 1834644.06 | 2.802
1901 | Indiana | MONTGOMERY |  | 04 | 0710917 | This project will upgrade and improve the traffic signals at US 231 and the SR 32/ SR 47 junction in Montgomery County. | Safety/Traffic Management | 06/09/2009 | 06/30/2009 | 07/17/2009 | 25048.8 | 0.01
1902 | Indiana | BLACKFORD |  | 06 | 0710921 | This project will improve sections and extend the life of SR 26 from 0.84 mile East of SR 3(Little Lick Creek) to SR 167 with a pavement surface overlay. | Pavement Improvement | 06/02/2009 | 08/24/2009 | 11/13/2009 | 871676.31 | 6.442
1903 | Indiana | GRANT |  | 05 | 0710933 | This project will improve sections and extend the life of SR 26 from SR 13 to I-69 with a pavement surface overlay. | Pavement Improvement | 08/27/2009 | 09/15/2009 | 10/16/2009 | 1236669.07 | 10.873
1904 | Indiana | HOWARD | KOKOMO | 05 | 0710943 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Bridge Construction | 06/01/2009 | 07/10/2009 | 06/15/2011 | 774131.29 | 0.175
1905 | Indiana | CARROLL, HOWARD |  | 02,05 | 0710948 | This project will improve sections and extend the life of SR 22 from SR 29 to 11.48 miles East of SR 29 with a pavement surface overlay. | Pavement Improvement | 06/16/2009 | 08/07/2009 | 11/13/2009 | 1766853.95 | 9.763
1906 | Indiana | HARRISON |  | 09 | 0711000 | This project will move the Historic Rothrock Mill bridge from it's current location to storage for preservation purposes. | Transportation Enhancements | 06/19/2009 | 07/13/2009 | 08/15/2009 | 41802.09 | 0.01
1907 | Indiana | WHITE |  | 04 | 0711020 | This project will improve sections and extend the life of US 24 with a pavement surface overlay. | Pavement Improvement | 04/15/2009 | 05/30/2009 | 07/31/2009 | 394030 | 1.347
1908 | Indiana | KOSCIUSKO |  | 03 | 0711022 | This project will improve sections and extend the life of SR 15 with a pavement surface overlay. | Pavement Improvement | 03/24/2009 | 05/01/2009 | 07/17/2009 | 357828.19 | 1.006
1909 | Indiana | NOBLE, STATEWIDE |  | 03 | 0711024 | This project will improve sections and extend the life of SR 9 with a pavement surface overlay. | Pavement Improvement | 03/31/2009 | 05/26/2009 | 10/31/2009 | 555377.21 | 1.83
1910 | Indiana | ORANGE |  | 09 | 0800005 | This project will improve drainage by repairing pipes at SR 145, between 1.6 Miles North TO 9.8 Miles North of SR 164 in Orange County. | Pavement Improvement | 04/13/2009 | 05/14/2009 | 10/30/2009 | 261166 | 7.736
1911 | Indiana | DUBOIS |  | 09 | 0800006 | This project will improve sections and extend the life of SR 164 with a pavement surface overlay. | Pavement Improvement | 04/30/2009 | 06/08/2009 | 09/24/2009 | 186935.08 | 0.467
1912 | Indiana | POSEY |  | 08 | 0800086 | This project will improve sections and extend the life of SR 62 from IL/IN State line to 1.96 miles East of SR 69 with a pavement surface overlay. | Pavement Improvement | 07/23/2009 |  | 11/10/2010 | 1571712.39 | 7.327
1913 | Indiana | DUBOIS |  | 08,09 | 0800122 | SR 56 - Jct with SR 257 to the W jct of US 231 | Pavement Improvement | 10/14/2009 |  | 07/01/2010 | 1363020.69 | 7.716
1914 | Indiana | LAWRENCE |  | 04 | 0800125 | This project will improve sections and extend the life of US 50 from 4.09 miles East of SR 37 to junction with SR 446 with a pavement surface overlay. | Pavement Improvement | 07/07/2009 |  | 11/01/2010 | 688431.96 | 5.553
1915 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0800158 | This project will improve sections and extend the life of US-6 from SR 19 to SR 15 in Elkhart County with a pavement surface overlay. | Pavement Improvement | 06/03/2009 | 07/08/2009 | 10/09/2009 | 979865.66 | 4.255
1916 | Indiana | HUNTINGTON |  | 05 | 0800162 | This project will improve sections and extend the life of US 41 in Huntington County with a pavement surface overlay | Pavement Improvement | 07/06/2009 | 08/19/2009 | 11/04/2009 | 2202419 | 5.192
1917 | Indiana | WABASH, WHITLEY |  | 03,05 | 0800176 | SR 114 - From 1.66 miles E of SR 13 (EEL River) to SR 105 | Pavement Improvement | 12/10/2009 |  | 08/13/2010 | 2098852.25 | 4.214
1918 | Indiana | WAYNE |  | 06 | 0800177 | This project will improve sections and extend the life of SR 227 from CSX R/R to US 27 with a pavement surface overlay. | Pavement Improvement | 07/22/2009 | 08/20/2009 | 11/20/2009 | 488200 | 2.851
1919 | Indiana | WAYNE |  | 06 | 0800191 | This project will improve sections and extend the life of US 27 from. 1.12 miles North of I-70 at East fork of Whitewater River to 5.71 miles North of I-70 at Fountain Circle with a pavement surface o | Pavement Improvement | 07/22/2009 | 08/20/2009 | 11/20/2009 | 985381.71 | 2.765
1920 | Indiana | ALLEN | FORT WAYNE | 03 | 0800196 | This project will improve lighting on I-69 at Airport Expressway in Allen County. | Safety/Traffic Management | 07/10/2009 | 08/18/2009 | 11/30/2009 | 71877.05 | 0.748
1921 | Indiana | HENRY |  | 06 | 0800200 | Road Work -Edit This Field | Pavement Improvement | 08/25/2009 | 09/04/2009 | 10/16/2009 | 527700 | 2.279
1922 | Indiana | JAY |  | 06 | 0800203 | This project will improve sections and extend the life of US 27 in the Town of Portland with a pavement surface overlay. | Pavement Improvement | 07/07/2009 | 08/20/2009 | 10/27/2009 | 674602.4 | 3.134
1923 | Indiana | STATEWIDE |  | 04 | 0800237 | This project will extend the bridge life by repainting bridge beams at various locations in Crawfordsville. | Bridge Improvement | 04/25/2009 | 05/28/2009 | 09/30/2009 | 447413.8 | 0.175
1924 | Indiana | GRANT |  | 05 | 0800260 | This project will improve sections and extend the life of US 35 from 1.65 miles East of SR 15 (10th St) to 0.24 miles East of I-69 and on SR 22 with a pavement surface overlay. | Pavement Improvement | 06/16/2009 | 08/26/2009 | 10/24/2009 | 743435.3 | 2.86
1925 | Indiana | JACKSON |  | 09 | 0800389 | This project will patch deteriorated pavement areas and seal cracks on US 31 4.11 mi. N of SR 250 in Jackson County. | Pavement Improvement | 03/26/2009 | 06/09/2009 | 07/15/2009 | 171134.87 | 0.962
1926 | Indiana | JASPER |  | 02,01 | 0800434 | This project will improve sections and extend the life of SR 10 with a pavement surface overlay. | Pavement Improvement | 04/09/2009 | 05/12/2009 | 06/26/2009 | 359177.3 | 5.991
1927 | Indiana | MARSHALL | SOUTH BEND (MI) | 02 | 0800438 | This project will improve sections and extend the life of SR 17 with a pavement surface overlay. | Pavement Improvement | 04/16/2009 | 09/08/2009 | 11/01/2009 | 324983.18 | 1.694
1928 | Indiana | STARKE |  | 02 | 0800439 | This project will improve sections and extend the life of SR 23 with a pavement surface overlay. | Pavement Improvement | 04/16/2009 | 07/10/2009 | 09/03/2009 | 275567.9 | 4.378
1929 | Indiana | JASPER |  | 01,04 | 0800440 | This project will improve sections and extend the life of SR 16 with a pavement surface overlay. | Pavement Improvement | 04/16/2009 | 05/18/2009 | 06/30/2009 | 508298.44 | 6.286
1930 | Indiana | KOSCIUSKO |  | 03 | 0800475 | This project will improve sections and extend the life of SR 25 with a pavement surface overlay. | Pavement Improvement | 03/24/2009 | 05/01/2009 | 07/17/2009 | 169077.25 | 0.571
1931 | Indiana | BARTHOLOMEW | COLUMBUS | 09 | 0800516 | This project will add turn lanes, nodernize the signal, and widen the intersection at SR 11and Bartholomw county Road 450S. | Safety/Traffic Management | 05/06/2009 | 06/01/2009 | 08/15/2010 | 41055.8 | 0.175
1932 | Indiana | MARION | INDIANAPOLIS | 07 | 0800517 | This project will install fiber optic lines from the Indianapolis Traffic Management Center to downtown Indianapolis to improve the closed circuit TV system used for traffic management. | Safety/Traffic Management | 06/11/2009 | 06/29/2009 | 05/28/2010 | 714614.44 | 3.57
1933 | Indiana | SPENCER |  | 09 | 0800753 | This project will improve sections and extend the life of SR 245 from junction with SR 70 to 3.50 miles South of SR 162 with a pavement surface overlay. | Pavement Improvement | 07/23/2009 |  | 11/01/2011 | 640303.87 | 1.781
1934 | Indiana | SPENCER |  | 09 | 0800766 | This project will improve sections and extend the life of SR 161 from Ky State Line to SR 66 with a pavement surface overlay. | Pavement Improvement | 07/23/2009 |  | 11/01/2011 | 1807885.98 | 8.179
1935 | Indiana | GIBSON |  | 08 | 0800817 | This project will improve sections and extend the life of SR 168 from US 41 to SR 57 with a pavement surface overlay. | Pavement Improvement | 07/23/2009 | 08/26/2009 | 05/31/2010 | 1519563.28 | 5.535
1936 | Indiana | POSEY |  | 08 | 0800821 | This project will improve sections and extend the life of SR 69 from 2.48 miles South of West junction with SR 66 to 0.1 miles North of I-64 with a pavement surface overlay. | Pavement Improvement | 07/09/2009 | 08/06/2009 | 08/01/2010 | 1323000 | 7.657
1937 | Indiana | TIPPECANOE, WHITE | LAFAYETTE-WEST LAFAYETTE | 04 | 0800831 | This project will improve sections and extend the life of SR 43 in Tippecanoe & White Counties with a pavement surface overlay | Pavement Improvement | 04/09/2009 | 08/20/2009 | 07/31/2009 | 466983.08 | 1.894
1938 | Indiana | WAYNE |  | 06 | 0800962 | This project will extend the bridge life by repainting bridge beams at I-70 in Wayne County. | Bridge Improvement | 08/20/2009 | 09/16/2009 | 11/24/2009 | 335618 | 0.175
1939 | Indiana | NOBLE, DE KALB |  | 03 | 0800974 | US 6 - From SR 3 E jct (Kendallville) to I-69 | Pavement Improvement | 12/16/2009 |  | 10/31/2010 | 2722326.86 | 5.034
1940 | Indiana | WHITLEY, HUNTINGTON |  | 03,05 | 0800975 | This project will improve sections and extend the life of US 24 from 1.66 Miles East of SR 9 E junction (Meridian Rd) to 0.75 Miles East of SR 114 with a pavement surface overlay. | Pavement Improvement | 07/07/2009 | 09/08/2009 | 10/23/2009 | 2710401.31 | 5.016
1941 | Indiana | ALLEN | FORT WAYNE | 03 | 0800984 | This project will improve sections and extend the life of US 24 in Allen County with a pavement surface overlay | Pavement Improvement | 03/25/2009 | 08/17/2009 | 09/04/2009 | 666979.75 | 2.009
1942 | Indiana | LAGRANGE |  | 03 | 0810097 | E US 20 - From 0.20 miles E of SR 9 to 4.28 miles E of SR 3 (Lagrange/Steuben Co Line). | Pavement Improvement | 12/29/2009 |  | 10/31/2010 | 1459541 | 11.331
1943 | Indiana | MIAMI, WABASH, HUNTINGTON |  | 05 | 0810100 | From SR 19 (Miami Co) to SR 5 (Huntington Co). | Pavement Improvement | 12/15/2009 |  | 10/01/2010 | 3126991.54 | 7.501
1944 | Indiana | STATEWIDE |  | 01,02,04 | 0810108 | This project will improve the pavement markings in the LaPorte Area. | Safety/Traffic Management | 04/16/2009 | 06/15/2009 | 11/12/2009 | 249489.2 | 0
1945 | Indiana | WARRICK |  | 08 | 0810123 | This project will improve drainage by repairing pipes at I-64, 1 mile East of SR 161 in Warrick County. | Pavement Improvement | 05/12/2009 | 06/10/2009 | 11/15/2009 | 117802.99 | 0.175
1946 | Indiana | CRAWFORD, WARRICK |  | 08 | 0810124 | This project will improve drainage by repairing pipes at I-64 from 5 miles East of I-164 to 1 mile West of SR 66 in Crawford and Warren Counties. | Pavement Improvement | 05/12/2009 | 06/10/2009 | 11/15/2009 | 139519.02 | 0.175
1947 | Indiana | WHITLEY |  | 03,05 | 0810228 | SR 114 - From SR 105 to SR 9 | Pavement Improvement | 12/16/2009 |  | 10/22/2010 | 2125280.99 | 4.553
1948 | Indiana | STEUBEN |  | 03 | 0810240 | This project will mitigate the environmental impacts of relocating a stream as part of the US 20 curve correction project, adding 370' of stream length, creating a floodplain and planting native veget | Other | 06/18/2009 | 08/24/2009 | 06/30/2010 | 92975 | 0.01
1949 | Indiana | WARREN |  | 08 | 0810254 | This project will extend the bridge life by repainting bridge beams at SR 55 over Big Pine Creek in Warren County. | Bridge Improvement | 09/01/2009 | 10/08/2009 | 11/15/2009 | 253700.68 | 0.175
1950 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0810342 | This project will improve sections and extend the life of US-31 from Youngs Creek Bridge to Westview Dr in Johnson County with a pavement surface overlay. | Pavement Improvement | 04/16/2009 | 05/14/2009 | 07/31/2009 | 694983.4 | 0.452
1951 | Indiana | TIPPECANOE, CLINTON |  | 04 | 0810387 | This project will improve drainage by repairing pipes at I-64 in Posey, Spencer and Vanderburgh Counties. | Pavement Improvement | 05/22/2009 | 06/15/2009 | 07/04/2009 | 253803.9 | 1.101
1952 | Indiana | PUTNAM |  | 08 | 0810388 | This project will improve sections and extend the life of SR 243 in Putnam County with a pavement surface overlay. | Pavement Improvement | 05/13/2009 | 06/09/2009 | 07/01/2009 | 650934.62 | 3.988
1953 | Indiana | JEFFERSON |  | 09 | 0810390 | This project will improve sections and extend the life of US 421 in Jefferson County with a pavement surface overlay | Pavement Improvement | 05/22/2009 | 06/24/2009 | 10/09/2009 | 652310.41 | 7.889
1954 | Indiana | JEFFERSON |  | 09 | 0810391 | This project will improve sections and extend the life of SR 57 in Jefferson County with a pavement surface overlay. | Pavement Improvement | 05/22/2009 | 06/25/2009 | 07/31/2009 | 229303.9 | 2.58
1955 | Indiana | MONROE, BROWN |  | 09 | 0810411 | This project will improve sections and extend the life of SR 46 from SR 446 to SR 135 with a pavement surface overlay. | Pavement Improvement | 05/13/2009 | 06/16/2009 | 08/31/2009 | 1784927.67 | 8.788
1956 | Indiana | JACKSON |  | 09 | 0810412 | This project will improve sections and extend the life ofS R-258 from SR 58 to Elm St in Jackson County with a pavement surface overlay. | Pavement Improvement | 06/01/2009 | 08/04/2009 | 11/13/2009 | 1224335.79 | 11.873
1957 | Indiana | JENNINGS, JEFFERSON |  | 09 | 0810413 | This project will improve sections and extend the life of SR 7 from 1.52 miles North of Clifty Creek Drive to SR 3 with a pavement surface overlay. | Pavement Improvement | 05/09/2009 | 08/13/2009 | 11/13/2009 | 1696103.37 | 5.907
1958 | Indiana | JENNINGS, JEFFERSON |  | 09 | 0810414 | This project will improve sections and extend the life of SR 250 from SR-3 to SR-7 with a pavement surface overlay. | Pavement Improvement | 10/07/2009 |  | 06/30/2010 | 735667.41 | 4.901
1959 | Indiana | DEARBORN |  | 06,09 | 0810415 | This project will improve sections and extend the life of SR-46 from SR 1 to US 52 in Dearborn County with a pavement surface overlay. | Pavement Improvement | 07/28/2009 | 08/28/2009 | 10/24/2009 | 513103.76 | 3.507
1960 | Indiana | FULTON |  | 02,05 | 0810431 | This project will improve sections and extend the life of US 31 from the Fulton/Miami County Line to Old US 31 with a pavement surface overlay. | Pavement Improvement | 06/09/2009 | 07/14/2009 | 07/18/2009 | 487095.33 | 3.819
1961 | Indiana | STARKE |  | 02 | 0810432 | This project will improve sections and extend the life of US 35 through the town of Knox with a pavement surface overlay. | Pavement Improvement | 06/17/2009 | 07/18/2009 | 07/31/2009 | 323005.7 | 1.596
1962 | Indiana | FOUNTAIN |  | 08 | 0810453 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Pavement Improvement | 06/17/2009 | 07/16/2009 | 08/31/2010 | 568694.99 | 1.014
1963 | Indiana | STATEWIDE |  | 01,02,04 | 0810532 | This project will improve pavement markings in the LaPorte Area. | Safety/Traffic Management | 06/19/2009 | 07/06/2009 | 09/11/2009 | 346985.82 | 0
1964 | Indiana | CARROLL |  | 02 | 0810598 | This project will construct canal boat support facilities for the Wabash and Erie Canal in the City of Delphi. | Transportation Enhancements | 06/19/2009 |  | 05/22/2010 | 401437.39 | 0.175
1965 | Indiana | WHITE |  | 04 | 0818022 | This project will improve the surface and rebuild sections of the bridge on US 421 over Little Monon Creek in White County. | Bridge Replacement | 03/21/2009 | 04/16/2009 | 08/28/2009 | 668112.1 | 0.175
1966 | Indiana | MADISON | ANDERSON | 06 | 0887013 | This project will add turn lanes and widen the intersection at SR 32 and Rangeline Road in Madison County. | Pavement Improvement | 07/08/2009 | 08/24/2009 | 07/31/2010 | 1920915 | 0.284
1967 | Indiana | SHELBY |  | 06 | 0900008 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | New Bridge Construction | 05/12/2009 | 07/22/2009 | 07/11/2011 | 252212.4 | 0.175
1968 | Indiana | POSEY, VANDERBURGH, SPENCER |  | 04 | 0900048 | This project will improve drainage by repairing pipes at I-64 in Posey, Spencer and Vanderburgh Counties. | Pavement Improvement | 05/12/2009 | 06/10/2009 | 11/15/2009 | 727204.41 | 10.569
1969 | Indiana | DUBOIS |  | 09 | 0900049 | Jasper Multi-Use Path - Ph 2; from W 20th St to 30th St | Transportation Enhancements | 11/23/2009 |  | 07/15/2010 | 442427.03 | 0.175
1970 | Indiana | TIPPECANOE |  | 04 | 0900079 | This project will improve sections and extend the life of US 52 in West Lafayette with a pavement surface overlay. | Pavement Improvement | 06/03/2009 | 06/15/2009 | 11/28/2009 | 3816213.94 | 5.51
1971 | Indiana | LA PORTE |  | 02 | 0900082 | US 35 - from Severs Rd to East Jct with US 20 | Pavement Improvement | 10/08/2009 | 10/15/2009 | 08/13/2010 | 1814476.19 | 3.867
1972 | Indiana | SHELBY |  | 06 | 0900083 | This project will build a new road from Amos Road to McKay Road in Shelby County. | New Construction | 08/11/2009 |  | 09/12/2010 | 1925233.13 | 0.175
1973 | Indiana | NEWTON |  | 01 | 0900084 | This project will improve sections and extend the life of US 41 in Newton County with a pavement surface overlay. | Pavement Improvement | 06/09/2009 | 07/17/2009 | 08/28/2009 | 1973246.73 | 5.917
1974 | Indiana | MARSHALL |  | 02 | 0900086 | This project will improve sections and extend the life of SR 106 in Marshall County with a pavement surface overlay. | Pavement Improvement | 06/17/2009 | 09/09/2009 | 10/16/2009 | 517285 | 4.304
1975 | Indiana | MARSHALL |  | 02 | 0900087 | This project will improve sections and extend the life of US 6 in Marshall County with a pavement surface overlay | Pavement Improvement | 06/17/2009 | 09/02/2009 | 10/02/2009 | 418872.18 | 3.652
1976 | Indiana | DEARBORN |  | 06 | 0900092 | This project will improve sections and extend the life of old US 52 on Old US-52 from IR-74 to West Harrison Corporate Limitswith a pavement surface overlay. | Pavement Improvement | 07/27/2009 | 08/21/2009 | 11/03/2009 | 352375.15 | 2.42
1977 | Indiana | DEARBORN |  | 09 | 0900093 | This project will improve sections and extend the life of York Ridge Road from SR-1 to North Dearborn Road with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 680783.55 | 7.44
1978 | Indiana | DEARBORN |  | 09 | 0900095 | This project will improve sections and extend the life of North Hogan Road from SR 350 to Hogan Road in Dearborn County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 |  | 10/09/2009 | 234751.67 | 11.89
1979 | Indiana | DEARBORN |  | 09 | 0900096 | This project will improve sections and extend the life of North Dearborn from Ripley county line to SR1 in Dearborn County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 |  | 10/09/2009 | 142476.7 | 7.56
1980 | Indiana | VIGO | TERRE HAUTE | 08 | 0900122 | This project will improve drainage by repairing pipes at I-70, .10 mile East of SR 46 in Vigo County. | Safety/Traffic Management | 06/25/2009 | 07/01/2009 | 08/21/2009 | 626338.95 | 0.175
1981 | Indiana | HAMILTON, HENDRICKS, MARION, BOONE | INDIANAPOLIS | 04,07 | 0900129 | This project will install traffic cameras on I-465, I-65, I-70 and I-74. | Other | 06/11/2009 | 08/05/2009 | 05/28/2010 | 475935 | 4.205
1982 | Indiana | TIPPECANOE |  | 04 | 0900133 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 1408413.79 | 0.175
1983 | Indiana | TIPPECANOE |  | 04 | 0900134 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 530746.71 | 0.139
1984 | Indiana | TIPPECANOE |  | 04 | 0900135 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 734550.61 | 0.175
1985 | Indiana | TIPPECANOE |  | 04 | 0900136 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 893652.86 | 0.175
1986 | Indiana | DEARBORN | CINCINNATI | 09 | 0900144 | This project will improve sections and extend the life of SR 148 from SR-48 to Maple Street with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/16/2010 | 827466.29 | 4.577
1987 | Indiana | JEFFERSON |  | 09 | 0900145 | This project will improve sections and extend the life of SR 56 from East Junction of SR-62 to Crooked Creek Bridgewith a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/16/2010 | 595391.45 | 1.819
1988 | Indiana | JACKSON |  | 09 | 0900147 | SR 235 - SR-135 to US-50 | Pavement Improvement | 10/07/2009 | 11/02/2009 | 11/15/2009 | 851274.13 | 5.053
1989 | Indiana | DEARBORN |  | 09 | 0900159 | This project will improve sections and extend the life of Ridge Ave. from Decker Ave to Robinson Avenue with a pavement surface overlay. | Pavement Improvement | 07/15/2009 | 08/07/2009 | 09/30/2009 | 84722.5 | 0.42
1990 | Indiana | STARKE |  | 02 | 0900176 | This project will improve sections and extend the life of SR 10 in Starke County with a pavement surface overlay. | Pavement Improvement | 08/20/2009 | 09/21/2009 | 11/15/2009 | 1655345.65 | 5.429
1991 | Indiana | LAKE, PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900211 | This project will patch deteriorated pavement areas and seal cracks on I-94 from 1.5 mi. E of I-65 to SR 249 in Lake and Porter Counties. | Pavement Improvement | 07/22/2009 |  | 11/30/2009 | 907112.68 | 3.885
1992 | Indiana | CARROLL, CASS |  | 02 | 0900218 | SR 25 - from SR 218 in Delphi to Logansport | Pavement Improvement | 01/22/2010 |  | 06/30/2010 | 165193.23 | 8.337
1993 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900219 | This project will patch deteriorated pavement areas and seal cracks on US 20 from SR 912 to Bridge St. in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 101851.5 | 2.929
1994 | Indiana | JOHNSON |  | 05,04,06 | 0900238 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | New Bridge Construction | 05/12/2009 | 07/22/2009 | 07/11/2011 | 242787.2 | 0.109
1995 | Indiana | PERRY |  | 09 | 0900296 | This project will improve safety and extend the life of the bridge(s) on County Road 211 over I-64 in Perry County. | Bridge Improvement | 07/07/2009 | 09/17/2009 | 06/30/2010 | 419566 | 0.175
1996 | Indiana | KNOX |  | 08 | 0900297 | This project will improve safety and extend the life of the bridge(s) on US 41 over Main Street in Knox County. | Bridge Improvement | 07/10/2009 |  | 07/31/2010 | 345750.5 | 0.175
1997 | Indiana | KNOX |  | 08 | 0900298 | This project will improve safety and extend the life of the bridge(s) on US 41 over Main Street in Knox County. | Bridge Improvement | 07/10/2009 |  | 07/31/2010 | 309249.5 | 0.175
1998 | Indiana | GREENE |  | 08 | 0900299 | This project will improve safety and extend the life of the bridge(s) on SR 157 over White River in Green County. | Bridge Improvement | 07/24/2009 | 09/22/2009 | 06/30/2010 | 961859.92 | 0.175
1999 | Indiana | OWEN |  | 08 | 0900300 | This project will improve safety and extend the life of the bridge(s) on US 231 over Fish Creek in Owen County. | Bridge Improvement | 07/24/2009 | 09/22/2009 | 06/30/2010 | 621795 | 0.175
2000 | Indiana | HUNTINGTON |  | 05 | 0900301 | This project will improve safety and extend the life of the bridge(s) on SR 124 over Brock Creek in Huntington County. | Bridge Improvement | 07/07/2009 | 08/21/2009 | 10/30/2009 | 271400.3 | 0.175
2001 | Indiana | HUNTINGTON |  | 05 | 0900302 | This project will improve safety and extend the life of the bridge(s) on County Road 300 South over I-69 in Huntington County. | Bridge Improvement | 07/07/2009 | 08/21/2009 | 10/30/2009 | 421012.07 | 0.175
2002 | Indiana | BARTHOLOMEW |  | 09 | 0900303 | This project will improve safety and extend the life of the bridge(s) on US 31 over Little Sand Creek in Bartholomew County. | Bridge Improvement | 10/09/2009 |  | 10/31/2010 | 662406.7 | 0.175
2003 | Indiana | BARTHOLOMEW |  | 09 | 0900304 | This project will improve safety and extend the life of the bridge(s) on SR 46 over the abandoned Railroad in Bartholomew County. | Bridge Improvement | 10/09/2009 |  | 10/31/2010 | 646372.3 | 0.096
2004 | Indiana | BROWN |  | 09 | 0900305 | This project will improve safety and extend the life of the bridge(s) on SR 45 over Beanblossom Creek in Brown County. | Bridge Improvement | 07/07/2009 |  | 10/29/2010 | 517603 | 0.175
2005 | Indiana | BROWN |  | 09 | 0900306 | This project will improve safety and extend the life of the bridge(s) on SR 45 over Beanblossom Creek in Brown County. | Bridge Improvement | 07/07/2009 |  | 10/29/2010 | 468003 | 0.175
2006 | Indiana | DECATUR |  | 06 | 0900307 | This project will improve safety and extend the life of the bridge(s) on SR 3 over Clifty Creek in Decatur County. | Bridge Improvement | 07/07/2009 |  | 11/19/2010 | 695500 | 0.175
2007 | Indiana | RIPLEY |  | 09 | 0900308 | This project will improve safety and extend the life of the bridge(s) on US 50 over Laughery Creek in Ripley County. | Bridge Improvement | 08/18/2009 |  | 11/19/2010 | 714059.5 | 0.175
2008 | Indiana | SCOTT |  | 09 | 0900309 | This project will improve safety and extend the life of the bridge(s) on SR 3 over the abandoned Railroad in Scott County. | Bridge Improvement | 07/24/2009 |  | 09/20/2010 | 520602.25 | 0.175
2009 | Indiana | VERMILLION |  | 08 | 0900310 | This project will improve safety and extend the life of the bridge(s) on SR 63 over Brouiletts Creek in Vermillion County. | Bridge Improvement | 08/18/2009 |  | 10/15/2010 | 775788 | 0.175
2010 | Indiana | WARREN |  | 08 | 0900311 | This project will improve safety and extend the life of the bridge(s) on SR 263 over Redwood Creek in Warren County. | Bridge Improvement | 07/17/2009 | 09/10/2009 | 07/18/2010 | 654751.5 | 0.175
2011 | Indiana | VERMILLION |  | 08 | 0900312 | This project will improve safety and extend the life of the bridge(s) on SR 71 over Little Vermillion River in Vermillion County. | Bridge Improvement | 08/18/2009 |  | 10/15/2010 | 455103 | 0.175
2012 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900314 | This project will patch deteriorated pavement areas and seal cracks on I-65 from SR 2 to US 231 in Lake County. | Pavement Improvement | 07/22/2009 |  | 11/30/2009 | 584240.48 | 3.826
2013 | Indiana | STARKE, PORTER, MARSHALL, LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02,01 | 0900315 | This project will patch deteriorated pavement areas and seal cracks on US 30 from the Lake/Porter County Line to SR 17 in LaPorte, Marshall, Porter and Starke Counties. | Pavement Improvement | 07/22/2009 |  | 11/30/2009 | 41600.48 | 8.72
2014 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900316 | This project will patch deteriorated pavement areas and seal cracks on US 30 from US 41 to SR 55 in Lake County. | Pavement Improvement | 07/22/2009 |  | 11/30/2009 | 36480.48 | 2.203
2015 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900317 | This project will patch deteriorated pavement areas and seal cracks on I-94 from SR 249 to SR 49 in Porter County. | Pavement Improvement | 07/22/2009 |  | 11/30/2009 | 68160.48 | 5.235
2016 | Indiana | LA PORTE | MICHIGAN CITY | 02 | 0900318 | This project will patch deteriorated pavement areas and seal cracks on I-94 from US 35 to the Michigan State Line in LaPorte County. | Pavement Improvement | 07/22/2009 |  | 11/30/2009 | 55680.48 | 5.831
2017 | Indiana | BARTHOLOMEW | COLUMBUS | 06 | 0900321 | This project will improve sections and extend the life of 25th St. from CR 350 E to SR 9 with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/09/2009 | 11/15/2009 | 531987 | 4.3
2018 | Indiana | PARKE |  | 08 | 0900322 | This project will improve the surface and rebuild sections of the bridge on SR 47 at Turkey Run in Parke County. | Bridge Improvement | 07/11/2009 | 09/16/2009 | 11/15/2009 | 303605.25 | 0.175
2019 | Indiana | WARREN |  | 08 | 0900323 | This project will improve the surface and rebuild sections of the bridge on US 136 at the Wabash River in Warren County. | Bridge Improvement | 07/07/2009 | 09/10/2009 | 09/30/2009 | 471268.58 | 0.175
2020 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900327 | This project will patch deteriorated pavement areas and seal cracks on US 231 from SR 912 to Bridge St. in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 22020.5 | 5.574
2021 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900329 | This project will patch deteriorated pavement areas and seal cracks on SR 2 from Cline Ave. to SR 53 in Porter County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 60440.5 | 6.643
2022 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900331 | This project will patch deteriorated pavement areas and seal cracks on US 41 from Huehn St. to 0.25 mi.. N. of Sheffield Ave. in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 32000.5 | 1.567
2023 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900333 | This project will patch deteriorated pavement areas and seal cracks on US 12 from W. of Calumet Ave. to the Illinois State Line. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 30625.5 | 0.791
2024 | Indiana | HOWARD |  | 05 | 0900334 | This project will improve sections and extend the life of Howard County Road 200N from 1350 East to the county line with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 26460.37 | 0.175
2025 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900335 | This project will patch deteriorated pavement areas and seal cracks on US 12 from Schrage Ave. to the lift bridge S. of Riley Road in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 89218 | 0.994
2026 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900336 | This project will improve the surface and rebuild sections of the bridge on SR 912 over I-80 in Lake County. | Bridge Improvement | 09/14/2009 |  | 06/30/2010 | 298381.48 | 0.175
2027 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900337 | This project will improve the surface and rebuild sections of the bridge on SR 912 over I-80 in Lake County. | Bridge Improvement | 09/14/2009 |  | 06/30/2010 | 300423.28 | 0.175
2028 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900338 | This project will improve the surface and rebuild sections of the bridge on SR 152 at the Conrail and IHB Railroad in Lake County. | Bridge Replacement | 09/16/2009 |  | 06/30/2010 | 634408.12 | 0.175
2029 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900339 | This project will patch deteriorated pavement areas and seal cracks on US 20 from SR 249 to US 20/I-94 in Porter County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 59680.5 | 1.772
2030 | Indiana | HOWARD |  | 02 | 0900340 | This project will improve sections and extend the life of Howard County Road 200W from County Road 200North to County Road 325 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 81387.28 | 0.175
2031 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900341 | This project will improve the surface and rebuild sections of the bridge on US 41 over Brown Ditch in Lake County. | Bridge Improvement | 09/14/2009 | 10/12/2009 | 10/31/2009 | 27193.25 | 0.175
2032 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900342 | This project will patch deteriorated pavement areas and seal cracks on SR 312 from US 41 to Parrish Ave. in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 32000.25 | 2.624
2033 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900343 | This project will improve the surface and rebuild sections of the bridge on US 41 over Brown Ditch in Lake County. | Bridge Improvement | 09/14/2009 | 10/12/2009 | 10/31/2009 | 23371.25 | 0.175
2034 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900344 | This project will patch deteriorated pavement areas and seal cracks on US 31 from US 20 to the Michigan State Line in St. Joseph County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 75952.75 | 3.788
2035 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900345 | This project will improve the surface and rebuild sections of the bridge on US 41 over Singleton Ditch in Lake County. | Bridge Improvement | 09/14/2009 | 10/12/2009 | 10/31/2009 | 23371.25 | 0.175
2036 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900346 | This project will improve the surface and rebuild sections of the bridge on US 41 over Singleton Ditch in Lake County. | Bridge Improvement | 09/14/2009 | 10/12/2009 | 10/31/2009 | 23371.25 | 0.175
2037 | Indiana | MARSHALL | SOUTH BEND (MI) | 02 | 0900347 | This project will patch deteriorated pavement areas and seal cracks ON US 6 from 0.5 mi. W of SR 106 to 0.5 mi. E of SR 106 in Marshall County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 27450.25 | 4.147
2038 | Indiana | JENNINGS |  | 09 | 0900348 | This project will improve the surface and rebuild sections of the bridge on US 50 at Vernon Fork Muscatatuck River in Jennings County. | Bridge Improvement | 09/17/2009 |  | 07/31/2010 | 280871.8 | 0.175
2039 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900349 | This project will patch deteriorated pavement areas and seal cracks on US 12 from SR 249 to SR 149 bridge in Porter County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 20400.25 | 1.439
2040 | Indiana | HARRISON |  | 09 | 0900350 | This project will improve the surface and rebuild sections of the bridge on SR 135 at Lick Run Creek in Harrison County. | Bridge Improvement | 07/20/2009 | 08/20/2009 | 09/26/2009 | 574000 | 0.175
2041 | Indiana | BARTHOLOMEW |  | 06 | 0900351 | This project will improve the surface and rebuild sections of the bridge on I-65 over Driftwood River in Bartholomew County. | Bridge Improvement | 08/18/2009 |  | 10/19/2010 | 606321.7 | 0.175
2042 | Indiana | BARTHOLOMEW |  | 06 | 0900352 | This project will improve the surface and rebuild sections of the bridge on I-65 over Driftwood River in Bartholomew County. | Bridge Improvement | 08/18/2009 |  | 10/19/2010 | 436878.3 | 0.175
2043 | Indiana | KNOX |  | 08 | 0900353 | This project will improve the surface and rebuild sections of the bridge on US 50 over Wabash River in Knox County. | Bridge Improvement | 07/15/2009 | 08/14/2009 | 10/15/2009 | 57812.21 | 0.01
2044 | Indiana | LA PORTE | MICHIGAN CITY | 02 | 0900354 | This project will patch deteriorated pavement areas and seal cracks on SR 212 from US 12 to US 20 in LaPorte County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/30/2009 | 32000.5 | 3.339
2045 | Indiana | KNOX |  | 08 | 0900355 | This project will improve the surface and rebuild sections of the bridge on US 50 over Wabash River in Knox County. | Bridge Improvement | 07/15/2009 | 08/14/2009 | 10/15/2009 | 60840.56 | 0.01
2046 | Indiana | LAWRENCE |  | 08 | 0900356 | This project will improve the surface and rebuild sections of the bridge on US 50 over White River in Lawrence County. | Bridge Improvement | 07/15/2009 | 08/14/2009 | 10/15/2009 | 52923.92 | 0.175
2047 | Indiana | WAYNE |  | 06 | 0900357 | This project will improve sections and extend the life of Arba Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 |  | 06/04/2010 | 350293.36 | 3.58
2048 | Indiana | LAWRENCE |  | 08 | 0900358 | This project will improve the surface and rebuild sections of the bridge on US 50 over White River in Lawrence County. | Bridge Improvement | 07/15/2009 | 08/14/2009 | 10/15/2009 | 53238.42 | 0.175
2049 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900363 | This project will extend the bridge life by repainting bridge beams at I-64 over SR 111 & Main Street in Floyd County. | Bridge Improvement | 10/29/2009 | 01/04/2010 | 10/28/2010 | 929831.88 | 0.175
2050 | Indiana | CASS |  | 02 | 0900364 | SR 25 - from Logansport to SR 16 | Pavement Improvement | 01/22/2010 |  | 06/30/2010 | 35019.04 | 10.264
2051 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900365 | This project will extend the bridge life by repainting bridge beams at I-64 over Southern Railroad in Floyd County. | Bridge Improvement | 10/29/2009 | 01/04/2010 | 10/28/2010 | 871470.52 | 0.175
2052 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900366 | This project will extend the bridge life by repainting bridge beams at I-64 over SR 111 & Main Street in Floyd County. | Bridge Improvement | 10/29/2009 | 01/04/2010 | 10/28/2010 | 1430958.6 | 0.175
2053 | Indiana | NEWTON |  | 01 | 0900367 | US 41 - from SR 114 to SR 14 | Pavement Improvement | 01/22/2010 |  | 06/30/2010 | 45725.58 | 5.309
2054 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0900368 | This project will extend the bridge life by repainting bridge beams at I-65 at Riverside Drive & Market Street in Clark County. | Bridge Improvement | 08/03/2009 | 09/23/2009 | 11/15/2009 | 578443.54 | 0.175
2055 | Indiana | JASPER |  | 01 | 0900369 | US 231 - from SR 14 to CR 600N | Pavement Improvement | 01/22/2010 |  | 06/30/2010 | 25143.09 | 5.076
2056 | Indiana | MARSHALL |  | 02 | 0900371 | US 31 - from SR 110 to 0.1mi S of SR 10 | Pavement Improvement | 01/22/2010 |  | 06/30/2010 | 92387.04 | 4.711
2057 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0900406 | This project will upgrade and improve the traffic signals at various locations in the town of Westfield. | Safety/Traffic Management | 11/23/2009 |  | 03/01/2010 | 65210.2 | 0.175
2058 | Indiana | CRAWFORD |  | 09 | 0900434 | This project will improve drainage by repairing pipes at I-64 in Crawford County. | Pavement Improvement | 07/16/2009 | 08/31/2009 | 06/01/2010 | 1605682 | 10.914
2059 | Indiana | VANDERBURGH |  | 08 | 0900436 | This project will improve drainage by repairing pipes at SR 66 in Crawford County. | Other | 07/06/2009 | 08/31/2009 | 10/15/2009 | 799196 | 3.992
2060 | Indiana | MARSHALL |  | 02 | 0900441 | This project will complete the restoration of the Bremen Train Depot. | Transportation Enhancements | 12/16/2009 |  | 10/31/2010 | 289960.37 | 0.175
2061 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900443 | Central Ave. from 119th to 116th and Oliver St. from 119th to 117th |  | 01/14/2010 |  | 06/30/2010 | 289180.25 | 0.175
2062 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900448 | This project will replace the bridge deck on SR 23 over Mishawaka Ave in St Joseph County. | Bridge Improvement | 08/18/2009 | 10/12/2009 | 05/15/2010 | 730528.5 | 0.175
2063 | Indiana | FOUNTAIN |  | 04 | 0900449 | This project will improve safety and extend the life of the bridge(s) on SR 341 over Coal Creek in Fountain County. | Bridge Improvement | 07/17/2009 | 09/10/2009 | 07/18/2010 | 357212.5 | 0.175
2064 | Indiana | PARKE |  | 08 | 0900450 | This project will improve safety and extend the life of the bridge(s) on US 41 over Big Raccoon Creek in Parke County. | Bridge Improvement | 07/07/2009 |  | 07/31/2010 | 795594.75 | 0.175
2065 | Indiana | WABASH |  | 05 | 0900451 | This project will improve safety and extend the life of the bridge(s) on Sr 13 over Paw Paw Creek in Wabash County. | Pavement Improvement | 07/07/2009 | 08/05/2009 | 10/30/2009 | 157785.47 | 0.175
2066 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900452 | This project will improve safety and extend the life of the bridge(s) on SR 4 over Rock Run Creek in Elkhart County. | Bridge Improvement | 08/18/2009 | 09/14/2009 | 10/23/2009 | 133305.1 | 0.175
2067 | Indiana | ADAMS |  | 06 | 0900453 | This project will improve safety and extend the life of the bridge(s) on SR 218 over Wagley Farlow Ditch in Adams County. | Bridge Improvement | 07/07/2009 | 09/03/2009 | 10/30/2009 | 326688.84 | 0.175
2068 | Indiana | JASPER |  | 01 | 0900469 | This project will improve sections and extend the life of County Road 900North from 200 west to 300 east in Jasper County with a pavement surface overlay. | Pavement Improvement | 12/31/2009 |  | 06/05/2010 | 449316.53 | 0.175
2069 | Indiana | JASPER |  | 02 | 0900470 | This project will improve sections and extend the life of County Road 400West from Northern County limits to intersection at SR 10 in Jasper County with a pavement surface overlay. | Pavement Improvement | 12/31/2009 |  | 06/05/2010 | 552780.17 | 0.175
2070 | Indiana | MARSHALL |  | 02 | 0900493 | This project will improve sections and extend the life of 9A Road from SR 31 to King Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/02/2010 | 16159.25 | 0.175
2071 | Indiana | MARSHALL |  | 02 | 0900496 | This project will improve sections and extend the life of Lincoln Highway from King Road to Fir Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/06/2009 | 06/30/2010 | 655089.73 | 0.175
2072 | Indiana | MARSHALL |  | 02 | 0900500 | This project will improve sections and extend the life of 4th Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/02/2010 | 5861.81 | 0.175
2073 | Indiana | MARSHALL |  | 02 | 0900501 | This project will improve sections and extend the life of King Road from Plymouth-Goshen Trail to 4th Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/02/2010 | 78275.02 | 0.145
2074 | Indiana | MARSHALL |  | 02 | 0900502 | This project will improve sections and extend the life of Plymouth-Goshen Trail from Linden Road to King Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/02/2010 | 17565.74 | 0.175
2075 | Indiana | MARSHALL |  | 02 | 0900514 | This project will improve sections and extend the life of Lincoln Highway from Fir Road to Elm Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/06/2009 | 06/30/2010 | 82480.85 | 0.175
2076 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900518 | Wisconsin St. from Old Ridge Road to 10th Street | Pavement Improvement | 12/16/2009 |  | 06/05/2010 | 350540.74 | 0.175
2077 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900521 | 3rd Street from S LaSalle St to Main Street | Pavement Improvement | 10/13/2009 | 11/05/2009 | 11/21/2009 | 303299.25 | 1.5
2078 | Indiana | BROWN |  | 09 | 0900535 | This project will improve sections and extend the life of Gatesville Rd. from SR 135 to Salt Cree with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 07/01/2010 | 389988 | 0.175
2079 | Indiana | BROWN |  | 09 | 0900536 | This project will improve sections and extend the life of Christiansburg Rd. Rd from SR 135 S to Bells with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 07/01/2010 | 263912.37 | 0.175
2080 | Indiana | KNOX |  | 08 | 0900537 | This project will improve sections and extend the life of Bicknell Slab Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/24/2009 | 11/30/2009 | 522524.3 | 8.03
2081 | Indiana | KNOX |  | 08 | 0900538 | This project will improve sections and extend the life of Sixth St in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/08/2009 | 11/30/2009 | 142978.5 | 1.53
2082 | Indiana | KNOX |  | 08 | 0900539 | This project will improve sections and extend the life of Sixth Street Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/24/2009 | 11/30/2009 | 182744.9 | 2.9
2083 | Indiana | DAVIESS |  | 08 | 0900540 | This project will improve sections and extend the life of Cannelburt Rd in Daviess County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/18/2009 | 11/30/2009 | 313718.95 | 3.2
2084 | Indiana | GREENE |  | 08 | 0900541 | NW 11th St to NW 5th St | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 73414.61 | 0.175
2085 | Indiana | GIBSON |  | 08 | 0900542 | 12th St to Main St | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 135273.51 | 0.175
2086 | Indiana | GREENE |  | 08 | 0900543 | 5th St to 12th St | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 74716.16 | 0.175
2087 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0900545 | Kopp Lane from Hallmark Blvd to Eastern Blvd | Pavement Improvement | 11/23/2009 |  | 04/07/2010 | 132100 | 0.72
2088 | Indiana | SPENCER |  | 09 | 0900546 | This project will improve sections and extend the life of Old SR 245 with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 09/25/2009 | 11/30/2009 | 599693.29 | 3.89
2089 | Indiana | DAVIESS |  | 08 | 0900547 | This project will improve the traffic signs in Daviess County. | Safety/Traffic Management | 09/01/2009 | 01/18/2010 | 03/31/2010 | 321489 | 0.175
2090 | Indiana | PERRY |  | 09 | 0900548 | This project will improve sections and extend the life of French Ridge Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/14/2009 | 11/30/2009 | 481228.21 | 0.175
2091 | Indiana | PERRY |  | 09 | 0900549 | This project will improve sections and extend the life of Leopold Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/14/2009 | 11/30/2009 | 546226.63 | 0.175
2092 | Indiana | MARSHALL |  | 02 | 0900550 | This project will improve sections and extend the life of South Michigan St. in Marshall County with a pavement surface overlay | Pavement Improvement | 09/11/2009 |  | 07/02/2010 | 292820.96 | 0.175
2093 | Indiana | MARSHALL |  | 02 | 0900551 | This project will improve sections and extend the life of Miami Highway from SR 106 to the county line in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/02/2010 | 42123.04 | 0.175
2094 | Indiana | MARSHALL |  | 02 | 0900556 | This project will improve sections and extend the life of Monterey Rd with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/02/2010 | 36552.76 | 0.175
2095 | Indiana | CARROLL |  | 02 | 0900560 | This project will improve sections and extend the life of Road 600S with a pavement surface overlay. | Pavement Improvement | 09/15/2009 |  | 06/30/2010 | 558472.41 | 0.175
2096 | Indiana | CARROLL |  | 02 | 0900561 | This project will improve sections and extend the life of Road 75W in Carroll County with a pavement surface overlay. | Pavement Improvement | 10/14/2009 |  | 06/15/2010 | 318496.9 | 0.175
2097 | Indiana | CASS |  | 02 | 0900562 | This project will improve sections and extend the life of Road 700E with a pavement surface overlay. | Pavement Improvement | 09/01/2009 |  | 10/12/2009 | 712668.62 | 0.175
2098 | Indiana | CASS |  | 02 | 0900563 | This project will improve sections and extend the life of Road 400S in Cass County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 |  | 10/12/2009 | 53499.41 | 0.175
2099 | Indiana | CASS |  | 02 | 0900564 | This project will improve sections and extend the life of Road 200E in Cass County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 |  | 06/30/2010 | 330703.46 | 0.088
2100 | Indiana | SPENCER |  | 09 | 0900566 | This project will improve sections and extend the life of Old SR 45 in Spencen County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 09/25/2009 | 11/30/2009 | 407871.5 | 3.79
2101 | Indiana | SPENCER |  | 09 | 0900567 | This project will improve sections and extend the life of Fulda Shortcut Rd with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 09/25/2009 | 11/30/2009 | 226584.75 | 0.175
2102 | Indiana | SPENCER |  | 09 | 0900568 | This project will improve sections and extend the life of Road 800 E in Spencer County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 09/25/2009 | 11/30/2009 | 123631.15 | 2.28
2103 | Indiana | MONTGOMERY |  | 04 | 0900572 | This project will replace and restore the pavement on Nucor Road in Crawfordsville. | Pavement Improvement | 09/03/2009 | 08/03/2009 | 11/15/2009 | 602184.39 | 5.86
2104 | Indiana | GIBSON |  | 08 | 0900573 | This project will improve sections and extend the life of Road 350 E in Gibson County with a pavement surface overlay | Pavement Improvement | 09/01/2009 | 09/15/2009 | 11/30/2009 | 464003.49 | 5.3
2105 | Indiana | MONTGOMERY |  | 04 | 0900574 | This project will replace and restore the pavement on Old SR 55 in Wingate. | Pavement Improvement | 09/03/2009 | 08/03/2009 | 11/15/2009 | 971121.01 | 10.92
2106 | Indiana | GIBSON |  | 08 | 0900575 | This project will improve sections and extend the life of Road 550 E in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 11/30/2009 | 387540.92 | 5.55
2107 | Indiana | GIBSON |  | 08 | 0900576 | This project will improve sections and extend the life of Road 350 S in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 11/30/2009 | 256461.99 | 2.62
2108 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900577 | This project will improve sections and extend the life of CR 50 S/Old Boonville HWY in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/06/2009 | 11/30/2009 | 212289.34 | 0.175
2109 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900578 | This project will improve sections and extend the life of Road 350S/Vann Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/06/2009 | 11/30/2009 | 381551.82 | 0.175
2110 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900579 | This project will improve sections and extend the life of Road 25w/Yankeetown Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/06/2009 | 11/30/2009 | 61260.82 | 0.175
2111 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900580 | This project will improve sections and extend the life of Old SR 66 in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/06/2009 | 11/30/2009 | 142745.27 | 0.175
2112 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900581 | This project will improve sections and extend the life of CR 800N/Elberfeld Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/16/2009 | 11/30/2009 | 126314.6 | 0.175
2113 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900582 | This project will improve sections and extend the life of Rd 1100S/North Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/16/2009 | 11/30/2009 | 131432.9 | 0.175
2114 | Indiana | HENDRICKS | INDIANAPOLIS | 08 | 0900584 | US 40 - In Plainfield from the East end of the Bridge over White Lick Creek to Carr Rd | Pavement Improvement | 09/18/2009 | 10/05/2009 | 12/03/2010 | 2424872.04 | 1.03
2115 | Indiana | KNOX |  | 08 | 0900585 | This project will improve sections and extend the life of 2nd St in Knox County with a pavement surface overlay | Pavement Improvement | 09/15/2009 | 10/30/2009 | 11/30/2009 | 107323.67 | 0.175
2116 | Indiana | MADISON |  | 06 | 0900599 | This project will improve sections and extend the life of Old SR 132 in Madison County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 |  | 10/30/2009 | 341656.7 | 0.175
2117 | Indiana | MADISON |  | 06 | 0900605 | This project will restore the pavement on Madison County Road 600 W with a new surface course. | Pavement Improvement | 09/14/2009 |  | 10/30/2009 | 349703.94 | 0.175
2118 | Indiana | NOBLE |  | 03 | 0900606 | This project will improve sections and extend the life of Northport Rd. from SR 9 to Angling Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/23/2009 | 10/31/2009 | 321091.35 | 2.85
2119 | Indiana | MADISON |  | 06 | 0900607 | This project will improve sections and extend the life of Madison County Road 100E with a pavement surface overlay. | Pavement Improvement | 09/01/2009 |  | 10/30/2009 | 92540.86 | 1.08
2120 | Indiana | MADISON |  | 06 | 0900608 | This project will improve sections and extend the life of 8th St. in Madison County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 |  | 10/30/2009 | 289817.43 | 0.175
2121 | Indiana | SHELBY |  | 05 | 0900609 | This project will improve sections and extend the life of Shelby County Road 400E on the east side of Shelbyville with a pavement surface overlay. | Pavement Improvement | 09/01/2009 |  | 11/02/2009 | 744886.72 | 0.175
2122 | Indiana | PUTNAM |  | 08 | 0900610 | This project will replace and restore the pavement on Indiana Street in Greencastle. | Pavement Improvement | 09/01/2009 | 09/18/2009 | 11/15/2009 | 80137.74 | 0.275
2123 | Indiana | FOUNTAIN |  | 08 | 0900612 | This project will improve sections and extend the life of N Perry St in Fountain County with a pavement surface overlay | Pavement Improvement | 09/01/2009 | 09/29/2009 | 11/15/2009 | 260458.14 | 0.871
2124 | Indiana | HAMILTON |  | 05 | 0900613 | From SR 32 to SR 47 in Washington & Adams Townships IN | Pavement Improvement | 11/23/2009 |  | 05/28/2010 | 448756.77 | 0.114
2125 | Indiana | RUSH |  | 06 | 0900614 | This project will replace and restore the pavement on County Road 800E, from CR-100N to CR-1200N, in Rush County. | Pavement Improvement | 09/01/2009 |  | 10/30/2009 | 104581.1 | 0.111
2126 | Indiana | RUSH |  | 06 | 0900615 | This project will replace and restore the pavement on County Road 800E, from CR-600N to CR-900N, in Rush County. | Pavement Improvement | 09/01/2009 |  | 10/30/2009 | 264417.9 | 0.093
2127 | Indiana | HANCOCK |  | 05 | 0900616 | This project will replace and restore the pavement on County Road 1050E, from US-40 to SR-650N, in Hancock County. | Pavement Improvement | 09/01/2009 |  | 10/30/2009 | 442900.07 | 0.112
2128 | Indiana | HANCOCK |  | 06 | 0900617 | This project will replace and restore the pavement on County Road 600E, from US-40 to SR-234, in Hancock County. | Pavement Improvement | 09/01/2009 |  | 10/30/2009 | 574036.19 | 0.175
2129 | Indiana | LAWRENCE |  | 04 | 0900624 | This project will improve sections and extend the life of Main St/Hoosier Ave with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/19/2009 | 11/30/2009 | 258595.55 | 0.175
2130 | Indiana | SULLIVAN |  | 08 | 0900626 | This project will improve sections and extend the life of CR 925N/CR 450W/CR 1100 N with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/07/2009 | 11/30/2009 | 592129.09 | 8.54
2131 | Indiana | SULLIVAN |  | 08 | 0900628 | This project will improve sections and extend the life of Old US 41 in Sullivan County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/07/2009 | 11/30/2009 | 316081.29 | 4.2
2132 | Indiana | MADISON |  | 06 | 0900635 | This project will restore the pavement on Madison County Road 1100 N with a new surface course. | Pavement Improvement | 09/14/2009 |  | 10/30/2009 | 221464.13 | 0.175
2133 | Indiana | MADISON |  | 06 | 0900638 | This project will restore the pavement on Madison County Road 1100 N with a new surface course. | Pavement Improvement | 09/14/2009 |  | 10/30/2009 | 422516.94 | 0.175
2134 | Indiana | TIPTON |  | 05 | 0900642 | This project will improve sections and extend the life of Division Rd. from US 31 to SR 1 with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 10/30/2009 | 529938.85 | 0.175
2135 | Indiana | TIPTON |  | 05 | 0900643 | This project will improve sections and extend the life of South Ash St. from SR 28 to Railroad with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 10/30/2009 | 44947.05 | 0.175
2136 | Indiana | HOWARD |  | 05 | 0900647 | This project will improve sections and extend the life of Howard County Road 1350 East from CR 200 North to CR 400 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 177353.25 | 0.095
2137 | Indiana | HOWARD |  | 05 | 0900648 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 1000 East to County Road 1200 East with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 110474.26 | 0.175
2138 | Indiana | CARROLL |  | 02 | 0900650 | This project will improve sections and extend the life of Road 300 W in Carroll County with a pavement surface overlay. | Pavement Improvement | 10/14/2009 |  | 06/15/2010 | 127529.17 | 0.175
2139 | Indiana | CARROLL |  | 02 | 0900651 | This project will improve sections and extend the life of Bicycle Rd with a pavement surface overlay. | Pavement Improvement | 10/14/2009 |  | 06/15/2010 | 404434.58 | 0.175
2140 | Indiana | CARROLL |  | 02 | 0900652 | This project will improve sections and extend the life of Road 100N in Carroll County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 |  | 06/15/2010 | 18887.61 | 0.14
2141 | Indiana | CARROLL |  | 02 | 0900655 | This project will improve sections and extend the life of Road 700W in Carroll County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 |  | 06/15/2010 | 372426.95 | 0.175
2142 | Indiana | CARROLL |  | 02 | 0900656 | This project will improve sections and extend the life of Meridian Rd in Carroll County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 |  | 06/15/2010 | 355236.21 | 0.175
2143 | Indiana | CASS |  | 02 | 0900657 | This project will replace and restore the pavement on Loganspot Road, from Longtree to SR-1100E, in Cass County. | Pavement Improvement | 09/01/2009 |  | 10/12/2009 | 655281.41 | 0.175
2144 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900661 | 45th Avenue from Kennedy to Kleinman | Pavement Improvement | 01/20/2010 |  | 09/30/2010 | 340503.85 | 0.133
2145 | Indiana | MARSHALL |  | 02 | 0900671 | This project will improve sections and extend the life of 9A Road from city limits to SR 31 in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/06/2009 | 06/30/2010 | 98051.42 | 0.175
2146 | Indiana | MARSHALL |  | 02 | 0900672 | This project will improve sections and extend the life of Plymouth-Goshen Trail from city limits to Lilac Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/02/2010 | 21436.96 | 0.175
2147 | Indiana | HOWARD |  | 05 | 0900681 | This project will improve sections and extend the life of Howard County 850 East from County Road 200 North to County Road 400 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 115921.11 | 0.175
2148 | Indiana | HOWARD |  | 05 | 0900682 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 700 West to County Road 710 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 7795.4 | 0.175
2149 | Indiana | HOWARD |  | 05 | 0900683 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 750 West to County Road 800 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 27403.93 | 0.175
2150 | Indiana | HOWARD |  | 05 | 0900684 | This project will improve sections and extend the life of Howard County Road 1150W from CR 400 North to CR 600 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 101305.36 | 0.134
2151 | Indiana | HOWARD |  | 05 | 0900685 | This project will improve sections and extend the life of Howard County Road 750W from SR 22 to County Road 200 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 66850.74 | 0.175
2152 | Indiana | HOWARD |  | 05 | 0900686 | This project will improve sections and extend the life of Howard County Road 750W with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 130543.23 | 0.175
2153 | Indiana | HOWARD |  | 05 | 0900687 | This project will improve sections and extend the life of Howard County Road 750 West from County Road 220 South to Russiaville town limits with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 78336.75 | 0.175
2154 | Indiana | HOWARD |  | 05,04 | 0900688 | This project will improve sections and extend the life of Howard County Road 600 South from County Road 800 West to County Road 870 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 36345.43 | 0.091
2155 | Indiana | HOWARD |  | 05 | 0900689 | This project will improve sections and extend the life of Howard County Road 220 South from County Road 750 West to County Road 766 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 8010.89 | 0.175
2156 | Indiana | HOWARD |  | 05 | 0900690 | This project will improve sections and extend the life of Howard County Road 750 West from Russioville Town limits to County Road 500 South with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 38789.21 | 0.175
2157 | Indiana | HOWARD |  | 05 | 0900691 | This project will improve sections and extend the life of Howard County Road 250 South from from County Road 600 West to County Road 750 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 89909.8 | 0.175
2158 | Indiana | CLAY |  | 08 | 0900692 | This project will replace and restore the pavement on Bowling Green Poland Road, from SR-46 to SR-42, in Clay County. | Pavement Improvement | 09/01/2009 | 09/30/2009 | 11/15/2009 | 632977.1 | 0.175
2159 | Indiana | WARREN |  | 08 | 0900693 | This project will replace and restore the pavement on Monroe Street, from Franklin Street to South 3rd Street, in Warren County. | Pavement Improvement | 09/01/2009 | 09/22/2009 | 11/15/2009 | 324468.42 | 0.175
2160 | Indiana | VIGO | TERRE HAUTE | 08 | 0900694 | This project will replace and restore the pavement on Cotton Drive from Singhurst Street to SR-159, in Vigo County. | Pavement Improvement | 09/02/2009 | 10/15/2009 | 11/15/2009 | 207440.79 | 0.1
2161 | Indiana | VIGO | TERRE HAUTE | 08 | 0900695 | This project will replace and restore the pavement on Rio Grande Avenue, from Baldwin Street to Twin Beach Street, in Vigo County. | Pavement Improvement | 09/02/2009 | 10/15/2009 | 11/15/2009 | 224772.74 | 0.175
2162 | Indiana | PUTNAM |  | 08 | 0900696 | This project will improve sections and extend the life of Walnut Road from the West Greencastle City Limits to West County Line Road in Putnam County with a pavement surface overlay. | Pavement Improvement | 09/03/2009 | 09/22/2009 | 11/15/2009 | 925215 | 8
2163 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900697 | CR17 From 1000? North of CR18 to 1160? South of Verdant | Pavement Improvement | 12/16/2009 |  | 08/15/2010 | 224721.76 | 0.6
2164 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900698 | CR 17 from 900' N of Verdant to SR 120 | Pavement Improvement | 12/16/2009 |  | 08/15/2010 | 679008.2 | 1.8
2165 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900699 | CR 17 from CR 6 to CR 4 | Pavement Improvement | 12/16/2009 |  | 08/15/2010 | 281029.85 | 1
2166 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0900700 | CR 45 from Fenmore Ave to CR 13 | Pavement Improvement | 12/16/2009 |  | 08/15/2010 | 181664 | 2.1
2167 | Indiana | VIGO | TERRE HAUTE | 08 | 0900701 | This project will replace and restore the pavement on Rosedale Road, from Rio Grande Avenue to Lambert Street, in Vigo County. | Pavement Improvement | 09/02/2009 | 10/15/2009 | 11/15/2009 | 357154.43 | 0.175
2168 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0900702 | SR 3 from Water St. to Park St. | Transportation Enhancements | 12/31/2009 |  | 10/01/2010 | 630286.66 | 0.175
2169 | Indiana | VERMILLION |  | 08 | 0900704 | This project will replace and restore the pavement on Main Street, from 50' North of the RR tracks to North of the City limits, in Vermillion County. | Pavement Improvement | 09/11/2009 | 10/05/2009 | 11/15/2009 | 293482.42 | 0.175
2170 | Indiana | POSEY |  | 08 | 0900709 | SR 62 to Middle Mt Vernon Rd | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 203274.03 | 0.175
2171 | Indiana | POSEY |  | 08 | 0900710 | Creamery Rd to SR 66 | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 451941.97 | 4.9
2172 | Indiana | POSEY |  | 08 | 0900711 | This project will improve sections and extend the life of Springfield Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/30/2009 | 739556.75 | 0.175
2173 | Indiana | STARKE |  | 02 | 0900712 | This project will improve sections and extend the life of Road 210 in Starke County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/01/2009 | 11/07/2009 | 102677.15 | 0.175
2174 | Indiana | STARKE |  | 02 | 0900713 | This project will improve sections and extend the life of Road 625E in Starke County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/01/2009 | 11/07/2009 | 90035.31 | 0.175
2175 | Indiana | STARKE |  | 02 | 0900714 | This project will improve sections and extend the life of Toto Rd in Starke County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/01/2009 | 11/07/2009 | 603557.12 | 0.175
2176 | Indiana | NOBLE |  | 03 | 0900717 | This project will improve sections and extend the life of County Road 600West from US 6 to county road 1200 north in Noble County with a pavement surface overlay. | Pavement Improvement | 09/10/2009 | 09/16/2009 | 09/30/2009 | 138858.13 | 4.8
2177 | Indiana | NOBLE |  | 03 | 0900718 | This project will improve sections and extend the life of Baseline Road from SR 3 to county road 1200 East in Noble County with a pavement surface overlay. | Pavement Improvement | 09/10/2009 | 09/16/2009 | 09/30/2009 | 35086.24 | 1.5
2178 | Indiana | SHELBY |  | 06 | 0900720 | This project will improve the surface and rebuild sections of the bridge on County Road 900 South over Big Blue River in Shelby County. | Bridge Improvement | 09/15/2009 |  | 07/30/2010 | 60502.5 | 0.01
2179 | Indiana | BOONE |  | 04 | 0900721 | This project will improve sections and extend the life of Elizaville Road from the Lebanon City Limits to County Road 500 East in Boone County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/05/2009 | 11/15/2009 | 555712 | 6.5
2180 | Indiana | BOONE |  | 05,04 | 0900722 | This project will improve sections and extend the life of County Road 1200East from County Road 300 South to SR 32 in Boone County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/05/2009 | 11/15/2009 | 80727.75 | 0.082
2181 | Indiana | BOONE |  | 04 | 0900723 | This project will improve sections and extend the life of County Road 400East from County Road 300 South to SR 32 in Boone County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/05/2009 | 11/15/2009 | 256080.25 | 0.175
2182 | Indiana | BOONE |  | 04 | 0900724 | This project will improve sections and extend the life of County Road 25West from the Hendricks County Line to County Road 250 South in Boone County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/05/2009 | 11/15/2009 | 425591.25 | 0.175
2183 | Indiana | KNOX |  | 08 | 0900727 | This project will improve sections and extend the life of Bicknell-Oaktown Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/24/2009 | 11/30/2009 | 70534 | 1.28
2184 | Indiana | KNOX |  | 08 | 0900728 | This project will improve sections and extend the life of Hart Street Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/24/2009 | 11/30/2009 | 399262.8 | 5.37
2185 | Indiana | WARREN |  | 08 | 0900735 | This project will improve sections and extend the life of River Rd in Warren County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/15/2009 | 202252.88 | 1.5
2186 | Indiana | WARREN |  | 08 | 0900736 | This project will improve sections and extend the life of Independence Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/15/2009 | 540687.15 | 5.5
2187 | Indiana | WARREN |  | 08 | 0900737 | This project will improve sections and extend the life of Rd 300N in Warren County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/15/2009 | 1389785.32 | 15
2188 | Indiana | NOBLE |  | 03 | 0900738 | This project will improve sections and extend the life of Angling Road from Northport Road to Kendallville City Limits in Noble County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/03/2009 | 10/24/2009 | 315050.3 | 3
2189 | Indiana | CLINTON |  | 04 | 0900739 | From old SR 28 to Mulberry City limits | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 578218.02 | 0.175
2190 | Indiana | NOBLE |  | 03 | 0900740 | This project will improve sections and extend the life of Albion Road from US 33 to the Albion City Line in Noble County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/03/2009 | 10/24/2009 | 616326.97 | 7
2191 | Indiana | SHELBY |  | 06 | 0900741 | This project will improve the surface and rebuild sections of the bridge on County Road 900 South over Big Blue River in Shelby County. | Bridge Improvement | 09/15/2009 |  | 07/30/2010 | 42424.5 | 0.01
2192 | Indiana | CLINTON |  | 04 | 0900742 | From SR 38 to Kelly Rd | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 274643.69 | 0.175
2193 | Indiana | CLINTON |  | 04 | 0900743 | From CR 100 N to CR 600 N | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 415432.94 | 0.175
2194 | Indiana | JACKSON |  | 09 | 0900771 | CR 150 N/100 N/50N from SR 11 to US 50 | Pavement Improvement | 10/14/2009 | 10/22/2009 | 11/15/2009 | 333568.5 | 0.175
2195 | Indiana | POSEY |  | 08 | 0900778 | This project will improve sections and extend the life of Lower New Harmony Rd with a pavement surface overlay. | Other | 09/01/2009 | 09/25/2009 | 11/30/2009 | 24773.9 | 0.175
2196 | Indiana | POSEY |  | 08 | 0900779 | This project will improve sections and extend the life of O'Donnel Rd/Brittle Bank Rd in Posey County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/30/2009 | 108116.7 | 0.175
2197 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900780 | Co Road 30 - Basher Road from Reliance Rd to US 33 | Pavement Improvement | 11/30/2009 |  | 08/06/2010 | 187317.05 | 1.48
2198 | Indiana | POSEY |  | 08 | 0900781 | This project will improve sections and extend the life of Main street (Old SR 69) with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/30/2009 | 10641.65 | 0.175
2199 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900782 | 8th Street from College Avenue to Lincoln Avenue | Pavement Improvement | 11/30/2009 |  | 08/06/2010 | 229199.95 | 1.41
2200 | Indiana | GIBSON |  | 08 | 0900783 | This project will improve sections and extend the life of Embree St in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 09/30/2009 | 170746.89 | 0.175
2201 | Indiana | GIBSON |  | 08 | 0900784 | This project will improve sections and extend the life of Makemson Ave in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 09/30/2009 | 22020.38 | 0.175
2202 | Indiana | GIBSON |  | 08 | 0900785 | This project will improve sections and extend the life of Seminary St in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 09/30/2009 | 45179.56 | 0.175
2203 | Indiana | GREENE |  | 08 | 0900794 | 5th Street to 4th Street | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 63261.55 | 0.175
2204 | Indiana | RUSH |  | 06 | 0900797 | This project will improve sections and extend the life of County Road 715West from SR 44 to BAse Road in Rush County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 |  | 11/14/2009 | 164124.2 | 0.175
2205 | Indiana | FAYETTE |  | 06 | 0900799 | This project will improve sections and extend the life of Veterans Memorial Highway from SR 121 to SR 1 in Fayette County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 10/14/2009 | 11/13/2009 | 100000 | 0.175
2206 | Indiana | KOSCIUSKO |  | 03 | 0900802 | This project will improve sections and extend the life of "OLD 30" from West County Line to 350West in Kosciusko County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 10/07/2009 | 07/16/2010 | 675733.42 | 8
2207 | Indiana | KOSCIUSKO |  | 03 | 0900803 | This project will improve sections and extend the life of "OLD 30" from US 30 to East County Line in Kosciusko County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 10/07/2009 | 07/16/2010 | 817838.69 | 8
2208 | Indiana | DUBOIS |  | 09 | 0900825 | This project will improve sections and extend the life of Jasper-Dubois Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 12/03/2009 | 748081.44 | 0.175
2209 | Indiana | DUBOIS |  | 09 | 0900826 | This project will improve sections and extend the life of Rd 1100S in Dubois County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 12/03/2009 | 439834.62 | 0.175
2210 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900840 | Oak Hill Road from US 20 to SR 49 | Pavement Improvement | 12/16/2009 |  | 05/28/2010 | 235996.35 | 0.175
2211 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900841 | Waverly Road from I-94 bridge abutment to US 12 | Pavement Improvement | 12/16/2009 |  | 05/28/2010 | 242080.22 | 0.175
2212 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900851 | Samuelson Road from 750 ft. South of Indiana Toll Road to Portage Avenue | Pavement Improvement | 01/15/2010 |  | 06/01/2010 | 171263.18 | 0.175
2213 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900852 | Central Avenue from Bridge over Willowcreek to Elm Street | Pavement Improvement | 01/15/2010 |  | 06/01/2010 | 168606.42 | 0.175
2214 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900853 | Swanson Road from CR 700N to US 6 | Pavement Improvement | 01/15/2010 |  | 06/01/2010 | 248224.22 | 0.094
2215 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900864 | Twyckenham Drive from Rockne Drive to South Bend Avenue (SR 23) | Pavement Improvement | 10/21/2009 |  | 07/15/2010 | 174928.66 | 0.175
2216 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900865 | Western Avenue from Walnut Street to Chapin Street | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 238542.75 | 0.126
2217 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900866 | McKinley Avenue from 500ft East of Ironwood Drive to Preston Drive | Pavement Improvement | 10/21/2009 |  | 07/15/2010 | 145765.73 | 0.175
2218 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900867 | Western Avenue from Lombardy Drive to Albert Avenue | Pavement Improvement | 10/21/2009 |  | 07/15/2010 | 114693.34 | 0.175
2219 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900868 | Edison Road from Ironwood Drive to Hickory Road | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 229667.43 | 0.121
2220 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900869 | Ireland Road from East of Miami Street to Ironwood Drive | Pavement Improvement | 10/21/2009 |  | 07/15/2010 | 222483.43 | 0.175
2221 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900870 | Portage Avenue from 370' N of Cleveland Road to Appaloosa Lane | Pavement Improvement | 10/21/2009 |  | 07/15/2010 | 86365.36 | 0.175
2222 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900871 | Ireland Road from St. Joseph Street to High Street | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 128937.28 | 0.175
2223 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900872 | Portage Avenue from Elwood Avenue to Lathrop Street | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 241847.6 | 0.11
2224 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900873 | Lincolnway W from Chapin Street to Olive Street | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 391219.1 | 0.175
2225 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900874 | Main Street from Chippewa Street to Sample Street | Pavement Improvement | 10/21/2009 |  | 07/15/2010 | 414615.95 | 0.098
2226 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0900890 | County Road 10 - John Weaver Parkway from CR 10 to CR 6 | Pavement Improvement | 01/21/2010 |  | 08/31/2010 | 446450.07 | 2.25
2227 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0900891 | Beardsley Ave from Nappanee St to 100' W of Beech St | Pavement Improvement | 01/21/2010 |  | 08/31/2010 | 51145.43 | 1.19
2228 | Indiana | OHIO |  | 09 | 0900897 | Cass Union Rd from Aberdeen Rd/SR 56 to SR 262 | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 447225.64 | 0.175
2229 | Indiana | OHIO |  | 09 | 0900898 | Hartford pike from Woods Ridge Road to Nelson Road | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 207500.5 | 1.7
2230 | Indiana | OHIO |  | 09 | 0900899 | Nelson Rd from Hartford Pike to Rising Sun Limits | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 617406.24 | 3.7
2231 | Indiana | MORGAN |  | 04 | 0900900 | This project will improve sections and extend the life of Centenary Rd. from Henderson Ford Road to 1 mile South of SR 144 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 305233.77 | 0.175
2232 | Indiana | MORGAN |  | 04 | 0900901 | This project will improve sections and extend the life of old SR 37 from Martinsville City Limits to SR 37 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 128201.09 | 0.175
2233 | Indiana | MORGAN |  | 04 | 0900902 | This project will improve sections and extend the life of Paragon Rd. from SR 67 to SR 37 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 292973.31 | 0.175
2234 | Indiana | WELLS |  | 06 | 0900904 | Lancaster St from Adams St to Bond St | Pavement Improvement | 10/14/2009 | 11/11/2009 | 06/12/2010 | 62063.86 | 1
2235 | Indiana | WELLS |  | 06 | 0900905 | Western Ave from Decker Dr to Midway St | Pavement Improvement | 10/14/2009 | 11/11/2009 | 06/12/2010 | 40637.19 | 0.4
2236 | Indiana | WELLS |  | 06 | 0900906 | Midway St from Western Ave to W Washington St | Pavement Improvement | 10/14/2009 | 11/11/2009 | 06/12/2010 | 126493.84 | 0.25
2237 | Indiana | MORGAN |  | 04 | 0900916 | This project will improve sections and extend the life of Rueben Dr. from Old SR 37 to SR 37 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 38600.04 | 0.175
2238 | Indiana | MORGAN |  | 04 | 0900917 | This project will improve sections and extend the life of Rob Hill Rd fROM SR 39 TO SR 67 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 259679.04 | 0.175
2239 | Indiana | MORGAN |  | 04 | 0900918 | This project will improve sections and extend the life of Blue Bluff Rd. from Centerton Rd. to Bridge with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 106946.28 | 0.175
2240 | Indiana | JENNINGS |  | 09 | 0900935 | This project will improve sections and extend the life of Greensburg Street from US 50 to Woodlaen Drive in Jennings County with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 07/15/2010 | 64497.6 | 0.44
2241 | Indiana | JEFFERSON |  | 09 | 0900941 | This project will improve sections and extend the life of Michigan Road from West Street to Green Road in Jefferson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 11/15/2009 | 209462.83 | 0.175
2242 | Indiana | CASS |  | 02 | 0900944 | This project will improve the traffic signs in the town of Galveston in Cass County. | Safety/Traffic Management | 09/15/2009 | 10/26/2009 | 11/30/2009 | 45256.42 | 0.175
2243 | Indiana | CASS |  | 02 | 0900945 | This project will improve the traffic signs in the town of Royal Center in Cass County. | Safety/Traffic Management | 09/15/2009 | 10/26/2009 | 11/30/2009 | 6202.99 | 0.175
2244 | Indiana | CASS |  | 02 | 0900946 | This project will improve the traffic signs in the town of Walton in Cass County. | Safety/Traffic Management | 09/15/2009 | 10/26/2009 | 11/30/2009 | 12247.47 | 0.175
2245 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900948 | This project will improve sections and extend the life of Patterson Rd from Watkins St to Kenilworth Rd with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 74686.15 | 0.175
2246 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900949 | This project will improve sections and extend the life of Beech Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 79231.77 | 0.175
2247 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900950 | This project will improve sections and extend the life of Timothy Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 53897.15 | 0.175
2248 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900952 | This project will improve sections and extend the life of Tamarach Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 396092.45 | 0.175
2249 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900953 | This project will improve sections and extend the life of Kern Rd in St Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 170869.44 | 0.175
2250 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900954 | This project will improve sections and extend the life of Oak Rd from New Rd to Roosevelt Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 195944.75 | 0.175
2251 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900955 | This project will improve sections and extend the life of Walkerton Trail from 0.01 MI S of Georgia St to 0.1 MI S of SR 23 with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 95534.15 | 0.175
2252 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900956 | This project will improve sections and extend the life of Main St in Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 30644.32 | 0.175
2253 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900957 | This project will improve sections and extend the life of Washington St in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 24899.42 | 0.175
2254 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900958 | This project will improve sections and extend the life of Patterson Rd from 0.04 MI E of Beeckler Court to Watkins St with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 21998.43 | 0.175
2255 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900959 | This project will improve sections and extend the life of Walkerton Trail from Spruce Rd to 0.1 MI S of Georgia St with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 132570.87 | 0.175
2256 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900960 | This project will improve sections and extend the life of Mayflower Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 26719.91 | 0.175
2257 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900961 | This project will improve sections and extend the life of Sumption Trail in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 46175.6 | 0.175
2258 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900962 | This project will improve sections and extend the life of Oak Rd from Roosevelt Rd to Kern Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 56716.64 | 1
2259 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900963 | This project will improve sections and extend the life of Beech Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 149295.99 | 0.175
2260 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900964 | This project will improve traffic signs in Walkerton in St Joseph County. | Safety/Traffic Management | 09/15/2009 |  | 06/30/2010 | 50414.87 | 0
2261 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900965 | This project will improve the traffic signs in North Liberty in St Joseph County. | Safety/Traffic Management | 09/15/2009 |  | 06/30/2010 | 38045.14 | 0.175
2262 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900966 | This project will improve the signs in New Carlisle in St Joseph County. | Safety/Traffic Management | 09/15/2009 |  | 06/30/2010 | 48885.14 | 0.175
2263 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900967 | This project will improve the traffic signs in Lakeville in St Joseph County. | Safety/Traffic Management | 09/15/2009 |  | 06/30/2010 | 31455.85 | 0.175
2264 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900968 | This project will improve the traffic signs in St Joseph County. | Safety/Traffic Management | 09/15/2009 |  | 06/30/2010 | 152149.03 | 0.175
2265 | Indiana | PIKE |  | 08 | 0900982 | E Old SR 64 - SR 257 to CR 1100E | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 250364.52 | 0.175
2266 | Indiana | PIKE |  | 08 | 0900983 | CR 500E to SR 257 | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 105812.74 | 0.175
2267 | Indiana | PERRY |  | 09 | 0900987 | Tell City Riverfront, 1,800' S Washington St to 3,400'N of the plaza | Transportation Enhancements | 12/18/2009 |  | 08/31/2010 | 434981.44 | 0.155
2268 | Indiana | DE KALB |  | 03 | 0900988 | This project will improve sections and extend the life of Dekalb County Road 48 with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/06/2009 | 10/31/2010 | 256193.6 | 1.6
2269 | Indiana | DE KALB |  | 03 | 0900993 | This project will improve sections and extend the life of Wayne Street from Cedar Street to Walnut Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 10/02/2009 | 146655.49 | 0.77
2270 | Indiana | MARION | INDIANAPOLIS | 07 | 0900994 | Arlington Ave. from 38th St. to 56th St. | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 1624100 | 0.175
2271 | Indiana | DE KALB |  | 03 | 0900996 | This project will improve sections and extend the life of N. Commerce Drive in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 10/02/2009 | 38650.93 | 0.21
2272 | Indiana | DE KALB |  | 03 | 0900997 | This project will improve sections and extend the life of Center Street from US 6 to Rope Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 10/02/2009 | 52189.49 | 0.48
2273 | Indiana | DE KALB |  | 03 | 0900998 | This project will improve sections and extend the life of Rope Street from Center Street to SR 427 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 10/02/2009 | 74286.14 | 0.47
2274 | Indiana | DE KALB |  | 03 | 0900999 | This project will improve sections and extend the life of Walnut Street from Albright Street to SR 39 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 10/02/2009 | 44769.41 | 0.25
2275 | Indiana | DE KALB |  | 03 | 0901000 | This project will improve sections and extend the life of Walnut Street from Center Street to Wayne Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 10/02/2009 | 46943.69 | 0.25
2276 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901004 | Colfax Street from Belshaw Road to 231st Avenue | Pavement Improvement | 12/16/2009 |  | 06/04/2010 | 601455.81 | 0.175
2277 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901005 | 231st Avenue from Monon Road to Colfax Street | Pavement Improvement | 12/16/2009 |  | 06/04/2010 | 297920.24 | 0.175
2278 | Indiana | HOWARD |  | 05 | 0901023 | This project will improve sections and extend the life of County Road 400North from County Road 850 East to County Road 900 East in Howard County with a pavement surface overlay. | Transportation Enhancements | 09/14/2009 | 09/24/2009 | 11/13/2009 | 42341.78 | 0.175
2279 | Indiana | PERRY |  | 09 | 0901024 | Gerald Rd (CR 10) to SR 70 | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 376584 | 0.175
2280 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901026 | This project will improve sections and extend the life of New Market Road from SR 3 to Zimmerman Road in Clark County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/29/2009 | 04/30/2010 | 207472.61 | 0.175
2281 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901027 | This project will improve sections and extend the life of Camp Creek-Bethlehem Road from Flint Road to Bethlehem New Washington in Clark County with a pavement surface overlay. | Pavement Improvement | 08/20/2009 | 09/29/2009 | 11/13/2009 | 202814.25 | 0.175
2282 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901029 | This project will improve sections and extend the life of Charlestown-Memphis Road from US 31 to SR 160 in Clark County with a pavement surface overlay. | Pavement Improvement | 10/09/2009 | 10/30/2000 | 05/14/2010 | 318500 | 0.153
2283 | Indiana | HOWARD |  | 05 | 0901030 | This project will improve sections and extend the life of County Road 750West from County Road 300 North to County Road 400 North in Howard County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 65574.31 | 0.175
2284 | Indiana | HOWARD |  | 05 | 0901031 | This project will improve sections and extend the life of County Road 100North from County Road 400 East to County Road 500 East in Howard County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 75481.89 | 0.175
2285 | Indiana | WAYNE |  | 06 | 0901036 | This project will improve sections and extend the life of Salisbury Road from Nolands Fork Road to Williamsburg Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/13/2009 | 163791.8 | 0.65
2286 | Indiana | WAYNE |  | 06 | 0901037 | This project will improve sections and extend the life of 37th Street from Hodgin Road to US 40 in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/20/2009 | 555942.75 | 1.14
2287 | Indiana | WAYNE |  | 06 | 0901038 | This project will improve sections and extend the life of Industries Road from Williamsburg Pike to Union Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/06/2009 | 228158.88 | 0.61
2288 | Indiana | FULTON |  | 02 | 0901039 | This project will improve sections and extend the life of Southway 31 in Fulton County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 11/25/2009 | 115530.27 | 0.175
2289 | Indiana | FULTON |  | 02 | 0901040 | Old US 31 N from CR 350N to SR 110 | Pavement Improvement | 10/14/2009 |  | 06/30/2010 | 449932.91 | 0.175
2290 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901041 | Greenwood Avenue between SR 231 and SR 55 | Pavement Improvement | 12/16/2009 |  | 06/01/2010 | 262655.46 | 0.175
2291 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901042 | Court Street from the North side of Town Square to 121st. Street | Pavement Improvement | 12/16/2009 |  | 06/01/2010 | 426397.65 | 0.175
2292 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901043 | 49th Avenue from Broadway to Grant | Pavement Improvement | 12/16/2009 |  | 06/01/2010 | 340184.95 | 0.175
2293 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901044 | 15th Avenue from I-65 to Martin Luther King Drive | Pavement Improvement | 12/16/2009 |  | 06/01/2010 | 249105.94 | 0.097
2294 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901045 | 35th Avenue from Broadway to Martin Luther King Drive | Pavement Improvement | 12/16/2009 |  | 06/01/2010 | 422672.03 | 0.175
2295 | Indiana | FULTON |  | 02 | 0901046 | Olson Road from CR 700 W to SR 17 | Pavement Improvement | 10/14/2009 |  | 06/30/2010 | 206332.77 | 0.175
2296 | Indiana | FULTON |  | 02 | 0901047 | This project will improve sections and extend the life of Wabash Ave with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 11/25/2009 | 108235.99 | 0.175
2297 | Indiana | FULTON |  | 02 | 0901048 | CR 550 S from CR 1200 W(Fulton/Pulaski Co Line) to SR 17 | Pavement Improvement | 10/14/2009 |  | 06/30/2010 | 167279.28 | 0.175
2298 | Indiana | FULTON |  | 02 | 0901049 | CR 600 S from SR 25 to CR 250 E | Pavement Improvement | 10/14/2009 |  | 06/30/2010 | 163888.4 | 0.175
2299 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901050 | This project will improve sections and extend the life of Engle Road from St John Road to Floyd County in Clark County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/27/2009 | 04/30/2010 | 115250 | 0.175
2300 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901051 | Hibernia Rd from SR 62 to Charlestown Bethlehem Rd | Pavement Improvement | 10/13/2009 | 10/20/2009 | 11/13/2009 | 108251.32 | 0.175
2301 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901052 | This project will improve sections and extend the life of Marble Hill Road from SR 62 to Gill Road in Clark County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/29/2009 | 04/30/2010 | 145544.3 | 1.72
2302 | Indiana | JEFFERSON |  | 09 | 0901057 | Old State Rd 62 from US 421 to SR 62 | Pavement Improvement | 10/13/2009 | 10/23/2009 | 11/15/2009 | 174705.63 | 0.175
2303 | Indiana | RUSH |  | 06 | 0901059 | Main Street from CR 800 to the RR Tracks at the town limit | Pavement Improvement | 10/13/2009 |  | 06/25/2010 | 357838.25 | 0.175
2304 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901062 | This project will improve sections and extend the life of Martinsburg Knob Road from Borden Greenville Road to Washington County in Clark County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/08/2009 | 11/13/2009 | 197357.5 | 0.175
2305 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901063 | This project will improve sections and extend the life of New Hope Church Road from Bethlehem Road to Jefferson County in Clark County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/29/2009 | 04/30/2010 | 88011 | 0.175
2306 | Indiana | GRANT |  | 05 | 0901065 | 38th Street from 460 feet E of Adams Street/SR 15 to S Todd Street | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 577282.65 | 1.68
2307 | Indiana | GRANT |  | 05 | 0901066 | Adams Street from 29th street to 26th street | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 88190.74 | 0.35
2308 | Indiana | GRANT |  | 05 | 0901067 | Nebraska Street from 26th Street to 23rd Street | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 452198.49 | 1.48
2309 | Indiana | JACKSON |  | 05 | 0901068 | Adams Street from Railroad Tracks S of 11th Street to 3rd Street | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 216308.82 | 0.58
2310 | Indiana | GRANT |  | 05 | 0901069 | Adams Street from Railroad Tracks S of 11th Street to 3rd Street | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 969607.16 | 2.67
2311 | Indiana | GRANT |  | 05 | 0901070 | This project will improve sections and extend the life of Kem Road from Miller Avenue to Wabash Avenue in Grant County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/13/2009 | 11/14/2009 | 242274.3 | 1.03
2312 | Indiana | MARION | INDIANAPOLIS | 07 | 0901071 | Allisonville Rd from Fall Creek Rd to 46th St | Pavement Improvement | 11/24/2009 |  | 06/30/2010 | 258971.27 | 0.175
2313 | Indiana | MARION | INDIANAPOLIS | 07 | 0901072 | 62nd St from Keystone Ave to Allisonville Rd | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 526400 | 0.175
2314 | Indiana | MONROE | BLOOMINGTON | 09 | 0901074 | Old SR 37 S, from SR 37 to Rogers Street | Pavement Improvement | 12/16/2009 |  | 07/30/2010 | 199360.86 | 0.136
2315 | Indiana | MONROE | BLOOMINGTON | 09 | 0901076 | Old SR 37 N, from Whisnand Rd to Wylie Rd | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 347214.07 | 0.175
2316 | Indiana | MONROE | BLOOMINGTON | 09 | 0901077 | Monroe Dam Rd, from SR 37 to Strain Ridge Rd | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 120024.61 | 0.175
2317 | Indiana | MONROE | BLOOMINGTON | 04 | 0901078 | Rockport Road from Victor Pike to May Rd | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 400239.05 | 0.175
2318 | Indiana | MONROE | BLOOMINGTON | 09 | 0901079 | Fairfax Road, from Pointe Rd to Dillman Rd | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 753438.27 | 0.175
2319 | Indiana | MARION | INDIANAPOLIS | 07 | 0901082 | Emerson Ave from 38th St to 56th St | Pavement Improvement | 11/23/2009 |  | 09/30/2010 | 1474042 | 0.175
2320 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901084 | Georgetown-Greenville Road from Church Rd to Harrison St | Pavement Improvement | 11/25/2009 |  | 06/12/2010 | 370200 | 6.5
2321 | Indiana | GRANT |  | 05 | 0901086 | This project will improve sections and extend the life of Garthwaite Road in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 116456.26 | 1.12
2322 | Indiana | GRANT |  | 05 | 0901087 | This project will improve sections and extend the life of County Road 300South from County Road 300 West to SR 37 in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 216593.63 | 3
2323 | Indiana | GRANT |  | 05 | 0901088 | This project will improve sections and extend the life of County Road 600East from SR 18 to County Road 700 North in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 521793.49 | 6.76
2324 | Indiana | GRANT |  | 05 | 0901089 | This project will improve sections and extend the life of County Road 200North from County Road 300 East to County Road 600 East in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 235982.37 | 3
2325 | Indiana | GRANT |  | 05 | 0901090 | This project will improve sections and extend the life of County Road 400East from Walnut Creek to County Road 200 South in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 75507.03 | 1.5
2326 | Indiana | GRANT |  | 05 | 0901091 | This project will improve sections and extend the life of County Road 950East from Matthews Town Limits to SR 26 in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 225619.87 | 2.27
2327 | Indiana | MARSHALL |  | 02 | 0901093 | This project will improve sections and extend the life of Olive Trail from 13th Road to Overmyer Drive in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 07/02/2010 | 66651.01 | 0.175
2328 | Indiana | BLACKFORD |  | 06 | 0901096 | This project will improve sections and extend the life of Wabash Avenue from Kickapoo Street to Park Avenue in Blackford County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/22/2009 | 10/30/2009 | 74602.69 | 0.3
2329 | Indiana | DE KALB |  | 03 | 0901097 | This project will improve sections and extend the life of County Road 40 from SR 1 to State Line in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/01/2009 | 11/05/2009 | 275134.74 | 3.4
2330 | Indiana | DE KALB |  | 03 | 0901098 | This project will improve sections and extend the life of Auburn Drive from Diehl Drive to Wayne Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/06/2009 | 11/05/2009 | 178013.07 | 1.42
2331 | Indiana | DE KALB |  | 03 | 0901099 | This project will improve sections and extend the life of Main Street from Gates Cove to County Road 36 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/06/2009 | 11/05/2009 | 172398.79 | 1.42
2332 | Indiana | HENDRICKS | INDIANAPOLIS | 04 | 0901100 | From 2500 N. Dan Jones to approx. 3000 S. Dan Jones Rd. | Pavement Improvement | 12/16/2009 |  | 05/01/2010 | 1094800 | 0.175
2333 | Indiana | HENDRICKS | INDIANAPOLIS | 04 | 0901101 | CR 200 N & Ronald Reagan Pkwy | Safety/Traffic Management | 10/23/2009 | 11/16/2009 | 06/30/2010 | 169869.75 | 0.01
2334 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901102 | From Wiggins St. to just south of Robinison St. | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 272515.74 | 0.53
2335 | Indiana | MARION | INDIANAPOLIS | 07 | 0901110 | Emerson Ave. over CSX Railroad | Bridge Improvement | 12/30/2009 |  | 07/31/2010 | 435104.95 | 0.175
2336 | Indiana | DAVIESS |  | 08 | 0901122 | NW 21st St to Front St | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 72134.34 | 0.175
2337 | Indiana | DAVIESS |  | 08 | 0901123 | US 50 to W Main St | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 44729.41 | 0.175
2338 | Indiana | DAVIESS |  | 08 | 0901124 | Jackson St to Wykoff Ln | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 39902.85 | 0.175
2339 | Indiana | DAVIESS |  | 08 | 0901125 | Field Ave to NW 21st St | Pavement Improvement | 12/16/2009 |  | 08/31/2010 | 45053.65 | 0.175
2340 | Indiana | SCOTT |  | 09 | 0901126 | Leota Rd from Boatman Rd to US 31 | Pavement Improvement | 11/23/2009 |  | 05/31/2010 | 180744.65 | 0.175
2341 | Indiana | MARION | INDIANAPOLIS | 07 | 0901128 | Westfield Blvd. over White River | Bridge Improvement | 12/30/2009 |  | 07/31/2010 | 344463.55 | 0.175
2342 | Indiana | WASHINGTON |  | 09 | 0901130 | Washington Blvd from Mulberry St. to Market St. | Pavement Improvement | 10/30/2009 | 11/02/2009 | 11/30/2009 | 77747.61 | 0.7
2343 | Indiana | MARION | INDIANAPOLIS | 07 | 0901133 | Southeastern Ave. from Raymond St. to Sheridan Ave. | Pavement Improvement | 11/23/2009 |  | 10/04/2010 | 1245788.95 | 0.175
2344 | Indiana | PULASKI |  | 02 | 0901139 | This project will improve sections and extend the life of County Road 500S outh from Market Street to county road 1050 west in Pulaski County with a pavement surface overlay. | Pavement Improvement | 12/31/2009 |  | 08/27/2010 | 109841.57 | 0.175
2345 | Indiana | WASHINGTON |  | 09 | 0901145 | SR 135 - Market St. from Washington Blvd to Alpine St. | Pavement Improvement | 10/30/2009 | 11/02/2009 | 11/30/2009 | 196150.23 | 0.175
2346 | Indiana | MARION | INDIANAPOLIS | 07 | 0901148 | Raymond St. from Shelby St. to Southeastern Ave. | Pavement Improvement | 11/23/2009 |  | 10/04/2010 | 2782134.53 | 0.175
2347 | Indiana | MARION | INDIANAPOLIS | 07 | 0901149 | Holt Rd. bridge over Big Eagle Creek | Bridge Improvement | 12/03/2009 |  | 09/30/2010 | 830749.22 | 0.175
2348 | Indiana | MARION | INDIANAPOLIS | 07 | 0901151 | Franklin Way/Rd. from 21st St. to 30th St. | Pavement Improvement | 11/23/2009 |  | 10/04/2010 | 452726.52 | 0.175
2349 | Indiana | MARION | INDIANAPOLIS | 05 | 0901153 | Walnut St. from Southport Rd. to Stop 10 Rd. | Pavement Improvement | 01/13/2010 |  | 08/16/2010 | 161969.95 | 0.175
2350 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901154 | Lantern Rd. from South St. to Lantern Wood Dr. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 155669.11 | 0.175
2351 | Indiana | WABASH |  | 05 | 0901155 | This project will improve sections and extend the life of County Road 250South from Old Sr 15 to America Road in Wabash County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 |  | 06/18/2010 | 441936.72 | 4.94
2352 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901156 | Hague Rd. from 96th St. to 116th St. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 253137.68 | 0.175
2353 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901157 | Cumberland Rd. from 121st St. to 141st St. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 232563.46 | 0.175
2354 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901159 | Cumberland Rd. from 106th St. to High Point Ridge | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 146668.9 | 0.175
2355 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901160 | Brooks School Rd. from 96th St. to 116th St. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 171114.89 | 0.175
2356 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901162 | 106th St. from Hague Rd. to Cumberland Rd. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 301042.97 | 0.175
2357 | Indiana | MARION | INDIANAPOLIS | 05 | 0901165 | 75th St.-Pennsyl. St. to College Ave. & sign repl. fr. Spring Mill to College Av | Pavement Improvement | 12/16/2009 |  | 06/01/2010 | 91196 | 0.092
2358 | Indiana | BLACKFORD |  | 06 | 0901166 | This project will improve sections and extend the life of Park Avenue from Gilkey Ave to Mill Street in Blackford County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 11/03/2009 | 05/29/2010 | 143863.5 | 1.5
2359 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901168 | Greensburg Rd. from 510 East to 450 East | Pavement Improvement | 12/16/2009 |  | 05/14/2010 | 132351.64 | 0.8
2360 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901169 | Morgantown Rd. from CR 600N to Fairview Rd. | Pavement Improvement | 12/16/2009 |  | 05/14/2010 | 307166.76 | 0.175
2361 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901170 | CR 144 from CR 500N to Bargersville City limits | Pavement Improvement | 12/16/2009 |  | 05/14/2010 | 215411.45 | 0.175
2362 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901171 | County Road 800 N - Olive Branch Rd. from 400 West to SR 135 | Pavement Improvement | 12/16/2009 |  | 05/14/2010 | 95598.96 | 0.175
2363 | Indiana | MORGAN | INDIANAPOLIS | 04 | 0901172 | Mann Rd. from Landersdale Rd. to the Marion County line | Pavement Improvement | 12/31/2009 |  | 08/30/2010 | 127283 | 0.175
2364 | Indiana | DELAWARE | MUNCIE | 03 | 0901173 | McGallliard Rd. from Wheeling Ave. to Riverside Ave. | Pavement Improvement | 11/23/2009 |  | 10/01/2010 | 896177.84 | 0.101
2365 | Indiana | DELAWARE | MUNCIE | 06 | 0901174 | Tillotson Ave from Riverside Ave to SR 332/McGalliard Rd | Pavement Improvement | 11/23/2009 |  | 10/01/2010 | 801336.17 | 1.3
2366 | Indiana | WAYNE |  | 06 | 0901175 | This project will improve sections and extend the life of Kepler Road from Jacksonburg Road to Washington Road in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/06/2009 | 255829.91 | 0.175
2367 | Indiana | WAYNE |  | 06 | 0901176 | This project will improve sections and extend the life of Pottershop Road from Abington to US 27 in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/23/2009 | 10/23/2009 | 67385.5 | 0.16
2368 | Indiana | WAYNE |  | 06 | 0901177 | SR 38 - Centerville Road (S-8189) from SR 38 to We Oler Road | Pavement Improvement | 11/18/2009 |  | 06/04/2010 | 574791.59 | 4.44
2369 | Indiana | WAYNE |  | 06 | 0901178 | This project will improve sections and extend the life of Jacksonburg Road from Swoveland Road to SR 38 in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/23/2009 | 11/13/2009 | 162990 | 0.121
2370 | Indiana | WAYNE |  | 06 | 0901179 | This project will improve sections and extend the life of Pottershop Road from Pennville Road to Abington in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 06/04/2010 | 70100 | 0.27
2371 | Indiana | WAYNE |  | 06 | 0901180 | This project will improve sections and extend the life of Pennville Road from Fayette County line to US 40 in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/06/2009 | 848176.55 | 0.175
2372 | Indiana | WAYNE |  | 06 | 0901181 | This project will improve sections and extend the life of Centerville Road from I-70 to SR 38 with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/12/2009 | 11/13/2009 | 221065 | 1.52
2373 | Indiana | WAYNE |  | 06 | 0901182 | This project will improve sections and extend the life of South L Street in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/25/2009 | 736150 | 1.52
2374 | Indiana | HANCOCK |  | 05 | 0901188 | I 70 - 5.75 mi W of SR 9 | Bridge Improvement | 10/09/2009 |  | 08/13/2010 | 469280 | 0.175
2375 | Indiana | DE KALB |  | 03 | 0901201 | This project will replace existing sidewalks and place new sidewalks in St. Joe, Indiana . | Safety/Traffic Management | 09/15/2009 |  | 05/27/2010 | 111590.35 | 0.36
2376 | Indiana | DE KALB |  | 03 | 0901203 | This project will improve sections and extend the life of Dekalb County Road 35 with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/06/2009 | 10/31/2010 | 139822.9 | 5.3
2377 | Indiana | CLAY |  | 08 | 0901208 | I-70 - From Center Point to Harmony. | Pavement Improvement | 12/16/2009 |  | 06/30/2010 | 823382.98 | 0.175
2378 | Indiana | MARION | INDIANAPOLIS | 04 | 0901210 | Mooresville Rd from Raceway Rd to West Newton | Pavement Improvement | 11/23/2009 |  | 08/09/2010 | 877991.05 | 0.175
2379 | Indiana | MARION | INDIANAPOLIS | 04 | 0901211 | Mooresville Rd from Southport Rd to High School Rd | Pavement Improvement | 11/23/2009 |  | 08/09/2010 | 279392.38 | 0.175
2380 | Indiana | MARION | INDIANAPOLIS | 04 | 0901229 | Mendenhall Rd from Camby Rd to SR 67 | Pavement Improvement | 11/23/2009 |  | 08/09/2010 | 339918.58 | 0.175
2381 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901235 | 116th St from 0.35 mi E. of Eller Rd to 2.4 mi W of I-69 | Pavement Improvement | 12/16/2009 |  | 07/31/2010 | 157808.07 | 0.175
2382 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901239 | Olio Rd from bridge over Geist Reservoir to 126th St | Pavement Improvement | 12/16/2009 |  | 07/31/2010 | 393619.79 | 0.098
2383 | Indiana | STEUBEN |  | 03 | 0901243 | County Highway 1100 W - CR-475S from Lagrange County line to CR-500S | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 169170.93 | 0.8
2384 | Indiana | STEUBEN |  | 03 | 0901244 | CR 500 S from CR 475 S to SR 327 | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 68689.4 | 0.7
2385 | Indiana | STEUBEN |  | 03 | 0901245 | N SR 327 - CR 500 N from SR-327 to CR 900 W | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 45702.26 | 0.5
2386 | Indiana | STEUBEN |  | 03 | 0901246 | CR 900 W from CR 500 N to Orland Rd | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 12326.59 | 0.1
2387 | Indiana | STEUBEN |  | 03 | 0901247 | Orland Road from CR 900 W to CR 800 W | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 96975.56 | 1
2388 | Indiana | STEUBEN |  | 03 | 0901248 | CR 800 W from Orland Rd (N Junction) to Orland Rd (S Junction) | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 11372.56 | 0.1
2389 | Indiana | STEUBEN |  | 03 | 0901249 | Orland Rd from CR 800 W to CR 675 N | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 143441.5 | 1.4
2390 | Indiana | STEUBEN |  | 03 | 0901250 | Kimble Rd from CR 550 W to Orland Rd | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 31577.22 | 0.35
2391 | Indiana | STEUBEN |  | 03 | 0901252 | Fox Lake Rd from Menges Rd to CR 200 W | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 227152.5 | 2.1
2392 | Indiana | STEUBEN |  | 03 | 0901253 | CR 200 W from Fox Lake Rd to US 20 | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 12115.8 | 0.3
2393 | Indiana | STEUBEN |  | 03 | 0901254 | Menges Rd from Waymire Rd to Fox Lake Rd | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 63008.97 | 0.7
2394 | Indiana | STEUBEN |  | 03 | 0901255 | Waymire Rd from Menges Rd to CR 150W | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 125311.16 | 1.3
2395 | Indiana | STEUBEN |  | 03 | 0901256 | E SR 120 - Van Guilder Road from SR-120 to North Baker St | Pavement Improvement | 10/15/2009 |  | 05/27/2010 | 149414.16 | 1.6
2396 | Indiana | JAY |  | 06 | 0901271 | N Charles Ave from W Water Street to SR 67 | Pavement Improvement | 12/04/2009 |  | 06/25/2010 | 60893.52 | 0.5
2397 | Indiana | JAY |  | 06 | 0901272 | Lincoln Street from N Franklin Street to US 27 (Meridian Street) | Pavement Improvement | 11/23/2009 |  | 06/25/2010 | 23676.5 | 0.17
2398 | Indiana | KOSCIUSKO |  | 03 | 0901284 | Country Club Rd from Country Club Dr S to Hackleman St | Pavement Improvement | 10/14/2009 | 10/28/2009 | 08/01/2010 | 144895.43 | 0.99
2399 | Indiana | KOSCIUSKO |  | 03 | 0901285 | Harrison St from Sheridan St to Dubois Drive | Pavement Improvement | 10/14/2009 | 10/28/2009 | 08/01/2010 | 49582.91 | 0.32
2400 | Indiana | KOSCIUSKO |  | 03 | 0901286 | Winona Ave from 200' E of Bronson St to McKinley St | Pavement Improvement | 10/14/2009 | 10/28/2009 | 08/01/2010 | 110450.99 | 0.72
2401 | Indiana | KOSCIUSKO |  | 03 | 0901287 | Rozella Rd from Brookview Ave to SR 15 | Pavement Improvement | 10/14/2009 | 10/28/2009 | 08/01/2010 | 53202.99 | 0.6
2402 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901290 | Olio Rd from 126th St to 136th St | Pavement Improvement | 12/16/2009 |  | 06/30/2010 | 274126.63 | 0.153
2403 | Indiana | HUNTINGTON |  | 05 | 0901323 | This project will improve sections and extend the life of County Road 900North from SR 9 to county road 600 east in Huntington County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/29/2009 | 06/12/2010 | 564063.47 | 7.14
2404 | Indiana | HUNTINGTON |  | 05 | 0901324 | This project will improve sections and extend the life of County Road 300West from county road 1200 south to county road 300 south in Huntington County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/29/2009 | 06/12/2010 | 680700.92 | 9.01
2405 | Indiana | HUNTINGTON |  | 05 | 0901325 | This project will improve sections and extend the life of County Road 800North from county road 1000 west to SR 9 in Huntington County with a pavement surface overlay. | Pavement Improvement | 10/14/2009 | 10/28/2009 | 06/12/2010 | 657672 | 9.04
2406 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901337 | Fir Road from Day Road to Brick Road (exluding intersections) | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 195575.51 | 0.175
2407 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901338 | Miami Road from Roosevelt Road to 0.7 miles south of Orchard Heights Drive | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 52748.56 | 0.175
2408 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901341 | Portage Road from 0.4 miles north of Bendix Drive to IN/MI State Line | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 259988.33 | 0.175
2409 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901342 | Ireland Road from SR 23 to Locust Road | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 153261.06 | 0.175
2410 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901344 | Ash Road from SR 933 to Elsie Avenue | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 199887.4 | 0.107
2411 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901345 | Ironwood Road from Douglas Road to indiana Toll Road | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 84988.69 | 0.5
2412 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901346 | Mayflower Road from the UAB, 0.3 miles north of Sumption Trail, to SR 23 | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 33113.49 | 0.175
2413 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901347 | Locust Road from Madison Road to Jackson Road | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 262227.2 | 2.9
2414 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901348 | I-80 - Juniper Road from 0.3 miles north of Douglas Rd. to Cleveland Road | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 64125.26 | 0.175
2415 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901351 | Beech Road from 0.5 miles S of Harrison road to .07 miles S of Adams St. | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 78529.76 | 0.5
2416 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901352 | Grant Road from US 20/US31 By-Pass to Mayflower Road | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 60090.72 | 0.175
2417 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901353 | County wide (urban areas only) sign replacement | Safety/Traffic Management | 12/16/2009 |  | 07/31/2010 | 172677.71 | 0.175
2418 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901354 | This project will improve roadway safety in the town of Osceola. | Safety/Traffic Management | 12/16/2009 |  | 07/31/2010 | 39977.69 | 0.175
2419 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901355 | Edison Road from Quince Road to Sundown Road | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 209393.94 | 0.175
2420 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901358 | Beech Road from SR 933 to .07 miles south of Adams Street | Pavement Improvement | 11/23/2009 |  | 08/15/2010 | 36104.42 | 0.175
2421 | Indiana | JAY |  | 06 | 0901362 | CR 200 S from Blaine Pike to Boundry Pike | Pavement Improvement | 10/13/2009 |  | 07/30/2010 | 218336.18 | 2.08
2422 | Indiana | JAY |  | 06 | 0901365 | CR 300 N from Pennville LIMITS TO us 27 | Pavement Improvement | 12/16/2009 |  | 07/30/2010 | 771313.38 | 0.175
2423 | Indiana | JAY |  | 06 | 0901366 | CR 400 S from CR 1150 W to SR 1 | Pavement Improvement | 10/13/2009 |  | 07/30/2010 | 262370.35 | 0.175
2424 | Indiana | JAY |  | 06 | 0901367 | CR 1150 W from Dunkirk to CR 900 S | Pavement Improvement | 12/16/2009 |  | 07/30/2010 | 341424.82 | 0.175
2425 | Indiana | JAY |  | 06 | 0901374 | West Water Street from Western City Limit to US 27 (Meridian Street) | Pavement Improvement | 12/30/2009 |  | 06/28/2010 | 159989.15 | 1.5
2426 | Indiana | JAY |  | 06 | 0901375 | W. High Street from N. Middle Street to US 27 (Meridian Street) | Pavement Improvement | 12/30/2009 |  | 06/28/2010 | 74517.54 | 0.37
2427 | Indiana | JAY |  | 06 | 0901379 | N. Wayne St to SR 26 to E. Votaw Street | Pavement Improvement | 12/30/2009 |  | 06/25/2010 | 61083.38 | 0.49
2428 | Indiana | RUSH |  | 06 | 0901384 | CR 800 E from Glenwood to CR 250 N | Pavement Improvement | 10/13/2009 |  | 10/30/2009 | 153089.34 | 0.094
2429 | Indiana | RUSH |  | 06 | 0901386 | CR 800 E from Orange Pike to Glenwood | Pavement Improvement | 10/13/2009 |  | 07/30/2010 | 259236.1 | 0.175
2430 | Indiana | RUSH |  | 06 | 0901388 | Fort Wayne from E. 3rd St to E. 11th St | Pavement Improvement | 10/13/2009 |  | 06/25/2010 | 173432.25 | 0.175
2431 | Indiana | RUSH |  | 06 | 0901390 | Conard-Harcourt Way from SR 3 to E. 11th Street | Pavement Improvement | 10/13/2009 |  | 06/25/2010 | 172800.26 | 0.175
2432 | Indiana | MIAMI, FULTON |  | 02,05 | 0901410 | SR 19 - From US 24 to 0.25 miles S of SR 14 (South limits of Akron) | Pavement Improvement | 12/15/2009 |  | 10/08/2010 | 2282166.8 | 6.339
2433 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901441 | Between CR 510 S & CR 430 S | Pavement Improvement | 12/16/2009 |  | 05/29/2010 | 231483.66 | 0.175
2434 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901458 | From Union Township line to Old US 231 | Pavement Improvement | 12/16/2009 |  | 05/29/2010 | 162779.45 | 0.175
2435 | Indiana | PULASKI |  | 02 | 0901465 | Rail banked corridor between Star City and Kenneth in Cass/Pulaski Co's | Transportation Enhancements | 12/31/2009 |  | 11/19/2010 | 2219753.6 | 0.175
2436 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0901480 | New York Street from 9th St to 12th Street | Transportation Enhancements | 11/30/2009 |  | 06/19/2010 | 46161.36 | 0.23
2437 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0901481 | 11th St from New York Ave to East Burdick St | Transportation Enhancements | 11/30/2009 |  | 06/19/2010 | 39247.07 | 0.14
2438 | Indiana | WAYNE |  | 06 | 0901487 | Centerville Rd from 900 feet S of Temple Dr,N 3.38 miles to the S ramp to I-70 | Pavement Improvement | 11/18/2009 |  | 06/11/2010 | 995595.45 | 3.41
2439 | Indiana | MONROE | BLOOMINGTON | 09 | 0901506 | S. Walnut St from Wylie to Country Club | Pavement Improvement | 12/31/2009 |  | 06/26/2010 | 705631.3 | 0.112
2440 | Indiana | ALLEN | FORT WAYNE | 03 | 0901552 | Hartzell Rd from RR tracks (approx. 1600' south of Rose Ave) to Rose Ave | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 36964.34 | 0.3
2441 | Indiana | ALLEN | FORT WAYNE | 03 | 0901553 | Rose Ave; from Green St. to Linden Rd | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 45610.65 | 0.61
2442 | Indiana | ALLEN | FORT WAYNE | 03 | 0901554 | Landin Rd from N River Rd to Maysville Rd | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 272228.08 | 1.89
2443 | Indiana | ALLEN | FORT WAYNE | 03 | 0901555 | New Haven Ave from Meyer Rd to SR 930 | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 89825.99 | 0.73
2444 | Indiana | ALLEN | FORT WAYNE | 03 | 0901556 | Rose Ave from Hartzell Rd to Landin Rd | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 55547.51 | 0.58
2445 | Indiana | ALLEN | FORT WAYNE | 03 | 0901557 | Minnich Rd from Seiler Rd to SR 930 | Pavement Improvement | 11/23/2009 |  | 06/26/2010 | 166342.1 | 1.15
2446 | Indiana | ALLEN | FORT WAYNE | 03 | 0901558 | Summit St from Bensman Ave to Linden Rd | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 59087.48 | 0.48
2447 | Indiana | ALLEN | FORT WAYNE | 03 | 0901559 | Lincoln Hwy from 365' E of Green St to City Limits (1320' W of Doyle St) | Pavement Improvement | 11/23/2009 |  | 07/30/2010 | 120619.5 | 1.1
2448 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901563 | Old US Hwy 231 - From CR 500 S to CR 350 S | Pavement Improvement | 12/16/2009 |  | 05/29/2010 | 283613.92 | 0.175
2449 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901571 | 45th Street from State Line east to Highland Line | Pavement Improvement | 12/16/2009 |  | 06/01/2010 | 647073.26 | 0.093
2450 | Indiana | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0901600 | Schultz Road from CR 600W to CR 400W | Pavement Improvement | 11/23/2009 | 11/24/2009 | 12/01/2009 | 293784.87 | 0.175
2451 | Indiana | ALLEN | FORT WAYNE | 03 | 0901631 | Aboite Center Rd from West Hamilton Rd to Homestead Rd | Pavement Improvement | 11/23/2009 |  | 06/26/2010 | 117466.77 | 1.26
2452 | Indiana | ALLEN | FORT WAYNE | 03 | 0901632 | Bass Road from W Co Ln Road to Scott Rd | Pavement Improvement | 11/23/2009 |  | 06/26/2010 | 230737.53 | 3.26
2453 | Indiana | ALLEN | FORT WAYNE | 03 | 0901633 | Covington Road from W Co Ln Road to 200 ft W of Braemar Dr | Pavement Improvement | 11/23/2009 |  | 06/26/2010 | 234296.18 | 1.87
2454 | Indiana | ALLEN | FORT WAYNE | 03 | 0901634 | West Hamilton Road frm US 24 to Bass Road | Pavement Improvement | 11/23/2009 |  | 06/26/2010 | 570440.24 | 5.63
2455 | Indiana | ALLEN | FORT WAYNE | 03 | 0901635 | Leesburg Road from Kroemer Road to Beineke Road | Pavement Improvement | 11/23/2009 |  | 06/26/2010 | 69613.18 | 1.02
2456 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901636 | This project will improve the traffic signs in the town of Indian Village. | Safety/Traffic Management | 12/16/2009 |  | 07/31/2010 | 4262.54 | 0.175
2457 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901637 | This project will improve the traffic signs in the town of Roseland. | Safety/Traffic Management | 12/16/2009 |  | 07/31/2010 | 25791.49 | 0.175
2458 | Indiana | ALLEN | FORT WAYNE | 03 | 0901722 | Liberty Mills Road frm W Co Ln Road to Amber Road | Pavement Improvement | 11/23/2009 |  | 08/14/2010 | 216179.98 | 1.79
2459 | Indiana | ALLEN | FORT WAYNE | 06 | 0901723 | Muldoon Road frm Ferguson Road to Winchester Road | Pavement Improvement | 11/23/2009 |  | 08/14/2010 | 99462.66 | 1.32
2460 | Indiana | ALLEN | FORT WAYNE | 03 | 0901724 | Smith Road from Airport Expressway to 120 feet N of Knoll Road (N&S Railroad) | Pavement Improvement | 11/23/2009 |  | 08/14/2010 | 182986.38 | 2.41
2461 | Indiana | ALLEN | FORT WAYNE | 03 | 0901725 | Wallen Road frm Huguenard Road to Hanauer Road | Pavement Improvement | 11/23/2009 |  | 08/14/2010 | 64261.09 | 0.93
2462 | Indiana | ALLEN | FORT WAYNE | 03 | 0901726 | Washington Center Road frm O'Day Road to Kroemer Road | Pavement Improvement | 11/23/2009 |  | 08/14/2010 | 137575.49 | 1.79
2463 | Indiana | ALLEN | FORT WAYNE | 06 | 0901727 | Winchester Road frm Ferguson Road to Lower Huntington Road | Pavement Improvement | 11/23/2009 |  | 08/14/2010 | 155975.24 | 1.97
2464 | Indiana | ALLEN | FORT WAYNE | 03 | 0901728 | Yohne Road frm Branstrator Rd to Smith Rd | Pavement Improvement | 11/23/2009 |  | 08/14/2010 | 181322.14 | 2.53
2465 | Indiana | ALLEN | FORT WAYNE | 03 | 0901787 | Wayne St from Broadway to Coombs St | Pavement Improvement | 12/31/2009 |  | 05/27/2010 | 439336.16 | 1.34
2466 | Indiana | ALLEN | FORT WAYNE | 03 | 0901788 | Berry St from Broadway to Coombs St | Pavement Improvement | 12/31/2009 |  | 05/27/2010 | 358357.16 | 1.35
2467 | Indiana | ALLEN | FORT WAYNE | 03 | 0901789 | Washington Blvd from Broadway to Clay St | Pavement Improvement | 12/31/2009 |  | 05/27/2010 | 260519.69 | 0.82
2468 | Indiana | ALLEN | FORT WAYNE | 03 | 0901790 | Jefferson Blvd from Calhoun St to Clay St | Pavement Improvement | 12/31/2009 |  | 05/27/2010 | 106107.14 | 0.33
2469 | Indiana | ALLEN | FORT WAYNE | 03 | 0901825 | E State Blvd: from Anthony Blvd to Hobson Rd | Pavement Improvement | 12/31/2009 |  | 06/26/2010 | 395065.82 | 0.88
2470 | Indiana | ALLEN | FORT WAYNE | 03 | 0901826 | E State Blvd from Hobson Rd to Coliseum Blvd (SR 930) | Pavement Improvement | 12/31/2009 |  | 06/26/2010 | 242034.21 | 0.52
2471 | Indiana | RANDOLPH |  | 06 | 1004017 | This project will replace the bridge on SR 32 over Sparrow Creek in Randolph County.. | Bridge Replacement | 05/13/2009 | 07/29/2009 | 11/20/2009 | 867750 | 0.175
2472 | Indiana | STARKE |  | 02 | 1475040 | This project will improve drainage by replacing the structure on US 35 ofer Laramore Ditch in Starke County. | Pavement Improvement | 06/04/2009 |  | 12/02/2009 | 793700 | 0.175
2473 | Indiana | LA PORTE |  | 02 | 1477002 | US 35 - At Schultz Rd, 0.14 mile N of I-80/90 Underpass | Safety/Traffic Management | 10/08/2009 | 10/15/2009 | 08/13/2010 | 1021010.76 | 0.278
2474 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 1621002 | This project will add turn lanes and improve the intersection of US 19 and county road 42 in Elkhart County. | Pavement Widening | 08/18/2009 |  | 06/30/2010 | 812909 | 0.175
2475 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 1810014 | SR 15 - Over Wolf Lake Drain, 2.65 miles N of US 33 | Pavement Improvement | 10/14/2009 |  | 10/01/2010 | 535754.07 | 0.175
2476 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 1941018 | This project will improve and widen intersections along SR 8 and SR 49 in Porter County. | Safety/Traffic Management | 08/27/2009 | 10/22/2009 | 06/29/2010 | 1947964 | 0.939
2477 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 2127112 | This project will widn US 6 in Elkhart County with the installation of sidewalks along the North side of the road and a wider median. | Pavement Widening | 07/17/2009 |  | 10/22/2010 | 4949108 | 0.934
2478 | Indiana | WHITLEY |  | 03 | 2192034 | US 33 - At Clingerman Avenue, 0.5 mile N of SR 205 | Pavement Improvement | 09/08/2009 | 10/21/2009 | 06/18/2010 | 302904 | 0.175
2479 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 2195026 | This project will construct a median left turn lane on US 33 near US 20 in Dunlap, Elkhart County. New pavement, drainage structures, signals and signs will be placed and a bridge widened. | New Construction | 03/27/2009 | 07/23/2009 | 10/07/2011 | 10667478.72 | 3.032
2480 | Indiana | UNION |  | 06 | 2493013 | This project will repair and restore the pavement and replace signs on US 27 from the Ohio State line north 3.6 miles in Union county. | Pavement Widening | 04/15/2009 | 08/05/2009 | 02/10/2012 | 9345892.93 | 3.066
2481 | Indiana | GRANT |  | 05 | 3227023 | This project will improve the sight distance at SR 26 and county road 750 south in Grant County. | Pavement Improvement | 07/07/2009 | 08/21/2009 | 12/01/2009 | 986682.26 | 0.175
2482 | Indiana | FULTON |  | 02 | 3325007 | This project will replace the bridge on SR 17 over Starr Ditch in Fulton County. | Bridge Replacement | 04/17/2009 | 07/06/2009 | 11/14/2009 | 601816.25 | 0.175
2483 | Indiana | HENDRICKS |  | 04 | 3632005 | This project will improve the surface and rebuild sections of the bridge on US 40 over White Lick Creek in Hendricks County. | Pavement Improvement | 03/24/2009 | 04/20/2009 | 11/24/2009 | 2847000 | 0.175
2484 | Indiana | SULLIVAN |  | 08 | 3677012 | This project will improve the intersection on SR 54 and add turn lanes at County Road 50 South, 1 mile West of SR 159. | Pavement Improvement | 05/08/2009 | 07/14/2009 | 04/17/2010 | 793449.25 | 0.275
2485 | Indiana | SCOTT |  | 09 | 4072004 | This project will replace the bridge on SR 356 over Town Creek in Scott County. | Bridge Replacement | 03/19/2009 | 04/07/2009 | 10/31/2009 | 627953.34 | 0.175
2486 | Indiana | FOUNTAIN |  | 08 | 4223005 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Pavement Improvement | 06/17/2009 | 07/16/2009 | 08/31/2010 | 3270050.51 | 1.014
2487 | Indiana | BARTHOLOMEW | COLUMBUS | 09 | 4303009 | This project will add turn lanes, nodernize the signal, and widen the intersection at SR 11and Bartholomw county Road 450S. | Pavement Improvement | 05/06/2009 | 06/01/2009 | 08/15/2010 | 1202944.2 | 0.175
2488 | Indiana | CLINTON |  | 04 | 4312005 | This project will improve the sight distance at SR 75 and county road 700 north in Clinton County. | Safety/Traffic Management | 06/03/2009 | 06/24/2009 | 11/15/2009 | 1206807.56 | 0.852
2489 | Indiana | MORGAN |  | 04 | 4455005 | This project will replace and restore the pavement on SR 42 in Morgan County from Monrovia to Martinsville. | Pavement Improvement | 06/04/2009 | 07/07/2009 | 11/20/2010 | 7339345 | 9.63
2490 | Indiana | STARKE |  | 02 | 4475002 | This project will improve drainage by replacing the structure over Cannon ditch on SR 8 in Starke County | Pavement Improvement | 08/19/2009 |  | 10/31/2009 | 341249.89 | 0.175
2491 | Indiana | FOUNTAIN |  | 04 | 4923003 | This project will improve the surface and rebuild sections of the bridge on SR 341 over I-74 in Fountain County. | Bridge Improvement | 03/23/2009 | 04/03/2009 | 08/12/2009 | 1220119 | 0.175
2492 | Indiana | ST JOSEPH |  | 02 | 5171008 | This project will improve drainage by replacing the structure on SR 331 over Madison Township Ditch in St. Joseph County. | Pavement Improvement | 03/24/2009 | 06/01/2009 | 08/29/2009 | 688526.05 | 0.175
2493 | Indiana | MIAMI |  | 05 | 5252007 | This project will improve drainage by replacing the structure on SR 16 over Washonis Creek in Miami County. | Pavement Improvement | 09/08/2009 | 10/19/2009 | 09/03/2010 | 397020.7 | 0.175
2494 | Indiana | JEFFERSON |  | 09 | 5639005 | This project will improve the sight distance at SR 250 and Scott Ridge Road in Jefferson County. | Safety/Traffic Management | 05/08/2009 |  | 09/25/2009 | 681704.39 | 0.175
2495 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 8571960 | US 41 - At 93rd Ave, 1.9 miles N of US 231 | Pavement Improvement | 06/30/2009 | 07/28/2009 | 10/31/2009 | 2083424.57 | 0.175
2496 | Indiana | ELKHART |  | 03 | 9031815 | This project will improve drainage by replacing the structure on SR 19 over Fisher-Gordon Ditch in Elkhart County. | Pavement Improvement | 05/18/2009 | 07/22/2009 | 10/23/2009 | 552259.39 | 0.099
2497 | Indiana | HARRISON |  | 09 | 9032075 | This project will improve drainage by replacing a pipe on SR 11 on the East side of Elizabeth. | Pavement Improvement | 07/09/2009 | 07/31/2009 | 10/17/2009 | 285000 | 0.175
2498 | Indiana | HUNTINGTON |  | 05 | 9301060 | This project will improve drainage by replacing the structure on SR 5 over Loon Creek in Huntington County. | Pavement Improvement | 08/14/2009 | 09/15/2009 | 11/13/2009 | 498659 | 0.175
2499 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9610820 | This project will replace the bridge on SR 312 over the Indiana Harbor Canal in Lake County. | Bridge Replacement | 06/18/2009 |  | 11/09/2009 | 2153446.87 | 0.175
2500 | Indiana | STEUBEN |  | 03 | 9803670 | This project will rebuild the US 20 and I-69 interchange in Steuben county to improve traffic flow. | Bridge Replacement | 06/01/2009 | 06/12/2009 | 10/15/2010 | 1994588.32 | 0.49
2501 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 9901720 | This project will replace the bridge on Locust Road over US 20 in St Joseph County. | Bridge Replacement | 06/03/2009 | 06/16/2009 | 11/17/2009 | 3054373.82 | 0.1
2502 | Indiana | PORTER |  | 01 | 9901740 | This project will replace the bridge on SR 49 over Pleasant Township Ditch in Porter County. | Bridge Replacement | 05/13/2009 | 06/26/2009 | 10/31/2009 | 825666.48 | 0.175
2503 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999193 | This project will extend the bridge life by repainting bridge beams at SR 49 over US 30 and SR 2 in Porter County. | Bridge Improvement | 05/13/2009 | 06/30/2009 | 09/03/2009 | 372762.88 | 0.175
2504 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999194 | This project will extend the bridge life by repainting bridge beams at Calumet Ave over SR 49 and US 6 in Porter County. | Bridge Improvement | 05/13/2009 | 06/30/2009 | 09/09/2009 | 378675 | 0.001
2505 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999228 | This project will upgrade and modernize the traffic signal at US 41 and 93rd Avenue in Lake County. | Safety/Traffic Management | 06/30/2009 | 07/28/2009 | 10/31/2009 | 115269.08 | 0.175
2506 | Indiana | TIPPECANOE |  | 04 | 9999231 | This project will add turn lanes and improve the intersection of SR 25 at county road 575 west and county road 500 west in Tippecanoe County. | Pavement Widening | 04/15/2009 | 05/04/2009 | 11/05/2009 | 1383518.57 | 0.707
2507 | Indiana | JACKSON |  | 09 | 9999235 | This project will improve sections and extend the life of SR 11 from SR 250 to US 50 in Jackson County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 09/28/2009 | 11/30/2009 | 1174075.55 | 8.002
2508 | Indiana | TIPPECANOE |  | 04 | 9999236 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 1025634.93 | 0.175
2509 | Indiana | MARION | INDIANAPOLIS | 07 | 9999241 | 21st Street over Big Eagle Creek | Bridge Improvement | 12/03/2009 |  | 09/30/2010 | 541220.57 | 0.175
2510 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | L720015 | This project will build a new bridge on US 52 over the Norfolk Southern Railroad, 2 miles South of SR 25 in Tippecanoe County. | New Bridge Construction | 06/05/2009 | 08/20/2009 | 11/30/2010 | 5791766.4 | 0.088
2511 | Iowa | FAYETTE |  | 1 | 000R002 | This project will replace track ballast and ties on 14 miles of D&W Railroad track between Dewar and Oelwein to improve operational efficiency and safety. | Other | 01/06/2010 |  |  | 764200 | 0
2512 | Iowa | PAGE |  | 5 | 0022044 | This project will provide an improved driving surface by widening and resurfacing 2.0 miles of Iowa Highway 2 from W State Street to S 16th Street in Clarinda with hot-mix asphalt. | Pavement Improvement | 03/30/2009 | 04/15/2009 | 11/01/2009 | 848817 | 1.9
2513 | Iowa | DAVIS |  | 2 | 0028035 | This project will provide an improved driving surface by widening and resurfacing with hot-mix asphalt 4.9 miles of Iowa Highway 2/US Highway 63 through Bloomfield from the west junction of these hig | Pavement Improvement | 06/29/2009 | 07/20/2009 | 07/01/2010 | 3391074 | 5
2514 | Iowa | PLYMOUTH |  | 5 | 0031075 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 3/South Dakota 50 over the Big Sioux River 0.5 miles North and 1.7 miles West of We | Bridge Replacement | 03/06/2009 | 03/30/2009 | 11/01/2009 | 1842961 | 0
2515 | Iowa | BUENA VISTA |  | 5 | 0032053 | This project will replace a bridge, which is in poor condition and narrow with a new bridge. The bridge is on Iowa 3 over Brooke Creek 6.1 miles West of US 71 or approximately 10 miles Northwest of S | Bridge Replacement | 07/31/2009 |  | 11/01/2010 | 782441 | 0
2516 | Iowa | POLK | DES MOINES | 3 | 0064152 | This project will reconstruct and widen approximately 900 feet of 111th Street south and west of the intersection with US Highway 6 (Hickman Road) in the City of Clive. The project will include concr | Pavement Improvement | 01/05/2010 |  |  | 586698 | 0
2517 | Iowa | WEBSTER, CALHOUN |  | 4 | 0074017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 11.7 miles of Iowa Highway 7 from 0.5 miles west of the Calhoun County Line to US Highway 1 | Pavement Improvement | 03/26/2009 | 04/13/2009 | 12/01/2009 | 5364499 | 11.9
2518 | Iowa | OSCEOLA |  | 5 | 0092021 | This project will improve the driving surface by applying an unbonded portland cement concrete overlay on approximately 8.6 miles of Iowa Highway 9 from just west of Polk Avenue to just east of Tanage | Pavement Improvement | 03/30/2009 | 05/11/2009 | 11/01/2009 | 4865289 | 8.8
2519 | Iowa | POLK | DES MOINES | 3 | 0132615 | Polk County is constructing a 0.4 mile extension of Adventureland Drive NW. The project will widen Adventureland Drive NW from a 2-lane roadway to a 4-lane roadway with median, sidewalk, and left-tur | Pavement Improvement | 09/14/2009 | 09/22/2009 | 12/01/2010 | 706977 | 0.3
2520 | Iowa | STORY | AMES | 4 | 0155662 | This project is in the city of Ames on George W. Carver Avenue from Stange Road to Bloomington Road. The project consists of one inch of hot-mix asphalt stress relief course and six inches of concret | Pavement Improvement | 09/28/2009 | 10/12/2009 | 12/01/2010 | 717794 | 0.9
2521 | Iowa | STORY | AMES | 4 | 0155664 | This project is in the city of Ames on Lincoln Way from Hickory Drive to just past Marshall Avenue. The project consists of milling the existing surface, patching problem areas, resurfacing with hot- | Pavement Improvement | 08/27/2009 | 09/18/2009 | 12/01/2010 | 577184 | 0.3
2522 | Iowa | STORY | AMES | 4 | 0155665 | This project will provide for the construction of .6 miles of the Skunk River Trail that will run along the west side of South Skunk River from just south of East 13th Street in South River Valley Par | Transportation Enhancements | 08/27/2009 |  | 12/01/2010 | 175728 | 0.6
2523 | Iowa | STORY | AMES | 4 | 0155668 | This project consists of milling and resurfacing with asphalt 0.44 miles of roadway along Duff Avenue from 7th Street N. to 13th Street in Ames, Iowa. | Pavement Improvement | 01/14/2010 |  |  | 504231 | 0
2524 | Iowa | WAPELLO |  | 2 | 0161017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 5.3 miles of Iowa Highway 16 from US Highway 34 to north city | Pavement Improvement | 04/01/2009 | 04/06/2009 | 12/01/2009 | 1837373 | 5.5
2525 | Iowa | DAVIS, WAPELLO, VAN BUREN |  | 2 | 0161018 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 0.16 miles of Iowa Highway 16 from north city limit of Eldon t | Pavement Improvement | 04/01/2009 | 04/06/2009 | 12/01/2009 | 1454798 | 4.3
2526 | Iowa | CHICKASAW |  | 4 | 0241017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 6.75 miles of Iowa Highway 24 from east city limit of New Hamp | Pavement Improvement | 04/03/2009 | 04/24/2009 | 11/01/2009 | 3200829 | 7.8
2527 | Iowa | CHICKASAW, WINNESHIEK |  | 4 | 0241020 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 6 miles of Iowa Highway 24 from the west city limit of Lawler | Pavement Improvement | 04/03/2009 | 04/24/2009 | 11/01/2009 | 2566288 | 6.3
2528 | Iowa | CASS |  | 5 | 0285612 | This project replaces the bridge supports, which are in very poor condition, to extend the service life of the bridge. The bridge is located on Nishna Street over an unnamed creek just South of 29th | Bridge Improvement | 10/12/2009 | 11/02/2009 | 12/01/2009 | 92520 | 0
2529 | Iowa | CASS |  | 5 | 0285613 | This project is in Atlantic, Iowa on South Olive Street from East 14th Street to East 22nd Street. The project consists of pavement rehabilitation which will provide a smoother ride and improved drai | Pavement Improvement | 01/21/2010 |  |  | 175000 | 0.5
2530 | Iowa | FREMONT |  | 5 | 0291068 | This project will replace two bridges, which are in poor condition, with new bridges. The bridges are on Interstate 29 over Plum Creek 0.5 miles South of Exit #20, or approximately 28 miles South of C | Bridge Replacement | 03/06/2009 | 03/30/2009 | 11/01/2009 | 2173992 | 0
2531 | Iowa | FREMONT |  | 5 | 0291069 | This project will replace two bridges, which are in poor condition with new bridges. The bridges are on Interstate 29 over County Road J24 at Exit #20, approximately 27 miles South of Council Bluffs. | Bridge Replacement | 03/06/2009 | 03/30/2009 | 11/01/2009 | 2797514 | 0
2532 | Iowa | FREMONT |  | 5 | 0291075 | On Interstate 29 in Fremont County Iowa, from 1.5 mile north of county road J-26 north to 1.5 mile north of county road J-24, a nine-inch concrete overlay will be placed on the northbound lanes and a | Pavement Improvement | 03/06/2009 | 03/30/2009 | 11/01/2009 | 11189757 | 4.2
2533 | Iowa | MILLS |  | 5 | 0292054 | This project will replace two bridges, which are in poor condition, with new bridges. The bridges are on Interstate 29 over St. Mary’s Creek 1 mile South of Exit #42, or approximately 5 miles South of | Bridge Replacement | 03/06/2009 | 03/23/2009 | 11/01/2009 | 1726111 | 0
2534 | Iowa | MILLS |  | 5 | 0292065 | On Interstate 29 in Mills County, Iowa, from 3 miles north of the north junction with US Highway 34 to the Pottawattamie County line, a nine-inch concrete overlay will be placed on the northbound lane | Pavement Improvement | 03/06/2009 | 03/23/2009 | 11/01/2009 | 11742272 | 6
2535 | Iowa | MONONA, HARRISON |  | 5 | 0295100 | The Iowa DOT is reconstruction of I-29 from Exit 95, which services Little Sioux, Iowa, to Exit 112, which services Onawa, Iowa. The project includes the reconstruction of the grade and Portland Ceme | Pavement Improvement | 04/23/2009 | 05/04/2009 | 11/01/2010 | 42253362 | 18.1
2536 | Iowa | MONONA |  | 5 | 0296167 | This project provides for a six inch hot-mix asphalt overlay on the north and southbound lanes of Interstate 29 in Monona County, Iowa, from just north of Iowa 175 north to the Woodbury County line. | Pavement Improvement | 06/29/2009 | 07/31/2009 | 09/01/2010 | 22401042 | 13.5
2537 | Iowa | MONONA |  | 5 | 0296182 | This project will replace a bridge, which is in poor condition with a new bridge. The bridge is on Interstate 29 southbound over Robinson Creek approximately 3.5 miles South of Exit#127 near Sloan. | Bridge Replacement | 03/06/2009 | 05/04/2009 | 11/01/2009 | 1169819 | 0
2538 | Iowa | TAMA |  | 3 | 0306151 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 11.9 miles of US Highway 30 from just east of M Avenue to Iow | Pavement Improvement | 06/26/2009 | 07/17/2009 | 07/01/2010 | 4065922 | 11.9
2539 | Iowa | CLARKE |  | 5 | 0351105 | This project will replace two bridges, which are in poor condition and have inadequate clearance over Interstate 35, with new bridges. The bridges are on US 34 over Interstate 35 in Osceola. | Bridge Replacement | 03/06/2009 | 04/01/2009 | 11/01/2009 | 1736085 | 0
2540 | Iowa | CLARKE |  | 5 | 0351111 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of the southbound lanes of I-35. The project begins approximately one mile north of Exit 22, which services Van Wert, Iowa, and e | Pavement Improvement | 03/30/2009 | 04/07/2009 | 11/01/2009 | 15304219 | 9.5
2541 | Iowa | CLARKE |  | 5 | 0351112 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of the northbound lanes of I-35. The project begins approximately one mile north of Exit 22, which services Van Wert, Iowa, and e | Pavement Improvement | 08/06/2009 |  | 11/01/2010 | 8471001 | 9.5
2542 | Iowa | CLARKE |  | 5 | 0351116 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of US Highway 34 at the interchange of I-35 and US Highway 34; Exit 33 which services Osceola, Iowa. The project is approximately | Bridge Replacement | 03/06/2009 | 03/30/2009 | 11/01/2009 | 1626415 | 0.4
2543 | Iowa | WARREN |  | 4 | 0352337 | This project provides for a four inch hot-mix asphalt overlay on the north and southbound lanes of Interstate 35 in Warren County Iowa, from the Clarke County line north to 2 miles south of Iowa 92 ne | Pavement Improvement | 04/13/2009 | 05/05/2009 | 11/01/2009 | 18607987 | 11.3
2544 | Iowa | CLAYTON |  | 1 | 0523031 | This project includes performing cracking and seating of the existing portland cement concrete pavement and then applying a hot-mix asphalt overlay on approximately 9.0 miles of US Highway 52 from jus | Pavement Improvement | 08/17/2009 | 08/24/2009 | 09/01/2010 | 3746694 | 9
2545 | Iowa | CLAYTON |  | 1 | 0523032 | This project will resurface eight miles of US 52 from Guttenberg to Garnavillo with six inches of hot-mix asphalt to improve pavement condition. | Pavement Improvement | 08/17/2009 | 08/24/2009 | 09/01/2010 | 3439573 | 9
2546 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 0587631 | In Bettendorf, Iowa on 23rd Street from Grant Street to Central Avenue. This project will be constructed in three stages to minimize impact on residents in the area. The street will be graded and pa | Pavement Improvement | 05/29/2009 | 06/08/2009 | 12/01/2009 | 739272 | 0
2547 | Iowa | LEE |  | 2 | 0611122 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 03/06/2009 | 04/08/2009 | 11/01/2009 | 126319 | 0
2548 | Iowa | LEE |  | 2 | 0611124 | The project is part of the grading of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-Pass. This project is for the grading of the new alignment which will be | New Construction | 03/06/2009 | 03/12/2009 | 09/01/2010 | 8245240 | 2.2
2549 | Iowa | LEE |  | 2 | 0611129 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 03/06/2009 | 03/18/2009 | 11/01/2009 | 549102 | 0
2550 | Iowa | LEE |  | 2 | 0611132 | The project is part of the grading of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-Pass. This project is for the grading of the new alignment which will be | New Construction | 03/06/2009 | 03/18/2009 | 09/01/2010 | 4912339 | 1.7
2551 | Iowa | LEE |  | 2 | 0611162 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 03/06/2009 | 03/18/2009 | 11/01/2009 | 251777 | 0
2552 | Iowa | LEE |  | 2 | 0611165 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 03/06/2009 | 03/18/2009 | 11/01/2009 | 295767.6 | 0
2553 | Iowa | MAHASKA |  | 3 | 0633078 | This project will mill, widen, and resurface 9 miles of US 63 from New Sharon south to 210th Street North with five inches of hot-mix asphalt to improve pavement condition and safety. The widening wi | Pavement Improvement | 07/17/2009 | 08/06/2009 | 07/01/2010 | 7406627 | 9.2
2554 | Iowa | DECATUR, CLARKE |  | 5 | 0691038 | This project will widen and resurface 31 miles of US 69 from Osceola south to Interstate 35 west of Davis City with three inches of hot-mix asphalt to improve pavement condition and safety. | Pavement Improvement | 04/01/2009 | 04/21/2009 | 11/01/2009 | 5037811 | 33
2555 | Iowa | POLK | DES MOINES | 3 | 0694092 | This project will mill 1.5 inches and resurface with 4.5 inches of hot-mix asphalt on US 69 from Iowa 160 (Oralabor Road) north1.7 miles to First Street in Ankeny to improve pavement condition. | Pavement Improvement | 10/02/2009 |  | 12/01/2009 | 1000000 | 0
2556 | Iowa | PAGE, MONTGOMERY |  | 5 | 0711030 | This project will widen and resurface 17 miles of US 71 from Iowa 2 near Clarinda north to the intersection with US 34 north of Villisca with three inches of hot-mix asphalt to improve pavement condit | Pavement Improvement | 03/30/2009 | 04/14/2009 | 11/01/2009 | 6189082 | 17.2
2557 | Iowa | SAC, CARROLL |  | 5 | 0715068 | This project will mill and replace two inches of the existing hot mix asphalt surface on approximately 12 miles of US 71 from just north of Carroll to the junction of Iowa 175 in Auburn to improve pav | Pavement Improvement | 04/20/2009 | 05/21/2009 | 11/01/2009 | 1423249 | 10.5
2558 | Iowa | POLK |  | 3 | 0747603 | This multi-use path will be constructed as an alternative mode of transportation in the city of Bondurant, in Polk county. The path is along Second Street from 450 ft west of Mallard Point Circle NW | Transportation Enhancements | 08/26/2009 | 08/26/2009 | 12/01/2009 | 389313.69 | 0.779
2559 | Iowa | BOONE |  | 4 | 0750627 | This project consistes of two roadways in Boone, Iowa: South Marshall Street from Hancock Drive to Crestwood Drive and Industrial Park Road from Linn Street to Argo Street. Both projects consist of p | Pavement Improvement | 01/29/2010 |  |  | 473410 | 0.6
2560 | Iowa | POTTAWATTAMIE |  | 5 | 0921059 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 92 over Keg Creek approximately 2.7 miles West of Treynor. | Bridge Replacement | 03/20/2009 | 04/08/2009 | 11/01/2009 | 1142159 | 0
2561 | Iowa | POTTAWATTAMIE |  | 5 | 0921060 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 92 over Middle Silver Creek approximately 0.1 miles West of Treynor. | Bridge Replacement | 03/20/2009 | 04/08/2009 | 11/01/2009 | 1279850 | 0
2562 | Iowa | DES MOINES |  | 2 | 0977632 | This project is in Burlington, Iowa on Mt. Pleasant Street from U.S. 61 to Osborn Street. The project consists of milling the existing surface down to the concrete subbase and paving two and a half i | Pavement Improvement | 09/03/2009 | 09/14/2009 | 12/01/2010 | 1364054.71 | 1.5
2563 | Iowa | LINN | CEDAR RAPIDS | 2 | 1001061 | IA 922/U.S. Business Route 151 (1st Avenue) and Collins Road will be widened in Cedar Rapids, Iowa. The project will start at 40th Steet Dr. SE for 1.3 miles ending at Tama Street SE. Widening will | Pavement Widening | 12/16/2009 |  |  | 2832566 | 0
2564 | Iowa | CLINTON |  | 1 | 1040602 | Camanche, Iowa on Washington Boulevard from US 67 to 22nd Avenue. The project consists of pavement rehabilitation which will provide a smoother ride and improved drainage. | Pavement Improvement | 01/15/2010 |  |  | 168623 | 0.6
2565 | Iowa | CARROLL |  | 5 | 1125612 | Carroll, Iowa on Clark Street from extended Anthony Street to 7th Street. The project consists of milling the existing surface and resurfacing with hot-mix asphalt. The three and a half inch overlay | Pavement Improvement | 12/08/2009 |  |  | 808258 | 0.7
2566 | Iowa | DUBUQUE |  | 1 | 1147603 | Cascade, Iowa on Tyler Street Northeast from 1st Avenue to just past Macomber Road. The project consists of milling the existing surface and resurfacing with three-inches of hot-mix asphalt providing | Pavement Improvement | 12/23/2009 |  |  | 64456 | 0.7
2567 | Iowa | BLACK HAWK |  | 1 | 1185641 | This project consists of replacing the pavement of multiple roadways in Cedar Falls, Iowa: State Street from East 2nd Street to East 4th Street, East 2nd Street from Main Street to State Street and Ea | Pavement Improvement | 10/19/2009 |  | 12/01/2010 | 700000 | 0
2568 | Iowa | BLACK HAWK |  | 1 | 1185642 | This two phase Trail widening and resurfacing project is located along the North and South sides of the Cedar River in the city of Cedar Falls in Blackhawk County. Phase I, North Riverside Trail , ru | Transportation Enhancements | 10/15/2009 |  | 12/01/2009 | 207500 | 1.939
2569 | Iowa | CHEROKEE |  | 5 | 1272618 | Cherokee, Iowa on North River Road from the city limits to the River Road Bridge. The project consists of a four inch hot-mix asphalt overlay with mail box turnouts and driveway/intersection fillets | Pavement Improvement | 06/16/2009 | 07/20/2009 | 12/01/2009 | 180000 | 0.9
2570 | Iowa | MONONA, WOODBURY |  | 5 | 1412041 | To improve safety and winter driving conditions this project will grade four miles along Iowa 141. The project starts at the Woodbury and Monona County Line just southeast of Smithland and ends 4 mil | Pavement Improvement | 03/27/2009 | 04/20/2009 | 11/01/2009 | 2271717 | 2.7
2571 | Iowa | CLINTON |  | 1 | 1415619 | Clinton County is extending 19th Avenue, approximately 1.9 miles, in the city of Clinton, Iowa, from Mill Creek Parkway east to Springdale Drive. The project is a new 4-lane Portland Cement Concrete | Pavement Improvement | 12/23/2009 |  |  | 815053 | 0
2572 | Iowa | BUCHANAN |  | 1 | 1503058 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 150 over Bear Creek approximately 3.3 mile South of Independence. | Bridge Replacement | 03/06/2009 | 03/26/2009 | 12/01/2009 | 983635 | 0
2573 | Iowa | POLK | DES MOINES | 3 | 1631080 | This project involves improvements at the intersection of Iowa Highway 163 and NE 75th Street in Pleasant Hill in Polk County, including the addition of portland cement concrete turn lanes and signal | Safety/Traffic Management | 06/16/2009 | 06/22/2009 | 12/01/2009 | 750000 | 0
2574 | Iowa | POTTAWATTAMIE | OMAHA (NE)-IA | 5 | 1642657 | The city of Council Bluffs, Iowa, is reconstructing College Road from US Highway 6 southeast and west to Valley View Drive. The project will replace approximately 0.96 miles of the existing roadway w | Pavement Improvement | 08/17/2009 | 08/10/2009 | 12/01/2010 | 2163357 | 1.5
2575 | Iowa | POTTAWATTAMIE | OMAHA (NE)-IA | 5 | 1642658 | The city of Council Bluffs, Iowa is repairing the transverse joints on 35th Street from Nebraska Avenue to 23rd Avenue. The project will extend the life of the existing Portland Cement Concrete (PCC) | Pavement Improvement | 12/02/2009 |  |  | 478467.01 | 3
2576 | Iowa | POTTAWATTAMIE |  | 5 | 1642659 | The new construction of a Bicycle Pedestrian Trail along the east side of 13th Street between Avenue A and Avenue H in the city of Council Bluffs in Pottawattamie county. This project will increase s | Transportation Enhancements | 10/15/2009 |  | 12/01/2010 | 200000 | 0.51
2577 | Iowa | RINGGOLD |  | 5 | 1691038 | This project is located on US 169 in Ringgold County from the intersection with Iowa 2 in Mount Ayr north 13 miles to the Union County line. The project will recycle three inches of the existing pave | Pavement Improvement | 07/10/2009 |  | 07/01/2010 | 4382345 | 12.9
2578 | Iowa | UNION |  | 5 | 1692021 | This project is located on US 169 in Union County, starting in Afton and proceeding south approximately 9 miles to the Union/Ringgold county line near Shannon City. The project will recycle three inc | Pavement Improvement | 07/10/2009 |  | 07/01/2010 | 3373398 | 8.7
2579 | Iowa | UNION |  | 5 | 1710609 | Creston, Iowa on East Prairie Street from Cherry Street to Mulberry Street. The project consists of a two inch hot-mix asphalt overlay which will provide a smoother ride on the roadway. The Poplar St | Pavement Improvement | 10/13/2009 | 09/10/2009 | 12/01/2010 | 62778 | 0.1
2580 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 1827659 | This project consists of a number of different sections on multiple roadways in Davenport, Iowa: Jersey Ridge Road, Northwest Boulevard, Division Street, Locust Street, and Rockingham Road in three lo | Pavement Improvement | 06/08/2009 | 07/20/2009 | 12/01/2009 | 1183107 | 0
2581 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 1827660 | The City of Davenport will patch the existing pavement at the intersection of Eastern Avenue and 53rd Street and Pine Street from 53rd Street to Northwest Boulevard to improve pavement conditions. Th | Pavement Improvement | 06/11/2009 | 06/17/2009 | 12/01/2009 | 800000 | 0
2582 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 1827661 | This project will consist of constructing a new raised median along US Highway 67 from Iowa Street to Gaines Street and along US Highway 61 from Gaines Street to Marquette Street in the City of Davenp | Pavement Improvement | 01/26/2010 |  |  | 267842.79 | 0.9
2583 | Iowa | CLINTON |  | 1 | 1855613 | De Witt, Iowa on 11th Street from 6th Avenue to Humeston Road. The roadway will be milled and overlaid with two inches of hot-mix asphalt which will provide a smoother ride. Selected sidewalk ramps a | Pavement Improvement | 06/01/2009 | 06/17/2009 | 12/01/2009 | 201885 | 0
2584 | Iowa | POLK | DES MOINES | 3 | 1945753 | Des Moines, Iowa on 6th Avenue from University Avenue to the Des Moines River Bridge. The roadway will be milled and problem areas will be patched as necessary. Traffic signal loops will be replaced | Pavement Improvement | 05/27/2009 | 07/26/2009 | 12/01/2009 | 543031 | 0.9
2585 | Iowa | WARREN | DES MOINES | 3 | 1945754 | Des Moines, Iowa on Fleur Drive/Blue Street from Beardsley Street to Southwest 9th Street. The existing roadway surface will be milled before being overlaid with five inches of asphalt. The five inc | Pavement Improvement | 05/27/2009 |  | 12/01/2009 | 496951 | 1.2
2586 | Iowa | POLK | DES MOINES | 3 | 1945755 | Des Moines, Iowa on McKinley Avenue from Fleur Drive to South Union Street. The existing roadway surface will be milled and the traffic signal loop detectors will be replaced before being overlaid wi | Pavement Improvement | 08/17/2009 | 09/29/2009 | 12/01/2010 | 339405 | 1.5
2587 | Iowa | POLK | DES MOINES | 3 | 1945756 | This project is in the city of Des Moines on Southeast 5th Street from East County Line Road to East Army Post Road. Three inches of hot-mix asphalt will be placed to improve driving quality and saf | Pavement Improvement | 08/17/2009 | 09/14/2009 | 12/01/2010 | 467340 | 1
2588 | Iowa | POLK | DES MOINES | 3 | 1945757 | This project is in the city of Des Moines on McKinley Avenue from South Union Street to Southeast 5th Street. The project consists of widening and placement of a 10-inch portland cement concrete surf | Pavement Improvement | 08/17/2009 |  | 12/01/2010 | 1286228 | 0.3
2589 | Iowa | POLK | DES MOINES | 3 | 1945758 | In Polk county, the city of Des Moines will improve safety, driving quality, and capacity through portland cement concrete pavement widening with hot-mix asphalt resurfacing along Army Post Road fro | Pavement Improvement | 12/07/2009 |  |  | 1000000 | 0.2
2590 | Iowa | POLK | DES MOINES | 3 | 1945759 | The construction of the Principal Riverwalk multi-purpose trail extensions run along the West side of Des Moines River from Grand Avenue south to Walnut Street and from Court Avenue south to Vine Stre | Transportation Enhancements | 10/06/2009 | 12/02/2009 | 12/01/2010 | 2849000 | 0.2
2591 | Iowa | DUBUQUE | DUBUQUE (IL) | 1 | 2100646 | The city of Dubuque, Iowa, is purchasing the right-of-way for the construction of a new roadway to be known as the Southwest Arterial. The roadway will connect US highway 20 to US Highway 61. The pro | Other | 09/10/2009 |  |  | 2909534 | 6.2
2592 | Iowa | DUBUQUE |  | 1 | 2160609 | This project replaces the bridge supports, which are in poor condition, to extend the service life of the bridge. The project also improves the aesthetics of the bridge to blend with the 1st Street i | Bridge Improvement | 12/07/2009 |  |  | 156901 | 0
2593 | Iowa | BENTON |  | 3 | 2186045 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on US 218 over Pratt Creek approximately 7.5 miles West of Vinton. | Bridge Replacement | 03/06/2009 | 04/20/2009 | 11/01/2009 | 1048906 | 0
2594 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 2290609 | In Scott county, the city of Eldridge will improve safety and mobility with hot-mix asphalt widening along 1st Street north of Trails Road and south of Fisher Court for .24 miles. | Pavement Improvement | 10/13/2009 | 10/21/2009 | 12/01/2010 | 140000 | 3.1
2595 | Iowa | SCOTT |  | 1 | 2290610 | This project provides for the design and engineering of a multi-use trail that will run along the east side of County Road Y-64 from north of the city limits of Eldridge to south of the city limits of | Other | 12/08/2009 | 12/08/2009 |  | 90152.21 | 0
2596 | Iowa | JEFFERSON |  | 2 | 2465617 | The city of Fairfield, Iowa is reconstructing Kirkwood Avenue from 5th Street east to 2nd Street which has deteriorated beyond maintenance repairs. The 0.23 mile long project replaces the old roadway | Pavement Improvement | 06/24/2009 | 08/31/2009 | 12/01/2009 | 283500 | 0.2
2597 | Iowa | LEE |  | 2 | 2697618 | In Lee county, the city of Fort Madison will improve traffic management, safety, mobility, and carrying capacity. These enhancements will be made with structural improvements to pavement and the addit | Pavement Improvement | 06/01/2009 | 06/01/2009 | 12/01/2010 | 550000 | 0
2598 | Iowa | POLK | DES MOINES | 3 | 3125607 | In Polk county, the city of Grimes will improve driving quality, capacity, and safety along South James Street, beginning south of 6th Street and ending north of Urbandale approximately 2.0 miles. Th | Pavement Improvement | 08/10/2009 | 08/24/2009 | 12/01/2010 | 1000000 | 2.2
2599 | Iowa | POWESHIEK |  | 3 | 3127622 | In Poweshiek county, the city of Grinnell will improve driving quality and safety through hot-mix asphalt resurfacing with milling along two sections of road; one along 8th Avenue from West Street (I | Pavement Improvement | 07/06/2009 | 09/10/2009 | 12/01/2009 | 196400 | 1
2600 | Iowa | IDA |  | 5 | 3650603 | In Ida county, the city of Ida Grove will improve driving quality and safety by patching Moorehead Avenue, from 2nd Street to Ohio Street (Iowa 59), with portland cement concrete before placing a ho | Pavement Improvement | 06/01/2009 | 09/08/2009 | 12/01/2009 | 200000 | 0
2601 | Iowa | WARREN |  | 4 | 3680612 | The City of Indianola will improve approximately ¾ of a mile of North Y Street between Iowa Highway 92 and West Euclid Avenue by replacing the existing granular surface with a new concrete pavement. | Pavement Improvement | 06/12/2009 | 10/20/2009 | 12/01/2009 | 494331 | 0
2602 | Iowa | JOHNSON | IOWA CITY | 2 | 3715643 | In Johnson county, the city of Iowa City will improve driving quality and safety through hot-mix asphalt resurfacing with milling along South Riverside Drive (Old Highway 218) beginning south of High | Pavement Improvement | 08/24/2009 | 07/26/2009 | 12/01/2010 | 600000 | 1.6
2603 | Iowa | POLK | DES MOINES | 3 | 3827611 | This project will involve widening of the existing pavement on approximately 0.8 miles of Northwest 86th Street from Chamberry Boulevard to Northwest 62nd Avenue in the City of Johnston. The new conc | Pavement Improvement | 01/26/2010 |  |  | 1144528 | 0.8
2604 | Iowa | MARION |  | 3 | 4040606 | In Marion county, the city of Knoxville will improve driving quality and safety through hot-mix asphalt resurfacing with milling along two sections of road. One along South Roche Street from Robinson | Pavement Improvement | 06/11/2009 | 10/05/2009 | 12/01/2009 | 296950 | 0
2605 | Iowa | SCOTT |  | 1 | 4252601 | This project provides preliminary and final design engineering for the Mississippi River Trail (MRT) that will run along U.S. Highway 67 from the Eastern most city limits of Bettendorf to the Northern | Other | 12/08/2009 | 12/08/2009 |  | 214190 | 0
2606 | Iowa | DELAWARE |  | 1 | 4682621 | In Delaware county, the city of Manchester will improve driving quality and safety through hot-mix asphalt resurfacing along East Main Street from Brewer Street to Bailey Drive. | Pavement Improvement | 11/03/2009 |  | 12/01/2010 | 210309 | 0
2607 | Iowa | JACKSON |  | 1 | 4742615 | In Jackson county, the city of Maquoketa will enhance safety and drainage with improvements to portland cement concrete curb and gutter along North Main Street from Grove Street to Quarry Street. Imp | Pavement Improvement | 05/29/2009 | 07/22/2009 | 12/01/2009 | 244514 | 0
2608 | Iowa | LINN |  | 2 | 4775620 | Marion, Iowa intends to improve North 35th Street from Tower Terrace Road to Indian Creek Road. Improvements will include patching of the existing roadway pavement and grading and construction of bic | New Construction | 01/27/2010 |  |  | 1274994 | 0
2609 | Iowa | LINN |  | 2 | 4775621 | Marion, Iowa intends to reconstruct North 10th Street from Indian Creek Road to Tower Terrace Road. Reconstruction will include intersection modifications, pavement widening, culvert replacement, tra | Pavement Improvement | 01/27/2010 |  |  | 1228500 | 0.7
2610 | Iowa | MARSHALL |  | 4 | 4797612 | In Marshall county, the city of Marshalltown will improve driving quality and safety by resurfacing along Iowa Avenue West, for 70 feet west of Parker Avenue to 648 feet east of south 6th street, wit | Pavement Improvement | 09/09/2009 | 09/24/2009 | 12/01/2010 | 524672 | 3
2611 | Iowa | MUSCATINE |  | 2 | 5330619 | In Muscatine county, the city of Muscatine will improve road safety, drainage, capacity and driving quality. Improvements will be obtained through replacement of portland cement concrete pavement, ce | Pavement Improvement | 06/18/2009 | 08/10/2009 | 12/01/2009 | 733544 | 0.6
2612 | Iowa | STORY |  | 4 | 5405607 | In Story county, the city of Nevada will improve the driving surface, and extend the service life of the pavement along W 4th Street, at U.S. Highway 30 heading north 1.0 mile to 1st Street, by resur | Pavement Improvement | 05/27/2009 | 08/10/2009 | 12/01/2009 | 245333 | 0
2613 | Iowa | JASPER |  | 3 | 5482611 | This project is on East 31st Street North and North 19th Avenue East from 1st Avenue east to East 19th Street in Newton. The project will improve the driving surface and extend the service life of th | Pavement Improvement | 09/21/2009 | 09/23/2009 | 06/06/2010 | 620472 | 0
2614 | Iowa | WAPELLO |  | 2 | 5825637 | This project will increase capacity, improve safety and mobility along Lake Road in the city of Ottumwa in Wapello County. The project begins at the city limits along Lake Road and heads north for | Pavement Improvement | 06/15/2009 | 10/05/2009 | 12/01/2009 | 632498 | 1.5
2615 | Iowa | WAPELLO |  | 2 | 5825638 | In Wapello county, the city of Ottumwa will conduct structural enhancements including hot-mix asphalt resurfacing and portland cement concrete patching along .74 miles of roadway on Madison Avenue f | Pavement Improvement | 06/15/2009 | 10/05/2009 | 12/01/2009 | 390447 | 1
2616 | Iowa | MARION |  | 3 | 5947613 | In Marion county, the city of Pella will replace deteriorating pavement on Independence Street heading south along Oskaloosa Street to southeast 9th Street. Smoother longer lasting pavement will be p | Pavement Improvement | 06/01/2009 | 06/01/2009 | 12/01/2010 | 323163 | 1
2617 | Iowa | DALLAS |  | 4 | 5970610 | This project will be rehabilitating the pavement along three roadways within the City of Perry totaling approximately 0.96 miles: Park Street from 1st Avenue to the east edge of Violet Hill Cemetery, | Pavement Improvement | 05/21/2009 | 08/22/2009 | 12/01/2009 | 295499 | 0.9
2618 | Iowa | BLACK HAWK | WATERLOO | 1 | 6342600 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 1.1 miles of County Route D-22/ Dubuque Road from the west to | Pavement Improvement | 07/10/2009 | 08/17/2009 | 12/01/2009 | 750000 | 0
2619 | Iowa | WOODBURY |  | 5 | 6890606 | The City of Sergeant Bluff will reconstruct approximately 0.3 miles of South Lewis Boulevard from 1st Street to Topaz Drive. The new concrete driving surface will improve ride quality and reduce main | Pavement Improvement | 06/08/2009 | 08/03/2009 | 12/01/2009 | 564300 | 0
2620 | Iowa | SIOUX | SIOUX CITY (NE-SD) | 5 | 7055621 | This project will be rehabilitating the pavement along three roadways within the City of Sioux Center totaling 0.65 miles: 2nd Avenue from 4th Street SW to 3rd Street NW, 3rd Street NE from 1st Avenue | Pavement Improvement | 05/18/2009 | 09/10/2009 | 12/01/2009 | 370399 | 0
2621 | Iowa | WOODBURY | SIOUX CITY (NE-SD) | 5 | 7057662 | The City of Sioux City will reconstruct and widen approximately ½ mile of South Martha Street from Stone Avenue to Gordon Drive. The new concrete driving surface will improve ride quality and capacit | Pavement Improvement | 06/25/2009 | 06/12/2009 | 12/01/2009 | 792853 | 0
2622 | Iowa | WOODBURY | SIOUX CITY (NE-SD) | 5 | 7057663 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on five sections of roadway within the City of Sioux City totaling 12.5 blocks: 3rd Street from Water Street | Pavement Improvement | 06/09/2009 | 06/29/2009 | 12/01/2009 | 495533 | 0
2623 | Iowa | JOHNSON |  | 2 | 7855606 | This project will replace existing deteriorated pavement with new full-depth portland cement concrete pavement patches on Sunset Street from Koser Avenue to Highland Drive and Melrose Avenue from Suns | Pavement Improvement | 01/29/2010 |  |  | 50000 | 0
2624 | Iowa | POLK | DES MOINES | 3 | 7875632 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 1 mile of Iowa 100th Street from Douglas Avenue to Hickman Road in Urbandale. | Pavement Improvement | 01/21/2010 |  |  | 1200000 | 0
2625 | Iowa | BLACK HAWK | WATERLOO | 1 | 8155708 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on four sections of roadway within the City of Waterloo totalling 1.93 miles: Broadway Street from Donald St | Pavement Improvement | 05/22/2009 | 07/20/2009 | 12/01/2009 | 1517000 | 1.9
2626 | Iowa | BLACK HAWK | WATERLOO | 1 | 8155709 | This project provides for construction of a bicycle and pedestrian trail on the south bank of the Cedar River from West 6th Street to West 18th Street in the city of Waterloo in Blackhawk County. Thi | Transportation Enhancements | 01/26/2010 |  |  | 477197 | 1.069
2627 | Iowa | BREMER |  | 1 | 8190623 | This project will upgrade traffic signals on Highway 3 (Bremer Avenue) in Waverly, Iowa at the following intersections; 15th Street West, 10th Street West, 6th Street West, 4th Street West, 1st Street | Safety/Traffic Management | 12/23/2009 |  |  | 394998 | 0
2628 | Iowa | POLK | DES MOINES | 3 | 8477610 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 1.6 miles of 73rd Street from Center Street to Hickman Road i | Pavement Improvement | 06/16/2009 | 07/08/2009 | 12/01/2010 | 538000 | 0
2629 | Iowa | ADAIR |  | 5 | C001071 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on 200th street over the West Fork of the Middle Nodaway River 0.5 miles East of Bridgewate | Bridge Replacement | 06/17/2009 | 06/30/2009 | 12/01/2009 | 312195 | 0.1
2630 | Iowa | ADAMS |  | 5 | C002054 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2.8 miles of County Route N26 from the town of Nodaway | Pavement Improvement | 08/24/2009 | 08/24/2009 | 12/01/2010 | 217179 | 2.8
2631 | Iowa | APPANOOSE |  | 2 | C004077 | This project consists of applying a hot mix asphalt overlay at two locations in Appanoose County. One location is approximately 2.8 miles on County Route T14 from Iowa Highway 2 to just north of the | Pavement Improvement | 07/08/2009 | 09/21/2009 | 12/01/2009 | 581000 | 3.3
2632 | Iowa | APPANOOSE |  | 2 | C004078 | This project provides for construction of a box culvert extension over Ham Creek on the south side of county road J18 east of Honey Creek Resort State Park, north of Rathbun Lake in Appanoose county. | Transportation Enhancements | 07/08/2009 | 07/20/2009 | 06/01/2009 | 150000 | 0.26
2633 | Iowa | BENTON |  | 3 | C006078 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 5.7 miles of County Route | Pavement Improvement | 08/24/2009 | 09/21/2009 | 12/01/2010 | 888727 | 5.5
2634 | Iowa | BLACK HAWK |  | 1 | C007116 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 2.8 miles of County Route | Pavement Improvement | 06/11/2009 |  | 12/01/2009 | 812212 | 3.5
2635 | Iowa | BOONE |  | 4 | C008053 | The project is located on Boone County Route R-21 which is also known as Nature Road. Boone County is placing Hot Mix Asphalt Resurfacing over Cold In-Place Recycling of the existing asphalt surface | Pavement Improvement | 05/13/2009 |  | 12/01/2009 | 558263 | 6.5
2636 | Iowa | BREMER |  | 1 | C009061 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 3.6 miles of County Route | Pavement Improvement | 07/20/2009 | 09/14/2009 | 12/01/2009 | 650000 | 3.5
2637 | Iowa | BUCHANAN |  | 1 | C010067 | This project will improve the driving surface and extend the life of the pavement by applying an unbonded concrete overlay on approximately 6.8 miles of County Route D22 from County Route V65 to Golf | Pavement Improvement | 05/13/2009 | 05/26/2009 | 12/01/2009 | 1730000 | 7
2638 | Iowa | BUENA VISTA |  | 5 | C011067 | This project will improve the driving surface and extend the life of the pavement by applying an unbonded concrete overlay on approximately 1.6 miles of 600th Street (East Milwaukee Road) from Geising | Pavement Improvement | 05/14/2009 | 05/26/2009 | 12/01/2009 | 717251 | 1.5
2639 | Iowa | CALHOUN |  | 4 | C013079 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 12 miles of County Route D15 from the Sac/Calhoun Count | Pavement Improvement | 08/24/2009 | 09/21/2009 | 12/01/2010 | 2000000 | 12
2640 | Iowa | CARROLL |  | 5 | C014124 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 7 miles of County Route N41 from US Highway 30 to Count | Pavement Improvement | 05/20/2009 | 07/06/2009 | 12/01/2009 | 1000000 | 9.9
2641 | Iowa | CARROLL |  | 5 | C014126 | For the reconstruction of a 13.5 mile segment of the Sauk Rail Trail from the city of Maple River Junction, which is just north of Highway 30, in Carroll County through the city of Breda towards the c | Transportation Enhancements | 09/24/2009 |  | 06/12/2010 | 1000000 | 12.9
2642 | Iowa | CASS |  | 5 | C015050 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 6.4 miles of County Route G35 from County Route N28 to | Pavement Improvement | 07/02/2009 | 07/06/2009 | 12/01/2009 | 1500000 | 6.5
2643 | Iowa | CEDAR |  | 2 | C016078 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 4.1 miles of County Route | Pavement Improvement | 08/17/2009 |  | 12/01/2010 | 773396 | 4.5
2644 | Iowa | CERRO GORDO |  | 4 | C017059 | This project includes performing cracking and seating of the existing concrete pavement and then doing a hot mix asphalt overlay. The work will be done on County Route B30 from the city of Mason City | Pavement Improvement | 05/28/2009 | 09/08/2009 | 12/01/2009 | 1009770.74 | 4.5
2645 | Iowa | CHEROKEE |  | 5 | C018054 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 3 miles of County Route M | Pavement Improvement | 05/27/2009 | 09/02/2009 | 12/01/2009 | 500000 | 3
2646 | Iowa | CLARKE |  | 5 | C020071 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2 miles of County Route H45 at three separate locations | Pavement Improvement | 07/10/2009 | 09/08/2009 | 12/01/2009 | 748000 | 1
2647 | Iowa | CLINTON |  | 1 | C023082 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 10.7 miles of County Route | Pavement Improvement | 06/03/2009 | 08/03/2009 | 12/01/2009 | 524593 | 6
2648 | Iowa | CRAWFORD |  | 5 | C024088 | The project is located on Crawford County Route (CCR) M55 (330th Street) and CCR E53 (S Avenue). Crawford County is replacing the existing Portland Cement Concrete roadway surface with a new Portland | Pavement Improvement | 05/14/2009 | 06/22/2009 | 12/01/2009 | 1391865.1 | 6.8
2649 | Iowa | DALLAS |  | 4 | C025075 | The project is located on Dallas County Route (DCR) R16 (R Avenue). Dallas County is replacing the existing Portland Cement Concrete roadway surface with a new Portland Cement Concrete roadway surfac | Pavement Improvement | 06/03/2009 | 07/08/2009 | 12/01/2009 | 726674 | 4.2
2650 | Iowa | DECATUR |  | 5 | C027042 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 1.9 miles of County Route J14 from Interstate 35 to US | Pavement Improvement | 07/01/2009 | 09/08/2009 | 12/01/2009 | 368000 | 2
2651 | Iowa | DELAWARE |  | 1 | C028067 | This project will provide an improved driving surface, extension of the life of the pavement, and improved site drainage by applying a hot mix asphalt overlay with cold-in-place recycling and the repl | Pavement Improvement | 05/21/2009 | 07/27/2009 | 12/01/2009 | 525953 | 3
2652 | Iowa | DICKINSON |  | 5 | C030037 | This project will improve the driving surface and enhance safety by applying an unbonded concrete overlay and doing necessary shoulder work on approximately 4.2 miles of County Route M27 from 190th St | Pavement Improvement | 06/11/2009 | 07/16/2009 | 12/01/2009 | 1417702 | 4.2
2653 | Iowa | DICKINSON |  | 5 | C030039 | This project provides for resurfacing and renovation of various segments of Spine and Poyzer Trails in the cities of Milford, Arnolds Park, Okoboji, Spirit Lake, and Orleans in Dickinson County. The | Transportation Enhancements | 01/11/2010 |  |  | 186365 | 8.54
2654 | Iowa | EMMET |  | 4 | C032038 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2.9 miles of County Route N22 from County Route A17 to | Pavement Improvement | 05/21/2009 | 07/17/2009 | 12/01/2009 | 487033 | 2.9
2655 | Iowa | EMMET |  | 4 | C032039 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2 miles of Emmet County Route A22 (170th Ave.) from the Dickinson/Emmet County line east to the Es | Pavement Improvement | 05/21/2009 | 07/17/2009 | 12/01/2009 | 597840 | 3.3
2656 | Iowa | FAYETTE |  | 1 | C033106 | This project consists of applying a concrete overlay on Fayette County Route V68 (W Ave.) from U.S. Highway 18 northerly to 3rd St. in the city of Waucoma. The project also includes a concrete overla | Pavement Improvement | 05/21/2009 |  | 12/01/2009 | 1920000 | 8
2657 | Iowa | FLOYD |  | 4 | C034077 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 7.5 miles of Floyd County Route B60 (270th St.) from the Cerro Gordo/Floyd County line east to Ind | Pavement Improvement | 05/15/2009 | 06/30/2009 | 12/01/2009 | 1268424.36 | 7.4
2658 | Iowa | FRANKLIN |  | 4 | C035057 | This project will improve safety along approximately ¾ mile of Franklin County Route S56 (Timber Ave.) from Iowa Highway 3 north to 155th St. on the south limits of the city of Hansell. The existing | Pavement Improvement | 05/20/2009 |  | 12/01/2009 | 229454 | 1
2659 | Iowa | GRUNDY |  | 3 | C038085 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2 miles of Grundy County Route T19 (F Ave.) from 1st Street in the city of Wellsburg north, past U | Pavement Improvement | 05/21/2009 |  | 12/01/2009 | 530000 | 2.5
2660 | Iowa | GRUNDY |  | 3 | C038086 | This project provides for construction of the East Lake Trail on the east side of Grundy County Lake located SW of interchange U.S. Highway 20 & County Road T-55 (Union Ave.) which is just SW of the c | Transportation Enhancements | 12/02/2009 |  |  | 433008.94 | 0.78
2661 | Iowa | GUTHRIE |  | 5 | C039052 | This project provides for resurfacing and construction of 5.7 miles of the Raccoon River Valley Trail from Clay Street in the city of Panora to the Trailhead in the city of Yale both in Guthrie county | Transportation Enhancements | 06/04/2009 | 06/04/2009 |  | 782454.72 | 5.34
2662 | Iowa | HAMILTON |  | 4 | C040052 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road R27 over the Boone River 5 miles North of Webster City. | Bridge Replacement | 05/11/2009 |  | 12/01/2009 | 600000 | 0.1
2663 | Iowa | HANCOCK |  | 4 | C041096 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 3.4 miles of Hancock County Route B20 (285th St./Quail Ave./290th St.) from Hancock County Route R | Pavement Improvement | 05/28/2009 | 07/30/2009 | 12/01/2009 | 385000 | 3.5
2664 | Iowa | HARDIN |  | 4 | C042064 | This project will provide an improved driving surface and reduce future roadway maintenance on Hardin County Route S56 from Iowa Highway 175 northerly to Hardin County Route D35 in Steamboat Rock. Th | Pavement Improvement | 05/21/2009 |  | 12/01/2009 | 699400 | 4.5
2665 | Iowa | HARRISON |  | 5 | C043068 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Harrison County Route F32 from U.S. Highway 30 in Woodbine east 4.6 miles | Pavement Improvement | 01/08/2010 |  |  | 1020000 | 4.1
2666 | Iowa | HENRY |  | 2 | C044064 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5.8 miles of Henry County Route J20 (Salem Road) from Ash Avenue in the city of Hillsboro easterly | Pavement Improvement | 06/08/2009 | 09/07/2009 | 12/01/2009 | 1138000 | 5
2667 | Iowa | HOWARD |  | 4 | C045059 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5 miles of Howard County Route V26 (Jade Ave.) from Iowa Highway 9 north to Howard County Route A2 | Pavement Improvement | 05/21/2009 | 05/26/2009 | 12/01/2009 | 960000 | 5
2668 | Iowa | IDA |  | 5 | C047045 | The project is located on Ida County Route (ICR) M15 (240th Street). Ida County is replacing the existing Portland Cement Concrete (PCC) roadway surface with a new PCC roadway surface which includes | Pavement Improvement | 07/02/2009 | 08/03/2009 | 12/01/2009 | 500000 | 0
2669 | Iowa | IOWA |  | 3 | C048056 | This project will provide an improved driving surface and reduce future roadway maintenance on Iowa County Route F67 (325th St.) from Iowa County Route V52 (H Ave.) easterly to North Knoll Ridge St. i | Pavement Improvement | 06/16/2009 | 06/18/2009 | 12/01/2009 | 773396 | 6.5
2670 | Iowa | JACKSON |  | 1 | C049046 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 1.3 miles of Jackson County Route Y53 (Hurstville Road) from Pershing Road in the city of Maquoke | Pavement Improvement | 07/20/2009 | 08/06/2009 | 12/01/2009 | 167439 | 2.6
2671 | Iowa | JACKSON |  | 1 | C049047 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2.6 miles of Jackson County Route D55 (300th St.) from ¼ mile east of U.S. Highway 61 east to 400 | Pavement Improvement | 07/20/2009 | 08/06/2009 | 12/01/2009 | 400000 | 2.5
2672 | Iowa | JASPER |  | 3 | C050087 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5.2 miles of Jasper County Route T38 from Mahaska/Jasper County line north to the Skunk River Brid | Pavement Improvement | 07/02/2009 |  | 12/01/2009 | 850142 | 5.1
2673 | Iowa | JEFFERSON |  | 2 | C051043 | This project will replace a narrow bridge with a new bridge. The bridge is on County Road V64/Douds Road over Lick Creek approximately 3 miles South of Libertyville. | Bridge Replacement | 12/11/2009 |  |  | 347681 | 0
2674 | Iowa | JOHNSON |  | 2 | C052090 | This project will reconstruct approximately 0.8 miles of Johnson County Route F12 (120th St.) and 1.1 miles of Iowa Highway 965 near the city of Swisher. County Route F12 will be rebuilt from 925 fee | Pavement Improvement | 12/29/2009 |  |  | 556302 | 0.6
2675 | Iowa | JOHNSON |  | 2 | C052093 | This project consists of applying a concrete overlay on Johnson County Route W64 (Oak Crest Hill Road) from the Washington/Johnson County line northerly to the south city limit of Hills (approximately | Pavement Improvement | 12/14/2009 |  |  | 556302 | 0.8
2676 | Iowa | JOHNSON |  | 2 | C052094 | This project provides for construction of the 1.5 mile extension of Dubuque Street Trail along Dubuque Street (County Road W-66) from West Overlook Road northwest to 275th Street just southeast of th | Transportation Enhancements | 08/17/2009 |  | 12/01/2009 | 252000 | 1.3
2677 | Iowa | JONES |  | 1 | C053066 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Jones County Route E34 (Fairview Rd.) from Quaker Ln. (just east of the ci | Pavement Improvement | 10/16/2009 |  | 12/01/2010 | 863137 | 2.8
2678 | Iowa | KEOKUK |  | 3 | C054082 | This project will improve drainage along and under Keokuk County Route V5G by replacing multiple pipe culverts under the 2.8 miles of roadway from Iowa Highway 149 to Iowa Highway 78 in the city of Ol | Pavement Improvement | 08/24/2009 |  | 12/01/2010 | 380278 | 11.2
2679 | Iowa | KOSSUTH |  | 4 | C055128 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 10 miles of Kossuth County Route R14 (240th Ave.) from U.S. Highway 18 (near the city of Wesley) n | Pavement Improvement | 07/28/2009 | 08/03/2009 | 12/01/2009 | 1428688 | 11
2680 | Iowa | LINN |  | 2 | C057102 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Linn County Route W45 (Troy Mills Rd.) from just north of Linn County Rout | Pavement Improvement | 05/20/2009 | 08/24/2009 | 12/01/2009 | 896785 | 2.7
2681 | Iowa | LOUISA |  | 2 | C058039 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 12.6 miles of Louisa County Route X99 from just east of the Iowa River Bridge (near the city of Wa | Pavement Improvement | 07/02/2009 | 09/14/2009 | 12/01/2010 | 1300000 | 12.5
2682 | Iowa | LUCAS |  | 3 | C059045 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 0.9 miles of Albia Road (475th Lane) in the city of Chariton from S. 5th Street southeasterly to U | Pavement Improvement | 10/21/2009 | 09/07/2009 | 12/01/2009 | 399000 | 1
2683 | Iowa | MADISON |  | 4 | C061083 | This project will provide an improved driving surface by applying an asphalt overlay to various locations on Madison County Route G4R (Cumming Road) between Quail Ridge Trail (approximately 6 miles no | Pavement Improvement | 06/03/2009 | 09/21/2009 | 12/01/2009 | 569170 | 3.5
2684 | Iowa | MAHASKA |  | 3 | C062066 | This project will replace the existing deteriorating pavement with new concrete pavement on approximately 2.2 miles of Osburn Avenue from Iowa Highway 23 to Iowa Highway 92 in Mahaska County. The new | Pavement Improvement | 06/02/2009 | 08/31/2009 | 12/01/2009 | 852647 | 2.1
2685 | Iowa | MARION |  | 3 | C063096 | This project will provide an improved driving surface by applying an asphalt overlay on Marion County Route G71 from Iowa Highway 5 southeasterly to the approximately ¼ mile north of 2nd Street in the | Pavement Improvement | 05/01/2009 | 05/07/2009 | 12/01/2009 | 314043 | 5
2686 | Iowa | MARION |  | 3 | C063097 | This project will provide an improved driving surface by applying an asphalt overlay on Marion County Route G76 from 1.5 miles east of Marion County Route S45 (southeast of the city of Melcher-Dallas) | Pavement Improvement | 05/01/2009 | 05/08/2009 | 12/01/2009 | 311651 | 1.5
2687 | Iowa | MARSHALL |  | 4 | C064109 | Marshall County will resurface 3.5 miles of County Road E-67 with new asphalt between Underwood and Yates Avenue west of the City of Gilman. This project will improve driving quality by providing a mo | Pavement Improvement | 05/14/2009 |  | 12/01/2009 | 805600 | 3.5
2688 | Iowa | MITCHELL |  | 4 | C066039 | Mitchell County will overlay 2 miles of County Road A-23 with new concrete between Walnut Avenue and Addison Avenue northeast of the City of McIntire. This project will improve driving quality and sig | Pavement Improvement | 05/21/2009 |  | 12/01/2009 | 400000 | 2
2689 | Iowa | MONONA |  | 5 | C067062 | The project is located on Monona County Road (MCR) E60. Monona County is improving the existing gravel roadway with a drainage system and new gravel surface. The project is located approximately 3.6 | Pavement Improvement | 05/26/2009 | 07/06/2009 | 12/01/2009 | 485537 | 1.7
2690 | Iowa | MONROE |  | 3 | C068063 | Monroe County will widen and resurface 1.6 miles of County Road H-35 with new asphalt south of the City of Albia. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 06/16/2009 | 09/14/2009 | 12/01/2009 | 624000 | 1.6
2691 | Iowa | MONTGOMERY |  | 5 | C069039 | Montgomery County will overlay 1.7 miles of County Road H-54 with new concrete east of the City of Colburg to Iowa Highway 48. This project will improve driving quality and significantly extend the li | Pavement Improvement | 11/23/2009 |  | 12/01/2010 | 405610 | 2.2
2692 | Iowa | MUSCATINE |  | 2 | C070049 | Muscatine County will resurface 2.5 miles of County Road F-70 with new asphalt between County Road X-54 and Iowa Highway 38 north of the City of Muscatine. Four inches of the existing asphalt road wil | Pavement Improvement | 07/17/2009 | 10/26/2009 | 12/01/2009 | 733544 | 2.5
2693 | Iowa | PALO ALTO |  | 4 | C074092 | Palo Alto County will widen and resurface 2 miles of County Road N-20 with new asphalt between the northern city limits of Ruthven and the intersection of County Road B-25 and 355th Avenue. This proje | Pavement Improvement | 05/20/2009 | 09/22/2009 | 12/01/2009 | 659874 | 2
2694 | Iowa | PLYMOUTH |  | 5 | C075120 | Plymouth County will resurface 3 miles of County Road C-12 with new asphalt between County Road K-22 and County Road K-30 east of the City of Craig. Three inches of the existing asphalt road will be r | Pavement Improvement | 06/05/2009 | 06/01/2009 | 12/01/2009 | 375000 | 3
2695 | Iowa | PLYMOUTH |  | 5 | C075121 | Plymouth County will resurface 1 mile of County Road K-30 with new asphalt between County Road C-12 and 100th Street north of the City of Craig. Three inches of the existing asphalt road will be recyc | Pavement Improvement | 06/05/2009 | 06/01/2009 | 12/01/2009 | 125000 | 1
2696 | Iowa | PLYMOUTH |  | 5 | C075122 | Plymouth County will replace 5.4 miles of County Road K-22 with new concrete between the Woodbury County border and County Road C-60 north of the City of Sioux City. This project will improve driving | Pavement Improvement | 11/20/2009 |  |  | 1189278 | 5.5
2697 | Iowa | POLK | DES MOINES | 3 | C077168 | Polk County will resurface 5.7 miles of Northwest/Northeast 118th Avenue with new asphalt between Northwest Sheldahl Drive and U.S. Highway 69 east of the City of Polk City. This project will improve | Pavement Improvement | 05/06/2009 |  | 12/01/2009 | 1950000 | 5.5
2698 | Iowa | POLK |  | 3 | C077169 | Polk County will resurface 3.5 miles of various city roads with new asphalt. Locations include Northwest 110th Avenue between Iowa Highway 17 and Northeast 121st Street northwest of the City of Des Mo | Pavement Improvement | 05/06/2009 |  | 12/01/2009 | 418779 | 3.5
2699 | Iowa | POWESHIEK |  | 3 | C079041 | Poweshiek County will resurface 2.7 miles of County Road F-62 with new asphalt between the Jasper County border and Iowa Highway 146 west of the City of Searsboro. Four inches of the existing asphalt | Pavement Improvement | 07/06/2009 |  | 12/01/2009 | 619700 | 3
2700 | Iowa | RINGGOLD |  | 5 | C080049 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road P64 over a tributary to Lotts Creek 3.7 miles Southwest of Kellerton. | Bridge Replacement | 08/12/2009 | 08/14/2009 | 12/01/2010 | 312555 | 0
2701 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | C082039 | Scott County will resurface 5.1 miles of County Road Y-48 with new asphalt between Iowa Highway 22 and County Road F-65 west of the City of Davenport. This project will improve driving quality by prov | Pavement Improvement | 05/26/2009 | 06/18/2009 | 12/01/2009 | 2100000 | 4
2702 | Iowa | SCOTT |  | 1 | C082042 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road F33/St. Ann’s Road over Mason Creek approximately 3 miles Northwest of Long | Bridge Replacement | 09/21/2009 | 10/02/2009 | 12/01/2010 | 299524.5 | 0
2703 | Iowa | SCOTT |  | 1 | C082044 | The project is for the replacement of a Reinforced Concrete Box (RCB) Culvert, Single Box, by Scott County. The existing RCB Culvert had deteriorated, and the structure no longer serves the drainage | New Bridge Construction | 09/21/2009 | 09/26/2009 | 12/01/2010 | 134516 | 0
2704 | Iowa | SCOTT |  | 1 | C082046 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road Y48/Maysville Road over Hickory Creek approximately 1.5 miles Southeast of M | Bridge Replacement | 09/28/2009 |  | 06/01/2010 | 288203.93 | 0
2705 | Iowa | SHELBY |  | 5 | C083046 | Shelby County will resurface 5.6 miles of County Road F-58 with new asphalt between Maple Road and County Road M-47 south of the City of Harlen. This project will improve driving quality by providing | Pavement Improvement | 08/17/2009 | 08/24/2009 | 12/01/2010 | 1400000 | 5.6
2706 | Iowa | SIOUX |  | 5 | C084130 | Sioux County will resurface 4.9 miles of County Road L-14 with new asphalt between U.S. Highway 18 and the Lyon County border north of the City of Boyden. Three inches of the existing asphalt road wil | Pavement Improvement | 05/18/2009 | 07/27/2009 | 12/01/2009 | 1052216 | 5
2707 | Iowa | SIOUX |  | 5 | C084132 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Harrison Avenue over a small stream 1 mile east and 3.5 miles South of Maurice. | Bridge Replacement | 05/18/2009 | 08/03/2009 | 12/01/2009 | 330396.12 | 0
2708 | Iowa | STORY |  | 4 | C085102 | Story County will resurface 4 miles of County Road E-29 with new asphalt between U.S. Highway 65 and the Marshall County border north of the City of Colo. This project will improve driving quality by | Pavement Improvement | 05/20/2009 | 07/20/2009 | 12/01/2009 | 858307 | 4
2709 | Iowa | TAMA |  | 3 | C086074 | Tama County will resurface 9.8 miles of various county roads south of the City of Tama with new asphalt. Locations include County Road E-69 between Iowa Highway 146 and U.S. Highway 63, and County Roa | Pavement Improvement | 06/17/2009 |  | 12/01/2009 | 966635.42 | 10
2710 | Iowa | TAYLOR |  | 5 | C087037 | This project will install longitudinal subdrains along both sides of the existing roadway for Taylor County Road N44 from the Missouri State Line north for 4.3 miles to Taylor County Road J55. The su | Pavement Improvement | 01/12/2010 |  |  | 201766 | 3.5
2711 | Iowa | TAYLOR |  | 5 | C087038 | This project will install longitudinal subdrains along both sides of the existing roadway for Taylor County Road P14 from the Missouri State Line north for 2.7 miles to Taylor County Road J55 and on T | Pavement Improvement | 01/12/2010 |  |  | 152496 | 3.5
2712 | Iowa | UNION |  | 5 | C088040 | Union County will resurface 3 miles of County Road P-33 with new asphalt between County Road H-17 and Adair-Union Street north of the City of Creston. This project will improve driving quality by prov | Pavement Improvement | 05/12/2009 | 05/19/2009 | 12/01/2009 | 437751 | 3
2713 | Iowa | VAN BUREN |  | 2 | C089057 | Van Buren County will remove the top three inches of existing pavement on County Road V-64 and resurface it with new asphalt between Iowa Highway 16 and the Jefferson-Van Buren County line west of the | Pavement Improvement | 05/14/2009 | 06/03/2009 | 12/01/2009 | 320993 | 3.4
2714 | Iowa | WAPELLO |  | 2 | C090060 | Wapello County will resurface 3.8 miles of various county roads near the City of Ottumwa with new asphalt. Locations include County Road H-21 between Blackhawk Road and County Road H-27, and County Ro | Pavement Improvement | 05/15/2009 | 05/08/2009 | 12/01/2009 | 423752 | 12.5
2715 | Iowa | WARREN |  | 4 | C091081 | Warren County will resurface 3.2 miles of County Road S-23 with new asphalt between County Road G-24 and Iowa Highway 5 west of the City of Hartford. This project will improve driving quality by provi | Pavement Improvement | 05/18/2009 | 06/08/2009 | 12/01/2009 | 576146 | 3.2
2716 | Iowa | WASHINGTON |  | 2 | C092075 | Washington County will overlay 4.2 miles of County Road W-64 with new concrete between 160th Street and Iowa Highway 22 east of the City of Riverside. This project will improve driving quality and sig | Pavement Improvement | 05/14/2009 | 08/24/2009 | 12/01/2009 | 732691 | 5.6
2717 | Iowa | WEBSTER |  | 4 | C094082 | This project will repair a bridge, which is in poor condition, by replacing the bridge deck. The bridge is on County Road C66 over Lizard Creek 5 miles West of Clare. | Bridge Improvement | 07/01/2009 |  | 12/01/2009 | 350000 | 0
2718 | Iowa | WINNEBAGO |  | 4 | C095055 | Winnebago County will resurface 3.7 miles of County Road R-60 with new asphalt between U.S. Highway 69 and the southern city limits of Scarville. This project will improve driving quality by providing | Pavement Improvement | 05/13/2009 | 06/15/2009 | 12/01/2009 | 532664.81 | 3.7
2719 | Iowa | WINNESHIEK |  | 4 | C096101 | Winneshiek County will overlay 2.2 miles of County Road V-68 with new concrete between the Fayette County border and Iowa Highway 24 in the City of Jackson Junction. This project will improve driving | Pavement Improvement | 05/21/2009 |  | 12/01/2009 | 664000 | 2.2
2720 | Iowa | WOODBURY |  | 5 | C097107 | This project will mill and place three and a half inches of hot-mix asphalt for 1.6 miles of Correctionville Road from Sioux City’s city limits to just past Buchanan Ave. The project will create a sm | Pavement Improvement | 05/26/2009 | 07/14/2009 | 12/01/2009 | 639833 | 1.8
2721 | Iowa | WOODBURY |  | 5 | C097108 | This project will mill and place four inches of pavement on county road L-37 for approximately 10.7 miles from near Danbury, IA to county road D-38. The project will improve pavement condition and sa | Pavement Improvement | 06/02/2009 | 08/24/2009 | 12/01/2009 | 500000 | 10
2722 | Iowa | WORTH |  | 4 | C098050 | This project places a concrete overlay on a bridge deck to extend the service life of the bridge. The bridge is located on 410th Street over the Shell Rock River 1.5 miles east of Kensett. | Bridge Improvement | 08/12/2009 |  | 12/01/2010 | 48418 | 0
2723 | Iowa | WORTH |  | 4 | C098051 | This project places a concrete overlay on a bridge deck to extend the service life of the bridge. The bridge is located on 495th Street over the Shell Rock River approximately 1 mile West and 2.5 mil | Bridge Improvement | 08/12/2009 |  | 12/01/2010 | 32696 | 0
2724 | Kansas | SEDGWICK | WICHITA | 04 | 1351209 | This project will reconstruct the I-135/KTA/47th St. interchange and 47th St from Broadway to Lulu St. This work will improve traffic capacity, operation and safety on these routes. | Pavement Widening | 08/20/2009 | 08/20/2009 | 02/24/2011 | 17131901.18 | 0
2725 | Kansas | STATEWIDE |  | 04 | A116910 | This project will provide skill training for women and minorities in highway construction work in central Kansas for Federal Fiscal Year 2010. | Other | 09/24/2009 | 09/24/2009 |  | 224600 | 0
2726 | Kansas | GOVE |  | 01 | A153401 | This project will replace the pavement on K-23, provide a 28 ft. roadway and replace guardrail as warranted to improve safety along K-23. | Pavement Improvement | 02/23/2009 | 02/23/2009 | 09/06/2010 | 3823789.37 | 8
2727 | Kansas | COMANCHE |  | 01 | C421801 | This project will replace a bridge on County Road 155, 1.0 mile West of Coldwater in Commanche County - improving structural and/or safety concerns. | Bridge Replacement | 11/01/2009 | 12/09/2009 | 05/05/2010 | 320027.86 | 0.25
2728 | Kansas | COWLEY |  | 04 | C422001 | This project will provide a 2 inch asphalt overlay on County Road 164 from Udall to County Road 18 in Cowley County, improving rideability and surface condition. | Pavement Improvement | 08/14/2009 | 08/14/2009 | 11/03/2009 | 877500 | 6.5
2729 | Kansas | ELLIS |  | 01 | C422801 | This project will replace a bridge 5.6 miles South and 0.8 miles West of the city of Walker in Ellis County - improving structural and/or safety concerns. | Bridge Replacement | 11/16/2009 | 11/16/2009 | 05/24/2010 | 491587.92 | 0.2
2730 | Kansas | ATCHISON |  | 02 | C453901 | This project will replace a bridge 4.0 miles North and 4.4 miles East of the city of Shannon in Atchison County - improving structural and/or safety concerns. | Bridge Replacement | 11/30/2009 | 11/30/2009 | 04/12/2010 | 216000 | 0.1
2731 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | C455101 | This project will redeck a bridge 1.4 miles East of the city of Jarbalo in Leavenworth County - improving surface conditions. | Bridge Replacement | 09/01/2009 | 09/01/2009 | 02/08/2011 | 386886.05 | 0.12
2732 | Kansas | BARBER |  | 01 | C455201 | This project will replace a bridge 2.0 miles East of the city of Hazelton on Rural Secondary Route 1381 - improving structural and/or safety concerns. | Bridge Replacement | 11/02/2009 |  | 04/12/2011 | 292272 | 0.2
2733 | Kansas | ROOKS |  | 01 | C455401 | This project resurfaces 2.6 Miles of Rural Secondary Route 916 and 1729 in the City of Woodston in Rooks County - improving surface conditions. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 02/08/2011 | 310000 | 2.6
2734 | Kansas | RENO |  | 01 | C455901 | This project will provide an asphalt overlay on 4th Avenue (Rural Secondary Route-636) from K-14 E to K-96 4th Avenue Interchange in Hutchinson in Reno County - improving surface conditions. | Pavement Improvement | 12/02/2009 |  | 12/23/2009 | 517593 | 0.2
2735 | Kansas | ANDERSON |  | 02 | C456201 | This project will rehabilitate a bridge on Rural Secondary Route1389 4.0 miles South and 1.7 miles East of the city of Harris in Anderson County - improving structural and/or safety concerns. | Bridge Improvement | 07/31/2009 | 07/31/2009 | 05/17/2011 | 57518.74 | 0.03
2736 | Kansas | CHAUTAUQUA |  | 04 | C456301 | This project will provide a 2.5-inch asphalt overlay on Independence Road (Rural Secondary Route 97) for 3.5 Miles in Chautauqua County - improving surface conditions. | Pavement Improvement | 11/13/2009 |  | 11/27/2009 | 442596.26 | 3.5
2737 | Kansas | FRANKLIN |  | 02 | C456501 | This project will provide a 2-inch asphalt overlay on John Brown Road (Rural Secondary Route 1066/259) Between Kentucky Road and Florida in Franklin County - improving surface conditions. | Pavement Improvement | 08/27/2009 | 08/27/2009 | 01/04/2011 | 501252.22 | 5.09
2738 | Kansas | GREENWOOD |  | 01 | C456601 | This project will provide a 2-inch asphalt overlay on Rural Secondary Route 291 from the city of Hamilton to the city of Virgil in Greenwood County - improving surface conditions. | Pavement Improvement | 10/22/2009 | 10/23/2009 | 11/12/2009 | 490000 | 4
2739 | Kansas | ELK |  | 04 | C456701 | This project will provide an asphalt resurfacing of Kansas Street in the city of Longton from US Highway 160 to 6th Street - improving surface conditions. | Pavement Improvement | 11/11/2009 |  | 11/25/2009 | 120751.89 | 0.36
2740 | Kansas | SCOTT |  | 01 | C457901 | This project will provide a 4-inch overlay of Federal Aid Secondary route 1898 2 miles West of K-95 Highway - improving surface conditions. | Pavement Improvement | 08/18/2009 | 09/28/2009 | 02/08/2011 | 461897.23 | 2
2741 | Kansas | STATEWIDE |  | 02 | K507010 | This project will provide skill training for women and minorities in highway construction work in northeast Kansas for Federal Fiscal Year 2010. | Other | 11/03/2009 | 11/03/2009 |  | 200402 | 0
2742 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | K825107 | This project will add two lanes, reconstruct the 95th Street interchange and add noise walls to selected sections. This work will improve traffic capacity, operation and safety on US-69. | Pavement Widening | 06/05/2009 | 06/05/2009 | 01/10/2012 | 31966458.83 | 1.84
2743 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | K825111 | This project will add two lanes & reconstruct US-69 and widen I-35. This work will improve traffic capacity, operation and safety on US-69 and I-35. | Pavement Widening | 06/05/2009 | 06/05/2009 | 01/11/2012 | 51977795.54 | 0
2744 | Kansas | MCPHERSON |  | 01 | K825301 | This project will construct a 4-Lane partial access controlled improvement with a bypass at the City of inman. This work will improve traffic capacity, operation and safety along K-61. | Pavement Widening | 05/06/2009 | 05/06/2009 | 11/23/2011 | 36046133.16 | 7.43
2745 | Kansas | MCPHERSON |  | 01 | K825302 | This project will construct a 4-Lane partial access controlled improvement. This work will improve traffic capacity, operation and safety along K-61. | Pavement Widening | 05/06/2009 | 05/06/2009 | 11/23/2011 | 36839656.44 | 7.06
2746 | Kansas | STATEWIDE | KANSAS CITY (MO) | 03 | K921806 | This project will extend operation of the Operation Green Light System to improve intersection traffic signal coordination on regional arterial routes in the bi-state Kansas City Metropolitan area. I | Other | 07/28/2009 | 07/28/2009 |  | 1000000 | 0
2747 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N037301 | This project will widen College Blvd from 4 to 6 lanes from Pflumm Road to US-69 in Overland Park in Johnson County - improving both capacity and safety. | Pavement Widening | 06/25/2009 |  | 09/08/2009 | 1000000 | 2
2748 | Kansas | BUTLER | WICHITA | 04 | N039001 | This project will improve Andover Road to 5 lanes with a center turn lane, curb and gutter, and a 10-ft bide/ped sidewalk from Harry Street to 1100 Feet South of US-54 in the city of Andover in Butler | Pavement Widening | 09/18/2009 | 09/18/2009 | 07/09/2010 | 1234800 | 0.8
2749 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N046701 | This project will widen 87th Street from 4 to 6 lanes from Renner Blvd. to Ridgeview Road in the city of Lenexa in Johnson County - improving capacity and safety. | Pavement Widening | 12/07/2009 |  | 09/10/2010 | 3000000 | 0.57
2750 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N048101 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on College Blvd From Benson Street to Nall Avenue in the city of Overland Park in Johnson County - improving surface | Pavement Improvement | 10/06/2009 | 10/06/2009 | 03/08/2011 | 2800000 | 2.3
2751 | Kansas | SEDGWICK | WICHITA | 04 | N048801 | This project will provide a full-depth reconstruction of the roadway to the bottom of the base, adding 7 inches of pavement, and striping of West Grand Ave. from Meridian Ave. to North Main Street in | Pavement Improvement | 08/12/2009 |  | 05/09/2011 | 797723.03 | 1
2752 | Kansas | SEDGWICK | WICHITA | 04 | N050001 | This project will provide concrete pavement replacement on Hillside from 9th Street to 12 Street in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 12/01/2009 | 12/01/2009 | 04/25/2011 | 864000 | 0.42
2753 | Kansas | NEOSHO |  | 02 | T033101 | This project will provide improvements to downtown Erie, KS along Main St from Fourth St, north to State St, then west on State St to US Highway 59, to include brick paver accents, curb and gutter, li | Transportation Enhancements | 10/16/2009 | 10/16/2009 | 11/03/2010 | 632470.42 | 0.8
2754 | Kansas | GREENWOOD |  | 04 | T033401 | Restore part of the interior and exterior and establish a transportation museum/welcome center in the former bus depot of the Greenwood Hotel at 300 N Main | Transportation Enhancements | 09/10/2009 | 09/10/2009 | 01/04/2011 | 1313197 | 0
2755 | Kansas | DOUGLAS | LAWRENCE | 03 | T033901 | This project will remove an existing asphalt overlay, provide restoration of historic brick streets and reconstruction of four intersections on New York Street from 9th Street to 12th Street in Lawren | Transportation Enhancements | 12/21/2009 | 12/21/2009 | 10/04/2010 | 946827 | 0
2756 | Kansas | RILEY |  | 02 | T034001 | Restore portions of interior of the historic Isaac Goodnow house in Manhattan, KS including stabilization work on the stairs & interior walls & surface restoration with historically appropriate plaste | Transportation Enhancements | 11/19/2009 | 11/19/2009 | 10/04/2010 | 148400 | 0
2757 | Kansas | STEVENS |  | 01 | T034201 | Project to provide new sidewalks w/ brick pavers, lighting, raised planters, ADA ramps, crosswalks, landscaping, irrigation, fence, benches & trash cans along Main St (US Hwy 56) from 5th to 7th St & | Transportation Enhancements | 11/20/2009 | 11/20/2009 | 10/04/2010 | 1550000 | 0
2758 | Kansas | WYANDOTTE | KANSAS CITY (MO) | 03 | T034401 | This project will provide streetscape improvements from the Kansas Highway 7 off ramp, along Front Street (Kansas Highway 32) to Elm Street, in Bonner Springs, Kansas, and will include decorative stre | Transportation Enhancements | 12/14/2009 | 12/14/2009 | 10/04/2010 | 325135 | 0
2759 | Kansas | DOUGLAS | LAWRENCE | 03 | T034701 | This project will remove an existing six-foot asphalt path and construct a ten-foot concrete path on the south side of Clinton Parkway from east of Wakarusa Drive to K-10 highway in Lawrence, Kansas. | Transportation Enhancements | 12/18/2009 | 12/18/2009 | 10/04/2010 | 800750 | 0
2760 | Kansas | SEDGWICK | WICHITA | 04 | T034801 | This project will construct a concrete ped/bike path from 111th St, along the Mulvane Sports Complex (MSC), then connect to existing path & another path section from 111th St south along Webb Road to | Transportation Enhancements | 10/19/2009 | 10/19/2009 | 10/04/2010 | 254232 | 0
2761 | Kansas | DOUGLAS | LAWRENCE | 03 | U204101 | This project will be a reconstruction of the Intersection of North 2nd Street and Locust Street in the City of Lawrence in Douglas County - improving surface condition and safety. | Safety/Traffic Management | 07/20/2009 | 07/28/2009 | 10/13/2010 | 2000000 | 0.2
2762 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | U223201 | This project will provide a variable mill (removal of existing pavement) and overlay on RS-348 (Nelson/ West 8th Street) From RailRoad to Morgan Street in the city of Edgerton in Johnson County - impr | Pavement Improvement | 10/22/2009 | 10/24/2009 | 03/08/2011 | 158441.76 | 0.95
2763 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223401 | This project will provide a surface overlay, aggregate shoulders, pavement markings, storm sewer improvements on 147th Street from South of Cottonwood Drive North to 4H Road in the city of Lansing in | Pavement Improvement | 10/01/2009 | 10/01/2009 | 03/08/2011 | 265578.16 | 1
2764 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223501 | This project will provide a pedestrian signal on US Highway 24 at NorthStar Drive in the city of Tonganoxie in Leavenworth County - improving safety. | Pavement Improvement | 10/12/2009 | 10/12/2009 | 11/09/2009 | 23800 | 0.01
2765 | Kansas | JEFFERSON |  | 02 | U223601 | This project will provide an overlay to Jefferson Street from Walnut to City Limits in the city of Oskaloosa in Jefferson County - improving surface conditions. | Pavement Improvement | 11/02/2009 | 11/02/2009 | 11/09/2009 | 32082.9 | 0.19
2766 | Kansas | DONIPHAN |  | 02 | U223701 | This project will provide surfacing and culvert work (replacing the Reinforced Concrete Bridge) on Old US-36 (RS-2128) just west of Elm Street in the city of Highland in Doniphan County - improving su | Pavement Improvement | 11/24/2009 | 11/24/2009 | 02/02/2010 | 214150.35 | 0.2
2767 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223901 | This project will provide storm sewer improvements on 4th Street at K-7/73and Spruce K-92 in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 11/02/2009 | 11/02/2009 | 04/12/2011 | 224885.43 | 0.02
2768 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U224001 | This project will provide storm sewer improvements on 5th Ave and Doniphan in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 11/02/2009 | 11/02/2009 | 04/12/2011 | 89586 | 0.02
2769 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U224101 | This project will provide storm sewer improvements on 10th Street and Wellington in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 11/02/2009 | 11/02/2009 | 04/12/2011 | 124435 | 0.02
2770 | Kansas | MONTGOMERY |  | 04 | U225301 | This project will provide an asphalt overlay on 4th Avenue (RS-809) from US 75 to Wood Street in the city of Caney in Montgomery County - improving surface conditions. | Pavement Improvement | 10/12/2009 |  | 10/26/2009 | 138944.29 | 0.57
2771 | Kansas | BOURBON |  | 02 | U225401 | This project will provide an asphalt overlay and curb work on SW National Street from Linker Street to Wall Street in the city of Fort Scott in Bourbon County - improving surface conditions. | Pavement Improvement | 10/01/2009 | 10/06/2009 | 12/10/2009 | 228180 | 0.2
2772 | Kansas | MIAMI |  | 02 | U225501 | This project will provide an asphalt overlay on 8th Street from the North City Limits to Main Street in the city of Osawatomie in Miami County - improving surface conditions. | Pavement Improvement | 10/30/2009 | 10/30/2009 | 11/13/2009 | 88146.75 | 0.2
2773 | Kansas | CRAWFORD |  | 02 | U225601 | This project will provide an asphalt overlay on Broadway Street from Centennial to Williams in the city of Pittsburg in Crawford County - improving surface conditions. | Pavement Improvement | 08/27/2009 | 08/27/2009 | 01/04/2011 | 229353.5 | 0.2
2774 | Kentucky | FAYETTE |  | 6 | 0114004 | CONSTRUCTION OF NEWTOWN PIKE ROADWAY EXTENSION FROM MAIN STREET TO VERSAILLES ROAD IN LEXINGTON, KENTUCKY. | New Construction | 07/10/2009 | 07/10/2009 |  | 11100000 | 0
2775 | Kentucky | BREATHITT |  | 5 | 0151065 | RECONSTRUCTION AND RELOCATION OF KY 15 ROADWAY FROM KY-15 AT JACKSON, KENTUCKY TO A POINT 0.43 MILES NORTH OF KY 15 IN BREATHITT COUNTY. | Pavement Improvement | 10/30/2009 |  |  | 11373292.84 | 0
2776 | Kentucky | BREATHITT |  | 5 | 0151066 | RECONSTRUCTION AND RELOCATION OF KY 15 ROADWAY FROM 0.43 MILES NORTH OF KY 15 AT JACKSON, KENTUCKY TO 0.31 MILES SOUTH OF STILL HOUSE HOLLOW IN BREATHITT COUNTY. | Pavement Improvement | 05/21/2009 | 05/21/2009 |  | 21960000 | 0
2777 | Kentucky | LETCHER |  | 5 | 0151067 | CONSTRUCTION OF LEFT TURN LANE ON KY-15 AT THE END OF EXISTING WHITESBURG BYPASS WEST OF WHITESBURG, KENTUCKY IN LETCHER COUNTY. | Safety/Traffic Management | 05/20/2009 | 05/20/2009 |  | 1600000 | 0.27
2778 | Kentucky | MONROE |  | 1 | 0159006 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-90 ROADWAY FROM 0.34 MILES SOUTH OF BUSHONG ROAD MILEPOINT 12.75 AND EXTENDING NORTHERLY TO 0.68 MILES SOUTH OF CYCLONE ROAD AT MILEPOINT 17.45 IN MONROE C | Pavement Improvement | 05/04/2009 | 05/04/2009 |  | 6804972.87 | 4.7
2779 | Kentucky | LYON, CALDWELL |  | 1 | 0242066 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-24 EAST BOUND AND WEST BOUND LANES FROM 0.5 MILE EAST OF KY-293 AT MILEPOINT 45.133 IN LYON COUNTY TO KY-139 AT MILEPOINT 65.300 IN CALDWELL COUNTY. | Pavement Improvement | 04/03/2009 | 04/03/2009 |  | 12226812 | 20.167
2780 | Kentucky | CAMPBELL | CINCINNATI (OH) | 4 | 0272109 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF US 27 ROADWAY FROM SOUTH OF KY-154 AT MILEPOINT 1.9 TO CAMPBELL COUNTY PARK AT MILEPOINT 5.0 IN CAMPBELL COUNTY. | Pavement Widening | 05/04/2009 | 05/04/2009 |  | 29120000 | 3.1
2781 | Kentucky | KENTON | CINCINNATI (OH) | 4 | 0273013 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF 12TH STREET ROADWAY FROM I-75 TO SCOTT STREET IN COVINGTON, KENTUCKY IN KENTON COUNTY. | Pavement Improvement | 05/22/2009 | 05/22/2009 |  | 7586554 | 0.47
2782 | Kentucky | KENTON | CINCINNATI (OH) | 4 | 0273014 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF 12TH STREET ROADWAY FROM I-75 TO SCOTT STREET IN COVINGTON, KENTUCKY IN KENTON COUNTY. | Pavement Improvement | 07/02/2009 | 07/02/2009 |  | 2175306 | 0.22
2783 | Kentucky | HARDIN | RADCLIFF-ELIZABETHTOWN | 2 | 0401068 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-144 ROADWAY TO PROVIDE HORIZONTAL AND VERTICAL REALIGNMENT OF EXISTING ROADWAY BETWEEN MILEPOINTS 0.8 TO MILEPOINT 1.1 JUST WEST OF KY-1500 AT VINE GROVE, | Safety/Traffic Management | 09/16/2009 | 09/16/2009 |  | 223819.4 | 0.3
2784 | Kentucky | JEFFERSON |  | 3 | 0655098 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-65 IN JEFFERSON COUNTY FROM FERN VALLEY ROAD AT MILEPOINT 128.13 TO MILEPOINT 131.89. | Pavement Improvement | 07/02/2009 | 07/02/2009 |  | 18000000 | 3.158
2785 | Kentucky | TRIGG |  | 1 | 0801075 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF US 68/KY 80 ROADWAY BETWEEN MILEPOINT 0.243 TO MILEPOINT 8.284 IN THE LAND BETWEEN THE LAKES AREA OF TRIGG COUNTY. | Pavement Widening | 04/30/2009 | 04/30/2009 |  | 30000000 | 8.041
2786 | Kentucky | CLINTON |  | 01 | 1271100 | RECONSTRUCTION OF 3.5 MILES OF US 127 IN CLINTON COUNTY BEGINNING AT THE ALBANY BYPASS AND EXTENDING NORTH TO KY 90. | Pavement Improvement | 01/26/2010 |  |  | 17105774.45 | 4.24
2787 | Kentucky | WASHINGTON |  | 2 | 1501096 | CONSTRUCTION OF NEW SPRINGFIELD NORTHWEST BYPASS FROM KY 555 TO US 150 NORTHWEST OF SPRINGFIELD, KENTUCKY. | New Construction | 05/05/2009 | 05/05/2009 |  | 13821653.83 | 3
2788 | Kentucky | ROCKCASTLE |  | 05 | 1501097 | RECONSTRUCTION OF 6 MILES OF US 150 IN ROCKCASTLE COUNTY BEGINNING AT BRODHEAD, KY AND EXTENDING EAST TO US 461 AT MT. VERNON, KY. | Pavement Improvement | 10/29/2009 |  |  | 25500000 | 0
2789 | Kentucky | ROCKCASTLE, LINCOLN |  | 6 | 1501099 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF APPROXIMATELY 7.2 MILES OF US-150 ROADWAY FROM CRAB ORCHARD, KENTUCKY IN LINCOLN COUNTY TO BRODHEAD, KENTUCKY IN ROCKCASTLE COUNTY. | Pavement Improvement | 04/07/2009 | 04/07/2009 |  | 25748598 | 6
2790 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 3 | 2641164 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-264 IN LOUISVILLE, KENTUCKY FROM NEWBURG ROAD AT MILEPOINT 13.710 TO BRECKINRIDGE LANE AT MILEPOINT 18.410 IN JEFFERSON COUNTY. | Pavement Improvement | 09/04/2009 | 09/04/2009 |  | 12078000 | 5.7
2791 | Kentucky | MARION |  | 2 | 3000786 | CONSTRUCTION OF A NEW ROADWAY CONNECTOR FROM THE INTERSECTION OF THE US-68/LEBANON NORTHERN BYPASS (KY 2154) AND EXTENDING SOUTHEAST TO INDUSTRIAL DRIVE IN LEBANON, KENTUCKY IN MARION COUNTY, BEING AP | New Construction | 04/07/2009 | 04/07/2009 |  | 4000000 | 1.3
2792 | Kentucky | JEFFERSON |  | 3 | 3001339 | CONSTRUCTION OF PEDESTRIAN AND SAFETY IMPROVEMENTS INCLUDING SIDEWALKS, LANDSCAPING, AND SIGNAL IMPROVEMENTS ALONG US 60A (EASTERN PARKWAY) AT 3RD STREET IN LOUISVILLE, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 07/02/2009 | 07/02/2009 |  | 2888182.29 | 0
2793 | Kentucky | BULLITT | LOUISVILLE (IN) | 02 | 3001343 | PAVEMENT REHABILITATION TO MILL AND GRIND EXISTING PAVEMENT, AND RESURFACE KY-1526 (KNOB CREEK ROAD) FROM KY-44 TO OLD BROOKS HILL ROAD (KY 2672) IN BULLITT COUNTY BEING APPROXIMATELY 4.9 MILES IN LEN | Pavement Improvement | 10/01/2009 | 10/01/2009 |  | 465996 | 0
2794 | Kentucky | BULLITT | LOUISVILLE (IN) | 02 | 3001344 | PAVEMENT REHABILITATION TO MILL AND GRIND EXISTING PAVEMENT, AND RESURFACE KY 1526 (BELLS MILL ROAD) FROM KY 44 TO KY 61 IN BULLITT COUNTY BEING APPROXIMATELY 3.9 MILES IN LENGTH. | Pavement Improvement | 10/01/2009 | 10/01/2009 |  | 482930 | 0
2795 | Kentucky | BARREN |  | 2 | 3013012 | CONSTRUCTION OF NEW GLASGOW OUTER LOOP ROADWAY FROM US-68 TO THE LOUIE B. NUNN PARKWAY EAST OF GLASGOW, KENTUCKY. | New Construction | 05/21/2009 | 05/21/2009 |  | 15678931 | 0
2796 | Kentucky | DAVIESS |  | 2 | 3023014 | RECONSTRUCTION AND RELOCATION OF THE EXISTING EAST US-60 BYPASS AT OWENSBORO, KENTUCKY (EAST COUNTY CORRIDOR) BEGINNING AT REID ROAD AND EXTENDING NORTHEAST TO EXISTING US 60 EAST OF OWENSBORO, KENTUC | Pavement Improvement | 07/02/2009 | 07/02/2009 |  | 27200000 | 2.2
2797 | Kentucky | BULLITT | LOUISVILLE (IN) | 2 | 5116024 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-61 ROADWAY FROM SOUTH OF JOHN HARPER HIGHWAY (BROOKS ROAD MILEPOINT 19.33) TO THE EXISTING 4-LANE SECTION SOUTH OF CARDINAL AVENUE AT MILEPOINT 210.5 IN BU | Pavement Widening | 05/04/2009 | 05/04/2009 |  | 6055912.18 | 0.7
2798 | Kentucky | NELSON |  | 2 | 5121010 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-245 ROADWAY FROM MILEPOINT 6.5 AT INTERSECTION OF KY-332 NORTH OF BARDSTOWN AND EXTENDING NORTHWEST TO MILEPOINT 7.6 TO THE FLAGET HOSPITAL SITE IN BARDSTO | Pavement Widening | 05/20/2009 | 05/20/2009 |  | 4627074 | 1
2799 | Kentucky | WHITLEY |  | 5 | 5147019 | ASPHALT SURFACING FOR THE RECONSTRUCTED SECTION OF KY 92 ROADWAY FROM CORNBREAD BRANCH NEAR OLD JELLICO ROAD AT MILEPOINT 4.4 AND EXTENDING EAST TO BRIER CREEK BRIDGE AT MILEPOINT 8.4 IN WHITLEY COUNT | Pavement Improvement | 05/01/2009 | 05/01/2009 |  | 6020000 | 4
2800 | Kentucky | MCCREARY |  | 05 | 5147020 | RECONSTRUCTION AND RELOCATION OF KY 92 ROADWAY BETWEEN MILEPOINT 16.6 TO MILEPOINT 21.5 IN MCCREARY COUNTY. | Pavement Improvement | 10/30/2009 |  |  | 14670000 | 0
2801 | Kentucky | KNOX, WHITLEY |  | 5 | 5155009 | CONSTRUCTION OF A NEW ROADWAY CONNECTOR FROM KY-6 AT WOODBINE IN WHITLEY COUNTY EXTENDING NORTHEAST TO THE CORBIN BYPASS IN KNOX COUNTY, BEING APPROXIMATELY 1.2 MILES IN LENGTH. | New Construction | 05/01/2009 | 05/01/2009 |  | 4790000 | 0
2802 | Kentucky | GALLATIN |  | 4 | 5170014 | SAFETY IMPROVEMENTS, REHABILITATION OF PAVEMENT, AND CONSTRUCT NEW BRIDGE DECK WITH BARRIER WALLS ON EXISTING US 127 BIG SUGAR BRIDGE BETWEEN MILEPOINT 3.88 TO MILEPOINT 3.98 IN GALLATIN COUNTY. | Bridge Improvement | 04/03/2009 | 04/03/2009 | 08/13/2009 | 463846.59 | 0.1
2803 | Kentucky | MADISON |  | 6 | 5192004 | CONSTRUCTION OF LEFT TURN LANES AT THE US25 AND KY1156 INTERSECTION AT RICHMOND, KENTUCKY IN MADISON COUNTY. | Safety/Traffic Management | 06/30/2009 | 06/30/2009 |  | 910000 | 0.318
2804 | Kentucky | FRANKLIN |  | 6 | 5196010 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF APPROXIMATELY 2.3 MILES OF US 421 ROADWAY FROM EXISTING US-60/KY 676 INTERCHANGE TO 1600 FEET EAST OF CHENAULT INDUSTRIAL ROAD IN FRANKLIN COUNTY. | Pavement Widening | 05/04/2009 | 05/04/2009 |  | 9934478.4 | 4.6
2805 | Kentucky | HENDERSON | EVANSVILLE (IN) | 01 | 7970012 | WIDENING OF US 41A AT KY 136 TO CONSTRUCT TWO-WAY LEFT TURN LANE | Pavement Improvement | 11/20/2009 |  |  | 1173502.07 | 0.1
2806 | Kentucky | FAYETTE | LEXINGTON-FAYETTE | 06 | 8591002 | PHASE 1B OF THE WIDENING OF 0.7 MILES OF LIBERTY ROAD/TODDS ROAD IN LEXINGTON, KENTUCKY BEGINNING AT THE INTERSECTION OF MAN O'WAR BLVD AND EXTENDING EAST TO FOREST HILL DRIVE. | Pavement Improvement | 10/30/2009 |  |  | 470000 | 0
2807 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 8723011 | EXTENDING EXISTING BLANKENBAKER PARKWAY (KY 913) AS 5 LANE ROADWAY IN JEFFERSON COUNTY FROM THE BLANKENBAKER ACCESS ROAD TO TAYLORSVILLE ROAD (KY 155). | Pavement Widening | 11/20/2009 |  |  | 4245662 | 0
2808 | Kentucky | GRAYSON |  | 2 | 9001011 | PAVEMENT REHABILITATION OF THE EASTBOUND LANES OF THE WESTERN KENTUCKY PARKWAY IN GRAYSON COUNTY FROM 0.9 MILES EAST OF CROW HOLLOW ROAD BRIDGE, BEGINNING AT MILEPOINT 114.9 AND EXTENDING EAST TO THE | Pavement Improvement | 05/20/2009 | 05/20/2009 | 09/13/2009 | 1100000 | 2.15
2809 | Louisiana | CADDO |  | 4 | 0021021 | This project will build 3.2 miles of new interstate highway from US 71(S) to LA 2. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas State Line in | New Construction | 11/16/2009 |  | 11/03/2009 | 7698891.02 | 3.15
2810 | Louisiana | WASHINGTON |  | 1 | 002S613 | These Washington Parish projects near Bogalusa will improve safety for the traveling public by replacing four existing structurally deficient timber bridges located on Burt Road and Claiborne Street o | Bridge Replacement | 05/03/2009 | 05/03/2009 | 07/06/2009 | 2052896.65 | 0
2811 | Louisiana | JEFFERSON | NEW ORLEANS | 1 | 0105370 | This project is Phase 2 of 2 for the improvement of the existing Interstate 10 @ Causeway Blvd interchange. The project includes the construction of new flyover ramps to improve the flow of traffic b | Pavement Widening | 08/04/2009 | 08/04/2009 | 08/03/2009 | 56194317.5 | 0.38
2812 | Louisiana | CADDO | SHREVEPORT | 4 | 0905504 | This project will build 4.6 miles of new interstate highway from Mira-Myrtis Road to LA 168. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas Sta | Pavement Improvement | 05/18/2009 | 05/18/2009 | 04/24/2009 | 34301108.98 | 5.8
2813 | Louisiana | IBERIA |  | 3 | 1104011 | This project will build a new bridge on US 90 at LA 85 in Iberia Parish as part of the upgrading of US 90 to become part of I-49 from Lafayette to New Orleans. | New Construction | 03/09/2009 | 03/09/2009 | 03/05/2009 | 29929858.86 | 1.17
2814 | Louisiana | CATAHOULA |  | 5 | 1308502 | This project is located at the northern and southern city limits of Sicily Island in Catahoula Parish along LA 15 and will providie landscaping along the reconstructed section of LA 15 through Sicily | Transportation Enhancements | 07/11/2009 | 07/11/2009 | 06/26/2009 | 168971.77 | 0.231
2815 | Louisiana | CONCORDIA |  | 5 | 1508500 | This project will remove approximately 7 miles of the deteriorated pavement along US 425 and place new asphalt from US 65 to Foules in Concordia and Catahoula Parishes. | Pavement Improvement | 09/12/2009 | 09/12/2009 | 09/04/2009 | 1908201.98 | 0.266
2816 | Louisiana | EAST BATON ROUGE |  | 6 | 1709503 | The project is located in Baton Rouge and consists of widening Interstate-10 from four to six lanes from the Seigen Lane Interchange to the Highland Road Interchange. | Pavement Widening | 03/09/2009 | 03/10/2009 | 03/05/2009 | 69605000 | 2
2817 | Louisiana | EVANGELINE |  | 3 | 2002502 | These Evangeline Parish projects on Red Fox Lane and 1st Street in Chataignier will replace the existing deficient timber bridges with a new concrete box culvert and a new concrete bridge. | Bridge Replacement | 06/22/2009 | 06/22/2009 | 06/10/2009 | 675463.47 | 0
2818 | Louisiana | JACKSON |  | 5 | 2508503 | This Jackson Parish project will place new asphalt along 6 miles of the existing two lanes on US 167 lanes from Quitman to the Lincoln Parish line. | Pavement Improvement | 07/15/2009 | 07/15/2009 | 06/26/2009 | 3303711.89 | 6.06
2819 | Louisiana | LAFOURCHE |  | 3 | 2909501 | This Lafourche Parish project will construct a new vertical lift bridge with concrete towers to replace the existing deficient pontoon bridge. The new bridge will be constructed on a realigned section | Bridge Replacement | 05/20/2009 | 05/20/2009 | 05/20/2009 | 37067216.83 | 0.57
2820 | Louisiana | ORLEANS | NEW ORLEANS | 1 | 3602513 | This project consists of the reconstruction of the existing roadway with new concrete pavement on Fleur De Lis Blvd from from Veterans Memorial Blvd to North of 30th St in Orleans Parish. | Pavement Improvement | 11/11/2009 | 11/11/2009 | 10/30/2009 | 11394596.94 | 0
2821 | Louisiana | OUACHITA |  | 7 | 3701525 | This Ouachita Parish project on Caples Road will replace the existing deficient timber bridge over Longs Creek with a new concrete bridge. | Bridge Replacement | 07/31/2009 | 07/31/2009 | 07/31/2009 | 622898.74 | 0
2822 | Louisiana | OUACHITA |  | 5 | 3701526 | This Ouachita Parish project on Sam Head Road will replace the existing deficient timber bridge over Bogaloosa Creek with a new concrete bridge. | Bridge Replacement | 09/08/2009 | 09/08/2009 | 06/29/2009 | 412663.08 | 0
2823 | Louisiana | ST CHARLES | NEW ORLEANS | 3 | 4502500 | This project will construct a bike and walking path on the St. Charles Parish West Bank Mississippi River levee between Davis Drive in Luling to Elm Street in Hahnville. | Transportation Enhancements | 09/03/2009 | 09/03/2009 | 08/26/2009 | 946000 | 0
2824 | Louisiana | ST MARTIN |  | 3 | 5003501 | This St. Martin Parish project in the City of Breaux Bridge on Refinery Road will replace the existing deficient timber bridge over Bayou Teche with a new concrete bridge. | Bridge Replacement | 06/15/2009 | 06/15/2009 | 06/10/2009 | 2071306.83 | 0
2825 | Louisiana | ST TAMMANY | SLIDELL | 1 | 5204528 | This St. Tammany Parish project will improve access at the LA 59 and Interstate 12 interchange by providing new turn lanes on LA 59 and widening of the ramp onto I-12. | Pavement Improvement | 08/21/2009 | 08/21/2009 | 08/17/2009 | 3246189.24 | 0.53
2826 | Louisiana | ST TAMMANY | SLIDELL | 1 | 5209503 | This St. Tammany Parish project located near Pearl River will widen the existing I-59 exit and entrance ramps and portions of LA 1090 at I-59. The project will provide additional turn lanes at the ex | Pavement Improvement | 09/08/2009 | 09/08/2009 | 09/04/2009 | 1398092.08 | 0.44
2827 | Louisiana | ST TAMMANY | MANDEVILLE-COVINGTON | 1 | 5209504 | This St. Tammany Parish project will improve traffic operations by constructing turn lanes and widening ramps at the US 11/I-12 interchange in Slidell, LA. | Pavement Improvement | 09/16/2009 | 09/16/2009 | 09/15/2009 | 5620179.56 | 0.05
2828 | Louisiana | TANGIPAHOA |  | 1 | 5302508 | The Tangipahoa Parish project in the City of Hammond on J.W. Davis Road will replace the existing deficient timber bridge over a canal with a concrete bridge. | Bridge Replacement | 06/29/2009 | 06/29/2009 | 07/02/2009 | 1203817.56 | 0
2829 | Louisiana | TANGIPAHOA |  | 1 | 5302509 | This Tangipahoa Parish project on Little Italy Road will replace the existing deficient timber bridge over a creek with a concrete bridge. | Bridge Replacement | 06/29/2009 | 06/29/2009 | 06/10/2009 | 642751.77 | 0
2830 | Louisiana | TANGIPAHOA |  | 1 | 5302510 | ThisTangipahoa Parish project on Bennett Road will replace the existing deficient concrete bridge over Natalbany Creek with a new concrete bridge. | Bridge Replacement | 07/09/2009 | 07/09/2009 | 06/16/2009 | 694251.14 | 0
2831 | Louisiana | TANGIPAHOA |  | 1 | 5302511 | This Tangipahoa Parish project on Cooper Road will replace the existing deficient timber bridge over Cooper Creek with a new concrete bridge. | Bridge Replacement | 07/13/2009 | 07/13/2009 | 06/02/2009 | 615400.1 | 0
2832 | Louisiana | ORLEANS | NEW ORLEANS | 2 | 6033009 | This Orleans Parish project consists of reconstructing and widening of Earhart Boulevard from Hamilton St to Fern St. | Pavement Improvement | 11/11/2009 | 11/11/2009 | 10/30/2009 | 12389212.74 | 0
2833 | Louisiana | WEST CARROLL |  | 5 | 6204500 | This West Carroll Parish project on Lingo Loop Road will replace the existing deficient timber bridge over Mill Bayou with a new concrete bridge. | Bridge Replacement | 08/05/2009 | 08/05/2009 | 08/05/2009 | 441716.34 | 0
2834 | Louisiana | WEST CARROLL |  | 5 | 6204501 | This West Carroll Parish project on Wood Road will ieplace the existing deficient timber bridge over Alligator Bayou with a new concrete bridge. | Bridge Replacement | 09/01/2009 | 09/01/2009 | 06/12/2009 | 532147.12 | 0
2835 | Louisiana | RAPIDES | ALEXANDRIA | 5 | 7869002 | Susek Drive is an existing two lane roadway in the northeast portion of Pineville, Louisiana in Rapides Parish. 2.2 miles of the roadway is to be reconstructed to two 12 foot lanes with curbs. The pro | Pavement Improvement | 09/08/2009 | 09/08/2009 | 09/04/2009 | 9477949.82 | 0
2836 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1048 | This Orelans Parish project consists of removing deteriorated pavement and placing new asphalt and striping on Leon C Simon Dr from London Ave Canal to Elysian Fields Ave. in New Orleans.. | Transportation Enhancements | 11/20/2009 |  | 09/18/2009 | 48530.58 | 0
2837 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1050 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Mirabeau Ave from St. Bernard Ave to Elysian Fields Ave. in New Orlea | Transportation Enhancements | 11/20/2009 |  | 09/18/2009 | 636814.8 | 0
2838 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1051 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Filmore Ave from St. Bernard Ave to Elysian Fields Ave. in New Orlean | Transportation Enhancements | 11/20/2009 |  | 09/18/2009 | 695535.25 | 0
2839 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1052 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on St. Bernard Ave from I-610 to Filmore Ave. in New Orleans. | Transportation Enhancements | 11/20/2009 |  | 09/18/2009 | 594994.56 | 0
2840 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1053 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Paris Ave from I-610 to Mirabeau Ave. in New Orleans. | Transportation Enhancements | 11/20/2009 |  | 09/18/2009 | 524076.92 | 0
2841 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1054 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Elysian Fields from Lakeshore Dr to US 90 in New Orleans. | Transportation Enhancements | 11/20/2009 |  | 09/18/2009 | 1075751.97 | 0
2842 | Louisiana | STATEWIDE |  | 4 | LA03003 | This project will provide four informational kiosks in the towns of Vivian, Plain Dealing, Sarepta, and Homer in Caddo, Bossier, Webster, Claiborne Parishes.. | Transportation Enhancements | 08/18/2009 | 08/18/2009 | 08/07/2009 | 214299.99 | 0
2843 | Maine | ANDROSCOGGIN |  | 2 | 1001700 | Lisbon, Sabattus, Rt 9. Reconstruction of 6.75 miles of Route 9 beginning 0.33 of a mile northerly of Route 196 and extending northeasterly 6.75 miles to the Maine Turnpike Overpass. Work involves g | Pavement Improvement | 08/11/2009 | 08/11/2009 | 07/31/2011 | 9646830.99 | 6.75
2844 | Maine | CUMBERLAND |  | 1 | 1015800 | Portland, Veranda Street Bridge, Replacement of Veranda Street Overpass Bridge over Canadian Railroad | Bridge Improvement | 05/06/2009 | 05/06/2009 | 02/28/2010 | 1420227.32 | 0
2845 | Maine | HANCOCK |  | 2 | 1107200 | Ellsworth, Route 1A. Reconstruction of 2.67 miles of Route 1A beginning at the Rabbit Road and extending southeasterly 2.67 miles to 0.15 of a mile northerly of the Old Bangor Road. Work includes gra | Pavement Improvement | 08/05/2009 | 08/05/2009 | 06/30/2011 | 6406557.4 | 2.67
2846 | Maine | CUMBERLAND | PORTLAND | 1 | 1184400 | Portland, Bayside Trail. This project will design an extension of the Portland Trails system through the Bayside area of Portland along the abandoned Union Branch Rail Line extending from the Eastern | Transportation Enhancements | 08/11/2009 | 08/11/2009 | 09/30/2009 | 800000 | 0
2847 | Maine | WALDO |  | 2 | 1267600 | Lincolnville, Knights Hill Culvert Replacement on Route 52 over Meservy Brook | Bridge Improvement | 05/21/2009 | 05/21/2009 | 10/12/2009 | 255000 | 0
2848 | Maine | ANDROSCOGGIN |  | 2 | 1273700 | Auburn, Joline Drive Intersection Improvement with a signal at the intersection of Center Street, Joline Street, and Stetson Street | Safety/Traffic Management | 05/28/2009 | 05/28/2009 | 12/31/2009 | 567134.95 | 0
2849 | Maine | ANDROSCOGGIN |  | 2 | 1277700 | Turner, Route 117. Reconstruction of 2.39 miles of Route 117 including grading, paving, drainage and guardrail improvements. | Pavement Improvement | 07/22/2009 | 07/22/2009 | 09/20/2009 | 2789003.76 | 2.39
2850 | Maine | ANDROSCOGGIN |  | 2 | 1305900 | Auburn, Joline Drive. Reconstruction of 0.18 of a mile beginning at Center Street and extending westerly to Turner Street. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 11/30/2009 | 379538 | 0.18
2851 | Maine | ANDROSCOGGIN |  | 2 | 1306100 | Lewiston, Russell Street. Reconstruction of 0.51 miles beginning at the convergence of the ramps to Main Street, extending easterly to Robinson Gardens. This project will include construction of left | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/11/2009 | 2106788.41 | 0.51
2852 | Maine | YORK |  | 1 | 1308500 | Biddeford, Route 111. Highway resurfacing beginning at Main Street (Route 9) and extending westerly 0.97 of a mile to 0.10 of a mile easterly of Marshall Avenue. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 583688.73 | 0.97
2853 | Maine | YORK |  | 1 | 1308600 | Biddeford, Route 9. Highway resurfacing beginning at Parkside and extending 0.95 of a mile to Alfred Street. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 429553.62 | 0.95
2854 | Maine | CUMBERLAND |  | 1 | 1310400 | Portland, Auburn Street. Intersection improvement with signal located at the intersection of Auburn Street and Lyseth Moore Drive. | Safety/Traffic Management | 07/02/2009 | 07/02/2009 | 12/31/2009 | 253396.5 | 0
2855 | Maine | YORK |  | 1 | 1311100 | Saco, North Street. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile northerly of Park Street and extending 1.00 mile to 0.34 of a mile southerly of Hillview Avenue. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 253205.96 | 1
2856 | Maine | YORK |  | 1 | 1334100 | Biddeford-Kennebunk, Eastern Trail, Construct a bicycle/pedestrian trail from Rt. 111 in Biddeford to Route 35 in Kennebunk. | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 07/31/2010 | 1437316 | 0
2857 | Maine | CUMBERLAND |  | 1 | 1480600 | Portland, Cumberland Avenue. Highway resurfacing beginning at Franklin Arterial and extending 0.29 of a mile to Elm Street. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 09/30/2009 | 141419.15 | 0.29
2858 | Maine | CUMBERLAND |  | 1 | 1480700 | Westbrook, Eisenhower Drive. Highway resurfacing beginning at Saco Street and extending 0.88 of a mile to Spring Street. Includes shoulder resurfacing. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 08/31/2009 | 570450.54 | 0.87
2859 | Maine | YORK |  | 1 | 1480800 | Saco, Beach Street-Ferry Road. Pave a 3/4" hot mix asphalt overlay beginning at North Street and extending 1.11 miles to Pine Ridge Road. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 224904.49 | 1.11
2860 | Maine | CUMBERLAND |  | 1 | 1480900 | Falmouth, Brook Road. Pave a 1 1/4" hot mix asphalt overlay beginning at the Westbrook town line and extending 0.74 of a mile to the Leighton Road. The project will include drainage and the installa | Pavement Improvement | 05/28/2009 | 05/28/2009 | 08/31/2009 | 497817.38 | 0.48
2861 | Maine | CUMBERLAND |  | 1 | 1481100 | Portland, Westbrook Street. Pave a 1 1/4" hot mix asphalt overlay beginning at the Westbrook town line and extending 0.89 miles to Congress Street. Project includes alteration of 24 catch basins and | Pavement Improvement | 06/16/2009 | 06/16/2009 | 09/30/2009 | 267978.85 | 0.89
2862 | Maine | SAGADAHOC |  | 1 | 1511450 | Interstate I-295 Northbound, Brunswick to Gardiner. This project involves reconstruction of the roadway including grinding and rubblizing the existing concrete roadway, grading and paving, drainage a | Pavement Improvement | 03/03/2009 | 03/03/2009 | 10/10/2009 | 33500000 | 23.88
2863 | Maine | KENNEBEC |  | 1 | 1511460 | Interstate I-295 Northbound, Topsham to Gardiner. This project involves building the crossovers from the northbound lanes to the southbound lanes as part of the traffic detour for the I-295 northboun | Safety/Traffic Management | 03/30/2009 | 03/30/2009 | 10/06/2009 | 1751386.05 | 0
2864 | Maine | LINCOLN |  | 1 | 1561300 | Damariscotta, Salt Bay Steel Culvert Bridge Replacement over Oyster Creek, located on Belvedere Road at the Damariscotta-Nobleboro town line. | Bridge Replacement | 05/29/2009 | 05/29/2009 | 10/08/2009 | 511591.54 | 0
2865 | Maine | KENNEBEC |  | 1 | 1561400 | Hallowell, Second Street Bridge Rehabilitation over Maine Central Railroad. Replace existing deck and repair concrtete bridge abutments and retaining walls. | Bridge Replacement | 05/05/2009 | 05/05/2009 | 03/30/2010 | 1232549 | 0
2866 | Maine | PENOBSCOT |  | 2 | 1562700 | Township 2 Region 8, Lincoln Spur Bridge Deck Replacement located over Interstate 95 northbound and southbound. Replace existing deck and install new safety barriers. | Bridge Improvement | 04/24/2009 | 04/24/2009 | 10/11/2009 | 1344424.7 | 0
2867 | Maine | HANCOCK |  | 2 | 1568900 | Sullivan, Route 1. Intersection Improvements including construction of a bypass lane located at the intersection of Route 1 and the Ashville Road. | Safety/Traffic Management | 06/24/2009 | 06/24/2009 | 08/31/2009 | 316313.74 | 0
2868 | Maine | OXFORD |  | 2 | 1571600 | Lovell, Main Street. Pave a 3/4" hot mix asphalt overlay beginning 0.82 of a mile north of Christian Hill Road and extending northerly 1.66 miles to 0.12 of a mile south of West Lovell Road. | Pavement Improvement | 04/14/2009 | 04/14/2009 | 10/09/2009 | 319487.96 | 1.66
2869 | Maine | CUMBERLAND |  | 1 | 1571900 | Sebago, Sebago Road. Pave a 3/4" hot mix asphalt overlay beginning at Shore Road and extending northerly 0.90 miles to 0.17 of a mile northerly of Woodland Road. | Pavement Improvement | 04/14/2009 | 04/14/2009 | 10/09/2009 | 263701.29 | 0.91
2870 | Maine | CUMBERLAND |  | 1 | 1572000 | Standish, Route 114. Pave a 3/4" hot mix asphalt overlay eginning 0.16 of a mile north of Route 35 and extending northerly 6.50 miles to 0.94 of a mile south of the Standish-Sebago town line. | Pavement Improvement | 04/14/2009 | 04/14/2009 | 10/09/2009 | 1121709.23 | 6.5
2871 | Maine | KENNEBEC |  | 2 | 1573700 | Clinton, Baker Street. Pave a 3/4" hot mix asphalt overlay beginning at Route 11 and extending northerly 1.16 miles. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/05/2009 | 411142.34 | 1.16
2872 | Maine | SOMERSET |  | 2 | 1573900 | Fairfield, Route 23. Pave a 3/4" hot mix asphalt overlay beginning at Route 201 and extending northerly 0.65 of a mile to 0.19 of a mile northerly of Pishon Ferry Road. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 109143.83 | 0.65
2873 | Maine | KENNEBEC |  | 2 | 1574600 | Oakland, Fairfield Street. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile northerly of Greeley Street and extending northerly 0.85 of a mile to 0.30 of a mile northerly of Municipal Dri | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/06/2009 | 153247.97 | 0.85
2874 | Maine | KENNEBEC |  | 2 | 1574700 | Oakland, Pleasant Street. Pave a 3/4" hot mix asphalt overlay beginning at Oak Street and extending easterly 0.37 of a mile to Route 11. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 84886.84 | 0.37
2875 | Maine | KENNEBEC |  | 1 | 1575000 | Randolph, Route 9. Pave a 3/4" hot mix asphalt overlay beginning 0.05 of a mile westerly of the Chelsea-Randolph town line and extending easterly 3.67 miles to 0.10 of a mile easterly of the Augusta- | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/05/2009 | 601652.04 | 3.59
2876 | Maine | KENNEBEC |  | 2 | 1575700 | Waterville, Oak Street. Pave a 3/4" hot mix asphalt overlay beginning at Main Street and extending easterly 0.46 of a mile to College Avenue. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/05/2009 | 117408.17 | 0.46
2877 | Maine | FRANKLIN |  | 2 | 1576500 | Eustis, Route 27. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile south of Route 16 and extending northerly 1.26 miles. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 09/30/2009 | 226899.25 | 1.26
2878 | Maine | SOMERSET |  | 2 | 1577000 | Jackman, Route 6. Pave a 3/4" hot mix asphalt overlay beginning 2.19 miles westerly of the Long Pond Twp town line and extending easterly 2.19 miles. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 608120.69 | 2.19
2879 | Maine | PISCATAQUIS |  | 2 | 1577400 | Sapling Township., Rockwood Road. Pave a 3/4" hot mix asphalt overlay beginning 0.05 of a mile westerly of the Sapling Township-Big Moose Township town line and extending easterly 6.10 miles to 0.46 | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 1112301.88 | 6.1
2880 | Maine | SOMERSET |  | 2 | 1579000 | Palmyra, Ell Hill Road. Pave a 3/4" hot mix asphalt overlay beginning at Somerset Avenue and extending northerly 6.27 miles to 0.03 of a mile northerly of Ford Hill Road. | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/10/2009 | 1178865.74 | 6.27
2881 | Maine | AROOSTOOK |  | 2 | 1579700 | Caswell, Van Buren Road. Pave a 3/4" hot mix asphalt overlay beginning 0.29 of a mile southerly of the Hamlin town line and extending northerly 5.69 miles to 1.18 miles southerly of Albert Cyr Road. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/08/2009 | 1588813.43 | 5.62
2882 | Maine | ANDROSCOGGIN |  | 2 | 1581400 | Auburn, Turner Street. Pave a 3/4" hot mix asphalt overlay beginning at Center Street and extending northerly 1.08 miles to 0.30 of a mile southerly of Mount Auburn Avenue. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 07/31/2009 | 381205.93 | 1.08
2883 | Maine | KENNEBEC |  | 1 | 1583000 | Gardiner, Water Street. Pave a 3/4" hot mix asphalt overlay beginning at Cobbossee Avenue and extending easterly 1.10 miles to Route 201. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/09/2009 | 278105.84 | 1.1
2884 | Maine | KENNEBEC |  | 1,2 | 1583100 | Litchfield, Route 9. Pave a 3/4" hot mix asphalt overlay beginning 0.17 of a mile westerly of the Huntington Hill Road and extending easterly 3.99 miles to 0.06 of a mile westerly of the Bog Hill Roa | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/09/2009 | 714525.86 | 4.01
2885 | Maine | KENNEBEC |  | 2 | 1583200 | Oakland, Route 11. Grind and remove 1 1/4" of existing pavement and replace with a 1 1/4" hot mix asphalt overlay beginning at Route 23 and extending northerly 4.46 miles to 0.01 of a mile northerly | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 844096.65 | 4.46
2886 | Maine | KENNEBEC |  | 1 | 1584000 | West Gardiner, Lewiston Road. Pave a 1 1/4" hot mix asphalt overlay beginning 0.42 of a mile westerly of the I-95 Exit 102 On-ramp and extending easterly 1.69 miles to 0.11 of a mile westerly of the | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/09/2009 | 722543.79 | 1.69
2887 | Maine | SOMERSET |  | 2 | 1584300 | Fairfield, Norridgewock Road. Grind and remove 1 1/4" of the existing pavement and replace with a 1 1/4" hot mix asphalt overlay beginning 1.87 miles west of Routes 104/139 and extending westerly 4.75 | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2009 | 988920.78 | 4.75
2888 | Maine | FRANKLIN |  | 2 | 1584900 | New Sharon, Route 27. Pave a 3/4" hot mix asphalt overlay beginning 0.38 of a mile southerly of York Hill Road and extending northerly 2.65 miles to Route 2. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/10/2009 | 511207.78 | 2.65
2889 | Maine | PENOBSCOT |  | 2 | 1585100 | Bangor, Broadway. Pave a 3/4" hot mix asphalt overlay beginning at the Interstate 95 southbound Exit 185 ramps and extending northerly 0.65 of a mile to Grandview Avenue. | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/08/2009 | 185816.55 | 0.56
2890 | Maine | PENOBSCOT |  | 2 | 1585300 | Bangor, Hogan Road. Grind and remove 1 1/4" of existing asphalt and replace with a 1 1/4" of hot mix asphalt overlay beginning 0.10 miles southerly of the intersection of Mt. Hope and extending north | Pavement Improvement | 07/08/2009 | 07/08/2009 | 08/31/2009 | 451562.08 | 1.24
2891 | Maine | WASHINGTON |  | 2 | 1586200 | East Machias, Route 1. Pave a 3/4" hot mix asphalt overlay beginning 0.37 of a mile northerly of Chase Mills Road and extending northerly 1.00 mile to 0.47 of a mile northerly of the Whiting town lin | Pavement Improvement | 07/21/2009 | 07/21/2009 | 06/30/2010 | 249231.28 | 1
2892 | Maine | SOMERSET |  | 2 | 1587500 | Pittsfield, Park Street. Grind and remove 1 1/4" of existing asphalt and replace with a 1 1/4" hot mix asphalt overlay beginning at North Main Street and extending northerly 0.19 of a mile to Somerse | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/10/2009 | 58907.85 | 0.19
2893 | Maine | ANDROSCOGGIN |  | 2 | 1588200 | Auburn, Route 202. Pave a 3/4" hot mix asphalt overlay beginning at Minot Avenue and extending northerly 0.68 of a mile to Lisbon Street. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 07/31/2009 | 279516.49 | 0.68
2894 | Maine | ANDROSCOGGIN |  | 2 | 1588500 | Auburn, Minot Avenue. Pave a 3/4" hot mix asphalt overlay beginning at High Street and extending northerly 0.51 of a mile to Court Street. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 07/31/2009 | 214358.35 | 0.51
2895 | Maine | CUMBERLAND |  | 1 | 1589100 | Interstate I-295 Southbound, Freeport. Work involves replacing culvert underneath I-295 Exit 22 on and off ramps. | Bridge Improvement | 07/07/2009 | 07/07/2009 | 10/31/2009 | 143100 | 0.06
2896 | Maine | CUMBERLAND |  | 1 | 1590100 | Portland, Forest Avenue. Grind and remove 1 1/4" existing asphalt and replace with 1 1/4" hot mix asphalt beginning at Warren Avenue and extending northerly 1.15 miles to Castine Avenue. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 09/30/2009 | 677796.29 | 0.98
2897 | Maine | CUMBERLAND |  | 1 | 1590300 | Interstate I-295 Southbound, Portland. Paving 0.42 miles beginning 0.13 of a mile north of the Washington Avenue Southbound on-ramp. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 08/31/2009 | 84242 | 0.42
2898 | Maine | LINCOLN |  | 1 | 1591800 | Edgecomb, Route 1. Pave a 3/4" hot mix asphalt overlay beginning 0.08 of a mile northerly of Eddy Road and extending northerly 1.02 miles to 0.05 of a mile northerly of Cochran Road. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2009 | 519451.66 | 1.02
2899 | Maine | SOMERSET |  | 2 | 1593200 | Caratunk, Route 201. Pave a 3/4" hot mix asphalt overlay beginning 3.74 miles southerly of the The Forks Plantation town line and extending northerly 3.77 miles. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 598207 | 3.77
2900 | Maine | FRANKLIN |  | 2 | 1593300 | Farmington, Route 2. Grind and remove 1 1/4" of existing pavement and replace with 1 1/4" of hot mix as[halt beginning 500 feet west of the bridge to Prescott Street; Route 2/4/27 intersection to Hil | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/10/2009 | 495279.15 | 2.87
2901 | Maine | SOMERSET |  | 2 | 1593600 | Moose River, Route 201. Pave a 3/4" hot mix asphalt overlay beginning 0.26 of a mile northerly of Sandy Stream Road and extending northerly 13.65 miles to the Canadian border. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 2226123.37 | 13.65
2902 | Maine | SOMERSET |  | 2 | 1594100 | West Forks Plantation., Route 201. Pave a 3/4" hot mix asphalt overlay beginning 0.16 of a mile southerly of the Parlin Pond Township town line and extending northerly 13.62 miles to 2.60 miles north | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 2189119.98 | 13.62
2903 | Maine | PENOBSCOT |  | 2 | 1594300 | Bangor, Broadway (Route 15). Pave a 3/4" hot mix asphalt overlay beginning 325' easterly of the I-95 northbound Exit 185 ramps and extending northerly 0.23 of a mile to the I-95 southbound Exit 185 r | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/08/2009 | 89609.23 | 0.23
2904 | Maine | PENOBSCOT |  | 2 | 1594800 | Hampden, Route 202. Pave a 3/4" hot mix asphalt overlay beginning at Western Avenue and extending northerly 4.02 miles to the Interstate 395 Exit 2 eastbound ramps. | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/08/2009 | 1262169.22 | 4.02
2905 | Maine | PENOBSCOT |  | 2 | 1595300 | Interstate I-95 Southbound, Mattamiscontis Township to Howland. 10.37 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2009 | 4259760.87 | 10.37
2906 | Maine | PENOBSCOT |  | 2 | 1595400 | Interstate I-95 Southbound, Township 2 Region 8 NWP to Mattamiscontis Township. 7.06 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/06/2009 | 2608466.57 | 7.06
2907 | Maine | HANCOCK |  | 2 | 1669600 | Deer Isle-Sedgwick Bridge Substructure Rehabilitation over Eggemoggin Reach, located on the Deer Isle-Sedgwick town line. Repair bridge tower piers. | Bridge Improvement | 09/16/2009 | 09/16/2009 | 10/31/2010 | 10094550.21 | 0
2908 | Maine | KNOX |  | 1 | 1674500 | South Thomaston, Spruce Head Bridge Replacement on Island Road. | Bridge Replacement | 08/19/2009 | 08/19/2009 | 05/31/2010 | 2196049.9 | 0
2909 | Maine | PENOBSCOT |  | 2 | 1677500 | Interstate I-95 Southbound, Howland to Old Town. 15.6 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2010 | 4513576.77 | 15.6
2910 | Maine | PENOBSCOT |  | 2 | 1682200 | Interstate I-95 Southbound, Township 2 Region 9 NWP to Township 2 Region 8 NWP. 8.22 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2010 | 2542725 | 8.22
2911 | Maine | WASHINGTON |  | 2 | 1698300 | Lubec, Route 189. Pave a 1-1/4" hot mix asphalt overlay beginning at the intersection of Route 1 and extending easterly approximately 6.7 miles. | Pavement Improvement | 07/21/2009 | 07/21/2009 | 06/30/2010 | 3294190.47 | 11.19
2912 | Maine | CUMBERLAND |  | 1 | 1700800 | South Portland-Portland, Long Creek Watershed. Pavement treatment on Maine Mall Road designed to enhance treatment of stormwater runoff in an urban impaired stream watershed as recommended by the Lon | Other | 06/29/2009 | 06/29/2009 | 12/31/2009 | 1685245 | 0
2913 | Maine | WALDO |  | 2 | 1763400 | Rehabilitation of the Maine State Ferry Service's pier structure and the Islesboro and Lincolnville locations. | Other | 11/19/2009 | 11/20/2009 | 12/30/2011 | 150000 | 0
2914 | Maine | PISCATAQUIS |  | 2 | A001000 | Highway Reconstruction: Beginning 0.59 of a mile southerly of the Range Road and extending northwesterly 1.29 miles to 0.13 of a mile southerly of the Bear Hill Road. | Pavement Improvement | 07/20/2009 | 07/20/2009 | 06/30/2010 | 2889444.44 | 1.29
2915 | Maryland | ANNE ARUNDEL |  | 1 | 000A368 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/22/2009 |  | 11/01/2011 | 4612024 | 0
2916 | Maryland | CALVERT |  | 1 | 000A369 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/05/2009 |  | 11/01/2011 | 4612038 | 0
2917 | Maryland | CHARLES |  | 5 | 000A370 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 04/29/2009 |  | 11/01/2011 | 4612050 | 0
2918 | Maryland | ST MARYS |  | 5 | 000A371 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 |  | 12/01/2011 | 6140665 | 0
2919 | Maryland | ANNE ARUNDEL |  | 5 | 000A373 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 07/16/2009 |  | 12/01/2011 | 4628533 | 0
2920 | Maryland | STATEWIDE |  | 4,5,6,8 | 000A375 | This is a signalization project. Signals and Reconstructs in District 3. This contract is required for routine capital signal improvement efforts in District 3. | Safety/Traffic Management | 08/20/2009 |  |  | 5287442 | 0
2921 | Maryland | CECIL |  | 1 | 000A379 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/09/2009 |  | 12/01/2011 | 2736022 | 0
2922 | Maryland | KENT |  | 1 | 000A380 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 |  | 11/01/2011 | 2306012 | 0
2923 | Maryland | QUEEN ANNES |  | 1 | 000A381 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 |  | 12/01/2011 | 2306006 | 0
2924 | Maryland | TALBOT |  | 1 | 000A382 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/05/2009 |  | 11/01/2011 | 2288019 | 0
2925 | Maryland | STATEWIDE |  | 4,5,6,8 | 000A387 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Montgomery and Prince George’s Counties. This work | Transportation Enhancements | 06/16/2009 |  | 07/01/2012 | 3612818 | 0
2926 | Maryland | STATEWIDE |  | 1,2,3,5 | 000A389 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Anne Arundel, Calvert, Charles, and St. Mary’s Cou | Transportation Enhancements | 07/14/2009 |  | 06/01/2011 | 2904467 | 0
2927 | Maryland | STATEWIDE |  | 3,6,7 | 000A390 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Carroll, Frederick, and Howard Counties. This work | Transportation Enhancements | 07/16/2009 |  | 06/01/2011 | 1987656 | 0
2928 | Maryland | DORCHESTER |  | 1 | 000A395 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. Various locations in | Pavement Improvement | 03/11/2009 |  | 12/01/2010 | 2588015 | 0
2929 | Maryland | SOMERSET |  | 1 | 000A396 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Somerset County that will enhance pavement life and provide | Pavement Improvement | 03/11/2009 |  | 12/01/2010 | 2306037 | 0
2930 | Maryland | WICOMICO |  | 1 | 000A397 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Wicomico County that will enhance pavement life and provide | Pavement Improvement | 04/08/2009 |  | 12/01/2010 | 2288001 | 0
2931 | Maryland | WORCESTER |  | 1 | 000A398 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Worcester County that will enhance pavement life and provid | Pavement Improvement | 03/11/2009 |  | 12/01/2010 | 2306058 | 0
2932 | Maryland | STATEWIDE |  | 1 | 000A400 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Dorchester, Somerset, Wicomico, and Worcester Counties. The work may als | Safety/Traffic Management | 06/09/2009 |  | 12/01/2011 | 379808 | 0
2933 | Maryland | STATEWIDE |  | 1 | 000A401 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Caroline, Cecil, Kent, Queen Anne’s and Talbot Counties. The work may al | Safety/Traffic Management | 06/09/2009 |  | 01/01/2012 | 299042 | 0
2934 | Maryland | STATEWIDE |  | 4,5,6,8 | 000A402 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Montgomery County and Prince George’s Counties. The work may also includ | Safety/Traffic Management | 06/03/2009 |  | 12/01/2011 | 468485 | 0
2935 | Maryland | STATEWIDE |  | 1,2,3,6,7 | 000A403 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Baltimore and Harford Counties. The work may also include installation o | Safety/Traffic Management | 05/20/2009 |  | 01/01/2012 | 441541 | 0
2936 | Maryland | STATEWIDE |  | 1,2,3,5 | 000A404 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Anne Arundel, Calvert, Charles, and St Mary’s Counties Counties. The wor | Safety/Traffic Management | 05/20/2009 |  | 12/01/2011 | 297440 | 0
2937 | Maryland | STATEWIDE |  | 3,6,7 | 000A405 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Carroll, Frederick, and Howard Counties. The work may also include instal | Safety/Traffic Management | 05/21/2009 |  | 01/01/2012 | 580636 | 0
2938 | Maryland | ALLEGANY |  | 6 | 000A406 | Resurfacing | Pavement Improvement | 06/09/2009 |  | 01/30/2012 | 2388080 | 0
2939 | Maryland | BALTIMORE |  | 1,2,3,6,7 | 000A407 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 10/07/2009 |  |  | 4612046 | 0
2940 | Maryland | BALTIMORE |  | 1,2,3,6,7 | 000A408 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 10/07/2009 |  |  | 4912023 | 0
2941 | Maryland | CARROLL |  | 6 | 000A409 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/18/2009 |  | 12/01/2011 | 2288005 | 0
2942 | Maryland | HARFORD |  | 1,2,6 | 000A410 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/09/2009 |  | 12/01/2011 | 4812006 | 0
2943 | Maryland | MONTGOMERY |  | 4,6,8 | 000A411 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 |  | 12/01/2011 | 4576015 | 0
2944 | Maryland | MONTGOMERY |  | 4,6,8 | 000A412 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/27/2009 |  | 12/01/2011 | 5056006 | 0
2945 | Maryland | PRINCE GEORGES |  | 4,5,8 | 000A413 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/15/2009 |  | 12/01/2011 | 4576050 | 0
2946 | Maryland | PRINCE GEORGES |  | 4.5 | 000A414 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 |  | 12/01/2011 | 4576063 | 0
2947 | Maryland | WASHINGTON |  | 6 | 000A415 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 |  | 12/01/2011 | 3078053 | 0
2948 | Maryland | FREDERICK |  | 6 | 000A416 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/21/2009 |  | 12/01/2011 | 5369051 | 0
2949 | Maryland | GARRETT |  | 6 | 000A417 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/09/2009 |  | 12/01/2011 | 2623007 | 0
2950 | Maryland | HOWARD |  | 3,7 | 000A418 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. At some locations, i | Pavement Improvement | 05/18/2009 |  | 12/01/2011 | 4612010 | 0
2951 | Maryland | STATEWIDE |  | 1,2,3,4,5,6,7,8 | 000A419 | This project will repair concrete pavement and curb at Truck Weigh/Inspection Stations due to severely cracked roadway surface. Project will also improve geometric and drainage. This is a statewide | Pavement Improvement | 06/09/2009 |  | 07/01/2012 | 1344595 | 0
2952 | Maryland | CAROLINE |  | 1 | 000A420 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/09/2009 |  | 12/01/2011 | 2306042 | 0
2953 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 4.5 | 000A421 | Clean/Paint Bridges | Bridge Improvement | 03/11/2009 |  | 06/01/2010 | 1789806 | 0
2954 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 4,5,8 | 000A422 | Cleaning and painting bridges for longer service life on US 1, MD201, MD202, MD212 and MD500 | Bridge Improvement | 03/30/2009 |  | 05/01/2010 | 1742046 | 0
2955 | Maryland | STATEWIDE |  | 1,2,3,6,7 | 000A423 | This project will improve safety for the travelling public. Maryland State Highway will rehabilitate existing substandard traffic barrier at various locations in Baltimore and Harford Counties. InB | Safety/Traffic Management | 06/10/2009 |  | 01/01/2011 | 833976 | 0
2956 | Maryland | STATEWIDE |  | 1,2,3,5 | 000A424 | Maryland State Highway will upgrade guard rails at various locations in Anne Arundel, Calvert, Charles and St. Mary's Counties. This project will will improve safety for the travelling public. In An | Safety/Traffic Management | 06/15/2009 |  | 01/01/2011 | 833976 | 0
2957 | Maryland | STATEWIDE |  | 3,6,7 | 000A425 | This project will improve safety for motorists by upgrading existing guardrails at various locations in Garrett, Washington, Carroll, Frederick and Howard Counties. | Safety/Traffic Management | 06/09/2009 |  | 01/01/2011 | 1904760 | 0
2958 | Maryland | STATEWIDE |  | 1,2,3,4,5,6,7,8 | 000A427 | This project will install and upgrade signing at various locations. This project will improve safety of motorist. | Safety/Traffic Management | 03/16/2009 |  | 04/01/2012 | 5922034 | 0
2959 | Maryland | STATEWIDE |  | 1 | 000A428 | Maryland State Highway will install new median traffic barrier and rehabilitate non-compliance traffic barrier on approximately 17 mile section of US50 in Dorchester, Somerset, Wicomico and Worcester | Safety/Traffic Management | 06/15/2009 |  | 01/01/2011 | 1615969 | 0
2960 | Maryland | STATEWIDE |  | 1 | 000A429 | Maryland State Highway will rehabilitate existing substandard traffic barrier at various locations in Cecil (along 17 miles of US40), Queen Anne's (along 15.5 miles of US50) and Talbot (along 21 miles | Safety/Traffic Management | 07/13/2009 |  | 01/01/2011 | 2283767 | 0
2961 | Maryland | STATEWIDE |  | 1,2,3,5,6,7 | 000A430 | This contract will provide for upgrades to camera video detection for the traffic control timing of the different phases of operation. It will install traffic detection at signalized intersections in | Safety/Traffic Management | 06/16/2009 |  | 07/01/2011 | 1824752 | 0
2962 | Maryland | STATEWIDE |  | 1,2,3,4,5,6,7,8 | 000A431 | This project is for dynamic message signs deployment to ncrease CHART's (Maryland State's traffic operation's center) information dissemmation capibilities. | Safety/Traffic Management | 07/28/2009 |  | 08/01/2012 | 3756551 | 0
2963 | Maryland | STATEWIDE |  | 1,2,3,5,6 | 000A434 | This project will install battery backups and other signal improvements throughout the state districts. | Safety/Traffic Management | 08/13/2009 |  | 09/01/2011 | 5296976 | 0
2964 | Maryland | STATEWIDE |  | 1,2,3,6,7 | 000A443 | This project will install containerized trees and seedlings at various locations including, but not limited to 34 sites throughout Baltimore, | Transportation Enhancements | 07/13/2009 |  | 09/30/2011 | 367839 | 0
2965 | Maryland | STATEWIDE |  | 1,2,3,4,5,6,7,8 | 000A445 | This project will install sign lighting system at various locations to improve safety for motorists. | Safety/Traffic Management | 08/25/2009 |  | 09/01/2011 | 2541339 | 0
2966 | Maryland | STATEWIDE |  | 1,2,3,5 | 000A446 | This project will install and establish trees at various locations in Anne Arundel, Calvert, Charles and Saint Mary Counties. This work involves the removal of dead or invasive species, as well as, | Transportation Enhancements | 12/23/2009 |  |  | 245907 | 0
2967 | Maryland | STATEWIDE |  | 1 | 000A447 | This project will plant trees and bare root seedlings at various locations including, but not limited to 25 sites throughout Caroline, Dorchester, Kent, Queen Anne’s, Talbot, Wicomico and Worcester Co | Transportation Enhancements | 10/07/2009 |  | 09/01/2011 | 251958 | 0
2968 | Maryland | STATEWIDE |  | 4,5,6,8 | 000A448 | This project will install and establish reforestation trees and shrubs at various locations throughout Prince Georges's and Montgomary Counties. Project will remove dead or invasive plants and install | Transportation Enhancements | 08/05/2009 |  | 08/01/2010 | 221260 | 0
2969 | Maryland | FREDERICK | FREDERICK | 6 | 000A452 | This project, located in Frederick County, is for vegetation management, invasive species removal, and installation, care, and establishment of reforestation and landscape plantings in the interchange | Transportation Enhancements | 08/05/2009 |  | 08/01/2011 | 496980 | 0.28
2970 | Maryland | BALTIMORE | BALTIMORE,MD | 2 | 000A481 | This project involves traffic signal reconstruction in Baltimore County at MD7, MD157 and MD7. | Safety/Traffic Management | 10/14/2009 |  | 11/30/2011 | 1720765 | 0
2971 | Maryland | ANNE ARUNDEL | BALTIMORE,MD | 2,3 | 000A486 | This project involves traffic signal reconstruction in Anne Arundel County at MD 2 and MD210. | Safety/Traffic Management | 11/25/2009 |  | 12/31/2011 | 1621285 | 0
2972 | Maryland | ALLEGANY |  | 6 | 0682033 | Maryland State Highway will perfrom patching and install a new layer that will enhance pavement life and provide smoother surface. In addition, the project will enhance safety by upgrading guradrails | Pavement Improvement | 06/08/2009 |  | 12/01/2009 | 3889716 | 3.42
2973 | Maryland | STATEWIDE |  | 6 | 0682034 | Maryland State Highway will Maryland State Highway will either replace guardrails not meeting the current standards or repair them or install new guardrails as needed. This project will improve safety | Safety/Traffic Management | 04/20/2009 |  | 12/01/2009 | 1715913 | 9.4
2974 | Maryland | STATEWIDE |  | 6 | 0682035 | Maryland State Highway will replace existing substandard weatherized traffic barrier along the roadside and median with galvanized traffic barrier on 17 mile section of Interstate 68 (from west of Hil | Safety/Traffic Management | 07/07/2009 |  | 01/01/2011 | 4075603 | 17
2975 | Maryland | ALLEGANY |  | 6 | 0682036 | This project will establish turfgrass in selected bare and eroded areas on MD 36 to Garrett County Line. | Transportation Enhancements | 08/25/2009 |  | 11/30/2009 | 417474 | 3.23
2976 | Maryland | FREDERICK |  | 6 | 0703055 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. In addition, the proj | Pavement Improvement | 06/15/2009 |  | 10/01/2009 | 4118813 | 6.86
2977 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 5 | 0952267 | This project includes work to remove invasive species and install reforestation and landscape plantings along roadsides and within median and quadrant sections of the US 50 / I-495/95 Interchange, loc | Transportation Enhancements | 08/13/2009 |  | 10/01/2011 | 638968 | 0
2978 | Maryland | STATEWIDE |  | 3,5 | 0953182 | Lanscaping using invasive plant control and native plant establishment on I-95 from I-495 to MD212 and from MD109 to MD100. Invasive plant species will be removed and native meadow plants will be pla | Transportation Enhancements | 04/29/2009 |  | 06/01/2011 | 414357 | 0
2979 | Maryland | GARRETT |  | 6 | 1016006 | Maryland State Highway will resurface at various locations in Allegany County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Improvement | 07/23/2009 |  | 02/01/2010 | 947460 | 0.79
2980 | Maryland | FREDERICK |  | 6 | 1051025 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. The project is locate | Pavement Improvement | 06/09/2009 |  | 11/01/2009 | 3163061 | 10.2
2981 | Maryland | FREDERICK |  | 6 | 1074009 | This project will improve roadway characterstics (geometrics improvements) in Frederick County at Fingerboard Rd and Ijamsville Rd/Big Woods Rd toimprove safety. | Pavement Improvement | 04/23/2009 |  | 03/01/2010 | 1948371 | 0.3
2982 | Maryland | HOWARD | BALTIMORE,MD | 3,7 | 1091062 | Maryland State Highway will resurface in Howard County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Improvement | 08/14/2009 |  | 05/01/2010 | 3865394 | 2.63
2983 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 5 | 1194004 | This a bridge replacement project in Prince George's County. | Bridge Replacement | 10/07/2009 |  | 12/31/2010 | 1645200 | 0
2984 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 3 | 1251034 | Baltimore City will resurface Orleans Street from Central Avenue to Wolfe Street for pavement preservation. This project will include updating sidewalks, traffic barriers, storm drains, and roadway l | Pavement Improvement | 08/03/2009 |  | 07/01/2010 | 7082521 | 0
2985 | Maryland | CECIL |  | 1 | 1266003 | This project, located in Cecil County, is for the construction of a 121’ x 77’ expansion of the ride sharing facility at MD 222 and Blythedale Road.This carpool lot in Cecil County has reached 85% cap | Pavement Widening | 06/22/2009 |  | 12/01/2009 | 330214 | 0
2986 | Maryland | STATEWIDE |  | 1 | 1271048 | This project will eradicate or control invasive plants on US 301 in Queen Anne's, Kent and Cecil Counties from US50/301 split to the Delaware line. Native meadow plants will be planted in place of in | Transportation Enhancements | 06/15/2009 |  | 07/01/2011 | 115953 | 0
2987 | Maryland | DORCHESTER |  | 1 | 1301141 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with the new layer that will enhance pavement life and provide smoother surface. This project is | Pavement Improvement | 06/15/2009 |  | 10/01/2009 | 1245512 | 4.49
2988 | Maryland | TALBOT |  | 1 | 1301142 | Maryland State Highway will improve sections of US 50 (from MD 662B to MD 309) in Talbot County by removing few inches of existing roadway and adding a new pavement layer that will wear longer and min | Pavement Improvement | 07/06/2009 |  | 08/01/2010 | 3454391 | 4.09
2989 | Maryland | GARRETT |  | 6 | 2011027 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. In addition, the pr | Pavement Improvement | 06/15/2009 |  | 03/01/2010 | 1383637 | 1.58
2990 | Maryland | GARRETT |  | 6 | 2011028 | This project will resurface US219 from .15 Miles North of MD 42 to Bumble Bee Rd to enhance roadway life and improve ride. | Pavement Improvement | 03/11/2009 |  | 10/01/2009 | 1742518 | 2.17
2991 | Maryland | GARRETT |  | 6 | 2061022 | Maryland State Highway will resurface MD135 from Chestnut Grove Road to Lee Road in Garrett County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 04/01/2009 |  | 02/01/2010 | 2227223 | 3.26
2992 | Maryland | WASHINGTON |  | 6 | 2211014 | This project will add a right turn lane on MD65 at MD63 (lower vertical crest) to facilitate traffic movement and improve safety. | Pavement Improvement | 09/03/2009 |  | 06/30/2010 | 688709 | 0.15
2993 | Maryland | CARROLL |  | 6 | 2341039 | Geometric Improvements | Pavement Improvement | 10/07/2009 |  | 06/30/2010 | 1498087 | 0
2994 | Maryland | CARROLL |  | 6 | 2371018 | Ramp widening (geometric improvement) at MD27 at MD140 ramps. This project will improve safety. | Pavement Improvement | 09/11/2009 |  | 06/30/2010 | 742980 | 0.23
2995 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 4 | 2451032 | MD 410 to wayne Avenue - Traffic Signal Reconstruction for safety. | Safety/Traffic Management | 12/23/2009 |  |  | 1225399 | 0
2996 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 4.8 | 2491025 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD650 from Milestone Drive to Venice Drive to enhance roadway life and smoothness. | Pavement Improvement | 03/03/2009 |  | 02/01/2010 | 2199158 | 1.17
2997 | Maryland | STATEWIDE | WASHINGTON (DC-MD-VA) | 8 | 2491026 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD650 from MD410 to Holton Lane to enhance roadway life and smoothness. | Pavement Improvement | 09/29/2009 |  |  | 1694294 | 0.83
2998 | Maryland | FREDERICK |  | 6 | 2707175 | Maryland State will perfrom patching, removal of surface (as needed) and resurface Northbound I270 from Structure 1007901 Bennett Creek to Structure 1007801 MD 80 to enhance roadway life, safety and s | Pavement Improvement | 03/26/2009 |  | 09/01/2009 | 1087867 | 1.26
2999 | Maryland | CAROLINE |  | 1 | 3001045 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 06/09/2009 |  | 01/01/2010 | 1121978 | 2.47
3000 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 2 | 3009010 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Hilton Street from Frederick Avenue to Mulberry Street to enhance roadway life and smoot | Pavement Improvement | 07/15/2009 |  | 12/01/2009 | 928143 | 0
3001 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 2 | 3019006 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Park Heights Avenue from NorthernPArkway to Garrison Bulevard to enhance roadway life an | Pavement Improvement | 10/15/2009 |  |  | 1619916 | 0
3002 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 2 | 3200001 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Frankford Avenue from Sinclair Lane to Moravia Park Drive to enhance roadway life and sm | Pavement Improvement | 07/06/2009 |  | 12/01/2009 | 1340347 | 0
3003 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 2 | 3341002 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Northern Parkway from Falls Road to Park Heights Avenue to enhance roadway life and smoo | Pavement Improvement | 06/22/2009 |  | 05/01/2010 | 7572091 | 0
3004 | Maryland | HARFORD |  | 1 | 3631001 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 06/22/2009 |  | 12/01/2009 | 1289267 | 2.14
3005 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 8 | 4952276 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In ad | Pavement Improvement | 07/16/2009 |  | 06/01/2010 | 8941712 | 3.92
3006 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 4,5 | 5008022 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. This p | Pavement Improvement | 10/14/2009 |  | 03/31/2010 | 2251154 | 1.12
3007 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 8 | 5010013 | Geometric Improvements | Pavement Improvement | 10/14/2009 |  | 09/30/2010 | 1155452 | 0
3008 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 8 | 5018026 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 06/09/2009 |  | 12/01/2011 | 4060019 | 1.76
3009 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 8 | 5067010 | This project will replace existing deteriorating pavement surface ( MD 212, Riggs Road from Washington D.C. line to Sargent Road) in Prince George's County with new pavement surface. It will also mak | Pavement Improvement | 10/23/2009 |  | 09/30/2010 | 2149319 | 0.93
3010 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 5 | 5067011 | This project will improve safety at MD212 at Allview Drive/Evans Trail by making Geometric improvements. | Pavement Improvement | 09/22/2009 |  |  | 1425410 | 0
3011 | Maryland | ALLEGANY | CUMBERLAND (WV) | 06 | 7509004 | Maryland State Highway Will reconstruct Maryland Avenue from Jefferson Street to Short Street in Allegany County. | Pavement Improvement | 10/08/2009 |  |  | 498000 | 0
3012 | Massachusetts | BRISTOL | FALL RIVER (RI) | 3,4 | 001S899 | The project includes the construction of a new interchange (Exit 8 1/2) on Route 24 in Freetown and construction of new access roadways east to the proposed Fall River Executive Park and west to South | Pavement Improvement | 11/30/2009 | 11/30/2009 |  | 32053618 | 0
3013 | Massachusetts | PLYMOUTH | TAUNTON | 4, 9 | 001S917 | This project will resurface Route 18/28 from Bridgewater Center to the Middleborough Rotary (intersection of Route 44) and make drainage improvements. | Pavement Improvement | 04/23/2009 | 04/23/2009 |  | 2842051 | 0
3014 | Massachusetts | BERKSHIRE |  | 1 | 001S918 | The project will begin at the Adams/Cheshire town boundary (MM 66.3) and will end just north of Commonwealth Avenue (MM 67.8) for a project length of approximately 1.5 miles. MassHighway will resurfac | Pavement Improvement | 04/23/2009 | 04/23/2009 |  | 2199456 | 1.5
3015 | Massachusetts | BARNSTABLE | HYANNIS | 10 | 001S919 | This project will resurface Route 6 (Scenic Highway) from the intersection with Nightingale Pond Road to just east of the intersection with Bourndale Road in the Town of Bourne. | Pavement Improvement | 04/23/2009 | 04/23/2009 |  | 1756160 | 2.41
3016 | Massachusetts | BRISTOL | NEW BEDFORD | 4 | 001S920 | Resurface Route 6 from west of the Dartmouth town line (milemarker 20.9±) to the Fall River city line (milemarker 16.3±), a distance of approximately 4.6 miles. | Pavement Improvement | 04/30/2009 | 04/30/2009 |  | 5074035 | 4.65
3017 | Massachusetts | WORCESTER |  | 1 | 001S921 | In the Town of Barre, this project will resurface Route 122 and a section of Rte 62. The state highway section of the project begins just west of Pleasant Street (milemarker 48.265) and proceeds weste | Pavement Improvement | 05/14/2009 | 05/14/2009 |  | 2268246 | 0
3018 | Massachusetts | BARNSTABLE |  | 10 | 001S922 | In Barnstable: Perform resurfacing and related work on the state-owned sections of Route 6A, from milemarker 8.12 to milemarker 16.56, a distance of approximately 8.5 miles. Also included in the proj | Pavement Improvement | 07/02/2009 | 07/02/2009 |  | 3150634 | 8.43
3019 | Massachusetts | MIDDLESEX |  | 7 | 001S923 | This project will resurface a section of Route 2 in Lincoln. Work includes guardrail, painting and signage. | Pavement Improvement | 05/14/2009 | 05/14/2009 |  | 1596500 | 3.05
3020 | Massachusetts | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 5 | 001S924 | This project will resurface Route 2 in Concord from Walden to the Sudbury town line and from Nine Acre Corner road to Elm Street. Work includes guardrail, painting and signage. | Pavement Improvement | 05/07/2009 | 05/07/2009 |  | 4313468 | 1.05
3021 | Massachusetts | BRISTOL | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 3 | 001S925 | Mill and resurface Route 6 in Swansea from the Somerset town line to the Rehoboth town line. Work on this project also includes the repair of frost heaves and the reconstruction of existing sidewalks. | Pavement Improvement | 04/23/2009 | 04/23/2009 |  | 4159044 | 5.5
3022 | Massachusetts | BARNSTABLE |  | 10 | 001S926 | Mill and resurface Route 6A in Dennis from the Yarmouth Town Line to the Brewster Town Line, a distance of approximately 4.3 miles. | Pavement Improvement | 06/25/2009 | 06/25/2009 |  | 1611976 | 4.28
3023 | Massachusetts | NORFOLK |  | 9 | 001S927 | This is a Pavement Preservation Project for Route 24 in Avon and Stoughton. | Pavement Improvement | 07/31/2009 | 07/31/2009 |  | 5718302.23 | 4
3024 | Massachusetts | WORCESTER |  | 1 | 001S932 | Mill and resurface Route 32 (Main Street) from the Ware/New Braintree town line (milemarker 22.383) to just past the New Braintree/Hardwick town line (milemarker 23.38), a distance of approximately 1 | Pavement Improvement | 05/14/2009 | 05/14/2009 |  | 657048 | 0.94
3025 | Massachusetts | FRANKLIN | FITCHBURG-LEOMINSTER | 1 | 001S933 | In Gill and Wendell: Work under this project will consist of milling the existing paved surface and repaving with 2" of HMA modified top course material. Work will also include repairs/upgrades to gua | Pavement Improvement | 04/30/2009 | 04/30/2009 |  | 3590569 | 0
3026 | Massachusetts | HAMPSHIRE |  | 1 | 001S934 | This project takes place in a number of locations between Westfield and Easthampton. The project will consist of milling the existing paved surface of Route 5 & 10 and repaving with 2" of HMA modified | Pavement Improvement | 05/21/2009 | 05/21/2009 |  | 3891211 | 0
3027 | Massachusetts | WORCESTER |  | 3 | 001S935 | This project will commence at Route 140 in Shrewsbury and continue in a westerly direction to Massasoit Road in Worcester, a distance of approximately 3.5 miles. | Pavement Improvement | 11/27/2009 | 11/27/2009 |  | 2775064 | 3.23
3028 | Massachusetts | FRANKLIN |  | 1 | 001S936 | The focus of the Northfield Street Improvement Project is to reconstruct sidewalks on Main Street and Parker Avenue in Northfield from a point north of the intersection with River Street continuing no | Transportation Enhancements | 05/07/2009 | 05/07/2009 |  | 1100620 | 0
3029 | Massachusetts | BERKSHIRE | PITTSFIELD | 1 | 001S937 | In Lenox: Reconstruction of State Highway from the Route 7 intersection north for approximately 1.25 miles to the end of the State Highway just south of the intersection with Route 183. Included in th | Pavement Improvement | 06/25/2009 | 06/25/2009 |  | 3670203.6 | 1.3
3030 | Massachusetts | NANTUCKET |  | 10 | 001S941 | This project in Nantucket consists of the mill and resurface of Milestone Road from just west of rotary that intersects Orange Street, Sparks Avenue, and Old South Road, to just east of rotary that in | Pavement Improvement | 05/21/2009 | 05/21/2009 |  | 4748670 | 0
3031 | Massachusetts | HAMPSHIRE |  | 1 | 001S942 | The purpose of this project is to resurface portions of Route 9 in Belchertown and Ware. Work will also include repairs/upgrades to guardrail end treatments as needed and new pavement markings. Beche | Pavement Improvement | 05/21/2009 | 05/21/2009 |  | 4699691 | 0
3032 | Massachusetts | BERKSHIRE |  | 1 | 001S945 | The proposed scope for this project consists of micro-milling Route 8 shoulders and partially into travel lanes, installing a stress absorbing interlayer (SAMI) over the travel lanes, and applying a h | Pavement Improvement | 05/14/2009 | 05/14/2009 |  | 1265387 | 0
3033 | Massachusetts | PLYMOUTH |  | 9 | 001S946 | In Brockton: Reconstruct Route 27, Pleasant Street, West Street and Westgate Mall Road. Work includes minor widening, geometric improvements, new traffic signals and interconnection of signalized int | Pavement Improvement | 07/30/2009 | 07/30/2009 |  | 2811883 | 0
3034 | Massachusetts | BERKSHIRE |  |  | 001S947 | This project proposes to resurface Route 7 in New Ashford and Lanesborough with hot-mix asphalt, and would also include repairing/improving the drainage system, resetting guardrail, upgrading guardrai | Pavement Improvement | 05/07/2009 | 05/07/2009 |  | 2406702 | 0
3035 | Massachusetts | WORCESTER | WORCESTER, MA-CT | 3, 5 | 001S949 | The proposed work under this project consists of bridge reconstruction, widening, guardrail installation and all other work on Water Street from its intersection with Bolton Street and Harris Street t | Bridge Replacement | 09/10/2009 | 09/10/2009 |  | 3514426 | 0
3036 | Massachusetts | WORCESTER | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 5 | 001S952 | Resurface Route 2 in Harvard and Littleton from the vicinity of the Littleton Road Bridge to the Boxborough town line, a distance of approximately 4.4 miles. Work includes minor box widening to extend | Pavement Improvement | 04/30/2009 | 04/30/2009 |  | 5175866 | 4.55
3037 | Massachusetts | HAMPSHIRE |  | 1 | 001S953 | The project involves roadway and sidewalk rehabilitation on town-owned Elm Street in the Town of Hatfield, and includes coldplaning, roadway reclamation, hot mix asphalt paving, replacement of sidewal | Pavement Improvement | 07/08/2009 | 07/09/2009 |  | 975700 | 0
3038 | Massachusetts | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 6 | 001S954 | The proposed expansion of the Newburyport Park & Ride facility will add 105 parking spaces. Work will include the construction of a soil nail retaining wall, upgrades to the existing lighting, as well | Safety/Traffic Management | 08/13/2009 | 08/13/2009 |  | 3958204 | 0
3039 | Massachusetts | HAMPDEN |  | 2 | 001S955 | This project consists of demolishing and replacing the Red Bridge Road Bridge over the Utilities Canal in Wilbraham. The new bridge will be a superstructure replacement constructed on an improved alig | Bridge Improvement | 07/23/2009 | 07/23/2009 |  | 1838194 | 0
3040 | Massachusetts | WORCESTER | FITCHBURG-LEOMINSTER | 1 | 001S961 | The Project limits are Route 2 in Westminster from Wyman Road/Village Inn Road (Exit 26), easterly into Fitchburg, to the Junction of Route 31 in Fitchburg, a distance of approximately 2.6 miles. The | Pavement Improvement | 08/07/2009 | 08/07/2009 |  | 7485002 | 2.26
3041 | Massachusetts | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 1, 2 | 001S962 | This multi-use recreational rail trail project starts at Ferry Street in Easthampton and ends at Earle Street in Northampton, for a total length of 4,400 Meters. It links the Manhan Bike Trail in Eas | Transportation Enhancements | 09/03/2009 | 09/03/2009 |  | 4211726.4 | 0
3042 | Massachusetts | MIDDLESEX |  | 5 | 001S964 | The Town of Westford is proposing to widen approximately 3,000 feet of Littleton Road (Route 110). The existing cross section contains one lane in each direction with an additional left turn lane for | Pavement Improvement | 08/06/2009 | 08/06/2009 |  | 2955042.35 | 0
3043 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8, 9 | 001S965 | This project will make safety and mobility improvements at four major intersections along the Dorchester Avenue corridor; Andrews Square, Glover's Corner, Fields Corner and Peabody Square. Improvemen | Pavement Improvement | 11/17/2009 | 11/17/2009 |  | 15127198 | 0
3044 | Massachusetts | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 1 | 001S967 | The purpose of this project is to improve access to the Jackson Street School by constructing new sidewalks, constructing a new access ramp to the nearby bikepath, installing 4' chain link fence at sc | Transportation Enhancements | 10/01/2009 | 10/01/2009 |  | 613114 | 0
3045 | Massachusetts | WORCESTER |  | 1 | 001S995 | The scope of work for the proposed project is to reconstruct Athol Richmond Road in the Town of Royalston from Elm Avenue in Royalston to the New Hampshire state border. The length of the roadway is a | Pavement Improvement | 11/27/2009 | 11/27/2009 |  | 1000000 | 0
3046 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8 | 002S015 | MassHighway proposes to construct the North Bank Bridge over the MBTA Commuter Rail tracks providing a bicycle/pedestrian connection from East Cambridge to City Square Charlestown and the Boston Harbo | Transportation Enhancements | 11/30/2009 | 11/30/2009 |  | 29176615 | 0
3047 | Massachusetts | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) |  | 002S026 | This project proposes to reconstruct Bridge Street (Route 1A) from the Beverly Salem Bridge to Washington Street. The project includes, sidewalks, curbing, trees and pavement markings. | Pavement Improvement | 12/17/2009 | 12/17/2009 |  | 7234415 | 0
3048 | Massachusetts | WORCESTER |  | 2 | 002S034 | This Footprint Road project in Southbridge involves milling and resurfacing, selected full-depth construction and minor box widening to provide a uniform width. (3.25 mi) | Pavement Improvement | 12/10/2009 | 12/10/2009 |  | 2000290 | 0
3049 | Massachusetts | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) |  | 002S053 | Fiber optic connectivity at three locations. Dist 4 via Rte 2 to MBTA Alewife station in Cambridge, Newton rest area on Rte 128 to MBTA riverside station, MEMA bunker to MTA toll plaza in Framingham | Safety/Traffic Management | 12/17/2009 | 12/17/2009 |  | 1400000 | 0
3050 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) |  | 002S055 | Upgrade of the TOC and BTD video systems to IP based virtual matrix switching system. | Safety/Traffic Management | 12/10/2009 | 12/10/2009 |  | 1000000 | 0
3051 | Massachusetts | SUFFOLK |  |  | 002S056 | The design of communication equipment at five locations to increase bandwidth and allow for single CCTV connections for viewing for the City of Boston. | Safety/Traffic Management | 12/10/2009 | 12/10/2009 |  | 402958 | 0
3052 | Michigan | INGHAM |  | 8 | 0833038 | 1.25 miles of roadway reconstruction of North Williamston Road from Sherwood Road to the city limits of Williamston in Ingham County. This project includes tree removals and drainage improvements. | Other | 03/23/2009 | 03/26/2009 | 08/21/2009 | 23000 | 1.25
3053 | Michigan | INGHAM |  | 8 | 0833039 | 2.0 miles of pavement resurfacing of North Williamston Road from Sherwood Road to Haslett Road just north of the city of Williamston in Ingham County. This project will improve pavement rideability a | Pavement Improvement | 03/23/2009 | 03/26/2009 | 08/21/2009 | 200000 | 1.999
3054 | Michigan | ALCONA |  | 1 | 0901004 | MDOT will resurface 5 miles of US-23 from Everett Rd to Black River Rd in the vicinity of Ossineke. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 05/05/2011 | 3402382.89 | 4.889
3055 | Michigan | ALCONA |  | 1 | 0901005 | MDOT will resurface 4.5 miles of M-72 from M-65 to west of O'Donnell Rd in the Huron National Forest. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/16/2009 | 07/16/2009 | 10/10/2009 | 1354849.7 | 4.31
3056 | Michigan | ALCONA |  | 1 | 0901006 | The Alcona County Road Commission will resurface 2.5 miles of East Black River Rd from US-23 to Lakeshore Rd east of the village of Lost Lake Woods. This will improve the driving quality by making th | Other | 07/30/2009 | 07/30/2009 | 04/01/2011 | 331618 | 2.949
3057 | Michigan | ALGER |  | 1 | 0902006 | This pavement project in Alger County will improve the drive quality and make the road smoother. | Pavement Improvement | 05/14/2009 | 06/01/2009 | 09/30/2009 | 93591 | 4.901
3058 | Michigan | ALGER |  | 1 | 0902007 | This pavement project in Alger County will improve the drive quality and make the road smoother. | Pavement Improvement | 05/14/2009 | 06/01/2009 | 09/30/2009 | 93591 | 5.039
3059 | Michigan | ALGER |  | 1 | 0902008 | This pavement project on Rock River Road in the Village of Chatham will improve the drive quality and make the road smoother. | Pavement Improvement | 05/14/2009 | 06/01/2009 | 09/30/2009 | 27765.54 | 1.519
3060 | Michigan | ALLEGAN |  | 6 | 0903321 | MDOT will resurface 7 miles of I-196, from 71st Street to 118th Avenue in Allegan County, just north of South Haven. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 05/30/2011 | 20616393.02 | 13.961
3061 | Michigan | ALLEGAN | HOLLAND | 6 | 0903322 | MDOT is installing median cable guardrail on 7 miles of I-196, from 71st Street to 118th Avenue in Allegan County, just north of South Haven, to improve safety. | Safety/Traffic Management | 04/02/2009 | 04/02/2009 | 11/06/2009 | 667075.67 | 6.98
3062 | Michigan | ALLEGAN |  | 6 | 0903323 | MDOT will renovate the Glenn Rest Area on I-196 in Allegan County, to improve convenience and service to stopping motorists. | Other | 04/02/2009 | 04/02/2009 | 05/30/2011 | 2230142.82 | 0.939
3063 | Michigan | ALLEGAN |  | 6 | 0903324 | MDOT will make repairs on the bridge carrying I-196 over 71st Street in Allegan County, just north of South Haven, to make the bridge last longer. | Bridge Replacement | 04/02/2009 | 04/02/2009 | 05/30/2011 | 395635.34 | 0
3064 | Michigan | ALLEGAN |  | 6 | 0903327 | "The City of Allegan will resurface 2.3 miles of Babylon Road from River Street to M-40 in the city. This will improve the driving quality by making the road smoother. | Other | 08/12/2009 | 09/22/2009 | 10/24/2009 | 120000 | 2.305
3065 | Michigan | ALLEGAN |  | 6 | 0903333 | "The Allegan County Road Commisssion will resurface 4.2 miles of 109th Avenue from 48th Street to 56th Street, in the southwest part of Allegan County. | Pavement Improvement | 10/06/2009 | 10/11/2009 | 11/13/2009 | 838743 | 4.209
3066 | Michigan | ALPENA |  | 1 | 0904009 | The Alpena County Road Commission resurface 3 miles of Leer Rd from Mellon Rd to Carr Rd in south of the village of Posen. This will improve the driving quality by making the road smoother. | Pavement Improvement | 12/28/2009 |  | 07/02/2010 | 309392 | 3.013
3067 | Michigan | ANTRIM |  | 1 | 0905006 | MDOT will resurface 1.4 miles of M-88 from South Eckhardt Rd to South Central Lake in the vicinity of Bellaire. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 05/05/2011 | 650439.76 | 1.361
3068 | Michigan | ANTRIM |  | 1 | 0905007 | MDOT will resurface 12 miles of M-66 from US-131 west to Lillac Creek in the vicinity of Mancelona. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 |  |  | 526310.56 | 11.977
3069 | Michigan | ARENAC |  | 1 | 0906004 | West of the City of Pinconning on M-65/Maple Ridge Road southeast quadrant and on M-61/I-75 southwest quadrant, there was the improvement to the park and ride lot to encourage ridesharing and reduce t | Other | 04/02/2009 | 04/02/2009 | 12/01/2010 | 80671.95 | 0
3070 | Michigan | ARENAC |  | 1 | 0906005 | Repairs will be made at the US-23 bridge over Big Creek North of the City of Standish to make the bridge last longer. | Pavement Improvement | 04/03/2009 | 04/03/2009 | 10/02/2009 | 65189.48 | 0
3071 | Michigan | BARAGA |  | 1 | 0907010 | This paving of road and shoulders and installed rumble strips project on US-41 south of the City of L'Anse will improve safety and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/20/2009 | 186665.18 | 1.503
3072 | Michigan | BARAGA |  | 1 | 0907011 | This paving of road and shoulders and installed rumble strips project south of the City of L'Anse will improve safety and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/18/2010 | 1827956.55 | 11.355
3073 | Michigan | BAY | BAY CITY | 1,5 | 0909009 | There is 52.76 miles of shoulder widening within the Cities of Standish, Omer, and Augres to improve mobility and reduce congestion. | Transportation Enhancements | 04/23/2009 | 04/23/2009 | 03/31/2010 | 3860807.34 | 52.875
3074 | Michigan | BAY | BAY CITY | 5 | 0909012 | Bay City is perfoming 0.19 miles of roadway realignment and intersection modifications on Marquette Avenue to improve safety. | Pavement Improvement | 06/02/2009 | 08/24/2009 | 06/01/2010 | 480000 | 0.402
3075 | Michigan | BAY | BAY CITY | 5 | 0909018 | Within Bay City, MDOT will replace I-75 from Squaconning Creet to Hotchkiss to improve safety and increase mobility. | Pavement Improvement | 09/03/2009 | 09/03/2009 | 09/19/2013 | 16243935.32 | 3.687
3076 | Michigan | BAY |  | 5 | 0909019 | Within Bay City, MDOT will replace I-75 from Squaconning Creet to Hotchkiss to improve safety and increase mobility. | Bridge Improvement | 01/25/2010 |  | 09/19/2013 | 2613068.07 | 0
3077 | Michigan | BAY | BAY CITY | 5 | 0909020 | Within Bay City, MDOT will replace M-84 over Squaconning Creek and Dutch Creek to improve safety and increase mobility. | Bridge Replacement | 10/01/2009 | 10/01/2009 | 09/19/2013 | 3060406.05 | 0
3078 | Michigan | BAY | SAGINAW | 5 | 0909021 | This is reconstructing 4.49 miles on 6 bridges to improve safety and increase capacity. | Pavement Widening | 01/25/2010 |  | 09/19/2013 | 13120368.56 | 3.261
3079 | Michigan | BERRIEN | BENTON HARBOR | 6 | 0911332 | "The City of St. Joseph will resurface 0.13 miles of Park St. from Lake Boulevard to Main Street in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/13/2009 | 09/08/2009 | 07/27/2011 | 210060.39 | 0.134
3080 | Michigan | BERRIEN | BENTON HARBOR | 6 | 0911335 | MDOT is installing median cable guardrail on 18 miles of I-94, from US-12 to I-94 BL near Bridgeman in Berrien County, just south of the Benton Harbor - St. Joseph metropolitan area, to improve safety | Safety/Traffic Management | 05/29/2009 | 05/29/2009 | 06/25/2010 | 3239999.4 | 36.096
3081 | Michigan | BERRIEN | BENTON HARBOR | 6 | 0911351 | "The Berrien County Road Commisssion will resurface 1.8 miles of Glenlord Road from I-94 BL to Cleveland Avenue and from Lincoln to M-139, through Stevensville and Shoreham, on the south side of the B | Pavement Improvement | 06/30/2009 | 08/03/2009 | 08/12/2009 | 75559.85 | 3.538
3082 | Michigan | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0911352 | "The Berrien County Road Commisssion will resurface 4 miles of Range Line Rd. from Walton Road north, between Buchanan and Berrien Springs in Berrrien County. This will improve the driving quality by | Pavement Improvement | 06/30/2009 | 07/14/2009 | 07/17/2009 | 68534.59 | 4.044
3083 | Michigan | BERRIEN |  | 6 | 0911353 | "The Berrien County Road Commisssion will resurface sections of Coloma Road and Range Line Road totalling 5 miles in northwest and southern Berrrien County. This will improve the driving quality by m | Pavement Improvement | 06/30/2009 | 07/20/2009 | 08/10/2009 | 91004.42 | 5.044
3084 | Michigan | BERRIEN |  | 6 | 0911354 | "The Berrien County Road Commisssion will resurface sections of Red Arrow Highway, Warren Woods Road and Shawnee Road totalling 4.2 miles in the southern part of Berrrien County. This will improve th | Pavement Improvement | 06/30/2009 | 08/03/2009 | 08/13/2009 | 89165.81 | 4.221
3085 | Michigan | BERRIEN |  | 6 | 0911355 | "The Berrien County Road Commisssion will resurface sections of Hagar Shore, Blue Star Highway and Paul Avenue totalling 5.5 miles in the northwest corner of Berrrien County. This will improve the dr | Pavement Improvement | 06/30/2009 | 07/20/2009 | 08/10/2009 | 77153.97 | 4.828
3086 | Michigan | BERRIEN | BENTON HARBOR | 6 | 0911359 | "The Berrien County Road Commisssion will resurface 8 miles of Pipestone Road, Nickerson Avenue, Sodius Parkway and Red Arrow Highway in the area south and east of the Benton Harbor - St. Joseph metro | Pavement Improvement | 01/14/2010 |  |  | 616054 | 7.982
3087 | Michigan | BERRIEN |  | 6 | 0911363 | "The City of Watervliet will resurface 0.41 miles of East St. Joseph Avenue from M-140 to Lewis in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/02/2010 |  | 08/15/2010 | 165000 | 0.414
3088 | Michigan | BERRIEN |  | 6 | 0911364 | "The village of Baroda will resurface 0.21 miles of Hills Road. from the village limits to 1st Street in the village. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/05/2010 |  | 06/04/2010 | 70000 | 0.214
3089 | Michigan | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0911373 | MDOT will resurface 0.31 miles of US-12 BR, from Grant Street to the St. Joseph River in Niles. This will improve the driving quality by making the road smoother. | Pavement Improvement | 12/22/2009 |  | 06/04/2010 | 313281.29 | 0.603
3090 | Michigan | BRANCH |  | 7 | 0912010 | "The Branch County Road Commisssion will resurface 5.5 miles of Jonesville Road from Fremont Road to the Hillsdale County Line, east of Coldwater. This will improve the driving quality by making the | Pavement Improvement | 06/04/2009 | 08/01/2009 | 09/30/2009 | 85200 | 5.462
3091 | Michigan | BRANCH |  | 7 | 0912011 | "The Branch County Road Commisssion will resurface 3.6 miles of North Fremont Road from Corless Road to US-12, just east of Coldwater. This will improve the driving quality by making the road smoothe | Pavement Improvement | 06/04/2009 | 08/01/2009 | 09/30/2009 | 35365.93 | 3.606
3092 | Michigan | BRANCH |  | 6,7 | 0912012 | "The Branch County Road Commisssion will resurface 5.6 miles of Burr Oak Road from Bronson city limits to the St. Joseph County Line, in Branch County. This will improve the driving quality by making | Pavement Improvement | 06/04/2009 | 07/27/2009 | 09/23/2009 | 79182.79 | 5.629
3093 | Michigan | BRANCH |  | 7 | 0912013 | "The Branch County Road Commisssion will resurface sections of Dunks Rd., Creamery Rd. and Railroad Rd. totalling 6.1 miles in the northwest corner of the county. This will improve the driving qualit | Pavement Improvement | 06/04/2009 | 08/01/2009 | 09/30/2009 | 85500 | 6.086
3094 | Michigan | BRANCH |  | 7 | 0912014 | The Branch County Road Commisssion will resurface 5.6 miles of Orland Road and Southern Road, from Rierson Road to Dewsenberry Road, in the southwest part of the county. This will improve the driving | Pavement Improvement | 06/09/2009 | 07/16/2009 | 08/03/2009 | 57378 | 5.565
3095 | Michigan | BRANCH |  | 7 | 0912015 | "The Branch County Road Commisssion will resurface 4 miles of Marshall Road from Newton Road to Girard Rd, just north of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/24/2009 | 09/23/2009 | 07/31/2010 | 68699 | 4.036
3096 | Michigan | BRANCH |  | 7 | 0912016 | "The Branch County Road Commisssion will repair one mile of Marshall Road from Newton Road to State Rd, just north of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/29/2009 | 09/22/2009 | 09/30/2009 | 13055 | 1.004
3097 | Michigan | BRANCH |  | 7 | 0912018 | "The City of Coldwater will repair various sections of W. Pearl Street totalling 8.9 miles in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/13/2009 | 09/22/2009 | 07/31/2010 | 52633 | 8.982
3098 | Michigan | BRANCH |  | 7 | 0912019 | "The Branch County Road Commisssion will resurface 2.5 miles of River road from Garfield Road to US-12 and from US-12 to Narrows Road, in the city of Coldwater. This will improve the driving quality | Pavement Improvement | 08/13/2009 | 08/27/2009 | 10/05/2009 | 47550.54 | 2.516
3099 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913222 | "The City of Battle Creek will resurface 1 mile of Beckley Road from Helmer Road to Stone Jug Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/04/2009 | 09/15/2009 |  | 189291.44 | 1.012
3100 | Michigan | CALHOUN | BATTLE CREEK | 6,7 | 0913223 | "The City of Battle Creek will resurface 1 mile of Capital Avenue SW from Beckley Road to the city limits. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/04/2009 | 09/15/2009 |  | 246674.85 | 1.001
3101 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913224 | "The City of Battle Creek will resurface 1.7 miles of Jackson Street from M-37 to Bedford Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/04/2009 | 09/15/2009 |  | 361852.38 | 1.692
3102 | Michigan | CALHOUN |  | 7 | 0913225 | The Calhoun County Road Commission is building sidewalks and ADA ramps on 1.5 miles of M-96 from Columbia Avenue to I-94 BL in the city of Battle Creek, to improve pedestrian mobility and safety. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/25/2009 | 241521.1 | 1.463
3103 | Michigan | CALHOUN |  | 7 | 0913229 | The Calhoun County Road Commission will resurface 3 miles ofN Drive N from 12 Mile Road to 15 Mile Road, east of Battle Creek. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/27/2011 | 441159.36 | 2.976
3104 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913231 | The Calhoun County Road Commission will resurface 1.9 miles of Bellevue Road from Verona Road to McAllister, in the Battle Creek urbanized area. This will improve the driving quality by making the ro | Pavement Improvement | 09/02/2009 | 10/16/2009 |  | 287351.15 | 1.869
3105 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913232 | The Calhoun County Road Commission will resurface 0.6 miles of Beadle Lake Road from B Drive N to Division Drive, in the Battle Creek urbanized area. This will improve the driving quality by making t | Pavement Improvement | 09/17/2009 | 09/30/2009 |  | 167331.71 | 0.6
3106 | Michigan | CALHOUN |  | 7 | 0913233 | "The City of Marshall will resurface 0.56 miles of North Kalamazoo Avenue from Brewer Street to Linden Street in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/23/2009 | 10/01/2009 | 11/15/2009 | 124881.35 | 0.559
3107 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913234 | "The City of Springfield will resurface 1.3 miles of Harmonia Road from M-37 to Evergreen in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/28/2009 | 09/08/2009 | 07/27/2011 | 330773 | 1.344
3108 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914019 | The Cass County Road Commission will resurface 1.8 miles of Ironwood Drive from Redfield Street to Bell Road, in the Niles urbanized area. This will improve the driving quality by making the road smo | Pavement Improvement | 07/09/2009 | 07/01/2010 | 07/10/2010 | 40360 | 1.76
3109 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914020 | The Cass County Road Commission will resurface 0.2 miles of Redfield Road from Adamsville Road to Mason Township, in the Niles urbanized area. This will improve the driving quality by making the road | Pavement Improvement | 07/09/2009 | 07/01/2010 | 07/10/2010 | 12150 | 0.192
3110 | Michigan | CASS |  | 6 | 0914021 | The Cass County Road Commission will resurface 0.5 miles of Matthews Street from Dailey Road to Cherry Grove Road, in the Dowagiac urbanized area. This will improve the driving quality by making the | Pavement Improvement | 07/07/2009 | 10/01/2009 | 10/31/2009 | 50000 | 0.503
3111 | Michigan | CASS |  | 6 | 0914022 | The Cass County Road Commisssion will resurface 3.7 miles of Decatur Road from M-60 to Kelsey Lake Road, near Cassopolis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 08/31/2009 | 09/15/2009 | 87279.15 | 3.717
3112 | Michigan | CASS |  | 6 | 0914023 | The Cass County Road Commisssion will resurface 3 miles of Brownsville Street from M-62 to Crooked Creek Road,south of Cassopolis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/30/2009 | 08/31/2009 | 09/15/2009 | 73916 | 2.962
3113 | Michigan | CASS |  | 6 | 0914024 | "The Cass County Road Commission will resurface various sections of Pine Lake, Monette and Dailey Streets totalling 7.3 miles in the southwest part of the county. This will improve the driving quality | Pavement Improvement | 06/30/2009 | 08/31/2009 | 09/15/2009 | 77650 | 2.64
3114 | Michigan | CASS |  | 6 | 0914025 | The Cass County Road Commisssion will resurface 1.7 miles of Indian Lake Road fromCrystal Springs to Smith Lake Road, between Niles and Dowagiac. This will improve the driving quality by making the r | Pavement Improvement | 06/30/2009 | 08/31/2009 | 09/15/2009 | 32041 | 1.716
3115 | Michigan | CASS |  | 6 | 0914026 | "The Cass County Road Commission will resurface various sections of Marcellus Highway totalling 0.9 miles in thenorth part of the county. This will improve the driving quality by making the road smoot | Pavement Improvement | 06/30/2009 | 08/31/2009 | 09/15/2009 | 82515.97 | 3.845
3116 | Michigan | CASS |  | 6 | 0914027 | The Cass County Road Commission will resurface 0.18 miles of Middle Crossing Road from Yaw Street to the city limits, in the Dowagiac urbanized area. This will improve the driving quality by making t | Pavement Improvement | 07/08/2009 | 05/01/2010 | 05/31/2010 | 20000 | 0.18
3117 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914031 | The Cass County Road Commission will resurface 1.4 miles of Huntly Road from Holly Street to Barron Lake Road, in the Niles urbanized area. This will improve the driving quality by making the road sm | Pavement Improvement | 07/20/2009 | 08/31/2009 | 09/15/2009 | 27500 | 1.36
3118 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914032 | The Cass County Road Commission will resurface 2.7 miles of Beebe Road from US-12 to Runkle Road and from Redfield Street to US-12, in the Niles urbanized area. This will improve the driving quality | Pavement Improvement | 07/20/2009 | 08/31/2009 | 09/15/2009 | 61948 | 2.798
3119 | Michigan | CASS |  | 6 | 0914033 | The Cass County Road Commisssion will resurface 4 miles of Dewey Lake Street from M-51 to Glenwood road, in the northeast part of the county. This will improve the driving quality by making the road | Pavement Improvement | 07/20/2009 | 07/01/2010 | 07/10/2010 | 75947 | 3.959
3120 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914034 | The Cass County Road Commission will resurface 2.5 miles of Pine Lake Road from M-60 to Anderson Road, in the Niles urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/21/2009 | 08/31/2009 | 09/15/2009 | 31578 | 1.584
3121 | Michigan | CHEBOYGAN |  | 1 | 0916011 | MDOT will resurface 1.2 miles of US-23 from M-27 to the Little Black River in the village of Cheboygan. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/27/2009 | 05/27/2009 | 09/18/2009 | 815730.18 | 1.172
3122 | Michigan | CHEBOYGAN |  | 1 | 0916013 | One and a quarter miles of Trowbridge Rd will be resurfaced from the Sturgeon River bridge to South Straights Hwy in the Village of Wolverine. This will improve the driving quality by making the road | Pavement Improvement | 12/10/2009 |  | 06/11/2010 | 15298 | 1.258
3123 | Michigan | CHEBOYGAN |  | 1 | 0916014 | Four tenths of a mile of South Straights Hwy will be resurfaced from Cedar St to the north village limits of the Village of Wolverine. This will improve the driving quality by making the road smoothe | Pavement Improvement | 12/10/2009 |  | 06/11/2010 | 58321.06 | 0.408
3124 | Michigan | CLARE |  | 4 | 0918007 | There will be 5.41 miles of paved pathway in the village of Farwell on the Pere Marquette Rail Trail for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 04/02/2009 | 04/02/2009 | 04/30/2010 | 804661.79 | 5.409
3125 | Michigan | CLINTON | LANSING | 8 | 0919009 | Near the city of Bath in Clinton County, MDOT will improve the driving surface of 6.5 miles of I-96 with a concrete restoration project. | Pavement Improvement | 05/01/2009 | 05/01/2009 | 06/16/2011 | 1740322.35 | 16.097
3126 | Michigan | CLINTON |  | 8 | 0919010 | Near the City of Dewitt, The Clinton County Road Commission is resurfacing 1 mile of West Alward Road from US-127BR to Williams Road to improve driving quality and make the road smoother. | Pavement Improvement | 08/03/2009 | 08/11/2009 | 09/18/2009 | 163735.7 | 1.004
3127 | Michigan | CLINTON | LANSING | 8 | 0919011 | In the city of Dewitt, over 1/2 mile of West Main Street will be resurfaced from Norris Road to Scott Street to improve ride quality and make the roadway smoother. Improvements include new sidewalk t | Pavement Improvement | 08/03/2009 | 08/24/2009 |  | 190414.02 | 0.602
3128 | Michigan | CLINTON | LANSING | 8 | 0919012 | Near the city of Dewitt, The Clinton County Road Commission is resurfacing 1 mile of East Clark Road from US-127BR to Wood Road to improve driving quality and make the road smoother. | Pavement Improvement | 08/03/2009 | 08/19/2009 | 09/18/2009 | 287307.25 | 1.003
3129 | Michigan | CLINTON |  | 8 | 0919013 | Close to the villages of Hubbardston and Pewamo, the Clinton county Road Commission will improve 4 miles of pavement on West Colony Road from the West Clinton County Line to Tallman Road. | Pavement Improvement | 06/02/2009 | 06/22/2009 | 07/11/2009 | 65955.65 | 3.945
3130 | Michigan | CLINTON |  | 8 | 0919014 | In Bath Township, the Clinton County Road Commission will resurface 1/2 mile of East Clark Road from Webster Road to the east to improve driving quality and make the road smoother. | Pavement Improvement | 08/14/2009 | 09/01/2009 | 09/18/2009 | 134651.7 | 0.5
3131 | Michigan | CLINTON |  | 7,8 | 0919015 | MDOT is reconstructing nearly 7 miles of I-96 in Clinton and Eaton Counties to improve driver mobility and make the roadway safer and smoother. This project is the 5000th Recovery Act project and is | Pavement Improvement | 06/24/2009 | 06/24/2009 | 03/01/2012 | 44930832.47 | 15.835
3132 | Michigan | CLINTON |  | 8 | 0919021 | 4 miles of East Colony Road is being resurfaced north of St. Johns to make the roadway smoother and improve ride quality. | Pavement Improvement | 08/05/2009 | 08/11/2009 | 08/31/2009 | 68354.97 | 4.013
3133 | Michigan | CRAWFORD |  | 1 | 0920009 | The Crawford County Road Commission will resurface 1.7 miles of South Wakely Bridge Rd from M-72 to The Au Sable River in the Huron National Forest near Grayling. This will improve the driving qual | Pavement Improvement | 09/03/2009 | 09/21/2009 | 10/30/2009 | 195116.35 | 1.664
3134 | Michigan | CRAWFORD |  | 1 | 0920010 | MDOT will resurface 2.4 miles of M-93 from Camp Grayling to M-72 in the vicinity of Grayling. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/13/2009 | 05/13/2009 | 06/25/2010 | 385568.05 | 2.606
3135 | Michigan | CRAWFORD |  | 1 | 0920013 | MDOT will resurface 5 miles of I-75 from south of the NYC RR to north of M-93 in the vicinity of Grayling. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/02/2009 | 06/02/2009 | 05/05/2011 | 3385359.89 | 5.319
3136 | Michigan | DELTA |  | 1 | 0921011 | This intersection project at US-2 and US-41 in the City of Rapid River will increase safety and improve the pavement condition which will make for a smoother ride. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2010 | 1510991.51 | 0.641
3137 | Michigan | DELTA |  | 1 | 0921014 | This pavement project on County Road 513 in Delta County will improve the drive quality and make the road smoother. | Pavement Improvement | 08/19/2009 | 04/15/2010 | 11/15/2010 | 489861 | 11.416
3138 | Michigan | DICKINSON |  | 1 | 0922007 | This Center Left-Turn lane project on M-95 in Sagola will improve safety and increase mobility. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 10/18/2010 | 374256.48 | 0.363
3139 | Michigan | DICKINSON |  | 1 | 0922008 | This pavement project on Balsam Street in the City of Kingsford will improve the drive quality and make the road smoother. | Pavement Improvement | 09/01/2009 | 09/28/2009 | 10/20/2009 | 235653.8 | 0.497
3140 | Michigan | EATON | LANSING | 7 | 0923010 | In Eaton County just outside of city of Lansing limits , 2.41 miles of Creyts Road is to be resurfaced from Lansing Road to I-496. This work will improve driving quality and make the road smoother. | Pavement Improvement | 06/29/2009 | 07/13/2009 | 10/30/2009 | 619427 | 2.414
3141 | Michigan | EATON | LANSING | 7 | 0923012 | In the City of Grand Ledge, just over 1/4 miles of Brookside Drive from Timbercreek Street to South Street will be reconstructed to improve rideability and make the roadway smoother. | Pavement Improvement | 07/31/2009 | 08/03/2009 | 09/14/2009 | 205654.6 | 0.349
3142 | Michigan | EATON | LANSING | 7 | 0923013 | In the City of Grand Ledge, 1/4 miles of Timber Creek Drive from Saginaw highway to Brookside Drive will be reconstructed to improve rideabilty and make the roadway smoother. | Pavement Improvement | 07/31/2009 | 08/03/2009 | 09/14/2009 | 188281.22 | 0.284
3143 | Michigan | EATON |  | 7 | 0923015 | In the City of Eaton Rapids, MDOT is working on building a streetscape project on South Clinton Trail and South Main Street (State Routes M-99 & M-50) The work will be from just west of Hallawood Lan | Pavement Improvement | 06/17/2009 | 06/17/2009 | 09/20/2012 | 2220411.77 | 1.385
3144 | Michigan | EATON |  | 7 | 0923016 | The City of Eaton Rapids in Eaton County will beautify its downtown by building this streetscape. The streetscape will include new brick pavers, lighting, decorative sidewalk and and additional lands | Pavement Improvement | 06/10/2009 | 06/10/2009 | 09/20/2012 | 853534.7 | 0.397
3145 | Michigan | EATON | LANSING | 7 | 0923017 | In Eaton County just outside of city of Lansing limits , 1/2 mile of Creyts Road is to be resurfaced from Saginaw highway to the north. This work will improve driving quality and make the road smooth | Pavement Improvement | 10/07/2009 |  | 05/31/2010 | 117146 | 0.499
3146 | Michigan | EMMET |  | 1 | 0924008 | The Emmet County Road Commission will resurface three quarters of a mile of Mitchell Rd from Division Rd east 3900 ft in the vicinity of Petoskey. This will improve the driving quality by making the | Pavement Improvement | 06/15/2009 | 06/15/2009 | 10/19/2009 | 155000 | 0.654
3147 | Michigan | EMMET |  | 1 | 0924009 | The Emmet County Road Commission will resurface 2.3 miles of W Conway Rd from Heydey St to Clayton Rd in Little Traverse Township. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/24/2009 | 10/01/2009 | 11/15/2009 | 354458 | 2.331
3148 | Michigan | GENESEE |  | 4,5 | 0925015 | Just west of the city of Flint, MDOT will repair M-13 over Mistequay Creek to make the bridge last longer. | Bridge Improvement | 04/02/2009 | 04/02/2009 | 12/31/2010 | 187661.7 | 0
3149 | Michigan | GENESEE |  | 4,5 | 0925016 | Just west of the city of Flint, MDOT will repair 12.2 miles of M-13 to extend the service life of the existing pavement. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 12/31/2010 | 5378467.98 | 12.227
3150 | Michigan | GENESEE |  | 5,10 | 0925018 | Within the City of Fenton, MDOT will resurface parking lot on US-23 to improve the quality of the parking surface and extend the life of the road pavement. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 12/31/2010 | 101873.02 | 0
3151 | Michigan | GENESEE | FLINT | 5 | 0925021 | The MDOT will design roadway and bridge improvements to I-475 from the I-75 and I-69 interchange south of Flint north 6.6 miles. | Other | 05/14/2009 | 05/14/2009 | 12/31/2009 | 789887.47 | 14.929
3152 | Michigan | GENESEE | FLINT | 5 | 0925023 | Near the city of Flint, MDOT is upgrading 1.16 miles of pavement on Pasadena Avenue from I-75 to the Flint city limits, Genesee County. This will improve the ride quality of the road. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 06/30/2010 | 1536295 | 1.087
3153 | Michigan | GENESEE | FLINT | 5 | 0925024 | There will be 1.10 miles of pavement repair on Clio Road from Pierson Road to Carpenter Road to improve safety and increase mobility. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 06/30/2010 | 1385335 | 0.997
3154 | Michigan | GENESEE |  | 5 | 0925032 | Genesee County is resurfacing 0.99 miles on Irish Road from Richfield Road northerly to Carpenter Road to improve the driving quality by making the road smoother. | Pavement Improvement | 06/23/2009 | 06/23/2009 | 06/30/2010 | 624753 | 0.925
3155 | Michigan | GENESEE | FLINT | 5 | 0925038 | Genesee County will repair the pavement of 0.83 miles on Morrish Road from I-69 to the Canadian National Railway railroad tracks in the city of Swartz Creek to improve the driving quality of the road. | Pavement Improvement | 07/02/2009 | 07/02/2009 | 06/01/2010 | 263716.04 | 0.918
3156 | Michigan | GENESEE | FLINT | 5 | 0925041 | In the City of Fenton in Genesee County there is 1.16 miles of resurfacing on Silver Parkway from Owen Road to Silver Lake Road to improve the driving quality by making the road smoother. | Pavement Improvement | 10/23/2009 | 10/26/2009 | 10/30/2010 | 1180758.17 | 0.912
3157 | Michigan | GENESEE | FLINT | 5 | 0925046 | In the city of Flint there is 0.95 miles of road reconstruction on Kettering Gateway from I-69 to Chevrolet Avenue to improve the driving quality by making the road smoother. | Pavement Improvement | 08/18/2009 | 10/06/2009 | 05/27/2011 | 2315955.02 | 0.64
3158 | Michigan | GENESEE | FLINT | 5 | 0925054 | In Genesee County, MDOT will perform a Design Build reconstruction of 4 bridge structures on I-475 from the south interchange to I-69 including Hill road and Bristol Road over I-475 and I-475 over Map | Pavement Improvement | 09/18/2009 | 09/18/2009 | 06/17/2011 | 20037904.5 | 14.929
3159 | Michigan | GLADWIN |  | 1 | 0926009 | The County of Gladwin is resurfacing 2.02 miles of roadway to improve the driving quality of the Knox Road from Shock Road easterly to Dundas Road. | Pavement Improvement | 09/02/2009 | 10/05/2009 | 11/07/2009 | 387200 | 1.987
3160 | Michigan | GOGEBIC |  | 1 | 0927008 | This pavement project on US-2 in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 05/01/2009 | 05/01/2009 | 10/18/2010 | 1917655.15 | 16.204
3161 | Michigan | GOGEBIC |  | 1 | 0927014 | This pavement and guardrail project on US-45 in Gogebic County will improve the safety and ride quality of the road. | Pavement Improvement | 08/13/2009 | 08/13/2009 | 07/02/2010 | 1844744.31 | 12.415
3162 | Michigan | GRAND TRAVERSE |  | 4 | 0928008 | East 8th St in Traverse City will be resurfaced for over a half mile from garfield to Woodmere St. This will improve the driving quality by making the road smoother. | Other | 10/19/2009 |  | 06/23/2010 | 210000 | 0.605
3163 | Michigan | GRAND TRAVERSE |  | 4 | 0928010 | The Grand Traverse County Road Commission will place new pavement markings at various locations on county roads in the county to provide more visible markings. | Safety/Traffic Management | 10/08/2009 |  | 06/18/2010 | 277500 | 1.434
3164 | Michigan | GRAND TRAVERSE |  | 4 | 0928011 | The Grand Traverse County Road Commission will place new pavement symbols at various locations on county roads in the county to provide safer roadways. | Safety/Traffic Management | 08/13/2009 | 09/18/2009 | 04/30/2010 | 90692.15 | 1.434
3165 | Michigan | GRAND TRAVERSE |  | 4 | 0928012 | The Grand Traverse County Road Commission will resurface 3.2 miles of karlin Rd from M-137 to Nessen Rd south of the village of Green Lake. This will improve the driving quality by making the road sm | Pavement Improvement | 12/17/2009 |  | 07/02/2010 | 404957.82 | 1.471
3166 | Michigan | GRATIOT |  | 4 | 0929208 | Near the city of Alma there will be 4.05 miles of resurfacing on Lumberjack Road from M-46 northerly to North County Line Road to improve driving quality by making the road smoother. | Other | 12/22/2009 |  | 08/13/2010 | 446327 | 4.057
3167 | Michigan | GRATIOT |  | 4 | 0929210 | The city of Alma is resurfacing 8.92 miles on M-46 from the Gratiot/Montcalm County line easterly to west of US-127BR to improve driving quality by making the road smoother. | Pavement Improvement | 09/21/2009 | 09/21/2009 | 11/01/2010 | 1648382.16 | 8.92
3168 | Michigan | HILLSDALE |  | 7 | 0930012 | 5.29 miles of South Waldron Road from Territorial Road northerly to Prattville Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness through the community | Pavement Improvement | 05/28/2009 | 06/30/2009 | 08/27/2009 | 69889.47 | 5.291
3169 | Michigan | HILLSDALE |  | 7 | 0930013 | 2.75 miles of Church Road from Waldon Road to US-127 will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness east of the city of Hillsdale, Hillsdale County. | Pavement Improvement | 05/28/2009 | 06/29/2009 | 09/17/2009 | 44312.91 | 2.754
3170 | Michigan | HILLSDALE |  | 7 | 0930014 | 2.91 miles of North Adams Road from the Village of Jonesville to Mimes Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness in Hillsdale County. | Pavement Improvement | 05/28/2009 | 06/11/2009 | 08/27/2009 | 93387.72 | 2.914
3171 | Michigan | HILLSDALE |  | 7 | 0930015 | 3.0 miles of North Adam Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, South of the City of Jackson in Hillsdale County. | Pavement Improvement | 05/28/2009 | 06/01/2009 | 08/27/2009 | 91506.45 | 3.004
3172 | Michigan | HILLSDALE |  | 7 | 0930016 | 3 miles of East Bacon Road will have a Chip and Seal treatment from Peterson Road to Osseo Road east of the village of Hillsdale, Hillsdale County. The work will preserve the pavement life and improv | Pavement Improvement | 05/28/2009 | 06/29/2009 | 09/17/2009 | 83859 | 2.993
3173 | Michigan | HILLSDALE |  | 7 | 0930017 | 5 miles of South Allen Road from Bankers Road to US-12 will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness. This proejct is located just west of the city of | Pavement Improvement | 06/02/2009 | 06/29/2009 | 08/27/2009 | 93791.85 | 4.96
3174 | Michigan | HOUGHTON |  | 1 | 0931007 | This paving project on US-41 east of the City of Houghton will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 06/22/2009 | 353754.39 | 2.046
3175 | Michigan | HOUGHTON |  | 1 | 0931008 | This pavement project on US-41 in Houghton County will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/18/2010 | 328382.32 | 2.654
3176 | Michigan | HOUGHTON |  | 1 | 0931009 | This shoulder paving and guardrail installation project on M-26 in Houghton County will serve cyclists, joggers and other non-motorized users and will improve safety. | Transportation Enhancements | 04/02/2009 | 04/02/2009 | 08/18/2009 | 176732.89 | 2.443
3177 | Michigan | HOUGHTON |  | 1 | 0931010 | This paving project on M-26 in the Village of Lake Linden will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/18/2010 | 472359 | 2.577
3178 | Michigan | HOUGHTON |  | 1 | 0931014 | This pavement project on Erickson Drive in the Houghton Urban Area will improve the drive quality and make the road smoother. | Pavement Improvement | 08/31/2009 | 09/23/2009 | 10/15/2009 | 90000 | 0.45
3179 | Michigan | HOUGHTON |  | 1 | 0931015 | This pavement project on 6th Street in the City of Larium will improve the drive quality and make the road smoother. | Pavement Improvement | 08/31/2009 | 09/23/2009 | 10/15/2009 | 115000 | 0.361
3180 | Michigan | HOUGHTON |  | 1 | 0931017 | This pavement project on Sharon Ave. in the Houghton Urban Area will improve the drive quality and make the road smoother. | Pavement Improvement | 09/01/2009 | 09/22/2009 | 10/15/2009 | 88521.77 | 0.48
3181 | Michigan | HURON |  | 10 | 0932213 | North of Sebewaing, MDOT is upgrading 3.6 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 04/14/2009 | 04/14/2009 | 05/01/2010 | 140515.08 | 3.588
3182 | Michigan | HURON |  | 10 | 0932214 | West of Port Austin, MDOT is upgrading 4.8 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Pavement Improvement | 04/16/2009 | 04/16/2009 | 05/21/2010 | 312799.82 | 4.886
3183 | Michigan | HURON |  | 10 | 0932219 | There will be 2.68 miles of resurfacing on Atwater Road from Parisville Road easterly to west of Ruth Road to improve the driving quality of the road by making the road smoother. | Pavement Improvement | 07/22/2009 | 08/29/2009 | 09/30/2009 | 361887 | 2.94
3184 | Michigan | HURON |  | 5,10 | 0932220 | Near the city of Sebewaing there are 16.28 miles sidewalk improvements on M-25 from south of Huron Line Road northeasterly to south of Myers Road, from south of Orchard Street northerly to south of De | Transportation Enhancements | 05/29/2009 | 05/29/2009 | 03/31/2010 | 324143.53 | 3.793
3185 | Michigan | INGHAM | LANSING | 8 | 0933024 | Near the community of Haslett MI, just over 1/4 miles of Marsh Road will be resurfaced from Baker Street to the north Ingham County Line. This project will improve rideabilty and make the roadway smo | Pavement Improvement | 07/02/2009 | 07/27/2009 | 07/31/2009 | 86778.25 | 0.34
3186 | Michigan | INGHAM |  | 8 | 0933025 | Between the cities of Leslie and Eaton Rapids in Ingham County, 6.0 miles of Bellevue Road will have Chip and Seal treatment to preserve pavement life and improve pavement rideabilty. | Pavement Improvement | 05/05/2009 | 07/07/2009 | 07/31/2009 | 93999.72 | 6.149
3187 | Michigan | INGHAM |  | 8 | 0933026 | South of Mason in Ingham County, Barnes Road will have Chip and Seal treatment from South College Road to South Meridian Road to preserve pavement life and improve pavement rideability. This project | Pavement Improvement | 05/05/2009 | 07/20/2009 | 07/24/2009 | 93999.85 | 6.474
3188 | Michigan | INGHAM | LANSING | 8 | 0933028 | 0.95 miles of South Washington Road from West Jolly Road to Miller Road will be resurfaced in the City of Lansing. Improvements include ADA sidewalk ramp upgrades for increased pedestrian access and | Pavement Improvement | 08/05/2009 | 08/05/2009 |  | 322116.67 | 0.948
3189 | Michigan | INGHAM | LANSING | 8 | 0933029 | In the City of East Lansing, 1 mile of East Mount Hope Avenue will be reconstructed along the southern limits of the city. The new roadway will improve rideablity and improve drainage features. | Pavement Improvement | 07/22/2009 | 07/29/2009 | 10/02/2009 | 685351.58 | 1.471
3190 | Michigan | INGHAM |  | 8 | 0933030 | West of the Village of Stockbridge, 4.75 miles of Morton and Heeney Roads will have Chip and Seal treatment to preserve pavement life and improve rideability. | Pavement Improvement | 05/21/2009 | 07/20/2009 | 07/24/2009 | 62576.43 | 4.079
3191 | Michigan | INGHAM | LANSING | 8 | 0933032 | 0.45 miles of Michigan Avenue from US-127 to Friendship Court will be resurfaced in the City of Lansing. Improvements include concrete curb & gutter and sidewalk replacement. The work will improve r | Pavement Improvement | 08/05/2009 | 08/17/2009 | 09/21/2009 | 447851.38 | 0.788
3192 | Michigan | INGHAM | LANSING | 8 | 0933034 | Near Williamston in Ingham county, MDOT will resurface about 8 miles of I-96 to improve driving quality by making the road smoother. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 12/31/2011 | 3477899.93 | 17.302
3193 | Michigan | INGHAM | LANSING | 8 | 0933036 | In the community of Holt in Ingham County, 1.37 miles of West Holt Road from Heatherton Drive to Thornburn Street will be resurfaced to improve rideabilty and make the roadway smoother. | Pavement Improvement | 07/07/2009 | 09/01/2009 | 11/15/2009 | 725374.31 | 1.329
3194 | Michigan | INGHAM | LANSING | 8 | 0933037 | Near the community of Haslett MI, 1/2 miles of Marsh Road will be resurfaced from Tihart Road to just north of Franklin Street in Ingham County. This project will improve rideabilty and make the road | Pavement Improvement | 09/21/2009 | 10/01/2009 | 05/31/2010 | 484059.58 | 0.789
3195 | Michigan | IONIA |  | 3 | 0934011 | The MDOT will resurface 4 miles of M-66 near the City of Ionia. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 12/31/2010 | 889891.1 | 3.902
3196 | Michigan | IONIA |  | 3 | 0934014 | The City of Ionia will resurface over a half mile of West Adams Street from M-66 to Jackson Street in the City of Ionia. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 08/31/2009 |  | 265000 | 0.691
3197 | Michigan | ISABELLA |  | 4 | 0937007 | Within the City of Mt. Pleasant, MDOT will repair 4.85 miles of US-127 south of the Blanchard Road interchange to extend the service life of the existing road as well as make repairs to the bridge to | Pavement Improvement | 04/28/2009 | 04/28/2009 | 09/19/2011 | 9955449.12 | 10.526
3198 | Michigan | ISABELLA |  | 4 | 0937012 | The City of Rosbush is reconstructing 3.00 miles on Vernon Road from Winn Road easterly to Vandecar Road and from Lincoln Road easterly to Mission Road to improve driving quality by making the road sm | Pavement Improvement | 10/05/2009 | 10/09/2009 | 11/06/2009 | 472051 | 3.004
3199 | Michigan | JACKSON |  | 7 | 0938221 | In Jackson County, the County Road Commission will reconstruct East Michigan Avenue from Fox Road to Gillett's Lake Road to improve driving quality by making the road smoother. | Pavement Improvement | 08/04/2009 | 08/17/2009 |  | 624776.04 | 0.755
3200 | Michigan | JACKSON | JACKSON | 7 | 0938222 | In the city of Jackson, Jackson County, the city will resurface 1/2 mile of Ganson Street from Cooper Street to East Avenue. The project will include sidewalk repairs and new ADA ramps to improve ped | Pavement Improvement | 08/26/2009 | 09/08/2009 |  | 270179 | 0.461
3201 | Michigan | JACKSON | JACKSON | 7 | 0938223 | In the city of Jackson, Jackson County, the city will resurface 1/2 mile of West Morrell Street from Brown Street to West Avenue. The project will improve driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 09/08/2009 |  | 328692.09 | 0.502
3202 | Michigan | JACKSON | JACKSON | 7 | 0938224 | In the city of Jackson, Jackson County, the city will reconstruct just under 1/2 mile of North Jackson Street from Glick Highway to Ganson Street to improve driving quality by making the road smoother | Pavement Improvement | 12/23/2009 |  | 07/30/2010 | 533236.53 | 0.371
3203 | Michigan | JACKSON | JACKSON | 7 | 0938241 | In Jackson County, the County Road Commission will resurface Springport Road from Shirley Drive to Airport Road to improve just over a mile of road to improve drive quality by making the road smoother | Pavement Improvement | 02/03/2010 |  |  | 854294.3 | 1.273
3204 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939011 | MDOT will reconstruct the interchange of I-94 at Westnedge Avenue to a new design and will reconstruct and add a lane in each direction to 1.9 miles of I-94, between Oakland Drive and Lovers Lane, in | Pavement Widening | 04/07/2009 | 04/07/2009 | 12/31/2012 | 47717636.6 | 5.517
3205 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939012 | "The City of Portage will resurface 1.6 miles of E. Centre Avenue from Portage Road to Westnedge Avenue in the Kalamazoo urbanized area. This will improve the driving quality by making the road smooth | Pavement Improvement | 06/22/2009 | 07/08/2009 | 07/27/2011 | 900000 | 1.612
3206 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939013 | "The City of Portage will resurface 0.75 miles of E. Kilgore Road from Westnedge Avenue to Grand Elk RR in the Kalamazoo urbanized area. This will improve the driving quality by making the road smooth | Pavement Improvement | 06/30/2009 | 07/20/2009 | 07/27/2011 | 647541.67 | 0.743
3207 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939015 | The Kalamazoo County Road Commisssion will resurface 2.6 miles of S Avenue from Sprinkle Road to 29th Street, in the Kalamazoo urbanized area. This will improve the driving quality by making the road | Pavement Improvement | 07/31/2009 | 08/24/2009 | 07/27/2011 | 940577.28 | 2.579
3208 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939016 | The Kalamazoo County Road Commisssion will resurface 1 mile of S. 8th Street from R Avenue to Q Avenue, in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoot | Pavement Improvement | 08/03/2009 | 08/24/2009 | 07/27/2011 | 336849.85 | 1.001
3209 | Michigan | KALAMAZOO |  | 6 | 0939017 | The Kalamazoo County Road Commisssion will resurface 1 mile of N. 12th Street from D Avenue to C Avenue, in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoo | Pavement Improvement | 08/03/2009 | 08/24/2009 | 07/27/2011 | 395590.35 | 1.005
3210 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939022 | "The City of Kalamazoo will resurface 1.15 miles of E. Cork Street from Westnedge Avenue to Lovers Lane in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/10/2009 | 09/21/2009 |  | 493397.75 | 1.151
3211 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939023 | "The City of Kalamazoo will resurface 0.6 miles of Reed Street from Burdick Avenue to Portage Avenue in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/10/2009 | 09/21/2009 |  | 194445.25 | 0.606
3212 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939024 | "The City of Kalamazoo will resurface 0.4 miles of S. Burdick Street from Cork Street to Crescent in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/10/2009 | 09/21/2009 |  | 179661.5 | 0.434
3213 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939025 | "The City of Kalamazoo will resurface 1.1 miles of Lovers Lane from Cork Street to Kilgore Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/10/2009 | 09/21/2009 |  | 254334.05 | 1.073
3214 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939026 | "The City of Kalamazoo will resurface 0.25 miles of N. Edwards Street from South Street to Kalamazoo Avenue in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/15/2009 | 09/22/2009 | 05/14/2010 | 330192.5 | 0.252
3215 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939032 | "The village of Schoolcraft will resurface 1 mile of E. Eliza Street from west village limits to 14th Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 10/20/2009 | 10/21/2009 | 06/18/2010 | 222339.04 | 0.987
3216 | Michigan | KALKASKA |  | 1,4 | 0940007 | The Kalkaska County Road Commission will resurface 5 miles of County Highway 612 from the east county line to Blue Lake Rd and Darke to Rogers Rd . This will improve the driving quality by making the | Pavement Improvement | 12/18/2009 |  | 06/11/2010 | 321701.47 | 4.687
3217 | Michigan | KENT | GRAND RAPIDS | 3 | 0941141 | The City of Wyoming will resurface one mile of Prairie Parkway from Byron Center to Burlingame Avenue in the City of Wyoming. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/13/2009 | 07/13/2009 | 09/30/2009 | 461140.4 | 1
3218 | Michigan | KENT | GRAND RAPIDS | 3 | 0941142 | The City of Wyoming will resurface two miles of Burlingame Avenue from 52 Street to 36th Street in the City of Wyoming. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/13/2009 | 07/13/2009 | 09/30/2009 | 942724.91 | 2.03
3219 | Michigan | KENT | GRAND RAPIDS | 3 | 0941143 | The City of Walker will resurface a half mile of Veteran's Memorial Drive from Riverbend to Maynard Avenue in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/02/2009 | 07/06/2009 | 08/31/2009 | 107983.75 | 0.499
3220 | Michigan | KENT | GRAND RAPIDS | 3 | 0941144 | The City of Walker will resurface 0.1 of a mile of Three Mile Road from Alpine Avenue to the I-196 exit ramp in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/29/2009 | 07/15/2009 | 08/31/2009 | 269634.14 | 0.13
3221 | Michigan | KENT | GRAND RAPIDS | 3 | 0941146 | The Kent County Road Commission will resurface two and three quarters of a mile of 5 Mile Road from Gavin Lake Road to Lincoln Lake Road in Kent County. This will improve the driving quality by makin | Pavement Improvement | 08/14/2009 | 09/14/2009 | 09/25/2009 | 677238.8 | 2.745
3222 | Michigan | KENT | GRAND RAPIDS | 3 | 0941147 | The MDOT will make repairs to the bridges at US-131and Pine Island Drive, Post Road, and 10 Mile Rd to make the bridges last longer. | Bridge Improvement | 04/23/2009 | 04/23/2009 | 12/31/2010 | 1740843.93 | 0
3223 | Michigan | KENT | GRAND RAPIDS | 2 | 0941149 | The City of Grand Rapids will resurface a half mile of Leonard Street from Nixon Street to Collingsdale Avenue in the City of Walker. This will improve the driving quality by making the road smoother | Pavement Improvement | 06/30/2009 | 07/13/2009 | 06/15/2011 | 1292485 | 0.52
3224 | Michigan | KENT | GRAND RAPIDS | 3 | 0941150 | The City of Grandville will resurface 0.2 of a mile of Potomac Avenue from 44th Street to Century Center in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/22/2009 | 09/14/2009 | 09/30/2009 | 74825 | 0.224
3225 | Michigan | KENT | GRAND RAPIDS | 2,3 | 0941151 | The City of Grandville will resurface 0.2 of a mile of Kenowa Avenue from the south City limits to Stonehenge Drive in the City of Grandville. This will improve the driving quality by making the road | Pavement Improvement | 07/22/2009 | 09/14/2009 | 09/30/2009 | 76696 | 0.17
3226 | Michigan | KENT | GRAND RAPIDS | 3 | 0941152 | The City of Grandville will resurface 0.4 of a mile of 44th Street from Potomac Avenue to Rivertown Parkway in the City of Grandville. This will improve the driving quality by making the road smoothe | Pavement Improvement | 07/22/2009 | 09/14/2009 | 09/30/2009 | 79502 | 0.373
3227 | Michigan | KENT | GRAND RAPIDS | 3 | 0941153 | The City of Grandville will resurface 0.1 of a mile of 44th Street from Kenowa Avenue to the I-196 ramp in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/22/2009 | 09/14/2009 | 09/30/2009 | 79502 | 0.114
3228 | Michigan | KENT | GRAND RAPIDS | 3 | 0941156 | The City of East Grand Rapids will resurface a 0.3 miles of Lake Drive from the west city limits to Plymouth Road in the City of East Grand Rapids. This will improve the driving quality by making t | Pavement Improvement | 07/30/2009 | 08/03/2009 | 10/31/2009 | 332036 | 0.33
3229 | Michigan | KENT | GRAND RAPIDS | 3 | 0941158 | The Kent County Road Commission will resurface over 1.5 miles of Patterson Avenue from 44th Street to M-37 in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/11/2009 | 08/13/2009 | 05/15/2010 | 1100000 | 1.596
3230 | Michigan | KENT | GRAND RAPIDS | 3 | 0941159 | The Kent County Road Commission will resurface two and half miles of 84th Street from Cherry Valley Avenue to Whitneyville Avenue in Kent County. This will improve the driving quality by making the r | Pavement Improvement | 07/17/2009 | 08/04/2009 | 10/31/2009 | 670308 | 2.508
3231 | Michigan | KENT | GRAND RAPIDS | 3 | 0941162 | The City of East Grand Rapids will resurface a quarter of a mile of Breton Avenue from the norht city limits to Burton Street in East Grand Rapids. This will improve the driving quality by making the | Pavement Improvement | 08/03/2009 | 08/10/2009 | 06/11/2010 | 300000 | 0.251
3232 | Michigan | KENT | GRAND RAPIDS | 3 | 0941166 | The MDOT will make repairs to the bridge at M-57 over the White Pine Trail north of Grand Rapids to make the bridge last longer. | Bridge Improvement | 05/28/2009 | 05/28/2009 | 05/31/2010 | 532283.83 | 0
3233 | Michigan | KENT |  | 2,3 | 0941172 | The MDOT is deploying ITS technology on M-6 at I-196, I-96 and at M-11 and M-6 in Kent County, Grand Rapids area to improve mobility and reduce congestion | Safety/Traffic Management | 06/15/2009 | 06/15/2009 | 01/01/2011 | 823158.18 | 46.718
3234 | Michigan | KENT | GRAND RAPIDS | 3 | 0941176 | The MDOT is integrating ITS technoligies on US-131, I-96 and I-196 at 31 locations around Kent County in the Grand Rapids area to improve mobility and reduce congestion. | Safety/Traffic Management | 06/23/2009 | 06/23/2009 | 04/15/2011 | 280000 | 0
3235 | Michigan | KENT |  | 3 | 0941177 | The MDOT will make repairs to the bridge at M-11 over the Grand River in the City of Walker to make the bridge last longer. | Bridge Improvement | 06/23/2009 | 06/23/2009 | 12/31/2010 | 811284.65 | 0
3236 | Michigan | KENT | GRAND RAPIDS | 3 | 0941179 | The City of Grand Rapids will beautify Madison Avenue and Hall Street in the vicinity of Adams St and in the vicinity of Jefferson Ave by building this streetscape. | Pavement Improvement | 10/15/2009 |  | 09/30/2012 | 744772.43 | 1.373
3237 | Michigan | KENT | GRAND RAPIDS | 3 | 0941187 | The MDOT will widen almost 4 miles of I-196 freeway from the Grand River East to Fuller Avenue in the Grand Rapids area to improve mobility and reduce congestion | Pavement Widening | 08/18/2009 | 08/18/2009 | 06/01/2011 | 33341155.4 | 7.374
3238 | Michigan | KENT | GRAND RAPIDS | 3 | 0941188 | The MDOT will replace 2 miles of I-196 freeway lighting from the Grand River East to Fuller Avenue in the Grand Rapids area to improve driver visibility. | Pavement Improvement | 08/18/2009 | 08/18/2009 | 06/01/2011 | 650996.74 | 3.876
3239 | Michigan | KENT | GRAND RAPIDS | 3 | 0941189 | The MDOT will replace the I-196 bridges over Lafayette Avenue in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 09/30/2009 | 10/03/2009 | 06/01/2011 | 2587985.19 | 0
3240 | Michigan | KENT | GRAND RAPIDS | 3 | 0941190 | The MDOT will replace the Coit Avenue bridge over I-196 in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 08/18/2009 | 08/18/2009 | 06/01/2011 | 2508509.56 | 0
3241 | Michigan | KENT | GRAND RAPIDS | 3 | 0941206 | The Kent County Road Commission will resurface one and a half miles of Leonard Street from M-44 to Crahen Street in Grand Rapids Township. This will improve the driving quality by making the road smo | Pavement Improvement | 01/14/2010 |  | 07/30/2010 | 484620 | 1.494
3242 | Michigan | KENT | GRAND RAPIDS | 3 | 0941211 | The City of Grand Rapids will resurface 0.2 miles of Lake Drive from Cherry Street to Fuller Avenue in the City of Grand Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/21/2009 | 04/19/2010 | 05/17/2010 | 230000 | 0.212
3243 | Michigan | KEWEENAW |  | 1 | 0942131 | This pavement project on Eagle Harbor Road in Keweenaw County will improve the drive quality and make the road smoother. | Other | 01/14/2010 |  | 07/01/2010 | 164462 | 3.51
3244 | Michigan | LAKE |  | 2 | 0943229 | The Lake County Road Commission will resurface 5 miles of South Hawkins Rd from US-10 south in the vicinity of Reed City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/02/2009 | 08/03/2009 | 08/27/2009 | 91940 | 4.987
3245 | Michigan | LAKE |  | 2 | 0943230 | The Lake County Road Commission will resurface 6 miles of W Star Lake Drive around Star Lake in the Manistee National Forest southwest of the village of Baldwin. This will improve the driving qualit | Pavement Improvement | 06/02/2009 | 08/03/2009 | 08/27/2009 | 93367 | 6.047
3246 | Michigan | LAKE |  | 2 | 0943231 | The Lake County Road Commission will resurface 5 miles of E 92nd St and S BroadwayRd from S Forman to 96th and from 72nd to 92nd St in the Manistee National Forest. This will improve the driving qua | Pavement Improvement | 06/02/2009 | 08/03/2009 | 08/27/2009 | 89005 | 4.797
3247 | Michigan | LAKE |  | 2 | 0943232 | The Lake County Road Commission will resurface 4 miles of West 52nd St from the Baldwin Village limits westward. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/04/2009 | 08/03/2009 | 08/27/2009 | 73501 | 3.629
3248 | Michigan | LAPEER |  | 10 | 0944088 | In the city of Fenton, MDOT is resurfacing existing car pool lots at the US-23 exit to Silver Lake Road, on M-24 north of Barnes Lake Road, on M-90 between Brush Street and Baldwin Avenue, and on M-24 | Pavement Improvement | 04/17/2009 | 04/17/2009 | 12/31/2010 | 61231.5 | 0
3249 | Michigan | LAPEER |  | 10 | 0944089 | Within the City of North Branch, MDOT will resurface parking lot on M-90 to improve the quality of the parking surface and extend the life of the road pavement. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 12/31/2010 | 24376.25 | 0
3250 | Michigan | LEELANAU |  | 4 | 0945329 | MDOT will resurface 16.5 miles of M-72 from the Village of Empire to Bugai Rd. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/09/2009 | 06/09/2009 | 05/05/2011 | 963795.38 | 16.401
3251 | Michigan | LEELANAU |  | 4 | 0945330 | The MDOT will construct a passing relief lane on M-72 from Cedar Run Rd to Goodrick Rd west of Traverse City. This will allow safer driving operations on M-72. | Pavement Widening | 06/30/2009 | 06/30/2009 | 07/09/2010 | 1735082.92 | 1.124
3252 | Michigan | LEELANAU |  | 4 | 0945332 | The Leelanau County Road Commission will resurface 1.5 miles of County Road 651 from Hohnke Rd to M-22 in the vicinity of Empire. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/18/2009 | 08/18/2009 | 11/12/2009 | 271725 | 1.585
3253 | Michigan | LIVINGSTON |  | 8 | 0947010 | 8.3 miles of resurfacng of US-23 from I-96 to M-59 just north of Brighton in Livingston County. This project will provide for improved rideability and increased pavement smoothness. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 02/09/2010 | 3334687.48 | 16.563
3254 | Michigan | LIVINGSTON |  | 8 | 0947011 | A new Carpool lot will be constructed at Burkhart Road just west of M-59 near the I-96 Interchange west of Howell. This lot will encourage ridesharing and reduce the number of cars on the roadway. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/30/2009 | 150716.91 | 0.02
3255 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947012 | MDOT will improve mobility and reduce congestion with installation of an Intelligent Transportation System (ITS) along I-96 from the city of Fowlerville easterly to the Oakland/Livingston County line | Safety/Traffic Management | 06/15/2009 | 06/15/2009 | 12/31/2010 | 533441.41 | 69.774
3256 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947015 | This project will provide for 1.5 miles of pavement resurfacing on East Grand River Avenue from Lake Chemung to 1/3 of a mile east of Hughes Road between the cities of Howell and Brighton in Livingsto | Pavement Improvement | 09/18/2009 | 09/22/2009 | 06/30/2010 | 1199887.3 | 1.517
3257 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947016 | This project will provide for 0.40 miles of pavement resurfacing on Main Street from Third Avenue to Grand River Avenue in the city of Brighton, Livingston County. This will provide for improved pave | Pavement Improvement | 09/21/2009 | 10/13/2009 |  | 254732.5 | 0.402
3258 | Michigan | LIVINGSTON |  | 8 | 0947018 | This project will provide for 2 miles of pavement resurfacing on Old US-23 from Dean Road to Faussett, north of the city of Brighton in Livingston County. This will provide for improved pavement ride | Pavement Improvement | 01/14/2010 |  |  | 442597.03 | 2.056
3259 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947020 | This project will provide for 1.1 miles of pavement resurfacing on North Michigan Avenue from Grand River Avenue to M-59 in the city of Howell, Livingston County. This will provide for improved pavem | Pavement Improvement | 10/07/2009 | 10/16/2009 | 11/14/2009 | 310163.14 | 1.104
3260 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947021 | 1/3 of a mile of Walnut Street is being resurfaced from Maple Street to Clinton Street in the City of Howell, Livingston County to make the roadway smoother and improve ride quality. | Pavement Improvement | 10/07/2009 | 10/16/2009 | 11/14/2009 | 106000 | 0.349
3261 | Michigan | MACKINAC |  | 1 | 0949011 | This pavement and Rumble Strip project on US-2 in Mackinac County will improve safety and make the road smoother. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/18/2010 | 2864178.64 | 6.012
3262 | Michigan | MACOMB | DETROIT,MI | 12 | 0950035 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of 12 Mile Road in Macomb County. | Pavement Improvement | 07/27/2009 | 08/03/2009 | 09/30/2009 | 550876.16 | 0.465
3263 | Michigan | MACOMB |  | 10,12 | 0950036 | Resurfacing to maintain the pavement condition and improve ride quality of ramps at I-94 at 9 Mile Road, 10 Mile Road, and 23 Mile Road, and on M-19 in the city of St. Clair Shores by MDOT. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 04/01/2011 | 504815.48 | 0.897
3264 | Michigan | MACOMB | DETROIT,MI | 12 | 0950037 | Resurfacing to maintain the pavement condition and improve ride quality of Ten Mile Road in Eastpointe. | Pavement Improvement | 08/04/2009 | 08/15/2009 | 11/30/2009 | 414092.55 | 0.505
3265 | Michigan | MACOMB | DETROIT,MI | 12 | 0950038 | One mile of resurfacing to maintain the pavement condition and improve ride quality of 10 Mile Road in East Pointe and Center Line. | Pavement Improvement | 08/04/2009 | 08/15/2009 | 11/30/2009 | 506882.52 | 0.839
3266 | Michigan | MACOMB |  | 10 | 0950040 | Resurfacing to maintain the pavement condition and improve ride quality of M-19 near Richmond by MDOT. | Pavement Improvement | 05/29/2009 | 05/29/2009 | 04/01/2011 | 2155133.96 | 4.112
3267 | Michigan | MACOMB |  | 10 | 0950041 | Three miles of microsurfacing to preserve the pavement condition and improve ride quality of North Avenue and 26 Mile Road in Macomb County. | Pavement Improvement | 09/08/2009 | 09/16/2009 | 10/30/2009 | 293571.55 | 2.954
3268 | Michigan | MACOMB | DETROIT,MI | 12 | 0950045 | 2 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along 15 Mile Road in Sterling Heights by MDOT. | Pavement Improvement | 09/10/2009 | 09/14/2009 | 06/30/2010 | 2089235.2 | 2.226
3269 | Michigan | MACOMB | DETROIT,MI | 12 | 0950046 | Two and a half miles of resurfacing to maintain the pavement condition and improve ride quality of M-3 in Mount Clemens by MDOT. | Pavement Improvement | 07/09/2009 | 07/09/2009 | 04/01/2011 | 4171721.24 | 1.705
3270 | Michigan | MACOMB | DETROIT,MI | 10 | 0950051 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Schoenherr Road in Macomb County. | Pavement Improvement | 10/06/2009 | 10/14/2009 | 11/01/2009 | 282091.8 | 1.002
3271 | Michigan | MACOMB | DETROIT,MI | 10 | 0950058 | 2 mile application of a preventive maintenace treatment to improve safety, smoothness, and extend the service life of the existing pavement on Washington Street in New Baltimore by MDOT. | Pavement Improvement | 12/23/2009 |  | 05/28/2010 | 300000 | 2.094
3272 | Michigan | MACOMB | DETROIT,MI | 12 | 0950059 | 2 miles of resurfacing to maintain the pavement condition and improve ride quality of 14 Mile Road in Sterling Heights. | Pavement Improvement | 02/02/2010 |  | 07/31/2010 | 1650000 | 0.94
3273 | Michigan | MACOMB | DETROIT,MI | 12 | 0950060 | Resurfacing to maintain the pavement condition and improve ride quality of 14 Mile Road in Clinton. | Pavement Improvement | 02/02/2010 |  | 07/31/2010 | 1283000 | 1.37
3274 | Michigan | MANISTEE |  | 2 | 0951308 | The Mainistee County Road Commission will resurface 4 miles of Stronach Rd from M-55 to Eastlake Rd in the vicinity of the Village of Eastlake in the Manistee National Forest. This will improve the d | Pavement Improvement | 09/17/2009 | 09/26/2009 | 11/01/2009 | 362028 | 3.564
3275 | Michigan | MANISTEE |  | 2 | 0951309 | The Mainistee County Road Commission will resurface 1 miles of Stronach Rd from US-31 to Grant south of the the City of Manistee. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/17/2009 | 09/26/2009 | 11/01/2009 | 80000 | 0.927
3276 | Michigan | MARQUETTE |  | 1 | 0952006 | This pavement project on US-41 in the City of Marquette will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 |  | 511516.27 | 2.056
3277 | Michigan | MARQUETTE |  | 1 | 0952007 | This pavement resurfacing and rumble strip project on US-41 in the City of Marquette will improve safety and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/18/2010 | 475088.11 | 1.93
3278 | Michigan | MARQUETTE |  | 1 | 0952009 | This roundabout project in Marquette County at the intersection of US-41/M-28 and Front Street will improve safety. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 10/18/2010 | 3203931.09 | 4.224
3279 | Michigan | MARQUETTE |  | 1 | 0952014 | This paving project on County Road 557 in Marquette County will improve the drive quality and make the road smoother. | Pavement Improvement | 09/28/2009 |  | 08/01/2010 | 652694.59 | 2.207
3280 | Michigan | MARQUETTE |  | 1 | 0952016 | This pavement project on Champion Street in the City of Marquette will improve the drive quality and make the road smoother. | Pavement Improvement | 08/28/2009 | 09/08/2009 | 08/15/2010 | 465000 | 0.36
3281 | Michigan | MARQUETTE |  | 1 | 0952020 | This pavement project on M-94 in Marquette County will improve the drive quality and make the road smoother. | Pavement Improvement | 08/04/2009 | 08/04/2009 |  | 730059.32 | 9.499
3282 | Michigan | MARQUETTE |  | 1 | 0952025 | This pavement project on M-28 BR in the City of Ishpeming will improve the drive quality and make the road smoother. | Pavement Improvement | 10/21/2009 |  |  | 440452.63 | 3.901
3283 | Michigan | MASON |  | 2 | 0953021 | MDOT will resurface 0.5 miles of US-10 at Dowland St in the vicinity of the Lake Michigan Car Ferry in Ludington. This will improve the driving quality by making the road smoother and provide better | Pavement Improvement | 06/04/2009 | 06/04/2009 | 05/05/2011 | 369730.05 | 0.47
3284 | Michigan | MASON |  | 2 | 0953024 | The City of Ludington will design improvements to 0.2 miles of South Williams St from Ludington Ave to Filer St in Ludington so as to improve the driving quality by making the road smoother. | Other | 08/18/2009 | 08/25/2009 | 05/28/2010 | 13748 | 0.144
3285 | Michigan | MECOSTA |  | 4 | 0954007 | The MDOT will resurface 2 miles of US-131BR/M-20 from US-131 east to Northland Drive near the City of Big Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 03/30/2010 | 447566.36 | 3.63
3286 | Michigan | MECOSTA |  | 4 | 0954008 | The MDOT will resurface 2 miles of US-131BR/M-20 from US-131 east to Northland Drive near the City of Big Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 03/30/2010 | 810114.61 | 4.356
3287 | Michigan | MECOSTA |  | 4 | 0954009 | The MDOT will make repairs to the bridge at Old State Road over US-131 near the Village of Stanwood to make the bridge last longer. | Bridge Improvement | 05/21/2009 | 05/21/2009 | 12/31/2010 | 658109.48 | 0
3288 | Michigan | MECOSTA |  | 4 | 0954010 | The Mecosta County Road Commission will resurface 20 Mile Road from 60th Ave to 50th Ave west of the Village of Barryton. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/24/2009 | 10/01/2009 | 11/14/2009 | 87420.72 | 1.008
3289 | Michigan | MECOSTA |  | 4 | 0954011 | Improvements will be made to guard rail on Arthur Road from 10th Avenue to Costabella Road west of the Village of Lake Isabella to improve safety. | Pavement Improvement | 06/24/2009 | 10/01/2009 | 11/14/2009 | 122015 | 1.002
3290 | Michigan | MECOSTA |  | 4 | 0954012 | The Mecosta County Road Commission will resurface Pierce Road from front St to 110th Ave in the village of Stanwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/24/2009 | 10/01/2009 | 11/14/2009 | 233284 | 7.336
3291 | Michigan | MIDLAND |  | 1,4,5 | 0956007 | Within the cities of Midland, Auburn and Bay, MDOT will be upgrading 16 bridge decks on US-10 from Sturgeon Road easterly to I-75 and on M-20/US-10BR from Saginaw Road easterly to Waldo Road to make t | Bridge Improvement | 05/29/2009 | 05/29/2009 | 12/31/2009 | 277823.6 | 0
3292 | Michigan | MIDLAND |  | 4 | 0956009 | The city of Midland will resurface 2.8 miles on Gordonville Road to improve the driving quality by making the road smoother. | Pavement Improvement | 07/24/2009 | 07/24/2009 | 10/30/2009 | 470000 | 9.392
3293 | Michigan | MIDLAND |  | 4 | 0956010 | In the city of Midland there is 17.20 miles of resurfacing on Smith Crossing Road, Freeland Road, Pine River Road, Nine Mile Road, Shepherd Road, Gordonville Road, Jefferson Road, Prairie Road, Eastma | Pavement Improvement | 07/30/2009 | 07/30/2009 | 10/30/2009 | 441633 | 8.757
3294 | Michigan | MIDLAND |  | 4 | 0956011 | The city of Midland will resurface 4.16 miles on M-20 from west of Meridian Road easterly to east of Vance Road to improve the driving quality by making the road smoother. | Pavement Improvement | 09/29/2009 | 09/29/2009 | 07/15/2010 | 1843233.58 | 4.015
3295 | Michigan | MISSAUKEE |  | 4 | 0957004 | The Missaukee Couth Road Commission willl resurface 5.5 miles of Falmouth/Hildebrand/Cadilac/Lucas Rds between M-66 and Dikerson Rd in the vicinity of Cadilac. This will improve the driving quality b | Pavement Improvement | 10/12/2009 | 10/19/2009 | 06/12/2010 | 281023.5 | 5.53
3296 | Michigan | MONROE | MONROE | 15 | 0958011 | 0.39 miles of pavement resurfacing on West 7th Street from Telegraph Road to Union Street in the city of Monroe, Monroe County. This project will improve pavement rideability and increase pavement sm | Pavement Improvement | 09/17/2009 | 10/05/2009 | 11/01/2009 | 162059.8 | 0.39
3297 | Michigan | MONROE | MONROE | 15 | 0958012 | 0.17 miles of pavement resurfacing on Riverview Avenue from Scottwood Street to Maywood Street in the city of Monroe, Monroe County. This project will improve pavement rideability and increase paveme | Pavement Improvement | 09/15/2009 | 09/28/2009 | 11/15/2009 | 186685 | 0.173
3298 | Michigan | MONTCALM |  | 4 | 0959004 | The MDOT will resurface seven and a half miles of M-91 from north of Colby Rd to north of Kedalville Rd near the village of Lakeview. This will improve the driving quality by making the road smoothe | Pavement Improvement | 06/22/2009 | 04/02/2009 | 11/14/2009 | 406541.43 | 7.455
3299 | Michigan | MONTCALM |  | 4 | 0959008 | The Moncalm County Road Commission will resurface South Youngman Rd from M-57 to Harlow Rd east of Greenville. This will improve the driving quality by making the road smoother. | Pavement Widening | 08/12/2009 | 08/13/2009 | 09/18/2009 | 94878.93 | 0.757
3300 | Michigan | MONTCALM |  | 4 | 0959009 | The MDOT will resurface seven miles of M-57 from Berridge Rd to east of M-66 near the City of Greenville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/26/2009 | 07/01/2009 | 03/30/2010 | 875679.55 | 7.053
3301 | Michigan | MONTCALM |  | 4 | 0959010 | The MDOT will resurface six miles of M-46 from US-131 to west of Amble Rd near the village of Lakeview. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/04/2009 | 06/04/2009 | 03/30/2010 | 746003.4 | 5.945
3302 | Michigan | MONTCALM |  | 4 | 0959011 | The Montcalm County Road Commission will resurface South Vickeryville Rd from Stanton Rd to Sidney Rd. near the village of Stanton. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/17/2009 | 09/22/2009 | 10/30/2009 | 471986 | 2.689
3303 | Michigan | MUSKEGON |  | 2 | 0961134 | The MDOT will make repairs to the bridge at Fruitport Rd over I-96 and the bridge at Russell Rd over US-31in Muskegon County to make the bridges last longer. | Bridge Improvement | 05/14/2009 | 05/14/2009 | 09/21/2011 | 1361153.66 | 0
3304 | Michigan | MUSKEGON |  | 2 | 0961135 | The MDOT will build a roundabout at M-37 and M-46 intersection and resurface M-37 from M-46 to Moon Rd for 2 miles west of the village of Casanovia to improve safety and road smoothness. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 06/01/2012 | 3278891.18 | 2.025
3305 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961138 | The City of Muskegon will resurface a half mile of Laketon Ave from Peck St to Wood St. This will improve driving quality by making the road smoother. | Pavement Improvement | 07/27/2009 | 08/18/2009 | 11/15/2009 | 800000 | 0.504
3306 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961139 | The City of Whitehall will resurface 3 tenths of a mile of Mears Ave from Lincoln Rd to Misco Drive. This will improve driving quality by making the road smoother. Needed utility work will also be d | Pavement Improvement | 09/03/2009 | 09/08/2009 | 10/16/2009 | 200000 | 0.285
3307 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961140 | The City of Montague will resurface a block of Old Channel Trail from Dowling St to Church St. This will improve driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 09/02/2009 | 09/30/2009 | 38051.1 | 0.073
3308 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961141 | The City of Montegue will resurface a one tenth of a mile of Dowling St from Meade St to Ferry St. This will improve driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 09/02/2009 | 09/30/2009 | 50000 | 0.111
3309 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961142 | The City of Muskegon will resurface 0.4 mile of Summit Ave from west of Henry St to Coolidge Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 08/31/2009 | 09/08/2009 | 09/30/2009 | 190000 | 0.355
3310 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961143 | The City of Norton Shores will resurface 0.8 miles of Pontaluna Rd Grand Haven Rd to Wood Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 08/25/2009 | 09/08/2009 | 11/15/2009 | 503211 | 0.769
3311 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963182 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Crooks Road in Oakland County. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 11/15/2009 | 802000 | 1.145
3312 | Michigan | OAKLAND | DETROIT,MI | 9,12 | 0963183 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Campbell Road in Madison Heights and Royal Oak. | Pavement Improvement | 05/14/2009 | 07/27/2009 | 11/29/2009 | 1153712.67 | 0.99
3313 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963184 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Orchard Lake Road in Oakland County. | Pavement Improvement | 07/31/2009 | 08/18/2009 | 10/23/2009 | 415000 | 1.012
3314 | Michigan | OAKLAND |  | 9 | 0963185 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Square Lake Road in Bloomfield Township by MDOT. | Pavement Improvement | 05/15/2009 | 05/15/2009 | 05/05/2011 | 5416538.52 | 2.563
3315 | Michigan | OAKLAND | DETROIT,MI | 12 | 0963196 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of 10 Mile Road in Oakland County. | Pavement Improvement | 08/10/2009 | 08/13/2009 | 10/09/2009 | 512000 | 0.536
3316 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963197 | Resurfacing to maintain the pavement condition and improve ride quality of Rochester Road in Clawson. | Pavement Improvement | 07/31/2009 | 08/17/2009 | 10/02/2009 | 350000 | 0.51
3317 | Michigan | OAKLAND | DETROIT,MI | 9,10 | 0963199 | 5.6 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along M-59 in Rochester Hills by MDOT. | Pavement Widening | 06/02/2009 | 06/02/2009 | 09/19/2012 | 55894785.43 | 11.892
3318 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963208 | 2 miles of resurfacing to maintain the pavement condition and improve ride quality of M-59 in Pontiac. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 06/30/2012 | 10119010.1 | 6.259
3319 | Michigan | OAKLAND | DETROIT,MI | 12 | 0963209 | Resurfacing to maintain the pavement condition and improve ride quality of East Progress Drive in Madison Heights by MDOT. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 12/15/2010 | 468941.98 | 0.832
3320 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963211 | Two miles of resurfacing to maintain the pavement condition and improve ride quality of Orchard Lake Road in Oakland County. | Pavement Improvement | 09/03/2009 | 09/08/2009 | 06/15/2010 | 1749000 | 2.095
3321 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963212 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Crooks Road in Oakland County. | Pavement Improvement | 08/28/2009 | 09/10/2009 | 06/15/2010 | 879000 | 1.235
3322 | Michigan | OAKLAND | DETROIT,MI | 11 | 0963215 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Novi Road in Novi. | Pavement Improvement | 09/10/2009 | 09/16/2009 | 11/02/2009 | 827000 | 1.004
3323 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963220 | 2 miles of concrete pavement repairs to maintain the pavement condition and improve ride quality of Halsted Road in Farmington Hills. | Pavement Improvement | 07/22/2009 | 07/22/2009 | 05/31/2010 | 1199136.89 | 1.622
3324 | Michigan | OAKLAND | DETROIT,MI | 11 | 0963224 | Resurfacing to maintain the pavement condition and improve ride quality of Nine Mile Road in Novi. | Pavement Improvement | 09/24/2009 | 10/03/2009 | 06/15/2010 | 328000 | 1.026
3325 | Michigan | OAKLAND | DETROIT,MI | 11 | 0963225 | Three miles of resurfacing to maintain the pavement condition and improve ride quality of Meadowbrook Road in Novi. | Pavement Improvement | 09/24/2009 | 10/03/2009 | 06/15/2010 | 340000 | 1
3326 | Michigan | OAKLAND | DETROIT,MI | 9,11 | 0963226 | Resurfacing to maintain the pavement condition and improve ride quality of Nine Mile Road in Novi. | Pavement Improvement | 09/24/2009 | 10/03/2009 | 06/15/2010 | 340000 | 1.038
3327 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963239 | Bridge replacement to improve safety and maintain mobility of Opdyke Road over M-59 in Pontiac by MDOT. | Bridge Improvement | 08/18/2009 | 08/18/2009 | 12/31/2010 | 2807747.16 | 0
3328 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963240 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Cass Avenue in Pontiac by MDOT. | Pavement Improvement | 08/18/2009 | 08/18/2009 | 03/01/2011 | 1832013.03 | 1.183
3329 | Michigan | OAKLAND | DETROIT,MI | 9,12 | 0963264 | One mile of resurfacing to maintain the pavement condition and improve ride quality of John R Road in Troy. | Pavement Improvement | 02/04/2010 |  | 07/02/2010 | 837000 | 1.028
3330 | Michigan | OCEANA |  | 2 | 0964332 | The MDOT will make repairs to the bridge at Taylor Rd over US-131 in Oceana County to make the bridge last longer. | Bridge Improvement | 05/29/2009 | 05/29/2009 | 03/31/2011 | 679727.94 | 0
3331 | Michigan | OGEMAW |  | 1 | 0965009 | MDOT will repair 10.6 miles of I-75 from the south Ogemaw County line to Cook Rd and from Ski Park Rd to the north county linein Ogemaw County to extend the service life of the existing roadway. | Pavement Improvement | 12/30/2008 | 12/30/2008 | 06/18/2009 | 906117.53 | 11.057
3332 | Michigan | OGEMAW |  | 1 | 0965010 | MDOT will design repairs to drainage culverts along I-75 in Ogemaw County to improve drainage and extend the life of the roadway drainage structures. | Other | 04/23/2009 | 04/23/2009 |  | 47297 | 10.034
3333 | Michigan | OGEMAW |  | 1 | 0965011 | MDOT will fix drainage culverts along I-75 in Ogemaw County to improve drainage and extend the life of the roadway drainage structures. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 06/01/2010 | 1105824.92 | 10.034
3334 | Michigan | ONTONAGON |  | 1 | 0966008 | This paving project on M-64 from Silver City to The City of Ontonagon will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/18/2010 | 2842828.15 | 11.84
3335 | Michigan | OSCEOLA |  | 4 | 0967010 | MDOT will design the resurfacing of 2 miles of US-10 from the west county line of Osceola to the US-131 interchange in the vicinity of Reed City. This will improve the driving quality by making the | Other | 04/29/2009 | 04/29/2009 |  | 65000 | 1.89
3336 | Michigan | OSCEOLA |  | 4 | 0967011 | MDOT will resurface 2 miles of US-10 from the west county line of Osceola to the US-131 interchange in the vicinity of Reed City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/15/2010 | 1255464.1 | 1.89
3337 | Michigan | OSCEOLA |  | 4 | 0967015 | The Osceola County Road Commission will resurface 4 and a quarter miles of 200th Ave from 20 Mile Rd to the county line in the vicinity of the village of Tustin. This will improve the driving quality | Other | 07/29/2009 | 10/27/2009 | 11/14/2009 | 146233 | 4.263
3338 | Michigan | OSCODA |  | 1 | 0968003 | The Oscoda County Road Commission will replace the bridge on Waterwheel Court over Big Creek to improve safety and increase mobility. | Bridge Replacement | 09/23/2009 | 05/01/2010 | 06/30/2010 | 87616.5 | 0.309
3339 | Michigan | OTSEGO |  | 1 | 0969014 | MDOT will resurface 5 miles of M-32 from east of Krys Rd to Turtle Lake Rd east of Gaylord. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 10/08/2009 | 393142.36 | 4.927
3340 | Michigan | OTSEGO |  | 1 | 0969016 | The Otsego County Road Commission will reconstruct 1.5 miles of Charles Brink Rd from E of Championship Dr to Opal Lake Rd in the vicinity of Otsego Lake. This will improve the driving quality by mak | Other | 09/18/2009 | 09/21/2009 | 11/13/2009 | 331098 | 1.565
3341 | Michigan | OTTAWA | HOLLAND | 2 | 0970019 | Almost 2 miles of Lakewood Blvd from River Ave to 120th Ave will be resurfaced in Holland Township. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/25/2009 | 07/01/2009 | 07/31/2009 | 615578.2 | 1.704
3342 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 0970020 | Five miles of 48th Ave will be resurfaced near the City of Hudsonville and in Georgetown Township from Chicago Drive to Bauer Rd. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/26/2009 | 07/01/2009 | 08/14/2009 | 1286988.26 | 4.672
3343 | Michigan | OTTAWA |  | 2 | 0970022 | The City of Holland will resurface almost 2 miles of Lakewood Blvd from River Ave to 120th Ave. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/26/2009 | 07/01/2009 | 08/14/2009 | 478595.04 | 1.965
3344 | Michigan | OTTAWA |  | 2 | 0970024 | The MDOT will make repairs to the I-196 bridges over 48th St near the City of Grandville to make the bridges last longer. | Bridge Improvement | 04/28/2009 | 04/28/2009 | 12/31/2010 | 618074.05 | 0
3345 | Michigan | OTTAWA |  | 2 | 0970026 | The MDOT will resurface 6 miles of I-96 from M-104 to 68th Ave in the vicinity of Spring Lake. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 06/30/2010 | 1597667.93 | 11.106
3346 | Michigan | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0970034 | The Ottawa County Road Commission will resurface 2 miles of Lake michigann Dr from Lakeshore Ave to US-31. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/23/2009 | 07/30/2009 | 09/11/2009 | 381161.25 | 1.96
3347 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 0970037 | The MDOT will resurface 1 mile of I-196 BL from US-31 east to the Macatawa River near the City of Holland. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/09/2009 | 06/09/2009 | 03/30/2010 | 376952.87 | 1.355
3348 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 0970038 | The MDOT will resurface 9 miles of I-196 from 64th Ave to Kenowa Ave near Hudsonville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/10/2009 | 06/10/2009 | 03/30/2010 | 2406902.54 | 13.499
3349 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 0970039 | The MDOT will resurface 11 miles of M-45 from US-31 east to 68th Ave near the city of Grand Haven. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/10/2009 | 06/10/2009 | 03/30/2010 | 1612262.97 | 11.095
3350 | Michigan | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0970040 | The City of Grand Haven will resurface three quarters of a mile of Robbins Rd from just east of US-31 to Beechtree St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/22/2009 | 09/25/2009 |  | 230691 | 0.721
3351 | Michigan | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0970041 | The City of Spring Lake will resurface 0. 2 miles of West Springlake Rd from Smith's Bridge to Bayberry Dr. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 09/08/2009 | 10/31/2009 | 200000 | 0.22
3352 | Michigan | OTTAWA |  | 2 | 0970044 | The MDOT will resurface a half mile of US-31 south bound from the Grand River bascule bridge to 3rd St including M-104 in the city of Ferrysburg. This will improve the driving quality by making the r | Pavement Improvement | 07/10/2009 | 07/10/2009 | 06/30/2010 | 294393.95 | 0.905
3353 | Michigan | ROSCOMMON |  | 1,4 | 0972006 | The MDOT is upgrading the guard rail along 17.5 miles of US-127 in Roscommon County from Snow Bowl Rd north to I-75 to improve safety. | Safety/Traffic Management | 04/02/2009 | 04/02/2009 | 07/10/2009 | 234887.87 | 30.285
3354 | Michigan | SAGINAW | SAGINAW | 4 | 0973027 | In the city of Saginaw, MDOT is making repairs on M-46 to make the bridge last longer. | Bridge Improvement | 05/11/2009 | 05/11/2009 | 12/31/2010 | 984609.01 | 0
3355 | Michigan | SAGINAW | SAGINAW | 5 | 0973028 | Within the city of Saginaw, MDOT will reconstruct 1.20 miles of M-13 to improve the driving quality by making the road smoother. | Pavement Improvement | 05/29/2009 | 05/29/2009 | 09/19/2012 | 5609565.18 | 1.258
3356 | Michigan | SAGINAW | SAGINAW | 5 | 0973030 | The City of Saginaw is resurfacing 1.48 miles on Outer Drive to improve driving quality by making the road smoother. | Pavement Improvement | 08/14/2009 | 08/17/2009 | 11/13/2009 | 1844073 | 1.484
3357 | Michigan | SAGINAW |  | 4 | 0973033 | The City of Chesaning is resurfacing 7 miles on S Hemlock Road to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 80000 | 10.75
3358 | Michigan | SAGINAW |  | 4 | 0973034 | The Saginaw County Road Commission is resurfacing 5.105 miles on Ditch Road south of Chesaning to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 80716.1 | 5.105
3359 | Michigan | SAGINAW |  | 4,5 | 0973035 | The City of Frankenmuth is resurfacing 5.03 miles on S Dehmel Road to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 80000 | 4.949
3360 | Michigan | SAGINAW |  | 4,5 | 0973036 | The City of Bridgeport is resurfacing 5.37 miles on Busch Rd & Moorish Rd to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 85000 | 5.348
3361 | Michigan | SAGINAW |  | 4 | 0973037 | The Saginaw County Road Commission is resurfacing 3.9 miles on Fergus Road from Sharon Rd to Bishop Rd near the Village of St. Charles to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 67368.88 | 3.943
3362 | Michigan | SAGINAW |  | 4 | 0973038 | In Tittabawassee Township there is 5 miles of resurfacing on Mackinaw Rd & Lawndale Rd to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 80000 | 4.996
3363 | Michigan | SAGINAW | SAGINAW | 5 | 0973041 | In the city of Saginaw there will be 0.98 miles reconstruction on East Genesee Avenue from Franklin Street to Janes Street to improve the driving quality and make the road smoother. | Pavement Improvement | 12/22/2009 |  | 09/18/2012 | 934074 | 0.427
3364 | Michigan | SAGINAW | SAGINAW | 5 | 0973042 | The city of Saginaw will beautify 0.45 miles along W Genesee Avenue. | Transportation Enhancements | 12/22/2009 |  | 09/18/2012 | 510000 | 0.427
3365 | Michigan | SAGINAW | SAGINAW | 5 | 0973051 | The city of Saginaw will reconstruct 0.51 miles on North Woodbridge Street from Houghton Avenue to Davenport Avenue to improve the driving quality by making the road smoother. | Other | 02/01/2010 |  | 10/23/2010 | 400000 | 0.555
3366 | Michigan | SAGINAW | SAGINAW | 4,5 | 0973053 | There is 15.39 miles of resurfacing on M-46 from Towerline Road easterly to west of M-15 and on M-84 from M-58 (State Street) northerly to north of Pierce Road to improve the driving quality by making | Pavement Improvement | 09/16/2009 | 09/16/2009 | 08/02/2010 | 3374881.08 | 15.434
3367 | Michigan | SANILAC |  | 10 | 0974004 | North of Port Sanilac, MDOT is upgrading 6.8 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 05/29/2009 | 05/29/2009 | 03/31/2010 | 402992.53 | 6.824
3368 | Michigan | SCHOOLCRAFT |  | 1 | 0975013 | This shoulder paving project on County Road 498 in Schoolcraft County will improve safety. | Pavement Improvement | 05/11/2009 | 07/27/2009 | 09/30/2009 | 91271 | 3.958
3369 | Michigan | SCHOOLCRAFT |  | 1 | 0975014 | This shoulder paving project on Thunder Lake Road in Schoolcraft County will improve safety. | Pavement Improvement | 05/11/2009 | 08/17/2009 | 11/15/2009 | 91680 | 10.314
3370 | Michigan | SCHOOLCRAFT |  | 1 | 0975016 | This shoulder paving project on County Road 436 in Schoolcraft County will improve safety. | Pavement Improvement | 09/01/2009 | 09/16/2009 | 09/30/2010 | 94000 | 2.998
3371 | Michigan | SHIAWASSEE |  | 8 | 0976208 | Near the city of Perry in Shiawausee county, MDOT will improve the driving surface of nearly 8 miles of I-96 with a resurfacing project. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 06/16/2011 | 3682328.68 | 15.748
3372 | Michigan | SHIAWASSEE |  | 4 | 0976211 | 0.2 of a mile of pavement resurfacing of East King Street from North Dewey Street to North Gould Street, in the city of Owosso, Shiawausee County. This project will improve pavement rideability and i | Pavement Improvement | 08/28/2009 | 10/02/2009 | 11/01/2009 | 100000 | 0.25
3373 | Michigan | SHIAWASSEE |  | 4 | 0976212 | 0.14 miles of pavement resurfacing of North Park Street from M-21 to Mason Street, in the city of Owosso, Shiawausee County. This project will improve pavement rideability and increase pavement smoot | Pavement Improvement | 08/28/2009 | 10/02/2009 | 11/01/2009 | 100000 | 0.135
3374 | Michigan | SHIAWASSEE |  | 4 | 0976213 | 0.24 miles of pavement resurfacing on Maple Street from M-71 to Main Street near the City of Durand, Shiawausee County. Improvements will enhance pavement rideability and increase pavement smoothness | Pavement Improvement | 09/25/2009 | 09/28/2009 | 11/30/2009 | 52000 | 0.244
3375 | Michigan | ST CLAIR | PORT HURON | 10 | 0977015 | The Michigan Department of Transportation will realign and make improvements to numerous local streets that cross under the Blue Water Bridge in Port Huron. The project will improve local traffic move | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2011 | 831088.52 | 0.618
3376 | Michigan | ST CLAIR | PORT HURON | 10 | 0977029 | 0.3 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along Collard Drive in Marysville. | Pavement Improvement | 01/06/2010 |  | 05/30/2011 | 409478.11 | 0.288
3377 | Michigan | ST CLAIR |  | 10 | 0977031 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Dryden Road in St. Clair County. | Pavement Improvement | 09/03/2009 | 10/21/2009 | 10/30/2009 | 213948 | 1.031
3378 | Michigan | ST CLAIR | PORT HURON | 10 | 0977035 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of Riverside Drive in Port Huron. | Pavement Improvement | 08/25/2009 | 09/03/2009 | 10/30/2009 | 292819.06 | 0.573
3379 | Michigan | ST CLAIR | PORT HURON | 10 | 0977040 | 10 miles of resurfacing to maintain the pavement condition and improve ride quality of M-25 in St. Clair by MDOT. | Pavement Improvement | 11/18/2009 |  | 10/15/2010 | 6151432.86 | 10.708
3380 | Michigan | ST CLAIR |  | 10 | 0977042 | Bridge replacement to improve safety and maintain mobility of I-94 over the Belle River in St. Clair County by MDOT. | Bridge Replacement | 12/02/2009 |  | 10/08/2012 | 6671137.3 | 0
3381 | Michigan | ST CLAIR |  | 10 | 0977044 | 3.6 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty on I-94 in St. Clair County. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 10/08/2012 | 19067246.74 | 4.479
3382 | Michigan | TUSCOLA |  | 5 | 0979010 | MDOT is upgrading 6.0 miles to create a paved pathway on M-15 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 06/02/2009 | 06/02/2009 | 03/31/2010 | 417760.26 | 6.047
3383 | Michigan | TUSCOLA |  | 5 | 0979014 | In the village of Mayville, Tuscola County there will be 0.20 miles of roadway reconstruction on Industrial Park Road at M-24 to improve the driving quality and make the road smoother. | Pavement Improvement | 09/28/2009 | 10/05/2009 | 06/01/2010 | 50000 | 0.12
3384 | Michigan | VAN BUREN |  | 6 | 0980009 | "The City of Hartford will resurface 0.5 miles of W. Main Street from the city limits to Center Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/20/2009 | 09/21/2009 |  | 180000 | 0.501
3385 | Michigan | VAN BUREN |  | 6 | 0980013 | "The village of Decatur will resurface 0.4 miles of N. Phelps Street (CR 653) from the village limits to Cedar Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/28/2009 | 09/16/2009 | 05/28/2010 | 295294.75 | 0.417
3386 | Michigan | VAN BUREN |  | 6 | 0980020 | "The village of Paw Paw will resurface 0.9 miles of East Michigan Avenue from the E. village limits to Kalamazoo Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 10/02/2009 | 10/09/2009 | 11/15/2009 | 135000 | 0.933
3387 | Michigan | WASHTENAW |  | 7 | 0981027 | 5.50 miles of pavement resurfacing on I-94 from the Freer Road easterly to Parker Road, west of Ann Arbor in Washtenaw County. This project includes ramp reconstruction, drainage improvements and fre | Pavement Improvement | 05/14/2009 | 05/14/2009 | 12/31/2012 | 15902463.48 | 11
3388 | Michigan | WASHTENAW |  | 7 | 0981028 | 6.62 miles of pavement resurfacing on I-94 from the west Washtenaw County line easterly to Freer Road. This project includes ramp reconstruction, drainage improvements and freeway shoulder widening. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 12/31/2012 | 3950107.41 | 13.24
3389 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981031 | 0.35 miles of pavement resurfacing and drainage improvements on North Ann Arbor Street from US-12 to Bennett Street in the City of Saline, Washtenaw County. | Pavement Improvement | 08/04/2009 | 08/31/2009 | 10/02/2009 | 210000 | 0.35
3390 | Michigan | WASHTENAW | ANN ARBOR | 15 | 0981035 | Throughout Washtenaw County the cracks in the pavement will be sealed to extend the life of the pavement. | Pavement Improvement | 07/29/2009 | 09/01/2009 | 09/01/2010 | 27220 | 7.795
3391 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981036 | 6.56 miles of roadway will be resurfaced in Washtenaw county, north of the City of Ann Arbor at multiple locations. North Territorial Road from Webster Church to Whitmore Lake, North Territorial Road | Pavement Improvement | 07/29/2009 | 07/29/2009 | 09/01/2010 | 616691.99 | 6.146
3392 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 0981037 | 5.44 miles of pavement repair in the city of Ann Arbor area. This project will provide for improved rideability and increased pavement smoothness on Jackson Road from Honey Creek Drive to Wagner Road | Pavement Improvement | 07/29/2009 | 06/01/2010 | 08/01/2010 | 88259.15 | 5.435
3393 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 0981038 | 11 miles of pavement resurfacing at various locations thourghout Washtenaw County to improve pavement rideability and pavement smoothness. Locations include Ann Arbor Road from Zeeb Road to West Ann | Pavement Improvement | 07/29/2009 | 05/01/2010 | 09/01/2010 | 1007882.17 | 11.055
3394 | Michigan | WASHTENAW | ANN ARBOR | 15 | 0981039 | 2.36 miles of Loer Road from Textile Road to W Ellsworth Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, south of the City of Ann Arb | Pavement Improvement | 07/29/2009 | 09/01/2009 | 09/01/2010 | 43026 | 2.364
3395 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981040 | 2.43 miles of pavement resurfacing on Huron River Drive along the scenic Huron River between the Village of Dexter and the City of Ann Arbor in Washtenaw County. Improvements will provide for increas | Pavement Improvement | 07/29/2009 | 05/01/2010 | 09/01/2010 | 250000 | 2.426
3396 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981042 | 2.0 miles of Baker Road from I-94 to Dan Hoey Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, West of the City of Ann Arbor in Washte | Pavement Improvement | 08/04/2009 | 09/01/2009 | 09/01/2010 | 49700 | 2.055
3397 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 0981043 | 1.78 miles of Ann Arbor-Saline Road from Oak Valley Drive to Maple Road and Maple Road from Ann Arbor-Saline Road to Saline City limits will have a Chip and Seal treatment to preserve pavement life an | Pavement Improvement | 08/04/2009 | 09/01/2009 | 09/01/2010 | 82000 | 1.778
3398 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981044 | 2.0 miles of Dexter Ann Arbor Road from Dan Hoey Road to Zeeb Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, West of the City of Ann | Pavement Improvement | 08/04/2009 | 09/01/2009 | 09/01/2010 | 48887 | 2.112
3399 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 0981050 | 2.23 miles of Miller Road from Dexter Ann Arbor Road to Wagner Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, west of the City of An | Pavement Improvement | 08/13/2009 | 09/01/2009 | 09/01/2010 | 59628 | 2.229
3400 | Michigan | WASHTENAW | ANN ARBOR | 15 | 0981061 | This project will provide for traffic signal upgrades on Packard Road from the East Eisenhower Parkway to East Stadium Blvd. This work will improve traffic safety, ease congestion and increase traffi | Safety/Traffic Management | 09/21/2009 | 03/15/2010 | 06/15/2010 | 188774.61 | 1.309
3401 | Michigan | WAYNE | DETROIT,MI | 11 | 0982054 | MDOT will repair and resurface . 9 miles of US-24 in Redford Township in Wayne County to improve driving quality and increase service life | Pavement Improvement | 05/14/2009 | 05/14/2009 | 12/31/2011 | 920378.03 | 0.921
3402 | Michigan | WAYNE | DETROIT,MI | 15 | 0982055 | MDOT will resurface .8 miles of US-24 in the City of Flat Rock to improve the driving quality and extend the service life of the road | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/01/2009 | 380360.58 | 0.816
3403 | Michigan | WAYNE | DETROIT,MI | 14 | 0982057 | MDOT will landscape and replace fence on . 6 miles of I-75 in the City of Hamtamck Wayne County which will beautify the drive and make it safer. | Transportation Enhancements | 05/14/2009 | 05/14/2009 | 09/19/2011 | 605927.78 | 1.553
3404 | Michigan | WAYNE | DETROIT,MI | 13,14 | 0982058 | MDOT will rehabilitate 7 bridges in the City of Detroit on I-96 to make the bridges last longer | Bridge Improvement | 05/14/2009 | 05/14/2009 | 09/07/2011 | 11733244.14 | 0
3405 | Michigan | WAYNE | DETROIT,MI | 13 | 0982059 | MDOT will repair the I-96 under Underwood Avenue bridge in the City of Detroit to make the bridge last longer | Bridge Improvement | 05/14/2009 | 05/14/2009 | 08/27/2010 | 1179301.38 | 0
3406 | Michigan | WAYNE | DETROIT,MI | 14 | 0982060 | MDOT will rehabilitate 3 bridges in the City of Detroit on I-96 to make the bridges last longer | Bridge Improvement | 05/19/2009 | 05/19/2009 | 12/31/2010 | 3918931.54 | 0
3407 | Michigan | WAYNE | DETROIT,MI | 11 | 0982061 | The City of Westland will reconstruct the Newburgh and Warren intersection in the City of Westland to improve the driving quality and safety | Pavement Improvement | 05/19/2009 | 05/19/2009 | 11/15/2009 | 681745.36 | 0.005
3408 | Michigan | WAYNE | DETROIT,MI | 14 | 0982064 | MDOT is removing 2 railroad bridges over I-96 in the City of Detroit because they are no longer used | Bridge Improvement | 05/21/2009 | 05/21/2009 | 12/31/2010 | 1013288.99 | 0
3409 | Michigan | WAYNE | DETROIT,MI | 11,15 | 0982066 | 1 mile of Warren Road in the City of Dearborn Heights will be resurfaced by Wayne County to improve the driving quality and increase the road service life | Pavement Improvement | 05/21/2009 | 05/21/2009 | 11/15/2009 | 937323.29 | 0.994
3410 | Michigan | WAYNE | DETROIT,MI | 15 | 0982067 | MDOT will construct a sound will at I-96 and US-24 to reduce road sounds to adjacent properties | Other | 05/29/2009 | 05/29/2009 | 09/20/2012 | 4283379.7 | 1.615
3411 | Michigan | WAYNE | DETROIT,MI | 13 | 0982076 | The City of Grosse Point will resurface .4 miles of St Clair Road to improve driving quality and increase road service life | Pavement Improvement | 07/31/2009 | 08/22/2009 | 10/30/2009 | 324883.76 | 0.388
3412 | Michigan | WAYNE | ANN ARBOR | 11 | 0982082 | MDOT will repair and resurface the ramps on I-94 at Belleville road in Van Buren Township Wayne County to improve the driving quality and increase service life | Pavement Improvement | 06/04/2009 | 06/04/2009 | 12/31/2010 | 621391.94 | 0.944
3413 | Michigan | WAYNE | STATEWIDE | 11 | 0982083 | MDOT will repair and resurface the ramps on I-94 at Haggerty Road in Van Buren Township Wayne County to improve the driving quality and increase service life | Other | 06/04/2009 | 06/04/2009 | 12/31/2010 | 638107.71 | 0.839
3414 | Michigan | WAYNE |  | 11 | 0982098 | MDOT will repair and resurface 6.3 miles of non motorized path along I-275 in Wayne County for cyclists, walkers and joggers to promote alternate modes of transportation | Transportation Enhancements | 07/07/2009 | 07/07/2009 | 03/02/2012 | 4496000 | 12.53
3415 | Michigan | WAYNE | DETROIT,MI | 13 | 0982100 | The City of Grosse Point Shores will resurface .4 miles of Vernier Road to improve driving quality and increase service life | Pavement Improvement | 08/19/2009 | 06/15/2010 | 08/31/2010 | 263330.54 | 0.364
3416 | Michigan | WAYNE | DETROIT,MI | 14 | 0982108 | MDOT will replace pumping equipment on I-94 in the City of Dearborn Wayne County to insure rainwater will not interfere with traffic | Pavement Improvement | 07/21/2009 | 07/21/2009 | 12/31/2010 | 1032329.78 | 0.324
3417 | Michigan | WAYNE | DETROIT,MI | 14 | 0982113 | MDOT will rehabilitate the M-8 under Joseph Campau bridge to make the bridge last longer | Bridge Improvement | 09/16/2009 | 09/16/2009 | 12/31/2011 | 1724905.14 | 0.226
3418 | Michigan | WAYNE | DETROIT,MI | 14 | 0982114 | MDOT will repair the M-8 under Charest Avenue walkover bridge to make the bridge last longer | Bridge Improvement | 09/16/2009 | 09/16/2009 | 12/31/2011 | 194264.47 | 0.048
3419 | Michigan | WAYNE | DETROIT,MI | 14 | 0982115 | MDOT will rehabilitate the M-8 under Goddard Avenue bridge to make the bridge last longer | Bridge Improvement | 09/16/2009 | 09/16/2009 | 12/31/2011 | 1714610.1 | 0.262
3420 | Michigan | WAYNE | DETROIT,MI | 14 | 0982116 | MDOT will resurface 1.4 miles of M-8 in the City of Detroit to improve driving quality and extend service life of the road | Pavement Improvement | 07/24/2009 | 07/24/2009 | 12/31/2011 | 12458747.68 | 2.722
3421 | Michigan | WAYNE | DETROIT,MI | 14 | 0982117 | MDOT will rehabilitate 5 bridges on M-8 to make the bridges last longer | Bridge Improvement | 09/16/2009 | 09/16/2009 | 12/31/2011 | 583657.03 | 0
3422 | Michigan | WAYNE | DETROIT,MI | 11 | 0982121 | Wayne County will resurface .5 Miles of Merriman Road in the Cities of Westland and Livonia to improve driving quality and increase service life | Pavement Improvement | 07/29/2009 | 04/15/2010 | 10/01/2010 | 795644.91 | 0.516
3423 | Michigan | WAYNE | DETROIT,MI | 11 | 0982122 | The City of Livonia will resurface .5 miles of Lyndon Road to improve driving quality and increase service life | Pavement Improvement | 07/29/2009 | 05/01/2010 | 08/30/2010 | 675000 | 0.502
3424 | Michigan | WAYNE | DETROIT,MI | 13 | 0982123 | Wayne County will resurface .6 miles of 7 Mile Road to improve driving quality and increase service life | Pavement Improvement | 07/30/2009 | 07/30/2009 | 10/01/2010 | 653456.8 | 0.625
3425 | Michigan | WAYNE | DETROIT,MI | 15 | 0982124 | MDOT will repair and resurface .4 miles of US-12 in the City of Dearborn to improve the driving quality and increase service life | Pavement Improvement | 08/03/2009 | 08/03/2009 | 12/31/2011 | 2449807.27 | 3.025
3426 | Michigan | WAYNE | DETROIT,MI | 13 | 0982130 | MDOT will install an active speed warning system on the I-94 Ebd ramp to I-96 in the City of Detroit which will improve safety | Safety/Traffic Management | 10/06/2009 |  | 11/15/2012 | 476061.37 | 0.07
3427 | Michigan | WAYNE | DETROIT,MI | 13 | 0982131 | MDOT will install an active speed warning system on the I-94 Wbd ramp to I-96 in the City of Detroit which will improve safety | Safety/Traffic Management | 10/06/2009 |  | 11/15/2012 | 395535.08 | 0.108
3428 | Michigan | WAYNE | DETROIT,MI | 13 | 0982136 | MDOT will repair 2 railroad bridges over M-85 in the City of Detroit to make the bridges last longer | Bridge Improvement | 10/21/2009 |  | 09/01/2010 | 910284.81 | 0
3429 | Michigan | WAYNE | DETROIT,MI | 14 | 0982141 | MDOT will repair and resurface 6 miles of M-39 in the cities of Detroit and Dearborn to improve driving quality and increase service life | Pavement Improvement | 08/11/2009 | 08/11/2009 | 05/21/2010 | 3072846.05 | 11.939
3430 | Michigan | WAYNE | DETROIT,MI | 14 | 0982152 | The City of Detroit is resurfacing portions of Seven Mile, Conner, McNichols, East Vernor, Mt Elliot, Mack and Warren Roads to improve driving quality and increase service life | Pavement Improvement | 08/20/2009 | 04/15/2010 | 11/02/2010 | 4717348 | 0.36
3431 | Michigan | WAYNE | DETROIT,MI | 13,14 | 0982153 | The City of Detroit is resurfacing portions of E. Congress, E. Lafayette, E. Larned, Clark, Chicago and Puritan Roads to improve driving quality and increase service life | Pavement Improvement | 08/20/2009 | 04/15/2010 | 11/02/2010 | 2870051.21 | 6.576
3432 | Michigan | WAYNE | DETROIT,MI | 14 | 0982154 | The City of Detroit is resurfacing portions of Meyers, Burt, Southfield Service Drive, Lodge Service Drive and Livernois Roads to improve driving quality and increase service life | Pavement Improvement | 08/20/2009 | 04/15/2010 | 11/02/2010 | 4094000 | 7.267
3433 | Michigan | WAYNE | DETROIT,MI | 11,15 | 0982170 | Wayne County will resurface 1.5 Miles of Middlebelt Road in the City of Romulus to improve driving quality and increase service life | Pavement Improvement | 09/09/2009 | 09/09/2009 | 10/01/2010 | 1846527.85 | 1.501
3434 | Michigan | WAYNE | DETROIT,MI | 11 | 0982173 | Wayne County will will reconstruct and widen to 5 lanes 1.4 miles of Canton Center Road in Canton Township to improve safety and ease congestion | Pavement Widening | 09/16/2009 | 04/15/2010 | 10/01/2010 | 3867492 | 1
3435 | Michigan | WEXFORD |  | 2 | 0983019 | The MDOT is replacing the US-131 bridge over the Manistee River in the City of Manistee to improve safety and increase mobility. | Bridge Replacement | 06/04/2009 | 06/04/2009 | 06/18/2010 | 164915.8 | 0.11
3436 | Michigan | STATEWIDE |  | 3,4 | 0984075 | The MDOT is undertaking areawide pavement repairs on 14 miles of roadway in Howard City area to improve the pavement condition and extend pavement life. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 11/14/2009 | 202569.95 | 19.42
3437 | Michigan | STATEWIDE |  | 2 | 0984076 | The MDOT is undertaking areawide pavement repairs on nearly 18 miles of roadway in the Grand Region area to improve the pavement condition and extend pavement life. | Pavement Improvement | 05/05/2009 | 05/05/2009 | 06/30/2010 | 296665.14 | 23.769
3438 | Michigan | STATEWIDE |  | 1 | 0984084 | The 8 weather towers, called an Environmental Sensor Station are designed to aid motorists and the Michigan Department of Transportation (MDOT), and are expected to be particularly helpful in the wint | Safety/Traffic Management | 05/05/2009 | 05/05/2009 | 10/30/2009 | 1150758.19 | 1.6
3439 | Michigan | STATEWIDE | DETROIT,MI | 13 | 0984088 | Throughout the Detroit Metropolitan Freeway System the automated traffic control system will receive upgrades to its equipment. This will lessen freeway congestion and improve safety. | Other | 06/04/2009 | 06/04/2009 | 12/31/2015 | 7000000 | 0
3440 | Michigan | GRAND TRAVERSE |  | 1,2,4 | 0984100 | MDOT will repair 27 miles of M-37, US-131, and US-31 at various locations in Grand Traverse Countyto extend the service life of the existing roadways. | Pavement Improvement | 09/17/2009 |  |  | 155497.02 | 27.206
3441 | Michigan | STATEWIDE |  | 1 | 0984103 | At numerous Statewide locations along US-23 and M-55 the guardrail will be replaced with upgraded guardrail to improve safety | Safety/Traffic Management | 06/17/2009 | 06/17/2009 | 05/28/2010 | 339789.51 | 29.15
3442 | Michigan | STATEWIDE |  | 1 | 0984107 | The weather tower and message sign project will consist of 12 Environmental Sensor Stations and 10 Dynamic Message Signs in 4 Counties and will improve safety and mobility. | Safety/Traffic Management | 07/07/2009 | 07/07/2009 | 12/01/2010 | 1326704.36 | 7.711
3443 | Michigan | STATEWIDE |  | 1,2,4 | 0984108 | The MDOT is installing environmental sensors in the North Region at various locations to monitor environmental conditions in the Region. | Safety/Traffic Management | 07/07/2009 | 07/07/2009 | 12/01/2010 | 1425543.8 | 13.871
3444 | Michigan | STATEWIDE | DETROIT,MI | 10,11 | 0984133 | Establishing a protective security fence around five towers in Oakland, Macomb and St. Clair Counties by MDOT. | Safety/Traffic Management | 08/17/2009 | 08/17/2009 | 11/15/2009 | 45999.75 | 0.001
3445 | Michigan | BERRIEN |  | 6 | 1011003 | "The village of Eau Claire will resurface 0.84 miles of E. Main Street throughout the limits of the village. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/05/2010 |  | 06/18/2010 | 92500 | 0.837
3446 | Michigan | CASS |  | 6 | 1014003 | The Cass County Road Commisssion will resurface 1.2 miles of Dixon Road from Indian Lake Road to M-152, in the northwest part of the county. This will improve the driving quality by making the road s | Pavement Improvement | 10/21/2009 | 06/01/2010 | 07/01/2010 | 24950 | 1.197
3447 | Michigan | CHIPPEWA |  | 1 | 1017003 | This pavement project on Riverside Drive in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 01/05/2010 |  | 07/02/2010 | 573808.58 | 4.986
3448 | Michigan | CLINTON |  | 8 | 1019005 | Seal Coat | Pavement Improvement | 11/23/2009 | 06/07/2010 | 06/30/2010 | 63760.98 | 4.887
3449 | Michigan | EATON |  | 7 | 1023005 | Seal Coat | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 71300 | 5.047
3450 | Michigan | EATON |  | 7 | 1023006 | Seal Coat | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 66400 | 4.552
3451 | Michigan | EATON |  | 7 | 1023007 | Seal Coat | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 68200 | 4.808
3452 | Michigan | EATON |  | 7 | 1023008 | Seal Coat | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 34600 | 2.373
3453 | Michigan | EATON |  | 7 | 1023009 | Seal Coat | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 47180 | 3.293
3454 | Michigan | EATON |  | 7 | 1023010 | Seal Coat | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 79800 | 5.526
3455 | Michigan | EATON |  | 7 | 1023011 | Seal Coat | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 76440 | 5.423
3456 | Michigan | EATON |  | 7 | 1023012 | Seal Coat | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 59000 | 4.03
3457 | Michigan | GENESEE |  | 5 | 1025003 | In Genesee County, MDOT will repair 8.11 miles on M-15 from the Oakland County line northerly to south of I-69 to extend the service life of the existing road. | Pavement Improvement | 12/10/2009 |  | 06/26/2010 | 1276737.62 | 8.243
3458 | Michigan | GENESEE | FLINT | 5 | 1025020 | Pavement repair, mill, resurf | Pavement Improvement | 12/22/2009 | 06/21/2010 | 09/17/2010 | 656000 | 0.524
3459 | Michigan | GRATIOT |  | 4 | 1029006 | From the St. Louis north city limit northerly to McGregor Road in Gratiot County there will be 0.76 miles reconstruction on Riverside Drive to improve the driving quality of the roadway. | Pavement Improvement | 01/22/2010 |  | 08/13/2010 | 299266.73 | 0.79
3460 | Michigan | HILLSDALE |  | 7 | 1030004 | 10.43 miles of South Meridian Road (US-127) from the Ohio State line north to M-34 will be resurfaced to improve pavement rideability and increase pavement smoothness. This project will include drain | Pavement Improvement | 10/29/2009 | 10/29/2009 | 11/15/2010 | 6539056.31 | 10.43
3461 | Michigan | INGHAM | LANSING | 8 | 1033010 | Restore and rehabilitate | Pavement Improvement | 01/20/2010 | 06/07/2010 | 09/07/2010 | 900000 | 2.463
3462 | Michigan | JACKSON |  | 7 | 1038005 | I-94 near the city of Jackson in Jackson County from East of Sargent Road to the Washtenaw County Line will be rebuilt to improve mobility and reduce congestion | Pavement Improvement | 10/26/2009 | 10/26/2009 | 12/31/2011 | 30000000 | 22.952
3463 | Michigan | KALAMAZOO |  | 6 | 1039009 | Non-Motorized Path | Transportation Enhancements | 11/18/2009 | 04/01/2010 | 08/28/2010 | 1766125 | 6.105
3464 | Michigan | KALAMAZOO |  | 6,7 | 1039012 | Single Course Chip Seal | Pavement Improvement | 01/27/2010 | 07/05/2010 | 08/06/2010 | 32384.65 | 2.185
3465 | Michigan | KALAMAZOO |  | 6 | 1039013 | Single Course Chip Seal | Pavement Improvement | 01/27/2010 | 07/05/2010 | 08/06/2010 | 91010 | 3.375
3466 | Michigan | KENT | GRAND RAPIDS | 3 | 1041007 | About a mile of Lake Drive From Fuller Avenue to Calton Avenue in the City of Gran in Kent County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 10/26/2009 | 04/19/2010 | 05/17/2010 | 158730.36 | 0.19
3467 | Michigan | KENT | GRAND RAPIDS | 3 | 1041020 | Mill,Joint Repairs, Resurface | Pavement Improvement | 01/06/2010 | 01/06/2010 |  | 2181011.43 | 1.849
3468 | Michigan | LAPEER |  | 10 | 1044006 | From the southern Macomb County line northerly to the northern village limit of Almont and from the northern village limit northerly to just south of I-69 in Lapeer County there will be 6.20 miles of | Pavement Improvement | 10/15/2009 | 10/15/2009 | 09/18/2010 | 1284955.19 | 6.57
3469 | Michigan | MACKINAC |  | 1 | 1049003 | This pavement project on M-134 in Mackinac County will improve the drive quality and make the road smoother. | Pavement Widening | 10/15/2009 | 10/15/2009 | 09/02/2010 | 2466828.62 | 13.535
3470 | Michigan | MACOMB | DETROIT,MI | 12 | 1050006 | MDOT will rebuild concrete barrier and landscaping along I-696 from Gratiot Road to I-75 in Metro Detroit in Macomb County to improve safety | Pavement Improvement | 01/25/2010 |  | 10/01/2013 | 10244971.18 | 17.407
3471 | Michigan | MONROE | TOLEDO (OH) | 15 | 1058010 | Rehabilitate culvert | Pavement Improvement | 01/27/2010 | 03/19/2010 | 07/16/2010 | 383000 | 0.037
3472 | Michigan | MONTMORENCY |  | 1 | 1060006 | Over 3 miles of County Road 624 from CR459 to Ess Lake Road near the city of Hillman in Montmorency County will be repaved to improve ride quality and make the road smoother | Other | 10/23/2009 | 11/01/2009 | 03/05/2010 | 11000 | 3.051
3473 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 1061305 | The MDOT is installing cable guard rail on US-31 from Airline Rd north to Marquette Ave in the Cities of Norton Shores and Muskegon to improve safety. | Safety/Traffic Management | 10/15/2009 | 10/15/2009 | 09/13/2010 | 731165.9 | 10.075
3474 | Michigan | NEWAYGO |  | 2 | 1062006 | A little over 3 miles of Alger Road from 128th Street to Moore Road near the city of Grant in Newaygo County will be repaved to improve ride quality and make the road smoother | Other | 10/23/2009 | 05/15/2010 | 07/30/2010 | 25000 | 2.013
3475 | Michigan | OSCEOLA |  | 4 | 1067006 | A little over 4 miles of River/115th/4 Mile Rpad snear the city of Evart in Osceola County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 10/21/2009 | 05/01/2010 | 07/01/2010 | 229923.57 | 4.143
3476 | Michigan | ROSCOMMON |  | 4 | 1072006 | Over 2 miles of US Old 27 from Mary Road to Yeager Road near the city of Houghton Lake in Roscommon County will have its shoulder widened to improve safety and improve mobility | Pavement Improvement | 10/26/2009 | 05/15/2010 | 07/15/2010 | 143000 | 2.218
3477 | Michigan | SAGINAW |  | 5 | 1073006 | In the city of Saginaw, MDOT will resurface 8.78 miles on M-81 from Indiantown Road easterly to Wadsworth Avenue to improve the driving quality of the roadway. | Pavement Improvement | 10/15/2009 | 10/15/2009 | 07/02/2010 | 861152.22 | 8.78
3478 | Michigan | SAGINAW |  | 4 | 1073007 | Single Course Chip Seal | Pavement Improvement | 11/10/2009 | 06/01/2010 | 08/31/2010 | 65000 | 3.972
3479 | Michigan | SAGINAW |  | 4 | 1073008 | Single Course Chip Seal | Pavement Improvement | 11/10/2009 | 06/01/2010 | 08/31/2010 | 66000 | 4.287
3480 | Michigan | SAGINAW |  | 4 | 1073009 | Single Course Chip Seal | Pavement Improvement | 11/10/2009 | 06/01/2010 | 08/31/2010 | 70000 | 4.188
3481 | Michigan | SAGINAW |  | 4 | 1073010 | Single Course Chip Seal | Pavement Improvement | 11/10/2009 | 06/01/2010 | 08/31/2010 | 80993.12 | 5.131
3482 | Michigan | SCHOOLCRAFT |  | 1 | 1075003 | This shoulder paving project on County Road 442 in Schoolcraft County will improve safety. | Pavement Improvement | 10/21/2009 | 08/16/2010 | 09/30/2010 | 94500 | 4.039
3483 | Michigan | SCHOOLCRAFT |  | 1 | 1075006 | Aggregate Shoulder | Pavement Improvement | 12/11/2009 | 07/01/2010 | 08/15/2010 | 11952 | 6.41
3484 | Michigan | ST JOSEPH |  | 6 | 1078006 | Single Course Chip Seal | Pavement Improvement | 12/22/2009 | 06/01/2010 | 08/31/2009 | 42260 | 3.048
3485 | Michigan | ST JOSEPH |  | 6 | 1078007 | Single Course Chip Seal | Pavement Improvement | 12/22/2009 | 06/01/2010 | 08/31/2009 | 86617 | 7.79
3486 | Michigan | ST JOSEPH |  | 6 | 1078009 | Reconstruct | Pavement Improvement | 01/27/2010 | 02/15/2010 | 08/31/2010 | 130000 | 0.532
3487 | Michigan | TUSCOLA |  | 5 | 1079006 | The Tuscola County Road Commission will replace the West Cass City Rd bridge over the Allen drain to improve safety and mobility. | Bridge Replacement | 02/01/2010 |  | 08/28/2010 | 342711 | 0.489
3488 | Michigan | VAN BUREN |  | 6 | 1080008 | Nonmotorized Path | Transportation Enhancements | 12/23/2009 | 05/01/2010 | 07/01/2010 | 900000 | 0.333
3489 | Michigan | WASHTENAW | ANN ARBOR | 15 | 1081002 | Nonmotorized expansion | Safety/Traffic Management | 12/09/2009 | 08/02/2010 | 09/17/2010 | 250000 | 2.278
3490 | Michigan | WASHTENAW | ANN ARBOR | 7 | 1081005 | Resurface | Pavement Improvement | 01/08/2010 | 04/01/2010 | 12/31/2010 | 82600 | 2.412
3491 | Michigan | WASHTENAW | ANN ARBOR | 15 | 1081006 | Resurface | Pavement Improvement | 01/08/2010 | 04/01/2010 | 12/31/2010 | 34100 | 1.468
3492 | Michigan | WASHTENAW | ANN ARBOR | 7 | 1081007 | Resurface | Pavement Improvement | 01/08/2010 | 04/01/2010 | 12/31/2010 | 20800 | 0.752
3493 | Michigan | WASHTENAW | ANN ARBOR | 7 | 1081008 | Resurface | Pavement Improvement | 01/08/2010 | 04/01/2010 | 12/31/2010 | 40600 | 0.595
3494 | Michigan | WASHTENAW | ANN ARBOR | 15 | 1081009 | Resurface | Pavement Improvement | 01/12/2010 | 04/01/2010 | 12/31/2010 | 409200 | 1.38
3495 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 1081010 | Resurface | Pavement Improvement | 01/12/2010 | 04/01/2010 | 12/31/2010 | 387700 | 2.04
3496 | Michigan | WAYNE | DETROIT,MI | 13 | 1082009 | Detroit is building a mile of paved pathway for cyclists, walkers, and joggers to promote alternative modes of transportation | Transportation Enhancements | 10/26/2009 | 10/26/2009 | 11/15/2012 | 1946988.29 | 0.824
3497 | Michigan | WAYNE | DETROIT,MI | 13 | 1082012 | Design and const of wharf | Other | 04/01/2009 |  |  | 599205 | 0.129
3498 | Michigan | WAYNE | DETROIT,MI | 13 | 1082013 | Terminal building expansion | Other | 04/01/2009 |  |  | 210250 | 0.129
3499 | Michigan | WAYNE | DETROIT,MI | 15 | 1082014 | Resurface road | Pavement Improvement | 11/18/2009 | 04/15/2010 | 09/15/2010 | 643000 | 3.67
3500 | Michigan | WAYNE | DETROIT,MI | 15 | 1082015 | Resurface road | Pavement Improvement | 11/25/2009 | 04/19/2010 | 10/31/2010 | 330408.25 | 0.464
3501 | Michigan | WAYNE | DETROIT,MI | 13 | 1082016 | Resurface road | Pavement Improvement | 11/18/2009 | 06/21/2010 | 08/27/2010 | 158000 | 0.213
3502 | Michigan | WAYNE | DETROIT,MI | 13,14 | 1082017 | Resurface roads | Pavement Improvement | 11/18/2009 | 04/15/2010 | 11/02/2010 | 5103729 | 10.093
3503 | Michigan | WAYNE | DETROIT,MI | 15 | 1082018 | Resurface road | Pavement Improvement | 11/18/2009 | 04/15/2010 | 09/15/2010 | 800000 | 0.897
3504 | Michigan | WAYNE | DETROIT,MI | 11 | 1082019 | Resurface road | Pavement Improvement | 11/18/2009 | 04/19/2010 | 07/01/2010 | 524000 | 0.558
3505 | Michigan | WAYNE | DETROIT,MI | 15 | 1082020 | Resurface road | Pavement Improvement | 11/18/2009 | 04/19/2010 | 10/31/2010 | 151000 | 0.18
3506 | Michigan | WAYNE | DETROIT,MI | 13 | 1082022 | Terminal building expansion | Other | 04/01/2009 |  |  | 1000000 | 0.129
3507 | Michigan | WAYNE | DETROIT,MI | 13 | 1082023 | Design and const of wharf | Other | 04/01/2009 |  |  | 6028 | 0.129
3508 | Michigan | WAYNE | DETROIT,MI | 13 | 1082024 | Resurface road | Pavement Improvement | 11/18/2009 | 06/21/2010 | 08/27/2010 | 479500 | 0.456
3509 | Michigan | WAYNE | DETROIT,MI | 13 | 1082025 | Resurface road | Pavement Improvement | 11/25/2009 | 04/15/2010 | 07/02/2010 | 237000 | 0.225
3510 | Michigan | WAYNE | DETROIT,MI | 14 | 1082036 | Resurface | Pavement Improvement | 01/12/2010 | 07/15/2010 | 10/15/2010 | 1300000 | 1.997
3511 | Michigan | WAYNE | DETROIT,MI | 15 | 1082038 | Resurface road | Pavement Improvement | 01/12/2010 | 04/15/2010 | 06/15/2010 | 1412000 | 1.001
3512 | Minnesota | TODD, WADENA |  | 7, 8 | 09ES001 | Remove and replace pavement on state highway 10 from Wadena to Staples. Add turn lanes, replace signs, pave shoulders, install rumble strips and lighting and improve pedestrian crossings | Pavement Improvement | 03/23/2009 | 05/01/2009 | 07/15/2009 | 7312124 | 40.78
3513 | Minnesota | BIG STONE |  | 7 | 09ES002 | Placement of bituminous surfacing on Trunk Highway 75 from Graceville to Ortonville | Pavement Improvement | 04/23/2009 | 05/04/2009 | 07/31/2009 | 5143074 | 18.952
3514 | Minnesota | MILLE LACS |  | 8 | 09ES003 | Remove and replace 13.4 miles of pavement on state highway 169 from Princeton to Milaca | Pavement Improvement | 03/11/2009 | 05/01/2009 | 09/25/2009 | 4163703 | 26.706
3515 | Minnesota | RICE |  | 2 | 09ES004 | Replace pavement, add new median guardrail and improve water drainage pipes on northbound and southbound lanes of I-35 through Faribault | Pavement Improvement | 05/04/2009 | 05/11/2009 | 09/11/2009 | 4769068 | 7.85
3516 | Minnesota | STATEWIDE |  | 1,2,7 | 09ES006 | Construct guardrails improvements on state highways throughout District 7 to improve safety | Safety/Traffic Management | 04/16/2009 | 05/04/2009 | 08/04/2009 | 483893 | 0
3517 | Minnesota | STATEWIDE |  | 1,2 | 09ES007 | Replace guardrail on Trunk highways throughout southeast Minnesota | Safety/Traffic Management | 04/17/2009 | 05/11/2009 | 10/01/2009 | 1695398 | 0
3518 | Minnesota | MOWER, OLMSTED |  | 1 | 09ES008 | Replace pavement, upgrade guardrail and improve water drainage pipes on eastbound I-90 from Stewartville to 8.6 miles west | Pavement Improvement | 04/17/2009 | 05/04/2009 | 07/05/2009 | 2108897 | 8.633
3519 | Minnesota | FREEBORN |  | 1 | 09ES009 | Replace pavement on I-90, upgrade guardrail and improve water drainage pipes from Albert Lea to Alden | Pavement Improvement | 03/23/2009 | 05/01/2009 | 09/30/2009 | 17117366 | 23.968
3520 | Minnesota | WINONA |  | 1 | 09ES010 | Replace existing pavement, upgrade guardrail and improve water drainage pipes on westbound I-90 from St. Charles to 14 miles east | Pavement Improvement | 06/10/2009 | 06/22/2009 | 08/28/2009 | 4511492 | 14.099
3521 | Minnesota | STEARNS, TODD |  | 6, 7 | 09ES011 | Install cable median barrier on I-94 from Sauk Centre to the Douglas/Todd County Line | Safety/Traffic Management | 03/23/2009 | 05/01/2009 | 09/20/2009 | 1551326 | 26.562
3522 | Minnesota | STATEWIDE |  | 8 | 09ES012 | Install hazardous curve signs at various locations on Trunk Highways 1, 38, 65, and 217 in Itasca, Koochiching and St Louis Counties in rural Northeast Minnesota | Safety/Traffic Management | 04/23/2009 | 05/11/2009 | 06/21/2009 | 45740 | 0
3523 | Minnesota | WINONA |  | 1 | 09ES013 | Replace existing pavement, upgrade guardrail and improve water drainage pipes on eastbound and westbound I-90 from Nodine to Dakota | Pavement Improvement | 04/27/2009 | 07/13/2009 | 10/23/2009 | 3016818 | 17.842
3524 | Minnesota | SIBLEY |  | 7 | 09ES014 | Remove and replace pavement on state highway 93 from LeSueur to Highway 169 | Pavement Improvement | 04/15/2009 | 05/11/2009 | 08/07/2009 | 437312 | 0.833
3525 | Minnesota | KANDIYOHI |  | 7 | 09ES015 | Resurface Highway 23 from County Road 31 near New London to County Road 6 near Paynesville in Kandiyohi County | Pavement Improvement | 03/23/2009 | 05/01/2009 | 10/12/2009 | 1202117 | 7.379
3526 | Minnesota | AITKIN |  | 8 | 09ES016 | Resurfacing and safety improvements on Trunk Highway (TH) 65 from TH 210 in McGregor to 1.1 miles South of Big Sandy River Bridge #01013 | Pavement Improvement | 06/10/2009 | 06/17/2009 | 08/21/2009 | 5161594 | 0
3527 | Minnesota | LAKE |  | 8 | 09ES017 | Skid prevention (grinding surface) in Silver Cliff and Lafayette Tunnels on Highway 61 north of Two Harbors | Safety/Traffic Management | 04/24/2009 | 04/27/2009 | 05/26/2009 | 78722 | 7.44
3528 | Minnesota | CARLTON |  | 8 | 09ES018 | "Install plantings to create a ""living"" snow fence to prevent blowing snow from crossing two bridges on I-35 3.7 miles south of Carlton" | Transportation Enhancements | 03/19/2009 | 06/01/2009 | 07/01/2009 | 77971 | 0
3529 | Minnesota | ST LOUIS |  | 8 | 09ES019 | Reinforced concrete pavement on Trunk Highway 169 from 0.39 miles South of County State Highway(CSAH) 5 to 0.43 miles West of CSAH 67 near Chisholm where underground mining had occurred | Pavement Improvement | 06/04/2009 | 06/08/2009 | 06/25/2010 | 7925926 | 3.562
3530 | Minnesota | BELTRAMI, CASS, STATEWIDE |  | 7, 8 | 09ES020 | Replace traffic signal at Trunk Highway 197 and Ridgeway Ave. in Bemidji and at Trunk Highway 2 and Grant Utley Ave. in Cass Lake | Safety/Traffic Management | 07/07/2009 | 07/15/2009 | 08/15/2009 | 317685 | 0
3531 | Minnesota | PENNINGTON, MARSHALL |  | 7 | 09ES021 | Resurface Trunk Highway 1 from Warren to Thief River Falls | Pavement Improvement | 03/11/2009 | 05/01/2009 | 10/01/2009 | 6632798 | 26.848
3532 | Minnesota | BELTRAMI |  | 7 | 09ES022 | Lowering roadway by removal of bridges over abandoned railroad tracks along with additional safety improvements on Trunk Highway 2 in Bemidji | Pavement Improvement | 07/23/2009 | 07/23/2009 | 09/30/2009 | 2515000 | 0.861
3533 | Minnesota | STEARNS, WRIGHT |  | 6 | 09ES023 | Repair pavement on I-94 from Clearwater to Monticello | Pavement Improvement | 03/18/2009 | 05/01/2009 | 08/19/2009 | 6312466 | 0
3534 | Minnesota | STEARNS |  | 6,7 | 09ES024 | Remove and replace bridge pavement at County Road 143 and I-94 | Bridge Improvement | 03/18/2009 | 05/01/2009 | 10/15/2009 | 1592142 | 0
3535 | Minnesota | OTTER TAIL, GRANT |  | 7 | 09ES025 | Concrete resurfacing and rest area preservation on I-94 north of Fergus Falls to Grant County line | Pavement Improvement | 05/04/2009 | 05/11/2009 | 06/18/2010 | 8762711 | 9.293
3536 | Minnesota | MOWER |  | 1 | 09ES026 | Replace west bound exit ramp bridge on I-90 into Austin | Bridge Replacement | 07/17/2009 | 07/17/2009 | 09/01/2010 | 5171891 | 0
3537 | Minnesota | NICOLLET |  | 1 | 09ES029 | Replace utilities, reconstruct pavement and install signal and pedestrian crossing on state highway 169 in St. Peter | Pavement Improvement | 06/01/2009 | 06/01/2009 | 07/25/2010 | 16662468 | 0
3538 | Minnesota | JACKSON |  | 1 | 09ES031 | Parking lot and sidewalk improvements at two rest areas on I-90 near Jackson | Pavement Improvement | 09/11/2009 | 09/21/2009 | 09/27/2009 | 375919 | 0
3539 | Minnesota | CHIPPEWA |  | 7 | 09ES033 | Resurface Highway 7 from Montevideo to Clara City in Chippewa County | Pavement Improvement | 03/18/2009 | 05/01/2009 | 08/28/2009 | 9897248 | 15.496
3540 | Minnesota | STATEWIDE |  | 1,7 | 09ES034 | Guardrail replacement at various locations in Southwest Minnesota | Safety/Traffic Management | 06/30/2009 | 06/30/2009 | 06/30/2010 | 921855 | 0
3541 | Minnesota | REDWOOD |  | 7 | 09ES035 | Resurface Highway 68 from Milroy to Wabasso in Redwood County | Pavement Improvement | 03/11/2009 | 08/01/2009 | 11/02/2009 | 2219889 | 15.189
3542 | Minnesota | CHISAGO, ISANTI |  | 8 | 09ES036 | Remove and replace pavement on state highway 95 from east of Cambridge to the Isanti/Chisago County Line, including culvert replacement | Pavement Improvement | 03/11/2009 | 05/01/2009 | 08/07/2009 | 2771586 | 9.02
3543 | Minnesota | ST LOUIS | DULUTH-SUPERIOR (WI) | 8 | 09ES039 | Resurface Trunk Highway 194(Central Entrance) from 0.8 miles Northwest of Anderson Road to 0.3 Northwest of Mesaba Ave in the Duluth Heights neighborhood of Duluth | Pavement Improvement | 05/06/2009 | 05/26/2009 | 07/15/2009 | 1572086 | 0
3544 | Minnesota | ST LOUIS | DULUTH-SUPERIOR (WI) | 8 | 09ES040 | Roadway Resurfacing, curb & gutter removal and replacement, sidewalks, lighting and safety improvements on Highway 23 from 1100 ft East of 130th Street to 1515 ft North of County Road 3 (Becks Road) n | Pavement Improvement | 06/05/2009 | 06/15/2009 | 09/30/2009 | 4560000 | 0
3545 | Minnesota | ST LOUIS |  | 8 | 09ES041 | Pavement reconstruction of Trunk Highway (TH) 53 from 8.6 miles North of North Junction TH 194 to 2.2. miles North of TH 33 (Northbound) and 0.33 miles North of County State Aid Highway 8 Junction of | Pavement Improvement | 06/05/2009 | 06/11/2009 | 10/30/2009 | 12582156 | 0
3546 | Minnesota | STATEWIDE |  | 7,8 | 09ES042 | Rest area sign replacement at five locations on Highway 2 | Safety/Traffic Management | 06/01/2009 | 07/06/2009 | 08/28/2009 | 115825 | 0
3547 | Minnesota | ITASCA |  | 8 | 09ES043 | Resurfacing on 4.5 miles of Trunk Highway (TH) 2 west of Deer River from County State Aid Highway 18 to west of Trunk Highway 6 , and 12.5 miles of TH 6 north of Deer River to North of Junction TH 2 | Pavement Improvement | 04/16/2009 | 06/01/2009 | 10/30/2009 | 4031685 | 0
3548 | Minnesota | MILLE LACS |  | 8 | 09ES046 | Remove and replace pavement on state highway 169 from Rum River rest area to south of Onamia | Pavement Improvement | 04/08/2009 | 05/01/2009 | 07/24/2009 | 4788587 | 0
3549 | Minnesota | MILLE LACS |  | 8 | 09ES047 | Replace bridge on Highway 23 over the Rum River in Milaca | Bridge Replacement | 04/20/2009 | 06/01/2009 | 11/13/2009 | 1692300 | 0
3550 | Minnesota | ISANTI |  | 8 | 09ES048 | Replace bridge on Highway 95 over the Rum River 3.7 miles west of Cambridge | Bridge Replacement | 04/20/2009 | 05/01/2009 | 11/13/2009 | 1410631 | 0
3551 | Minnesota | KANABEC |  | 8 | 09ES049 | Remove and replace bridge on state highway 107 over the Snake River in Grasston | Bridge Replacement | 04/20/2009 | 06/01/2009 | 11/13/2009 | 1322178 | 0
3552 | Minnesota | STATEWIDE |  | 6,7,8 | 09ES050 | Improve road safety and operations by coordinating 85 traffic signals in Big Lake, Brainerd, Baxter, Elk River, Monticello, St. Cloud and St. Michael | Safety/Traffic Management | 08/26/2009 | 08/26/2009 | 04/27/2011 | 413094 | 0
3553 | Minnesota | DOUGLAS |  | 7 | 09ES052 | Install a traffic signal at I-94 and Trunk Highway 27 in Alexandria | Safety/Traffic Management | 04/10/2009 | 07/01/2009 | 09/07/2009 | 227909 | 0
3554 | Minnesota | OTTER TAIL |  | 7 | 09ES053 | Install a traffic signal at Trunk Highway 210 and Redwood Lane in Fergus Falls | Safety/Traffic Management | 08/19/2009 | 09/12/2009 | 10/28/2009 | 380084 | 0
3555 | Minnesota | WILKIN |  | 7 | 09ES054 | Install railroad gates and signals at Trunk Highway 9 west of Nashua | Safety/Traffic Management | 06/10/2009 | 08/03/2009 | 06/15/2010 | 115403 | 0
3556 | Minnesota | STEVENS |  | 7 | 09ES055 | Install railroad gates, signals cantilevers at Trnuk Highway 28 southwest of Morris | Safety/Traffic Management | 05/06/2009 | 08/03/2009 | 05/12/2010 | 263338 | 0
3557 | Minnesota | FARIBAULT, FREEBORN |  | 1 | 09ES059 | Remove and replace pavement on I-90 between Alden and state highway 22 | Pavement Improvement | 06/10/2009 | 06/16/2009 | 09/30/2009 | 3923374 | 0
3558 | Minnesota | ROCK |  | 1 | 09ES060 | Build new state entrance sign at the South Dakota border on I-90 at the Beaver Creek rest area | Transportation Enhancements | 04/28/2009 | 08/01/2009 | 10/01/2009 | 66806 | 0
3559 | Minnesota | MORRISON |  | 8 | 09ES061 | Plant living snow fence on Highway 371 in Crow Wing and Morrison Counties | Transportation Enhancements | 04/08/2009 | 05/01/2009 | 07/01/2009 | 119698 | 0
3560 | Minnesota | ST LOUIS | DULUTH-SUPERIOR (WI) | 8 | 09ES063 | Preserve the historic Aerial lift bridge over the Duluth Shipping Canal on Park Point, replacing lead based paint, structural steel and concrete elements | Transportation Enhancements | 08/14/2009 | 09/22/2009 | 03/20/2011 | 4900000 | 0
3561 | Minnesota | ST LOUIS | MINNEAPOLIS-ST. PAU, MN | 8 | 09ES064 | Resurfacing, curb and drainage repairs on the Rice Lake Road from Arrowhead Rd to Mesaba Ave in Duluth | Pavement Improvement | 07/21/2009 | 08/06/2009 | 09/18/2009 | 1178846 | 0
3562 | Minnesota | AITKIN |  | 8 | 09ES066 | Replace bridge on County Road 14 four miles northeast of Highway 65, north of McGregor in Aitkin County | Bridge Replacement | 06/18/2009 | 06/22/2009 | 10/23/2009 | 1180574 | 0
3563 | Minnesota | HUBBARD |  | 8 | 09ES067 | Replacement of bridge on County Road 9 over the Schoolcraft River, about 10 miles southwest of Bemidji in Hubbard County | Bridge Replacement | 07/01/2009 | 07/01/2009 | 10/16/2009 | 417899 | 0
3564 | Minnesota | KITTSON |  | 7 | 09ES068 | Replacement of bridge on County Road 1 over the North Branch of Two Rivers, five miles north of Hallock in Kittson County | Bridge Replacement | 06/16/2009 | 06/22/2009 | 11/01/2009 | 798863 | 0
3565 | Minnesota | BELTRAMI |  | 7 | 09ES069 | Rehabilitate surface, new curb and gutter, replace sewers and fix water lines on Irvine Ave from 3rd St. to State Hihway 197 in Bemidji | Pavement Improvement | 06/30/2009 | 07/06/2009 | 10/30/2009 | 1453986 | 0
3566 | Minnesota | MARSHALL |  | 7 | 09ES070 | 14 miles west of Grygla on County Road 7, replace bridge with a box culvert in Marshall County | Bridge Replacement | 06/03/2009 | 08/05/2009 | 08/15/2009 | 65353 | 0
3567 | Minnesota | MARSHALL |  | 7 | 09ES071 | Replace timber bridge on County Road 15 over the Snake River with two culverts, one half mile west of Warren in Marshall County | Bridge Replacement | 07/17/2009 | 08/03/2009 | 09/04/2009 | 537485 | 0
3568 | Minnesota | MORRISON |  | 8 | 09ES072 | Reconstruction of Lindbergh Drive from State Highway 27 to the North city limits in Little Falls | Pavement Improvement | 08/21/2009 | 08/24/2009 | 11/15/2009 | 894237 | 0
3569 | Minnesota | ISANTI |  | 8 | 09ES073 | Replace bridge on County Road 6 over Stanchfield Creek 6.8 miles west of Grandy in Isanti County | Bridge Replacement | 08/17/2009 | 08/24/2009 | 12/25/2009 | 369849 | 0
3570 | Minnesota | MORRISON |  | 8 | 09ES074 | Reconstruct 2 miles of County Road 203 beginning at State Highway 10 and add additional bituminous surface for another 2 miles of CountyRoad 203 to CountyRroad 2 in Morrision County, 6 miles south of | Pavement Improvement | 05/27/2009 | 06/15/2009 | 09/01/2009 | 626164 | 0
3571 | Minnesota | BECKER |  | 7 | 09ES075 | Replace existing bridge with three culverts on County Highway 7, 4 miles north of Lake Park in Becker County | Bridge Replacement | 08/31/2009 | 08/31/2009 | 09/09/2009 | 304089 | 0
3572 | Minnesota | DOUGLAS |  | 7 | 09ES076 | Resurface County Road 7 from the north city limits of Brandon to the south city limits of Millerville in Douglas County | Pavement Improvement | 05/29/2009 | 05/29/2009 | 07/31/2009 | 813899 | 0
3573 | Minnesota | SWIFT |  | 7 | 09ES077 | Replace bridge with two culverts on County Road 33 over Mud Creek, 1.3 miles NE of Murdock in Swift County | Bridge Replacement | 07/01/2009 | 07/13/2009 | 08/15/2009 | 244039.21 | 0
3574 | Minnesota | TRAVERSE |  | 7 | 09ES078 | Place 4 miles of asphalt pavement and gravel shoulders on County Road 6 from the South Dakota State line to Highway 75, 8 miles north of Wheaton in Traverse County | Pavement Improvement | 06/16/2009 | 06/18/2009 | 09/15/2009 | 1441828 | 0
3575 | Minnesota | STEELE |  | 1 | 09ES079 | Replace Cedar Ave. bridge over Maple Creek in Owatonna; also replace two railroad crossing signals | Pavement Improvement | 07/15/2009 | 08/04/2009 | 07/16/2010 | 1365638 | 0
3576 | Minnesota | GOODHUE |  | 2 | 09ES080 | Reconstruct 1.3 miles of County Highway 1 in Red Wing, includingbridge replacement, new pavement, drainage pipe replacement and new storm sewer in Goodhue County | Pavement Improvement | 06/09/2009 | 06/09/2009 | 11/30/2009 | 1784727 | 0
3577 | Minnesota | JACKSON |  | 1 | 09ES081 | Replace bridge on County Road 20 about 2 miles southwest of Okabena in Jackson County | Bridge Replacement | 07/16/2009 | 07/27/2009 | 10/02/2009 | 326354.34 | 0
3578 | Minnesota | WASECA |  | 1 | 09ES082 | Replace bridge on County Road 3 over the LeSueur River 7 miles south of Janesville in Waseca County | Bridge Replacement | 07/21/2009 | 07/23/2009 | 10/30/2009 | 609994 | 0
3579 | Minnesota | WASECA |  | 1 | 09ES083 | Replace bridge with culvert to carry Iosco Creek under County Road 3, about 5 miles northeast of Janesville in Waseca County | Bridge Replacement | 07/21/2009 | 09/22/2009 | 10/30/2009 | 328828 | 0
3580 | Minnesota | NOBLES |  | 1 | 09ES084 | Resurface 8 miles of County Road 1 from Brewster to Kinbrae in Nobles County | Pavement Improvement | 06/04/2009 | 08/24/2009 | 09/11/2009 | 1521461 | 0
3581 | Minnesota | BLUE EARTH |  | 1 | 09ES085 | Construct a new bridge on a new roadway on County Road 12 over the DM&E RR in east Mankato in Blue Earth County | New Bridge Construction | 08/19/2009 | 08/24/2009 | 07/06/2010 | 3073031 | 0
3582 | Minnesota | CHIPPEWA |  | 7 | 09ES086 | Replace bridge on County Road 32, 3.9 miles SE of the City of Milan in Chippewa County | Bridge Replacement | 06/08/2009 | 07/27/2009 | 09/24/2010 | 476489 | 0
3583 | Minnesota | LYON |  | 7 | 09ES087 | Replace bridge on County Road 3 over the south branch of the Yellow Medicine River, 2 miles south of Minneota in Lyon County | Bridge Replacement | 06/19/2009 | 06/24/2009 | 11/15/2009 | 308307 | 0
3584 | Minnesota | MCLEOD |  | 7 | 09ES088 | Replace timber bridge on County Road 7 over High Island County Road 4.3 miles south of Stewart in McLeod County | Bridge Replacement | 06/01/2009 | 06/15/2009 | 08/24/2009 | 323937 | 0
3585 | Minnesota | LINCOLN |  | 7 | 09ES089 | Resurface County Road 6 from South County Line to Highway 14, 3 miles south of Tyler; Resurface County Road 9 from County Road 1 to County Road 2, West of Verdi; Resurface County Road 11 from County R | Pavement Improvement | 05/21/2009 | 05/21/2009 | 06/12/2009 | 792678 | 0
3586 | Minnesota | RENVILLE |  | 7 | 09ES090 | Replace bridge on County Road 9 over Chetamba Creek in Renville County | Bridge Replacement | 06/24/2009 | 06/24/2009 | 09/30/2009 | 332117 | 0
3587 | Minnesota | YELLOW MEDICINE |  | 7 | 09ES091 | Replace bridge on County Road 3 over Lac Qui Parle River in Yellow Medicine County | Bridge Replacement | 06/10/2009 | 08/10/2009 | 08/21/2009 | 211809 | 0
3588 | Minnesota | ITASCA |  | 8 | 09ES092 | Complete reconstruction, including utilities, on 7th Ave SE from 17th St SE to 33rd St SE in Grand Rapids | Pavement Improvement | 06/03/2009 | 06/04/2009 | 07/15/2010 | 1498037 | 0
3589 | Minnesota | BELTRAMI |  | 8 | 09ES093 | Resurface 4.6 miles of County Road 23 two miles northwest of Tenstrike, pave shoulders and increase road strength in Beltrami County | Pavement Improvement | 06/18/2009 | 06/22/2009 | 07/10/2009 | 776124.27 | 0
3590 | Minnesota | CLEARWATER |  | 7 | 09ES094 | Resurfacing 9.6 miles of County Road 5 from Clearbrook to the Red Lake Reservation line in Clearwater County | Pavement Improvement | 06/19/2009 | 06/22/2009 | 07/09/2009 | 1257948 | 0
3591 | Minnesota | TODD |  | 7 | 09ES095 | Resurfacing on County Road 2 from Highway 28 to County Road 11 northeast of Sauk Center in Todd County | Pavement Improvement | 06/18/2009 | 06/25/2009 | 08/14/2009 | 872252 | 0
3592 | Minnesota | SHERBURNE |  | 6 | 09ES096 | Replace bridge on County Road 5 over St. Francis River 0.25 miles South of Sherburne County Road 3 | Bridge Replacement | 06/04/2009 | 06/04/2009 | 10/02/2009 | 469472 | 0
3593 | Minnesota | WRIGHT |  | 6 | 09ES097 | Reconstruction and widening including curb and gutter and recreational trail on Jamison Ave from County Road 119 to County Road 18 in St. Michael | Pavement Improvement | 06/22/2009 | 06/23/2009 | 07/16/2010 | 2136106 | 0
3594 | Minnesota | OTTER TAIL |  | 7 | 09ES098 | Resurface and add shoulders to County Road 1from Sophus Anderson Rd to County Road 10 east of Fergus Falls in Ottertail County | Pavement Improvement | 07/07/2009 | 07/07/2009 | 09/30/2009 | 1213957 | 0
3595 | Minnesota | OTTER TAIL |  | 7 | 09ES099 | Replace bridge over Otter Tail River on Concord Street in Fergus Falls | Bridge Replacement | 06/30/2009 | 07/06/2009 | 10/15/2009 | 776855 | 0
3596 | Minnesota | YELLOW MEDICINE |  | 7 | 09ES100 | Resurface County Road 8 from Highway 67 to County Road 5, 3 miles north of Clarkfield in Yellow Medicine County | Pavement Improvement | 06/03/2009 | 07/08/2009 | 09/18/2009 | 907552 | 0
3597 | Minnesota | KANDIYOHI, RENVILLE |  | 7 | 09ES101 | Resurface County Road 2, 1.37 miles south of County Road 77 to Highway 7 in Renville and Kandiyohi Counties | Pavement Improvement | 05/28/2009 | 06/30/2009 | 08/10/2010 | 2297109 | 0
3598 | Minnesota | ST LOUIS |  | 8 | 09ES103 | Resurfacing on St. Louis County Road 4 from Arrowhead Road to Martin Road in Duluth | Pavement Improvement | 06/26/2009 | 07/29/2009 | 10/09/2009 | 1895908 | 0
3599 | Minnesota | STEARNS |  | 6 | 09ES104 | Reconstruction and widening of Pinecone Rd in St. Cloud, adding lanes and two roundabouts | Pavement Improvement | 08/17/2009 | 08/20/2009 | 05/30/2010 | 1509238 | 0
3600 | Minnesota | STEARNS |  | 6 | 09ES105 | Extending 28th Ave from State Highway 23 to County Road 137 in the City of Waite Park | Pavement Improvement | 09/28/2009 | 09/28/2009 | 08/01/2010 | 2433666 | 0
3601 | Minnesota | OLMSTED | ROCHESTER | 1 | 09ES106 | Replace 4th Street bridge over Bear Creek in Rochester | Bridge Replacement | 08/17/2009 | 09/01/2009 | 10/15/2010 | 2810822 | 0
3602 | Minnesota | STATEWIDE |  | 8 | 09ES107 | Replace deteriorated landscaping at the state entry signs at the US/Canada border on Highway 61 near Grand Portage, and the Minnesota/Wisconsin border on I-535 and Highway 2 in Duluth | Transportation Enhancements | 04/16/2009 | 06/01/2009 | 11/15/2011 | 132579 | 0
3603 | Minnesota | FREEBORN |  | 1 | 09ES122 | Replacing landscaping around Entering and Leaving Minnesota Signs on I-35 at the Iowa Border near Albert Lea | Transportation Enhancements | 05/13/2009 | 08/01/2009 | 10/01/2009 | 60642 | 0
3604 | Minnesota | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 8 | 09ES124 | Plant living snow fence on I-35 at County Road 17 south of North Branch | Transportation Enhancements | 07/13/2009 | 09/14/2009 | 11/01/2010 | 79895 | 0
3605 | Minnesota | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 8 | 09ES125 | Remove and replace 7 miles of pavement on I-35 north of North Branch; repair drainage and replace lighting and pavement at the Goose Creek Rest Area | Pavement Improvement | 07/08/2009 | 07/09/2009 | 10/30/2009 | 9096643 | 0
3606 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 6 | 09ES126 | Reconstruct 1.5 miles of state highway 5 from south of state highway 36 to Manning Avenue. Drainage improvements were made through this section and west to I-694 | Pavement Improvement | 07/01/2009 | 08/04/2009 | 10/03/2009 | 2066476 | 0
3607 | Minnesota | DAKOTA, HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES127 | Replace lighting on Highway 100 from 50th in Edina to Excelsior Blvd. in St. Louis Park | Safety/Traffic Management | 04/24/2009 | 06/01/2009 | 05/20/2010 | 2296429 | 0
3608 | Minnesota | DAKOTA, STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES128 | Remove and replace 2 traffic signals on state highway 13 in Burnsville | Safety/Traffic Management | 05/22/2009 | 08/01/2009 | 11/06/2009 | 493780 | 0
3609 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES130 | Rebuild the cable median barrier on I-94 from I-494 in Maple Grove to the Crow River | Safety/Traffic Management | 04/24/2009 | 06/01/2009 | 09/07/2009 | 1239274 | 0
3610 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 6 | 09ES131 | Remove and replace 4.3 miles of pavement at the north junction of I-35E and I-35W, including extending a merge lane on I-35 | Pavement Improvement | 07/09/2009 | 08/03/2009 | 10/30/2009 | 6139952 | 0
3611 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES132 | Plant landscaping on I-494 from state highway 5 to I-394 | Other | 05/28/2009 | 08/01/2009 | 10/30/2012 | 573664 | 0
3612 | Minnesota | POLK |  | 7 | 09ES133 | Replace the bridge over the Red River and approaches on County Road 9 in Polk County | Bridge Replacement | 09/11/2009 | 09/11/2009 | 10/01/2010 | 6763057 | 0
3613 | Minnesota | CLAY | FARGO-MOORHEAD (ND) | 7 | 09ES135 | Restore landscaping at state entry sign in Moorhead | Transportation Enhancements | 06/04/2009 | 08/01/2009 | 10/19/2009 | 65879 | 0
3614 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES136 | Construct 3 miles of State Highway 610 from County Road 81 to State Highway 169 in Maple Grove and Brooklyn Park | Pavement Widening | 05/14/2009 | 08/01/2009 | 09/15/2011 | 28772763 | 0
3615 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,5,6 | 09ES137 | Remove and replace traffic signals and lighting on state highways and interstate throughout the twin cities region | Safety/Traffic Management | 05/27/2009 | 07/01/2009 | 12/28/2009 | 1927016 | 0
3616 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES138 | Add a traffic lane to the ramp from westbound I-494 to westbound state highway 212 | Pavement Improvement | 07/23/2009 | 08/17/2009 | 09/23/2009 | 1275463 | 0
3617 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES139 | Separate existing westbound and eastbound I-494 interchange ramps as they merge onto I-35E southbound | Safety/Traffic Management | 07/23/2009 | 08/07/2009 | 09/21/2009 | 836447 | 0
3618 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,5,6,8 | 09ES140 | Install Fiber Optic cable throughout the twin cities region on state highways and interstate | Safety/Traffic Management | 05/27/2009 | 08/01/2009 | 10/31/2010 | 1246688 | 0
3619 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,5,6,8 | 09ES141 | Install pavement markings throughout the twin cities region on state highways and interstate | Pavement Improvement | 05/27/2009 | 08/01/2009 | 11/15/2009 | 1140008 | 0
3620 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 5 | 09ES143 | Remove and replace lighting on state highway 169 from I-494 TO I-94 | Safety/Traffic Management | 05/27/2009 | 08/01/2009 | 06/19/2010 | 4525919 | 0
3621 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES145 | In Rosemount and Inver Grove Heights, resurface road and repair four bridges on 4 miles of Highway 52 from County Road 42 to Highway 55 in Dakota County | Pavement Improvement | 10/06/2009 | 10/13/2009 | 06/04/2010 | 3944447 | 0
3622 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 6 | 09ES146 | Remove and replace pavement on state highway 95 from Stillwater 16 to state highway 97 | Pavement Improvement | 08/25/2009 | 09/08/2009 | 06/04/2010 | 5145778 | 0
3623 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,5,6,8 | 09ES147 | Installation of changeable message signs in the Minneapolis-St. Paul Metro area | Safety/Traffic Management | 09/03/2009 | 09/09/2009 | 05/13/2010 | 1470917 | 0
3624 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4 | 09ES148 | Storm tunnel restoration on I-35E at Shepard Rd. in St. Paul | Pavement Improvement | 12/23/2009 | 01/04/2010 | 05/31/2010 | 1682848 | 0
3625 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES155 | Landscaping along I-94 from I-494 in Maple Grove to Brooklyn Blvd in Brooklyn Park, Hennepin County | Transportation Enhancements | 08/03/2009 | 08/03/2009 | 10/30/2012 | 210494 | 0
3626 | Minnesota | CARVER | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES156 | Landscape Highway 212 interchange at State Highway 101 and at Carver County Road 17 (Powers Blvd) in Chanhassen in Carver County | Transportation Enhancements | 08/03/2009 | 08/03/2009 | 06/15/2010 | 236776 | 0
3627 | Minnesota | CARVER | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES157 | Landscape Highway 212 interchange at Carver County Road 10 (Engler Blvd) and Carver County Road 11 in Chaska, Carver County | Transportation Enhancements | 08/03/2009 | 08/03/2009 | 06/15/2010 | 358078 | 0
3628 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES158 | Landscape Highway 212 at Hennepin County Road 4 and Dell Road in Eden Prairie, Hennepin County | Transportation Enhancements | 08/03/2009 | 08/03/2009 | 06/15/2010 | 201631 | 0
3629 | Minnesota | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 8 | 09ES159 | Reconstruct interchange of Highway 95 and I-35 in North Branch, Chisago County | Pavement Improvement | 11/16/2009 | 11/19/2009 | 06/20/2011 | 7375397 | 0
3630 | Minnesota | STATEWIDE |  | 2,4,5,6,8 | 09ES166 | Guardrail upgrades at various locations around the east Minneapolis-St. Paul Metro area | Safety/Traffic Management | 11/13/2009 |  | 07/17/2010 | 288884 | 0
3631 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES171 | Construct interchange at Highway 7 & Wooddale Avenue including pedestrian walkway & trail in St. Louis Park | New Bridge Construction | 09/25/2009 | 10/20/2009 | 11/01/2010 | 3465000 | 0
3632 | Minnesota | CLAY | FARGO-MOORHEAD (ND) | 7 | 09ES173 | Reconstruct 20th Street between 12th Ave S and 24th Ave S. replacing pavement, curb and gutter and storm sewer | Other | 08/26/2009 | 08/28/2009 | 11/13/2009 | 1098380 | 0
3633 | Minnesota | CLAY | FARGO-MOORHEAD (ND) | 7 | 09ES174 | Repair and repaint bridge over the Red River on Center Avenue in Moorhead | Bridge Improvement | 09/21/2009 | 10/05/2009 | 07/01/2010 | 909806 | 0
3634 | Minnesota | ST LOUIS |  | 8 | 09ES175 | Construct/Place Bituminous Surface on the Mesabi Trail system from the Giants Ridge recreation area near Biwabik to Trunk Highway 135. including pedestrian bridge 69675 over Narrows bewteen Sabin Lake | Transportation Enhancements | 12/18/2009 |  | 09/15/2010 | 1407835 | 0
3635 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES176 | Realign and widen County Road 10 from County Road 101 to West of Peony Lane in Maple Grove | Pavement Widening | 09/02/2009 | 09/03/2009 | 11/15/2010 | 3064000 | 0
3636 | Minnesota | SCOTT | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES179 | Constructing a paved surface on a new alignment for County Road 21 from County Road 42 in Prior Lake to County Road 16 in Shakopee in Scott County | Pavement Improvement | 11/12/2009 | 11/16/2009 | 07/20/2012 | 7324000 | 0
3637 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 5 | 10ES002 | Provide a wider pedestrian path from the Cedar Lake Bike Trail system to the new downtown Minneapolis ballpark | Transportation Enhancements | 11/05/2009 | 11/06/2009 | 05/15/2010 | 695067 | 0
3638 | Minnesota | CARVER | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES019 | Resurface four sections of county roads in Carver County: County Road 10 from CountyRoad 15 to Chaska Blvd, County Road 15 from County Road 10 to Wildwood Way, County Road 15 from Shadow Lane to 1110 | Pavement Improvement | 09/10/2009 | 11/01/2009 | 11/01/2009 | 856368 | 0
3639 | Minnesota | ANOKA | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES026 | Upgrade 56 existing signal systems in Coon Rapids, including new lenses, pedestrian lights with count down timers and revised pedestrian signs | Safety/Traffic Management | 10/07/2009 | 11/01/2009 | 03/01/2010 | 180000 | 0
3640 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES030 | Resurface Holyoke/Highview Ave from Heritage Drive to Dodd Blvd in Lakeville | Pavement Improvement | 10/06/2009 | 10/07/2009 | 08/01/2010 | 812122 | 0
3641 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 10ES035 | Reconstruct the pavement, improve and construct additional storm sewer, replace failing water main, complete spot repair of sanitary sewer, replace portions of curb and gutter and widen portions of ex | Pavement Improvement | 12/01/2009 |  | 07/22/2011 | 834000 | 0
3642 | Minnesota | DAKOTA |  | 2 | 10ES038 | Reconstruct Dakota County Road 96 from West of 11th Ave to State Highway 3, a rural 2-lane gravel road to a paved 2-lane roadway with paved shoulders and right turn lanes at intersections. This projec | Pavement Improvement | 10/19/2009 | 10/23/2009 | 08/01/2010 | 1677105 | 0
3643 | Minnesota | ST LOUIS |  | 8 | 10ES041 | Roadway resurfacing and drainage improvements on a 12.9 mile segment of Thunk Highway 2 ending 10 miles west of Duluth | Pavement Improvement | 09/29/2009 | 10/07/2009 | 07/15/2010 | 3677037 | 0
3644 | Minnesota | AITKIN |  | 8 | 10ES042 | Replace a deficient and deteriorated bridge located 3.5 miles north of Aitkin on County Highway 1in Aitkin County | Bridge Replacement | 11/18/2009 |  | 10/11/2010 | 869880 | 0
3645 | Minnesota | PINE |  | 8 | 10ES044 | Replace failed piers on closed St Croix Valley railroad bridge over Snake river in Pine County | Bridge Improvement | 10/05/2009 | 10/05/2009 | 01/31/2010 | 1030026 | 0
3646 | Minnesota | STATEWIDE |  | 3,4,6,7 | 10ES050 | Provide Commercial Drivers License training and certification for women and minorities | Other | 12/21/2009 | 12/15/2009 | 03/01/2010 | 286812 | 0
3647 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES071 | 1/4 mi N and S of the Progressive Rail crossing N of Cannon Falls on State Highway 52 - replace existing RR signals and add advance warning signs | Safety/Traffic Management | 11/23/2009 | 11/23/2009 | 12/30/2009 | 285193 | 0
3648 | Mississippi | ATTALA |  | 2 | 0004017 | "This project will resurface and extend the life of the pavement on two sites in Attala county. The first site 25.6 miles in length on Vaiden French Camp Road just south of French Camp and the other | Pavement Improvement | 07/20/2009 | 08/20/2009 | 01/06/2010 | 1183400 | 31
3649 | Mississippi | COPIAH |  | 2 | 0015029 | This project will resurface and extend the life of the pavement on Carter Hill Road from Old Port Gibson Road to Dentville Road and on Browns Wells Road from Sylvarena Road to 0.7 miles south of Highw | Pavement Improvement | 06/08/2009 | 06/08/2009 | 10/30/2009 | 456620 | 12.8
3650 | Mississippi | NOXUBEE |  | 3 | 0023071 | This project will resurface and extend the life of the pavement on US 45 from the Kemper County Line to Brooksville in Noxubee county. | Pavement Improvement | 04/10/2009 | 06/01/2009 | 07/06/2010 | 12702800 | 21.581
3651 | Mississippi | MONROE |  | 1 | 0025065 | This project will resurface and extend the life of the pavement for approximately 8 miles on US Highway 45 between New Wren and the Lee County Line, Monroe county. | Pavement Improvement | 07/09/2009 | 06/14/2009 | 03/30/2010 | 3656300 | 7.66
3652 | Mississippi | ALCORN |  | 1 | 0028014 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas on the Alcorn County Welcome Center, Alcorn county. | Transportation Enhancements | 10/08/2009 |  | 07/16/2010 | 186700 | 0
3653 | Mississippi | JACKSON | PASCAGOULA-MOSS POINT | 4 | 0031086 | This project will widen, add turn lanes and resurface US 90 from SR 57 to the West Pascagoula River Bridge in Jackson county. | Pavement Improvement | 08/06/2009 | 08/10/2009 | 08/31/2010 | 10799800 | 0
3654 | Mississippi | MARSHALL |  | 1 | 0047320 | This project will reconstruct and add new pavement for 0.9 miles on the Chickasaw Trail Industrial Park Access Road approx. 6 miles north of Byhalia, Marshall county. | Pavement Improvement | 11/23/2009 | 11/23/2009 | 05/17/2010 | 242645 | 1
3655 | Mississippi | PANOLA |  | 1 | 0054032 | This project will replace the bridge over McLvor Canal on Mt. Level Road in Panola county. This project is located approx. 4 miles west of Sardis. | Bridge Replacement | 07/02/2009 | 07/02/2009 | 12/22/2009 | 745300 | 0.2
3656 | Mississippi | PANOLA |  | 1 | 0054034 | This project will replace the bridge over Bobo Creek on Benson Herron Road 1.5 miles southwest from the town of Courtland, Panola county. | Bridge Replacement | 07/02/2009 | 07/02/2009 | 11/21/2009 | 297600 | 0.19
3657 | Mississippi | SHARKEY |  | 2 | 0063010 | This project will resurface various roads in the town of Anguilla, Sharkey county. | Pavement Improvement | 05/04/2009 | 05/05/2009 | 08/31/2009 | 102200 | 5.6
3658 | Mississippi | ITAWAMBA |  | 1 | 0063036 | This project will upgrade US 78 to interstate standards from the east end of the Tenn-Tom Bridge to the Alabama State Line. This includes shoulder paving, guardrail upgrade, rumble strips and fencing. | Pavement Improvement | 04/09/2009 | 04/20/2009 | 08/28/2009 | 4629100 | 13.667
3659 | Mississippi | LEE |  | 1 | 0063037 | This project will upgrade approximately 5 miles of US Highway 78 in Tupelo to interstate standards McCullough Boulevard @ Belden to US 45. This includes shoulder paving, guardrail upgrade, rumble stri | Pavement Improvement | 06/11/2009 | 06/26/2009 | 09/16/2009 | 3227900 | 5.259
3660 | Mississippi | TALLAHATCHIE |  | 2 | 0068100 | This project will resurface and extend the life of the pavement on 14 different roads in the town of Webb, Tallahatchie county: Main Street Extension, 5th Street, Deere Avenue, Plow Street, John Stree | Pavement Improvement | 08/20/2009 | 08/20/2009 | 10/29/2009 | 47000 | 2.9
3661 | Mississippi | ALCORN |  | 1 | 0071074 | This project will resurface and extend the life of the pavement for approximately 15 miles on US Highway 72 between the Tippah County Line and State Route 2, Alcorn county. | Pavement Improvement | 07/09/2009 | 08/07/2009 | 04/26/2010 | 6927600 | 15.47
3662 | Mississippi | COVINGTON |  | 3 | 0082093 | This project will resurface and extend the life of the pavement on approximately 18 miles of US Highway 49 northbound lanes from Seminary to the Simpson County Line in Covington county. | Pavement Improvement | 04/09/2009 | 04/20/2009 | 09/29/2009 | 4206800 | 17.6
3663 | Mississippi | SIMPSON |  | 3 | 0082094 | This project will resurface and extend the life of the pavement for approximately 6 miles of US Highway 49 beginning 15.9 miles north of the Covington county line then running north for 5.6 miles near | Pavement Improvement | 08/06/2009 | 08/13/2009 | 11/25/2009 | 2565500 | 5.6
3664 | Mississippi | SIMPSON |  | 3 | 0082095 | This project will resurface and extend the life of the pavement for approximately 16 miles on US Highway 49 beginning at the Covington county line and continuing north, Simpson county. Northbound lane | Pavement Improvement | 08/06/2009 | 09/04/2009 | 03/25/2010 | 3603900 | 15.9
3665 | Mississippi | YAZOO |  | 2 | 0084061 | This project will resurface and extend the life of the pavement on US Highway 49 between the Madison County Line and Bentonia in Yazoo county. | Pavement Improvement | 04/08/2009 | 05/12/2009 | 08/07/2009 | 2473900 | 4.95
3666 | Mississippi | LEFLORE |  | 2 | 0085028 | This project will resurface and extend the life of the pavement for approximately 11 miles on US 49 from US 82 to SR 8, Leflore County. | Pavement Improvement | 08/06/2009 | 08/06/2009 | 12/07/2009 | 4247400 | 0
3667 | Mississippi | LOWNDES |  | 1 | 0113076 | This project will resurface and extend the life of the pavement for approximately 9 miles on US Highway 82 between near Military Road in Columbus and the Alabama State Line, Lowndes county. | Pavement Improvement | 07/09/2009 | 07/20/2009 | 10/13/2009 | 3473000 | 0
3668 | Mississippi | PEARL RIVER |  | 4 | 0124040 | This project will replace four bridges over Hobolochito Creek on Burned Bridge-Pine Grove Road west of Picayune, Pearl River county. | Bridge Replacement | 08/24/2009 | 08/24/2009 | 04/06/2010 | 2199700 | 0.9
3669 | Mississippi | WALTHALL |  | 3 | 0142060 | This project will resurface and extend the life of the pavement on approximately 6 miles of U.S. Highway 98 between the Pike County Line and Tylertown in Walthall county. | Pavement Improvement | 04/09/2009 | 04/13/2009 | 08/12/2009 | 3174600 | 5.961
3670 | Mississippi | WALTHALL |  | 3 | 0142061 | This project will resurface and extend the life of the pavement on approximately 5 miles of US Highway 98 from the west end of the Tylertown bypass to the east end of the Tylertown bypass, Walthall co | Pavement Improvement | 06/11/2009 | 08/14/2009 | 09/02/2009 | 1809000 | 4.692
3671 | Mississippi | LAMAR |  | 4 | 0142063 | This project will resurface and improve the safety of US 98 from State Route 589 to Weathersby Road in Lamar county. | Pavement Improvement | 10/08/2009 | 11/03/2009 | 09/30/2010 | 7811200 | 0
3672 | Mississippi | ADAMS |  | 3 | 0151054 | This project will resurface and extend the life of the pavement on US 84 from US 61 Intersection to the Franklin county line, Adams county. | Pavement Improvement | 07/24/2009 | 07/30/2009 | 11/30/2009 | 4311200 | 10.04
3673 | Mississippi | ADAMS |  | 3 | 0151060 | This project will install aesthetic street and bridge lighting and traffic cameras on the bridge over the Mississippi River in Natchez in Adams county. | Transportation Enhancements | 07/09/2009 | 10/29/2009 | 04/30/2010 | 1702600 | 1
3674 | Mississippi | FRANKLIN |  | 3 | 0151063 | This project will resurface and extend the life of the pavement on approximately 8 miles of U.S. Hwy 84 west the Bude/Meadville By-Pass in Franklin county. | Pavement Improvement | 03/31/2009 | 04/28/2009 | 09/30/2009 | 4383300 | 8.719
3675 | Mississippi | BOLIVAR, SUNFLOWER |  | 2 | 0161029 | This project will construct 2 additional lanes on State Route 8 between Cleveland and Ruleville in Bolivar and Sunflower Counties. | Pavement Widening | 06/11/2009 | 06/19/2009 | 07/09/2010 | 8630000 | 0
3676 | Mississippi | BOLIVAR, SUNFLOWER |  | 2 | 0161033 | This project will resurface and extend the life of the pavement on State Route 8 from the Bolivar county Hospital to Ruleville, Bolivar and Sunflower county. | Pavement Improvement | 07/09/2009 | 08/06/2009 | 10/09/2009 | 2626200 | 0
3677 | Mississippi | AMITE, PIKE |  | 3 | 0168010 | This project will reconstruct the existing pavement, replace utilities, and improve safety on State Route 570 from .58 miles west of the Pike county line to the Pike county line and on State Route 570 | Pavement Improvement | 07/30/2009 | 08/26/2009 | 04/26/2011 | 6372500 | 0
3678 | Mississippi | JONES |  | 4 | 0221072 | This project will resurface and extend the life of the pavement approximately 2 miles in length on State Route 15 from 115th Street to Old Highway 15 in Laurel, Jones. | Pavement Improvement | 04/08/2009 | 04/09/2009 | 06/04/2009 | 1331400 | 4.466
3679 | Mississippi | CHICKASAW |  | 01 | 0223023 | This project will resurface and extend the life of the pavement for approximately 9 miles on State Route 15 between Houston and the Pontotoc county line, Chickasaw county. | Pavement Improvement | 07/09/2009 | 07/16/2009 | 09/25/2009 | 2571300 | 8.5
3680 | Mississippi | PERRY |  | 4 | 0224034 | This project will replace a bridge on State Route 29 over Black Creek in Perry county. | Bridge Improvement | 06/01/2009 | 06/01/2009 | 07/30/2010 | 4258100 | 0
3681 | Mississippi | ATTALA |  | 2 | 0232047 | This project will resurface and extend the life of the pavement on State Route 35 multilane section in Kosciusko from Natchez Trace Parkway to State Route 12, approximately 3 miles, Attala county. | Pavement Improvement | 09/10/2009 | 10/22/2009 | 02/26/2010 | 1342300 | 0
3682 | Mississippi | NEWTON, NESHOBA |  | 3 | 0261076 | This project will construct additional lanes on State Route 19 between the Lauderdale County Line and SR 492 in Newton and Neshoba county. | Pavement Widening | 04/06/2009 | 04/15/2009 | 02/01/2012 | 34406000 | 0
3683 | Mississippi | LINCOLN |  | 3 | 0275017 | This project will resurface, improve drainage, and extend the life of the pavement on approx. 7.2 miles of the Eddiceton-Caseyville Road in the Homochitto National Forrest located approx. ten miles we | Pavement Improvement | 11/09/2009 | 11/30/2009 | 02/24/2011 | 1668230 | 8
3684 | Mississippi | DE SOTO |  | 1 | 0311018 | This project will replace 4 bridges on MS Highway 305 from Cockrum to Lewisburg in Desoto county. | Bridge Replacement | 07/09/2009 | 07/09/2009 | 08/03/2011 | 7551300 | 1.33
3685 | Mississippi | JEFFERSON DAVIS |  | 2 | 0371051 | This project will resurface and extend the life of the pavement on State Route 13 from north of the Marion County Line to US 84, Jefferson Davis county. | Pavement Improvement | 07/09/2009 | 07/06/2009 | 09/30/2009 | 1749000 | 8
3686 | Mississippi | SIMPSON |  | 3 | 0392050 | This project will replace a bridge over the Middle Prong- Silver Creek on the Rockport-Shivers and Mount Zion Road 2.5 miles north of the Jefferson Davis/Simpson county line, Simpson County. | Bridge Replacement | 07/07/2009 | 08/07/2009 | 01/11/2010 | 525400 | 0.3
3687 | Mississippi | BOLIVAR |  | 2 | 0432015 | This project will resurface and extend the life of the pavement on approximately 11 miles of State Route 1 north of Rosedale in Bolivar county. | Pavement Improvement | 05/19/2009 | 05/21/2009 | 07/24/2009 | 3026300 | 9.69
3688 | Mississippi | COPIAH |  | 2 | 0541050 | This project will resurface and extend the life of the pavement on approximately 10 miles of State Route 27 north of Georgetown in Copiah county. | Pavement Improvement | 04/09/2009 | 04/28/2009 | 07/15/2009 | 3421000 | 10
3689 | Mississippi | COPIAH |  | 2 | 0551095 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Rest Area in Copiah County - North Bound Lanes. | Transportation Enhancements | 12/03/2009 | 12/03/2009 | 08/31/2010 | 760900 | 0
3690 | Mississippi | HOLMES |  | 2 | 0552210 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the rest area on I-55 Northbound north of Durant, Holmes county. | Transportation Enhancements | 10/01/2009 | 10/22/2009 | 06/30/2010 | 467600 | 0
3691 | Mississippi | CARROLL |  | 2 | 0553083 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Rest Area near Vaiden, Carroll county. | Transportation Enhancements | 10/08/2009 | 10/12/2009 | 07/12/2010 | 166000 | 0
3692 | Mississippi | DE SOTO |  | 1 | 0554091 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Desoto County Rest Area, Desoto county. | Transportation Enhancements | 12/03/2009 | 12/18/2009 |  | 498300 | 0
3693 | Mississippi | RANKIN |  | 3 | 0561068 | This project will resurface and extend the life of the pavement on State Route 25 from State Route 471 to State Route 43 in Rankin county. | Pavement Improvement | 04/10/2009 | 06/27/2009 | 05/07/2010 | 8833500 | 9.787
3694 | Mississippi | COAHOMA |  | 2 | 0571004 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the Delma Furniss Hospitality Station, Coahoma county. | Transportation Enhancements | 10/08/2009 | 10/14/2009 | 09/14/2010 | 263800 | 0
3695 | Mississippi | PEARL RIVER |  | 4 | 0591105 | This is a design build project which will add shoulders to 12 bridges on I-59 from the Louisiana state line to Poplarville, Pearl River County. | Bridge Improvement | 08/10/2009 | 10/20/2009 | 09/01/2010 | 10000000 | 0
3696 | Mississippi | LAUDERDALE |  | 3 | 0593084 | This project will build a new interchange at I-20/59 and Hawkins Rd. & 23rd Ave in Meridian in Lauderdale county. This project will add new pavement, street lights, and bridge construction. | New Construction | 07/09/2009 | 07/09/2009 | 07/29/2011 | 15311899 | 1.9
3697 | Mississippi | LAUDERDALE, NEWTON |  | 3 | 0593090 | This project is a design build project which will extend the I-59/I-20 merge lanes in Lauderdale county. Also, this project will add shoulders to 6 bridges on I-20 in Newton county. | Bridge Improvement | 10/21/2009 |  | 10/16/2010 | 9999999 | 0
3698 | Mississippi | WASHINGTON |  | 2 | 0622027 | This project will resurface and extend the life of the pavement for approximately 10 miles on State Route 438 from US 61 through Arcola to Highway 1, Washington county. | Pavement Improvement | 06/11/2009 | 06/17/2009 | 09/04/2009 | 2500800 | 9.572
3699 | Mississippi | WINSTON |  | 3 | 0679004 | This project will resurface and extend the life of the pavement on Ellison Ridge Road for approx 4 miles in length located 7 miles northeast of Noxapater, Winston county. | Pavement Improvement | 06/26/2009 | 07/09/2009 | 10/27/2009 | 409900 | 4.15
3700 | Mississippi | PANOLA |  | 1 | 0703016 | This project will resurface and extend the life of the pavement for approximately 11 miles on eastbound lanes for State Route 6 east of Batesville, Panola county. | Pavement Improvement | 08/04/2009 | 08/06/2009 | 12/14/2009 | 3227500 | 0
3701 | Mississippi | LAUDERDALE |  | 3 | 0741010 | This project will resurface and extend the life of the pavement on State Route 39 From I-20 to 52nd Street in Meridian, Lauderdale county. | Pavement Improvement | 07/09/2009 | 08/03/2009 | 11/24/2009 | 3867400 | 3.88
3702 | Mississippi | MONROE, CLAY |  | 1 | 0791029 | This project will resurface and extend the life of the pavement on US 45 Alternative from West Point to one mile north of State Route 25, Monroe and Clay county. | Pavement Improvement | 07/09/2009 | 07/14/2009 | 11/09/2009 | 4199800 | 0
3703 | Mississippi | LOWNDES |  | 1 | 0791030 | This project will resurface and extend the life of the pavement on US 45 Alternative from 9 miles north of the Noxubee County Line to the Clay county line, Lowndes county. | Pavement Improvement | 07/09/2009 | 08/03/2009 | 10/19/2009 | 2735100 | 6.57
3704 | Mississippi | MONROE, CHICKASAW |  | 1 | 0792015 | This project will resurface and extend the life of the pavement on approximately 9 miles of US 45 Alternative between State Route 8 and the northern Monroe county line, Monroe and Chickasaw county. | Pavement Improvement | 07/09/2009 | 07/29/2009 | 11/23/2009 | 4174300 | 0
3705 | Mississippi | LAFAYETTE |  | 1 | 0793002 | This project will replace a bridge on State Route 331 over Yocona River near State Route 334 in Lafayette county. | Bridge Replacement | 07/09/2009 | 07/09/2009 | 04/08/2011 | 3960000 | 0.92
3706 | Mississippi | FORREST | HATTIESBURG | 4 | 0801015 | This project will resurface and extend the life of the pavement on US 49 from Edwards St. to 31st. Avenue in Hattiesburg, Forrest county. | Pavement Improvement | 07/09/2009 | 07/10/2009 | 04/30/2010 | 8636900 | 5.819
3707 | Mississippi | TISHOMINGO |  | 1 | 0948008 | This project will resurface and extend the life of the pavement on State Route 365 from the Prentiss/Tishomingo County Line to US 72 in Tishomingo county | Pavement Improvement | 07/09/2009 | 07/03/2009 | 09/02/2009 | 1548700 | 6.55
3708 | Mississippi | PERRY |  | 4 | 1152001 | This project will replace the existing bridge on State Route 198 over Dickey Creek near Beaumont in Perry county. | Bridge Replacement | 07/09/2009 | 07/13/2009 | 03/31/2010 | 1469900 | 0.2
3709 | Mississippi | YALOBUSHA, CALHOUN |  | 1 | 2791008 | This project will replace 9 bridges on State Route 32 from Water Valley to State Route 330 in Yalobusha and Calhoun county. | Bridge Replacement | 08/06/2009 | 08/14/2009 | 09/26/2011 | 5923600 | 0
3710 | Mississippi | TATE |  | 1 | 2920001 | This project will construct two additional lanes on US 51 between Senatobia and Coldwater in Tate county. | New Construction | 10/08/2009 | 10/08/2009 | 02/01/2012 | 10497777 | 0
3711 | Mississippi | HINDS | JACKSON | 2 | 7314022 | This project will improve safety and traffic operations by installing a traffic signal installation at the intersection of US Hwy 80 and Shaw Road in Hinds county. | Safety/Traffic Management | 06/11/2009 | 09/08/2009 | 11/24/2009 | 134800 | 0
3712 | Mississippi | HINDS | JACKSON | 2 | 7314023 | This project will resurface and extend the life of the pavement on US 80 from Springridge Road to Terry Road, Hinds county. | Pavement Improvement | 07/09/2009 | 07/22/2009 | 11/24/2009 | 6478100 | 8
3713 | Mississippi | PIKE |  | 3 | 7570004 | This project will reconstruct the existing pavement and replace utilities and improve safety on State Route 570 from West limits of McComb East .9 miles in Pike county. | Pavement Improvement | 07/30/2009 | 08/26/2009 | 04/26/2011 | 1889000 | 0.87
3714 | Mississippi | LEE |  | 1 | 8193007 | The city of Tupelo will build a new bridge to extend Eason Boulevard over Town Creek and Kings Creek. | Bridge Improvement | 09/28/2009 | 10/19/2009 | 09/28/2010 | 1227688 | 0
3715 | Mississippi | MARSHALL |  | 1 | 9025100 | This project will add pavement to 2.1 miles of the North Holly Springs Industrial Bypass Road just north of Holly Springs. This project will make the road smoother and extend the life of the pavement. | New Construction | 09/28/2009 | 09/28/2009 | 06/16/2010 | 1637100 | 2.1
3716 | Missouri | CASS |  | 04 | 0021032 | This project consist of a thin lift asphalt overlay from Commercial Street to Route ZZ in Cass and Johnson counties | Pavement Improvement | 06/08/2009 | 07/29/2009 | 12/01/2009 | 504700 | 14.656
3717 | Missouri | CAMDEN |  | 04 | 0053053 | This project consist of widening Route 5 to three lanes through Sunrise Beach in Camden county | Pavement Widening | 06/15/2009 | 06/15/2009 | 05/28/2010 | 984700 | 0.9
3718 | Missouri | BENTON |  | 04 | 0072039 | This project consist of rehabilitation of bridges on Route 7 over Truman Lake (Osage Arm Bridge and Grand River Arm Bridge) in Benton county | Bridge Improvement | 06/15/2009 | 06/18/2009 | 10/15/2010 | 5026400 | 2
3719 | Missouri | PLATTE | KANSAS CITY (KS)-MO | 06 | 0091015 | This project consists of interchange improvements, building ramps and roundabout from SB Rte. 9 to Briarcliff in Clay county. | Pavement Improvement | 01/04/2010 |  | 11/01/2010 | 2500000 | 0.941
3720 | Missouri | PLATTE | KANSAS CITY (KS)-MO | 06 | 0091016 | This project consists of a bridge replacement on Route 9 over the White Aloe Branch in Platte county south of Route FF. | Bridge Replacement | 01/04/2010 |  | 10/01/2010 | 105000 | 0.113
3721 | Missouri | MONROE |  | 09 | 0151011 | This project consist of pavement and shoulder improvements from Route 154 north junction to 1.1 miles north of Route 22 in Monroe and Audrain counties | Pavement Improvement | 05/18/2009 | 09/15/2009 | 12/01/2009 | 2227800 | 24.572
3722 | Missouri | AUDRAIN |  | 09 | 0151012 | This project consist of pavement improvements from 1.1 miles north of Route 22 to 0.2 miles north of Route 54 in Audrain county | Pavement Improvement | 07/06/2009 | 08/18/2009 | 12/01/2009 | 880500 | 5.038
3723 | Missouri | TEXAS |  | 08 | 0171009 | This project consist of a thin lift asphalt overlay from Route 106 in Summersville to Route 60 in Mt. View in Texas and Howell counties | Pavement Improvement | 06/08/2009 | 07/09/2009 | 12/01/2009 | 564200 | 13.251
3724 | Missouri | HOWELL |  | 08 | 0171010 | This project consist of a thin lift asphalt overlay from Route 60 in Mt. View to Route 160 in Howel county | Pavement Improvement | 06/08/2009 | 07/08/2009 | 12/01/2009 | 860643 | 19.349
3725 | Missouri | MILLER |  | 09 | 0172010 | This project consist of replacement of bridge over the Osage River one mile east of Tuscumbia in Miller county, project involves bridge J0719 | Bridge Replacement | 02/17/2009 | 02/23/2009 | 10/01/2010 | 8277485 | 0.591
3726 | Missouri | MILLER |  | 04 | 0172011 | This project consist of a thin lift asphalt overlay from Route 54 to Brush Creek in Cole and Miller counties | Pavement Improvement | 06/08/2009 | 06/12/2009 | 12/01/2009 | 831600 | 19.266
3727 | Missouri | MONTGOMERY |  | 09 | 0194012 | This project consists of asphalt resurfacing from near Route B (just north of Montgomery City) to 1.7 miles south of Route I-70. | Pavement Improvement | 01/04/2010 |  | 12/01/2010 | 2140300 | 8.792
3728 | Missouri | WASHINGTON |  | 08 | 0211018 | This project consist of pavement improvements from 1.7 miles south of Route 8 in Potosi to Route N in Iron county | Pavement Improvement | 06/08/2009 | 06/24/2009 | 11/01/2009 | 2311900 | 21.247
3729 | Missouri | MARIES |  | 09 | 0281009 | This project consist of a thin lift asphalt overlay from Route 63 to Dixon in Maries and Pulaski counties | Pavement Improvement | 04/06/2009 | 06/09/2009 | 12/01/2009 | 815732.51 | 16.964
3730 | Missouri | PLATTE |  | 06 | 0291111 | This project consists of extensive pavement repair, hot in place recycle and asphalt resurfacing from Rte. 273 near Platte City for 18 miles (North and South) to Vivion Road, new rumble strip and pave | Pavement Improvement | 05/04/2009 | 05/18/2009 | 11/01/2009 | 11799300 | 34.857
3731 | Missouri | BUCHANAN |  | 06 | 0311005 | This project consist of a thin lift asphalt overlay from Route 36 to Route 169 in Buchanan county | Pavement Improvement | 07/06/2009 | 09/25/2009 | 10/01/2010 | 301800 | 6.222
3732 | Missouri | WAYNE |  | 08 | 0341035 | The project consists of adding shoulders, repaving, and several new alignments between Piedmont and Patterson. The alignment will change several curves and eliminate at least one 's' curve. A three | Pavement Widening | 11/17/2008 | 11/17/2008 | 12/01/2010 | 14105900 | 13.349
3733 | Missouri | CLINTON |  | 06 | 0352082 | This project consists of asphalt resurfacing on I-35 north of Shoal Creek to north of Route 116 near Lathrop. | Pavement Improvement | 02/17/2009 | 02/17/2009 | 12/15/2009 | 14156500 | 7.057
3734 | Missouri | LINN |  | 06 | 0362077 | This project consist of a thin lift asphalt overlay from Route 36 to Route 11 in Linn county | Pavement Improvement | 06/08/2009 | 08/06/2009 | 12/01/2009 | 172000 | 1.772
3735 | Missouri | LAWRENCE |  | 07 | 0391022 | This project consist of a thin lift asphalt overlay from Route 60 to 1.5 miles north of Route 248 in Barry and Lawrence county | Pavement Improvement | 04/06/2009 | 04/14/2009 | 12/01/2009 | 498500 | 12.113
3736 | Missouri | CARROLL |  | 04,06 | 0411003 | This project consist of pavement and shoulder improvements from Route 24 to Route 240 in Saline and Carroll counties | Pavement Improvement | 03/30/2009 | 03/30/2009 | 12/01/2009 | 1632900 | 17.68
3737 | Missouri | SALINE |  | 04 | 0411004 | This project consist of a thin lift asphalt overlay from Route 240 to Route TT in Saline county | Pavement Improvement | 03/30/2009 | 03/30/2009 | 12/01/2009 | 518300 | 10.268
3738 | Missouri | PHELPS |  | 08 | 0442223 | This project consist of major pavement rehabilitation/reconstruction on westbound lanes from Business Loop 44 (Rolla) to Sugartree Road Interchange in Phelps county | Pavement Improvement | 07/06/2009 | 09/08/2009 | 12/01/2009 | 11128700 | 8.213
3739 | Missouri | PULASKI |  | 04 | 0442224 | This project consist of an asphalt mill and fill from SP 44 to Route H/I-44 in St. Robert/Waynesville in Pulaski county | Pavement Improvement | 07/06/2009 | 10/16/2009 | 12/01/2009 | 865600 | 5.62
3740 | Missouri | CRAWFORD |  | 09 | 0443100 | This project consist of pavement rehabilitation on westbound lanes from 0.6 miles west of Route H to the Phelps County line in Crawford county | Pavement Improvement | 06/08/2009 | 09/21/2009 | 12/01/2009 | 897500 | 12.507
3741 | Missouri | FRANKLIN |  | 09 | 0443101 | This project consist of rebuilding of pavement from Viaduct Street to Route 100 West in Franklin county | Pavement Widening | 08/10/2009 | 08/21/2009 | 10/01/2010 | 17377500 | 5.072
3742 | Missouri | PLATTE |  | 06 | 0451025 | This project consist of a thin lift asphalt overlay from Route 273 to Spur 45 south in Platte county | Pavement Improvement | 06/08/2009 | 10/05/2009 | 12/01/2009 | 507200 | 11.89
3743 | Missouri | PERRY |  | 08 | 0512016 | This project consist of pavement improvements from I-55 to Route 72 in Perry and Bollinger counties | Pavement Improvement | 06/08/2009 | 06/24/2009 | 11/01/2009 | 1722800 | 16.297
3744 | Missouri | HENRY |  | 04 | 0521007 | This project consist of a thin lift asphalt overlay from the St. Clair county line to Route 13 in Henry county | Pavement Improvement | 06/08/2009 | 07/29/2009 | 12/01/2009 | 509600 | 15.143
3745 | Missouri | BATES |  | 04 | 0521008 | This project consist of a thin lift asphalt overlay from Route BB to 1.6 miles east of Route W in Bates county | Pavement Improvement | 06/08/2009 | 07/29/2009 | 12/01/2009 | 212200 | 5.268
3746 | Missouri | ST CLAIR |  | 04 | 0521009 | This project consist of a thin lift asphalt overlay from 1.0 miles west of Route P to 1.8 miles east of Route A in St. Clair county | Pavement Improvement | 06/08/2009 | 07/29/2009 | 12/01/2009 | 192400 | 4.741
3747 | Missouri | NEW MADRID |  | 08 | 0551134 | This project consist of pavement rehabilitation of north and south bound lanes from Route 84 to Scott county in New Madrid county | Pavement Improvement | 02/17/2009 | 05/12/2009 | 10/31/2010 | 15743400 | 46.834
3748 | Missouri | PEMISCOT |  | 08 | 0551135 | This project consist of pavement rehabilitation on the northbound lanes from the Arkansas state line to I-155 in Pemiscot county | Pavement Improvement | 06/08/2009 | 06/24/2009 | 07/30/2010 | 16085700 | 15.282
3749 | Missouri | NEW MADRID |  | 08 | 0551136 | The construction of a new Welcome Center on I-55 at Marston | Transportation Enhancements | 01/23/2009 | 01/23/2009 | 11/15/2010 | 5768950 | 0.3
3750 | Missouri | ATCHISON |  | 06 | 0591025 | This project consist of a thin lift asphalt overlay from the Iowa state line to Route 136 in Atchison county | Pavement Improvement | 06/08/2009 | 06/29/2009 | 12/01/2009 | 713200 | 9.908
3751 | Missouri | BARRY |  | 07 | 0601030 | The jobs combine to provide new surface and alternating passing lane improvements for 22 plus miles of a 25 mile stretch of Route 60 in Barry, Lawrence, Christian, and Greene Counties. As designed, J | Pavement Improvement | 02/17/2009 | 07/08/2009 | 11/01/2009 | 1820200 | 17.617
3752 | Missouri | BARRY |  | 07 | 0601031 | The jobs combine to provide new surface and alternating passing lane improvements for 22 plus miles of a 25 mile stretch of Route 60 in Barry, Lawrence, Christian, and Greene Counties. As designed, J | Pavement Improvement | 02/17/2009 | 07/08/2009 | 11/01/2009 | 6286450 | 15.894
3753 | Missouri | GREENE | SPRINGFIELD | 07 | 0602067 | This project consists of improvements at the James River Freeway and National Avenue interchange. | Pavement Widening | 09/23/2009 | 09/23/2009 | 12/01/2011 | 4569383 | 0.474
3754 | Missouri | CARTER |  | 08 | 0603095 | Van Buren sidewalk from Oliver to Alexander | Transportation Enhancements | 01/04/2010 |  | 05/14/2010 | 104800 | 0.098
3755 | Missouri | MISSISSIPPI |  | 08 | 0621022 | This project consist of a thin lift asphalt overlay from Route B in Bertrand to the City of Charleston in Mississippi county | Pavement Improvement | 06/08/2009 | 06/16/2009 | 12/01/2009 | 325700 | 5.856
3756 | Missouri | HOWELL |  | 08 | 0631029 | This project consist of an asphalt mill and fill from Route 63 North to Broadway in West Plains in Howell county | Pavement Improvement | 07/06/2009 | 10/28/2009 | 12/01/2009 | 506000 | 1.801
3757 | Missouri | ADAIR |  | 09 | 0634066 | This is the first in a series of two projects to construct an Alternate Route 63 around Kirksville Missouri. This project runs from the North edge of Kirksville to Route 6, just east of Kirksville. | New Construction | 08/03/2009 | 08/12/2009 | 08/01/2011 | 17433500 | 8.5
3758 | Missouri | GREENE |  | 07 | 0652063 | This project consist of widening route to six lanes from Business 65 (Chestnut Expressway) to Route D (Sunshine Street) in Greene County | Pavement Widening | 08/24/2009 | 08/24/2009 | 12/01/2011 | 8613400 | 2.027
3759 | Missouri | GREENE |  | 07 | 0652064 | This project consist of widening route to six lanes from Route D (Sunshine Street) to Route 60 (James River Freeway) in Greene County | Pavement Widening | 08/24/2009 | 08/24/2009 | 12/01/2011 | 4285116 | 3.466
3760 | Missouri | GREENE | SPRINGFIELD | 07 | 0652065 | This project consist of widening route to six lanes from Business 65 (Chestnut Expressway) to Route D (Sunshine Street) in Greene County | Pavement Widening | 08/24/2009 | 08/24/2009 | 12/01/2011 | 9701900 | 2.027
3761 | Missouri | BENTON |  | 04 | 0653088 | This project consist of rehabilitation of bridge on Route 65 over the Osge River near Warsaw in Benton county | Bridge Improvement | 06/15/2009 | 06/18/2009 | 10/15/2010 | 1497700 | 0.144
3762 | Missouri | ST LOUIS |  | 01 | 0673109 | This project consists of ADA sidwalk improvements from I-270 to Old St. Charles Rd and on Route AC from Route 67 (Lindbergh) to I-270 in St. Louis county | Transportation Enhancements | 09/08/2009 | 09/28/2009 | 05/01/2010 | 1667700 | 7.5
3763 | Missouri | CLAY |  | 06 | 0691013 | This project consist of a thin lift asphalt overlay from the Clinton county line to Route 92 in Clay county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 260300 | 6.017
3764 | Missouri | JACKSON |  | 04,05,06 | 0701179 | This project consist of constructing a new half diamond interchange at Route 40 - I435, replacement of Blue Ridge cut off bridge over I-70, add lanes to I-70, and modification to some ramps in Jackson | New Construction | 10/07/2009 | 10/07/2009 | 03/01/2012 | 30127600 | 5.437
3765 | Missouri | LAFAYETTE |  | 04 | 0702101 | This project consists of resurfacing of the roadway and shoulders on eastbound and westbound Interstate 70 from the Lafayette County line to Odessa. | Pavement Improvement | 05/04/2009 | 06/15/2009 | 12/01/2009 | 6861500 | 20.23
3766 | Missouri | COOPER |  | 06 | 0703217 | This project consist of pavement improvements on the westbound lanes from 0.3 miles east of Route B to the Saline county line in Cooper county | Pavement Improvement | 04/06/2009 | 06/12/2009 | 12/01/2009 | 7612000 | 17.1
3767 | Missouri | BOONE |  | 09 | 0703218 | This project consist of a thin lift asphalt overlay from Route 63 north connector to Route Z in Boone county | Pavement Improvement | 06/08/2009 | 08/10/2009 | 12/01/2009 | 290000 | 5.34
3768 | Missouri | ST LOUIS CITY |  | 01 | 0705314 | This project consist of pavement improvements from I-44/I-55 to Washington Ave. in St. Louis City | Pavement Improvement | 07/20/2009 | 07/20/2009 | 12/01/2009 | 5092700 | 0.57
3769 | Missouri | BARTON |  | 04 | 0712061 | This project consists of constructing a new interchange at Route 71 and 126. Work includes grading, asphalt pavement and new bridge. | New Construction | 06/22/2009 | 06/22/2009 | 10/01/2010 | 4516400 | 3.805
3770 | Missouri | BARTON |  | 04 | 0712062 | This project consists of constructing a new interchange at Route 71 and DD/EE. Work includes grading, asphalt pavement and new bridge. | New Construction | 07/06/2009 | 07/13/2009 | 10/01/2010 | 3667300 | 3.059
3771 | Missouri | BARTON |  | 04 | 0712063 | This project consists of constructing a new interchange at Route 71 and V/C. Work includes grading, asphalt pavement and new bridge. | New Construction | 07/06/2009 | 07/13/2009 | 10/01/2010 | 3681800 | 6.2
3772 | Missouri | BATES |  | 04 | 0713045 | This project consists of the construction of an overpass with on and off ramps at the junction of Highway 71 and Highway 52 East. Two other bridges will be built as part of this project. One will re | New Construction | 07/06/2009 | 08/18/2009 | 10/01/2010 | 5096700 | 2.904
3773 | Missouri | TANEY |  | 07 | 0761014 | This project consist of ADA sidewalk improvements from Roark Valley Road to Gretna (Branson) in Taney county | Transportation Enhancements | 07/27/2009 | 08/19/2009 | 12/01/2009 | 680200 | 2.864
3774 | Missouri | TANEY |  | 07 | 0761015 | This project consists of construction of a roundabout and new bridge over Lake Taneycomo. | New Bridge Construction | 06/23/2009 | 06/23/2009 | 07/01/2011 | 8170000 | 0.21
3775 | Missouri | BENTON |  | 04 | 0831001 | This project consist of rehabilitation of bridge on Route 83 over Truman Lake near Mockingbird Road in Benton county | Bridge Improvement | 06/15/2009 | 06/18/2009 | 10/15/2010 | 2399300 | 0.5
3776 | Missouri | NEWTON |  | 07 | 0861007 | This project consist of improvements on existing pavement and shoulders with the addition of rumble strips from Route P to 0.2 miles west of Route 71 in Newton county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 801000 | 9.952
3777 | Missouri | BARRY |  | 07 | 0861008 | This project consist of improvements on existing pavement and shoulders with the addition of rumble strips from Route F to 2.9 miles east of Route H in Barry county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 949700 | 11.596
3778 | Missouri | WEBSTER |  | 04 | 1045005 | This project consist of a thin lift asphalt overlay from Route 60 to south of railroad in Webster county | Pavement Improvement | 06/08/2009 | 09/09/2009 | 12/01/2009 | 28100 | 1.19
3779 | Missouri | CAPE GIRARDEAU |  | 08 | 1130006 | This project consist of rehabilitating pavement surface from I-55 to Kingshighway in Cape Girardeau county | Pavement Improvement | 07/06/2009 | 07/24/2009 | 08/14/2009 | 556600 | 1.703
3780 | Missouri | BUTLER |  | 08 | 1200003 | This project consist of a thin lift asphalt overlay from County Road 462 to Route 67 in Butler county | Pavement Improvement | 04/06/2009 | 06/09/2009 | 12/01/2009 | 362300 | 8.183
3781 | Missouri | RIPLEY |  | 08 | 1206005 | This project consist of a thin lift asphalt overlay from Route V west of Doniphan to Route 160 in Doniphan in Ripley county | Pavement Improvement | 04/06/2009 | 08/31/2009 | 12/01/2009 | 763700 | 14.548
3782 | Missouri | BUTLER |  | 08 | 1221003 | This project consist of a thin lift asphalt overlay from Route WW in Poplar Bluff to Route 158 in Butler county | Pavement Improvement | 04/06/2009 | 06/09/2009 | 12/01/2009 | 269215 | 5.628
3783 | Missouri | CAPE GIRARDEAU |  | 08 | 1277002 | This project consist of resurfacing and improving shoulders from Lasalle Ave to Lexington Ave. in Cape Girardeau county | Pavement Improvement | 11/09/2009 |  | 12/01/2010 | 2348100 | 4.2
3784 | Missouri | PEMISCOT |  | 08 | 1286003 | This project consist of a thin lift asphalt overlay from Route 164 to the Arkansas state line in Pemiscot county | Pavement Improvement | 05/08/2009 | 05/08/2009 | 12/01/2009 | 364910 | 6.465
3785 | Missouri | PEMISCOT |  | 08 | 1321002 | This project consist of a thin lift asphalt overlay from Route U to Route 164 in Pemiscot county | Pavement Improvement | 05/08/2009 | 05/08/2009 | 12/01/2009 | 467599 | 6.091
3786 | Missouri | HOLT |  | 06 | 1324003 | This project consist of a thin lift asphalt overlay on Spur 113 in Holt County from Route 113 to Route A and on Route A in Nodaway County from Spur 113 to Route 71 | Pavement Improvement | 07/06/2009 | 08/24/2009 | 07/01/2010 | 670300 | 11.702
3787 | Missouri | ATCHISON |  | 06 | 1361059 | This project involves painting, redeck and bridge repairs of the Missouri River brige at Brownville, NE | Bridge Improvement | 08/31/2009 | 08/31/2009 | 12/01/2011 | 4868280 | 0.6
3788 | Missouri | PUTNAM |  | 06 | 1362025 | This project consist of a thin lift asphalt overlay from Route 63 to Route N in Schuyler and Putnam counties | Pavement Improvement | 04/06/2009 | 04/10/2009 | 12/01/2009 | 842800.72 | 8.334
3789 | Missouri | ST LOUIS |  | 03 | 1411029 | This project consist of right of way acquisition to relocate and construct Route 141 from Route 40 to Route 340 (Olive Blvd). In cooperation with St. Louis County, construct Route 141 from Route 340 | New Construction | 08/19/2009 | 08/19/2009 | 03/01/2012 | 55036392.34 | 2.7
3790 | Missouri | ST LOUIS |  | 01,02,03 | 1411034 | This project consist of grading for the utility relocation at Route 340 in St. Louis county | Pavement Improvement | 09/08/2009 | 09/08/2009 | 05/01/2010 | 741600 | 0.5
3791 | Missouri | JACKSON |  | 04 | 1501010 | This project consists of grading, drainage and new concrete pavement to construct a divided 4 lane highway on Route 9 from Horridge Road to Route 291 in Lee's Summit. | Pavement Widening | 09/08/2009 | 09/08/2009 | 11/01/2011 | 14101900 | 3.426
3792 | Missouri | PEMISCOT |  | 08 | 1641008 | This project consist of a thin lift asphalt overlay from Route D to Route DD in Pemiscot county | Pavement Improvement | 05/08/2009 | 05/08/2009 | 12/01/2009 | 99362 | 1.725
3793 | Missouri | CLAY |  | 06 | 1691086 | A $1.1 million contract awarded to St. Joseph Fuel Oil & Manufacturing Company for two miles of sidewalk improvements. Included are new upgrades to the existing sidewalk and adding curb ramps to accom | Transportation Enhancements | 08/10/2009 | 08/10/2009 | 11/01/2009 | 1116700 | 2.023
3794 | Missouri | ANDREW |  | 06 | 1692021 | This project consist of pavement and shoulder improvements from Route 31 to I-29 in Dekalb, Andrew, and Buchanan counties | Pavement Improvement | 07/06/2009 | 09/25/2009 | 12/01/2009 | 2694300 | 21.438
3795 | Missouri | SALINE |  | 04 | 2401019 | This project consist of a thin lift asphalt overlay from east of Route 65 to Route 41 in Saline county | Pavement Improvement | 03/30/2009 | 03/30/2009 | 12/01/2009 | 74300 | 0.391
3796 | Missouri | HOWARD |  | 06 | 2401020 | This project consist of pavement and shoulder improvements from Route 5 to Route 40 in Howard county | Pavement Improvement | 06/08/2009 | 09/28/2009 | 12/01/2009 | 1047300 | 12.8
3797 | Missouri | STONE |  | 07,08 | 2651001 | This project consist of a thin lift asphalt overlay from Route 76 to Route 165 in Stone and Taney counties | Pavement Improvement | 04/06/2009 | 04/14/2009 | 12/01/2009 | 285500 | 5.364
3798 | Missouri | GREENE |  | 07 | 2661012 | This project consist of a thin lift asphalt overlay from Route AB to Farm Road 107 in Greene county | Pavement Improvement | 06/08/2009 | 07/14/2009 | 12/01/2009 | 62800 | 1.324
3799 | Missouri | ST CHARLES |  | 02 | 3641032 | This project consist of extending Page Ave. from 0.3 miles west of Harvester to 0.6 miles east of Central School Road at Woodstream in St. Charles county | New Construction | 10/05/2009 | 10/05/2009 | 09/30/2011 | 20570800 | 0.3
3800 | Missouri | ST CHARLES |  | 02 | 3641033 | This project consist of extending Page Ave. from 0.6 miles east of Central School Road at Woodstream to 0.3 miles wet of Central School Road in St. Charles county | New Construction | 10/05/2009 | 10/05/2009 | 09/30/2011 | 23240000 | 0.9
3801 | Missouri | STATEWIDE |  | Statewide | 4500205 | This project consist of cold in Place Recycling on various routes in Nodaway, Caldwell, Harrison, DeKalb, Daviess,Worth, Andrew and Gentry counties | Pavement Improvement | 06/08/2009 | 06/23/2009 | 10/01/2009 | 3490060 | 0
3802 | Missouri | FRANKLIN | ST. LOUIS (IL) | 09 | 6201602 | The City of Union has received additional funds for improvments on the Church Street project including sidewalks, paved approaches, curb and gutter, utility adjustments and retaining walls from Route | Transportation Enhancements | 05/04/2009 | 07/01/2009 | 08/01/2009 | 207932 | 1.2
3803 | Missouri | BOONE |  | 09 | 7401020 | This project consist of pavement improvements on westbound and eastbound lanes from Broadway to Route 63 in Boone county | Pavement Improvement | 07/13/2009 | 07/13/2009 | 10/05/2009 | 1682300 | 5.303
3804 | Missouri | STONE |  | 07 | 9900832 | In Gelena, the city will be doing sidewalk improvements around the square along 4th Street, Maple Street, and Main Street | Transportation Enhancements | 10/15/2009 | 11/01/2009 | 09/01/2010 | 227447.93 | 0.15
3805 | Missouri | OZARK |  | 08 | 9900840 | In Gainsville, the city will be doing sidewalk rehabilitation and construction near the square and along various city streets | Transportation Enhancements | 09/23/2009 | 09/23/2009 | 09/01/2010 | 113780 | 0.35
3806 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | 9900860 | This project will provide scoping and final design to improve safety and capacity of Route CC from Main Street in the City of Nixa to Route NN/J in the City of Ozark. | Other | 09/21/2009 | 09/28/2009 | 09/01/2010 | 900000 | 3.7
3807 | Missouri | BUCHANAN | ST. JOSEPH (KS) | 06 | ES01001 | This project consist of constructing a new truck staging area along Stockyard Expressway and intersections improvements in the St. Joseph Regional Port area | Pavement Widening | 07/17/2009 | 08/27/2009 | 11/01/2010 | 1300000 | 0
3808 | Missouri | NODAWAY |  | 06 | ES01002 | The City of Maryville will be constructing Phase A-II, which is a walking/biking trail located within the city limits of Maryville. This trail will be 3760 ft. in length and 6' to 8' in wide with a co | Transportation Enhancements | 09/11/2009 | 09/11/2009 | 07/01/2010 | 201900 | 0.712
3809 | Missouri | CHARITON |  | 06 | ES02002 | The City of Brunswick will be replacing existing sidewalks along Route 24 from Polk Street to Adams Street | Transportation Enhancements | 10/13/2009 | 10/14/2009 | 07/01/2010 | 348700 | 0.712
3810 | Missouri | WARREN |  | 09 | ES03002 | City will construct a new ADA (Americans with Disabilities Act) compliant sidewalk, which will provide connectivity of Marthasville?s ?Uptown? section to the ?Downtown? section. There will be replace | Transportation Enhancements | 09/23/2009 | 10/01/2009 | 07/31/2010 | 58028 | 0.15
3811 | Missouri | LEWIS |  | 09 | ES03003 | City will remove old, deteriorated existing sidewalks with safe new sidewalks, which will be constructed to American with Disabilities Act (ADA) Standards. The five-foot-wide sidewalk will connect th | Transportation Enhancements | 08/07/2009 | 08/07/2009 | 07/01/2010 | 70000 | 0.09
3812 | Missouri | PIKE |  | 09 | ES03004 | City will install historic/ornamental lighting in the downtown district. The new lighting will be in the vicinity of Lewis Street, Clark Street and 4th Street (State Route B) | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 07/01/2010 | 90000 | 0.4
3813 | Missouri | MONROE |  | 09 | ES03005 | The City of Paris will replace existing sidewalk with new sidewalk that will be constructed to American with Disabilities Act (ADA) Standards. There will also be the installation of historic lightin | Transportation Enhancements | 08/20/2009 | 08/20/2009 | 07/01/2010 | 88849.5 | 0.6
3814 | Missouri | MONTGOMERY |  | 09 | ES03007 | The City of Jonesburg proposes to remove 982 linear feet of existing sidewalk and construct 4? concrete sidewalk that will be constructed to American with Disabilities Act (ADA) Standards. The sidewa | Transportation Enhancements | 10/19/2009 | 10/19/2009 | 07/31/2010 | 79900 | 0.19
3815 | Missouri | CLAY | KANSAS CITY (KS)-MO | 06 | ES04001 | The City of Gladstone will be doing landscaping, decorative lighting, crosswalks and other scenic corridor improvements along North Oak Trafficway from NE 69th Street to NE 71st Street | Pavement Improvement | 09/21/2009 | 09/22/2009 | 08/01/2009 | 305097.35 | 1.51
3816 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 04,06 | ES04002 | The City of Blue Springs will be doing mill, asphalt overlay, and curb pavement markings at Adams Dairy Parkway from Duncan to Moreland School Road | Pavement Improvement | 10/20/2009 | 10/21/2009 | 08/01/2009 | 378061 | 0.4
3817 | Missouri | CLAY | KANSAS CITY (KS)-MO | 06 | ES04003 | The City of Liberty will be putting in additional curbs, lane width and improvements of medians of Kansas Street, Liberty Drive, and Mill Street | Pavement Improvement | 10/12/2009 | 10/13/2009 | 08/01/2009 | 378061 | 0.803
3818 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 06 | ES04007 | Jackson County will be replacing failing deck and upgrading guardrail system on Blue Mills Bridge | Bridge Improvement | 10/08/2009 |  | 12/01/2009 | 378061 | 0.049
3819 | Missouri | STATEWIDE | KANSAS CITY (KS)-MO | 04,05,06 | ES04016 | Signal retiming/synchronization, vehicle detection on creitical intersection, cameras added, Operation Green Light location expansion, new communication tower and upgrades to the wireless backbone. | Safety/Traffic Management | 08/26/2009 | 08/27/2009 | 01/01/2010 | 4195070.44 | 0
3820 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04019 | The City of Independence will be widening Jackson Drive from Holke Road to M-78 Highway from the existing 2 lanes to 4. There will also be installation of curb, gutter, sidewalk, and shared use path | Pavement Widening | 10/21/2009 |  | 08/01/2009 | 1066900.85 | 0.604
3821 | Missouri | STATEWIDE | KANSAS CITY (KS)-MO | 05,06 | ES04023 | A planning study to develop detailed transit implementation, phasing, and costing information to support expanded local, county, and retional service implementation. | Other | 08/12/2009 | 08/12/2009 | 08/01/2009 | 261250 | 0
3822 | Missouri | CLAY | KANSAS CITY (KS)-MO | 04 | ES04029 | The City of Gladstone will be doing mill and overlay work on Broadway from Englewood Road to north city limits | Transportation Enhancements | 09/21/2009 | 09/22/2009 | 12/01/2009 | 200000 | 0.25
3823 | Missouri | PLATTE |  | 04 | ES04032 | The City of Weston will be constructing new 5' wide sidewalks on 5th Street | Transportation Enhancements | 09/17/2009 | 09/17/2009 | 01/01/2010 | 61440 | 0.09
3824 | Missouri | LAFAYETTE |  | 04 | ES04034 | The City of Higginsville will be constructing new 5' wide sidewalks on Fairground Park/Grandview Elementary Sidewalks | Transportation Enhancements | 08/19/2009 | 08/19/2009 | 01/01/2010 | 142752.79 | 0.57
3825 | Missouri | HENRY |  | 04 | ES04035 | This project consist of sidewalk improvements on Route 18 from east of 9th Street to west of Pawnee Street in the City of Clinton | Transportation Enhancements | 09/11/2009 | 09/21/2009 |  | 129896.52 | 0.428
3826 | Missouri | CLAY |  | 04 | ES04036 | City of Kearney will be installing street lights, 5' sidewalks, fence handrail landscape along Main Street | Transportation Enhancements | 09/25/2009 | 09/25/2009 | 01/01/2010 | 100846 | 0.22
3827 | Missouri | BOONE | COLUMBIA | 09 | ES05003 | In Columbia, the city will be building a raiload bridge over Route 63 north of Route B in Boone county | Safety/Traffic Management | 08/14/2009 | 08/17/2009 | 10/01/2010 | 3329148.38 | 0.2
3828 | Missouri | FRANKLIN | ST. LOUIS (IL) | 01 | ES06001 | Goodfellow-Skinker Asphalt Overlay and Pedestrian Improvements . Design Study - Engineering Design Study -pedestrian facilities,streetscaping elements, and reconfiguration of the MO T / Front Street i | Other | 07/10/2009 | 07/10/2009 | 03/01/2010 | 327404.08 | 0.2
3829 | Missouri | FRANKLIN | ST. LOUIS (IL) | 09 | ES06002 | Franklin County will be doing a pedestrian/bike path along the west side of Route T from Great Oaks Drive to Labadie Elementary School | Transportation Enhancements | 07/10/2009 | 07/10/2009 | 10/01/2010 | 343864.17 | 0.6
3830 | Missouri | FRANKLIN | ST. LOUIS (IL) | 09 | ES06006 | The City of Washington will be doing asphalt resurfacing on various streets: W. Eighth Street, W. Main Street, Grand Avenue, Pottery Road, Old Route 100, Route 47 to Stafford Street | Pavement Improvement | 08/07/2009 | 08/07/2009 | 10/01/2009 | 683713.6 | 3
3831 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06007 | The City of Crystal City will be doing aphalt resurfacing on Crystal City Heights Road from Missouri Ave. to Commercial Blvd | Pavement Improvement | 08/19/2009 | 08/19/2009 | 10/01/2009 | 369778.1 | 1.4
3832 | Missouri | FRANKLIN | ST. LOUIS (IL) | 09 | ES06008 | Washington Special Road Distrct will be doning asphalt resurfacing on Bieker Road from S. Pointe Road to the Washington City limits. | Pavement Improvement | 08/27/2009 | 08/27/2009 | 11/01/2009 | 192368 | 4
3833 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06009 | Jefferson County will be doing asphalt resurfacing on Antire Road from High Ridge Blvd. to the St. Louis County line | Pavement Improvement | 12/15/2009 |  | 09/01/2009 | 311351.1 | 3.96
3834 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06011 | Jefferson County will be doing asphalt resurfacing on River Street Road from Route K to Route 61/67 | Pavement Improvement | 11/19/2009 | 11/23/2009 | 10/01/2009 | 67515.5 | 0.22
3835 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06015 | Festust Special Road District will be doing asphalt resurfacing on Scenic Dr., County Road, Cherry Ln., Scenic - Herculaneum city limits to Festus city limit, Cherry - Route Z to County Rd., County Ro | Pavement Improvement | 09/10/2009 | 09/10/2009 | 10/01/2010 | 481698.54 | 3
3836 | Missouri | ST CHARLES | ST. LOUIS (IL) | 09 | ES06018 | The City of Cottleville will be constructing a new traffice signal at Route N and Brittany Cove | Pavement Widening | 08/21/2009 | 08/21/2009 | 12/01/2010 | 172293.09 | 0.1
3837 | Missouri | ST CHARLES | ST. LOUIS (IL) | 09 | ES06019 | The City of O'Fallon will be doing asphalt Resurfacing on Main (Rte.M), Sonderen, East Pitman: Main St. (Rte. M) - I-70 to 3rd St., Sonderen - Wabash Ave. to I-70, East Pitman St. - Main St. to Sonde | Pavement Improvement | 09/01/2009 | 09/01/2009 | 10/01/2009 | 623575.63 | 1.32
3838 | Missouri | ST CHARLES | ST. LOUIS (IL) | 09 | ES06021 | St. Charles County will be installing a shared use lane on Route 94 from Defiance Road to Walnut Springs Road | Pavement Widening | 09/08/2009 | 09/08/2009 | 10/01/2010 | 430000 | 0.5
3839 | Missouri | ST LOUIS | ST. LOUIS (IL) | 02 | ES06023 | Great Streets Demonstration Project - Manchester Road - Rte. 141 to Rte. 109Engineering Planning and Design Study of entrances and exits and traffic flow. | Other | 09/08/2009 | 09/10/2009 | 03/01/2010 | 1100000 | 5
3840 | Missouri | ST LOUIS | ST. LOUIS (IL) | 01 | ES06024 | Engineering Design Study of Great Streets Demonstration Project - Natural Bridge Rd. - Lucas & Hunt Rd. to UMSL South Metrolink Station in Normandy | Other | 10/13/2009 | 10/19/2009 | 03/01/2010 | 998644.49 | 0.75
3841 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06025 | Great Streets Demostration Project on South Grand from Arsenel to McDonald in City of St. Louis to improve entrances and exits and traffic flow. | Other | 07/10/2009 | 07/10/2009 | 03/01/2010 | 890000 | 0.4
3842 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06026 | Grand Center/Grand Blvd. Streetscape- Lindell to Page Ave.Sidewalk improvements, new pedestrian signs, crosswalks and traffic calming | Pavement Widening | 08/12/2009 | 08/12/2009 | 05/01/2011 | 2000000 | 0.66
3843 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01,03 | ES06028 | St. Louis City will be doing streetscapes on Vandeventer Avenue, Kingshighway to Shaw; segment of Accomac. They will be adding pedestrian signal, solar powered lighting, and rain garden | Pavement Widening | 08/12/2009 | 08/12/2009 | 12/01/2010 | 778363 | 0.45
3844 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06029 | The Land Clearance for Development Authority for the City of St. Louis will be doing reconstruction, reconstruct and new construction of sidewalks, improved railroad crossings, signal improvements at | Pavement Widening | 07/29/2009 | 07/29/2009 | 07/01/2010 | 2800000 | 0.6
3845 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06033 | St. Louis City will be doing signal interconnect/Upgrade on Morgan Ford Road. This will consist of 11 signalized intersections from Arsenal Street to City limits. Interconneect traffic signals, signa | Safety/Traffic Management | 07/24/2009 | 07/24/2009 | 04/01/2011 | 2396627.57 | 3.74
3846 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06034 | The Land Clearance for Development Authority of the City of St. Louis will be doing mill/resurfacesurfacing and new curbs, bumpouts, sidewalks, ramps, lighting, and signals on North Sarah Street from | Pavement Improvement | 06/22/2009 | 06/22/2009 | 09/01/2010 | 1250000 | 0.26
3847 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06035 | St. Louis City will be doing overlay and pedestrian improvements on Good Fellow/Skinker. This will consist of asphalt mill and overlay, sidewalk improvements, new ADA compliant curb ramps, and stripin | Pavement Improvement | 08/12/2009 | 08/12/2009 | 07/01/2011 | 2575000 | 7.3
3848 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06036 | South Broadway Streetscape - Courtois to Upton St..Traffic calming measures, access management, new lighting, sidewalks | Pavement Widening | 08/12/2009 | 08/12/2009 | 03/01/2010 | 1220362.54 | 0.28
3849 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06040 | This project invovles the stabilization of the existing port muncipal dock at the St. Louis City Regional Port | Other | 09/23/2009 | 09/23/2009 | 12/01/2011 | 381683.05 | 0
3850 | Missouri | JASPER | JOPLIN | 07 | ES07002 | In Carl Junction, the city will be doing the design and construction of a pedestrian and bicycle trail from Briarbrook Drive to Copper Oaks Drive. The beginning of this project starts where the previ | Transportation Enhancements | 08/06/2009 | 08/06/2009 | 12/01/2009 | 175323 | 0.67
3851 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | ES08002 | In Ozark, the city will be doing surface improvements by paving the existing Frisco Highline Trail from Springfield to Willard | Transportation Enhancements | 12/11/2009 | 01/14/2010 | 01/01/2010 | 78087.65 | 0.2
3852 | Missouri | GREENE | SPRINGFIELD | 07 | ES08003 | This project includes the construction of sidewalks along Highway Z from the existing Frisco Highline trail to the Willard Recreation Center in the City of Willard. | Transportation Enhancements | 10/16/2009 | 10/19/2009 | 01/01/2010 | 79625 | 0.6
3853 | Missouri | GREENE | SPRINGFIELD | 07 | ES08004 | This project will pave an existing segment of the Frisco Highline Trail from Willard to 3 miles north of Springfield | Transportation Enhancements | 11/05/2009 | 11/06/2009 | 06/01/2010 | 186482 | 0
3854 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | ES08006 | This project will provide an analysis of existing and projected traffic in order to develop an efficient traffic plan on 3rd Street from Jackson St. to Church St. | Other | 09/08/2009 | 09/08/2009 | 09/01/2010 | 13188 | 0.2
3855 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | ES08007 | This project consists of a Transportation Planning Study to determine priority corridors and priority projects with some prelminary scoping of transportation projects within the boundaries of the City | Other | 09/23/2009 | 09/23/2009 | 09/01/2010 | 40000 | 0
3856 | Missouri | GREENE | SPRINGFIELD | 07 | ES08008 | In Battlefield, the city will be constructing sidewalks along Cloverdale from Elm North | Transportation Enhancements | 11/04/2009 | 11/30/2009 | 09/01/2010 | 55879 | 0
3857 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | ES08009 | This project will provide final design to improve safety and capacity at the intersection of Highway 160 & Highway 14 in the City of Nixa. | Other | 08/11/2009 | 08/25/2009 | 01/01/2010 | 119913 | 5.7
3858 | Missouri | PHELPS |  | 08 | ES09001 | The City of St. James will replace inadequate and unsafe sidewalk and extend sidewalk where none exists, along Highway 68 from the downtown south to the city limits and on east and west Scioto Streets | Transportation Enhancements | 12/12/2009 | 12/18/2009 | 01/12/2010 | 165354.3 | 0.75
3859 | Missouri | TEXAS |  | 08 | ES09002 | The City of Houston is constructing 1.1 miles of new five foot sidewalk along Airport Road, Lone Star Drive, and Westwood Drive on city owned property at the Houston Memorial Airport. The sidewalk is | Transportation Enhancements | 10/23/2009 | 11/12/2009 | 12/01/2009 | 142096.84 | 1.1
3860 | Missouri | CAPE GIRARDEAU |  | 08 | ES10001 | This project involves the construction of a high-water rail line that will allow port rail to operate during high-water events | Other | 11/16/2009 | 11/16/2009 | 07/01/2010 | 890960.02 | 0
3861 | Missouri | NEW MADRID |  | 08 | ES10002 | This project involves extending a rail spur to a site for a new tenant. This includes rail extension, switch, crossings, and siding. | Safety/Traffic Management | 09/30/2009 | 11/16/2009 | 07/01/2010 | 662888.2 | 0
3862 | Missouri | STE GENEVIEVE |  | 03 | ES10003 | This project involves construction of phase 1 on a new port, which involves excavation and site developments. | Other | 04/01/2009 | 04/01/2009 | 07/01/2010 | 931816.81 | 0
3863 | Missouri | LEWIS |  | 09 | FB03006 | This project involves port capital improvements. These improvements include making the existing road and staging area concrete, installing public restrooms and storage depot, and improving existing d | Other | 01/05/2010 | 01/05/2010 | 06/01/2011 | 21000 | 0
3864 | Missouri | STATEWIDE |  | 01 | FY09005 | The project is part of an ongoing program that is designed to increase participation among minorities, women and disadvantaged individuals in the highway construction workforce and train and prepare i | Other | 01/13/2010 | 01/13/2010 | 10/31/2010 | 145000 | 0
3865 | Missouri | BOONE |  | 09 | FY09006 | The project is part of an ongoing program that provides minorities, women and disadvantaged individuals the educational experiences to enhance work maturity skills, GED attainment, tools, equipment an | Other | 01/13/2010 | 01/13/2010 | 10/31/2010 | 190433.54 | 0
3866 | Missouri | ATCHISON |  | 06 | S001011 | This project consist of a thin lift asphalt overlay from Route 136 to I-29 in Atchison county | Pavement Improvement | 06/08/2009 | 06/29/2009 | 10/01/2009 | 267900 | 3.75
3867 | Missouri | NODAWAY |  | 06 | S004007 | This project consist of a thin lift asphalt overlay from Route 148 to Route E in Nodaway county | Pavement Improvement | 07/06/2009 | 08/24/2009 | 07/01/2010 | 376500 | 8.133
3868 | Missouri | ATCHISON |  | 06 | S007006 | This project consist of a thin lift asphalt overlay from Route C to Route 136 in Atchison county | Pavement Improvement | 06/08/2009 | 06/29/2009 | 10/01/2009 | 593200 | 9.881
3869 | Missouri | ANDREW |  | 06 | S029004 | This project consist of a thin lift asphalt overlay from Route 48 to Route E in Andrew county | Pavement Improvement | 07/06/2009 | 08/24/2009 | 07/01/2010 | 414900 | 7.984
3870 | Missouri | BUCHANAN |  | 06 | S058005 | This project consist of a thin lift asphalt overlay from Route 371 to Route MM in Buchanan county | Pavement Improvement | 07/06/2009 | 09/25/2009 | 07/01/2010 | 214300 | 4.036
3871 | Missouri | CLINTON |  | 06 | S067011 | This project consist of a thin lift asphalt overlay from Route 69 to Route H in Clinton county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 577500 | 11.022
3872 | Missouri | BUCHANAN |  | 06 | S083013 | "This project consists of concrete pavement repair to the existing concrete roadway and a 3-3/4"" asphalt overlay over the existing concrete roadway along with a 3-3/4"" asphalt overlay of the existin | Pavement Improvement | 08/10/2009 | 09/10/2009 | 12/01/2009 | 1937900 | 2.4
3873 | Missouri | LIVINGSTON |  | 06 | S111009 | This project consist of a thin lift asphalt overlay from the Daviess County line to Route 65 in Livingston county | Pavement Improvement | 06/08/2009 | 08/06/2009 | 11/01/2009 | 1218800 | 12.13
3874 | Missouri | MACON |  | 09 | S116007 | This project consist of a thin lift asphalt overlay from Route 63 to Route 156 in LaPlata in Macon county | Pavement Improvement | 04/06/2009 | 04/10/2009 | 12/01/2009 | 74654.59 | 0.916
3875 | Missouri | MACON |  | 09 | S124007 | This project consist of a thin lift asphalt overlay in Macon County from Route 63 to the Knox county line | Pavement Improvement | 04/06/2009 | 04/10/2009 | 12/01/2009 | 541918.62 | 8.989
3876 | Missouri | SCHUYLER |  | 06 | S189007 | This project consist of a thin lift asphalt overlay from the Iowa state line to Route 63 in Schuyler county | Pavement Improvement | 04/06/2009 | 04/10/2009 | 12/01/2009 | 547629.5 | 8.502
3877 | Missouri | MARION |  | 09 | S192003 | This project consist of a thin lift asphalt overlay on Route W from Route 61 north junction to Route 61 south junction, and Route 61 outer road from Route W to 0.3 miles south of Route W in Marion cou | Pavement Improvement | 04/06/2009 | 05/12/2009 | 12/01/2009 | 181500 | 3.378
3878 | Missouri | RANDOLPH |  | 09 | S205005 | This project consist of a thin lift asphalt overlay from Business Route 63 to Route B in Randolph county | Pavement Improvement | 06/08/2009 | 10/23/2009 | 12/01/2009 | 577200 | 9.56
3879 | Missouri | MONROE |  | 04 | S206007 | This project consist of a thin lift asphalt overlay from Route 24 to Route J in Ralls and Monroe counties | Pavement Improvement | 04/06/2009 | 05/12/2009 | 12/01/2009 | 231800 | 4.006
3880 | Missouri | SHELBY |  | 09 | S233005 | This project consist of a thin lift asphalt overlay from Business Route 36 to Route 24 in Shelby and Monroe counties | Pavement Improvement | 06/08/2009 | 10/23/2009 | 12/01/2009 | 1112200 | 22.13
3881 | Missouri | LINCOLN |  | 02 | S264004 | This project consist of a thin lift asphalt overlay from Old Route 61 to Route W in Lincoln county | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/01/2009 | 305400 | 6.361
3882 | Missouri | LINCOLN |  | 02 | S270004 | This project consist of a thin lift asphalt overlay from Route Y to Route 47 in Lincoln county | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/01/2009 | 262000 | 5.259
3883 | Missouri | PLATTE |  | 06 | S286005 | This project consist of pavement improvements on Route 273 from Route JJ to I-29 and Spur 92 from Route 273 to Route 92 in Platte county | Pavement Improvement | 06/08/2009 | 10/05/2009 | 12/01/2009 | 478800 | 4.907
3884 | Missouri | RALLS |  | 09 | S301018 | This project consist of a thin lift asphalt overlay from Route EE to Route 154 in Ralls county | Pavement Improvement | 04/06/2009 | 05/12/2009 | 12/01/2009 | 421400 | 7.713
3885 | Missouri | RALLS |  | 09 | S301019 | This project consist of a thin lift asphalt overlay from Route J to Route 19 in Ralls county | Pavement Improvement | 04/06/2009 | 05/12/2009 | 12/01/2009 | 252000 | 4.684
3886 | Missouri | CLAY |  | 06 | S304023 | A $1.2 million contract awarded to Musselman and Hall Contractors, LLC for nearly three miles of sidewalk improvements. Included are new upgrades to the existing sidewalk and adding curb ramps to acco | Transportation Enhancements | 08/10/2009 | 08/10/2009 | 11/01/2009 | 1220000 | 2.623
3887 | Missouri | STATEWIDE |  | 02 | S321005 | This project consist of a thin lift asphalt overlay from Route 47 to the Warren County line in Lincoln County, and from the Lincoln County line to I-70 north outer road in Warren county | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/01/2009 | 520900 | 11.537
3888 | Missouri | RAY |  | 04 | S349005 | This project consist of a thin lift asphalt overlay from Route C to Route 10 in Ray county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 206200 | 5.763
3889 | Missouri | RAY |  | 04 | S351005 | This project consist of a thin lift asphalt overlay from Route U to Route 10 in Ray county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 182000 | 5.117
3890 | Missouri | BOONE |  | 09 | S375003 | This project consist of a thin lift asphalt overlay from Route 124 to I-70 | Pavement Improvement | 06/08/2009 | 08/10/2009 | 12/01/2009 | 827600 | 19.186
3891 | Missouri | CALLOWAY |  | 09 | S383010 | This project will widen Route OO in Callaway couty to three lanes to add capacity and improve safty in holts Summit. | Pavement Widening | 09/15/2009 | 09/15/2009 | 12/01/2010 | 486100 | 0.841
3892 | Missouri | LAFAYETTE |  | 04 | S388005 | This project consist of a thin lift asphalt overlay from Gillespie Drive to Route O in LaFayette county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 437900 | 12.287
3893 | Missouri | WARREN |  | 09 | S429007 | This project consist of a thin lift asphalt overlay from Route T to Route 94 in Warren and St. Charles counties | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/01/2009 | 179700 | 3.5
3894 | Missouri | PETTIS |  | 04 | S434005 | This project consist of intersection improvements at Winchester Road in Sedalia in Pettis county | Pavement Improvement | 01/04/2010 |  | 12/01/2010 | 351800 | 0.3
3895 | Missouri | JOHNSON |  | 04 | S467005 | This project consist of pavement improvements from Route 50 to Route 2 in Johnson county | Pavement Improvement | 06/08/2009 | 08/18/2009 | 12/01/2009 | 1209700 | 16.143
3896 | Missouri | MONITEAU |  | 04 | S498006 | This project consist of pavement improvements from Route AA to Route 52 in Cole, Moniteau, and Morgan counties | Pavement Improvement | 05/26/2009 | 06/10/2009 | 12/01/2009 | 2054900 | 21.1
3897 | Missouri | MONITEAU |  | 04 | S579017 | This project consist of a thin lift asphalt overlay from Route O to Route C in Moniteau county | Pavement Improvement | 06/08/2009 | 06/12/2009 | 12/01/2009 | 485200 | 10.5
3898 | Missouri | ST FRANCOIS |  | 08 | S638004 | This project consist of a thin lift asphalt overlay from the Washington County line to the City of Bonne Terre in St. Francois county | Pavement Improvement | 06/08/2009 | 09/03/2009 | 12/01/2009 | 181075 | 5.219
3899 | Missouri | ST FRANCOIS |  | 08 | S638005 | This project consist of a thin lift asphalt overlay from the City of Bonne Terre to Route 67 in St. Francois county | Pavement Improvement | 06/08/2009 | 09/03/2009 | 12/01/2009 | 127500 | 1.788
3900 | Missouri | IRON |  | 08 | S670010 | Ironton sidewalk | Transportation Enhancements | 01/04/2010 |  | 06/01/2010 | 125000 | 0.282
3901 | Missouri | VERNON |  | 04 | S706003 | This project consist of a thin lift asphalt overlay from Route 54 to 0.9 mile north of Highland in Vernon county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 125000 | 2.377
3902 | Missouri | VERNON |  | 04 | S708004 | This project consist of a thin lift asphalt overlay from Business 71 to County Road 507 in Vernon county | Pavement Improvement | 04/20/2009 | 04/18/2009 | 12/01/2009 | 111700 | 2.489
3903 | Missouri | VERNON |  | 04 | S710009 | This project consist of a thin lift asphalt overlay from Route 54 to Route F in Vernon county | Pavement Improvement | 04/18/2009 | 04/20/2009 | 12/01/2009 | 275500 | 5.913
3904 | Missouri | POLK |  | 04 | S736004 | This project consist of a thin lift asphalt overlay from Route 123 to Route 13 in Polk county | Pavement Improvement | 06/08/2009 | 07/14/2009 | 12/01/2009 | 333600 | 10.9
3905 | Missouri | JASPER |  | 07 | S770004 | This project consist of a thin lift asphalt overlay from Route J to Route 66 in Jasper county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 211200 | 4.446
3906 | Missouri | JASPER |  | 07 | S776011 | This project consist of widening Route FF to include a center two-way left turn lane form US 71 to Prigmor Avenue in Jasper/Newton counties | Pavement Improvement | 08/03/2009 | 09/30/2009 | 11/01/2010 | 1924000 | 1.169
3907 | Missouri | JASPER | JOPLIN | 07 | S776012 | This project consists of constructing new signalized intersection and turn lanes on route FF, one mile east of Route 71. Work includes grading, asphalt pavement and new signals. | Pavement Improvement | 05/29/2009 | 05/29/2009 | 11/01/2010 | 1390617 | 0.2
3908 | Missouri | STE GENEVIEVE |  | 03 | S811005 | This project consist of a thin lift asphalt overlay from Route 51 to Route 61 in Ste. Genevieve and Perry counties | Pavement Improvement | 06/08/2009 | 09/03/2009 | 12/01/2009 | 329808 | 6.844
3909 | Missouri | JASPER |  | 07 | S853002 | This project consist of a thin lift asphalt overlay from Route Z to Route P in Jasper county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 172400 | 3.959
3910 | Missouri | GREENE |  | 07 | S938008 | This project consist of a thin lift asphalt overlay from Route AB to Route 160 in Greene county | Pavement Improvement | 06/08/2009 | 07/14/2009 | 12/01/2009 | 241700 | 5.417
3911 | Missouri | WEBSTER |  | 04 | S946008 | This project consist of a thin lift asphalt overlay from Route 60 to 1.0 mile west of Route FF in Webster county | Pavement Improvement | 06/08/2009 | 09/09/2009 | 12/01/2009 | 50800 | 1.78
3912 | Missouri | GREENE |  | 07 | S947011 | This project consist of a thin lift asphalt overlay from south of Route KK to north of Valley Water Mill Road in Greene county | Pavement Improvement | 06/08/2009 | 09/11/2009 | 12/01/2009 | 153900 | 3.857
3913 | Missouri | POLK |  | 04 | S947012 | This project consist of pavement and shoulder improvements from Route 32 to Route WW in Polk and Greene counties | Pavement Improvement | 06/08/2009 | 09/11/2009 | 12/01/2009 | 1273000 | 20.57
3914 | Missouri | GREENE |  | 07 | S953005 | This project consist of a thin lift asphalt overlay from Route 160 to Route 266 in Greene county | Pavement Improvement | 06/08/2009 | 07/14/2009 | 12/01/2009 | 289128.16 | 6.121
3915 | Missouri | WEBSTER |  | 04 | S967004 | This project consist of a thin lift asphalt overlay from Route AD to Business Route 60 in Webster county | Pavement Improvement | 06/08/2009 |  | 12/01/2009 | 162700 | 5.683
3916 | Montana | FLATHEAD |  | 00 | 0015090 | Construct New Bypass segment - US 93 to Airport Road | New Construction | 12/21/2009 | 12/28/2009 | 09/01/2011 | 8148323 | 0
3917 | Montana | FLATHEAD |  | 00 | 0015091 | Construct New Bypass segment - Airport Road to Foys Lake Road | New Construction | 11/30/2009 |  | 09/01/2011 | 5361624 | 0
3918 | Montana | FLATHEAD |  | 00 | 0015092 | Construct New Bypass segment - Foys Lake Road to US 2 | New Construction | 11/30/2009 |  | 09/01/2011 | 7780165 | 0
3919 | Montana | GALLATIN |  | 00 | 0016073 | Wetland mitigation in the NW quadrant of the I-90 East Main Street Interchange in Bozeman. | Other | 07/06/2009 | 08/03/2009 | 10/01/2009 | 296700 | 0
3920 | Montana | LEWIS AND CLARK |  | 00 | 0025050 | Reconstruction of existing Wylie Drive in Lewis & Clark County. | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 07/01/2010 | 1186274 | 0
3921 | Montana | TETON |  | 00 | 0032033 | Replacement of the US 89 Big Muddy Creek Bridge, North of Bynum | Bridge Replacement | 07/20/2009 | 09/10/2009 | 07/01/2010 | 2728753 | 0.4
3922 | Montana | GLACIER |  | 00 | 0034013 | Overlay, Slope Flattening & Widening on US 89 within the Blackfeet Reservation | Pavement Improvement | 07/06/2009 | 07/13/2009 | 07/01/2010 | 9884850 | 8.93
3923 | Montana | PARK |  | 00 | 0034026 | Off site wetland mitigation reserve for Watershed #13 - Upper Yellowstone in Park County | Other | 07/20/2009 | 09/09/2009 | 10/01/2009 | 375399 | 0
3924 | Montana | RAVALLI |  | 00 | 0071118 | Reconstruct and widen approximately 1.8 miles of US-93 near Stevensville | Pavement Widening | 08/12/2009 | 08/17/2009 | 07/01/2010 | 5493307 | 1.855
3925 | Montana | MADISON |  | 00 | 0131045 | Replacement of an existing irrigation siphon with a culvert on US 287 south of Cameron | Pavement Improvement | 10/05/2009 | 10/21/2009 | 08/01/2010 | 348911 | 0
3926 | Montana | LEWIS AND CLARK |  | 00 | 0154089 | I 15 Dearborn Rest Area Replacement | Safety/Traffic Management | 08/14/2009 | 01/08/2010 | 05/01/2011 | 4018300 | 0
3927 | Montana | CARTER |  | 00 | 0271009 | Bridge Replacement Project on MT 7 North of Ekalaka | Pavement Improvement | 08/03/2009 | 09/15/2009 | 09/01/2010 | 2301902 | 0
3928 | Montana | FALLON |  | 00 | 0272019 | Reconstruction of the existing roadway and structure work on MT 7 | Pavement Improvement | 09/21/2009 | 09/28/2009 | 10/01/2010 | 7255566 | 5.321
3929 | Montana | DANIELS |  | 00 | 0322016 | 14.2 mile chip seal on MT 13 in Daniels County north of Scoby | Pavement Improvement | 06/15/2009 | 06/29/2009 | 10/01/2009 | 518694 | 14.292
3930 | Montana | SHERIDAN |  | 00 | 0341009 | 15.3 mile overlay on MT 16 between Plentywood and the Port of Raymond in Sheridan County. | Pavement Improvement | 08/17/2009 |  | 10/01/2009 | 3022926 | 15.3
3931 | Montana | BIG HORN |  | 00 | 0371033 | Mill and fill 5.5 miles of US 212 in Big Horn County and within the Northern Cheyenne Reservation. | Pavement Improvement | 07/17/2009 | 07/21/2009 | 10/01/2009 | 2287646 | 5.58
3932 | Montana | ROSEBUD |  | 00 | 0391039 | 8.1 mile pavement preservation, minor widening & pavement marking/guardrail upgrade on MT 39 in Rosebud County, just north of the Northern Cheyenne Reservation. | Pavement Improvement | 06/08/2009 | 06/12/2009 | 09/01/2009 | 1905486 | 8.168
3933 | Montana | DAWSON |  | 00 | 0512004 | 9 mile overlay on MT 200 west of Richey, in Dawson County | Pavement Improvement | 06/22/2009 | 07/13/2009 | 08/01/2009 | 2306303 | 9.03
3934 | Montana | GALLATIN |  | 00 | 0861040 | 14.6 mile chip seal on MT 86 northeast of Bozeman in Gallatin County. | Pavement Improvement | 07/06/2009 | 07/13/2009 | 10/01/2009 | 899351 | 14.63
3935 | Montana | GALLATIN |  | 00 | 0906087 | Reconstruction of the I-90 East Three Forks Interchange | Pavement Improvement | 10/05/2009 | 10/19/2009 | 10/01/2010 | 3676814 | 0.265
3936 | Montana | SWEET GRASS |  | 00 | 0907089 | 5 mile mill and resurface of I 90 in Sweet Grass County | Pavement Improvement | 08/17/2009 |  | 10/01/2009 | 3205584 | 5.003
3937 | Montana | YELLOWSTONE | BILLINGS | 00 | 0908157 | Cold mill and overlay I -90 at the Pinehills Interchange and 3.2 miles to the west. | Pavement Improvement | 08/05/2009 | 08/08/2009 | 10/01/2009 | 1229277 | 3.285
3938 | Montana | YELLOWSTONE, BIG HORN |  | 00 | 0909098 | 13.3 mile full width overlay of I 90. Ramps will be cold milled and overlaid. The rest area parking lot will be crack sealed and s&c. | Pavement Improvement | 06/01/2009 | 08/13/2009 | 10/01/2009 | 8244422 | 13.3
3939 | Montana | CUSTER, ROSEBUD, DAWSON, WIBAUX |  | 00 | 0943059 | I 94 Bridge Deck Rehabilitation In Rosebud County | Bridge Improvement | 08/03/2009 | 08/10/2009 | 11/01/2010 | 5356486 | 0
3940 | Montana | WIBAUX |  | 00 | 0947028 | 6.2 mile mill and fill on I 94 east of Wibaux, in Wibaux County. | Pavement Improvement | 07/20/2009 | 07/21/2009 | 10/01/2009 | 1319731 | 6.298
3941 | Montana | YELLOWSTONE | BILLINGS | 00 | 1028004 | 1.4 mile overlay on Hardin Road in Billings | Pavement Improvement | 06/01/2009 | 06/26/2009 | 08/01/2009 | 556542 | 1.46
3942 | Montana | YELLOWSTONE | BILLINGS | 00 | 1031009 | Reconstruct an approximate 1.7 mile segment of Shilo Road from 2 lane to 4 lane - Billings | Pavement Widening | 06/01/2009 | 06/15/2009 | 08/01/2010 | 9301727 | 1.714
3943 | Montana | YELLOWSTONE | BILLINGS | 00 | 1031011 | Reconstruct the remaining 2.11 mile segment of Shiloh Road - Billings | Pavement Widening | 11/02/2009 | 11/13/2009 | 09/01/2010 | 5789636 | 2.117
3944 | Montana | SILVER BOW |  | 00 | 1806008 | 0.7 mile mill and fill on Front Street in Butte | Pavement Improvement | 06/22/2009 | 06/23/2009 | 08/01/2009 | 1380530 | 0.7
3945 | Montana | PHILLIPS |  | 00 | 2081006 | Reconstruction of 9.4 miles of Seconday 208 between Whitewater and US 191 | Pavement Improvement | 11/30/2009 |  | 11/01/2011 | 5943362 | 9.424
3946 | Montana | GALLATIN |  | 00 | 2351011 | Reconstruct existing State Secondary 235 east of MT 85 | Pavement Improvement | 10/05/2009 | 10/29/2009 | 11/01/2010 | 4924155 | 2.55
3947 | Montana | LINCOLN |  | 00 | 2601005 | 3.5 mile chip seal on S 260 north of Libby | Pavement Improvement | 07/06/2009 | 07/07/2009 | 07/01/2009 | 186403 | 3.5
3948 | Montana | GRANITE |  | 00 | 2711010 | 2.3 mile chip seal on S 271 northeast of Drummond in Powell County | Pavement Improvement | 06/29/2009 | 06/29/2009 | 08/01/2009 | 111165 | 2.3
3949 | Montana | LEWIS AND CLARK |  | 00 | 2791013 | Installing post mounted flashers at the intersection of S-279 & S 231 north of Helena | Safety/Traffic Management | 08/03/2009 | 08/20/2009 | 09/01/2009 | 34010 | 0.8
3950 | Montana | LEWIS AND CLARK |  | 00 | 2801019 | Installing post mounted flashers on York Road northeast of Helena | Safety/Traffic Management | 08/03/2009 | 08/20/2009 | 09/01/2009 | 30098 | 0.2
3951 | Montana | MEAGHER |  | 00 | 2941008 | Reconstruction of the roadway and structure work on State Secondary 294 | Pavement Improvement | 01/04/2010 |  | 08/01/2011 | 4001426 | 0
3952 | Montana | CARBON |  | 00 | 3081026 | 7.7 mile overlay on S-308 in Carbon County west of Belfry | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/01/2009 | 1343448 | 7.7
3953 | Montana | CARTER |  | 00 | 3231029 | Pave State Secondary 323 from RP 24.83 to 37.1 This is the section that is currently under contract with a total reconstruct to a all weather gravel surface. | Pavement Improvement | 07/06/2009 | 07/16/2009 | 07/01/2010 | 8652601 | 12.274
3954 | Montana | MISSOULA | MISSOULA | 00 | 3275813 | 2.6 mile seal and cover on a state highway west of Missoula. | Pavement Improvement | 07/06/2009 | 07/07/2009 | 08/01/2009 | 260040 | 2.6
3955 | Montana | STILLWATER |  | 00 | 4211004 | Reconstruction of the existing roadway and constructing bus turn arounds on State Secondary 421 7 km E. of Columbus | Pavement Improvement | 10/05/2009 | 10/23/2009 | 09/01/2011 | 3795714 | 2.732
3956 | Montana | FLATHEAD |  | 00 | 4241008 | 4.6 mile chip seal on S 424 west of Kalispell | Pavement Improvement | 06/29/2009 | 06/30/2009 | 08/01/2009 | 186479 | 4.61
3957 | Montana | LEWIS AND CLARK |  | 00 | 4301008 | Reconstruction of the existing roadway and structure work on Canyon Ferry Road | Pavement Improvement | 10/05/2009 | 10/09/2009 | 09/01/2011 | 7862308 | 4.2
3958 | Montana | FLATHEAD |  | 00 | 5031010 | 3.5 mile chip seal on S 503 southwest of Kalispell | Pavement Improvement | 06/29/2009 | 06/30/2009 | 08/01/2009 | 154610 | 3.5
3959 | Montana | MINERAL, MISSOULA |  | 00 | 5071008 | 2.4 mile mill and fill on S 507 east of Alberton, Missoula County | Pavement Improvement | 06/22/2009 | 07/22/2009 | 08/01/2009 | 460118 | 2.498
3960 | Montana | CASCADE | GREAT FALLS | 00 | 5205024 | 0.9 mile overlay on River Drive in Great Falls | Pavement Improvement | 07/20/2009 | 08/17/2009 | 10/01/2009 | 598282 | 0.94
3961 | Montana | CASCADE | GREAT FALLS | 00 | 5208002 | 0.7 mile overlay of Park Drive in Great Falls. | Pavement Improvement | 07/20/2009 | 08/10/2009 | 09/01/2009 | 355008 | 0.7
3962 | Montana | CASCADE | GREAT FALLS | 00 | 5209005 | 0.6 mile overlay of 6th Street in Great Falls. | Pavement Improvement | 07/20/2009 | 08/10/2009 | 09/01/2009 | 327122 | 0.61
3963 | Montana | CASCADE | GREAT FALLS | 00 | 5210018 | 0.18 mile mill and fill on 1st Avenue NW of River Drive in Great Falls | Pavement Improvement | 07/20/2009 | 08/17/2009 | 10/01/2009 | 355857 | 0.18
3964 | Montana | CASCADE | GREAT FALLS | 00 | 5299080 | Multiple Location sidewalk Improvment Project - Great Falls | Transportation Enhancements | 06/22/2009 | 07/06/2009 | 10/01/2009 | 1052700 | 0
3965 | Montana | CASCADE | GREAT FALLS | 00 | 5299081 | Phase 3 of a Multiple Location sidewalk Improvment Project - Great Falls | Transportation Enhancements | 09/14/2009 | 09/17/2009 | 05/01/2010 | 413691 | 0
3966 | Montana | CASCADE | GREAT FALLS | 00 | 5299086 | Construction of approx. 2300 ln ft of asphalt and concrete paths including fencing, drainage culverts, signing, striping and retaining wall in Great Falls. | Transportation Enhancements | 10/16/2009 | 10/16/2009 | 09/01/2010 | 361458 | 0
3967 | Montana | LEWIS AND CLARK |  | 00 | 5802012 | Widneing 1.09 mile segment of Custer Avenue in Helena | Pavement Improvement | 07/06/2009 | 08/03/2009 | 08/01/2009 | 675340 | 1.09
3968 | Montana | LEWIS AND CLARK |  | 00 | 5805013 | 0.3 mile mill and fill on Benton Ave in Helena | Pavement Improvement | 06/29/2009 | 06/29/2009 | 08/01/2009 | 242918 | 0.3
3969 | Montana | LEWIS AND CLARK |  | 00 | 5822002 | 0.83 mile overlay on Hauser Blvd in Helena | Pavement Improvement | 06/29/2009 | 06/29/2009 | 08/01/2009 | 383990 | 0.83
3970 | Montana | YELLOWSTONE |  | 00 | 6905002 | Reconstruct the existing 8th Ave Roadway in Laurel | Pavement Improvement | 11/16/2009 | 01/22/2010 | 08/01/2010 | 2798134 | 0.64
3971 | Montana | PARK |  | 00 | 7406007 | 0.7 mile mill and fill on Chinook and Gallatin Street in Livingston | Pavement Improvement | 06/15/2009 | 06/18/2009 | 08/01/2009 | 225500 | 0.71
3972 | Montana | MISSOULA | MISSOULA | 00 | 8105014 | 0.8 mile mill and fill on Russell Street in Missoula | Pavement Improvement | 06/01/2009 | 06/15/2009 | 07/01/2009 | 150745 | 0.8
3973 | Montana | MISSOULA | MISSOULA | 00 | 8107019 | 0.17 mile mill and fill on Orange Street in Missoula | Pavement Improvement | 06/01/2009 | 06/15/2009 | 07/01/2009 | 84399 | 0.173
3974 | Montana | MISSOULA | MISSOULA | 00 | 8109002 | On the Scott Street overpass in Missoula, Bridge deck repair and replacing the surface with a high strength epoxy concrete. | Bridge Improvement | 07/13/2009 | 07/22/2009 | 11/01/2009 | 1939051 | 0
3975 | Montana | MISSOULA | MISSOULA | 00 | 8113006 | 0.3 mile mill and fill on Higgins Street in Missoula | Pavement Improvement | 06/01/2009 | 06/15/2009 | 07/01/2009 | 119570 | 0.34
3976 | Montana | MISSOULA | MISSOULA | 00 | 8117006 | Higgins/Hill/Beckwith Intersection & Signal Improvement in Missoula | Pavement Improvement | 06/15/2009 | 06/17/2009 | 08/01/2009 | 689800 | 0
3977 | Montana | MISSOULA | MISSOULA | 00 | 8120005 | 2 mile mill and fill on South Avenue in Missoula | Pavement Improvement | 06/01/2009 | 06/15/2009 | 07/01/2009 | 627174 | 2
3978 | Montana | BLAINE |  | 00 | 9003032 | Replacement of an off system bridge & approaches in Blaine County. | Bridge Replacement | 06/22/2009 | 07/10/2009 | 05/01/2010 | 2402036 | 0
3979 | Montana | BLAINE |  | 00 | 9003039 | Bridge Replacement 7 KM west of Harlem | Bridge Replacement | 01/04/2010 |  | 07/01/2011 | 2546147 | 0
3980 | Montana | DEER LODGE |  | 00 | 9012131 | Replace existing structure over the Clark Fork, 2 KM East of Warm Springs | Bridge Replacement | 11/02/2009 |  | 10/01/2010 | 399726 | 0
3981 | Montana | FALLON |  | 00 | 9013015 | Off-system Bridge Replacement Project North West of Baker in Fallon County | Pavement Improvement | 08/03/2009 | 09/15/2009 | 09/01/2010 | 684245 | 0
3982 | Nebraska | DODGE |  | 1 | 0027052 | This project will replace existing street lights located on Main Street from 5th to 1st Streets with historic replica lighting in Fremont. | Transportation Enhancements | 01/15/2010 |  | 10/30/2010 | 132804 | 0
3983 | Nebraska | ADAMS |  | 3 | 0064125 | 12.1 miles of asphalt resurfacing and bridge repair west of Hastings, including the spurs to Juniata and the Hastings Regional Center. | Pavement Improvement | 05/07/2009 | 05/14/2009 | 11/28/2009 | 3665228 | 9.86
3984 | Nebraska | PLATTE |  | 3 | 0071030 | This project will construct a 10-foot-wide concrete pedestrian and bicycle trail approximately one mile in length, connecting the existing Wilderness Park Trail and the Robert Bob White Trail on the o | Transportation Enhancements | 11/19/2009 |  | 06/19/2010 | 325863 | 0
3985 | Nebraska | BUFFALO |  | 3 | 0102115 | This resurfacing project will bring this roadway to a state of good repair. It will address pavement deficiencies with an asphalt overlay. | Pavement Improvement | 09/22/2009 |  | 10/30/2010 | 1321101 | 10
3986 | Nebraska | HALL |  | 3 | 0112116 | This project provides for installation of landscaping along Highway N-11 along the Loup River Scenic Byway. It includes landscape areas in the downtown corridor (2.5 blocks); and a 20-foot wide lands | Transportation Enhancements | 01/27/2010 |  | 05/29/2010 | 149078 | 0
3987 | Nebraska | JEFFERSON |  | 3 | 0151113 | Replacement of 2 deficient bridges south of Fairbury on N-15. The structure at reference post 3.07 is over a stream. The second structure at R.P 4.53 is over Rose Creek. | Bridge Replacement | 05/04/2009 | 05/18/2009 | 04/30/2011 | 2966171 | 0
3988 | Nebraska | HOLT |  | 3 | 0204117 | The project consists of resurfacing the existing 24 foot roadway and 8 foot surfaced shoulders of US-20 just southeast of the city of O'Neill and continue southeast 5.14 miles. The project will mill 4 | Pavement Improvement | 11/25/2009 |  | 10/30/2010 | 1459958 | 5.02
3989 | Nebraska | ANTELOPE |  | 3 | 0205111 | The project consists of resurfacing the existing 24 foot roadway and 8 foot surfaced shoulders of US-20 from Royal to Plainview and for a short length on S-2B. The project along US-20 will mill off f | Pavement Improvement | 12/11/2009 |  | 10/30/2010 | 5274390 | 14.15
3990 | Nebraska | PHELPS |  | 3 | 0233105 | Asphalt resurfacing of the 6.96 miles of N-23 between Loomis and Holdrege. The existing 4' shoulders will be widened to 6' with 2' being surfaced. | Pavement Improvement | 07/17/2009 | 09/08/2009 | 08/05/2010 | 2594512 | 6.96
3991 | Nebraska | BUFFALO |  | 3 | 0304148 | This project is on US-30 from Avenue B to Avenue E and from Avenue I to Avenue L in the city of Kearney. The existing narrorw raised median will be widened to 15 feet to accommodate turn lanes. To acc | Pavement Improvement | 06/08/2009 | 07/13/2009 | 07/01/2010 | 2318659 | 0.22
3992 | Nebraska | MADISON |  | 1 | 0325106 | "Improvements of this project east of Madison will include the vertical realignment of N-32 at the bridge over Union Creek at R.P. 36.73, which will be replaced along with raising the highway grade 9 | Bridge Replacement | 09/23/2009 |  | 11/13/2010 | 3643201 | 0.74
3993 | Nebraska | HALL |  | 3 | 0344131 | "This project is located on US-34 and US-281 just south of and in the city of Grand Island. It extends from just north of the I-80 interchange to just south of Capital Avenue for a total lenth of 8.33 | Pavement Improvement | 06/03/2009 | 07/13/2009 | 07/01/2010 | 6504399 | 5.06
3994 | Nebraska | LANCASTER | LINCOLN | 1 | 0346139 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement, bridge and guardrail deficiencies with an asphalt overlay, bridge repair and new guardrail. | Pavement Improvement | 07/13/2009 | 07/27/2009 | 06/19/2010 | 2049649 | 2.49
3995 | Nebraska | DAKOTA |  | 1 | 0354118 | This bridge replacement project will bring this roadway to a state of good repair. It will replace two deficient bridges and rehabilitate another bridge. | Bridge Replacement | 06/03/2009 | 06/22/2009 | 10/01/2010 | 1944384 | 0
3996 | Nebraska | OTOE |  | 1 | 0502128 | This resurfacing and bridge project will bring this roadway to a state of good repair. It will improve safety by eliminating surface and bridge deficiencies through an asphalt overlay and bridge reha | Pavement Improvement | 03/25/2009 | 03/31/2009 | 07/31/2010 | 4907360 | 9.46
3997 | Nebraska | VALLEY |  | 3 | 0704107 | This project is located on N-70 near Arcadia. The existing 275' bridge with a 28' roadway will be widened and rehabilitated with a new south span and new superstructure. The rehabilitated bridge will | Bridge Improvement | 05/11/2009 | 05/18/2009 | 08/21/2010 | 1717017 | 0
3998 | Nebraska | KIMBALL |  | 3 | 0712109 | This resurfacing project will bring this roadway to a state of good repair by providing a new, wider driving surface. | Pavement Improvement | 06/03/2009 | 06/29/2009 | 11/21/2009 | 4633135 | 14.86
3999 | Nebraska | DEUEL |  | 3 | 0802090 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies through an asphalt overlay. | Pavement Improvement | 05/04/2009 | 06/15/2009 | 07/24/2010 | 6943834 | 9.82
4000 | Nebraska | CHEYENNE |  | 3 | 0802093 | This rehabilitation and restoration project will bring this roadway to a state of good repair. It will extend the life and improve the surface condition of the existing pavement. | Pavement Improvement | 05/11/2009 | 06/15/2009 | 09/30/2009 | 1380504 | 24.85
4001 | Nebraska | DEUEL |  | 3 | 0803119 | The improvements on this project will consist of concrete pavement repairs to the existing dual 24' roadway, plus the 3' inside and 10' outside shoulders. The existing inside shoulders and roadway wil | Pavement Improvement | 12/02/2009 |  | 10/30/2010 | 4074809 | 4.22
4002 | Nebraska | KEITH |  | 3 | 0803135 | This project rehabilitates Interstate 80 between the Brule and Ogallala interchanges by milling the surface and placing new asphaltic concrete. | Pavement Improvement | 12/17/2009 |  | 10/09/2010 | 4149433 | 0
4003 | Nebraska | KEITH |  | 3 | 0803139 | This project rehabilitates Interstate 80 between the Ogallala and Roscoe interchanges by milling the surface and placing new asphaltic concrete. | Pavement Improvement | 01/20/2010 |  | 08/28/2010 | 3465321 | 0
4004 | Nebraska | LINCOLN |  | 3 | 0804104 | This rehabilitation project will bring this roadway to a state of good repair, by preserving the structure (the interchange over I-80) and providing an improved driving surface. | Bridge Improvement | 03/23/2009 | 05/18/2009 | 09/16/2009 | 1315548 | 0
4005 | Nebraska | DAWSON |  | 3 | 0804129 | This rehabilitation project will bring this roadway to a state of good repair, by preserving the structure (the interchange over I-80) and providing an improved driving surface. | Bridge Improvement | 04/28/2009 | 06/08/2009 | 10/04/2009 | 1050940 | 0
4006 | Nebraska | LINCOLN |  | 3 | 0804133 | This restoration and rehabilitation project will bring this roadway to a state of good repair. It will extend the life and improve the surface condition of the existing pavement. | Pavement Improvement | 07/23/2009 | 09/08/2009 | 07/23/2010 | 1743733 | 5.87
4007 | Nebraska | DAWSON |  | 3 | 0805069 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 03/25/2009 | 06/15/2009 | 10/10/2009 | 6670500 | 10.49
4008 | Nebraska | HALL |  | 3 | 0806097 | This project will resurface 11.61 miles of I-80 between the Wood River and West Grand Island Interchanges. Improvements consist of joint repair, pavement repair, milling and resurfacing with asphalt a | Pavement Improvement | 06/08/2009 | 07/06/2009 | 06/26/2010 | 5255421 | 11.63
4009 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 0809889 | This reconstruction project will bring this roadway to a state of good repair and will improve the level of service (traffic flow). This expansion of I-80 on the Nebraska side is occurring in conjunct | Pavement Widening | 07/09/2009 | 08/10/2009 | 06/01/2012 | 16486652 | 2.23
4010 | Nebraska | YORK |  | 3 | 0812142 | The project begins 0.6 miles north of US-34 north of York and continues 7.2 miles north, including 0.6 miles at the S-93 junction. It consists of asphaltic concrete resurfacing of the roadway and shou | Pavement Improvement | 01/06/2010 |  | 10/30/2010 | 2712263 | 0
4011 | Nebraska | THOMAS |  | 3 | 0833106 | This bridge project will bring this roadway to a state of good repair and will improve mobility and safety, by eliminating existing at-grade rail and highway crossings (over the BNSF RR) in close prox | Bridge Replacement | 04/01/2009 | 05/04/2009 | 07/12/2010 | 6943648 | 1.66
4012 | Nebraska | CHERRY |  | 3 | 0834113 | The scope of this project consists of resurfacing US Highway 83 (US-83) for approximately 10 miles. The project will be milled and constructed using 4 inches of High RAP Base which contains a high Rec | Pavement Improvement | 11/25/2009 |  | 10/02/2010 | 3442996 | 10.05
4013 | Nebraska | LOUP |  | 3 | 0913107 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 06/08/2009 | 08/24/2009 | 10/31/2009 | 2135795 | 8.47
4014 | Nebraska | PLATTE |  | 3 | 0915121 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 05/14/2009 | 06/01/2009 | 09/10/2009 | 3745305 | 11.95
4015 | Nebraska | COLFAX |  | 1 | 0916111 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 05/14/2009 | 06/22/2009 | 08/31/2009 | 2395806 | 16.71
4016 | Nebraska | DIXON |  | 1 | 1164102 | This bridge replacement project will bring this roadway to a state of good repair. It is replacing a 52-year old structure. | Bridge Replacement | 05/04/2009 | 05/18/2009 | 10/31/2009 | 372654 | 0
4017 | Nebraska | THAYER |  | 3 | 1365111 | Milling and asphalt resurfacing of 4.2 miles of US-136 from 1.7 miles west of Gilead to the Thayer/Jefferson county line. | Pavement Improvement | 03/25/2009 | 06/03/2009 | 07/21/2009 | 1635326 | 5.02
4018 | Nebraska | GAGE |  | 1 | 1366116 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 04/29/2009 | 06/25/2009 | 10/31/2009 | 3304415 | 9.41
4019 | Nebraska | JEFFERSON |  | 3 | 1366118 | This project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 03/25/2009 | 06/19/2009 | 08/22/2009 | 2878863 | 8.1
4020 | Nebraska | NEMAHA |  | 1 | 1367122 | This bridge rehabilitation project will bring this roadway to a state of good repair. It will extend the life and improve the safety of the existing bridge by repairing and rehabilitating the structu | Bridge Improvement | 10/05/2009 | 08/31/2009 | 12/01/2011 | 3245529 | 0
4021 | Nebraska | FRONTIER |  | 3 | 1575003 | This project is on a county road 9.5 miles south and 9.0 miles east of Stockville, continuing north 3.1 miles. It consists of an asphalt resurfacing of the 22' roadway and rehabilitation of the 4' ear | Pavement Improvement | 01/25/2010 |  | 10/30/2010 | 932064 | 0
4022 | Nebraska | HOLT |  | 3 | 2280005 | Replace a deficient bridge on a county road 14.2 miles east of O'Neill, crossing the middle branch of Verdigris Creek with a twin 9' x 8' x 88' concrete box culvert. | Pavement Improvement | 01/25/2010 |  | 06/19/2010 | 294744 | 0
4023 | Nebraska | HOLT |  | 3 | 2814118 | The scope of this project consists of resurfacing the existing 24' asphalt roadway and 8' surfaced shoulders of US-281 near the city of O'Neill (approximately 7.5 miles in length). The project will m | Pavement Improvement | 11/25/2009 |  | 10/09/2010 | 2276268 | 7.41
4024 | Nebraska | JEFFERSON |  | 3 | 3005008 | This project consists of a 3 inch asphaltic concrete overlay of an existing bituminous road. The project includes earth shoulder construction to match the pavement rise along both sides of the road. T | Pavement Improvement | 01/07/2010 |  | 10/30/2010 | 756007 | 0
4025 | Nebraska | GAGE |  | 1 | 3265004 | New 30' x 28' concrete slab bridge over Plum Creek 0.7 miles south of Barneston. | Bridge Replacement | 01/26/2010 |  | 11/27/2010 | 781430 | 0
4026 | Nebraska | SAUNDERS |  | 1 | 3430006 | The project is the replacement of a deficient bridge with a triple 16' x 16' x 18' concrete box culvert. It is located on a county road (Highway Avenue) on the southern edge of Prague, crossing Cotton | Bridge Replacement | 02/03/2010 |  | 11/27/2010 | 511336 | 0
4027 | Nebraska | BOX BUTTE |  | 3 | 3854129 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 04/29/2009 | 08/10/2009 | 10/31/2009 | 3139546 | 7.91
4028 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 4809776 | This is a new 311' x 58' bridge on US-75 southbound over 30th St. and the exit ramps in Omaha. | Bridge Replacement | 08/19/2009 | 08/31/2009 | 06/11/2011 | 1680143 | 0
4029 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 4809777 | Rehabilitation of the I-480 183' x 72' steel girder bridge over 24th St. in Omaha | Bridge Improvement | 08/19/2009 | 08/31/2009 | 06/11/2011 | 1600854 | 0
4030 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 4809778 | This project is the reconstruction of the I-480 / US-75 southbound interchange in Omaha. Work consists of grading, mechanically stabilized earth walls, culverts, three bridge removals, guardrail, fenc | Pavement Improvement | 08/19/2009 | 08/31/2009 | 06/11/2011 | 13146340 | 0.88
4031 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 4809787 | This project is the widening and rehabilitiation of the southbound US-75 bridge over Burt St. and Cuming St. in Omaha. The new structure will be 532' long and 58' wide. | Bridge Improvement | 08/19/2009 | 08/31/2009 | 06/11/2011 | 3262610 | 0
4032 | Nebraska | LANCASTER | LINCOLN | 1 | 5220003 | Asphalt resurfacing on A Street between 63rd St. and Imperial Drive and on Van Dorn St. from Normal Blvd. to 70th St. in Lincoln. | Pavement Improvement | 01/26/2010 |  | 09/30/2010 | 661017 | 0
4033 | Nebraska | LANCASTER | LINCOLN | 1 | 5250003 | Asphalt resurfacing on Adams St. from 57th St. to 62nd St. in Lincoln | Pavement Improvement | 02/02/2010 |  | 07/23/2010 | 452946 | 0
4034 | Nebraska | LANCASTER | LINCOLN | 1 | 5254009 | This project consists of bridge rehabilitation for the Superior Street Bridge over Salt Creek just west of 40th Street in Lincoln. The existing steel girder structure is 293 feet long and 50 feet wid | Bridge Improvement | 01/27/2010 |  | 08/15/2010 | 244076 | 0
4035 | Nebraska | ADAMS |  | 3 | 5527001 | 0.56 mile of asphalt resurfacing on Showboat Blvd. between 7th and 12th Streets in Hastings. | Pavement Improvement | 01/29/2010 |  | 10/30/2010 | 282133 | 0
4036 | Nebraska | REDWILLOW |  | 3 | 6156002 | Reconstruction of 0.72 mile of West J Street from West 10th St. to Norris Ave. in McCook. Project inlcudes storm sewers, sidewalks, ADA ramps and traffic signals. | Pavement Improvement | 07/22/2009 | 07/27/2009 | 04/16/2010 | 1071992 | 0
4037 | Nebraska | ADAMS |  | 3 | 7001014 | Replacement of a deficient bridge with a new 83' x 28' steel girder structure. The project is located 4 miles south and 0.8 mile west of Juniata, crossing the west branch of 32 mile Creek | Bridge Replacement | 01/27/2010 |  | 11/27/2010 | 447073 | 0
4038 | Nebraska | FRANKLIN |  | 3 | 7031012 | New twin 9' x 9' x 52' concrete box culvert on the Bostwick irrigation canal 1.5 miles east of Naponee | Bridge Replacement | 01/26/2010 |  | 11/20/2010 | 76982 | 0
4039 | Nebraska | JOHNSON |  | 1 | 7049021 | New 232' x 28' pre-stressed concrete girder bridge over the middle branch of the Big Nemaha River on a county road 2.0 miles west of Sterling. | Bridge Replacement | 01/21/2010 |  | 11/27/2010 | 870598 | 0
4040 | Nebraska | NUCKOLLS |  | 3 | 7065021 | Triple 3.66m x 18.5m concrete box culvert on Oak Creek 1.0 mile south of Oak on a county road. | Bridge Replacement | 02/02/2010 |  | 11/27/2010 | 254018 | 0
4041 | Nebraska | PHELPS |  | 3 | 7069015 | Triple 10' x 8' concrete box culvert on the Central Nebraska Public Power Irrigation District canal on a county road 1 miles west of Funk | Bridge Replacement | 01/25/2010 |  | 11/27/2010 | 124014 | 0
4042 | Nebraska | CLAY |  | 3 | S18B104 | This project is on the Edgar Spur from N-14 to the city of Edgar, a length of 4.0 miles. The scope consists of resurfacing and widening the existing roadway to provide a 24' roadway with 1' surfaced s | Pavement Improvement | 04/07/2009 | 05/11/2009 | 09/05/2009 | 1947585 | 3.99
4043 | Nebraska | DOUGLAS, LANCASTER, STATEWIDE | STATEWIDE | 1,2,3 | STWD093 | This project assists counties, municipalilties and metropolitan planning organizations in completing requirements for environmental documentation on ARRA projects. Six consulting engineering firms ar | Other | 07/09/2009 |  |  | 997500 | 0
4044 | Nevada | CLARK | LAS VEGAS | 2 | 0003126 | The City of Mesquite will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 11/30/2009 | 11/30/2009 | 01/28/2010 | 755622 | 0
4045 | Nevada | HUMBOLDT |  | 2 | 0013019 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade sur | Pavement Improvement | 06/29/2009 | 07/07/2009 | 01/04/2010 | 1588585 | 0
4046 | Nevada | CARSON CITY, LYON |  | 2 | 0032071 | The Nevada Commission for the Reconstruction of the V&T Railway will construct just over one mile of railroad track along of the historic Virginia and Truckee Railway roadbed on existing railroad grad | Transportation Enhancements | 07/16/2009 | 07/21/2009 | 11/04/2009 | 2033899 | 0
4047 | Nevada | CLARK |  | 2 | 0151140 | NDOT will use asphalt overlay on I-15 From CA/NV Stateline to Milepost 17.00 (CL0.00 to CL17.00) as part of the pavement preservation program. | Pavement Improvement | 11/23/2009 |  | 09/06/2010 | 8379233 | 16
4048 | Nevada | HUMBOLDT |  | 2 | 0289001 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 06/29/2009 | 07/07/2009 | 01/04/2010 | 1011170 | 0
4049 | Nevada | STATEWIDE |  | 2 | 0318013 | The Nevada Department of Transportation will generally cold in place recycle 3 inches depth of existing asphalt pavement, a 3 inch plantmix asphalt overlay with open grade surface course, or 8 inch ro | Pavement Improvement | 07/13/2009 | 07/27/2009 | 02/22/2010 | 14016262 | 0
4050 | Nevada | CHURCHILL |  | 2 | 0801165 | The Nevada Department of Transportation will cold mill 1.5 inches depth of existing asphalt pavement and place a plantmix asphalt overlay with open grade surface course. This will improve driving qual | Pavement Improvement | 12/21/2009 |  | 06/21/2010 | 10820369 | 0
4051 | Nevada | PERSHING |  | 2 | 0802052 | NDOT will preserve and extend the pavement life of about 14 miles of I-80 by milling 1 inch of existing pavement and replacing it with 3 inches of new asphalt and an open-graded wearing course. | Pavement Improvement | 06/08/2009 | 06/08/2009 | 12/07/2009 | 12349915 | 0
4052 | Nevada | LANDER |  | 2 | 0803059 | The Nevada Department of Transportation will construct 8 inch roadbed modification with 5.5 inches of plantmix asphalt with open grade surface course. This will improve driving quality by resurfacing | Pavement Improvement | 07/20/2009 | 08/17/2009 | 10/26/2009 | 2422580 | 0
4053 | Nevada | CLARK |  | 2 | 0932002 | NDOT will use asphalt overlay on US93 from 15.82 miles N of I15 at Garnet Interchange to the CL/LN County Line (CL67.83 to CL86.59) as part of the pavement preservation program. | Pavement Improvement | 09/14/2009 |  | 09/13/2010 | 6609682 | 19
4054 | Nevada | LINCOLN |  | 2 | 0932004 | Add Sidewalk | Transportation Enhancements | 11/20/2009 | 11/20/2009 | 01/18/2010 | 146554 | 0
4055 | Nevada | ELKO |  | 2 | 0935006 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 3 inch plantmix asphalt overlay with open grade surface course. This will imp | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/07/2009 | 10645650 | 0
4056 | Nevada | ELKO |  | 2 | 0935007 | The Nevada Department of Transportation will construct a approximately 66 feet wide by 162 feet long precast concrete arch overpass in a location with a history of many animal/vehicle collisions and a | New Bridge Construction | 08/10/2009 | 09/09/2009 | 11/28/2009 | 1075515 | 0
4057 | Nevada | CLARK |  | 3 | 0951041 | NDOT will build a Visitor's Center on US 95 to enhance the experience of the travelling public. | Transportation Enhancements | 07/15/2009 | 07/15/2009 | 01/18/2010 | 2975000 | 0
4058 | Nevada | CLARK | LAS VEGAS | 1 | 0952055 | NDOT will perform landscaping on US95 from Martin Luther King Blvd. to Rainbow Blvd. | Transportation Enhancements | 09/21/2009 | 09/29/2009 | 07/05/2010 | 3477042 | 0
4059 | Nevada | NYE |  | 2 | 0952056 | NDOT will use asphalt overlay on US 95 from 1.63 mi S of Jackass Flat to 0.62 mi N of SR 160. MP NY6.98 - NY14.38 as part of the pavement preservation program. | Pavement Improvement | 09/14/2009 | 09/14/2009 | 11/23/2009 | 2441345 | 7
4060 | Nevada | HUMBOLDT |  | 2 | 0956007 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 06/29/2009 | 07/07/2009 | 01/04/2010 | 1191458 | 0
4061 | Nevada | HUMBOLDT |  | 2 | 0956008 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 06/29/2009 | 07/07/2009 | 01/04/2010 | 3256353 | 0
4062 | New Hampshire | MERRIMACK |  | 02 | A000091 | WINNIPESAUKEE RIVER TRAIL PHASE 2B: SIGN TEMPORARY TRAIL CONNECTION FROMPARK STREET IN NORTHFIELD TO MORRISON AVENUE IN TILTON AND CONSTRUCTION OF NEW TRAIL THROUGH TILTON TO THE INTERSECTION AT NH 14 | Transportation Enhancements | 02/09/2010 |  | 08/30/2010 | 429646.25 | 1
4063 | New Hampshire | HILLSBOROUGH |  | 02 | A000094 | In Hillsborough, on route US 202/NH 9, a historic stone arch bridge will be preserved and resurfaced to better accommodate pedestrians and bicycles | Transportation Enhancements | 10/20/2009 |  | 06/14/2010 | 150045 | 0
4064 | New Hampshire | HILLSBOROUGH | NASHUA | 02 | A000095 | In Hudson, the town will be building almost a mile of new sidewalk and a nearly mile long bicycle lane on Route 102 between Evergreen Drive and Megan. | Transportation Enhancements | 07/17/2009 |  | 09/01/2009 | 357000 | 0
4065 | New Hampshire | ROCKINGHAM | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 02 | A000127 | On I-93 near Exit 3 in the Salem and Windham area, new northbound and southbound travel lanes will be constructed to improve safety and relieve congestion. | New Construction | 05/07/2009 | 06/17/2009 | 11/01/2011 | 27135145.95 | 2.2
4066 | New Hampshire | HILLSBOROUGH |  | 01 | A000258 | This project will widen the FE Everett Turnpike to provide improved access to and from the Manchester-Boston Regional Airport. | Pavement Widening | 04/16/2009 | 05/11/2009 | 06/01/2011 | 10365508.68 | 2.9
4067 | New Hampshire | HILLSBOROUGH |  | 02 | A000341 | In Bennington, this project will provide over a half-mile of sidewalk with crosswalks, and will clearly separate these facilities from vehicular traffic and parking to improve pedestrian access and sa | Transportation Enhancements | 07/22/2009 | 08/10/2009 | 05/01/2010 | 617600 | 0
4068 | New Hampshire | MERRIMACK |  | 02 | A000342 | This project in Boscawen will provide new sidewalks on Main Street through the route US3/4 intersection and along King Street. New crosswalks and pedestrian signals will enhance pedestrian safety at t | Transportation Enhancements | 08/21/2009 | 09/24/2009 | 05/01/2010 | 440231.5 | 0
4069 | New Hampshire | STRAFFORD |  | 01 | A000345 | On Durham's Main Street near the downtown area and the University of New Hampshire, this project will improve bicycle and pedestrian access and mobility by providing over a mile of new sidewalks, sepa | Transportation Enhancements | 11/13/2009 | 12/08/2009 | 09/30/2010 | 758258.55 | 0
4070 | New Hampshire | BELKNAP |  | 01 | A000349 | This project will provide around 1.5 miles of trail within an active rail corridor for bicyclists and pedestrians that will run from Main Street in Laconia to Elm Street in Lakeport. Improvements will | Transportation Enhancements | 08/31/2009 | 09/03/2009 | 12/01/2009 | 575980.5 | 0
4071 | New Hampshire | HILLSBOROUGH | MANCHESTER | 01 | A000390 | This project consists of earthwork west of the Merrimack River for Manchester Airport Access Road. | New Construction | 07/17/2009 | 08/05/2009 | 06/01/2011 | 5110519.37 | 0.62
4072 | New Hampshire | HILLSBOROUGH |  | 02 | A000566 | This project in Litchfield will help improve pedestrian and bicycle access and mobility by building nearly 2 miles of pedestrian and bike trail along Albuquerque Avenue. | Transportation Enhancements | 09/10/2009 | 09/25/2009 | 05/15/2010 | 394477.25 | 0
4073 | New Hampshire | ROCKINGHAM |  | 01 | A000620 | In Epping and Exeter, this project will provide new pavement on a 9.5 mile section of State Route 101 between Exit 6 and the Squamscott River Bridge in Exeter. | Pavement Improvement | 04/02/2009 | 04/10/2009 | 08/01/2009 | 7073670.8 | 9.74
4074 | New Hampshire | STATEWIDE |  | 02 | A000837 | This project will provide a thin layer of new pavement on about 7 miles of I-89 roadway from Exit 12A to Exit 13 in the New London and Grantham area. | Pavement Improvement | 05/07/2009 | 06/04/2009 | 09/01/2009 | 1032533.01 | 6.086
4075 | New Hampshire | MERRIMACK |  | 02 | A000838 | This project will provide crack filling and will provide a thin layer of new pavement on 4.9 miles of I-393 from I-93 to it's ending point in the Concord area. | Pavement Improvement | 06/18/2009 | 06/24/2009 | 09/01/2009 | 817740 | 3.197
4076 | New Hampshire | MERRIMACK |  | 02 | A000839 | This project provides new pavement to 5.4 miles of I-93 from Exit 14 to Exit 17 from the Concord area to Canterbury. Guardrail posts will also be replaced to improve safety. | Pavement Improvement | 06/18/2009 | 06/24/2009 | 10/01/2010 | 5356186 | 6.17
4077 | New Hampshire | STATEWIDE |  | 02 | A000840 | This project in the Sanbornton area provides new pavement on a 4 mile section of I-93 from north of Exit 19 in Northfield to Exit 22 in Sanbornton. The project also includes some bridge rehabilitation | Pavement Improvement | 05/21/2009 | 06/29/2009 | 06/01/2010 | 2188626 | 6.27
4078 | New Hampshire | GRAFTON |  | 02 | A000841 | This project provides new pavement on 7 miles of I-93 from Plymouth to Thornton, just south of the Exit 27 interchange north to the railroad bridge. | Pavement Improvement | 05/21/2009 | 06/09/2009 | 10/01/2009 | 747127.22 | 7.83
4079 | New Hampshire | ROCKINGHAM | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 01 | A000842 | This Portsmouth area project provides new pavement and some bridge deck and guardrail improvements for safety on about 1 and a half miles of I-95 from the Portsmouth traffic circle to the bridge over | Pavement Improvement | 07/17/2009 | 07/30/2009 | 08/01/2010 | 3470149.15 | 12.966
4080 | New Hampshire | GRAFTON |  | 02 | A000843 | This project provides new pavement and bridge improvements on 5.4 miles of I-93 from Exit 30 to Exit 32 in the Woodstock and Lincoln areas. | Pavement Improvement | 07/17/2009 | 07/30/2009 | 10/01/2010 | 8082359.5 | 58.275
4081 | New Hampshire | STATEWIDE |  | 01,02 | A000845 | This project is located in the New Hampton and Ashland and will provide new pavement and bridge improvements on about 6 miles of I-93. | Pavement Improvement | 05/21/2009 | 06/04/2009 | 06/01/2010 | 3924108.25 | 6.083
4082 | New Hampshire | MERRIMACK |  | 02 | A000846 | This New London area project on 5 miles of I-89 provides new pavement from Exit 11 north to Exit 12A. | Pavement Improvement | 04/02/2009 | 04/21/2009 | 08/01/2010 | 5315917 | 6.31
4083 | New Hampshire | STATEWIDE |  | 02 | A000871 | This project provides new pavement on various roadways in the counties of Coos, Carroll, and Grafton. | Pavement Improvement | 04/02/2009 | 05/05/2009 | 09/01/2009 | 3297522.19 | 56.58
4084 | New Hampshire | STATEWIDE |  | 01,02 | A000872 | This project is located along multiple sections of roadway within the counties of Grafton, Sullivan, and Merrimack. The project involves the resurfacing of approx. 48 miles of various roadways.; all | Pavement Improvement | 04/02/2009 | 05/14/2009 | 09/02/2009 | 3161306.53 | 47.18
4085 | New Hampshire | STATEWIDE |  | 01,02 | A000873 | This project provides about 48 miles of new pavement along many sections of roadway in Carroll, Grafton, and Belknap counties. | Pavement Improvement | 04/16/2009 | 05/27/2009 | 09/03/2009 | 3118908.13 | 47.26
4086 | New Hampshire | STATEWIDE |  | 02 | A000874 | This project provides new pavement and safety improvements on about 41 miles of multiple sections of roadway in Cheshire and Hillsborough counties. | Pavement Improvement | 05/07/2009 | 05/20/2009 | 09/01/2009 | 2710153.4 | 40.63
4087 | New Hampshire | STATEWIDE |  | 01,02 | A000875 | This project provides about 28 miles of new pavement on various sections of roadway in Merrimack, Hillsborough and Rockingham counties. | Pavement Improvement | 05/07/2009 | 05/28/2009 | 09/01/2009 | 3027549.6 | 35.32
4088 | New Hampshire | STATEWIDE | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 01,02 | A000876 | This project provides new pavement and intersection safety improvements on various roadways in Rockingham and Strafford counties. | Pavement Improvement | 05/07/2009 | 06/11/2009 | 09/01/2009 | 2941966.74 | 43.38
4089 | New Hampshire | GRAFTON |  | 02 | A000947 | This project on I-89 provides a more efficient I-89/NH 12A interchange at Exit 20 in Lebanon. The project includes bridge and ramp improvements for the interchange, including the bridge over the K-Mar | Pavement Widening | 10/08/2009 | 10/13/2009 | 10/28/2011 | 16217629.33 | 0.9
4090 | New Jersey | CAPE MAY |  | 02 | 0007109 | The Route 52 Causeway Contract B project replaces the two bridges located closest to Somers Point and Ocean City at Ship Channel and Beach Thorofare, respectively, with high level (55' clearance) brid | Bridge Replacement | 07/10/2009 | 08/11/2009 | 01/25/2012 | 73333333 | 1.09
4091 | New Jersey | ATLANTIC |  | 01 | 0016157 | This project will replace deteriorated pavement with new pavement along 4.5 miles of Route 30 in Hammonton and Mullica Townships in Atlantic County NJ. | Pavement Improvement | 07/08/2009 | 08/24/2009 | 12/01/2009 | 2348430 | 4.4
4092 | New Jersey | CAMDEN |  | 01 | 0016158 | This project will relieve flooding on Route 30 for 1.5 miles by upgrading pavement and replaceing the inlets, pipes and basins in Township of Pennsauken and City of Camden, Camden County. | Pavement Improvement | 08/24/2009 | 09/21/2009 | 09/14/2010 | 9899923 | 1.65
4093 | New Jersey | OCEAN |  | 03 | 0019110 | The project will extend the life of the bridge by including deck repair and curb repair on the entire deck (2.75 miles) of Rt.72 over the Manhawkin Bay in Townships of Stafford and Ship Bottom, Ocean | Bridge Improvement | 09/04/2009 | 09/16/2009 | 04/30/2009 | 4872010 | 2.15
4094 | New Jersey | MIDDLESEX |  | 13 | 0029163 | This project will design the work to replace the bridge deck of Route 18 over Route 1 in the city of New Brunswick, Middlesex County. | Other | 09/01/2009 |  |  | 1231172 | 0.5
4095 | New Jersey | HUNTERDON |  | 12 | 0031124 | This project will replace deteriorated pavement with new pavement and improve water drainage along 1 one mile of Route 29 in West Amwell Township & City of Lambertville in Hunterdon County. | Pavement Improvement | 08/19/2009 | 09/14/2009 | 10/04/2010 | 2778977 | 1.02
4096 | New Jersey | HUNTERDON |  | 12 | 0031125 | This project is the utility relocaitons associated with the Route 29 project in West Amwell Township & City of Lambertville in Hunterdon County. | Other | 08/19/2009 | 09/14/2009 |  | 168405 | 1.02
4097 | New Jersey | HUDSON |  | 01,09 | 0033274 | This project will paint two Route 1&9(Truck) movable bridges over the Hackensack and Passaic Rivers in the cities of Newark, Jersey City and Kearny, Hudson and Essex County. | Pavement Improvement | 07/16/2009 | 11/02/2009 | 12/31/2011 | 30717257 | 1.06
4098 | New Jersey | MERCER |  | 12 | 0033277 | This project will replace deteriorated pavement with new pavement along 2 miles of Route 1 in both northbound and southbound directions located in the Townships of Lawrence and West Windsor, Mercer Co | Pavement Improvement | 07/30/2009 | 08/04/2009 | 10/30/2009 | 4149459 | 2.02
4099 | New Jersey | MIDDLESEX |  | 06 | 0034109 | This project will replace the bridge decks of Rt 440 NB over Ramp WI and Ramp WK over CR 514. Both bridges are within the interchange of RT 440, CR 514 and NJTA exit 10. in the township of Edison, Mi | Pavement Improvement | 09/01/2009 | 09/15/2009 | 06/01/2010 | 4869837 | 0.27
4100 | New Jersey | MIDDLESEX |  | 13 | 0034110 | This project will design the work to replace the bridge deck of Route 440 Ramp V over Boggs Street, West Side Avenue, State Street and NJ transit in the city of Perth Amboy, Middlesex County. | Other | 07/30/2009 | 10/09/2009 | 09/01/2010 | 1014247 | 0.23
4101 | New Jersey | BERGEN |  | 09 | 0056151 | This project will design the work for a bridge deck replacement for Route 4 over Flat Rock Road in Englewwod City Bergen County | Other | 08/31/2009 | 08/31/2009 |  | 410961 | 0.2
4102 | New Jersey | ESSEX |  | 10 | 0785101 | This project will replace deteriorated pavement with new pavement and improve safety along nearly 2 miles of I-78 in the City of Newark, Essex County. | Pavement Improvement | 07/20/2009 | 08/31/2009 | 11/10/2010 | 15138024 | 1.43
4103 | New Jersey | HUNTERDON |  | 07 | 0785102 | This project will design the work to replace the bridge deck of I-78 ramp A, over I-78 in Township of Clinton Hunterdon County. | Other | 08/31/2009 |  | 09/01/2010 | 457281 | 0.5
4104 | New Jersey | WARREN |  | 05 | 0785103 | This project will remove the existing concrete slabs and replace with new pavement for nearly 1 mile on I-78 in Greenwich Township, Warren County. | Pavement Improvement | 08/18/2009 | 09/14/2009 | 08/01/2010 | 4243137 | 0.54
4105 | New Jersey | PASSAIC |  | 08,09 | 0805087 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 6 miles on I-80 Eastbound from West of Madison Ave to Polifly Road | Pavement Improvement | 07/16/2009 | 08/19/2009 | 09/02/2011 | 17258976 | 6.5
4106 | New Jersey | ESSEX |  | 11 | 0805088 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 8 miles on I-80 westbound form East of South Beverwyck Road to West | Pavement Improvement | 06/02/2009 | 06/24/2009 | 03/12/2010 | 10887007 | 7.7
4107 | New Jersey | MORRIS |  | 11 | 0805090 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and repairing bridge supports for the I-80 EB and WB bridges over Berkshire Valley Road i | Bridge Improvement | 07/07/2009 | 07/29/2009 | 06/11/2010 | 10320395 | 0.59
4108 | New Jersey | PASSAIC |  | 08,11 | 0805091 | This project will paint 5 bridges on Route I-80 in the Counties of Bergen, Essex, Passaic, Warren and Essex. | Pavement Improvement | 09/14/2009 | 11/05/2009 |  | 8206557 | 0.28
4109 | New Jersey | ESSEX |  | 09,10 | 2806103 | This project will paint 16 bridges on Route I-280 between mile points 12.7 to 14.5 in the Cities of Newark, Orange, East and West Orange, Essex County | Pavement Improvement | 07/28/2009 | 09/21/2009 | 08/15/2011 | 8965761 | 1.72
4110 | New Jersey | ESSEX |  | 08,10 | 2806105 | This project will paint 17 bridges on Route I-280 between mile points 7.5 to 11.1 in the Cities of Newark, Orange, East and West Orange, Essex County | Pavement Improvement | 07/27/2009 | 11/02/2009 | 08/15/2011 | 6833569 | 3.62
4111 | New Jersey | MIDDLESEX |  | 06 | 2873080 | This project will replace existing deteriorating bridge decks and pavement with new pavement, upgrade guardrails and improve water drainage on nearly 7 miles on I-287 NB and SB in Piscataway, Middlese | Pavement Improvement | 09/14/2009 | 09/17/2009 | 11/09/2011 | 34704512 | 7
4112 | New Jersey | MORRIS |  | 11 | 2873081 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck for the I-287 NB bridge over Route 46 in Parsippany-Troy Hills, Morris County. | Pavement Improvement | 07/10/2009 | 08/03/2009 | 09/30/2009 | 1674195 | 0
4113 | New Jersey | SALEM |  | 10 | 2952121 | This project will address the painting needs for 49 bridges on the Route I-295 corridor in Gloucester and Salem Counties. | Pavement Improvement | 08/31/2009 | 10/19/2009 | 09/01/2010 | 3084703 | 0
4114 | New Jersey | CAMDEN |  | 01,03 | 2952123 | This project will replace existing deteriorating bridge decks and pavement with new pavement, upgrade guardrails and improve water drainage on nearly 8 miles on I-295 NB and SB in West Deptford, Deptf | Pavement Improvement | 06/29/2009 | 06/29/2009 | 07/20/2012 | 77525524 | 7.9
4115 | New Jersey | CAMDEN |  | 01 | 2952124 | This project provides the funding for the ROW acquisition to allow for the construction of a new alignment that carries I-295 mainline through the interchange of Route 42 and I-76 in Bellmawr and Mt. | Other | 04/24/2009 | 04/24/2009 |  | 4807500 | 3.62
4116 | New Jersey | BURLINGTON |  | 04 | 4395101 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and repairing bridge supports for the Main St. (CR 543) over Rt. 206 bridge in Townships | Pavement Improvement | 08/26/2009 | 10/28/2009 | 11/09/2010 | 1576043 | 0.02
4117 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | 7044101 | This project will resurface 4 miles of roadway and improve water drainage from mile point 0 to mile point 4 on Route 35 in Berkely Township, Seside Heights, Seaside Park and Toms River, Ocean County. | Other | 06/17/2009 | 08/31/2009 | 11/01/2010 | 1491129 | 4
4118 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | 7044102 | This project will resurface 5 miles of roadway and improve water drainage from mile point 4 to mile point 9 on Route 35 in Toms River, Lavallette and Mantoloking, Ocean County. | Other | 05/20/2009 |  | 10/01/2010 | 1498266 | 5
4119 | New Jersey | MIDDLESEX |  | 06 | 7269101 | This project will extend the life of the bridge and improve safety replacing the existing deteriorated deck and in the Township of Woodbridge, Middlesex County. | Bridge Improvement | 08/28/2009 | 08/27/2009 | 09/01/2010 | 3029239 | 0.3
4120 | New Jersey | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09,13 | 7675115 | This project will design the work for a new bridge over the Hackensack River in Jersey City and Kearny, Hudson County. | Other | 04/14/2009 | 08/27/2009 | 12/23/2010 | 3471845 | 0.3
4121 | New Jersey | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09,13 | 7675116 | This project will design the work for the approaches and a new bridge and over the Hackensack River in Jersey City and Kearny, Hudson County. | Other | 08/04/2009 |  | 03/23/2011 | 9716313 | 0.6
4122 | New Jersey | MORRIS |  | 11 | 7741139 | This project will design the work to replace the bridge deck of County route 665 (Salem Street) over Route 10 over Randolph, Morris County. | Other | 08/31/2009 |  | 06/01/2011 | 617616 | 0.11
4123 | New Jersey | MORRIS |  | 11 | 7789102 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and is located in the Township of Montville, Morris County. in addition this project will | Bridge Improvement | 07/14/2009 | 07/31/2009 | 04/26/2010 | 1341542 | 0.01
4124 | New Jersey | BERGEN |  | 09 | 7802160 | This project will replace two bridges at the intersection of Route 46 over Main Street , improve safety and drainage in the Borough of Lodi, Bergen County. | Pavement Improvement | 05/28/2009 | 06/15/2009 | 09/01/2012 | 30684976 | 0.42
4125 | New Jersey | BERGEN |  | 09 | 7802163 | This project is the utility relocaitons associated with the Route 46 over Main Street in the Borough of Lodi, Bergen County. | Other | 05/28/2009 | 06/18/2009 | 09/01/2012 | 2589220 | 0.42
4126 | New Jersey | HUDSON |  | 13 | 7811116 | This project will replace deteriorated pavement with new pavement along 1.5 miles of Route 440 in both northbound and southbound directions from JFK Blvd. to 22nd street. The project is located in the | Pavement Improvement | 07/28/2009 | 08/11/2009 | 11/19/2009 | 3660338 | 1.4
4127 | New Jersey | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 8112137 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck of the Roff Avenue Bridge over Route 46 in Palisades Park, Bergen County. | Bridge Improvement | 08/17/2009 |  | 11/05/2010 | 2052177 | 0
4128 | New Jersey | PASSAIC |  | 08 | 8112138 | This project will improve safety and extend the life of the Grove Street (CR 623) bridge over Route 46 in Clifton Passaic County, by replacing the existing deteriorated deck, and repairing bridge supp | Pavement Improvement | 08/26/2009 | 10/14/2009 |  | 3097525 | 0.1
4129 | New Jersey | BERGEN |  | 11 | 8112139 | This project is the utility relocaitons associated with the Roff Avenue bridge over Route 46 in Palisades Park, Bergen County. | Other | 08/17/2009 | 11/04/2009 |  | 261101 | 0.02
4130 | New Jersey | BERGEN |  | 09 | 8669101 | This project will extend the life of the bridge and improve safety and drainage by replacing the existing deteriorated deck and repairing bridge supports in Township of Mahwah, Bergen County NJ. | Bridge Improvement | 06/16/2009 | 06/18/2009 | 08/14/2009 | 761170 | 0.03
4131 | New Jersey | STATEWIDE |  | 04,12 | B00S785 | This project (Contract #10) will provide guiderail down the middle of the roadway on 5.14 miles of Route 18 and 4.64 miles of Route I-95 in the Counties of Mercer, Middlesex, Monmouth. | Safety/Traffic Management | 08/17/2009 | 09/30/2009 | 07/01/2010 | 3337794 | 8.22
4132 | New Jersey | STATEWIDE |  | 11 | B00S786 | This project (Contract #11) will provide guiderail down the middle of the roadway on 5.14 miles of Route 18 and 4.64 miles of Route I-95 in the Counties of Mercer, Middlesex, Monmouth. | Other | 08/24/2009 | 09/14/2009 | 11/01/2010 | 1204790 | 6.6
4133 | New Jersey | SOMERSET | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S816 | Somerset County will resurface the existing asphalt roadway with new asphalt on multiple County roads. This will improve driving quality by resurfacing the road, which will make the road smoother and | Transportation Enhancements | 09/10/2009 | 10/19/2009 |  | 5580954 | 0
4134 | New Jersey | CUMBERLAND | ATLANTIC CITY | 02 | B00S829 | Cumberland County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at | Pavement Improvement | 10/06/2009 |  |  | 2350000 | 0
4135 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | PLHD001 | Ocean County will improve the intersection to improve traffic flow and increase safety. | Pavement Improvement | 10/07/2009 |  |  | 197429 | 0
4136 | New Mexico | EDDY |  | 02 | 0062004 | Project consists of construction of two new lanes on US62/180 (northbuond lanes) between White City and Carlsbad to allow for a four lane highway. Project consists of new roadway, shoulders, striping, | Pavement Widening | 04/08/2009 | 04/08/2009 | 10/07/2010 | 14855940.31 | 10
4137 | New Mexico | DONA ANA | LAS CRUCES | 02 | 0102111 | The I-10 six lane project will provide a total of (3) lanes for both east and west bound traffic, the additional lanes will be constructed within NMDOT ROW, this project is 18.3 miles in length, sta | Pavement Widening | 11/30/2009 | 12/23/2009 | 07/13/2011 | 10000000 | 20.4
4138 | New Mexico | GRANT |  | 02 | 0356005 | The project will include rebuilding and aligning of the curb and gutter, sidewalks, lighting and improvements so that people with disabilities will be able to use the sidewalks. It will, also, includ | Pavement Improvement | 02/02/2010 | 03/08/2010 | 06/16/2010 | 350000 | 0
4139 | New Mexico | BERNALILLO | ALBUQUERQUE | 01 | 0403104 | The City of Albuquerque proposes to construct a trail which would connect existing facilities to enhance the multi-modal transportation network | Transportation Enhancements | 10/26/2009 | 10/26/2009 | 07/26/2010 | 5358782 | 0
4140 | New Mexico | BERNALILLO |  | 01 | 0403168 | Reconstruction of I-40 and West Central consists of construction of a new overpass over I-25, new on and off ramps, new construction of Paseo Del Volcan and Central Avenue, and re-alignment of Central | Pavement Widening | 04/28/2009 | 04/28/2009 | 10/24/2010 | 14800000 | 1
4141 | New Mexico | SANTA FE |  | 03 | 0511097 | This project will reconstruction the four lanes of US 84/285 from Arroyo Seco to La Puebla and adds a two-way frontage road on both sides of the highway. | Pavement Widening | 05/27/2009 | 05/27/2009 | 10/10/2010 | 13040682.99 | 2.9
4142 | New Mexico | SANTA FE |  | 03 | 0511098 | This project will reconstruct the four lanes of US 84/285 highway and adds medians from Dandy Burger South to the Dreamcatcher Theater. It will also add a new traffic signal at the Upper San Pedro in | Pavement Improvement | 04/08/2009 | 04/08/2009 | 06/15/2010 | 9023269.25 | 1.5
4143 | New Mexico | COLFAX |  | 03 | 0649036 | This project will construct 2 new lanes on US64/87 from Des Moines to Capulin, converting this portion of US64/87 to a 4-lane facility. This is Phase Vi of a seven Phase project to widen US64/87 to 4 | New Construction | 08/12/2009 | 08/12/2009 | 01/26/2011 | 26209085.9 | 16
4144 | New Mexico | OTERO |  | 03 | 0821026 | STRUCTURAL EVALUATION, PRESERVATION OF SOUND TIMBERS & REPLACEMENT OF DECAYED/MISSING TIMBERS. | Transportation Enhancements | 08/26/2009 | 08/26/2009 | 09/29/2009 | 249747 | 0
4145 | New Mexico | LEA |  | 02 | 1271015 | Project consists of total reconstruction of a 14.4 mile segment of NM128 between Carlsbad and Jal on an offset new alignment. Project will consist of new roadway, shoulders, striping, permanent signin | Pavement Improvement | 04/13/2009 | 04/13/2009 | 05/19/2010 | 8252068.4 | 14.11
4146 | New Mexico | SANDOVAL | ALBUQUERQUE | 01 | 4007003 | This project will complete Stage II of the Paseo Del Volcan corridor within the city of Rio Rancho. The project will consist of a new 2-lane facility including lighting, bridges, and various drainage | Pavement Widening | 08/10/2009 | 08/10/2009 | 02/11/2011 | 14000000 | 0
4147 | New Mexico | SAN JUAN |  | 03 | 4911011 | This project will provide two new traveling lanes to make the US 491 roadway a four lane facility. This is one segment of 9 segments to four lane US 491 from MP 15.7 to MP 84.7. | New Construction | 06/30/2009 | 06/30/2009 | 05/04/2010 | 21921582.36 | 8
4148 | New Mexico | MCKINLEY |  | 03 | 4911031 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. Project will also provide intersection improvements for better t | Pavement Improvement | 04/10/2009 | 04/10/2009 | 03/04/2010 | 10577392.48 | 13.9
4149 | New Mexico | RIO ARRIBA |  | 03 | 5348002 | To construct road improvements to Industrial Park Road for its entire length of 1.1 miles in Espanola that includes added lanes, drainage improvements, pedestrian facilities, utilities, curb and gutte | Pavement Improvement | 10/07/2009 | 10/07/2009 | 06/16/2010 | 1250000 | 0
4150 | New Mexico | LUNA |  | 02 | ES11220 | RECONSTRUCTION TO INCLUDE PEDESTRIAN FACILITIES | Pavement Improvement | 12/22/2009 | 01/03/2010 | 11/08/2010 | 850000 | 0
4151 | New Mexico | GRANT |  | 02 | ES11240 | This project will include grinding down existing old pavement and replacing with new pavement on 12th Street from Gold Street to Mississippi Street. In addition, it will include inspection and oversi | Pavement Improvement | 02/02/2010 | 02/03/2010 | 05/30/2010 | 600000 | 0
4152 | New Mexico | LEA |  | 02 | ES21070 | This project will include downtown beautification consisting of new pavement, lighting, crosswalks, sidewalks, curb and gutter and landscaping on NM 176 from mile post 34.9 to milepost 35.4 and on NM | Transportation Enhancements | 02/05/2010 | 02/08/2010 | 06/27/2010 | 249747 | 0
4153 | New Mexico | CHAVES |  | 02 | ES21250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 11/02/2009 | 04/01/2010 | 05/30/2010 | 830000 | 0
4154 | New Mexico | CURRY |  | 02 | ES21280 | BRIDGE REPLACEMENT ON HULL STREET SPANNING OVER BURLINGTON NORTHERN SANTA FE RAILROAD | Bridge Replacement | 11/24/2009 | 01/04/2010 | 10/31/2010 | 831489 | 0.3
4155 | New Mexico | LEA |  | 02 | ES21320 | PAVMENT RECONSTRUCTION INCLUDING MILLING EXCAVATION, SUBGRADE BASE COURSE, ASPHALT TREATED BASE, HOT-MIX ASPHALT AND MINOR CONCRETE. | Pavement Improvement | 01/04/2010 | 01/25/2010 | 07/24/2010 | 831489 | 1
4156 | New Mexico | LOS ALAMOS |  | 03 | ES51140 | REHABILITATE & RECONSTRUCT HIGHLY DETERIORATED ROADWAY TO INCLUDE; PAVEMENT, CURB, GUTTER, SIDEWALKS, STORM DRAIN SYSTEMS & ROADWAY LIGHTING. | Pavement Widening | 11/02/2009 | 11/02/2009 | 03/01/2010 | 1962217 | 0
4157 | New Mexico | MCKINLEY |  | 03 | ES61250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 01/13/2010 | 02/03/2010 | 04/04/2010 | 4000000 | 0
4158 | New Mexico | SANTA FE |  | 01 | ESS1010 | This project will provide landscaping of all medians on Rodeo Road from Galisteo Street to Camino Carlos Rey. | Transportation Enhancements | 09/22/2009 | 09/22/2009 | 11/30/2009 | 150000 | 0
4159 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 1 | 0016263 | Completely renovating 3.5 miles of New York Route 112 in Brookhaven, Suffolk County to improve the safety for the approximately 20,000 motorists, pedestrians and bicyclists who use the roadway daily. | Pavement Improvement | 08/06/2009 | 08/06/2009 | 11/11/2011 | 37015010 | 3
4160 | New York | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 4 | 0758463 | Provide new bike lanes and improved pedestrian facilities, including new sidewalks and crosswalks, on Prospect Avenue between Brush Hollow Road and Cantiague Rock Road in New Cassel, in the Town of No | Safety/Traffic Management | 10/13/2009 | 10/13/2009 | 07/30/2010 | 5000000 | 0
4161 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2 | 0758583 | Reconstruct Walt Whitman Road in the Town of Huntington | Pavement Improvement | 10/06/2009 | 10/06/2009 | 04/29/2011 | 5436138 | 0
4162 | New York | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 2, 3, 4, 5 | 0759373 | A project to clean, paint, and thereby preserve the integrity of four bridges accessing Hempstead Lake Park in the Village of Rockville Centre, Nassau County. | Bridge Improvement | 09/28/2009 | 09/28/2009 | 07/01/2010 | 3287345 | 0
4163 | New York | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 3 | 0759383 | A project to provide safety, pavement and drainage improvements on Cedar Swamp Road in Glen Cove, Town of North Hempstead, Nassau County. | Pavement Improvement | 11/11/2009 | 11/11/2009 | 07/01/2010 | 3678937 | 0
4164 | New York | NASSAU |  | 2, 3, 4, 5 | 0759393 | Resurface select local roads in Nassau County. The existing deteriorated pavement surface will be removed and replaced with new asphalt and pavement markings. | Pavement Improvement | 08/14/2009 | 08/14/2009 | 05/31/2010 | 3715000 | 0
4165 | New York | NASSAU |  | 2, 3, 4, 5 | 0759403 | Resurface select local roads in Nassau County. The existing deteriorated pavement surface will be removed and replaced with new asphalt and pavement markings. | Pavement Improvement | 08/14/2009 | 08/14/2009 | 05/31/2010 | 4085000 | 0
4166 | New York | NASSAU |  | 2, 3, 4, 5 | 0759413 | A project to construct a seven-mile shared-use bike path in Mitchell Park, Nassau County. The new, shared-use path will provide a non-motorized transportation facility that connects multiple recreat | Transportation Enhancements | 11/11/2009 | 11/11/2009 | 07/01/2010 | 2449975 | 0
4167 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2 | 0759423 | Recondition, preserve asphalt pavement and improve drainage on Commack Road, County Road 4, between Nicolls Road and Polo Street in the towns of Babylon and Huntington, Suffolk County. | Pavement Improvement | 09/07/2009 | 09/07/2009 | 08/13/2010 | 3500000 | 0
4168 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2 | 0759433 | Rehabilitate the roadway pavement and make needed drainage improvements on County Route 67 between the Long Island Expressway (LIE/I495) and County Route 17 in the Town of Islip, Suffolk County. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 05/01/2010 | 3723129 | 3.65
4169 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 1, 2 | 0759443 | A project to remove the top layer of worn, distressed pavement on Long Island Expressway service roads between Exit 59 and 63 in the towns of Islip and Brookhaven, Suffolk County, and replace it w | Pavement Improvement | 11/30/2009 | 11/30/2009 | 06/01/2010 | 7291736 | 6.8
4170 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2 | 0759453 | A project to remove the top layer of worn, distressed pavement on Long Island Expressway service roads between Exit 54 and 59 in the towns of Islip and Brookhaven, Suffolk County, and replace it w | Pavement Improvement | 09/22/2009 | 09/22/2009 | 06/01/2010 | 8506185 | 7.5
4171 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 2, 3, 4, 5 | 0808183 | Improve roadway storm water run off, clean and repair or replace drainage basins to locations on NY25A, Nassau County, NY RT102, Nassau County, NY RT25A, Suffolk County, & Robert Moses Causeway, Suffo | Other | 08/12/2009 | 08/12/2009 | 05/22/2010 | 743417 | 0.51
4172 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 1, 2, 5 | 0808193 | Resurface approximately nine miles of State roadways in Nassau and Suffolk counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement marki | Pavement Improvement | 06/26/2009 | 06/26/2009 | 06/30/2010 | 6895000 | 7.71
4173 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 2, 3, 4 | 0808393 | Much-needed concrete pavement repairs to sections of distressed, aging roadway systems throughout Nassau and Suffolk counties to improve pavement smoothness, reduce accidents and maintain pavement int | Pavement Improvement | 06/24/2009 | 06/24/2009 | 06/19/2010 | 1892219 | 23.59
4174 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2, 3 | 0808503 | Clean the steel of 10 bridges in Babylon, Brookhaven and Islip in Suffolk County to eliminate corrosion and rust and to paint the structures. These preventative-maintenance repairs will maintain the b | Bridge Improvement | 06/15/2009 | 06/15/2009 | 12/31/2010 | 4940948 | 0
4175 | New York | STATEWIDE |  | 1, 2, 3, 4, 5 | 0808553 | Upgrade approximately 900 traffic signals in Nassau and Suffolk counties by replacing existing incandescent lights with more energy efficient Light Emitting Diode (LED) bulbs to reduce energy use and | Safety/Traffic Management | 08/20/2009 | 08/20/2009 | 04/23/2011 | 4208000 | 0
4176 | New York | STATEWIDE |  | 1, 2, 3, 4, 5 | 0808563 | Upgrade the outdated, 22-year-old original technology that operates 53 out of 190 motorist information signs operated by NYSDOT INFORM's transportation management center. The project will increase the | Safety/Traffic Management | 10/07/2009 | 10/07/2009 | 03/31/2011 | 2645664 | 0
4177 | New York | SUFFOLK |  | 1 | 0808643 | Preserve the Stony Brook Mill Pond as a fragile aquatic resource and better protect motorists from roadway flooding conditions on NY Route 25A (North Country Road) in Stony Brook, Town of Brookhaven, | Other | 10/01/2009 | 10/01/2009 | 04/09/2010 | 701872 | 1.6
4178 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1753373 | Relocate the Maxwell Road intersection with Albany Shaker Road in the town of Colonie, Albany County 800 feet to the east, away from the existing intersection. The existing intersection will remain, b | Pavement Widening | 08/05/2009 | 08/05/2009 | 11/30/2010 | 5333409 | 0
4179 | New York | WASHINGTON |  | 20 | 1755153 | Replace the bridge carrying Clinton Street, Saunders Street and Division Street over the Delaware and Hudson Railroad in the Village of Whitehall in Washington County. This rail line serves the area a | Bridge Replacement | 09/01/2009 | 09/01/2009 | 12/31/2010 | 4917794 | 0
4180 | New York | WARREN |  | 20 | 1755213 | Replace the County Route 3/Warrensburg Road Bridge over Stony Creek in the Town of Stony Creek, Warren County. | Bridge Replacement | 06/05/2009 | 06/05/2009 | 04/30/2010 | 1458010 | 0.01
4181 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756353 | Replace the bridge over the Fifth Branch of the Mohawk River in the City of Cohoes, Albany County. A new five-span steel bridge will be constructed on existing bridge alignment, including reconstructi | Bridge Replacement | 07/28/2009 | 07/28/2009 | 07/31/2010 | 7463000 | 0.09
4182 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756593 | Reconstruction of 19th Street in the City of Watervliet in Albany County. 19th Street carries New York State Touring Route 2 through the City between the Congress Street Bridge and the City Line and s | Pavement Improvement | 07/29/2009 | 07/29/2009 | 11/30/2010 | 6627194 | 1.17
4183 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756613 | Reconstruct Delaware Avenue for the 1.6 miles between Madison Avenue and the bridge over the New York State Thruway linking Albany and Delmar, Albany County. The project will include curb, drainage an | Pavement Improvement | 04/09/2009 | 04/09/2009 | 10/31/2010 | 14897612 | 1.63
4184 | New York | RENSSELAER | ALBANY-SCHENECTADY-TROY | 21 | 1756623 | Reconstruction of NY Route 2 from 5th Avenue to 11th Street in the City of Troy | Pavement Widening | 09/09/2009 | 09/09/2009 | 12/31/2010 | 6695070 | 0
4185 | New York | RENSSELAER |  | 20 | 1757083 | Replace the bridge carrying Caretaker Road over the Walloomsac River in the town of Hoosick, Rensselaer County. This bridge, built in 1900, accesses a historic site, the Bennington Battlefield. Withou | Bridge Replacement | 08/11/2009 | 08/11/2009 | 12/31/2009 | 1215112 | 0
4186 | New York | GREENE |  | 20 | 1757123 | Replacement of the bridge carrying New Baltimore Road over Hannacrois Creek in the Town of New Baltimore in Greene County. The existing box-beam bridge, built in 1972 and owned by Greene County, conti | Bridge Replacement | 07/29/2009 | 07/29/2009 | 12/31/2009 | 1262477 | 0.01
4187 | New York | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1757143 | Reconstruct a portion of Church Street -- State Touring Route 9N -- in the city of Saratoga Springs, Saratoga County. The project will improve Church Street between West Avenue and North Van Rensselae | Pavement Improvement | 09/11/2009 | 09/11/2009 | 07/30/2010 | 2805782 | 0
4188 | New York | WARREN |  | 20 | 1757173 | Replace the Grist Mill Road Bridge over Stony Creek in the Town of Stony Creek, Warren County. | Bridge Replacement | 06/05/2009 | 06/05/2009 | 04/30/2010 | 1017426 | 0.01
4189 | New York | ESSEX |  | 20 | 1758333 | Rehabilitation of Essex County Route 84, Blue Ridge Road, between the Adirondack Northway and State Route 28N in the towns of Newcomb, Minerva and North Hudson in Essex County. This county road, measu | Pavement Improvement | 08/04/2009 | 08/04/2009 | 08/01/2009 | 3807134 | 17.36
4190 | New York | WARREN |  | 20 | 1758613 | The second phase of the reconstruction of Bay Street in the City of Glens Falls in Warren County. This deteriorating city street is a major north-south route linking the City and the Town of Queensbur | Pavement Improvement | 07/28/2009 | 07/28/2009 | 06/30/2010 | 2889596 | 1.03
4191 | New York | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1758623 | A project to complete the Zim Smith Trail in the towns of Ballston and Malta in Saratoga County. The project will construct 2 miles of pedestrian trail and connect two existing trails between Oak St | Transportation Enhancements | 11/24/2009 | 11/24/2009 | 06/30/2010 | 669237 | 0
4192 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1758673 | Washington Avenue Pavement Resurfacing, Washington Avenue, Fuller Road to I-90, Jermain Street to North Main Avenue, Ontario Streen to Lark Street. | Pavement Improvement | 09/25/2009 | 09/25/2009 | 11/30/2009 | 2755336 | 0
4193 | New York | RENSSELAER | ALBANY-SCHENECTADY-TROY | 21 | 1758693 | Pavement Resurfacing of County Route 145, Oakwood Avenue. | Pavement Improvement | 09/04/2009 | 09/04/2009 | 11/30/2009 | 847655 | 1.32
4194 | New York | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758713 | Resurfacing of Rosendale Road/River Road in the Town of Niskayuna. | Pavement Improvement | 12/30/2009 | 12/30/2009 | 11/30/2009 | 313788 | 0
4195 | New York | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758723 | Pavement resurfacing of Van Vanken Avenue, Nott Street to Maxon Road in the City of Schenectady. | Pavement Improvement | 10/05/2009 | 10/05/2009 | 11/30/2009 | 1241513 | 0
4196 | New York | GREENE |  | 20 | 1758743 | Resurface Greene County Route 28, Schoharie Turnpike, between U.S. Route 9W in the town of Athens and Second Street in the village of Athens. The project will remove and replace deteriorating pavement | Pavement Improvement | 10/02/2009 | 10/02/2009 | 10/31/2009 | 400082 | 0
4197 | New York | STATEWIDE |  | 21 | 1807993 | Pavement improvements on Route 5 in Albany, Schenectady and the towns of Colonie, Albany County, and Niskayuna, Schenectady County. Work also will include the installation at 159 intersections of ramp | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/15/2010 | 7340489 | 6.84
4198 | New York | STATEWIDE |  | 20, 21 | 1808173 | Resurface Albany, Rensselaer, Saratoga and Schenectady counties. Locations include: State Route 9 in Halfmoon, Clifton Park and Malta between State Route 146 and Crescent Avenue; State Route 20 in Gui | Pavement Improvement | 08/27/2009 | 08/27/2009 | 11/15/2009 | 8896897 | 24.07
4199 | New York | HERKIMER |  | 24 | 2012043 | Rehabilitate the bridge carrying Route 169 over the CSX railroad and the Erie Canal in the City of Little Falls, Herkimer County. The project will include repairing deteriorated concrete and repaving | Bridge Improvement | 05/27/2009 | 05/27/2009 | 06/30/2010 | 1262528 | 0
4200 | New York | STATEWIDE |  | 21, 23, 24 | 2804843 | Paint and wash bridges carrying state highways in Oneida, Madison, Herkimer, Hamilton, Fulton and Montgomery counties. These preventative maintenance treatments will inhibit deterioration and extend t | Bridge Improvement | 04/29/2009 | 04/29/2009 | 11/30/2009 | 2423639 | 0
4201 | New York | STATEWIDE |  | 21, 23, 24 | 2804853 | Paint and wash bridges carrying state highways in Oneida, Madison, Herkimer, Hamilton, Fulton and Montgomery counties. These preventative maintenance treatments will inhibit deterioration and extend t | Bridge Improvement | 05/14/2009 | 05/14/2009 | 11/30/2009 | 292091 | 0
4202 | New York | ONEIDA | UTICA-ROME | 24 | 2804893 | Resurface Routes 5A and 69 in the City of Rome, Town of Whitestown and villages of Oriskany, Yorktown and Whitesboro in Oneida County. The project will include repaving, traffic signal replacement and | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/18/2009 | 2657494 | 14.76
4203 | New York | ONEIDA | UTICA-ROME | 24 | 2805083 | Replace the bridge joints on five structures along Interstate 790 in the City of Utica, Oneida County. This preventative maintenance project will maintain the bridges structural reliability. | Bridge Improvement | 05/19/2009 | 05/19/2009 | 11/30/2009 | 520969 | 0
4204 | New York | STATEWIDE |  | 21, 23, 24 | 2ST0043 | Paint 14 bridges, one in Fulton County, four in Herkimer County, two in Montgomery County and seven in Oneida County. The structural steel elements of each bridge will be commercially sandblasted to e | Bridge Improvement | 08/21/2009 | 08/21/2009 | 05/14/2010 | 2657480 | 0
4205 | New York | HAMILTON |  | 23 | 2ST0343 | Replace the bridge carrying Big Brook Road over Lake Abanake in the town of Indian Lake, Hamilton County. The existing structure will be replaced with a higher bridge to accommodate boat traffic in th | Bridge Replacement | 09/17/2009 | 09/17/2009 | 09/30/2010 | 694413 | 0
4206 | New York | STATEWIDE |  | 21, 23 | 2ST1003 | Resurface approximately three miles of Route 5S from the Herkimer County Line to Sanders Road in the town of Minden, Montgomery County and resurface approximately 5.5 miles of Route 29 from Vail Mills | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 961455 | 8.9
4207 | New York | HERKIMER | UTICA-ROME | 24 | 2ST1013 | Resurface highways in Herkimer County, including approximately 1.5 miles of Route 5S from Main Street in Frankfort to Route 51 in Ilion; approximately three miles of Route 28 from Route 8 to Comstock | Pavement Improvement | 10/05/2009 | 10/05/2009 | 07/30/2010 | 1426649 | 4.35
4208 | New York | ONEIDA | UTICA-ROME | 23, 24 | 2ST1023 | Rehabilitate several state highways in Oneida County, including resurfacing approximately 16 miles of various highways and approximately five miles of shoulders along I-790 in Oneida County. In the ur | Pavement Improvement | 10/06/2009 | 10/06/2009 | 11/30/2009 | 4348801 | 35.58
4209 | New York | STATEWIDE |  | 21, 24 | 2ST2003 | Rehabilitate pavement at 14 sites in the cities of Amsterdam, Montgomery County; Johnstown and Gloversville, Fulton County; and Little Falls, Herkimer County. Work will consist primarily of milling an | Pavement Improvement | 10/06/2009 | 10/06/2009 | 08/31/2010 | 3368195 | 0
4210 | New York | MONTGOMERY |  | 21 | 2V09513 | Resurface Route 67 through the towns of Amsterdam and Mohawk in Montgomery County. This preventive maintenance project will seal the asphalt surface to prevent water from entering cracks in the paveme | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/30/2010 | 145068 | 3.07
4211 | New York | STATEWIDE |  | 23, 24 | 2V09613 | Resurface approximately 15 miles of Routes 8, 12 and 20 through the towns of Trenton, Steuben, Forestport and Cazenovia in Oneida County and the Town of Brookfield, Madison County. This preventive mai | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/30/2010 | 963062 | 11.51
4212 | New York | STATEWIDE |  | 23, 24 | 2V09713 | Resurface approximately nine miles of Route 12B in the towns of Marshall and Kirkland, Oneida County, and the towns of Madison and Augusta, Madison County. This preventive maintenance project will sea | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/30/2010 | 679345 | 9
4213 | New York | CAYUGA |  | 24 | 3155243 | Replace two bridges on State Route 90 in Cayuga County. One bridge is over Little Salmon Creek in the Town of Genoa and the other is over Paines Creek in the Town of Ledyard. This project will remove | Bridge Replacement | 10/13/2009 | 10/13/2009 | 05/25/2010 | 3261673 | 0.01
4214 | New York | ONONDAGA |  | 25 | 3501423 | Replacement of the bridge carrying Bartell Road over Interstate 81 in the Town of Cicero, Onondaga County. The new bridge will increase safety and capacity. | Bridge Replacement | 05/21/2009 | 05/21/2009 | 01/28/2010 | 6671356 | 0.1
4215 | New York | ONONDAGA | SYRACUSE | 25 | 3601923 | Resurface almost five miles of Interstate 690 eastbound and westbound from the Teall Avenue interchange to the Interstate 481 interchange. This essential maintenance in the City of Syracuse, Onondaga | Pavement Improvement | 05/25/2009 | 05/25/2009 | 12/05/2009 | 9946552 | 11.32
4216 | New York | ONONDAGA | SYRACUSE | 25 | 3602033 | Resurface Route 20 in Madison County and Onondaga County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 1213799 | 8.6
4217 | New York | OSWEGO |  | 23 | 3602043 | Paving Route 11 in the Town of Hastings, Onondaga County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 477523 | 2.5
4218 | New York | TOMPKINS | ITHACA | 24 | 3602063 | Resurface Route 79 from the Tioga County line to Besner Hill in the Town of Caroline, Tompkins County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fr | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 1584000 | 7
4219 | New York | TOMPKINS | ITHACA | 22, 24 | 3602073 | Resurface Route 79 through the towns of Ithaca and Enfield, Tompkins County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 1080000 | 8.46
4220 | New York | OSWEGO |  | 23 | 3602106 | Paving Route 34, Cayuga County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 529000 | 3.6
4221 | New York | OSWEGO |  | 23 | 3602113 | Paving Route 104A, Cayuga County Line To Oswego County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 455000 | 2.78
4222 | New York | SENECA |  | 24 | 3602313 | Paving Route 96 to Village of Waterloo, Seneca County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 901863 | 6.24
4223 | New York | CAYUGA |  | 24 | 3602353 | Paving Route 34, County Route 43B at Venice Center to Skillet/Mosher Road. Towns of Scipio and Venice, Cayuga County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 960000 | 5.97
4224 | New York | CAYUGA |  | 24 | 3602393 | Paving Route 38, Hamlet of Cascade to Wyckoff Road, Towns of Venice & Scipio, Cayuga County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 1142203 | 6.95
4225 | New York | CORTLAND |  | 24 | 3602403 | Paving Route 11/41, City of Cortland to Village of McGraw, Town of Cortlandville, Cortland County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 900000 | 5.66
4226 | New York | SENECA |  | 24 | 3602493 | Paving Route 414, Fayette South Town Line to Village of Seneca Falls, Towns of Fayette and Seneca Falls, Seneca County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2010 | 910000 | 5.79
4227 | New York | ONONDAGA |  | 25 | 3752893 | Rehabilitate the Dorwin Avenue bridge over Onondaga Creek in the City of Syracuse, Onondaga County. The bridge deck and superstructure will be removed and replaced with a new multi-girder steel supers | Bridge Improvement | 08/03/2009 | 08/03/2009 | 07/01/2010 | 1396000 | 0.02
4228 | New York | ONONDAGA | SYRACUSE | 25 | 3752983 | Reconstruct Taft Road from South Bay Road to Northern Boulevard in the town of Clay and Cicero, Onondaga County. The project will rehabilitate and widen Taft Road from South Bay Road to Church Street | Pavement Improvement | 07/06/2009 | 07/06/2009 | 12/01/2010 | 8444943 | 3.1
4229 | New York | TOMPKINS | ITHACA | 24 | 3753733 | Reconstruct County Route 121, Warren Road, from Route 13 to North Asbury Road in the Village and Town of Lansing, Tompkins County. The safety-improvement project will include new asphalt and fresh pav | Pavement Improvement | 07/09/2009 | 07/09/2009 | 09/07/2010 | 5313433 | 2.97
4230 | New York | SENECA |  | 24 | 3754223 | A project sponsored by Seneca County to replace the Brewer Road bridge over Black Brook. This project will remove this bridge from the deficient bridge inventory. | Bridge Replacement | 07/28/2009 | 07/28/2009 | 06/01/2010 | 405000 | 0
4231 | New York | STATEWIDE |  | 23, 24, 25 | 3804963 | Clean and paint nine different state bridges in Cayuga, Oswego, and Onondaga counties. This project will protect the structural integrity of the steel and improve the aesthetic appearance of each brid | Bridge Improvement | 07/23/2009 | 07/23/2009 | 11/27/2009 | 1939980 | 0.01
4232 | New York | CORTLAND |  | 24 | 3M07283 | Paving Route 222, Cortlandville, Cortland/Tompkins County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/01/2009 | 790000 | 3.5
4233 | New York | OSWEGO |  | 23 | 3M07293 | Paving Route 11, Town of Parish- Oswego County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/01/2009 | 425805 | 0
4234 | New York | CAYUGA |  | 25 | 3M07303 | Paving Route 104, Towns of Sterling & Victory, Cayuga County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/01/2009 | 1250000 | 4
4235 | New York | OSWEGO |  | 23 | 3M07323 | Paving Route 104, Town and Village of Hannibal, Oswego County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/01/2029 | 545658 | 0
4236 | New York | OSWEGO |  | 23 | 3M07333 | Paving Route 104, Village of Hannibal, Oswego County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/01/2009 | 1103533 | 3.1
4237 | New York | STATEWIDE |  | 23, 24, 25 | 3M09043 | Rehabilitate multiple state-owned bridges in Cayuga, Cortland, Onondaga, Oswego and Seneca counties. This project will improve the overall condition and safety of multiple state-owned bridges. | Bridge Improvement | 11/03/2009 | 11/03/2009 | 02/26/2010 | 2140952 | 0
4238 | New York | LIVINGSTON |  | 26 | 4005503 | Resurfacing of Route 5 from the Village of Lima to Ontario County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 262000 | 2.17
4239 | New York | LIVINGSTON |  | 26 | 4005573 | Resurfacing of Route 5 from the Village of Avon to the Village of Lima | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 656000 | 5.53
4240 | New York | MONROE | ROCHESTER | 29 | 4015343 | Resurface a portion of State Route 15 from Route 252 to I-390 in the towns of Brighton and Henrietta, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new | Pavement Improvement | 07/24/2009 | 07/24/2009 | 11/30/2009 | 1981778 | 1.8
4241 | New York | WYOMING |  | 26 | 4019563 | Resurfacing of Route 19 from Route 78 to Route 19a - Town of Gainseville | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 339000 | 2.03
4242 | New York | ONTARIO |  | 29 | 4021223 | Resurfacing of Route 21 from Route 332 to Route 96 - City of Canandaigua | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/30/2010 | 861000 | 7.2
4243 | New York | ONTARIO |  | 29 | 4021243 | Resurfacing of Route 21 from Griesha Hill Road to Bopple Hill Road | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/30/2010 | 615000 | 10.92
4244 | New York | MONROE | ROCHESTER | 28 | 4031393 | Replace the Route 31F bridge over Irondequoit Creek in the Town of Perinton. (BIN 1022120) | Bridge Replacement | 12/17/2009 | 12/17/2009 | 12/30/2010 | 803000 | 0
4245 | New York | ORLEANS |  | 26 | 4031763 | Resurfacing of Route 31 from Niagara County to Salt Works Road | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 318000 | 2.4
4246 | New York | MONROE | ROCHESTER | 28, 29 | 4031793 | Resurface a portion of State Route 31F from Route 250 in the village of Fairport to the Wayne County line in the town of Perinton, Monroe County. The top layer of worn, deteriorated pavement will be r | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 1195719 | 3.78
4247 | New York | WAYNE |  | 25, 29 | 4031823 | RESURFACING OF VARIOUS FA ROUTES REGIONWIDE RT 31 | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 795000 | 7.56
4248 | New York | LIVINGSTON |  | 26 | 4036173 | Construction of a Genesee Valley Greenway Trail bridge over the Genesee River at Route 36 in the towns of Mt. Morris and Leicester, Livingston County. This new pedestrian bridge will make continuous a | Bridge Improvement | 08/12/2009 | 08/12/2009 | 12/31/2010 | 1884379 | 0
4249 | New York | LIVINGSTON |  | 26 | 4036183 | Resurface a portion of State Route 36 from the Steuben County line to Route 63 and from Route 63 to Route 436 in town of Dansville, Livingston County. The top layer of worn, deteriorated pavement will | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/19/2009 | 664113 | 2.32
4250 | New York | LIVINGSTON |  | 26 | 4036213 | Resurfacing of Route 36 from Route 20 to Route 5 | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 696000 | 7.38
4251 | New York | WYOMING |  | 26 | 4039493 | Install edge drain on State Route 39 from Route 98 to Eagle Road in towns of Arcade and Eagle, Wyoming County. Edge drain will improve the proper draining of storm-water runoff and aid in prevention o | Pavement Improvement | 05/26/2009 | 05/26/2009 | 07/10/2009 | 700515 | 6.19
4252 | New York | WYOMING |  | 26 | 4039523 | Resurfacing of Route 39, Wyoming County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 520000 | 5.65
4253 | New York | MONROE | ROCHESTER | 29 | 4064103 | Resurfacing of Route 64 from Route 5 & 20 in Ontario/Monroe County | Pavement Improvement | 08/04/2009 | 08/04/2009 | 08/30/2010 | 679000 | 14.45
4254 | New York | ONTARIO |  | 29 | 4064113 | Resurfacing of Route 64 from Dugway Road To Route 5&20 | Pavement Improvement | 07/16/2009 | 07/16/2009 | 10/30/2009 | 750000 | 7.01
4255 | New York | GENESEE |  | 26 | 4077063 | Resurface a portion of State Route 77 from Route 20 to Route 5 and on Route 5 from Route 33 to the Corfu village line in the towns of Darien and Pembroke and the village of Corfu, Genesee County. The | Pavement Improvement | 05/26/2009 | 05/26/2009 | 12/31/2009 | 2910000 | 16.04
4256 | New York | WAYNE |  | 25, 26 | 4088183 | Resurfacing of Route 88 from Village of Newark to Route 104 | Pavement Improvement | 08/04/2009 | 08/04/2009 | 10/30/2009 | 356000 | 12.25
4257 | New York | MONROE | ROCHESTER | 29 | 4096513 | Resurface a portion of State Route 96 from Kreag Road in the town of Perinton, Monroe County, to Route 64 in the town of Pittsford, Monroe County. The top layer of worn, deteriorated pavement will be | Pavement Improvement | 08/03/2009 | 08/03/2009 | 11/19/2009 | 940000 | 2.61
4258 | New York | ONTARIO |  | 29 | 4096523 | Resurface a portion of State Route 96 from Rt. 88 to Lester Road in the village of Phelps, Ontario County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt an | Pavement Improvement | 07/23/2009 | 07/23/2009 | 09/03/2009 | 409896 | 1.8
4259 | New York | GENESEE | ROCHESTER | 26 | 4098393 | Repave Rt. 98 between Rt. 5 (Main St.) and Noonan Drive in the City of Batavia, Genesee County. | Pavement Improvement | 07/06/2009 | 07/06/2009 | 11/30/2009 | 529281 | 1.18
4260 | New York | MONROE | ROCHESTER | 26 | 4104423 | Resurface a portion of State Route 104 from Route 259 to Route 261 in the towns of Greece and Parma, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new a | Pavement Improvement | 07/14/2009 | 07/14/2009 | 10/12/2009 | 1320000 | 2.01
4261 | New York | WYOMING |  | 26 | 4246083 | Resurfacing of Route 246 from Route 39 to the North Village Line | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 152000 | 1.01
4262 | New York | LIVINGSTON |  | 26 | 4256063 | Paving on Route 256 from Sliker Hill Road to Route 20A | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 1330000 | 9.83
4263 | New York | MONROE | ROCHESTER | 26 | 4259063 | Resurface a portion of State Route 259 from Colby Street to Big Ridge Road in town of Ogden and village of Spencerport, Monroe County. The top layer of worn, deteriorated pavement will be removed and | Pavement Improvement | 06/25/2009 | 06/25/2009 | 10/29/2009 | 1406970 | 1.67
4264 | New York | MONROE | ROCHESTER | 26 | 4261063 | Resurfacing of Route 261 from Route 104 to Route 18 | Pavement Improvement | 07/16/2009 | 07/16/2009 | 10/30/2009 | 329000 | 2.62
4265 | New York | GENESEE |  | 26 | 4262063 | Resurfacing of Route 262 from Route 98 to Route 237 | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 557000 | 6.51
4266 | New York | ONTARIO | ROCHESTER | 29 | 4332053 | Repave Rt. 332 from Rt. 5 & 20 to Chapel Street in the City of Canandaigua, Ontario County. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 10/30/2009 | 1792450 | 3.42
4267 | New York | WYOMING |  | 26 | 4354063 | Resurfacing of Route 354 from Erie County Line to Route 98 | Pavement Improvement | 07/16/2009 | 07/16/2009 | 10/30/2009 | 872000 | 11.21
4268 | New York | ONTARIO |  | 29 | 4364023 | Resurfacing of Route 364 from Gateway Road to Route 5/20 | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 436000 | 5.29
4269 | New York | MONROE | ROCHESTER | 29 | 4390553 | Resurface a portion of Interstate 390 from the New York State Thruway to the interchange of Interstate 590 in the town of Henrietta, Monroe County. The top layer of worn, deteriorated pavement will be | Pavement Improvement | 08/25/2009 | 08/25/2009 | 08/30/2010 | 2200248 | 5.07
4270 | New York | ONTARIO |  | 29 | 4488043 | Resurfacing of Route 488 from Route 21 To Route 96, Ontario County. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 10/30/2009 | 268000 | 9.13
4271 | New York | MONROE | ROCHESTER | 26, 29 | 4531063 | Resurface a portion of State Route 531 from Route 36 in the town of Ogden, Monroe County, to I-490 in the town of Gates, Monroe County. The top layer of worn, deteriorated pavement will be removed and | Pavement Improvement | 07/07/2009 | 07/07/2009 | 11/20/2010 | 2430400 | 7.56
4272 | New York | STATEWIDE | ROCHESTER | 25, 26, 28, 29 | 4805653 | Apply a preventative maintenance treatment to seal cracks in the pavement along various state highways in Genesee and Monroe counties. This type of work keeps the highway system in a state of good rep | Pavement Improvement | 07/16/2009 | 07/16/2009 | 10/30/2009 | 263924 | 0
4273 | New York | STATEWIDE | ROCHESTER | 25, 26, 28, 29 | 4805693 | Wash bridges and seal bridge decks at selected locations in Wayne, Ontario, Monroe, Livingston, Orleans, Genesee and Wyoming counties. This type of work keeps the system in a state of good repair. | Bridge Improvement | 07/27/2009 | 07/27/2009 | 08/26/2009 | 525076 | 0
4274 | New York | STATEWIDE | ROCHESTER | 25 | 4805733 | Regionwide Resurfacing Of Rural/Low Volume Highways | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 569000 | 0
4275 | New York | MONROE | ROCHESTER | 26, 28 | 4947213 | Resurfacing of Route 947A -Lake Ontario State Parkway | Pavement Improvement | 08/10/2009 | 08/10/2009 | 08/30/2010 | 864000 | 6.79
4276 | New York | GENESEE |  | 26 | 4LS0003 | A Genesee County project to resurface a portion of Batavia-Stafford Town Line Road from Route 33 to Assemblyman R. Steven Hawley Drive, and a portion of Assemblyman R. Steven Hawley Drive from Bank St | Pavement Improvement | 08/01/2009 | 08/01/2009 | 12/30/2009 | 860000 | 0
4277 | New York | LIVINGSTON |  | 26 | 4LS0023 | A Livingston County project to resurface a portion of Sliker Hill Road from Route 256 to Route 15 in the town of Conesus, and a portion of Perry Road from Route 36 to Route 20A in the town of Leiceste | Pavement Improvement | 08/05/2009 | 08/05/2009 | 12/31/2009 | 1601700 | 0
4278 | New York | LIVINGSTON |  | 26 | 4LS0043 | A village of Dansville project to resurface a portion of Maple Avenue from Route 63 to Route 36 in the village of Dansville, Livingston County. The top layer of worn, deteriorated pavement will be rem | Pavement Improvement | 08/25/2009 | 08/25/2009 | 12/30/2009 | 370000 | 0
4279 | New York | LIVINGSTON |  | 26 | 4LS0073 | A village of Geneseo project to resurface a portion of Lima Road from North Street to Geneseo village line in the village of Geneseo, Livingston County. The top layer of worn, deteriorated pavement wi | Pavement Improvement | 09/09/2009 | 09/09/2009 | 12/30/2009 | 285000 | 0
4280 | New York | MONROE | ROCHESTER | 28 | 4LS0083 | Upgrade bridges on Driving Park, East Main Street, Main Street, Court Street, Elmwood Avenue, Lake Avenue, Andrews Street and Ford Street in the City of Rochester, Monroe County, with appropriate prev | Bridge Improvement | 07/20/2009 | 07/20/2009 | 01/06/2010 | 2002000 | 0
4281 | New York | MONROE | ROCHESTER | 28, 29 | 4LS0153 | A city of Rochester project to resurface a portion of Thurston Road from Brooks Avenue to Chili Avenue in the city of Rochester, Monroe County. A thin layer of asphalt will be placed on top of the exi | Pavement Improvement | 11/24/2009 | 11/24/2009 | 06/30/2010 | 2301000 | 0
4282 | New York | MONROE | ROCHESTER | 28 | 4LS0273 | Streetscape Enhancements on North Clinton Avenue | Other | 09/30/2009 | 09/30/2009 | 06/30/2010 | 1100000 | 0
4283 | New York | MONROE | ROCHESTER | 26, 28, 29 | 4LS0323 | A Monroe County project to resurface Chili Center Coldwater Road from Route 33A to Westside Drive in the town of Chili, Elmgrove Road from Route 33 to Route 531 in the town of Gates, North Greece Road | Pavement Improvement | 08/25/2009 | 08/25/2009 | 06/30/2010 | 3555000 | 0
4284 | New York | MONROE |  | 25, 26 | 4LS0343 | Resurface various roads owned by Monroe County including: Dewey Avenue, Long Pond Road, English Road, East Ridge Road, North Goodman Street, Thomas Avenue, Culver Road, Panorama Trail, and Old Ridge R | Pavement Improvement | 07/29/2009 | 07/29/2009 | 12/30/2009 | 6104500 | 0
4285 | New York | MONROE | ROCHESTER | 26, 28 | 4LS0363 | Preventative maintenance projects on Monroe County bridges. The Flynn Road bridge in the town of Greece and the Brick School House bridge in the town of Hamlin will be deck sealed; the Redman Road and | Bridge Improvement | 09/23/2009 | 09/23/2009 | 12/31/2009 | 560000 | 0
4286 | New York | ONTARIO |  | 29 | 4LS0653 | A city of Canandaigua project to resurface a portion of Lakeshore Drive from Muar Street to S. Main Street in the city of Canandaigua, Ontario County. The top layer of worn, deteriorated pavement will | Pavement Improvement | 09/03/2009 | 09/03/2009 | 12/30/2009 | 160000 | 0
4287 | New York | ONTARIO | ROCHESTER | 29 | 4LS0663 | A city of Canandaigua project to replace the West Avenue Bridge over Sucker Brook in the city of Canandaigua, Ontario County. | Bridge Replacement | 09/03/2009 | 09/03/2009 | 08/30/2010 | 556600 | 0
4288 | New York | ONTARIO |  | 29 | 4LS0673 | An Ontario County project to resurface County Road 41 from State Route 332 to County Road 8 in the town of Farmington, Bankert Road from State Route 96 to County Road 13 in the town of Phelps and Coun | Pavement Improvement | 08/20/2009 | 08/20/2009 | 12/30/2009 | 2790000 | 0
4289 | New York | ORLEANS |  | 25 | 4LS0703 | An Orleans County project to replace signs in various municipalities around the county. | Other | 07/28/2009 | 07/28/2009 | 12/30/2009 | 200000 | 0
4290 | New York | WAYNE |  | 25 | 4LS0713 | A town of Arcadia to locally administer a project to make element-specific repairs to the Van Buren Street Bridge over CSX Railroad in the town of Arcadia, Wayne County. The deck will be sealed and wo | Bridge Improvement | 08/25/2009 | 08/25/2009 | 06/30/2010 | 475000 | 0
4291 | New York | WAYNE |  | 25 | 4LS0723 | Resurface a portion of Lake Bluff Road from Route 104 to Ridge Road in the town of Sodus, Wayne County and a portion of Newark Marion Road from Lyon Road to the gravel pit in the town of Palmyra, Wayn | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/30/2009 | 177000 | 0
4292 | New York | WAYNE |  | 25 | 4LS0763 | Resurface a portion of Atlantic Avenue from Downs Road to Route 350 in the town of Walworth, Wayne County. The top layer of worn, deteriorated pavement will be removed and replaced with new surface an | Pavement Improvement | 08/04/2009 | 08/04/2009 | 12/30/2009 | 135000 | 0.65
4293 | New York | WYOMING |  | 26 | 4LS0793 | Resurface a portion of Bixby Hill Road from Route 39 to the Cattaraugus county line in the town of Arcade, Wyoming County. The top layer of worn, deteriorated pavement will be removed and replaced wit | Pavement Improvement | 06/25/2009 | 06/25/2009 | 12/30/2009 | 700000 | 1
4294 | New York | MONROE | ROCHESTER | 25, 28, 29 | 4LSA303 | Resurface various roads owned by Monroe County including: Brighton-Henrietta Town Line Road, South Winton Road, Calkins Road, Creek Street, Whalen Road, Five Mile Line Road, Whitney Road, Philips Road | Pavement Improvement | 07/31/2009 | 07/31/2009 | 06/30/2010 | 5880000 | 0
4295 | New York | MONROE | ROCHESTER | 25, 26, 28, 29 | 4T47103 | Install detectable warning fields at more than 800 locations across the seven-county region. The installation of plastic tiles containing raised bumps will help alert pedestrians with visual impairmen | Other | 08/11/2009 | 08/11/2009 | 08/30/2010 | 279630 | 0
4296 | New York | CATTARAUGUS |  | 29 | 5006743 | Rehabilitate approximately 6.5 miles of Interstate 86 eastbound in the towns of Randolph and Cold Springs and the village of Randolph, all in Cattaraugus County. The project is addressing deterioratin | Other | 07/31/2009 | 07/31/2009 | 10/15/2009 | 900000 | 6.31
4297 | New York | CHAUTAUQUA |  | 27 | 5006753 | Rehabilitate approximately 12 miles of Interstate 86 in the Towns of Sherman, North Harmony, and Ellery, in Chautauqua County. Eleven miles eastbound and 1 mile westbound will be improved. | Pavement Improvement | 09/09/2009 | 09/09/2009 | 01/31/2011 | 2800000 | 11.63
4298 | New York | CATTARAUGUS |  | 29 | 5017283 | Replace two culverts on NY Route 242 in the towns of Ellicottville and Little Valley, Cattaraugus County. This project will eliminate culvert deficiencies and ensure good structural condition. | Other | 06/23/2009 | 06/23/2009 | 08/27/2010 | 1300637 | 0
4299 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5019233 | Repave two sections of NY Route 265 (Military Road) in Erie County. Section 1 is .4 miles in length and extends from Fletcher Street to Tonawanda Creek in the city of Tonawanda, Erie County. Section 2 | Pavement Improvement | 08/21/2009 | 08/21/2009 | 12/18/2010 | 1221901 | 1.94
4300 | New York | CHAUTAUQUA |  | 27 | 5058393 | Conduct a bridge replacement and highway resurfacing and reconstruction project in the city of Jamestown, Chautauqua County. The objective of the project is to replace the Washington Street Bridge ove | Bridge Replacement | 10/06/2009 | 10/06/2009 | 12/30/2010 | 4011173 | 0.5
4301 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5101793 | Repair culverts on US Route 219 and NY Route 400 in the towns of Boston and Concord, Erie County. This preventative maintenance work will eliminate corrosion and restore drainage elements to a state o | Other | 05/22/2009 | 05/22/2009 | 12/29/2009 | 826561 | 4.7
4302 | New York | CHAUTAUQUA |  | 27 | 5111903 | Replace the bridge for NY Route 20 over Bell Creek in the Town of Westfield, Chautauqua County. The existing bridge will be replaced with 3-side precast concrete bridge. | Bridge Replacement | 07/24/2009 | 07/24/2009 | 10/15/2010 | 1092868 | 0
4303 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5470243 | Rehabilitate the stone facade of a notable bridge carrying NY Route 198, the Scajaquada Expressway, over NY Route 384 in the City of Buffalo, Erie County. The bridge is located in the historic site of | Bridge Replacement | 08/03/2009 | 08/03/2009 | 10/07/2010 | 2383814 | 0
4304 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5512463 | Route 33 Retaining Wall Railing and Corridor Enhancements | Other | 10/23/2009 | 10/23/2009 | 12/15/2010 | 3790004 | 2.75
4305 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5580393 | Replace two highway ramp bridges at the Interstate I-190/ I-290 interchange in the Town of Tonawanda, Erie County. New bridges will be installed on new alignments to the north of the existing bridges, | Bridge Replacement | 11/06/2009 | 11/06/2009 | 12/30/2011 | 1914426 | 0
4306 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26 | 5755473 | Reconstruct Maple Road for 1.6 miles from Route 62 to Flint Road -- the entrance to State University of New York at Buffalo -- in the Town of Amherst, Erie County. The project will also reconstruct a | Pavement Improvement | 08/20/2009 | 08/20/2009 | 07/24/2011 | 7000000 | 0.43
4307 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5755993 | Construct four new local roads in support of the Inner Harbor Redevelopment Plan, City of Buffalo, Erie County. The four roads are Lloyd, Hanover, Perry, and Prime Slip. | New Construction | 09/22/2009 | 09/22/2009 | 12/18/2011 | 1900000 | 0
4308 | New York | STATEWIDE |  | 26 | 5757213 | Replace the Cedar Street Bridge over Tonawanda Creek in the town of Newstead, Erie County, and the town of Royalton, Niagara County. The bridge is in poor condition and will be reconstructed so that i | Bridge Replacement | 08/11/2009 | 08/11/2009 | 06/15/2011 | 1998000 | 0
4309 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759213 | Repave 1.6 miles of Main Street (NY Route 104) from Ontario Street to Pierce Street in the city of Niagara Falls, Niagara County ( Main Street, Walnut Avenue to Ontario Avenue; 11th Street, Lockport S | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/15/2009 | 1034000 | 0
4310 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759223 | Repave 0.4 miles of Packard Road from Niagara Falls Bou levard to the CSX Bridge in the City of Niagara Falls, Niagara County. The project will address deteriorating pavement conditions. | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/15/2009 | 939000 | 0
4311 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759233 | Repave 1.6 miles of Pine Avenue US Route 62 to Main Street (NY Route 104) in the city of Niagara Falls, Niagara County. The project will address deteriorating pavement conditions. | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/15/2009 | 1441000 | 0
4312 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759243 | Repave a two-mile section of Townline Road from Beach Ridge Road to the Bridge Over Bull Creek in the towns of Pendleton and Wheatfield in Niagara County to address deteriorating pavement conditions. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/15/2010 | 1990000 | 1.7
4313 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759253 | Conduct guide rail end replacements at approximately 50 locations throughout Niagara County to meet current federal standards. | Other | 08/10/2009 | 08/10/2009 | 08/15/2010 | 210000 | 0
4314 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759263 | Repave a 3.1 mile section of Hartland Road, from Townline Road to Lake Road (NY Route 18), in the town of Somerset, Niagara County. The roadway will be paved to address deteriorating pavement conditio | Pavement Improvement | 08/10/2009 | 08/10/2009 | 08/15/2010 | 450000 | 2.95
4315 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759273 | Repave a one-mile section of Nash Road from Cherry Hill Road to Steig Road in the town of Wheatfield, Niagara County. The paving address deteriorating pavement conditions. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 08/15/2011 | 580000 | 0.93
4316 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759283 | Improve storm water management along Tonawanda Creek Road in the Town of Pendleton, Niagara County. | Other | 08/10/2009 | 08/10/2009 | 08/15/2011 | 80000 | 1.81
4317 | New York | CHAUTAUQUA |  | 27 | 5759293 | Repave 4.1 miles of NY Route 430 from County Route 128/44 to County Route 13 in the Town of Ellery, Chautauqua County. The project will address deteriorating pavement conditions. | Pavement Improvement | 10/20/2009 | 10/20/2009 | 12/15/2009 | 803504 | 0
4318 | New York | CHAUTAUQUA |  | 27 | 5759303 | Repave 5.6 miles of Hunt Road (County Route 82/32) from County Route 43 to the Jamestown city line in the towns of Busti, Ellicott, and North Harmony, in Chautauqua County. The project will address de | Pavement Improvement | 10/06/2009 | 10/06/2009 | 12/15/2009 | 1177686 | 0
4319 | New York | CATTARAUGUS |  | 29 | 5759313 | Repave 1.7 miles of State Route 417 (West State Street) from the Olean city line to State Route 16 in the City of Olean, Cattaraugus County. The project will address deteriorating pavement conditions. | Pavement Improvement | 10/20/2009 | 10/20/2009 | 06/30/2010 | 904963 | 1.7
4320 | New York | CHAUTAUQUA |  | 27 | 5759323 | Repave 0.2 miles of Doughty Street from the NY Route 60 to Lincoln Avenue in the City of Dunkirk, Chautauqua County. The project will address deteriorating pavement conditions. | Pavement Improvement | 10/19/2009 | 10/19/2009 | 06/30/2010 | 498925 | 0
4321 | New York | CATTARAUGUS |  | 29 | 5759343 | Repave 1.2 miles of County Route 4 (Broadway Road) in the Town of Persia, Cat taraugus County. The project will address deteriorating pavement conditions. | Pavement Improvement | 09/03/2009 | 09/03/2009 | 11/01/2009 | 1100000 | 0
4322 | New York | CATTARAUGUS |  | 29 | 5759363 | Repave 2.1 miles of NY Route 417 (Wildwood Avenue) from Linwood Avenue to the east City line in the City of Salamanca, Cattaraugus County. The project will address deteriorating pavement conditions. | Pavement Improvement | 09/10/2009 | 09/10/2009 | 12/15/2009 | 1210000 | 0
4323 | New York | CHAUTAUQUA |  | 27 | 5759413 | Enhancement project that will construct a two-classroom building for traffic and personal safety instruction at the Chautauqua Children's Safety Education Village in the town of North Harmony, Chautau | Transportation Enhancements | 09/15/2009 | 09/15/2009 | 08/15/2011 | 1760000 | 0
4324 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5805903 | Replace nine traffic signals and 41 pedestrian signals at various locations in Erie County. | Other | 08/21/2009 | 08/21/2009 | 12/31/2010 | 941570 | 0
4325 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5806113 | Replace selected signs on state highways throughout the City of Buffalo, towns of Amherst and Cheektowaga and Village of Williamsville, Erie County. | Other | 07/03/2009 | 07/03/2009 | 08/23/2010 | 200000 | 0
4326 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 28 | 5807623 | Repair and replace bridge joints along Interstate 290 in the towns of Tonawanda and Amherst, Erie County. Joints require periodic repair to prevent water from penetrating onto other bridge elements, | Bridge Improvement | 10/23/2009 | 10/23/2009 | 11/15/2010 | 200000 | 0
4327 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27, 28 | 5807653 | Paint eight bridges in various locations in the city of Buffalo and town of Tonawanda, Erie County. The bridge painting is preventive maintenance. | Bridge Improvement | 08/13/2009 | 08/13/2009 | 06/03/2011 | 500000 | 0
4328 | New York | STATEWIDE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5808233 | Install approximately 285 detectable warnings at various locations in the city of Buffalo and the town of Cheektowaga in Erie County, and the city of Niagara Falls and the town of Wheatfield in Niagar | Transportation Enhancements | 08/21/2009 | 08/21/2009 | 08/15/2010 | 263066 | 0
4329 | New York | CATTARAUGUS |  | 29 | 5810433 | Resurface approximately three miles of pavement on US Route 219 and NY Route 417 in the City of Salamanca, Cattaraugus County, and Allegany Reservation of the Seneca Nation of Indians. The top layer o | Pavement Improvement | 07/02/2009 | 07/02/2009 | 09/30/2009 | 1322909 | 6.24
4330 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5810463 | Mill and repave highway access ramps with a single course overlay. Ramp locations, all in Erie County, include: N.Y. Route 78 in the towns of Clarence and Amherst, N.Y. Route 263 in the town of Amhers | Other | 07/23/2009 | 07/23/2009 | 10/19/2009 | 567090 | 1.46
4331 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27 | 5810473 | Resurface approximately 1.5 miles of pavement on NY Route 78 in the Village of Depew and towns of Lancaster and Cheektowaga, Erie County. The top layer of worn, deteriorated pavement will be removed a | Pavement Improvement | 05/28/2009 | 05/28/2009 | 10/22/2009 | 726874 | 1.44
4332 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5810513 | Repave Route 957A, Robert Moses Parkway, from Interstate 190 to JB Daly Boulevard in the City of Niagara Falls, Niagara County. The top layer of worn, deteriorated pavement will be removed and replace | Pavement Improvement | 07/23/2009 | 07/23/2009 | 12/10/2009 | 1242226 | 3.23
4333 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5810563 | Clean and repair closed drainage systems along State Routes 198, 78, 277, 5 and 425 in the towns of Tonawanda, Amherst and Clarence and the city of Buffalo, Erie County. Collapsed drainage structures | Other | 08/06/2009 | 08/06/2009 | 12/29/2009 | 261041 | 5.04
4334 | New York | STATEWIDE |  | 26, 27, 28, 29 | 5810613 | Replace two overhead sign structures on State Route 400 in the towns of West Seneca and Elma and also install a 511 system signage region-wide. 511 is the state's latest traveler-advisory system. With | Other | 08/12/2009 | 08/12/2009 | 06/15/2010 | 491210 | 0
4335 | New York | ERIE |  | 27, 28 | 5810623 | Replace joints on various bridges along the NY Route 33 corridor in the city of Buffalo and town of Cheektowaga, Erie County. | Bridge Improvement | 07/03/2009 | 07/03/2009 | 12/31/2009 | 481358 | 0
4336 | New York | STATEWIDE |  | 26, 27, 28 | 5810723 | Install signs for bike route 517 in Erie, Niagara, and Chautauqua counties. The project also includes sidewalk construction at the intersection of State Route 263 and State Route 270 in the Town of Am | Transportation Enhancements | 10/27/2009 | 10/27/2009 | 06/30/2010 | 318340 | 0
4337 | New York | CATTARAUGUS |  | 29 | 5V09133 | Repave portions of State Route 394 totaling 6.2 miles in the towns of Cold Spring, Conewango, Napoli and Randolph and the village of East Randolph, in Cattaraugus County. The new pavement will address | Pavement Improvement | 10/08/2009 | 10/08/2009 | 06/15/2010 | 720000 | 6.16
4338 | New York | CATTARAUGUS |  | 29 | 5V09153 | Repave a five-mile portion of U.S. Route 62, from the Chautauqua County line to Youngs Road in the towns of Conewango and Leon, Cattaraugus County. | Pavement Improvement | 09/22/2009 | 09/22/2009 | 06/18/2010 | 380000 | 3.1
4339 | New York | CATTARAUGUS |  | 29 | 5V09163 | Conduct pavement crack sealing on approximately 100 miles of roads throughout Cattaraugus County. Asphalt pavement will be cleaned and sealant will be applied. | Pavement Improvement | 09/01/2009 | 09/01/2009 | 12/15/2009 | 280000 | 0
4340 | New York | STATEWIDE |  | 27, 29 | 5V09213 | Repave approximately 21 miles of Interstate 86 in the towns of Ellery, Ellicott and Poland, the village of Falconer and the city of Jamestown in Chautauqua County, and the town and village of Randolph | Pavement Improvement | 09/01/2009 | 09/01/2009 | 06/18/2010 | 1780000 | 21.34
4341 | New York | CATTARAUGUS |  | 27 | 5V09223 | Repave a 2.5 mile bypass from Interstate 86 to NY Route 430 in the town of Ellery and village of Bemus Point, Chautauqua County. A single course overlay will be applied to address deteriorating paveme | Pavement Improvement | 09/22/2009 | 09/22/2009 | 06/18/2010 | 380000 | 1.62
4342 | New York | CHAUTAUQUA |  | 27 | 5V09253 | Conduct pavement crack sealing on approximately 100 miles of roads throughout Chautauqua County. Asphalt pavement will be cleaned and sealant will be applied. | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/15/2009 | 250000 | 0
4343 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5V09323 | Seal pavement cracks on federal aid-eligible routes in northern Erie County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pave | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/15/2010 | 128297 | 0
4344 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09413 | Repave a 0.8 mile portion of US Route 20, from Cazenovia Creek to Seneca Street (NY Route 16) in the towns of West Seneca and Elma, Erie County. | Pavement Improvement | 09/22/2009 | 09/22/2009 | 10/15/2010 | 240000 | 1.54
4345 | New York | ERIE |  | 27 | 5V09423 | Repave a one-mile portion of U.S. Route 20A (Quaker Street) in the village of Orchard Park, Erie County. The project will address deteriorating pavement conditions. The top layer of worn, deteriorated | Pavement Improvement | 09/21/2009 | 09/21/2009 | 09/15/2009 | 130000 | 1.02
4346 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09433 | Repave a 5.8-mile-long section of N.Y. Route 39 in Erie County, from N.Y. Route 75 in the town of Collins to Trevett Road in the town of Concord. The project will address deteriorating pavement condit | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/15/2010 | 447857 | 5.77
4347 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09443 | Repave a 3.5-mile-long portion of N.Y. Route 249 in the Town of North Collins, Erie County. The project will address deteriorating pavement conditions. The top layer of worn, deteriorated pavement wil | Pavement Improvement | 09/23/2009 | 09/23/2009 | 09/15/2009 | 660000 | 3.48
4348 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09463 | Seal pavement cracks on federal aid-eligible routes in southern Erie County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pave | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/15/2010 | 252000 | 0
4349 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09513 | Repave a 3.7-mile-long portion of N.Y. Route 425 in the town of Cambria, Niagara County. The paving will extend from Upper Mountain Road to N.Y. Route 104. It will address deteriorating pavement condi | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/15/2010 | 727696 | 3.74
4350 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09523 | Repave a 10.4-mile-long portion of N.Y. Route 77 in the towns of Lockport and Royalton, Niagara County. The project will extend from N.Y. Route 31 to the Genesee County line. It will address deteriora | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/15/2010 | 1922529 | 10.44
4351 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26, 28 | 5V09533 | Repave a 5.8-mile-long portion of NY Route 429 in Niagara County. The project will extend from Lockport Road in the town of Wheatfield to N.Y. Route 104 in the towns of Cambria and Lockport, where the | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/15/2010 | 1325383 | 5.81
4352 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26, 28 | 5V09543 | Seal pavement cracks on federal aid-eligible routes in Niagara County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pavements | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/15/2010 | 142988 | 0
4353 | New York | STEUBEN |  | 29 | 6008513 | Build embankment and pavement on a five-mile section of relocated US Route 15 in the Town of Lindley, Steuben County. This project is the first phase of a staged project to build a four lane highway w | Other | 09/14/2009 | 09/14/2009 | 08/31/2012 | 5000000 | 0
4354 | New York | SCHUYLER |  | 29 | 6017213 | Replace the bridge carrying State Route 224 over Catharine Creek in the village of Montour Falls, Schuyler County. | Bridge Improvement | 01/13/2010 | 01/13/2010 | 12/15/2010 | 1795935 | 0
4355 | New York | ALLEGANY |  | 29 | 6021143 | Replace the bridge carrying State Route 244 over the north branch of Phillips Creek in the town of Amity, Allegany County. | Bridge Replacement | 01/14/2010 | 01/14/2010 | 12/15/2010 | 1450629 | 0
4356 | New York | STEUBEN |  | 29 | 6037173 | Replace the bridge on Route 415 over Wolf Run Creek in the town of Campbell, Steuben County. | Bridge Replacement | 05/20/2009 | 05/20/2009 | 12/30/2009 | 1574989 | 0
4357 | New York | ALLEGANY |  | 29 | 6056233 | Replace the bridge carrying State Route 417 over Dyke Creek in the town of Andover, Allegany County. | Bridge Replacement | 01/12/2010 | 01/12/2010 | 12/11/2010 | 1317359 | 0
4358 | New York | STEUBEN |  | 29 | 6066843 | Replace the I-86 bridge over Route 415 in the town of Painted Post, Steuben County. | Bridge Replacement | 05/15/2009 | 05/15/2009 | 11/30/2010 | 4595880 | 0
4359 | New York | CHEMUNG | ELMIRA | 29 | 6754133 | A project to reconstruct Washington Avenue, from Davis Street to Walnut Street, in the city of Elmira, Chemung County. | Pavement Improvement | 12/07/2009 | 12/07/2009 | 06/30/2010 | 741000 | 0
4360 | New York | ALLEGANY |  | 29 | 6754293 | Resurface seven miles of County Route 12 from the Village of Alfred to State Route 417 in the towns of Andover, Ward, and Alfred, Allegany County. Existing pavement will be overlaid to provide a smoot | Pavement Improvement | 08/20/2009 | 08/20/2009 | 11/30/2009 | 795290 | 0
4361 | New York | SCHUYLER |  | 29 | 6754303 | Resurface 2.5 miles of County Route 16 from Meads Hill Road to Townsend Road in the Town of Dix, Schuyler County. The existing pavement will be resurfaced to provide a smooth surface and prolong the l | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 241000 | 0
4362 | New York | YATES |  | 29 | 6754313 | Resurface 1.8 miles of County Route 32 from County Route 29 to County Route 33 in the Town of Jerusalem, Yates County. Existing pavement will be overlaid to provide a smooth surface and prolong the li | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 233929 | 0
4363 | New York | STEUBEN |  | 29 | 6754323 | Resurface 1.9 miles of County Route 14 from County Route 15 south in the Town of Bath, Steuben County. The existing pavement will be recycled and resurfaced with new asphalt. | Pavement Improvement | 08/06/2009 | 08/06/2009 | 11/30/2009 | 228000 | 0
4364 | New York | STEUBEN |  | 29 | 6754333 | Resurface 3.3 miles of County Route 14 from County Route 69 north in the towns of Bath and Howard, Steuben County. The existing pavement will be recycled and resurfaced with new asphalt. | Pavement Improvement | 07/16/2009 | 07/16/2009 | 11/30/2009 | 435000 | 0
4365 | New York | STEUBEN |  | 29 | 6754343 | Resurface four-tenths of a mile of East Avenue from Main Street to Addison Street in the Village of Arkport, Steuben County. The existing deteriorated pavement surface will be removed and replaced wit | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 81000 | 0
4366 | New York | STEUBEN |  | 29 | 6754353 | Resurface 1.2 miles of streets in the City of Hornell, Steuben County. The project will overlay the existing pavement on portions of Thatcher, North Church, Erie, Center, and Adsit Streets to provide | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 151000 | 0
4367 | New York | STEUBEN | ELMIRA | 29 | 6754443 | Resurface two-tenths of a mile of West Third Street in the City of Corning, Steuben County. The existing deteriorated pavement surface, from Walnut Street to State Street, will be removed and replaced | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 22000 | 0
4368 | New York | STEUBEN | ELMIRA | 29 | 6754453 | Resurface one-tenth of a mile of East Third Street from Cedar Street to Pine Street in the City of Corning, Steuben County. The existing deteriorated pavement surface will be removed and replaced with | Pavement Improvement | 08/11/2009 | 08/11/2009 | 11/30/2009 | 19000 | 0
4369 | New York | STEUBEN | ELMIRA | 29 | 6754463 | Resurface four-tenths of a mile of West William Street from Pulteney Street to Bissell Avenue in the City of Corning, Steuben County. The existing deteriorated pavement surface will be removed and rep | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 89000 | 0
4370 | New York | STEUBEN |  | 29 | 6803963 | Rehabilitate culverts in various locations in the towns of Urbana and Pulteney, Steuben County. | Pavement Improvement | 04/20/2009 | 04/20/2009 | 11/30/2009 | 979870 | 0
4371 | New York | STATEWIDE |  | 29 | 6804183 | Wash bridges and seal bridge decks at various locations in Allegany and Steuben counties. | Bridge Improvement | 05/14/2009 | 05/14/2009 | 09/30/2009 | 629132.47 | 0
4372 | New York | STATEWIDE |  | 29 | 6804223 | A project to remove hazardous trees along select state rights-of-way in Allegany, Schuyler, Steuben, and Yates counties. | Other | 12/15/2009 | 12/15/2009 | 05/30/2010 | 243469 | 0
4373 | New York | STATEWIDE |  | 29 | 6804233 | Sidewalk Reconstruction for ADA compliance, Montour Falls, Addison, Southport. | Transportation Enhancements | 10/27/2009 | 10/27/2009 | 06/30/2010 | 207073 | 1.37
4374 | New York | STATEWIDE |  | 29 | 6804273 | Rock Slope Remediation of 10 sites in Allegany & Steuben Counties. | Other | 01/14/2010 | 01/14/2010 | 06/30/2010 | 495779 | 0.1
4375 | New York | STATEWIDE |  | 29 | 6804283 | Paint bridges on I-86 and I-390 at various locations in Allegany and Steuben counties. | Bridge Improvement | 07/14/2009 | 07/14/2009 | 10/31/2010 | 1085544 | 0
4376 | New York | STATEWIDE |  | 29 | 6804293 | Rehabilitate bridges in various locations in Allegany and Steuben counties. | Bridge Improvement | 06/15/2009 | 06/15/2009 | 10/31/2009 | 444923 | 0
4377 | New York | ALLEGANY |  | 29 | 6804333 | Repair 21 culverts on Interstate 86 in the towns of Cuba and Friendship, Allegany County. The project includes drainage structure replacement and culvert relining. | Other | 08/03/2009 | 08/03/2009 | 06/30/2010 | 916349 | 0
4378 | New York | ST LAWRENCE |  | 23 | 7752473 | Replace the County Route 39 Bridge over the Grasse River in the Town of Louisville, St. Lawrence County. This project involves replacing the historic stone arch bridge with a steel structure adjacent | Bridge Replacement | 08/03/2009 | 08/03/2009 | 11/09/2011 | 3653885 | 0
4379 | New York | JEFFERSON |  | 23 | 7752583 | A project to replace the Lisk Bridge carrying County Route 69 over Sandy Creek in the Town of Adams, Jefferson County. The new structure will be built adjacent to the existing bridge. Improvements w | Bridge Replacement | 10/09/2009 | 10/09/2009 | 01/21/2011 | 2389999.53 | 0
4380 | New York | FRANKLIN |  | 23 | 7752913 | Replace the Willow Street Bridge over the Salmon River in the Village of Malone, Franklin County. This project involves replacing the existing steel structure with a concrete structure at the same loc | Bridge Replacement | 08/04/2009 | 08/04/2009 | 11/03/2010 | 1361000 | 0
4381 | New York | LEWIS |  | 23 | 7752973 | Pave County Route 29, West Road, in the Town of Martinsburg, Lewis County. This project involves the rehabilitation of nearly three miles of roadway from Cemetery Road to State Route 26. | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/07/2009 | 1157038 | 0
4382 | New York | CLINTON |  | 23 | 7753033 | Replace the Silver Lake Road Bridge over the Saranac River in the Town of Black Brook, Clinton County. The existing steel bridge will be replaced with a concrete structure at the same location. | Bridge Replacement | 09/23/2009 | 09/23/2009 | 08/10/2010 | 1529682 | 0
4383 | New York | CLINTON |  | 23 | 7753103 | Resurface approximately one mile of Oak Street, a Plattsburgh city street, and one mile of North Catherine Street (State Route 22), also in Plattsburgh. The streets, which run parallel to each other, | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/02/2009 | 384903 | 3.33
4384 | New York | JEFFERSON |  | 23 | 7753113 | Resurface Arsenal Street and Washington Street in the City of Watertown | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/02/2009 | 353116 | 1.79
4385 | New York | STATEWIDE |  | 23 | 7804393 | Replace five intersection signal systems in Clinton, Franklin and Jefferson counties. These signal improvements will maximize travel efficiency at the intersections as well as provide an added measure | Safety/Traffic Management | 07/03/2009 | 07/03/2009 | 12/31/2009 | 624067 | 0
4386 | New York | STATEWIDE |  | 23 | 7804453 | Restore the protective paint on eight bridges in Jefferson and St. Lawrence counties. Structures to be addressed in the contract include Interstate bridges on I-81 in Jefferson County, as well as a pa | Bridge Improvement | 07/14/2009 | 07/14/2009 | 07/30/2010 | 3080301 | 0
4387 | New York | STATEWIDE |  | 23 | 7804553 | Provide much-needed maintenance to approximately 500 miles of highway in Lewis, Jefferson, St. Lawrence, Franklin and Clinton counties. This work involves cleaning and sealing cracks in the pavement t | Pavement Improvement | 07/03/2009 | 07/03/2009 | 06/30/2010 | 1060415 | 0
4388 | New York | STATEWIDE |  | 23 | 7804573 | Rehabilitate four large culverts in Jefferson and St. Lawrence counties. The culverts are located on State Routes 72, 184 and 342 and will be receiving new linings as well as inlet and outlet cleaning | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/22/2009 | 2873297 | 0
4389 | New York | STATEWIDE |  | 23 | 7804733 | Clean and repaint nine state highway bridges in order to extend their useful service life. The project includes bridges carrying State Routes 22, 37, 37 C, 420 and 458 and U.S. Route 11 in Franklin, C | Bridge Improvement | 08/20/2009 | 08/20/2009 | 03/17/2010 | 3433155 | 0
4390 | New York | STATEWIDE |  | 23 | 7804763 | Repair bridges in Lewis, Jefferson, St. Lawrence, Franklin and Clinton counties. This work will help curb deterioration and improve overall bridge conditions. | Bridge Improvement | 08/26/2009 | 08/26/2009 | 07/02/2010 | 2200000 | 0
4391 | New York | ST LAWRENCE |  | 23 | 7805033 | Provide needed maintenance work to two bridges in St. Lawrence County. One structure is on State Route 11B and crosses the East Branch of the St. Regis River while the second is on State Route 420 and | Bridge Improvement | 06/03/2009 | 06/03/2009 | 12/24/2009 | 1340812 | 0
4392 | New York | STATEWIDE |  | 23 | 7805053 | Replacing deteriorated guide rail in the Adirondack Park in Clinton Franklin and St. Lawrence counties. | Safety/Traffic Management | 07/03/2009 | 07/03/2009 | 11/30/2009 | 1196390 | 0
4393 | New York | STATEWIDE |  | 23 | 7805213 | Reconstruct 1.5 miles of sidewalks and approximately 100 sidewalk ramps to bring them into compliance with federal Americans with Disabilities Act guidelines. Construction will focus on sidewalks and | Other | 07/31/2009 | 07/31/2009 | 07/30/2010 | 702182 | 0
4394 | New York | JEFFERSON |  | 23 | 7BRD083 | Construct two new traffic lanes and enhance shoulders on Interstate 81 on Wellesley Island in the Town of Orleans, Jefferson County. The improvements will help expedite border crossing movements and e | Pavement Widening | 08/20/2009 | 08/20/2009 | 12/31/2009 | 1471232 | 0.18
4395 | New York | CLINTON |  | 23 | 7V09113 | Resurface 1.3 Miles of Route 374, Village of Dannemora | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 240000 | 1.3
4396 | New York | CLINTON |  | 23 | 7V09123 | Resurface 1.4 Miles of Route 9, Village of Champlain | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 174000 | 1.4
4397 | New York | CLINTON |  | 23 | 7V09133 | Resurface 0.4 Miles Of Route 2U, US Route 11 - Vermont State Line | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 68545 | 0.4
4398 | New York | FRANKLIN |  | 23 | 7V09243 | Resurface 4.8 Miles Of Route 374, Chateaugay - Brainardsville | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/16/2009 | 517000 | 4.8
4399 | New York | FRANKLIN |  | 23 | 7V09293 | Resurface 2.0 Miles of Route 3, Saint Lawrence County -Tupper Lake | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 288000 | 2
4400 | New York | FRANKLIN |  | 23 | 7V09294 | Resurface 9.2 Miles Of Route 11, Malone - Chateaugay | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 1400000 | 9.2
4401 | New York | FRANKLIN |  | 23 | 7V09295 | Resurface 0.8 Miles Of Route 30, Malone, Elm Street & Constable Street | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 140000 | 0.5
4402 | New York | ST LAWRENCE |  | 23 | 7V09594 | Resurface 3.9 Miles Of Route 68, Pierrepont - Colton | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 412000 | 3.9
4403 | New York | ST LAWRENCE |  | 23 | 7V09595 | Resurface 1.1 Miles Of Route 184, Heuvelton Village (Union St) | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 143000 | 1.07
4404 | New York | COLUMBIA |  | 20 | 8001443 | Rehabilitate the Route 9G bridge over the Roeliff Jansen Kill in the Town of Germantown, Columbia County. | Bridge Improvement | 10/06/2009 | 10/06/2009 | 08/31/2010 | 6741732 | 0.1
4405 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8010683 | A project to install a stormwater treatment system along Route 9, adjacent the Wappingers Lake in the Village of Wappingers Falls, Dutchess County. The new system will help to reduce pollutants enter | Other | 11/26/2009 | 11/26/2009 | 01/31/2011 | 438002 | 0.29
4406 | New York | ORANGE | NEWBURGH | 22 | 8062123 | Provide much-needed general maintenance of four bridges carrying Interstate 84 in the Town of Newburgh, Orange County. The work will extend the service life of the structures. | Bridge Improvement | 09/07/2009 | 09/07/2009 | 06/30/2010 | 742023 | 0
4407 | New York | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 19 | 8093573 | Replace the Palisades Interstate Parkway bridge over Route 202 in the towns of Haverstraw and Ramapo, Rockland County. | Bridge Replacement | 06/11/2009 | 06/11/2009 | 01/31/2011 | 15085348 | 1.52
4408 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 17, 18, 19 | 8099413 | Install an automated traffic management system on the Cross County Parkway in Westchester County. The new system will include acoustic vehicle detectors that will communicate with the regional Transpo | Safety/Traffic Management | 05/29/2009 | 05/29/2009 | 12/31/2010 | 5363251 | 122.46
4409 | New York | ULSTER |  | 22 | 8177323 | Construct new bluestone sidewalks along Route 209 in the Hamlet of Stone Ridge located in the Town of Marbletown, Ulster County. The project will restore the historic sidewalk, repave a nearly one mil | Pavement Improvement | 07/09/2009 | 07/09/2009 | 05/31/2010 | 2653481 | 0.96
4410 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 20 | 8753783 | Replace the Leedsville Road (County Road 2) bridge over the Webutuck Tributary in the Town of Amenia, Dutchess County. | Bridge Replacement | 12/28/2009 | 12/28/2009 | 11/30/2010 | 593000 | 0
4411 | New York | ULSTER |  | 22 | 8756193 | Replace the Main Street bridge over the Rondout Creek in the Town of Wawarsing, Ulster County. | Bridge Replacement | 09/14/2009 | 09/14/2009 | 08/31/2010 | 4614656 | 0
4412 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8756673 | Replace the Popham Road Bridge over the Metro-North Railroad tracks in the Village of Scarsdale, Westchester County. | Bridge Replacement | 08/25/2009 | 08/25/2009 | 06/30/2010 | 13376683 | 0.01
4413 | New York | DUTCHESS |  | 19 | 8757253 | Rehabilitate the Lime Kiln Road bridge over the Ten Mile River in the Town of Dover, Dutchess County. The project will include cleaning and painting bridge members, waterproofing the bridge deck, repa | Bridge Improvement | 09/24/2009 | 09/24/2009 | 06/30/2010 | 1610100 | 0.02
4414 | New York | WESTCHESTER | POUGHKEEPSIE-NEWBURGH | 18 | 8757723 | Replace the Odell Avenue Bridge over abandoned railroad tracks in the City of Yonkers, Westchester County. | Bridge Replacement | 04/01/2009 | 04/01/2009 | 03/30/2010 | 2461927 | 0.02
4415 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 17 | 8757733 | Replace the South First Avenue Bridge over the Metro-North Railroad tracks in the City of Mount Vernon, Westchester County. | Bridge Replacement | 09/08/2009 | 09/08/2009 | 06/30/2010 | 7567157 | 0
4416 | New York | ULSTER |  | 22 | 8758023 | Rehabilitate the Beckley Drive bridge over the Fantine Kill in the Town of Wawarsing, Ulster County. | Bridge Replacement | 11/10/2009 | 11/10/2009 | 10/31/2010 | 1165000 | 0
4417 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19, 20 | 8759123 | Provide new pavement markings along select highways throughout Dutchess County. The new pavement markings will improve roadway safety by increasing their reflectivity and better delineating the travel | Other | 09/25/2009 | 09/25/2009 | 08/31/2010 | 770140 | 0
4418 | New York | ULSTER |  | 22 | 8760193 | Construct a pedestrian walkway along the Rondout Creek waterfront from Ravine Street to Route 9W in the City of Kingston, Ulster County. The project will build approximately .25 miles of walkway and 4 | Transportation Enhancements | 09/16/2009 | 09/16/2009 | 01/31/2011 | 200000 | 0
4419 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760533 | Improve intersection lighting along the Bronx River Parkway in Westchester County. The intersections include Virginia Road, Parkway Holmes Road, Fisher Lane, Old Tarrytown Road, and Strathmore Road. | Other | 08/17/2009 | 08/17/2009 | 06/30/2010 | 334018 | 0
4420 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18, 19 | 8760543 | Upgrade 60 traffic signals at select locations in Westchester County. | Other | 08/17/2009 | 08/17/2009 | 06/30/2010 | 302642 | 0
4421 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18, 19 | 8760553 | Install an automated traffic management system on the Bronx River Parkway in Westchester County. The new system will include in-pavement vehicle detectors capable of monitoring traffic volume and spee | Other | 08/17/2009 | 08/17/2009 | 12/31/2009 | 619827 | 0
4422 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18, 19 | 8760563 | Replace guide rail at select locations in Westchester County. | Other | 08/17/2009 | 08/17/2009 | 01/31/2010 | 849000 | 0
4423 | New York | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 17, 19 | 8760583 | Replace roadside guiderail at select locations on local roadways throughout Rockland County. | Other | 09/23/2009 | 09/23/2009 | 08/31/2010 | 661845 | 0
4424 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760593 | Upgrade and modernize existing traffic and pedestrian signal equipment in the City of Yonkers, Westchester County. | Safety/Traffic Management | 09/23/2009 | 09/23/2009 | 05/05/2010 | 1000000 | 0
4425 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760653 | Rehabilitate the pavement along Buckingham Avenue from East Cedar Street to Fulton Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 09/16/2009 | 09/16/2009 | 12/31/2009 | 258000 | 0
4426 | New York | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760833 | Resurface select local roadways throughout the Town of Clarkstown, Rockland County. | Pavement Improvement | 10/07/2009 | 10/07/2009 | 09/30/2010 | 801661 | 0
4427 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 17, 18, 19 | 8810893 | Provide much-needed general maintenance of 18 bridges along Interstate 684 in Westchester County, helping to extend the service life of the structures. | Bridge Improvement | 06/30/2009 | 06/30/2009 | 04/30/2010 | 13958837 | 0
4428 | New York | STATEWIDE | STATEWIDE | 19, 20 | 8810903 | Repave approximately 18 miles of state roadway in Columbia, Dutchess and Putnam counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement | Pavement Improvement | 06/18/2009 | 06/18/2009 | 05/31/2010 | 5073732 | 11.12
4429 | New York | STATEWIDE |  | 19, 22 | 8810993 | Repave approximately 22 miles of state roadway in Orange and Ulster counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings to | Pavement Improvement | 06/15/2009 | 06/15/2009 | 05/31/2010 | 4398529 | 10.06
4430 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 17, 18, 19 | 8811003 | Repave approximately 34 miles of state roadway in Westchester and Rockland counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement marki | Pavement Improvement | 06/10/2009 | 06/10/2009 | 04/30/2010 | 6853715 | 14.37
4431 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 19 | 8811123 | Pavement Resurfacing on the Taconic State Parkway Southbound | Pavement Improvement | 09/18/2009 | 09/18/2009 | 07/31/2010 | 4671430 | 3.3
4432 | New York | ULSTER |  | 22 | 8811293 | Repave approximately four miles of Route 28 between Route 212 and Route 214 in the Town of Shandaken, Ulster County. The top layer of worn, deteriorated pavement will be removed and replaced with new | Pavement Improvement | 07/23/2009 | 07/23/2009 | 06/30/2010 | 1642659 | 3.43
4433 | New York | ORANGE | NEWBURGH | 22 | 8811303 | Rebuild existing sidewalks and curb ramps along South Street from Dubois Street to Liberty Street in the City of Newburgh, Orange County. The project will improve pedestrian access and safety. | Safety/Traffic Management | 11/11/2009 | 11/11/2009 | 09/30/2010 | 237000 | 0.24
4434 | New York | TIOGA | BINGHAMTON | 22 | 9038193 | Resurface State Route 434 from the Court Street Bridge to the eastern intersection with Marshland Road in the Village and Town of Owego, Tioga County. This project will improve 11 miles of pavement, r | Pavement Improvement | 09/30/2009 | 09/30/2009 | 08/26/2010 | 5045655 | 11.08
4435 | New York | TIOGA | BINGHAMTON | 22 | 9067323 | Resurface State Route 17 between Pumpelly Creek in the Village of Owego and the Broome County line in the Town of Owego, Tioga County.The top layer of 42 miles of worn, deteriorated pavement will be r | Pavement Improvement | 08/31/2009 | 08/31/2009 | 07/09/2010 | 8355750 | 10.59
4436 | New York | TIOGA |  | 22 | 9067333 | Resurface State Route 17 between the Chemung County Line and Sackett's Creel in the Village of Waverly and towns of Barton and Nichols, Tioga County. This project will improve 40 miles of pavement, re | Pavement Improvement | 09/04/2009 | 09/04/2009 | 08/20/2010 | 6389717 | 10
4437 | New York | BROOME |  | 22 | 9067343 | Resurface 18 miles of State Route 17 in the Town of Windsor in Broome County. | Pavement Improvement | 09/09/2009 | 09/09/2009 | 06/25/2010 | 2127369 | 4.46
4438 | New York | SCHOHARIE |  | 21 | 9358093 | Rehabilitate approaches to seven bridges carrying Interstate 88 in Schoharie County. Guide rail will also be improved at these locations. | Bridge Improvement | 07/28/2009 | 07/28/2009 | 11/30/2009 | 2183315 | 0
4439 | New York | CHENANGO |  | 24 | 9752543 | Replace the bridge carrying County Route 34 over Johnson Creek in the Town of Norwich, Chenango County. | Bridge Replacement | 09/14/2009 | 09/14/2009 | 06/09/2010 | 913802 | 0
4440 | New York | BROOME | BINGHAMTON | 22 | 9753473 | Resurface Main Street from Front Street to the western city line in the City of Binghamton, Broome County. | Pavement Improvement | 09/30/2009 | 09/30/2009 | 02/05/2010 | 1033000 | 1.67
4441 | New York | DELAWARE |  | 20 | 9753493 | Resurface approximately one mile of County Route 7 from the Sullivan County line to Beaver Kill Road in the Town of Colchester, Delaware County. | Pavement Improvement | 09/10/2009 | 09/10/2009 | 10/30/2009 | 388603 | 0.95
4442 | New York | DELAWARE |  | 20 | 9753503 | Resurface County Route 21 from Leland Hull Road to Oak Hill Road in the Town of Franklin, Delaware County. | Pavement Improvement | 12/21/2009 | 12/21/2009 | 06/30/2010 | 547808 | 0
4443 | New York | CHENANGO |  | 24 | 9753513 | Install new signage on County Routes 5, 10A, 25, 32, 32A, 32B, 33, 34, 35, 36 and 44 in Chenango County. | Safety/Traffic Management | 07/27/2009 | 07/27/2009 | 02/01/2010 | 143000 | 0
4444 | New York | OTSEGO |  | 20 | 9753533 | Highway Resurfacing on County Route 33, Village of Cooperstown to Route 166, Town of Middlefield. | Pavement Improvement | 09/16/2009 | 09/16/2009 | 12/16/2009 | 832959 | 0
4445 | New York | SULLIVAN |  | 22 | 9753543 | Paint 22 local bridges in Sullivan County. | Bridge Improvement | 09/17/2009 | 09/17/2009 | 11/30/2010 | 2225000 | 0
4446 | New York | SULLIVAN |  | 22 | 9753573 | Replace approximately 132 signs on various county roads in Sullivan County. | Other | 10/20/2009 | 10/20/2009 | 01/07/2010 | 103294 | 0
4447 | New York | SULLIVAN |  | 22 | 9753583 | Upgrade five traffic signals in the towns of Fallsburg, Highland, Rockland and Tusten in Sullivan County. | Safety/Traffic Management | 10/12/2009 | 10/12/2009 | 02/18/2010 | 134400 | 0
4448 | New York | SCHOHARIE |  | 21 | 9753593 | Culvert replacement project on County Route 8 in the Town of Cobleskill, Schoharie County. | Pavement Improvement | 09/23/2009 | 09/23/2009 | 06/30/2010 | 246000 | 0
4449 | New York | OTSEGO |  | 20, 21, 24 | 9805603 | Rehabilitate twelve culverts along Interstate 88 in the Towns of Otego, Oneonta, Milford and Maryland, Otsego County. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 12/29/2009 | 2985920 | 81.93
4450 | New York | STATEWIDE | BINGHAMTON | 22, 24 | 9805633 | Paint 25 bridges on State Route 17 in Broome and Tioga counties in the towns of Vestal, Candor, Nichols, Barton and the Village of Waverly. The work will be entirely funded by ARRA. Bridge painting he | Bridge Improvement | 07/27/2009 | 07/27/2009 | 08/02/2010 | 6610000 | 0
4451 | New York | STATEWIDE |  | 20, 21, 22, 24 | 9805643 | Replace signage on state highways in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. Signs that are no longer in compliance with federal and state standards will be updated | Safety/Traffic Management | 08/12/2009 | 08/12/2009 | 09/02/2010 | 856624 | 0
4452 | New York | BROOME | BINGHAMTON | 22 | 9805653 | Bring sidewalks and curbs at select locations in the Town of Union and the villages of Johnson City and Endicott, Broome County, into compliance with Americans with Disabilities Act guidelines. | Safety/Traffic Management | 07/21/2009 | 07/21/2009 | 12/03/2009 | 459005 | 0
4453 | New York | STATEWIDE |  | 22, 24 | 9805663 | Perform bridge maintenance at various locations in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. The projects will be entirely funded by ARRA. This work includes repairs | Bridge Improvement | 08/26/2009 | 08/26/2009 | 04/30/2010 | 1000000 | 0
4454 | New York | STATEWIDE |  | 20, 21, 22, 24 | 9805673 | Perform bridge maintenance at various locations in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. The projects will be entirely funded by ARRA. This work includes repairs | Other | 08/26/2009 | 08/26/2009 | 04/30/2010 | 1084624 | 0
4455 | New York | DELAWARE |  | 20, 22 | 9805713 | Remove hazardous trees in south Delaware County. Removal of these trees will increase safety for the traveling public. | Safety/Traffic Management | 07/23/2009 | 07/23/2009 | 08/07/2009 | 485538 | 0
4456 | New York | STATEWIDE |  | 10, 12, 13, 15, 5, 6, 7, 9 | X805933 | Replace sign panels on highway s in Bronx, Kings, New York, Queens and Richmond counties. Approximately 150 overhead and 11 ground-mounted sign panels that are exhibiting deterioration, have lost refl | Safety/Traffic Management | 10/20/2009 | 10/20/2009 | 03/31/2011 | 1937815 | 0
4457 | New York | STATEWIDE |  | 15, 16, 17, 5, 7, 9 | X806253 | Repair and resurface approximately 45 miles of pavement on highways in Bronx, New York and Queens counties. In Bronx County, work will be done on the Major Deegan Expressway southbound lanes from the | Pavement Improvement | 09/09/2009 | 09/09/2009 | 09/02/2011 | 21630220 | 10.85
4458 | New York | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X806383 | Park & Ride Lot Expansion at Huguenot Ave, Richmond County | Transportation Enhancements | 10/01/2009 | 10/01/2009 | 03/16/2010 | 1942472 | 0
4459 | New York | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X806393 | Park & Ride Lot Expansion (Adding 159 Spaces) at Eltingville Transit Center- Richmond County | Other | 09/07/2009 | 09/07/2009 | 05/12/2010 | 2475075 | 0
4460 | New York | STATEWIDE |  | 10, 12, 13, 14, 15, 16, 17, 5, 6, 7, 8, 9 | X806463 | Repairs to Various State Highway Bridges- Richmond, Kings, Queens, New York and Bronx Counties | Bridge Improvement | 10/20/2009 | 10/20/2009 | 03/12/2012 | 8101708 | 0
4461 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 13, 5, 6, 9 | X806533 | THIS PROJECT WILL REPLACE SIGN PANELS, OVERHEAD AND GROUND MOUNTED, IN POOR CONDITION ON STATE HIGHWAYS WITH PANELS CONFORMING TO THE MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES. | Safety/Traffic Management | 12/23/2009 | 12/23/2009 | 12/20/2010 | 1714204 | 18.01
4462 | North Carolina | FRANKLIN |  | 2 | 0001122 | This project will repave US 1 in Franklin County from Wake County line to NC 56 to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 10/30/2009 | 2321445 | 0
4463 | North Carolina | LEE |  | 2 | 0001123 | This project will repave US 1 in Lee County from US 1 Business to Farrell Road to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/20/2009 | 2483458 | 0
4464 | North Carolina | MOORE |  | 6 | 0001124 | This project will add paved shoulders on US 1 in Moore County from Morganton Road to Aiden Road to enhance safety. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/20/2009 | 1371666 | 0
4465 | North Carolina | VANCE |  | 2 | 0001133 | This project will repave the following roadways in Vance County to improve road condition: US 1 in Kittrell, US 1/158 Business from Henderson to the Warren County line, NC 39 from Rock Springs Road to | Pavement Improvement | 12/21/2009 |  | 10/15/2010 | 2000000 | 0
4466 | North Carolina | BUNCOMBE |  | 11 | 000S531 | Preliminary engineering to rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for m | Other | 04/29/2009 | 04/29/2009 |  | 235000 | 0
4467 | North Carolina | CHOWAN |  | 1 | 000S534 | This project will clean and paint the structural steel on Bridge #26 over US 17 Bypass on SR 1234, Bridge #28 over US17 Bypass on SR 1319, Bridge #27 over NC 32 on US17 Bypass and Bridge #30 over the | Bridge Improvement | 06/15/2009 | 06/15/2009 | 11/04/2011 | 555850 | 0
4468 | North Carolina | CHOWAN |  | 1 | 000S536 | This project will relocate the lighthouse to a new foundation system, complete required hazardous material abatement, perform structural repairs, historic restoration and stabilization of the lighthou | Transportation Enhancements | 06/15/2009 | 08/17/2009 |  | 841215 | 0
4469 | North Carolina | DAVIDSON |  | 13 | 000S538 | This project will repave the following roadways in Davidson County to improve road condition: NC 62 from NC 109 to the Randolph County line, NC 109 from Denton Road to north of Ben Lee Road, NC 150 f | Pavement Improvement | 05/22/2009 | 05/22/2009 | 11/01/2009 | 1986099 | 0
4470 | North Carolina | DAVIE |  | 5,6,12 | 000S540 | This project will repave the following roadways in Davidson and Davie Counties to improve road condition: US 64 from Lake Louise Golf Course to east of the Yadkin River, US 64-601 from US 158 to US 6 | Pavement Improvement | 06/12/2009 | 06/12/2009 | 11/30/2009 | 3384782 | 0
4471 | North Carolina | ROWAN |  | 6,12 | 000S541 | This project will repave various roadways in Rowan County, including the following, to improve road condition: Section of US 52, Section of NC 150, Section of NC 152, Section of NC 801, Sections of 8 | Pavement Improvement | 05/22/2009 | 05/22/2009 | 11/30/2009 | 4465640 | 0
4472 | North Carolina | STOKES |  | 5 | 000S542 | This project will repave various roadways in Stokes County, including the following, to improve road condition: US 52 from King City limits to Surry County line, Section of NC 65, Section of NC 66, S | Pavement Improvement | 06/12/2009 | 06/12/2009 | 11/30/2009 | 3226120 | 0
4473 | North Carolina | FORSYTH |  | 5 | 000S568 | This project will repave Northwest Boulevard and construct sidewalk in Winston-Salem / Forsyth County to improve road condition and provide pedestrian accommodation. | Pavement Improvement | 08/11/2009 | 09/09/2009 | 04/30/2010 | 383584 | 0
4474 | North Carolina | HARNETT |  | 2 | 000S574 | Landscaping - PE | Other | 11/01/2009 |  |  | 5000 | 0
4475 | North Carolina | STATEWIDE |  | 5, 12 | 000S577 | These funds will provide the preliminary engineering for the project that will renovate the landscape enhancement for the I-85 Rest Area in Davidson County and the I-40/US-52 landscape initiative in F | Other | 08/05/2009 | 08/05/2009 |  | 4311 | 0
4476 | North Carolina | STATEWIDE |  | 11 | 000S582 | The project will install landscape enhancement planting in Columbus at the US 74 and I-26 Interchange in Polk County and at the intersection of US 64 and Jones Cove Road in Haywood County. | Transportation Enhancements | 08/20/2009 |  | 03/05/2010 | 100377 | 0
4477 | North Carolina | ORANGE | DURHAM | 4 | 000S588 | This project provides for the construction of a 10 foot multi-use asphalt trail including bridge over Jones Creek for the Twin Creeks Park Greenway in Orrange County. This is a locally administered p | Transportation Enhancements | 09/23/2009 |  |  | 429457 | 0
4478 | North Carolina | BUNCOMBE |  | 11 | 000S593 | Rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for motorists. | Bridge Improvement | 10/26/2009 |  | 08/15/2010 | 4419325 | 0
4479 | North Carolina | HENDERSON |  | 11 | 000S605 | The project will install flowering tree seedlings for reforestation at the following locations: I-26 at US 25 in Henderson County, I-26 at US 74 in Polk County, US 64 from US 74 to NC 141 in Cherokee | Transportation Enhancements | 09/09/2009 |  | 02/26/2010 | 179371 | 0
4480 | North Carolina | FORSYTH |  | 05 | 000S610 | Dynamic Message Signs Upgrade | Safety/Traffic Management | 12/17/2009 |  | 10/01/2010 | 500000 | 0
4481 | North Carolina | HERTFORD |  | 1 | 0011015 | This project will resurface NC 11 Business in Hertford County from NC 11 to the Aulander East City Limits to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 280500 | 0
4482 | North Carolina | HERTFORD |  | 1 | 0011017 | This project will resurface NC 11in Hertford County from SR 1130 (Modlin Hatchery Road) southward for 2.6 miles to the Bridge over Ahoskie Creek to improve road condition. | Pavement Improvement | 01/04/2010 |  | 06/30/2011 | 650000 | 0
4483 | North Carolina | MARTIN |  | 1 | 0011018 | This project will clean and paint the structural steel on Bridge #39 over the Roanoke River on NC 11 in Martin County to extend the life of the structure. | Bridge Improvement | 11/24/2009 |  | 12/15/2010 | 390000 | 0
4484 | North Carolina | HYDE |  | 3 | 0012036 | This project will resurface NC 12 from the Northern Ferry Dock to Ocracoke Village in Hyde County to improve road condition. Widen paved shoulders to accommodate bicycles will be added on a 3.26 mile | Pavement Improvement | 06/15/2009 | 06/15/2009 | 08/20/2010 | 2753560 | 0
4485 | North Carolina | HYDE |  | 3 | 0012037 | This project will construct a multi-use asphalt trail adjacent to NC 12 from Ocracoke Village to the National Park Service Campground in Hyde County to enhance pedestrian and bicycle access and safety | Transportation Enhancements | 06/15/2009 | 06/15/2009 | 08/20/2010 | 627400 | 0
4486 | North Carolina | HERTFORD |  | 1 | 0013028 | This project will strengthen and resurface US 13 in Hertford County from SR 1130 (Modlin Hatchery Road) to NC 461 to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 10/30/2009 | 567984 | 0
4487 | North Carolina | HERTFORD |  | 1 | 0013029 | Replace deficient bridges #12 and #25 carrying US 13 over Ahoskie Creek and Ahoskie Creek Overflow in Hertford County. | Bridge Replacement | 04/21/2009 | 04/21/2009 | 10/28/2011 | 3196983 | 0
4488 | North Carolina | BERTIE |  | 1 | 0013031 | This project will resurface US 13-US 17 from the Roanoke River to Saint Francis Road in Bertie County to improve road condition. | Pavement Improvement | 11/10/2009 |  | 06/15/2010 | 1330039 | 0
4489 | North Carolina | BERTIE |  | 1 | 0013032 | This project will level existing pavement and resurface US 13/US 17 in Bertie County from SR 1106( St. Francis Road) to SR 1102 (Pleasant Oak Road) to improve road condition. | Pavement Improvement | 11/10/2009 |  | 06/15/2010 | 1094911 | 0
4490 | North Carolina | GRANVILLE, ORANGE |  | 13 | 0015020 | This project will repave US 15 in Granville County from Tar River Road south of Oxford to Industry Drive in Oxford to improve road condition. | Pavement Improvement | 11/16/2009 |  | 10/15/2010 | 3362624 | 0
4491 | North Carolina | ORANGE |  | 4 | 0015026 | Thie project provides for the construciton of the Morgan Creek Greenway, Phase I, to improve pedestrian access from US 15/501 (Culbeth Road) to Smith Level Road in Orange County. This project is loc | Transportation Enhancements | 10/14/2009 |  |  | 300000 | 0
4492 | North Carolina | CHATHAM | DURHAM | 4 | 0015027 | Preliminary engineering for pedestrian enhancements to traffic signals and sidewalks on East and/or the west side of US 15-501 in the Cole Park area north to the Orange County line using the existing | Transportation Enhancements | 06/23/2009 | 07/09/2009 | 06/15/2010 | 157013 | 0
4493 | North Carolina | CHATHAM | DURHAM | 8 | 0015028 | This project will renovate the existing landscape enhancement US 421 & US 64 in Chatham County. | Transportation Enhancements | 06/23/2009 | 07/09/2009 | 06/15/2010 | 36571 | 0
4494 | North Carolina | DURHAM |  | 04 | 0015030 | US 15-501 Business South From NC 98 to US 15/501 Business; US 15/501 Business North From US 15/501 to NC 98; US 15/501 Business From US 15/501 to SR 1361 (Vickers Avenue) and SR 1127 (Chapel Hill Stre | Pavement Improvement | 12/17/2009 |  |  | 960790 | 0
4495 | North Carolina | UNION | CHARLOTTE | 9 | 0016046 | This project includes turning lane radius improvements, traffic signal upgrades and a railroad crossing upgrade in Waxhaw on NC 16 at the NC 75 intersection to improve intersection operations and safe | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/15/2009 | 699999 | 0
4496 | North Carolina | WILKES |  | 5 | 0016047 | This project will rehabilitate pavement and improve guardrail on NC 16 N from SR 1559 (Old NC 16) to the Ashe County line in Wilkes County to improve road condition and safety. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/31/2009 | 1602356 | 0
4497 | North Carolina | ASHE |  | 5 | 0016048 | This project will rehabilitate pavement and improve guardrail on NC 16 from NC 88 to the Virginia line in Ashe County to improve road condition and safety. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/31/2009 | 2311563 | 0
4498 | North Carolina | MARTIN |  | 1 | 0017089 | This project will mill asphalt from existing pavement and resurface US 17 Business in Williamston from NC 125 to 0.7 miles east to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 216000 | 0
4499 | North Carolina | PERQUIMANS |  | 1 | 0017090 | This project will resurface US 17 in Perquimans County from SR 1101 (Bear Swamp Road) to SR 1302 (Union Hall Road) to improve road condition. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 07/10/2010 | 2373375 | 0
4500 | North Carolina | NEW HANOVER, BRUNSWICK |  | 7 | 0017097 | Construct US 17 Bypass (Future I-140) from NC 87 to US 74-76 in Brunswick County. Route will be a four lane divided freeway to alleviate congestion on surrounding roadways. | New Bridge Construction | 10/14/2009 | 10/14/2009 | 10/15/2013 | 25900000 | 0
4501 | North Carolina | MONTGOMERY |  | 8 | 0024036 | Widen NC 24-27 in Biscoe / Montgomery County, between US 220A and Future I-73/74, to enhance safety and mobility. | Pavement Widening | 03/02/2009 | 03/02/2009 | 08/01/2011 | 4883604 | 0
4502 | North Carolina | MOORE |  | 6 | 0024037 | This project will widen NC 24-27 in Moore County and add turn lanes, from Montgomery County line to NC 705, to enhance safety and mobility. | Pavement Widening | 03/26/2009 | 03/26/2009 | 06/25/2010 | 3313779 | 0
4503 | North Carolina | STANLY |  | 8 | 0024042 | This project includes resurfacing NC 740 from SR 1730 (Vickers Store Rd) to Island in Stanly County. Milling and resurfacing NC 24/27 from NC 740 to Bird St in Stanly County. Pavement rehabilitation | Pavement Improvement | 11/17/2009 |  | 07/30/2010 | 2063691 | 0
4504 | North Carolina | BUNCOMBE |  | 11 | 0025025 | Preliminary engineering for the installation of trees, shrubs, and flowering plants as well as hardscape items and native grasses in Asheville on future I-26, Exit 23, interchange in Woodfin and I-2 | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 06/30/2011 | 213433 | 0
4505 | North Carolina | ROCKINGHAM |  | 13 | 0029044 | This project will repair and rehabilitate concrete pavement and shoulders on US 29 in Rockingham County from Guilford County line to Troublesome Creek to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 10/16/2009 | 1712661 | 0
4506 | North Carolina | ROCKINGHAM |  | 13 | 0029045 | Repair bridge expansion joints on 8 structures: Bridge 23 on US 29 Business, Bridge 116 on SR 2600, Bridge 134 on NC 700, Bridge 168 on NC 14/87, Bridge 169 on NC 770, Bridge 124 on SR 2177, Bridge 1 | Bridge Improvement | 09/18/2009 |  | 05/29/2010 | 123202 | 0
4507 | North Carolina | GUILFORD |  | 12, 13 | 0029046 | The project will install landscape enhancement plantings in Greensboro on US 29 from SR 4240 (Lee Street) to 16th Street in Guilford County. | Transportation Enhancements | 12/29/2009 |  | 04/30/2012 | 181542 | 0
4508 | North Carolina | GUILFORD | GREENSBORO | 13 | 0029048 | US 29 From Phillips Avenue to North of SR 2835 (Mcknight Mill Road) - Upgrade Fiberglass Poles With Metal Breakaway Poles and Install High Mast Lighting at Interchanges in Greensboro | Pavement Improvement | 12/21/2009 |  | 07/31/2011 | 820000 | 0
4509 | North Carolina | NORTHAMPTON |  | 1 | 0035005 | This project will resurface NC 35 in Northampton County from US 158 to SR 1545 (Buck Boone Road) to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 11/13/2009 | 285500 | 0
4510 | North Carolina | PERQUIMANS |  | 1 | 0037002 | The project will replace Culvert #6 with a new aluminum culvert for Burnt Mill Creek on NC 37 at the Perquimans/Chowan County Line in Perquimans County. | Bridge Replacement | 08/17/2009 | 08/17/2009 | 04/15/2010 | 313120 | 0
4511 | North Carolina | JOHNSTON |  | 2 | 0042020 | This project provides improvements to increase safety and mobility on NC 42 at the intersection with SR 1010 (Cleveland Road) in Johnston County. | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/15/2009 | 708406 | 0
4512 | North Carolina | PITT |  | 3 | 0043012 | This project adds sidewalks along the southwest side of NC43 in Greenville from US 264A to Red Banks Road in Pitt County to improve pedestrian safety. | Transportation Enhancements | 08/18/2009 | 09/11/2009 |  | 60090 | 0
4513 | North Carolina | CRAVEN |  | 1 | 0043013 | This project will resurface and do minimal widening on NC 43 from US 17 South to Bosch Boulevard in Craven County to improve road condition. | Pavement Improvement | 09/21/2009 |  | 11/15/2010 | 2926890 | 0
4514 | North Carolina | WASHINGTON |  | 1 | 0045004 | This project will replace deficient Bridge #1 over a canal on NC 45/99 0.6 miles north of the Hyde County line in Washington County. | Bridge Improvement | 08/05/2009 | 08/05/2009 | 07/31/2010 | 306410 | 0
4515 | North Carolina | NORTHAMPTON |  | 1 | 0048006 | This project will resurface NC 48 in Northampton County from SR 1200 (James Jones Road) to the Gaston East City Limits to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 11/13/2009 | 250000 | 0
4516 | North Carolina | PERSON |  | 13 | 0049027 | This project will repave the following roadways in Person County to improve road condition: NC 49 from south of Salem Church Road to Hassell Horton Road, NC 49 from Roxboro southern city limits to US | Pavement Improvement | 11/09/2009 |  | 11/01/2010 | 1674973 | 0
4517 | North Carolina | MECKLENBURG |  | 9 | 0051028 | This project will widen NC 51 from the South Carolina state line to SR 3645 (Downs Circle) in Mecklenburg County to improve safety and mobility. | Pavement Widening | 03/02/2009 | 03/02/2009 | 11/24/2010 | 5601845 | 0
4518 | North Carolina | SURRY |  | 5 | 0052033 | This project will rehabilitate pavement on US 52 from Stokes County line to SR 1815 (Cooke School Rd) in Surry County to improve road condition. | Pavement Improvement | 08/05/2009 |  | 06/15/2010 | 3247234 | 0
4519 | North Carolina | STOKES |  | 05 | 0052036 | Ultrathin Bonded Course Overlay on US 52 From the King City Limits to the Surry County Line | Pavement Improvement | 12/17/2009 |  | 08/15/2010 | 100000 | 0
4520 | North Carolina | DURHAM |  | 4 | 0055042 | This project will add turn lanes on NC 55 in Durham at the Riddle Road intersection to enhance safety and improve mobility. | Pavement Improvement | 08/03/2009 | 08/03/2009 | 10/30/2009 | 250000 | 0
4521 | North Carolina | CARTERET |  | 3 | 0058011 | Construct the Emerald Isle Bike Path in Emerald Isle which includes a 10 feet multiuse path along NC58 from Black Skimmer Drive (MP 19) to the Regional Beach Access (MP 15) and future site of the new | Transportation Enhancements | 07/16/2009 | 01/04/2010 | 06/30/2010 | 478171 | 0
4522 | North Carolina | ALAMANCE |  | 6 | 0062008 | Repair bridge expansion joints four (4) structures: Bridge 12 on NC 62, Bridge 109 on SR 2309, Bridge 115 on SR 1154 and Bridge 75 on SR 1158 in Alamance County to extend the life of the structures. | Bridge Improvement | 08/05/2009 | 08/05/2009 | 05/29/2010 | 123202 | 0
4523 | North Carolina | MARTIN |  | 1 | 0064117 | This project will mill asphalt from existing pavement and resurface US 64 in Martin County from the Jamesville East City Limit to west of Sweetwater Creek to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 10/01/2009 | 3231445 | 0
4524 | North Carolina | MARTIN |  | 1 | 0064118 | This project will resurface US 64 from Edgecombe County Line to US 64 Alternate in Williamston in Martin County to improve road condition. | Pavement Improvement | 05/06/2009 | 05/06/2009 | 11/15/2010 | 6925166 | 0
4525 | North Carolina | TYRRELL |  | 3 | 0064119 | This project will resurface US 64 in Tyrrell County from the Bridge over the Alligator River westward for 3 miles to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 335500 | 0
4526 | North Carolina | WAKE |  | 2, 13 | 0064120 | This project will repave US 64 and US 264 in Wake and Franklin Counties from US 64 / US 264 interchange to Nash County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/01/2009 | 6711634 | 0
4527 | North Carolina | ALEXANDER |  | 5 | 0064121 | This project will resurface US 64 from NC 90 in Iredell County to NC 90 in Alexander County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 10/16/2009 | 2699831 | 0
4528 | North Carolina | NASH |  | 2, 3 | 0064122 | This project will resurface US 64 from the Franklin County Line to Winstead Avenue in Nash County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/15/2009 | 3822437 | 0
4529 | North Carolina | EDGECOMBE, NASH |  | 2, 3 | 0064123 | This project will resurface US 64 from Winstead Avenue in Nash County to the Tar River Bridge in Edgecombe County to improve road condition. | Pavement Improvement | 04/10/2009 | 04/10/2009 | 11/15/2009 | 7576280 | 0
4530 | North Carolina | DARE |  | 3 | 0064125 | This project will clean and paint the structural steel of Bridge #9 (Old Manns Harbor Bridge) carrying US 64 over Croatan Sound in Dare County to extend the life of the structure. | Bridge Replacement | 06/15/2009 | 06/15/2009 | 11/04/2011 | 3529350 | 0
4531 | North Carolina | DARE |  | 3 | 0064126 | This project will construct a stormwater wetland at the corner of US64/264 Business and Greenville Street in Manteo, NC in Dare County. This saltwater wetland will be used to treat stormwater runoff | Other | 09/24/2009 | 09/24/2009 | 05/11/2010 | 250000 | 0
4532 | North Carolina | EDGECOMBE |  | 1 | 0064130 | This is the preliminary engineering for the project that will focus efforts to improve enhancement of the landscape at the interchanges US 64 / US 258 and US 64 / McNair Road in Halifax County. | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 12/15/2010 | 96055 | 0
4533 | North Carolina | NASH |  | 1,2,3 | 0064131 | This is the preliminary engineering for the project that will improve the landscape at the interchanges US 64 / Buck Leonard Boulevard and I-95 / NC 481 in Nash and Halifax Counties. | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 12/15/2010 | 107694 | 0
4534 | North Carolina | MARTIN |  | 1 | 0064132 | This project will mill asphalt pavement from US 64 Alt. in Williamston and resurface with new asphalt pavement from SR 1446 (Sycamore St.) to SR 1445 (Main Street) to improve road condition. | Pavement Improvement | 09/24/2009 |  | 11/30/2010 | 789300 | 0
4535 | North Carolina | TYRRELL |  | 3 | 0064135 | This project will provide concrete repairs to the bridge supports and clean & paint the structural steel on Bridge #7 over the Alligator River on US 64 at the Tyrrell/Dare County Line to extend the li | Bridge Improvement | 12/16/2009 |  | 06/30/2011 | 1355390 | 0
4536 | North Carolina | MACON |  |  | 0064137 | US 64 at the intersections of SR 1516 (Sanders Road), SR 1517 (Bethel Church Road) and SR 1533 (Walnut Creek Road) - Install Left Turn Lanes - Preconstruction | Pavement Improvement | 11/19/2009 | 12/02/2009 | 07/30/2010 | 673839 | 0
4537 | North Carolina | TYRRELL, WASHINGTON |  | 1 | 0064138 | Landscape Plantings | Transportation Enhancements | 09/24/2009 |  | 02/28/2010 | 145000 | 0
4538 | North Carolina | ROCKINGHAM |  | 13 | 0065007 | Replace deficient bridge Number 54 carrying NC 65 over Rock House Creek in Rockingham County. | Bridge Replacement | 11/09/2009 |  | 11/01/2010 | 1333747 | 0
4539 | North Carolina | GUILFORD |  | 6 | 0068012 | This project will repave, widen and add trun lanes on NC 68 in Guilford County from SR 2011 (Edgefield Road) south of Oak Ridge to NC 65 north of Stokesdale to improve road condition. | Pavement Widening | 09/28/2009 |  | 07/31/2010 | 1690795 | 0
4540 | North Carolina | ORANGE |  | 4 | 0070127 | Repair bridge expansion joints on one (1) structure: Bridge 6 on US 70 in Orange County to extend the life of the structure. | Bridge Improvement | 09/18/2009 |  | 05/29/2010 | 26753 | 0
4541 | North Carolina | STANLY |  | 8 | 0073019 | Replace deficient bridge carrying NC 73 over Long Creek in Stanly County. | Bridge Replacement | 03/02/2009 | 03/02/2009 | 12/31/2010 | 3020655 | 0
4542 | North Carolina | CABARRUS |  | 8 | 0073020 | "This project includes construction to repair drainage and pavement issues in Mount Pleasant on NC 73 from east of the City Limits to SR 1411 (Cold Springs Road) as follows: Project 1: Removes the ex | Other | 06/02/2009 | 06/02/2009 | 12/15/2009 | 25000 | 0
4543 | North Carolina | MECKLENBURG | CHARLOTTE |  | 0073021 | Widen NC 73 from US 21 to NC 115 in Mecklenburg County to improve safety and mobility. | Pavement Widening | 09/21/2009 | 09/21/2009 | 11/15/2012 | 23050448 | 0
4544 | North Carolina | CLEVELAND |  | 10 | 0074104 | This project will resurface US 74 from SR 1170 (Lucas Rd) to West Lee in Cleveland County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/02/2009 | 1515551 | 0
4545 | North Carolina | SWAIN |  | 11 | 0074105 | This project will rehabilitate pavement on US 74 from SR 1159 (Spring St) to the Jackson County line in Swain County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 12/15/2009 | 6483915 | 0
4546 | North Carolina | ANSON |  | 8 | 0074108 | This project will include pavement rehabilitation, paved shoulders, and guardrail on US 74 westbound from beginning of divided highway west of SR 1259 to Union County line in Anson County, improving r | Pavement Improvement | 09/09/2009 |  | 07/02/2010 | 3457413 | 0
4547 | North Carolina | LEE |  | 2 | 0078004 | This project will widen NC 78 in Sanford / Lee County, from Tramway to beyond St. Andrews Road, to enhance safety and mobility. | Pavement Widening | 03/26/2009 | 03/26/2009 | 04/30/2010 | 1648979 | 0
4548 | North Carolina | ALAMANCE |  | 6 | 0087022 | This project provides for the replacement of existing signal poles & mast arms at the NC 87 (Webb Avenue) and Elmira Street intersection to improve road conditions in Alamance County. | Other | 08/05/2009 | 08/05/2009 | 02/16/2010 | 944 | 0
4549 | North Carolina | ALLEGHANY |  | 5 | 0093003 | This project will rehabilitate pavement on NC 93 from US 221 to SR 1337 (Mt. Carmel Rd) in Alleghany County to improve road condition. | Pavement Improvement | 06/22/2009 | 07/01/2009 | 07/01/2010 | 1299452 | 0
4550 | North Carolina | DURHAM |  | 4 | 0098025 | This project will repave NC 98 in Durham County from Junction Road to Sherron Road to improve road condition. | Pavement Widening | 05/13/2009 | 05/13/2009 | 05/14/2010 | 1284838 | 0
4551 | North Carolina | FRANKLIN |  | 2 | 0098026 | This project will repave the following roadways in Franklin County to improve road condition: NC 98 from US 401 to Bunn and US 1A from US 1 to NC 56 in Franklinton. | Pavement Improvement | 11/09/2009 |  | 11/01/2010 | 2657356 | 0
4552 | North Carolina | CUMBERLAND | FAYETTEVILLE | 2 | 0100017 | This project will perform grading and construct the bridges on the future I-295 Fayetteville Outer Loop in Cumberland County from Bragg Boulevard to Murchison Road for a four lane divided highway. Pa | Pavement Widening | 04/21/2009 | 04/21/2009 | 07/01/2012 | 54501720 | 0
4553 | North Carolina | ALAMANCE |  | 6, 13 | 0119003 | This project will repave NC 119 with two foot shoulders in Alamance County from the Mebane north city limits to the Caswell County line to improve road condition. | Pavement Improvement | 11/16/2009 |  | 05/17/2010 | 1947330 | 0
4554 | North Carolina | GRAHAM |  | 11 | 0129002 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 10 over East Buffaloe Creek on US 129 in Graham County to extend the life of the structure. | Bridge Improvement | 10/15/2009 | 10/15/2009 | 02/01/2010 | 800000 | 0
4555 | North Carolina | CHEROKEE |  | 11 | 0141005 | This project will rehabilitate pavement on NC 141 from US 64 to US 74 in Cherokee County to improve road condition. | Pavement Improvement | 07/08/2009 | 07/08/2009 | 02/23/2010 | 538659 | 0
4556 | North Carolina | CAMDEN |  | 3 | 0158040 | This project will widen US 158-NC 34 from East of the Pasquotank River in Elizabeth City to North of Havenwood Road in Camden County from two lanes to multi-lanes to improve traffic operations and im | Pavement Widening | 03/02/2009 | 03/02/2009 | 08/01/2011 | 7057343 | 0
4557 | North Carolina | DARE |  | 3 | 0158042 | This project will perform renovations to the existing buildings at the Kitty Hawk Rest Area on US 158 including replacement of wall tile and plumbing fixtures, addition of an ADA compliant family rest | Pavement Improvement | 05/26/2009 | 05/26/2009 | 03/20/2010 | 209000 | 0
4558 | North Carolina | NORTHAMPTON |  | 1 | 0158043 | This project will resurface US 158 from Halifax County Line to multi-lane section west of Hertford County Line in Northampton County to improve road condition. | Pavement Improvement | 08/05/2009 | 08/05/2009 | 11/15/2011 | 8290662 | 0
4559 | North Carolina | HENDERSON |  | 11 | 0176006 | This project will rehabilitate pavement on US 176 from NC 225 to US 25 in Henderson County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 12/15/2009 | 2986038 | 0
4560 | North Carolina | RICHMOND |  | 8 | 0177003 | The project will install landscape enhancement plantings at the NC 177 and SR1900 Battlet Dairy Road interchange in Richmond County. | Transportation Enhancements | 09/21/2009 | 11/30/2009 | 02/26/2009 | 26500 | 0
4561 | North Carolina | AVERY |  | 5 | 0194010 | This project will rehabilitate pavement and widen NC 194 from US 221 to US 19 E in Avery County to improve road condition and safety. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 06/01/2010 | 1030620 | 0
4562 | North Carolina | BEAUFORT |  | 3 | 0207002 | Landscape Plantings | Transportation Enhancements | 10/23/2009 |  | 03/15/2010 | 25000 | 0
4563 | North Carolina | TRANSYLVANIA |  | 11 | 0215004 | This project will install and revise guardrail on NC 215 from US 64 to the Haywood County line in Transylvania County to improve safety. | Safety/Traffic Management | 05/13/2009 | 05/13/2009 | 08/01/2010 | 2534653 | 0
4564 | North Carolina | UNION |  | 8, 9 | 0218008 | This project will rehabilitate pavement on NC 218 from east of I-485 to west of US 601 in Mecklenburg and Union Counties to improve road condition. | Pavement Improvement | 06/16/2009 | 07/08/2009 | 09/30/2011 | 1736308 | 0
4565 | North Carolina | UNION |  | 8,9 | 0218009 | This project will rehabilitate pavement on NC 218 from east of US 601 to west of NC 205 in Union County to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 10/30/2009 | 3480424 | 0
4566 | North Carolina | UNION |  | 8 | 0218010 | This project will rehabilitate pavement on NC 218 from east of NC 205 to US 74 in Anson and Union Counties to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 11/20/2009 | 4634986 | 0
4567 | North Carolina | UNION |  | 8,9 | 0218011 | Widening for turn lanes on NC 218 @ NC 205, Also widening for turn lanes on US 601 @ NC 218. | Pavement Widening | 05/07/2009 | 05/07/2009 | 09/30/2009 | 467301 | 0
4568 | North Carolina | UNION |  | 8,9,12 | 0218012 | This project will construct three filtration basins and a stormwater wetland for the purpose of treating stormwater runoff, from the intersection of US 601 and NC 218 in Union County, before dischargi | Other | 09/15/2009 | 09/15/2009 | 02/15/2010 | 109788 | 0
4569 | North Carolina | ROCKINGHAM |  | 13 | 0220041 | This project will repave US 220 in Rockingham County from NC 135 to the Virginia State line to improve road condition. | Pavement Improvement | 09/08/2009 |  | 09/24/2010 | 3086728 | 0
4570 | North Carolina | LENOIR |  | 3 | 0224013 | Perform grading and construct the bridges on C. Felix Harvey Parkway in Lenoir County from US 70 to US 258 for a four lane divided highway. Paving contract will be done as a separate project in the f | New Construction | 05/08/2009 | 05/08/2009 | 08/01/2012 | 42926208 | 0
4571 | North Carolina | CRAVEN |  | 1,3 | 0229010 | Landscaping | Transportation Enhancements | 09/21/2009 |  | 12/31/2010 | 302130 | 0
4572 | North Carolina | BUNCOMBE |  | 11 | 0240003 | This project will construct three filtration basin systems for treating stormwater runoff, from I-240, near mile marker 6, just west of Chuns Cove Road, in Asheville, NC before discharging to Ross Cre | Other | 11/05/2009 |  | 07/02/2010 | 300000 | 0
4573 | North Carolina | NORTHAMPTON |  | 1 | 0258015 | This project will mill asphalt from existing pavement and resurface US 258 from Roanoke River to NC 305 in Northampton County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/01/2009 | 1114172 | 0
4574 | North Carolina | GREENE |  | 1 | 0258017 | This project will resurface and do minimal widening on US 258 from Contentnea Creek to NC 123 in Greene County to improve road condition. | Pavement Improvement | 09/21/2009 |  | 11/15/2010 | 1364804 | 0
4575 | North Carolina | PAMLICO |  | 3 | 0259002 | Landscape Plantings | Transportation Enhancements | 10/23/2009 |  | 03/15/2010 | 25000 | 0
4576 | North Carolina | BUNCOMBE |  | 11 | 0261083 | Mill areas where potholes, cracking and/or delamination of the asphalt surface has occurred and resurface to promote the life of the roadway surface on I-26 from mile post 31 to mile post 37 in Buncom | Pavement Improvement | 04/15/2009 | 04/15/2009 | 09/30/2010 | 9108169 | 6
4577 | North Carolina | POLK |  | 11 | 0261085 | This project provides for preconstruction activities to rehabilitate the pavement on I-26 from milepost 61 to milepost 71 in Polk County to improve road condition. | Pavement Improvement | 07/08/2009 | 07/08/2009 | 09/30/2010 | 1011743 | 0
4578 | North Carolina | DARE |  | 3 | 0264039 | This project will resurface US 264 in Dare County from SR 1100 (Stumpy Point Road) to the Navy Range to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 386500 | 0
4579 | North Carolina | PITT |  | 1 | 0264042 | This project adds an additional turn lane on US 264 in Greenville at the intersection of Stantonsburg Road and Arlington Blvd in Pitt County to ease congestion and improve safety. This is a locally a | Pavement Widening | 08/18/2009 | 09/08/2009 |  | 91267 | 0
4580 | North Carolina | WILSON |  | 3 | 0264043 | This project will resurface US 264 from NC 58 to the Greene County Line in Wilson County to improve road condition. | Pavement Improvement | 09/09/2009 |  | 11/01/2010 | 4016081 | 0
4581 | North Carolina | NASH, WILSON |  | 2, 3 | 0264045 | This project will resurface US 264 from the Wake County Line to US 264 Alternate in Nash and Wilson Counties to improve road condition. | Pavement Improvement | 11/10/2009 |  | 10/01/2010 | 4524723 | 0
4582 | North Carolina | PITT |  | 1 | 0264046 | Landscape Plantings | Transportation Enhancements | 11/02/2009 |  | 12/15/2010 | 122000 | 0
4583 | North Carolina | GASTON |  | 9 | 0274007 | This project will widen NC 274 from SR 1484 (Maine Ave) to NC 275 in Gaston County to improve safety and mobility. | Pavement Widening | 03/02/2009 | 03/02/2009 | 07/01/2011 | 5922937 | 0
4584 | North Carolina | TRANSYLVANIA |  | 11 | 0276008 | This project will rehabilitate pavement and install paved shoulders on US 276 from Pisgah Forest to Brevard in Transylvania County to improve road condition and safety. | Pavement Improvement | 04/10/2009 | 04/10/2009 | 05/15/2010 | 2294179 | 0
4585 | North Carolina | BERTIE |  | 1 | 0305001 | This project will mill asphalt from existing pavement, overlay with an asphalt surface treatment (mat & seal) and resurface the pavement of NC 305 NC 305 from US 13 to NC 11 in Bertie County to improv | Pavement Improvement | 05/06/2009 | 05/06/2009 | 07/01/2010 | 1880984 | 0
4586 | North Carolina | BERTIE |  | 1 | 0308004 | This project will resurface NC 308 in Windsor from King Street to Sterlingworth Street to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 81100 | 0
4587 | North Carolina | BERTIE |  | 1 | 0308005 | This project will resurface NC 308 in Bertie County from the Kelford East City Limits to the Kelford West City Limits to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 147000 | 0
4588 | North Carolina | BERTIE |  | 1 | 0308006 | This project will resurface NC 308 in Bertie County from SR 1119 (Jack Branch Road) to SR 1247 (Mount Olive Road) to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 165000 | 0
4589 | North Carolina | GUILFORD |  | 6, 12 | 0311026 | This project includes the preparation of an environmental document for the replacement of the interchange at US 311 & NC 68 in High Point in Guilford County. This is a locally administered project by | Other | 08/21/2009 | 08/21/2009 |  | 400000 | 0
4590 | North Carolina | GUILFORD |  | 6 | 0311027 | This project will modify two existing hazardous spill basins and construct a linear filtration basin to collect the runoff from the bridge over the Oak Hollow Reservoir located on US-311/SR-1979 in Gu | Other | 12/21/2009 |  | 10/30/2010 | 68568 | 0
4591 | North Carolina | CALDWELL |  | 5 | 0321020 | This project will rehabilitate pavement on US 321 from SR 1178 (Hibriten Dr SE) to city limits of Lenoir in Caldwell County to improve road condition. | Pavement Improvement | 06/01/2009 | 08/31/2009 | 10/30/2009 | 478748 | 0
4592 | North Carolina | NEW HANOVER |  | 7 | 0332034 | This project will construct a 0.6 mile long asphalt multi-use path in Wilmington along South 17th Street between the Cameron Art Museum and Halyburton Park and an 0.2 mile long asphalt multi-use path | Transportation Enhancements | 01/25/2010 |  |  | 350000 | 0
4593 | North Carolina | NEW HANOVER |  | 7 | 0332035 | This project will construct a 2.6 mile long asphalt multi-use path in Wilmington between Randall Parkway and Converse Road, parallel to Rosemont Avenue, Caswell Street, Park Avenue and Independence Bo | Transportation Enhancements | 05/28/2009 |  |  | 1650000 | 0
4594 | North Carolina | HAYWOOD |  | 11 | 0401200 | This project will improve drainage and?complete minor landscape improvements to the I-40 west bound rest area building in Haywood County at MM 10. | Transportation Enhancements | 07/27/2009 |  | 03/05/2010 | 26375 | 0
4595 | North Carolina | BUNCOMBE |  | 11 | 0401204 | Rehabilitate pavement on I-40 from SR 2838 (Exit 55) to mile post 67 in Buncombe County to improve road condition. | Pavement Improvement | 11/17/2009 |  | 10/30/2010 | 8968579 | 8
4596 | North Carolina | WAKE | RALEIGH | 13 | 0401206 | Widen US 401 in Wake County between Neuse River and Louisburg Road near Rolesville, to enhance safety and mobility. | Pavement Widening | 11/09/2009 |  | 12/31/2011 | 9823735 | 0
4597 | North Carolina | HAYWOOD |  |  | 0401210 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 124 over SR 1338 ON I-40 in Haywood County to extend the life of the structure. | Bridge Improvement | 10/15/2009 | 10/15/2009 | 01/31/2010 | 450000 | 0
4598 | North Carolina | HAYWOOD |  | 11 | 0401211 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 205 over SR 1364 ON I-40 in Haywood County to extend the life of the structure. | Bridge Improvement | 11/19/2009 | 11/20/2009 | 01/31/2010 | 300000 | 0
4599 | North Carolina | HAYWOOD |  | 11 | 0401212 | I-40 Replace 6 Dynamic Message Signs at MP 33.4 (East and Westbound) MP 28.7 (East and Westbound) MP 21 (Westbound) and MP 0.7 (Eastbound) | Safety/Traffic Management | 11/02/2009 |  | 08/27/2010 | 862000 | 0
4600 | North Carolina | BURKE |  | 10 | 0402142 | This project will resurface the roadway with an asphalt microsurface (a thinner yet extremely durable treatment) to extend the life of the road and provide improved rideability on I-40 from mile post | Pavement Improvement | 04/17/2009 | 04/17/2009 | 06/30/2010 | 10195245 | 0
4601 | North Carolina | FORSYTH |  | 12 | 0403122 | Resurface I-40 from Clemmonsville Road to US 311 in Winston-Salem / Forsyth County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 09/15/2009 | 1393250 | 1.8
4602 | North Carolina | GUILFORD |  | 6 | 0403123 | Resurface I-40/85 from Rock Creek Dairy Road in Guilford County to University Drive in Alamance County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 10/30/2009 | 4355084 | 5.3
4603 | North Carolina | FORSYTH |  | 5 | 0403124 | Resurface I-40 from Harper Road to Jonestown Road in Forsyth County to improve road condition. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 06/15/2010 | 3502841 | 0
4604 | North Carolina | GUILFORD |  | 6,13 | 0403125 | Replace damaged/missing reflectors in pavement lane markers on I-40/85 in Guilford County, between I-40 and I-85 junction east of Greensboro to beyond Mount Hope Church Road, to improve nighttime visi | Pavement Improvement | 08/05/2009 | 08/05/2009 | 05/01/2010 | 10950 | 0
4605 | North Carolina | ALAMANCE |  | 6 | 0403126 | The project will install landscape enhancement in Burlington at the interchange of I-40/85 and SR 1226 (University Drive) in Alamance County. | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 12/15/2011 | 190000 | 0
4606 | North Carolina | SAMPSON, DUPLIN |  | 2, 7 | 0405052 | Resurface I-40 from east of Newton Grove in Sampson County to east of Warsaw in Duplin County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/15/2010 | 14560349 | 20.9
4607 | North Carolina | JOHNSTON |  | 2 | 0405053 | This projects provides for the resurfacing of I-40 from west of Morgan Road to the Sampson County Line in Johnston County to improve road condition. | Pavement Improvement | 04/10/2009 | 04/10/2009 | 11/15/2010 | 2516114 | 11
4608 | North Carolina | DUPLIN |  | 07 | 0405054 | I-40 from mp 369.4 in Duplin County to mp 389.5 - Milling, Resurfacing & Shoulder Reconstruction in Pender County | Pavement Improvement | 12/16/2009 |  | 05/31/2011 | 1000000 | 0
4609 | North Carolina | NEW HANOVER, SAMPSON, DUPLIN, PENDER |  | 7 | 0405055 | Landscaping | Transportation Enhancements | 10/09/2009 |  | 04/02/2010 | 171000 | 0
4610 | North Carolina | WAYNE |  | 1 | 0414004 | This project will install a computerized central signal system in the City of Goldsboro to synchronize the traffic signals to improve traffic flow. | Safety/Traffic Management | 08/05/2009 | 08/05/2009 | 02/01/2012 | 3622986 | 0
4611 | North Carolina | WATAUGA |  | 5 | 0421047 | This project will widen US 421 (King Street) from NC 194 to US 321 in Watauga County to improve safety and mobility. | Pavement Widening | 05/06/2009 | 05/06/2009 | 12/31/2011 | 16637727 | 0
4612 | North Carolina | LEE |  | 2 | 0421050 | Construct section of Sanford Bypass between NC 42 and NC 87 south of Sanford, to reduce congestion and improve mobility. | New Construction | 11/09/2009 |  | 11/15/2012 | 29846428 | 0
4613 | North Carolina | GUILFORD | GREENSBORO | 6 | 0421053 | This project will repave US 421 in Guilford County from the Randolph County line to north of SR 3485 (Harmont Drive) to improve road condition. | Pavement Improvement | 10/13/2009 |  | 09/03/2010 | 3893903 | 0
4614 | North Carolina | CHATHAM |  | 6 | 0421055 | Landscape Plantings | Transportation Enhancements | 10/23/2009 | 01/26/2010 | 03/31/2010 | 197000 | 0
4615 | North Carolina | FORSYTH |  | 05 | 0421057 | US 421 pavement joint at ramps at Lewisville to the Yadkin County Line - Milling, Milled Rumble Strips & Shoulder Drop-off Repair in Forsyth County | Pavement Improvement | 12/17/2009 |  | 09/30/2010 | 500000 | 0
4616 | North Carolina | WILKES |  | 05 | 0421058 | US 421 from SR 1765 (Unifi Industrual Rd) Yadkin County to Boone Town limits in Watauga County Reforestation and Manual Clearing in Wilkes County | Transportation Enhancements | 10/22/2009 | 01/27/2010 | 04/23/2010 | 75000 | 0
4617 | North Carolina | WAKE |  | 13 | 0440006 | Remove sections of concrete pavement and replace with asphalt to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 06/30/2010 | 3963204 | 3
4618 | North Carolina | WAKE |  | 13 | 0440007 | Resurface I-440 Beltline in Raleigh from Wade Avenue to Wake Forest Road to improve road condition | Pavement Improvement | 03/26/2009 | 03/26/2009 | 12/31/2009 | 4094553 | 5
4619 | North Carolina | WAKE | RALEIGH | 13 | 0440008 | This project consists of cleaning and painting bridges in Raleigh along I-440 including bridge numbers, 249 (Glen Eden), 252 (Ridge Road), 139 (US 401), 287 (US 1), and 288 (US 410 SBL) to extend lif | Bridge Improvement | 08/24/2009 |  | 10/30/2010 | 1006775 | 0
4620 | North Carolina | WAKE |  | 13 | 0440009 | This project provides for the installation of a Wireless Camera System on the Northern Section of I-440 in Raleigh to improve response to traffic congestion in Wake County. | Safety/Traffic Management | 04/30/2009 | 04/30/2009 | 03/02/2010 | 414299 | 0
4621 | North Carolina | MECKLENBURG |  | 8,9,12 | 0485016 | This project will construct a filtration basin/wetland at NC 51/I-485 to treat stormwater runoff from NC 51 in Mecklenburg County helping to prevent pollutants from entering into a tributary of Clear | Other | 10/15/2009 | 10/15/2009 | 04/30/2010 | 161000 | 0
4622 | North Carolina | DURHAM |  | 4 | 0501014 | This project will repave Duke Street in Durham from Horton Road to Hudson Street to improve road condition. | Pavement Widening | 05/13/2009 | 05/13/2009 | 05/14/2010 | 770485 | 0
4623 | North Carolina | WAKE | RALEIGH | 4 | 0501015 | This project will install a traffic signal in Apex at the Intersection of SR 1010 (Center Street) and SR 1011 (North Salem Street) to improve safety. This is a locally administered project by the Tow | Safety/Traffic Management | 09/18/2009 |  | 05/14/2010 | 92191 | 0
4624 | North Carolina | WAKE | RALEIGH | 4 | 0503007 | This project will construct a portion of the Black Creek Greenway pedestrian and bicycle facilities from the Credit Union near the intersection of Chapel Hill Road and Northwest Maynard Road to the Sh | Transportation Enhancements | 09/23/2009 |  |  | 1379200 | 0
4625 | North Carolina | DURHAM |  | 4 | 0505034 | This project will provide for traffic signal upgrades in Durham including pedestrian installed equipment at various locations for the city maintained signals to improve operating efficiency and safety | Safety/Traffic Management | 09/23/2009 | 01/15/2010 | 09/12/2010 | 125729 | 0
4626 | North Carolina | DURHAM |  | 4 | 0505036 | The project provides for the installation of a new traffic signal in Durham at Northpoint Drive at Home Depot Entrance and Dehaven?s Entrance to improve safety in Durham County. This is a locally adm | Safety/Traffic Management | 09/23/2009 | 01/15/2010 | 09/12/2010 | 346539 | 0
4627 | North Carolina | DURHAM |  | 4 | 0505037 | This project provides for the installation of a new signal on Renaissance Parkway at the ATT Crossing and at the Mall Site Drive to improve access and safety in Durham County. This is a locally admin | Safety/Traffic Management | 09/23/2009 | 01/15/2010 | 09/12/2010 | 232071 | 0
4628 | North Carolina | DURHAM | DURHAM | 4 | 0505039 | This project will remove the free flow traffic turn lane in Durham at the intersection of SR 1670 (Greer Street) and Miami Boulevard to improve safety a the intersection in Durham County. This is a | Pavement Improvement | 09/18/2009 |  |  | 80000 | 0
4629 | North Carolina | DURHAM | DURHAM | 4 | 0505040 | The project will provide for replacement of trees in Durham along Duke and Gregson streets to improve neighborhood appearance in Durham County. This is a locally administered project by the City of D | Transportation Enhancements | 09/23/2009 | 01/10/2010 | 04/10/2010 | 108572 | 0
4630 | North Carolina | DURHAM | DURHAM | 4 | 0505042 | This project will construct neighborhood accesses to the Third Fork Creek Greenway to improve community access in Durham County. This is a locally administered project by the City of Durham. | Transportation Enhancements | 09/23/2009 | 01/18/2010 | 10/15/2010 | 827000 | 0
4631 | North Carolina | DURHAM | DURHAM | 4 | 0505043 | This project will resurface asphalt on the North-South Greenway Trail in Durham from Lavender Street to Murray Avenue to improve pavement life and ride quality in Durham County. This is a locally adm | Transportation Enhancements | 09/18/2009 |  |  | 342183 | 0
4632 | North Carolina | WAKE |  | 13 | 0520028 | This project will construct the Neuse River Greenway pedestrian and bicycle facilities from Falls Lake Dam to the South Soccer Complex on SR 2006 (Perry Creek Road) in Wake County. This project is lo | Transportation Enhancements | 01/19/2010 | 01/19/2010 |  | 3250000 | 0
4633 | North Carolina | WAKE | RALEIGH | 4 | 0527006 | This project provides for the construction of the Dunn Creek Greenway to improve pedestrain access and safety from Smith Creek Soccer Center to the NC 98 Bypass in Wake County. This is a locally adm | Transportation Enhancements | 09/18/2009 |  | 07/23/2010 | 450000 | 0
4634 | North Carolina | WAKE | RALEIGH | 6 | 0529001 | This project provides for the construction of crosswalks at Athird and Main Streets to improve pedestrain safety and mobility in Wake County. This is a locally administered project by the Town of Wen | Transportation Enhancements | 09/10/2009 |  | 03/13/2010 | 33810 | 0
4635 | North Carolina | WAKE | RALEIGH | 4 | 0529002 | This project provides for the construction of 4500 feet of sidewalk in Wendell along Third Street and Buffaloe Road to improve pedestrian access to the park in Wake County. This is a locally adminis | Transportation Enhancements | 09/24/2009 |  |  | 375749 | 0
4636 | North Carolina | WAKE | RALEIGH | 4 | 0532003 | This project constructs sidewalk in Zebulon on West Judd Street from North Wakfield Street to North Church Street in Wake County. This is a locally administered project by the Town of Zebulon. | Transportation Enhancements | 09/10/2009 |  | 04/08/2010 | 65467 | 0
4637 | North Carolina | DURHAM |  | 4 | 0540015 | Widen ramp from I-540 west to I-40 west in Durham and Wake Counties, and add merge lane on I-40 westbound between I-540 and Page Road in Durham County, to reduce congestion. | Pavement Improvement | 12/17/2009 |  | 12/31/2010 | 2000000 | 0
4638 | North Carolina | WAKE |  | 4 | 0540016 | Resurface I-540 in Wake County from north of I-40 to US 70 to improve road condition | Pavement Improvement | 04/15/2009 | 04/15/2009 | 05/27/2010 | 2569522 | 4
4639 | North Carolina | WAKE | RALEIGH | 13 | 0540018 | The project will provide for landscape enhancement in Knightdale at the interchange of I-540 and US 64 in Wake County. This is a locally administered project by the Town of Knightdale. | Transportation Enhancements | 08/14/2009 |  |  | 130697 | 0
4640 | North Carolina | HERTFORD |  | 1 | 0561020 | This project will widen and resurface NC 561 from NC 11 to Northampton County in Hertford County to improve road condition. | Pavement Widening | 09/28/2009 |  | 06/30/2011 | 2063972 | 0
4641 | North Carolina | ALAMANCE |  | 6 | 0701018 | This project provides for the replacement of existing signal poles & mast arms at the SR 1300 (University Drive) and Rural Retreat Road intersection to improve road conditions in Alamance County. | Safety/Traffic Management | 08/05/2009 | 08/05/2009 |  | 413272 | 0
4642 | North Carolina | BLADEN |  | 7 | 0701020 | This project will construct bicycle lanes on US 701 between Elizabethtown and White Lake for approximately 6 miles by widening the existing paved shoulder to four feet on both sides in Bladen County. | Transportation Enhancements | 08/07/2009 | 08/07/2009 | 06/01/2010 | 975000 | 0
4643 | North Carolina | ALAMANCE |  | 13 | 0701022 | This project provides for the construction of sidewalks, including curb and gutter to improve pedestrian mobility and safety on Piedmont Street from SR 1785 (Sellars Mill Road) to the Cummings High S | Transportation Enhancements | 09/23/2009 |  |  | 25138 | 0
4644 | North Carolina | ALAMANCE |  | 6 | 0701023 | This project provides for the construction of sidewalk and the installation of pedestrian signals to improve pedestrian safety and mobility on US 70 (Church Street)/SR 1158 (Huffman Mill Rd) from SR | Transportation Enhancements | 12/21/2009 |  | 06/30/2010 | 38189 | 0
4645 | North Carolina | ALAMANCE |  | 6 | 0701024 | This project provides for the construction of an ADA-compliant crosswalk and sidewalk to improve pedestrian mobility and safety on SR 1158 (Huffman Mill Road) and Forestdale Drive in Alamance County. | Transportation Enhancements | 12/21/2009 |  | 06/30/2010 | 65300 | 0
4646 | North Carolina | ORANGE | DURHAM | 4 | 0702015 | This project provides for the construction of Bus Stop Shelters to improve pedestrain mobility and safety at various locations in Carboro in Orange County. This is a locally administered project by t | Transportation Enhancements | 08/28/2009 | 08/28/2009 | 09/30/2009 | 76296 | 0
4647 | North Carolina | ORANGE | DURHAM | 4 | 0702016 | This project proivdes for the construction of sidewalk on one side of Ashe Street from West Main Street to Shelton Street in Carrboro in Orange County. This is a locally administered project by the T | Other | 09/11/2009 |  |  | 139938 | 0
4648 | North Carolina | ORANGE | DURHAM | 4 | 0702017 | This project provides for the construction of sidewalk on one side of Bim Street from SR 1005 (Jones Ferry Rd) to Fidelity Street in Carrboro in Orange County. This is a locally administered project | Transportation Enhancements | 09/11/2009 |  |  | 200100 | 0
4649 | North Carolina | ORANGE | DURHAM | 4 | 0703014 | This project will upgrade the citywide traffic signal system at 124 intersections and install fiber optic communications cable in Chapel Hill / Orange County to reduce congestion and emissions and imp | Safety/Traffic Management | 08/05/2009 | 08/05/2009 | 08/01/2012 | 5686446 | 0
4650 | North Carolina | ORANGE | DURHAM | 4 | 0703017 | This project provides for the construction of pedestrian safety improvements, pedestrain refuge islands, at one (1) location on NC 86 (Martin Luther King, Jr. Drive) and four (4) locations on east Fra | Transportation Enhancements | 07/29/2009 | 08/05/2009 |  | 403952 | 0
4651 | North Carolina | GUILFORD | GREENSBORO | 6, 13 | 0708023 | This project provides for the construction of intersection improvements and sidewalk and widening Lake Jeanette Road from Lawndale Drive to SR 2348 (Bass Chapel Road/Elm Street) to improve safety and | Pavement Widening | 09/18/2009 |  | 05/23/2011 | 2867263 | 0
4652 | North Carolina | GUILFORD | GREENSBORO | 12 | 0708024 | This project provides for the construction of pedestrain improvements by replacing the median turn lane on South Elm-Sugene Street from JJ Drive to Vandalia Road to improve safety and mobility in Gree | Pavement Improvement | 09/01/2009 |  | 09/15/2010 | 1628417 | 0
4653 | North Carolina | GUILFORD | GREENSBORO | 6, 12 | 0708025 | This project will repave Holden Road from SR 4121 (High Point Road) to Pinecroft Road, Cone Boulevard form Elm Street to Summitt Avenue, Friendly Avenue from Radience Drive to Elam Avenue and Smith St | Pavement Improvement | 09/18/2009 |  | 09/03/2010 | 1501890 | 0
4654 | North Carolina | GUILFORD |  | 12 | 0710021 | High Point-SR 1486 (Lexington Ave) High Point Greenway to SR 1471 (Montlieu Ave) High Point Greenway to Carolina St - construct sidewalks in Guilford County | Transportation Enhancements | 12/21/2009 |  | 05/15/2010 | 177000 | 0
4655 | North Carolina | ORANGE |  | 4 | 0711011 | This project provides for the construction of sidewalks to improve pedestrian safety and mobility on Nash Street, Faucette Mill Street, Revere Road, Hayes Street, Union Street, Eno Street and Allison | Transportation Enhancements | 09/23/2009 |  |  | 351459 | 0
4656 | North Carolina | CHATHAM | DURHAM | 4 | 0751023 | This project will construct left turn lanes and a traffic signal on NC-751 at the intersection of O'Kelly Church Road in Chatham County to ease congestion. | Safety/Traffic Management | 08/18/2009 |  | 04/30/2009 | 523000 | 0
4657 | North Carolina | ROCKINGHAM |  | 13 | 0770003 | This project will construct curb & gutter and sidewalk to improve pedestrian mobility on the north side of NC 770 from Westridge Apartments to SR 1405 (South Glenn Street) in Rockingham County. Thi | Transportation Enhancements | 12/29/2009 |  | 05/15/2010 | 252462 | 0
4658 | North Carolina | SURRY |  | 5 | 0771192 | Rehabilitate pavement on I-77 from US 21 (Exit 79) to milepost 84 in Surry and Yadkin Counties to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 12/31/2009 | 4032676 | 5
4659 | North Carolina | MECKLENBURG |  | 12 | 0771194 | I-77 from Nations Ford Rd to Catawba Avenue - Paint Bridges at selected locations in Mecklenburg County | Other | 05/13/2009 |  |  | 20000 | 0
4660 | North Carolina | YADKIN |  | 5 | 0771195 | Rehabilitate pavement on I-77 from Iredell County line to south of SR 1125 (Asbury Church Rd) in Yadkin County to improve road condition. | Pavement Improvement | 09/08/2009 |  | 07/01/2010 | 1087392 | 3.2
4661 | North Carolina | SURRY |  | 5 | 0771196 | Rehabilitate pavement on I-77 from mile post 88.4 to mile post 90 in Surry County to improve road condition. | Pavement Improvement | 08/06/2009 | 08/06/2009 | 11/20/2009 | 246790 | 2
4662 | North Carolina | SURRY |  | 5 | 0771197 | Paint bridges carrying I-77 over NC 89 and I-74 eastbound lane in Surry County to extend the life of the structures. | Bridge Improvement | 05/01/2009 |  | 10/23/2010 | 686061 | 0
4663 | North Carolina | MECKLENBURG |  | 8,9,12 | 0771198 | This project will construct a linear wetland at the I-77 Welcome Center in Mecklenburg County, NC. The purpose of this project is to treat stormwater runoff from the Welcome Center parking lot helpin | Other | 12/07/2009 |  | 03/01/2010 | 72199 | 0
4664 | North Carolina | IREDELL |  | 10 | 0771199 | This project will construct a stormwater wetland, at the I-77SB Rest Area in Iredell County, to treat stormwater runoff from the Rest Area and a portion of the roadway before discharging into Lake Nor | Other | 10/30/2009 |  | 04/30/2010 | 132000 | 0
4665 | North Carolina | IREDELL |  | 10 | 0771200 | The project will install landscape enhancement plantings at the I-77 and Langtree Road interchange in Iredell County. | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 12/15/2009 | 260000 | 0
4666 | North Carolina | LEE |  | 2 | 0837005 | This project will construct the Endor Iron Furnace Greenway in Sanford which is a 10 feet wide paved asphalt multi-use greenway trail from Kiwanis Family Park on Carbonton Road to Boone Drive (approxi | Transportation Enhancements | 08/14/2009 |  | 10/12/2010 | 500000 | 0
4667 | North Carolina | CABARRUS |  | 8 | 0852067 | This project will rehabilitate existing pavement on I-85 from US 29/601 to NC 73 in Cabarrus County to improve road condition. | Pavement Improvement | 03/27/2009 | 03/27/2009 | 10/30/2009 | 2647031 | 3
4668 | North Carolina | GASTON |  | 9 | 0852068 | Mill and resurface I-85 from mile post 21.8 to mile post 23.5 in Gaston County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/02/2009 | 926217 | 1.7
4669 | North Carolina | CABARRUS |  | 8,12 | 0852070 | This project will renovate the existing pair of?rest area buildings located on I-85, west of Concord at Mile Post 59 into vending,?security offices?and storage, construct a new pair of restroom buildi | Pavement Improvement | 08/05/2009 |  | 10/15/2010 | 1719300 | 0
4670 | North Carolina | GUILFORD |  | 6 | 0853195 | This project provides for resurfacing I-85 in Guilford County from US 29-70/Business 85 to Groometown Road to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 08/13/2010 | 2684769 | 1.4
4671 | North Carolina | DAVIDSON |  | 6 | 0853200 | This project will renovate the existing pair of?rest area located on I-85, south of Thomasville at Mile Post 100 into vending,?security offices?and storage, construct a new pair of restroom buildings | Pavement Improvement | 08/05/2009 | 08/05/2009 | 08/15/2010 | 1944158 | 0
4672 | North Carolina | GUILFORD | GREENSBORO | 6,12,13 | 0853201 | Install pavement marking reflectors and replace damaged/missing reflectors on I-85 in Guilford County, between Groomtown Road (milepost 131) and I-40 / I-85 junction east (milepost 120) of Greensboro, | Pavement Improvement | 08/05/2009 |  | 05/01/2010 | 644332 | 0
4673 | North Carolina | GUILFORD |  | 6 | 0853202 | Install pavement marking reflectors and replace damaged/missing reflectors on I-85 in Guilford County, between NC 62 near Archdale and Business 85 in Greensboro, to improve nighttime visibility. | Pavement Improvement | 08/05/2009 |  | 05/01/2010 | 244621 | 0
4674 | North Carolina | ORANGE |  | 4 | 0854113 | Resurface I-85 in Orange County from I-40 / I-85 interchange to SR 1006 (Orange Grove Road) to improve road condition. | Pavement Improvement | 09/08/2009 |  | 07/16/2010 | 2022805 | 0
4675 | North Carolina | DURHAM |  | 04 | 0854114 | Various routes: I-85 from the Orange County line to SR 1401 (Cole Mill Road); NC 147 from I-85 to the End of Asphalt Roadway near Exit 14; US 15/501 Bypass from I-85 to US 15/501 Business - Milling, R | Pavement Improvement | 12/17/2009 |  | 12/16/2010 | 1000000 | 0
4676 | North Carolina | FORSYTH |  | 5 | 0909004 | This project constructs 481 square yards of sidewalk in Kernersville along the west side of Oakhurst Drive from Cherry St north past Lambeth Farm Lane to enhance pedestrian safety in Forsyth County. | Transportation Enhancements | 07/14/2009 |  |  | 54140 | 0
4677 | North Carolina | FORSYTH |  | 12 | 0918068 | This projects constructs new sidewalk & installs one bus shelter and required retaining walls in Winston-Salem on east side of New Walkertown Road from Waterworks Road to Spaulding Drive to enhance pe | Transportation Enhancements | 08/14/2009 |  |  | 109916 | 0
4678 | North Carolina | FORSYTH |  | 12 | 0918069 | This project constructs new sidewalk and installs two bus shelters in Winston-Salem on east side of Peters Creek Parkway from Brewer Road to the existing sidewalk and from existing sidewalk to the bus | Transportation Enhancements | 08/14/2009 | 09/24/2009 |  | 95786 | 0
4679 | North Carolina | FORSYTH |  | 12 | 0918070 | This project provides intersection improvements in Winston-Salem along Shattalon Drive intersections from Murray Road to Bright Oak Avenue to improve safety in Forsyth County. This is a locally admin | Safety/Traffic Management | 06/23/2009 | 09/24/2009 | 08/25/2010 | 292000 | 0
4680 | North Carolina | FORSYTH |  | 5 | 0923003 | This project will construct 725 feet of sidewalk in Walkertown on East Friendly Road from SR 2004 (Main Street) to Willoughby Drive with high visibility improvements to the Friendly Road/Walkertown El | Transportation Enhancements | 06/05/2009 | 01/06/2010 | 03/05/2010 | 44000 | 0
4681 | North Carolina | FORSYTH |  | 5 | 0923004 | This project will construct 617 feet of 5 feet wide concrete sidewalk in Walkertown on the east shoulder of Morris Street between Old Hollow Road (NC 66) and New Walkertown Road (US 311) to enhance pe | Transportation Enhancements | 07/14/2009 |  | 03/05/2010 | 36000 | 0
4682 | North Carolina | FORSYTH |  | 5 | 0926003 | This project constructs 5,750 feet of sidewalk and required storm drainage in the Village of Clemmons on Middlebrook Drive between Idols Road and Greenbrook Drive to enhance pedestrian safety in Forsy | Transportation Enhancements | 07/02/2009 | 01/25/2010 | 04/24/2010 | 203228 | 0
4683 | North Carolina | CUMBERLAND |  | 7 | 0951080 | This the preliminary engineering for the project that will renovate and improve existing landscape enhancements at the interchange of I-95 and NC 87 in Cumberland County. | Other | 07/13/2009 | 07/13/2009 |  | 187 | 0
4684 | North Carolina | ROBESON |  | 7 | 0951081 | The project will renovate and improve existing landscape enhancement along I-95 between Mile Post 4 through 30 in Robeson County | Transportation Enhancements | 09/24/2009 |  | 02/27/2010 | 89970 | 0
4685 | North Carolina | CUMBERLAND |  | 07 | 0951082 | Landscape | Transportation Enhancements | 10/23/2009 |  | 05/28/2010 | 363285 | 0
4686 | North Carolina | ROBESON |  | 07 | 0951083 | Landscape | Transportation Enhancements | 10/28/2009 |  | 04/02/2010 | 11875 | 0
4687 | North Carolina | JOHNSTON |  | 2 | 0952114 | Resurface I-95 from North of US 70 to North of Main Street in Johnston County to improve road condition. | Pavement Improvement | 09/11/2009 |  | 08/01/2010 | 2384640 | 0
4688 | North Carolina | WILSON |  | 3 | 0953104 | This is the preliminary engineering for the project that will focus on landscape enhancement at the interchanges US 264/US 264 Alt & I-95 / US 264 in Wilson County. | Transportation Enhancements | 07/09/2009 | 07/09/2009 | 12/15/2010 | 160265 | 0
4689 | North Carolina | STATEWIDE |  | 2, 3 | 0953105 | This project provides for pavement rehabilitation and resurfacing I-95 from south of the Nash County line (Milepost 123) in Wilson County to south of NC 58 (Milepost 128) in Nash County to improve ro | Pavement Improvement | 09/09/2009 |  | 08/15/2010 | 1720373 | 0
4690 | North Carolina | FORSYTH |  | 5 | 0999007 | This project constructs sidewalk in Rural Hall on NC 66 between Paso Street and Wall Street and constructs sidewalk and curb and gutter along Park Street between NC 66 and Church Street to improve ped | Transportation Enhancements | 06/12/2009 |  |  | 190000 | 0
4691 | North Carolina | STANLY |  | 08 | 1001052 | Albemarle: Snyder Greenway from Salisbury Avenue to Depot Street - Construct Greenway in Stanley County | Transportation Enhancements | 11/02/2009 |  |  | 225000 | 0
4692 | North Carolina | MECKLENBURG | CHARLOTTE | 9, 12 | 1003085 | This project will design the upgrade and expansion of Charlotte's Intelligent Transportation System (ITS) Communications backbone which will provide for on-the-fly remote operation of Traffic Signaliz | Safety/Traffic Management | 05/21/2009 | 05/21/2009 | 12/22/2011 | 1085000 | 0
4693 | North Carolina | MECKLENBURG |  | 12 | 1003086 | This project includes the construction of two miles of the Toby Creek Greenway in Charlotte from Mallard Creek Greenway near US 29 to University Blvd (NC 49) to improve pedestrian access in Mecklenbur | Transportation Enhancements | 09/22/2009 | 09/22/2009 |  | 1169772 | 0
4694 | North Carolina | MECKLENBURG | CHARLOTTE | 9 | 1003089 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the South Charlotte area including surveillance system along Providence Road, Ballentyne Commons Parkway and NC 51 | Safety/Traffic Management | 09/09/2009 | 09/09/2009 | 10/15/2010 | 715000 | 0
4695 | North Carolina | MECKLENBURG |  | 9 | 1003090 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the Northwest Charlotte area including surveillance system along Beatties Ford Road, Sunset Road, Statesville Road | Safety/Traffic Management | 05/19/2009 | 10/15/2009 | 12/15/2010 | 1100000 | 0
4696 | North Carolina | MECKLENBURG |  | 8,9 | 1003091 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the University area (Northwest Charlotte) including surveillance system along W. T. Harris, The Plaza, North Tryon | Safety/Traffic Management | 10/15/2009 | 10/15/2009 | 12/15/2010 | 1100000 | 0
4697 | North Carolina | MECKLENBURG |  | 9, 12 | 1003093 | Charlotte: Various locations - install pedestrian signals and crosswalk markings in Mecklenberg County | Transportation Enhancements | 10/14/2009 | 10/20/2009 |  | 800000 | 0
4698 | North Carolina | MECKLENBURG |  | 09 | 1003094 | Charlotte: Shasta lane from Randolph Rd to Sardis Rd - Install Sidewalk in Mecklenberg County | Transportation Enhancements | 10/20/2009 | 10/20/2009 | 08/15/2010 | 485000 | 0
4699 | North Carolina | DURHAM |  | 4 | 1004039 | This project will repave Old Oxford Road in Durham County from Roxboro Street to Granville County line to improve road condition. | Pavement Widening | 05/13/2009 | 05/13/2009 | 05/14/2010 | 1670081 | 0
4700 | North Carolina | MECKLENBURG |  | 12 | 1006034 | Davidson: West Branch Rocky River Greenway from River Ford Drive Eastward along West Branch Rocky River for 1.1 miles in Mecklenberg County | Transportation Enhancements | 10/20/2009 | 10/20/2009 |  | 1100000 | 0
4701 | North Carolina | UNION | CHARLOTTE | 8, 9 | 1008020 | This project will construct left turn lanes in Indian trail on Unionville Indian Trail Road at the intersection with Faith Church Road in Union County to improve safety. | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/11/2009 | 692364 | 0
4702 | North Carolina | MECKLENBURG | CHARLOTTE | 9 | 1013002 | This project includes milling existing asphalt, patching existing asphalt, repaving existing roadway, thermoplastic long life pavement markings in Matthews from North Trade Street/Matthews-Mint Hill R | Pavement Improvement | 08/18/2009 | 08/19/2009 | 06/01/2010 | 702765 | 0
4703 | North Carolina | MECKLENBURG |  | 09 | 1031007 | Mint Hill: Wilgrove-Mint Hill Rd from NC 51 to Jim Harper Lane - Construct Sidewalks in Mecklenberg County | Transportation Enhancements | 10/09/2009 | 12/10/2009 | 05/31/2010 | 300000 | 0
4704 | North Carolina | IREDELL |  | 5 | 1100024 | Widen Brawley School Rd from Centre Church Rd to I-77 in Iredell County to improve safety and mobility. | Pavement Widening | 09/15/2009 |  | 07/01/2013 | 24698618 | 0
4705 | North Carolina | ORANGE |  | 4 | 1107016 | This project will widen Old Fayetteville Road to accommodate pedestrain, bicycle and transit traffic in Carrboro / Orange County from NC 54 to Stroud Lane to provide bike lanes, sidewalks and bus turn | Transportation Enhancements | 06/22/2009 | 06/22/2009 | 09/15/2010 | 800000 | 0
4706 | North Carolina | PITT |  | 3 | 1133006 | This project adds sidewalks along the south side of SR 1133 (Main Street) in Winterville from Graham Street to Railroad Street in Pitt County to improve pedestrian safety. | Transportation Enhancements | 07/24/2009 | 09/11/2009 |  | 75000 | 0
4707 | North Carolina | PITT |  | 3 | 1133007 | This project adds sidewalks along the south side of SR 1133 (Main Street) in Winterville from Mill Street to Winterville Parkway in Pitt County to improve pedestrian safety. | Transportation Enhancements | 07/24/2009 | 09/11/2009 |  | 55000 | 0
4708 | North Carolina | SURRY |  | 5 | 1138016 | Paint bridges carrying SR 1138 (CC Camp Rd), SR 1131, SR 1122 (Dobbins Mill Rd), SR 1001, and SR 1345 over I-77 in Surry County to extend the life of the structures. | Bridge Improvement | 05/01/2009 |  | 10/23/2010 | 1071971 | 0
4709 | North Carolina | PITT |  | 3 | 1149007 | This project adds sidewalks along SR 1149 (Lee Street/Old NC 11) in Ayden from West Barwick Street to Allen Drive in Pitt County to improve pedestrian safety. | Transportation Enhancements | 07/14/2009 | 09/11/2009 |  | 75500 | 0
4710 | North Carolina | PITT |  | 3 | 1149008 | This project adds sidewalks along the west side of SR 1149 (Lee Street/Old NC 11) in Ayden from the northernmost intersection of Countryaure Drive to First Street in Pitt County to improve pedestrian | Transportation Enhancements | 09/11/2009 | 09/11/2009 |  | 166100 | 0
4711 | North Carolina | BERTIE |  | 1 | 1221013 | This project will replace deficient Bridge #36 over Connaritsa Swamp on SR 1221 (Charles Taylor Road) in Bertie County. | Bridge Replacement | 08/21/2009 |  |  | 810000 | 0
4712 | North Carolina | CURRITUCK |  | 3 | 1222012 | Replace deficient bridge carrying Tullis Creek Road over Shingle Landing Creek in Currituck County. | Bridge Replacement | 03/02/2009 | 03/02/2009 | 12/01/2009 | 650000 | 0
4713 | North Carolina | BERTIE |  | 1 | 1260002 | This project will replace deficient Bridge #16 over the Cashie River on SR 1260 (Republican Road) in Bertie County. | Bridge Replacement | 08/21/2009 |  |  | 980000 | 0
4714 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302043 | This project will provide safe, efficient mobility for bicyclist while making much needed repairs to Coxe Avenue in the Asheville in Buncombe County. | Transportation Enhancements | 08/24/2009 |  | 09/17/2010 | 246340 | 0
4715 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302044 | This is an enhancement project to provide trees, shrubs and other landscape items in the downtown central business district and a Gateway locations on Lexington and Clingman Avenues, College Street me | Transportation Enhancements | 08/28/2009 |  | 05/04/2010 | 94717 | 0
4716 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302046 | This project will provide and promote safe pedestrian facilities including the upgrade of traffic signals to for pedestrian use along Fairview Road at heavily traveled intersections in Asheville in Bu | Transportation Enhancements | 08/18/2009 |  | 05/04/2010 | 67481 | 0
4717 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302047 | This City of Asheville plans to build sidewalks to fill in gaps along city streets and NCDOT facilities to provide safe, effective pedestrian mobility to communities and businesses within Asheville in | Transportation Enhancements | 09/09/2009 |  | 09/17/2010 | 502458 | 0
4718 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302048 | This project includes repaving Kimberly Avenue from Edwin Place to Gracelyn Road and is focused at providing safe, efficient mobility for bicyclist while making much needed repairs in Asheville in Bun | Pavement Improvement | 12/03/2009 |  | 10/15/2010 | 598994 | 0
4719 | North Carolina | BUNCOMBE |  | 11 | 1302050 | This project consist of installing a pedestrian crosswalk with signals to allow safe travel between two schools located on either side of Overlook Road (SR 3503) in Buncombe County. | Transportation Enhancements | 10/19/2009 |  | 03/19/2010 | 20000 | 0
4720 | North Carolina | BUNCOMBE |  | 11 | 1302051 | This project consist of installing sidewalk and wheelchair ramps at SR 3503 (Overlook Road) at Pinchot Drive in Buncombe County. This project is in conjunction with E-5105A. | Transportation Enhancements | 10/19/2009 |  | 02/19/2010 | 17223 | 0
4721 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1305006 | This project will extend existing sidewalk along the US 70 in Black Mountain from Blue Ridge Road to Grovestone Road to promote walkability from surrounding neighborhoods to businesses along this rou | Transportation Enhancements | 08/11/2009 |  | 07/31/2010 | 233328 | 0
4722 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1305007 | Preliminary engineering for the Flat Creek Greenway from Cotton Avenue for Charlotte Street as a part of a larger plan to promote multimodal forms of transportation in the Town of Black Mountain and s | Transportation Enhancements | 08/11/2009 | 08/19/2009 | 06/30/2011 | 196503 | 0
4723 | North Carolina | ALAMANCE |  | 6 | 1306020 | This project will widen SR 1306 (Mebane Street) in Burlington / Alamance County from Huffman Mill Road to Chapel Hill Road to four naes with a divided media to enhance safety and improve mobility. | Pavement Widening | 03/02/2009 | 03/02/2009 | 08/15/2011 | 14577081 | 0
4724 | North Carolina | YANCEY |  | 11 | 1307004 | This project includes construction of 850 feet of sidewalk in Burnsville to include curb and gutter and drainage items to connect with existing sidewalks and provide safe pedestrian travel along Mitch | Transportation Enhancements | 10/28/2009 |  | 05/21/2010 | 167320 | 0
4725 | North Carolina | NASH |  | 2 | 1316012 | Replace deficient bridge Number 82 carrying SR 1316/SR 1612 over Cypress Creek in Nash County. | Bridge Replacement | 08/05/2009 | 08/05/2009 | 09/26/2010 | 722314 | 0
4726 | North Carolina | DURHAM |  | 4 | 1321005 | This project will repave Hillandale Road / Fulton Street in Durham from I-85 to Erwin Road to improve road condition. | Pavement Widening | 05/18/2009 | 05/18/2009 | 05/14/2010 | 299865 | 0
4727 | North Carolina | PITT |  | 1 | 1323004 | This project adds sidewalks along the east side of SR 1323 (Arlington Boulevard) in Greenville from SR 1467 (Stantonsburg Road) to US 13 in Pitt County to improve pedestrian safety. | Transportation Enhancements | 08/18/2009 | 09/11/2009 |  | 108897 | 0
4728 | North Carolina | BRUNSWICK |  | 7 | 1357005 | This project will realign the intersection of Smith Avenue and NC 130 in Brunswick County to eliminate the offset condition to improve safety and congestion. | Pavement Widening | 03/02/2009 | 03/02/2009 | 12/31/2010 | 7243601 | 0
4729 | North Carolina | CHEROKEE |  | 11 | 1393004 | Replace deficient bridge carrying SR 1393 (Rocky Creek-Wakefield Roads) over Junaluska Creek in Cherokee County. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 11/15/2009 | 480727 | 0
4730 | North Carolina | SURRY |  | 5 | 1396002 | Paint bridges carrying SR 1396 (Pine Ridge Rd), SR 1602, and SR 1649 (Clyde Hayes Rd) over I-77 in Surry County to extend the life of the structures. | Bridge Improvement | 05/01/2009 |  | 10/23/2010 | 385910 | 0
4731 | North Carolina | HENDERSON | ASHEVILLE | 11 | 1413010 | This project will construct a new road around the Oakdale Cemetery in Hendersonville and will provide access from US 64 to Hendersonville Elementary and Middle schools without disturbing the cemetery | Other | 10/26/2009 | 11/05/2009 | 05/05/2010 | 363000 | 0
4732 | North Carolina | HENDERSON | ASHEVILLE | 11 | 1429003 | This project will construct the Cane Creek Greenway in Fletcher which includes a 10 feet multi-use greenway trail along the banks of Cane Creek to enhance pedestrian access in Henderson County. This | Transportation Enhancements | 09/23/2009 |  | 06/30/2010 | 339544 | 0
4733 | North Carolina | HENDERSON | ASHEVILLE | 11 | 1429004 | This project will construct a sidewalk in Fletcher along St. Johns Road from US 25 to Fanning Bridge Road to enhance pedestrian access within the Town of Fletcher in Henderson County. This is a local | Transportation Enhancements | 09/23/2009 |  | 06/30/2010 | 390830 | 0
4734 | North Carolina | HENDERSON | ASHEVILLE | 11 | 1430006 | This project will construct a brick paver sidewalk in the Village of Flat Rock along US 225 and Little River Road to enhance pedestrian access within the central historic area of the Village in Haywoo | Transportation Enhancements | 09/23/2009 |  |  | 55000 | 0
4735 | North Carolina | WAKE | RALEIGH | 04 | 1435008 | SR1435 (Old Raleigh Road) from Mason Street to SR 1521 (Lake Pine Drive) and SR 1521 (Lake Pine Drive) from SR 1435 (Old Raleigh Road) to US-64 - Milling, Strengthening and Resurfacing in Wake County | Pavement Improvement | 12/15/2009 |  |  | 674164 | 0
4736 | North Carolina | GUILFORD |  | 6,12 | 1486002 | This project will repave SR 1486/1768 (Lexington Avenue) from Montlieu Avenue to US 311 Business in High Point in Guilford County to improve ride quality and extend pavement life. | Pavement Improvement | 09/14/2009 |  | 11/15/2009 | 689533 | 0
4737 | North Carolina | HAYWOOD | ASHEVILLE | 11 | 1499003 | Preliminary engineering for the construction of sidewalks along Moody Farm Road terminating at Soco Road (US 19) enhancing pedestrian access within the Town of Maggie Valley in Haywood County. This i | Transportation Enhancements | 08/19/2009 | 08/19/2009 |  | 915738 | 0
4738 | North Carolina | GUILFORD |  | 6, 12 | 1538007 | This project will provide for the realignment, resurfacing, sidewalks and drainiage improvements on SR 1538 (Deep River Road) at Sunset Hollow Drive to NC 68 (Eastchester Drive) at Lake Forest Drive o | Pavement Improvement | 09/23/2009 |  | 11/06/2010 | 1508572 | 0
4739 | North Carolina | STANLY |  | 8 | 1542009 | This project will relocate a portion of SR 1542 (Ridge St) and extend SR 1542 on new location from existing Ridge Street west of SR 1545 (Mountain View Church Rd) to SR 1549 (Airport Rd) in Stanly Cou | New Construction | 03/02/2009 | 03/02/2009 | 12/31/2010 | 4109737 | 0
4740 | North Carolina | RANDOLPH |  |  | 1547008 | This project will make improvements to increase mobility and safety at the intersection of SR 1547 (Finch Farm Road) at the intersection of SR 1533 (Mountain Road) and SR 3106 (Kennedy Road) in Trini | Other | 09/17/2009 | 09/17/2009 |  | 135000 | 0
4741 | North Carolina | FORSYTH, STOKES | WINSTON-SALEM | 5 | 1611007 | Widen Doral Drive / Main Street in Forsyth and Stokes Counties, between Tobaccoville and King, to enhance safety and mobility. | Pavement Widening | 04/27/2009 | 04/27/2009 | 08/15/2011 | 15853522 | 0
4742 | North Carolina | ANSON |  | 8 | 1627009 | Replace deficient bridge carrying SR 1627 (Pinkston-River Rd.) over Winston-Salem Southbound Railroad in Anson County. | Bridge Replacement | 06/22/2009 | 06/22/2009 | 09/01/2011 | 2526117 | 0
4743 | North Carolina | DURHAM |  | 4 | 1666002 | This project provides for the installation of sidewalk in Durham on SR 1666 (Dearborn Drive) from SR 1004 (Old Oxford Highway) to Ruth Street to improve pedestrian access and safety in Durham County. | Transportation Enhancements | 09/23/2009 |  |  | 579977 | 0
4744 | North Carolina | SCOTLAND |  | 8 | 1674005 | This project will widen Lauchwood Drive in Laurinburg / Scotland County from US 15-401 Business to US 501 to improve traffic flow. | Pavement Widening | 03/02/2009 | 03/02/2009 | 07/15/2010 | 2757443 | 0
4745 | North Carolina | PITT |  | 3 | 1708008 | This project provides for the construction of SR 1708 (Fire tower Road) from SR 1709 (Corey Road) to NC 43 to improve safety and mobility in Pitt County. This is a locally administered project by the | Pavement Improvement | 10/19/2009 |  | 08/31/2010 | 800000 | 0
4746 | North Carolina | WAKE |  | 13 | 1728004 | This project will repave the following roadways in Wake County to improve road condition: Wade Avenue from Faircloth Street to Capital Boulevard (Raleigh), Old Raleigh Road from Gregson Drive to Maso | Pavement Improvement | 08/05/2009 | 08/05/2009 | 06/11/2010 | 1497307 | 0
4747 | North Carolina | GUILFORD |  | 06 | 1853001 | SR 1853 (Sandy Camp Road) at the West Maintenance Yard (Sandy Camp Ridge) - Environmental Restoration and Pollution Abatement in Guilford County | Other | 12/29/2009 |  | 10/30/2010 | 146719 | 0
4748 | North Carolina | JOHNSTON |  | 2 | 1923009 | This project will extend Booker Dairy Road from US 70 Business to Buffalo Road in Johnston County. Route will be a two lane roadway with a new bridge over the Neuse River. | New Construction | 04/09/2009 | 04/09/2009 | 12/31/2011 | 12820595 | 0
4749 | North Carolina | NASH |  | 2 | 1945005 | Replace deficient bridge Number 69 carrying SR 1945 over Toisnot Swamp in Nash County. | Bridge Replacement | 09/11/2009 | 09/11/2009 |  | 782000 | 0
4750 | North Carolina | RANDOLPH |  | 06 | 1952001 | SR 1952 (High Point St) at SR 1950 (Academy St) & Sr 1989 (Tiger's Den Rd) and the Walmart entrance - Intersection Improvements in Randolph County | Other | 11/09/2009 |  |  | 1185000 | 0
4751 | North Carolina | GUILFORD |  | 6 | 1970001 | Repair bridge expansion joints on 12 structures: Bridge 12 on SR 1970, Bridge 274 on US 220, Bridge 136 on SR 2254, Bridge 220 on SR 1547, Bridge 757 on US 311 Business, Bridge 287 on US 70 (Wendover | Bridge Improvement | 08/05/2009 | 08/05/2009 | 05/29/2010 | 199652 | 0
4752 | North Carolina | DURHAM |  | 4 | 1978003 | This project will repave US 158 Bypass in Granville County from US 15 to US 158 Business to improve road condition. | Pavement Widening | 05/13/2009 | 05/13/2009 | 05/14/2010 | 128414 | 0
4753 | North Carolina | RUTHERFORD |  | 10, 11 | 2169001 | The project will realign Brick Store Road (SR 2194) to intersect across from Pine Ridge Rd (SR 2159) and with Oakland Rd (SR 2193) at the existing signal in Forrest City in Rutherford County. The pur | Pavement Improvement | 10/19/2009 |  | 10/22/2010 | 633052 | 0
4754 | North Carolina | MECKLENBURG | CHARLOTTE | 9, 12 | 2693002 | This project includes the construction of a roundabout in Davidson at the intersection of SR-2420 (East Rocky River Road) and SR 2693 (Davidson-Concord Road) to improve safety In Mecklenburg County. | Safety/Traffic Management | 05/13/2009 | 05/13/2009 | 10/23/2009 | 516055 | 0
4755 | North Carolina | GUILFORD |  | 06 | 2825001 | SR 2825 (Camp Burton Rd) at the East Maintenance Yard (Camp Burton) - Environmental Restoration and Pollution Abatement in Guilford County | Other | 12/29/2009 |  | 10/30/2010 | 135511 | 0
4756 | North Dakota | CASS |  | 00 | 0009030 | This Cass County project is a Structure Replacement project on a Off-System Bridge at Maple River, 6 miles East & 6 miles south of Alice. | Bridge Replacement | 06/01/2009 | 08/20/2009 | 10/03/2009 | 514417.6 | 0.047
4757 | North Dakota | TOWNER |  | 00 | 0048010 | This Towner County project is a Structure Replacement project on Off-System Bridge Off-System - 2 Miles South & 1 Mile West of Cando. | Bridge Replacement | 08/10/2009 | 09/28/2009 | 10/31/2009 | 287305.08 | 0.047
4758 | North Dakota | BARNES |  | 00 | 0221069 | This Barnes County project is a Microsurfacing on CMC 221 - From10 Miles South of Valley City, N to preserve the pavement structure. | Pavement Improvement | 06/23/2009 | 09/03/2009 | 09/15/2009 | 533000 | 9.607
4759 | North Dakota | BOTTINEAU |  | 00 | 0520055 | This Bottineau County project is a Microsurfacing on CMC 0520 - From the Souris River, E to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 06/23/2009 | 09/01/2009 | 243068.95 | 4.56
4760 | North Dakota | CASS |  | 00 | 0918055 | This Cass County project is a Thin Lift Overlay on CMC 0918 - From 8 Miles West of ND 18, E to preserve the pavement structure. | Pavement Improvement | 06/01/2009 | 06/11/2009 | 08/28/2009 | 995719 | 8.039
4761 | North Dakota | CAVALIER |  | 00 | 1017061 | This Cavalier County project is a Chip Seal Coat on CMC 1017 - From ND 5, N to Wales to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 08/03/2009 | 09/01/2009 | 243461.81 | 8.966
4762 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1083086 | This Bismarck project is a Mill & Asphalt Overlay, Curb & Gutter, Marking and Video Detection on Bismarck - 7th Street from Bismarck Expressway to Boulevard Avenue to rehabilitate the pavement structu | Pavement Improvement | 07/14/2009 | 08/10/2009 | 10/15/2009 | 658920 | 1.47
4763 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1083087 | This Bismarck project is a Mill & Asphalt Overlay, Curb & Gutter, Marking and Video Detection on Bismarck - 9th Street from Bismarck Expressway to Boulevard Avenue to rehabilitate the pavement structu | Pavement Improvement | 07/14/2009 | 08/24/2009 | 10/15/2009 | 403664 | 1.47
4764 | North Dakota | KIDDER |  | 00 | 1094121 | This NDDOT project is a Mill & Hot Bituminous Pavement on I 94 - From County Line E TO Dawson to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 |  | 09/19/2010 | 4355847 | 16.248
4765 | North Dakota | KIDDER |  | 00 | 1094122 | This NDDOT project is a Mill & Hot Bituminous Pavement on I 94 - From County Line TO E Dawson Interchange to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 |  | 09/19/2010 | 5214656.59 | 16.248
4766 | North Dakota | DIVIDE |  | 00 | 1249059 | This Divide County project is a Chip Seal Coat on CMC 1249 - From 9 & 18 Miles South of Noonan, N to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 07/22/2009 | 09/01/2009 | 159553 | 6.127
4767 | North Dakota | EMMONS |  | 00 | 1515051 | This Emmons County project is a Hot Bituminous Pavement on CMC 1515 - 0.5 miles south of ND 32, N to rehabilitate the pavement structure. | Pavement Improvement | 07/27/2009 | 09/09/2009 | 10/01/2009 | 161532.12 | 0.5
4768 | North Dakota | BURLEIGH |  | 00 | 1981086 | This Bismarck project is a Hot Bituminous Pavement and Curb & Gutter on Bismarck - North 19th Street from 75' N of E Century Ave to Oregon Dr to rehabilitate the pavement structure. | Pavement Improvement | 08/17/2009 | 09/02/2009 | 08/01/2010 | 755631.64 | 0.28
4769 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1981088 | This Bismarck project is a Concrete Pavement Repair and Mill & Overlay on Bismarck - West Main Avenue from Washington Street to Memorial Highway to rehabilitate the pavement structure. | Pavement Improvement | 06/23/2009 | 07/16/2009 | 08/01/2010 | 1367500 | 0.88
4770 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1981089 | This Bismarck project is a Mill & Asphalt Overlay on Bismarck - South Washington Street from Bismarck Expressway to 175' south of Billings Drive to rehabilitate the pavement structure. | Pavement Improvement | 08/17/2009 | 09/28/2009 | 08/01/2010 | 594755 | 1
4771 | North Dakota | MORTON | BISMARCK-MANDAN | 00 | 1988026 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - Division St NE from Collins Ave to 8th Ave NE to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 08/03/2009 | 09/18/2009 | 300000 | 0.511
4772 | North Dakota | MORTON | BISMARCK-MANDAN | 00 | 1988028 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 14th St NE from Collins Ave to 3rd Avenue NE to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 08/26/2009 | 09/18/2009 | 150000 | 0.246
4773 | North Dakota | MORTON | BISMARCK-MANDAN | 00 | 1988029 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 3rd Ave NE from 5th St NE to 14th St NE to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 08/17/2009 | 09/18/2009 | 250000 | 0.39
4774 | North Dakota | MORTON |  | 00 | 1988030 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 27th St NW from 12th Ave NW to 8th Ave NW to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 10/08/2009 | 06/30/2010 | 150000 | 0.231
4775 | North Dakota | MORTON | BISMARCK-MANDAN | 00 | 1988031 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - Old Red Trail from Sunset Drive to Collins Avenue to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 10/08/2009 | 06/30/2010 | 400000 | 0.795
4776 | North Dakota | BARNES |  | 00 | 2001053 | This NDDOT project is a Thin Lift Overlay on ND 1 - From W Jct I-94 N To Jct ND 26-DAZEY to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 4332048.58 | 19.057
4777 | North Dakota | MCINTOSH |  | 00 | 2013028 | This NDDOT project is a Thin Lift Overlay on ND 13 - From JCT 30 East To E JCT 56 to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 09/17/2009 | 10/17/2009 | 2247034.08 | 19.685
4778 | North Dakota | KIDDER |  | 00 | 2094081 | This NDDOT project is a Hot Bituminous Pavement on I 94 - From E Dawson Interchange To Crystal Springs to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 2778734.27 | 10.781
4779 | North Dakota | BARNES |  | 00 | 2094082 | This NDDOT project is a Hot Bituminous Pavement on I 94 - From W Eckelson E To E ND 1-OAKES to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 2887483.15 | 10.348
4780 | North Dakota | KIDDER |  | 00 | 2215054 | This Kidder County project is a Hot Bituminous Pavement on CMC 2215 - From 5 Miles South of ND 36, N to rehabilitate the pavement structure. | Pavement Improvement | 06/24/2009 | 09/23/2009 | 10/02/2009 | 742699 | 5.17
4781 | North Dakota | LA MOURE |  | 00 | 2281034 | This NDDOT project is a Microsurfacing and Chip Seal on US 281 - From Edgeley To 1.345 MI N JCT 46 to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/24/2009 | 09/19/2009 | 784019.27 | 19.066
4782 | North Dakota | MCHENRY |  | 00 | 2511055 | This McHenry County project is a Microsurfacing on CMC 2511 - From 7 Miles North of Granville, N to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 06/16/2009 | 09/01/2009 | 273265.93 | 5.006
4783 | North Dakota | MCKENZIE |  | 00 | 2755053 | This McKenzie County project is a Hot Bituminous Pavement on CMC 2755 - From 4.5 Miles North of Keene, N to rehabilitate the pavement structure. | Pavement Improvement | 05/29/2009 |  | 09/01/2009 | 264525 | 6.275
4784 | North Dakota | MCLEAN |  | 00 | 2800009 | This McLean County project is a Microsurfacing on CMC 2828, 2836, & 2879 - County Wide to preserve the pavement structure. | Pavement Improvement | 06/29/2009 | 07/09/2009 | 09/19/2009 | 323855 | 12.176
4785 | North Dakota | STUTSMAN |  | 00 | 2987031 | This Jamestown project is a Mill and Overlay, Signing, Striping, and Mailbox Post Replacement on Jamestown - 3rd Street E from BNSF Railroad to 87th Avenue SE to rehabilitate the pavement structure. | Pavement Improvement | 07/17/2009 | 08/18/2009 | 09/05/2009 | 745036.12 | 2.88
4786 | North Dakota | MORTON |  | 00 | 3000009 | This Morton County project is a Chip Seal Coat on CMC 3003 & 3006 - County Wide to preserve the pavement structure. | Pavement Improvement | 08/03/2009 | 08/28/2009 | 09/01/2009 | 358562 | 14.485
4787 | North Dakota | RAMSEY |  | 00 | 3002099 | This NDDOT project is a Concrete Pavement Repair, Dowel Bar Retrofit and Grinding on US 2 - From Mauvais Coulee To Channel A to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 |  | 09/15/2010 | 4519241.25 | 13.652
4788 | North Dakota | PIERCE |  | 00 | 3002106 | This NDDOT project is a Thin Lift Overlay on US 2 - From Rugby E To Near Leeds to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 3783505.47 | 24.039
4789 | North Dakota | PIERCE |  | 00 | 3003023 | This NDDOT project is a Hot Bituminous Pavement on ND 3 - From Rugby N TO JCT 66-Fonda to rehabilitate the pavement structure. | Pavement Improvement | 05/26/2009 | 06/22/2009 | 10/10/2009 | 5126342.72 | 22.877
4790 | North Dakota | RAMSEY |  | 00 | 3019047 | This Devils Lake project is a Mill & Asphalt Overlay on Devils Lake - ND 19 from US 2 to ND 20 (Asphalt Portion only) to rehabilitate the pavement structure. | Pavement Improvement | 05/26/2009 | 08/22/2009 | 10/01/2009 | 75000 | 0.182
4791 | North Dakota | WARD |  | 00 | 3020081 | This Devils Lake project is a Mill & Asphalt Overlay on Devils Lake - ND 20 from US 2 to (RP 104.408) Urban Limits (exception 3rd St NW to 6th St NE) to rehabilitate the pavement structure. | Pavement Improvement | 05/26/2009 | 08/05/2009 | 10/01/2009 | 647824 | 1.504
4792 | North Dakota | MOUNTRAIL |  | 00 | 3100009 | This Mountrail County project is a Chip Seal Coat on CMC 3114, 3133, 3136, & 3143 - County Wide to preserve the pavement structure. | Pavement Improvement | 07/21/2009 | 08/21/2009 | 09/04/2009 | 264592 | 11.835
4793 | North Dakota | NELSON |  | 00 | 3204064 | This Nelson County project is a Chip Seal Coat on CMC 3204 - From ND 1, E to preserve the pavement structure. | Pavement Improvement | 05/22/2009 | 08/05/2009 | 08/15/2009 | 283946.62 | 9.993
4794 | North Dakota | PEMBINA |  | 00 | 3428053 | This Pembina County project is a Structure Replacement project on CMC 3428 - 6 Miles West of Pittsburg. | Bridge Replacement | 07/13/2009 | 07/28/2009 | 10/31/2009 | 299600.91 | 0.1
4795 | North Dakota | PIERCE |  | 00 | 3521058 | This Pierce County project is a Chip Seal Coat on CMC 3521 - City of Rugby to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 07/23/2009 | 09/01/2009 | 109852 | 2.807
4796 | North Dakota | PIERCE |  | 00 | 3521059 | This Pierce County project is a Chip Seal Coat on CMC 3521 - City of Rugby CMC 3521 Spur to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 07/24/2009 | 09/01/2009 | 37571.44 | 1.116
4797 | North Dakota | RANSOM |  | 00 | 3705055 | This Ransom County project is a Chip Seal Coat on CMC 3705 - 8 miles south of ND 46, N to preserve the pavement structure. | Pavement Improvement | 06/16/2009 | 08/25/2009 | 09/01/2009 | 185632 | 8.022
4798 | North Dakota | RICHLAND |  | 00 | 3913054 | This Richland County project is a Hot Bituminous Pavement on CMC 3913 - 4 miles north of Barney, N to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 |  | 10/02/2009 | 407833 | 4
4799 | North Dakota | WARD |  | 00 | 4002084 | This NDDOT project is a Thin Lift Overlay on US 2 - From 3 Miles W Jct 52 E TO 1 Mile W Jct 83 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 2381095.48 | 13.63
4800 | North Dakota | WARD |  | 00 | 4002092 | This NDDOT project is a Thin Lift Overlay on US 2 - From 3 Miles West of Jct 52 East TO 1 Mile West Jct 83 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 2311718.04 | 14.274
4801 | North Dakota | ROLETTE |  | 00 | 4006060 | This Rolette County project is a Hot Bituminous Pavement on CMC 4006 - From 5.7 Miles West of St. John, E to rehabilitate the pavement structure. | Pavement Improvement | 05/26/2009 | 07/24/2009 | 10/09/2009 | 796362 | 5.667
4802 | North Dakota | MOUNTRAIL |  | 00 | 4023009 | This NDDOT project is a Thin Lift Overlay on ND 23 - From JCT 8 East To Makoti to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/17/2009 | 10/10/2009 | 2348797.22 | 21.299
4803 | North Dakota | WARD |  | 00 | 4023010 | This NDDOT project is a Thin Lift Overlay on ND 23 - From Makoti E To JCT US 83 to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/17/2009 | 10/10/2009 | 2542353.46 | 24.813
4804 | North Dakota | MCLEAN |  | 00 | 4037012 | This NDDOT project is a Thin Lift Overlay on ND 37 - From JCT 23-Parshall-S TO 1 MI W ND 1804 to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/10/2009 | 10/10/2009 | 1986624.37 | 14.985
4805 | North Dakota | MCLEAN |  | 00 | 4037013 | This NDDOT project is a Thin Lift Overlay on ND 37 - From 1 MI W JCT 1804 E & S TO Emmet Corner to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/10/2009 | 10/10/2009 | 3048303.35 | 28.865
4806 | North Dakota | MCLEAN |  | 00 | 4083053 | This NDDOT project is a Grading, Base and Asphalt Pavement project on US 83 - From Near JCT 37 N TO 0.6 MI N Max Southbound to reconstruction the existing pavement. | Pavement Improvement | 04/21/2009 | 05/20/2009 | 10/17/2009 | 9371770.49 | 12.01
4807 | North Dakota | STARK |  | 00 | 4510060 | This Stark County project is a Thin Lift Overlay on CMC 4510 - From South Heart, East to preserve the pavement structure. | Pavement Improvement | 07/07/2009 | 08/12/2009 | 10/16/2009 | 680000 | 4.871
4808 | North Dakota | GRIGGS |  | 00 | 4612051 | This Steele County project is a Chip Seal Coat on CMC 4612 - Griggs co ln, east to ND 32 to preserve the pavement structure. | Pavement Improvement | 07/07/2009 | 07/20/2009 | 09/01/2009 | 136481 | 8
4809 | North Dakota | STUTSMAN |  | 00 | 4718058 | This Stutsman County project is a Chip Seal Coat on CMC 4718 - From Buchanan, E to preserve the pavement structure. | Pavement Improvement | 06/16/2009 | 07/14/2009 | 09/01/2009 | 148334.07 | 7.141
4810 | North Dakota | STUTSMAN |  | 00 | 4718059 | This Stutsman County project is a Chip Seal Coat on CMC 4718 - From ND 20, E to preserve the pavement structure. | Pavement Improvement | 06/16/2009 | 07/14/2009 | 09/01/2009 | 164762.06 | 8.01
4811 | North Dakota | WARD |  | 00 | 4989070 | This Minot project is a Mill & Asphalt Overlay on Minot - 31st Ave SW from Broadway to 16th St SW to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 | 08/03/2009 | 07/01/2010 | 379301.71 | 1.009
4812 | North Dakota | WARD |  | 00 | 4989071 | This Minot project is a Mill & Asphalt Overlay on Minot - 4th Ave NW from Broadway to Bypass to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 | 08/03/2009 | 07/01/2010 | 878864.52 | 1.822
4813 | North Dakota | WARD |  | 00 | 4989072 | This Minot project is a Chip Seal Coat on Minot - 11th Ave S from Hiawatha to 16th St SW to preserve the pavement structure. | Pavement Improvement | 07/17/2009 |  | 09/01/2009 | 90661.88 | 1.391
4814 | North Dakota | WARD |  | 00 | 4989073 | This Minot project is a Chip Seal Coat on Minot - 31st Ave SE from Broadway to 13th St SE to preserve the pavement structure. | Pavement Improvement | 07/17/2009 |  | 09/01/2009 | 49839.39 | 0.987
4815 | North Dakota | WARD |  | 00 | 4989075 | This Minot project is a Mill & Asphalt Overlay on Minot - 3rd St NE from Hillcrest to Airport to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 | 08/04/2009 | 07/01/2010 | 136353.18 | 0.502
4816 | North Dakota | WARD |  | 00 | 4989076 | This Minot project is a Chip Seal Coat on Minot - 3rd St NE from Hillcrest to 5th Ave NE to preserve the pavement structure. | Pavement Improvement | 07/17/2009 |  | 09/01/2009 | 43499.82 | 0.417
4817 | North Dakota | WARD |  | 00 | 4989077 | This Minot project is a Asphalt Overlay on Minot - 11th Ave SE from 31st St SE to 42nd St SE to rehabilitate the pavement structure. | Pavement Improvement | 12/30/2009 |  | 10/15/2010 | 160242.09 | 0.739
4818 | North Dakota | WARD |  | 00 | 4989078 | This Minot project is a Asphalt Overlay on Minot - 31st St SE from Burdick Expressway to 11th Ave SE to rehabilitate the pavement structure. | Pavement Improvement | 12/30/2009 |  | 10/15/2010 | 32489.52 | 0.254
4819 | North Dakota | WARD |  | 00 | 4989079 | This Minot project is a Mill & Asphalt Overlay on Minot - Railway Ave from 5th St NE to 13th St NE to rehabilitate the pavement structure. | Pavement Improvement | 12/30/2009 |  | 10/15/2010 | 227356.26 | 0.53
4820 | North Dakota | WARD |  | 00 | 4989080 | This Minot project is a Chip Seal Coat on Minot - 27th St from Burdick to Railway Ave to preserve the pavement structure. | Pavement Improvement | 07/17/2009 |  | 09/01/2009 | 42761.53 | 0.657
4821 | North Dakota | WARD |  | 00 | 4989081 | This Minot project is a Chip Seal Coat on Minot - 21st Ave NW from US 83 Bypass to 20th St NW to preserve the pavement structure. | Pavement Improvement | 07/17/2009 |  | 09/01/2009 | 42122.69 | 0.625
4822 | North Dakota | WALSH |  | 00 | 5000009 | This Walsh County project is a Chip Seal Coat on CMC 5018 & 5047 - County Wide to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 07/28/2009 | 09/01/2009 | 316589.27 | 12.494
4823 | North Dakota | STARK |  | 00 | 5008033 | This NDDOT project is a Thin Lift Overlay on ND 8 - From 1.4 Miles N County Line N Through Richardton to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/09/2010 | 2612119.85 | 16.748
4824 | North Dakota | STARK |  | 00 | 5022085 | This Dickinson project is a Slurry Seal on Dickinson - ND 22 from 8th Street SW to Heart River Bridge to rehabilitate the pavement structure. | Pavement Improvement | 09/08/2009 | 08/27/2009 | 09/19/2009 | 128321.41 | 0.597
4825 | North Dakota | STARK |  | 00 | 5094045 | This NDDOT project is a PCC Pavement Recycle project on I 94 - From Youngmans Butte to near Eagles Nest to reconstruction the existing pavement. | Pavement Improvement | 03/24/2009 | 05/01/2009 | 10/17/2009 | 19503471.09 | 12.89
4826 | North Dakota | STARK |  | 00 | 5094055 | This NDDOT project is a I-94 landscaping enhancement near Dickinson - I-94 from Exit 59 to Exit 64. | Transportation Enhancements | 11/10/2009 |  | 10/29/2010 | 272395.64 | 5.395
4827 | North Dakota | BILLINGS |  | 00 | 5094067 | This NDDOT project is a Slurry Seal on I 94 - From Fryburg To Belfield to preserve the pavement structure. | Pavement Improvement | 04/07/2009 | 08/17/2009 | 09/01/2009 | 677742 | 15.489
4828 | North Dakota | WARD |  | 00 | 5153056 | This Ward County project is a Chip Seal Coat on CMC 5153 - From 4 Miles East of Surrey, N & from 17 Miles South & 1 Mile west of Sawyer, N to preserve the pavement structure. | Pavement Improvement | 06/29/2009 | 07/07/2009 | 09/01/2009 | 626623 | 26.021
4829 | North Dakota | WILLIAMS |  | 00 | 5351053 | This Williams County project is a Hot Bituminous Pavement on CMC 5351 - FROM From 4 Miles South of US 2, N to rehabilitate the pavement structure. | Pavement Improvement | 06/02/2009 |  | 10/01/2009 | 439452.04 | 3.968
4830 | North Dakota | STARK |  | 00 | 5983038 | This Dickinson project is a Slurry Seal on Dickinson - ND 22 Frontage Roads from 8th Street SW to Heart River Bridge to rehabilitate the pavement structure. | Pavement Improvement | 09/08/2009 | 08/27/2009 | 09/19/2009 | 91857.18 | 0.5
4831 | North Dakota | STARK |  | 00 | 5983039 | This Dickinson project is a Slurry Seal on Dickinson - 4th Avenue E from Villard to Museum Drive to rehabilitate the pavement structure. | Pavement Improvement | 09/08/2009 | 08/27/2009 | 09/19/2009 | 147567.51 | 1.1
4832 | North Dakota | STARK |  | 00 | 5983040 | This Dickinson project is a Mill & Asphalt Overlay on Dickinson - 21st Street W from 10th Avenue W to 10th Ave E to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/21/2009 | 10/16/2009 | 721357.13 | 1.447
4833 | North Dakota | NELSON |  | 00 | 6002078 | This NDDOT project is a Thin Lift Overlay on US 2 - From Michigan Bypass E To County Line? to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 1705937.92 | 10.189
4834 | North Dakota | PEMBINA |  | 00 | 6066016 | This NDDOT project is a Thin Lift Overlay on ND 66 - From S Jct 81-St. Thomas E TO I-29 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 1729395.06 | 11.866
4835 | North Dakota | CAVALIER |  | 00 | 6066017 | This NDDOT project is a Thin Lift Overlay on ND 66 - From District Boundary E TO N Jct 32 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 798701.9 | 8.038
4836 | North Dakota | PEMBINA |  | 00 | 6066018 | This NDDOT project is a Mill & Asphalt Overlay on ND 66 - From S JCT 32-Gardar E To Crystal to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 1325483.57 | 8.922
4837 | North Dakota | PEMBINA |  | 00 | 6066019 | This NDDOT project is a Thin Lift Overlay on ND 66 - From Crystal E To N Jct 81 St. Thomas to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 1461386.28 | 10.13
4838 | North Dakota | WALSH |  | 00 | 6985042 | This Grafton project is a Mill & Asphalt Overlay on Grafton - 5th Street from McHugh Avenue to Burgamott Avenue to rehabilitate the pavement structure. | Pavement Improvement | 06/12/2009 | 06/16/2009 | 10/02/2009 | 332027.92 | 0.6
4839 | North Dakota | WALSH |  | 00 | 6985043 | This Grafton project is a Chip Seal Coat on Grafton Urban Roads - 10 Sites to preserve the pavement structure. | Pavement Improvement | 07/02/2009 | 07/08/2009 | 09/01/2009 | 209850 | 4
4840 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986087 | This Grand Forks project is a Signals and Pavement Marking on Grand Forks - Intersection of 47th Ave S and Washington Street to preserve the pavement structure. | Pavement Improvement | 06/17/2009 | 07/22/2009 | 11/01/2009 | 372275.65 | 0.06
4841 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986088 | This Grand Forks project is a Sign Replacement project on various Streets. | Other | 11/03/2009 |  | 07/01/2010 | 257142.56 | 9.118
4842 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986090 | This Grand Forks project is a Chip Seal Coat on Grand Forks - University Avenue from 3rd Street N to State Street to preserve the pavement structure. | Pavement Improvement | 07/15/2009 |  | 09/01/2009 | 258000 | 2.42
4843 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986091 | This Grand Forks project is a Chip Seal Coat on Grand Forks - Mill Road from Gateway Drive N to Urban limit to preserve the pavement structure. | Pavement Improvement | 07/15/2009 |  | 09/01/2009 | 57000 | 1.56
4844 | North Dakota | GRAND FORKS |  | 00 | 6986092 | This Grand Forks project is a Chip Seal Coat on Grand Forks - 20th Street N from Gateway Drive to University Avenue to preserve the pavement structure. | Pavement Improvement | 07/15/2009 |  | 09/01/2009 | 42600 | 0.73
4845 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986093 | This Grand Forks project is a Chip Seal Coat on Grand Forks - 20th Street S from 24th Avenue S to 32nd Avenue to preserve the pavement structure. | Pavement Improvement | 07/15/2009 |  | 09/01/2009 | 28000 | 0.48
4846 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986096 | This Grand Forks project is a Concrete Pavement Repair and Mill & Overlay on Grand Forks - 8th Avenue N from 3rd Street N to Columbia Road to rehabilitate the pavement structure. | Pavement Improvement | 07/15/2009 | 08/06/2009 | 10/01/2009 | 365000 | 1.06
4847 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986099 | This Grand Forks project is a Concrete Pavement Repair on Grand Forks - 17th Avenue S from Washington Street to 42nd Ave S to rehabilitate the pavement structure. | Pavement Improvement | 07/15/2009 | 07/27/2009 | 10/01/2009 | 679879.12 | 1.96
4848 | North Dakota | MCKENZIE |  | 00 | 7023027 | This NDDOT project is a Hot Bituminous Pavement on ND 23 - From Watford City East TO JCT 73 to rehabilitate the pavement structure. | Pavement Improvement | 05/05/2009 | 06/29/2009 | 10/10/2009 | 4255041.2 | 15.587
4849 | North Dakota | MCKENZIE |  | 00 | 7023029 | This NDDOT project is a Thin Lift Overlay on ND 23 - From JCT 73 N&E TO Reservation Boundary to preserve the pavement structure. | Pavement Improvement | 05/05/2009 | 06/29/2009 | 10/10/2009 | 2492984.65 | 19.112
4850 | North Dakota | WILLIAMS |  | 00 | 7804034 | This NDDOT project is a Thin Lift Overlay on ND 1804 - From Beaver Creek W TO E BN Overpass to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/19/2009 | 10/10/2009 | 3462202.62 | 29.009
4851 | North Dakota | WILLIAMS |  | 00 | 7993030 | This Williston project is a Mill & Asphalt Overlay, Curb Ramps, and Driveways on Williston - 22nd St from 2nd Avenue West to University Ave to rehabilitate the pavement structure. | Pavement Improvement | 06/26/2009 | 07/07/2009 | 10/02/2009 | 240000 | 0.487
4852 | North Dakota | WILLIAMS |  | 00 | 7993031 | This Williston project is a Mill & Asphalt Overlay, Curb Ramps, Sidewalks, and Driveways on Williston - 22nd St E from University Ave to 12th Ave E (E Dakota Parkway) to rehabilitate the pavement stru | Pavement Improvement | 06/26/2009 | 07/07/2009 | 10/02/2009 | 108686 | 0.33
4853 | North Dakota | WILLIAMS |  | 00 | 7993032 | This Williston project is a Mill & Asphalt Overlay, Sidewalk, Driveway, Valley Gutters, Curb Ramps on Williston - 26th St W from 6th Ave W to 16th Ave W to rehabilitate the pavement structure. | Pavement Improvement | 06/26/2009 | 07/07/2009 | 10/02/2009 | 260000 | 0.675
4854 | North Dakota | WILLIAMS |  | 00 | 7993033 | This Williston project is a Mill & Asphalt Overlay, Sidewalk, Driveway, Valley Gutters, Curb Ramps on Williston - West 2nd Avenue W Frontage Road from 6th Ave W to 42nd Street to rehabilitate the pav | Pavement Improvement | 06/26/2009 | 07/08/2009 | 10/02/2009 | 210000 | 0.7
4855 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8010034 | This Fargo project is a Mill & Asphalt Overlay on Fargo - Main Avenue from 2nd Street N to 25th Street to rehabilitate the pavement structure. | Pavement Improvement | 07/29/2009 | 08/19/2009 | 10/01/2009 | 495000 | 1.54
4856 | North Dakota | SARGENT |  | 00 | 8011022 | This NDDOT project is a Thin Lift Overlay on ND 11 - From N Jct 32 To S JCT 32-Forman to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 09/19/2010 | 98553.13 | 0.791
4857 | North Dakota | RICHLAND |  | 00 | 8029099 | This NDDOT project is a Concrete Pavement Repair on I 29 - From ND 13 N TO Christine Interchange to rehabilitate the pavement structure. | Pavement Improvement | 03/24/2009 | 06/10/2009 | 09/26/2009 | 1315100.15 | 21.244
4858 | North Dakota | RICHLAND |  | 00 | 8029104 | This NDDOT project is a Concrete Pavement Repair on I 29 - From ND 13 N TO Christine Interchange to rehabilitate the pavement structure. | Pavement Improvement | 03/24/2009 | 06/16/2009 | 09/26/2009 | 1611906.87 | 21.268
4859 | North Dakota | SARGENT |  | 00 | 8032028 | This NDDOT project is a Thin Lift Overlay on ND 32 - From SD Line to S. Jct. ND 11 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 09/19/2010 | 1205336.44 | 10.024
4860 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8984113 | This Fargo project is a Structure Replacement project on Fargo - 38th St Bridge over Drain 27. | Bridge Replacement | 12/14/2009 |  | 09/03/2010 | 751743.94 | 0.091
4861 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8984114 | This Fargo project is a Structure Widening project on Fargo - 45th St at Drain 27. | Bridge Improvement | 12/14/2009 |  | 09/03/2010 | 317000 | 0.022
4862 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8984116 | This Fargo project is a Mill & Asphalt Overlay on Fargo - 25th Street from 32nd Avenue S to Rose Coulee to rehabilitate the pavement structure. | Pavement Improvement | 07/29/2009 | 07/13/2009 | 08/22/2009 | 362500 | 1.487
4863 | North Dakota | CASS | BISMARCK-MANDAN | 00 | 8984118 | This Fargo project is a Asphalt Overlay and Concrete Pavement Repair on Fargo - Old HWY 81 from Dakota Dr to Co. Rd 20 to rehabilitate the pavement structure. | Pavement Improvement | 07/29/2009 | 09/21/2009 | 10/01/2009 | 380000 | 1.94
4864 | North Dakota | CASS | BISMARCK-MANDAN | 00 | 8984119 | This Fargo project is a City wide pavement marking project to restore pavement markings. | Pavement Improvement | 07/20/2009 | 07/27/2009 | 10/15/2009 | 400000 | 10.075
4865 | North Dakota | RICHLAND |  | 00 | 8991021 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 6th Street S from Dakota Ave. to 11th Ave. S. to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/12/2009 | 10/02/2009 | 102000 | 0.658
4866 | North Dakota | RICHLAND |  | 00 | 8991022 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 4th Avenue S from 6th St. S to 11th St. S to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/12/2009 | 10/02/2009 | 41000 | 0.34
4867 | North Dakota | RICHLAND |  | 00 | 8991023 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 2nd Avenue N from 2nd St. N to 11th St. N to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/12/2009 | 10/02/2009 | 56000 | 0.698
4868 | North Dakota | RICHLAND |  | 00 | 8991024 | This Wahpeton project is a Pavement Patching and Seal Coat on Wahpeton - 7th Street N from 8th Ave N to 16th Ave N to preserve the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 48236.61 | 0.747
4869 | North Dakota | RICHLAND |  | 00 | 8991025 | This Wahpeton project is a Chip Seal Coat on Wahpeton - 4th Street N from 2nd Ave N to ND 210 to preserve the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 121146.63 | 1.69
4870 | North Dakota | RICHLAND |  | 00 | 8991026 | This Wahpeton project is a Mill & Asphalt Overlay on Wahpeton - 11th Street N from 16th Ave N to ND 210 to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 148473.92 | 0.487
4871 | North Dakota | RICHLAND |  | 00 | 8991027 | This Wahpeton project is a Pavement Patching and Mill & Asphalt Overlay on Wahpeton - 7th Street N from 2nd Ave N to 8th Ave N to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 119400 | 0.435
4872 | North Dakota | RICHLAND |  | 00 | 8991028 | This Wahpeton project is a Pavement Patching and Mill & Asphalt Overlay on Wahpeton - 11th Street N from Dakota to B Ave to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 106984 | 0.794
4873 | North Dakota | CASS |  | 00 | 8992031 | This West Fargo project is a Mill & Asphalt Overlay on West Fargo, 6 locations to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 | 07/15/2009 | 08/15/2009 | 1226294 | 5.24
4874 | Ohio | LUCAS |  | 9 | E031995 | This is a preservation project on I-75 from North Cove bridge to Cecilia. It will prevent future pavement decay on this priority route. The resurfacing project will prolong the life of I-75 between Be | Pavement Improvement | 08/25/2009 | 09/08/2009 | 11/20/2009 | 1225000 | 2.7
4875 | Ohio | CRAWFORD |  | 5 | E032086 | This project will resurface approximately 11.50 miles of SR 4 from the north corporation limit of the city of Bucyrus to the Seneca County line. It includes bridge work at seven locations. | Pavement Improvement | 08/06/2009 | 09/16/2009 | 07/30/2010 | 3250840 | 11.33
4876 | Ohio | SUMMIT | AKRON | 13 | E032369 | This project is to reconstruct the 15th street bridge over ABC railroad in Barberton | Bridge Replacement | 09/11/2009 |  | 06/30/2011 | 268000 | 0
4877 | Ohio | JACKSON |  | 18 | E035110 | This is a four-lane minor rehabilitation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Jackson County. The project includes re | Pavement Improvement | 08/06/2009 | 08/28/2009 | 10/31/2010 | 9669140 | 9.69
4878 | Ohio | CLERMONT |  | 1, 2, 3, 7, 8 | E035574 | Painting of Clinton U.S. 68 bridge over Cowan Creek; Clinton U.S. 68 over Anderson Ford; Wilmington Road bridge over I-71 in Warren; Stubbs Mills Road bridge over I-71 in Warren. | Bridge Improvement | 06/15/2009 | 08/21/2009 | 06/01/2010 | 1334490 | 0
4879 | Ohio | PREBLE |  | 8 | E035896 | Repave portions of SR 732; also resurface Eaton-Oxford Rd., CR 29, in from the Morning Sun Outpost | Pavement Improvement | 08/06/2009 |  | 06/30/2010 | 2332670 | 13.54
4880 | Ohio | LICKING |  | 12, 18 | E036406 | This project includes the resurfacing of State Route 16 from mile marker 19.72 near the 21st Street bridge east to mile marker 23.66 near the Dayton Road Intersection. The project also includes the re | Pavement Improvement | 09/03/2009 | 09/08/2009 | 10/30/2010 | 6230065.56 | 6.3
4881 | Ohio | JACKSON |  | 18 | E036464 | This is a preservation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Jackson County. The project will resurface 11.45 miles (2 | Pavement Improvement | 07/23/2009 | 09/21/2009 | 10/31/2009 | 1580350 | 11.45
4882 | Ohio | CUYAHOGA | CLEVELAND, OH | 10 | E036720 | This project is to rahabilitate the West 77th Street bridge over Norfolk Southern Railroad and GCRTA located between Franklin Ave and Madison Ave in Cleveland | Bridge Replacement | 10/16/2009 | 01/06/2010 | 06/30/2011 | 1509000 | 0
4883 | Ohio | MIAMI | DAYTON | 3,8 | E040008 | Improving travel and providing better connectivity is what this project will do. 5 miles of roadway will be resurfaced from the Montgomery/Miami county line to Tipp City in Miami County. | Pavement Improvement | 06/25/2009 | 07/08/2009 | 09/30/2009 | 1800000 | 4.84
4884 | Ohio | ATHENS |  | 6, 18 | E040367 | The project is a five-mile, two-lane resurfacing project which includes two miles of SR 682 in Athens County and six miles of SR 356 in Vinton County. | Pavement Improvement | 06/15/2009 | 08/21/2009 | 06/15/2010 | 803850 | 12.52
4885 | Ohio | TUSCARAWAS |  | 18 | E040567 | Replace existing bridge constructed in 1906 over the Tuscarawas River between Front Street and Broadway in the city of Dover with a new multi-span, multi-beam bridge with sidewalks and pedestrian rail | Transportation Enhancements | 06/15/2009 | 09/18/2009 | 06/30/2011 | 160944 | 0.06
4886 | Ohio | HANCOCK |  | 4 | E040571 | Pave deteriorated sections along Interstate 75 in Hancock County, starting at State Route 613 north to the Wood County line. | Pavement Improvement | 06/12/2009 | 07/06/2009 | 08/30/2009 | 1128068.62 | 2.81
4887 | Ohio | HARDIN |  | 4 | E040577 | Repave route SR37 from the Hancock County line to the Wyandot County line through the village of Forest and SR53 from the North Corporation limit of Kenton to SR37 in Hardin County due to pavement det | Pavement Improvement | 07/08/2009 | 08/27/2009 | 10/01/2009 | 291000 | 12.87
4888 | Ohio | LORAIN |  | 9 | E040597 | This project in southern Lorain County replaces 2 structures west of the Village of Wellington. The first is a 133' structure over the West Branch of the Black River, 0.57-mile west of Quarry Road and | Bridge Replacement | 12/01/2009 |  | 09/01/2011 | 1000000 | 0.08
4889 | Ohio | MUSKINGUM |  | 18 | E050443 | To improve this major distribution link in East Central Ohio, this project will resurface approximately 3 miles of State Route 16 in Muskingum County and almost 10 miles of State Route 16 in Coshocton | Pavement Improvement | 06/15/2009 | 07/06/2009 | 11/20/2009 | 2998548.2 | 13
4890 | Ohio | MERCER |  | 4 | E050631 | This project will correct deficiencies in the bridge as part of an Ohio Department of Transportation (ODOT) initiative to ?Fix it First.? Preserving this bridge on SR 118 in Mercer County by removing | Bridge Improvement | 07/06/2009 | 08/27/2009 | 09/30/2009 | 205790 | 0
4891 | Ohio | HOCKING |  | 18 | E050633 | This project is a nine mile, two-lane resurfacing project using an asphalt overlay on SR-180 in Hocking county | Pavement Improvement | 09/03/2009 |  | 07/15/2010 | 961651.6 | 9.16
4892 | Ohio | PICKAWAY |  | 7 | E051164 | This project rehabilitates nine bridges on US 23 throughout Pickaway County. Original construction of these bridges was in the 1950s. Rehabilitation includes resurfacing or replacement of the bridge d | Pavement Improvement | 07/24/2009 | 07/24/2009 | 09/30/2010 | 10000000 | 0.58
4893 | Ohio | STARK | CANTON | 16 | E051227 | Construct bicycle/pedestrian bridge at Deer Creek Dam spill way in Stark County | Transportation Enhancements | 08/12/2009 | 09/14/2009 | 06/30/2010 | 611485 | 0
4894 | Ohio | FRANKLIN |  | 15 | E051293 | Bridge maintenance projects on the Broad Street bridge over I-71 including backwall repair, new barrier wall, vandal fence and curb ramps. | Bridge Improvement | 08/20/2009 | 10/26/2009 | 05/31/2010 | 714080 | 0.01
4895 | Ohio | MONTGOMERY | DAYTON | 3 | E051298 | Reconstruction 5 lanes of MOT CR 99 from Stonequarry Road to Cresthill Drive in Vandalialanes. | Pavement Improvement | 07/06/2009 | 09/16/2009 | 05/31/2010 | 126392 | 0.449
4896 | Ohio | SENECA |  | 5 | E060167 | Bridge replacement on State Route 67, near State Route 100, in Seneca County. This project will provide a new bridge structure. | Bridge Replacement | 06/26/2009 | 08/25/2009 | 09/30/2010 | 1575119.1 | 0.089
4897 | Ohio | TUSCARAWAS |  | 18 | E060275 | This project is to construct a new interchange off I-77 at CR 80 in Dover to help relieve congestion at the existing I-77 interchanges in Dover and Strasburg. This interchange will provide improved ac | New Construction | 07/23/2009 | 09/16/2009 | 06/30/2011 | 2149271.79 | 1.739
4898 | Ohio | HURON |  | 5 | E060304 | Replacement of the North Street Bridge in the Village of Plymouth. The existing bridge is in very poor condition, has an ODOT bridge appraisal rating of 2P and a load limit of 20 tons. The project inc | Bridge Replacement | 07/09/2009 | 09/08/2009 | 10/30/2009 | 210000 | 0.02
4899 | Ohio | HANCOCK |  | 4 | E060317 | Add turn lanes on the north and west approaches of the intersection at SR 568 and Township Road 236 | Safety/Traffic Management | 08/06/2009 | 08/31/2009 | 11/30/2009 | 475500 | 0.22
4900 | Ohio | CRAWFORD |  | 5 | E060342 | This project involves the full reconstruction of State Route 4/State Route 98 (Sandusky Avenue) through Downtown Bucyrus. The 0.51 mile long project begins at Charles Avenue and concludes at the Sandu | Pavement Improvement | 07/14/2009 | 08/03/2009 | 10/27/2010 | 4675652.3 | 0.55
4901 | Ohio | BELMONT |  | 6, 18 | E060378 | Resurface almost six miles of SR 147, from Belmont to SR 9 near Centerville, and over six miles of SR 149 from SR 9 at Warnock to Belmont. | Pavement Improvement | 07/23/2009 | 08/31/2009 | 10/30/2009 | 935980 | 11.98
4902 | Ohio | PERRY |  | 7 | E060540 | Modernizing a main connector for residents and businesses to the major cities of Zanesville in Muskingum County and Lancaster in Fairfield County, this project will resurface 14 miles of highly-travel | Pavement Improvement | 06/25/2009 | 08/20/2009 | 09/30/2009 | 1548480.7 | 7.5
4903 | Ohio | LICKING |  | 18 | E060550 | As part of the Ohio Department of Transportation?s ?Fix it First? initiative, this project will help correct deficiencies in the bridges at two locations on U.S. 40 in Licking and Muskingum counties. | Bridge Improvement | 08/20/2009 | 09/08/2009 | 09/15/2010 | 356130 | 0.039
4904 | Ohio | PUTNAM |  | 5 | E060605 | Repave routes SR189 and SR190 through the village of Ft. Jennings from the west corporation limits to US224 and SR694 from SR115 to the west corporation limit of the village of Glandorf in Putnam Coun | Pavement Improvement | 06/25/2009 | 09/25/2009 | 10/31/2009 | 958437.3 | 9.62
4905 | Ohio | AUGLAIZE |  | 4 | E060946 | This project is to resurface the existing roadway with asphalt concrete on SR-362 in Auglaize county from the Shelby/Auglaize county line to the Village of Minster and in Shelby county from Lake Loram | Pavement Improvement | 06/11/2009 | 07/21/2009 | 08/31/2009 | 476000 | 3.37
4906 | Ohio | SHELBY |  | 4 | E060967 | This project is to resurface the existing roadway with asphalt concrete on SR47 from 0.59 mile East of SR66 to Kuther Road in Shelby county | Pavement Improvement | 08/06/2009 | 09/15/2009 | 10/31/2009 | 1306370 | 8.17
4907 | Ohio | HIGHLAND |  | 3 | E070048 | This is a preservation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Highland County. The project will resurface U.S. Route 62 | Pavement Improvement | 06/15/2009 | 09/09/2009 | 10/31/2009 | 549730 | 12.02
4908 | Ohio | LAWRENCE |  | 6 | E070064 | This project will replace a deficient structure situated over Dick Creek, at the 5.78-mile marker on state Route 217, just west of the route?s junction with state Route 378. This project is necessary | Bridge Replacement | 07/23/2009 | 08/17/2009 | 12/04/2009 | 349960 | 0
4909 | Ohio | SCIOTO |  | 2 | E070067 | This project will replace a deficient structure situated over Gas Hollow and located at the 1.28-mile marker on U.S. Route 52 (just east of Township Road 97 and the Adams-Scioto County line) and inclu | Bridge Replacement | 06/15/2009 | 07/13/2009 | 12/31/2009 | 759470 | 0
4910 | Ohio | GEAUGA |  | 14 | E070129 | Resurfacing of State Route 700 from U.S. 422 to State Route 168 in Troy and Burton Townships. | Pavement Improvement | 08/06/2009 |  | 08/31/2010 | 987570 | 5.04
4911 | Ohio | MUSKINGUM |  | 18 | E070130 | This project includes the resurfacing of approximately 7 miles of State Route 60 from the Morgan County line to the south corporation limit of Duncan Falls in Muskingum County. | Pavement Improvement | 08/24/2009 | 09/08/2009 | 10/19/2009 | 1485391.2 | 8.15
4912 | Ohio | CLERMONT |  | 2 | E070273 | Resurface portions of SR 232 in Clermont County to include just over 10 miles of roadway. | Pavement Improvement | 08/06/2009 | 10/06/2009 | 07/30/2010 | 567090 | 10.19
4913 | Ohio | BELMONT |  | 6, 18 | E070284 | Resurface over 14 miles of SR 148 from SR 145 to SR 7 at Powhatan Point in Belmont County; resurface over four miles of SR 164 in Carroll County from SR 9 at Kilgore to SR 43 at Amsterdam; and resurfa | Pavement Improvement | 08/06/2009 |  | 07/31/2010 | 2850600 | 19.02
4914 | Ohio | BELMONT |  | 6 | E070294 | Replace SR 148 bridge deck just west of the junction with SR 7 near Steinersville. | Bridge Improvement | 07/23/2009 |  | 07/15/2010 | 210583.55 | 0.01
4915 | Ohio | BELMONT |  | 6, 18 | E070304 | Resurface just over five miles of SR 149 from the village of Flushing in Belmont County to the village of New Athens in Harrison County, as well as resurfacing just under a mile of SR 9 in New Athens. | Pavement Improvement | 06/15/2009 | 08/13/2009 | 04/15/2010 | 841960 | 6.15
4916 | Ohio | ASHLAND |  | 16 | E070379 | This project will rehabilitate a deficient 160-foot bridge over Claremont Avenue, 0.25-mile south of Baney Road. | Bridge Improvement | 07/17/2009 | 07/28/2009 | 09/15/2010 | 1216227.98 | 0.02
4917 | Ohio | CLERMONT |  | 2 | E070407 | This project is to replace the bridge that carries SR 276 over Kain Run in Clermont county. | Pavement Improvement | 06/15/2009 | 08/03/2009 | 10/30/2009 | 354570 | 0
4918 | Ohio | CLINTON |  | 3 | E070412 | In Clinton county replace Culvert on SR 124 and SR 350 | Pavement Improvement | 08/06/2009 | 08/28/2009 | 09/01/2010 | 226720 | 0.1
4919 | Ohio | BUTLER |  | 8 | E070422 | This project will resurface portions of US 27 for approximately 15 miles. | Pavement Improvement | 08/10/2009 | 09/11/2009 | 06/30/2010 | 2281937.33 | 14.94
4920 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 6 | E070634 | Rehab existing single span steel beam bridge, originally built in 1952. Reconstruction of bridge/approach railing with decorative stone face wall. Installation of bridge lighting. Drainage improvement | Transportation Enhancements | 09/17/2009 | 09/15/2009 | 12/31/2010 | 400000 | 0.46
4921 | Ohio | GEAUGA | CLEVELAND, OH | 14 | E070642 | Resurface Washington Street from the County line to Chillicothe Rd. (SR-306) in the Village of South Russell and Bainbridge Twp | Pavement Improvement | 08/10/2009 | 08/10/2009 | 12/01/2009 | 369249.37 | 2.18
4922 | Ohio | GEAUGA | CLEVELAND, OH | 14 | E070646 | This project is to resurface Wilson Mills Road from County Line Rd. to Chillicothe Road (SR-306) in Chester Twp in Geauga county | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/01/2009 | 521950.52 | 2.75
4923 | Ohio | CHAMPAIGN |  | 4 | E070751 | This project is to resurface the existing roadway with asphalt concrete on SR-55 in Champaign county from the junction of SR-560 to the Urbana west county line. | Pavement Improvement | 06/15/2009 | 08/31/2009 | 09/30/2009 | 445310 | 3.43
4924 | Ohio | MEDINA | CLEVELAND, OH | 16 | E070780 | In Medina county on Marks Road (CR 22) - from Fenn Road (CR 70) to Hamilton Road (CR 76) resurface existing pavement and add paved shoulders to provide a new pavement surface and preserve the pavemen | Pavement Improvement | 08/07/2009 | 09/21/2009 | 10/16/2009 | 606369.06 | 1.84
4925 | Ohio | DARKE |  | 8 | E070781 | The project will resurface 4.5 miles of SR 571 near the Darke/Miami County Line, specifically between the City Greenville and the Village of West Milton. This route is heavily traveled by truck traffi | Pavement Improvement | 06/16/2009 | 08/17/2009 | 09/30/2009 | 510000 | 4.15
4926 | Ohio | MEDINA | CLEVELAND, OH | 16 | E070785 | This project is to resurface CR 19 (Lake Road) - from CR 50 (Chippewa Road) to SR 162 (Wedgewood Road) which will include adding paved shoulders to provide a new pavement surface and preserve the pave | Pavement Improvement | 08/07/2009 | 09/21/2009 | 10/16/2009 | 366647.49 | 1.54
4927 | Ohio | LOGAN |  | 4 | E070856 | The project will replace the bridge on SR 274 over the Great Miami River, which is two miles west of SR 235. The original structure was built in 1954 and is being replaced because of its age as well a | Bridge Replacement | 06/15/2009 | 07/20/2009 | 10/30/2009 | 856200 | 0
4928 | Ohio | DARKE |  | 8 | E070933 | This project is to resurface SR503 from the Preble/Darke county line to SR121 | Pavement Improvement | 07/23/2009 | 09/15/2009 | 10/31/2009 | 1055290 | 9.29
4929 | Ohio | GUERNSEY |  | 6, 18 | E070951 | Interstate 77 is a major North-South economic corridor for eastern Ohio. This project will upgrade and rehabilitate approximately 2.5 miles of I-77 through Guernsey County. | Pavement Improvement | 06/26/2009 | 07/01/2009 | 10/15/2009 | 1604000 | 2.51
4930 | Ohio | PERRY |  | 7 | E070959 | This project calls for the replacement of a deficient bridge deck located over Penn Central railroad on SR 93. This project is necessary for the safety of the traveling public, as well as to preserve | Bridge Improvement | 06/15/2009 | 07/06/2009 | 06/30/2010 | 1188410 | 0.019
4931 | Ohio | MAHONING |  | 17 | E071098 | Resurfacing SR 7 from Midlothian Blvd. to Indianola Ave; nearly one-half mile of U.S. 62 from Williamson Ave. to Hadnett Drive, and three-quarter miles of SR 625 from Midlothian Blvd. to U.S. 62. | Pavement Improvement | 08/04/2009 | 09/08/2009 | 10/15/2009 | 879598.91 | 1.979
4932 | Ohio | STARK | CANTON | 16 | E071109 | This is a safety project to reconstruct and rehabilitate sections of SR153 in Louisville including new curbs, gutters, sidewaly pavement widening west of California and Signals at California | Other | 06/16/2009 | 06/16/2009 | 09/30/2012 | 330000 | 1.09
4933 | Ohio | SUMMIT |  | 14 | E071111 | The project is for the slope repair and reconstruction on I-271 at two locations between the Ohio Turnpike and Brandywine Road. | Pavement Improvement | 06/24/2009 | 08/05/2009 | 12/01/2009 | 788799.18 | 0.02
4934 | Ohio | MAHONING |  | 6 | E080099 | Bridge deck replacement and painting of the SR 11 twin bridges over Indian Run between U.S. 224 and Western Reserve Road. | Bridge Improvement | 08/04/2009 | 08/24/2009 | 10/15/2010 | 1897104.09 | 0
4935 | Ohio | MEDINA |  | 16 | E080129 | The project will replace a deficient 68-foot, three-span bridge on State Route 301, over Rudd Creek, north of the Village of Spencer. | Bridge Replacement | 06/09/2009 |  | 10/29/2010 | 391432.6 | 0.039
4936 | Ohio | LORAIN |  | 13 | E080130 | This project involves the replacement of a deficient 38-foot bridge structure over the Carpenter Ditch, 0.17 mile north of Jason Road. | Bridge Replacement | 06/11/2009 | 06/18/2009 | 10/29/2010 | 427996.38 | 0.01
4937 | Ohio | LORAIN | CLEVELAND, OH | 9 | E080278 | In Loraine county, resurface CR 57 (Russia Road) from SR 58 to CR 231 (Oberlin Elyria Road) | Pavement Improvement | 11/12/2009 | 01/07/2010 | 10/29/2010 | 1584000 | 4.91
4938 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E080541 | Realignment of four sets of railroad tracks to the south of the present location along US 50 in Cincinnati, Ohio. Track realignment is necessary to permit maintenance of traffic for the future roadwa | Pavement Improvement | 12/01/2009 | 01/05/2010 | 06/30/2011 | 1075000 | 0.1
4939 | Ohio | SHELBY |  | 4 | E080582 | This project is to replace a heavily deteriorated 9'x5' concrete culvert. The project is located 0.87 miles east of the Darke/Shelby county line. This section of SR 47 runs between the Village of Vers | Pavement Improvement | 06/05/2009 | 07/21/2009 | 08/31/2009 | 146678 | 0.01
4940 | Ohio | COLUMBIANA |  | 6 | E080586 | Resurface nearly five miles of SR 45, from McCracken Rd. south of Salem to U.S. 62 in Salem, and resurface just over 12 miles of SR 558 from SR 45 at Teegarden to SR 517 at East Fairfield, and from SR | Pavement Improvement | 08/06/2009 |  | 07/31/2010 | 1097130 | 17.11
4941 | Ohio | CARROLL |  | 18 | E080587 | This project includes the resurfacing of approximately five miles of SR 39 in Carroll County and almost eight miles of SR 39 and SR 44 in Columbiana County. | Pavement Improvement | 07/01/2009 | 07/20/2009 | 04/15/2010 | 1486660 | 13.07
4942 | Ohio | CARROLL |  | 18 | E080588 | Almost three miles of SR 183 will be resurfaced, including just over a mile in Carroll County, from the Tuscarawas County line to the Stark County line at Magnolia, and about a mile and a half in Tusc | Pavement Improvement | 07/23/2009 | 09/12/2009 | 06/30/2010 | 393060 | 2.85
4943 | Ohio | COLUMBIANA |  | 6 | E080657 | Replace existing box beam bridge on SR 154, located approximately one mile east of SR 7 at Rogers, with a steel beam superstructure. | Bridge Improvement | 07/23/2009 |  | 07/15/2010 | 559650 | 0.5
4944 | Ohio | WAYNE |  | 16 | E080696 | This project will rehabilitate a 282' bridge on State Route 539 over Interstate 71 in northwestern Wayne County. The project is between Ruff Road and Palmer Road. The SR-539/I-71 interchange is south | Bridge Replacement | 09/09/2009 |  | 10/15/2010 | 1325730.17 | 0.009
4945 | Ohio | ERIE |  | 9 | E080699 | This project will replace twin 10-foot arch bridges on SR-61 over Old Woman?s Creek, 0.15-mile east of the south juncture with State Route 113. | Pavement Improvement | 06/12/2009 | 07/24/2009 | 10/15/2009 | 321491 | 0.02
4946 | Ohio | HARRISON |  | 18 | E080712 | Fifteen miles of asphalt resurfacing and base repairs on SR 9 as well as six miles of asphalt resurfacing and chip sealing on SR 799 in Harrison County. | Pavement Improvement | 07/17/2009 | 07/20/2009 | 11/30/2009 | 2706796 | 21.07
4947 | Ohio | GREENE |  | 3, 7 | E080736 | This project is to resurface U.S. 35 from the Montgomery/Greene county line to the US 35/I-675 interchange | Bridge Improvement | 07/23/2009 | 09/29/2009 | 07/31/2010 | 6000790 | 1.09
4948 | Ohio | DARKE |  | 8 | E080747 | The project will reconstruct and lower USR 36 just west of Arcanum-Bears Mill Road to improve visibility and intersection safety. Due to the high accident rate at this intersection, the road grade wil | Safety/Traffic Management | 06/12/2009 | 07/07/2009 | 07/21/2009 | 107902 | 0.089
4949 | Ohio | CUYAHOGA |  | 14 | E080755 | The project is a minor rehabilitation of Interstate 271, from Wilson Mills Road to Interstate 90 in Cuyahoga County and Lake County. The work includes replacement of overhead signs. | Pavement Improvement | 07/06/2009 | 08/03/2009 | 10/15/2010 | 9355450 | 4.31
4950 | Ohio | LUCAS |  | 9 | E080757 | This safety related resurfacing project on SR 2 will provide motorists with safer access to Interstate 475 from the Spring Meadows shopping corridor. The safety project includes updated pavement marki | Safety/Traffic Management | 07/23/2009 | 09/09/2009 | 12/15/2009 | 143120 | 0.43
4951 | Ohio | ASHTABULA |  | 14 | E080763 | Resurfacing 7.88 miles of U.S. 20 from SR 11 to the Norfolk and Southern Railroad. | Pavement Improvement | 06/26/2009 | 07/14/2009 | 10/31/2009 | 2680540 | 7.88
4952 | Ohio | MEIGS |  | 6 | E080790 | The project focuses on pavement surfacing of a 7-mile portion of SR 7 through Meigs County. The two-lane micro-surfacing will improve pavement deficiencies and pavement conditions, thereby enhancing t | Pavement Improvement | 06/25/2009 | 07/02/2009 | 08/31/2009 | 1397239.43 | 7.29
4953 | Ohio | WASHINGTON |  | 6 | E080793 | Six miles of SR 60 in Washington County is being resurfaced. The work includes resurfacing on both lanes of the project. | Pavement Improvement | 08/06/2009 | 09/03/2009 | 10/31/2009 | 1202410 | 6.09
4954 | Ohio | WYANDOT |  | 5 | E080796 | Grind and pave deteriorated pavement on US23 from County Road 62 to the CSX railroad in Wyandot county | Pavement Improvement | 06/25/2009 | 07/06/2009 | 10/10/2009 | 500000 | 3.48
4955 | Ohio | MONROE |  | 6 | E080827 | An eight-mile stretch of SR 379 in Monroe County will be resurfaced. The project includes resurfacing work on both lanes of the roadway. | Pavement Improvement | 07/23/2009 | 10/07/2009 | 06/30/2010 | 232940 | 8.07
4956 | Ohio | STARK | CANTON | 16 | E080895 | Resurfacing I-77 from the US 30 interchange to the SR 800/Cleveland Avenue interchange. Resurfacing of various ramps at both the US 30 and the SR 800/Cleveland Ave. interchanges. The project also incl | Pavement Improvement | 06/15/2009 | 07/17/2009 | 07/01/2010 | 2939729 | 1.05
4957 | Ohio | CHAMPAIGN |  | 4 | E081032 | In Champaign county, replace 23 foot bridge over Jumping Run with minimal approach work. | Bridge Replacement | 09/02/2009 | 09/28/2009 | 10/31/2009 | 314212 | 0
4958 | Ohio | HAMILTON |  | 1 | E081077 | Improve the pavement condition of Interstate 75 from south of SR 126 to south of the Lockland corporation. Project includes several minor bridge rehabilitations. | Pavement Improvement | 08/04/2009 | 08/11/2009 | 08/01/2010 | 6100000 | 2.49
4959 | Ohio | BELMONT |  | 6, 18 | E081127 | Chip seal will be used as a preventive maintenance treatment to extend the pavement life on almost seven miles of SR 379 in Belmont County, between the Monroe and Noble county lines. Additionally, it | Pavement Improvement | 08/06/2009 |  | 08/30/2010 | 123100 | 9.4
4960 | Ohio | CARROLL |  | 6, 18 | E081129 | Chip seal will be used as a preventive maintenance treatment to extend the pavement life on about 18 miles of two-lane roadways in Carroll and Columbiana counties. Six miles of SR 9 in Carroll County | Pavement Improvement | 06/15/2009 | 08/10/2009 | 04/15/2010 | 674860 | 17.6
4961 | Ohio | CLINTON |  | 3, 7 | E090047 | Resurface State Route 380 from Greene County to Highland County | Pavement Improvement | 08/06/2009 |  | 07/01/2010 | 1895250 | 9.71
4962 | Ohio | STARK |  | 16, 18 | E090118 | Resurfacing of SR 800 from the Tuscarawas County line to south of Faircrest Street in Canton and Pike Townships and in the Village of East Sparta. | Pavement Improvement | 07/01/2009 | 07/24/2009 | 12/01/2009 | 1256052.25 | 7.03
4963 | Ohio | CLINTON |  | 3 | E090187 | Resurface State Route 72 from Highland County to Greene County to improve pavement condition. | Pavement Improvement | 06/15/2009 | 07/08/2009 | 10/30/2009 | 3139010 | 14
4964 | Ohio | MONROE |  | 6 | E090192 | The project is a seven-mile, two-lane resurfacing project of SR 7 in Monroe County, including four miles of SR 7 in Washington County. | Pavement Improvement | 08/20/2009 | 09/30/2009 | 07/15/2010 | 2439830 | 12.46
4965 | Ohio | MORGAN |  | 18 | E090196 | Ten miles of SR 376 in Morgan County are being resurfaced. The project includes resurfacing work on both lanes of the highway. | Pavement Improvement | 07/23/2009 | 08/12/2009 | 06/30/2010 | 1437520 | 9.73
4966 | Ohio | ALLEN |  | 4 | E090292 | Repair and replace sections of deteriorated safety median wall barrier on both Interstate 75 in Allen County and U.S. Route 68 in Hancock County. Excessive deterioration of the existing concrete walls | Safety/Traffic Management | 06/15/2009 | 07/27/2009 | 10/01/2009 | 887222.71 | 4.65
4967 | Ohio | GEAUGA | CLEVELAND, OH | 14 | E090309 | This project is resurface Wilson Mills Road from Chillicothe Road (SR-306) to Heath Rd. in Chester Township | Pavement Improvement | 08/19/2009 | 08/17/2009 | 12/01/2009 | 406344.89 | 2.2
4968 | Ohio | STARK |  | 16 | E090325 | This project is to resurface U.S. Route 62 from Sugar Creek to Navarre. | Pavement Improvement | 06/16/2009 | 07/28/2009 | 12/01/2009 | 1946899.26 | 5.26
4969 | Ohio | MAHONING |  | 17 | E090373 | Resurfacing four miles of I-680 from SR 11 to Steel Street. Project also includes minor bridge work. | Pavement Improvement | 07/27/2009 | 08/13/2009 | 06/30/2010 | 4506180 | 4.06
4970 | Ohio | GREENE |  | 7 | E090375 | This project will resurface I-675 from SR 235 to the Clark County line and resurface SR 444 at I-675 interchange | Bridge Improvement | 08/20/2009 | 09/21/2009 | 06/01/2010 | 5003060 | 3.24
4971 | Ohio | VAN WERT |  | 5 | E090387 | Repave route SR49 in Van Wert and Paulding County from US30 to the south corporation limit of Payne due to pavement deterioration | Pavement Improvement | 06/12/2009 | 09/08/2009 | 11/04/2009 | 675236.63 | 8.26
4972 | Ohio | MEDINA |  | 16 | E090427 | This project will replace a deficient 12-foot structure over small creek in Medina County on SR 421, .25 miles west of SR 85. | Pavement Improvement | 05/28/2009 |  | 10/15/2010 | 661967.49 | 0.04
4973 | Ohio | SUMMIT |  | 13 | E090439 | This project is to rehabilitate the State Street bridge in downtown Akron. | Other | 09/17/2009 |  | 07/31/2014 | 500000 | 0.01
4974 | Ohio | ADAMS |  | 2 | E090442 | This is a four-lane preventive maintenance (preservation) project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Adams County. The proj | Pavement Improvement | 08/06/2009 |  | 08/31/2010 | 3804860 | 13.7
4975 | Ohio | GREENE | DAYTON | 7 | E090485 | Resurface South Maple Avenue from Doris Drive to Dayton Yellow Springs Road-Asphalt. | Pavement Improvement | 09/10/2009 | 09/25/2009 | 10/31/2009 | 272935.36 | 1.2
4976 | Ohio | WARREN |  | 3 | E090503 | Resurface Clearcreek-Franklin Road from approximately 160 feet south of Whispering Pines to Pennyroyal Road. | Pavement Improvement | 01/07/2010 |  | 08/01/2010 | 185900 | 0.76
4977 | Ohio | GREENE |  | 7 | E090504 | Resurface Dayton-Yellow Springs Road from Kauffman Avenue to Ironwood Drive to improve pavement condition | Pavement Improvement | 10/23/2009 | 10/07/2009 | 05/28/2010 | 227824 | 0.64
4978 | Ohio | MORGAN |  | 18 | E090508 | The majority of bridges in Morgan County accommodate mostly truck, car and school bus traffic. All but one bridge in Morgan County spans a river or waterway. Some of the bridges are as old as 1914 and | Bridge Improvement | 07/01/2009 | 07/27/2009 | 09/21/2009 | 94620 | 0
4979 | Ohio | MORGAN |  | 18 | E090509 | Safety studies have indicated that guardrail is needed along 11,000 feet of roadway that parallels the Muskingum River. Slopes in these areas are very steep and guardrail would protect vehicles from g | Safety/Traffic Management | 09/03/2009 | 10/19/2009 | 11/15/2009 | 128620 | 16.29
4980 | Ohio | WASHINGTON |  | 6 | E090511 | Resurfacing over seven miles of Marietta city streets, reconstructing 100 ADA curb ramps along city streets, and limited drainage improvements. Includes various sections on Acme, Colegate, Front, Gilm | Pavement Improvement | 08/06/2009 | 09/03/2009 | 06/30/2010 | 1172170 | 9
4981 | Ohio | GALLIA |  | 6 | E090512 | The project will focus on the resurfacing of 5.25 miles of Gallia County roads, thereby reducing maintenance needs and providing structural strength for all local travelers. The roads are as follows: | Pavement Improvement | 07/06/2009 | 09/03/2009 | 06/30/2010 | 372960 | 5.01
4982 | Ohio | VINTON |  | 18 | E090513 | This project will focus on resurfacing over ten miles of Vinton County roads, reducing maintenance needs and providing structural strength for all local travelers. | Pavement Improvement | 06/15/2009 |  | 06/30/2010 | 426720 | 4.44
4983 | Ohio | ALLEN |  | 4 | E090516 | This railroad grade separation underpass project in the city of Lima?s south side is located on Vine St. between Main St. and Central Ave. The project is being constructed in conjunction with IGCC (Li | New Bridge Construction | 05/18/2009 |  | 03/03/2012 | 13424852 | 0
4984 | Ohio | MONTGOMERY |  | 3, 8 | E090517 | The KROC Center is a $66 million community center under construction in the Keowee/Webster Street area of Dayton. The $66 million is also being invested to renovate a very large historic home once cov | Pavement Improvement | 10/06/2009 | 09/08/2009 | 11/30/2009 | 368202.78 | 0.83
4985 | Ohio | MONTGOMERY |  | 3 | E090518 | As the largest city in Montgomery County, Dayton has more than 150,000 residents. This project will improve the safety of five major thoroughfares that are deteriorating and will continue to unless im | Pavement Improvement | 08/19/2009 | 08/31/2009 | 12/15/2009 | 1238793.9 | 5.61
4986 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 6 | E090526 | Resurfacing from Presidential Drive to Mathews Rd in Mahoning County | Pavement Improvement | 11/12/2009 |  | 09/30/2010 | 986008.52 | 1.45
4987 | Ohio | LICKING |  | 18 | E090530 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. Bayer and the City of Newark requested Federal Stimulus funds for the replacement of a crossing surface on a | Safety/Traffic Management | 09/01/2009 | 09/25/2009 | 07/31/2010 | 100000 | 0.099
4988 | Ohio | MORROW |  | 4 | E090531 | The project will replace the traffic signal at US Route 42 and State Route 529 in Cardington in Morrow County. The traffic signal is old and outdated. | Safety/Traffic Management | 01/04/2010 |  | 06/04/2010 | 85000 | 0.02
4989 | Ohio | MARION |  | 4 | E090532 | Marion County is in a unique position in that its industrial base is on the west side of the county, yet the major route for moving commerce is located on the east side of Marion. The Northwest Indust | New Construction | 01/04/2010 |  | 12/31/2010 | 5100000 | 0
4990 | Ohio | BELMONT |  | 6 | E090541 | Install a traffic control device at the intersection of State Route 7 and State Route 148 in the village of Powhatan Point. There are currently stop signs at this intersection because the traffic sign | Safety/Traffic Management | 06/11/2009 |  | 10/01/2010 | 122000 | 0.02
4991 | Ohio | CARROLL |  | 18 | E090542 | The project will install new energy efficient traffic signals with integrated traffic demand devices in an effort to reduce traffic idling and fuel waste. With the installation of five new traffic sig | Safety/Traffic Management | 06/05/2009 |  | 10/01/2010 | 796767 | 0.1
4992 | Ohio | HOLMES |  | 18 | E090543 | Repair and resurface over a mile of State Route 39 from Grant St. to Port Washington Rd. in the village of Millersburg as well as two miles of State Route 83 from Jackson St. to the western village co | Pavement Improvement | 01/07/2010 |  | 07/31/2010 | 241040 | 13.07
4993 | Ohio | JEFFERSON |  | 6 | E090544 | SR 43 (Washington St) was built with concrete pavement in 1973 and is currently in very poor condition. The roadway is a four-lane, east-west arterial through the city, carrying approximately 15-18,00 | Pavement Improvement | 08/27/2009 | 08/27/2009 | 09/30/2011 | 7485000 | 1.09
4994 | Ohio | ROSS |  | 18 | E090548 | The project will rehabilitate and correct deficiencies of the U.S Rail in the city of Jackson. This rail service is crucial for business in rural, Appalachian Ohio serving two of the poorest counties, | Safety/Traffic Management | 12/02/2009 |  | 12/31/2010 | 2000000 | 0
4995 | Ohio | HENRY |  | 5 | E090553 | The replacement and widening of the existing bridge along Oakwood Avenue in Napoleon will restore legal load limits to the structure, allowing for larger vehicles and trucks to use this potential haul | Bridge Replacement | 08/19/2009 | 08/31/2009 | 12/31/2009 | 400000 | 0.01
4996 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090560 | This is a project to upgarde signalization at 13 intersections in Lucas County and to perform necessary related work. | Safety/Traffic Management | 09/14/2009 |  | 06/25/2010 | 420000 | 0.01
4997 | Ohio | HURON |  | 5 | E090563 | This project will replace the Gibbs Road Bridge in Norwalk Township, east of the City of Norwalk. There is minimal road work involved; however the existing bridge is in poor condition. The ODOT bridge | Bridge Replacement | 12/17/2009 |  | 10/29/2010 | 208590.24 | 0.05
4998 | Ohio | HURON |  | 5 | E090564 | The project will replace the deteriorated Ogan Rd Bridge, west of the Village of Wakeman. The existing 1-span steel beam bridge has a clear span of 28' and a width of 20'; has a bridge rating of 3P7 a | Bridge Replacement | 07/09/2009 | 07/20/2009 | 10/30/2009 | 220000 | 0.13
4999 | Ohio | LORAIN |  | 13 | E090567 | The project involves the continued re-development of Lorain?s waterfront on a portion of a U.S. Army Corps of Engineers 58-acre dredge disposal site. The project is part of a plan to diversify Lorain? | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 10/29/2010 | 3539665.17 | 0
5000 | Ohio | MUSKINGUM |  | 18 | E090570 | This project involves overhauling and rehabilitating the overpasses carrying Zane Grey Road (County Road 199) and Moose Eye Road (County Road 436) over Interstate 70. To ensure continued safety for tr | Bridge Improvement | 08/06/2009 | 08/31/2009 | 07/31/2010 | 1655920 | 0.079
5001 | Ohio | MONTGOMERY | DAYTON | 3 | E090574 | Union Boulevard from I-70 to National Road-Smooth sealing of the roadway. | Pavement Improvement | 08/12/2009 | 09/17/2009 | 09/19/2009 | 200000 | 1.5
5002 | Ohio | MIAMI | DAYTON | 8 | E090575 | This project is to pave Evanston Road from CR 25A easterly to the CSX RR tracks in Tipp City. | Pavement Improvement | 08/29/2009 | 08/29/2009 | 09/08/2009 | 217510 | 1.59
5003 | Ohio | MIAMI | DAYTON | 8 | E090576 | Plane and resurface West Stanfield Road from South Stanfield Road to 300' west of Industry Court. | Pavement Improvement | 10/07/2009 | 10/16/2009 | 11/30/2009 | 111711 | 0.25
5004 | Ohio | MIAMI | DAYTON | 8 | E090577 | Plane and resurface South Stanfield Road from State Route 41 to West Stanfield Road. | Pavement Improvement | 10/07/2009 | 10/16/2009 | 11/30/2009 | 151311 | 0.38
5005 | Ohio | MONTGOMERY | DAYTON | 3 | E090578 | Wilmington Pike from Smithville Road to the Kettering North Corp Line -Mill the existing roadway, repair concrete pavement base, resurface and install new pavement markings, including raised pavement | Pavement Improvement | 11/10/2009 | 11/03/2009 | 09/10/2010 | 504277.85 | 1
5006 | Ohio | MONTGOMERY | DAYTON | 8 | E090579 | Various locations in Huber Heights-Rehab pavement at the following locations: Taylorsville Road from State Route 202 to Gentry Lane and from Wildcat Road to Timbercrest Drive; Powell Road from the wes | Pavement Improvement | 11/23/2009 |  | 06/15/2010 | 491788 | 0.529
5007 | Ohio | MONTGOMERY | DAYTON | 3 | E090583 | Wolf Creek Street from McMaken Lane to Market Street-Mill and overlay roadway, including restriping and improving curb ramps. | Pavement Improvement | 10/01/2009 |  | 06/15/2010 | 200000 | 1.43
5008 | Ohio | MONTGOMERY | DAYTON | 3, 8 | E090584 | Spinning Road from Airway Road to Linden Avenue-Slurry seal of the existing pavement with some full depth base repairs, utility manhole and valve adjustments and thermoplastic striping. | Pavement Improvement | 01/08/2010 |  | 06/15/2010 | 319000 | 2.03
5009 | Ohio | MONTGOMERY | DAYTON | 3 | E090585 | Paragon Road from Congress Park to Normandy Road and Paragon Road from Alex-Bell Road to Grants Trail-Street resurfacing. | Pavement Improvement | 10/27/2009 |  | 07/01/2010 | 205282 | 0.72
5010 | Ohio | MONTGOMERY | DAYTON | 3 | E090592 | Bigger Road from State Route 725 to the Centerville North Corp Line-Mill and resurface the existing roadway, maintenance to the curb, sidewalk and shared use path. Upgrade ramps to meet ADA compliance | Pavement Improvement | 10/22/2009 | 10/12/2009 | 06/30/2010 | 608526 | 1.04
5011 | Ohio | MIAMI | DAYTON | 8 | E090594 | Plane and resurface North Elm Street from State Route 41 to the Troy City Limits. | Pavement Improvement | 10/07/2009 | 10/05/2009 | 11/30/2009 | 195729.5 | 0.38
5012 | Ohio | MONTGOMERY | DAYTON | 3 | E090595 | Various locations in Oakwood-Replace current curb ramps with ADA compliant ramps and associated work. | Safety/Traffic Management | 01/07/2010 |  | 05/31/2010 | 184209 | 2.84
5013 | Ohio | FRANKLIN | COLUMBUS | 7, 12, 15 | E090605 | In Franklin County, resurfacing and pavement reconstruction of various roadways. Locations include Alkire Road from MAD County to Big Darby Creek; Brice Road from Chatterton Road to Refugee Road; Cas | Pavement Improvement | 10/06/2009 | 09/11/2009 | 12/01/2009 | 2226274.06 | 12.87
5014 | Ohio | FRANKLIN | COLUMBUS | 15 | E090609 | Approximately 9000' of new sidewalks on school bus routes. Glenn Avenue: Tremont to Northwest; Waltham Road: Hampshire Road to Cambridge Blvd; Tremont Road: Pemberton Drive to Private Road; Mountview | Transportation Enhancements | 01/04/2010 |  | 07/01/2010 | 466000 | 0
5015 | Ohio | DELAWARE | COLUMBUS | 12 | E090613 | Replace deck and superstructure members.Modify or replace bridge abutments.Possible piers work, minor roadway approach work, guardrail replacement. Vilage of Galena. South Old 3C Highway over Hoover R | Bridge Improvement | 01/21/2010 |  | 08/15/2010 | 912503.47 | 0.04
5016 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090636 | This project is to to resurface Hill Ave, in the City of Toledo, from Westwood Ave to Detroit Ave. | Pavement Improvement | 11/09/2009 |  | 11/19/2010 | 1175000 | 0.83
5017 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090637 | This project is to resurface South Ave, in the City of Toledo, from Airport Hwy (SR-2) to Detroit Ave (US-24) | Pavement Improvement | 11/17/2009 |  | 05/21/2010 | 242522 | 0.21
5018 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | E090650 | This project is on Galbraith from Deer Park West Corp line to Blue Ash Road to resurface and restore pavement, curbs, improve drainage, and replace traffic loops | Pavement Improvement | 12/10/2009 |  | 07/02/2010 | 648840 | 0.539
5019 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E090653 | This project involves Troy Ave and Morse Road. Resurfacing, curb replacement, base repairs, inlet reconstruction and storm sewer to restore roadway intergrity and ride quality and improve drainage. | Pavement Improvement | 01/07/2010 |  | 08/01/2010 | 226120 | 0.35
5020 | Ohio | ASHTABULA |  | 14 | E090658 | Reconstruction and paving of North Eagle Street in the city of Geneva. | Pavement Improvement | 07/09/2009 | 07/09/2009 | 09/30/2010 | 450000 | 0.5
5021 | Ohio | MAHONING |  | 17 | E090660 | The Norfolk Southern Line relocation entails the relocation of rail line in conjunction with the $900,000,000 steel mill expansion. The project will free up 100 acres for future growth and development | Safety/Traffic Management | 10/14/2009 | 11/01/2009 | 05/30/2010 | 3927397.32 | 0
5022 | Ohio | STARK |  | 16 | E090663 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project will involve three (3) crossings in Hartville and the surrounding area. One of the crossings wa | Safety/Traffic Management | 11/12/2009 | 11/12/2009 | 05/11/2011 | 540000 | 0.01
5023 | Ohio | STARK |  | 16 | E090664 | This project is Wheeling Lake Erie Rail Line track rehabilitation in Stark, Portage, Jefferson, Wayne, Lorain, Tuscarawas, and Cuyahoga counties | Other | 09/08/2009 | 09/15/2009 | 12/15/2010 | 1200000 | 0
5024 | Ohio | SUMMIT |  | 13 | E090665 | The city of Akron is proposing to hydro-demo and resurface approximately 24,500 squar yards of the Y-Bridge deck from Perkins to the northern limits of the bridges along with other minor associated br | Bridge Improvement | 11/25/2009 |  | 05/01/2011 | 6767748.63 | 0
5025 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E090668 | Resurfacing Olive St from Ohio Ave to northern corp. limits in the Village of McDonald | Pavement Improvement | 10/29/2009 |  | 06/30/2010 | 233580 | 0.5
5026 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 17 | E090669 | Resurfacing 12th street from Robinson Rd to Coitsville Rd in the city of Campbell. | Pavement Improvement | 11/25/2009 |  | 09/01/2010 | 399660 | 1.22
5027 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E090677 | This project involves Dining Lane to Catalina Apartments west driveway. Resurface, curb replacement, base repairs and inlet reconstruction to restore roadway integrity and ride quality and improve dr | Pavement Improvement | 01/08/2010 |  | 08/01/2010 | 308000 | 1.1
5028 | Ohio | PORTAGE | AKRON | 17 | E090680 | This project is to replace or rehabilitate the bridge over the Cuyahoga River and CSX. It will also improve the Crain Ave intersection | Bridge Replacement | 07/31/2009 | 09/18/2009 | 12/01/2012 | 3000000 | 0.09
5029 | Ohio | ROSS |  | 7, 18 | E090681 | State Route 104 is currently a two-lane highway between U.S. Route 35 and the new state Route 207 extension to U.S. Route 23, and it serves as the northwest bypass of Chillicothe. The project consists | Pavement Improvement | 07/01/2009 | 07/02/2009 | 09/30/2010 | 6500000 | 3.76
5030 | Ohio | HOCKING |  | 18 | E090683 | This is part 2 of 3 for the Nelsonville By-Pass Project. The portion of this project is for preliminary engineering and right of way activities. | New Construction | 09/29/2009 | 10/07/2009 | 03/03/2012 | 45522525.57 | 4.56
5031 | Ohio | CUYAHOGA | CLEVELAND, OH | 10 | E090686 | Construct a grade separation at Columbia Road (SR-252) and the CSX Railroad Company tracks in the City of Olmsted Falls, from north of Sprague Road to the Ohio Turnpike (IR-80). | New Bridge Construction | 07/21/2009 | 07/21/2009 | 06/30/2011 | 7693000 | 0.35
5032 | Ohio | HOCKING |  | 18 | E090688 | The US 33 Corridor is a designated National Highway System route that extends from Michigan to Virginia and includes the Nelsonville Bypass. This construction project will focus on the west end of a n | New Construction | 09/14/2009 | 09/21/2009 | 03/03/2012 | 93838443.8 | 3.04
5033 | Ohio | UNION | COLUMBUS | 15 | E090691 | This project takes place at the Intersection of SR-161, CR1(Industrial Parkway) and CR24 (Post Rd). MORPC stimulus project for $1,000,000.Realignment of 2050' of Industrial Parkway on north side of S | New Construction | 11/02/2009 |  | 11/30/2010 | 1000000 | 0.82
5034 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 6 | E090692 | Resurfacing from Main St to Beloit Village limit with ADA compliant intersections. | Pavement Improvement | 07/23/2009 | 08/27/2009 | 10/30/2009 | 185460 | 0.75
5035 | Ohio | PREBLE |  | 8 | E090709 | Replace small culvert; existing culvert is an 84? by 40? cast-in-place concrete culvert in Preble county | Pavement Improvement | 06/11/2009 | 07/31/2009 | 08/07/2009 | 135640 | 0.009
5036 | Ohio | BUTLER | CINCINNATI (KY) | 8 | E090710 | In Butler county, resurface sections of Tylersville and River Roads and replace striping. | Pavement Improvement | 09/03/2009 | 09/08/2009 | 06/30/2010 | 2289190.2 | 6
5037 | Ohio | CLERMONT | CINCINNATI (KY) | 2 | E090711 | This project is to resuface county roads in Clermont county and add curb and ADA curb ramps on Buckwheat Road | Pavement Improvement | 08/26/2009 | 08/26/2009 | 05/28/2010 | 2464300 | 32.48
5038 | Ohio | GREENE | DAYTON | 7 | E090712 | Construct second phase of Access Road from Union Road to State Route 380, south and west of US 35 and Route 68 interchange. | New Construction | 10/13/2009 | 12/14/2009 | 06/18/2010 | 1350905.49 | 0
5039 | Ohio | GREENE | DAYTON | 7 | E090713 | Overlay of pavement, striping and berm repair of Valley Road from Upper Bellbrook Road to US 35 | Pavement Improvement | 09/02/2009 | 09/11/2009 | 04/16/2010 | 185881 | 1.79
5040 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | E090715 | This project is to microsurface Cornell Road from the bridge over I-71 to the bridge over I-275. This will include new pavement marking and curb ramps. | Pavement Improvement | 09/29/2009 | 09/18/2009 | 11/15/2009 | 117469.95 | 0.68
5041 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | E090716 | Resurface a portion of the Reed Hartman Hwy. Also, perform pavement repair, curb & gutter repair, replace signal loops with video detection, replacing pavement striping, place new RPMs, and where ap | Pavement Improvement | 08/12/2009 | 08/10/2009 | 10/31/2009 | 799432.86 | 1.2
5042 | Ohio | WARREN | CINCINNATI (KY) | 2, 3 | E090717 | Resurfacing of Kings Island Drive from the theater entrance to Western Row Road. | Pavement Improvement | 11/25/2009 | 11/16/2009 | 03/17/2010 | 307880 | 1.2
5043 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E090718 | This project is for resurfacing, curb replacement, base repairs and inlet reconstruction on Harrison Ave from Section Road to Lovell Avenue to restore roadway integrity | Pavement Improvement | 11/06/2009 | 10/09/2009 | 05/01/2010 | 635000 | 1
5044 | Ohio | WARREN | DAYTON | 3 | E090721 | Various locations on State Route 73 and State Route 741 in Springboro-Replace existing traffic signal lamps with LED lamps. Install three battery backups and interconnect three traffic signals between | Safety/Traffic Management | 01/07/2010 |  | 10/01/2010 | 191000 | 0.01
5045 | Ohio | WARREN | DAYTON | 3 | E090722 | Franklin-Trenton Road from the Franklin West Corp Line to Park Ave.-Resurface roadway including restriping and making curb ramps ADA compliant. | Pavement Improvement | 12/09/2009 |  | 06/23/2010 | 218260 | 1.8
5046 | Ohio | WARREN | CINCINNATI (KY) | 2 | E090724 | In Warren county, on Columbia road and various county roads resurface, stripe, and add berm and curb ramp. | Pavement Improvement | 12/09/2009 |  | 06/30/2010 | 2081480 | 1
5047 | Ohio | FRANKLIN | COLUMBUS | 7, 12, 15 | E090747 | This project is in Columbus and includes various routes in the City of Columbus. Regional resurfacing program in City of Columbus. | Pavement Improvement | 09/09/2009 |  | 06/15/2010 | 2938282.91 | 6.2
5048 | Ohio | DELAWARE | COLUMBUS | 12 | E090748 | In Delaware County, resurfacing and pavement reconstruction of various county roads and city streets. Locations include London Road in the City of Delaware from US42 north 0.10 miles; Liberty Street | Pavement Improvement | 10/08/2009 | 09/28/2009 | 10/01/2010 | 1795005 | 14.07
5049 | Ohio | CUYAHOGA |  | 10, 11 | E090751 | Widening of the ramp from I-490 eastbound to I-77 northbound and re-facing of the outside parapets on the I-77 bridge over U.S. 422 (Orange Avenue) and East 30th Street. The work includes replacement | Bridge Improvement | 05/14/2009 | 06/02/2009 | 05/15/2010 | 2613279.82 | 0.84
5050 | Ohio | WOOD |  | 5, 9 | E090752 | This project consists of replacing the current bridge deck surface on the Disalle bridge crossing the Maumee River. Additional bridge work will be performed at Miami Street overpass and railroad bridg | Bridge Improvement | 06/15/2009 | 07/09/2009 | 10/15/2010 | 5585106.13 | 0.8
5051 | Ohio | HARRISON |  | 18 | E090753 | Three bridges on U.S. 22 (eastbound U.S. 22, westbound U.S. 22, and the westbound on-ramp to U.S. 22) over an abandoned railroad just west of SR 9 in Cadiz Township will be removed and replaced with e | Bridge Replacement | 05/26/2009 | 06/30/2009 | 04/15/2010 | 910619.13 | 0
5052 | Ohio | TUSCARAWAS |  | 18 | E090755 | Resurfacing nearly four miles of U.S. 250 from SR 800 at Dennison to the Harrison County line, and just over a mile of SR 800 from Thornwood Park in Dennison to U.S. 250. | Pavement Improvement | 06/15/2009 | 09/11/2009 | 04/15/2010 | 1093310 | 4.99
5053 | Ohio | LOGAN |  | 4 | E090756 | This project is to resurface Main Street in Bellefontaine from Lake Street (SLM 7.32) to Water Street (SLM 7.94) with asphalt concrete. | Pavement Improvement | 06/25/2009 | 09/16/2009 | 09/30/2009 | 227525 | 0.62
5054 | Ohio | CUYAHOGA |  | 10 | E090757 | The project calls for a complete ramp replacement at the Interstate 480/West 130th Street interchange in the city of Cleveland. The work will include a complete replacement of aging pavements. | Pavement Improvement | 08/06/2009 | 09/25/2009 | 06/30/2010 | 816050 | 0
5055 | Ohio | ASHLAND |  | 16 | E090767 | This project will replace the bridge over Jerome Fork on SR89 in Ashland County. | Bridge Replacement | 06/15/2009 | 08/17/2009 | 08/15/2010 | 393060 | 0.04
5056 | Ohio | SUMMIT | AKRON | 14 | E090779 | This project invloves resurfacing of Liberty Road from Cannon Road to Cuyahoga County line. | Pavement Improvement | 11/06/2009 |  | 08/31/2010 | 534600 | 2.54
5057 | Ohio | SUMMIT | AKRON | 13, 14 | E090780 | This project involves Reconstruction and Adding turn lanes on Summit CR 145 from Wyoga Lake Road to Allen Road. | Pavement Widening | 06/05/2009 | 06/05/2009 | 12/31/2010 | 2560000 | 1.17
5058 | Ohio | ASHLAND |  | 16 | E090785 | This project will replace a deficient 3-span steel beam bridge over the Muddy Fork on State Route 302, 0.19 mile west of Township Road 63, in Perry Township. This is east of the community known as Red | Bridge Replacement | 06/15/2009 | 08/31/2009 | 07/15/2010 | 439070 | 0.03
5059 | Ohio | WAYNE |  | 16 | E090786 | This project will rehabilitate a deficient bridge on SR 301 in Wayne county over Interstate 71. | Bridge Improvement | 07/06/2009 |  | 10/15/2010 | 1519660 | 0.01
5060 | Ohio | CUYAHOGA | CLEVELAND, OH | 10, 11, 13, 14 | E090788 | To provide access to work for low income individuals not able otherwise to hold a job. Some of these services are provided directly by GCRTA and some are contracted to other area transportation provi | Other | 09/23/2009 |  |  | 1863358 | 0
5061 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090789 | This project is to resurface Telegraph Rd (US-24) from Alexis Rd (SR-184) to just south of the Michigan State Line in the City of Toledo. | Pavement Improvement | 11/09/2009 |  | 05/28/2010 | 315000 | 0.53
5062 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090790 | This project is to resurface Detroit Ave (US-24) in the City of Toledo from I-75 near Monroe St to Central Ave (SR-120). | Pavement Improvement | 11/09/2009 |  | 06/04/2010 | 570000 | 0.859
5063 | Ohio | KNOX |  | 18 | E090793 | Knox and Muskingum Counties are considered smaller to medium sized counties with populations that have grown in the last decade. The average driver in these counties spends between 16 and 26 minutes i | Bridge Improvement | 08/28/2009 | 09/04/2009 | 11/09/2009 | 1100000 | 0.46
5064 | Ohio | WAYNE |  | 5 | E090800 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project involves five grade crossings on the W&LE rail line between Smithville and Orrville. All five c | Safety/Traffic Management | 09/16/2009 | 10/20/2009 | 06/17/2010 | 850000 | 0
5065 | Ohio | CLARK |  | 4, 7 | E090801 | This project expands the existing investment by the State of Ohio and the West Central Ohio Port Authority (WESTCO) by improving bridge and track conditions on the rail lines. | Other | 11/04/2009 | 11/12/2009 | 12/31/2011 | 1000000 | 0
5066 | Ohio | PORTAGE | AKRON | 14 | E090807 | In the City of Aurora (Portage Co.), widening and resurfacing of 2.15 miles of SR 43 (North Aurora Road) including new storm sewer, curb and gutter, water mains, traffic signals, signing and pavement | Pavement Improvement | 07/17/2009 | 08/31/2009 | 12/31/2010 | 1000000 | 2.01
5067 | Ohio | CUYAHOGA, SUMMIT |  | 10, 11, 13, 14 | E090808 | This is a two-part project to install a new intelligent transportation system. Part 1 (Cuyahoga, Lorain, Medina, Summit, Portage & Lake Counties) includes the putting in place of approximately 83 traf | Safety/Traffic Management | 06/17/2009 | 10/21/2009 | 09/30/2011 | 21498660 | 0
5068 | Ohio | GEAUGA | CLEVELAND, OH | 14 | E090813 | In Geauga county this project will resurface Auburn Road from Kinsman Rd. to Fairmount Rd. in Newbury Twp | Pavement Improvement | 12/01/2009 |  | 07/31/2010 | 283806.79 | 1.77
5069 | Ohio | STARK | CANTON | 16 | E090846 | In Stark County, CR-98, from SR-241(Wales Ave.) to Brunerdale Ave. Widen existing road to four lanes with curb and gutters. Increase to 5 lanes at all major intersections. Includes Storm Sewer and tra | Pavement Widening | 09/30/2009 | 09/21/2009 | 07/31/2011 | 4800000 | 2.54
5070 | Ohio | STATEWIDE |  | 4, 8 | E090854 | Railroad tie replacement and other related track work to rehabilitate RJ Corman-owned lines in Western Ohio. Overall, the RJC Western Ohio lines generated 4,274 (2005), 4,541 (2006), and 3,648 (2007) | Other | 11/18/2009 | 11/30/2009 | 06/30/2010 | 1300000 | 0
5071 | Ohio | PORTAGE |  | 17 | E090927 | This project replaces the Brady Lake Road bridge over the CSX Railroad and Breakneck Creek in Franklin Township, Portage County. | Bridge Replacement | 09/16/2009 |  | 12/31/2010 | 1124000 | 0.01
5072 | Ohio | MONTGOMERY | DAYTON | 3 | E091106 | From the southern terminus of Hempstead Station Drive, north along Hempstead Station Drive to Stroop Road then east along Stroop to the southwest corner of the Stroop/Wilmington Pike intersection-Cons | Transportation Enhancements | 11/23/2009 |  | 06/30/2010 | 179792 | 0
5073 | Ohio | CUYAHOGA | CLEVELAND, OH | 14 | E091267 | The project consists of reconstructing approximately 2.44 miles of Bainbridge Road within the City of Solon. The work includes a new flexible pavement, integral bike lanes, and a new curb. | Pavement Improvement | 01/21/2010 |  | 06/30/2012 | 14000000 | 2.46
5074 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E091291 | This project will resurface and rehab Girard-I80/SR11 to Girard south corp. limit. It will include planing the entire roadway, repairing and widening sub-standard lane widths, pavement marking applic | Pavement Improvement | 01/14/2010 |  | 12/31/2010 | 800000 | 1.32
5075 | Oklahoma | MUSKOGEE |  | 2 | STIM001 | Resurface 6.50 miles of concrete pavement on east and westbound I-40 from MP 281.67 to MP 288.22 and replace the east and westbound Dirty Creek bridges. | Pavement Improvement | 06/01/2009 | 06/01/2009 | 01/21/2011 | 26884000 | 6.55
5076 | Oklahoma | LE FLORE |  | 2 | STIM008 | Roadway construction of the remaining 2 lanes of a 4 lane facility from SH-9A extending east to SH-112 to add capacity for an existing two lane facility and replace structurally obsolete and/or defien | Bridge Replacement | 09/14/2009 | 12/01/2009 | 09/13/2010 | 5968238 | 1.8
5077 | Oklahoma | ATOKA |  | 2 | STIM009 | Roadway and Bridge construction of a new 2 lane facility offset to an existing 2 lane facility from 0.33 miles West of the Atoka and Pushmataha County Line extending East into Atoka County 1.82 miles. | Pavement Widening | 04/27/2009 | 04/27/2009 | 11/22/2009 | 3818000 | 1.82
5078 | Oklahoma | GARVIN |  | 4 | STIM010 | This project will extend the life of the pavement and significantly improves ride quality on 6.57 miles of I-35 by stabalizing the existing pavement. Project begins at SH-29 and extends to SH-19. | Pavement Improvement | 04/27/2009 | 04/27/2009 | 11/27/2010 | 24830000 | 6.57
5079 | Oklahoma | SEMINOLE |  | 5 | STIM011 | Full depth concrete pavement reconstruction for 2.47 miles on I-40 in Seminole County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 07/13/2009 | 07/07/2009 | 01/28/2010 | 2730000 | 2.47
5080 | Oklahoma | MCCLAIN |  | 4 | STIM013 | Asphalt pavement resurfacing and bridge repair on I-44 in McClain County. This project was resurfaced within existing right of ways and no lanes were added. | Pavement Improvement | 04/27/2009 | 04/27/2009 | 09/23/2009 | 6760000 | 7.5
5081 | Oklahoma | CANADIAN |  | 3 | STIM015 | This project overlays the existing concrete pavement with a concrete overlay. Also, 2 additional lanes are being added injunction with reconstructing the existing bridges The project starts at Mile Ma | Pavement Improvement | 06/01/2009 | 06/01/2009 | 08/09/2011 | 30000000 | 4
5082 | Oklahoma | KAY |  | 3 | STIM019 | This project reconstructs the pavement surfacing upgrades the bridges and installs cable barrier in the median. The project starts at Mile Marker 224.4 and extends to Mile Marker 229.3 on I-35. | Pavement Improvement | 06/01/2009 | 06/01/2009 | 03/02/2011 | 22328960 | 4.9
5083 | Oklahoma | BECKHAM |  | 3 | STIM024 | This project replaces deteriorated bridge decks and improves deteriorated pavement for eight miles of I-40 near Sayre, OK. | Pavement Improvement | 04/27/2009 | 05/01/2009 | 01/21/2010 | 13379000 | 8
5084 | Oklahoma | TEXAS |  | 3 | STIM028 | This project seals cracks and overlays the existing asphalt pavement. The project starts at Guymon and extends east 7.0 miles on US- 412 | Pavement Improvement | 04/27/2009 | 04/27/2009 | 09/23/2009 | 6297000 | 7.3
5085 | Oklahoma | CIMARRON |  | 3 | STIM031 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at 7.5 miles east of Jct. with US-287 on US-64 and extends 14.5 miles east. | Pavement Improvement | 06/09/2009 | 07/28/2009 |  | 6410000 | 8
5086 | Oklahoma | TEXAS |  | 3 | STIM033 | This project crack seals and overlays the existing asphalt pavement. The project starts at the Texas/Cimarron County Line and extends east 4.5 miles on US-64 north of Guymon. | Pavement Improvement | 04/27/2009 | 04/27/2009 | 09/03/2009 | 3567000 | 4.5
5087 | Oklahoma | ELLIS |  | 3 | STIM034 | This project installs a new bridge on US -283 over 25 mile creek 0.5 miles north of the Jct with State Highway 15 | Pavement Improvement | 04/27/2009 | 04/27/2009 | 11/22/2009 | 3472000 | 0.75
5088 | Oklahoma | COMANCHE |  | 4 | STIM037 | This project replaces the deficient bridge over Beaver Creek for the west bound lanes of State Highway 7 west of Lawton, OK. | Bridge Replacement | 04/27/2009 | 05/06/2009 | 12/02/2009 | 2241000 | 0.381
5089 | Oklahoma | CARTER |  | 4 | STIM038 | This project replaces a deficient bridge over Red Oak Creek on US 70 west of Ardmore, OK. | Bridge Replacement | 04/27/2009 | 04/27/2009 | 12/22/2009 | 1272000 | 0.25
5090 | Oklahoma | STEPHENS |  | 4 | STIM039 | This project constructs a new interchange at US 81 and Bois D'Arc Avenue in Duncan, OK to provide four lanes of Bois D'Arc Avenue at this location. | Pavement Widening | 06/01/2009 | 06/01/2009 | 02/25/2009 | 4954000 | 0.44
5091 | Oklahoma | CARTER |  | 4 | STIM040 | This project widens about 3 miles of US 70 from two lanes to four lanes east of the Jefferson County line west of Ardmore, OK. | Pavement Improvement | 04/27/2009 | 04/27/2009 | 12/22/2009 | 5344000 | 3.08
5092 | Oklahoma | TULSA | TULSA | 1 | STIM047 | This project is located on the north bound lanes of Interstate 244 beginning at the U.S. Highway 75 interchange extending north to the U.S. Highway 64 interchange (also referred to as the west leg of | Bridge Improvement | 06/08/2009 | 06/08/2009 | 01/08/2011 | 11850000 | 1.176
5093 | Oklahoma | TULSA | TULSA | 1 | STIM048 | This project is located on the south bound lanes of Interstate 244 beginning at the U.S. Highway 75 interchange extending north to the U.S. Highway 64 interchange (also referred to as the west leg of | Bridge Improvement | 06/08/2009 | 06/08/2009 | 01/08/2011 | 19716000 | 1.124
5094 | Oklahoma | TULSA | TULSA | 1 | STIM049 | This project is located on the east bound lanes of Interstate 244 beginning at the U.S. Highway 64 interchange extending east to the U.S. Highway 75 interchange (also referred to as the north leg of t | Bridge Improvement | 06/08/2009 | 06/08/2009 | 01/08/2011 | 15100000 | 1.754
5095 | Oklahoma | TULSA | TULSA | 1 | STIM050 | This project is located on the west bound lanes of Interstate 244 beginning at the U.S. Highway 64 interchange extending east to the U.S. Highway 75 interchange (also referred to as the north leg of t | Bridge Improvement | 06/08/2009 | 06/08/2009 | 01/08/2011 | 18100000 | 1.751
5096 | Oklahoma | TULSA |  | 1 | STIM061 | This project will replace the pavement approaching the State Highway 151 bridges over State Highway 51 and SL/SF railroad, replace the both deteriorated bridges and install new safety barriers. The p | Bridge Replacement | 06/01/2009 | 05/27/2009 | 03/27/2010 | 6059000 | 0.25
5097 | Oklahoma | NOWATA |  | 2 | STIM062 | This project will resurface 6.0 mile of U.S. Highway 169 beginning at the Kansas State Line by replacing 2 to 4 inches of existing asphalt with 4 inches of new asphalt which results in a smoother ride | Pavement Widening | 07/06/2009 | 07/23/2009 | 09/03/2009 | 3535000 | 6
5098 | Oklahoma | WOODS |  | 3 | STIM063 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 4.5 miles north of the Woods/Major County Line on US-281 and entends south 3.7 miles | Pavement Improvement | 07/06/2009 | 04/29/2009 | 08/24/2009 | 706900 | 3.7
5099 | Oklahoma | TEXAS |  | 3 | STIM064 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 5.3 miles southwest of the Junction with State Highway 94 on State Highway 54 and entends northeast 5. | Pavement Improvement | 07/22/2009 |  |  | 1090729 | 5
5100 | Oklahoma | TEXAS |  | 3 | STIM065 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 9.8 miles northeast of the Texas State line on US 54 miles entends 1.6 miles to the Goodwell City limi | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/03/2009 | 807900 | 1.6
5101 | Oklahoma | TEXAS |  | 3 | STIM066 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 11.4 miles northeast of the Texas State line on US 54 miles entends 7.0 miles. | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/03/2009 | 1424500 | 7
5102 | Oklahoma | WOODS |  | 3 | STIM067 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 4.6 miles east of the Jct US-281 on State Highway 45 and entends east 3.5 miles. | Pavement Improvement | 07/06/2009 | 04/29/2009 | 08/24/2009 | 598700 | 3.5
5103 | Oklahoma | CUSTER |  | 3 | STIM069 | This project resurfaces about 6 miles of US 183 north of Clinton, OK to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 06/24/2009 | 08/28/2009 |  | 1197383 | 5.96
5104 | Oklahoma | CUSTER |  | 3 | STIM070 | This project resurfaces about 5 miles of US 183 north of Clinton, OK to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 06/24/2009 | 08/28/2009 |  | 938475 | 4.66
5105 | Oklahoma | JACKSON |  | 4 | STIM071 | This project resurfaces about 8 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 06/01/2009 | 06/01/2009 | 09/08/2009 | 997900 | 7.7
5106 | Oklahoma | TILLMAN |  | 3 | STIM086 | This project resurfaces about 4 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 06/01/2009 | 06/01/2009 | 09/08/2009 | 795600 | 3.92
5107 | Oklahoma | TILLMAN |  | 3 | STIM087 | This project resurfaces about 7 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 06/01/2009 | 06/01/2009 | 09/08/2009 | 1463000 | 7.13
5108 | Oklahoma | ROGERS |  | 2 | STIM088 | This project extends the service life of the pavement by removing 2 inches of asphalt and placing 2 inches of new asphalt on U.S. Highway 412 beginning at the McClelan Kerr Navigation Channel extendin | Pavement Improvement | 07/06/2009 | 07/30/2009 | 10/03/2009 | 1378900 | 5.02
5109 | Oklahoma | OKFUSKEE |  | 2 | STIM093 | This project resurfaces about 8 miles of I-40 east of the Seminole County line to improve the smoothness of the road and to extend it's life. This project was reconstructed within existing right of w | Pavement Improvement | 06/09/2009 | 08/31/2009 |  | 3380000 | 8
5110 | Oklahoma | POTTAWATOMIE |  | 5 | STIM095 | Asphalt pavement resurfacing for 7.72 miles on I-40 in Seminole County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 07/06/2009 | 05/18/2009 | 08/19/2009 | 1296700 | 7.72
5111 | Oklahoma | SEMINOLE |  | 5 | STIM096 | Resurface I-40 from the Pottawatomie county line going east about 6.5 miles. | Pavement Improvement | 07/06/2009 | 05/18/2009 | 08/19/2009 | 1086200 | 6.46
5112 | Oklahoma | MURRAY |  | 4 | STIM120 | This project resurfaces about 7 miles of I-35 north of the Carter County line to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 04/27/2009 | 05/26/2009 | 07/20/2009 | 4927000 | 6.56
5113 | Oklahoma | CARTER |  | 4 | STIM121 | This project resurfaces about 8 miles of US 70 east of Ardmore, OK to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 06/09/2009 | 11/09/2009 |  | 2915633 | 8
5114 | Oklahoma | ATOKA |  | 2 | STIM150 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 1.44 miles to 3.80 miles North of State Highway to repair deteriorating pavement section. | Pavement Improvement | 04/20/2009 | 04/21/2009 | 10/16/2009 | 640070 | 3.8
5115 | Oklahoma | BRYAN |  | 2 | STIM152 | Asphalt pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.21 miles to 5.26 miles North of Oklahoma-Texas State Line for Southbound and Northbound Lanes to repair det | Pavement Improvement | 07/06/2009 | 07/22/2009 | 09/18/2009 | 3992600 | 5.26
5116 | Oklahoma | CANADIAN |  | 3 | STIM153 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at Mile Marker 108 and entends to Mile Marker 115 on I-40 west of Oklahoma city | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/18/2009 | 1716300 | 7
5117 | Oklahoma | CANADIAN |  | 3 | STIM154 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at Mile Marker 115 and entends to Mile Marker 118 on I-40 west of Oklahoma city | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/18/2009 | 922650 | 4.2
5118 | Oklahoma | GARVIN |  | 4 | STIM156 | Asphalt pavement resurfacing for 8.01 miles on State Highway 76 in Garvin County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 07/06/2009 | 05/29/2009 | 08/09/2009 | 1128800 | 8.01
5119 | Oklahoma | HASKELL |  | 2 | STIM157 | 13.85 miles of 9.5" thick of concrete patching and concrete surface smoothing at varies locations in Haskell county. These project were reconstructed within existing right of ways and no lanes were ad | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 242250 | 1.07
5120 | Oklahoma | MUSKOGEE |  | 2 | STIM158 | Concrete pavement reconstrcution of the driving lanes and shoulder along SH-2 beginning 14 miles north of Haskell County line and going north approximately 2 miles. | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 473800 | 1.75
5121 | Oklahoma | OKMULGEE |  | 2 | STIM159 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-75 beginning at I-40 and going north approximately 2.5 miles. | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 857500 | 2.44
5122 | Oklahoma | WAGONER |  | 1 | STIM163 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-69 beginning 0.5 miles north of SH-51 and going north approximately 8 miles. | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 1716800 | 7.84
5123 | Oklahoma | WAGONER |  | 1 | STIM164 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-69 beginning 1/4 miles south of SH-51 and going north approximately 1 mile. | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 393800 | 0.75
5124 | Oklahoma | LE FLORE |  | 2 | STIM169 | Roadway and Bridge Construction of driving lanes and shoulder on an offset alignment of along US Highway 59 from State Highway West to 5.26 miles North of Junction to increase the capacity and update | Pavement Widening | 09/08/2009 | 07/06/2009 | 11/01/2010 | 12000000 | 5
5125 | Oklahoma | HUGHES |  | 2 | STIM172 | Asphalt pavement resurfacing for 1.96 miles on U.S. Highway 270B in Hughes County. Part of this project include full depth concrete patching. This project was reconstructed within existing right of wa | Pavement Improvement | 07/06/2009 | 06/16/2009 | 08/04/2009 | 387000 | 1.96
5126 | Oklahoma | LINCOLN |  | 3 | STIM173 | This project resurfaces about 8 miles of SH-105 in Lincoln County, OK between US-177 and SH-18 to improve the smoothness of the road and to extend it's life. This project was reconstructed within exi | Pavement Improvement | 07/06/2009 | 07/02/2009 | 08/04/2009 | 985000 | 7.97
5127 | Oklahoma | LINCOLN |  | 3 | STIM174 | Asphalt pavement resurfacing for 5.05 miles on State. Highway 18 in Lincoln County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 07/06/2009 | 07/13/2009 | 08/04/2009 | 487000 | 5.05
5128 | Oklahoma | MAYES |  | 2 | STIM175 | This project will provide a smother ride and extend the service life of the pavement by rehabilitating the existing concrete pavement. Improvements include patching deteriorated sections, adding supp | Pavement Improvement | 06/01/2009 | 07/28/2009 | 09/28/2009 | 1871300 | 4.5
5129 | Oklahoma | NOBLE |  | 3 | STIM176 | Resurface both directions of I-35 starting about 1 mile north of the Payne county line and going north 6 miles. | Pavement Improvement | 07/06/2009 | 07/17/2009 | 08/19/2009 | 1255000 | 6
5130 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM177 | This project will extend the life of the pavement and significantly improves ride quality on 3.5 miles of I-235 in Oklahoma City by stabalizing the existing pavement. | Pavement Improvement | 04/27/2009 | 05/18/2009 | 07/25/2009 | 2532000 | 3.47
5131 | Oklahoma | PITTSBURG |  | 2 | STIM178 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.00 miles to 3.0 miles North of County Line for Southbound and Northbound Lanes to repair deteriorating pav | Pavement Improvement | 04/20/2009 | 04/21/2009 | 10/16/2009 | 1571640 | 3
5132 | Oklahoma | PITTSBURG |  | 2 | STIM179 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.30 miles to 4.65 miles North of Atoka County Line for Southbound Lanes and from 3.08 miles to 6.0 miles No | Pavement Improvement | 04/20/2009 | 04/21/2009 | 10/16/2009 | 2121700 | 4.65
5133 | Oklahoma | ROGERS |  | 2 | STIM180 | This project extends the service life of the pavement by removing 2 inches of asphalt and placing 3 inches of new asphalt on State Highway 266 beginning at State Highway 167 extending east approximate | Pavement Improvement | 07/06/2009 | 07/30/2009 | 10/03/2009 | 1008200 | 6
5134 | Oklahoma | SEMINOLE |  | 5 | STIM181 | Asphalt pavement resurfacing for 4.76 miles on State Highway 56 in Seminole County. Part of this project include full depth concrete patching. This project was reconstructed within existing right of w | Pavement Improvement | 07/06/2009 | 06/30/2009 | 09/03/2009 | 935000 | 4.76
5135 | Oklahoma | TILLMAN |  | 4 | STIM182 | This project resurfaces about 4 miles of US 183 south of Frederick, OK to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 07/06/2009 | 07/09/2009 | 08/04/2009 | 713900 | 4.05
5136 | Oklahoma | MAYES |  | 2 | STIM183 | This project will replace a deteriorated county bridge on EW-58 over Chouteau Creek located approximately 0.3 mile south and 2.3 miles east of Chouteau. | Bridge Replacement | 09/08/2009 | 09/29/2009 | 03/06/2010 | 980000 | 0.06
5137 | Oklahoma | MAYES |  | 2 | STIM184 | This project replaces a deteriorated bridge over Brushy Creek located approximately 2.2 miles south and 2.5 miles west of the U.S. Highway 412/69 junction. | Bridge Replacement | 09/08/2009 | 10/05/2009 | 01/05/2010 | 290000 | 0.02
5138 | Oklahoma | TULSA |  | 1 | STIM185 | This project replaces a deteriorated county bridge over Delaware Creek overflow on Cincinnati Avenue located 0.5 mile south of 86th Street North in Tulsa. | Bridge Replacement | 08/03/2009 | 08/03/2009 | 01/29/2010 | 900000 | 0.4
5139 | Oklahoma | WASHINGTON |  | 1 | STIM186 | This project will replace a low water crossing on N-401 over Unnamed Creek located 0.6 miles south and 4.2 miles east of the U.S. Highway 75/ Kansas Border junction. | Bridge Replacement | 08/03/2009 | 07/24/2009 | 03/30/2010 | 636000 | 0.02
5140 | Oklahoma | WASHINGTON |  | 1 | STIM187 | This project will replace a low water crossing with a new bridge on N-400 over Brush Creek located approximately 0.8 mile south and 2.0 miles east of the U.S. Highway / State Highway 10 junction. | New Bridge Construction | 08/03/2009 | 07/24/2009 | 03/30/2010 | 480000 | 0.2
5141 | Oklahoma | ADAIR |  | 2 | STIM188 | Construct a new bridge on Peavine Road about 4 miles north of junction US-59/SH-51. Additional right of way was acquired to construct this project. | New Bridge Construction | 09/08/2009 | 09/08/2009 | 01/25/2010 | 584000 | 0.25
5142 | Oklahoma | CHEROKEE |  | 2 | STIM189 | Replace the bridge over the Telmay Hollow creek in Cherokee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 08/03/2009 | 07/27/2009 | 10/31/2009 | 288000 | 0.23
5143 | Oklahoma | MCINTOSH |  | 2 | STIM190 | Replace the bridge over the Flat Rock creek creek in McIntosh county. Additional right of way was acquired to construct this project. | Bridge Replacement | 09/08/2009 | 08/10/2009 | 12/06/2009 | 335000 | 0.25
5144 | Oklahoma | MUSKOGEE |  | 2 | STIM191 | Replace the bridge over Cloud creek north and east of Boyton in Muskogee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 11/30/2009 | 11/30/2009 | 04/28/2010 | 438449 | 0.365
5145 | Oklahoma | OKMULGEE |  | 2 | STIM192 | Replace the bridge over the unnamed creek creek that is about 4 miles east and 2 miles north of US-75 in Okmulgee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 09/08/2009 | 07/13/2009 | 01/05/2010 | 320000 | 0.2
5146 | Oklahoma | SEQUOYAH |  | 2 | STIM193 | Construct a new bridge over the Prairie Creek just south and west of Akins in Sequoyah county. Additional right of way was acquired to construct this project. | New Bridge Construction | 12/07/2009 | 09/08/2009 | 04/05/2010 | 300000 | 0.25
5147 | Oklahoma | WAGONER |  | 1 | STIM194 | Replace the bridge 1 mile north and 4 miles west of the junction of US-69 and SH-51 in Wagoner county. Additional right of way was acquired to construct this project. | Bridge Replacement | 08/03/2009 | 07/22/2009 | 10/31/2009 | 220000 | 0.125
5148 | Oklahoma | BRYAN |  | 2 | STIM195 | County Bridge Constrcution of the driving lanes and shoulders over Island Bayou and Island Bayou Tributaries located 2.60 miles North of State Highway 78 on NS 380 Section Line Road to replace a struc | Bridge Replacement | 08/03/2009 | 08/17/2009 | 11/30/2009 | 558000 | 0.4
5149 | Oklahoma | BRYAN |  | 2 | STIM196 | County Bridge Constrcution of the driving lanes and shoulders over Red Ranch Creek located 1.00 miles North and 1.50 miles East of the Town of Smith-Lee to replace a strucutrally defecient or obsolete | Bridge Replacement | 08/03/2009 | 08/17/2009 | 11/30/2009 | 381000 | 0.3
5150 | Oklahoma | LATIMER |  | 2 | STIM197 | County Bridge Constrcution of the driving lanes and shoulders over Peachland Creek located 0.70 miles North and 2.00 miles West of the Town of Bengal to replace a strucutrally defecient or obsolete lo | Bridge Replacement | 08/03/2009 | 08/14/2009 | 11/30/2009 | 535000 | 0.2
5151 | Oklahoma | LE FLORE |  | 2 | STIM198 | County Bridge Constrcution of the driving lanes and shoulders over Fourche Maline Creek located 1.50 miles North and 2.30 miles East of the Town of LeFLore to replace a strucutrally defecient or obso | Bridge Replacement | 10/05/2009 | 06/10/2009 | 03/03/2010 | 1000000 | 0.5
5152 | Oklahoma | PITTSBURG |  | 2 | STIM199 | County Bridge Constrcution of the driving lanes and shoulders over Unnamed Creek located 2.00 miles North and 3.70 miles West of the Town of Quinton to replace a strucutrally defecient or obsolete loc | Bridge Replacement | 10/05/2009 | 06/25/2009 | 02/01/2010 | 330000 | 0.3
5153 | Oklahoma | COAL |  | 2 | STIM200 | Replace the bridge over Coal Creek thats about 2 miles east and 2 miles south of Lehigh | Bridge Replacement | 08/03/2009 | 08/03/2009 | 01/29/2010 | 295400 | 0.2
5154 | Oklahoma | COAL |  | 2 | STIM201 | Replace the bridge over the tributary to Keel Creek that is about 8 miles north and 7 miles east of Coalgate. | Bridge Replacement | 08/03/2009 | 08/03/2009 | 01/29/2010 | 162000 | 0.2
5155 | Oklahoma | HUGHES |  | 2 | STIM202 | Replace the bridge over the Big creek that is about 4 miles east of Allen in Hughes county. Additional right of way was acquired to construct this project. | Bridge Replacement | 09/08/2009 | 08/17/2009 | 01/05/2010 | 429292 | 0.3
5156 | Oklahoma | LINCOLN |  | 3 | STIM203 | Replace the bridge over the Spring creek about a mile west of US-177 junction SH-66 in Lincoln county. Additional right of way was acquired to construct this project. | Bridge Replacement | 08/03/2009 | 08/03/2009 | 11/30/2009 | 259200 | 0.3
5157 | Oklahoma | OKFUSKEE |  | 2 | STIM204 | Replace the bridge over the Harrican creek that is about 3 miles south of Micawber in Okfuskee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 08/03/2009 | 06/05/2009 | 11/30/2009 | 401400 | 0.24
5158 | Oklahoma | PONTOTOC |  | 4 | STIM205 | Replace the bridge over the Grayson Creek that is about 2 miles south and 7 miles east of SH-59a junction SH-3w. | Bridge Replacement | 09/08/2009 | 09/01/2009 | 04/05/2010 | 387159 | 0.02
5159 | Oklahoma | PONTOTOC |  | 4 | STIM206 | Replace the bridge over the Mill creek that is about 0.5 miles north and 2 miles east of Fittstown. Additional right of way was acquired to construct this project. | Bridge Replacement | 09/08/2009 | 09/01/2009 | 04/05/2010 | 275105 | 0.02
5160 | Oklahoma | POTTAWATOMIE |  | 5 | STIM207 | Replace the bridge over the Popshego creek that is about 3 miles east of St. Louis, Oklahoma. Additional right of way was acquired to construct this project. | Bridge Replacement | 09/08/2009 | 09/09/2009 | 01/05/2010 | 491743 | 0.02
5161 | Oklahoma | GARVIN |  | 4 | STIM208 | Replace the bridge over the unnamed creek that is about 3.5 miles north of SH-7. | Bridge Replacement | 08/03/2009 | 07/01/2009 | 11/30/2009 | 544000 | 0.3
5162 | Oklahoma | LOGAN |  | 3 | STIM209 | Replace the bridge on EW-81 over Blue Creek about 4 miles west of Meridian. | Bridge Replacement | 08/03/2009 | 07/01/2009 | 11/30/2009 | 400000 | 0.21
5163 | Oklahoma | MURRAY |  | 4 | STIM210 | Replace the bridge over Guy Sandy Creek that is about 8 miles north and a mile west of Sulphur in Murray County. | Bridge Replacement | 10/05/2009 | 10/05/2009 | 02/01/2010 | 600000 | 0.25
5164 | Oklahoma | PAYNE |  | 3 | STIM211 | Replace the bridge over Clear Creek that is about 2 miles east and 7 miles south of the junction of I-35 and SH-51 | Bridge Replacement | 08/03/2009 | 07/21/2009 | 10/31/2009 | 400000 | 0.25
5165 | Oklahoma | CANADIAN |  | 3 | STIM212 | This project installs a new bridge and approaches on a county bridge 3.9 miles west and 1 mile south of Piedmont | Bridge Replacement | 08/03/2009 | 06/12/2009 | 12/30/2009 | 462972 | 0.2
5166 | Oklahoma | CANADIAN |  | 3 | STIM213 | This project installs a new box culvert and approaches on a county road 2 miles north and 3.6 mile east of Geary | Bridge Replacement | 08/03/2009 | 06/12/2009 | 12/30/2009 | 166877 | 0.2
5167 | Oklahoma | COTTON |  | 4 | STIM214 | This project replaces the deficient county bridge over East Cache Creek near Walters, OK. | Bridge Replacement | 08/03/2009 | 07/20/2009 | 11/30/2009 | 239425 | 0.25
5168 | Oklahoma | JEFFERSON |  | 4 | STIM215 | This project replaces the deficient county bridge over Mud Creek near Ringling, OK. | Bridge Replacement | 08/03/2009 | 05/29/2009 | 12/30/2009 | 477024 | 0.25
5169 | Oklahoma | LOVE |  | 2 | STIM216 | This project replaces a low water crossing with a new bridge over Simon Creek northeast of the intersection of State Highways 76 and 32. | New Bridge Construction | 08/03/2009 | 08/11/2009 | 12/30/2009 | 519881 | 0.12
5170 | Oklahoma | STEPHENS |  | 4 | STIM217 | This project replaces the deficient county bridge over Deer Creek southeast of Comanche, OK. | Bridge Replacement | 10/05/2009 | 09/08/2009 | 05/02/2010 | 382956 | 0.01
5171 | Oklahoma | STEPHENS |  | 4 | STIM218 | This project replaces the deficient county bridge over Stage Stand Creek southwest of Duncan, OK. | Bridge Replacement | 10/05/2009 | 09/08/2009 | 05/02/2010 | 452164 | 0.01
5172 | Oklahoma | BECKHAM |  | 3 | STIM219 | This project replaces a deficient county bridge over Buffalo Creek located about 7.5 miles north of Erick, OK. | Bridge Replacement | 08/03/2009 | 08/03/2009 | 11/30/2009 | 707000 | 0.01
5173 | Oklahoma | CUSTER |  | 3 | STIM220 | This project replaces the deficient county bridge over Barnitz Creek northwest of Clinton, OK. | Bridge Replacement | 08/03/2009 | 08/03/2009 | 10/31/2009 | 465500 | 0.2
5174 | Oklahoma | DEWEY |  | 3 | STIM221 | This project replaces the deficient county bridge over the South Canadian River northwest of Oakwood, OK. | Bridge Replacement | 10/05/2009 | 09/16/2009 | 04/02/2010 | 1726572 | 0.379
5175 | Oklahoma | GREER |  | 3 | STIM222 | This project replaces the deficient county bridge over Unnamed Creek southwest of Willow, OK. | Bridge Replacement | 10/05/2009 | 08/12/2009 | 01/02/2010 | 360000 | 0.01
5176 | Oklahoma | TILLMAN |  | 4 | STIM223 | This project replaces the deficient county bridge over Deep Red Creek southeast of Loveland, OK. | Bridge Replacement | 08/03/2009 | 07/28/2009 | 11/30/2009 | 445109 | 0.2
5177 | Oklahoma | ALFALFA |  | 3 | STIM224 | This project resurfaces the existing asphalt pavement with and asphalt overlay on county road ( NS-271) 1.0 miles west Goltry and extends north 2.1 miles | Pavement Improvement | 08/03/2009 | 07/06/2009 | 10/01/2009 | 468364 | 2.2
5178 | Oklahoma | BEAVER |  | 3 | STIM225 | This project installs a new bridge and approaches on a county road ( NS-146) 7.0 miles east and 3.5 miles south of Elmwood | Bridge Replacement | 08/03/2009 | 07/28/2009 | 03/30/2010 | 496040 | 0.2
5179 | Oklahoma | CIMARRON |  | 3 | STIM226 | This project rehabitates the existing bridge over the Beaver River on a county road ( NS-13) 1.2 miles north of Felt | Bridge Improvement | 08/03/2009 | 08/03/2009 | 10/31/2009 | 267370 | 0.01
5180 | Oklahoma | GARFIELD |  | 3 | STIM227 | This project installs a new bridge and approaches on a county road ( NS-188) 0.6 miles north and 6.6 miles east of Waukomis | Bridge Replacement | 08/03/2009 | 07/06/2009 | 12/30/2009 | 539870 | 0.25
5181 | Oklahoma | GRANT |  | 3 | STIM228 | This project installs a new bridge and approaches on a county bridge over Sand Creek 1.0 miles north and 1.5 miles east of the junction with State Highway 11 and State Highway 132. | Bridge Replacement | 08/03/2009 | 09/01/2009 | 12/30/2009 | 516378 | 0.25
5182 | Oklahoma | GRANT |  | 3 | STIM229 | This project resurfaces the existing asphalt pavement with and asphalt overlay on a county road 5.3 miles south of Pond Creek and extends north 5.3 miles | Pavement Improvement | 08/03/2009 | 08/06/2009 | 11/30/2009 | 50000 | 5.3
5183 | Oklahoma | KINGFISHER |  | 3 | STIM230 | This project installs a new bridge and reconstruct the roadway approaches on a county bridge 4.5 miles west State Highway74F in Cashion | Bridge Replacement | 08/03/2009 | 09/08/2009 | 12/30/2009 | 571545 | 0.2
5184 | Oklahoma | NOBLE |  | 3 | STIM231 | This project installs a new bridge and approaches on county road over Red Rock Creek 4.5 miles west of the Junction with US 77 and State Highway 15 | Bridge Replacement | 08/03/2009 | 07/09/2009 | 12/30/2009 | 765687 | 0.2
5185 | Oklahoma | BEAVER |  | 3 | STIM232 | This project installs a new bridge and approaches on county road over Bull Creek 3.0 miles west and 3.4 miles north of the junction with State Highway 3 and US 83 at Byran Corner | Bridge Replacement | 08/03/2009 | 07/28/2009 | 03/30/2010 | 439600 | 0.1
5186 | Oklahoma | PITTSBURG |  | 2 | STIM233 | Embankment Stablization and Asphalt Paving reconstrcution of the driving lanes and shoulder along local road and bridge approach causeway over Lake Eufaulat o repair embankment sloughing and pavement | Pavement Widening | 02/01/2010 | 10/26/2009 | 08/29/2010 | 450000 | 0.1
5187 | Oklahoma | CANADIAN | OKLAHOMA CITY | 3 | STIM235 | This project installs a new bridge and approaches on county road over a unnamed creek 15.0 miles east and 7.0 miles south of Okarche | Bridge Replacement | 12/07/2009 | 11/18/2009 | 03/06/2010 | 225000 | 0.25
5188 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM236 | Installation of traffic signals and signal interconnection on 24th West Avenue beginning at State Highway 9 extending North to Tecumseh Road in Norman. | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 10/01/2009 | 598663 | 0.01
5189 | Oklahoma | NOBLE |  | 3 | STIM237 | This project resurfaces and widens the existing asphalt pavement with an concrete overlay The project starts at Mile Marker 198 and entends to Mile Marker 203 on I-35 north of Perry | Pavement Widening | 09/08/2009 | 08/10/2009 | 12/21/2010 | 8474000 | 5
5190 | Oklahoma | CANADIAN |  | 3 | STIM238 | This project resurfaces the existing asphalt pavement with a Ultrathin MicroSurfacing preventive maintenance treatment The project starts at at the Kingfisher County Line on State Highway 3 east of Ok | Pavement Improvement | 06/05/2009 | 08/31/2009 |  | 2500000 | 15.54
5191 | Oklahoma | GARFIELD |  | 3 | STIM239 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the Major County Line on US 60 and extends east 5.0 miles toward Enid | Pavement Improvement | 06/05/2009 | 08/10/2009 |  | 2201741 | 5
5192 | Oklahoma | WASHITA |  | 3 | STIM240 | This project widens 2.5 miles of US 183 from two lanes to four lanes just south of Cordell, OK. | Pavement Widening | 08/03/2009 | 08/03/2009 | 01/19/2010 | 3781000 | 2.5
5193 | Oklahoma | BLAINE |  | 3 | STIM241 | This project resurfaces about 8 miles of US 270 west of Watonga, OK to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 05/29/2009 | 08/19/2009 |  | 2778000 | 7.9
5194 | Oklahoma | TULSA | TULSA | 1 | STIM264 | Resurface Elm Place from New Orleans St. to Florence St. | Pavement Improvement | 02/01/2010 |  | 06/30/2010 | 812315 | 1
5195 | Oklahoma | TULSA | TULSA | 1 | STIM265 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt at the intersection of Elm Place and Houston Street in Broken Arrow. The | Pavement Improvement | 02/01/2010 |  | 06/30/2010 | 222405 | 0.25
5196 | Oklahoma | TULSA | TULSA | 1 | STIM266 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Kenosha Street from Main Street to Sixth Street in Broken Arrow. This | Pavement Improvement | 02/01/2010 | 11/16/2009 | 05/31/2010 | 242578 | 0.5
5197 | Oklahoma | TULSA | TULSA | 1 | STIM267 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Kenosha Street from Hickory Court to Aspen Avenue in Broken Arrow. The | Pavement Improvement | 02/01/2010 | 11/16/2009 | 05/31/2010 | 295984 | 0.5
5198 | Oklahoma | TULSA | TULSA | 1 | STIM268 | Resurface intersection of 9th Street and Houston Street | Pavement Improvement | 02/01/2010 |  | 06/30/2010 | 198538 | 0.25
5199 | Oklahoma | TULSA | TULSA | 1 | STIM269 | Installation of traffic signals at the intersection of Albany Street and Stone Ridge Drive in Broken Arrow. | Safety/Traffic Management | 01/04/2010 |  | 04/03/2010 | 106331 | 0.125
5200 | Oklahoma | TULSA | TULSA | 1 | STIM270 | Installation of traffic signals at the intersection of New Orleans and 9th Street in Broken Arrow. | Safety/Traffic Management | 01/04/2010 |  | 04/03/2010 | 88505 | 0.125
5201 | Oklahoma | TULSA | TULSA | 1 | STIM271 | Installation of traffic signals at the intersection of Elm Place and Stonewood Drive in Broken Arrow. | Safety/Traffic Management | 01/04/2010 |  | 04/03/2010 | 105921 | 0.01
5202 | Oklahoma | ROGERS | TULSA | 1 | STIM272 | Installation of traffic signals at the intersection of Cherokee and South School Access in Catoosa. | Safety/Traffic Management | 02/01/2010 |  | 05/31/2010 | 149975 | 0.125
5203 | Oklahoma | WAGONER | TULSA | 1 | STIM273 | Installation of traffic signals at the intesection of 141st Street and State Highway 51 in Coweta. | Safety/Traffic Management | 02/01/2010 |  | 05/01/2010 | 9653 | 0.125
5204 | Oklahoma | WAGONER | TULSA | 1 | STIM274 | Resurface 151st St. from Division to SH-72 | Pavement Improvement | 02/01/2010 |  | 05/01/2010 | 34507 | 0.25
5205 | Oklahoma | TULSA | TULSA | 3 | STIM278 | This project will resurface the pavement of Airport Access Road from Euchee Creek Boulevard to West Shellcreek Road in Sand Springs by placing 2 to 2-3/4 inches of new asphalt which results in a smoot | Pavement Improvement | 10/05/2009 | 10/05/2009 | 11/18/2009 | 472877 | 3
5206 | Oklahoma | CREEK | TULSA | 3 | STIM279 | This project will remove and replace the 6 inch concrete pavement on East Line Street from Mission Street to Moccasin Place in Sapulpa. | Pavement Improvement | 11/02/2009 | 11/03/2009 | 03/01/2010 | 450828 | 0.5
5207 | Oklahoma | TULSA | TULSA | 1 | STIM281 | This project includes pavement and driveway repairs and will resurface the pavement to Mohawk Boulevard from Cincinnati Avenue to Hartford Avenue in Tulsa by placing 2 inches of new asphalt. The proj | Pavement Improvement | 10/05/2009 | 10/05/2009 | 02/01/2010 | 687730 | 0.5
5208 | Oklahoma | TULSA | TULSA | 1 | STIM282 | Pavement reconstruction and drainage improvements on Yale Avenue from Admiral Place to Pine Street in Tulsa. | Pavement Improvement | 01/04/2010 |  | 08/01/2010 | 1195167 | 1
5209 | Oklahoma | TULSA | TULSA | 1 | STIM283 | This project includes full depth concrete repairs and complete concrete pavement replacement on Southwest Boulevard from 23rd Street South to the Arkansas River Bridge in Tulsa. This project also rep | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/25/2010 | 1940282 | 0.75
5210 | Oklahoma | TULSA | TULSA | 1 | STIM284 | This project will extend the service life of the pavement by removing 2-3/4 inches of asphalt and placing 3 inches of new asphalt on Sheridan Road from 111th Street South to Admiral Boulevard in Tulsa | Pavement Improvement | 01/04/2010 |  | 03/29/2011 | 1371058 | 1
5211 | Oklahoma | TULSA | TULSA | 1 | STIM286 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Sheridan Road from 11th Street South to 21st Street South in Tulsa. Th | Pavement Improvement | 01/04/2010 |  | 03/29/2011 | 1434857 | 1
5212 | Oklahoma | TULSA | TULSA | 1 | STIM287 | This project will extend the service life of the pavement and makes driveway repairs to East 31st Street South from just west of South 132nd East Avenue to just east of South 140th East Avenue in Tuls | Pavement Improvement | 10/05/2009 | 10/05/2009 | 04/02/2010 | 516454 | 1
5213 | Oklahoma | TULSA | TULSA | 1 | STIM288 | This project will extend the service life of the pavement by removing 3-1/2" of existing asphalt and placing 3" of new asphalt pavement. The project also includes bridge deck repairs, upgrades an exi | Pavement Improvement | 01/11/2010 |  | 11/06/2010 | 1374172 | 1
5214 | Oklahoma | TULSA | TULSA | 1 | STIM289 | This project removes and replaces the existing pavement on East 41st Street from Interstate 44 to Sheridan Road and South Yale Avenue from 31st Street South to 36st Street South in Tulsa. The project | Pavement Improvement | 01/11/2010 | 01/11/2010 | 09/07/2010 | 1841843 | 0.75
5215 | Oklahoma | OSAGE |  | 3 | STIM290 | This project will extend the service life of the pavement by placing 3 inches of new asphalt pavement on U.S. Highway 60 beginning 0.75 mile east of the Osage/Kay County Line extending east 4.44 miles | Pavement Improvement | 07/06/2009 | 07/01/2009 | 07/28/2009 | 1240000 | 4.44
5216 | Oklahoma | OSAGE |  | 3 | STIM291 | This project will extend the service life of the pavement by removing 1 inch of asphalt pavement and placing 2 inches of new asphalt pavement on State Highway 99 beginning 0 .86 mile north of the Stat | Pavement Improvement | 07/06/2009 | 06/24/2009 | 08/05/2009 | 670000 | 4.17
5217 | Oklahoma | PAWNEE |  | 3 | STIM293 | This project will extend the service life of the pavement by patching the existing concrete pavement, installing supports at the joints, and grinding the surface to provide a smooth ride on U.S. Highw | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/14/2009 | 2108340 | 7.65
5218 | Oklahoma | PAWNEE |  | 3 | STIM294 | This project will extend the service life of the pavement by patching the existing concrete pavement, installing supports at the joints, and grinding the surface to provide a smooth ride on U.S. Highw | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/14/2009 | 1141660 | 6.7
5219 | Oklahoma | MUSKOGEE |  | 2 | STIM295 | Asphalt pavement resurfacing for 2.77 miles on I-40 in Muskogee County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 06/05/2009 | 08/24/2009 |  | 2360000 | 4.39
5220 | Oklahoma | COMANCHE | LAWTON | 4 | STIM296 | This project repairs 5 bridges, reconstructs deteriorated pavement, and improves safety features for about 2.5 miles of I-44 in Lawton, OK. | Pavement Improvement | 08/24/2009 | 08/24/2009 | 08/18/2010 | 14217384 | 1.52
5221 | Oklahoma | CIMARRON |  | 3 | STIM299 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the Junction with US 287 and extends east 7.5 miles on US 412 | Pavement Improvement | 06/09/2009 | 07/28/2009 |  | 2150000 | 7.5
5222 | Oklahoma | LOGAN | OKLAHOMA CITY | 3 | STIM300 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the on County Line road in the Cashion Area and extends from Seward Road to Forest Hill Road | Pavement Improvement | 09/28/2009 | 09/28/2009 | 12/11/2009 | 176426 | 1
5223 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM302 | Resurface Etowah road from 108th Ave to 180th Ave SE. | Pavement Improvement | 08/12/2009 | 08/31/2009 |  | 587297 | 6
5224 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 4 | STIM303 | This project will resurface 1.75 miles of road in Del City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. | Pavement Improvement | 02/01/2010 | 11/23/2009 | 03/02/2010 | 262802 | 1.75
5225 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM305 | This project will resurface 1 mile of road in the vicinity of Forrest Park in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 |  | 05/09/2010 | 147302 | 1
5226 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM308 | This project will resurface 1.5 miles of Main Street in Jones to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 |  | 05/09/2010 | 131157 | 1.5
5227 | Oklahoma | LOGAN | OKLAHOMA CITY | 3 | STIM309 | Resurface Pensylvania avenue from Oklahoma Couty line north into logan county | Pavement Improvement | 09/28/2009 | 09/28/2009 | 12/11/2009 | 443708 | 1.7
5228 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM401 | Resurface Janeway and Santa Fe from NW 12th to NW 27th | Pavement Improvement | 08/12/2009 | 08/31/2009 |  | 612303 | 2
5229 | Oklahoma | CANADIAN | OKLAHOMA CITY | 4 | STIM403 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts is on N Sara Rd in Mustang and extends from State Highwy 152 to SW 59th Street and South Mustage Fronta | Pavement Improvement | 08/19/2009 | 10/16/2009 |  | 279620 | 2
5230 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM405 | This project will resurface 1 mile of road in the vicinity of Nicoma Park in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 |  | 05/09/2010 | 61197 | 1
5231 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM407 | "Asphalt pavement resurfacing of portions of Eufaula Street, Flood Avenue, Jenkins Avenue, Lindsey Street, Porter Avenue, and University Boulevard in Cleveland County. This project was reconstructed | Pavement Improvement | 08/12/2009 | 08/31/2009 |  | 1272437 | 3.74
5232 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM408 | This project will resurface 5 miles of Memorial Road through north east Oklahoma City and Edmond to improve ride quality and extend the life of the pavement. In addition, new curb ramps will be instal | Pavement Improvement | 08/13/2009 | 08/24/2009 |  | 1355644 | 5
5233 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM409 | This project will resurface 8 miles of road in north west Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. | Pavement Improvement | 10/05/2009 | 10/05/2009 | 12/18/2009 | 3189188 | 8
5234 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM410 | This project will resurface 1.7 miles of road in north west Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. | Pavement Improvement | 08/19/2009 | 08/31/2009 |  | 652692 | 1.7
5235 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM411 | This project will resurface 3 miles of May Avenue in south Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. | Pavement Improvement | 08/19/2009 | 08/31/2009 |  | 966992 | 3
5236 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM412 | This project will resurface 3.5 miles of Shields Boulevard in south Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. | Pavement Improvement | 07/27/2009 | 07/20/2009 | 11/23/2009 | 1514850 | 3.5
5237 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM413 | Resurface multiple locations on Penn and May in the areas of SW 89th and SW 119th. | Pavement Improvement | 07/27/2009 | 07/20/2009 | 11/23/2009 | 1416273 | 5
5238 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM414 | This project will resurface 6 miles of road in Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. | Pavement Improvement | 09/28/2009 | 09/15/2009 | 11/26/2009 | 2202725 | 6
5239 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM415 | This project will resurface 6.3 miles of Midwest Boulevard in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 |  | 05/09/2010 | 2250617 | 6.3
5240 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM416 | This project will resurface 3 miles of road north of Luther to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 |  | 05/09/2010 | 522272 | 3
5241 | Oklahoma | CANADIAN | OKLAHOMA CITY | 3 | STIM417 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts is on Piedmont Rd in Mustang and extends from Arrowhead Road to Apache Street. | Pavement Improvement | 07/27/2009 | 08/03/2009 | 08/26/2009 | 188523 | 1
5242 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 4 | STIM418 | This project will resurface 1 mile of road south of Spencer to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 |  | 05/09/2010 | 118461 | 1
5243 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM419 | This project will resurface 1 mile of Penn Avenue in the city of Village to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. | Pavement Improvement | 08/19/2009 | 08/31/2009 |  | 278129 | 1
5244 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM420 | This project will resurface 0.5 mile of road in the city of Warr Acres to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramp | Pavement Improvement | 02/01/2010 |  | 03/02/2010 | 117535 | 0.5
5245 | Oklahoma | TULSA | TULSA | 1 | STIM422 | This project will extend the service life of the pavement by removing 2 inches of asphalt and placing 2 inches of new asphalt on East 2nd Street from Main Street to Adams Street in Sand Springs. | Pavement Improvement | 10/05/2009 | 10/05/2009 | 11/18/2009 | 185046 | 0.5
5246 | Oklahoma | MCCLAIN | OKLAHOMA CITY | 4 | STIM424 | Installation of traffic signals on U.S. Highway 77 at the intesections of State Highway 74 and State Highway 39. | Safety/Traffic Management | 02/08/2010 |  | 05/08/2010 | 170026 | 0.01
5247 | Oklahoma | CIMARRON |  | 3 | STIM428 | This project reconstructs the existing pavement with a new asphalt pavement. The project starts 7.0 miles south of the juncton with US 64 on US 287 and extends 0.8 miles | Pavement Improvement | 08/17/2009 | 08/26/2009 | 02/12/2010 | 2084606 | 0.83
5248 | Oklahoma | LOGAN |  | 3 | STIM429 | This project installs a new bridge and approaches on a county bridge over Wof Creek 2.0 miles north and 2.2 miles east of the junction with State Highway 74 and State Highway 74C. | Bridge Replacement | 01/04/2010 | 11/30/2009 | 04/03/2010 | 172636 | 0.25
5249 | Oklahoma | MURRAY |  | 4 | STIM430 | This project replaces the deficient county bridge over Eight Mile Creek near Hennepin, OK. | Bridge Replacement | 12/07/2009 | 11/30/2009 | 04/05/2010 | 247000 | 0.25
5250 | Oklahoma | ALFALFA |  | 3 | STIM431 | This project installs a new bridge and approaches on a county bridge over West Clay Creek on county road( NS 262) 1.0 miles east and 2.7 miles north of SH-8 junction with US-64 | Bridge Replacement | 01/05/2010 | 01/05/2010 | 05/04/2010 | 519465 | 0.2
5251 | Oklahoma | TULSA | TULSA | 1 | STIM482 | Intersection modifications and installation of traffic signals at 21st Street and Sheridan Road in Tulsa. | Pavement Improvement | 01/04/2010 |  | 03/29/2011 | 686902 | 0.01
5252 | Oregon | LANE |  | 4 | 0000183 | Enhance safety to pedestrians and bicyclists by repaving the EWEB Bike Path between Pioneer Parkway and 31st street in Eugene. | Other | 05/11/2009 | 05/11/2009 | 06/18/2009 | 5000 | 0
5253 | Oregon | LINN |  | 4 | 0100030 | Pave Salem Ave between Sherman St and the UP railroad crossing in Albany to improve safety and extend pavement life. | Pavement Improvement | 07/14/2009 | 07/22/2009 |  | 1040874.6 | 0
5254 | Oregon | LINN |  | 4 | 0100031 | Pave Salem Ave between Sherman St and the UP railroad crossing in Albany to improve safety and extend pavement life. | Other | 04/28/2009 | 04/28/2009 | 06/25/2009 | 3129.4 | 0
5255 | Oregon | JACKSON |  |  | 0305019 | Improves safety on Hersey St between Oak St and Ann St in Ashland by reconstructing sidewalks. | Transportation Enhancements | 07/14/2009 | 08/05/2009 | 11/20/2009 | 194597.81 | 0
5256 | Oregon | JACKSON | MEDFORD | 2 | 0305020 | Pave several city streets in Ashland to improve safety and extend pavement life. | Other | 04/15/2009 | 04/15/2009 | 07/16/2009 | 20000 | 0
5257 | Oregon | JACKSON |  |  | 0305021 | Improves safety on Hersey St between Oak St and Ann St in Ashland by reconstructing sidewalks. | Other | 04/15/2009 | 04/15/2009 | 06/16/2009 | 5000 | 0
5258 | Oregon | JACKSON | MEDFORD | 2 | 0305022 | Pave several city streets in Ashland to improve safety and extend pavement life. | Pavement Improvement | 08/11/2009 | 09/22/2009 | 10/30/2009 | 396607.29 | 0
5259 | Oregon | CLATSOP |  | 1 | 0315007 | Pave several city streets in Astoria to improve safety and extend pavement life. | Other | 07/23/2009 | 07/23/2009 |  | 20000 | 0
5260 | Oregon | MARION |  | 5 | 0330007 | Improve pedestrian and bicycle safety by adding sidewalks, curb cuts and drainage on OR 99E between Main St and 4th Street in Aurora. | Transportation Enhancements | 07/24/2009 |  |  | 159569.44 | 0
5261 | Oregon | MARION |  | 5 | 0330008 | Improve pedestrian and bicycle safety by adding sidewalks, curb cuts and drainage on OR 99E between Main St and 4th Street in Aurora. | Other | 06/25/2009 | 06/25/2009 | 06/26/2009 | 10000 | 0
5262 | Oregon | BAKER |  | 2 | 0365020 | Construct a pedestrian/bicycle shared use path on the Leo Adler Memorial Parkway between Madison St and Court St in Baker City. | Transportation Enhancements | 11/23/2009 |  |  | 217064 | 0
5263 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535022 | Pave Hall Blvd between Hart Rd and Ridgecrest Dr in Beaverton to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 | 12/18/2009 | 77150 | 0
5264 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535023 | Improve pedestrian safety and access by constructing sidewalks and ADA ramps on Laurelwood Ave and 87th Ave in Beaverton. | Other | 07/08/2009 | 07/08/2009 |  | 240000 | 0
5265 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535024 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Other | 08/05/2009 | 08/05/2009 |  | 200000 | 0
5266 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535026 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Safety/Traffic Management | 08/28/2009 | 08/28/2009 |  | 280000 | 0
5267 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535027 | 2 IN PAVEMENT OVERLAY IN ACCORDANCE WITH 1R GUIDELINES | Pavement Improvement | 12/18/2009 |  |  | 568757.05 | 0
5268 | Oregon | DESCHUTES |  | 2 | 0580035 | Pave several city streets in Bend to improve safety and extend pavement life. | Pavement Improvement | 09/18/2009 |  |  | 1181404.7 | 0
5269 | Oregon | DESCHUTES | BEND | 2 | 0580036 | Pave several city streets in Bend to improve safety and extend pavement life. | Other | 05/04/2009 | 05/04/2009 | 07/13/2009 | 50000 | 0
5270 | Oregon | CLACKAMAS |  | 5 | 1075005 | Improve vehicle and pedestrian safety and extend pavement life by paving and adding curbs and sidewalk on North Knights Bridge Rd between Knights Bridge and N Grant St in Canby. | Other | 06/22/2009 | 06/22/2009 |  | 40000 | 0
5271 | Oregon | JACKSON | MEDFORD | 2 | 1240012 | Pave Pine St between 1st St and 6th St in Central Point to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 25000 | 0
5272 | Oregon | WASCO |  | 2 | 1342003 | Improves safety and access on US 30 at the Brewery Grade intersection in The Dalles by reconstructing intersection to a round-about. | Pavement Improvement | 07/09/2009 | 08/25/2009 |  | 2524023.94 | 0
5273 | Oregon | LANE | EUGENE | 4 | 1440000 | Improve safety and drainage by repaving East Locust St and North Diamond St in Coburg. | Other | 06/04/2009 | 06/04/2009 | 11/19/2009 | 10000 | 0
5274 | Oregon | COOS |  | 4 | 1525004 | Pave North 10th St between Central Ave and Cedar Ave in Coos County to improve safety and extend pavement life. | Pavement Improvement | 10/09/2009 | 11/30/2009 |  | 349118.56 | 0
5275 | Oregon | WASHINGTON |  | 1 | 1555007 | Improve pavement, add curbs, sidewalks and signals to enhance safety and reduce wear and tear on OR Hwy 8 in Cornelius. | Other | 04/09/2009 | 04/09/2009 | 06/16/2009 | 40000 | 0
5276 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 1555008 | Improve pavement, add curbs, sidewalks and signals to enhance safety and reduce wear and tear on OR Hwy 8 in Cornelius. | Pavement Improvement | 05/22/2008 | 06/09/2008 | 09/10/2009 | 495659 | 0
5277 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 1555011 | Improve safety and extend the life of the pavement by sealing craks and repaving several streets in Cornelius. | Other | 09/17/2009 | 09/17/2009 |  | 65000 | 0
5278 | Oregon | BENTON | CORVALLIS | 4 | 1580031 | Pave several city streets in Corvallis to improve safety and extend pavement life. | Pavement Improvement | 08/28/2009 | 09/08/2009 |  | 738125 | 0
5279 | Oregon | BENTON |  | 4 | 1580032 | Enhance safety to pedestrians and bicyclists by repaving the Corvallis-Phillomath multi-use bicycle and pedestrian path in Benton County. | Pavement Improvement | 07/09/2009 | 07/29/2009 | 09/09/2009 | 352040.18 | 0
5280 | Oregon | LANE |  | 4 | 1595004 | Improve safety on South 8th St and Woodson Bridge approaches in Cottage Grove by adding curb, gutter, sidewalks and paved shoulders. | Other | 08/13/2009 | 08/13/2009 |  | 15000 | 0
5281 | Oregon | POLK |  | 5 | 1770002 | Pave several city streets in Dallas to improve safety and extend pavement life. | Pavement Improvement | 08/06/2009 | 08/24/2009 | 09/16/2009 | 318807 | 0
5282 | Oregon | POLK |  | 5 | 1770003 | Pave several city streets in Dallas to improve safety and extend pavement life. | Other | 06/04/2009 | 06/04/2009 | 07/16/2009 | 10000 | 0
5283 | Oregon | LANE |  | 4 | 2385059 | Improves access to the Eugene train depot by adding sidewalk and lighting to the pedestrian access. | Transportation Enhancements | 07/13/2009 | 08/03/2009 |  | 177900 | 0
5284 | Oregon | LANE | EUGENE | 4 | 2385060 | Enhances bridge and trail elements to improve usage of the Delta Ponds multi-use path between Goodpasture Island and Robin Hood Ln in Eugene. | Transportation Enhancements | 08/10/2009 | 08/24/2009 |  | 1229085.82 | 0
5285 | Oregon | LANE | EUGENE | 4 | 2385061 | Complete pavement preservation project on Garfeield St between W 6th Ave and W 11th Ave in Eugene to improve safety and extend the life of the pavement. | Other | 05/21/2009 | 05/21/2009 | 11/19/2009 | 45000 | 0
5286 | Oregon | LANE | EUGENE | 4 | 2385063 | Complete pavement preservation project on Crescent Ave between Gamefarm Rd and Shadowview in Eugene to improve safety and extend the life of the pavement. | Other | 06/19/2009 | 06/19/2009 | 11/19/2009 | 6000 | 0
5287 | Oregon | LANE | EUGENE | 4 | 2385064 | Complete pavement preservation project on High St between 3rd Ave and 17th Ave in Eugene to improve safety and extend the life of the pavement. | Other | 06/19/2009 | 06/19/2009 | 11/19/2009 | 55000 | 0
5288 | Oregon | LANE |  | 4 | 2605001 | Pave several city streets in Florence to improve safety and extend pavement life. | Other | 04/29/2009 | 04/29/2009 | 12/10/2009 | 15000 | 0
5289 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 2620003 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Other | 04/04/2006 | 04/04/2006 | 06/17/2009 | 170000 | 0
5290 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 2620004 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Transportation Enhancements | 04/04/2008 | 04/28/2008 |  | 1490000 | 0
5291 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 2620005 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Other | 08/29/2007 | 08/29/2007 | 06/17/2009 | 66978 | 0
5292 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 2900008 | Pave several city streets in Gladstone to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 100000 | 0
5293 | Oregon | JOSEPHINE |  | 4 | 3055403 | Pave several city streets in Grants Pass to improve safety and extend pavement life. | Other | 06/05/2009 | 06/05/2009 |  | 60000 | 0
5294 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | 3125034 | Improve safety and access to vehicles, bicycles and pedestrians on 242nd and Hogan Rd between Glisan St and Stark St by widening the seciton of road and adding four travel lanes, center turn lane, bic | Other | 06/11/2009 | 06/11/2009 | 10/22/2009 | 34033 | 0
5295 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | 3125035 | Improve safety and access to vehicles, bicycles and pedestrians on 242nd and Hogan Rd between Glisan St and Stark St by widening the seciton of road and adding four travel lanes, center turn lane, bic | Pavement Improvement | 11/24/2009 |  |  | 1711867.04 | 0
5296 | Oregon | CLACKAMAS | PORTLAND (WA) | 3 | 3205001 | Extend the life of the pavement on city streets in Happy Valley by sealing and resurfacing several minor arterial streets. | Other | 05/15/2009 | 05/15/2009 |  | 77000 | 0
5297 | Oregon | UMATILLA |  | 2 | 3370003 | 2 IN PAVEMENT OVERLAY IN ACCORDANCE WITH 1R GUIDELINES | Pavement Improvement | 12/22/2009 |  |  | 326219.17 | 0
5298 | Oregon | UMATILLA |  | 2 | 3370004 | Pave Feedville Rd and Kelli blvd between OR 395 and Cook Industrial site in Umatilla County to improve safety and extend pavement life. | Other | 07/29/2009 | 07/29/2009 | 07/31/2009 | 17500 | 0
5299 | Oregon | MORROW |  | 2 | 3650003 | Enhance pedestrian and bicycle safety by constructing sidewalks, bike lanes, and a planter strip with street trees along 1st St and Main Ave in Irrigon. | Transportation Enhancements | 07/09/2009 | 07/23/2009 |  | 1377596.59 | 0
5300 | Oregon | MORROW |  | 2 | 3650004 | Enhance pedestrian and bicycle safety by constructing sidewalks, bike lanes, and a planter strip with street trees along 1st St and Main Ave in Irrigon. | Other | 05/13/2009 | 05/13/2009 | 06/18/2009 | 85356 | 0
5301 | Oregon | JACKSON | MEDFORD | 2 | 3700009 | Improve bicycle and pedestrian safety and mobility by adding bike lanes and sidewalks to C St in Jacksonville. | Other | 05/14/2009 | 05/14/2009 |  | 58000 | 0
5302 | Oregon | KLAMATH |  | 2 | 3970018 | Improve safety of pedestrian connections to the bus and train station in Klamath Falls by restoring fencing, adding lighting and crossing enhancements. Improves mobility by repaving Spring St. | Transportation Enhancements | 06/10/2009 | 07/13/2009 |  | 136097.56 | 0
5303 | Oregon | UNION |  | 2 | 4035015 | Pave Spruce St between Monroe Ave and Z avenue in LaGrande to improve safety and extend pavement life. | Other | 07/29/2009 | 07/29/2009 |  | 30000 | 0
5304 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 4055009 | Pave Royce and McNary St in Lake Oswego to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 97747 | 0
5305 | Oregon | LINN |  | 4 | 4165008 | Pave 2nd St and Airport Rd in Lebanon to improve safety and extend pavement life. | Other | 07/01/2009 | 07/01/2009 |  | 80000 | 0
5306 | Oregon | YAMHILL |  | 1 | 4500006 | Pave several city streets in McMinnville to improve safety and extend pavement life. | Pavement Improvement | 07/16/2009 | 08/13/2009 | 10/20/2009 | 874200.11 | 0
5307 | Oregon | YAMHILL |  | 1 | 4500007 | Pave several city streets in McMinnville to improve safety and extend pavement life. | Other | 06/18/2009 | 06/18/2009 | 06/19/2009 | 10000 | 0
5308 | Oregon | CLACKAMAS | PORTLAND (WA) | 3 | 4865010 | Improve pedestrian safety and access by reconstructing sidewalks, streetscape, and curb extensions on Jackson St between Main St and 21st Ave in Clackamas. | Other | 08/05/2009 | 08/05/2009 |  | 210000 | 0
5309 | Oregon | POLK |  | 5 | 4955002 | Pave Stadium Dr and Jackson St in Monmouth to improve safety and extend pavement life. | Other | 08/10/2009 | 08/10/2009 | 10/12/2009 | 10000 | 0
5310 | Oregon | GRANT |  | 2 | 5025101 | Install additional lights on Main Street in Mt. Vernon to improve pedestrian safety. | Transportation Enhancements | 02/24/2009 | 03/30/2009 | 08/14/2009 | 100000 | 0
5311 | Oregon | YAMHILL |  | 1 | 5210002 | PAVEMENT PRESERVATION PROJECT | Other | 10/30/2009 | 10/30/2009 |  | 90000 | 0
5312 | Oregon | LINCOLN |  | 5 | 5245004 | Improve safety and access with repairs to sidewalks, curb and gutter, paving, and lighting on Bay Blvd in Newport. | Pavement Improvement | 08/17/2009 | 09/08/2009 |  | 583000 | 0
5313 | Oregon | LINCOLN |  | 5 | 5245005 | Improve safety and access with repairs to sidewalks, curb and gutter, paving, and lighting on Bay Blvd in Newport. | Other | 04/15/2009 | 04/15/2009 | 07/16/2009 | 10000 | 0
5314 | Oregon | JACKSON | MEDFORD | 2 | 5245006 | Improve safety and extend pavement life on several city streets in Talent and Phoenix by paving, addind additional signage and signals. | Pavement Improvement | 08/11/2009 | 10/12/2009 |  | 387054.89 | 0
5315 | Oregon | LINCOLN |  | 5 | 5245007 | Pave several city streets in Newport to improve safety and extend pavement life. | Other | 05/21/2009 | 05/21/2009 | 07/16/2009 | 10000 | 0
5316 | Oregon | LINCOLN |  | 5 | 5245008 | Pave several city streets in Newport to improve safety and extend pavement life. | Pavement Improvement | 08/07/2009 | 09/01/2009 | 10/20/2009 | 216483 | 0
5317 | Oregon | MALHEUR |  | 2 | 5490003 | Enhance safety by widening and repaving roadway, and installing sidewalks and curbs on N Oregon St between Idaho Ave and NW 1st St in Ontario. | Pavement Improvement | 07/06/2009 | 07/24/2009 |  | 1991199.17 | 0
5318 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 5520019 | Improve vehicle and pedestrian safety, mobility and traffic flow on Warner Milne Rd between Beaversreek and Mollala in Oregon City buy realigning the intersection, updating signal timing and adding si | Safety/Traffic Management | 08/18/2009 | 09/21/2009 |  | 885000 | 0
5319 | Oregon | CLACKAMAS |  | 5 | 5520020 | Enhance safety on historic McLoughlin Promenade multi-use path between 7th St and S 1st St in Oregon City by restoring historing walls, including wall caps and joints, handrails, stairs and tunnel. | Transportation Enhancements | 07/09/2009 | 08/20/2009 |  | 1065721 | 0
5320 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 5520023 | Improve vehicle and pedestrian safety, mobility and traffic flow on Warner Milne Rd between Beaversreek and Mollala in Oregon City buy realigning the intersection, updating signal timing and adding si | Other | 04/27/2009 | 04/27/2009 | 08/31/2009 | 15000 | 0
5321 | Oregon | UMATILLA |  | 2 | 5715014 | Pave Tutuilla Rd between US 395 (Southgate) and SW Athens Way in Umatilla County to improve safety and extend pavement life. | Other | 07/29/2009 | 07/29/2009 | 07/31/2009 | 30000 | 0
5322 | Oregon | MULTNOMAH | PORTLAND (WA) | V | 5900201 | Improve bicycle safety and mobility by adding striping, signage and wayfinding to the Portland bicycle boulevard project. | Other | 07/21/2009 | 07/21/2009 | 11/10/2009 | 100000 | 0
5323 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | 5900202 | Improve interesection safety and access by adding a right turn lane from 82nd Ave to westbound Columbia Blvd in Portland. | Other | 07/20/2009 | 07/20/2009 |  | 200000 | 0
5324 | Oregon | MULTNOMAH | PORTLAND (WA) | V | 5900203 | Pave Springwater Trail between UPRR Bridge and the East City border in Portland to improve safety and extend the life of the pavement. | Other | 07/21/2009 | 07/21/2009 | 12/15/2009 | 151000 | 0
5325 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | 5900204 | Complete pavement preservation project on several streets in SE Portland to improve safety and extend the life of the pavement. | Other | 08/05/2009 | 08/05/2009 | 12/07/2009 | 15000 | 0
5326 | Oregon | MULTNOMAH | PORTLAND (WA) | V | 5900207 | Improve safety and accessibility in southwest and east Portland with curb cuts and sidewalks on variuos streets. | Other | 08/05/2009 | 08/05/2009 | 12/07/2009 | 300000 | 0
5327 | Oregon | CROOK |  | 2 | 5985008 | Improve mobility and safety by adding 2nd Street egress to OR 126 (3rd St) in Prineville. | Other | 03/24/2009 | 03/24/2009 | 06/16/2009 | 10000 | 0
5328 | Oregon | CROOK |  | 2 | 5985009 | Improve mobility and safety by adding 2nd Street egress to OR 126 (3rd St) in Prineville. | New Construction | 07/13/2009 | 08/24/2009 |  | 284798.58 | 0
5329 | Oregon | CROOK |  | 2 | 5985010 | Pave several city streets in Prineville to improve safety and extend pavement life. | Pavement Improvement | 08/05/2009 | 09/02/2009 |  | 217987 | 0
5330 | Oregon | CROOK |  | 2 | 5985011 | Pave several city streets in Prineville to improve safety and extend pavement life. | Other | 03/24/2009 | 03/24/2009 | 07/16/2009 | 3312.4 | 0
5331 | Oregon | DESCHUTES |  | 2 | 6120009 | Improve safety by reconstructing 5th St between SW Glacier and Jackpine in Redmond. Project includes paving, stormwater system, curb repair and sidewalks. | Other | 02/23/2009 | 02/23/2009 | 06/16/2009 | 25000 | 0
5332 | Oregon | DESCHUTES |  | 2 | 6120010 | Improve safety by reconstructing 5th St between SW Glacier and Jackpine in Redmond. Project includes paving, stormwater system, curb repair and sidewalks. | Pavement Improvement | 07/07/2009 | 08/03/2009 |  | 3636425.62 | 0
5333 | Oregon | COLUMBIA |  | 1 | 6460003 | Improve vehcile and pedestrian safety and extend pavement life on Columbia Blvd between US 30 and 1st St in St. Helens by paving and adding sidewalks, curb and gutter. | Other | 08/14/2009 | 08/14/2009 |  | 60000 | 0
5334 | Oregon | POLK |  | 5 | 6490071 | Preserve investment in Union Street Rail Road bridge shared use path in Salem by removing lead based paint and re-painting upper portion of the bridge. | Other | 05/11/2009 | 05/11/2009 | 09/24/2009 | 20213.81 | 0
5335 | Oregon | MARION | SALEM | 5 | 6490072 | Pave sections of Hyacinth St, Chemawa Rd, Cordon Rd, Hawthorne Ave and Kuebler Blvd in Salem to improve safety and extend pavement life. | Other | 08/13/2009 | 08/13/2009 |  | 50000 | 0
5336 | Oregon | MARION |  | 5 | 6490075 | Preserve investment in Union Street Rail Road bridge shared use path in Salem by removing lead based paint and re-painting upper portion of the bridge. | Transportation Enhancements | 10/16/2009 | 11/09/2009 |  | 2066707.9 | 0
5337 | Oregon | POLK | SALEM | 5 | 6490077 | BICYCLE/PEDESTRIAN PATH ALONG EDGE OF WALLACE MARINE PARK | Other | 11/24/2009 | 11/24/2009 |  | 50000 | 0
5338 | Oregon | COLUMBIA |  | 1 | 6550002 | Improve safety along road by removing and replacing curb, gutter, sidewalk and street trees along US 30 between Old Portland Rd and Crown Zellerbach Rd in Scappoose. | Transportation Enhancements | 07/15/2009 | 08/05/2009 |  | 251831.27 | 0
5339 | Oregon | COLUMBIA |  | 1 | 6550003 | Improve safety along road by removing and replacing curb, gutter, sidewalk and street trees along US 30 between Old Portland Rd and Crown Zellerbach Rd in Scappoose. | Other | 04/15/2009 | 04/15/2009 | 06/18/2009 | 59079.34 | 0
5340 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 6710003 | Pave Sherwood Blvd between 3rd St and Langer Dr in Sherwood to improve safety and extend pavement life. | Other | 09/17/2009 | 09/17/2009 |  | 75000 | 0
5341 | Oregon | LANE | EUGENE | 4 | 6900026 | Complete pavement preseravation project on 23rd St between Yolanda and Hayden Bridge Rd in Springfield to improve safety and extend the life of the pavement. | Other | 07/01/2009 | 07/01/2009 | 11/19/2009 | 10000 | 0
5342 | Oregon | LANE | EUGENE | 4 | 6960020 | Complete pavement preservation project on Pioneer Parkway between Hayden Bridge and Q St in Springfield to improve safety and extend pavement life. | Other | 07/13/2009 | 07/13/2009 |  | 250000 | 0
5343 | Oregon | LANE | EUGENE | 4 | 6960030 | Improve safety on several city streets in Springfield by replacing low pressure sodium lights with high pressure sodium and metal halide lights. | Other | 08/10/2009 | 08/10/2009 | 11/19/2009 | 15000 | 0
5344 | Oregon | LANE | EUGENE | 4 | 6960031 | Improve safety and traffic flow on several city streets in Springfield retiming traffic signals. | Other | 08/13/2009 | 08/13/2009 | 11/19/2009 | 10000 | 0
5345 | Oregon | JACKSON | MEDFORD | 2 | 7250009 | Improve safety and extend pavement life on several city streets in Talent and Phoenix by paving, addind additional signage and signals. | Other | 04/16/2009 | 04/16/2009 | 07/16/2009 | 43161 | 0
5346 | Oregon | WASHINGTON | PORTLAND (WA) | V | 7365007 | Pave Bonita, Durham and 72nd Ave in Tigard to improve safety and extend pavement life. | Other | 08/21/2009 | 08/21/2009 |  | 112000 | 0
5347 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 8015000 | Pave Salamo Rd between Barrington Dr and Rosemont in West Linn to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 100000 | 0
5348 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 8280005 | Improve vehicle, bicycle and pedestrian safety on Barber St between Boberg Rd and Boones Ferry Rd in Wilsonville by widening to allow for bike lanes and sidewalks on both sides and a center turn lane. | Other | 08/26/2009 | 08/26/2009 |  | 60000 | 0
5349 | Oregon | BAKER |  | 2 | C001012 | Pave Wingville Ln from mile point 0 to milp point 4.76 in Baker County to improve safety and extend pavement life. | Other | 07/21/2009 | 07/21/2009 | 07/31/2009 | 40000 | 0
5350 | Oregon | BENTON |  | 4 | C003035 | Pave Alpine Rd in Benton County to improve safety and extend pavement life. | Pavement Improvement | 07/20/2009 | 07/20/2009 | 07/24/2009 | 339247.17 | 0
5351 | Oregon | BENTON |  | 5 | C003036 | Improve safety to pedestrians and bicyclists by repaving the Campus Way multi-use bicycle and pedestrian path between 35th St and 53rd St in Corvallis. | Pavement Improvement | 07/02/2009 | 07/06/2009 | 07/29/2009 | 90000 | 0
5352 | Oregon | CLATSOP |  | 1 | C007023 | Pave Lewis & clark Rd between Tucker Creek Rd and Lyngstad Heights Rd in Clatsop County to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 | 09/10/2009 | 60000 | 0
5353 | Oregon | CLATSOP |  | 1 | C007024 | Pave Lewis & clark Rd between Tucker Creek Rd and Lyngstad Heights Rd in Clatsop County to improve safety and extend pavement life. | Pavement Improvement | 12/09/2009 |  |  | 481530 | 0
5354 | Oregon | COLUMBIA |  | 1 | C009055 | Pave Apiary Rd between mile point 14 and mile point 19 in Columbia County to improve safety and extend pavement life. | Other | 06/09/2009 | 06/09/2009 |  | 59839.48 | 0
5355 | Oregon | COLUMBIA |  | 1 | C009056 | Pave Apiary Rd between mile point 14 and mile point 19 in Columbia County to improve safety and extend pavement life. | Safety/Traffic Management | 10/09/2009 |  |  | 719692.52 | 0
5356 | Oregon | COOS |  | 4 | C011058 | Pave and add additional signage to Central Blvd between OR 42 and 10th St in Coos County to improve safety and extend pavement life. | Other | 06/12/2009 | 06/12/2009 | 02/04/2010 | 60000 | 0
5357 | Oregon | COOS |  | 4 | C011059 | Repair the Anson Rogers Bridge on South Coos River Rd in Coos County to improve safety and extend the life of the bridge. | Other | 06/10/2009 | 06/10/2009 | 01/14/2010 | 50000 | 0
5358 | Oregon | CROOK |  | 2 | C013016 | Pave Lone Pine Rd and Smith Rock Way in Crook County to improve safety and extend pavement life. | Other | 05/05/2009 | 05/05/2009 | 10/26/2009 | 50000 | 0
5359 | Oregon | DESCHUTES |  | 2 | C017013 | Pave Huntington Rd and Riverview Rd between South Century Drive and Burgess Rd in Deschutes County to improve safety and extend pavement life. | Pavement Improvement | 08/27/2009 | 09/30/2009 |  | 1024637.3 | 0
5360 | Oregon | DESCHUTES |  | 2 | C017014 | Pave Huntington Rd and Riverview Rd between South Century Drive and Burgess Rd in Deschutes County to improve safety and extend pavement life. | Other | 05/03/2009 | 05/03/2009 | 06/15/2009 | 19841.7 | 0
5361 | Oregon | DOUGLAS |  | 4 | C019036 | Pave Dillard Hwy between mile point .71 and mile point 5.85 in Douglas County to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 | 09/24/2009 | 28087.55 | 0
5362 | Oregon | DOUGLAS |  | 4 | C019037 | Pave Dillard Hwy between mile point .71 and mile point 5.85 in Douglas County to improve safety and extend pavement life. | Pavement Improvement | 10/09/2009 |  |  | 1516177.45 | 0
5363 | Oregon | HARNEY |  | 2 | C025019 | Place chip seal on Silver Creek Rd and Green House Ln in Harney County to improve safety and extend pavement life. | Pavement Improvement | 09/16/2009 | 09/23/2009 |  | 427396.72 | 0
5364 | Oregon | HARNEY |  | 2 | C025021 | Place chip seal on Silver Creek Rd and Green House Ln in Harney County to improve safety and extend pavement life. | Other | 07/21/2009 | 07/21/2009 | 10/31/2009 | 5750.58 | 0
5365 | Oregon | HOOD RIVER |  | 2 | C027013 | Pave Belmont Dr and Cooper Spur Rd in Hood River County to improve safety and extend pavement life. | Other | 05/15/2009 | 05/15/2009 |  | 100000 | 0
5366 | Oregon | JACKSON |  | 2 | C029058 | Pave several county roads in Jackson County to improve safety and extend pavement life. | Other | 04/29/2009 | 04/29/2009 | 08/20/2009 | 85000 | 0
5367 | Oregon | JACKSON |  | 2 | C029059 | Improve pedestrian and bicycle safety and access by constructing a shared use path on Barnett Rd in Jackson County. | Transportation Enhancements | 10/07/2009 | 11/16/2009 |  | 1027699 | 0
5368 | Oregon | JACKSON |  | 2 | C029061 | Pave several county roads in Jackson County to improve safety and extend pavement life. | Pavement Improvement | 09/10/2009 | 10/06/2009 | 11/19/2009 | 1390795 | 0
5369 | Oregon | JEFFERSON |  | 2 | C031004 | Pave Lone Pine Rd from mile point 0 to mile point 3.7 in Jefferson County to improve safety and extend pavement life. | Pavement Improvement | 09/03/2009 | 10/01/2009 |  | 448488.35 | 0
5370 | Oregon | JEFFERSON |  | 2 | C031005 | Pave Lone Pine Rd from mile point 0 to mile point 3.7 in Jefferson County to improve safety and extend pavement life. | Other | 05/05/2009 | 05/05/2009 | 06/22/2009 | 15527.2 | 0
5371 | Oregon | JOSEPHINE |  | 4 | C033031 | Pave Old Hwy 99 from mile point 0 to mile point .67 in Josephine County to improve safety and extend pavement life. | Other | 06/04/2009 | 06/04/2009 | 07/30/2009 | 1386.94 | 0
5372 | Oregon | JOSEPHINE |  | 4 | C033032 | Pave Old Hwy 99 from mile point 0 to mile point .67 in Josephine County to improve safety and extend pavement life. | Pavement Improvement | 08/17/2009 | 09/28/2009 | 10/30/2009 | 203390.44 | 0
5373 | Oregon | KLAMATH |  | 2 | C035024 | Improve safety on Washburn Way between Crosby and Joe Wright Rd in Klamath Falls by paving and adding additional signage. | Other | 05/01/2009 | 05/01/2009 | 06/08/2009 | 60426 | 0
5374 | Oregon | KLAMATH |  | 2 | C035025 | Improve safety on Washburn Way between Crosby and Joe Wright Rd in Klamath Falls by paving and adding additional signage. | Pavement Improvement | 08/10/2009 | 09/09/2009 | 10/23/2009 | 1032597.72 | 0
5375 | Oregon | LANE | EUGENE | 4 | C039027 | Enhance safety to pedestrians and bicyclists by repaving the EWEB Bike Path between Pioneer Parkway and 31st street in Eugene. | Pavement Improvement | 07/15/2009 | 07/20/2009 | 09/30/2009 | 314268.1 | 0
5376 | Oregon | LANE |  | 4 | C039028 | Pave Clear Lake Rd and Marcola Rd in Lane County to improve safety and extend pavement life. | Other | 05/07/2009 | 05/07/2009 | 11/19/2009 | 104000 | 0
5377 | Oregon | LANE |  | 4 | C039029 | 2 IN PAVEMENT OVERLAY IN ACCORDANCE WITH 1R GUIDELINES | Pavement Improvement | 12/17/2009 |  |  | 1596640.02 | 0
5378 | Oregon | LANE | EUGENE | 4 | C039030 | Complete pavement preservation project on River Rd, 23rd St and Coburg Rd in Eugene to improve safety and extend the life of the pavement. | Other | 06/04/2009 | 06/04/2009 | 11/19/2009 | 40000 | 0
5379 | Oregon | LANE | EUGENE | 4 | C039031 | LOCAL PAVEMENT PRESERVATION PROJECT | Pavement Improvement | 12/17/2009 |  |  | 1013064.98 | 0
5380 | Oregon | LANE | EUGENE | 4 | C039032 | Complete pavement preservation project on W 1st Ave between Seneca Rd and Bertelsen Rd in Eugene to improve safety and extend the life of the pavement. | Other | 06/11/2009 | 06/11/2009 | 11/19/2009 | 26000 | 0
5381 | Oregon | LINCOLN |  | 5 | C041009 | Pave Northbank Rd and Schooner Creek Rd in Lincoln County to improve safety and extend pavement life. | Other | 05/05/2009 | 05/05/2009 | 07/16/2009 | 55000 | 0
5382 | Oregon | LINCOLN |  | 5 | C041010 | Pave Northbank Rd and Schooner Creek Rd in Lincoln County to improve safety and extend pavement life. | Pavement Improvement | 08/24/2009 | 09/11/2009 | 10/21/2009 | 822455 | 0
5383 | Oregon | LINN |  | 4 | C043021 | Pave Stayton-Scio Rd and Oakville Rd in Linn County to improve safety and extend pavement life. | Other | 05/07/2009 | 05/07/2009 | 08/27/2009 | 60000 | 0
5384 | Oregon | LINN |  | 4 | C043022 | Pave Stayton-Scio Rd and Oakville Rd in Linn County to improve safety and extend pavement life. | Pavement Improvement | 09/17/2009 | 09/21/2009 |  | 1237130 | 0
5385 | Oregon | MALHEUR |  | 2 | C045026 | Pave Foothill Dr, Halliday St and Railroad Ave in Malheur County to improve safety and extend pavement life. | Other | 01/14/2009 | 01/14/2009 | 07/31/2009 | 30000 | 0
5386 | Oregon | MARION | SALEM | 5 | C047041 | Pave several county roads in Marion County and Young St in Woodburn to improve safety and extend pavement life. | Pavement Improvement | 08/28/2009 |  |  | 1636132.72 | 0
5387 | Oregon | MARION | SALEM | 5 | C047042 | Pave sections of Auburn Rd, Hazelgreen Rd, State St, Turner Rd, Center St, Ward Dr and Brown Rd in Marion County (Salem and Keizer) to improve safety and extend pavement life. | Other | 06/05/2009 | 06/05/2009 | 07/23/2009 | 10000 | 0
5388 | Oregon | MARION | SALEM | 5 | C047043 | Pave sections of Auburn Rd, Hazelgreen Rd, State St, Turner Rd, Center St, Ward Dr and Brown Rd in Marion County (Salem and Keizer) to improve safety and extend pavement life. | Pavement Improvement | 08/28/2009 |  |  | 1509533.64 | 0
5389 | Oregon | MARION |  | 5 | C047044 | Pave several county roads in Marion County and Young St in Woodburn to improve safety and extend pavement life. | Other | 06/19/2009 | 06/19/2009 | 07/23/2009 | 10000 | 0
5390 | Oregon | MARION | SALEM | 5 | C047047 | UPGRADE SIGNAL TO IMPROVE SAFETY | Other | 10/14/2009 | 10/14/2009 |  | 40000 | 0
5391 | Oregon | MARION |  | 2 | C047049 | REPLACE FERRY BOAT AND IMPROVEMENTS TO FERRY TERMINI | Other | 12/22/2009 | 12/22/2009 |  | 257000 | 0
5392 | Oregon | MORROW |  | 2 | C049013 | Pave Upper Rhea Creek Rd from mile point 2.2 to mile point 4.5 in Morrow County to improve safety and extend pavement life. | Pavement Improvement | 10/07/2009 |  |  | 509211 | 0
5393 | Oregon | MULTNOMAH |  | 3 | C051070 | Improve safety and mobility at the intersection of 282nd Ave and Stone Rd in Multnomah County by widening 282nd Ave to provide left turn lanes and widening and aligning Stone Rd. | Pavement Improvement | 05/05/2008 | 05/22/2008 |  | 184655 | 0
5394 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | C051080 | Improve safety on NW Cornelius Pass Rd in Portland by installing signs and signals and repairing guardrail. | Safety/Traffic Management | 10/07/2009 |  |  | 205161.11 | 0
5395 | Oregon | MULTNOMAH | PORTLAND (WA) | 1 | C051081 | Improve pedestrian safety and access by constructing sidwalks on Halsey St and Stark St in Multnomah County. | Other | 06/05/2009 | 06/05/2009 | 09/30/2009 | 40000 | 0
5396 | Oregon | MULTNOMAH |  | 3 | C051082 | Improve safety on NW Cornelius Pass Rd in Portland by installing signs and signals and repairing guardrail. | Other | 06/11/2009 | 06/11/2009 | 09/30/2009 | 14838.89 | 0
5397 | Oregon | POLK |  | 5 | C053033 | Pave Falls City Rd from mile point 0 to mile point 3.8 in Polk County to improve safety and extend pavement life. | Pavement Improvement | 09/17/2009 | 10/07/2009 | 10/29/2009 | 403929 | 0
5398 | Oregon | POLK |  | 5 | C053034 | Pave Falls City Rd from mile point 0 to mile point 3.8 in Polk County to improve safety and extend pavement life. | Other | 06/09/2009 | 06/09/2009 | 08/27/2009 | 50000 | 0
5399 | Oregon | TILLAMOOK |  | 5 | C057034 | Repave Long Prairie Rd and the Johnson Bridge Rd approaches in Tillamook county to improve safety and extend pavement life. | Pavement Improvement | 08/07/2009 | 09/16/2009 |  | 626548 | 0
5400 | Oregon | UMATILLA |  | 2 | C059038 | Pave Despain Gulch Rd between Pendleton-Cold Springs Hwy and mile point 6 in Umatilla County to improve safety and extend pavement life. | Pavement Improvement | 11/24/2009 |  |  | 979867.34 | 0
5401 | Oregon | UMATILLA |  | 2 | C059039 | Pave Despain Gulch Rd between Pendleton-Cold Springs Hwy and mile point 6 in Umatilla County to improve safety and extend pavement life. | Other | 07/29/2009 | 07/29/2009 | 07/31/2009 | 17215.66 | 0
5402 | Oregon | WALLOWA |  | 2 | C063019 | Pave Upper Diamond Ln between OR 82 and Lower Diamond Ln in Wallowa County to improve safety and extend pavement life. | Other | 09/09/2009 | 09/09/2009 |  | 47000 | 0
5403 | Oregon | WASCO |  | 2 | C065018 | Pave severla county roads in Wasco County to improve safety and extend pavement life. | Pavement Improvement | 11/02/2009 |  |  | 424744.05 | 0
5404 | Oregon | WASCO |  | 2 | C065019 | Pave severla county roads in Wasco County to improve safety and extend pavement life. | Other | 04/23/2009 | 04/23/2009 | 08/24/2009 | 50000 | 0
5405 | Oregon | WASHINGTON |  | 1 | C067063 | Pave several county roads in Washington County to improve safety and extend pavement life. | Other | 05/06/2009 | 05/06/2009 |  | 97000 | 0
5406 | Oregon | WASHINGTON |  | 1 | C067064 | Improve safety by installing upgraded bridge guardrail on several bridges in Washington County. | Other | 05/06/2009 | 05/06/2009 |  | 50000 | 0
5407 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067065 | Improve school zone safety by installing new solar powered school zone flasher units at several school zones in Washington County. | Other | 05/06/2009 | 05/06/2009 | 09/10/2009 | 25000 | 0
5408 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067066 | Improve safety and traffic flow on several streets in Washington County by installing new signal hardware to include flasshing yellow arrows and replacing illuminated signs. | Other | 06/11/2009 | 06/11/2009 |  | 55000 | 0
5409 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067067 | Pave several city streets in Washington County to improve safety and extend pavement life. | Other | 05/07/2009 | 05/07/2009 |  | 250000 | 0
5410 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067068 | Improve mobility and traffic flow at several intersections in Washington County by evaluating signal timing and making changes to the signal timing as necessary. | Safety/Traffic Management | 05/28/2009 | 05/28/2009 |  | 600000 | 0
5411 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067072 | Improve school zone safety by installing new solar powered school zone flasher units at several school zones in Washington County. | Safety/Traffic Management | 10/07/2009 |  |  | 225000 | 0
5412 | Oregon | STATEWIDE | PORTLAND (WA) | 1 | C067073 | Improve safety and traffic flow on several streets in Washington County by installing new signal hardware to include flasshing yellow arrows and replacing illuminated signs. | Safety/Traffic Management | 12/09/2009 |  |  | 470809.12 | 0
5413 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067076 | Improve safety by installing emergency vehicle signal pre-emption devices at approximately 86 intersections in Washington County. | Other | 08/28/2009 | 08/28/2009 |  | 30000 | 0
5414 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067080 | Improve safety and traffic flow by installing traffic video detection equipment at 20 intersections in Washington County and Tigard. | Other | 09/01/2009 | 09/01/2009 |  | 35000 | 0
5415 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067081 | Improve pedestrian safety by installing pedestrian countdown timers at approximately 150 intersections in Washington County. | Other | 08/28/2009 | 08/28/2009 |  | 55000 | 0
5416 | Oregon | WHEELER |  | 2 | C069002 | 2 IN PAVEMENT OVERLAY IN ACCORDANCE WITH 1R GUIDELINES | Other | 10/14/2009 | 10/14/2009 |  | 50000 | 0
5417 | Oregon | YAMHILL |  | 1 | C071014 | Pave Baker Creek Rd between Michelbrook Ln and Power House Hill Rd in Yamhill County to improve safety and extend pavement life. | Pavement Improvement | 07/14/2009 | 08/10/2009 | 09/03/2009 | 731685.88 | 0
5418 | Oregon | JOSEPHINE |  | 4 | S000312 | Preserves road by extending current project replacing poor pavement on OR 99 and OR 238 in Josephine County. | Other | 10/31/2006 | 10/31/2006 |  | 50000 | 0
5419 | Oregon | JOSEPHINE |  | 4 | S000393 | Preserves road by extending current project replacing poor pavement on OR 99 and OR 238 in Josephine County. | Pavement Improvement | 02/25/2009 | 03/03/2009 |  | 3025555.32 | 0
5420 | Oregon | UMATILLA |  | 2 | S000431 | Improves safety of a dangerous rail crossing on US 30 between Pendleton and Athena through reconstruction and paving. | Pavement Improvement | 05/19/2009 | 06/24/2009 |  | 899516.23 | 0.1
5421 | Oregon | LINCOLN |  | 5 | S000457 | Improve safety on US 20 between Pioneer Mountain Loop Rd and Yaquina River in Lincoln County by removing narrow, winding roads. | Other | 07/09/2009 | 07/09/2009 | 12/17/2009 | 250000 | 0
5422 | Oregon | STATEWIDE |  | 4 | S000481 | Enhance safety by replacing damaged or substandard guardrail on OR 219, OR 34, OR 58, OR 126, and US 101. | Safety/Traffic Management | 07/02/2009 |  |  | 1075678.38 | 0
5423 | Oregon | BAKER |  | 2 | S000485 | Improve safety for motorists and pedestrians by paving and adding curb and gutter to Birch Street in Baker City. | Pavement Improvement | 05/22/2009 | 06/08/2009 | 10/28/2009 | 648626.83 | 0
5424 | Oregon | BAKER |  | 2 | S000489 | Improve safety by replacing the aging Dewey Ave Union Pacific rail-road crossing on OR 7in Baker City. | Pavement Improvement | 05/22/2009 | 06/08/2009 |  | 1485113.71 | 0
5425 | Oregon | STATEWIDE |  | V | S000493 | Improve mobility and safety at 277 intersections in the Portland Metropolitan reagion by installing 2070 signal controllers and updating signal control software at the intersections. | Other | 04/09/2009 | 04/09/2009 | 06/11/2009 | 397300 | 0
5426 | Oregon | STATEWIDE |  | V | S000497 | Improve mobility and safety at 277 intersections in the Portland Metropolitan reagion by installing 2070 signal controllers and updating signal control software at the intersections. | Other | 07/07/2009 |  |  | 2670766.52 | 0
5427 | Oregon | STATEWIDE |  | 4 | S000499 | Improves safety by replacing or retrofitting restrooms at rest areas in Western Oregon. | Other | 05/05/2009 | 05/05/2009 | 08/11/2009 | 20000 | 0
5428 | Oregon | LINN |  | V | S000502 | Enhance freight operations by repairing 7 miles of track in along the Albany & Eastern Rail Road rail line. | Other | 05/05/2009 | 05/05/2009 | 06/12/2009 | 30000 | 0
5429 | Oregon | CROOK |  | V | S000503 | Enhance freight operations by repairing unsafe track in Prineville. | Other | 05/06/2009 | 05/06/2009 |  | 20000 | 0
5430 | Oregon | LINN |  | V | S000504 | Improve safety at 7 rail road crossings and replace track on the Portland & Western Rail Road in Portland. | Other | 05/06/2009 | 05/06/2009 |  | 50000 | 0
5431 | Oregon | LANE |  | V | S000505 | Enhance freight operations by repairing unsafe track on the Coos Bay Rail Line in Coos Bay. | Other | 05/07/2009 | 05/07/2009 |  | 20000 | 0
5432 | Oregon | MORROW |  | V | S000506 | Enhance shipping by adding additional rail capacity at the Port of Morrow in Morrow County. | Other | 05/07/2009 | 05/07/2009 | 06/04/2009 | 30000 | 0
5433 | Oregon | MULTNOMAH | PORTLAND (WA) | V | S000507 | Enhance mobility with improved switching on the North Portland Junction crossovers in Portland. | Other | 05/18/2009 | 05/18/2009 | 06/16/2009 | 50000 | 0
5434 | Oregon | BAKER |  | 2 | S000513 | Improve safety for motorists and pedestrians by paving and adding curb and gutter to Birch Street in Baker City. | Other | 04/30/2009 | 04/30/2009 | 04/30/2009 | 60000 | 0
5435 | Oregon | STATEWIDE |  | 2 | S000522 | Improves safety by replacing or retrofitting restrooms at 6 rest areas in Eastern Oregon. Repave one rest area. | Other | 06/19/2009 | 06/19/2009 | 07/31/2009 | 20000 | 0
5436 | Oregon | DOUGLAS |  | 4 | S001233 | Improves pedestrian access and safety by extending fairground multi-use path in Roseburg. | Transportation Enhancements | 05/05/2008 | 06/03/2008 | 10/05/2009 | 434000 | 0
5437 | Oregon | DOUGLAS |  | 4 | S001329 | Improves safety on I5 between Booth Rand and Glendale in Douglas county by replacing poor pavement. | Pavement Improvement | 05/13/2009 | 06/04/2009 | 10/30/2009 | 7074682 | 0
5438 | Oregon | JACKSON |  | 2 | S001332 | Improve safety by replacing pavement worn down by chains, severe weather on 11 miles of I-5 in Ashland. | Pavement Improvement | 05/01/2009 | 05/11/2009 | 10/29/2009 | 2154263.69 | 7
5439 | Oregon | STATEWIDE |  | 4 | S001333 | Improve safety by replacing worn striping on I-5 between mile point 18 and 168. | Safety/Traffic Management | 04/23/2009 | 06/03/2009 | 09/24/2009 | 2248483.72 | 0
5440 | Oregon | MARION |  | 5 | S001338 | Reduce truck crash probability on I-5 in Marion County by replacing substandard barriers. | Safety/Traffic Management | 06/23/2009 | 10/15/2009 |  | 4518000.82 | 0
5441 | Oregon | WASHINGTON |  | 1 | S001339 | Pavement overlay of I-5 between Tualitin River Bridge and Willsonville Rd to improve traffic flow for vehicles merging on and off the freeway; added cable barrier to reduce risk of fatal crashes. | Pavement Improvement | 05/21/2009 | 06/08/2009 |  | 3675781.89 | 0
5442 | Oregon | JACKSON |  | 4 | S001361 | INSTALL WELCOME SIGN | Other | 11/09/2009 | 11/09/2009 |  | 10000 | 0
5443 | Oregon | STATEWIDE |  | V | S002079 | Repair and reconstruct access control fencing along I-84 between Sandy River and The Dalles to reduce weather/animal-related crashes. | Pavement Improvement | 06/02/2009 |  |  | 299999.61 | 0
5444 | Oregon | UMATILLA |  | 2 | S002109 | Builds rockfall screen along busy section of I-84 over Cabbage Hill to improve safety. | Safety/Traffic Management | 05/26/2009 | 08/24/2009 | 09/16/2009 | 206652.17 | 0
5445 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | S002110 | Enhances mobility by adding a right turn lane to I-84 exit at 257th in Troutdale. | Pavement Widening | 06/26/2009 | 08/10/2009 |  | 602567.5 | 0
5446 | Oregon | DESCHUTES |  | 2 | S004120 | Enhance safety on US 97 between Lava Butte and S Century Driver by adding lanes and access routes in Deschutes County. Improves safety by restoring fencing and crossing enhancements at the US 97 Lava | Pavement Improvement | 06/11/2009 | 06/22/2009 |  | 11736733.38 | 9.69
5447 | Oregon | WASCO |  | 2 | S004125 | Enhances bicycle and pedestrian safety by building sidewalks, curbs, and multi-use paths on US 197 between Burnham Ave and 3rd St in Maupin. | Transportation Enhancements | 01/27/2009 | 02/11/2009 |  | 800000 | 0
5448 | Oregon | WASCO |  | 2 | S004132 | Improve safety in extreme weather area by extending current pavement project on US 197 between The Dalles and Eight Mile Creek. | Pavement Improvement | 06/16/2009 | 07/31/2009 |  | 3150982 | 0
5449 | Oregon | KLAMATH |  | 2 | S004133 | Improve safety and mobility by adding a 2 mile passing lane to US 97 at mile point 230 in Klamath County. | Pavement Improvement | 06/04/2009 | 06/22/2009 |  | 5450893.73 | 3
5450 | Oregon | DESCHUTES |  | 2 | S004136 | Improves mobility and safety by installing an adaptive traffic signal control system at 19 intersections in Redmond. | Other | 03/13/2009 | 03/13/2009 | 06/18/2009 | 150000 | 0
5451 | Oregon | DESCHUTES |  | 2 | S004137 | Improves mobility and safety by installing an adaptive traffic signal control system at 19 intersections in Redmond. | Safety/Traffic Management | 07/13/2009 | 08/17/2009 |  | 1327816.22 | 0
5452 | Oregon | HARNEY |  | 2 | S007051 | Complete pavement preservation project on US 20 between Bulger Creek and Riley Junction in Hines. | Pavement Improvement | 05/20/2009 | 06/11/2009 |  | 7046699.91 | 31
5453 | Oregon | TILLAMOOK |  | 5 | S009317 | Repave US 101 between 12th St and Farmer Creek Rd in Tillamook to improve safety and reduce maintainance costs by preventing water permeation. | Pavement Improvement | 04/29/2009 |  |  | 5139997.26 | 0
5454 | Oregon | DOUGLAS |  | 4 | S009323 | Improves safety along US 101 and OR 38 between Reedsport and Winchester Bay by repaving poor highway and upgrading sidewalks. | Pavement Improvement | 03/23/2009 | 04/20/2009 | 08/24/2009 | 781361.49 | 4.12
5455 | Oregon | CURRY |  | 4 | S009337 | Paves poor section of US 101 between Bethel Cr and Crystal Cr in Coos County to improve safety. | Pavement Improvement | 05/13/2009 | 08/10/2009 | 11/12/2009 | 1967967.45 | 10
5456 | Oregon | DOUGLAS |  | 4 | S009338 | Improve safety on OR 38 and US 101 between Lane County and Gardner in douglas County by replacing poor pavement. | Pavement Improvement | 05/20/2009 | 05/23/2009 |  | 5428845.55 | 11.72
5457 | Oregon | JACKSON |  | 2 | S022031 | Improves safety and extends pavement life on OR 62 and OR 140 between Medford and White city by replacing worn out pavement. | Pavement Improvement | 06/08/2009 | 07/07/2009 |  | 9511292.59 | 25.7
5458 | Oregon | CLACKAMAS |  | 3 | S026066 | Improve safety and extend pavement life with paving on US 26 between the Salmon River Bridge and E Lolo Pass Road. | Safety/Traffic Management | 06/23/2008 | 07/21/2008 | 08/23/2009 | 200000 | 0
5459 | Oregon | POLK |  | 5 | S030017 | Enhances safety by paving roadway and repairing guardrail on OR 22 between OR 18 and OR 99W in Polk County. | Pavement Improvement | 06/03/2009 | 06/04/2009 |  | 5341543.22 | 0
5460 | Oregon | POLK |  | 5 | S030018 | Repaves bridge deck on OR 22 over Willamette River and paves older sections of OR 22 to increase safety in Polk County. | Pavement Improvement | 05/29/2009 | 08/20/2009 |  | 7199497.33 | 5.39
5461 | Oregon | LINCOLN |  | 5 | S033021 | Improve safety on US 20 between Pioneer Mountain and Eddyville in Lincoln County by improving alignment, widening shoulders and adding channelization at appropriate locaitons. | Pavement Widening | 07/05/2005 | 07/05/2005 |  | 4800526.6 | 0
5462 | Oregon | BENTON |  | 4 | S033031 | Install median landscaping on new section of US 20 / OR 34 between Newton Creek and Jade Place in Philomath. | Other | 06/05/2009 | 06/05/2009 | 11/12/2009 | 10000 | 0
5463 | Oregon | BENTON | CORVALLIS | 4 | S033034 | Design and Construct Median Landscaping | Transportation Enhancements | 12/11/2009 |  |  | 226817.44 | 0
5464 | Oregon | DOUGLAS |  | 4 | S045037 | Improve safety by paving OR 38 between Rock Cr and I-5 and OR 138 between Elkton and mile point 8 in Douglas County. | Pavement Improvement | 06/01/2009 | 06/12/2009 | 08/25/2009 | 4301032.58 | 0
5465 | Oregon | WASHINGTON |  | 1 | S047074 | Replaces pavement on the Sunset Highway (US 26) between North Plains and Cornell Road to fix severe rutting and reduce hydroplaning and installs cable barrier to improve safety. | Pavement Improvement | 03/16/2009 | 04/17/2009 |  | 1171732.52 | 9.8
5466 | Oregon | MORROW |  | 2 | S052018 | Improves roadway and pedestrian safety on OR 74 between Willow Creek Bridge and Morrow County fairgrounds in Heppner by repairing the bridge, adding bicycle and pedestrian facilities and repaving the | Safety/Traffic Management | 02/27/2009 | 03/11/2009 | 11/17/2009 | 1018000 | 0
5467 | Oregon | MULTNOMAH |  | 1 | S061009 | Replace existing concrete roadway on I-405 between the Freewont and Marquam bridges to reduces wear and tear on the roadway. Adds new lights and signs to improve safety on the same section of road. | Pavement Improvement | 05/18/2009 | 06/02/2009 |  | 3696873.14 | 0
5468 | Oregon | JACKSON |  | 4 | S063030 | Repair the 70-year-old culvert at the Bear Gulch Slide Drainage Tunnel in Jackson County to preserve road. | Other | 07/21/2009 | 08/13/2009 |  | 540425.38 | 0
5469 | Oregon | MULTNOMAH |  | 3 | S081014 | Pave detour streets to improve safety and reduce wear and tear while work is performed to replace the Martin Luther King Viaduct in Portland. | Pavement Improvement | 01/12/2007 | 02/27/2007 |  | 1250000 | 0
5470 | Oregon | POLK |  | 5 | S091037 | PRESERVE & REPAIR BIKE PATHS WITHIN HIGHWAY ROW | Other | 11/17/2009 | 11/17/2009 |  | 25000 | 0
5471 | Oregon | MULTNOMAH | PORTLAND (WA) | 1 | S092017 | Updates signage along US 30 in Portland to improve visibility and safety as part of the Yeon Street preservation project. | Other | 12/09/2008 | 12/09/2008 | 06/01/2009 | 40000 | 0
5472 | Oregon | MULTNOMAH |  | 1 | S092028 | Updates signage along US 30 in Portland to improve visibility and safety as part of the Yeon Street preservation project. | Pavement Improvement | 12/09/2008 | 02/03/2009 | 09/30/2009 | 160000 | 0
5473 | Oregon | COLUMBIA |  | 1 | S092029 | Enhance mobility and safety on US 30 in Scappoose with a new RR crossing, improved signalization and street widening. | Pavement Improvement | 07/23/2009 |  |  | 1153930.35 | 0
5474 | Oregon | COLUMBIA |  | 1 | S092030 | Enhance mobility and safety on US 30 in Scappoose with a new RR crossing, improved signalization and street widening. | Safety/Traffic Management | 06/23/2009 | 06/23/2009 | 06/23/2009 | 2000000 | 0
5475 | Oregon | COLUMBIA |  | 1 | S092031 | Enhance mobility and safety on US 30 in Scappoose with a new RR crossing, improved signalization and street widening. | Other | 06/23/2009 | 06/23/2009 | 06/23/2009 | 274500 | 0
5476 | Oregon | DOUGLAS |  | 4 | S138002 | Pavement preservation project to extend the life of existing pavement on OR 138 between mile point 4 and 18 and US 199 between mile point 20 and 41 in Douglas and Josephine Counties. | Pavement Improvement | 04/17/2009 | 06/29/2009 |  | 4261225.59 | 0
5477 | Oregon | CLACKAMAS |  | 5 | S160040 | Preserves roadway with new pavement and adds signing, signal loops and lighting on OR 213 between I-205 and Redland Rd in Clackamas County. | Pavement Improvement | 07/21/2008 | 08/20/2008 | 11/05/2009 | 2500000 | 0
5478 | Oregon | MARION |  | 5 | S162040 | Enhance safety by installing cable and concrete barriers on OR 22 between Lancaster Dr and Golf Club Rd in Marion County. | Safety/Traffic Management | 07/08/2009 | 07/22/2009 |  | 2025788.59 | 0
5479 | Oregon | LANE |  | 4 | S229010 | Complete pavement preservation project on OR 36 between OR 200 and OR 99W. | Pavement Improvement | 06/16/2009 | 07/30/2009 | 10/15/2009 | 1018931.86 | 0
5480 | Oregon | MALHEUR |  | 2 | S455016 | Complete pavement preservation projecton OR 201 between Weiser interchange and the Snake River (Payette Bridge). | Pavement Improvement | 06/04/2009 | 07/14/2009 |  | 6959443.39 | 0
5481 | Pennsylvania | CRAWFORD |  | 3 | Z011211 | This is a Safety and drainage improvement project involving pavement resurfacing, markings, guiderail upgrade on State Route 77 covering seven municipalities in Crawford County. | Pavement Improvement | 05/18/2009 | 06/22/2009 | 12/11/2009 | 2920000 | 11.378
5482 | Pennsylvania | CRAWFORD |  | 3 | Z011212 | This project located in the City of Meadville, Crawford County, updates and retrofits Curb Ramps and pedestrian signals for Pedestrian Safety and in compliance with ADA requirements. | Transportation Enhancements | 04/27/2009 | 05/18/2009 | 01/27/2010 | 850000 | 4.09
5483 | Pennsylvania | CRAWFORD |  | 3 | Z011213 | This project replaces the bridges and reconstructs the roadway approaches on State Routes 1020 and 3025 in Venango and Crawford Counties of District 1. | Bridge Improvement | 06/25/2009 | 07/30/2009 | 06/20/2010 | 825000 | 0.017
5484 | Pennsylvania | CRAWFORD |  | 3 | Z011214 | This is a Safety and roadway preservation project of about 5 miles of Interstate 79 in Crawford and Mercer Counties. The project involves concrete patching, milling and resurfacing of the roadway as w | Pavement Improvement | 08/03/2009 | 08/27/2009 | 07/07/2010 | 4300000 | 10.38
5485 | Pennsylvania | CRAWFORD |  | 3 | Z011216 | Multi-use trail North of the Borough of Spartansburg to the Borough of Centerville in Spartansburg & Centerville Boroughs, Sparta & Rome Townships. | Transportation Enhancements | 01/27/2010 |  | 07/30/2010 | 1124263 | 0
5486 | Pennsylvania | CRAWFORD |  | 3 | Z011217 | In Blooming Valley borough of Crawford County, this project will improve safety and drainage as well as extend the life of about 2 miles of Blooming Valley road by milling and resurfacing of the deter | Pavement Improvement | 10/07/2009 |  | 07/25/2010 | 1066173 | 1.636
5487 | Pennsylvania | ERIE |  | 3 | Z012356 | This is a Safety project to install durable Railroad Crossing markings on various state routes in District 1, and this covers the Counties of Crawford, Erie, Forest, Mercer, Venango and Warren. | Safety/Traffic Management | 04/27/2009 | 05/04/2009 | 12/25/2009 | 377037.44 | 0
5488 | Pennsylvania | ERIE |  | 3 | Z012357 | This project will extend the life of the bridges over Elk Creek and improve roadway approaches on State Route 98 in Fairview Township of Erie County. | Bridge Improvement | 05/04/2009 | 05/04/2009 | 10/15/2009 | 620221.97 | 0.043
5489 | Pennsylvania | ERIE |  | 3 | Z012358 | This milling and resurfacing project will extend the life of the existing roadway, State Route 20 in Springfield, Millcreek and Girard Townships of Erie County; and upgrade Curb ramps to comply with A | Pavement Improvement | 06/29/2009 | 06/29/2009 | 01/17/2010 | 4375000 | 20.049
5490 | Pennsylvania | ERIE |  | 3 | Z012359 | The project extends the life of the pavement on State Route 8 in Venango and Millcreek Townships of the City of Erie, Erie County. It involves pavement resurfacing and markings, guiderail improvements | Pavement Improvement | 06/16/2009 | 06/23/2009 | 11/05/2009 | 1240090.49 | 4.623
5491 | Pennsylvania | ERIE | ERIE | 3 | Z012360 | This project replaces the bridges over Six Mile Creek and Seven Mile Creek on State Route 955 in Harborcreek Township of Erie County. The project will also include drainage and guiderail upgrades as w | Bridge Replacement | 07/06/2009 | 07/06/2009 | 02/14/2011 | 2144238 | 0.52
5492 | Pennsylvania | ERIE |  | 3 | Z012361 | This project in the City of Erie, Erie County, improves Pedestrian Safety through the construction of sidewalks, installation of curb ramps, lightings, and signals improvements on City Street and Para | Transportation Enhancements | 08/25/2009 | 08/25/2009 | 07/27/2010 | 800000 | 0
5493 | Pennsylvania | ERIE | ERIE | 3 | Z012363 | This project, located in the City of Erie, Erie County, will update and retrofit Curb Ramps and pedestrian signals for Pedestrian Safety and in compliance with ADA requirements. | Transportation Enhancements | 06/01/2009 | 06/01/2009 | 06/05/2010 | 1609000 | 33.017
5494 | Pennsylvania | ERIE |  | 3 | Z012364 | This project will preserve the pavement and prevent skidding on 10 miles of Interstate 79 covering Franklin, McKean and Summit Townships in Erie County. It will involve the use of friction-resistant p | Pavement Improvement | 07/22/2009 | 08/17/2009 | 08/21/2010 | 5920000 | 21.111
5495 | Pennsylvania | ERIE | ERIE | 3 | Z012371 | This Erie County project extends the life of the pavement and improves Safety and drainage on 1.5 miles of State Route 290 (the Bayfront Connector); and this involves pavement resurfacing, guiderail a | Pavement Improvement | 10/14/2009 |  | 07/15/2010 | 553076 | 0.768
5496 | Pennsylvania | ERIE | ERIE | 3 | Z012372 | This project will preserve the pavement and improve drainage on PA 5 (Lake road) in Harborcreek and Lawrence Townships of Erie County. It involves pavement resurfacing and other miscellaneous work. | Pavement Improvement | 10/08/2009 |  | 06/16/2010 | 798000 | 3.051
5497 | Pennsylvania | ERIE | ERIE | 3 | Z012373 | This project in the City of Erie, Erie County, improves Pedestrian Safety through the construction of sidewalks, installation of curb ramps, lightings, and landscaping on State Street between Bayfront | Transportation Enhancements | 10/23/2009 | 10/23/2009 | 10/29/2010 | 900000 | 0
5498 | Pennsylvania | ERIE |  | 3 | Z012386 | Replacement of the bridge carrying Concord Road (SR 2010) over Pine Run in Union Township. | Bridge Replacement | 01/27/2010 |  | 02/17/2011 | 860000 | 0.365
5499 | Pennsylvania | FOREST |  | 5 | Z013119 | This project will restore State route 66 in Jenks Township of Forest County; and it involves pavement resurfacing and guiderail safety upgrades. | Pavement Improvement | 06/08/2009 | 07/13/2009 | 11/12/2009 | 917920.42 | 4.292
5500 | Pennsylvania | FOREST |  | 5 | Z013122 | Patch, level and overlay, guiderail updates and shoulder construction on State Route 666 from Kelletville east one mile towards Mayburg in Kingley Township (Approved Federal Lands Highway Program Proj | Pavement Improvement | 10/06/2009 |  | 07/04/2010 | 28832 | 1.398
5501 | Pennsylvania | MERCER | YOUNGSTOWN | 3 | Z014231 | This project will extend the life of the pavement and improve pedestrian Safety on State Routes 18, 2005 and 4019 in Greenville Borough, Pine Hempfield, Sugar Grove and Salem Townships of Mercer Coun | Pavement Improvement | 06/24/2009 | 06/29/2009 | 10/21/2009 | 1602000 | 4.116
5502 | Pennsylvania | MERCER |  | 3 | Z014232 | This project will restore and preserve various State Routes including 62, 19, 58, 1028 located in various Townships and Boroughs in Mercer County; it involves milling and overlays as well as guiderail | Pavement Improvement | 06/29/2009 | 06/29/2009 | 12/03/2009 | 2144664.79 | 13.347
5503 | Pennsylvania | MERCER | YOUNGSTOWN | 3, 4 | Z014233 | This project on State Route 3011 (Keel Ridge Road) in Shenango Township and City of Hermitage of Mercer County, will preserve the pavement and improve Safety; it involves pavement repairs and overlays | Pavement Improvement | 06/24/2009 | 07/06/2009 | 04/15/2010 | 950000 | 6.547
5504 | Pennsylvania | MERCER | YOUNGSTOWN | 3, 4 | Z014235 | This project will extend the life of pavement on 17 miles of Interstate 80 in Shenango, Lackawannock and East Lackawannock Townships of Mercer County; it involves pavement patching and overlay, guide | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/20/2010 | 1450000 | 31.068
5505 | Pennsylvania | MERCER |  | 3 | Z014240 | This project will restore the deteriorating portion of US Route 62 in CoolSpring and Jackson Townships and Jackson Center Borough of Mercer County; it involves pavement and bridge repairs, overlay, | Pavement Improvement | 07/20/2009 | 08/17/2009 | 10/28/2009 | 2028683 | 5.141
5506 | Pennsylvania | MERCER |  | 1 | Z014243 | Replace the bridge carrying Baker Hill Road (SR 4024) over Lenango Creek in Delaware Township | Bridge Replacement | 01/19/2010 |  | 11/28/2010 | 858751 | 0
5507 | Pennsylvania | MERCER | YOUNGSTOWN | 3 | Z014247 | This project on State Route 3020 (Lamar Road) in the City of Hermitage of Mercer County, will improve safety and mobility through roadway widening, guiderail and drainage upgrades. | Pavement Widening | 12/04/2009 |  | 07/11/2010 | 700000 | 0.549
5508 | Pennsylvania | MERCER |  | 3, 5 | Z014248 | This project will extend the life of the pavement and improve drainage on approximately 1.15 miles of State Route 322 (28th Division Highway) in French Creek Township of Mercer County; it involves pav | Pavement Improvement | 09/21/2009 |  | 06/06/2010 | 428649 | 1.147
5509 | Pennsylvania | VENANGO |  | 5 | Z015189 | This project will extend the life of the pavement on US Route 62 in the City of Franklin, French Creek and Sandy Creek Townships of Venango County; it also involves improvements to drainage and guide | Pavement Improvement | 05/11/2009 | 07/25/2009 | 11/10/2009 | 1330276.28 | 6.74
5510 | Pennsylvania | VENANGO |  | 5 | Z015190 | This project will replace two bridges over Prathers Run and Little Sugar Creek on State Route 428 in Oakland Township of Venango County; it also includes improvements to the approach roadways and drai | Bridge Replacement | 06/24/2009 | 07/06/2009 | 02/25/2011 | 1797589 | 0.021
5511 | Pennsylvania | VENANGO |  | 5 | Z015193 | This project will stabilize and preserve pavement on State Route 8 Bypass in the City of Oil City of Venango County; it involves construction of a retaining wall; it also involves guiderail and draina | Other | 08/11/2009 | 10/12/2009 | 09/01/2010 | 2992748 | 0.782
5512 | Pennsylvania | WARREN |  | 5 | Z016177 | This project will preserve about 2.5 miles of pavement on State Route 3005 covering various Townships in Warren County; it involves pavement repairs and overlay as well as improvements to guiderail an | Pavement Improvement | 05/04/2009 | 06/11/2009 | 10/13/2009 | 599631.19 | 2.451
5513 | Pennsylvania | WARREN |  | 5 | Z016178 | This project will replace the bridge over Six Mile Creek on State Route 6 (Grand Army Highway) in Mead Township of Warren County. | Bridge Replacement | 08/25/2009 |  | 08/04/2011 | 1715000 | 0.008
5514 | Pennsylvania | WARREN |  | 5 | Z016185 | Slide correction work on the Warren Bypass (US 6) left side mechanically stabilized earth wall in Mead Township | Pavement Improvement | 01/27/2010 |  | 07/09/2010 | 500000 | 0.306
5515 | Pennsylvania | CENTRE |  | 5 | Z021241 | This project will improve safety and mobility on State Route 26, in Pleasant Gap of Center County. This is an alternate emergency Route to terstate 80. The work involves widening, resurfacing, guider | Pavement Improvement | 04/08/2009 | 06/17/2009 | 11/19/2009 | 3400000 | 6.372
5516 | Pennsylvania | CENTRE |  | 5 | Z021253 | This project will replace the existing bridge over Marsh Creek on State Route 1001 in Curtin Township of Center County; it also involves drainage and guiderail upgrades. | Bridge Replacement | 04/27/2009 | 05/18/2009 | 02/04/2010 | 1200000 | 0.778
5517 | Pennsylvania | CENTRE | STATE COLLEGE | 5 | Z021254 | This project will extend the life of bridges on State Route 322 including bridges in College and Harris Townships of Center County. The bridges will be painted for protection from rusts and other dete | Bridge Improvement | 06/01/2009 | 07/06/2009 | 01/18/2010 | 975000 | 0.585
5518 | Pennsylvania | CENTRE |  | 5 | Z021255 | This project will replace the bridge over the Tributary to Penns Creek on State Route 2014 in Gregg Township of Center County; it also involves guiderail and drainage upgrades. | Bridge Replacement | 05/18/2009 | 06/15/2009 | 11/24/2009 | 515000 | 0.496
5519 | Pennsylvania | CENTRE |  | 5, 9 | Z021259 | This project extends the life of 5.59 miles of pavement on State Route 3040 (Old SR 220) covering Taylor and Worth Townships in Center County; it also involves roadway resurfacing, guiderail and drain | Pavement Improvement | 09/08/2009 |  | 11/07/2010 | 1835000 | 5.611
5520 | Pennsylvania | CLEARFIELD |  | 5 | Z022246 | This project will improve the existing roadway, on State Route 219 in Brady, Union and Bloom Townships of Clearfield County, for longevity and Safety; it involves resurfacing, bridge deck repairs, min | Pavement Improvement | 04/20/2009 | 04/20/2009 | 03/08/2010 | 2825000 | 3.077
5521 | Pennsylvania | CLEARFIELD |  | 5 | Z022249 | This project is for roadway preservation and Safety on State Route 970 in Bradford and Goshen Townships of Clearfield County; it involves pavement widening and resurfacing, guiderail and drainage upgr | Pavement Improvement | 06/23/2009 | 06/23/2009 | 12/18/2009 | 4200000 | 5.122
5522 | Pennsylvania | CLEARFIELD |  | 5 | Z022252 | This project will preserve six bridges at various locations in various municipalities grouped together as GROUP-2-09-R04 in Cameron, Clearfield, McKean and Potter Counties; it involves bridge deck rep | Bridge Improvement | 07/27/2009 | 08/03/2009 | 08/08/2011 | 4450000 | 2.649
5523 | Pennsylvania | CLEARFIELD |  | 5, 9 | Z022253 | This project will preserve seven bridges at various locations in various municipalities grouped together as GROUP-2-09-R05 in Clearfield and Potter Counties; it involves bridge deck repairs, steel pai | Bridge Improvement | 07/31/2009 | 09/01/2009 | 12/09/2010 | 2489218 | 1.423
5524 | Pennsylvania | CLINTON |  | 5 | Z023177 | The project will construct a new asphalt riding surface on Lock Haven Bypass from Salona to Avis in Pine Creek, Wayne, Castenea, Bald Eagle and Lamar Townships | Pavement Improvement | 06/15/2009 | 06/22/2009 | 08/15/2010 | 7425000 | 28.174
5525 | Pennsylvania | CLINTON |  | 5, 10 | Z023178 | This project is for the preservation of 24 miles of roadway and associated bridges on Interstate 80 in Greene, Lamar and Porter Townships of Clinton and Union Counties; it involves concrete and bridge | Pavement Improvement | 09/10/2009 | 09/28/2009 | 11/20/2010 | 15301066 | 95.906
5526 | Pennsylvania | CAMERON |  | 5 | Z024116 | Bridge Replacement on SR 0555 (Low Grade Road), over Hicks Run, north of Run road in Gibson Township Cameron County. | Bridge Replacement | 01/27/2010 |  | 12/05/2010 | 1270703 | 0.17
5527 | Pennsylvania | MCKEAN |  | 5 | Z025185 | This project will extend pavement life and improve Safety on US Route 219 in Bradford Township of Mckean County; it involves roadway repairs and resurfacing, drainage and guiderail upgrades. | Pavement Improvement | 07/23/2009 | 09/11/2009 | 10/03/2010 | 3250000 | 3.503
5528 | Pennsylvania | MCKEAN |  | 5 | Z025187 | This project will replace the bridge over Janders Run on State 44 in Ceres Township of McKean County; it also involves guiderail and drainage upgrades. | Bridge Replacement | 11/06/2009 |  | 07/09/2010 | 850000 | 0.005
5529 | Pennsylvania | POTTER |  | 5 | Z026154 | This project will restore the deteriorating portion of US Route 6 in Coudersport Borough and Eulalia Township in Potter County; it involves pavement, sidewalk and bridge repairs, overlay, guiderail | Pavement Improvement | 04/13/2009 | 04/14/2009 | 01/25/2010 | 2406000 | 1.688
5530 | Pennsylvania | POTTER |  | 5 | Z026161 | Highway Restoration on SR 0006 (Second Street), east of SR 0144 (Main Street), Coudersport Borough and Eulalia Township, Potter County. | Pavement Improvement | 01/25/2010 |  | 10/30/2010 | 2154460 | 2.049
5531 | Pennsylvania | MIFFLIN |  | 5 | Z027151 | This project will preserve 1.5 miles of pavement on State Route 1005 (Electric Avenue) in Derry Township and Burnham Borough of Mifflin County; it involves milling and resurfacing of roadway, guiderai | Pavement Improvement | 11/30/2009 |  | 09/25/2010 | 1383935 | 1.274
5532 | Pennsylvania | ELK |  | 5 | Z028158 | This project will extend the life of 5 miles of pavement on State Route 219 in Johnsonburg Borough, Ridgeway and Jones Townships in Elk County; it involves pavement repairs and resurfacing as well as | Bridge Replacement | 09/14/2009 | 10/08/2009 | 09/17/2010 | 975000 | 5.166
5533 | Pennsylvania | JUNIATA |  | 9 | Z029135 | This project will extend the life of bridge over Juniata River on State Route 75 in the Borough of Port Royal and Walker Township in Juniata County; it involves deck and steel repairs, bridge paintin | Bridge Improvement | 06/22/2009 | 06/22/2009 | 08/27/2010 | 4600000 | 0.246
5534 | Pennsylvania | COLUMBIA |  | 5, 9, 10, 11 | Z031209 | The project will replace deteriorated, outdated, and substandard major guide signs and install additional major guide signs on various highways in Lycoming County to improve visibility and legibility | Safety/Traffic Management | 06/10/2009 | 07/23/2009 | 11/29/2009 | 187153 | 538.206
5535 | Pennsylvania | COLUMBIA |  | 11 | Z031211 | Rehabilitation of State Route 42 over Roaring Creek in Catawissa and Locust Townships | Bridge Improvement | 07/10/2009 |  | 12/24/2010 | 843343 | 0
5536 | Pennsylvania | COLUMBIA |  | 11 | Z031212 | Rehabilitation of State Route 2001 over Tributary of Roaring Creek in Locust Township | Bridge Improvement | 07/10/2009 |  | 12/24/2010 | 419250 | 0
5537 | Pennsylvania | COLUMBIA |  | 11 | Z031213 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck of the State Route 42 bridge over State Route 11 at Bloomsburg in Montour Township in Col | Bridge Improvement | 09/04/2009 |  | 10/03/2010 | 1365490 | 0.074
5538 | Pennsylvania | LYCOMING |  | 5, 10 | Z032285 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 05/18/2009 | 08/03/2009 | 07/18/2010 | 1008000 | 0.791
5539 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5, 10 | Z032286 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 15 from Beauty's Run to Trout Run in Lewis, Old Lycoming, and Lycoming | Pavement Improvement | 05/18/2009 | 07/27/2009 | 06/13/2010 | 2393457 | 7.488
5540 | Pennsylvania | LYCOMING |  | 10 | Z032287 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 220 from Lycoming County Line to Muncy Valley in Davidson Township, Sul | Pavement Improvement | 06/01/2009 | 06/29/2009 | 12/13/2009 | 672781 | 1.696
5541 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5 | Z032288 | This project will overlay the existing deteriorating pavement with new asphalt pavement on State Route 2014 from Montour Street to Fairfield Road in Montoursville Borough in Lycoming County. | Pavement Improvement | 06/01/2009 | 06/29/2009 | 12/09/2009 | 528498 | 1.89
5542 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5 | Z032290 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the US Route 220 bridge over Pine Run in Woodward Township | Pavement Improvement | 07/06/2009 | 03/29/2010 | 10/02/2010 | 655024 | 0.076
5543 | Pennsylvania | LYCOMING |  | 10 | Z032291 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the State Route 2085 bridge over Muncy Creek in Penn Towns | Bridge Improvement | 09/02/2009 |  | 09/22/2010 | 650000 | 0.095
5544 | Pennsylvania | LYCOMING |  | 10 | Z032292 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the State Route 2048 bridge over Little Muncy Creek in Mun | Bridge Improvement | 08/21/2009 |  | 11/07/2010 | 800000 | 0.024
5545 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5 | Z032298 | Mill and resurface SR 3028 from Thomas to Main Street in Jersey Shore Borough and Porter Township | Pavement Improvement | 10/05/2009 |  | 08/08/2010 | 549136 | 0
5546 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5 | Z032300 | This project will make the road smoother by removing several inches of deteriorating pavement and replacing it with asphalt on SR 3028 from Thomas to Main Street in Jersey Shore Borough and Porter Tow | Pavement Improvement | 10/05/2009 |  | 08/08/2010 | 235000 | 1.099
5547 | Pennsylvania | LYCOMING |  | 10 | Z032308 | Microsurface PA 14 from Red Burn Road in McIntyre Township to Tioga County line | Pavement Improvement | 02/01/2010 |  | 08/08/2010 | 900842 | 14.081
5548 | Pennsylvania | MONTOUR |  | 10, 11 | Z033128 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on Interstate 80 Eastbound from West of Grey Hill Road to Old US Route 15 in White | Pavement Improvement | 05/28/2009 | 06/25/2009 | 10/21/2009 | 158143.87 | 4.609
5549 | Pennsylvania | MONTOUR |  | 10 | Z033129 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 54 from State Route 44 to State Route 254 in Anthony, Derry, Limesto | Pavement Improvement | 06/22/2009 | 08/17/2009 | 02/23/2010 | 1663941 | 4.665
5550 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034190 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 54 from State Route 2024 to Natalie in Coal, Mt. Carmel and Ralpho T | Pavement Improvement | 06/19/2009 | 06/25/2009 | 02/16/2010 | 1707618 | 4.399
5551 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034191 | Resurfacing of State Route 54 from State Route 2024 to Natalie in Coal, Mt. Carmel and Ralpho Townships | Pavement Improvement | 06/19/2009 | 06/25/2009 | 02/16/2010 | 932709 | 0
5552 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034192 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 05/13/2009 | 06/01/2009 | 10/20/2009 | 514248 | 1.067
5553 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034193 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck on the State Route 4009 bridge over Shamokin Creek in Upper Augusta Township in Northumbe | Bridge Improvement | 06/02/2009 | 06/15/2009 | 01/25/2010 | 1028213 | 0.158
5554 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034194 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the Interstate 180 bridge over State Route 44 in Delaware | Bridge Improvement | 08/07/2009 | 04/05/2010 | 12/12/2010 | 3191614 | 0.124
5555 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034197 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on Snydertown Road from Zimmermans Hollow Road to PA 487 in Northumberland County. | Pavement Improvement | 10/26/2009 | 10/26/2009 | 09/26/2010 | 2070789 | 8.287
5556 | Pennsylvania | SNYDER |  | 10 | Z035131 | Resurfacing of State Route 235 from Snyder/Union County Line to Breinnger Run in Adams Township | Pavement Improvement | 06/05/2009 | 06/08/2009 | 02/11/2010 | 957900 | 0
5557 | Pennsylvania | SNYDER |  | 10 | Z035132 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the State Route 35 bridge over Tributary to Middle Creek i | Bridge Improvement | 07/10/2009 |  | 12/24/2010 | 1300807 | 0.076
5558 | Pennsylvania | SNYDER |  | 10 | Z035133 | This project will remove the existing deteriorating bridge and replace it with a new bridge on State Route 3009 over Middle Creek in Franklin Township in Snyder County. | Bridge Replacement | 08/19/2009 | 09/14/2009 | 12/19/2010 | 2150357 | 0.104
5559 | Pennsylvania | SULLIVAN |  | 10 | Z036129 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 220 from Ringdale to Dushore in Cherry and Laporte Townships in Sulliva | Pavement Improvement | 06/01/2009 | 09/01/2009 | 01/28/2010 | 1176000 | 4.689
5560 | Pennsylvania | SULLIVAN |  | 10 | Z036130 | Resurfacing of US Route 220 from Lycoming County Line to Muncy Valley in Davidson Township | Pavement Improvement | 06/01/2009 | 06/29/2009 | 12/13/2009 | 852727 | 0
5561 | Pennsylvania | SULLIVAN |  | 5, 10 | Z036131 | This project will upgrade the old metal guardrail to meet new design standards at various locations in Lycoming County | Safety/Traffic Management | 06/22/2009 | 06/22/2009 | 02/17/2010 | 689551 | 36.631
5562 | Pennsylvania | TIOGA |  | 5 | Z037222 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 04/02/2009 | 05/27/2009 | 09/10/2009 | 344583 | 0.288
5563 | Pennsylvania | TIOGA |  | 5 | Z037223 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 287 from Wilson Creek to Shumway Hill Road in Delmar Township, Tioga | Pavement Improvement | 05/15/2009 | 05/25/2009 | 09/20/2009 | 1651035 | 4.65
5564 | Pennsylvania | TIOGA |  | 5 | Z037224 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 15 from State Route 287 to Tioga River in Lawrence, Tioga Townships and | Pavement Improvement | 05/15/2009 | 05/18/2009 | 01/05/2010 | 1952894 | 4.839
5565 | Pennsylvania | TIOGA |  | 5 | Z037225 | This project will remove the existing deteriorating bridge and replace it with a new bridge on State Route 414 bridge over Zimmerman's Creek in Liberty Township, Tioga County. | Bridge Replacement | 06/29/2009 | 04/05/2010 | 08/29/2010 | 1062834 | 0.082
5566 | Pennsylvania | TIOGA |  | 5 | Z037226 | Preservation of State Route 2005 bridge over Blockhouse Creek in Liberty Township | Bridge Improvement | 06/29/2009 | 04/05/2010 | 08/29/2010 | 24960 | 0
5567 | Pennsylvania | TIOGA |  | 5 | Z037233 | Mill and resurface of US 15 southbound from US 6 to the Welcome Center in Mansfield Borough, and Tioga and Richmond Townships | Pavement Improvement | 01/29/2010 |  | 09/05/2015 | 1978116 | 7.797
5568 | Pennsylvania | UNION |  | 10 | Z038150 | Resurfacing on Interstate 80 Eastbound from West of Grey Hill Road to Old US Route 15 in White Deer Township | Pavement Improvement | 05/28/2009 | 06/25/2009 | 10/21/2009 | 114468.93 | 0
5569 | Pennsylvania | UNION |  | 10 | Z038151 | Resurfacing on Interstate 80 Westbound from old US Route 15 to White Deer Pike in White Deer Township | Pavement Improvement | 05/28/2009 | 06/25/2009 | 10/21/2009 | 114619.5 | 0
5570 | Pennsylvania | UNION |  | 10 | Z038152 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 235 from Snyder/Union County Line to Breinnger Run in Adams Township | Pavement Improvement | 06/05/2009 | 06/08/2009 | 02/11/2010 | 990129 | 5.299
5571 | Pennsylvania | UNION |  | 10 | Z038153 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 08/27/2009 | 03/29/2010 | 10/03/2010 | 1326000 | 0.05
5572 | Pennsylvania | BRADFORD |  | 5, 10 | Z039194 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 06/25/2009 | 03/29/2010 | 10/03/2010 | 1716714 | 0.258
5573 | Pennsylvania | BRADFORD |  | 10 | Z039195 | This project will preserve the concrete deck by removing the top layer of concrete and replacing or patching it with a latex-modified concrete and add an epoxy overlay on the State Route 187 bridge ov | Bridge Improvement | 07/21/2009 | 08/03/2009 | 07/25/2010 | 1025483 | 0.189
5574 | Pennsylvania | BRADFORD |  | 10 | Z039196 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the US Route 6 bridge over Sugar Creek in Sylvania Borough | Bridge Improvement | 07/29/2009 | 04/05/2010 | 12/05/2010 | 990000 | 0.196
5575 | Pennsylvania | BRADFORD |  | 10 | Z039197 | Rehabilitation of State Route 187 over Bullard Creek in Rome Borough and Township | Bridge Improvement | 07/29/2009 | 04/05/2010 | 12/05/2010 | 801000 | 0
5576 | Pennsylvania | BRADFORD |  | 10 | Z039198 | Rehabilitation of State Route 1055 over Parks Creek in Rome Township | Bridge Improvement | 07/29/2009 | 04/05/2010 | 12/05/2010 | 530450 | 0
5577 | Pennsylvania | BRADFORD |  | 10 | Z039202 | This project will preserve the deteriorating steel beams by painting the bridges on PA 187 over Susquehanna River in Asylum and Wysox Townships, in Bradford County. | Bridge Improvement | 10/02/2009 |  | 10/31/2010 | 1000000 | 0.189
5578 | Pennsylvania | LACKAWANNA | SCRANTON--WILKES-BARRE | 11 | Z042405 | This project in Lackawanna County will resurface a heavily travelled local road to improve ride quality and extend the life of the pavement. | Pavement Improvement | 09/23/2009 |  | 06/26/2010 | 1163452 | 1.795
5579 | Pennsylvania | LUZERNE | SCRANTON--WILKES-BARRE | 11 | Z043387 | This project in Luzerne County is construction of a new Cleveland Street Bridge over Mill Creek in Plains Township to replace one that had been closed to traffic. | Bridge Replacement | 06/04/2009 | 06/04/2009 | 09/12/2010 | 1636000 | 0
5580 | Pennsylvania | LUZERNE | SCRANTON--WILKES-BARRE | 11 | Z043407 | This project in Luzerne County will extend the life of the State Route 29 Bridges over the Susquehanna River and over State Route 2002 by repairing deteriorated steel, replacing the deteriorated decks | Bridge Improvement | 08/03/2009 | 08/10/2009 | 11/10/2011 | 21925548 | 0.563
5581 | Pennsylvania | LUZERNE |  | 10, 11 | Z043408 | This project in Luzerne County will extend the life of the State Route 4001 bridge over Branch of Hunlock Creek and State Route 4016 bridge over Marsh Creek by repairing deteriorated steel, replacing | Bridge Improvement | 06/03/2009 | 07/13/2009 | 10/23/2010 | 1029000 | 1.001
5582 | Pennsylvania | LUZERNE |  | 11 | Z043411 | This 11.5 mile-long project in Luzerne County will mill and resurface a heavily travelled Interstate Highway to improve ride quality and extend the life of the pavement on both the northbound and sou | Pavement Improvement | 07/09/2009 | 07/09/2009 | 12/24/2009 | 3200000 | 10.694
5583 | Pennsylvania | LUZERNE |  | 11 | Z043412 | This 28 mile-long project will mill and resurface a heavily travelled Interstate Highway to improve ride quality and extend the life of the pavement on both the northbound and southbound lanes includi | Pavement Improvement | 06/30/2009 | 07/22/2009 | 02/05/2010 | 8631968 | 43.866
5584 | Pennsylvania | LUZERNE |  | 11 | Z043415 | This project in Luzerne and Lackawanna Counties will resurface a number heavily travelled highways (SR 924, 11, 3033, 3027, 347, 315) to improve ride quality and extend the life of the pavement. Inclu | Pavement Improvement | 07/17/2009 | 08/03/2009 | 07/04/2010 | 6300000 | 16.095
5585 | Pennsylvania | PIKE |  | 10 | Z044172 | This 5 mile long project in Pike and Wayne Counties will improve safety for bicyclists utilizing US Route 6 by widening the shoulders, placing new bituminous pavement, painting new pavement markings a | Transportation Enhancements | 06/01/2009 | 06/01/2009 | 05/21/2010 | 2240000 | 13.502
5586 | Pennsylvania | PIKE |  | 10 | Z044180 | This 2.8 mile-long project in Blooming Grove Township, Pike County, will resurface a heavily travelled highway to improve ride quality and extend the life of the pavement. Included in this project ar | Pavement Improvement | 07/08/2009 | 07/08/2009 | 12/08/2009 | 591000 | 3.338
5587 | Pennsylvania | PIKE |  | 10 | Z044181 | This 28 mile-long project will mill and resurface a heavily travelled Interstate 84 highway in Pike County to improve ride quality and extend the life of the pavement on the eastbound lanes includin | Pavement Improvement | 08/17/2009 | 07/22/2009 | 06/20/2010 | 7535000 | 57.18
5588 | Pennsylvania | PIKE |  | 10 | Z044184 | This project in Pike County will extend the life of the US Route 6 bridge over the Delaware River by repairing deteriorated steel, replacing the deteriorated deck with a new concrete deck, and repairi | Bridge Improvement | 10/21/2009 | 10/21/2009 | 11/25/2010 | 2727280 | 0.125
5589 | Pennsylvania | PIKE |  | 10 | Z044185 | This 5 mile-long project in Pike County will resurface a heavily travelled highway to improve ride quality and extend the life of the pavement. Included in this project are edge repairs, resurfacing | Pavement Improvement | 09/08/2009 | 09/08/2009 | 03/03/2010 | 1122000 | 4.959
5590 | Pennsylvania | PIKE |  | 10 | Z044191 | Replace the bridge carrying Twin Lakes Road (SR 1005) over Shohola Creek in Shohola Township | Bridge Replacement | 01/04/2010 | 01/04/2010 | 10/14/2010 | 897035 | 0.028
5591 | Pennsylvania | PIKE |  | 10 | Z044192 | Replace the bridge carrying Twin Lakes Road (SR 1005) over Shohola Creek in Shohola Township | Bridge Replacement | 01/04/2010 | 01/04/2010 | 10/14/2010 | 996906 | 0
5592 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045231 | This 0.5 mile long project in Susquehanna County will repair a section of roadway embankment on State Route 267 in Coconut Township damaged by numerous storms between 2006 and 2009. Repairs will inclu | Pavement Improvement | 05/27/2009 | 06/11/2009 | 12/30/2009 | 514000 | 0.294
5593 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045244 | This project in Susquehanna County will extend the life of the bridge on State Route 2040 over the Lackawanna River by installing new prestressed concrete beams, a new concrete deck, and replacing the | Bridge Improvement | 08/06/2009 | 08/24/2009 | 12/12/2010 | 1243000 | 0.038
5594 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045245 | This 16 mile long project will resurface two heavily travelled highways, SR 11 and SR 2023 in Susquehanna County, to improve ride quality and extend the life of the pavement. Included in this project | Pavement Improvement | 06/22/2009 | 07/13/2009 | 12/30/2009 | 670000 | 6.398
5595 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045246 | Resurfacing on various State Routes in Susquehanna County | Pavement Improvement | 06/22/2009 | 07/13/2009 | 12/30/2009 | 1715000 | 0
5596 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045249 | This 4 mile long project in Susquehanna County will resurface a local highway, SR 4002 (Laurel Lake Road) to improve ride quality and extend the life of the pavement. Included in this project are edg | Pavement Improvement | 09/14/2009 | 10/08/2009 | 02/07/2010 | 725000 | 4.231
5597 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045251 | Replace the bridge carrying Graham Road (SR 3033) over Wyalusing Creek in Rush Township | Bridge Replacement | 01/08/2010 |  | 12/01/2010 | 900000 | 0.016
5598 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045252 | Replace the bridge carrying Graham Road (SR 3033) over Wyalusing Creek in Rush Township | Bridge Replacement | 01/08/2010 |  | 12/01/2010 | 257029 | 0
5599 | Pennsylvania | WAYNE |  | 10 | Z046215 | This project will extend the lives of the SR 3037 Bridge over Middle Creek in Cherry Ridge Township, Wayne County, and the SR 2005 Bridge over Roaring Brook in Moscow, Lackawanna County. On 3037, the | Bridge Improvement | 04/20/2009 | 04/20/2009 | 11/29/2009 | 890000 | 0.495
5600 | Pennsylvania | WAYNE |  | 10 | Z046217 | This project in Wayne County will extend the life of the State Route 3006 Ledgedale Road bridge over Ariel Creek by replacing the deteriorated superstructure with a new concrete superstructure. | Bridge Improvement | 06/22/2009 | 06/22/2009 | 06/16/2010 | 578000 | 0.409
5601 | Pennsylvania | WAYNE |  | 10 | Z046218 | This State Route 4031 bridge over Johnson Creek, painting project in Wayne County will include containment and disposal of hazardous material and painting the steel beams to extend the life of the bri | Bridge Improvement | 06/08/2009 | 07/13/2009 | 12/17/2009 | 115000 | 0.428
5602 | Pennsylvania | WYOMING |  | 10 | Z047189 | This project will extend the lives of the SR 29 Bridge in Laceyville Borough and the SR 3001 Bridge in Eaton Township, Wyoming County. On SR 29, the project will repair the deteriorated deck, constru | Bridge Improvement | 07/07/2009 | 07/07/2009 | 12/05/2010 | 3840000 | 1.569
5603 | Pennsylvania | BERKS | READING | 6 | Z051239 | This project will make the road smoother by removing several inches of deteriorating pavement, patching the concrete, and replacing it with new pavement surface on SR 3222 from PA 724 (Philadelphia Av | Pavement Improvement | 10/22/2009 |  | 11/30/2010 | 2488198 | 3.776
5604 | Pennsylvania | BERKS | READING | 6, 17 | Z051240 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 2005 - 5th Street in the City of Reading, Berks County. | Pavement Improvement | 06/03/2009 | 10/13/2009 | 11/30/2010 | 3597652 | 3.789
5605 | Pennsylvania | BERKS | READING | 6, 16, 17 | Z051241 | The project will paint the steel beams on 11 bridges in various locations in Berks County | Bridge Improvement | 05/14/2009 | 05/14/2009 | 11/30/2010 | 5314150 | 2.991
5606 | Pennsylvania | BERKS | READING | 6 | Z051242 | The project will install metal guardrail in median of State Route 100 to improve safety and reduce median crossover crashes in Berks County. | Safety/Traffic Management | 09/22/2009 | 10/13/2009 | 03/22/2010 | 340000 | 1.645
5607 | Pennsylvania | BERKS | READING | 16, 17 | Z051243 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and adding linestriping on US Route 222 in Spring, Muhlenberg, Ontelaunee and Mai | Pavement Improvement | 07/07/2009 | 07/08/2009 | 12/30/2010 | 11577050 | 28.311
5608 | Pennsylvania | BERKS |  | 17 | Z051246 | The project will install cameras and changeable message signs to improve traveler information availability on Interstate 78 from the Lebanon County Line to State Route 61 in Berks County. | Safety/Traffic Management | 06/29/2009 | 09/09/2009 | 07/24/2010 | 1943027 | 0.8
5609 | Pennsylvania | BERKS | READING | 17 | Z051247 | Replacement of Precast Bridge Parapets on Interstate 78 in Lenhartsville, Greenwich Township | Safety/Traffic Management | 10/13/2009 |  | 12/01/2011 | 1050000 | 0
5610 | Pennsylvania | CARBON |  | 11 | Z052135 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 209 from McCall Bridge through Lehighton in Carbon County | Pavement Improvement | 06/30/2009 | 09/23/9 | 08/23/2010 | 1967400 | 4.249
5611 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053191 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 329 in North Whitehall and Whitehall Townships in Lehigh County | Pavement Improvement | 06/04/2009 | 10/26/2009 | 01/30/2010 | 2149192 | 1.51
5612 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053193 | This project will increase the life of several bridges by painting the steel beams on 11 bridges in various locations in Lehigh County | Bridge Improvement | 05/21/2009 | 05/21/2009 | 11/30/2010 | 1625824 | 0.18
5613 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053194 | The project will repair bridge parapets on various state routes in Weisenberg, South Whitehall, Whitehall, Washington Townships and City of Bethlehem, in Lehigh and Northampton Counties | Safety/Traffic Management | 10/13/2009 |  | 12/01/2011 | 4213088 | 1.997
5614 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053202 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and add curb ramps on Fairmont Avenue from MacArthur Road to Fullerton Avenue in Wh | Pavement Improvement | 01/19/2010 | 01/19/2010 | 11/30/2010 | 895895 | 0
5615 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053203 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and add curb ramps on Hanover Avenue from the Lehigh River Bridge to Irving Street | Pavement Improvement | 01/19/2010 |  | 11/30/2010 | 2772642 | 0
5616 | Pennsylvania | MONROE |  | 11, 17 | Z054183 | The project will replace the deteriorated decks of 10 bridges in various locations in Monroe and Schuylkill Counties | Bridge Improvement | 06/04/2009 | 06/15/2009 | 11/30/2010 | 2332200 | 0.254
5617 | Pennsylvania | MONROE |  | 11 | Z054184 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 33 and State Route 8017 in Hamilton Township, Monroe County. | Pavement Improvement | 07/16/2009 | 08/17/2009 | 09/01/2010 | 7997775 | 6.324
5618 | Pennsylvania | MONROE |  | 11, 17 | Z054185 | This project will upgrade existing traffic barrier on bridges to improve safety on Interstate 80 in Pocono Township, Monroe County. This project will also upgrade existing traffic barrier on bridge | Safety/Traffic Management | 09/25/2009 |  | 11/11/2011 | 2163959 | 1.804
5619 | Pennsylvania | MONROE |  | 11 | Z054186 | Replacement of Precast Bridge Parapets on Interstate 80 in Pocono Township | Safety/Traffic Management | 09/25/2009 |  | 11/11/2011 | 5132986 | 0
5620 | Pennsylvania | MONROE |  | 11 | Z054187 | Replacement of Precast Bridge Parapets in Stroud, Smithfield Townships, Stroudsburg and East Stroudsburg Boroughs | Safety/Traffic Management | 09/25/2009 |  | 11/11/2011 | 3797563 | 0
5621 | Pennsylvania | MONROE |  | 11 | Z054189 | The project will construct curb ramps for improving pedestrian access and safety at various locations in Coolbaugh, Middle Smithfield, Pocono, Polk, Smithfield and Stroud Townships, the Boroughs of Ea | Transportation Enhancements | 01/21/2010 | 01/21/2010 | 11/29/2010 | 458695 | 23.907
5622 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055193 | The project will replace the deteriorated decks of 7 bridges in various locations in Northampton County | Bridge Improvement | 05/14/2009 | 05/14/2009 | 01/11/2010 | 1778376 | 0.198
5623 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055194 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and linestriping on State Route 33 from Belfast to Wind Gap in Northampton County | Pavement Improvement | 06/30/2009 |  | 12/30/2010 | 10177789 | 13.53
5624 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055195 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 412 from Interstate 78 through Hellertown in Northampton County | Pavement Improvement | 05/27/2009 | 07/20/2009 | 02/21/2010 | 1548975 | 1.991
5625 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055197 | This project will construct curb ramps to improve pedestrian access and safety at various locations in Northampton County. | Transportation Enhancements | 01/22/2010 | 01/21/2010 | 01/30/2011 | 1128270 | 40.962
5626 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055198 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on Interstate 78 from State Route 412 to Easton in Northampton County | Bridge Replacement | 09/15/2009 |  | 01/30/2011 | 9552180 | 31.883
5627 | Pennsylvania | SCHUYLKILL |  | 17 | Z056178 | Replacement of precast bridge parapets | Safety/Traffic Management | 09/25/2009 |  | 11/11/2011 | 677600 | 0
5628 | Pennsylvania | SCHUYLKILL |  | 17 | Z056179 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 924 from State Route 61 to 4 lane section north of Frackville in Sch | Pavement Improvement | 07/09/2009 | 07/13/2009 | 08/19/2010 | 832809 | 0.963
5629 | Pennsylvania | SCHUYLKILL |  | 17 | Z056180 | The project will construct curb ramps at various locations in Schuylkill County to improve pedestrian access and safety. | Safety/Traffic Management | 01/04/2010 |  | 01/29/2011 | 398047 | 49.616
5630 | Pennsylvania | SCHUYLKILL |  | 17 | Z056182 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on PA 54 from the Bridge over the Reading and Blue Mountain Railroad, near Coles S | Pavement Improvement | 01/20/2010 |  | 12/15/2010 | 3941910 | 5.131
5631 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 8 | Z061100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Bucks County | Transportation Enhancements | 06/19/2009 | 07/20/2009 | 04/01/2010 | 1129214 | 3.835
5632 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 2, 8, 13 | Z061101 | This project will add cameras, message boards and instrumentation to detect incidents and provide Travel Times to help the traveling public on Interstate 95 in various locations of Bucks and Philadelp | Safety/Traffic Management | 06/30/2009 | 08/31/2009 | 10/09/2013 | 23905402 | 46.963
5633 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 8, 13 | Z061102 | This project will add cameras, message boards and instrumentation to detect incidents and provide Travel Times to help the traveling public in various locations of Philadelphia and Bucks Counties. | Safety/Traffic Management | 09/14/2009 | 09/14/2009 | 11/27/2013 | 20841948 | 41.837
5634 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 8 | Z061103 | This project will mill and overlay the existing pavement, install a landscaped median, provide new traffic signals, pavement markings and signing on Stoopville Road in Newton Township, Bucks County. | Pavement Improvement | 09/23/2009 | 11/09/2009 | 06/19/2010 | 1523683 | 4.112
5635 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 8, 13, 15 | Z061104 | This project will provide a paved pedestrian and bike trail from the New Hope borough municipal parking lot to the New Hope-Ivyland historic train station in Bucks County. | Transportation Enhancements | 12/10/2009 | 01/27/2010 | 08/20/2010 | 251699 | 0
5636 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7, 16 | Z062100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Chester County | Transportation Enhancements | 04/30/2009 | 06/29/2009 | 06/27/2010 | 4978590 | 101.163
5637 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6 | Z062101 | This project will mill and overlay 5 miles of existing pavement, install an updated median barrier, shoulder rumble strips, pavement markings, and updated signing and guiderail on the US Route 30 Exto | Pavement Improvement | 08/24/2009 | 08/24/2009 | 02/21/2010 | 4779807 | 10.249
5638 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 16 | Z062102 | This project will convert 2 miles of abandoned railway into a paved pedestrian and bike trail from State Route 29 to Church Farm School Road in Tredyffrin, East Whiteland and West Whiteland Townships, | Transportation Enhancements | 09/20/2009 | 09/23/9 | 09/19/2010 | 3668414 | 0
5639 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 16 | Z062103 | Removal of the State Street Bridge over AMTRAK in Parkesburg Borough | Pavement Improvement | 01/27/2010 |  | 08/01/2010 | 737000 | 0
5640 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7 | Z062105 | This project will provide new sidewalks along sections of Old Lancaster Rd., Conestoga Rd., Howelville Rd., and Irish Rd. It will also install traffic calming measures and provide storm water manageme | Transportation Enhancements | 01/06/2010 |  | 06/24/2010 | 2181452 | 0
5641 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 7 | Z063100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Delaware County. | Transportation Enhancements | 05/08/2009 | 06/15/2009 | 06/27/2010 | 5396777 | 27.008
5642 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 6, 7 | Z063101 | This project on I-95 and I-476, in Philadelphia, Delaware, and Montgomery Counties, will install cameras, message boards, and instrumentation to detect incidents and provide Travel Times to minimize d | Safety/Traffic Management | 07/13/2009 | 07/20/2009 | 10/09/2013 | 15009061 | 72.188
5643 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 7 | Z063102 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings on Bridgewater and Brookhaven Roads in Brookhaven Borough, Delaware County. | Transportation Enhancements | 07/06/2009 | 10/21/2009 | 03/07/2010 | 248385 | 0.769
5644 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 7 | Z063103 | This project will provide new traffic signal equipment at the intersection of Darby-Paoli and Whitehorse Roads in Newtown Township, Delaware County. | Safety/Traffic Management | 08/31/2009 | 08/31/2009 | 02/15/2010 | 149000 | 0.361
5645 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 7 | Z063104 | This project will replace incandescent traffic signal heads with more efficient Light Emitting Diode traffic signal heads at 7 intersections and pedestrian signals at 4 locations in Darby, Brookhaven | Safety/Traffic Management | 08/31/2009 | 08/31/2009 | 01/16/2010 | 234000 | 2.551
5646 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 7 | Z063105 | This project will provide a smoother road by milling and repaving Valley Rd. from Middletown Road to Brick House Farm Road in Edgemont Township, Delaware County. | Pavement Improvement | 09/25/2009 | 10/01/2009 | 01/25/2010 | 189562 | 0
5647 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7 | Z064100 | This project will repair existing pavement and resurface and provide pavement markings and drainage and guiderail improvements on US Route 422 from State Route 29 to Township Line in Limerick and Upp | Pavement Improvement | 05/22/2009 | 05/22/2009 | 07/27/2010 | 13439569 | 10.05
5648 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7, 15 | Z064101 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Montgomery County to improve pedestrian access and safety. | Transportation Enhancements | 05/19/2009 | 07/20/2009 | 04/11/2010 | 1343935 | 7.197
5649 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 13 | Z064102 | This project will provide landscaping enhancements along Bethlehem Pike in Springfield and Whitemarsh Townships, Montgomery County, to improve the aesthetics for drivers and pedestrians. | Transportation Enhancements | 07/17/2009 | 07/17/2009 | 11/29/2009 | 273000 | 0.095
5650 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7 | Z064103 | This project will reconstruct the pavement and shoulders along I-476 from I-76 to the PA Turnpike, in Plymouth Township and West Conshohocken Borough, Montgomery County. This project also include bri | Pavement Improvement | 08/31/2009 | 09/14/2009 | 11/22/2012 | 3525084 | 9.831
5651 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 7 | Z064104 | This project will construct new ramps to and from I-76 at Henderson Rd. in Upper Merion Township, Montgomery County. | Pavement Improvement | 10/15/2009 | 11/06/2009 | 07/19/2012 | 11638178 | 3.718
5652 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 13 | Z064105 | This project will include traffic signal improvements and pedestrian signals, and construct concrete curb ramp for pedestrian access and safety in 11 municipalities in Montgomery County.. | Safety/Traffic Management | 12/31/2009 | 12/31/2009 | 07/28/2011 | 4673888 | 0.51
5653 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 2, 13 | Z065100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings on various state highways in the City of Philadelphia, Philadelphia County. | Transportation Enhancements | 06/25/2009 | 08/17/2009 | 11/29/2009 | 1605428 | 18.345
5654 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 2, 6, 8, 13 | Z065101 | This project provides for milling and paving of over 20 miles of Philadelphia City streets and installing concrete curb ramps. | Transportation Enhancements | 10/14/2009 | 10/14/2009 | 12/12/2010 | 6744539 | 0
5655 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1 | Z065102 | This project will repair and paint structural steel, and redeck the bridge surface on the Girard Point Bridge on I-95 in Philadelphia. | Bridge Improvement | 10/02/2009 | 10/02/2009 | 10/24/2012 | 77377214 | 1.958
5656 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 2, 6, 8, 13 | Z065103 | This project provides for milling and paving various Philadelphia City streets and providing concrete curb ramps. | Transportation Enhancements | 01/29/2010 |  | 10/19/2010 | 4407115 | 0
5657 | Pennsylvania | ADAMS |  | 19 | Z081001 | This project will improve rideability and safety by resurfacing and updating guiderail on 6 miles of US 15 north of Gettysburg in Adams County. | Pavement Improvement | 06/22/2009 | 06/25/2009 | 11/18/2011 | 6785000 | 9.378
5658 | Pennsylvania | CUMBERLAND |  | 9 | Z082001 | This project will improve safety by replacing an existing deteriorated bridge on SR 34 north of Carlisle in Cumberland County. | Bridge Replacement | 04/29/2009 | 06/11/2009 | 02/18/2010 | 1949460 | 0.032
5659 | Pennsylvania | CUMBERLAND |  | 19 | Z082002 | This Cumberland County project will improve rideability and safety by resurfacing about 8 miles of I-81 SB from Exit 57 to Exit 65, Restoring concrete pavement at Milepost 50.5 Northbound near Carlisl | Pavement Improvement | 07/27/2009 | 07/30/2009 | 03/03/2010 | 5338077 | 18.534
5660 | Pennsylvania | CUMBERLAND | HARRISBURG | 19 | Z082003 | This project will extend the life of the bridge and improve safety of the SR 15 bridge over SR 114 south of the Pennsylvania Turnpike and of the Wesley Road/Rossmoyne Road bridge over US 15 north of t | Bridge Improvement | 07/08/2009 | 07/13/2009 | 10/31/2009 | 3559735 | 0.076
5661 | Pennsylvania | CUMBERLAND | HARRISBURG | 9, 19 | Z082004 | This project will improve rideability and safety by resurfacing about 2 miles of SR 641 from US 11 to PA 465 in North Middletown Township on the west side of Carlisle, in Cumberland County. This pr | Pavement Improvement | 09/23/2009 | 09/28/2009 | 08/22/2010 | 2112800 | 4.658
5662 | Pennsylvania | FRANKLIN |  | 9 | Z083001 | This project will improve rideability and safety by resurfacing 6 miles of US 30 from Norlo Road to the Adams County Line in Guilford and Greene Townships east of Chambersburg in Franklin County. | Pavement Improvement | 05/18/2009 | 05/20/2009 | 01/21/2010 | 3258000 | 6.843
5663 | Pennsylvania | YORK | YORK | 19 | Z083002 | This project will improve rideability and safety by resurfacing, updating guiderail and restoring 3 structures (surfacing and substructure repairs) on about 5 miles of US 30 from the Hellam Interchang | Pavement Improvement | 06/08/2009 | 06/11/2009 | 01/12/2010 | 3650372 | 9.954
5664 | Pennsylvania | FRANKLIN |  | 9 | Z083003 | This Franklin County project will improve rideability and safety by resurfacing and updating guiderail on US 30 from State Route 3012 (Jack Road) to Hilltop Drive in St Thomas and Hamilton Townships w | Pavement Improvement | 07/02/2009 | 07/06/2009 | 03/11/2010 | 3324510 | 5.717
5665 | Pennsylvania | FRANKLIN |  | 9 | Z083004 | This Franklin County project will extend the life of the PA 433 bridge over Rowe Run in Southampton Township and improve safety by replacing the superstructure (beams and deck) and improving approache | Bridge Improvement | 09/14/2009 | 09/17/2009 | 05/15/2010 | 418000 | 0.108
5666 | Pennsylvania | FRANKLIN |  | 9 | Z083005 | This bridge painting project will preserve the steel beams on the US 11 bridge (Molly Pitcher Highway) over I-81 Exit 3 in Antrim Township in Franklin County. | Bridge Improvement | 09/14/2009 | 09/17/2009 | 08/14/2010 | 500000 | 0.052
5667 | Pennsylvania | FRANKLIN |  | 9 | Z083006 | Rehabilitation of bridge carrying Mont Alto Road (SR 2031) over Tributary to Conococheague Creek in Guilford Township | Bridge Improvement | 02/08/2010 |  | 10/02/2010 | 500000 | 0.006
5668 | Pennsylvania | YORK | YORK | 17, 19 | z084001 | This work will provide 3 closed circuit TV cameras in the York County Area on I-83 (Exits 21, 24, Milepost 30) and 1 Highway Advisory Radio (HAR) & 4 Signs at I-83 (Exit 22) to allow the District to m | Safety/Traffic Management | 05/29/2009 |  | 08/30/2009 | 662988 | 0
5669 | Pennsylvania | YORK | YORK | 19 | Z084002 | This project will improve rideability and safety by resurfacing and updating guiderail on about 2.5 miles of US 30 from Interstate 83 to State Route 24 in Manchester and Springettsbury Townships on th | Pavement Improvement | 08/17/2009 | 08/20/2009 | 06/26/2011 | 8260000 | 7.499
5670 | Pennsylvania | YORK | YORK | 19 | Z084003 | This York County project will improve rideability and safety by resurfacing the roadway and upgrading guiderail on about 7.5 miles of US 15 from Golf Course Road to Cumberland County Line in Carroll T | Pavement Improvement | 09/23/2009 |  | 11/18/2010 | 3185000 | 5.035
5671 | Pennsylvania | DAUPHIN |  | 17 | Z085001 | This project will improve rideability and safety by resurfacing and updating guiderail on 1.5 miles of PA 147 from Fisher Street to Dawn Road north of Halifax, in Dauphin County. This Dauphin Count | Pavement Improvement | 04/30/2009 | 05/18/2009 | 12/30/2009 | 2389445 | 5.344
5672 | Pennsylvania | DAUPHIN |  | 17 | Z085002 | This project will upgrade the crashworthiness of precast concrete parapets on bridges in Dauphin County at US 22 Eastbound, Westbound, Ramps and Retaining Walls over the Susquehanna River at Clarks Fe | Safety/Traffic Management | 06/23/2009 | 06/23/2009 | 09/24/2010 | 5283850 | 1.372
5673 | Pennsylvania | DAUPHIN | HARRISBURG | 6, 10, 17, 19 | z085003 | This Dauphin County project will provide 5 closed circuit TV cameras in the Harrisburg Metropolitan Area on I-81 (Exits 45, 47, Milepost 74, Milepost 79) and US 22/322 (PA39 Exit) to allow the Distric | Safety/Traffic Management | 05/29/2009 |  | 08/30/2009 | 689500 | 0
5674 | Pennsylvania | DAUPHIN | HARRISBURG | 17 | Z085004 | This Dauphin County project will improve rideability and safety by resurfacing 2 miles of I-83 south of Union Deposit Road interchange to Bridge over Valley Road in Lower Paxton Township from Exit 48 | Pavement Improvement | 07/27/2009 | 08/31/2009 | 08/22/2010 | 3360000 | 8.802
5675 | Pennsylvania | DAUPHIN | HARRISBURG | 17 | Z085006 | This project will relieve congestion and improve safety of about 1.5 miles of PA 39 with pavement widening and reconstruction, installing traffic signals and other misc. work at the PA 39/I-81 Interch | Pavement Widening | 07/17/2009 | 07/20/2009 | 12/31/2011 | 10700000 | 2.045
5676 | Pennsylvania | DAUPHIN | HARRISBURG | 17 | Z085007 | This Dauphin County project will improve rideability and safety by resurfacing, drainage improvements, ADA ramps and other misc. improvements on about 2 miles of SR 230 (Cameron Street) and about 6 mi | Pavement Improvement | 09/28/2009 |  | 09/29/2010 | 2395500 | 3.651
5677 | Pennsylvania | LANCASTER | LANCASTER | 16 | Z087001 | This Lancaster County project will improve safety and remove weight restrictions on the PA 324 bridge over Pequea Creek in Pequea and Martic Townships by replacing the superstructure (beams and deck) | Bridge Improvement | 04/20/2009 | 04/20/2009 | 05/21/2010 | 1686041 | 0.037
5678 | Pennsylvania | LANCASTER |  | 9, 16, 19 | Z087002 | This project will upgrade the crashworthiness of precast concrete parapets on bridges in Adams County on SR 1005 over Mud Creek, 3 miles southeast of York Springs; in Cumberland County on I-83 over SR | Safety/Traffic Management | 06/23/2009 | 06/23/2009 | 07/08/2010 | 2160928 | 2.947
5679 | Pennsylvania | LANCASTER | LANCASTER | 6, 16, 17, 19 | z087003 | This Lancaster County project will provide 2 closed circuit TV Cameras in the Lancaster County Area on US 30 (PA 501 and PA 283 Exits under Part IV of Contract 354R23, Phase 4 (Expansion of the Harris | Safety/Traffic Management | 05/29/2009 |  | 08/30/2009 | 318350 | 0
5680 | Pennsylvania | LANCASTER | LANCASTER | 16 | Z087004 | This Lancaster County project will improve rideability and safety by resurfacing and updating guiderail on about 7.5 miles of State Route 222 from north of Bushong Road to US Route 322 in Ephrata, Man | Pavement Improvement | 06/22/2009 | 06/24/2009 | 02/06/2011 | 12922035 | 12.297
5681 | Pennsylvania | LANCASTER |  | 16 | Z087005 | This Lancaster County project will improve rideability and safety by resurfacing and updating guiderail on about 5 miles of State Route 222 from Quarryville to Brennenman Road in Providence and Stras | Pavement Improvement | 08/14/2009 | 08/17/2009 | 09/12/2010 | 3390677 | 5.218
5682 | Pennsylvania | LANCASTER | LANCASTER | 16 | Z087006 | This Lancaster County project will improve rideability and safety by resurfacing and updating guiderail on US 30 from PA 896 to PA 897 in East Lampeter, Leacock, Paradise, and Salisbury Townships east | Pavement Improvement | 09/28/2009 | 09/30/2009 | 11/14/2010 | 4480000 | 9.8
5683 | Pennsylvania | LEBANON |  | 17 | Z088001 | This Lebanon County project will improve rideability and safety by resurfacing, upgrading guiderail, placing concrete median barrier and constructing left turn lanes on about 3 miles of US 22 from Lin | Pavement Improvement | 08/14/2009 | 08/17/2009 | 09/15/2010 | 6500000 | 5.89
5684 | Pennsylvania | PERRY |  | 9, 17 | Z089001 | This Perry County project will improve rideability and safety by resurfacing and updating guiderail on about 3 miles of State Route 74 east of Loysville. | Pavement Improvement | 04/30/2009 | 06/15/2009 | 12/24/2009 | 1112947 | 3.134
5685 | Pennsylvania | BEDFORD |  | 9 | Z091001 | This project will overlay the existing deteriorating pavement with new asphalt pavement of State Route 30 from Stony Lane (T-720) to the Snake Spring Twp Line in Bedford Township and Bedford Borough i | Pavement Improvement | 04/29/2009 | 04/29/2009 | 01/22/2011 | 6728697 | 9.321
5686 | Pennsylvania | BEDFORD |  | 9, 12 | Z091002 | The project will paint the steel beams of 20 bridges in Bedford, Blair, Cambria, Fulton, Huntingdon and Somerset Counties | Bridge Improvement | 05/04/2009 | 05/18/2009 | 02/10/2010 | 4966587 | 2.495
5687 | Pennsylvania | BEDFORD |  | 9 | Z091003 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated decks on various structures in Bedford County | Bridge Improvement | 05/01/2009 | 07/14/2009 | 02/01/2010 | 287267 | 0.103
5688 | Pennsylvania | BEDFORD |  | 9 | Z091004 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams of 2 bridges on State Route 915 over Sandy Run in Broadtop To | Bridge Improvement | 07/22/2009 | 08/17/2009 | 12/10/2010 | 1615000 | 0.134
5689 | Pennsylvania | BEDFORD |  | 9 | Z091005 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on SR 1010 (Woy Bridge Road) over Raystown Branch of the Jun | Bridge Improvement | 09/11/2009 |  | 11/24/2010 | 1990000 | 0.134
5690 | Pennsylvania | BLAIR | ALTOONA | 9 | Z092001 | The Blair County project will construct new pavement surface, guardrail, and curb ramps on State Route 1001 from Convention Center Blvd north to 3rd Street and on State Route 36 from Pine St (T-612) t | Pavement Improvement | 05/20/2009 | 05/26/2009 | 02/01/2010 | 4238377 | 11.386
5691 | Pennsylvania | BLAIR | ALTOONA | 9 | Z092002 | The project will construct a new pavement surface and curb ramps on Penn Street (State Route 36) from Chimney Rocks Road to Pine Street in Hollidaysburg Borough, Blair County. | Pavement Improvement | 06/23/2009 | 06/23/9 | 11/13/2010 | 3327317 | 1.842
5692 | Pennsylvania | BLAIR | ALTOONA | 9 | Z092003 | The project will replace deteriorated bridge deck surfaces on various bridges in Snyder, Antis Townships and Tyrone Borough, Blair County. | Bridge Improvement | 07/21/2009 | 08/03/2009 | 09/09/2011 | 1627306 | 0.293
5693 | Pennsylvania | CAMBRIA | JOHNSTOWN | 9 | Z093001 | Replacement of deteriorated bridge decks on 3 bridges on State Route 1021 over Wyerough Run, State Route 1026 over Slate Lake Run, State Route 4024 over Chest Creek in White and Chest Township, Cambri | Bridge Improvement | 06/16/2009 | 08/03/2009 | 02/13/2011 | 1666233 | 0.062
5694 | Pennsylvania | CAMBRIA | JOHNSTOWN | 12 | Z093002 | The project will construct a new pavement surface on US Route 219 from Galleria Drive to Palestine Road and resurface the bridge deck on the Palestine Road Bridge in Adams and Richland Townships in | Pavement Improvement | 07/16/2009 | 10/26/2009 | 03/06/2011 | 5708217 | 9.457
5695 | Pennsylvania | CAMBRIA |  | 9, 12 | Z093003 | The project will replace deteriorated bridge decks for 2 bridges on Manor Drive (State Route 1001) over R. J. Corman Railroad near the intersection of Munster Rd (State Route 1003) and over R. J. Corm | Bridge Improvement | 07/20/2009 | 08/03/2009 | 12/12/2010 | 1009991 | 0.038
5696 | Pennsylvania | CAMBRIA | JOHNSTOWN | 12 | Z093005 | Rehabilitation of bridge carrying Eisenhower Boulevard (SR 3006) over Stonycreek River near the intersection of Ferndale Avenue (PA 403) in Upper Yoder and Stonycreek Townships | Bridge Improvement | 02/02/2010 |  | 12/04/2010 | 1734606 | 0.044
5697 | Pennsylvania | FULTON |  | 9 | Z094001 | This Fulton County project will replace bridge decks of 3 bridges on State Route 1003 over Cove Creek, State Route 3006 over Little Tonoloway, and State Route 4004 over Wooden Bridge Creek in Ayr an | Bridge Improvement | 04/13/2009 | 04/20/2009 | 11/30/2009 | 506138.69 | 0.03
5698 | Pennsylvania | FULTON |  | 9 | Z094002 | The Fulton County project will construct a new pavement surface on US Route 30 from Bedford County line to the Truck Pull-off in Brush Creek Township. | Pavement Improvement | 04/17/2009 | 05/05/2009 | 12/27/2009 | 591442.83 | 2.624
5699 | Pennsylvania | HUNTINGDON |  | 9 | Z095001 | The project will replace the bridge on State Route 1010 in Huntingdon Borough over Standing Stone Creek in Huntingdon County. | Bridge Replacement | 05/06/2009 | 06/12/2009 | 02/04/2010 | 1416753 | 0.024
5700 | Pennsylvania | HUNTINGDON |  | 9 | Z095002 | The project will construct a new pavement surface on US Route 22 from Old Twenty-two Road (T-613) to Walnut Terrace Road (T-561) in Smithfield and Porter Townships, Huntingdon County. | Pavement Improvement | 05/20/2009 | 05/26/2009 | 01/22/2010 | 1324826 | 1.904
5701 | Pennsylvania | HUNTINGDON |  | 9 | Z095003 | The project will replace the deteriorated bridge deck surface on US 522 over Pump Station Road (T-396), Aughwick Creek and East Broad Top Railroad in Shirley Township | Bridge Improvement | 09/24/2009 |  | 01/12/2011 | 1622000 | 0.216
5702 | Pennsylvania | SOMERSET |  | 12, 18 | Z097001 | The project will construct a new pavement surface on US Route 30 from Westmoreland County Line to State Route 985 in Jenner Township and Jennerstown Borough | Pavement Improvement | 04/15/2009 | 05/13/2009 | 10/15/2009 | 1222568.55 | 3.816
5703 | Pennsylvania | SOMERSET |  | 9 | Z097002 | The project will replace 3 bridges and 2 deteriorated bridge decks on State Route 2019 and State Route 2021 over Shaffers Run in Fairhope Township | Bridge Replacement | 06/01/2009 | 06/22/2009 | 12/17/2011 | 2607571 | 0.105
5704 | Pennsylvania | SOMERSET |  | 12 | Z097003 | The project will remove a bridge and place it with earth fill and asphalt pavement at Wilber Coal Company Coal Mine Railroad bridge in Quemahoning Township | Bridge Replacement | 07/20/2009 | 08/11/2009 | 11/13/2010 | 515890 | 0.076
5705 | Pennsylvania | ARMSTRONG |  | 3 | Z101207 | This project will extend the life of one bridge by placing an epoxy overlay on the deck. The bridge is on Iron Bridge Road, in Armstrong County, South Buffalo Township just west of the South Scenic Dr | Bridge Improvement | 04/27/2009 | 06/08/2009 | 11/18/2009 | 315000 | 0.066
5706 | Pennsylvania | ARMSTRONG |  | 3 | Z101208 | This project will patch the existing concrete roadway on State Route 422 in Armstrong County West Franklin township and Worthington Borough. The project is from approximately 0.26 miles west of the SR | Pavement Improvement | 04/27/2009 | 04/27/2009 | 01/20/2010 | 5400000 | 13.338
5707 | Pennsylvania | ARMSTRONG | PITTSBURGH , PA | 3 | Z101209 | This project will patch the existing concrete on State Route 28 and overlay it with asphalt from the overpass at Iron Bridge Road to the overpass at State Route 128, in Armstrong County South Buffalo | Pavement Improvement | 05/27/2009 | 05/27/2009 | 01/26/2010 | 6510800 | 9.376
5708 | Pennsylvania | ARMSTRONG |  | 3 | Z101219 | This project will extend the life of two bridges and improve safety by replacing the existing deteriorated decks on two State Route 422 bridges that pass over State Route 28 in Armstrong County's East | Bridge Improvement | 07/17/2009 | 08/17/2009 | 09/30/2010 | 4835000 | 2.417
5709 | Pennsylvania | ARMSTRONG |  | 12 | z101220 | This is a Transportation Enhancement project that consists of a tar and chip widening of approximately 1/2 mile of the existing trail, construction of about two miles of new trail, and construction of | Transportation Enhancements | 08/11/2009 | 08/11/2009 | 01/25/2010 | 780000 | 0
5710 | Pennsylvania | BUTLER |  | 3 | Z102224 | This project will extend the service life of one bridge by patching the deck/joints and overlaying the deck with a latex modified concrete surface. The bridge is on State Route 528 in Butler County ap | Bridge Improvement | 04/27/2009 | 04/27/2009 | 10/04/2009 | 420000 | 0.058
5711 | Pennsylvania | BUTLER |  | 3 | Z102225 | This project will extend the life of four bridges in Butler County with preservation activities, including, shear key replacement, concrete beam repair and placement of concrete composite deck on Stat | Bridge Improvement | 04/27/2009 | 05/04/2009 | 12/16/2009 | 735000 | 0.348
5712 | Pennsylvania | BUTLER |  | 4 | Z102226 | This project will replace the existing bridge with a new two-lane six span multi-girder steel bridge on State Route 3027 in Butler County, Jackson Township. | Bridge Replacement | 06/08/2009 | 06/08/2009 | 07/10/2010 | 5700000 | 0.287
5713 | Pennsylvania | BUTLER |  | 3 | Z102229 | This project will extend the life of the roadway by replacing the surface course on State Route 422 in Butler County from the SR 422/T439 Whipporwill Road intersection to approximately 500 feet east o | Pavement Improvement | 07/13/2009 | 07/27/2009 | 01/17/2010 | 1638200 | 3.915
5714 | Pennsylvania | BUTLER |  | 3 | Z102233 | This project will replace the bridge deck on I-79 in Worth Township in Butler County and replace the bridge decks on two structures over Interstate 79, with one being State Route 4007 and the other Pa | Bridge Improvement | 08/03/2009 | 08/31/2008 | 10/30/2010 | 3381000 | 0.085
5715 | Pennsylvania | CLARION |  | 5 | Z103194 | This project will extend the service life of two bridges by replacing the decks. These are the bridges that carry State Route 68 over interstate 80 in Clarion County. The project will replace the d | Bridge Improvement | 05/18/2009 | 07/20/2009 | 08/11/2010 | 6915000 | 0.87
5716 | Pennsylvania | CLARION |  | 5 | Z103196 | Bridge preservation activities, including, shear key replacement, concrete beam repair, placement of concrete composite deck and other miscellaneous construction for State routes 66(#1), 66(#2), 2007( | Bridge Improvement | 05/04/2009 | 05/04/2009 | 10/20/2009 | 764537 | 0.176
5717 | Pennsylvania | CLARION |  | 5 | Z103200 | This project will replace an existing two lane single span structure with a two lane single span prestressed spread box beam bridge with minimal approach work on state route 28 in Clarion County Redba | Bridge Replacement | 07/21/2009 | 10/19/2009 | 11/14/2010 | 2200000 | 0.27
5718 | Pennsylvania | CLARION |  | 5 | Z103201 | This project will increase Americans with Disabilities Act facilities by building ADA compliant curb ramps on State Route 322 in Clarion Borough, Clarion County from approximately the First Avenue int | Transportation Enhancements | 12/01/2009 |  | 08/29/2010 | 402000 | 0.842
5719 | Pennsylvania | INDIANA |  | 9 | Z104234 | This project will extend the service life of the roadway by patching the existing concrete pavement and overlaying it with asphalt. The project is on State Route 119 in Indiana County from the SR 56/S | Pavement Improvement | 06/08/2009 | 07/01/2009 | 02/07/2010 | 1205000 | 2.272
5720 | Pennsylvania | INDIANA |  | 12 | Z104235 | This project will extend the service life of two bridges by replacing their decks and repairing the piers. The bridges are on eastbound and westbound State Route 422 at the Chestnut Ridge Road overpas | Bridge Improvement | 07/20/2009 | 08/04/2009 | 07/30/2010 | 3705000 | 0.378
5721 | Pennsylvania | INDIANA |  | 9 | Z104236 | This project will extend the service life of the existing concrete pavement by performing slab stabilization, full depth slab patching, dowel bar retrofits, crack and joint sealing and microsurfacing. | Pavement Improvement | 09/18/2009 | 09/24/2009 | 07/30/2010 | 4900000 | 7.014
5722 | Pennsylvania | INDIANA |  | 12 | Z104241 | Replacement of the bridge carrying PA 403 over Dixon Run and Two Lick Creek in Clymer Borough | Bridge Replacement | 01/04/2010 |  | 12/18/2011 | 5590583 | 0.379
5723 | Pennsylvania | INDIANA |  | 9 | Z104242 | Rehabilitation of the bridge carrying Yellow Creek Park Road (PA 259) over Blacklick Creek in West Wheatfield and Brush Valley Townships | Bridge Improvement | 01/28/2010 |  | 06/30/2011 | 1598000 | 0.03
5724 | Pennsylvania | JEFFERSON |  | 5 | Z105182 | This project will extend the service life of one bridge by performing preventative maintenance activities such as shear key replacement, concrete beam repair and the placement of concrete composite de | Bridge Improvement | 05/18/2009 | 06/24/2009 | 01/04/2010 | 630000 | 0.045
5725 | Pennsylvania | JEFFERSON |  | 5 | Z105183 | This project will replace the superstructure (bridge beams and deck) on a one Span Steel Multi-Girder Structure. The structure is on State Route 2023 (Knoxdale Road) in Jefferson County approximately | Bridge Improvement | 05/18/2009 | 06/01/2009 | 02/02/2010 | 1110000 | 0.095
5726 | Pennsylvania | JEFFERSON |  | 5 | Z105185 | This project will extend the service life of State Route 36 in Punxsutawney Borough by performing activities such as leveling, Superpave overlay, transverse joint repair, guiderail and ADA ramp upgrad | Pavement Improvement | 06/22/2009 | 06/22/2009 | 02/03/2010 | 1842310 | 5.633
5727 | Pennsylvania | JEFFERSON |  | 5 | Z105187 | This project will construct ADA compliant curb ramps along State Route 28 in Brockway Borough from approximately the SR 28/Second Avenue intersection to approximately the SR 28/SR 219 intersection. | Transportation Enhancements | 10/13/2009 |  | 10/30/2010 | 469000 | 1.159
5728 | Pennsylvania | JEFFERSON |  | 5 | Z105188 | This project will extend the service life of the existing roadway by milling the surface course and replacing it with a bituminous overlay. This project is on State Route 436 in Punxsutawney Borough | Pavement Improvement | 09/22/2009 |  | 08/22/2010 | 786655 | 1.792
5729 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 18 | Z111300 | The project involves reconstructing the ramp pavement, eliminating 2 ramps, and installing new signals and signs in Robinson and North Fayette Townships. It will also construct new asphalt pavement al | Pavement Improvement | 06/01/2009 | 06/08/2009 | 12/19/2010 | 11800000 | 1.65
5730 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 14 | Z111606 | This project involves relocating a railroad, moving a pier, building a few retaining walls to prepare for the next project phase which will widen Route 28 from Troy Hill to Milvale in the City of Pitt | Other | 11/02/2009 | 11/02/2009 | 06/09/2012 | 24150000 | 4.112
5731 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 14 | Z111624 | The project will fix or repair various tunnel components that are worn out or deteriorated of the tunnel carrying State Route 3069 from the Liberty Bridge over the Monongahela River to State Route 51 | Pavement Improvement | 09/21/2009 | 10/01/2009 | 09/30/2010 | 11059162 | 2.252
5732 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 14, 18 | Z111625 | The project will replace the bridge deck surfaces on the Ft. Duquesne Bridge in City of Pittsburgh | Bridge Improvement | 07/07/2009 | 07/07/2009 | 11/28/2010 | 26190521 | 2.265
5733 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 4 | Z111640 | The project will construct a new pavement surface along the entire route. | Pavement Improvement | 09/10/2009 | 09/10/2009 | 01/21/2011 | 845658 | 5.728
5734 | Pennsylvania | BEAVER | PITTSBURGH , PA | 4 | Z112213 | The project will repair steel members, paint the bridge, and replace expansion joints on the Rochester Bridge over Beaver River in Rochester and Bridgewater Boroughs | Bridge Improvement | 05/18/2009 | 05/18/2009 | 01/30/2011 | 12160227 | 0.329
5735 | Pennsylvania | LAWRENCE |  | 4 | Z114210 | The project will upgrade the interchange by adding a lane on SR60 southbound, installing new signs and sign structures, and modifying ramps at various interchanges to meet standards in preparing for t | Pavement Improvement | 11/16/2009 | 01/20/2010 | 10/14/2010 | 10450000 | 15.802
5736 | Pennsylvania | LAWRENCE |  | 4 | Z114220 | The project will construct a new asphalt riding surface on US Route 422 (Ben Franklin Highway) from Pine Glen Road to Zoccoli Road in Mahoning and Pulaski Townships | Pavement Improvement | 06/22/2009 | 06/23/2009 | 01/28/2010 | 2800518 | 4.392
5737 | Pennsylvania | LAWRENCE |  | 4 | Z114221 | The project will replace the deck and provide other miscellaneous repairs of the State Route 2004 (Grove Street) bridge over Neshannock Creek in City of New Castle. | Bridge Improvement | 06/30/2009 | 08/10/2009 | 08/08/2010 | 3491447 | 0.149
5738 | Pennsylvania | LAWRENCE |  | 4 | Z114227 | Patch and overlay on US 422 from Cascade Street (SR 2004) to Ben Franklin Highway (Butler County Line) in the City of New Castle, Shenango and Slippery Rock Townships | Pavement Improvement | 01/28/2010 |  | 11/15/2010 | 8680988 | 10.266
5739 | Pennsylvania | FAYETTE | UNIONTOWN-CONNELLSVILLE | 9, 12, 18 | Z121001 | This project includes the replacement of bridge strip seals, bridge beam repair and minor concrete bridge deck repair for 31 bridges throughout Fayette, Greene, Washington and Westmoreland Counties. T | Bridge Improvement | 05/07/2009 | 07/08/2009 | 07/07/2010 | 1315216 | 1.462
5740 | Pennsylvania | FAYETTE |  | 9 | Z121002 | This project is the full replacement of a structurally deficient two span bridge carrying State Route 3006 over York Run. The roadway rehabilitation will consist of bridge approach slabs, drainage enh | Bridge Replacement | 07/20/2009 |  | 10/12/2011 | 1692353 | 0.17
5741 | Pennsylvania | FAYETTE |  | 12 | Z121003 | This project is the full replacement of two structurally deficient bridges carrying State Route 1054 over Trout Run. The roadway rehabilitation will consist of bridge approach slabs, drainage enhancem | Bridge Replacement | 07/20/2009 |  | 10/30/2011 | 1478845 | 0.01
5742 | Pennsylvania | FAYETTE | UNIONTOWN-CONNELLSVILLE | 12 | Z121004 | This project includes the full bridge replacement of SR 1039 over Dickerson Run in Dunbar Township, Fayette County. | Bridge Replacement | 07/09/2009 |  | 11/13/2011 | 947000 | 0.004
5743 | Pennsylvania | FAYETTE | UNIONTOWN-CONNELLSVILLE | 12 | Z121005 | This project consists of concrete pavement overlay to 2.19 miles of SR 0119 from Penn State Fayette to Pechin Road in North Union and Dunbar Townships. This project includes existing pavement milling, | Pavement Improvement | 08/06/2009 | 01/01/2010 | 10/30/2010 | 4930000 | 6.214
5744 | Pennsylvania | GREENE |  | 12 | Z122001 | This project is the full replacement of a structurally deficient bridge carrying State Route 0018 over Browns Creek in Franklin Township, Greene County. The roadway rehabilitation will consist of brid | Bridge Replacement | 10/02/2009 | 10/02/2009 | 12/14/2011 | 2200000 | 0.018
5745 | Pennsylvania | GREENE |  | 12 | Z122002 | This project is the full replacement of a structurally deficient bridge carrying State Route 0018 over a Branch of Browns Run in Morris Township, Greene County. The roadway rehabilitation will consist | Bridge Replacement | 08/07/2009 | 08/17/2009 | 12/10/2011 | 1200000 | 0.006
5746 | Pennsylvania | GREENE |  | 12 | Z122003 | This project is the full replacement of a structurally deficient bridge carrying State Route 0018 over Garner's Run in Washington Township, Greene County. The roadway rehabilitation will consist of br | Pavement Improvement | 08/07/2009 | 08/17/2009 | 09/03/2011 | 985606 | 0.004
5747 | Pennsylvania | GREENE |  | 12 | Z122004 | This is a safety improvement project that will upgrade curb ramps to current standards in the Borough of Waynesburg and Franklin Township, Greene County. | Transportation Enhancements | 07/31/2009 | 09/15/2008 | 11/28/2010 | 1754864 | 3.9
5748 | Pennsylvania | WASHINGTON |  | 18 | Z124001 | This project is the full replacement of the Pattersons Mill Bridge over the North Fork of Cross Creek on SR 4029 in Cross Creek Township, Washington County. | Bridge Replacement | 07/24/2009 |  | 11/25/2011 | 1191800 | 0.15
5749 | Pennsylvania | WASHINGTON |  | 18 | Z124002 | This project consists of pavement preservation and other miscellaneous construction for State Route 0019, in Washington County, North Strabane Township from approximately Conklin Rd. (T-639) to approx | Pavement Improvement | 07/28/2009 | 08/17/2009 | 01/20/2010 | 835000 | 3.126
5750 | Pennsylvania | WASHINGTON | PITTSBURGH , PA | 12, 18 | Z124003 | This project includes repairing the deteriorating concrete roadway by concrete patches on Interstate 79 from Canonsburg to the Allegheny County Line in Washington County | Pavement Improvement | 10/21/2009 | 10/21/2009 | 10/01/2011 | 16696267 | 14.218
5751 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 12, 18 | Z125001 | This project will consist of existing pavement milling, pavement resurfacing, installing concrete barrier in the median, adding left turn lanes at the following intersections: SR 30/ Monastery Dr (T-7 | Pavement Improvement | 05/07/2009 | 05/20/2009 | 03/15/2010 | 2272000 | 4.005
5752 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 18 | Z125002 | This project consists of existing pavement milling, bituminous pavement overlay, minor drainage improvements, new guide rail, bridge approach slabs, traffic signal improvements for State Route 0030, i | Pavement Improvement | 07/30/2009 | 08/23/9 | 07/22/2010 | 3010000 | 5.434
5753 | Pennsylvania | WESTMORELAND | MONESSEN | 12 | Z125003 | This project consists of steel repairs, bridge beam painting, and concrete pier repairs for State Route over Interstate 70, in Westmoreland County, Rostraver Township. These upgrades will extend the l | Bridge Improvement | 07/01/2009 | 08/22/2009 | 01/19/2010 | 860341 | 0.029
5754 | Pennsylvania | WESTMORELAND |  | 12 | Z125004 | This project is the full bridge replacement of SR 1006 (Moon's Bridge) over a Tubmill Run in Fairfield Township, Westmoreland County. | Bridge Replacement | 07/02/2009 |  | 11/13/2011 | 837891 | 0.008
5755 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 18 | Z125005 | This project will consist of a truss bridge rehabilitation and concrete bridge deck rehabilitation for State Route 993 (Larimer Bridge) over Brush Creek, in Westmoreland County, North Huntingdon Towns | Bridge Improvement | 08/04/2009 |  | 11/08/2010 | 2473179 | 0.028
5756 | Pennsylvania | WESTMORELAND |  | 12 | Z125006 | This project consists of the full replacement of the existing one span concrete bridge of State Route 201 over Pollock Run in Rostraver Township, Westmoreland County. The structurally deficient bridge | Bridge Replacement | 07/17/2009 | 07/27/2009 | 09/10/2010 | 832060 | 0.005
5757 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 18 | Z125007 | This project consists of painting the ends of the bridge beams at expansion joints, repairing bridge pier columns and caps at various locations, jacking and resetting of expansion bearings at piers 3 | Bridge Improvement | 07/13/2009 | 07/20/2009 | 12/27/2009 | 1132170 | 0.175
5758 | Pennsylvania | WESTMORELAND | MONESSEN | 12 | Z125008 | This project includes bridge abutment upgrades, spot painting, pier protection, and new bridge lighting for State Route 981 (Smithton Lo-Level Bridge), in Westmoreland County, Smithton Borough, Rostra | Bridge Improvement | 07/13/2009 | 07/20/2009 | 11/08/2009 | 570000 | 0.136
5759 | Pennsylvania | WESTMORELAND | MONESSEN | 12 | Z125009 | This project includes the enhancing several traffic signalized intersections. The work includes upgrading vehicular and pedestrian signal heads, replacing existing detection sensors, amplifiers, contr | Safety/Traffic Management | 07/29/2009 | 08/24/2009 | 05/09/2010 | 202223 | 1.133
5760 | Rhode Island | WASHINGTON |  | 2 | 0001104 | This project includes excavating planting beds, placing loam and installing new planting material in select locations in the U.S. Route 1 median between Mooresfield Road and the Oliver Stedman Governm | Pavement Improvement | 03/03/2009 | 06/15/2009 | 11/30/2010 | 156981.9 | 3.46
5761 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 2 | 0010011 | This project involves replacement of all signage on Route 10 from Park Avenue/Route 12 in Cranston to I-95 in Providence (5 miles). | Safety/Traffic Management | 05/20/2009 |  | 09/22/2010 | 4403205.41 | 9.9
5762 | Rhode Island | WASHINGTON |  | 2 | 0043002 | This project will rehabilitate both Wyoming Bridges in Hopkinton, which carry Bridge Street over the Wood River, which are presently closed to traffic due to structural deterioration. | Bridge Replacement | 06/03/2009 |  |  | 2791702.65 | 0.033
5763 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1 | 0146020 | This project will resurface Route 146 in Lincoln, from the Route 116 interchange to area of Sherman Avenue and Old Louisquisset Pike/Route 246 interchange, and will include guardrail replacement, join | Pavement Improvement | 09/22/2009 |  |  | 10802278.79 | 1.15
5764 | Rhode Island | WASHINGTON |  | 2 | 0481001 | This project will rehabilitate three bridges at the Dillons Corner Rotary in Narragansett. Work to consist of superstructure replacement of Dillions Corner Bridge (two structures), which carries Route | Bridge Improvement | 06/30/2009 |  | 05/21/2011 | 8344543.05 | 0.099
5765 | Rhode Island | WASHINGTON |  | 1,2 | 0800003 | This project will fund continued long-term maintenance on the Jamestown-Verrazzano Bridge, which carries Route 138 over the West Passage of Narragansett Bay. | Bridge Improvement | 05/26/2009 |  | 09/24/2010 | 1180959.5 | 1.4
5766 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1 | 0882002 | This project will rehabilitate Industrial Drive Bridge, which carries Industrial Drive over the Moshassuck River in Providence, including sidewalk repairs and resurfacing with new pavement. | Bridge Improvement | 06/09/2009 |  |  | 3433107.53 | 0.031
5767 | Rhode Island | WASHINGTON |  | 2 | 0953108 | This project is the first phase of a 25-mile resurfacing project of I-95 from Connecticut line to Exit 8 in Warwick. Stimulus funds will pay for first 7.6 miles from the State line to Exit 3 (Route 13 | Pavement Improvement | 04/15/2009 | 07/13/2009 | 12/09/2009 | 9061550 | 15.06
5768 | Rhode Island | KENT |  | 2 | 2955108 | This project will removal and replace light poles and electrical systems for overhead lighting on I-295 at Exits 1, 2, 4 and 5 in Warwick, Cranston and Johnston. Contract also includes additional traf | Safety/Traffic Management | 03/16/2009 | 07/12/2009 | 11/04/2010 | 3865243.39 | 11.9
5769 | Rhode Island | STATEWIDE |  | 1 | 4444072 | This project involves the application of striping on State roadways in Burrillville, Central Falls, Cumberland, Glocester, Lincoln, North Providence, North Smithfield, Pawtucket, Smithfield and Woonso | Safety/Traffic Management | 03/03/2009 | 05/10/2009 | 11/30/2010 | 1811221.25 | 0
5770 | Rhode Island | STATEWIDE |  | 1,2 | 4444073 | This project involves the application of striping on State roadways in Barrington, Bristol, East Providence, Little Compton, Middletown, Newport, Portsmouth, Providence, Tiverton and Warren. | Safety/Traffic Management | 03/03/2009 | 05/17/2009 | 11/30/2010 | 1695755.5 | 0
5771 | Rhode Island | PROVIDENCE |  | 2 | 8888180 | This enhancement project will improve the Manton Avenue streetscape in Providence, from Delaine Street to Sisson Street, and will include new sidewalks, crosswalks, street trees and street lighting (0 | Safety/Traffic Management | 03/17/2009 | 08/01/2009 | 07/15/2010 | 175547.74 | 0.8
5772 | Rhode Island | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1,2 | 8888181 | This statewide maintenance contract which involves signal repair and minor resurfacing as needed at roughly 60 different intersections throughout the state | Safety/Traffic Management | 06/02/2009 |  | 05/18/2010 | 1245448.96 | 1
5773 | Rhode Island | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 01 | 8888182 | This project will make various traffic signal improvements including the installation of new signals, signal modifications, and island modifications in Barrington, Burrillville, Foster, Johnston, Nort | Safety/Traffic Management | 06/03/2009 |  | 08/18/2010 | 948050.79 | 1
5774 | Rhode Island | STATEWIDE |  | 2 | 8888183 | This project will make various traffic signal improvements including the installation of new signals, signal modifications, and island modifications in Coventry, East Greenwich, Exeter, North Kingstow | Safety/Traffic Management | 09/09/2009 |  |  | 696968.88 | 1
5775 | Rhode Island | STATEWIDE |  | 1,2 | 9999071 | The project involves the replacement and repair of rusted, damaged and/or substandard guardrail throughout the state to improve traffic safety. | Safety/Traffic Management | 03/09/2009 | 05/10/2009 | 03/31/2011 | 848648.82 | 1
5776 | Rhode Island | NEWPORT |  | 1 | AWDA016 | This project will install new sidewalks and curbing on Bristol Ferry Road in Portsmouth, from West Main Road/Route 114 to Boyd's Lane, and will Include intersection improvements and new traffic signal | Pavement Improvement | 03/04/2009 | 05/18/2009 | 11/12/2009 | 1919374.39 | 1.225
5777 | Rhode Island | KENT |  | 2 | AWDA019 | This project includes installation of new sidewalks and curbing in West Warwick on Legion Way, from Main Street to Providence Street, and on Providence Street, from Legion Way to East Main Street/Rout | Pavement Improvement | 03/16/2009 | 07/01/2009 | 09/16/2009 | 881335.99 | 0.7
5778 | Rhode Island | BRISTOL |  | 1 | AWDA020 | This project includes installation of new sidewalks in Warren, including new curbs and curb ramps, on Child Street from Cutler Street to the Massachusetts State line. (2.2 miles). | Pavement Improvement | 04/07/2009 |  | 08/20/2010 | 2397793.22 | 2.2
5779 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 2 | AWDA021 | This project will repair a number of sidewalks in downtown Providence along Washington Street, from Empire Street to Eddy Street, and on Westminster Street, from Empire Street to 100 feet east of Math | Transportation Enhancements | 07/13/2009 |  |  | 1328267.94 | 1.5
5780 | Rhode Island | STATEWIDE |  | 1,2 | DRNG015 | This project involves drainage improvements in the following communities: Hopkinton (Mechanic Street), Johnston (Winsor Avenue at Hawkins Pond), North Smithfield (Greenville Road), and West Greenwich | Pavement Improvement | 03/03/2009 | 06/09/2009 | 09/15/2009 | 585317.75 | 1
5781 | Rhode Island | STATEWIDE |  | 2 | DRNG016 | This project will improve the drainage at the intersection of Ten Rod Road/Route 165 and Black Plain Rd in Exeter. | Pavement Improvement | 03/04/2009 | 06/22/2009 | 09/15/2009 | 273698.97 | 1
5782 | Rhode Island | STATEWIDE |  | 1,2 | DRNG018 | This project involves various drainage improvements in the following communities: Cranston (Pippin Orchard Road), Lincoln (River Road/Route 126), and Narragansett (Bridgetown Road). | Pavement Improvement | 05/20/2009 |  | 10/30/2009 | 222753.47 | 1
5783 | Rhode Island | STATEWIDE |  | 1,2 | MAIN022 | This project involves the power washing of 65 of Rhode Island's 772 bridges to remove road salts, dirt and bird droppings. Includes bridges located in the following towns: Cumberland, East Providence, | Bridge Improvement | 03/03/2009 |  |  | 1391634.55 | 1
5784 | Rhode Island | STATEWIDE |  | 1,2 | MAIN023 | This project will power wash bridges to remove road salts, dirt and bird droppings. Includes bridges located in the following towns: Burrillville, Charlestown, Cranston, East Greenwich, Exeter, Hopkin | Bridge Improvement | 03/03/2009 | 06/29/2009 | 11/30/2009 | 461518 | 1
5785 | Rhode Island | PROVIDENCE |  | 1 | R012009 | This project will result in the construction of a 400-foot rocky seawall along the shoreline of the Seekonk River in East Providence and will include salt marsh mitigation, installation of a stone dus | Other | 03/04/2009 | 06/20/2009 | 11/10/2009 | 425169.72 | 1
5786 | Rhode Island | PROVIDENCE |  | 2 | RESF136 | This project will resurface Putnam Pike/Route 44 in Glocester, from Tourtellot Hill Road to the RIDOT Maintenance Facility, and will include drainage improvements and guardrail replacement (2 miles). | Pavement Improvement | 03/06/2009 | 06/29/2009 | 08/26/2009 | 1324323.93 | 1.202
5787 | Rhode Island | PROVIDENCE |  | 1 | RESF137 | This project will resurface Putnam Pike/Route 44 in Smithfield, from Austin Avenue to West Greenville Road, and will include replacement of sidewalks and curbing, drainage improvements, and a new sign | Pavement Improvement | 04/07/2009 | 08/03/2009 | 05/07/2010 | 2072739.3 | 0.998
5788 | Rhode Island | NEWPORT |  | 1 | RESF138 | This project will resurface Main Road/Route 138 in Tiverton, from John Street to the Massachusetts State Line, and will include curbing, sidewalks, and drainage and guardrail improvements (2.3 miles). | Pavement Improvement | 03/03/2009 | 03/23/2009 | 09/21/2009 | 2840557.66 | 2.375
5789 | Rhode Island | PROVIDENCE |  | 1 | RESF139 | This project will resurface Old Louisquisset Pike/Route 246 in Lincoln, from Breakneck Hill Road/Route 123 to Route 116/Route 146 interchange (2.3 miles). | Pavement Improvement | 03/03/2009 | 05/18/2009 | 09/18/2009 | 1632539.58 | 2.318
5790 | Rhode Island | NEWPORT |  | 1 | RESF144 | This project will resurface West Main Road in Middletown, from Coddington Highway to John Kesson Lane, and will include curbing and sidewalk replacement, new signage and pavement markings, replacement | Pavement Improvement | 03/06/2009 | 05/25/2009 | 10/06/2010 | 5882718.35 | 2.22
5791 | Rhode Island | STATEWIDE |  | 1,2 | RESF147 | This project involves the application of a rubberized asphalt chip seal on top of existing pavement to extend pavement service life. Roads will be sealed in Burrillville, Charlestown, Coventry, East G | Pavement Improvement | 03/03/2009 | 06/03/2009 | 09/03/2009 | 2504018.26 | 21.8
5792 | Rhode Island | STATEWIDE |  | 1,2 | RESF148 | This project involves the cleaning and sealing of cracks and open joints in existing pavement with a hot applied rubberized asphalt sealant to extend the pavement service life of roads in the southern | Pavement Improvement | 03/31/2009 | 07/13/2009 | 09/30/2009 | 239338 | 1
5793 | Rhode Island | STATEWIDE |  | 1,2 | RESF149 | This project involves cleaning and sealing cracks and open joints in existing pavement with a hot applied rubberized asphalt sealant to extend the pavement service life of the roads in the northern an | Pavement Improvement | 03/31/2009 | 08/03/2009 | 09/30/2009 | 226057.8 | 1
5794 | Rhode Island | WASHINGTON |  | 2 | RESF151 | This project will resurface Kingstown Road/Route 138 in Richmond, from Beaver River Road to 660 feet west of Route 112 (2 miles). | Pavement Improvement | 05/04/2009 | 07/22/2009 | 11/06/2009 | 2802073.89 | 2.22
5795 | Rhode Island | WASHINGTON |  | 2 | RESF153 | This project will resurface Ocean Road in Narragansett, from Narragansett Town Beach to Point Judith (3.7 miles), and Shore Road in Westerly, from Post Road to Ocean View Highway (4.5 miles). | Pavement Improvement | 03/09/2009 | 05/18/2009 | 10/15/2009 | 3003428.08 | 8.729
5796 | Rhode Island | PROVIDENCE |  | 2 | RESF159 | This project will add chip seal overlay along Hartford Pike/Route 101, from the Connecticut State line to Route 94 in Foster, and from Anan Wade Road to Route 102 in Scituate (4 miles). | Pavement Improvement | 05/14/2009 |  | 10/30/2009 | 1640832.43 | 4.201
5797 | Rhode Island | PROVIDENCE |  | 1 | RESF160 | This project will resurface Nate Whipple Highway/Route 120 in Cumberland, from Diamond Hill Road/Route 114 to Mendon Road/Route 122, and will include new curbing, sidewalk, guardrail, minor drainage w | Pavement Improvement | 03/06/2009 | 06/01/2009 | 11/30/2009 | 2791050 | 2.628
5798 | Rhode Island | PROVIDENCE |  | 1 | RESF166 | This project will resurface Nate Whipple Highway/Route 120, in Cumberland, from Diamond Hill Road/Route 114 to the Massachusetts State line, and will include new curbing, sidewalk, guardrail, minor dr | Pavement Improvement | 06/09/2009 |  | 08/20/2010 | 1870898.88 | 1.7
5799 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1 | RESF170 | This project will resurface Diamond Hill Road/Route 114 in Woonsocket, from Social Street to Bound Road, and will include curbing, sidewalks, guardrail, minor drainage improvements, and signal work (2 | Pavement Improvement | 08/03/2009 |  | 10/22/2010 | 4455588.1 | 2.16
5800 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 2 | RESF174 | This project involves reconstruction of Hartford Avenue/Route 6A in Johnston, from the I-295 interchange to Atwood Avenue/Route 5, and will include curbing, sidewalks, widening a portion to provide a | Pavement Improvement | 05/20/2009 |  | 10/29/2010 | 4291253.67 | 2.542
5801 | Rhode Island | PROVIDENCE |  | 1 | RESF175 | This project will resurface High Street/Diamond Hill Road/Route 114 in Woonsocket, from the Cumberland Public Library to Blackstone Street, and will include curbing, sidewalk, guardrail, minor drainag | Pavement Improvement | 09/09/2009 |  |  | 1461894.6 | 1.021
5802 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 2 | RESF178 | This project involves the resurfacing of three streets in Providence, from West Exchange Street to Point Street, encompassing Dean Street, Cahir Street and Stewart Street. It will include upgraded sig | Pavement Improvement | 05/20/2009 |  | 12/14/2010 | 4636641.58 | 0.739
5803 | Rhode Island | WASHINGTON |  | 2 | RESF179 | This project will resurface Oak Street/Westerly Bradford Road/Route 91 in Westerly, from Route 3 to Westerly Maintenance Facility, and will include new sidewalks, minor drainage improvements, water li | Pavement Improvement | 06/17/2009 |  | 10/21/2009 | 3779852.1 | 1.305
5804 | Rhode Island | PROVIDENCE |  | 2 | SDRP007 | This project involves the construction of a storm water treatment pond at the interchange of Route 6 on the Providence/Johnston line at the Killingly Street/Route 128 exit. | Other | 03/03/2009 | 04/13/2009 | 10/16/2009 | 917943.77 | 1
5805 | Rhode Island | PROVIDENCE |  | 1,2 | SDRP008 | This project will review approximately 60 out of 130 storm water drainage systems, ponds, catch basins, etc. that were previously upgraded to meet Federal Best Management Practices, in accordance with | Other | 06/04/2009 |  |  | 197832.4 | 1
5806 | Rhode Island | STATEWIDE |  | 1,2 | SIGN015 | This project will replace signage along I-95 at Exits 6, 7 and 8 (West Greenwich, East Greenwich, West Warwick, and Warwick), Exit 12B (Warwick), Exists 16-18 (Cranston and Providence), and Exit 29 (P | Safety/Traffic Management | 03/09/2009 |  | 07/07/2010 | 3001224.46 | 15.003
5807 | Rhode Island | PROVIDENCE |  | 2 | SIGN016 | This project will replace all road signage on Route 37 from Post Road/Route 1 in Warwick to Natick Avenue in Cranston (3.2 miles). | Safety/Traffic Management | 03/09/2009 | 07/20/2009 | 08/26/2010 | 3221335.62 | 6.424
5808 | Rhode Island | PROVIDENCE |  | 2 | TEA2060 | This enhancement project will improve the Manton Avenue streetscape in Providence, from Delaine Street to Sisson Street, and will include new sidewalks, crosswalks, street trees and street lighting (0 | Transportation Enhancements | 03/17/2009 | 08/01/2009 | 12/01/2010 | 500000 | 0.77
5809 | Rhode Island | PROVIDENCE |  | 02 | TEAC090 | This project will improve the Westminster Street streetscape in Providence, from Service Road No. 7 to Olneyville Square/Manton Avenue/Plainfield Street, and will include sidewalks, crosswalks, bicycl | Transportation Enhancements | 06/11/2009 |  |  | 3300000 | 1.223
5810 | Rhode Island | STATEWIDE |  | 1,2 | TRMS009 | This project involves the installation of radar-based vehicle detectors, at the same location as existing traffic cameras, to collect data on traffic volume and speeds. The new detectors provide alert | Safety/Traffic Management | 03/09/2009 | 06/07/2009 | 06/11/2010 | 382888.54 | 0
5811 | Rhode Island | STATEWIDE |  | 1,2 | TRMS010 | This project involves the installation of radar-based vehicle detectors in several locations to collect data on traffic volume, speed, and vehicle classification used for annual reporting requirements | Safety/Traffic Management | 03/03/2009 | 05/31/2009 | 06/16/2010 | 913832.26 | 0
5812 | South Carolina | AIKEN |  | 3 | SP09001 | Resurfacing various road in Aiken County. | Pavement Improvement | 01/25/2010 |  | 10/31/2010 | 3009977.47 | 0
5813 | South Carolina | KERSHAW |  | 5 | SP09002 | Resurfacing various roads in Kershaw County. | Pavement Improvement | 02/04/2010 |  | 07/31/2010 | 2480329.86 | 0
5814 | South Carolina | RICHLAND |  | 6 | SP09005 | Resurfacing various roads in Richland County. | Pavement Improvement | 07/31/2009 | 07/29/2009 | 11/30/2009 | 2343090.99 | 2.42
5815 | South Carolina | ANDERSON |  | 3 | SP09014 | Resurfacing various roads in Anderson County. | Pavement Improvement | 07/31/2009 | 07/31/2009 | 04/30/2010 | 3389929.67 | 0
5816 | South Carolina | MARION, FLORENCE |  | 6 | SP09028 | Resurfacing various roads in Florence and Marion Counties. | Pavement Improvement | 06/26/2009 | 08/03/2009 | 06/30/2010 | 4479716.13 | 0
5817 | South Carolina | GEORGETOWN, WILLIAMSBURG, HORRY |  | 1 | SP09029 | Resurfacing various roads in Georgetown and Horry Counties. | Pavement Improvement | 08/17/2009 | 08/31/2009 | 05/31/2010 | 8228104.08 | 3.36
5818 | South Carolina | BERKELEY |  | 6 | SP09035 | Resurfacing various roads in Berkeley County. | Pavement Improvement | 07/15/2009 | 08/10/2009 | 11/30/2009 | 1914024.75 | 2.5
5819 | South Carolina | BERKELEY, CHARLESTON |  | 6 | SP09036 | Pavement Reconstruction/Rehab | Pavement Improvement | 11/13/2009 |  | 11/30/2010 | 2867171.49 | 0
5820 | South Carolina | STATEWIDE |  | 6 | SP09044 | Resurfacing various roads in Orangeburg County. | Pavement Improvement | 02/02/2010 |  | 08/31/2010 | 4883991.06 | 0
5821 | South Carolina | KERSHAW |  | 5 | SP09048 | Resurfacing various roads in Kershaw County. | Pavement Improvement | 07/17/2009 | 07/14/2009 | 11/30/2009 | 1366589.44 | 0.56
5822 | South Carolina | SUMTER, LEE |  | 5, 6 | SP09049 | Resurfacing various roads in Lee County. | Pavement Improvement | 08/05/2009 | 08/05/2009 | 05/31/2010 | 2501220.77 | 0
5823 | South Carolina | LEXINGTON |  | 2 | SP09050 | Resurfacing various roads in Lexington County. | Pavement Improvement | 08/24/2009 | 08/26/2009 | 04/30/2010 | 3273380.28 | 0
5824 | South Carolina | GREENWOOD, LAURENS, ABBEVILLE |  | 3 | SP09053 | Resurfacing various roads in Abbeville, Greenwood, and Laurens Counties. | Pavement Improvement | 06/09/2009 | 09/10/2009 | 05/31/2010 | 6117334.59 | 0
5825 | South Carolina | EDGEFIELD, NEWBERRY, SALUDA, MCCORMICK |  | 3 | SP09054 | Resurfacing various roads in Edgefield, McCormick, Newberry, and Saluda Counties. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 05/31/2010 | 5562117.73 | 9.92
5826 | South Carolina | GREENVILLE |  | 4 | SP09061 | Resurfacing various roads in Greenville County. | Pavement Improvement | 07/24/2009 | 07/27/2009 | 04/30/2010 | 5497874.66 | 0
5827 | South Carolina | OCONEE |  | 3 | SP09062 | Resurfacing various roads in Oconee County. | Pavement Improvement | 06/19/2009 | 06/12/2009 | 11/30/2009 | 2413293.95 | 0
5828 | South Carolina | PICKENS |  | 3 | SP09063 | Resurfacing various roads in Pickens County. | Pavement Improvement | 07/10/2009 | 07/16/2009 | 04/30/2010 | 2487281.1 | 0
5829 | South Carolina | SPARTANBURG |  | 4 | SP09064 | Resurfacing various roads in Spartanburg County. | Pavement Improvement | 11/19/2009 |  | 11/30/2010 | 5071592.61 | 0
5830 | South Carolina | CHEROKEE, UNION |  | 5 | SP09065 | Resurfacing various roads in Cherokee and Union Counties. | Pavement Improvement | 06/19/2009 | 07/20/2009 | 05/31/2010 | 2302842.63 | 5.47
5831 | South Carolina | CHESTER |  | 5 | SP09066 | Resurfacing various roads in Chester County. | Pavement Improvement | 06/19/2009 | 07/06/2009 | 04/30/2010 | 1300877.82 | 0
5832 | South Carolina | CHESTERFIELD |  | 5 | SP09067 | Resurfacing various roads in Chesterfield County. | Pavement Improvement | 07/10/2009 | 07/06/2009 | 11/30/2009 | 1592520.82 | 0
5833 | South Carolina | LANCASTER |  | 5 | SP09069 | Resurfacing various roads in Lancaster County. | Pavement Improvement | 07/24/2009 | 07/27/2009 | 11/30/2009 | 1813681.97 | 0
5834 | South Carolina | YORK |  | 5 | SP09071 | Resurfacing various roads in York County. | Pavement Improvement | 07/24/2009 | 06/24/2009 | 11/30/2009 | 1905153.79 | 0
5835 | South Carolina | DILLON, DARLINGTON, MARLBORO |  | 5 | SP09072 | Resurfacing various roads in Darlington, Dillion, and Marlboro Counties. | Pavement Improvement | 07/17/2009 | 09/03/2009 | 05/31/2010 | 3662322.67 | 0
5836 | South Carolina | BEAUFORT |  | 2 | SP09080 | Resurfacing various roads in Beaufort County. | Pavement Improvement | 07/31/2009 | 08/14/2009 | 10/31/2009 | 2293705.65 | 0
5837 | South Carolina | CHARLESTON |  | 1, 6 | SP09082 | Resurfacing various roads in Charleston County. | Pavement Improvement | 07/10/2009 | 08/12/2009 | 11/30/2009 | 2704835.67 | 0
5838 | South Carolina | COLLETON |  | 6 | SP09083 | Resurface various roads in Colleton County. | Pavement Improvement | 07/24/2009 | 10/15/2009 | 11/30/2009 | 1928204.41 | 0
5839 | South Carolina | DORCHESTER |  | 1, 6 | SP09084 | Resurfacing various roads in Dorchester County. | Pavement Improvement | 07/24/2009 | 09/03/2009 | 11/30/2009 | 1729762.43 | 0
5840 | South Carolina | JASPER |  | 2 | SP09085 | Resurfacing various roads in Jasper County. | Pavement Improvement | 07/31/2009 | 08/18/2009 | 11/30/2009 | 1729264.13 | 2.42
5841 | South Carolina | BAMBERG, HAMPTON, ALLENDALE, BARNWELL |  | 2 | SP09086 | Resurfacing various roads in Allendale, Bamberg, Barnwell, and Hampton Counties. | Pavement Improvement | 06/09/2009 | 07/15/2009 | 05/31/2010 | 4556504.78 | 0
5842 | South Carolina | CLARENDON, ORANGEBURG, CALHOUN |  | 6, 2 | SP09089 | Resurfacing various roads in Calhoun, Clarendon, and Orangeburg Counties. | Pavement Improvement | 06/19/2009 | 06/29/2009 | 05/31/2010 | 4957777.28 | 0
5843 | South Carolina | AIKEN |  | 3 | SP09093 | Resurfacing various roads in Aiken County. | Pavement Improvement | 01/21/2010 |  | 09/30/2010 | 3086735.13 | 0
5844 | South Carolina | RICHLAND |  | 6 | SP09095 | Resurfacing various roads in Richland County. | Pavement Improvement | 09/26/2009 |  | 08/31/2010 | 2024617.01 | 0
5845 | South Carolina | SPARTANBURG |  | 4 | SP09110 | Resurfacing various roads in Spartanburg County. | Pavement Improvement | 01/20/2010 |  | 04/30/2011 | 9150459.55 | 0
5846 | South Carolina | CHEROKEE |  | 5 | SP09111 | Resurfacing various roads in Cherokee County. | Pavement Improvement | 11/23/2009 |  | 06/30/2010 | 2176549.67 | 0
5847 | South Carolina | CHESTER |  | 5 | SP09112 | Resurfacing various roads in Cherster County. | Pavement Improvement | 11/12/2009 |  | 07/30/2010 | 1515069.71 | 3.34
5848 | South Carolina | CHESTERFIELD |  | 5 | SP09113 | Resurfacing various roads in Chesterfield County. | Pavement Improvement | 12/01/2009 |  | 08/31/2010 | 3187544.2 | 0.79
5849 | South Carolina | LANCASTER |  | 5 | SP09115 | Resurfacing various roads in Lancaster County. | Pavement Improvement | 02/02/2010 |  | 07/31/2010 | 2385184.77 | 0
5850 | South Carolina | DILLON, DARLINGTON, MARLBORO |  | 5 | SP09118 | Resurfacing various roads in Dillon, Darlington, and Marlboro Counties. | Pavement Improvement | 01/06/2010 |  | 05/31/2011 | 4782577.62 | 8.82
5851 | South Carolina | WILLIAMSBURG, FLORENCE |  | 6 | SP09125 | Resurfacing various roads in Florence County. | Pavement Improvement | 11/05/2009 | 12/28/2009 | 06/30/2011 | 7678448.91 | 8.68
5852 | South Carolina | CALHOUN |  | 2 | SP09135 | Resurfacing various roads in Calhoun County. | Pavement Improvement | 02/02/2010 |  | 07/31/2010 | 1286276.33 | 2.66
5853 | South Carolina | RICHLAND |  | 6 | SP09143 | Resurfacing various roads in Richland County. | Pavement Improvement | 06/19/2009 | 07/17/2009 | 11/30/2009 | 2138817.41 | 0
5854 | South Carolina | OCONEE, PICKENS |  | 3 | SP09154 | Resurfacing various roads in Oconee and Pickens Counties. | Pavement Improvement | 10/26/2009 | 10/28/2009 | 09/30/2010 | 2229416.86 | 0
5855 | South Carolina | YORK |  | 5 | SP09163 | Resurfacing various roads in York County. | Pavement Improvement | 11/27/2009 |  | 11/30/2010 | 1702975.78 | 3.96
5856 | South Carolina | STATEWIDE |  | 1, 6 | SPBR001 | Replacement of eight bridges on US 378 over the Little Pee Dee River and Maple Swamp areas of Marion and Horry Counties. | Bridge Replacement | 07/10/2009 |  | 10/31/2011 | 21000000 | 7.2
5857 | South Carolina | LAURENS |  | 3 | SPBR002 | Replacement of bridge over Durbin Creek on Allen Bridge Road in Laurens County 14.8 miles west of Laurens. | Bridge Replacement | 11/11/2009 | 11/18/2009 | 11/30/2010 | 1331973.78 | 0.1
5858 | South Carolina | EDGEFIELD |  | 3 | SPBR003 | Replacement of bridge over Turkey Creek on Weaver Road in Edgefield County 3.1 miles west of Johnston SC, and replacement of bridge over Bartly Branch on Bland Baptist Road 2.5 miles north west of Joh | Bridge Replacement | 09/23/2009 | 10/26/2009 | 07/31/2010 | 1891689.08 | 0.2
5859 | South Carolina | CHARLESTON | CHARLESTON | 1 | SPBR005 | Replacement of bridge over Tidal Creek on Brickyard Road in Charleston County. | Bridge Replacement | 07/24/2009 | 07/27/2009 | 04/30/2010 | 521042.29 | 0
5860 | South Carolina | JASPER |  | 2 | SPBR007 | Replace bridge to Knowles Island in Jasper County. | Bridge Replacement | 10/12/2009 | 10/12/2009 | 06/30/2010 | 1619971.75 | 0.04
5861 | South Carolina | KERSHAW, LEE |  | 5 | SPEH001 | Sidewalk repairs, replacement, and construction in various locations in Kershaw and Lee Counties. | Transportation Enhancements | 10/12/2009 | 11/04/2009 | 06/30/2010 | 271356.3 | 0
5862 | South Carolina | LEXINGTON |  | 2 | SPEH003 | Sidewalk repairs, replacement, and construction in various locations in Lexington County. | Transportation Enhancements | 11/16/2009 | 11/16/2009 | 07/31/2010 | 318476.49 | 0
5863 | South Carolina | YORK |  | 5 | SPEH004 | Sidewalk repairs, replacement, and construction in various locations in York County | Transportation Enhancements | 01/23/2010 |  | 07/31/2010 | 526455.43 | 0
5864 | South Carolina | RICHLAND, LEXINGTON |  | 2,6 | SPEH007 | Sidewalk repairs, replacement, and construction in various locations in Richland County | Transportation Enhancements | 01/18/2010 |  | 12/31/2010 | 688243.5 | 0
5865 | South Carolina | GREENWOOD, EDGEFIELD |  | 3 | SPEH014 | Sidewalk repairs, replacement, and construction in various locations in Edgefield, Greenwood, and McCormick Counties | Transportation Enhancements | 12/23/2009 |  | 06/30/2010 | 660122.48 | 0
5866 | South Carolina | GREENVILLE |  | 4 | SPEH020 | Sidewalk repairs, replacement, and construction in various locations in Greenville County | Transportation Enhancements | 12/01/2009 |  | 07/31/2010 | 673205.15 | 0
5867 | South Carolina | OCONEE, PICKENS |  | 3 | SPEH024 | Sidewalk repairs, replacement, and construction in various locations in Oconee and Pickens Counties | Transportation Enhancements | 02/02/2010 |  | 06/30/2010 | 536991.48 | 0
5868 | South Carolina | CHESTER, FAIRFIELD |  | 5 | SPEH029 | Sidewalk repairs, replacement, and construction in various locations in Chester County | Transportation Enhancements | 12/10/2009 |  | 08/31/2010 | 413370 | 0
5869 | South Carolina | CHESTERFIELD, LANCASTER |  | 5 | SPEH030 | Sidewalk repairs, replacement, and construction in various locations in Chesterfield County | Transportation Enhancements | 11/19/2009 |  | 10/10/2010 | 597586.98 | 0
5870 | South Carolina | DILLON, DARLINGTON, MARLBORO |  | 5 | SPEH037 | Sidewalk repairs, replacement, and construction in various locations in Darlingtion, Dillon, and Marlboro Counties | Transportation Enhancements | 09/28/2009 | 09/28/2009 | 04/30/2010 | 285364.22 | 0
5871 | South Carolina | DILLON, DARLINGTON, MARLBORO, FLORENCE |  | 5,6 | SPEH045 | Sidewalk repairs, replacement, and construction in various locations in Darlington, Dillon, Florence, and Marlboro Counties. | Transportation Enhancements | 12/27/2009 | 12/29/2009 | 06/30/2010 | 265725.97 | 0
5872 | South Carolina | GEORGETOWN, MARION, WILLIAMSBURG, HORRY |  | 1,6 | SPEH050 | Sidewalk repairs, replacement, and construction in various locations in Georgetown, Horry, Marion, and Williamsburg Counties. | Transportation Enhancements | 12/27/2009 |  | 06/30/2010 | 139104 | 0
5873 | South Carolina | BAMBERG, HAMPTON, ALLENDALE, BARNWELL |  | 2,6 | SPEH065 | Sidewalk repairs, replacement, and construction in various locations in Allendale, Bamberg, Barnwell, Hampton Counties | Transportation Enhancements | 12/07/2009 |  | 07/31/2010 | 358502.1 | 0
5874 | South Carolina | CLARENDON, ORANGEBURG, CALHOUN |  | 6,2 | SPEH068 | Sidewalk repairs, replacement, and construction in various locations in Calhoun, Clarendon, and Orangeburg Counties | Transportation Enhancements | 02/02/2010 |  | 06/30/2010 | 471919.61 | 0
5875 | South Carolina | STATEWIDE |  | 2, 6 | SPIM001 | Resurface and rehabilitate the east bound lane of I-20 in Lexington and Richland Counties from approximately US-378 to approximately US-321. | Pavement Improvement | 09/14/2009 | 09/14/2009 | 10/31/2010 | 10540556.3 | 10
5876 | South Carolina | AIKEN |  | 3 | SPIM002 | Resurface and rehabilitate the east bound lane of I-20 in Aiken County from approximately US-1 to approximately US-178. | Pavement Improvement | 08/24/2009 | 08/24/2009 | 09/30/2010 | 11868849.35 | 16
5877 | South Carolina | RICHLAND | COLUMBIA | 6 | SPIM003 | Resurface and rehabilitate the south bound lane of I-77 in Richland County from approximately S-151 to approximately US-1 | Pavement Improvement | 09/08/2009 | 09/08/2009 | 06/30/2010 | 2745808.23 | 5
5878 | South Carolina | CLARENDON |  | 6 | SPIM004 | Resurface and rehabilitate the south bound lane of I-95 in Clarendon County from approximately mile marker 99 to approximately mile marker 100. | Pavement Improvement | 08/10/2009 | 08/23/2009 | 07/31/2010 | 4542026.62 | 6
5879 | South Carolina | CHARLESTON | CHARLESTON | 1 | SPIM005 | Resurface and rehabilitate the east bound and west bound lane of I-26 in Charleston County from approximately mile marker 212 near I-526 to approximately mile marker 218 at Heriot Steet. | Pavement Improvement | 08/26/2009 | 09/30/2009 | 04/30/2011 | 14668347.24 | 18
5880 | South Carolina | JASPER |  | 2 | SPIM008 | Resurface and rehabilitate a portion of I-95 in Jasper County from approximately mile marker 18.3 to approximately mile marker 23.9 | Pavement Improvement | 09/18/2009 | 09/18/2009 | 06/30/2010 | 4882506.75 | 4.89
5881 | South Carolina | FLORENCE |  | 6 | SPIM010 | Resurface and rehabilitate the north bound lane of I-95 in Florence County from approximately mile marker 156 to approximately mile marker 161. | Pavement Improvement | 10/15/2009 | 10/15/2009 | 08/31/2010 | 1951212.7 | 5
5882 | South Carolina | GREENVILLE | GREENVILLE | 3 | SPIM012 | Resurface and rehabilitate Northbound I-185, from I-85 to Road S-260 near Greenville | Pavement Improvement | 02/08/2010 |  | 10/31/2010 | 2394585.57 | 0
5883 | South Carolina | ANDERSON | ANDERSON | 3 | SPMC001 | Construction of a five lane roadway on new location in Anderson County known as the East - West Connector from US76-US178 (Clemson Boulevard) to SC Route 81 (Greenville Street). | New Construction | 10/20/2009 | 10/20/2009 | 10/31/2011 | 7363520.32 | 0
5884 | South Carolina | PICKENS | GREENVILLE | 3 | SPMC002 | Intersection improvement project at Calhoun Memorial Highway and Prince Perry in Easley, SC and includes replacing the bridge over the CSX railroad . | Pavement Improvement | 12/14/2009 |  | 09/30/2010 | 5382417.52 | 0.85
5885 | South Carolina | NEWBERRY |  | 5 | SPMC004 | Intersection improvement in Newberry County at SC Route 391 and Stoney Hill Road and Mt. Pillgram Road. | Pavement Improvement | 02/09/2010 |  | 05/31/2010 | 160000 | 0.1
5886 | South Carolina | BEAUFORT |  | 2 | SPMC006 | Widening from two lanes to five lanes Simmonsville Road in Bluffton, SC from US78 to Bluffton Parkway. Adding a lane eastbount and westbound to the existing 2 lanes along with a center turing lane | Pavement Widening | 06/28/2009 |  | 11/30/2010 | 7000000 | 0.75
5887 | South Carolina | HORRY |  | 1 | SPMC009 | Intersection improvement project at US 17 Mineola Avenue in Horry County. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 06/30/2010 | 329373.91 | 0.28
5888 | South Carolina | GEORGETOWN |  | 1 | SPMC010 | Improvement of intersection of Fraiser Street and Front Street in Georgetown, SC. The project improvement includes signal upgrades, additonal pedestrian signals, and crosswalk and sidewalk improvement | Pavement Improvement | 01/04/2010 |  | 06/30/2010 | 194403.49 | 0
5889 | South Carolina | YORK | ROCK HILL | 5 | SPMC018 | Widening of SC 5 Bypass from the interection of SC 5 Business and SC 161 on the east side of York , SC westward to SC 5 (Black Highway). This project is a part of the 1997 Pennies for Progress Progra | Pavement Widening | 12/27/2009 |  | 08/31/2012 | 5750000 | 4.24
5890 | South Carolina | HORRY | MYRTLE BEACH | 1 | SPMC019 | New Construction from SC 544 to SC 707 to include clearing of new location and relocation of utilities. | Other | 01/04/2010 | 01/04/2010 | 06/27/2011 | 8838395.05 | 0
5891 | South Carolina | BERKELEY |  | 1 | SPMC027 | Widening of US 17 Alternate in Moncks Corner, SC by adding additional 2 lanes with center turning lane infrom Cypress Garden Road to near Moncks Corner. | Pavement Widening | 11/16/2009 |  | 06/30/2012 | 1000000 | 7.3
5892 | South Carolina | STATEWIDE |  | 5 | SPSA004 | Pavement marking project on Interstate 20 in Kershaw and Lee Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime | Safety/Traffic Management | 07/24/2009 | 07/14/2009 | 10/31/2009 | 641424 | 32.9
5893 | South Carolina | STATEWIDE |  | 3, 4 | SPSA005 | Pavement marking project on Interstate 26 in Laurens and Spartanburg Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve | Safety/Traffic Management | 08/03/2009 | 08/20/2009 | 10/31/2009 | 341188.9 | 17.4
5894 | South Carolina | STATEWIDE |  | 5 | SPSA006 | Pavement marking project on Interstate 77 in Chester and Fairfield Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve da | Safety/Traffic Management | 07/17/2009 | 08/19/2009 | 10/31/2009 | 267323.25 | 14.1
5895 | South Carolina | FLORENCE |  | 6 | SPSA007 | Pavement marking project on Interstate 95 in Florence County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night | Safety/Traffic Management | 06/26/2009 | 06/19/2009 | 10/31/2009 | 341576.45 | 12
5896 | South Carolina | AIKEN |  | 3 | SPSA008 | Pavement marking project on Interstate 20 in Aiken County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night ti | Safety/Traffic Management | 08/03/2009 | 08/22/2009 | 11/20/2009 | 297499.95 | 0
5897 | South Carolina | RICHLAND |  | 2 | SPSA009 | Pavement marking project on Interstate 20 in Richland County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night | Safety/Traffic Management | 09/01/2009 | 11/02/2009 | 11/20/2009 | 244560.15 | 7
5898 | South Carolina | STATEWIDE |  | 2, 5 | SPSA010 | Pavement marking project on Interstate 77 in Fairfield and Richland Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve d | Safety/Traffic Management | 07/16/2009 |  | 11/20/2009 | 559817.7 | 23.4
5899 | South Carolina | COLLETON |  | 6 | SPSA011 | Pavement marking project on Interstate 95 in Colleton County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night | Safety/Traffic Management | 07/31/2009 | 10/23/2009 | 11/20/2009 | 170717.5 | 6.8
5900 | South Carolina | SPARTANBURG |  | 4 | SPSA012 | Pavement marking project on Interstate 26 in Spartanburg County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and ni | Safety/Traffic Management | 07/24/2009 | 10/06/2009 | 06/30/2010 | 332034.9 | 21.2
5901 | South Carolina | STATEWIDE |  | 5 | SPSA013 | Pavement marking project on Interstate 20 in Darlington and Lee Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve dayti | Safety/Traffic Management | 08/10/2009 | 08/04/2009 | 06/30/2010 | 385296.58 | 18.3
5902 | South Carolina | CHARLESTON |  | 1 | SPSA014 | Pavement marking project on Interstate 526 in Charleston County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and ni | Safety/Traffic Management | 07/30/2009 | 10/28/2009 | 06/30/2010 | 213296.54 | 7
5903 | South Carolina | LEXINGTON |  | 2 | SPSA016 | Install fiber optic lines along various interstates and Fish Hatchery Road to connect to the Emergency Management Division office for the purpose of monitoring traffic camers in emergency situations. | Safety/Traffic Management | 07/01/2009 | 10/26/2009 | 02/26/2010 | 652005.96 | 0
5904 | South Carolina | LEXINGTON | COLUMBIA | 2 | SPSA017 | Realign and add turn lanes on Fish Hatchery Road in Lexington County. This project is to improve safety along Fish Hactchery Road | Safety/Traffic Management | 10/19/2009 |  | 09/30/2010 | 691835.19 | 0.3
5905 | South Carolina | DARLINGTON |  | 5 | SPSA018 | Addition of turn lanes at the intersection of US 15 and S-10 in Darlington County. | Safety/Traffic Management | 07/24/2009 | 08/03/2009 | 11/30/2009 | 1364511.43 | 1.5
5906 | South Carolina | ANDERSON |  | 3 | SPSA019 | Improvement of interestion of Lane Avenue and S-283 (road) in Anderson County to realign, add turn lanes, and signals. | Pavement Improvement | 08/13/2009 | 08/13/2009 | 11/15/2009 | 411913.15 | 0.1
5907 | South Carolina | CHEROKEE |  | 5 | SPSA020 | Safety Improvement to flatten curve on SC105 in Cherokee County | Safety/Traffic Management | 09/21/2009 | 09/21/2009 | 08/31/2010 | 945740.33 | 0.65
5908 | South Carolina | RICHLAND |  | 2 | SPSA021 | Install gardrail at various locations along Wilson Road in Richland County. | Safety/Traffic Management | 08/10/2009 | 08/27/2009 | 10/31/2009 | 198366.78 | 0.199
5909 | South Carolina | STATEWIDE |  | 3, 4 | SPSA022 | Upgrade signal by installing LED signal heads at various interestions through out District 2 - Abbeville, Anderson, Edgefield, Greenwood, Laurens, McCormick, Newberry, and Saluda Counties. | Safety/Traffic Management | 08/19/2009 | 08/24/2009 | 08/31/2010 | 1555356.39 | 0
5910 | South Carolina | STATEWIDE |  |  | SPSA023 | Upgrade signal by installing LED signal heads at various interestions through out District 3 - Greenivlle, Oconee, Pickens, Spartanburg Counties. | Safety/Traffic Management | 08/04/2009 | 10/06/2009 | 06/30/2010 | 1024357 | 0
5911 | South Carolina | CHARLESTON, STATEWIDE |  | 1 | SPSA025 | Installation of fiber optic cable along I-526 from Clements Ferry Road to Johnny Dodds Boulevard. | Safety/Traffic Management | 08/05/2009 | 10/06/2009 | 04/30/2010 | 618961.12 | 9
5912 | South Carolina | MARION |  | 6 | SPSA030 | Intersection improvement at US76 Wahee Road and SC 576. Improvement includes adding turn lanes and signals. | Pavement Improvement | 12/27/2009 |  | 08/31/2010 | 881027.28 | 0.39
5913 | South Dakota | HAND |  | 00 | 0014165 | This pavement grinding project will extend the life of US Highway 14 from Miller to east of Wessington. The project will also improve safety as the result of a smoother driving surface. | Pavement Improvement | 03/27/2009 | 06/01/2009 | 10/02/2009 | 1679515.65 | 18.7
5914 | South Dakota | PENNINGTON | RAPID CITY | 00 | 0016068 | This resurfacing project will extend the roadway life of US Highway 16 from Spring Creek Road to Cathedral Drive in Rapid City. | Pavement Improvement | 06/17/2009 | 09/14/2009 | 07/28/2010 | 4296900.46 | 5.7
5915 | South Dakota | SPINK |  | 00 | 0020092 | This resurfacing project will extend the roadway life for SD Highway 20 from SD Highway 45 to Brentford. | Pavement Improvement | 04/03/2009 | 05/11/2009 | 07/31/2010 | 6213585.95 | 34.8
5916 | South Dakota | PERKINS |  | 00 | 0020093 | This resurfacing project will extend the roadway life of SD Highway 20 from Prairie City to 2.6 miles west of Bison. | Pavement Improvement | 03/30/2009 | 10/03/2009 | 10/31/2009 | 4302829.35 | 14
5917 | South Dakota | CHARLES MIX |  | 00 | 0021094 | Mill & AC Overlay | Pavement Improvement | 12/28/2009 |  | 10/29/2010 | 4445171.34 | 23.7
5918 | South Dakota | DOUGLAS, CHARLES MIX, HUTCHINSON |  | 00 | 0021147 | Mill & AC Overlay | Pavement Improvement | 12/16/2009 |  | 10/29/2010 | 5908945.64 | 30.174
5919 | South Dakota | HAAKON |  | 00 | 0034132 | This resurfacing project will extend the roadway life of SD Highway 34 from east of the Cheyenne River to near the east junction with SD Highway 73. The project will also improve safety as a result o | Pavement Improvement | 03/30/2009 | 08/19/2009 | 10/16/2009 | 2576604.49 | 14.9
5920 | South Dakota | MOODY |  | 00 | 0034135 | This project will reconstruct SD Highway 34 from 1 mile west of SD Highway 13 to the Mineesota State Line. | Pavement Improvement | 12/17/2009 |  | 05/27/2011 | 4753746 | 7.7
5921 | South Dakota | CUSTER |  | 00 | 0036010 | This resurfacing project will extend the roadway life for SD Highway 36 from the junction of US Highway 16A, easat 0.9 miles. | Pavement Improvement | 05/19/2009 |  | 06/18/2010 | 178505.19 | 0.9
5922 | South Dakota | PENNINGTON, JACKSON |  | 00 | 0041144 | Mill & Asphalt Concrete Resurfacing | Pavement Improvement | 11/18/2009 |  | 10/15/2010 | 2121331.59 | 12.525
5923 | South Dakota | TURNER |  | 00 | 0044140 | This resurfacing project will extend the roadway life for SD Highway 44 from US Highway 81 to Marion Road. The safety of the route will also be improved by have a smoother driving surface. | Pavement Improvement | 12/17/2009 |  | 10/15/2010 | 1706113.71 | 8
5924 | South Dakota | MELLETTE, TRIPP |  | 00 | 0044142 | This resurfacing project will extend the roadway life of SD Highway 44 from Wood to the US 183 Junction. | Pavement Improvement | 12/15/2009 |  | 10/15/2010 | 4010027.74 | 24.994
5925 | South Dakota | LYMAN |  | 00 | 0053004 | This resurfacing project will extend the roadway life of SD Highway 53 from the end of the pavement north of the White River to south of I-90 near Vivian. The project will also improve safety as the | Pavement Improvement | 03/27/2009 | 05/25/2009 | 10/30/2009 | 1303169.65 | 8
5926 | South Dakota | HARDING |  | 00 | 0079066 | This resurfacing project will extend the roadway life of SD Highway 79 from the Slim Buttes area to west of the junction with SD Highway 20. The road will also improve safety as the result of a smoot | Pavement Improvement | 03/31/2009 |  | 07/31/2010 | 3174933.43 | 14
5927 | South Dakota | BUTTE |  | 00 | 0085051 | This project will reconstruct US Highway 85 in Belle Fourche from Hay Creek to the Belle Fourche River. | Pavement Widening | 10/22/2009 |  | 12/03/2010 | 6203681.6 | 1.111
5928 | South Dakota | ROBERTS |  | 00 | 0127006 | This resurfacing project will extend the roadway life of SD Highway 127 from I-29 west of the town of Victor, east and north to the North Dakota State Line. Safety will also be improved with the smoo | Pavement Improvement | 12/28/2009 |  | 10/15/2010 | 2939603.46 | 16.546
5929 | South Dakota | CUSTER |  | 00 | 016A002 | This resurfacing project will extend the roadway life of US Highway 16A from the west entrance of Custer State Park, easat to the junction with SD Highway 36. The project will also improve safety as | Pavement Improvement | 05/19/2009 |  | 06/18/2010 | 2637284.48 | 13.7
5930 | South Dakota | CLARK |  | 00 | 0212113 | This pavement restoration project will extend the life of the section of US Highway 212 from the Spink/Clark County Line to East of Clark, and the section of US Highway 212 that goes through the town | Pavement Improvement | 03/27/2009 |  | 09/03/2010 | 1613862.66 | 9
5931 | South Dakota | MCPHERSON |  | 00 | 0247005 | This resurfacing project will extend the roadway life of SD Highway 247 from Roscoe to north of SD Highway 10. The project will also improve safety as a result of a smoother driving surface. | Pavement Improvement | 10/08/2009 |  | 10/15/2010 | 2839699.59 | 22.535
5932 | South Dakota | UNION |  | 00 | 0291075 | This project will remove and replace the existing surface of the northbound lanes of I-29 from Elk Point to the SD Highway 50 exit. | Pavement Improvement | 10/26/2009 |  | 11/24/2010 | 10516999.37 | 9.586
5933 | South Dakota | UNION |  | 00 | 0291101 | This project will remove and replace the concrete surface on the northbound lanes of I-29 from south of the Volin Exit to south of the Beresford exit. | Pavement Improvement | 04/02/2009 | 04/17/2009 | 08/20/2010 | 8433624.78 | 9.4
5934 | South Dakota | CODINGTON |  | 00 | 0297030 | This project will remove and replace the current concrete pavement on the southbound lanes of I-90 from SD Highway 20 north, 14.7 miles, to US Highway 212. The improvements will improve safety with a | Pavement Improvement | 03/27/2009 | 04/15/2009 | 10/30/2009 | 14752119.03 | 14.7
5935 | South Dakota | JACKSON |  | 00 | 0903078 | This resurfacing project will extend the pavement life of a section of both the east and west bound sections of I-90 from Murdo to the Jackson/Jones County Line. Safety will also be improved by shoul | Pavement Improvement | 04/01/2009 | 05/11/2009 | 07/16/2010 | 13791192.58 | 32.2
5936 | South Dakota | AURORA |  | 00 | 0907052 | This project will remove and replace the concrete surface on the westbound lanes of I-90 from White Lake to Mount Vernon. | Pavement Improvement | 03/30/2009 | 05/05/2009 | 10/29/2010 | 23279965.99 | 21.8
5937 | South Dakota | CHARLES MIX |  | 00 | 1804008 | This resurfacing project will extend the roadway life of SD Highway 1804 from SD Highway 44 south 8 miles. The project will also improve safety as the result of a smoother driving surface. | Pavement Improvement | 03/30/2009 | 04/25/2009 | 10/30/2009 | 1614350.26 | 8
5938 | South Dakota | BUTTE |  | 00 | 3034001 | This resurfacing project will extend the roadway life of SD Highway 34 from the Wyoming State Line to Belle Fourche. Safety will also be improved as the result of a smoother driving surface. | Pavement Improvement | 03/30/2009 | 06/22/2009 | 07/31/2010 | 1727993.61 | 9.8
5939 | South Dakota | CUSTER |  | 00 | 3040008 | This project will reconstruct SD Highway 40 in Hermosa, from SD Highway 79 to the trailer park east of the railroad tracks. Along with a new road surface, the project will include storm sewers, curb | Pavement Improvement | 07/21/2009 | 11/30/2009 | 08/14/2010 | 1643771.18 | 0.9
5940 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07,08,09 | 0001236 | This project located on SR-1 FROM ISABELLE STREET TO WHITE STATION ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ext | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1132123 | 2.7
5941 | Tennessee | WARREN |  | 04 | 0001237 | This project includes the necessary grading, drainage work, and bridge construction in preparation for a future paving project. | New Construction | 04/07/2009 | 04/07/2009 | 09/30/2011 | 8951029 | 5.2
5942 | Tennessee | VAN BUREN |  | 04 | 0001240 | This project located on SR-1 FROM WARREN COUNTY LINE TO WHITE COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 05/13/2009 | 05/13/2009 | 10/31/2009 | 321330 | 2.85
5943 | Tennessee | WARREN |  | 04 | 0001242 | This project located on SR-1 FROM VICTOR J. YOUNG ROAD TO VAN BUREN COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 05/13/2009 | 05/13/2009 | 10/31/2009 | 149908 | 1.15
5944 | Tennessee | WHITE |  | 04 | 0001243 | This project located on SR-1 FROM VAN BUREN COUNTY LINE TO COLE ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 05/13/2009 | 05/13/2009 | 10/31/2009 | 216950 | 1.89
5945 | Tennessee | HAYWOOD |  | 08 | 0001244 | This project located on SR-1 FROM TIPTON COUNTY LINE TO OVERFLOW BRIDGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ext | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/15/2009 | 883296 | 5.58
5946 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0001245 | This project is for the rehabilitation/upgrading of sidewalks on Harding Pike/West End Avenue from White Bridge Road to I-440 in Nashville | Transportation Enhancements | 11/06/2009 | 11/06/2009 | 09/30/2015 | 708620 | 1.68
5947 | Tennessee | LOUDON | KNOXVILLE | 02 | 0002092 | This project located on SR-2 FROM WEST OF SR-73 TO WEST OF SR-1 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 909796 | 5
5948 | Tennessee | RUTHERFORD | MURFREESBORO | 06 | 0002093 | This project located on SR-2 FROM NORTH OF RUTHERFORD BOULEVARD TO EPPS MILL ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will als | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1097355 | 6.8
5949 | Tennessee | BRADLEY | CLEVELAND | 03 | 0002094 | This project located on SR-2 FROM CLEVELAND CITY LIMITS TO SR-40 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 735118 | 2.6
5950 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0002095 | This project located on SR-2 FROM LILAC AVENUE TO NORFOLK SOUTHERN R/R OVERPASS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 846775 | 3
5951 | Tennessee | COFFEE |  | 04 | 0002096 | This project located on SR-2 FROM RUTHERFORD COL TO OLD HWY 41 (LT) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 840636 | 6.1
5952 | Tennessee | MCMINN |  | 02 | 0002097 | This project located on SR-2 FROM NORTH OF NIOTA TO MONROE COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 04/07/2009 | 04/07/2009 | 06/30/2010 | 417824 | 2.5
5953 | Tennessee | COFFEE |  | 04 | 0002098 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-2 with a new BRIDGE OVER DUCK RIVER IN MANCHESTER to serve the community for the next s | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2010 | 5572946 | 0.3
5954 | Tennessee | LAUDERDALE |  | 08 | 0003110 | This project located on SR-3 FROM TIPTON COUNTY LINE TO STATE HIGHWAY GARAGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also hel | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1456692 | 5
5955 | Tennessee | LAWRENCE |  | 04 | 0006070 | This project located on SR-6 FROM BUSBY ROAD TO LEOMA will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of th | Pavement Improvement | 04/01/2009 | 04/01/2009 | 06/30/2010 | 2129355 | 5
5956 | Tennessee | LAWRENCE |  | 04 | 0006072 | This project located on SR-6 FROM LAWRENCEBURG TO ALEXANDER SPRINGS ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ex | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 2011100 | 6.8
5957 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 0006075 | This project is for the construction of a median and addition of roadway lighting on SR-6 (West Main Street) from the Davidson County line to New Shackle Island Road in Hendersonville. | Other | 04/06/2009 | 04/06/2009 | 09/15/2015 | 68182 | 4.26
5958 | Tennessee | GILES |  | 04 | 0007020 | This project located on SR-7 FROM POLLY ROAD TO SR-15 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of th | Pavement Improvement | 04/01/2009 | 04/01/2009 | 06/30/2010 | 932540 | 4.6
5959 | Tennessee | MAURY |  | 04 | 0007021 | This project located on SR-7 FROM GILES COUNTY LINE TO SOUTH OF SR-50 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exten | Pavement Improvement | 04/01/2009 | 04/01/2009 | 06/30/2010 | 1609573 | 11.6
5960 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0008041 | This project is for improvements to the intersection of SR-8 (Ringgold Road) at Camp Jordan Parkway and including traffic signals | Safety/Traffic Management | 05/14/2009 | 05/14/2009 | 01/15/2010 | 134390 | 0
5961 | Tennessee | COCKE |  | 01 | 0009059 | This project located on SR-9 FROM SR-35 TO WHITE OAK AVENUE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/15/2009 | 1819695 | 4.2
5962 | Tennessee | CAMPBELL |  | 04 | 0009060 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-9 with a new BRIDGE OVER CSX RAILROAD IN LAFOLLETTE to serve the community for the next | Bridge Replacement | 05/15/2009 | 05/15/2009 | 06/30/2011 | 5176486 | 0.36
5963 | Tennessee | TROUSDALE |  | 06 | 0010037 | This project located on SR-10 FROM SR-141 TO SOUTH OF SR-25 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/15/2009 | 05/15/2009 | 06/30/2010 | 425735 | 2.86
5964 | Tennessee | MARSHALL |  | 06 | 0011051 | This project located on SR-11 FROM CHAPEL HILL CITY LIMITS TO WILLIAMSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 994550 | 6.1
5965 | Tennessee | RUTHERFORD |  | 06 | 0011052 | This project located on SR-11 FROM WILLIAMSON COUNTY LINE TO WILLIAMSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will a | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 488371 | 2.6
5966 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 0011053 | This project located on SR-11 FROM DAVIDSON COUNTY LINE TO SOUTH OF KASPER WAY will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 250213 | 0.6
5967 | Tennessee | WILLIAMSON |  | 04,07 | 0011054 | This project located on SR-11 FROM MARSHALL COUNTY LINE TO RUTHERFORD COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will als | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 122319 | 0.7
5968 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0012038 | This project located on SR-12 FROM I-65 TO SR-112 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the ro | Pavement Improvement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 1138099 | 3
5969 | Tennessee | MONTGOMERY | CLARKSVILLE (KY) | 07 | 0012039 | This project located on SR-12 FROM SR-374 TO KENTUCKY STATE LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/14/2009 | 05/14/2009 | 06/30/2010 | 1545491 | 4.06
5970 | Tennessee | HUMPHREYS |  | 08 | 0013033 | This project located on SR-13 FROM NORTH OF TUMBLING CREEK ROAD TO SOUTH OF PUMPKIN CREEK will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and | Pavement Improvement | 05/13/2009 | 05/13/2009 | 06/30/2010 | 1228304 | 6.91
5971 | Tennessee | TIPTON |  | 08 | 0014048 | This project will widen SR-14 from 2 lanes to 4 lanes FROM NORTH OF SR-206 TO 1.2 MILES EAST OF SR-384 | Pavement Widening | 04/06/2009 | 04/06/2009 | 12/15/2011 | 15487112 | 3.9
5972 | Tennessee | MCNAIRY |  | 07 | 0015141 | This project will widen SR-15 from 2 lanes to 4 lanes FROM NEAR SR-225 TO SANDY FLAT ROAD | Pavement Widening | 04/06/2009 | 04/06/2009 | 11/15/2011 | 24392926 | 3.4
5973 | Tennessee | FRANKLIN |  | 04 | 0015157 | This project located on SR-15 FROM NORTH OF SR-56 TO GRUNDY COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ext | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 653008 | 3.5
5974 | Tennessee | MCNAIRY |  | 07 | 0015158 | This project located on SR-15 FROM SR-5 (US-45 LEFT) TO SR-5 (US-45 RIGHT) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/10/2009 | 1066974 | 2.5
5975 | Tennessee | MADISON |  | 08 | 0018025 | This project located on SR-18 FROM MERIDIAN CREEK TO BRIDGE OVER ABANDONED R/R will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 967257 | 4.9
5976 | Tennessee | MADISON |  | 08 | 0020045 | This project located on SR-20 FROM POPLAR CORNER ROAD TO BRIDGE OVER OLD SR-20 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1619040 | 4.4
5977 | Tennessee | CARROLL |  | 08 | 0022057 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-22 with a new BRIDGES OVER OVERFLOW BEAVER CREEK, & OVERFLOW IN HUNTINGDON to serve the | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 3329318 | 0
5978 | Tennessee | WILSON |  | 05,06 | 0026029 | This project located on SR-26 FROM NEAR MADDOX-SIMPSON PARKWAY TO EAST OF TAYLOR ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 873664 | 7.7
5979 | Tennessee | WHITE |  | 04 | 0026030 | This project located on SR-26 FROM EAST OF SR-136 TO WEST OF SR-111 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 648304 | 4.5
5980 | Tennessee | WILSON | NASHVILLE-DAVIDSON | 05 | 0026034 | This project on SR-26 will include the purchase of property for the future construction of an intersection at Maddox-Simpson Parkway in Lebanon. | Other | 09/08/2009 | 09/08/2009 | 09/30/2015 | 1000000 | 0
5981 | Tennessee | CUMBERLAND |  | 04 | 0028039 | This project located on SR-28 FROM NORTH OF WINNINGHAM ROAD TO SR-68 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 593422 | 5
5982 | Tennessee | SCOTT |  | 04 | 0029069 | This project located on SR-29 FROM WOLF RIVER ROAD TO SOUTH OF GLASSHOUSE ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 520082 | 6.9
5983 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0029070 | This project located on SR-29 FROM OVERHEAD OVER DAYTON PIKE TO OLD DAYTON PIKE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 1966738 | 5.4
5984 | Tennessee | RHEA |  | 03 | 0029071 | This project located on SR-29 FROM SOUTH OF VANN'S CREEK ROAD/HOYAL ROAD TO SOUTH OF MACEDONIA ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automob | Pavement Improvement | 05/14/2009 | 05/14/2009 | 06/30/2010 | 553449 | 4.74
5985 | Tennessee | BLEDSOE |  | 04 | 0030047 | This project located on SR-30 FROM WEST OF CRANWELL ROAD RT TO SR-28 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/30/2009 | 765167 | 4.8
5986 | Tennessee | UNION |  | 03 | 0033075 | This project located on SR-33 FROM KNOX COUNTY LINE TO EAST OF MAIN STREET RIGHT will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/15/2009 | 672684 | 7.57
5987 | Tennessee | POLK |  | 03 | 0033076 | This project will widen SR-33 from 2 lanes to 4 lanes FROM BENTON NORTH CITY LIMITS TO SR-30 EAST | Pavement Widening | 04/07/2009 | 04/07/2009 | 12/31/2011 | 26667858 | 5.3
5988 | Tennessee | CLAIBORNE |  | 03 | 0033077 | This project located on SR-33 FROM SOUTH OF MOLLY HOLLOW ROAD TO SOUTH OF OLD SR-33 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will a | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/15/2009 | 564508 | 2.22
5989 | Tennessee | HAMBLEN | MORRISTOWN | 01 | 0034069 | This project is for traffic signal upgrades on SR-34 at the intersection of SR-34 and SR-160 in Morristown | Safety/Traffic Management | 07/17/2009 | 07/17/2009 | 09/30/2015 | 221362 | 0
5990 | Tennessee | CARTER | JOHNSON CITY | 01 | 0037014 | This project located on SR-37 FROM NORTH OF CROOK STREET TO BRIDGE OVER WATAUGA RIVER will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 2625811 | 5.3
5991 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 0041019 | This project located on SR-41 FROM DICKERSON PIKE TO SR-257 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/31/2009 | 1246880 | 5.3
5992 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 0044006 | This project located on SR-44 FROM SR-34 TO VIRGINIA STATE LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/01/2009 | 04/01/2009 | 10/31/2009 | 416929 | 2.5
5993 | Tennessee | DICKSON |  | 08 | 0046012 | This project located on SR-46 FROM ROBIN HOOD ROAD TO SR-1 BYPASS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend th | Pavement Improvement | 04/01/2009 | 04/01/2009 | 06/30/2010 | 1724001 | 4.4
5994 | Tennessee | WILLIAMSON |  | 04 | 0046013 | This project located on SR-46 FROM PEWITT ROAD TO NEAR SR-100 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 05/12/2009 | 05/12/2009 | 06/30/2010 | 472552 | 5.21
5995 | Tennessee | HOUSTON |  | 08 | 0049020 | This project located on SR-49 FROM SR-147 TO SR-13 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 05/12/2009 | 05/12/2009 | 06/30/2010 | 743934 | 4.94
5996 | Tennessee | MORGAN |  | 04 | 0052055 | This project located on SR-52 FROM END OF BRIDGE OVER CLEAR FORK RIVER TO SCOTT COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, an | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 709884 | 3.9
5997 | Tennessee | SCOTT |  | 04 | 0052056 | This project located on SR-52 FROM MORGAN COUNTY LINE TO SR-29 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 818707 | 5.1
5998 | Tennessee | CLAY |  | 06 | 0052057 | This project located on SR-52 FROM EAST END OF CUMBERLAND RIVER BRIDGE TO SR-53 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 318728 | 1.1
5999 | Tennessee | FENTRESS |  | 04 | 0052058 | This project located on SR-52 FROM EAST OF BRIDGE OVER SR-28 TO SR-296 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/15/2009 | 790617 | 4
6000 | Tennessee | MACON |  | 06 | 0052059 | This project located on SR-52 FROM LAFAYETTE CITY LIMITS TO NEAR BUTLER ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also hel | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 1252325 | 5.35
6001 | Tennessee | MACON |  | 06 | 0056057 | This project located on SR-56 FROM JACKSON COUNTY LINE TO SR-262 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 11/15/2009 | 94252 | 2.7
6002 | Tennessee | GRUNDY |  | 04 | 0056058 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-56 with a new BRIDGE OVER FIRESCALD CREEK IN ALTAMONT to serve the community for the ne | Bridge Replacement | 05/12/2009 | 05/12/2009 | 05/31/2010 | 1691111 | 0
6003 | Tennessee | FAYETTE |  | 07 | 0057045 | This project located on SR-57 FROM COWAN LOOP ROAD TO SR-18 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 383123 | 5.04
6004 | Tennessee | HAMILTON |  | 03 | 0058032 | This project located on SR-58 FROM NORTH OF RUNYAN ROAD TO SOUTH OF SR-60 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 481373 | 4.73
6005 | Tennessee | TIPTON |  | 08 | 0059023 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-59 with a new BRIDGE OVER LITTLE BEAVER CREEK INCLUDING A DRAINAGE DITCH to serve the c | Bridge Replacement | 04/06/2009 | 04/06/2009 | 01/15/2010 | 1431494 | 0
6006 | Tennessee | MEIGS |  | 03 | 0060017 | This project located on SR-60 FROM NEAR MCINTRUFF ROAD IN MEIGS COUNTY TO NEAR FIVE POINTS ROAD IN RHEA COUNTY will provide a smoother riding surface for motorists, thus decreasing wear and tear on th | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 731190 | 1.46
6007 | Tennessee | ANDERSON |  | 03 | 0061022 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-61 with a new BRIDGE OVER POPLAR CREEK to serve the community for the next several deca | Bridge Replacement | 05/12/2009 | 05/12/2009 | 06/30/2010 | 1736988 | 0
6008 | Tennessee | SEVIER |  | 01 | 0066039 | This project will widen SR-66 from 4 lanes to 6 lanes FROM NORTH OF NICHOLS STREET IN SEVIERVILLE TO SR-338 (BOYDS CREEK HIGHWAY) | Pavement Widening | 05/15/2009 | 05/15/2009 | 12/31/2011 | 40690695 | 4.22
6009 | Tennessee | HAMBLEN | MORRISTOWN | 01 | 0066042 | This resurfacing project located on SR-66 WEST 1ST NORTH STREET, FROM MARS AVENUE TO NORTH CUMBERLAND STREET IN MORRISTOWN will provide a smoother riding surface for motorists, thus decreasing wear an | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 356575 | 0.98
6010 | Tennessee | BENTON |  | 08 | 0069068 | This project located on SR-69 FROM SOUTH OF SR-1 TO SOUTH OF SR-391 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 513194 | 1.5
6011 | Tennessee | HENRY |  | 08 | 0069069 | This project located on SR-69A FROM SCARBOROUGH RD TO SR-69 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1217993 | 6.4
6012 | Tennessee | HARDIN |  | 07 | 0069070 | This project located on SR-69 FROM HOLLAND CREEK ROAD TO SR-226 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 1363878 | 7.37
6013 | Tennessee | GREENE |  | 01 | 0070015 | This project located on SR-70 FROM RAMP TO I-81 TO HAWKINS COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/15/2009 | 881696 | 5.4
6014 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 0075009 | This project located on SR-75 FROM SOUTH OF SHADDEN ROAD TO NORTH OF I-26 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 04/01/2009 | 04/01/2009 | 12/15/2009 | 542054 | 1.5
6015 | Tennessee | GIBSON |  | 08 | 0076051 | This project will widen SR-76 from 2 lanes to 4 or 5 lanes FROM SR-43 IN MILAN TO NEAR THE CARROLL COUNTY LINE | Pavement Widening | 06/17/2009 | 06/17/2009 | 12/15/2011 | 20600000 | 4.4
6016 | Tennessee | HAYWOOD |  | 08 | 0076058 | This project located on SR-76 FROM FAYETTE COUNTY LINE TO SR-179 RT will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1354207 | 5.6
6017 | Tennessee | STEWART |  | 08 | 0076059 | This project will widen SR-76 from 2 lanes to 4 lanes FROM SR-120 TO EAST OF MONTGOMERY COUNTY LINE | Pavement Widening | 05/15/2009 | 05/15/2009 | 11/01/2011 | 21460607 | 5.8
6018 | Tennessee | LAKE |  | 08 | 0078015 | This project located on SR-78 FROM SR-21 TO VAN WORKS ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 513098 | 4.95
6019 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 0081017 | This project located on SR-81 FROM SOUTH OF RIDGECREST ROAD TO NORTH OF ANDERSON ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/01/2009 | 04/01/2009 | 12/15/2009 | 626585 | 2.5
6020 | Tennessee | OBION |  | 08 | 0089016 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-89 with a new BRIDGE OVER GRASSY CREEK to serve the community for the next several deca | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 1111679 | 0
6021 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 0091033 | This project located on SR-91 FROM LEGION STREET TO SR-34(WB) AND FROM SR-34 TO LEGION STREET (EB) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobi | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 827195 | 1.36
6022 | Tennessee | ANDERSON |  | 03 | 0095007 | This project located on SR-95 FROM MELTON LAKE ROAD TO SR-61 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the lif | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 469175 | 1.17
6023 | Tennessee | CANNON |  | 06 | 0096024 | This project located on SR-96 FROM RUTHERFORD COUNTY LINE TO WILSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 948744 | 5
6024 | Tennessee | DECATUR |  | 07 | 0100045 | This project located on SR-100 FROM SR-69 TO BRIDGE AT RUSHING CREEK will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 561165 | 2.4
6025 | Tennessee | HARDEMAN |  | 07 | 0100046 | This project located on SR-100 FROM OLD SR-18 TO CHESTER COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 631960 | 3.9
6026 | Tennessee | ANDERSON |  | 03 | 0100047 | This project will improve safety and reliability of the transportation system by replacing an older bridge on BINKLEY ACRES ROAD with a new BRIDGE OVER BRUSHY FORK CREEK to serve the community for th | Bridge Replacement | 04/07/2009 | 04/07/2009 | 06/15/2010 | 468838 | 0
6027 | Tennessee | ANDERSON |  | 03 | 0100048 | This project will improve safety and reliability of the transportation system by replacing an older bridge on YARNELL ROAD with a new BRIDGE OVER LITTLE DISMAL CREEK NEAR CLINTON to serve the communi | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 209099 | 0.1
6028 | Tennessee | ANDERSON |  | 03 | 0100049 | This project will improve safety and reliability of the transportation system by replacing an older bridge on HALF MOON ROAD with a new BRIDGE OVER STONEY FLAT CREE to serve the community for the next | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/31/2010 | 212832 | 0.1
6029 | Tennessee | CUMBERLAND |  | 04 | 0101015 | This project will widen SR-101 from 2 lanes to 5 lanes including bike lanes and sidwalks FROM SR-282 TO SR-392 | Pavement Widening | 06/30/2009 | 06/30/2009 | 11/01/2011 | 18025020 | 2.8
6030 | Tennessee | RUTHERFORD |  | 06 | 0102011 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-102 with a new BRIDGES OVER BRANCH AND ROCKY FORK CREEK to serve the community for the | Bridge Replacement | 04/06/2009 | 04/06/2009 | 05/31/2010 | 1476763 | 0
6031 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0106025 | This project located on SR-106 FROM HARDING PLACE TO I-440 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/15/2009 | 05/15/2009 | 10/31/2009 | 2006979 | 2.68
6032 | Tennessee | WASHINGTON |  | 01 | 0107014 | This project located on SR-107 FROM GREENE COUNTY LINE TO SR-81 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 2524017 | 11.34
6033 | Tennessee | SUMNER |  | 06 | 0109024 | This paving project will complete SR-109 from the Gallatin bypass to south of Hollis Chapel Road | New Construction | 05/15/2009 | 05/15/2009 | 10/31/2010 | 11372855 | 5.2
6034 | Tennessee | ANDERSON |  | 03 | 0116010 | This project located on SR-116 FROM NORTH OF BRADEN FLATS LANE TO SR-330 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ex | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 519097 | 3.4
6035 | Tennessee | WARREN |  | 04 | 0127012 | This project located on SR-127 FROM OLD SHELLSFORD ROAD TO SR-30 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 553902 | 3
6036 | Tennessee | COFFEE |  | 04 | 0127013 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-127 with a new BRIDGE OVER I-24 to serve the community for the next several decades. | Bridge Replacement | 04/06/2009 | 04/06/2009 | 09/30/2010 | 3890007 | 0
6037 | Tennessee | KNOX | KNOXVILLE | 02 | 0131020 | This project located on SR-131 FROM SR-33 TO SR-331 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the | Pavement Improvement | 04/07/2009 | 04/07/2009 | 11/15/2009 | 825168 | 4.9
6038 | Tennessee | KNOX | KNOXVILLE | 02 | 0131022 | This project located on SR-131 FROM SR-9 TO WEST OF GILL ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 459525 | 2.25
6039 | Tennessee | KNOX | KNOXVILLE | 02 | 0131025 | This project will widen SR-131 / LOVELL ROAD from 2 lanes to 5 lanes FROM WEST OF PELLISSIPPI PARKWAY TO SCHAEFFER ROAD | Pavement Widening | 01/29/2010 |  |  | 3081740 | 0.11
6040 | Tennessee | PUTNAM |  | 06 | 0135012 | This project located on SR-135 FROM NORTH OF DIXIE AVENUE TO JACKSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 868846 | 4.9
6041 | Tennessee | CARTER |  | 01 | 0143006 | This project located on SR-143 FROM NORTH CAROLINA STATE LINE TO SR-37 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 2235383 | 12.6
6042 | Tennessee | CANNON |  | 06 | 0146004 | This project located on SR-146 FROM SR-1 TO DEKALB COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 462876 | 9.7
6043 | Tennessee | DE KALB |  | 06 | 0146005 | This project located on SR-146 FROM CANNON COUNTY LINE TO NORTH OF BRIDGE OVER PINE CREEK will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 273628 | 5.5
6044 | Tennessee | BENTON |  | 08 | 0147002 | This project located on SR-147 FROM SR-69A TO PINE GROVE ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/30/2009 | 808586 | 5.4
6045 | Tennessee | MARION |  | 04 | 0156006 | This project located on SR-156 FROM MARION-FRANKLIN FOREST TO ORME MOUNTAIN ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 423488 | 6.4
6046 | Tennessee | JOHNSON |  | 01 | 0167004 | This project located on SR-167 FROM LITTLE DRY RUN ROAD TO SR-34 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 1496706 | 7.59
6047 | Tennessee | WILSON | NASHVILLE-DAVIDSON | 05 | 0171024 | This project will widen SR-171 (MOUNT JULIET ROAD) from 3 lanes to 5 lanes FROM DIVISION STREET TO SR-24 (US-70, LEBANON ROAD) | Pavement Widening | 06/17/2009 | 06/17/2009 | 11/15/2011 | 10297296 | 2.2
6048 | Tennessee | CARTER |  | 01 | 0173007 | This project located on SR-173 FROM UNICOI COUNTY LINE TO SR-37 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 353518 | 4.28
6049 | Tennessee | WEAKLEY |  | 08 | 0190009 | This project located on SR-190 FROM CARROLL COUNTY LINE TO SR-124 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend th | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 687289 | 4.55
6050 | Tennessee | BENTON |  | 08 | 0191004 | This project located on SR-191 FROM SR-391 TO MAGNOLIA AVENUE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 04/06/2009 |  | 02/15/2010 | 79915 | 0.2
6051 | Tennessee | FAYETTE |  | 07 | 0194011 | This project located on SR-194 FROM SR-15 TO SR-59 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 607166 | 8.43
6052 | Tennessee | DECATUR |  | 07 | 0202015 | This project located on SR-202 FROM SR-114 TO SR-69 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 780126 | 5.2
6053 | Tennessee | HENRY |  | 08 | 0218006 | Construction of a new bypass on the northwest side of Paris from SR-54 west of Paris to SR-69 northwest of Paris | New Construction | 04/06/2009 | 04/06/2009 | 11/30/2010 | 8673704 | 3.08
6054 | Tennessee | MADISON | JACKSON | 08 | 0223009 | This project located on SR-223 FROM SOUTH OF LOWER BROWNSVILLE RD TO BRIDGE OVER I-40 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 449372 | 0.6
6055 | Tennessee | CHESTER |  | 07 | 0225003 | This project located on SR-225 FROM OLD FRIENDSHIP ROAD TO MONTEZUMA ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 612968 | 5.3
6056 | Tennessee | MONTGOMERY |  | 07 | 0238003 | This project located on SR-238 FROM SR-76 TO KENTUCKY STATE LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/14/2009 | 05/14/2009 | 12/15/2009 | 619755 | 8.25
6057 | Tennessee | MARION |  | 04 | 0242127 | This project located on I-24 FROM SR-27/150 TO TENNESSEE RIVER BRIDGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exten | Pavement Improvement | 05/15/2009 | 05/15/2009 | 06/30/2010 | 2416979 | 8.23
6058 | Tennessee | COFFEE |  | 04 | 0242129 | This project located on I-24 FROM RAMP FROM SR-55 (McMINNVILLE HWY) TO RAMP FROM AEDC will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/01/2009 | 04/01/2009 | 06/30/2010 | 5222948 | 6.1
6059 | Tennessee | COFFEE |  | 04 | 0242130 | This project located on I-24 FROM NOAH FORK CREEK TO RAMP FROM SR-2 EB will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 05/15/2009 | 05/15/2009 | 06/30/2010 | 3447909 | 5.32
6060 | Tennessee | CHEATHAM |  | 05,07 | 0251012 | This project located on SR-251 FROM SR-249 TO DAVIDSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend t | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 623630 | 4
6061 | Tennessee | ROBERTSON |  | 06 | 0257004 | This project located on SR-257 FROM SR-49 TO NEAR NEW CUT ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 797103 | 5.8
6062 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 0258007 | This project is for the development of design plans for the future widening of New Shackle Island Road from Iris Drive north to SR-386 in Hendersonville | Other | 08/12/2009 | 08/12/2009 | 09/30/2015 | 375000 | 0.86
6063 | Tennessee | MACON |  | 06 | 0262009 | This project located on SR-262 FROM SR-56 TO JACKSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 11/15/2009 | 98105 | 2.81
6064 | Tennessee | LINCOLN |  | 04 | 0275006 | This project located on SR-275 FROM NEAR 4-WAY STOP TO SR-15 EAST will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend th | Pavement Improvement | 05/15/2009 | 05/15/2009 | 11/15/2009 | 314669 | 7
6065 | Tennessee | SEQUATCHIE |  | 04 | 0283010 | This project located on SR-283 FROM MARION COUNTY LINE TO SR-8 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 632221 | 5.5
6066 | Tennessee | OVERTON |  | 06 | 0294002 | This project located on SR-294 FROM SR-111 TO OAKLEY-ALLONS ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 508318 | 6.2
6067 | Tennessee | CAMPBELL |  | 04 | 0297002 | This project located on SR-297 FROM WEST OF LICK FORK LANE LEFT TO EAST OF LITTLE ELK CREEK ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobile | Pavement Improvement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 956522 | 6.1
6068 | Tennessee | BENTON |  | 08 | 0300028 | This streetscape beautification project in Camden includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 07/30/2009 | 07/30/2009 | 09/30/2015 | 760934 | 0
6069 | Tennessee | BRADLEY |  | 03 | 0308006 | This project located on SR-308 FROM I-75 TO SR-2 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the roa | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 884548 | 3.3
6070 | Tennessee | POLK |  | 03 | 0314004 | This project located on SR-314 FROM SR-40 TO SR-33 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 1147964 | 6.08
6071 | Tennessee | FENTRESS |  | 04 | 0325007 | This project located on SR-325 FROM FENTRESS-PICKETT COUNTY LINE TO SR-28 IN PICKETT COUNTY will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, an | Pavement Improvement | 05/12/2009 | 05/12/2009 | 11/15/2009 | 240814 | 2.53
6072 | Tennessee | PICKETT |  | 04 | 0325008 | This project located on SR-325 FROM WEST OF HILL ROAD TO FENTRESS COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also he | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 393179 | 4.53
6073 | Tennessee | HAMBLEN | MORRISTOWN | 01 | 0343007 | This project located on SR-343 FROM SR-32 TO SR-34 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 06/18/2009 | 06/18/2009 | 06/30/2010 | 728362 | 3.89
6074 | Tennessee | HAWKINS |  | 01 | 0344006 | This project located on SR-344 FROM SR-113 TO HOLSTON RIVER BRIDGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend t | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 462078 | 3.8
6075 | Tennessee | HENRY |  | 08 | 0356001 | This project located on SR-356 FROM SR-69/54 TO SR-76 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of th | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 558548 | 1
6076 | Tennessee | CARTER |  | 01 | 0361003 | This project located on SR-361 FROM SR-359 TO SR-37 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 1620171 | 8.9
6077 | Tennessee | MARSHALL |  | 06 | 0373007 | This project will widen SR-373 from 2 lanes to 5 lanes FROM I-65 TO EAST OF SR-417 IN LEWISBURG | Pavement Widening | 04/07/2009 | 04/07/2009 | 12/15/2011 | 19252288 | 4
6078 | Tennessee | BENTON |  | 08 | 0391015 | This project located on SR-391 FROM SR-1 TO SR-1 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the roa | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 1528298 | 5.3
6079 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 0400023 | This project located on SR-400 FROM NORTH BROADWAY STREET TO WEST MAIN STREET (SB) AND FROM WEST MAIN STREET TO NORTH BROADWAY STREET (NB) will provide a smoother riding surface for motorists, thus de | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/15/2009 | 1062141 | 1.63
6080 | Tennessee | MADISON | JACKSON | 08 | 0401317 | This project located on I-40 FROM WEST OF EXIT 74 TO EAST OF EXIT 83 (Excludes LM 13.59 to LM 15.57) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automo | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 3299826 | 9.5
6081 | Tennessee | HENDERSON |  | 07 | 0402087 | This project located on I-40 FROM MADISON COUNTY LINE TO SR-104 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/01/2009 | 04/01/2009 | 06/30/2010 | 2248548 | 6.1
6082 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403140 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-155 with a new BRIDGE OVER I-40 AT ROBERTSON ROAD to serve the community for the next s | Bridge Replacement | 04/09/2009 | 04/09/2009 | 09/15/2011 | 3570807 | 0
6083 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403141 | This project located on I-40 FROM CHARLOTTE PIKE TO OVERHEAD BRIDGE AT WESTBORO DRIVE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/07/2009 | 04/07/2009 | 09/30/2009 | 1507199 | 2.2
6084 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403142 | This project will complete the second phase of the interchange improvements at Briley Parkway/Robertson Road on Interstate 40 | Safety/Traffic Management | 04/09/2009 | 04/09/2009 | 09/15/2011 | 28200000 | 0.4
6085 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403143 | This project located on I-40 FROM SR-1 TO CHARLOTTE PIKE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 1950500 | 4.64
6086 | Tennessee | SMITH |  | 06 | 0405135 | This project located on I-40 FROM SR-53 TO PUTNAM COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 04/07/2009 | 04/07/2009 | 06/30/2010 | 2414768 | 8.6
6087 | Tennessee | PUTNAM |  | 06 | 0406143 | This project located on I-40 FROM SMITH COUNTY LINE TO EAST OF SR-56 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/01/2009 | 04/01/2009 | 06/30/2010 | 1864459 | 6.6
6088 | Tennessee | WEAKLEY |  | 08 | 0431011 | This project located on SR-431 FROM CENTRAL STREET TO SR-22 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 1555941 | 2.19
6089 | Tennessee | BEDFORD |  | 06 | 0437002 | Construction of a new bypass on the northeast side of Shelbyville from SR-10 north of Shelbyville to SR-16 east of Shelbyville | New Construction | 04/07/2009 | 04/07/2009 | 08/31/2011 | 15740454 | 6.3
6090 | Tennessee | BLEDSOE |  | 04 | 0443002 | This project located on SR-443 FROM 90 DEGREE TURN TO RHEA COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 05/12/2009 | 05/12/2009 | 11/30/2009 | 79377 | 1.38
6091 | Tennessee | RHEA |  | 03 | 0443003 | This project located on SR-443 FROM BLEDSOE COUNTY LINE TO SR-30 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 431702 | 6.87
6092 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 0473002 | This project is for the optimization of traffic signal timing on SR-473/Martin Luther King Jr. Boulevard in Bristol | Safety/Traffic Management | 12/30/2009 |  | 09/30/2015 | 119624 | 0
6093 | Tennessee | BLOUNT |  | 02 | 0500039 | This project will improve safety and reliability of the transportation system by replacing an older bridge on THOMPSON BRIDGE ROAD with a new BRIDGE OVER NINE MILE CREEK to serve the community for th | Bridge Replacement | 04/07/2009 | 04/07/2009 | 11/30/2010 | 1386644 | 0.001
6094 | Tennessee | BLOUNT |  | 02 | 0500040 | This project will improve safety and reliability of the transportation system by replacing an older bridge on REGAN MILL ROAD with a new BRIDGE OVER NINE MILE CREEK to serve the community for the ne | Bridge Replacement | 04/07/2009 | 04/07/2009 | 11/30/2010 | 357833 | 0.2
6095 | Tennessee | BRADLEY | CLEVELAND | 03 | 0751118 | This project located on I-75 FROM EAST OF SR-60 TO SOUTH OF MCMINN COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 04/01/2009 | 04/01/2009 | 06/30/2010 | 4245453 | 5.6
6096 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0751126 | This project includes installation of landscaping at the Welcome Center near the Georgia state line on I-75 in Chattanooga | Transportation Enhancements | 05/14/2009 | 05/14/2009 | 05/15/2010 | 130000 | 0
6097 | Tennessee | LOUDON |  | 02 | 0752037 | This project located on I-75 FROM TENNESSEE RIVER BRIDGE TO SR-73 INTERCHANGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also he | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 5402750 | 6.9
6098 | Tennessee | KNOX | KNOXVILLE | 02 | 0753147 | This project located on I-75 FROM I-640 TO SOUTH OF CALLAHAN DRIVE AND ON I-275, FROM CONCRETE PAVEMENT TO I-640 will provide a smoother riding surface for motorists, thus decreasing wear and tear on | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 2856699 | 3.4
6099 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 0811107 | This project includes installation of landscaping at the Welcome Center near the Virginia state line on I-81 in Bristol | Transportation Enhancements | 05/14/2009 | 05/14/2009 | 05/15/2010 | 130000 | 0
6100 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 0811108 | This project located on I-81 FROM SOUTH OF SR-357 TO NORTH OF SR-394 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 05/15/2009 | 05/15/2009 | 06/30/2010 | 5191759 | 7.2
6101 | Tennessee | CARROLL |  | 08 | 0900031 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Westport Road with a new Bridges over the Big Sandy River and Overflow to serve the commu | Bridge Replacement | 03/03/2009 | 03/03/2009 | 06/01/2010 | 1802813 | 0.3
6102 | Tennessee | CARTER |  | 01 | 1000025 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Steel Bridge Road (Wilbur Dam Rd) with a new Bridge over the Watauga River to serve the co | Bridge Replacement | 03/03/2009 | 03/03/2009 | 09/01/2010 | 1702780 | 0.1
6103 | Tennessee | RUTHERFORD | MURFREESBORO | 06 | 1048006 | This resurfacing project located on THOMPSON LANE FROM SR-66 TO SR-1 (US-41/70S) IN MURFREESBORO will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobile | Pavement Improvement | 08/20/2009 | 08/20/2009 | 09/30/2015 | 629537 | 4.24
6104 | Tennessee | CHEATHAM |  | 05,07 | 1100027 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SPRING CREEK ROAD with a new BRIDGE OVER SPRING CREEK to serve the community for the next | Bridge Replacement | 04/07/2009 | 04/07/2009 | 05/31/2010 | 512092 | 0.1
6105 | Tennessee | COCKE |  | 01 | 1500050 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Splashaway Road with a new Bridge over Sinking Creek to serve the community for the next s | Bridge Replacement | 03/03/2009 | 03/03/2009 | 10/01/2009 | 185976 | 0
6106 | Tennessee | COFFEE |  | 04 | 1600016 | This project will improve safety and reliability of the transportation system by replacing an older bridge on MCKELLAR DRIVE with a new BRIDGE OVER LITTLE DUCK RIVER IN MANCHESTER to serve the communi | Bridge Replacement | 05/14/2009 | 05/14/2009 | 05/15/2010 | 537458 | 0
6107 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 1900029 | This project will improve safety and reliability of the transportation system by replacing an older bridge on CHESTNUT STREET with a new BRIDGE OVER CSX RAILROAD IN NASHVILLE to serve the community fo | Bridge Replacement | 06/30/2009 | 06/30/2009 | 07/31/2010 | 1799796 | 0
6108 | Tennessee | ROBERTSON | NASHVILLE-DAVIDSON | 06 | 1953001 | This resurfacing project located on CALISTA ROAD FROM OZZY FULKS ROAD TO SR-41 (US-31W) IN WHITE HOUSE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their auto | Pavement Improvement | 08/13/2009 | 08/13/2009 | 09/30/2015 | 514812 | 4.86
6109 | Tennessee | DECATUR |  | 07 | 2000013 | This project is for the construction of new sidewalks along SR-641 in Decatur County | Transportation Enhancements | 11/12/2009 | 11/12/2009 | 09/30/2015 | 604110 | 0
6110 | Tennessee | DECATUR |  | 07 | 2000014 | This streetscape beautification project in Parsons includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 08/21/2009 | 08/21/2009 | 09/30/2015 | 1042530 | 0
6111 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 2041001 | This project is for the construction of a new bridge on Big Station Camp Creek Boulevard from 0.2 miles north of SR-6 to 0.2 miles south of SR-6 including realigning the roadway to the new bridge in | Pavement Widening | 11/16/2009 |  | 09/30/2015 | 1000000 | 0.2
6112 | Tennessee | FAYETTE |  | 07 | 2400032 | This project will improve safety and reliability of the transportation system by replacing an older bridge on FEATHERS CHAPEL ROAD with a new BRIDGE OVER TREADVILLE CREEK to serve the community for th | Bridge Replacement | 05/13/2009 | 05/13/2009 | 01/15/2010 | 345937 | 0.1
6113 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 2401289 | This project located on I-240 FROM MADISON AVENUE TO I-55 AND ON I-55, FROM NONCONNAH CREEK TO I-240 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automo | Pavement Improvement | 05/15/2009 | 05/15/2009 | 06/30/2010 | 4163630 | 5.65
6114 | Tennessee | FENTRESS |  | 04 | 2500024 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Delk Creek Road with a new Bridge over Delk Creek to serve the community for the next seve | Bridge Replacement | 03/03/2009 | 03/03/2009 | 11/01/2009 | 468403 | 0.1
6115 | Tennessee | GIBSON |  | 08 | 2700051 | This project will improve safety and reliability of the transportation system by replacing an older bridge on McMurry Road with a new Bridges over Branch, Davis Creek and Reagan Creek to serve the co | Bridge Replacement | 03/03/2009 | 03/03/2009 | 06/01/2010 | 1016860 | 0.3
6116 | Tennessee | GILES |  | 04 | 2800032 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Earl Townsend Road with a new Bridge over the West Fork of Shoal Creek to serve the commun | Bridge Replacement | 03/03/2009 | 03/03/2009 | 12/15/2009 | 273702 | 0.1
6117 | Tennessee | GILES |  | 04 | 2800033 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ELLA WEST ROAD with a new BRIDGE OVER EAST FORK OF LYNN CREEK to serve the community for | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 209891 | 0
6118 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3300046 | This project located on STANDIFER GAP ROAD FROM BILL REED ROAD TO BANKS ROAD and WOODLAND DRIVE FROM PATTENTOWN ROAD SOUTH TO BILL REED ROAD will provide a smoother riding surface for motorists, thus | Pavement Improvement | 12/07/2009 | 12/07/2009 | 09/30/2015 | 281360 | 2.42
6119 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3300047 | This project located on MOSES ROAD FROM BOY SCOUT ROAD TO GANN ROAD/WEST CRABTREE ROAD FROM MIDDLE VALLEY ROAD TO BOWMAN ROAD/LOVELL ROAD FROM DAISY DALLAS ROAD TO THE SODDY DAISY CITY LIMITS will pro | Pavement Improvement | 12/07/2009 | 12/07/2009 | 09/30/2015 | 432070 | 3.14
6120 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3300048 | This project located on FAIRVIEW ROAD FROM THE CHATTANOOGA CITY LIMITS TO GOLD POINT CIRCLE ROAD and GOLD POINT CIRCLE ROAD FROM HIXSON PIKE TO FAIRVIEW ROADwill provide a smoother riding surface for | Pavement Improvement | 12/07/2009 | 12/07/2009 | 09/30/2015 | 251315 | 2.02
6121 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3300049 | This project located on CHAMPION ROAD FROM THE CHATTANOOGA CITY LIMITS TO HARRISON PIKE and HARRISON-OOLTEWAH ROAD FROM SR-58 TO THE ENTERPRISE SOUTH INDUSTRIAL PARK will provide a smoother riding sur | Pavement Improvement | 12/07/2009 | 12/07/2009 | 09/30/2015 | 270595 | 2.02
6122 | Tennessee | HARDEMAN |  | 07 | 3500036 | This project will improve safety and reliability of the transportation system by replacing an older bridge on VAN BUREN ROAD with a new BRIDGE OVER HAMER CREEK to serve the community for the next sev | Bridge Replacement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 513939 | 0.1
6123 | Tennessee | HARDEMAN |  | 07 | 3500037 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Teague Road with a new Bridge over Clover Creek to serve the community for the next severa | Bridge Replacement | 03/03/2009 | 03/03/2009 | 06/01/2010 | 754281 | 0.1
6124 | Tennessee | HARDEMAN |  | 07 | 3500038 | This project will improve safety and reliability of the transportation system by replacing an older bridge on PARK SWAIN ROAD with a new BRIDGE OVER INDIAN CREEK to serve the community for the next s | Bridge Replacement | 04/06/2009 | 04/06/2009 | 09/30/2010 | 1019302 | 0.3
6125 | Tennessee | HAWKINS |  | 01 | 3700028 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Okolona Road with a new Bridge over Alexander Creek to serve the community for the next se | Bridge Replacement | 03/03/2009 | 03/03/2009 | 06/01/2010 | 549433 | 0.1
6126 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 3942003 | This project located on Walton Ferry Road From West Main Street to Curtis Cross Roads in Hendersonville will provide a smoother riding surface for motorists, thus decreasing wear and tear on their au | Pavement Improvement | 08/12/2009 | 08/12/2009 | 09/30/2015 | 620941 | 5.82
6127 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 3943003 | This project is for the development of design plans for a future bicycle and pedestrian facility project located on INDIAN LAKE BOULEVARD INTERSECTION AT SR-386 IN HENDERSONVILLE | Other | 08/12/2009 | 08/12/2009 | 09/15/2015 | 429931 | 0
6128 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 4404077 | This project will rehabilitate the concrete pavement on I-440 from I-40 to I-24 in Nashville | Pavement Improvement | 05/15/2009 | 05/15/2009 | 05/31/2010 | 4768267 | 7.6
6129 | Tennessee | JEFFERSON | MORRISTOWN | 01 | 4500025 | This project located on Agricultural Park Boulevard From US-25E to the Railroad Bridge in White Pine will provide a smoother riding surface for motorists, thus decreasing wear and tear on their autom | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 80121 | 0.58
6130 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 4967003 | This project is for the construction of a bridge carrying Nashville and Eastern Railroad over Central Pike in Nashville | Pavement Widening | 09/25/2009 | 09/25/2009 | 09/30/2015 | 1000000 | 0
6131 | Tennessee | LAWRENCE |  | 04 | 5000014 | This project will improve safety and reliability of the transportation system by replacing an older bridge on LONG BRANCH ROAD with a new BRIDGE OVER LONG BRANCH to serve the community for the next s | New Bridge Construction | 04/06/2009 | 04/06/2009 | 01/15/2010 | 423673 | 0
6132 | Tennessee | LAWRENCE |  | 04 | 5000015 | This project will improve safety and reliability of the transportation system by replacing an older bridge on PINEY ROAD with a new BRIDGE OVER PINEY BRANCH to serve the community for the next sever | Bridge Replacement | 04/06/2009 | 04/06/2009 | 01/01/2010 | 412870 | 0
6133 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 5365001 | This resurfacing project located on SOUTH WATER AVENUE FROM MAPLE STREET TO BUSH AVENUE IN GALLATIN will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automob | Pavement Improvement | 08/12/2009 | 08/12/2009 | 09/30/2015 | 1329100 | 1.1
6134 | Tennessee | MCNAIRY |  | 07 | 5500050 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SULPHUR SPRINGS ROAD with a new BRIDGE OVER MOSSES CREEK to serve the community for the n | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/15/2010 | 534583 | 0.1
6135 | Tennessee | MACON |  | 06 | 5600045 | This project will improve safety and reliability of the transportation system by replacing an older bridge on CARR BRANCH ROAD with a new BRIDGE OVER CARR CREEK to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 05/31/2010 | 326442 | 0
6136 | Tennessee | MACON |  | 06 | 5600046 | This project will improve safety and reliability of the transportation system by replacing an older bridge on West Wixtown Road with a new Bridge over the West Fork of Long Creek to serve the communit | Bridge Replacement | 03/03/2009 | 03/03/2009 | 12/01/2009 | 309392 | 0
6137 | Tennessee | MADISON |  | 08 | 5700066 | This project will improve safety and reliability of the transportation system by replacing an older bridge on JOHN ANDERSON ROAD with a new BRIDGES OVER BRANCHS to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2009 | 315464 | 0.1
6138 | Tennessee | MEIGS |  | 03 | 6100021 | This project will improve safety and reliability of the transportation system by replacing an older bridge on LAMONTVILLE ROAD with a new BRIDGE OVER PRICE CREEK to serve the community for the next s | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/15/2010 | 532463 | 0
6139 | Tennessee | MONROE |  | 02 | 6200022 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Belcher Gap Road with a new Bridge over Notchy Creek to serve the community for the next s | Bridge Replacement | 03/03/2009 | 03/03/2009 | 11/30/2009 | 341498 | 0.1
6140 | Tennessee | MONROE |  | 02 | 6200023 | This project will improve safety and reliability of the transportation system by replacing an older bridge on GRIFFITH BRANCH ROAD with a new BRIDGE OVER NOTCHY CREEK to serve the community for the n | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2009 | 760048 | 0
6141 | Tennessee | PERRY |  | 07 | 6800022 | This streetscape beautification project in Linden includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 09/25/2009 | 09/25/2009 | 09/30/2015 | 1602008 | 0
6142 | Tennessee | SEVIER |  | 01 | 7800053 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ROARING FORK EXT. ROAD with a new BRIDGE OVER ROARING FORK CREEK IN GATLINBURG to serve t | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2009 | 206916 | 0
6143 | Tennessee | SEVIER |  | 01 | 7800054 | This project will improve safety and reliability of the transportation system by replacing an older bridge on OLD NEWPORT HIGHWAY with a new BRIDGE OVER EAST FORK LITTLE PIGEON RIVER to serve the com | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/15/2010 | 568065 | 0
6144 | Tennessee | SEVIER |  | 01 | 7800055 | This project will improve safety and reliability of the transportation system by replacing an older bridge on LECONTE STREET with a new BRIDGE OVER WEST PRONG LITTLE PIGEON RIVER IN GATLINBURG to ser | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/31/2010 | 1338750 | 0
6145 | Tennessee | SEVIER |  | 01 | 7800056 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ROCKY FLATS ROAD with a new BRIDGE OVER DUNN CREEK to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/15/2010 | 611328 | 0
6146 | Tennessee | STEWART |  | 08 | 8100009 | This project is for the construction of a new visitors' center in Stewart County on Highway 79 | Transportation Enhancements | 05/14/2009 | 05/14/2009 | 09/30/2015 | 1045000 | 0
6147 | Tennessee | TIPTON |  | 08 | 8400067 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ROBERT JOHNSON ROAD with a new BRIDGE OVER DRAINAGE CANAL to serve the community for the | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2009 | 289775 | 0
6148 | Tennessee | TIPTON |  | 08 | 8400068 | This project will improve safety and reliability of the transportation system by replacing an older bridge on BUCKSNORT ROAD with a new BRIDGE OVER MATHIS CREEK to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 05/15/2010 | 754386 | 0
6149 | Tennessee | TIPTON |  | 08 | 8400069 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ANTIOCH HIGHWAY with a new BRIDGE OVER FLAT CREEK to serve the community for the next sev | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/15/2010 | 716762 | 0
6150 | Tennessee | TIPTON |  | 08 | 8400070 | This project will improve safety and reliability of the transportation system by replacing an older bridge on PORTERSVILLE ROAD with a new BRIDGE OVER HEBRON BRANCH to serve the community for the next | Bridge Replacement | 05/15/2009 | 05/15/2009 | 01/15/2010 | 489562 | 0.1
6151 | Tennessee | TROUSDALE |  | 06 | 8500018 | This streetscape beautification project in Hartsville includes elevator upgrades in the Hartsville Courthouse, rehabilitating/upgrading sidewalks, installing/upgrading lighting, pedestrian amenities a | Transportation Enhancements | 05/12/2009 | 05/21/2009 | 09/30/2015 | 548452 | 0
6152 | Tennessee | WASHINGTON |  | 01 | 9000045 | This project will improve safety and reliability of the transportation system by replacing an older bridge on BOB DAVIS ROAD with a new BRIDGE OVER CSX RAILROAD to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 05/31/2010 | 953845 | 0
6153 | Tennessee | BLOUNT | KNOXVILLE | 02 | 9101011 | This project is for the construction of a new pedestrian bridge over State Route 115 in Alcoa for the Culton Creek Greenway | Transportation Enhancements | 09/25/2009 | 09/25/2009 | 09/15/2015 | 1600000 | 0
6154 | Tennessee | BLOUNT | KNOXVILLE | 02 | 9101012 | This resurfacing project located on CALDERWOOD STREET FROM JOULE STREET TO THE CITY LIMITS OF ALCOA/SINGLETON STATION ROAD FROM SR-115 (ALOCA HWY) TO THE CITY LIMITS OF ALCOA will provide a smoother | Pavement Improvement | 08/07/2009 | 08/07/2009 | 09/30/2015 | 561878 | 4.1
6155 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 9102007 | This project located on OLD JONESBORO ROAD FROM THE CITY LIMITS TO GALWAY ROAD/EXIDE DRIVE FROM SR-34 (US-11E) TO EDISON CIRCLE/ASH STREET FROM MARTIN LUTHER KING JR. BOULEVARD TO SR-34 (US-421)/BROAD | Pavement Improvement | 01/07/2010 |  | 09/30/2015 | 796000 | 5.1
6156 | Tennessee | CARTER | JOHNSON CITY | 01 | 9103013 | This project will widen LYNN AVENUE from 2 lanes to 5 lanes including bike lanes and sidwalks FROM SR-67 (BROAD STREET) TO EAST ELK AVENUE IN ELIZABETHTON | Pavement Improvement | 07/10/2009 | 07/10/2009 | 11/01/2010 | 1212573 | 0.17
6157 | Tennessee | GREENE |  | 01 | 9104011 | This project will improve safety and reliability of the transportation system by replacing an older bridge on HANNAH STREET (OLD TUSCULUM ROAD) with a new BRIDGE OVER HOLLEY CREEK IN GREENEVILLE to s | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2009 | 302820 | 0
6158 | Tennessee | JEFFERSON | MORRISTOWN | 03 | 9106011 | This project located on North Russell Avenue From SR-92 to Old Andrew Johnson Highway in Jefferson City/North Chucky Pike From Clearbrook Drive to Old Andrew Johnson Highway in Jefferson City/North S | Pavement Improvement | 08/07/2009 | 08/07/2009 | 09/30/2015 | 400162 | 2.94
6159 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 9107009 | This project is for the construction of a bicycle and pedestrian path in Johnson City including landscaping and pedestrian amenities | Transportation Enhancements | 09/03/2009 | 09/03/2009 | 09/15/2015 | 400000 | 0
6160 | Tennessee | SULLIVAN | KINGSPORT (VA) | 01 | 9108031 | This project located on NORTH EASTMAN ROAD FROM LINCOLN STREET TO EAST STONE DRIVE/CLINCHFIELD STREET FROM WEST CENTER STREET TO WEST STONE DRIVE/EAST CENTER STREET FROM FORT HENRY DRIVE TO MEMORIAL B | Pavement Improvement | 09/22/2009 | 09/22/2009 | 09/30/2015 | 1392309 | 3.75
6161 | Tennessee | SULLIVAN | KINGSPORT (VA) | 01 | 9108032 | This project located on OREBANK ROAD FROM MEMORIAL BOULEVARD TO LAMBERTH STREET/BLOOMINGDALE PIKE FROM WEST STONE DRIVE TO GRAVELY ROAD IN KINGSPORT will provide a smoother riding surface for motorist | Pavement Improvement | 09/22/2009 | 09/22/2009 | 09/30/2015 | 581878 | 3.65
6162 | Tennessee | SULLIVAN | KINGSPORT (VA) | 01 | 9108033 | This project located on NETHERLAND INN ROAD FROM WEST STONE DRIVE TO WEST CENTER STREET/ EAST RIVERPORT ROAD FROM BRIDGE OVER HOLSTON RIVER TO JARED DRIVE IN KINGSPORT will provide a smoother riding s | Pavement Improvement | 09/22/2009 | 09/22/2009 | 09/30/2015 | 192008 | 5.37
6163 | Tennessee | KNOX | KNOXVILLE | 02 | 9109130 | This project will widen CAMPBELL STATION ROAD from 4 lanes to 5 lanes FROM PARKSIDE DRIVE TO JAMESTOWN BOULEVARD IN FARRAGUT | Pavement Widening | 05/15/2009 | 05/15/2009 | 12/31/2010 | 2355370 | 0.94
6164 | Tennessee | KNOX | KNOXVILLE | 02 | 9109131 | This project is for traffic signal timing upgrades at various locations in Knoxville. | Other | 07/17/2009 | 07/17/2009 | 09/30/2015 | 100000 | 0
6165 | Tennessee | KNOX | KNOXVILLE | 02 | 9109132 | This project is for the construction of the Papermill Bluff bicycle/pedestrian pathway from Papermill Road to Weisgarber Road that includes landscaping. | Transportation Enhancements | 07/17/2009 | 07/17/2009 | 09/30/2015 | 642000 | 0
6166 | Tennessee | KNOX | KNOXVILLE | 02 | 9109134 | This project is for the development of design plans for a future bicycle and pedestrian facility project located on EAST WOODLAND AVENUE FROM NORTH CENTRAL STREET TO NORTH BROADWAY STREET IN KNOXVILLE | Other | 07/17/2009 | 07/17/2009 | 09/30/2015 | 35000 | 0.94
6167 | Tennessee | LOUDON | KNOXVILLE | 02 | 9111003 | This resurfacing project located on ADESA BOULEVARD ADESA BOULEVARD, FROM OLD HWY 95 TO SR-73 (US-321) IN LENOIR CITY/BROWDER HOLLOW ROAD/ JOHNSTON DRIVE FROM SR-2 (US-11) TO NEAR JOHNSON CIRCLE IN LE | Pavement Improvement | 09/22/2009 | 09/22/2009 | 09/30/2015 | 388574 | 4.24
6168 | Tennessee | HAMBLEN | MORRISTOWN | 01 | 9113014 | This resurfacing project located on EAST 2ND NORTH STREET FROM ANDERSON STREET TO NORTH CUMBERLAND STREET IN MORRISTOWN will provide a smoother riding surface for motorists, thus decreasing wear and t | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 273132 | 0.8
6169 | Tennessee | ANDERSON |  | 03 | 9117011 | This project will improve safety and reliability of the transportation system by replacing an older bridge on YARNELL ROAD with a new BRIDGE OVER LITTLE DISMAL CREEK IN CLINTON to serve the community | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/31/2010 | 286734 | 0.1
6170 | Tennessee | MCMINN |  | 02 | 9201011 | This streetscape beautification project in Athens includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 09/01/2009 | 01/04/2010 | 09/30/2015 | 1159743 | 0
6171 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9202095 | This project is for the construction of a new trail and bikeway along South Chickamauga Creek in Chattanooga | Transportation Enhancements | 09/02/2009 | 09/02/2009 | 09/15/2015 | 500000 | 0
6172 | Tennessee | BRADLEY | CLEVELAND | 03 | 9203013 | This resurfacing project located on FREEWILL ROAD FROM CUMBERLAND HILLS CIRCLE TO NORTH OF COTTONWOOD BEND IN CLEVELAND will provide a smoother riding surface for motorists, thus decreasing wear and t | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 510359 | 4.76
6173 | Tennessee | BRADLEY | CLEVELAND | 03 | 9203014 | This resurfacing project located on RAIDER DRIVE FROM KEITH STREET TO PEERLESS ROAD IN CLEVELAND will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobile | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 468017 | 0.96
6174 | Tennessee | BRADLEY | CLEVELAND | 03 | 9203015 | This project is for the construction of a new comfort station that will include restrooms and drinking fountain for the Mouse Creek Greenway | Transportation Enhancements | 11/24/2009 | 11/24/2009 | 09/30/2015 | 40000 | 0
6175 | Tennessee | WHITE |  | 04 | 9300039 | This project will improve safety and reliability of the transportation system by replacing an older bridge on FANCHER MILL ROAD with a new BRIDGE OVER TAYLOR CREEK to serve the community for the next | Bridge Replacement | 05/15/2009 | 05/15/2009 | 09/30/2010 | 891195 | 0.2
6176 | Tennessee | MAURY |  | 04 | 9302016 | This project will improve safety and reliability of the transportation system by replacing an older bridge on INDUSTRIAL PARK ROAD with a new BRIDGE OVER THE DUCK RIVER IN COLUMBIA to serve the commun | Bridge Replacement | 05/15/2009 | 05/15/2009 | 10/15/2010 | 2693882 | 0
6177 | Tennessee | DICKSON |  | 08 | 9303010 | This project includes the construction and installation of transportation exhibits in the Halbrook Hotel Railroad Museum in Dickson | Transportation Enhancements | 11/13/2009 |  | 09/30/2014 | 200000 | 0
6178 | Tennessee | WILLIAMSON | NASHVILLE-DAVIDSON | 07 | 9305024 | This project is for the development of design plans for a future installation of video technology in Franklin to expand the existing traffic monitoring system and to assist incident management and qui | Other | 01/07/2010 |  | 09/30/2015 | 250000 | 0
6179 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 9306014 | This streetscape beautification project in Gallatin includes landscaping, pedestrian amenities, lighting, upgrading/rehabilitating sidewalks and utility relocation | Transportation Enhancements | 10/30/2009 | 10/30/2009 | 09/15/2015 | 480000 | 0
6180 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 99 | 9312090 | This project located on TROUSDALE DRIVE FROM HARDING PLACE TO HOGAN ROAD/ABBOTT MARTIN ROAD FROM HILLSBORO PIKE TO THE CITY LIMITS/BOWLING AVENUE FROM WEST END AVENUE TO WOODLAWN AVENUE /HICKORY HOLLO | Pavement Improvement | 12/14/2009 | 12/14/2009 | 09/30/2015 | 2290963 | 7.46
6181 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312091 | This project located on JEFFERSON STREET FROM RAILROAD BRIDGE TO DR. DB TODD, JR./ELLISTON PLACE FROM WEST END AVENUE TO CHURCH STREET BOULEVARD/CHURCH STREET FROM 21ST AVENUE NORTH TO 16TH AVENUE NOR | Pavement Improvement | 12/14/2009 | 12/14/2009 | 09/30/2015 | 2118768 | 6.46
6182 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312092 | This project located on CENTRAL PIKE FROM DODSON CHAPEL ROAD TO OLD HICKORY BOULEVARD/SOUTH GRAYCROFT AVENUE FROM OLD HICKORY BOULEVARD TO DUE WEST AVENUE/ELM HILL PIKE FROM ATRIUM WAY TO DONELSON PIK | Pavement Improvement | 12/14/2009 | 12/14/2009 | 09/30/2015 | 2277639 | 7.57
6183 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312093 | This project will provide for the signal timing upgrades at various locations in Nashville | Safety/Traffic Management | 11/04/2009 | 11/04/2009 | 09/30/2015 | 1000000 | 0
6184 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312094 | This project is for the optimization of traffic signal timing at various intersections in Nashville | Safety/Traffic Management | 09/11/2009 | 09/11/2009 | 09/30/2015 | 1000000 | 0
6185 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312095 | This project is for the construction of a new bicycle and pedestrian path from the levee at Metro Center to Clifton Avenue in Nashville | Transportation Enhancements | 09/01/2009 | 09/01/2009 | 09/30/2015 | 1000000 | 0
6186 | Tennessee | WILSON | NASHVILLE-DAVIDSON | 05 | 9312096 | This project is for the construction of a new greenway on West Division Street From the Music City Star Station to 4th Street in Mount Juliet. | Transportation Enhancements | 09/23/2009 | 09/23/2009 | 09/15/2015 | 450000 | 0
6187 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312097 | This project is for intersection improvements including traffic light and crosswalk signal upgrades at various intersections on Harding Place (SR-255), Bell Road (SR-254), Nolensville Pike (SR-11), an | Safety/Traffic Management | 11/13/2009 | 11/13/2009 | 09/30/2015 | 1000000 | 0
6188 | Tennessee | RUTHERFORD | MURFREESBORO | 06 | 9317007 | This project will widen WALDRON ROAD/PARTHENON BOULEVARD from 3 lanes to 5 lanes FROM NORTH OF INDUSTRIAL DRIVE/ENTERPRISE BOULEVARD TO SR-1 | Pavement Widening | 09/17/2009 | 09/17/2009 | 11/30/2011 | 1000000 | 2.19
6189 | Tennessee | MADISON | JACKSON | 08 | 9406008 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SECOND STREET with a new BRIDGE OVER ANDERSON BRANCH IN JACKSON to serve the community f | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 375956 | 0
6190 | Tennessee | WEAKLEY |  | 08 | 9408008 | This streetscape beautification project in Martin includes elevator upgrades in the Hartsville Courthouse, rehabilitating/upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and l | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 09/30/2015 | 1470900 | 0
6191 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 9409135 | This resurfacing project located on HACKS CROSS ROAD FROM STATE LINE ROAD TO THE MEMPHIS CITY LIMITS/HOUSTON LEVEE ROAD FROM THE WOLD RIVER BRIDGE TO WOLF RIVER PARKWAY/WALNUT GROVE ROAD FROM ROCKY PO | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 2550995 | 28.94
6192 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9409137 | This project is for the development of design plans for a future bicycle and pedestrian facility project located on AIRLINE ROAD FROM THE C.S.X. RAILROAD TO I-40 IN ARLINGTON and to provide a smoother | Other | 07/21/2009 | 07/21/2009 | 09/30/2015 | 32650 | 4.34
6193 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9409138 | This project is for the development of design plans for a future bicycle and pedestrian facility project located on CHESTER STREET FROM GRIFFIN ROAD TO MILTON WILSON ROAD IN ARLINGTON and to provide a | Other | 04/01/2009 | 07/21/2009 | 09/30/2015 | 8193 | 0.98
6194 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9409140 | This project is for the construction of a bicycle/pedestrian pathway on Canada Road that includes landscaping. | Transportation Enhancements | 05/27/2009 | 05/27/2009 | 09/30/2015 | 1043432 | 2.5
6195 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 08 | 9411006 | This resurfacing project located on FROM PAUL BARRET PARKWAY TO THE CITY LIMITS OF MILLINGTON/CHURCH STREET FROM NAVY ROAD TO PAUL BARRET PARKWAY IN MILLINGTON/EASLEY ROAD FROM HWY 51 TO NAVY ROAD IN | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 1431200 | 6.08
6196 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 08 | 9411007 | This project consists of repairs to the bridge over Big Creek on Raleigh-Millington Road in Millington | Other | 07/17/2009 | 07/17/2009 | 09/30/2015 | 7240 | 0
6197 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 08 | 9411008 | This resurfacing project located on BIG CREEK CHURCH ROAD FROM HWY 51 TO RALIEGH-MILLINGTON ROAD IN MILLINGTON will provide a smoother riding surface for motorists, thus decreasing wear and tear on th | Other | 07/17/2009 | 07/17/2009 | 09/30/2015 | 18760 | 2.44
6198 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 08 | 9411009 | This streescape project is for landscaping and scenic beautification on Navy Road from US-51 to east of Veterans Parkway in Millington | Transportation Enhancements | 07/17/2009 | 07/17/2009 | 09/30/2015 | 769729 | 2.5
6199 | Tennessee | LAUDERDALE |  | 08 | 9418009 | This streetscape beautification project in Ripley includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 05/14/2009 | 05/14/2009 | 09/30/2015 | 1122000 | 0
6200 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9419003 | This resurfacing project located on ST. ELMO ROAD FROM MEMPHIS-ARLINGTON ROAD TO KIRBY WHITTEN ROAD IN BARTLETT/ELMORE PARK ROAD FROM ELMORE PARK TO YALE ROAD IN BARTLETT/SYCAMORE VIEW ROAD FROM STAGE | Other | 07/17/2009 | 07/17/2009 | 09/30/2015 | 61000 | 9.58
6201 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9419004 | This resurfacing project located on BARTLETT BOULEVARD FROM THE SOUTH CITY LIMITS TO MEMPHIS-ARLINGTON ROAD IN BARTLETT/ALTRURIA ROAD FROM SUMMER AVENUE TO YALE ROAD IN BARTLETT will provide a smooth | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 1619000 | 8.42
6202 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9420002 | This project is for the replacement of existing roadway pavement and including sidewalks on Farmington Boulevard from Allenby Road to Wolf River Boulevard in Germantown. | Other | 07/17/2009 | 07/17/2009 | 09/30/2015 | 130000 | 2.06
6203 | Tennessee | STATEWIDE |  | 05 | 9900013 | The On-the-Job Training/Supportive Services program will train ready, willing and able individuals for entry or re-entry into the workforce. | Other | 02/01/2010 | 02/01/2010 | 01/31/2011 | 800000 | 0
6204 | Texas | DENTON |  | 24 | 0095067 | SPN:0918-46-065-REPLACE BRIDGE AND APPROACHES (NEW STEEL TRUSS) : ON GREGORY ROAD AT DUCK CREEK ; | Bridge Replacement | 07/02/2009 | 08/26/2009 | 05/01/2010 | 398815.28 | 0.07
6205 | Texas | HARRIS | HOUSTON | 10 | 0099026 | SPN:0912-71-586-CONSTRUCT 2 LANE ASPHALT ROAD WITH TURN LANES : ON GOSLING RD FROM KUYKENDAHL ; | New Construction | 09/28/2009 |  | 05/01/2011 | 1621404.85 | 0.503
6206 | Texas | CHAMBERS |  | 14 | 2000065 | SPN:0508-03-075-CONSTRUCT TOURIST AND VISITOR CENTER, PARKING LOT AND LANDSCAPING : 2 MI WEST OF FM 1724 ; | Transportation Enhancements | 10/16/2009 |  |  | 11017416.59 | 0.001
6207 | Texas | NAVARRO |  | 06 | 2000293 | SPN:0166-01-041-RECONSTRUCTION OF SAFETY REST AREA : 2 MILES S OF RICHLAND ; | Transportation Enhancements | 09/28/2009 | 10/08/2009 | 06/01/2009 | 11770092.74 | 1.231
6208 | Texas | HARRIS | HOUSTON | 18 | 2000597 | SPN:0912-71-705-LANDSCAPE AND SCENIC BEAUTIFICATION OF HISTORIC TRANSPORTATION HUB : AT ALLEN`S LANDING IN HOUSTON ; | Transportation Enhancements | 12/04/2009 |  | 12/04/2009 | 902024.64 | 0.13
6209 | Texas | WILLIAMSON |  | 31 | 2002110 | SPN:0914-05-122-CONSTRUCT TRAIL; | Transportation Enhancements | 06/23/2009 | 10/05/2009 | 08/01/2014 | 331580.8 | 0.001
6210 | Texas | DALLAS | DALLAS-FORT WORTH | 30 | 2002129 | SPN:0918-45-643-CONSTRUCT 2 MILES OF BICYCLE WEB ROUTE (TENISON TRAIL PHASE ONE-EAST DALLAS VELOWAY) : WINSTED DR WITHIN OLD SP&SF RR ROW, ; | Transportation Enhancements | 08/19/2009 | 09/10/2009 | 12/01/2010 | 1786702.8 | 2.372
6211 | Texas | SHERMAN |  | 13 | 2002207 | SPN:0904-40-010-TRANS ENHANCEMENT : STRATFORD STREETSCAPE ; | Transportation Enhancements | 09/01/2009 | 10/19/2009 | 09/01/2009 | 1558107.81 | 0.001
6212 | Texas | HALL |  | 13 | 2002754 | SPN:0925-09-021-REPLACE EXISTING BRIDGE FACILITY : CR P @ DRAW ; | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 248320.15 | 0.066
6213 | Texas | FORT BEND | HOUSTON | 14 | 2005833 | SPN:0912-34-117-REPLACE BRIDGE AND APPROACHES : MULLINS REYNOLDS AT BESSIES CREEK ; | Bridge Replacement | 10/16/2009 |  |  | 493945.57 | 0.057
6214 | Texas | SMITH |  | 01 | 2005996 | SPN:3487-01-004-CONSTRUCT 2 LNS CONTROLLED ACCESS TOLL ROAD ON NEW LOCATION (ULTIMATE 4-LANE FACILITY) (TOLL) : .11 M N OF SH 31(2 M E OF FM 2661)S ; | New Construction | 07/21/2009 | 08/06/2009 | 08/01/2013 | 29872772.08 | 6.569
6215 | Texas | GALVESTON | GALVESTON | 22 | 2006063 | SPN:0912-73-114-REPLACE BRIDGE : MCKAY ROAD AT DRAINAGE DITCH ; | Bridge Replacement | 05/28/2009 | 06/29/2009 | 11/01/2009 | 313362.02 | 0.065
6216 | Texas | STARR |  | 28 | 2006304 | SPN:0921-26-015-REHABILITATION OF PAVEMENT, CURB & GUTTER, STORM SEWER, AND RESTRIPE TO ONE WAY PAIR : US 83 N ON AVASOLO ST. ; | Pavement Improvement | 08/10/2009 | 10/20/2009 | 02/01/2011 | 1371513.37 | 0.678
6217 | Texas | RANDALL |  | 13 | 2006439 | SPN:0904-11-022-WIDEN TO A 4 LANE ARTERIAL : ON GEORGIA STREET, FROM SW 58TH AVE ; | Pavement Widening | 11/02/2009 |  |  | 1940000 | 0.681
6218 | Texas | COLLIN | DALLAS-FORT WORTH | 03 | 2006470 | SPN:0091-05-055-INTERSECTION IMPROVEMENTS; | Pavement Improvement | 09/19/2009 |  | 02/01/2010 | 1034202.48 | 0.001
6219 | Texas | HARTLEY |  | 13 | 2007003 | SPN:0041-01-038-REHAB EXISTING ROADWAY (NBL) : DALHART SOUTH CITY LIMITS ; | Pavement Improvement | 06/29/2009 | 07/20/2009 | 01/01/2010 | 3824417.4 | 13.647
6220 | Texas | BURLESON |  | 10 | 2007109 | SPN:0186-03-057-OVERLAY CONSISTING OF A ONE COURSE SURFACE TREATMENT, AN HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : BRUSHY CREEK ; | Pavement Improvement | 06/29/2009 | 09/01/2009 | 03/01/2010 | 1921016.47 | 6.001
6221 | Texas | DALLAS | DALLAS-FORT WORTH | 30 | 2007383 | SPN:0196-07-027-CONSTRUCTION OF DECK AND PLAZA OVER FREEWAY WOODALL RODGERS DECK PLAZA : WEST OF SAINT PAUL ; | Transportation Enhancements | 09/22/2009 | 10/19/2009 | 06/01/2009 | 16700000 | 0.25
6222 | Texas | VAL VERDE |  | 23 | 2007565 | SPN:0922-11-027-FOR THE CONSTRUCTION OF A HIKE & BIKE TRAIL FACILITY PHASE II : BRIDGE ST ; | Transportation Enhancements | 10/06/2009 | 11/02/2009 |  | 64558.22 | 0.225
6223 | Texas | COMAL |  | 21 | 2007704 | SPN:0857-01-025-WIDEN NARROW ROADWAY TO ADD SHOULDERS AND PASSING LANES : FM 484 ; | Pavement Improvement | 07/10/2009 | 08/06/2009 | 01/01/2010 | 668050.28 | 0.863
6224 | Texas | ELLIS | DALLAS-FORT WORTH | 06 | 2007710 | SPN:0918-22-119-REPLACE BRIDGE AND APPROACHES : NORTH WARD ST AT HOUSTON CREEK ; | Bridge Replacement | 09/22/2009 | 10/22/2009 | 05/01/2010 | 229500 | 0.071
6225 | Texas | HARRIS |  | 10 | 2007822 | SPN:3050-03-012-CONSTRUCT RAILROAD-HIGHWAY GRADE SEPARATION : 0.307 MILES NORTH OF UPRR ; | New Bridge Construction | 10/14/2009 | 10/19/2009 |  | 6871970.66 | 0.777
6226 | Texas | HARRIS | HOUSTON | 29 | 2007854 | SPN:3256-03-072-TURN RADIUS IMPROVEMENTS AT VARIOUS LOCATIONS : AT VISTA,SPENCER,PASADENA BLVD_& ; | Pavement Improvement | 11/02/2009 |  |  | 2349189.33 | 0.36
6227 | Texas | HALL |  | 13 | 2008245 | SPN:0925-09-025-REPLACEMENT OF EXISTING BRIDGE FACILITY : CR C TRIBUTARY DRY SALT CREEK ; | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 279174.3 | 0.18
6228 | Texas | HALL |  | 13 | 2008246 | SPN:0925-09-028-REPLACE EXIST BRIDGE FACILITY : CR I @ DRAW CREEK ; | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 218989 | 0.063
6229 | Texas | TAYLOR |  | 19 | 2008341 | SPN:0908-33-079-REPLACE BRIDGE AND APPROACHES : ON CR 344 ; | Bridge Replacement | 06/22/2009 | 07/10/2009 | 01/01/2011 | 84185.18 | 0.051
6230 | Texas | TAYLOR |  | 19 | 2008348 | SPN:0908-33-075-REPLACE BRIDGE & APPROACHES : ON CR 173 (PSN 1) ; | Bridge Replacement | 06/22/2009 | 07/10/2009 | 01/01/2011 | 129821.6 | 0.042
6231 | Texas | TAYLOR |  | 19 | 2008350 | SPN:0908-33-077-REPLACE BRIDGE & APPROACHES : ON CR 345 (PSN 1) ; | Bridge Replacement | 06/22/2009 | 07/10/2009 | 01/01/2011 | 99519.34 | 0.044
6232 | Texas | TAYLOR |  | 19 | 2008351 | SPN:0908-33-078-REPLACE BRIDGE AND APPROACHES : ON CR 344 ; | Bridge Replacement | 06/22/2009 | 07/10/2009 | 01/01/2011 | 195260.2 | 0.068
6233 | Texas | CHILDRESS |  | 13 | 2008530 | SPN:0925-08-017-REPLACEMENT OF EXISTING BRIDGE FACILITY : CR 25 @ DRAW ; | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 134256 | 0.085
6234 | Texas | HALL |  | 13 | 2008532 | SPN:0925-09-027-REPLACE EXIST BRIDGE FACILITY : CR CC @ KENT CREEK ; | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 173523.7 | 0.227
6235 | Texas | ELLIS |  | 06 | 2008536 | SPN:0918-22-112-REPLACE BRIDGE AND APPROACHES : FRANKS ROAD AT RICHLAND CREEK ; | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 525000 | 0.074
6236 | Texas | ELLIS |  | 06 | 2008537 | SPN:0918-22-114-REPLACE BRIDGE AND APPROACHES : PLUTO RD. AT MILL CREEK ; | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 181000 | 0.65
6237 | Texas | ELLIS |  | 06 | 2008538 | SPN:0918-22-116-REPLACE BRIDGE : MORGAN RD AT HOG CREEK TRIB ; | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 208990.25 | 0.001
6238 | Texas | ELLIS |  | 06 | 2008539 | SPN:0918-22-117-REPLACE BRIDGE AND APPROACHES : SCHIELD ROAD AT ELM BRANCH ; | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 262000 | 0.001
6239 | Texas | ELLIS |  | 06 | 2008540 | SPN:0918-22-118-REPLACE BRIDGE AND APPROACHES : PECAN TREE ROAD AT BIG ONION CREEK ; | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 214992.25 | 0.001
6240 | Texas | JEFFERSON | PORT ARTHUR | 02 | 2008658 | SPN:0306-03-118-RAISE ROADWAY ELEVATION : 0.96 MI W OF RAINBOW BRIDGE ; | Pavement Improvement | 11/02/2009 |  |  | 408556.79 | 0.321
6241 | Texas | HALL |  | 13 | 2008721 | SPN:0925-09-026-REPLACEMENT OF EXISTING BRIDGE FACILITY : CR 7 @TURKEY CREEK ; | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 169359.15 | 0.065
6242 | Texas | MILLS |  | 11 | 2009012 | SPN:0054-09-030-SCARIFY AND RESHAPE BASE, NEW BASE, STRUCTURES, & SURFACING : US 183, EAST ; SPN:0055-01-025-SCARIFY AND RESHAPE BASE, NEW BASE, STRUCTURES, AND SURFACING : LOOP 15, EAST ; | Pavement Widening | 07/10/2009 | 08/07/2009 | 10/01/2011 | 4605444.97 | 9.848
6243 | Texas | TAYLOR |  | 19 | 2009054 | SPN:0733-03-032-REPLACE BRIDGE & APPROACHES : ON FM 126 (PSN 13) ; | Bridge Replacement | 07/06/2009 | 08/17/2009 | 03/01/2010 | 622795.2 | 0.112
6244 | Texas | LUBBOCK |  | 19 | 2009104 | SPN:0783-02-064-WIDEN FREEWAY TO 6 MAIN LANES AND NEW OVERPASS : 200`EAST OF FM 2528 (FRANKFORD AVE) ; | Pavement Widening | 07/21/2009 | 08/06/2009 | 01/01/2011 | 16518640.06 | 2.281
6245 | Texas | FREESTONE |  | 06 | 2009153 | SPN:0456-03-015-RESTORATION OF EXISTING ROAD CONSISTING OF GRADING, STRUCTURES, BASE, SURFACE AND PAVEMENT MARKINGS AND MARKERS : SH 75 ; SPN:0612-03-012-RESTORE EXISTING ROAD CONSISTING OF GRADING, F | Pavement Improvement | 06/12/2009 | 06/26/2009 | 07/01/2010 | 2957146.49 | 17.333
6246 | Texas | ZAVALA |  | 23 | 2009237 | SPN:0037-03-071-FOR THE CONSTRUCTION OF SEALCOAT TYPE WORK : 2.33 MI S. OF FM 1025 0.32 MI N OF FM 1433; SPN:0037-05-041-FOR THE CONSTRUCTION OF SEALCOAT TYPE WORK : ZAVALA/DIMMIT CO.LINE SH 85; SPN | Pavement Improvement | 11/18/2009 |  |  | 2400948.66 | 49.048
6247 | Texas | OCHILTREE |  | 13 | 2009455 | SPN:0030-02-041-REHAB EXISTING RDWY : PERRYTON ; | Pavement Improvement | 06/12/2009 | 06/17/2009 | 09/01/2009 | 1366893.73 | 7.761
6248 | Texas | ARMSTRONG |  | 13 | 2009456 | SPN:0042-03-038-REHAB EXISTING ROADWAY : CARSON COUNTY LINE ; | Pavement Improvement | 06/12/2009 | 07/13/2009 | 02/01/2010 | 8895225.05 | 8.646
6249 | Texas | RANDALL |  | 13 | 2009457 | SPN:0168-09-154-OVERLAY : POTTER COUNTY LINE ; | Pavement Improvement | 06/04/2009 | 06/09/2009 | 11/01/2010 | 1325113.17 | 2.608
6250 | Texas | HARDEMAN |  | 13 | 2009459 | SPN:0043-02-067-MILL & HOTMIX OVERLAY : CHILDRESS C/L, SE ; | Pavement Improvement | 06/22/2009 | 08/04/2009 | 10/01/2009 | 1256628.27 | 9.924
6251 | Texas | HALL, CHILDRESS |  | 13 | 2009460 | SPN:0704-01-018-REHABILITATION OF EXISTING ROADWAY : HALL C/L ; SPN:0704-03-012-REHABILITATION OF EXISTING ROADWAY : 1.818 MI N OF COTTLE C/L, NE ; | Pavement Improvement | 06/09/2009 | 06/25/2009 | 07/01/2010 | 3563720.58 | 6.97
6252 | Texas | BREWSTER |  | 23 | 2009461 | SPN:0020-11-046-MILL AND INLAY : MOSLEY LANE ; | Pavement Improvement | 06/23/2009 | 08/03/2009 | 10/01/2009 | 1956262.54 | 7.921
6253 | Texas | EL PASO |  | 16 | 2009462 | SPN:2326-01-020-OVERLAY, MILL AND INLAY : FM 3255 ; | Pavement Improvement | 05/07/2009 | 06/03/2009 | 09/01/2009 | 596777.5 | 2.938
6254 | Texas | EL PASO |  | 23 | 2009463 | SPN:1281-01-016-OVERLAY : INT OF FM 76 AND FM 1110 ; | Pavement Improvement | 05/19/2009 | 06/04/2009 | 09/01/2009 | 299899.9 | 1.2
6255 | Texas | EL PASO |  | 16 | 2009464 | SPN:2552-04-039-MILL AND INLAY AND BRIDGE DECK REPAIR : US 54/LP 375 ; | Pavement Improvement | 05/06/2009 | 05/30/2009 | 10/01/2009 | 1325044.9 | 1.74
6256 | Texas | CASTRO |  | 19 | 2009465 | SPN:1291-01-012-REHABILITATION OF EXISTING ROAD : SH 86 ; SPN:1291-08-005-REHABILITATION OF EXISTING ROAD : FM 2397 ; SPN:3133-02-002-REHABILITATION OF EXISTING ROAD RAISE LAKEFILLS : DEAF SMITH COU | Pavement Improvement | 06/02/2009 | 08/20/2009 | 03/01/2011 | 7681000 | 15.607
6257 | Texas | HALE, FLOYD |  | 19 | 2009466 | SPN:2125-01-011-OVERLAY : FM 400 ; SPN:2125-02-007-OVERLAY : HALE COUNTY LINE ; | Pavement Improvement | 06/05/2009 | 07/24/2009 | 03/01/2010 | 2448350.4 | 10.23
6258 | Texas | SWISHER, HALE, LUBBOCK |  | 19 | 2009467 | SPN:0905-06-077-IH 27 PAVEMENT REPAIR FY 2009 BACKLOG PROJECT; PLACEHOLDER CSJ : IH 27, CITY OF LUBBOCK ; SPN:0905-12-037-IH 27 PAVEMENT REPAIR FY 2009 BACKLOG PROJECT; PLACEHOLDER CSJ : IH 27, LUBB | Pavement Improvement | 05/19/2009 | 06/15/2009 | 07/01/2010 | 6219330.21 | 90.304
6259 | Texas | MARTIN |  | 11 | 2009468 | SPN:0494-02-023-PAVEMENT STRUCTURE RESTORATION : 7 MI SOUTH OF DAWSON CO.LINE ; | Pavement Improvement | 06/05/2009 | 09/16/2009 | 11/01/2009 | 1435027.95 | 7
6260 | Texas | PECOS |  | 23 | 2009469 | SPN:0866-06-018-PAVEMENT STRUCTURE RESTORATION : SPUR 194 ; | Pavement Improvement | 06/16/2009 | 08/27/2009 | 11/01/2009 | 1498725.45 | 17.914
6261 | Texas | ANDREWS |  | 11 | 2009470 | SPN:0548-01-036-ROADWAY REHABILITATION : US 385 ; SPN:0548-05-041-ROADWAY REHABILITATION : 1.0 MILE WEST OF US 385 ; | Pavement Improvement | 06/29/2009 | 07/14/2009 | 03/01/2010 | 4077150.57 | 1.535
6262 | Texas | IRION |  | 11 | 2009471 | SPN:0077-04-028-RESTORATION OF EXISTING ROADWAY : 10.219 MI. S. OF THE TOM GREEN C/L ; SPN:0077-05-027-RESTORATION OF EXISTING ROADWAY : 6.30 MILE SOUTH TOM GREEN CNTY LINE ; | Pavement Improvement | 06/22/2009 | 07/13/2009 | 10/01/2009 | 2253797.36 | 6.758
6263 | Texas | MENARD, EDWARDS |  | 23 | 2009472 | SPN:0235-02-043-CONSTRUCT BRIDGE AND APPROACHES : AT LITTLE HACKBERRY CREEK ; SPN:1296-01-016-CONSTRUCT BRIDGE AND APPROACHES : AT SAN SABA RIVER ; | Pavement Improvement | 06/18/2009 | 07/27/2009 | 09/01/2011 | 2489936.82 | 1.541
6264 | Texas | TRAVIS |  | 21 | 2009473 | SPN:1378-01-033-SEAL & THIN OVERLAY : LAGO VISTA CITY LIMITS ; | Pavement Improvement | 06/22/2009 | 07/08/2009 | 11/01/2009 | 3300717.11 | 7.962
6265 | Texas | TRAVIS |  | 10, 21 | 2009474 | SPN:3136-01-165-MILL, SEAL, & OVERLAY FRONTAGE ROADS : DUVAL ST ; | Pavement Improvement | 06/04/2009 | 08/25/2009 | 11/01/2009 | 2330028.81 | 9.857
6266 | Texas | WILLIAMSON |  | 31 | 2009475 | SPN:0204-01-060-FULL DEPTH REPAIR & OVERLAY : IH 35 NBFR ; | Pavement Improvement | 06/08/2009 | 06/24/2009 | 09/01/2009 | 1345917.68 | 1.704
6267 | Texas | HAYS |  | 25 | 2009478 | SPN:2293-01-021-SEAL & THIN OVERLAY : CENTERPOINT RD ; | Pavement Improvement | 06/12/2009 | 07/06/2009 | 08/01/2009 | 301864.1 | 2.197
6268 | Texas | LLANO |  | 11 | 2009479 | SPN:0700-04-037-MILL, SEAL & OVERLAY : SH 16 ; | Pavement Improvement | 06/09/2009 | 07/15/2009 | 08/01/2009 | 328245.14 | 1.815
6269 | Texas | KAUFMAN |  | 05 | 2009480 | SPN:0751-04-001-UPGRADE EXISTING COUNTY ROAD : FM 1392, 1.0 MI SW OF SH 205, SE ; | Pavement Improvement | 07/14/2009 |  | 06/01/2011 | 2705889.55 | 2.249
6270 | Texas | HAYS |  | 25 | 2009487 | SPN:0366-01-065-OVERLAY : EBONY STREET ; | Pavement Improvement | 06/29/2009 | 07/15/2009 | 07/01/2009 | 292810.93 | 1.172
6271 | Texas | BLANCO |  | 21 | 2009488 | SPN:0253-01-047-MILL, SEAL & THIN OVERLAY : S OF US 290 ; | Pavement Improvement | 06/16/2009 | 08/24/2009 | 08/01/2009 | 610452.84 | 2.377
6272 | Texas | JIM WELLS |  | 15 | 2009490 | SPN:0255-01-068-OVERLAY ROADWAY : FM 1352 ; | Pavement Improvement | 06/09/2009 | 07/20/2009 |  | 650000 | 2.154
6273 | Texas | KLEBERG, JIM WELLS |  | 15 | 2009491 | SPN:0383-03-022-REHAB. EXISTING ROADWAY : KLEBERG CO. LINE ; SPN:0383-04-054-REHAB. EXISTING ROADWAY : JIM WELLS CO. LINE ; | Pavement Improvement | 06/29/2009 | 08/20/2009 |  | 3060294.94 | 12.62
6274 | Texas | SAN PATRICIO |  | 15 | 2009492 | SPN:0371-07-006-MILL, SEAL AND OVERLAY : US 181 ; SPN:0372-03-006-MILL, SEAL AND OVERLAY : US 181 ; | Pavement Improvement | 06/22/2009 | 07/29/2009 |  | 820342.92 | 3.778
6275 | Texas | SAN PATRICIO |  | 15 | 2009493 | SPN:0507-01-017-REHAB AND WIDEN ROADWAY : IH 37 ; | Pavement Improvement | 06/16/2009 | 06/23/2009 | 10/01/2009 | 1288706.05 | 5.737
6276 | Texas | REFUGIO |  | 15 | 2009494 | SPN:0371-02-066-MILL AND OVERLAY__(NORTH BOUND LANES ONLY) : 6 MI N. OF REFUGIO ; SPN:0371-03-109-MILL AND OVERLAY_(NORTH BOUND LANES ONLY) : N. OF REFUGIO N. CITY LIMITS ; | Pavement Improvement | 06/29/2009 | 08/03/2009 |  | 2087652.55 | 8.515
6277 | Texas | SAN PATRICIO |  | 15 | 2009495 | SPN:0371-05-016-REHAB AND WIDEN ROADWAY : COUNTY ROAD 82D ; | Pavement Improvement | 06/16/2009 | 07/02/2009 |  | 812909.47 | 3.267
6278 | Texas | BEE |  | 15 | 2009496 | SPN:0100-07-045-UNDERSEAL AND OVERLAY : KARNES COUNTY LINE ; SPN:0100-08-086-UNDERSEAL AND OVERLAY : O.76 MI. S. OF FM 1465 ; | Pavement Improvement | 06/16/2009 | 08/12/2009 |  | 2643872.33 | 10.983
6279 | Texas | DUVAL |  | 25 | 2009497 | SPN:0086-10-043-REHABILITATION OF AN EXISTING ROADWAY : SOUTH END OF SAN DIEGO CREEK BRIDGE ; | Pavement Improvement | 06/16/2009 | 07/02/2009 | 09/01/2009 | 733053.88 | 0.792
6280 | Texas | VAL VERDE |  | 23 | 2009498 | SPN:0022-08-022-REHABILITATION OF AN EXISTING ROADWAY : 4.44 MI SOUTH OF SH 163 ; | Pavement Improvement | 06/08/2009 | 10/27/2009 | 11/01/2009 | 1863200.78 | 4.023
6281 | Texas | MAVERICK |  | 23 | 2009499 | SPN:0299-03-047-REHABILITATION OF AN EXISTING ROADWAY : 2.899 MI NORTH OF FM 1664 ; | Pavement Improvement | 06/22/2009 | 07/13/2009 | 12/01/2009 | 2829391.92 | 5.928
6282 | Texas | MAVERICK |  | 23 | 2009500 | SPN:2636-01-007-RESTORATION OF AN EXISTING HIGHWAY : DIMMIT COUNTY LINE ; | Pavement Improvement | 06/04/2009 | 07/06/2009 | 03/01/2010 | 2325707.47 | 12.303
6283 | Texas | HIDALGO |  | 15, 28 | 2009502 | SPN:0342-01-078-FULL DEPTH REPAIR BOTH LANES : FM 2128 ; | Pavement Improvement | 06/22/2009 | 07/13/2009 | 12/01/2009 | 2143338.79 | 3.7
6284 | Texas | STARR |  | 28 | 2009504 | SPN:0039-01-073-OVERLAY : FM 1430 ; SPN:0039-02-061-OVERLAY : FM 2221 ; SPN:0342-01-079-OVERLAY : FM 2128 ; SPN:0433-02-048-OVERLAY : KING ST ; SPN:0433-04-021-OVERLAY : BUSINESS 77 ; SPN:0517-07 | Pavement Improvement | 06/22/2009 | 07/15/2009 | 12/01/2009 | 6758353.23 | 34.57
6285 | Texas | KERR |  | 21 | 2009508 | SPN:0193-01-035-REPLACE BRIDGE AND APPROACHES : AT LYNX HAVEN CROSSING ; | New Bridge Construction | 06/09/2009 | 07/08/2009 | 03/01/2010 | 1048332.35 | 0.154
6286 | Texas | KERR |  | 21 | 2009509 | SPN:0829-04-029-REPLACE BRIDGE AND APPROACHES : AT MAYHUGH CROSSING ; | New Bridge Construction | 06/09/2009 | 08/14/2009 | 01/01/2010 | 518704.16 | 0.085
6287 | Texas | KERR |  | 21 | 2009510 | SPN:0855-05-009-REMOVE & REPLACE GUADALUPE RVR BRIDGE & RECONST APPROACHES : 0.1 MILE W. OF GUADALUPE RIVER ; | Pavement Improvement | 06/09/2009 | 07/27/2009 | 11/01/2009 | 827437.76 | 0.169
6288 | Texas | UVALDE |  | 23 | 2009511 | SPN:0369-03-027-REHAB EXISTING ROADWAY & ADD SHOULDERS : 0.2 MI SOUTH OF US 90 IN SABINAL ; | Pavement Improvement | 07/06/2009 | 07/29/2009 | 08/01/2010 | 3703743.51 | 11.42
6289 | Texas | MEDINA |  | 23 | 2009512 | SPN:0848-01-030-WIDEN NARROW ROADWAY & ADD SHOULDERS : FM 1250 ; | Pavement Improvement | 06/18/2009 | 07/20/2009 | 05/01/2010 | 1844944.89 | 4.716
6290 | Texas | TARRANT | DALLAS-FORT WORTH | 24 | 2009513 | SPN:0353-03-059-RECONSTRUCT FREEWAY, FRONTAGE ROADS AND RAMPS; SPN:0353-03-079-CONSTRUCT SEPARATE FREEWAY (MANAGED FACILITY); SPN:0364-01-113-RECONST FREEWAY 4 TO 6 LANES; | Pavement Widening | 10/26/2009 | 10/26/2009 | 03/01/2014 | 250000000 | 10.452
6291 | Texas | HARRIS | HOUSTON | 18 | 2009514 | SPN:0271-07-301-RECONSTRUCT ROADWAY : IH 45 NORTH ; SPN:0508-01-329-RECONSTRUCT ROADWAY : WHITE OAK BAYOU BRIDGE ; | Pavement Improvement | 10/16/2009 | 11/01/2009 |  | 18038764.02 | 2.346
6292 | Texas | MEDINA |  | 23 | 2009515 | SPN:0017-05-073-CONSTRUCT NB EXIT RAMP AT CR 770 : 0.2 MI S OF CR 770 ; SPN:0017-05-074-RELOCATE EXISTING NB ENTRANCE RAMP : ON NBFR FROM SH 173, N ; SPN:0017-05-088-CONSTRUCTION NEW SB FRONTAGE ROA | Pavement Widening | 06/09/2009 |  | 05/01/2010 | 2259919.03 | 2.022
6293 | Texas | COMAL |  | 21 | 2009516 | SPN:3106-01-012-WIDEN NARROW ROADWAY TO ADD SHOULDERS AND PASSING LANES : US 281 ; | Pavement Improvement | 06/08/2009 | 06/29/2009 | 11/01/2011 | 5146936.2 | 5.255
6294 | Texas | FRIO |  | 28 | 2009517 | SPN:0748-04-036-INSTALL CURB INLETS & STORM SEWER SYSTEM : TREVINO ST. ; | Pavement Improvement | 06/16/2009 | 07/20/2009 | 01/01/2010 | 656092.55 | 0.568
6295 | Texas | HARRIS |  | 18, 29 | 2009519 | SPN:0271-14-223-RECONSTRUCT ROADWAY : EAST OF ELLA ; | Pavement Improvement | 09/01/2009 | 09/16/2009 | 02/01/2012 | 28655986.56 | 2.91
6296 | Texas | GRAYSON | SHERMAN-DENISON | 04 | 2009520 | SPN:0666-01-022-WIDEN EXISTING HIGHWAY TO INCLUDE TURN LANES, TURN BAYS AND RAISED MEDIANS : 1,520` WEST OF US 75 C/L ; | Pavement Improvement | 08/26/2009 | 09/21/2009 | 11/01/2010 | 3000000 | 0.758
6297 | Texas | WHARTON |  | 14 | 2009521 | SPN:0027-04-039-SEAL COAT, ACP & SET : 3.3 MI E OF LISSIE ; | Pavement Improvement | 06/16/2009 | 07/20/2009 | 11/01/2009 | 3184624.51 | 7.157
6298 | Texas | AUSTIN |  | 10 | 2009522 | SPN:1258-01-021-GRADING, BASE, SURFACING : SH 36 ; | Pavement Improvement | 06/02/2009 | 06/22/2009 | 12/01/2009 | 2540876.78 | 3.755
6299 | Texas | COLORADO, DE WITT, VICTORIA |  | 14 | 2009523 | SPN:0088-06-003-ASPHALTIC CONCRETE PAVEMENT : GUADALUPE RIVER BRIDGE IN VICTORIA ; SPN:0270-01-047-ASPHALTIC CONCRETE PAVEMENT : SH 119 ; SPN:0270-02-038-ASPHALTIC CONCRETE PAVEMENT : FM 2980 ; SPN | Pavement Improvement | 06/16/2009 | 07/15/2009 | 09/01/2009 | 2844587.62 | 7.31
6300 | Texas | MATAGORDA |  | 14 | 2009524 | SPN:0847-01-013-REHABILITATE ROADWAY : FM 457 ; | Pavement Improvement | 06/23/2009 | 07/14/2009 | 11/01/2009 | 1856668.17 | 3.153
6301 | Texas | FAYETTE |  | 25 | 2009525 | SPN:0211-06-053-PAVEMENT REPAIR AND ACP SURFACING : ROITSCH STREET ; SPN:0268-01-052-PAVEMENT REPAIR AND ACP SURFACING : BS 71-E ; | Pavement Improvement | 06/22/2009 | 07/20/2009 | 08/01/2009 | 955283.03 | 1.672
6302 | Texas | HARDIN |  | 08 | 2009526 | SPN:0811-01-010-RESTORE EXISTING ROADWAY : US 69, EAST ; | Pavement Improvement | 06/12/2009 | 06/22/2009 | 09/01/2009 | 657757.84 | 3.807
6303 | Texas | JASPER |  | 08 | 2009527 | SPN:0784-03-014-PROVIDE ADDITIONAL PAVED SURFACE WIDTH : FM 105, SOUTH ; | Pavement Improvement | 06/22/2009 | 07/24/2009 | 11/01/2009 | 2569366.36 | 7.479
6304 | Texas | TYLER |  | 08 | 2009528 | SPN:0200-07-049-OVERLAY EXISTING ROADWAY : US 190 IN WOODVILLE, SOUTH ; SPN:0213-06-039-OVERLAY EXISTING ROADWAY : 3.9 MI W OF US 69 ; | Pavement Improvement | 06/02/2009 | 07/16/2009 | 09/01/2009 | 2393603.28 | 5.141
6305 | Texas | JEFFERSON |  | 02 | 2009529 | SPN:0508-04-154-OVERLAY EXISTING ROADWAY AND BASE REPAIRS : CHAMBERS COUNTY LINE ; | Pavement Improvement | 06/16/2009 | 07/22/2009 | 12/01/2009 | 4097310.61 | 18.993
6306 | Texas | CHAMBERS |  | 02 | 2009530 | SPN:0508-03-090-SPOT LEVEL UP & OVERLAY : 0.278 MI W OF FM 1406, EAST ; SPN:0739-01-044-SPOT LEVEL UP & OVERLAY : SH 73, EAST ; SPN:0762-02-044-OVERLAY EXISTING ROADWAY : US 90, SOUTH ; | Pavement Improvement | 06/02/2009 | 06/29/2009 | 09/01/2009 | 813243.57 | 3.718
6307 | Texas | HARDIN |  | 08 | 2009532 | SPN:0784-01-043-OVERLAY EXISTING ROADWAY : FM 92 IN SILSBEE, EAST ; | Pavement Improvement | 06/02/2009 | 06/22/2009 | 09/01/2009 | 383159.32 | 1.688
6308 | Texas | NEWTON |  | 08 | 2009533 | SPN:0304-08-012-UPGRADE BRIDGE RAIL : AT LITTLE COW CREEK ; SPN:0304-09-004-UPGRADE BRIDGE RAIL : AT TWO MILE BRANCH ; SPN:0627-02-017-UPGRADE BRIDGE RAIL : AT LITTLE COW CREEK, DRAW & WHITMAN ; SP | Safety/Traffic Management | 05/19/2009 | 07/07/2009 | 12/01/2010 | 1043652 | 2.402
6309 | Texas | ORANGE |  | 08 | 2009534 | SPN:0784-05-034-MILL & OVERLAY EXISTING ROADWAY, SEAL COAT : SH 12, EAST ; | Pavement Improvement | 06/03/2009 | 07/06/2009 | 09/01/2009 | 525420.19 | 1.657
6310 | Texas | BRAZOS |  | 17 | 2009535 | SPN:0116-04-096-OVERLAY CONSISTING OF A SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : FM 2818 ; SPN:0117-01-043-REHABILITATE EXISTING ROAD CONSISTING OF SPOT REPAIRS, SURFACE TREA | Pavement Improvement | 06/02/2009 | 07/17/2009 | 02/01/2010 | 672160.99 | 1.587
6311 | Texas | BRAZOS |  | 17 | 2009536 | SPN:0506-01-093-OVERLAY CONSISTING OF SPOT REPAIRS, SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : FM 2818 ; SPN:0506-01-094-OVERLAY CONSISTING OF A ONE COURSE SURFACE TREATMENT, H | Pavement Improvement | 05/19/2009 | 06/12/2009 | 01/01/2010 | 892019.28 | 2.462
6312 | Texas | BRAZOS |  | 17 | 2009537 | SPN:1316-01-053-OVERLAY CONSISTING OF A SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : 0.1 MILE EAST OF FM 158 ; | Pavement Improvement | 05/19/2009 | 06/03/2009 | 12/01/2009 | 298091.9 | 1
6313 | Texas | LEON |  | 06 | 2009538 | SPN:0675-03-068-OVERLAY CONSISTING OF CONCRETE PAVEMENT REPAIR, A ONE COURSE SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS : KEECHI CREEK ; | Pavement Improvement | 06/04/2009 | 08/17/2009 | 03/01/2010 | 6623247.22 | 7.269
6314 | Texas | HOWARD |  | 19 | 2009539 | SPN:0005-05-101-FLEXIBLE PAVEMENT REPAIR & ACP OVERLAY : MARTIN COUNTY LINE ; | Pavement Improvement | 05/28/2009 | 06/29/2009 | 12/01/2009 | 4997459.67 | 10.284
6315 | Texas | MORRIS |  | 04 | 2009540 | SPN:0222-03-056-WIDEN TO ADD SHOULDERS AND RESURFACE 4-LANE DIVIDED RURAL HIGHWAY : 0.7 MI. E. OF US 259 ; | Pavement Improvement | 05/28/2009 | 07/01/2009 | 10/01/2009 | 991156.2 | 2.021
6316 | Texas | BRAZORIA |  | 14 | 2009541 | SPN:0178-03-138-ONE-COURSE SURFACE TREATMENT, ASPHALT CONCRETE PAVEMENT OVERLAY, LOOP DETECTORS AND PAVEMENT MARKERINGS : SOUTH OF SH 35 BYPASS ; | Pavement Improvement | 06/08/2009 | 07/06/2009 | 11/01/2009 | 3249043.61 | 16.01
6317 | Texas | HARRIS |  | 22, 29 | 2009542 | SPN:0502-01-203-FULL DEPTH CONCRETE REPAIR AND REPAIR OF SPALLING IN CONCRETE PAVEMENT : SHELL OVERPASS ; | Pavement Improvement | 06/29/2009 | 07/30/2009 | 11/01/2009 | 882735.4 | 4.397
6318 | Texas | FORT BEND |  | 22 | 2009543 | SPN:3223-01-009-BASE REPAIR AND OVERLAY : US 90A ; | Pavement Improvement | 06/05/2009 | 06/23/2009 | 11/01/2009 | 207545.37 | 1.021
6319 | Texas | MONTGOMERY |  | 08 | 2009544 | SPN:0912-37-200-FAULT LINE BASE REPAIRS : VARIOUS LOCATIONS ON IH 45, LP 336 ; | Pavement Improvement | 06/02/2009 | 06/18/2009 | 11/01/2009 | 500000 | 0.001
6320 | Texas | FORT BEND |  | 22 | 2009545 | SPN:0188-01-036-REPLACE ASPHALT WITH CONCRETE : US 90A ; | Pavement Improvement | 06/05/2009 | 07/30/2009 | 11/01/2009 | 1269484.81 | 0.369
6321 | Texas | GALVESTON |  | 14 | 2009546 | "SPN:0389-11-057-BASE REPAIRS, MILLING & 1.5"" ASPHALT OVERLAY : FM 1765 ; " | Pavement Improvement | 06/05/2009 | 07/13/2009 | 11/01/2009 | 646223.04 | 1.77
6322 | Texas | BRAZORIA |  | 14 | 2009547 | SPN:1004-02-014-ASPHALT OVERLAY AND PAVEMENT MARKINGS : FM1301 ; SPN:1413-01-016-ASPHALT OVERLAY AND PAVEMENT MARKINGS : SH 35 ; | Pavement Improvement | 06/02/2009 | 07/21/2009 | 11/01/2009 | 1360458.79 | 11.799
6323 | Texas | FORT BEND |  | 14, 22 | 2009548 | SPN:0027-06-055-BASE REPAIR AND OVERLAY : WHARTON COUNTY LINE ; | Pavement Improvement | 06/04/2009 | 07/23/2009 | 11/01/2009 | 1118221.98 | 9.741
6324 | Texas | MONTGOMERY |  | 08 | 2009549 | SPN:0177-14-026-WIDEN SUBGRADE, OCST AND ACP OVERLAY : US 59 ; | Pavement Improvement | 06/02/2009 | 06/18/2009 | 07/01/2010 | 4317263.89 | 8.022
6325 | Texas | FORT BEND |  | 14 | 2009550 | SPN:1258-02-031-BASE REPAIR AND OVERLAY : FM 1489 ; | Pavement Improvement | 05/27/2009 | 06/17/2009 | 11/01/2009 | 821886.22 | 4.704
6326 | Texas | WALLER |  | 10 | 2009551 | SPN:0523-02-030-ADD SHOULDERS AND ACP OVERLAY : BU US 290 ; | Pavement Improvement | 06/02/2009 | 11/16/2009 | 12/01/2009 | 961664.41 | 0.971
6327 | Texas | HARRIS |  | 10 | 2009552 | SPN:3050-03-016-GRADING, LIME TREATED SUBGRADE, CEMENT TREATED BASE, ASPHALTIC OVERLAY AND PAVMENT MARKINGS : 0.140 MI N. OF HUFSMITH KUYKENDAHL ; | Pavement Improvement | 06/12/2009 | 06/28/2009 | 11/01/2009 | 366817.39 | 0.369
6328 | Texas | HARRIS |  | 07 | 2009553 | SPN:0050-08-088-CRACK & SPALL REPAIR, FULL DEPTH CONCRETE REPAIR (IN SECTIONS) : SH 6 ; | Pavement Improvement | 06/04/2009 | 06/24/2009 | 11/01/2009 | 118220 | 3.845
6329 | Texas | HARRIS |  | 07, 09 | 2009554 | "SPN:1258-04-058-2"" PLANING, 2"" ACP OVERLAY, PAVEMENT MARKINGS : DAIRY ASHFORD ; " | Pavement Improvement | 06/05/2009 | 08/17/2009 | 11/01/2009 | 4459705.68 | 8.923
6330 | Texas | WALLER |  | 10 | 2009555 | SPN:0527-02-015-SUBGRADE WIDENING, SEAL COAT, ACP O/L AND PAVEMENT MARKINGS : FM 359 ; | Pavement Improvement | 06/08/2009 | 09/01/2009 | 11/01/2009 | 2009247.78 | 7.292
6331 | Texas | GALVESTON |  | 14 | 2009556 | SPN:0367-02-073-RAISE, REHABILITATE AND OVERLAY (TO 5 YR. STORM ELEVATION) : INTERSECTION AT SH 124 ; SPN:0367-03-035-REHABILITATE AND OVERLAY (TO 5 YR. STORM ELEVATION) : CRYSTAL BEACH ; SPN:0367-0 | Pavement Improvement | 06/02/2009 | 06/18/2009 | 12/01/2009 | 6167954.73 | 21.338
6332 | Texas | HARRIS |  | 02 | 2009557 | SPN:0028-02-087-MILL, SEAL COAT, BASE REPAIR AND ACP OVERLAY : W OF KRENEK ; | Pavement Improvement | 06/08/2009 | 07/06/2009 | 11/01/2009 | 1241291.35 | 2.072
6333 | Texas | FORT BEND |  | 22 | 2009558 | SPN:0111-03-054-BASE REPAIR AND OVERLAY : SH 6 ; | Pavement Improvement | 06/05/2009 | 07/08/2009 | 11/01/2009 | 653888.42 | 4.807
6334 | Texas | WALLER |  | 10 | 2009559 | "SPN:0523-02-041-SEAL COAT AND 1.5"" OVERLAY, PAVEMENT MARKINGS : 0.5 MI N. OF CLAPP RD ; " | Pavement Improvement | 06/04/2009 | 06/22/2009 | 11/01/2009 | 654828.08 | 3.492
6335 | Texas | NACOGDOCHES |  | 01 | 2009560 | SPN:0138-06-039-RESURFACE WITH POROUS FRICTION COURSE : RUSK COUNTY LINE ; | Pavement Improvement | 06/02/2009 | 07/21/2009 | 09/01/2009 | 3300000 | 6.327
6336 | Texas | BURLESON |  | 17 | 2009561 | SPN:0648-03-046-WIDEN TO 4 LANE DIVIDED HIGHWAY : FM 50 ; | Pavement Widening | 06/16/2009 | 06/27/2009 | 01/01/2011 | 7505830.38 | 2.752
6337 | Texas | SHELBY |  | 01 | 2009562 | SPN:0743-02-022-RECONSTRUCT AND WIDEN EXISTING PAVEMENT : NACOGDOCHES CO LINE ; | Pavement Improvement | 06/18/2009 | 07/27/2009 | 06/01/2010 | 1199983.65 | 5.457
6338 | Texas | SHELBY |  | 01 | 2009563 | SPN:0175-02-080-REHAB EXISTING PAVEMENT : TENAHA CITY LIMITS ; | Pavement Improvement | 06/12/2009 | 08/25/2009 | 08/01/2010 | 4664748.68 | 9.375
6339 | Texas | HOUSTON |  | 06 | 2009564 | SPN:0937-03-015-RECONSTRUCT AND WIDEN EXISTING PAVEMENT : SH 21 ; | Pavement Improvement | 06/17/2009 | 06/26/2009 | 08/01/2010 | 2691341.91 | 11.173
6340 | Texas | MORRIS, TITUS |  | 04 | 2009565 | SPN:0222-01-046-OVERLAY 4-LANE RURAL HIGHWAY WITH ASPHALTIC CONCRETE : 1.6 MI WEST OF FM 2348 ; SPN:0222-02-051-OVERLAY 4-LANE RURAL HIGHWAY WITH ASPHALTIC CONCRETE : TITUS COUNTY LINE ; | Pavement Improvement | 07/09/2009 | 07/22/2009 | 11/01/2009 | 4699268.05 | 7.4
6341 | Texas | PANOLA |  | 01 | 2009566 | SPN:0247-02-043-WIDEN TO ADD SHOULDERS AND RESURFACE 4-LANE RURAL HIGHWAY : 0.1 MI. S. OF MILL CREEK ; | Pavement Improvement | 06/12/2009 | 06/30/2009 | 10/01/2009 | 2384758.4 | 3.187
6342 | Texas | CASS |  | 01, 04 | 2009568 | SPN:0569-01-048-WIDEN TO ADD SHOULDERS AND RESURFACE 2-LANE RURAL HIGHWAY : SOUTH OF FM 2328 ; | Pavement Improvement | 06/05/2009 | 07/24/2009 | 06/01/2010 | 886614.14 | 3.024
6343 | Texas | CASS |  | 04 | 2009569 | SPN:0277-03-024-WIDEN TO ADD SHOULDERS AND RESURFACE 2-LANE RURAL HIGHWAY : SH 8 IN DOUGLASSVILLE ; SPN:0277-03-025-WIDEN TO ADD SHOULDERS AND RESURFACE 2-LANE RURAL HIGHWAY : FM 96 ; | Pavement Improvement | 05/22/2009 | 06/15/2009 | 07/01/2010 | 2023245.06 | 11.305
6344 | Texas | BROWN |  | 11 | 2009570 | SPN:0054-06-090-MILL AND OVERLAY : 0.5 MI. W OF FM 3254 ; | Pavement Improvement | 06/05/2009 | 08/05/2009 | 10/01/2009 | 1562249.76 | 3.055
6345 | Texas | NAVARRO |  | 24 | 2009571 | SPN:0997-01-038-OV-ASPHALTIC CONCRETE PAVEMENT, OVERLAY, RESTORE PAVEMENT STRUCTURE AND UPGRADE DRAINAGE : FM 744 ; SPN:1289-01-028-OV-ASPHALTIC CONCRETE PAVEMENT, OVERLAY, RESTORE PAVEMENT STRUCTURE | Pavement Improvement | 06/22/2009 | 07/08/2009 | 12/01/2010 | 7287236.14 | 14.329
6346 | Texas | LEON |  | 06 | 2009572 | SPN:0426-03-037-RESTORE EXISTING ROAD CONSISTING OF GRADING, FLEXIBLE BASE, SURFACE AND PAVEMENT MARKINGS AND MARKERS : 2.5 MILES NORTH OF SH 7 ; | Pavement Improvement | 07/06/2009 | 08/17/2009 | 04/01/2010 | 422835.98 | 2.534
6347 | Texas | HOPKINS |  | 04 | 2009575 | SPN:0083-02-046-REHAB WITH SHOULDERS : 0.47 MI EAST OF FM 2653 S ; | Pavement Improvement | 08/21/2009 | 08/31/2009 | 06/01/2011 | 4160215 | 3.447
6348 | Texas | GRAYSON |  | 04 | 2009576 | SPN:0510-01-022-REHABILITATE EXISTING ROADWAY : SH 289 ; | Pavement Improvement | 05/28/2009 | 06/30/2009 | 06/01/2010 | 1876832.4 | 5.895
6349 | Texas | LAMAR |  | 04 | 2009577 | SPN:0680-01-012-REHAB EXIST ROAD : 3.38 MILES N OF FM 1497 ; | Pavement Improvement | 05/28/2009 | 05/28/2009 | 05/01/2010 | 896178.3 | 3.38
6350 | Texas | GRAYSON |  | 04 | 2009578 | SPN:0729-01-034-REHABILITATE EXISTING ROADWAY : US 377 ; | Pavement Improvement | 06/02/2009 | 06/16/2009 | 11/01/2010 | 3701118.28 | 11.354
6351 | Texas | LAMAR |  | 04 | 2009579 | SPN:1320-01-021-REHAB EXIST ROAD : FM 1497 NORTH ; | Pavement Improvement | 06/02/2009 | 06/04/2009 | 09/01/2011 | 2447477.14 | 10.32
6352 | Texas | GREGG |  | 01 | 2009580 | SPN:0096-06-071-PLANE & RESURFACE ROADWAY : SP 63/SH 31 IN LONGVIEW, E ; | Pavement Improvement | 06/05/2009 | 06/22/2009 | 11/01/2009 | 1766928.52 | 2.874
6353 | Texas | ANDERSON |  | 05 | 2009581 | SPN:0123-01-034-ADD SHOULDERS & RESURFACE ROADWAY : 3 MI E OF FM 3266, E OF P`STINE, E ; | Pavement Improvement | 06/02/2009 | 06/26/2009 | 11/01/2010 | 4110707.46 | 5.602
6354 | Texas | WOOD |  | 05 | 2009582 | SPN:0190-03-076-PLANE & RESURFACE ROADWAY : FM 564(N) IN MINEOLA, S ; SPN:0190-03-077-PLANE & RESURFACE ROADWAY : US 69/SH 37 SPLIT IN MINEOLA, S ; | Pavement Improvement | 05/22/2009 | 06/17/2009 | 11/01/2009 | 1795187.97 | 2.377
6355 | Texas | SMITH |  | 01 | 2009583 | SPN:0190-05-058-RESURFACE ROADWAY : 0.134 MI N OF IH 20 IN LINDALE, S ; | Pavement Improvement | 06/02/2009 | 07/20/2009 | 11/01/2009 | 2499423.32 | 7.045
6356 | Texas | GREGG |  | 01 | 2009584 | SPN:0393-01-088-PLANE & RESURFACE ROADWAY : IH 20 N FRONTAGE RD, N ; | Pavement Improvement | 05/19/2009 | 06/16/2009 | 10/01/2009 | 2312517.53 | 3.62
6357 | Texas | VAN ZANDT |  | 05 | 2009586 | SPN:0522-02-028-CONCRETE SURFACE REPAIR OF BRIDGE STRUCTURES : AT CANEY CRK, CANEY CREEK RELIEF ; | Pavement Improvement | 06/16/2009 | 07/06/2009 | 10/01/2009 | 61344 | 0.133
6358 | Texas | BELL |  | 31 | 2009588 | SPN:0015-05-043-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : FM 93 (6TH AVE) IN BELTON, SOUTH ; SPN:0398-04-067-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : 13TH ST IN BELTON, SOUTH ; | Pavement Improvement | 06/04/2009 | 06/22/2009 | 09/01/2009 | 1287407.66 | 1.607
6359 | Texas | CORYELL |  | 31 | 2009589 | SPN:0055-03-023-REHABILITATE ROADWAY, ADD PASSING LANES AND SHOULDERS : FM 932 ; | Pavement Improvement | 06/18/2009 | 06/24/2009 | 06/01/2011 | 8735023.01 | 10.235
6360 | Texas | CORYELL |  | 31 | 2009590 | SPN:0231-02-050-CONSTRUCT OVERPASS FOR FT HOOD ACCESS : @ RAILHEAD RD ; | New Bridge Construction | 08/10/2009 | 08/24/2009 | 04/01/2010 | 2368151.52 | 2.642
6361 | Texas | BELL |  | 31 | 2009591 | SPN:3534-02-002-ADD TURN LANES, TRAFFIC SIGNAL AND LIGHTING FOR IMPROVED ACCESS TO WEST FT HOOD : @ MOHAWK DRIVE IN KILLEEN ; | Pavement Improvement | 06/09/2009 | 06/23/2009 | 04/01/2010 | 1220438.55 | 0.8
6362 | Texas | WILBARGER |  | 13 | 2009592 | SPN:0043-07-104-SEAL COAT AND HMAC OVERLAY : NEAR US 70 IN OKLAUNION ; | Pavement Improvement | 06/09/2009 | 08/19/2009 | 12/01/2009 | 2590420.9 | 7.273
6363 | Texas | ARCHER |  | 19 | 2009593 | SPN:0137-05-028-EXTEND CULVERTS AND ADD SHOULDERS : FM 368 ; | Pavement Improvement | 06/09/2009 | 08/12/2009 | 10/01/2010 | 3147193.46 | 9.364
6364 | Texas | COOKE |  | 26 | 2009594 | SPN:0194-02-088-HEAVY HOT MIX OVERLAY : NEAR RED RIVER ; | Pavement Improvement | 06/05/2009 | 08/12/2009 | 11/01/2009 | 2396645.99 | 5.765
6365 | Texas | COOKE |  | 13, 26 | 2009595 | SPN:1855-01-021-ADD SHOULDERS : FM 372 ; | Pavement Improvement | 06/22/2009 | 07/14/2009 | 12/01/2010 | 2108363.87 | 8.579
6366 | Texas | RUSK |  | 01 | 2009596 | SPN:0138-02-034-PLANE & RESURFACE ROADWAY : US/BU 259 SPLIT, S OF KILGORE, S ; | Pavement Improvement | 05/22/2009 | 06/10/2009 | 11/01/2009 | 2886918.15 | 5.1
6367 | Texas | TRAVIS |  | 21, 25 | 2009597 | SPN:3136-01-162-MILL, SEAL & THIN OVERLAY : COLORADO RIVER ; | Pavement Improvement | 06/12/2009 | 07/28/2009 | 10/01/2009 | 1696542.45 | 2.818
6368 | Texas | TRAVIS |  | 25 | 2009598 | SPN:3136-01-166-MILL, SEAL, AND OVERLAY : GAINES CREEK ; | Pavement Improvement | 06/16/2009 | 07/06/2009 | 10/01/2009 | 1054970.05 | 2
6369 | Texas | DENTON |  | 24 | 2009599 | SPN:0918-46-217-REPLACE BRIDGE AND APPROACHES : ON FREEMAN RD ; | Pavement Improvement | 07/02/2009 | 08/26/2009 | 05/01/2010 | 203297 | 0.001
6370 | Texas | DALLAS | DALLAS-FORT WORTH | 24, 30 | 2009600 | SPN:1047-02-044-INTERSECTION APPROACH WIDENING, SIGNAL UPGRADES AND TURN LANES AT STRAUS ROAD : AT STRAUS RD ; SPN:1047-03-062-INTERSECTION APPROACH WIDENING, SIGNAL UPGRADES AND TURN LANES AT STRAUS | Pavement Improvement | 05/28/2009 | 06/22/2009 | 10/01/2009 | 1388408.1 | 0.167
6371 | Texas | KAUFMAN |  | 24 | 2009601 | SPN:1091-01-016-REPLACE BRIDGE AND APPROACHES : BUFFALO CREEK ; SPN:1091-01-018-REPLACE BRIDGE AND APPROACHES : BUFFALO CREEK RELIEF ; | Pavement Improvement | 09/28/2009 |  | 11/01/2010 | 2856520.65 | 0.323
6372 | Texas | KAUFMAN |  | 24 | 2009602 | SPN:1397-01-021-REPLACE BRIDGE AND APPROACHES : AT BIG COTTONWOOD CREEK ; SPN:1397-01-022-REPLACE BRIDGE AND APPROACHES : AT LITTLE COTTONWOOD CREEK ; | Pavement Improvement | 06/29/2009 | 09/11/2009 | 06/01/2010 | 1708659.34 | 0.402
6373 | Texas | PARKER |  | 12 | 2009603 | SPN:0008-03-096-2 INCH OVERLAY : SPUR 312 ; | Pavement Improvement | 06/05/2009 | 08/03/2009 | 11/01/2009 | 3460812.46 | 7.517
6374 | Texas | TARRANT |  | 12 | 2009604 | "SPN:0008-14-110-PAVEMENT AND BRIDGE JOINT REPAIR WITH 2"" HMAC OVERLAY : MARINE CREEK PARKWAY ; " | Pavement Improvement | 05/22/2009 | 06/15/2009 | 12/01/2009 | 3967559.84 | 4.983
6375 | Texas | WISE |  | 12 | 2009605 | SPN:0013-08-117-PLANE AND TEXTURIZE CRCP NORTHBOUND LANES : 1355` S OF CR 4840 ; SPN:0013-08-118-PLANE AND TEXTURIZE CRCP NORTHBOUND : NBL 1300` S OF CR 4421 ; SPN:0013-08-120-MILL ASPHALT, CONCRETE | Pavement Improvement | 06/12/2009 | 07/06/2009 | 11/01/2009 | 1846266.94 | 9.526
6376 | Texas | ERATH, HOOD, JOHNSON |  | 17 | 2009606 | "SPN:0080-03-050-MILL 2"" AND HMAC OVERLAY : BRAZOS RIVER BRIDGE ; SPN:0080-05-027-MILL 2"" AND HMAC OVERLAY : PARKER COUNTY LINE ; SPN:0250-07-014-MILL AND HMAC OVERLAY : BU 377J ; SPN:0365-02-028 | Pavement Improvement | 06/09/2009 | 07/27/2009 | 10/01/2009 | 1789000 | 7.483
6377 | Texas | JOHNSON |  | 17 | 2009607 | SPN:0259-04-036-PAVEMENT REPAIR AND OVERLAY : APPROX. 120 FT WEST OF FM 2331 ; SPN:0422-03-070-PAVEMENT REPAIR AND HOTMIX OVERLAY : PR 21 ; | Pavement Improvement | 05/22/2009 | 06/15/2009 | 10/01/2009 | 662994.26 | 2.314
6378 | Texas | WISE |  | 12 | 2009608 | SPN:0352-01-054-MILL AND HMAC OVERLAY : 0.33 MILE SOUTH OF US 380 INTERSECT ; | Pavement Improvement | 06/16/2009 | 08/17/2009 | 10/01/2009 | 553102.84 | 1.208
6379 | Texas | TARRANT |  | 26 | 2009609 | "SPN:0363-01-133-PAVEMENT REPAIR, 2"" MILLING, AND 2"" HMAC OVERLAY WITH PAVEMENT MARKINGS : NEAR FM 1938 ; " | Pavement Improvement | 06/02/2009 | 07/01/2009 | 11/01/2009 | 740758 | 3.22
6380 | Texas | PARKER |  | 12 | 2009610 | SPN:0365-01-042-MILL 1.5 INCH, FABRIC, HMAC OVERLAY AND TRAFFIC SIGNAL LOOPS : US 180 ; | Pavement Improvement | 06/04/2009 | 06/15/2009 | 09/01/2009 | 682212.31 | 1.2
6381 | Texas | JOHNSON |  | 17 | 2009611 | SPN:0019-01-135-HMAC OVERLAY : WILLINGHAM STREET ; SPN:0019-02-030-HMAC OVERLAY : AT&SF RAILROAD ; SPN:0519-01-026-HMAC OVERLAY : NORTH OF RIO VISTA ; | Pavement Improvement | 06/09/2009 | 07/28/2009 | 11/01/2009 | 1833526.78 | 8.631
6382 | Texas | TARRANT |  | 06 | 2009613 | SPN:0747-03-076-REPAIR FAILURES AND OVERLAY WITH 2 INCHES : COPELAND ROAD ; | Pavement Improvement | 06/05/2009 | 07/01/2009 | 09/01/2009 | 662733.1 | 1.393
6383 | Texas | TARRANT |  | 12, 24, 26 | 2009614 | SPN:0902-48-745-VARIOUS LOCATIONS FOR EXPANSION JOINT REPAIRS IN NORTH TARRANT COUNTY : VARIOUS LOCATIONS ; | Pavement Improvement | 06/05/2009 | 06/28/2009 | 02/01/2010 | 1065751 | 0.1
6384 | Texas | PARKER |  | 12 | 2009615 | SPN:3516-01-014-REHAB EXISTING ROADWAY WITH PAVEMENT REPAIRS AND OVERLAY : FM 1886 ; | Pavement Improvement | 10/30/2009 |  |  | 587643.05 | 3.143
6385 | Texas | CHAMBERS |  | 14 | 2009622 | SPN:0242-03-068-OVERLAY EXISTING ROADWAY & SEAL COAT : LIBERTY CO/L, SOUTH ; | Pavement Improvement | 05/28/2009 | 06/23/2009 | 09/01/2009 | 814457.27 | 4.39
6386 | Texas | GUADALUPE |  | 28 | 2009624 | SPN:0535-01-065-RESTORE EXISTING ROADWAY WITH CRCP : 0.44 MI W OF SH 46 ; | Pavement Improvement | 09/18/2009 | 10/04/2009 | 09/01/2011 | 1784603.23 | 0.55
6387 | Texas | MATAGORDA |  | 14 | 2009625 | SPN:0179-04-089-ASPHALTIC CONCRETE PAVEMENT : SOUTH OF FM 457 ; | Pavement Improvement | 06/04/2009 | 07/10/2009 | 08/01/2009 | 567067.43 | 1.895
6388 | Texas | WHARTON |  | 14 | 2009626 | SPN:2819-02-009-PAVEMENT REPAIR AND ACP SURFACING : 0.14 MI. SOUTHWEST OF SH 71 ; | Pavement Improvement | 06/12/2009 | 07/06/2009 | 09/01/2009 | 789228.78 | 2.402
6389 | Texas | ELLIS |  | 06 | 2009627 | SPN:0092-10-007-REHABILITATE EXISTING ROADWAY : DALLAS COUNTY LINE ; | Pavement Improvement | 08/07/2009 | 08/28/2009 | 10/01/2010 | 1284123.14 | 2.285
6390 | Texas | MASON |  | 11 | 2009632 | SPN:0149-04-015-SEAL COAT : US 87 ; SPN:0396-02-024-SEAL COAT : MENARD C/L ; | Pavement Improvement | 07/02/2009 | 06/22/2009 | 09/01/2009 | 1045214.63 | 27.578
6391 | Texas | WISE |  | 12 | 2009633 | SPN:0013-08-114-3 INCH OVERLAY AND CONCRETE TEXTURE SOUTHBOUND LANES : SBL FROM 475` S OF US 380 ; | Pavement Improvement | 06/16/2009 | 08/24/2009 | 10/01/2009 | 1309578.7 | 12.75
6392 | Texas | BURNET |  | 11 | 2009634 | SPN:2206-01-013-OVERLAY : 11.7 MI N OF SH 29 ; | Pavement Improvement | 06/22/2009 | 06/29/2009 | 10/01/2009 | 1444444 | 9.444
6393 | Texas | CALDWELL |  | 25 | 2009635 | SPN:0286-02-028-PAVEMENT REPAIR,MILL,SEAL & OVERLAY : 0.35 MILES WEST OF HAYS C/L ; | Pavement Improvement | 07/06/2009 | 08/10/2009 | 10/01/2009 | 3794304.93 | 11.695
6394 | Texas | WISE |  | 12 | 2009636 | SPN:0013-08-116-MILL ASPHALT, CONCRETE REPAIRS, OVERLAY 2 INCHES : 2750` N OF PIONEER ROAD ; | Pavement Improvement | 06/16/2009 | 08/24/2009 | 10/01/2009 | 732136.28 | 3.289
6395 | Texas | ATASCOSA |  | 28 | 2009638 | SPN:0517-01-040-WIDEN EXISTING ROADWAY TO PROVIDE PASSING LANES : 0.3 S OF FM 1332 ; | Pavement Improvement | 10/13/2009 | 10/26/2009 |  | 1849585.53 | 17.779
6396 | Texas | HENDERSON |  | 05 | 2009639 | SPN:0163-04-053-PLANE & RESURFACE ROADWAY : 1.2 MI E OF SH 198 IN MALAKOFF, E ; | Pavement Improvement | 06/02/2009 | 06/25/2009 | 10/01/2009 | 2119884.1 | 4.944
6397 | Texas | LEE |  | 10 | 2009640 | SPN:3114-01-010-LEVEL-UP & SEAL COAT : US 290 ; | Pavement Improvement | 06/22/2009 | 07/27/2009 | 09/01/2009 | 570362.56 | 13.155
6398 | Texas | LIVE OAK |  | 15 | 2009646 | SPN:0542-06-041-CONSTRUCT FOUR LANE BOULEVARD : US 281 ; SPN:0542-07-008-CONSTRUCT 4 LANE BOULEVARD : BU 59 INTERSECTION ; SPN:0542-07-012-CONSTRUCT RAILROAD GRADE SEPARATION STRUCTURE AND APPROACHE | Pavement Widening | 10/21/2009 |  |  | 17155044.24 | 3.953
6399 | Texas | JIM WELLS |  | 15 | 2009647 | SPN:0255-01-074-CONSTRUCT DIAMOND INTERCHANGE : 0.95 MI. N. OF FM 2508 ; | Pavement Widening | 09/14/2009 | 11/16/2009 | 12/01/2011 | 13000000 | 1.84
6400 | Texas | WICHITA |  | 13 | 2009648 | "SPN:0156-14-027-""ULTRA THIN BONDED HOT MIX WEARING COURSE (UTBHMWC)"" : LP 11 ; " | Pavement Improvement | 08/04/2009 | 08/26/2009 | 10/01/2009 | 788364.75 | 1.706
6401 | Texas | HAYS |  | 25 | 2009650 | SPN:0016-02-104-REPLACE BRIDGE AND APPROACHES & WIDEN FRONTAGE ROADS : 2250 FT N OF MAIN ST ; | Pavement Improvement | 10/09/2009 | 11/02/2009 |  | 7000000 | 0.777
6402 | Texas | WEBB |  | 28 | 2009651 | SPN:0086-16-002-FOR THE CONSTRUCTION OF A NEW LOCATION 4 LANE DIVIDED ROADWAY : 4.8 MILES SOUTH OF SH 359 ; SPN:0086-16-003-FOR THE CONSTRUCTION OF A NEW LOCATION 4 LANE DIVIDED ROADWAY : 1.0 MILES SO | New Construction | 10/16/2009 |  |  | 21758949 | 4.701
6403 | Texas | WEBB |  | 28 | 2009652 | SPN:0086-16-001-FOR THE CONSTRUCTION OF A NEW LOCATION 2 LANE ROADWAY : MANGANA-HEIN ROAD ; | New Construction | 10/16/2009 |  |  | 9660310.81 | 2.267
6404 | Texas | BRAZOS |  | 17 | 2009657 | SPN:0050-02-082-CONSTRUCT NEW INTERCHANGE CONSISTING OF GRADING, STRUCTURES, BASE AND SURFACE - FUNDING CSJ FOR 0050-02-094 : AT BARRON ROAD ; | Pavement Improvement | 06/29/2009 | 07/17/2009 | 03/01/2011 | 7504904.44 | 1.676
6405 | Texas | HARRIS |  | 02, 18, 29 | 2009658 | SPN:3256-02-074-CONSTRUCT 4 DIRECT CONNECTORS : AT US 59 NORTH ; | New Bridge Construction | 10/06/2009 | 10/15/2009 |  | 29595089.52 | 1.624
6406 | Texas | BROOKS |  | 15 | 2009663 | SPN:0255-03-026-CONSTRUCT 4 LANE EXPRESSWAY_WITH TOLLED MAIN LANES : BUS 281 NORTH SIDE ; SPN:0255-04-072-CONSTRUCT 4 LANE EXPRESSWAY_WITH TOLLED MAIN LANES : 0.9 MILES SOUTH OF FM 3066 ; | Pavement Widening | 07/14/2009 | 08/18/2009 | 08/01/2012 | 40039527.42 | 5.581
6407 | Texas | BROOKS |  | 15 | 2009664 | SPN:0255-14-001-CONSTRUCT 4 LANE EXPRESSWAY WITH TOLLED MAIN LANES : BUS 281 NORTH SIDE ; | Pavement Widening | 07/14/2009 | 08/18/2009 | 08/01/2012 | 25860723.89 | 2.062
6408 | Texas | RUNNELS, TOM GREEN, COLEMAN |  | 11 | 2009665 | SPN:7107-09-001-REHABILITATION OF SOUTH ORIENT RR; SPN:7107-10-001-REHABILITATION OF SOUTH ORIENT RR; SPN:7123-11-001-REHABILITATION OF SOUTH ORIENT RR; | Other | 09/01/2009 | 09/15/2009 | 12/01/2010 | 5078194.05 | 0.003
6409 | Texas | SMITH |  | 01 | 2009679 | SPN:3487-01-013-INSTALL ELECTRONIC TOLL GANTRIES AND EQUIPMENT FOR NEW 2-LN TOLL ROAD (ULTIMATE 4-LANE FACILITY) : SH 31,2.0 MI E OF FM 2661,S & SE ; SPN:3487-02-010-INSTALL ELECTRONIC TOLL GANTRIES A | Other | 07/21/2009 | 08/06/2009 | 08/01/2013 | 3876000 | 9.019
6410 | Texas | CAMERON |  | 27 | 2009682 | SPN:1425-04-020-WIDEN TO 4 LANE DIVIDED : 1.06 MILES S. OF US 77/83 ; | Pavement Widening | 08/10/2009 |  | 06/01/2010 | 1887239.52 | 0.8
6411 | Texas | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2009689 | "SPN:0921-02-132-WIDEN TO 4 LANES : ON ""I"" ROAD FROM US 281 SOUTH ; " | Pavement Widening | 09/17/2009 | 10/13/2009 | 03/01/2011 | 4071711.18 | 1.761
6412 | Texas | SHELBY |  | 01 | 2009696 | SPN:0064-01-064-RESURFACE WITH HOT MIX ASPHALT : JACKSON STREET ; SPN:0109-11-003-RESURFACE WITH HOT MIX ASPHALT : US 287 (N) ; SPN:0118-09-008-RESURFACE WITH HOT MIX ASPHALT : SH 21 ; SPN:0176-06- | Pavement Improvement | 07/28/2009 | 10/06/2009 | 09/04/2009 | 1612585.31 | 6.619
6413 | Texas | BRAZORIA | HOUSTON | 14 | 2009697 | SPN:2523-02-030-WIDEN TO 4 LANE DIVIDED SUBURBAN SECTION : SH 288 ; SPN:2523-02-058-CONSTRUCT RAILROAD-HIGHWAY GRADE SEPARATION : AT CR 288 AND UPRR ; | Pavement Widening | 09/01/2009 | 10/15/2009 | 10/01/2010 | 18452982.51 | 3.092
6414 | Texas | HARRIS | HOUSTON | 09 | 2009699 | SPN:0598-01-089-FRONTAGE ROAD INTERSECTION IMPROVEMENTS (TSM) : AT BW 8 ; | Pavement Improvement | 10/06/2009 | 10/27/2009 |  | 635655.19 | 0.603
6415 | Texas | WALLER | HOUSTON | 10 | 2009700 | SPN:0523-01-015-WIDEN TO 4-LANE DIVIDED URBAN SECTION : BU 290 ; | Pavement Widening | 09/09/2009 | 10/19/2009 | 10/01/2010 | 2485857.89 | 0.551
6416 | Texas | STARR |  | 28 | 2009711 | SPN:1103-04-025-REHABILITATION OF PAVEMENT, ADD CURB & GUTTER, STORM SEWER AND RESTRIPE TO ONE WAY PAIR : US 83 NORTH ; | Pavement Improvement | 08/10/2009 | 10/20/2009 | 02/01/2011 | 2521180.59 | 0.921
6417 | Texas | CAMERON |  | 27 | 2009712 | SPN:1425-03-053-OVERLAY : US 77 ; | Pavement Improvement | 08/19/2009 | 09/21/2009 | 09/01/2009 | 1671691.1 | 3.463
6418 | Texas | POTTER |  | 13 | 2009713 | SPN:0904-02-033-OVERLAY : ON HASTINGS AVE, FROM RIVER ROAD ; | Pavement Improvement | 10/22/2009 |  |  | 231677.92 | 1
6419 | Texas | RANDALL |  | 13 | 2009715 | SPN:0904-11-046-OVERLAY : ON S GEORGIA ST, FR .3 MI N OF FARM ; | Pavement Improvement | 11/02/2009 |  |  | 155676.82 | 1
6420 | Texas | ELLIS |  | 06 | 2009801 | SPN:0092-08-015-REHABILITATE EXISTING ROADWAY : SOUTH OF SH 34 IN ENNIS ; | Pavement Improvement | 08/26/2009 | 09/15/2009 | 08/01/2010 | 1950526.15 | 2.26
6421 | Texas | CALLAHAN |  | 19 | 2009804 | SPN:0181-03-024-PLANNING, UNDERSEAL, ASPHALT CONCRETE PAVEMENT OVERLAY, AND METAL BEAM GUARD FENCE : US 283 ; SPN:0452-02-034-PLANNING, UNDERSEAL, ASPHALT CONCRETE PAVEMENT OVERLAY, AND METAL BEAM GUA | Pavement Improvement | 08/06/2009 | 08/10/2009 | 02/01/2010 | 4960299.07 | 18.082
6422 | Texas | SAN PATRICIO |  | 15 | 2009805 | SPN:0372-01-093-OVERLAY ROADWAY : ODEM N. CITY LIMITS ; | Pavement Improvement | 09/09/2009 | 09/25/2009 | 02/01/2009 | 2015197.58 | 4.182
6423 | Texas | WILLIAMSON |  | 31 | 2009866 | SPN:2211-02-021-RECONST TO 4-LANE DIVIDED RDWY : CHANDLER RD ; | Pavement Widening | 10/30/2009 |  |  | 9229357.32 | 2.356
6424 | Texas | DALLAS |  | 03, 05 | 2009874 | SPN:0009-02-058-ACP OVERLAY,CONCRETE FULL DEPTH REPAIR AND PAVEMENT MARKINGS : IH 635 ; | Pavement Improvement | 09/09/2009 | 10/19/2009 | 01/01/2010 | 1568590.18 | 3.256
6425 | Texas | TARRANT |  | 06 | 2009912 | "SPN:0172-02-067-REPAIR FAILURES, MILL, 2"" HMAC OVERLAY, PAVEMENT MARKINGS & SIGNALS : OAK STREET IN MANSFIELD ; SPN:0747-04-062-MILL EXISTING 2"" AND OVERLAY : 1000 FT SOUTH OF DEBBIE LANE ; SPN:23 | Pavement Improvement | 11/06/2009 |  |  | 1267997.97 | 3.296
6426 | Texas | BOWIE | TEXARKANA (TX-AR) | 04 | 2009921 | SPN:0218-01-070-CONSTRUCT RAILROAD GRADE SEPARATION STRUCTURE AND APPROACHES : AT UNION PACIFIC RR OVERPASS ; | Pavement Improvement | 11/02/2009 | 11/19/2009 |  | 1713000 | 0.506
6427 | Texas | NUECES |  | 27 | 2009928 | SPN:2263-02-086-CONSTRUCT 2ND NEW 28 CAR FERRY BOAT PLANS BY NAVAL ARCHITECT : AT THE PORT ARANSAS FERRY LANDING ; | Other | 08/31/2009 |  | 05/01/2011 | 6506000 | 0.001
6428 | Texas | STEPHENS |  | 19 | 2010003 | SPN:0257-01-038-FLEX BASE AND SEAL COAT : FM 576W, SOUTH ; | Pavement Improvement | 10/14/2009 | 11/19/2009 |  | 1648067 | 4.264
6429 | Texas | HAYS |  | 25 | 2010004 | SPN:0016-02-130-SEAL COAT, MILL&INLAY, OVERLAY W\PFC : 2000 FT N OF FM 2001 ; | Pavement Improvement | 10/09/2009 | 11/02/2009 |  | 431995.37 | 0.379
6430 | Texas | COKE |  | 11 | 2010005 | SPN:0264-04-046-CONCRETE PAVEMENT AT INTERSECTION : 0.353 MI NORTH OF SH 158 (MAIN ST) ; | Pavement Improvement | 10/21/2009 | 11/09/2009 |  | 387885.5 | 0.001
6431 | Texas | JOHNSON |  | 17 | 2010006 | SPN:2464-01-013-RECONSTRUCT ROADWAY : FM 4 END OF ROADWAY; | Pavement Improvement | 11/30/2009 |  |  | 1249457.36 | 6.266
6432 | Texas | CASS |  | 01 | 2010007 | SPN:0919-00-064-INSTALLATION AND UPGRADE OF TRAFFIC CONTROL DEVICES : VARIOUS LOCATIONS IN ATL DISTRICT ; | Safety/Traffic Management | 10/16/2009 |  |  | 399251.94 | 0.001
6433 | Texas | MARION |  | 01 | 2010008 | SPN:0632-01-028-RESTORE SECTION AND RESURFACE 2 LANE HIGHWAY : FM 2208 ; | Pavement Improvement | 11/02/2009 |  |  | 267595.18 | 3.047
6434 | Texas | BOWIE | TEXARKANA (TX-AR) | 04 | 2010009 | SPN:0945-01-036-UPGRADE EXISTING TRAFFIC SIGNALS : AT 40TH/KENNEDY LANE IN TEXARKANA ; | Safety/Traffic Management | 10/16/2009 |  |  | 134750.78 | 0.066
6435 | Texas | UPSHUR |  | 01 | 2010012 | SPN:0392-02-080-REPAIR PAVEMENT ON EXISTING 4 LANE HIGHWAY : 0.2 MI S OF FM 557 ; | Pavement Improvement | 10/16/2009 |  |  | 715360 | 3.23
6436 | Texas | LIBERTY |  | 08 | 2010024 | SPN:1146-01-027-RESTORE EXISTING ROADWAY : SH 146, EAST ; | Pavement Improvement | 10/14/2009 | 10/12/2009 |  | 994796.57 | 6
6437 | Texas | MILAM |  | 31 | 2010027 | SPN:0204-08-053-OVERLAY CONSISTING OF MILLING, HMA OVERLAY, SURFACE TREATMENT AND PAVEMENT MARKINGS AND MARKERS : 0.4 MILE WEST OF FM 2095 ; | Pavement Improvement | 10/30/2009 |  |  | 766187.19 | 5.56
6438 | Texas | GRIMES |  | 17 | 2010029 | SPN:0212-04-032-OVERLAY CONSISTING OF HMA LEVEL-UP, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : FM 244 ; | Pavement Improvement | 10/14/2009 | 11/02/2009 |  | 1849901.76 | 8.067
6439 | Texas | FREESTONE |  | 06 | 2010030 | SPN:0426-02-018-RESTORE EXISTING ROAD CONSISTING OF GRADING, FLEXIBLE BASE, SURFACE AND PAVEMENT MARKINGS AND MARKERS : FM 1848 ; SPN:2144-01-013-RESTORE EXISTING ROAD CONSISTING OF GRADING, FLEXIBLE | Pavement Improvement | 11/06/2009 |  |  | 1317884.18 | 10.464
6440 | Texas | DICKENS |  | 13 | 2010031 | SPN:0651-04-016-SEALCOAT ECONOMIC STIMULUS : FM 2565, SE ; | Pavement Improvement | 10/15/2009 | 10/27/2009 |  | 90114 | 7.715
6441 | Texas | JIM WELLS |  | 15 | 2010032 | SPN:0086-11-041-REHAB. EXISTING ROADWAY : VENTURA ST., IN SAN DIEGO, EAST ; | Pavement Improvement | 11/12/2009 |  |  | 3776701.94 | 8.71
6442 | Texas | ARANSAS, SAN PATRICIO |  | 14 | 2010033 | SPN:0180-05-058-MILL,SEAL AND OVERLAY : STAPP ST. ; SPN:0180-06-088-MILL,SEAL AND OVERLAY : ARANSAS/SAN PAT CO. LINE ; | Pavement Improvement | 10/26/2009 |  |  | 782350.63 | 1.942
6443 | Texas | SAN PATRICIO |  | 15 | 2010034 | SPN:0371-04-056-OVERLAY AND SEAL EXISTING LANES : ARANSAS RIVER BRIDGE ; | Pavement Improvement | 11/06/2009 |  |  | 2224860.59 | 5.502
6444 | Texas | COLLIN |  | 04 | 2010037 | SPN:0387-05-019-RECONSTRUCT RURAL 2 LANE HIGHWAY TO 2 LANE URBAN WITH SHOULDERS AND TWLTL : US 380 ; | Pavement Improvement | 10/26/2009 |  |  | 4887963.33 | 1.054
6445 | Texas | PRESIDIO, BREWSTER |  | 23 | 2010040 | SPN:0020-09-017-OVERLAY : 1.286 MI E BREWSTER/PRESIDIO CO LIN ; SPN:0020-10-017-OVERLAY : APPROX 7 MI. W. OF MOSLEY LANE ; | Pavement Improvement | 09/30/2009 | 10/02/2009 |  | 1241892.51 | 2.819
6446 | Texas | EL PASO |  | 16 | 2010041 | SPN:0924-00-067-UPGRADING OVERHEAD AND LARGE GROUND MOUNTED SIGNS : VARIOUS LOCATIONS DISTRICTWIDE ; | Safety/Traffic Management | 10/16/2009 |  |  | 635030.08 | 1
6447 | Texas | PALO PINTO |  | 13 | 2010043 | "SPN:0007-08-026-CEMENT TREAT EXISTING BASE ON NB LANE AND SHOULDER, SEAL COAT AND 2"" HMAC OVERLAY ENTIRE ROADWAY : PALO PINTO CREEK ; " | Pavement Improvement | 11/02/2009 |  |  | 1473364.87 | 11.262
6448 | Texas | WISE |  | 12 | 2010044 | SPN:0013-08-115-2 INCH OVERLAY NORTHBOUND LANES : NBL 475` S OF US 380 ; | Pavement Improvement | 11/02/2009 |  |  | 837946.86 | 4.092
6449 | Texas | JOHNSON |  | 17 | 2010045 | SPN:0019-01-136-HOTMIX OVERLAY : NORTH OF POINDEXTER ST; IN CLEBURNE ; | Pavement Improvement | 11/16/2009 |  |  | 2086653.12 | 2.829
6450 | Texas | JOHNSON |  | 17 | 2010046 | SPN:0019-02-031-SEAL COAT : CLEBURNE CITY LIMITS ; | Pavement Improvement | 11/12/2009 |  |  | 1009579.3 | 3.588
6451 | Texas | HOOD |  | 17 | 2010047 | SPN:0080-08-024-MILL AND HMAC OVERLAY : US 377 ; | Pavement Improvement | 11/06/2009 |  |  | 385831.92 | 2.01
6452 | Texas | ERATH, SOMERVELL |  | 31 | 2010048 | SPN:0258-01-026-SEAL COATS : FM 847 IN DUBLIN ; SPN:0258-02-050-SEAL COAT : 5.9 MI EAST OF FM 847 ; SPN:0259-02-045-SEAL COATS : ERATH COUNTY LINE ; | Pavement Improvement | 11/16/2009 |  |  | 1138715.02 | 18.31
6453 | Texas | GALVESTON |  | 14 | 2010051 | SPN:0051-09-023-RAISE ROADWAY AND BASE REPAIRS (PHASE 1) : SAN LUIS PASS TOLL BRIDGE ; | Pavement Improvement | 11/02/2009 | 11/18/2009 |  | 3227313 | 18.273
6454 | Texas | HARRIS | HOUSTON | 02, 18 | 2010053 | SPN:0110-05-116-PAVEMENT MARKINGS : NORTH OF BW 8 ; SPN:0110-06-130-PAVEMENT MARKINGS : SOUTH OF BW 8 ; | Safety/Traffic Management | 11/02/2009 |  |  | 324477.4 | 8.818
6455 | Texas | WALLER |  | 10 | 2010055 | SPN:0543-01-059-SEAL COAT, OVERLAY AND PAVEMENT MARKINGS : BU 290 ; | Pavement Improvement | 10/21/2009 | 11/16/2009 |  | 1657626 | 10.859
6456 | Texas | FORT BEND | HOUSTON | 22 | 2010056 | SPN:0543-03-059-REPLACE BRIDGE AND APPROACHES : AT SMITHERS LAKE ; | Bridge Replacement | 10/16/2009 |  |  | 1288241.82 | 0.124
6457 | Texas | HARRIS | HOUSTON | 02, 29, 22, 09, 07, 18 | 2010057 | SPN:0912-00-335-UPGRADE/RECONSTRUCT TRAFFIC SIGNALS : VARIOUS LOCATIONS DISTRICTWIDE ; | Safety/Traffic Management | 11/16/2009 |  | 10/30/2009 | 898349.73 | 0.001
6458 | Texas | HARRIS | HOUSTON | 02, 29, 22, 07, 18, 14, 09, 08, 10 | 2010058 | SPN:0912-00-383-UPGRADE/RECONSTRUCT TRAFFIC SIGNALS : VARIOUS LOCATIONS DISTRICTWIDE ; | Safety/Traffic Management | 10/30/2009 |  |  | 946870.85 | 0.001
6459 | Texas | FORT BEND |  | 14, 22 | 2010059 | SPN:0912-34-148-LANDSCAPE DEVELOPMENT : VARIOUS LOCATIONS ON US 59 ; | Transportation Enhancements | 11/16/2009 |  |  | 186209.34 | 0.001
6460 | Texas | HARRIS |  | 22, 29, 02, 18, 09, 07, 10 | 2010061 | SPN:0912-72-181-BRIDGE MAINTENANCE-REPAIRING STEEL MEMBERS, SEALING ACCESS DOORS, CLEANING AND PAINTING CAPS AND OTHER MISC WORK : VARIOUS LOCATIONS ; | Other | 10/26/2009 | 11/18/2009 |  | 1348545 | 0.001
6461 | Texas | WALLER |  | 10 | 2010064 | SPN:1418-01-010-SEAL COAT, OVERLAY AND PAVEMENT MARKINGS : IH 10 EB FRONTAGE ROAD ; | Pavement Improvement | 10/21/2009 | 11/06/2009 |  | 777940 | 4.842
6462 | Texas | MONTGOMERY |  | 08 | 2010065 | SPN:1986-01-059-DRAINAGE IMPROVEMENTS : 0.212 MI NW OF MILLS ROAD ; | Other | 11/06/2009 |  | 11/06/2009 | 367819.89 | 0.338
6463 | Texas | HARRIS |  | 07 | 2010066 | SPN:3256-01-094-RESHAPE AND STABILIZE EROSION : AT WHITE OAK BAYOU ; | Other | 11/04/2009 |  |  | 106335.6 | 0.034
6464 | Texas | LA SALLE |  | 28 | 2010067 | SPN:0017-08-070-RECONSTRUCTION OF NORTH BOUND MAINLANES, RAMPS : LA SALLE/FRIO COUNTY LINE ; | Pavement Improvement | 11/18/2009 |  |  | 1574216.7 | 8.468
6465 | Texas | CROSBY, FLOYD |  | 13 | 2010074 | SPN:0453-04-021-SEAL COAT ECONOMIC STIMULUS : US 62 ; SPN:0806-01-011-SEAL COAT ECONOMIC STIMULUS : US 62 EAST ; SPN:1143-01-009-SEAL COAT ECONOMIC STIMULUS : US 62 ; SPN:2497-02-005-SEAL COAT ECONOMI | Pavement Improvement | 10/15/2009 | 10/27/2009 |  | 840770.5 | 38.637
6466 | Texas | SAN AUGUSTINE, SABINE, SAN JACINTO |  | 08 | 2010075 | SPN:0177-02-085-MICROSURFACING : 0.61 MI S OF RR OVERPASS ; SPN:0177-02-086-MICROSURFACING : TRINITY RIVER BRIDGE ; SPN:0336-07-060-MICROSURFACING : FM 1751 ; SPN:0336-08-024-MICROSURFACING : SAN | Pavement Improvement | 11/02/2009 | 11/18/2009 |  | 1275635.47 | 23.09
6467 | Texas | WINKLER |  | 11 | 2010077 | SPN:0463-06-024-ROADWAY REHABILITATION : 1.3 MILES EAST OF SH 18 IN KERMIT ; | Pavement Improvement | 10/21/2009 | 11/17/2009 |  | 1773715.49 | 16.312
6468 | Texas | GRAYSON |  | 04 | 2010078 | SPN:0045-19-045-OVERLAY EXISTING 2 LANE ROADWAY : BETHANY ROAD ; | Pavement Improvement | 10/26/2009 |  |  | 2943236.01 | 5.362
6469 | Texas | HIDALGO |  | 15 | 2010080 | SPN:0342-01-080-OVERLAY : 0.163 MI E OF FM 493 ; SPN:1586-01-055-OVERLAY : SH 107 ; | Pavement Improvement | 11/02/2009 |  |  | 1603329.13 | 10.155
6470 | Texas | CAMERON |  | 27 | 2010081 | SPN:0872-04-025-UPGRADE DRAINAGE CULVERT AND RAISE ROAD : 2.96 MI N OF US 83 ; | Other | 10/15/2009 | 10/16/2009 |  | 864254.25 | 0.92
6471 | Texas | HIDALGO | MCALLEN-PHARR-EDINBURG | 15, 28 | 2010083 | SPN:1939-01-049-REHAB SB OUTSIDE LANE & OVERLAY FULL ROADWAY WIDTH : 1250` N. OF TRENTON RD ; | Pavement Improvement | 11/06/2009 |  |  | 540908 | 2.377
6472 | Texas | BEXAR | SAN ANTONIO | 20, 23 | 2010087 | SPN:0291-10-097-LANDSCAPE PLANTING, IRRIGATION SYSTEM, & SPECIALIZED PAVING : AT LP 1604 ; | Transportation Enhancements | 11/02/2009 | 11/18/2009 |  | 191565.56 | 0.5
6473 | Texas | UVALDE |  | 23 | 2010088 | SPN:0369-03-028-REHAB EXISTING ROADWAY & ADD SHOULDERS : 0.8 MI. S OF SABINAL RIVER ; | Pavement Improvement | 10/15/2009 |  |  | 1285287.46 | 5.566
6474 | Texas | BEXAR | SAN ANTONIO | 20 | 2010089 | SPN:0521-04-261-LANDSCAPE DEVELOPMENT : AT IH 10 ; | Transportation Enhancements | 11/02/2009 | 11/18/2009 |  | 865906.52 | 0.001
6475 | Texas | ATASCOSA |  | 28 | 2010090 | SPN:0613-02-055-LANDSCAPE PLANTING & IRRIGATION SYSTEM : AT SH 173, N OF JOURDANTON ; | Transportation Enhancements | 10/21/2009 |  |  | 85788 | 0.7
6476 | Texas | FRIO |  | 28 | 2010091 | SPN:0748-01-028-REHAB AND WIDEN NARROW ROADWAY : 2.2 MI E OF PEARSALL ; | Pavement Improvement | 10/15/2009 | 10/19/2009 | 10/19/2009 | 3097967.34 | 10.7
6477 | Texas | GUADALUPE |  | 28 | 2010092 | SPN:0915-46-036-LANDSCAPE PLANTING AND IRRIGATION : VARIOUS LOCATIONS IN SEGUIN ; | Transportation Enhancements | 10/16/2009 | 11/01/2009 |  | 491794.72 | 0.001
6478 | Texas | SMITH | TYLER | 01 | 2010094 | SPN:0191-03-021-PLANE & RESURFACE ROADWAY : LP 323 IN TYLER, S ; | Pavement Improvement | 10/21/2009 |  |  | 736484.3 | 1.593
6479 | Texas | ANDERSON |  | 05 | 2010095 | SPN:0205-07-071-PLANE & RESURFACE ROADWAY : 0.4 MI SE OF FM 2394 IN P`STINE, NE ; SPN:0206-01-046-PLANE & RESURFACE ROADWAY : 0.5 MI W OF SH 155 (JACKSON ST), NE ; | Pavement Improvement | 10/22/2009 |  |  | 1582436.6 | 3.391
6480 | Texas | MCLENNAN, LIMESTONE |  | 17 | 2010097 | SPN:0056-01-032-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : SH 31 ; SPN:0056-02-030-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : MCLENNAN CO LINE ; SPN:0056-03-057-REPAIR AND RESURFACE WITH ASPHALT | Pavement Improvement | 11/06/2009 | 12/03/2009 |  | 2332820 | 32.206
6481 | Texas | WILBARGER |  | 13 | 2010098 | SPN:0124-03-059-PLANING AND NOVACHIP OVERLAY : US 287 ; | Pavement Improvement | 10/26/2009 |  |  | 605866.52 | 1.619
6482 | Texas | WHARTON |  | 14 | 2010099 | SPN:0089-07-140-PAVEMENT REPAIR & ACP SURFACING : CANEY CREEK ; SPN:0089-08-090-PAVEMENT REPAIR & ACP SURFACING : NORTH OF SH 60 ; | Pavement Improvement | 11/12/2009 |  |  | 4409900.24 | 7.03
6483 | Texas | CALHOUN |  | 14 | 2010100 | SPN:0180-01-074-ASPHALTIC CONCRETE PAVEMENT : MILDRED DR IN PORT LAVACA ; | Pavement Improvement | 11/24/2009 |  |  | 1813198.22 | 11.04
6484 | Texas | RANDALL |  | 13 | 2010103 | SPN:0168-09-153-CURB RAMPS AND CONCRETE MEDIAN : AT WESTERN, GEORGIA & REBECCA STRS ; | Pavement Improvement | 10/30/2009 |  |  | 80828 | 0.414
6485 | Texas | LA SALLE, VAL VERDE |  | 28 | 2010199 | SPN:0017-17-006-FOR THE CONSTRUCTION OF MICROSEAL TYPE OF WORK : IH 35/BI-35C NORTH INTERSECTION 1.867 MI SOUTH; SPN:0022-10-056-FOR THE CONSTRUCTION OF MICROSEAL TYPE OF WORK : STRICKLEN DRIVE 17TH | Pavement Improvement | 11/16/2009 |  |  | 573297.57 | 4.557
6486 | Utah | DUCHESNE |  | 3 | 0040051 | This project widens US 40 to three lanes from West Roosevelt to Ioka Junction | Pavement Widening | 01/21/2005 | 04/01/2009 |  | 3230069.03 | 2
6487 | Utah | SALT LAKE | SALT LAKE CITY | 3 | 0068049 | This project will reconstruct the intersection of 6200 South and Redwood Road to add capacity and improve traffic operations | Other | 03/16/2009 | 03/19/2009 | 07/31/2011 | 11090229.9 | 0.1
6488 | Utah | DAVIS | OGDEN | 1 | 0108024 | This project reconstructs and widens Syracuse Road (SR 108) from 1000 West to 2000 West in Syracuse | Other | 07/12/2007 | 04/01/2009 | 04/30/2010 | 19999849.11 | 1
6489 | Utah | SALT LAKE | SALT LAKE CITY | 2 | 0209013 | This project improves intersection operations at 9000 South and 450 West by adding turn lanes and other improvments | Pavement Improvement | 10/06/2006 | 06/24/2008 |  | 705446.19 | 0
6490 | Utah | SAN JUAN |  | 3 | 0491005 | This project reconstructs the pavement on SR-491 from milepost 0 to Milepost 1.5 in Monticello, Utah | Pavement Improvement | 12/13/2007 | 04/01/2009 |  | 3800000 | 1.5
6491 | Utah | SUMMIT |  | 3 | 0846088 | This project rehabilitates the pavement on I-84 form the Morgan County Line to Henefer by removing some of the existing pavement and adding a structural overlay. | Pavement Improvement | 12/12/2005 | 04/01/2009 |  | 600000 | 3
6492 | Utah | SALT LAKE | SALT LAKE CITY | 2 | 2172004 | This project adds safety improvements and reconstructs 3900 South from Highland Drive to 2300 East | Pavement Improvement | 01/01/2008 | 04/11/2008 | 07/13/2010 | 5578566.22 | 4
6493 | Utah | UTAH | PROVO-OREM | 3 | 2896002 | This project reconstructs 50 South in American fork from 700 East to 1100 East | New Construction | 04/26/2005 | 04/01/2009 | 02/26/2010 | 2299000 | 4
6494 | Utah | CACHE | LOGAN | 1 | F002726 | This project constructs a new three lane roadway from 800 South to 300 South along new and existing alignments in Logan | New Construction | 02/08/2008 | 01/27/2009 | 09/30/2010 | 2860580 | 5
6495 | Utah | WEBER |  | 1 | F003664 | This project reconstructs the pavement and adds pedestrian ramps on Wall Avenue (SR-204) From 23rd Street to US-89 in Ogden | Pavement Improvement | 03/09/2009 | 04/01/2009 | 10/30/2009 | 5486782.08 | 1
6496 | Utah | SUMMIT |  | 1 | F004135 | This project rehabilitated the pavement on I-80 from Echo Junction to Emory by removal some of the existing asphalt and adding a structural overlay. | Pavement Improvement | 03/16/2009 | 04/01/2009 |  | 14225000 | 12
6497 | Utah | WEBER |  | 1 | F004474 | This project constructs a new Bike and Pedestrian Trail in Hooper, Utah | Transportation Enhancements | 12/14/2007 | 04/01/2009 | 11/30/2009 | 359000 | 0
6498 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F004615 | This project adds auxillary lanes on I-15 from 10000 South to 7200 South. These lanes will improve traffic operations and capacity. | Pavement Widening | 02/10/2009 | 03/31/2009 | 12/02/2009 | 15000070.7 | 2
6499 | Utah | UTAH | PROVO-OREM | 3 | F004654 | This project reahbilitates the pavement on US-189 from University Parkway to Provo Canyon and improves and widens intersections. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 3855000 | 0.5
6500 | Utah | UTAH | PROVO-OREM | 3 | F004680 | This project adds an asphalt overlay on SR-92 from SR-74 to SR-146. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1486379.83 | 1.8
6501 | Utah | SALT LAKE |  | 3 | F004864 | This project rehabilitates the concrete pavement on I-215 from 4700 South to SR-201, repairing potholes and grinding to improve rideability. | Pavement Improvement | 03/17/2009 | 04/01/2009 | 03/31/2010 | 3818620.3 | 3
6502 | Utah | SALT LAKE |  | 3 | F004890 | This project rehabilitates the asphalt pavement on SR-111 (8400 West) from 3500 South to SR-201 in Salt Lake county by removing some of the existing asphalt and adding a structural overlay | Pavement Improvement | 03/10/2009 | 04/01/2009 | 10/01/2009 | 935279.52 | 1.9
6503 | Utah | UTAH | PROVO-OREM | 3 | F005122 | This project replaces 3 bridge decks on I-15 in the Payson, Utah area. | Bridge Improvement | 03/03/2009 | 04/01/2009 |  | 5850000 | 1
6504 | Utah | CARBON |  | 3 | F005269 | This project reconstructs the pavement on Carbonville Road near Price, Utah | Pavement Improvement | 04/01/2009 | 04/01/2009 | 06/30/2010 | 2100940.31 | 0
6505 | Utah | SUMMIT |  | 3 | F005667 | This project reconstructs Coalville Main Street and SR-280 in Coalville, Utah | Pavement Improvement | 11/24/2008 | 04/01/2009 | 03/31/2010 | 1211276.5 | 0
6506 | Utah | SUMMIT |  | 3 | F005671 | This project replaces two bridges on I-80 over Echo Frontage Road near Echo Junction. | Bridge Replacement | 12/23/2008 | 02/17/2009 |  | 4975000 | 1
6507 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F005693 | This project provides intersection improvements along 6200 South from 3000 East to I-215. | Pavement Widening | 03/10/2009 | 04/01/2009 | 03/31/2010 | 1753656.3 | 0
6508 | Utah | WEBER | OGDEN | 1 | F005706 | This project applied a chip seal to various locations on US-89 to improve skid resistance and extend pavement life. It also retrofitted existing and installed new pedestrian ramps. | Pavement Improvement | 06/12/2008 | 03/31/2009 |  | 1033441.16 | 0
6509 | Utah | CACHE | LOGAN | 1 | F005788 | This project applied a chip seal on SR-101 from SR-23 to SR-165 to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 | 05/08/2009 | 1961000 | 5.9
6510 | Utah | UTAH | PROVO-OREM | 3 | F005828 | This project applied a thin bonded overlay to the pavement on I-15 from the Benjamin interchange to Spanish Fork. This improves skid resistance and extends pavement life. | Pavement Improvement | 01/14/2009 | 03/31/2009 |  | 1765949.56 | 3.95
6511 | Utah | SALT LAKE |  | 1 | F005952 | This project rehabilitates the asphalt pavement on SR-269 and SR-270 at various locations. | Pavement Improvement | 03/09/2009 | 04/01/2009 |  | 1745728.08 | 0
6512 | Utah | SALT LAKE |  | 2 | F005957 | This project rehabilitates the concrete pavement on I-215 from Milepost 5.709 to Milepost 7.585, repairing potholes and grinding to improve rideability. | Pavement Improvement | 01/13/2009 | 01/13/2009 |  | 986793.56 | 1.876
6513 | Utah | SAN JUAN |  | 3 | F005983 | This project applied a chip seal on US-191 from Milepost 73 to Milepost 86 to improve skid resistance and extend pavement life. | Pavement Improvement | 01/06/2009 | 03/31/2009 |  | 720852.47 | 13
6514 | Utah | SANPETE |  | 3 | F005994 | This project applied a chip seal on US-89 from Milepost 227.6 to 267.2 and on SR-132 to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 938417 | 0
6515 | Utah | SEVIER |  | 3 | F005996 | This project applied a lane leveling asphalt overlay on SR-118 from Milepost 6.9 to 10.0. | Pavement Improvement | 03/19/2009 | 04/01/2009 |  | 1000000 | 3.1
6516 | Utah | UTAH | PROVO-OREM | 3 | F006024 | This project applied a polymer overaly on six bridges, extending the life of the bridge decks. | Bridge Improvement | 04/01/2009 | 04/01/2009 |  | 230562.44 | 0
6517 | Utah | TOOELE |  | 1 | F006065 | This project applied a 1 1/2 inch overlay on SR-36 from the Junction of SR 73 to Three O'Clock drive in Tooele, Utah to improve ride, skid resistance and extend the life of the pavement. | Pavement Improvement | 06/04/2009 | 08/17/2009 |  | 1685000 | 9.89
6518 | Utah | MILLARD |  | 3 | F006071 | This project applied a asphalt wearing surface on I-15 from Milepost 158.5 to 169 to improve skid resistance and extend the pavement life. | Pavement Improvement | 03/09/2009 | 04/01/2009 | 03/31/2010 | 4961123.59 | 10.5
6519 | Utah | SEVIER |  | 3 | F006072 | This project rehabilitated the concrete pavement on I-70 from Mile post 6.8 to 17.7. This rehabilitation included slab replacment and joint sealing. | Pavement Improvement | 03/10/2009 | 04/01/2009 |  | 1300000 | 10.9
6520 | Utah | WASHINGTON |  | 2 | F006073 | This project applied an asphalt wearing surface on SR-9 form Mile post 0 to 4.9 to improve skid resistance and extend pavement life. | Pavement Improvement | 03/03/2009 | 04/01/2009 |  | 2127812.14 | 4.9
6521 | Utah | WASHINGTON | ST. GEORGE | 2 | F006074 | This project constructs a new bridge over the Santa Clara River in St. George, Utah. | Bridge Replacement | 03/03/2009 | 04/01/2009 | 04/30/2010 | 3800000 | 0
6522 | Utah | STATEWIDE |  | 1 | F006076 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 1(Northern Utah). | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 250000 | 0
6523 | Utah | STATEWIDE |  | 2 | F006077 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 1 (Northern Utah). | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 250000 | 0
6524 | Utah | STATEWIDE |  | 1 | F006080 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 2 (Salt Lake Area). | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 500000 | 0
6525 | Utah | STATEWIDE |  | 3 | F006082 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 3 (Central Utah). | Transportation Enhancements | 04/01/2009 | 04/01/2009 | 12/31/2009 | 450000 | 0
6526 | Utah | STATEWIDE |  | 1 | F006084 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Cedar City District of Region 4. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 150000 | 0
6527 | Utah | STATEWIDE |  | 2 | F006085 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Price District of Region 4. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 150000 | 0
6528 | Utah | STATEWIDE |  | 3 | F006086 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Richfield District of Region 4. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 151000 | 0
6529 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006088 | This project constructed safe sidewalks and installed pedestrian ramps in various locatons on SR-171. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 200000 | 0
6530 | Utah | WEBER |  | 1 | F006089 | This project constructed safe sidewalks and installed pedestrian ramps on US-89; 400 South to 4400 South in Ogden, Utah. | Transportation Enhancements | 03/03/2009 | 04/01/2009 |  | 150000 | 0
6531 | Utah | DAVIS |  | 1 | F006090 | This project constructed safe sidewalks and installed pedestrian ramps on SR-107; 4000 West to 4050 West in West Point, Utah. | Transportation Enhancements | 03/03/2009 | 04/01/2009 |  | 60000 | 0
6532 | Utah | DAVIS |  | 1 | F006091 | This project constructed safe sidewalks and installed pedestrian ramps on SR-37; 3500 West to 3550 West, in Clinton, Utah. | Transportation Enhancements | 03/12/2009 | 04/01/2009 |  | 145000 | 0
6533 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006092 | This project constructed safe sidewalks and installed pedestrian ramps on SR-266; Redwood Road to 550 West in Taylorsville, Utah. | Transportation Enhancements | 03/12/2009 | 03/12/2009 |  | 400000 | 0
6534 | Utah | DUCHESNE |  | 2 | F006093 | This project constructed safe sidewalks and installed pedestrian ramps on SR-87; 800 NOrth to 1400 North in Duchesne, Utah. | Transportation Enhancements | 03/03/2009 | 04/01/2009 |  | 200000 | 0
6535 | Utah | STATEWIDE |  | 2 | F006095 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Cedar City District of Region 4. | Transportation Enhancements | 03/17/2009 | 04/01/2009 |  | 100000 | 0
6536 | Utah | STATEWIDE |  | 3 | F006096 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Price District of Region 4. | Transportation Enhancements | 03/03/2009 | 04/01/2009 |  | 150000 | 0
6537 | Utah | STATEWIDE |  | 1 | F006097 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Richfield District of Region 4. | Transportation Enhancements | 03/03/2009 | 04/01/2009 |  | 115000 | 0
6538 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006099 | This project constructed safe sidewalks and installed pedestrian ramps in variouslocations on SR-48. | Transportation Enhancements | 03/12/2009 | 03/12/2009 |  | 100000 | 0
6539 | Utah | WEBER | LOGAN | 1 | F006109 | This project provided fiber optic connections on US-89 from I-84 to Harrison Blvd to improve traffic signal operations. | Safety/Traffic Management | 04/01/2009 | 04/01/2009 |  | 251999.6 | 0
6540 | Utah | SALT LAKE |  | 2 | F006110 | This project provided traffic signal interconnection on SR-190 & SR-210; Wasatch Boulevard from I-215 to Cottonwood Canyon to improve traffic operations. | Safety/Traffic Management | 04/01/2009 | 04/01/2009 | 06/22/2010 | 1300000 | 1
6541 | Utah | SUMMIT |  | 1 | F006118 | This project constructs wildlife fence along I-80 in Parley's Canyon to enhance safety for both drivers and wildlife. | Other | 03/10/2009 | 04/01/2009 |  | 395000 | 1
6542 | Utah | GARFIELD |  | 2 | F006119 | This project extends the bike path along SR-12 in Garfield County | Transportation Enhancements | 03/31/2009 | 04/01/2009 | 01/25/2010 | 750000 | 1
6543 | Utah | TOOELE |  | 1 | F006120 | This project constructed a new roadway along 1000 North from SR-112 to 600 West in Tooele, Utah. | New Construction | 03/12/2009 | 03/12/2009 | 12/31/2010 | 3500000 | 0
6544 | Utah | DAVIS | OGDEN | 1 | F006121 | This project will reconstruct 500 South into a five-lane roadway with two lanes in each direction and a center turning lane. Additional improvements include 12-foot shoulders to accommodate on street | Transportation Enhancements | 04/01/2009 | 04/01/2009 | 12/01/2009 | 4450000 | 1
6545 | Utah | UTAH | PROVO-OREM | 3 | F006123 | This project on US-89 widens the shoulders to accomodate bicycles and pedestrians. | Transportation Enhancements | 03/16/2009 | 04/01/2009 |  | 263686 | 0.5
6546 | Utah | UTAH | PROVO-OREM | 3 | F006146 | This project Expands and installs computer hardware and software to update the emergency data intregration in Region 3. Enancing the commuter link system and providing better traffic operations. | Safety/Traffic Management | 03/12/2009 | 04/01/2009 |  | 526000 | 0
6547 | Utah | DAVIS | OGDEN | 1 | F006147 | This project provides signal detection upgrades in Weber and Davis Counties | Other | 03/12/2009 | 04/01/2009 |  | 524999.57 | 0
6548 | Utah | WEBER | OGDEN | 1 | F006148 | This project installs conduit to on I-15 from Layton to Riverdale Road to enhance the commuter link program, improving traffic operations. | Safety/Traffic Management | 03/12/2009 | 04/01/2009 |  | 575289.7 | 0
6549 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006149 | This project expands the Advanced Traffic Management System (ATMS) through improvements to the signal interconnection in the Salt Lake County Area. | Safety/Traffic Management | 03/03/2009 | 04/01/2009 | 09/30/2010 | 999091.81 | 0
6550 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006150 | This project expands the Variable Message Signs in the downtown Salt Lake Area, enhancing traffic operations. | Safety/Traffic Management | 03/03/2009 | 04/01/2009 |  | 369383.37 | 0
6551 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006151 | This project provdes upgrades to the traffic operations systems (signals Variable Message Signs etc.) along Bangerter Highway from 90th South to SR-201. | Safety/Traffic Management | 03/12/2009 | 04/01/2009 |  | 220000 | 0
6552 | Utah | EMERY |  | 2 | F006152 | This project reconstructs the Goblin Valley (Temple Mountain Road in Emery County, Utah | Pavement Widening | 03/12/2009 | 03/26/2009 |  | 1719953.6 | 0
6553 | Utah | UTAH |  | 2 | F006161 | This project constructed safe sidewalks and installed pedestrian rampson SR-198 at various locations in Payson and Santaquin, Utah. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 195000 | 0
6554 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006188 | This project made intersection imporvements at 9000 South and 700 East in Sandy, Utah. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1047652.54 | 0
6555 | Utah | UINTAH |  | 1 | F006191 | This project made improvements to the signalized intersection on US-40 at 1000 South and 500 East in Vernal, Utah | Other | 04/01/2009 | 04/01/2009 | 12/31/2009 | 220000 | 1
6556 | Utah | UTAH | PROVO-OREM | 2 | F006241 | This project made repairs to the SR-189 bridge at 600 South University AVenue. | Bridge Improvement | 04/01/2009 | 04/01/2009 |  | 2500000 | 1
6557 | Utah | DUCHESNE | PROVO-OREM | 2 | F006242 | This project repainted the structural steel on the US-40 Bridge over Starvation Reservoir. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1234000 | 1
6558 | Utah | DAVIS | OGDEN | 1 | F006243 | This project entails applying a chip seal to the existing SR-109 roadway surface between Fairfield Road (MP 1.07) and US-89 (MP 2.962) in Layton City, UT. After applying the chip seal, traffic contro | Pavement Improvement | 04/01/2009 | 04/01/2009 | 05/20/2009 | 310000 | 24
6559 | Utah | DAVIS |  | 1 | F006244 | This project applied microsurfacing to SR-273 From US-89 To 200 South in Kaysville to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 | 05/20/2009 | 582458.89 | 1.4
6560 | Utah | SALT LAKE |  | 2 | F006245 | This project applied an asphalt seal coat to SR-190 from 3000 East to the sR-210 in Salt Lake County to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 484203.38 | 1.55
6561 | Utah | SALT LAKE |  | 2 | F006246 | This project applied a 1 1/2 inch overaly on SR-173 from 3200 West to 1900 West in Salt Lake County | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 661053.97 | 1.28
6562 | Utah | SALT LAKE |  | 2 | F006247 | This project applied a 1 1/2 inch overaly on SR-173 from 5600 West to 4800 West in Salt Lake County | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 460025.34 | 0.98
6563 | Utah | CARBON |  | 3 | F006248 | This project provided surface treatements on SR-10 and SR-55 in Carbon County to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 2365525.05 | 0
6564 | Utah | DAVIS |  | 1 | F006250 | This project made safety improvements to I-215 from Redwood Road to I-15. | Safety/Traffic Management | 04/01/2009 | 04/01/2009 | 06/01/2009 | 130395.8 | 1.9
6565 | Utah | SANPETE |  | 3 | F006253 | This project applied a slurry seal to US-89; Ephraim, Manti, Panguitch Main Streets and Snow College roads to improve skid resistance and exxtend pavement life | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 486159.52 | 1.2
6566 | Utah | IRON |  | 1 | F006254 | This project applied a wearing course on SR-130 in Iron County from milepost 0 to 5 to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1540000 | 5
6567 | Utah | SALT LAKE |  | 2 | F006307 | This project applied a polymer overlay on US-89; State Street from 90th South to 106th South and on SR-71; 700 East. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 800000 | 0
6568 | Utah | SALT LAKE |  | 2 | F006308 | This project installed median cable barrier on SR-154 north of SR-201 in Salt Lake County. | Safety/Traffic Management | 04/01/2009 | 04/01/2009 |  | 400000 | 0
6569 | Utah | SALT LAKE |  | 2 | F006309 | This project rehabilitated the asphalt pavement on SR-186; Foothill Boulevard from Sunnyside AVenue to 1300 East in Salt Lake City. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 2300000 | 0
6570 | Utah | UTAH | PROVO-OREM | 3 | F006315 | This project applied a wearing surface on SR-114 from SR-89 in Provo to SR-89 In Pleasant grove to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 2733916.68 | 0
6571 | Utah | WEBER | OGDEN | 1 | F006316 | This project Removes existing asphalt to a depth of approximately 7 inches, and replaces with 7 inches on SR-204 from SR-26 to 32nd street . Once all paving is complete, the manholes will be raised. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1122433.92 | 0
6572 | Utah | IRON |  | 1 | F006338 | This project rehabilitates the asphalt pavement on SR-143 in Iron County from Milepost 2 to 2.4 and on SR-274 from Milepost 0.57 to 1.3 by removing some of the existing asphalt and adding a structural | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 205297 | 0
6573 | Utah | UTAH | PROVO-OREM | 3 | I156172 | This project applies a micro surface seal to the pavement on I-15 from SR-75 to the Provo River, improving and extending the pavement life. | Pavement Improvement | 01/18/2008 | 03/31/2009 |  | 3417560.07 | 5
6574 | Utah | UTAH | PROVO-OREM | 3 | I156173 | This project rehabilitates the pavement on I-15 from 800 South, Payson to the Juab County Line by removal of some of the existing asphalt pavement and adding a structural overlay. | Pavement Improvement | 01/18/2008 | 03/31/2009 |  | 1894367.46 | 9.3
6575 | Utah | SALT LAKE |  | 2 | I803148 | This project replaces the I-80 bridges over 2300 East | Bridge Replacement | 02/23/2009 | 04/01/2009 |  | 6300000 | 1
6576 | Utah | SALT LAKE | SALT LAKE CITY | 2 | I803149 | This project widens the ramps from I-80 East bound to I-215 from a single off ramp to a dual off ramp, improving operations and capacity. | Pavement Widening | 02/05/2009 | 04/01/2009 | 12/04/2009 | 2200227.97 | 0.099
6577 | Utah | SANPETE |  | 3 | LC39009 | This project reconstructs the Pigeon Hollow Road from Pigeon Hollow to Spring City | Pavement Improvement | 12/12/2005 | 04/01/2009 |  | 2098932.3 | 0
6578 | Utah | UTAH | PROVO-OREM | 3 | LC49089 | This project constructs a new trail along the historic Utah South Rail line via the UPRR North Lehi line | Pavement Improvement | 05/27/2005 | 04/01/2009 | 04/10/2010 | 2399999.69 | 0
6579 | Utah | WASATCH | PROVO-OREM | 3 | LC51008 | This project reconstructs Center Street in Heber City from Main Street to 1400 East | Pavement Improvement | 04/24/2007 | 04/01/2009 | 06/01/2010 | 1290303.2 | 1
6580 | Utah | WASHINGTON |  | 1 | LC53022 | This project reconstructs the roadway from 600 North to SR-9 in Hurricane | Pavement Improvement | 11/24/2003 | 04/01/2009 |  | 1290303.2 | 0
6581 | Utah | WASHINGTON |  | 1 | LC53034 | This project reconstructs and widens Washington Fields Road, including the Virgin River Bridge from Indian Springs Drive to Telegraph Road in Washington. | Pavement Widening | 04/24/2008 | 04/01/2009 |  | 1035000 | 0
6582 | Utah | WASHINGTON |  | 1 | LC53042 | This project realigns Hilton Drive and Black Ridge Drive to improve traffic operations | Pavement Improvement | 08/28/2007 | 04/01/2009 | 08/02/2010 | 2069768.89 | 0
6583 | Vermont | WINDSOR |  | 00 | 0136001 | Repaving the roadway | Pavement Widening | 04/02/2009 | 04/02/2009 | 10/16/2009 | 2413660.57 | 4.4
6584 | Vermont | RUTLAND |  | 00 | 0193495 | Reconstruction of the existing roadway to provide wider shoulders. | Pavement Widening | 11/04/2009 | 11/04/2009 | 06/29/2012 | 11456392.57 | 4.347
6585 | Vermont | CHITTENDEN | BURLINGTON | 00 | 0209006 | This project replaces deteriorated truss members and aging concrete deck, along with providing a wider and friendlier pedestrian walkway, for this historic steel truss bridge in the town of Richmond. | Bridge Improvement | 02/06/2009 | 02/06/2009 | 07/06/2009 | 1990999.21 | 0.06
6586 | Vermont | WASHINGTON |  | 00 | 0283036 | This project improves motorist safety by replacing a functionally obsolete 3-span bridge with a long-lasting single-span weathering steel girder bridge utilizing a high performance concrete deck, a ne | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/18/2010 | 2301276.64 | 0.027
6587 | Vermont | CALEDONIA |  | 00 | 0302018 | This project replaces an antiquated and deficient bridge on State Route 15 with a fully modern structure. | Bridge Improvement | 06/15/2009 | 06/15/2009 | 11/30/2009 | 969891.15 | 0.018
6588 | Vermont | WASHINGTON |  | 00 | 0372009 | Replace exisitng Bridge #69 ON VT14 in East Montpelier. | Pavement Improvement | 10/16/2009 | 10/16/2009 | 10/01/2010 | 1420790.97 | 0.038
6589 | Vermont | WINDSOR |  | 00 | 0891054 | Repaving the roadway | Pavement Improvement | 04/10/2009 | 04/10/2009 | 11/13/2009 | 7948259.08 | 7.9
6590 | Vermont | WINDSOR |  | 00 | 0891055 | Repairing the existing pipes by putting new pipes inside the existing pipes. | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/30/2009 | 1301016.35 | 25.8
6591 | Vermont | WINDSOR, ORANGE |  | 00 | 0912072 | This is a safety project for the removal of ledge from the edge of the roadway on Interstate I-91 at various locations between milepoint 69 and 110 in both the northbound and southbound lanes | Pavement Improvement | 09/16/2009 | 09/16/2009 | 11/19/2010 | 3024403.49 | 37.9
6592 | Vermont | RUTLAND |  | 00 | 1443039 | Replace Deck Bridge #15 ON TH3 in Clarendon. | Bridge Improvement | 09/14/2009 | 09/14/2009 | 08/20/2010 | 411132.22 | 0
6593 | Vermont | RUTLAND |  | 00 | 1443045 | Replace existing Bridge #19 ON TH23 (SHORT STRUCTURE) in Chittenden. | Pavement Improvement | 10/28/2009 | 10/28/2009 | 10/29/2010 | 425255.55 | 0.07
6594 | Vermont | RUTLAND |  | 00 | 1443046 | Replace Bridge #20 ON TH23 (SHORT STRUCTURE) in Chittenden. | Pavement Improvement | 10/28/2009 | 10/28/2009 | 10/29/2010 | 385076.63 | 0.07
6595 | Vermont | ORLEANS |  | 00 | 1449028 | This project will replace a severely deteriorated Town Highway bridge for the Town of Brownington | Bridge Replacement | 03/20/2009 | 03/20/2009 | 11/06/2009 | 1225051.02 | 0
6596 | Vermont | WINDSOR |  | 00 | 2206001 | This is a paving project for 5 miles of US route 5 between Hartford and Norwich. This project also includes paving the Wilder State highway and safety improvements at the I-91 off ramp with the Wilder | Pavement Improvement | 06/22/2009 | 06/22/2009 | 10/16/2009 | 2132427.52 | 4.3
6597 | Vermont | ORANGE |  | 00 | 2213001 | Resurfacing VT25 - Bradford-Orange. | Pavement Improvement | 07/22/2009 | 07/22/2009 | 10/30/2009 | 5201359.13 | 11.33
6598 | Vermont | FRANKLIN |  | 00 | 2217001 | This is a paving project for 11 miles of Vermont Route 104 between the Towns of Fairfax and Saint Albans starting at milepoint 6.8 in the town of Fairfax. | Pavement Improvement | 09/03/2009 | 09/03/2009 | 06/11/2010 | 3305425.65 | 11.653
6599 | Vermont | WINDSOR |  | 00 | 2602001 | This project is for paving .8 miles of US Route 5 and the Norwich State Highway and . 5 miles of Vermont Route 10A | Pavement Improvement | 06/22/2009 | 06/22/2009 | 10/16/2009 | 2341988.98 | 1.6
6600 | Vermont | WASHINGTON |  | 00 | 2604001 | This is a paving project for 3 miles of US 2 in Montpelier from Bailey Ave to Granite Street | Pavement Improvement | 06/08/2009 | 06/08/2009 | 08/26/2009 | 2307091.99 | 2.8
6601 | Vermont | RUTLAND |  | 00 | 2614001 | This project will resurface approximately 5.1 miles along route 4A in the Towns of Fair Haven and Castelton to provide a much smoother and safer ride. In addition key drainage improvements will be ma | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/16/2009 | 2625839.72 | 5.1
6602 | Vermont | RUTLAND |  | 00 | 2615001 | This project will resurface approximately 1.6 miles of deteriorated pavement which will provide for a smoother and safer ride along Route 4A in the Town of Fair Haven. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/16/2009 | 1075645.17 | 1.6
6603 | Vermont | CHITTENDEN | BURLINGTON | 00 | 2616001 | This project is for paving 2.9 miles of Vermont Route 15 in Colchester and Essex starting at the Winooski/Colchester town Line. | Pavement Improvement | 04/03/2009 | 04/03/2009 | 10/02/2009 | 2683849.59 | 2.9
6604 | Vermont | CHITTENDEN | BURLINGTON | 00 | 2617001 | This project is for paving .25 miles of Vermont Route 15 from the US Route 7/ Vermont Route 15 intersection to the Winooski/Colchester line. This project aslo includes concrete repair on US Route 7 in | Pavement Improvement | 06/14/2009 | 06/14/2009 | 10/14/2009 | 2557395.38 | 0.8
6605 | Vermont | WASHINGTON |  | 00 | 2618001 | This project is for paving of .9 miles US Route 302 in Montpelier starting from the US Route 2/US Route 302 intersection. | Pavement Improvement | 06/08/2009 | 06/08/2009 | 08/26/2009 | 742254.74 | 0.9
6606 | Vermont | WINDHAM, WINDSOR |  | 00 | 2628001 | Repaving the roadway | Pavement Improvement | 04/24/2009 | 04/24/2009 | 10/16/2009 | 4095863.87 | 9.4
6607 | Vermont | WINDSOR |  | 00 | 2701001 | This is a paving project for 1.5 miles of Vermont Route 14 starting at the US Route 5 intersection.This project also include paving .25miles of US 4 in Hartford. | Pavement Improvement | 06/08/2009 | 06/08/2009 | 10/16/2009 | 1548596.92 | 1.7
6608 | Vermont | ESSEX |  | 00 | 2724001 | REpaving the roadway | Pavement Improvement | 08/24/2009 | 08/24/2009 | 09/26/2010 | 6209476.04 | 7.781
6609 | Vermont | ESSEX |  | 00 | 2725001 | Repaving the roadway | Pavement Improvement | 08/24/2009 | 08/24/2009 | 09/24/2010 | 5895533.52 | 7.96
6610 | Vermont | CHITTENDEN | BURLINGTON | 00 | 2726001 | This project is for paving US Route 7 from the South Burlington/Burlington city line and extending north .2 miles to include the intersection of Interstate 189 | Pavement Improvement | 06/14/2009 | 06/14/2009 | 10/14/2009 | 857779.42 | 0.2
6611 | Vermont | CHITTENDEN | BURLINGTON | 00 | 2727001 | This project is for paving US Route 7 from the Intersate 189 intersection and extending north for .25 miles to Hadley Road | Pavement Improvement | 06/14/2009 | 06/14/2009 | 10/14/2009 | 655443.12 | 0.2
6612 | Vermont | WASHINGTON |  | 00 | 6000015 | This project improves motorist safety by rehabilitating existing bridge abutments and replacing the bridge superstructure with a modern steel beam bridge in Barre City. | Bridge Improvement | 04/15/2009 | 04/15/2009 | 11/27/2009 | 1341315.22 | 0.02
6613 | Vermont | WASHINGTON |  | 00 | 6400031 | Rehabilitate Bridge #5 ON Taylor ST (TRUSS BR) in Montpelier. | Transportation Enhancements | 12/16/2009 | 12/16/2009 |  | 1746920.78 | 0.067
6614 | Vermont | CALEDONIA |  | 00 | SURF014 | REPAVING THE ROADWAY WITH A THIN BITUMINOUS SURFACE TREATMENT. | Pavement Improvement | 07/27/2009 | 07/27/2009 | 10/15/2010 | 2423413.12 | 9.42
6615 | Virginia | BOTETOURT | ROANOKE | 06 | FS09001 | This project includes a slab removal on the right travel lane on both the NBL and SBL of I-81. On the SBL it will begin at the South end of Rte 640 overpass (exit 156) moving South for 4.3 miles. On | Pavement Improvement | 07/08/2009 | 08/03/2009 | 10/04/2010 | 19457862 | 9.64
6616 | Virginia | HENRICO | RICHMOND | 07 | FS09002 | Conversion of CRCP pavement to composite; extensive pavement rehab. Project underway. Completion date June 2010. | Pavement Improvement | 07/16/2009 | 07/16/2009 |  | 6465729 | 3.28
6617 | Virginia | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09003 | "This project will repair the existing deterioriated concrete pavement and then place 3.5"" inches of asphalt over the existing concrete pavement on I-64 in the City of Chesapeake." | Pavement Improvement | 07/08/2009 | 08/10/2009 |  | 15627101 | 15.6
6618 | Virginia | WYTHE |  | 09 | FS09004 | Milling, paving and guardrail upgrade in Wythe County Northbound I-77 from mile posts 24.19 to 25.69 and 26.59 to 29.22; and on Southbound I-77 from mile posts 40.69 to 46.31. | Pavement Improvement | 07/01/2009 |  |  | 6257313 | 0
6619 | Virginia | WASHINGTON | BRISTOL (VA-TN) | 09 | FS09005 | Milling, paving and guardrail upgrade on Southbound I-81 from mile post 19.63 to 25.36 in Washington County. | Pavement Improvement | 08/04/2009 | 08/04/2009 |  | 2905650 | 5.73
6620 | Virginia | PRINCE EDWARD |  | 05 | FS09006 | This project includes milling the existing 24 foot wide pavement and existing paved shoulder (approx. 2 inches on each side) of Rte. 460 EBL from 1.35 miles East of Rte. 735 to the Nottoway County Lin | Pavement Improvement | 08/10/2009 | 08/10/2009 | 04/01/2010 | 3166600 | 2.88
6621 | Virginia | STATEWIDE |  | 04 | FS09007 | Basic bituminous overlay on Routes 360 and 460 in Richmond district. Complete. | Pavement Improvement | 06/22/2009 | 06/22/2009 |  | 2123382 | 23.08
6622 | Virginia | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09008 | VDOT will patch and seal cracks in the exitsting asphalt on I-464 in the City of Chesapeake then place 1.5 inches of new asphalt over the existing asphalt surface. This project also will upgrade the | Pavement Improvement | 07/08/2009 | 07/22/2009 |  | 5428192 | 5.95
6623 | Virginia | STAFFORD | FREDERICKSBURG | 08 | FS09009 | I-95, basic bituminous overlay. Work in Spotsylvania County is complete and work in Stafford to be done next year. | Pavement Improvement | 07/15/2009 | 08/06/2009 |  | 10221032 | 16.7
6624 | Virginia | RICHMOND |  | 01 | FS09010 | Basic bituminous overlay, Route 3 and Route 360 in Lancaster and Richmond counties. Complete. | Pavement Improvement | 07/01/2009 | 07/29/2009 |  | 2933654 | 16.2
6625 | Virginia | FAUQUIER |  | 10 | FS09011 | This resurfacing project inludes mill and overlay of 17.21 miles in length on various routes in Warrenton Residency | Pavement Improvement | 06/09/2009 | 09/11/2009 |  | 3823687 | 17.27
6626 | Virginia | CULPEPER |  | 07 | FS09012 | This resurfacing project includes mill and overlay of 18.41 miles on various routes in Culpeper Residency of VDOT | Pavement Improvement | 06/16/2009 | 07/06/2009 |  | 2849924 | 18.41
6627 | Virginia | ALBEMARLE | CHARLOTTESVILLE | 07 | FS09013 | This resurfacing project is in Albemarle County of Culpeper District includes mill and overlay of 20.3 miles on various routes | Pavement Improvement | 07/08/2009 | 08/02/2009 |  | 3557080 | 20.39
6628 | Virginia | WARREN |  | 07 | FS09014 | Asphalt overlay, rumble strips and guardrail upgrade on Westbound I-66 from mile post 6.6 to 10.7 in Warren County. | Pavement Improvement | 06/09/2009 | 08/04/2009 |  | 1411053 | 4.1
6629 | Virginia | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09015 | Mill existing asphalt 2 inches and overlay with 2 inches of asphalt | Pavement Improvement | 07/06/2009 | 07/09/2009 |  | 3426970 | 9
6630 | Virginia | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | 08 | FS09016 | Milling existing asphalt 2 inches and overlay with 2 inches of asphalt | Pavement Improvement | 08/16/2009 | 08/16/2009 |  | 4442320 | 17.5
6631 | Virginia | STATEWIDE | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01, 03 | FS09030 | This project will widen a 3.15 mile section of Route 105 in the City of Newport News and York County from 2 existing lanes to a 4 lane divided principle arterial.? | Pavement Widening | 11/02/2009 | 11/02/2009 |  | 19795937 | 6.8
6632 | Virginia | SMYTH |  | 09 | FS09031 | Milling, paving and guardrail upgrade on Northbound and Southbound I-81 from mile posts 34.25 to 35.35 (on NBL) and 35.35 to 34.32 (on SBL) in Smyth County. | Pavement Improvement | 07/23/2009 | 09/16/2009 |  | 1795745 | 2.13
6633 | Virginia | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09032 | This project will repair cracks and patch the exisitng deteriorated pavement and then place a thin layer of asphalt of the existing pavement. | Pavement Improvement | 07/08/2009 | 07/24/2009 | 08/01/2010 | 7677483 | 12.83
6634 | Virginia | BOTETOURT |  | 06 | FS09039 | This project will resurface and upgrade the guarrails on a portion of Rte. 220 and Rte. 58. | Pavement Improvement | 08/25/2009 |  |  | 2919572 | 14.38
6635 | Virginia | MADISON |  | 07 | FS09040 | This project will provide smooth surface by milling and overlaying a portion of Route 230, 231 and 29 in Culpeper. | Pavement Improvement | 07/08/2009 | 07/15/2009 |  | 2253695 | 15.6
6636 | Virginia | STATEWIDE |  | 05 | FS09041 | Districtwide pavement overlay in Lynchburg District. | Pavement Improvement | 10/01/2009 | 10/20/2009 |  | 335869 | 2.97
6637 | Washington | SNOHOMISH |  | 02 | 0002300 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 05/07/2009 | 05/07/2009 | 07/01/2010 | 1879282.23 | 5.23
6638 | Washington | PEND OREILLE |  | 05 | 0002301 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 06/09/2009 | 06/09/2009 | 12/01/2009 | 5831649 | 12.68
6639 | Washington | LINCOLN |  | 05 | 0002302 | Construct a new sidewalk and pedestrian crossing that will provide safer passage for pedestrians to cross from Wilbur Street. | Safety/Traffic Management | 06/22/2009 | 06/22/2009 | 12/31/2009 | 160000 | 0.36
6640 | Washington | THURSTON, GRAYS HARBOR |  | 06, 03 | 0008012 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 11/02/2009 | 11/02/2009 | 05/15/2010 | 1860390 | 20.63
6641 | Washington | COLUMBIA |  | 05 | 0012194 | Add landscaping and irrigation system to the West entrance into the City of Dayton along US 12. | Transportation Enhancements | 09/14/2009 |  |  | 148593 | 0.166
6642 | Washington | KLICKITAT |  | 04 | 0014062 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 05/26/2009 | 05/26/2009 | 10/01/2009 | 509307 | 5.36
6643 | Washington | CLARK |  | 03 | 0014063 | Construct a pedestrian tunnel underneath State Route 14 to improve pedestrian access and safety. | Transportation Enhancements | 07/06/2009 |  |  | 506783 | 0.02
6644 | Washington | JEFFERSON |  | 06 | 0020163 | Construct roundabouts, center median, sidewalks, drainage, bike lanes, and turn lanes. | Pavement Widening | 09/15/2009 |  |  | 1959623 | 0.795
6645 | Washington | SNOHOMISH |  | 02 | 0045005 | Construction of a pedestrian and bike trail on the south side of 188th Street between 59th Avenue and 67th Avenue in Arlington. | Transportation Enhancements | 09/08/2009 |  |  | 122000 | 0.57
6646 | Washington | COWLITZ |  | 03 | 0051270 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 07/01/2009 | 07/01/2009 | 11/22/2010 | 2879937 | 17.33
6647 | Washington | COWLITZ |  | 03 | 0051277 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 05/18/2009 | 05/18/2009 | 11/01/2010 | 7124791 | 7.01
6648 | Washington | CLARK |  | 03 | 0051278 | Constructs a new interchange that includes a wider bridge across I-5 and reconstruct the I-5 on and off ramps. | Bridge Replacement | 08/14/2009 | 08/14/2009 | 08/01/2011 | 8200000 | 1.21
6649 | Washington | CLARK, COWLITZ | PORTLAND-VANCOUVER, OR-WA | 03 | 0051281 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 07/27/2009 | 07/27/2009 | 11/01/2009 | 1703331 | 14.76
6650 | Washington | LEWIS |  | 03 | 0052202 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 11/01/2009 | 2881514.35 | 13.29
6651 | Washington | PIERCE | SEATTLE-TACOMA, WA | 09 | 0053948 | This project will construct HOV lanes to relieve congestion and reduce the risk of collisions. | Bridge Replacement | 07/13/2009 | 07/13/2009 | 11/01/2011 | 35388653 | 2.89
6652 | Washington | THURSTON, PIERCE | SEATTLE-TACOMA, WA | 03,09 | 0053949 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 11/02/2009 | 11/02/2009 | 11/01/2010 | 10520853 | 21.94
6653 | Washington | PIERCE | TACOMA | 06 | 0053951 | This project reconstructs the eastbound interchange at I-5 and SR 16. This includes replacing the bridges over Nalley Valley, constructing freeway connections, reconstructing all of the ramp roadways | Other | 06/09/2009 | 06/09/2009 | 07/05/2011 | 7784925 | 1
6654 | Washington | SNOHOMISH |  | 02 | 0054272 | Install fiber, cameras and data stations in the corridor. Compliments conduit installation as part of the median barrier project. | Safety/Traffic Management | 06/15/2009 | 06/15/2009 | 12/01/2010 | 2500000 | 10.58
6655 | Washington | SKAGIT, SNOHOMISH |  | 02 | 0054277 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 06/01/2009 | 06/01/2009 | 09/01/2010 | 7148336 | 6.1
6656 | Washington | OKANOGAN |  | 05 | 0097137 | Construct curb; gutter; sidewalk; lighting; and stormwater drainage on US 97, 16th Ave, and Juniper St. | Transportation Enhancements | 09/08/2009 |  |  | 491383 | 1.58
6657 | Washington | KLICKITAT |  | 04 | 0097140 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 05/26/2009 | 05/26/2009 | 11/01/2009 | 3536233 | 23.32
6658 | Washington | KING | SEATTLE-TACOMA, WA | 07 | 0099078 | Construct a bridge to separate railroad and vehicle traffic on Duwamish Avenue South. | New Construction | 11/30/2009 |  |  | 2875171 | 0.2
6659 | Washington | GRAYS HARBOR |  | 06 | 0101318 | Remove and replace existing deteriorated curbs and sidewalks, along Heron Street from K Street to F Street. | Transportation Enhancements | 06/18/2009 |  | 08/25/2009 | 614448 | 0.4
6660 | Washington | PIERCE |  | 08 | 0162017 | Reconstruction of State Route 162 between Calistoga and Bridge Streets. Includes signalization, addition of left turn lanes, installation of street lighting, and landscaping. | Pavement Improvement | 09/08/2009 |  |  | 420000 | 0.26
6661 | Washington | KING | SEATTLE-TACOMA, WA | 09 | 0167044 | Provide a bypass for surface water draining into the Rainier Ave South pump station. | Other | 09/21/2009 |  |  | 1948674 | 0.22
6662 | Washington | WHITMAN |  | 05 | 0195046 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 06/18/2009 | 06/18/2009 | 11/20/2009 | 118868 | 17.75
6663 | Washington | SPOKANE | SPOKANE | 05 | 0195047 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project also includes some h | Pavement Improvement | 10/12/2009 | 10/12/2009 | 09/30/2010 | 2795404 | 4.56
6664 | Washington | STEVENS |  | 05 | 0205002 | Replace existing timber bridge with new concrete bridge. | Pavement Improvement | 09/02/2009 |  |  | 350000 | 0.01
6665 | Washington | SPOKANE |  | 05 | 0206003 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 12/01/2009 | 716066 | 2.44
6666 | Washington | OKANOGAN |  | 05 | 0215006 | Construct sidewalk along Okoma Drive from Jasmine St. to W. 4th Avenue. Also includes installation of sidewalk ramps at intersections; crosswalks; and new curbs. | Transportation Enhancements | 08/10/2009 |  |  | 166002 | 0.91
6667 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 0365007 | Pavement repairs and resurfacing of Dayton St. (5th Ave S to Admiral Way), 212th St SW (72nd Ave W to 84th Ave W), 220th St SW (SR 99 to 84th Ave W), and Olympic View Dr (76th Ave to Puget Dr). | Pavement Improvement | 09/21/2009 |  |  | 999985 | 2
6668 | Washington | STEVENS |  | 05 | 0395081 | Construct sidewalks and drainage improvements along US 395 from Juniper Street to Kettle Falls City limits. | Transportation Enhancements | 09/08/2009 |  |  | 43174 | 0.44
6669 | Washington | STEVENS |  | 05 | 0395088 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 05/27/2009 | 05/27/2009 | 12/01/2009 | 2176575 | 6.69
6670 | Washington | STEVENS |  | 05 | 0395089 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 06/12/2009 | 06/12/2009 | 11/01/2009 | 6376092 | 22.27
6671 | Washington | BENTON |  | 04 | 03EI001 | Construct new sidewalks on 7th Street from Ellen Avenue to the North City Limits. | Transportation Enhancements | 09/21/2009 |  |  | 207000 | 0.436
6672 | Washington | WAHKIAKUM |  | 03 | 0409001 | Replace the existing Puget Island ferry ramp. | Bridge Replacement | 08/18/2009 |  |  | 590000 | 0.02
6673 | Washington | COWLITZ | LONGVIEW (OR) | 03 | 0433010 | Clean and paint the remaining steel elements on SR 433/Lewis and Clark Bridge. | Bridge Improvement | 04/30/2009 | 04/30/2009 | 10/22/2011 | 12500000 | 0.54
6674 | Washington | THURSTON |  | 03 | 0507024 | Pedestrian and street lighting improvements on Sussex Avenue from Ritter Street to Ragless Street. | Transportation Enhancements | 09/28/2009 |  |  | 554000 | 0.4
6675 | Washington | KING | SEATTLE-TACOMA, WA | 09 | 0509020 | Reconstruct 1st Ave SW between SW 192nd and SW 200th Streets to include three vehicle lanes, bike lanes, street lights, landscaping, and sidewalk. | Pavement Improvement | 08/03/2009 |  |  | 3834000 | 0.5
6676 | Washington | KING | SEATTLE-TACOMA, WA | 08 | 0520042 | Construct a new bridge over State Route 520. Bridge includes two vehicle lanes, bike lanes, sidewalks, street lighting. | New Bridge Construction | 05/12/2009 |  |  | 4594075 | 0.5
6677 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 0529017 | Widen sidewalk along West Marine View Drive to improve pedestrian/bicycle safety. | Transportation Enhancements | 09/28/2009 |  |  | 1427465 | 0.53
6678 | Washington | GRAYS HARBOR |  | 06 | 0560006 | New sidewalk and sidewalk ramps on State Route 101 and 7th St, Simpson, 8th St, L St, K St, 6th St, J St, 5th St, H St, Emerson, Jefferson, Grant, Cleveland, 4th St, Riverside, Sumner, 24th St. | Transportation Enhancements | 07/02/2009 | 07/02/2009 | 03/01/2010 | 195000 | 0
6679 | Washington | PACIFIC |  | 03 | 0575004 | Construct beach/ocean scenic overlook at Beards Hollow on State Route 100. | Transportation Enhancements | 10/09/2009 |  |  | 100000 | 0
6680 | Washington | THURSTON | OLYMPIA | 09 | 0643005 | Construct missing segments of the Woodland Trail from the Chehalis-Western Regional Trail to the Woodland Creek Community Park through the City of Lacey. | Transportation Enhancements | 06/26/2009 |  |  | 1000000 | 2.4
6681 | Washington | YAKIMA | YAKIMA | 04 | 0822128 | This project will rearrange the interchange to increase safety, relieve congestion and improve traffic flow movements. | Bridge Replacement | 04/01/2009 | 04/01/2009 | 10/15/2011 | 23169445 | 1.8
6682 | Washington | YAKIMA |  | 04 | 0822131 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 05/26/2009 | 05/26/2009 | 11/01/2009 | 6887312 | 14.73
6683 | Washington | KITTITAS, KING |  | 04,08 | 0901476 | Replace the existing traveler information cameras in the Snoqualmie Pass vicinity with low light cameras to provide improved visibility of roadway conditions at night. | Safety/Traffic Management | 08/10/2009 | 08/10/2009 | 10/01/2009 | 60000 | 91.71
6684 | Washington | KITTITAS |  | 04 | 0902259 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 04/03/2009 | 04/03/2009 | 10/01/2009 | 2428622 | 3.73
6685 | Washington | KITTITAS |  | 04 | 0902260 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 04/03/2009 | 04/03/2009 | 10/01/2009 | 2973679 | 4.68
6686 | Washington | KITTITAS |  | 04 | 0902283 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 06/01/2009 | 06/01/2009 | 11/01/2009 | 3634518 | 3.21
6687 | Washington | KITTITAS |  | 04 | 0902302 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 06/01/2009 | 06/01/2009 | 06/01/2011 | 17657700 | 9.5
6688 | Washington | KITTITAS |  | 04 | 0902315 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 04/30/2009 | 04/30/2009 | 10/28/2011 | 18520000 | 5.5
6689 | Washington | SPOKANE |  | 05 | 0902319 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 07/17/2009 | 10/05/2009 | 11/20/2009 | 32751 | 11.84
6690 | Washington | GRANT |  | 04 | 0904118 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 07/13/2009 | 07/13/2009 | 10/01/2009 | 4005860 | 6.17
6691 | Washington | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 09WA004 | Reconstruct North Parkway Avenue from North Onsdorff Boulevard to N 5th Street. The road will include three traffic lanes, curb & gutter, sidewalks, landscaping, and street lighting. | Pavement Widening | 10/02/2009 |  |  | 43788 | 0.45
6692 | Washington | KING | SEATTLE-TACOMA, WA | 09 | 1073004 | Construct new curb, gutter, and sidewalk along East Valley Highway between S. 212th St. and State Route 167; add a third vehicle lane; and traffic signal improvements. | Pavement Widening | 07/27/2009 |  |  | 2000000 | 0.85
6693 | Washington | SPOKANE | SPOKANE | 05 | 1220021 | Construct a 4.4 mile long trail to connect to an existing trail. Includes the rehabilitation of 5 bridges and trailhead facility. | Transportation Enhancements | 07/07/2009 |  |  | 778317 | 4.4
6694 | Washington | KING | SEATTLE-TACOMA, WA | 09 | 1301003 | Construction of sidewalk, bicycle lane, and street lights on the east side of 4th Avenue SW between SW 153rd Street and SW 156th Street. | Transportation Enhancements | 08/17/2009 |  |  | 536293 | 0.22
6695 | Washington | YAKIMA | YAKIMA | 04 | 1335009 | Construct an approximately 0.6 mile long pedestrian pathway. | Transportation Enhancements | 08/24/2009 |  | 09/11/2009 | 121201 | 0.576
6696 | Washington | CHELAN | WENATCHEE | 04 | 1405006 | Cleaning and painting of an historic bridge. | Transportation Enhancements | 09/28/2009 |  |  | 1506749 | 0.208
6697 | Washington | KING | SEATTLE-TACOMA, WA | 07 | 1482010 | Construct a bridge parallel and connected to the existing Spokane Street Viaduct. Includes the construction of new on and off ramps. | Pavement Widening | 12/09/2009 |  |  | 15443000 | 0.75
6698 | Washington | CLALLAM |  | 06 | 2005075 | Construct a multi-use trail along railroad right of way on the north side of Lake Crescent. | Transportation Enhancements | 07/06/2009 |  |  | 335000 | 6.4
6699 | Washington | CLALLAM |  | 06 | 2005076 | Construct an approximately 0.7 mile long mult-use trail along railroad right of way. | Transportation Enhancements | 07/14/2009 |  | 09/16/2009 | 111000 | 0.682
6700 | Washington | GARFIELD |  | 05 | 2012017 | Pavement resurfacing on the following roadways: Gould City-Mayview Rd, Iron Springs Rd, Mountain Rd, and Peola Rd. | Pavement Improvement | 05/01/2009 |  | 07/27/2009 | 230915 | 14.99
6701 | Washington | ISLAND |  | 02 | 2015076 | Pavement resurfacing of the following roadways in Island County: Front Street; Alexander Street; Maxwelton Road; 3rd Street; and NE Regatta Drive. | Pavement Improvement | 08/27/2009 |  |  | 325167 | 2.97
6702 | Washington | KING | SEATTLE-TACOMA, WA | 07 | 2017090 | Construct a pedestrian walkway along SW 98th St. corridor between 12th Avenue SW and 11th Avenue SW. | Transportation Enhancements | 06/25/2009 |  |  | 1270557 | 0.05
6703 | Washington | KITTITAS |  | 04 | 2019024 | Improve a visitor center located south of Ellensburg on the Yakima River Canyon Scenic Byway by adding gravel to the parking area, and replacing fencing and restroom facilities. | Transportation Enhancements | 10/19/2009 |  |  | 42798 | 0
6704 | Washington | KITTITAS |  | 04 | 2019025 | Installation of guardrail and related safety improvements on roadways within Kittitas County. | Safety/Traffic Management | 09/14/2009 |  |  | 424335 | 2.2
6705 | Washington | SKAMANIA |  | 03 | 2030005 | Rehabilitation and resurfacing of an asphalt pathway section along Cascade Drive from Hot Springs to Greenleaf in the City of North Bonneville. | Transportation Enhancements | 07/30/2009 |  | 08/06/2009 | 13719 | 0.253
6706 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2506003 | Reconstruction of the roadway to include asphalt pavement resurfacing, new curb ramps, storm drainage repairs, and new bicycle lanes. | Pavement Improvement | 07/07/2009 |  |  | 856977 | 0.5
6707 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2523001 | Modify the existing Interstate 5/196th Street SW interchange to provide a pedestrian route across Interstate 5 and along 196th Street SW. | Transportation Enhancements | 07/17/2009 |  |  | 1250000 | 0.3
6708 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2674004 | This safety project will replace an existing 4-way stop sign controlled intersection with a roundabout. | Pavement Improvement | 01/11/2010 |  |  | 920000 | 0.2
6709 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2699002 | Asphalt resurfacing of 67th Ave from Grove Street to State Route 528 and 8th Street from State Ave to Cedar Ave. Includes replacing sidewalk ramps. | Pavement Improvement | 08/17/2009 |  | 09/25/2009 | 470207 | 0.75
6710 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2701004 | Remove existing culvert, construct 600 feet of new stream channel, and install new culvert fully open to fish passage. | Pavement Improvement | 08/17/2009 |  |  | 1403223 | 0.114
6711 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2722001 | Reconstruction of approximately 0.5 miles of roadway serving major residential and industrial areas. | Pavement Improvement | 07/15/2009 |  |  | 888692 | 0.511
6712 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01,02 | 2787001 | Improve Holly Drive with the construction of curbs, gutters, sidewalks, and bike lanes. | Transportation Enhancements | 09/14/2009 |  |  | 385447 | 0.2
6713 | Washington | SNOHOMISH |  | 02 | 31BH001 | Reconstruct roadway and construct curb, gutter and sidewalk on 68th Avenue NW between approximately 279th Street NW and at 280th Street NW. | Pavement Improvement | 08/13/2009 |  |  | 641439 | 0.2
6714 | Washington | PIERCE | SEATTLE-TACOMA, WA | 09 | 3217001 | Construct an extension of Shaw Road from Pioneer to E Main, including a new bridge over the Burlington Northern/Santa Fe railroad tracks. | New Construction | 08/04/2009 |  |  | 1201972 | 0.76
6715 | Washington | PIERCE | SEATTLE-TACOMA, WA | 09 | 3266006 | Construction of a new bridge that will eliminate four existing roadway/railroad crossings. | New Bridge Construction | 07/31/2009 |  |  | 15408000 | 0.4
6716 | Washington | SPOKANE |  | 05 | 32DE001 | Rehabilitate the Rutter Parkway bridge by repairing bridge supports, removing the existing bridge deck, installing a new concrete deck, and resurfacing the adjacent roadway with asphalt. | Bridge Improvement | 07/06/2009 |  | 08/19/2009 | 346837 | 0.044
6717 | Washington | BENTON | RICHLAND-KENNEWICK | 04 | 3412007 | Construct approximately 0.5 miles of concrete sidewalk. Includes landscaping of an existing median. | Transportation Enhancements | 06/22/2009 |  | 09/02/2009 | 121862 | 0
6718 | Washington | BENTON | RICHLAND-KENNEWICK | 04 | 3502002 | Reconstruct roadway and construct bike lanes, curb, gutter, and sidewalks. Install traffic signal at George Washington. Add sidewalks along George Washington and 1st Street. | Pavement Widening | 10/01/2009 |  |  | 1600000 | 0.5
6719 | Washington | WHATCOM |  | 02 | 37A1001 | Asphalt resurfacing of the existing pavement. | Pavement Improvement | 09/11/2009 |  | 09/28/2009 | 112304.45 | 0.72
6720 | Washington | SPOKANE | SPOKANE | 05 | 3840008 | Asphalt resurfacing of the existing roadway, upgrade curb ramps, and improve the stormwater drainage system. | Pavement Improvement | 07/20/2009 |  |  | 2606469 | 2
6721 | Washington | SPOKANE | SPOKANE | 05 | 3867001 | Construction of a new roadway between Lincoln Road and Ash Street. Includes new sidewalks, curbs, bike lanes, and landscaping. Also includes asphalt resurfacing from Austin Road to Ash Street. | Pavement Improvement | 05/08/2009 |  |  | 112720 | 1.3
6722 | Washington | SPOKANE | SPOKANE | 05 | 3867002 | Replace existing pavement with three inches of asphalt pavement. | Pavement Improvement | 07/06/2009 |  | 08/27/2009 | 859000 | 1.95
6723 | Washington | SPOKANE | SPOKANE | 05 | 3867003 | Reconstruct a portion of Five Mile Road between Berridae and Waikiki by replacing the existing pavement with a new asphalt pavement. The remaining portions of Five Mile Road will be resurfaced with o | Pavement Improvement | 09/08/2009 |  |  | 331000 | 1.43
6724 | Washington | KING | SEATTLE-TACOMA, WA | 08 | 4053858 | Construct on and off ramps to provide relief in a highly congested area of I-405 in the vicinity of downtown Bellevue and the I-405/SR 520 Interchange. | Pavement Improvement | 05/04/2009 |  | 12/01/2012 | 58937553.42 | 1.5
6725 | Washington | KING, SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 4053859 | Northbound I-405 will be widened to add an auxiliary (add/drop) lane between NE 195th Street and SR 527. | Pavement Widening | 08/24/2009 | 08/24/2009 | 12/01/2010 | 26991402 | 3
6726 | Washington | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 4242022 | Improve rail access into the Port of Vancouver by providing new rail infrastructure within existing facilities, and new track at Terminal 5. | Other | 11/09/2009 |  |  | 2500000 | 0
6727 | Washington | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 4410002 | Widen NE 99th Street to three vehicle lanes, bicycle lanes, and sidewalks between State Route 503 and NE 137th Ave. | Pavement Improvement | 10/19/2009 |  |  | 1831151 | 1.05
6728 | Washington | YAKIMA | YAKIMA | 04 | 4566009 | Reconstruct portions of the Nob Hill Boulevard pavement from 64th Avenue to 72nd Avenue. Includes improvements to the curb & gutter, sidewalk, stormwater drainage system, and street lighting. | Pavement Improvement | 09/01/2009 |  |  | 766683 | 0.5
6729 | Washington | YAKIMA |  | 04 | 4628006 | Asphalt resurfacing of the roadway, and upgrading of the curb ramps. | Pavement Improvement | 07/20/2009 |  | 09/07/2009 | 400000 | 0.99
6730 | Washington | YAKIMA | YAKIMA | 04 | 4645001 | Widen and reconstruct approximately 0.3 miles of Beaudry Road, including curb and gutter, sidewalks, stormwater drainage system, and street lighting. | Pavement Improvement | 07/20/2009 |  |  | 500000 | 0.284
6731 | Washington | YAKIMA | YAKIMA | 04 | 4708001 | Reconstruct approximately 0.7 miles of Speyers Road, from the west City limits to Fremont Avenue, including curb and gutter, sidewalk, stormwater drainage system, and street lighting. | Pavement Improvement | 08/17/2009 |  |  | 1598000 | 0.68
6732 | Washington | THURSTON | OLYMPIA | 03 | 5235012 | Construction of a dedicated five foot wide bicycle path on the east side of the roadway, and relocation of the existing sidewalk to accommodate the new bicycle path. | Transportation Enhancements | 07/29/2009 |  |  | 307144 | 0.66
6733 | Washington | THURSTON | OLYMPIA | 03 | 5235013 | Asphalt resurfacing of Capitol Blvd. from Dennis Street to Israel Road. | Pavement Improvement | 08/10/2009 |  | 09/16/2009 | 159034 | 0.25
6734 | Washington | THURSTON | OLYMPIA | 03 | 5346001 | Asphalt resurfacing of Union Avenue from Capitol Way to Plum Street. | Pavement Improvement | 07/28/2009 |  |  | 1098824 | 0.44
6735 | Washington | THURSTON |  | 09 | 5394003 | Construct sidewalks, street lighting, and intersection crossing improvements on Steilacoom Road, between Stonewood Drive and Duterrow Road. | Transportation Enhancements | 07/31/2009 |  | 09/02/2009 | 110244 | 0.17
6736 | Washington | LEWIS |  | 03 | 5667003 | Asphalt resurfacing of Jackson Highway. | Pavement Improvement | 07/09/2009 |  | 09/15/2009 | 775898 | 1.59
6737 | Washington | ASOTIN |  | 05 | 6005002 | Asphalt resurfacing of Scenic Way from 2nd Avenue to Fleshman Way. | Pavement Improvement | 08/16/2009 |  |  | 641147 | 0.98
6738 | Washington | GRANT |  | 04 | 6061001 | Asphalt resurfacing of the roadway, including improvements to curbs, sidewalks, bike path, and stormwater drainage system. | Pavement Improvement | 08/24/2009 |  |  | 1200000 | 1
6739 | Washington | GRANT |  | 04 | 6065004 | Construction an approximately 0.5 mile long eight foot wide pedestrian path. | Transportation Enhancements | 08/24/2009 |  |  | 28647 | 0.48
6740 | Washington | YAKIMA |  | 04 | 6340003 | Asphalt resurfacing of the intersection located at Yakima Valley Highway and Lincoln Avenue. | Pavement Improvement | 11/09/2009 |  |  | 150000 | 0.2
6741 | Washington | YAKIMA | YAKIMA | 04 | 6408004 | Asphalt resurfacing of existing road surface; and reconstruction of driveways, crosswalk accesses, and sidewalks. | Pavement Improvement | 09/14/2009 |  |  | 290839 | 0.21
6742 | Washington | KITSAP | BREMERTON | 01 | 6683004 | Project will improve safety and mobility on Viking Avenue by constructing a two-way left turn lane, bike lanes, stormwater drainage improvements, curb, sidewalk, and intersection channelization at Fin | Pavement Improvement | 06/23/2009 |  |  | 2729358 | 0.66
6743 | Washington | KITSAP | BREMERTON | 01 | 6701001 | Widen roadway shoulders near Blakely Elementary School to improve pedestrian safety. | Transportation Enhancements | 08/03/2009 |  | 09/28/2009 | 150000 | 0.133
6744 | Washington | COWLITZ | LONGVIEW (OR) | 03 | 6739001 | Roadway reconstruction and widening, and improvements to the roadway and intersection alignments to increase safety. | Pavement Widening | 08/10/2009 |  |  | 1056593 | 1.23
6745 | Washington | COWLITZ | LONGVIEW (OR) | 03 | 6763001 | Asphalt resurfacing of approximately 1.0 miles of South 13th Avenue. | Pavement Improvement | 07/20/2009 |  |  | 290587 | 0.975
6746 | Washington | KITTITAS |  | 04 | 6949002 | Asphalt resurfacing and restriping of Canyon Road from Interstate 90 to Umptanum Road. | Pavement Improvement | 06/23/2009 |  | 08/13/2009 | 394865 | 0.5
6747 | Washington | WALLA WALLA |  | 05 | 7166001 | Construct a multi-use pathway connecting major residential development, a local airport, schools, and the existing pedestrian system. | Transportation Enhancements | 09/21/2009 |  |  | 58000 | 0.27
6748 | Washington | WALLA WALLA |  | 05 | 7169001 | Reconstruct 13th Avenue from Rose St. to Abadie St. and from Cherry St. to Rees Ave. Includes sidewalks, bike facilities, stormwater drainage facilities, street lighting, and traffic signals. | Pavement Widening | 10/05/2009 |  |  | 1980000 | 0.714
6749 | Washington | SKAGIT | MOUNT VERNON | 02 | 7337006 | Construct an extension of Laventure Road extending south from Fowler St. to Blackburn Road. Roadway includes two traffic lanes, turn lane, bike lanes, and sidewalks. | New Construction | 07/27/2009 |  |  | 923769 | 0.25
6750 | Washington | SKAGIT |  | 02 | 7390001 | Reconstruct Fruitdale Road from State Route 20 to McGarigle Road. Includes construction of curbs, gutters, sidewalks, and street lighting. | Pavement Improvement | 06/01/2009 |  |  | 134867 | 1.34
6751 | Washington | WHITMAN |  | 05 | 7418002 | Asphalt resurfacing of approximately 0.46 miles of the following roadways: Whitman St from Kamiaken to Maple, Maiden Lane from Whitman to Opal, and Opal from Maiden Lane to Campus. | Pavement Improvement | 07/07/2009 |  | 08/04/2009 | 358819 | 0.462
6752 | Washington | CLALLAM |  | 06 | 7541001 | Reconstruct and widen Mount Pleasant Road. | Pavement Improvement | 08/31/2009 |  |  | 568000 | 0.4
6753 | Washington | SPOKANE |  | 05 | 7690002 | The construction of a turn lane, curb, sidewalk, street lighting and bicycle pathways on Cheney-Spangle Road from State Route 904 to Cheney City limits. | Transportation Enhancements | 09/08/2009 |  |  | 576416 | 0.4
6754 | Washington | ISLAND |  | 02 | 7790002 | Widening of Ault Field Road between Oak Harbor Road and Goldie Road to provide an additional travel lane. | Pavement Improvement | 07/23/2009 |  |  | 1357704 | 0.24
6755 | Washington | WHATCOM |  | 02 | 8037001 | Reconstruction of existing road and construction a new road on 2nd Ave from Washington to Portal Way at the Interstate-5 southbound offramp. | New Construction | 09/01/2009 |  |  | 1541000 | 0.5
6756 | Washington | YAKIMA |  | 04 | 8051001 | Asphalt resurfacing of Euclid Road from Forsell Road to Stassen Way. | Pavement Improvement | 06/25/2009 |  | 08/21/2009 | 318327 | 0.767
6757 | Washington | WHATCOM |  | 02 | 8158001 | Widening and asphalt resurfacing of roadway; and improvements to curb, gutter, and stormwater drainage. | Pavement Improvement | 06/09/2009 |  |  | 981169 | 0.6
6758 | Washington | CLALLAM |  | 06 | 9905005 | Asphalt resurfacing of existing street, striping, and curb ramp installation. | Pavement Improvement | 08/10/2009 |  |  | 393000 | 0.341
6759 | Washington | PIERCE |  | 08 | 9927049 | Construction of pedestrian amenities to include sidewalks, curb ramps, street lighting, and landscaping. | Pavement Widening | 09/21/2009 |  |  | 588101 | 1
6760 | Washington | STEVENS |  | 05 | 9933001 | Asphalt resurfacing of Williams Lake and Cedonia-Addy Roads. | Pavement Improvement | 06/22/2009 |  | 07/15/2009 | 980276 | 33.37
6761 | Washington | WHATCOM | BELLINGHAM | 02 | 9937002 | Installation of enhanced pedestrian crossings on high volume streets to improve safety and connectivity. Improvements include flashing lights, illuminated signage, and concrete pedestrian refuge isla | Transportation Enhancements | 07/22/2009 |  |  | 308596 | 0.1
6762 | Washington | YAKIMA | YAKIMA | 04 | 9939018 | Asphalt resurfacing of Rudkin Road and the Main Street/Ahtanum Road Intersection. | Pavement Improvement | 09/08/2009 |  |  | 266906 | 0.504
6763 | Washington | PACIFIC |  | 03 | 9999546 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 04/03/2009 | 04/03/2009 | 11/01/2009 | 394691 | 3.97
6764 | Washington | GRANT |  | 04 | 9999547 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 05/04/2009 | 05/04/2009 | 10/01/2009 | 6088296 | 13.49
6765 | Washington | GRANT, OKANOGAN |  | 05 | 9999548 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 05/04/2009 | 05/04/2009 | 08/01/2009 | 3574243 | 68.5
6766 | Washington | STEVENS, ADAMS, FERRY |  | 05 | 9999549 | Replace portable Highway Advisory Radio (HAR) trailers deployed on SR 20 and US 395 for Sherman Pass with permanent HAR stations and install a new station in the vicinity of the Hatton Coulee Rest Are | Safety/Traffic Management | 06/24/2009 | 06/24/2009 | 03/01/2010 | 240000 | 0
6767 | Washington | STATEWIDE |  | 04 | 9999550 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Other | 04/29/2009 | 04/29/2009 | 11/19/2010 | 200000 | 0
6768 | Washington | STATEWIDE |  | 04 | 9999551 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Other | 04/29/2009 | 04/29/2009 | 11/19/2010 | 500000 | 0
6769 | Washington | GRANT, CHELAN, BENTON, DOUGLAS, LINCOLN, FRANKLIN, YAKIMA, SPOKANE |  | 04 | 9999554 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 07/27/2009 | 07/27/2009 | 11/01/2010 | 685141 | 235.74
6770 | Washington | ISLAND, SKAGIT, KING, SNOHOMISH, WHATCOM |  | 01,02,08 | 9999556 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 07/20/2009 | 07/20/2009 | 11/01/2010 | 849940 | 147.79
6771 | Washington | KING, THURSTON, WHATCOM |  | 08 | 9999557 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 07/20/2009 | 07/20/2009 | 11/01/2010 | 1125234 | 6.009
6772 | Washington | GRANT, KITTITAS |  | 04 | 9999558 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 07/27/2009 | 07/27/2009 | 11/01/2010 | 823200 | 10.62
6773 | Washington | BENTON |  | 04 | A032001 | Reconstruction of Sheridan Avenue from Third Street to Sixth Street including sidewalks, curb and gutter, drainage, and street lighting. | Pavement Improvement | 07/20/2009 |  |  | 474511 | 0.275
6774 | Washington | CHELAN |  | 04 | A045002 | Reconstruct asphalt pavement, increase the vertical clearance at a railroad trestle, and construct a shared-use path through the trestle. | Pavement Improvement | 06/08/2009 |  |  | 1021318 | 0.56
6775 | Washington | CLALLAM |  | 06 | A058001 | Asphalt resurfacing and minor roadway widening to add curb, gutter and sidewalk. | Pavement Improvement | 08/12/2009 |  |  | 160000 | 0.51
6776 | Washington | COWLITZ |  | 03 | A083002 | Asphalt pavement resurfacing, including improvements to the street lighting, sidewalks, crosswalks, and stormwater drainage. | Transportation Enhancements | 09/08/2009 |  |  | 416250 | 0.3
6777 | Washington | LINCOLN |  | 05 | A221003 | Asphalt resurfacing of approximately 4 miles of roadway. | Pavement Improvement | 07/20/2009 |  | 07/30/2009 | 654000 | 4.24
6778 | Washington | SKAMANIA |  | 03 | A301006 | Asphalt pavement resurfacing of approximately 1.0 mile of Wind River Road. | Pavement Improvement | 07/30/2009 |  | 08/06/2009 | 306711 | 0.92
6779 | Washington | WHITMAN |  | 05 | A381004 | Asphalt resurfacing and striping of approximately 5.5 miles of Wawawai Road. | Pavement Improvement | 08/11/2009 |  | 09/04/2009 | 896000 | 5.44
6780 | Washington | YAKIMA |  | 04 | A393001 | Asphalt resurfacing of Harrah Road from South Town Limits to North Town Limits. | Pavement Improvement | 09/14/2009 |  |  | 360000 | 0.625
6781 | Washington | ADAMS |  | 05 | B012002 | Resurface approximately 3.0 miles of roadway with two inches of asphalt. | Pavement Improvement | 07/08/2009 |  | 07/27/2009 | 762232 | 3.03
6782 | Washington | CLARK |  | 03 | B063002 | Asphalt resurfacing of Hillhurst Road between South 15th Circle and South 22nd Circle. | Pavement Improvement | 08/25/2009 |  | 09/18/2009 | 168054 | 0.56
6783 | Washington | COLUMBIA |  | 05 | B074001 | Asphalt resurfacing of East Dayton Avenue from Front Street to US 12. | Pavement Improvement | 08/24/2009 |  | 10/05/2009 | 225000 | 0.25
6784 | Washington | FRANKLIN |  | 04 | B111002 | Relocation of the south 1.1 miles of the R-170 Road outside of the existing roadside slide area. | Pavement Improvement | 09/08/2009 |  |  | 750000 | 1.1
6785 | Washington | PACIFIC |  | 03 | B256007 | Asphalt resurfacing of Sandridge Road from State Route 101 to 67th Place; and install a traffic signal at the intersection of Sandridge Road and Sid Snyder Drive. | Pavement Improvement | 08/03/2009 |  |  | 279396 | 1.62
6786 | Washington | YAKIMA |  | 04 | B391002 | Asphalt resurfacing of South Camas Street, from 3rd Street to 9th Street. | Pavement Improvement | 10/07/2009 |  |  | 312000 | 0.4
6787 | Washington | WAHKIAKUM |  | 03 | C350002 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 12/28/2009 | 200000 | 27.76
6788 | Washington | KITSAP |  | 06 | D185001 | Construction of approximately 1.5 miles of new roadway, intersection improvements, bicycle lanes, and a separated asphalt pedestrian path. | New Construction | 10/12/2009 |  |  | 2623386 | 1.5
6789 | Washington | PEND OREILLE |  | 05 | D261001 | Asphalt resurfacing of Deer Valley Road from Coyote Trail to Gray Road. | Pavement Improvement | 09/14/2009 |  |  | 471000 | 1.17
6790 | Washington | SAN JUAN |  | 02 | D281003 | Asphalt resurfacing of Fisherman Bay Road, and installation of safety fencing. | Pavement Improvement | 08/28/2009 |  | 09/24/2009 | 416620 | 1.76
6791 | Washington | SKAGIT |  | 02 | D291002 | Asphalt resurfacing of Maple Avenue from Morris Street to Caledonia Street, installation of curb ramps. | Pavement Improvement | 08/06/2009 |  | 08/29/2009 | 154800 | 0.502
6792 | Washington | OKANOGAN |  | 05 | F241005 | Asphalt resurfacing of approximately 0.5 miles of Main Street (from south city limits to Lake Street) & East Lake Street (from Main Street east to city limits). | Pavement Improvement | 06/15/2009 |  | 06/19/2009 | 126198 | 0.54
6793 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | H310001 | Asphalt pavement resurfacing on 84th Street NE. | Pavement Improvement | 02/03/2010 |  |  | 504000 | 4.72
6794 | Washington | WHITMAN |  | 05 | I382004 | Asphalt resurfacing of South Main Street from State Route 195 to the Fairview Street and Meadow intersection. | Pavement Improvement | 09/08/2009 |  | 09/21/2009 | 141069 | 0.284
6795 | Washington | MASON |  | 06 | K232001 | Asphalt resurfacing of approximately 1.6 miles of McEwan Prairie Road. | Pavement Improvement | 08/26/2009 |  | 09/04/2009 | 291298 | 1.62
6796 | Washington | THURSTON |  | 09 | K340001 | Widen and provide an asphalt overlay of Minnesota Street, construct sidewalks and crosswalks, and update traffic signs. | Pavement Improvement | 08/25/2009 |  |  | 729437 | 0.3
6797 | Washington | KLICKITAT |  | 04 | L201003 | Asphalt resurfacing of approximately 2.4 miles of South Columbus Street. | Pavement Improvement | 09/04/2009 |  |  | 521656 | 2.39
6798 | Washington | KLICKITAT |  | 04 | M201002 | Asphalt resurfacing of approximately 1.6 miles of Bickleton Highway. | Pavement Improvement | 09/04/2009 |  |  | 255000 | 1.58
6799 | Washington | GRANT |  | 04 | P130002 | Construction of a new concrete bridge. | Bridge Replacement | 11/16/2009 |  |  | 750000 | 0.12
6800 | Washington | GRANT |  | 04 | P137001 | Asphalt resurfacing of approximately 2.0 miles of L-NE Road from Kittleson to 3-NE Road. | Pavement Improvement | 07/06/2009 |  | 07/28/2009 | 487009 | 2.01
6801 | Washington | WHATCOM |  | 02 | P368001 | Constructs approximately 0.1 miles of new roadway to provide an improved roadway connector between State Route 543 and the commercial and industrial areas. | New Construction | 08/21/2009 |  |  | 348000 | 0.133
6802 | Washington | JEFFERSON |  | 06 | Q161007 | Asphalt resurfacing of approximately 2.0 miles of Center Road. | Pavement Improvement | 07/20/2009 |  | 08/07/2009 | 358000 | 2
6803 | Washington | WHATCOM |  | 02 | T371008 | Replace the existing bridge on Hannegan Road over Scott Ditch, south of Lynden, Washington. | Bridge Replacement | 08/03/2009 |  |  | 600000 | 0.05
6804 | Washington | COWLITZ |  | 03 | X085001 | Reconstruct roadway to include curb, gutter and sidewalk. Includes channelization improvements to the existing intersection with State Route 504. | Pavement Widening | 07/14/2009 |  |  | 330000 | 0.73
6805 | Washington | LEWIS |  | 03 | Y210001 | Reconstruction and asphalt resurfacing of approximately 2.3 miles of Davis Lake Road. | Pavement Improvement | 07/09/2009 |  | 09/15/2009 | 1027000 | 2.29
6806 | Washington | SPOKANE |  | 05 | Y329008 | Reconstruction of Crawford Avenue, including the installation of a roundabout, curb and gutter, sidewalk, and stormwater drainage system. | Pavement Improvement | 05/11/2009 |  | 09/15/2009 | 1674431 | 0.61
6807 | Washington | YAKIMA |  | 04 | Z939004 | Asphalt resurfacing of 2nd Street and 3rd Street. Includes replacement of substandard curb, gutter, and sidewalk along 2nd Street, 3rd Street, and Canal Street. | Pavement Improvement | 08/17/2009 |  | 09/24/2009 | 326000 | 0.227
6808 | West Virginia | PLEASANTS |  | 1 | 0002474 | This project will improve safety for motorists by resurfacing 2.72 miles of West Virginia 2 from the City of Waverly to Willow Island Road in Pleasants County. | Pavement Improvement | 04/21/2009 | 05/27/2009 | 10/30/2009 | 906900 | 2.72
6809 | West Virginia | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 0002483 | This project will improve safety for motorists by resurfacing 1.31 miles of deteriorated pavement on West Virginia Route 2 from the City of Weirton to Kings Creek Road. | Pavement Improvement | 12/01/2009 |  | 06/30/2010 | 504700 | 1.31
6810 | West Virginia | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 0002484 | This project will improve safety for motorists by resurfacing 1.55 miles of deteriorated pavement on West Virginia Route 2 from the City of New Cumberland to Moscow Road. | Pavement Improvement | 12/01/2009 |  | 06/30/2010 | 395223 | 1.55
6811 | West Virginia | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 0002487 | This project will extend the life of the historic Market Street Bridge by repairing bridge components, replacing the lighting and light fixtures on the bridge, cleaning the structure and repainting it | Bridge Improvement | 12/10/2009 |  | 11/30/2011 | 10594435 | 0.01
6812 | West Virginia | MONROE |  | 3 | 0003216 | This project will improve safety for motorists by resurfacing the deck of the Alderson Bridge with Latex Modified Concrete. The bridge is located on West Virginia Route 3 at approximately milepoint 0. | Bridge Improvement | 05/12/2009 | 08/31/2009 | 10/30/2009 | 582200 | 0.17
6813 | West Virginia | BOONE |  | 3 | 0003217 | This project will improve safety for motorists by resurfacing 1.67 miles of deteriorated pavement and replace the existing guardrails on West Virginia Route 3 from the Big Coal River Bridge to West Vi | Pavement Improvement | 04/28/2009 | 05/05/2009 | 10/30/2009 | 664200 | 1.67
6814 | West Virginia | MERCER |  | 3 | 0003218 | This project will extend the life of two bridges, the County Route 3 Turnpike Overpass Bridge and the Camp Creek Overpass Bridge #2, by cleaning the structures and then painting them. The bridges are | Bridge Improvement | 07/21/2009 | 07/25/2009 | 10/15/2009 | 416100 | 0.07
6815 | West Virginia | TAYLOR |  | 1 | 0003221 | This project will improve safety for motorists by replacing the Berry Run Bridge due to condition. The bridge is located on County Route 3 at approximately milepoint 0.16 in Taylor County. | Bridge Replacement | 01/11/2010 | 01/11/2010 | 07/30/2010 | 400600 | 0.01
6816 | West Virginia | RALEIGH |  | 3 | 0003222 | This project will improve safety for motorists by the installation of piling for embankment stabilization on West Virginia Route 3 (Metalton Road) at approximately milepoint 29.13 in Raleigh County. | Pavement Improvement | 04/20/2009 | 04/20/2009 | 10/30/2009 | 339600 | 0.01
6817 | West Virginia | HARRISON |  | 1 | 0005119 | This project will improve safety for motorists by replacing the Big Arch Bridge due to condition. The bridge is located on County Route 5 at approximately milepoint 2.46 in Harrison County. | Bridge Replacement | 11/13/2009 |  | 06/30/2010 | 539800 | 0.01
6818 | West Virginia | TAYLOR |  | 1 | 0007219 | This project will improve safety for motorists by replacing the Irontown Girder Bridge due to condition. The bridge is located on County Route 7 at approximately milepoint 3.2 in Taylor County. | Bridge Replacement | 09/21/2009 | 11/11/2009 | 06/30/2010 | 864500 | 0.01
6819 | West Virginia | WIRT |  | 2 | 0007221 | This project will improve safety for motorists by resurfacing 4.36 miles of deteriorated pavement on County Route 7 (Garfield Road) beginning at milepoint 6.10 in Wirt County. | Pavement Improvement | 09/02/2009 | 09/19/2009 | 10/30/2009 | 794200 | 4.36
6820 | West Virginia | PENDLETON |  | 2 | 0009194 | This project will extend the life of the 4-U Bridge by cleaning and painting the structure. The bridge is located on County Route 9 at approximately milepoint 9.24 in Pendleton County. | Bridge Improvement | 06/08/2009 |  | 10/15/2009 | 178800 | 0.01
6821 | West Virginia | JEFFERSON |  | 2 | 0009196 | This project will reduce traffic congestion and improve access to the area by the upgrade of the existing West Virginia Route 9 to four lanes and the construction of a new bridge. The project is locat | Pavement Widening | 09/22/2009 | 09/22/2009 | 05/31/2011 | 18743700 | 0.27
6822 | West Virginia | HARRISON |  | 1 | 0009197 | This project will improve safety for motorists by replacing the West Robey Arch Bridge due to condition. The bridge is located on County Route 9 at approximately milepoint 6.75 in Harrison County. | Bridge Replacement | 11/12/2009 | 11/17/2009 | 06/30/2010 | 581700 | 0.01
6823 | West Virginia | BARBOUR |  | 1 | 0011124 | This project will improve safety for motorists by resurfacing 4.46 miles of deteriorated pavement on County Route 11 (Audra Park Road) in Barbour County. | Pavement Improvement | 09/09/2009 | 09/09/2009 | 10/30/2009 | 556100 | 4.46
6824 | West Virginia | PENDLETON |  | 2 | 0012048 | This project will improve safety for motorists by replacing the Deer Run Park Bridge due to condition. The bridge is located on County Route 12 at approximately milepoint 4.15 in Pendleton County. | Bridge Replacement | 10/13/2009 |  | 06/10/2010 | 434200 | 0.01
6825 | West Virginia | TYLER |  | 1 | 0013056 | This project will improve safety for motorists by replacing the Walnut Fork Bridge due to condition. The bridge is located on County Route 13 at approximately milepoint 6.06 in Tyler County. | Bridge Replacement | 08/05/2009 |  | 07/30/2010 | 560400 | 0.01
6826 | West Virginia | KANAWHA |  | 2 | 0015078 | This project will improve safety for motorists by replacing the Middle Fork Bridges due to condition. The bridges are located on County Route 15 at approximately milepoint 13.71 in Kanawha County. | Bridge Replacement | 09/18/2009 |  | 06/30/2010 | 793700 | 0.01
6827 | West Virginia | DODDRIDGE |  | 1 | 0015079 | This project will improve safety for motorists by replacing Long Run Bridge due to condition. The bridge is located on County Route 15 at approximately milepoint 2.18 in Doddridge County. | Bridge Replacement | 10/09/2009 | 11/02/2009 | 06/30/2010 | 751200 | 0.01
6828 | West Virginia | RITCHIE |  | 1 | 0016205 | This project will improve safety for motorists by resurfacing 3.26 miles of deteriorated pavement on West Virginia 16 from the City of Washburn to Harrisville Road in Ritchie County. | Pavement Improvement | 06/18/2009 | 07/11/2009 | 07/30/2009 | 812500 | 3.26
6829 | West Virginia | CALHOUN |  | 2 | 0016206 | This project will improve safety for motorists by resurfacing 1.31 miles of deteriorated pavement on West Virginia Route 16 from the City of Grantsville to Smithville Road. | Pavement Improvement | 07/01/2009 | 07/01/2009 | 09/11/2009 | 381700 | 1.31
6830 | West Virginia | RALEIGH |  | 3 | 0016207 | This project will improve safety for motorists by resurfacing 0.47 miles of West Virginia Route 16 from South Oakwood Avenue to Bus Station Road in Beckley, Raleigh County. | Pavement Improvement | 07/10/2009 | 07/20/2009 | 10/30/2009 | 538900 | 0.47
6831 | West Virginia | WETZEL |  | 1 | 0017086 | This project will improve safety for motorists by replacing the McBee Bridge due to condition. The bridge is located on County Route 17 at approximately milepoint 3.68 in Wetzel County. | Bridge Replacement | 12/16/2009 | 12/16/2009 | 07/30/2010 | 473200 | 0.01
6832 | West Virginia | TYLER |  | 1 | 0018119 | This project will improve safety for motorists by the installation of piling for embankment stabilization at five locations beginning at milepoint 11.12 and extending 0.50 miles on West Virginia 18 in | Pavement Improvement | 12/01/2009 |  | 07/30/2010 | 1004300 | 0.5
6833 | West Virginia | NICHOLAS |  | 3 | 0019338 | This project will improve safety for motorists by resurfacing 1.94 miles of United States Route 19 from the City of Fockler Branch to Muddlety Road in Nicholas County. | Pavement Improvement | 07/07/2009 | 07/07/2009 | 10/30/2009 | 1532400 | 1.94
6834 | West Virginia | LEWIS |  | 2 | 0019339 | This project will improve safety for motorists by resurfacing 1.89 miles of deteriorated pavement on United States Route 19 in the City of Weston, Lewis County. | Pavement Improvement | 05/22/2009 | 06/29/2009 | 10/30/2009 | 342700 | 1.89
6835 | West Virginia | RALEIGH |  | 3 | 0019340 | This project will help eliminate congestion by the relocation and upgrade to four lanes of United States Route 19 beginning at approximately milepoint 15.52 and bridge improvements ending at the South | New Construction | 08/20/2009 | 09/18/2009 | 08/30/2011 | 22190000 | 0.89
6836 | West Virginia | RALEIGH |  | 3 | 0019343 | This project will improve safety for motorists by resurfacing 0.50 miles of deteriorated pavement on United States Route 19 from the City of Prosperity to the Crossroads Mall in Raleigh County. | Pavement Improvement | 09/04/2009 | 10/01/2009 | 10/30/2009 | 412400 | 0.5
6837 | West Virginia | NICHOLAS |  | 3 | 0020254 | This project will improve safety for motorists by replacing the existing and failing piling currently restricting slippage of the embankment on West Virginia Route 20 at approximately milepoint 26.75 | Pavement Improvement | 09/01/2009 | 09/01/2009 | 10/30/2009 | 224500 | 0.01
6838 | West Virginia | UPSHUR |  | 2 | 0020255 | This project will improve safety for motorists by resurfacing 2.02 miles of West Virginia 20 From the City of French Creek to Adrian Road in Upshur County. | Pavement Improvement | 07/06/2009 | 07/06/2009 | 10/30/2009 | 303578 | 2.02
6839 | West Virginia | GREENBRIER |  | 3 | 0020256 | This project will improve safety for motorists by the construction of a 1.23 mile long truck climbing lane on West Virginia Route 20 in Greenbrier County. | Pavement Widening | 11/25/2009 | 12/10/2009 | 06/30/2010 | 2296600 | 1.23
6840 | West Virginia | MASON |  | 2 | 0029022 | This project will improve safety for motorists by replacing the Arlee Slab Bridge due to condition. The bridge is located on County Route 29 at approximately milepoint 5.59 in Mason County. | Bridge Replacement | 07/31/2009 | 11/10/2009 | 10/15/2009 | 331000 | 0.01
6841 | West Virginia | PENDLETON |  | 2 | 0033320 | This project will improve safety for motorists by resurfacing the deck of the Judy Gap Bridge with Latex Modified Concrete. The bridge is located on United States Route 33 at approximately milepoint 1 | Bridge Improvement | 11/16/2009 |  | 06/30/2010 | 336700 | 0.05
6842 | West Virginia | UPSHUR |  | 2 | 0033321 | This project will improve safety for motorists by resurfacing 4.53 miles of United States Route 33 from the City of Buckhannon to Elkins Road in Upshur County. | Pavement Improvement | 07/06/2009 | 07/06/2009 | 10/30/2009 | 1566500 | 4.53
6843 | West Virginia | JACKSON |  | 2 | 0033322 | This project will improve safety for motorists by resurfacing 4.16 miles of deteriorated pavement on United States Route 33 from the City of Ripley to Frozencamp Road. | Pavement Improvement | 07/01/2009 | 07/11/2009 | 09/01/2009 | 1245100 | 4.16
6844 | West Virginia | PENDLETON |  | 2 | 0033327 | This project will improve safety for motorists by replacing the Rough Run Bridge due to condition. The bridge is located on County Route 3/3 at approximately milepoint 0.73 in Pendleton County. | Bridge Replacement | 10/29/2009 |  | 06/30/2010 | 524600 | 0.01
6845 | West Virginia | RALEIGH |  | 3 | 0034067 | This project will improve safety for motorists by replacing the Horse Creek Bridge #5 due to condition. The bridge is located on County Route 3/4 at approximately milepoint 2.12 in Raleigh County. | Bridge Replacement | 09/16/2009 | 09/17/2009 | 06/30/2010 | 479600 | 0.009
6846 | West Virginia | WAYNE | HUNTINGTON-ASHLAND (KY-OH) | 3 | 0037028 | This project will improve safety for motorists by the installation of piling for embankment stabilization on West Virginia Route 37 at milepoint 18.64 in Wayne County. | Pavement Improvement | 11/12/2009 | 12/01/2009 | 06/30/2010 | 184200 | 0.03
6847 | West Virginia | NICHOLAS |  | 3 | 0039406 | This project will improve safety for motorists by resurfacing 1.29 miles of deteriorated pavement on West Virginia 39 (Deer Creek Road) beginning at approximately milepoint 35.12 in Nicholas County. | Pavement Improvement | 05/29/2009 | 06/26/2009 | 10/30/2009 | 440000 | 1.29
6848 | West Virginia | NICHOLAS |  | 3 | 0041072 | This project will improve safety for motorists by resurfacing 2.10 miles of deteriorated pavement on West Virginia 41 from the City of Glade Creek to Nile Road. | Pavement Improvement | 10/14/2009 | 10/30/2009 | 05/30/2010 | 596600 | 2.01
6849 | West Virginia | RITCHIE |  | 1 | 0050276 | This project will improve safety for motorists by resurfacing 2.18 miles of deteriorated pavement on United States Route 50 beginning at approximately milepoint 26.98 in Ritchie County. | Pavement Improvement | 04/21/2009 | 06/28/2009 | 09/22/2009 | 1069900 | 2.18
6850 | West Virginia | RITCHIE |  | 1 | 0050277 | This project will improve safety for motorists by resurfacing 2.23 miles of deteriorated pavement on United States Route 50 beginning at approximately milepoint 31.65 in Ritchie County. | Pavement Improvement | 04/21/2009 | 07/04/2009 | 09/08/2009 | 1041700 | 2.23
6851 | West Virginia | HAMPSHIRE |  | 2 | 0050278 | This project will improve safety for motorists by resurfacing 0.86 miles and the construction of a center turning lane on United States Route 50 at approximately milepoint 8.50. | Pavement Improvement | 08/31/2009 | 09/10/2009 | 06/30/2010 | 3861400 | 1.58
6852 | West Virginia | TAYLOR |  | 1 | 0050279 | This project will improve safety for motorists by the construction of a 1.90 mile truck climbing lane and the realignment of a hazardous curve on United States Route 50 beginning at milepoint 3.46 in | Pavement Widening | 06/22/2009 | 08/10/2009 | 10/30/2009 | 2439400 | 1.9
6853 | West Virginia | WAYNE |  | 3 | 0052263 | This project will improve safety for motorists by resurfacing 2.29 miles of United States Route 52 from the City of Stonecoal to the Mingo County line in Wayne County. | Pavement Improvement | 07/01/2009 | 07/08/2009 | 10/30/2009 | 1346700 | 2.29
6854 | West Virginia | MERCER |  | 3 | 0052264 | This project will improve safety for motorists by resurfacing 1.50 miles of deteriorated pavement on United States Route 52 from the City of Pinnacle Rock to Lorton Lick Road in Mercer County. | Pavement Improvement | 05/20/2009 | 06/11/2009 | 10/30/2009 | 672800 | 1.5
6855 | West Virginia | WAYNE | HUNTINGTON-ASHLAND (KY-OH) | 3 | 0052265 | This project will improve safety for motorists by resurfacing 5.42 miles of United States Route 52 from West Virginia Route 75 to Whites Creek Road in Wayne County. | Pavement Improvement | 08/17/2009 | 08/24/2009 | 10/30/2009 | 834800 | 6.42
6856 | West Virginia | MERCER |  | 3 | 0052270 | This project will extend the life of the Tunnel Overpass Bridge by cleaning and repainting the structure. The bridge is located on United States Route 52 at approximately milepoint 18.67 in Mercer Cou | Bridge Improvement | 07/21/2009 | 08/24/2009 | 10/15/2009 | 328100 | 0.04
6857 | West Virginia | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 3 | 0052271 | This project will extend the life of the Madison Avenue Overpass Bridge by cleaning the structure and repainting it. The bridge is located at Milepoint 0.73 on West Virginia Route 52 in Cabell County. | Bridge Improvement | 09/16/2009 |  | 10/15/2009 | 180600 | 0.01
6858 | West Virginia | FAYETTE |  | 3 | 0060252 | This project will improve safety for motorists by replacing the existing and failing piling currently restricting slippage of the embankment on US 60 at milepoint 14.60 in Fayette County. | Pavement Improvement | 07/23/2009 | 08/25/2009 | 10/30/2009 | 198500 | 0.01
6859 | West Virginia | FAYETTE |  | 3 | 0061065 | This project will improve safety for motorists by resurfacing 1.24 miles of deteriorated pavement on West Virginia Route 61 from the City of Kincaid to Page Road in Fayette County. | Pavement Improvement | 05/20/2009 | 07/07/2009 | 10/30/2009 | 418300 | 1.24
6860 | West Virginia | FAYETTE |  | 3 | 0061066 | This project will improve safety for motorists by resurfacing 0.95 miles of deteriorated pavement on West Virginia Route 61 (Ingram Branch Road) in Fayette County. | Pavement Improvement | 06/23/2009 | 07/10/2009 | 10/30/2009 | 364500 | 0.95
6861 | West Virginia | RANDOLPH |  | 2 | 0062832 | This project will improve safety for motorists by replacing the Lower Mingo Bridge due to condition. The bridge is located on County Route 62 at approximately milepoint 0.08 in Randolph County. | Bridge Replacement | 10/29/2009 |  | 06/30/2010 | 547300 | 0.01
6862 | West Virginia | PRESTON |  | 1 | 0068135 | This project will improve safety for motorists by resurfacing the deck of the Laurel Run Bridges (West bound & East bound) with Latex Modified Concrete. The bridge is located on Interstate 68 at appro | Bridge Improvement | 12/07/2009 |  | 07/30/2010 | 690500 | 0.01
6863 | West Virginia | MONONGALIA |  | 1 | 0068137 | This project will improve safety for motorists by resurfacing 2.20 miles of deteriorated pavement on Interstate 68 from the City of Pierpont to the West end of the Cheat Lake Bridge in Monongalia Coun | Pavement Improvement | 07/21/2009 | 07/23/2009 | 10/30/2009 | 1312200 | 2.2
6864 | West Virginia | MONONGALIA |  | 1 | 0068139 | This project will extend the life of the Cheat Lake Bridge by cleaning and repainting the structure. The bridge is located on Interstate 68 at approximately milepoint 9.39 in Monongalia County. | Bridge Improvement | 07/06/2009 |  | 10/15/2010 | 6434600 | 0.02
6865 | West Virginia | OHIO | WHEELING (OH) | 1 | 0070158 | This project will improve safety for motorists by replacement of the existing bridge approach slabs, concrete repairs and drainage improvements on Interstate 70 beginning at the West Virginia/Ohio sta | Pavement Improvement | 05/27/2009 | 05/27/2009 | 10/30/2009 | 3065400 | 0.05
6866 | West Virginia | MARSHALL | WHEELING (OH) | 1 | 0074051 | This project will improve safety for motorists by replacing the Shepherd Bridge due to condition. The bridge is located on County Route 74 at approximately milepoint 16.8 in Marshall County. | Bridge Replacement | 05/28/2009 | 05/28/2009 | 05/28/2010 | 1621000 | 0.05
6867 | West Virginia | MCDOWELL |  | 3 | 0080032 | This project will improve safety for motorists by resurfacing 2.00 miles of West Virginia Route 80 from the City of Beartown to Iaeger Road in McDowell County. | Pavement Improvement | 05/01/2009 | 05/15/2009 | 10/30/2009 | 700900 | 2
6868 | West Virginia | KANAWHA | CHARLESTON | 2 | 0094168 | This project will improve safety for motorists by resurfacing 5.52 miles of West Virginia Route 94 beginning at approximately milepoint 1.48 from the City of Hernshaw to the City of Marmet. | Pavement Improvement | 05/01/2009 | 05/11/2009 | 10/30/2009 | 2342400 | 5.52
6869 | West Virginia | GREENBRIER |  | 3 | 0099099 | This project will improve safety for motorists by replacing the Sinking Creek Bridge due to condition. The bridge is located on County Route 9/9 in Greenbrier County. | Bridge Replacement | 09/30/2009 | 12/01/2009 | 06/30/2010 | 252000 | 0.01
6870 | West Virginia | MONONGALIA |  | 1 | 0109013 | This project will help eliminate congestion and help in the movement of motorists and commerce by the construction of 0.14 miles of four lane highway, interstate ramp, a box culvert and construction o | New Construction | 07/21/2009 | 08/12/2009 | 10/29/2010 | 13378800 | 0.14
6871 | West Virginia | LINCOLN |  | 3 | 0119339 | This project will extend the life of the Little Coal River Bridges (North & South) by cleaning and repainting the structure. The bridges are located on United States Route 119 at approximately milepoi | Bridge Improvement | 09/16/2009 | 09/12/2009 | 10/15/2009 | 841200 | 0.039
6872 | West Virginia | KANAWHA | CHARLESTON | 2 | 0119342 | This project will improve safety for motorists by resurfacing 2.54 miles of deteriorated pavement on United States Route 119 beginning approximately at milepoint 39.13. | Pavement Improvement | 09/30/2009 |  | 05/28/2010 | 645600 | 2.54
6873 | West Virginia | MINGO |  | 3 | 0119344 | This project will improve safety for motorists by resurfacing the deck of the West Belo Bridge with Latex Modified Concrete. The bridge is located on United States Route 119 at approximately milepoint | Bridge Improvement | 07/15/2009 | 08/11/2009 | 10/30/2009 | 422300 | 0.05
6874 | West Virginia | GREENBRIER |  | 3 | 0206002 | This project will improve safety for motorists by replacing the Greenbrier Avenue Bridge due to condition. The bridge is located on County Route 20/6 in Rainelle, Greenbrier County. | Bridge Replacement | 07/09/2009 | 07/20/2009 | 11/06/2009 | 493600 | 0.04
6875 | West Virginia | RANDOLPH |  | 2 | 0219299 | This project will improve safety for motorists by replacing the Jones Run Bridge due to condition. The bridge is located on United States Route 219 at approximately milepoint 28.50 in Randolph County. | Bridge Replacement | 07/15/2009 | 08/19/2009 | 09/10/2010 | 922900 | 0.01
6876 | West Virginia | MONROE |  | 3 | 0219300 | This project will improve safety for motorists by resurfacing 2.34 miles of deteriorated pavement on United States Route 219 beginning at approximately milepoint 0.50 in Peterstown, Monroe County. | Pavement Improvement | 05/15/2009 | 05/15/2009 | 10/30/2009 | 917500 | 2.34
6877 | West Virginia | TUCKER |  | 1 | 0219302 | This project will improve safety for motorists by resurfacing 1.20 miles of deteriorated pavement on United States Route 219 from the City of Parsons to Mackeyville Road in Tucker County. | Pavement Improvement | 09/21/2009 | 09/21/2009 | 05/28/2010 | 893700 | 1.2
6878 | West Virginia | RANDOLPH |  | 2 | 0219303 | This project will improve safety for motorists by resurfacing 1.20 miles of deteriorated pavement on United States Route 219, construction of turning lanes and the improvement of drainage from the Cit | Pavement Widening | 07/14/2009 | 07/30/2009 | 10/30/2009 | 1686100 | 1.2
6879 | West Virginia | PENDLETON |  | 2 | 0220182 | This project will improve safety for motorists by the installation of piling on United States Route 220 at approximately milepoint 13.30 between Smith Creek and Franklin Road for embankment stabilizat | Pavement Improvement | 04/13/2009 | 05/21/2009 | 10/30/2009 | 1013800 | 0.18
6880 | West Virginia | MINERAL |  | 1 | 0220183 | This project will improve safety for motorists by resurfacing 0.87 miles of deteriorated pavement on United States Route 220 beginning at approximately milepoint 13.96 in Mineral County. | Pavement Improvement | 07/29/2009 | 08/18/2009 | 10/30/2009 | 1053600 | 0.97
6881 | West Virginia | MONROE |  | 3 | 0238046 | This project will improve safety for motorists by replacing the Indian Creek Bridge due to condition. The bridge is located at approximately milepoint 1.93 on County Route 23/8 in Monroe County. | Bridge Replacement | 11/06/2009 | 11/16/2009 | 06/30/2010 | 706300 | 0.01
6882 | West Virginia | MARSHALL | WHEELING (OH) | 1 | 0250183 | This project will improve safety for motorists by resurfacing the deck of the Bellaire Interchange Bridge with Latex Modified Concrete. The bridge is located on United States Route 250 at approximatel | Bridge Improvement | 07/27/2009 | 10/06/2009 | 06/30/2010 | 580800 | 0.01
6883 | West Virginia | MARSHALL | WHEELING (OH) | 1 | 0250184 | This project will improve safety for motorists by resurfacing 5.44 miles of deteriorated pavement on United States Route 250 in the City of McMechen, Marshall County. | Pavement Improvement | 05/06/2009 | 05/06/2009 | 10/30/2009 | 4584100 | 5.44
6884 | West Virginia | KANAWHA | CHARLESTON | 2 | 0271001 | This project will improve safety for motorists by replacing the Eden's Fork Pony Truss Bridge due to condition. The bridge is located on County Route 27/1 at approximately milepoint 1.1 in Kanawha Cou | Bridge Replacement | 08/14/2009 | 09/18/2009 | 04/06/2010 | 1006700 | 0.03
6885 | West Virginia | MERCER |  | 3 | 0385005 | This project will improve safety for motorists by replacing the Jug Neck Bridge due to condition. The bridge is located on County Route 38/5 at approximately milepoint 0.85 in Mercer County. | Bridge Replacement | 07/24/2009 | 08/04/2009 | 11/06/2009 | 453800 | 0.01
6886 | West Virginia | MERCER |  | 3 | 0385006 | This project will improve safety for motorists by replacing the Blake Bridge due to condition. The bridge is located on County Route 38/5 at approximately milepoint 4.00 in Mercer County. | Bridge Replacement | 08/07/2009 | 08/07/2009 | 11/06/2009 | 468700 | 0.01
6887 | West Virginia | WAYNE |  | 3 | 0411002 | This project will improve safety for motorists by replacing the Turkey Creek Pony Truss Bridge downstream due to condition. The bridge is located on County Route 41/1 at approximately milepoint 0.01 i | Bridge Replacement | 12/11/2009 | 12/07/2009 | 08/31/2010 | 955600 | 0.01
6888 | West Virginia | MERCER |  | 3 | 0460038 | This project will improve safety for motorists by resurfacing the deck of both the East bound and West bound Oakvale Bridges with Latex Modified Concrete. The bridges are located on United States Rout | Bridge Improvement | 06/04/2009 | 06/18/2009 | 10/30/2009 | 936200 | 0.1
6889 | West Virginia | MERCER |  | 3 | 0460039 | This project will improve safety for motorists by resurfacing 1.67 miles of deteriorated pavement on United States Route 460 beginning at approximately milepoint 4.29 in Bluefield, Mercer County. | Pavement Improvement | 04/13/2009 | 04/20/2009 | 07/27/2009 | 1407164 | 1.67
6890 | West Virginia | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 3 | 0641334 | This project will improve safety for motorists by resurfacing 1.59 miles of deteriorated pavement on Interstate 64 from the City of Milton to County Route 60/19. | Pavement Improvement | 06/16/2009 | 06/24/2009 | 10/30/2009 | 1108100 | 1.56
6891 | West Virginia | PUTNAM | HUNTINGTON-ASHLAND (KY-OH) | 2 | 0641335 | This project will improve safety for motorists by resurfacing 4.67 miles of deteriorated pavement on Interstate 64 from the Hurricane Interchange to the Winfield Interchange in Putnam County. | Pavement Improvement | 10/02/2009 | 10/12/2009 | 06/15/2010 | 8292800 | 4.67
6892 | West Virginia | GREENBRIER |  | 3 | 0644170 | This project will extend the life of the Mountain Avenue Bridges (North & South) by cleaning the structure and repainting it. The bridges are located at approximately milepoint 179.36 of Interstate 64 | Bridge Improvement | 08/26/2009 | 09/16/2009 | 10/30/2009 | 701000 | 0.179
6893 | West Virginia | GREENBRIER |  | 3 | 0644171 | This project will improve safety for motorists by resurfacing 1.50 miles of deteriorated pavement on Interstate 64 at approximately milepoint 174.61 in Greenbrier County. | Pavement Improvement | 05/15/2009 |  | 10/30/2009 | 2748900 | 1.5
6894 | West Virginia | GREENBRIER |  | 3 | 0644172 | This project will improve safety for motorists by resurfacing 1.00 miles of deteriorated pavement on Interstate 64 at approximately milepoint 160.00 in Greenbrier County. | Pavement Improvement | 05/15/2009 | 05/27/2009 | 10/30/2009 | 1645900 | 1
6895 | West Virginia | MONONGALIA |  | 1 | 0705011 | This project will improve safety for motorists by resurfacing 1.00 miles of deteriorated pavement on West Virginia Route 705 beginning approximately at milepoint 2.55 in Morgantown, Monongalia County. | Pavement Improvement | 09/09/2009 | 09/14/2009 | 05/28/2010 | 1957100 | 1
6896 | West Virginia | WOOD | PARKERSBURG (OH) | 1 | 0773399 | This project will improve safety for motorists by resurfacing the deck of four bridges, the County Route 25 Overpass Bridges (North & South), Wolf Run Overpass and the Buck Run Overpass with Latex Mod | Bridge Improvement | 07/27/2009 | 07/27/2009 | 05/28/2010 | 1289900 | 0.01
6897 | West Virginia | WOOD | PARKERSBURG (OH) | 1 | 0773402 | This project will improve safety for motorists by resurfacing the deck of five bridges, the I-77/US 50 Interchange Bridge, Worthington Creek Bridge, West Virginia 31 Overpass Bridge and the Williamsto | Bridge Improvement | 07/27/2009 | 07/27/2009 | 06/18/2010 | 1232000 | 9.45
6898 | West Virginia | LEWIS |  | 2 | 0792156 | This project will improve safety for motorists by resurfacing two bridges, Stone Coal Creek Bridge and the County Route 14 Overpass Bridge, on Interstate 79 in Lewis County. | Bridge Improvement | 08/05/2009 |  | 10/30/2009 | 1221199 | 0.109
6899 | West Virginia | BRAXTON |  | 2 | 0792158 | This project will improve safety for motorists by resurfacing the deck of three bridges, the Little Kanawha River Bridge and the Oil Creek Bridges (North & South) on Interstate 79 in Braxton County.,w | Bridge Improvement | 08/05/2009 |  | 01/28/2010 | 2206800 | 0.439
6900 | West Virginia | BRAXTON |  | 2 | 0792161 | This project will extend the life of the Kenton Meadows Senior Bridges (North & South) by cleaning the structures and repainting them. The bridges are located on Interstate 79 at approximately milepoi | Bridge Improvement | 09/16/2009 |  | 10/15/2009 | 1234000 | 0.28
6901 | West Virginia | ROANE |  | 2 | 0792162 | This project will extend the life of the Amma/Big Sandy Bridges (North & South) by cleaning and painting the structures. The bridges are located on Interstate 79 at approximately milepoint 25.79 in Ro | Bridge Improvement | 06/29/2009 | 07/22/2009 | 09/18/2009 | 1045600 | 0.18
6902 | West Virginia | BRAXTON |  | 2 | 0792164 | This project will improve safety for motorists by resurfacing 6.99 miles of detiorated pavement, installation of raised pavement markers, guardrail repair/replacement and shoulder pavement/reconstruct | Pavement Improvement | 07/13/2009 | 07/27/2009 | 10/30/2009 | 3287300 | 6.99
6903 | West Virginia | BRAXTON |  | 2 | 0792167 | This project will extend the life of the Saltlick Creek Bridges (North & South) by cleaning the structures and repainting them. The bridges are located on Interstate 79 at approximately milepoint 78.1 | Bridge Improvement | 09/16/2009 | 09/18/2009 | 10/15/2010 | 711900 | 0.119
6904 | West Virginia | ROANE |  | 2 | 0792168 | This project will improve Safety for motorists by resurfacing 4.49 miles of deteriorated pavement on Interstate 79 between the City of Amma and Wallback Road in Roane County. | Pavement Improvement | 05/11/2009 | 06/08/2009 | 10/30/2009 | 3069900 | 4.49
6905 | West Virginia | MONONGALIA |  | 1 | 0793222 | This project will improve safety for motorists by resurfacing the deck of the Westover Bridge with Latex Modified Concrete. The bridge is located on Interstate 79 at approximately milepoint 152.53 in | Bridge Improvement | 10/13/2009 |  | 06/30/2010 | 1037400 | 0.48
6906 | West Virginia | MARION |  | 1 | 0793223 | This project will improve safety for motorists by resurfacing 2.19 miles of deteriorated pavement on Interstate 79 beginning at approximately milepoint 136.68 in Fairmont, Marion County. | Pavement Improvement | 04/16/2009 | 04/17/2009 | 10/30/2009 | 1299900 | 2.19
6907 | West Virginia | BERKELEY | HAGERSTOWN | 2 | 0811104 | This project will improve safety for motorists by resurfacing 4.65 miles of deteriorated pavement on Interstate 81 from Falling Waters to the Maryland/West Virginia State line. | Pavement Improvement | 07/01/2009 | 07/12/2009 | 10/30/2009 | 2439900 | 4.65
6908 | West Virginia | BERKELEY | HAGERSTOWN | 2 | 0811105 | This project will improve safety for motorists by resurfacing 4.27 miles of deteriorated pavement on Interstate 81 from the Virginia/West Virginia State Line to Inwood Road. | Pavement Improvement | 07/01/2009 | 08/11/2009 | 10/30/2009 | 1827700 | 4.27
6909 | West Virginia | LEWIS |  | 2 | 1191007 | This project will improve safety for motorists by replacing the Sleeths Run Truss Bridge due to condition. The bridge is located at approximately milepoint 0.09 in Lewis County. | Bridge Replacement | 07/17/2009 | 07/30/2009 | 08/30/2010 | 1334700 | 0.02
6910 | West Virginia | FAYETTE |  | 3 | 1601001 | This project will improve safety for motorists by replacing the Michigan Avenue Bridge due to condition. The bridge is located at approximately milepoint 0.01 of County Route 160/17 in Fayette County. | Bridge Replacement | 08/21/2009 | 08/21/2009 | 04/06/2010 | 688400 | 0.01
6911 | West Virginia | MCDOWELL |  | 3 | 1659001 | This project will improve safety for motorists by replacing the South Roselawn Street Bridge on County Route 16/59 at approximately milepoint 0.01 in McDowell County. | Bridge Replacement | 11/02/2009 |  | 05/28/2010 | 462200 | 0.001
6912 | West Virginia | NICHOLAS |  | 3 | 1919002 | This project will improve safety for motorists by replacing the Peters Creek Bridge due to condition. The bridge is located on County Route 19/19 at approximately milepoint 0.03 in Nicholas County. | Bridge Replacement | 08/27/2009 |  | 11/30/2010 | 476700 | 0.001
6913 | Wisconsin | PORTAGE |  | 7 | 2009242 | This is a bridge replacement project in Portage County on a town road, County Highwy P - Cemetery Road. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 600094.25 | 0.076
6914 | Wisconsin | WOOD |  | 7 | 2009244 | This is a bridge replacement project in Wood County on County Highway K, Branch of Mill Creek Crossing. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 333166.61 | 0.057
6915 | Wisconsin | PRICE |  | 7 | 2009245 | This is a bridge replacement project in Price County on a town road, Holmes Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 321338.95 | 0.086
6916 | Wisconsin | PRICE |  | 7 | 2009246 | This is a bridge replacement project in Price County on a town road, Douglas Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 193456.06 | 0.062
6917 | Wisconsin | TAYLOR |  | 7 | 2009254 | This is a bridge replacement project in Taylor County on County Highway D, Mondeaux River Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 538764.35 | 0
6918 | Wisconsin | JEFFERSON |  | 5 | 2009366 | This is a reconstruction project in Jefferson County on State Highway 59, Village of Palmyra, Maple Street. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 1343575.52 | 0.85
6919 | Wisconsin | JEFFERSON |  | 2,5 | 2009367 | This is a restoration and rehabilitation project in Jefferson County on State Highway 59, Whitewater - Palmyra Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 2202046.04 | 7.45
6920 | Wisconsin | DANE | MADISON | 2 | 2009368 | This is a bridge rehabilitation project in Dane County on US Highway 151, Sun Prairie Bypass. | Bridge Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 524210.55 | 0.02
6921 | Wisconsin | ROCK |  | 2 | 2009369 | This is a reconstruction project in Rock County on State Highway 11, Footville - Janesville Bypass. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 3222941.36 | 5.6
6922 | Wisconsin | VERNON |  | 3 | 2009370 | This is a restoration and rehabilitation project in Vernon County on State Highway 82, LaFarge and Otter Creek Bridges. | Pavement Improvement | 05/15/2009 | 05/15/2009 | 10/01/2009 | 890878.8 | 0.231
6923 | Wisconsin | SAUK |  | 2 | 2009371 | This is a bridge rehabilitation project in Sauk County on US Highway 12, Lake Delton, Dell Creek Bridge and approaches. | Bridge Improvement | 05/15/2009 | 05/15/2009 | 06/01/2010 | 3038220.19 | 0.133
6924 | Wisconsin | RACINE |  | 1 | 2009372 | This is a reconstruction project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 08/01/2010 | 4626581.72 | 0.61
6925 | Wisconsin | RACINE |  | 1 | 2009373 | This is a reconstruction project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 08/01/2010 | 6124945.95 | 0.61
6926 | Wisconsin | RACINE |  | 1 | 2009374 | This is a reconstruction with additional lanes project in Racine County on Interstate 94, North South Freeway, County Highway G Interchange. | Pavement Widening | 03/30/2009 | 03/30/2009 | 08/01/2010 | 10839551.47 | 0.61
6927 | Wisconsin | RACINE |  | 1 | 2009375 | This is a fencing project in Racine County on Interstate 94. | Other | 03/30/2009 | 03/30/2009 | 03/31/2010 | 95401.9 | 0.61
6928 | Wisconsin | KENOSHA |  | 1 | 2009376 | This is a reconstruction with additional lanes project in Kenosha County on Interstate 94, North-South Freeway, County Highway C Interchange, mainline and ramps. | Pavement Widening | 03/30/2009 | 03/30/2009 | 12/01/2010 | 27023140.6 | 0.54
6929 | Wisconsin | KENOSHA |  | 1 | 2009377 | This is a reconstruction with additional lanes project in Kenosha County on Interstatet 94, North - South Freeway, Illinois State Line to County Highway C, mainline. | Pavement Widening | 03/30/2009 | 03/30/2009 | 12/01/2010 | 34193016.87 | 3.3
6930 | Wisconsin | KENOSHA |  | 1 | 2009378 | This is a bridge replacement with added lanes project in Kenosha County on Interstate 94, North South Freeway, County Highway C to State Highway 50, mainline. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 12/01/2010 | 5007480.82 | 0.66
6931 | Wisconsin | WAUPACA |  | 8 | 2009379 | This is a project in Waupaca County on State Highway 49, City of Waupaca. | Safety/Traffic Management | 03/30/2009 | 03/30/2009 | 09/01/2009 | 164374.87 | 0.095
6932 | Wisconsin | LINCOLN |  | 7 | 2009380 | This is a bridge rehabilitation project in Lincoln County on US Highway 51, Merrill - Tomahawk. | Bridge Improvement | 03/30/2009 | 03/30/2009 | 12/01/2009 | 1182735.39 | 0.8
6933 | Wisconsin | WOOD |  | 7 | 2009381 | This is a resurfacing project in Wood County on State Highway 13, Pittsville - Marshfield. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 12/30/2009 | 818600.13 | 2.538
6934 | Wisconsin | MARATHON |  | 7 | 2009382 | This is a resurfacing project in Marathon County on State Highway 153, Mosinee, Crooked Lake Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 06/01/2009 | 904349.76 | 6.228
6935 | Wisconsin | LANGLADE |  | 8 | 2009383 | This is a restoration and rehabilitation project in Langlade County on State Highway 52, Lily, Forest County Line. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 979725.21 | 5.54
6936 | Wisconsin | ST CROIX |  | 3 | 2009384 | This is a resurfacing project in St. Croix County on State Highway 64, New Richmond, Connorsville Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 3907157.55 | 7.21
6937 | Wisconsin | ST CROIX |  | 3 | 2009385 | This is a project in St. Croix County on State Highway 64, New Richmond, Connorsville Road. | Safety/Traffic Management | 03/30/2009 | 03/30/2009 | 10/01/2009 | 505495.91 | 0.09
6938 | Wisconsin | POLK |  | 7 | 2009386 | This is a resurfacing project in Polk County on US Highway 8, St. Croix Falls - Turtle Lake. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 3225447.52 | 9.27
6939 | Wisconsin | BURNETT |  | 7 | 2009387 | This is a resurfacing project in Burnett County on State Highway 70, Siren - Spooner. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 3196143.72 | 12.05
6940 | Wisconsin | DUNN |  | 3 | 2009388 | This is a restoration and rehabilitation project in Dunn County on State Highway 25, Menomonie - Wheeler Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 2274559.1 | 5.78
6941 | Wisconsin | DUNN |  | 3 | 2009389 | This is a resurfacing project in Dunn County on State Highway 64, New Richmond - Bloomer. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 1718368.73 | 6.48
6942 | Wisconsin | DANE |  | 2 | 2009390 | This is a reconstruction project in Dane County on County Highway B, Village of Rockdale. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 05/01/2010 | 972530.98 | 0.8
6943 | Wisconsin | LAFAYETTE |  | 3 | 2009391 | This is a bridge replacement project in Lafayette County on County Highway H, Fever River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 643416.39 | 0.145
6944 | Wisconsin | CRAWFORD |  | 3 | 2009392 | This is a reconstruction project in Crawford County on a town road, Rush Creek Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 436610.67 | 0.1
6945 | Wisconsin | SAUK |  | 3 | 2009393 | This is a bridge replacement project in Sauk County on County Highway G, Baraboo River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 905734.22 | 0.28
6946 | Wisconsin | WAUKESHA | MILWAUKEE | 1 | 2009394 | This is a bridge rehabilitation with added lanes project in Waukesha County on local streets, Valentine Road, Bridge over Oconomowoc River. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 228238.14 | 0
6947 | Wisconsin | WASHINGTON |  | 5 | 2009395 | This is a bridge replacement project in Washington County on County Highway W, bridge over Rock River. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 462426.06 | 0
6948 | Wisconsin | MANITOWOC |  | 6 | 2009396 | This is a reconstruction project in Manitowoc County on a town road, Newton Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 272330.66 | 0.66
6949 | Wisconsin | MANITOWOC |  | 6 | 2009397 | This is a reconstruction project in Manitowoc County on a town road, Valley Drive Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 199108.49 | 0
6950 | Wisconsin | MANITOWOC |  | 6 | 2009398 | This is a reconstruction project in Manitowoc County on a town road, South Cleveland Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 221783.43 | 0
6951 | Wisconsin | MANITOWOC |  | 6 | 2009399 | This is a reconstruction project in Manitowoc County on a town road, County line Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 195139.2 | 0
6952 | Wisconsin | FOND DU LAC |  | 6 | 2009400 | This is a bridge replacement project in Fond du Lac County on a town road, Youth Camp Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 410865.84 | 0
6953 | Wisconsin | IRON |  | 7 | 2009401 | This is a bridge replacement project in Iron County on local streets, Montreal River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 666325.92 | 0.043
6954 | Wisconsin | TREMPEALEAU |  | 3 | 2009402 | This is a bridge replacement project in Trempealeau County on County Highway D, Bruce Valley Creek Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 07/01/2009 | 429733.64 | 0.071
6955 | Wisconsin | BARRON |  | 7 | 2009403 | This is a bridge replacement project in Barron County on a town road, Yellow River Bridge. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 504690.05 | 0.14
6956 | Wisconsin | DOUGLAS |  | 7 | 2009404 | This is a bridge replacement project in Douglas County on local streets, Town of Cloverland, McNeil's Landing Road, Brule River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 387000.5 | 0
6957 | Wisconsin | DOUGLAS |  | 7 | 2009405 | This is a bridge replacement project in Douglas County on a town road, Town of Oakland, Rice Farm Road, Little Amnicon River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 360847.17 | 0
6958 | Wisconsin | TAYLOR |  | 7 | 2009406 | This is a bridge replacement project in Taylor County on local streets, City of Medford, Black River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 657757.63 | 0
6959 | Wisconsin | MONROE |  | 3 | 2009407 | This is a reconstruction project in Monroe County on a town road, Kettle Road, Town of Wilton. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 07/01/2009 | 183311.19 | 0.038
6960 | Wisconsin | LINCOLN |  | 7 | 2009408 | This is a bridge replacement project in Lincoln County on County Highway H, Little Pine Creek Bridge. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 258558.88 | 0.081
6961 | Wisconsin | TAYLOR |  | 7 | 2009409 | This is a resurfacing project in Taylor County on State Highway 64, Medford - Goodrich. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 2338134.15 | 14.293
6962 | Wisconsin | WAUPACA |  | 8 | 2009411 | This is a resurfacing project in Waupaca County on US Highway 45, Winchester - New London. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 585582.05 | 3.515
6963 | Wisconsin | EAU CLAIRE |  | 3 | 2009412 | This is a resurfacing project in Eau Claire County on US Highway 12, Augusta - Fairchild Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 07/01/2009 | 1027265.12 | 9.26
6964 | Wisconsin | DANE |  | 2 | 2009486 | This is a bridge rehabilitation project in Dane County on Interstate 90, Madison - Janesville Road, Drotning Road bridges. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 208970.4 | 0.03
6965 | Wisconsin | DANE |  | 2 | 2009487 | This is a bridge rehabilitation project in Dane County on Interstate 39, Madsion to Janesville Road, County Highway W bridges. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 182316.4 | 0.03
6966 | Wisconsin | DANE |  | 2 | 2009488 | This is a bridge rehabilitation project in Dane County on Interstate 39, Madison - Janesville Road, County Highway B bridges. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 175866.4 | 0.03
6967 | Wisconsin | ROCK |  | 1 | 2009489 | This is a bridge rehabilitation project in Rock County on County Highway A, Blackhawk Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 166702.97 | 0.057
6968 | Wisconsin | DANE | MADISON | 2 | 2009490 | This is a bridge rehabilitation project in Dane County on County Highway N, Edgerton - Stoughton, Yahara River Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 738953.16 | 0.1
6969 | Wisconsin | RICHLAND |  | 3 | 2009491 | This is a bridge replacement project in Richland County on County Highway I, Gault Hollow Creek Bridge. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 11/01/2009 | 446955.73 | 0.15
6970 | Wisconsin | SAUK |  | 3 | 2009492 | This is a bridge rehabilitation project in Sauk County on County Highway PF, Seeley Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 565380.82 | 0.07
6971 | Wisconsin | IOWA |  | 3 | 2009493 | This is a bridge rehabilitation project in Iowa County on a town road, River Road Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 452491.06 | 0.11
6972 | Wisconsin | GRANT |  | 3 | 2009494 | This is a reconstruction project in Grant County on County Highway C, US Highway 18 - Millville Road, Warner Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 559133.53 | 0.09
6973 | Wisconsin | LA CROSSE | LA CROSSE (MN) | 3 | 2009495 | This is a reconstruction project in La Crosse County on local streets, Oak Avenue, Onalaska and LaCrosse. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 1119781.66 | 0.88
6974 | Wisconsin | DANE | MADISON | 2 | 2009496 | This is a pedestrian and bicycle path project in Dane County, Starkweather Creek Bike and Pedestrian Path. | Transportation Enhancements | 04/17/2009 | 04/17/2009 | 05/01/2010 | 2542571.88 | 0
6975 | Wisconsin | DODGE |  | 6 | 2009497 | This is a reconstruction project in Dodge County on County Highway G, Beaver Dam - Randolph. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 08/01/2009 | 1131154.48 | 2.137
6976 | Wisconsin | LA CROSSE | LA CROSSE (MN) | 3 | 2009498 | This is a resurfacing project in La Crosse County on State Highway 16, La Crosse, West Salem and Monegan O'Head. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 723910.16 | 0.08
6977 | Wisconsin | WALWORTH |  | 1 | 2009499 | This is a restoration and rehabilitation project in Walworth County on US Highway 12, State Highway 67 to State Highway 50. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 11/01/2009 | 3939200.72 | 10.81
6978 | Wisconsin | WALWORTH |  | 1 | 2009500 | This is a bridge rehabilitation project in Walworth County on Interstate 43, Rock Freeway. | Pavement Improvement | 04/20/2009 | 04/20/2009 | 11/01/2009 | 3305066 | 26.9
6979 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2009501 | This is a reconstruction project in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2010 | 9469411.63 | 15.9
6980 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2009502 | This is a new roadway construction project of 15.9 milesin Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 04/17/2009 | 04/17/2009 | 07/01/2010 | 4600000 | 15.9
6981 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2009503 | This is a new roadway construction project of 2.07 miles in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 04/17/2009 | 04/17/2009 | 08/01/2010 | 3582652.15 | 2.07
6982 | Wisconsin | MANITOWOC |  | 6 | 2009504 | This is a resurfacing project in Manitowoc County on State Highway 147, Two Rivers - Mishicot. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 1334233.69 | 5.37
6983 | Wisconsin | MANITOWOC |  | 6 | 2009505 | This is a resurfacing project in Manitowoc County on State Highway 147, Mishicot, and Interstate 43. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 1394027.81 | 7.16
6984 | Wisconsin | DOOR |  | 8 | 2009506 | This is a reconstruction project in Door County on local streets, Michigan Street. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 879021.38 | 0.23
6985 | Wisconsin | FOND DU LAC |  | 6 | 2009507 | This is a reconstruction project in Fond du Lac County on a town road, Lake Maria Road Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 219529.54 | 0.03
6986 | Wisconsin | FOND DU LAC |  | 6 | 2009508 | This is a bridge replacement project in Fond du Lac County on a town road, Oak Grove Road Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 280635.24 | 0
6987 | Wisconsin | MARATHON |  | 7 | 2009509 | This is a reconstruction project in Marathon County on Interstate 39, Stevens Point - Wausau. | Pavement Improvement | 04/20/2009 | 04/20/2009 | 07/01/2010 | 8694548.76 | 5.68
6988 | Wisconsin | MARATHON | WAUSAU | 7 | 2009510 | This is a reconstruction project in Marathon County on Interstate 39, Stevens Point - Wausau. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 07/01/2010 | 3190260.9 | 3.44
6989 | Wisconsin | WOOD |  | 7 | 2009511 | This is a resurfacing project in Wood County on State Highway 73, Pittsville - Neilsville. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 08/01/2009 | 1414972.87 | 6.794
6990 | Wisconsin | VILAS |  | 8 | 2009512 | This is a resurfacing project in Vilas County on US Highway 45, Eagle River - Land-o-Lakes. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 2118628.08 | 6.74
6991 | Wisconsin | MARATHON |  | 7 | 2009513 | This is a bridge replacement project in Marathon County on County Highway F, Stoney Creek Crossing. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 08/01/2009 | 417406.51 | 0.1
6992 | Wisconsin | ASHLAND |  | 7 | 2009514 | This is a restoration and rehabilitation project in Ashland County on US Highway 2, Odanah - Saxon, Government Road. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 08/01/2009 | 3261761.13 | 8.72
6993 | Wisconsin | POLK |  | 7 | 2009515 | This is a bridge rehabilitation project in Polk County on US Highway 8, St. Croix Falls - Turtle Lake. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 105650.36 | 0.01
6994 | Wisconsin | TREMPEALEAU |  | 3 | 2009516 | This is a bridge rehabilitation project in Trempealeau County on County Highway G, Pine Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 11/01/2009 | 391209.3 | 0.076
6995 | Wisconsin | JACKSON |  | 3 | 2009517 | This is a reconstruction project in Jackson County on County Highway A, Hixton - Black River Falls. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 2093840.77 | 2.03
6996 | Wisconsin | SAWYER |  | 7 | 2009518 | This is a resurfacing project in Sawyer County on State Highway 77, Ghost Lake - Clam Lake. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 2894786.57 | 9.92
6997 | Wisconsin | TAYLOR |  | 7 | 2009519 | This is a bridge replacement project in Taylor County on County Highway M, Branch River Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 11/01/2009 | 257871.04 | 0
6998 | Wisconsin | WALWORTH |  | 1 | 2009520 | This is a reconstruction project in Walworth County on County Highway C, Stateline Road - Pleasant Street. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 992903.18 | 0.49
6999 | Wisconsin | VILAS |  | 8 | 2009521 | This is a resurfacing project in Vilas County on US Highway 45, Eagle River to Land-o-Lakes. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 3157710.31 | 8.32
7000 | Wisconsin | KENOSHA |  | 1 | 2009523 | This is a reconstruction with additional lanes project in Kenosha County on Interstate 94, North-South Freeway, County Highway C Interchange fencing. | Pavement Widening | 05/14/2009 | 05/14/2009 | 12/01/2010 | 155588.13 | 5.83
7001 | Wisconsin | SHEBOYGAN |  | 6 | 2009524 | This is a bridge rehabilitation project in Sheboygan County on Interstate 43, Milwaukee, Green Bay Road. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 07/01/2010 | 2329511.86 | 17.66
7002 | Wisconsin | SHEBOYGAN | SHEBOYGAN | 6 | 2009525 | This is a resurfacing project in Sheboygan County on Interstate 43, Port Washington - Manitowoc. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 07/01/2010 | 14319091.08 | 10.39
7003 | Wisconsin | DANE | MADISON | 2 | 2009530 | This is a bridge replacement project in Dane County on Interstate 94, Madison - Milwaukee Road. | Pavement Widening | 05/14/2009 | 05/14/2009 | 11/01/2011 | 46925107.6 | 5.2
7004 | Wisconsin | WASHINGTON |  | 5 | 2009531 | This is a resurfacing project in Washington County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 670965.87 | 0.998
7005 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2009532 | This is a reconstruction with additional lanes project in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 05/14/2009 | 05/14/2009 | 10/01/2010 | 17122027.12 | 1.61
7006 | Wisconsin | BROWN |  | 8 | 2009533 | This is a bridge replacement project in Brown County on US Highway 41, Green Bay - Suamico. | Bridge Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 343409.42 | 0.04
7007 | Wisconsin | OCONTO |  | 8 | 2009534 | This is a bridge rehabilitation project in Oconto County on US Highway 41, Suamico - Abrams. | Bridge Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 142873.75 | 0.02
7008 | Wisconsin | MANITOWOC |  | 6 | 2009535 | This is a restoration and rehabilitation project in Manitowoc County on Interstate 43, Denmark, Manitowoc River, CN Railroad. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 07/01/2010 | 8410801 | 8.57
7009 | Wisconsin | BROWN |  | 6, 8 | 2009536 | This is a resurfacing project in Brown County on Interstate 43, US Highway 12 - County Highway M. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 07/01/2010 | 8146435.56 | 7.75
7010 | Wisconsin | FOND DU LAC |  | 6 | 2009537 | This is a resurfacing project in Fond du Lac County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 2181230.34 | 7.98
7011 | Wisconsin | FOND DU LAC |  | 6 | 2009538 | This is a resurfacing project in Fond du Lac County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 2036702.25 | 6.448
7012 | Wisconsin | GREEN LAKE |  | 6 | 2009539 | This is a bridge rehabilitation project in Green Lake County on County Highway A, Grand River Crossing. | Bridge Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 383750.73 | 0.057
7013 | Wisconsin | MARATHON | WAUSAU | 7 | 2009540 | This is a reconstruction project in Marathon County on County Highway NN, Creek Road - Thornapple Road. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/01/2009 | 2041664.43 | 5.63
7014 | Wisconsin | FOREST |  | 8 | 2009541 | This is a restoration and rehabilitation project in Forest County on County Highway W, County Highway Q - US Highway 8. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/01/2009 | 1130738.95 | 3.96
7015 | Wisconsin | MENOMINEE |  | 8 | 2009542 | This is a resurfacing project in Mennominee County on County Highway M, Strawberry Lane. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 4759370.81 | 17.57
7016 | Wisconsin | CLARK |  | 3 | 2009543 | This is a bridge replacement project in Clark County on a town road, Town of Sherwood Ballard Road, Hay Creek Bridge and approaches. | Bridge Replacement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 207542.32 | 0
7017 | Wisconsin | WASHINGTON | MILWAUKEE | 5 | 2009592 | This is a reconstruction with additional lanes project in Washington County on County Highway Q, County Line Road, Pilgrim Road. | Pavement Widening | 05/18/2009 | 05/18/2009 | 10/01/2009 | 3754459.37 | 0.81
7018 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009594 | This is a bridge rehabilitation project in Milwaukee County on local streets, River Road. | Bridge Improvement | 05/18/2009 | 05/18/2009 |  | 295959.76 | 0
7019 | Wisconsin | OUTAGAMIE |  | 8 | 2009609 | This is a bridge replacement project in Outagamie County on a town road, Weyers Road Bridge and approaches. | Bridge Replacement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 677761 | 0
7020 | Wisconsin | GREEN LAKE |  | 6 | 2009610 | This is a resurfacing project in Green Lake County on County Highway A, Markesan - Green Lake. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 09/01/2009 | 1353000 | 3.12
7021 | Wisconsin | MARATHON |  | 7 | 2009611 | This is a bridge replacement project in Marathon County on a town road, Huckleberry Road, Fenwood Creek Crossing. | Bridge Replacement | 05/18/2009 | 05/18/2009 | 11/01/2009 | 243540 | 0.038
7022 | Wisconsin | PORTAGE |  | 7 | 2009612 | This is a resurfacing project in Portage County on County Highway W, Kellner - Bankroft Road. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 3075000 | 11.8
7023 | Wisconsin | WOOD |  | 7 | 2009613 | This is a resurfacing project in Wood County on County Highway A, Pittsville - Marshfield. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 09/01/2009 | 3697562 | 12.42
7024 | Wisconsin | WOOD |  | 7 | 2009614 | This is a reconstruction project in Wood County on a town road, Lincoln Avenue, City of Marshfield. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 06/01/2010 | 1725690 | 0.498
7025 | Wisconsin | LINCOLN |  | 7 | 2009615 | This is a resurfacing project in Lincoln County on County Highway CC, Nick Road to Tannery Road. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 1733070 | 6.127
7026 | Wisconsin | MARATHON |  | 7 | 2009622 | This is a bridge replacement project in Marathon County on a town road, Badger Road Bridge. | Bridge Replacement | 05/18/2009 | 05/18/2009 | 01/01/2010 | 732896 | 0.095
7027 | Wisconsin | CLARK |  | 3 | 2009623 | This is a bridge replacement project in Clark County on County Highway OO, Black River Bridge. | Bridge Replacement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 1476000 | 0
7028 | Wisconsin | ROCK |  | 2 | 2009624 | This is a bridge replacement project in Rock County on County Highway H, Raccoon Creek Bridge. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 488309.99 | 0.19
7029 | Wisconsin | ADAMS |  | 6 | 2009680 | This is a reconstruction project in Adams County on County Highway Z, Town of Strongs Prairie and Monroe. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 04/01/2010 | 5424989 | 6.9
7030 | Wisconsin | MARATHON | WAUSAU | 7 | 2009681 | This is a reconstruction project in Marathon County on local streets, Village of Weston, Ross Avenue. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 12/01/2009 | 2867007 | 2.68
7031 | Wisconsin | MARATHON | WAUSAU | 7 | 2009682 | This is a resurfacing project in Marathon County on local streets, Stewart Avenue - Elm Street. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 10/01/2009 | 730620 | 0.29
7032 | Wisconsin | PORTAGE |  | 7 | 2009683 | This is a resurfacing project in Portage County on County Highway D, Almond. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 11/01/2009 | 1599000 | 5.8
7033 | Wisconsin | FLORENCE |  | 8 | 2009684 | This is a restoration and rehabilitation project in Florence County on County Highway U, Marinette County Line - County Highway N. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 11/01/2009 | 3000000 | 6.1
7034 | Wisconsin | WAUPACA |  | 8 | 2009685 | This is a resurfacing project in Waupaca County on local streets, City of Clintonville, North 12th Street. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 375150 | 0.7
7035 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009686 | This is a reconstruction project in Milwaukee County on local streets, West State Street. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 07/01/2010 | 1638019 | 0.68
7036 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009687 | This is a reconstruction project in Milwaukee County on local streets, West Oklahoma Avenue. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 08/01/2010 | 2200000 | 0.72
7037 | Wisconsin | MONROE |  | 3 | 2009688 | This is a resurfacing project in Monroe County on County Highway O, Warrens. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 1107000 | 2.73
7038 | Wisconsin | ROCK | JANESVILLE | 1 | 2009689 | This is a resurfacing project in Rock County on local streets, City of Janesville, various streets. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 1575630 | 3.194
7039 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009690 | This is a reconstruction project in Milwaukee County on local streets, West Lisbon Avenue. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 06/01/2010 | 2793868 | 0.85
7040 | Wisconsin | BARRON |  | 7 | 2009691 | This is a bridge replacement project in Barron County on a town road, Pokegama Creek Bridge. | Bridge Replacement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 295200 | 0
7041 | Wisconsin | FOND DU LAC |  | 6 | 2009692 | This is a bridge replacement project in Fond du Lac County on local streets, Kiel Road Bridge and approaches. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 392370 | 0
7042 | Wisconsin | WAUPACA |  | 8 | 2009693 | This is a bridge replacement project in Waupaca County on County Highway Q, Waupaca River Crossing. | Bridge Replacement | 06/24/2009 | 06/24/2009 | 01/01/2010 | 1357354 | 0.38
7043 | Wisconsin | TAYLOR |  | 7 | 2009694 | This is a bridge rehabilitation project in Taylor County on County Highway A, Pine Creek Bridge. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 12/30/2009 | 159900 | 0
7044 | Wisconsin | MARINETTE |  | 8 | 2009695 | This is a new roadway construction project of 1.15 miles in Marinette County on County Highway T, Roosevelt Road, City of Marinette. | New Construction | 06/25/2009 | 06/25/2009 | 06/01/2010 | 3382500 | 1.15
7045 | Wisconsin | FOREST |  | 8 | 2009696 | This is a pedestrian and bicycle path project in Forest County, Mole Lake Multi-Use Trail. | Transportation Enhancements | 06/24/2009 | 06/24/2009 | 11/01/2009 | 738000 | 0
7046 | Wisconsin | VILAS |  | 8 | 2009697 | This is a bicycle path project in Vilas County, Trout Lake Bicycle Trail. | Transportation Enhancements | 06/24/2009 | 06/24/2009 | 10/01/2009 | 279379 | 0
7047 | Wisconsin | DANE | MADISON | 2 | 2009866 | This is the design engineering effort for a construction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 62040 | 0.8
7048 | Wisconsin | MILWAUKEE | MILWAUKEE | 1 | 2009867 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 51st Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 5300 | 0
7049 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009868 | This is the design engineering effort for a construction project in Milwaukee County on local streets, West Vliet Street Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 25000 | 0
7050 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009869 | This is the design engineering effort for a construction project in Milwaukee County on local streets, North Sherman Blvd. Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 10600 | 0
7051 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009870 | This is the design engineering effort for a construction project in Milwaukee County on local streets, North Sherman Blvd. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 9100 | 0
7052 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2009871 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 76th Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 12260 | 0
7053 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009872 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 6th Street Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 19025 | 0
7054 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009873 | This is the design engineering effort for a construction project in Waukesha County on County Highway ES, Calhoun Road to County Highway O. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8200 | 0
7055 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009874 | This is the design engineering effort for a construction project in Milwaukee County on local streets, West National Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4800 | 0
7056 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2009875 | This is the design engineering effort for a construction project in Milwaukee County on local streets, Hampton Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 80000 | 0
7057 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009876 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South Cesar Chavez Drive. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 75000 | 0
7058 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009877 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 6th Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4580 | 0
7059 | Wisconsin | MILWAUKEE | MILWAUKEE | 5 | 2009878 | This is the design engineering effort for a construction project in Milwaukee County on local streets, 70th Street Brige. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 15800 | 0
7060 | Wisconsin | OZAUKEE | MILWAUKEE | 5 | 2009879 | This is the design engineering effort for a construction project in Ozaukee County on County Highway O, North Green Bay Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 15600 | 0
7061 | Wisconsin | OZAUKEE | MILWAUKEE | 5 | 2009880 | This is the design engineering effort for a construction project in Ozaukee County on local streets, West Donges Bay Road. | Other | 07/30/2009 | 07/30/2009 | 12/15/2009 | 5000 | 0
7062 | Wisconsin | RACINE | RACINE | 1 | 2009881 | This is the design engineering effort for a construction project in Racine County on local streets, North Main Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 31000 | 0
7063 | Wisconsin | RACINE | RACINE | 1 | 2009882 | This is the design engineering effort for a construction project in Racine County on County Highway C, Spring Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 6122 | 0
7064 | Wisconsin | KENOSHA | KENOSHA | 1 | 2009883 | This is the design engineering effort for a construction project in Kenosha County on local streets, 38th Street Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 16180 | 0
7065 | Wisconsin | RACINE | RACINE | 1 | 2009884 | This is the design engineering effort for a construction project in Racine County on local streets, Lathrop Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 7073 | 0
7066 | Wisconsin | RACINE | RACINE | 1 | 2009885 | This is the design engineering effort for a construction project in Racine County on local streets, Taylor Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 3122 | 0
7067 | Wisconsin | WASHINGTON |  | 5 | 2009886 | This is the design engineering effort for a construction project in Washington County on local streets, Decorah Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 12284 | 0
7068 | Wisconsin | WASHINGTON |  | 5 | 2009887 | This is the design engineering effort for a construction project in Washington County on local streets, 7th Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 1956 | 0
7069 | Wisconsin | WASHINGTON |  | 5 | 2009888 | This is the design engineering effort for a construction project in Washington County on local streets, Indiana Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8316 | 0
7070 | Wisconsin | WASHINGTON |  | 5 | 2009889 | This is the design engineering effort for a construction project in Washington County on local streets, Vine Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 1976 | 0
7071 | Wisconsin | WASHINGTON |  | 5 | 2009890 | This is the design engineering effort for a construction project in Washington County on local streets, Park Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 1730 | 0
7072 | Wisconsin | WASHINGTON |  | 5 | 2009891 | This is the design engineering effort for a construction project in Washington County on local streets, Jefferson Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4096 | 0
7073 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009892 | This is the design engineering effort for a construction project in Waukesha County on local streets, Wisconsin Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 18300 | 0
7074 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009893 | This is the design engineering effort for a construction project in Waukesha County on County Highway O, South Moorland Blvd. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 23250 | 0
7075 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009894 | This is the design engineering effort for a construction project in Waukesha County on County Highway K, North 132nd Street to North 124th Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 17393 | 0
7076 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009895 | This is the design engineering effort for a construction project in Waukesha County on County Highway T, Grandview Blvd.. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4400 | 0
7077 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009896 | This is the design engineering effort for a construction project in Waukesha County on County Highway V, Townline Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 16050 | 0
7078 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009897 | This is the design engineering effort for a construction project in Waukesha County on County Highway Y, Baker Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 20000 | 0
7079 | Wisconsin | MILWAUKEE | MILWAUKEE | 1 | 2009898 | This is the design engineering effort for a construction project in Milwaukee County on County Highway ZZ, West Loomis Road to South 51st Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 18150 | 0
7080 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2009899 | This is the design engineering effort for a construction project in Milwaukee County on local streets, Eastbrook Park Drive. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 16200 | 0
7081 | Wisconsin | WALWORTH |  | 1 | 2009900 | This is the design engineering effort for a construction project in Walworth County on local streets, Wrigley Drive. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 12000 | 0
7082 | Wisconsin | WALWORTH |  | 1 | 2009901 | This is the design engineering effort for a construction project in Walworth County on local streets, Mohawk Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 3560 | 0
7083 | Wisconsin | GRANT |  | 3 | 2009902 | This is the design engineering effort for a construction project in Grant County on County Highway D, City of Platteville, Chestnut Street. | Other | 07/30/2009 | 07/30/2009 | 12/15/2009 | 40500 | 0.6
7084 | Wisconsin | SHAWANO |  | 8 | 2009903 | This is the design engineering effort for a construction project in Shawano County on County Highway D, North Branch Embarrass River Crossing. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 9900 | 0
7085 | Wisconsin | TREMPEALEAU |  | 3 | 2009904 | This is the design engineering effort for a construction project in Trempealeau County, Whitehall Historic Railroad Depot. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 7820 | 0
7086 | Wisconsin | PIERCE |  | 3 | 2009905 | This is the design engineering effort for a construction project in Pierce County on County Highway P, May Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 11200 | 0
7087 | Wisconsin | POLK |  | 7 | 2009906 | This is the design engineering effort for a construction project in Polk County, Amery to Dresser Trail. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 13300 | 0
7088 | Wisconsin | WASHBURN |  | 7 | 2009907 | This is the design engineering effort for a construction project in Washburn County, Spooner Bicycle and Pedestrian Facility. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 6260 | 0
7089 | Wisconsin | BAYFIELD |  | 7 | 2009908 | This is the design engineering effort for a construction project in Bayfield County on State Highway 13, Red Cliff streetscape improvement. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 15300 | 0
7090 | Wisconsin | WASHBURN |  | 7 | 2009909 | This is the design engineering effort for a construction project in Washburn County on County Highway E, Namekagon River Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4000 | 0
7091 | Wisconsin | CHIPPEWA | EAU CLAIRE | 7 | 2009910 | This is the design engineering effort for a construction project in Chippewa County on local streets, First Avenue. | Other | 08/26/2009 | 08/26/2009 | 12/15/2009 | 8800 | 0
7092 | Wisconsin | CHIPPEWA | EAU CLAIRE | 7 | 2009911 | This is the design engineering effort for a construction project in Chippewa County on County Highway X, 57th Avenue West to 184th Street. | Other | 08/26/2009 | 08/26/2009 | 12/01/2009 | 7400 | 0
7093 | Wisconsin | DOUGLAS | DULUTH-SUPERIOR (MN) | 7 | 2009912 | This is the design engineering effort for a construction project in Douglas County on local streets, East 5th Street, 6th Avenue East to 20th Avenue East. | Other | 08/26/2009 | 08/26/2009 | 12/15/2009 | 7500 | 0
7094 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009914 | This is the design engineering effort for a construction project in Milwaukee County on County Highway S, North 84th Street to North 56th Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 211427 | 0
7095 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009915 | This is the design engineering effort for a construction project in Milwaukee County, South Cesar Chavez Drive, West National Avenue to Greenfield Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8000 | 0
7096 | Wisconsin | RACINE | RACINE | 1 | 2009916 | This is the design engineering effort for a construction project in Racine County, North Shore Multi-Use Path. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8880 | 0
7097 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009917 | This is the design engineering effort for a construction project in Waukesha County, Lake Country Trail. | Other | 07/30/2009 | 07/30/2009 | 12/15/2009 | 17511 | 0
7098 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009918 | This is the design engineering effort for a construction project in Milwaukee County , Kinnickinnic River Bike Trail. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 7000 | 0
7099 | Wisconsin | KENOSHA | KENOSHA | 1 | 2009919 | This is the design engineering effort for a construction project in Kenosha County on local streets, 30th Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 16290 | 0
7100 | Wisconsin | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 1 | 2009920 | This is the design engineering effort for a construction project in Kenosha County on County Highway Z, Main Street East. | Other | 07/30/2009 | 07/30/2009 | 12/22/2009 | 9520 | 0
7101 | Wisconsin | KENOSHA |  | 1 | 2009921 | This is the design engineering effort for a construction project in Kenosha County on local streets, Cooper Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 5000 | 0
7102 | Wisconsin | RACINE |  | 1 | 2009922 | This is the design engineering effort for a construction project in Racine County on local streets, Kane Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 7120 | 0
7103 | Wisconsin | KEWAUNEE |  | 8 | 2009924 | This is the design engineering effort for a construction project in Kewaunee County on County Highway A, Town of Luxemburg. | Other | 07/30/2009 | 07/30/2009 | 12/15/2009 | 8325 | 0
7104 | Wisconsin | BROWN | GREEN BAY | 8 | 2009925 | This is the design engineering effort for a construction project in Brown County on County Highway I, Town of Scott. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 6706 | 1.2
7105 | Wisconsin | BROWN | GREEN BAY | 8 | 2009926 | This is the design engineering effort for a construction project in Brown County on local streets, City of DePere, Jordan Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 3560 | 0.91
7106 | Wisconsin | BROWN | GREEN BAY | 8 | 2009927 | This is the design engineering effort for a construction project in Brown County, Fox River Recreation Trail. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4140 | 0
7107 | Wisconsin | BROWN | GREEN BAY | 8 | 2009928 | This is the design engineering effort for a construction project in Brown County on local streets, City of Green Bay, Manitowoc Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 13178 | 0.83
7108 | Wisconsin | BROWN | GREEN BAY | 8 | 2009929 | This is the design engineering effort for a construction project in Brown County, Verlin Road Bike and Pedestrian Facilities. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 7447 | 0
7109 | Wisconsin | JUNEAU |  | 3 | 2009930 | This is the design engineering effort for a construction project in Juneau County on County Highway A, New Lisbon, Krypton Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 37350 | 6.5
7110 | Wisconsin | ROCK | JANESVILLE | 1 | 2009931 | This is the design engineering effort for a construction project in Rock County, Rotamer Road Bike Trail Connector. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8700 | 0
7111 | Wisconsin | LA CROSSE | LA CROSSE (MN) | 3 | 2009932 | This is the design engineering effort for a construction project in La Crosse County on State Highway 35, Mormon Coulee Road Bike Path improvement. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8620 | 0.35
7112 | Wisconsin | WINNEBAGO |  | 6 | 2009933 | This is the design engineering effort for a construction project in Winnebago County on County Highway D, Town of Winneconnie and Town of Poygan. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 23550 | 0
7113 | Wisconsin | PORTAGE |  | 7 | 2009934 | This is the design engineering effort for a construction project in Portage County on local streets, City of Stevens Point, Minnesota Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 53000 | 0.8
7114 | Wisconsin | BROWN | GREEN BAY | 8 | 2009935 | This is the design engineering effort for a construction project in Brown County on County Highway EB, Village of Howard. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 11120 | 2.22
7115 | Wisconsin | FOREST |  | 8 | 2009941 | This is the design engineering effort for a construction project in Forest County, the rebuild and rehabilitation of Laona Northern Railroad Track. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 10240 | 0
7116 | Wisconsin | OUTAGAMIE | APPLETON | 6 8 | 2009942 | This is the design engineering effort for a construction project in Outagamie County, Fox River Navigation, Lock Keeper Houses. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 15391 | 0
7117 | Wisconsin | DOUGLAS |  | 7 | 2009947 | This is the design engineering effort for a construction project in Douglas County on County Highway C, State Highway 35 to Kronberg Road. | Other | 10/20/2009 | 10/20/2009 | 12/01/2009 | 20000 | 0
7118 | Wisconsin | JEFFERSON |  | 5 6 | 2009953 | This is the design engineering effort for a construction project in Jefferson County on County Highway F, Sullivan to I-94. | Other | 08/04/2009 | 08/04/2009 | 12/01/2009 | 18900 | 3.9
7119 | Wisconsin | GRANT |  | 3 | 2009954 | This is the design engineering effort for a construction project in Grant County on local streets, Village of Bloomington, Mill Street. | Other | 08/04/2009 | 08/04/2009 | 12/15/2009 | 12120 | 0.93
7120 | Wisconsin | IOWA |  | 3 | 2009955 | This is the design engineering effort for a construction project in Iowa County on County Highway X, Village of Linden, Babcock Avenue. | Other | 08/04/2009 | 08/04/2009 | 12/15/2009 | 3860 | 0.13
7121 | Wisconsin | ROCK |  | 2 | 2009956 | This is the design engineering effort for a construction project in Rock County on County Highway C, North 4th Street and West Main Street. | Other | 08/04/2009 | 08/04/2009 | 12/01/2009 | 9600 | 0.8
7122 | Wisconsin | DANE | MADISON | 2 | 2009957 | This is the design engineering effort for a construction project in Dane County on local streets, City of Verona, North Nine Mound Road. | Other | 08/06/2009 | 08/06/2009 | 12/01/2009 | 15200 | 0.41
7123 | Wisconsin | ROCK | BELOIT (IL) | 2 | 2009958 | This is the design engineering effort for a construction project in Rock County on Town Road, Town of Beloit, Inman Parkway. | Other | 10/20/2009 | 01/25/2010 | 03/31/2010 | 10900 | 1.4
7124 | Wisconsin | DANE | MADISON | 2 | 2009959 | This is the design engineering effort for a construction project in Dane County on County Highway Q, City of Middleton, Allen Blvd.. | Other | 08/06/2009 | 08/06/2009 | 12/01/2009 | 4560 | 0
7125 | Wisconsin | DANE | MADISON | 2 | 2009960 | This is the design engineering effort for a construction project in Dane County on County Highway MS, City of Madison, University Avenue. | Other | 08/06/2009 | 08/06/2009 | 12/01/2009 | 41400 | 0.8
7126 | Wisconsin | DANE |  | 2 | 2009965 | This is the design engineering effort for a construction project in Dane County on County Highway K, US Highway 12 and County Highway M. | Other | 08/13/2009 | 08/13/2009 | 12/01/2009 | 9600 | 1.7
7127 | Wisconsin | SHEBOYGAN | SHEBOYGAN | 6 | 2010051 | This is the design engineering effort for a construction project in Sheboygan County on local streets, Taylor Drive, Superior Avenue, and Saemann Avenue. | Other | 09/29/2009 | 09/29/2009 | 12/01/2009 | 13266 | 1.14
7128 | Wisconsin | BARRON |  | 7 | 2010059 | This is a reconstruction project in Barron County on US Highway 53, New Auburn - Spooner. | Pavement Improvement | 12/16/2009 | 12/16/2009 |  | 11123487.78 | 12.38
7129 | Wisconsin | BARRON |  | 7 | 2010060 | This is a reconstruction project in Barron County on US Highway 53, New Auburn - Spooner. | Pavement Improvement | 12/16/2009 | 12/16/2009 |  | 11764869 | 12.38
7130 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010062 | This is a bridge rehabilitation project in Milwaukee County on local streets, West Vliet Street Bridge. | Bridge Improvement | 12/04/2009 | 12/04/2009 |  | 307500 | 0
7131 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010063 | This is a bridge rehabilitation project in Milwaukee County on local streets, North Sherman Blvd. Bridge. | Bridge Improvement | 12/04/2009 | 12/04/2009 |  | 651900 | 0
7132 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010064 | This is a resurfacing project in Milwaukee County on local streets, North Sherman Blvd. | Pavement Improvement | 12/04/2009 | 12/04/2009 |  | 559650 | 0
7133 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2010065 | This is a resurfacing project in Milwaukee County on local streets, South 76th Street. | Pavement Improvement | 12/04/2009 | 12/04/2009 |  | 753990 | 0
7134 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010066 | This is a resurfacing project in Milwaukee County on local streets, West National Avenue. | Pavement Improvement | 12/02/2009 | 12/02/2009 |  | 295200 | 0
7135 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010067 | This is a resurfacing project in Milwaukee County on local streets, South Cesar Chavez Drive. | Pavement Improvement | 12/04/2009 | 12/04/2009 |  | 707250 | 0
7136 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010068 | This is a landscaping and other scenic beautification project in Milwaukee County, South Cesar Chavez Drive. | Transportation Enhancements | 12/04/2009 | 12/04/2009 |  | 492000 | 0
7137 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010069 | This is a resurfacing project in Milwaukee County on local streets, South 68th Street. | Pavement Improvement | 12/04/2009 | 12/04/2009 |  | 281670 | 0
7138 | Wisconsin | RACINE | RACINE | 1 | 2010070 | This is a pedestrian and bicycle path project in Racine County, North Shore Multi-use Path. | Transportation Enhancements | 12/04/2009 | 12/04/2009 |  | 546120 | 0
7139 | Wisconsin | RACINE |  | 1 | 2010073 | This is a restoration and rehabilitation project in Racine County on County Highway G, Union Church Drive. | Pavement Improvement | 12/04/2009 | 12/04/2009 |  | 2638350 | 0
7140 | Wisconsin | RACINE |  | 1 | 2010074 | This is a restoration and rehabilitation project in Racine County on County Highway K, East Wink Lake Rd - Overson Road. | Pavement Improvement | 12/04/2009 | 12/04/2009 |  | 1212780 | 0
7141 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010075 | This is a bridge rehabilitation project in Milwaukee County on local streets, Jackson Park Drive. | Bridge Improvement | 12/04/2009 | 12/04/2009 |  | 605000 | 0
7142 | Wisconsin | MANITOWOC |  | 6 | 2010076 | This is a bridge replacement project in Manitowoc County on local streets, Pioneer Road. | Bridge Replacement | 12/07/2009 | 12/07/2009 |  | 341663 | 0
7143 | Wisconsin | WINNEBAGO | APPLETON | 6 | 2010077 | This is a bridge replacement project in Winnebago County on local streets, City of Neenah, Adams Street. | Bridge Replacement | 12/10/2009 | 12/10/2009 |  | 504300 | 0
7144 | Wisconsin | MONROE |  | 3 | 2010079 | This is a bridge replacement project in Monroe County on County Highway M, County Higway A - State Highway 16. | Other | 12/04/2009 | 12/04/2009 |  | 383760 | 0.1
7145 | Wisconsin | MONROE |  | 3 | 2010080 | This is a bridge replacement project in Monroe County on County Highway M, County Higway A - State Highway 16. | Other | 12/04/2009 | 12/04/2009 |  | 471090 | 0.1
7146 | Wisconsin | VERNON |  | 3 | 2010081 | This is a bridge replacement project in Vernon County on County Highway UU, Victory Creek Bridge and approaches. | Bridge Replacement | 12/04/2009 | 12/04/2009 |  | 348090 | 0.06
7147 | Wisconsin | CRAWFORD |  | 3 | 2010082 | This is a bridge replacement project in Crawford County on a town road, Town of Freeman, Buck Creek Bridge. | Bridge Replacement | 12/04/2009 | 12/04/2009 |  | 258300 | 0.06
7148 | Wisconsin | DANE |  | 2 | 2010083 | This is a reconstruction project in Dane County on County Highway K, US Highway 12 - County Highway M. | Pavement Improvement | 12/04/2009 | 12/04/2009 |  | 590400 | 1.7
7149 | Wisconsin | OUTAGAMIE |  | 8 | 2010085 | This is a bridge replacement project in Outagamie County on a town road, Greiner Road Bridge and approaches. | Other | 12/10/2009 | 12/10/2009 |  | 418200 | 0.025
7150 | Wisconsin | OUTAGAMIE |  | 8 | 2010086 | This is a bridge replacement project in Outagamie County on a town road, Central Valley Road Bridge and approaches. | Bridge Replacement | 12/07/2009 | 12/07/2009 |  | 405900 | 0.04
7151 | Wisconsin | WAUSHARA |  | 6 | 2010087 | This is a reconstruction project in Waushara County on County Highway I, Alder Creek Crossing. | New Bridge Construction | 12/16/2009 | 12/16/2009 |  | 175000 | 0
7152 | Wisconsin | PORTAGE |  | 7 | 2010088 | This is a resurfacing project in Portage County on local streets, City of Stevens Point, Minnesota Avenue. | Pavement Improvement | 12/16/2009 | 12/16/2009 |  | 430500 | 0.8
7153 | Wisconsin | BAYFIELD |  | 7 | 2010089 | This is a bridge rehabilitation project in Bayfield County on County Highway D, Namekagon River Bridge. | Bridge Improvement | 12/16/2009 | 12/16/2009 |  | 246000 | 0
7154 | Wisconsin | FOREST |  | 8 | 2010091 | This is an historic preservation project in Forest County to rebuild and rehabilitate the Laona Northern Railroad Track. | Transportation Enhancements | 12/16/2009 | 12/16/2009 |  | 629760 | 0
7155 | Wisconsin | PRICE |  | 7 | 2010092 | This is a bridge replacement project in Price County on a town road, Sailor Creek Bridge and approaches. | Bridge Replacement | 12/16/2009 | 12/16/2009 |  | 420660 | 0.01
7156 | Wisconsin | JEFFERSON |  | 5 6 | 2010093 | This is a reconstruction project in Jefferson County on County Highway F, Sullivan - Interstate 94. | Pavement Improvement | 12/04/2009 | 12/04/2009 |  | 1549800 | 3.9
7157 | Wisconsin | ROCK | BELOIT (IL) | 1 | 2010172 | This is a reconstruction project in Rock County on a town road, Town of Turtle. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 196800 | 2
7158 | Wisconsin | DODGE |  | 6 | 2010173 | This is a reconstruction project in Dodge County on County Highway DJ, Village of Juneau, East Oak Grove Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 372690 | 0
7159 | Wisconsin | RICHLAND |  | 3 | 2010174 | This is a reconstruction project in Richland County on County Highway C, Vernon County Line, Rolt Lane. | Pavement Improvement | 01/12/2010 | 01/12/2010 |  | 1482150 | 0
7160 | Wisconsin | RICHLAND |  | 3 | 2010175 | This is a reconstruction project in Richland County on County Highway D, Rockbrook Bridge. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 1166040 | 0
7161 | Wisconsin | JUNEAU |  | 3 | 2010176 | This is a reconstruction project in Juneau County on County Highway A, Monroe County Line - New Lisbon. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 3062700 | 6.5
7162 | Wisconsin | ROCK |  | 2 | 2010177 | This is a reconstruction project in Rock County on County Highway C, North 4th Street and West Main Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 590400 | 0.8
7163 | Wisconsin | ROCK | BELOIT (IL) | 2 | 2010178 | This is a reconstruction project in Rock County on a town road, Town of Beloit, Inman Parkway. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 670350 | 1.4
7164 | Wisconsin | ROCK | BELOIT (IL) | 2 | 2010179 | This is a reconstruction project in Rock County on local streets, Town of Beloit, Cranston Road. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 129150 | 0
7165 | Wisconsin | LA CROSSE | LA CROSSE (MN) | 3 | 2010180 | This is a bicycle path project in La Crosse County on State Highway 35, Mormon Coulee Road Bike Path Improvement. | Transportation Enhancements | 12/31/2009 | 12/31/2009 |  | 530130 | 0.35
7166 | Wisconsin | DANE | MADISON | 2 | 2010181 | This is a reconstruction project in Dane County on County Highway MS, City of Madison, University Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 3394800 | 0.8
7167 | Wisconsin | DODGE |  | 6 | 2010182 | This is a reconstruction project in Dodge County on various highways, Madison Street and University Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 956940 | 0
7168 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010183 | This is a roundabout project in Milwaukee County on local streets, West Winnebago Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 1164213 | 0
7169 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010184 | This is a reconstruction project in Milwaukee County on local streets, East and West Keefe Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 3425005 | 0
7170 | Wisconsin | MILWAUKEE | MILWAUKEE | 1 | 2010185 | This is a resurfacing project in Milwaukee County on local streets, West Grange Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 688800 | 0
7171 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010186 | This is a reconstruction project in Milwaukee County on local streets, East and West North Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 2413949 | 0
7172 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2010187 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Hampton Avenue. | Pavement Improvement | 01/12/2010 | 01/12/2010 |  | 1111400 | 0
7173 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010188 | This is a restoration and rehabilitation project in Milwaukee County on local streets, 15th Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 799500 | 0
7174 | Wisconsin | OZAUKEE | MILWAUKEE | 5 | 2010189 | This is a restoration and rehabilitation project in Ozaukee County on County Highway O, North Green Bay Road. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 959400 | 0
7175 | Wisconsin | KENOSHA | KENOSHA | 1 | 2010190 | This is a bridge rehabilitation project in Kenosha County on local streets, 38th Street Bridge. | Bridge Replacement | 01/13/2010 | 01/13/2010 |  | 995000 | 0
7176 | Wisconsin | WASHINGTON |  | 5 | 2010191 | This is a resurfacing project in Washington County on local streets, Decorah Road. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 755466 | 0
7177 | Wisconsin | WASHINGTON |  | 5 | 2010192 | This is a resurfacing project in Washington County on local streets, 7th Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 120294 | 0
7178 | Wisconsin | WASHINGTON |  | 5 | 2010193 | This is a resurfacing project in Washington County on local streets, Indiana Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 511434 | 0
7179 | Wisconsin | WASHINGTON |  | 5 | 2010194 | This is a resurfacing project in Washington County on local streets, Vine Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 121524 | 0
7180 | Wisconsin | WASHINGTON |  | 5 | 2010195 | This is a resurfacing project in Washington County on local streets, Park Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 106395 | 0
7181 | Wisconsin | WASHINGTON |  | 5 | 2010196 | This is a resurfacing project in Washington County on local streets, Jefferson Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 251904 | 0
7182 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2010197 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Eastbrook Park Drive. | Pavement Widening | 01/12/2010 | 01/12/2010 |  | 1186100 | 0
7183 | Wisconsin | KENOSHA | KENOSHA | 1 | 2010198 | This is a resurfacing project in Kenosha County on local streets, 30th Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 1335780 | 0
7184 | Wisconsin | KENOSHA |  | 1 | 2010199 | This is a pedestrian access and safety project in Kenosha County. | Transportation Enhancements | 01/13/2010 | 01/13/2010 |  | 250182 | 0
7185 | Wisconsin | KENOSHA | KENOSHA | 1 | 2010201 | This is a resurfacing project in Kenosha County on local streets, 80th Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 553500 | 0
7186 | Wisconsin | RACINE |  | 1 | 2010202 | This is a resurfacing project in Racine County on local streets, Kane Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 437880 | 0
7187 | Wisconsin | RACINE |  | 1 | 2010203 | This is a restoration and rehabilitation project in Racine County on various highways, Market Street, Pine Street - Dodge Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 433575 | 0
7188 | Wisconsin | RACINE |  | 1 | 2010204 | This is a resurfacing project in Racine County on various highways, Grove Street, Oak Street - Briody Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 551110 | 0
7189 | Wisconsin | OUTAGAMIE | APPLETON | 6 8 | 2010205 | This is an historic preservation project in Outagamie County, the rehabilitation of the Fox River Navigation System Lock Keeper houses. | Transportation Enhancements | 01/13/2010 | 01/13/2010 |  | 946576 | 0
7190 | Wisconsin | OUTAGAMIE | APPLETON | 8 | 2010206 | This is a reconstruction project in Outagamie County on local streets, Village of Little Chute, Washington Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 360390 | 0.15
7191 | Wisconsin | BROWN | GREEN BAY | 8 | 2010207 | This is a pedestrian and bicycle path project in Brown County, Fox River Recreation Trail. | Transportation Enhancements | 01/13/2010 | 01/13/2010 |  | 254610 | 0
7192 | Wisconsin | BROWN | GREEN BAY | 8 | 2010208 | This is a pedestrian and bicycle path project in Brown County, Verlin Road Bike Pedestrian Facilities. | Transportation Enhancements | 01/13/2010 | 01/13/2010 |  | 457978 | 0
7193 | Wisconsin | WINNEBAGO | APPLETON | 6 | 2010209 | This is a restoration and rehabilitation project in Winnebago County on local streets, City of Mehasha, Tayco Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 473550 | 0.7
7194 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2010210 | This is a resurfacing project in Winnebago County on local streets, City of Oshkosh, Snell Road. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 717090 | 1
7195 | Wisconsin | WINNEBAGO | APPLETON | 6 | 2010211 | This is a restoration and rehabilitation project in Winnebago County on local streets, City of Neenah, Wisconsin Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 492000 | 0.14
7196 | Wisconsin | SHEBOYGAN | SHEBOYGAN | 6 | 2010212 | This is a reconstruction project in Sheboygan County on local streets, Taylor Drive, Superior Avenue, and Saemann Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 815870 | 1.14
7197 | Wisconsin | OCONTO |  | 8 | 2010213 | This is a bridge rehabilitation project in Oconto County on County Highway S, Pensaukee River Bridge. | Bridge Improvement | 01/13/2010 | 01/13/2010 |  | 430500 | 0
7198 | Wisconsin | OCONTO |  | 8 | 2010214 | This is a bridge rehabilitation project in Oconto County on County Highway S, Pensaukee River Bridge. | Bridge Improvement | 01/13/2010 | 01/13/2010 |  | 344400 | 0
7199 | Wisconsin | MARINETTE |  | 8 | 2010215 | This is a reconstruction project in Marinette County on local streets, Cleveland Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 638370 | 0
7200 | Wisconsin | MARINETTE |  | 8 | 2010216 | This is a reconstruction project in Marinette County on local streets, Hattie Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 129150 | 0
7201 | Wisconsin | MARINETTE |  | 8 | 2010217 | This is a reconstruction project in Marinette County on local streets, Hosmer Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 116850 | 0
7202 | Wisconsin | MARINETTE |  | 8 | 2010218 | This is a reconstruction project in Marinette County on local streets, Marinette Mid-city Bike and Pedestrian Path. | Other | 01/13/2010 | 01/13/2010 |  | 285826 | 0
7203 | Wisconsin | DUNN |  | 3 | 2010220 | This is a reconstruction project in Dunn County on County Highway P, Spring Valley - Menomonie. | Pavement Improvement | 01/14/2010 | 01/14/2010 |  | 1184490 | 0
7204 | Wisconsin | PIERCE |  | 3 | 2010221 | This is a reconstruction project in Pierce County on County Highway P, May Avenue. | Pavement Improvement | 01/14/2010 | 01/14/2010 |  | 688800 | 0
7205 | Wisconsin | DUNN |  | 3 | 2010222 | This is a resurfacing project in Dunn County on local streets, City of Menomonie, 3M Drive and 9th Street. | Pavement Improvement | 01/14/2010 | 01/14/2010 |  | 1629750 | 0
7206 | Wisconsin | DOUGLAS |  | 7 | 2010225 | This is a bridge replacement project in Douglas County on a town road, Town of Wascott, Cheever Road, Ounce River Bridge. | Bridge Replacement | 01/14/2010 | 01/14/2010 |  | 238620 | 0
7207 | Wisconsin | DOUGLAS |  | 7 | 2010226 | This is a bridge replacement project in Douglas County on a town road, Town of Wascott, East Coppermine Road, Ounce River Bridge. | Bridge Replacement | 01/14/2010 | 01/14/2010 |  | 252150 | 0
7208 | Wisconsin | RUSK |  | 7 | 2010227 | This is a restoration and rehabilitation project in Rusk County on County Highway F, Bear Lake, Potato Lake Road. | Pavement Improvement | 01/14/2010 | 01/14/2010 |  | 541200 | 0
7209 | Wisconsin | WASHBURN |  | 7 | 2010228 | This is a bridge rehabilitation project in Washburn County on County Highway E, Namekagon River Bridge. | Bridge Improvement | 01/14/2010 | 01/14/2010 |  | 246000 | 0
7210 | Wisconsin | CHIPPEWA | EAU CLAIRE | 7 | 2010229 | This is a restoration and rehabilitation project in Chippewa County on local streets, City of Chippewa Falls Bridge Street. | Pavement Improvement | 01/14/2010 | 01/14/2010 |  | 221400 | 0
7211 | Wisconsin | DOUGLAS | DULUTH-SUPERIOR (MN) | 7 | 2010230 | This is a resurfacing project in Douglas County on local streets, City of Superior, Hill Avenue and Broadway Street. | Pavement Improvement | 01/14/2010 | 01/14/2010 |  | 528900 | 0
7212 | Wisconsin | OUTAGAMIE | APPLETON | 8 | 3009018 | This is the design engineering effort for a construction project in Outagamie County, Greenville Pedestrian Trail. | Other | 09/10/2009 | 09/10/2009 | 12/15/2009 | 10860 | 0
7213 | Wisconsin | WINNEBAGO | APPLETON | 6 | 3009019 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Neenah, Adams Street. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 8200 | 0
7214 | Wisconsin | CALUMET | APPLETON | 6 | 3009020 | This is the design engineering effort for a construction project in Calumet County, Town of Harrison, Noe Road, Bike and Pedestrian Facilities. | Transportation Enhancements | 09/10/2009 | 09/10/2009 | 12/01/2009 | 5653 | 0
7215 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 3009021 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Oshkosh, Snell Road. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 11660 | 1
7216 | Wisconsin | WINNEBAGO | APPLETON | 6 | 3009022 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Neenah, Wisconsin Avenue. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 8000 | 0.14
7217 | Wisconsin | OUTAGAMIE | APPLETON | 8 | 3009023 | This is the design engineering effort for a construction project in Outagamie County on local streets, Village of Little Chute, Washington Street. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 5860 | 0.15
7218 | Wisconsin | WINNEBAGO | APPLETON | 6 | 3009024 | This is the design engineering effort for a construction project in Winnebago County on local streets, City and Town of Menasha, Manitowoc Road. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 9252 | 1.2
7219 | Wisconsin | WINNEBAGO | APPLETON | 6 | 3009025 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Menasha, Tayco Street. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 7700 | 0.7
7220 | Wisconsin | ROCK | BELOIT (IL) | 1 | 3009145 | This is the design engineering effort for a construction project in Rock County on Town Road, Town of Turtle, Townline Road. | Other | 09/21/2009 | 09/21/2009 | 12/01/2009 | 3200 | 2
7221 | Wyoming | LINCOLN |  | 00 | 0007035 | Construction of retaining walls on US 189 in Diamondville in Lincoln County. | Transportation Enhancements | 05/20/2009 |  | 07/31/2010 | 204160 | 0
7222 | Wyoming | BIG HORN |  | 00 | 0200028 | Pavement overlay on approximately 14 miles of WYO 30 between Basin and Burlington in Big Horn County. | Pavement Improvement | 05/06/2009 |  | 06/30/2010 | 1529767 | 13.79
7223 | Wyoming | CAMPBELL |  | 00 | 0300044 | Pavement overlay of 12 miles of WYO 50 between Gillette and Pine Tree Junction in Campbell County. | Pavement Improvement | 08/21/2009 |  | 10/31/2010 | 2451589 | 6.79
7224 | Wyoming | CAMPBELL |  | 00 | 0300045 | Pavement overlay of 12 miles of WYO 50 between Gillette and Pine Tree Junction in Campbell County. | Pavement Improvement | 08/21/2009 |  | 10/31/2010 | 1599679 | 5.3
7225 | Wyoming | GOSHEN |  | 00 | 0800010 | Pipe, curb and gutter, and sidewalk replacement on 0.38 miles of WYO 151 in the Town of Lagrange in Goshen County, Wyoming. | Other | 05/19/2009 |  | 09/30/2009 | 97770 | 0.53
7226 | Wyoming | CROOK |  | 00 | 0904121 | Pavement overlay of 7 miles of I-90 between Sundance and the South Dakota State Line in Crook County. | Pavement Improvement | 05/08/2009 |  | 07/31/2010 | 6509002 | 7
7227 | Wyoming | NATRONA |  | 00 | 1301018 | Drainage repairs of pipe locations on WYO 251 (Casper Mountain Road) in Natrona County. | Other | 05/11/2009 |  | 10/31/2009 | 346426 | 0
7228 | Wyoming | PARK |  | 00 | 1501007 | Pavement overlay on approximately 7 miles of WYO 291 between Cody and South Fork in Park County. | Pavement Improvement | 07/14/2009 |  | 09/15/2010 | 3171338 | 6.66
7229 | Wyoming | SHERIDAN |  | 00 | 1701013 | Replace right-of-way fence on 2.24 miles of WYO 331 between Sheridan and Beckton in Sheridan County. | Other | 05/11/2009 |  | 10/31/2010 | 82343 | 2.2
7230 | Wyoming | WESTON |  | 00 | 2302011 | Pavement overlay and bridge rehabilitation on WYO 116 north of WYO 450 in Weston County. | Pavement Improvement | 05/06/2009 |  | 10/31/2010 | 7734004 | 7.29
7231 | Wyoming | UINTA |  | 00 | 6598005 | Sidewalk and curb and guter replacement on Harrison Drive in Evanston, Wyoming. | Transportation Enhancements | 08/18/2009 |  | 08/31/2010 | 341402 | 0.31
7232 | Wyoming | STATEWIDE |  | 00 | B045012 | Bridge preventive maintenance at various locations in Wyoming Transportation District 5. | Bridge Improvement | 05/11/2009 |  | 09/30/2009 | 95057 | 0
7233 | Wyoming | STATEWIDE |  | 00 | B082008 | Preventive maintenance (contract patching) and miscellaneous work at various locations in Wyoming Transportation District 2. | Pavement Improvement | 06/24/2009 |  | 09/30/2010 | 3465400 | 35
7234 | Wyoming | BIG HORN |  | 00 | B085011 | Fence replacement on approximately 11 miles of US 14 east and west of Greybull in Big Horn and Park Counties. | Other | 05/13/2009 |  | 09/30/2009 | 460590 | 0
7235 | Wyoming | STATEWIDE |  | 00 | B091005 | Preventive Maintenance, Crack sealing on 85.15 miles of various highways in District 1. | Pavement Improvement | 05/19/2009 |  | 04/30/2010 | 569576 | 0
7236 | Wyoming | STATEWIDE |  | 00 | B091008 | Preventive Maintenance, Bituminous Pavement Patches at various locations in District 1. | Pavement Improvement | 05/19/2009 |  | 09/30/2009 | 715110 | 0
7237 | Wyoming | BIG HORN |  | 00 | B095014 | Preventive maintenance (crack seal) on 125 miles of various roads in Wyoming Transportation District 5. | Pavement Improvement | 05/11/2009 |  | 03/31/2010 | 897140 | 0
7238 | Wyoming | STATEWIDE |  | 00 | B151002 | Preventive Maintenance, Chip Seals on various roadways in District 1. | Pavement Improvement | 05/20/2009 |  | 08/31/2010 | 3788779 | 0
7239 | Wyoming | STATEWIDE |  | 00 | B152005 | Preventive maintenance (chip seal) and miscellaneous work on approzimately 84 miles of highway in Wyoming Transportation District Two. | Pavement Improvement | 05/11/2009 |  | 08/31/2010 | 2653752 | 0
7240 | Wyoming | STATEWIDE |  | 00 | B152006 | Preventive maintenance (crack seal) and miscellaneous work on approximately 367 miles of highway in Wyoming Transporatation District 2. | Pavement Improvement | 08/04/2009 |  | 05/31/2010 | 3713131 | 0
7241 | Wyoming | LARAMIE |  | 00 | I180017 | Install a new pedestrian railing and upgrade the lighting system on I-180 in Cheyenne. | Transportation Enhancements | 05/08/2009 |  | 11/30/2009 | 953556 | 0
7242 | Wyoming | PLATTE |  | 00 | I252157 | Landscaping and miscellaneous work at the Dwyer Junction Rest at the intersection of US 26 and I-25 in Platte County. | Transportation Enhancements | 10/12/2009 |  | 07/31/2010 | 146735 | 0
7243 | Wyoming | UINTA |  | 00 | I801175 | Bridge maintenance and rehabilitation at various location on I-80 in Uinta County. | Bridge Improvement | 08/18/2009 |  | 08/31/2010 | 621915 | 0
7244 | Wyoming | UINTA |  | 00 | I801176 | Preventive pavement maintenance and miscellaneous work on 23.20 miles of I-80 between Carter and LaBarge in Sweetwater and Uinta Counties. | Pavement Improvement | 06/10/2009 |  | 09/30/2010 | 2883277 | 0
7245 | Wyoming | UINTA |  | 00 | I801177 | Preventive pavement maintenance and rehabilitation of 28.10 miles of I-80 beginning at the Utah State Line in Uinta County. | Pavement Improvement | 05/27/2009 |  | 09/30/2010 | 11140697 | 28.1
7246 | Wyoming | SWEETWATER |  | 00 | I802192 | Concrete Pavement Rehabilitation on 15.34 miles of I-80 between Green River and Rock Springs in Sweetwater County. | Pavement Improvement | 06/24/2009 |  | 09/30/2010 | 7539909 | 15.37
7247 | Wyoming | SWEETWATER |  | 00 | I803140 | Preventive pavement maintenance and miscellaneous work on 33.50 miles of I-80 east of Rock Springs in Sweetwater County. | Pavement Improvement | 05/27/2009 |  | 09/30/2010 | 4017946 | 34
7248 | Wyoming | CARBON |  | 00 | I804245 | Pavement resurfacing of 6.39 miles of I-80 east of Sinclair in Carbon County. | Pavement Improvement | 06/24/2009 |  | 08/31/2010 | 5284945 | 6.229
7249 | Wyoming | ALBANY |  | 00 | I804250 | Preventive Maintenance, Replace Snow Fence along 23.35 miles of I-80 in Albany and Carbon Counties. | Other | 06/11/2009 |  | 09/15/2010 | 5332241 | 23.25
7250 | Wyoming | CARBON |  | 00 | I804251 | Pavement resurfacing and bridge repair along 13.04 miles of I-80 near Elk Mountain. | Pavement Improvement | 10/01/2009 |  | 10/31/2010 | 2640051 | 5.06
7251 | Wyoming | ALBANY |  | 00 | I805165 | Preventive Maintenance, Installation of a friction course on I-80 in Telephone Canyon east of Laramie. | Pavement Improvement | 06/24/2009 |  | 09/30/2010 | 2146646 | 5.17
7252 | Wyoming | JOHNSON |  | 00 | I902118 | Pavement overlay and surface treatment on 6.2 miles of I-90 between Buffalo and Gillette in Johnson County. | Pavement Improvement | 05/20/2009 |  | 07/15/2010 | 3622801 | 6.2
7253 | Wyoming | JOHNSON |  | 00 | I902119 | Pavement overlay and surface treatment on 6.2 miles of I-90 between Buffalo and Gillette in Johnson County. | Pavement Improvement | 05/20/2009 |  | 07/15/2010 | 4861911 | 8
7254 | Wyoming | CROOK |  | 00 | I904130 | Pavement preventive maintenance on 12.7 miles of I-90 between Moorcroft and Sundance in Crook County. | Pavement Improvement | 06/10/2009 |  | 06/30/2010 | 2760480 | 12.71
7255 | Wyoming | FREMONT |  | 00 | N202062 | Rest Area rehabilitation of the Sweetwater Station Rest Area between Muddy Gap and Lander. | Other | 06/10/2009 |  | 08/27/2010 | 489496 | 0
7256 | Wyoming | FREMONT |  | 00 | N203063 | Pavement overlay of approximately 4 miles of US 26 between Riverton and Shoshoni in Fremont County. | Pavement Improvement | 05/20/2009 |  | 09/30/2010 | 1626740 | 4.91
7257 | Wyoming | PARK |  | 00 | N291036 | Pavement reconstruction and widening of 3.85 miles of US 14A between Cody and Powell in Park County. | Pavement Widening | 06/24/2009 |  | 10/15/2010 | 11456488 | 3.62
7258 | Wyoming | FREMONT |  | 00 | N303049 | Rest Area rehabilitation of the Diversion Dam Rest Area between Diversion Dam Junction and Dubois. | Other | 06/10/2009 |  | 08/27/2010 | 476537 | 0
7259 | Wyoming | BIG HORN |  | 00 | N312013 | Safety improvements including slope flattening and guardrail upgrades on 1.48 miles of US 14/16 between Cody and Greybull. | Safety/Traffic Management | 06/10/2009 |  | 10/15/2009 | 391600 | 1.48
7260 | Wyoming | HOT SPRINGS |  | 00 | N331025 | Rest Area rehabilitation of the Gooseberry Creek Rest Area between Thermopolis and Meeteetse. | Other | 06/10/2009 |  | 08/27/2010 | 382087 | 0
7261 | Wyoming | NATRONA |  | 00 | N341105 | Rest Area rehabilitation of the Waltman Rest Area between Casper and Shoshoni. | Other | 06/10/2009 |  | 08/27/2010 | 291150 | 0
7262 | Wyoming | FREMONT |  | 00 | N342042 | Pavement overlay on 11 miles of US 26 between Casper and Shoshoni in Fremont County. | Pavement Improvement | 08/18/2009 |  | 09/30/2010 | 3438963 | 11
7263 | Wyoming | BIG HORN |  | 00 | N345080 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Safety/Traffic Management | 06/11/2009 |  | 10/31/2010 | 874253 | 5.099
7264 | Wyoming | BIG HORN |  | 00 | N345089 | Rest Area rehabilitation of the Greybull Rest Area northwest of Greybull. | Other | 06/10/2009 |  | 08/27/2010 | 375571 | 0
7265 | Wyoming | BIG HORN |  | 00 | N345095 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Pavement Improvement | 06/11/2009 |  | 10/31/2010 | 1746271 | 4.99
7266 | Wyoming | BIG HORN |  | 00 | N345096 | Pavement overlay on approximately 6 miles of US 16.20 between Manderson and Basin in Big Horn County. | Pavement Improvement | 08/18/2009 |  | 09/30/2010 | 1374760 | 6.049
7267 | Wyoming | BIG HORN |  | 00 | N345101 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Safety/Traffic Management | 06/11/2009 |  | 10/31/2010 | 148117 | 7
7268 | Wyoming | NIOBRARA |  | 00 | N402016 | Pavement widening and overlay on 9.90 miles of US 18/20 between Lusk and Manville in Niobrara County. | Pavement Improvement | 05/27/2009 |  | 10/31/2010 | 12223783 | 10
7269 | Wyoming | WESTON |  | 00 | N442066 | Enhancements to US 16 (Upton Main Street) including landscaping, sidewalk, curb and gutter, in Weston County. | Transportation Enhancements | 08/17/2009 |  | 10/31/2010 | 150000 | 1.25
7270 | Wyoming | GOSHEN |  | 00 | N853084 | Pavement overlay and miscellaneous work on 9.51 miles of US 85 north of Lagrange in Goshen County. | Pavement Improvement | 05/20/2009 |  | 08/31/2010 | 3415493 | 9.75
7271 | Wyoming | NIOBRARA |  | 00 | N854071 | Pavement overlay and bridge repair of 5 miles of US 85 between Newcastle and Mule Creek Junction in Niobrara County. | Pavement Improvement | 08/04/2009 |  | 10/31/2010 | 2143461 | 6.65
7272 | Wyoming | LINCOLN |  | 00 | P112021 | Construction of retaining walls on US 189 in Diamondville in Lincoln County. | Transportation Enhancements | 05/20/2009 |  | 07/31/2010 | 250000 | 0
7273 | Wyoming | FREMONT |  | 00 | P142041 | Rest Area rehabilitation of the South Pass Rest Area between Farson and Lander. | Other | 06/10/2009 |  | 08/27/2010 | 454160 | 0
7274 | Wyoming | CARBON |  | 00 | P182029 | Pavement rehabilitation and installation of a wildlife underpass on WYO 789 south of Creston Junction. | Pavement Improvement | 06/11/2009 |  | 10/31/2010 | 1071737 | 4
7275 | Wyoming | UINTA |  | 00 | P341108 | Pavement rehabilitation, sidewalk replacement and curb and gutter replacement, and bridge repair on Casper Streets in Natrona County. | Pavement Improvement | 05/20/2009 |  | 10/31/2010 | 2508438 | 1.09
7276 | Wyoming | UINTA |  | 00 | P501001 | Pavement overlay and miscellaneous work on 10.45 miles of WYO 89 north of Evanston in Uinta County. | Pavement Improvement | 06/11/2009 |  | 09/30/2010 | 3216146 | 10.48
7277 | Wyoming | UINTA |  | 00 | P511018 | Sidewalk and curb and guter replacement on Harrison Drive in Evanston, Wyoming. | Transportation Enhancements | 08/18/2009 |  | 08/31/2010 | 169715 | 0.31
7278 | Wyoming | LARAMIE |  | 00 | P561028 | Reconstruct West Lincolnway (US-30) in Cheyenne. | Pavement Improvement | 07/20/2009 |  | 10/15/2010 | 10255177 | 1.289
7279 | Wyoming | CONVERSE |  | 00 | P581025 | Landscaping and miscellaneous work on US 20/26/87 in the City of Douglas. | Transportation Enhancements | 10/12/2009 |  | 07/31/2010 | 84315 | 0.759
7280 | Puerto Rico |  | AGUDILLA | 00 | 0002040 | This project consists of the replacement of BRIDGE NO. 763 ON PR-2 KM 127.4, over HIGHWAY PR-2R, in the municipality of Aguadilla, PR. | Pavement Improvement | 08/14/2009 | 08/14/2009 |  | 6716258.75 | 0.49
7281 | Puerto Rico |  | SAN JUAN | 00 | 0020007 | This project consists of replacing damaged bearing pads under the bridge on PR-20, to raise it to its original grade and elevation. It also includes repairs to the bridge deck. It is located in Guay | Bridge Improvement | 10/30/2009 | 10/30/2009 |  | 571297 | 0.073
7282 | Puerto Rico |  |  | 00 | 0173008 | This project consists of the realignment of highway PR-173 at KM 3.0 in the municipality of Cidra. This road was affected by a landslide. | Pavement Improvement | 11/05/2009 | 11/05/2009 |  | 414374.9 | 0.152
7283 | Puerto Rico |  |  | 00 | 9999088 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region, Unit I in | Pavement Improvement | 08/10/2009 | 08/10/2009 |  | 2128944.4 | 3.181
7284 | Puerto Rico |  |  | 00 | 9999092 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region Unit II in | Pavement Improvement | 07/31/2009 | 07/31/2009 |  | 3758034.4 | 18.026
7285 | Puerto Rico |  |  | 00 | 9999093 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region Unit III in | Pavement Improvement | 07/13/2009 | 07/13/2009 |  | 3455054.83 | 11.386
7286 | Virgin Islands | VIRGIN ISLANDS |  | VI00 | 0032008 | This project proposes to improve pedestrian mobility by constructing sidewalks, installing new crosswalks, new pedestrian crossing signs and installing new roadway striping from the Red Hook Marine Te | Other | 01/11/2010 | 01/11/2010 | 05/21/2010 | 1050359.96 | 0.35
7287 | Virgin Islands | VIRGIN ISLANDS |  | VI00 | 0070011 | This project proposes to repave 2 miles of asphalt roadway along the eastern section of Queen Mary Highway. The project will also make improvements to prevent flooding on the roadway. | New Construction | 10/16/2009 | 10/29/2009 | 10/28/2010 | 4859669.4 | 2.05
7288 | Virgin Islands | VIRGIN ISLANDS |  | VI00 | 0104003 | This project proposes to repave over 2 miles of asphalt roadway. The project will also replace culverts and pipes along the roadway to prevent flooding of the road. The project will install pedestrian | New Construction | 10/05/2009 | 10/05/2009 | 07/02/2010 | 4782469 | 2.83
7289 | (HQFL) IRR | BELTRAMI, MN |  | 07 | F52409SI | Rehabilitation | 4R Restoration and Rehabilitation | 09/14/2009 | 09/14/2009 |  | 87000 | 14.42
7290 | (HQFL) IRR | BELTRAMI, MN |  | 07 | F52409SJ | Rehabilitation | 4R Resurfacing | 09/14/2009 | 09/14/2009 |  | 2626283 | 0.04
7291 | (HQFL) IRR | CASS, MN |  | 08 | F53407SA | Reconstruction of 15.7 miles of surface renovation. | 4R Reconstruction, Added Capacity | 10/15/2009 | 10/15/2009 | 06/30/2010 | 2403373 | 15.7
7292 | (HQFL) IRR | ISABELLA, MI |  | 21 | F60472SB | Rehabilitation | 4R Resurfacing | 09/21/2009 | 08/16/2009 | 12/31/2010 | 540000 | 0.3
7293 | (HQFL) IRR | ISABELLA, MI |  | 21 | F60472SC | Rehabilitation | 4R Resurfacing | 09/21/2009 | 08/16/2009 | 12/31/2010 | 270000 | 8.47
7294 | (HQFL) IRR | GOGEBIC, MI |  | 01 | F6047307 | Rehabilitation | 4R Resurfacing | 09/14/2009 | 09/01/2009 | 10/31/2009 | 379305 | 2.02
7295 | (HQFL) IRR | CIBOLA, NM |  | 2 | RN 125 | Milling and Paving Rehabilitation | 4R Reconstruction, No Added Capacity | 05/26/2009 |  | 08/31/2009 | 644000 | 9
7296 | (HQFL) IRR | AROOSTOOK, ME |  | 2 | S503190 | OverLayment | 4R Resurfacing | 10/26/2009 | 11/04/2009 | 09/30/2010 | 54083 | 0.4
7297 | Federal Lands Eastern Division | CLARENDON, SC |  | 6 | 1515450SNT001 | Located in Clarendon County, SC, the project will rehabilitate Center Road and Wildlife Drive, key access points serving thousands of motorists annually. The refuge is home to endangered species like | 4R Restoration and Rehabilitation | 06/30/2009 |  | 05/01/2010 | 1261660.1 | 0
7298 | Federal Lands Eastern Division | BLOUNT, TN |  | 2 | 1515471220011 | The purpose of this project is to continue construction of "Missing Link" in the Foothills Parkway. The work will include the construction of one bridge (~800 feet ) and the construction of the roadwa | Bridge, New Construction | 05/21/2009 |  | 12/01/2011 | 25264957.65 | 0
7299 | Federal Lands Eastern Division | YORK, VA |  | 0 | 1515514290011 | The purpose of this projects is to rehabilitate five bridges within Colonial National Historical Park - Beaverdam Creek Bridge, Yorktown Creek Bridget, Powhatan Creek Bridget, and College Creek Bridge | Bridge Rehabilitation, No Added Capacity | 06/30/2009 | 06/30/2009 |  | 165524 | 0
7300 | Federal Lands Eastern Division | FAIRFAX, VA |  | 11 | 151551FFXPK05 | Phase IV of the Fairfax County Parkway Project consists of the construction of the Boudinot Drive Interchange. This new interchange will provide full access to the Parkway from the Fullerton Industri | New Construction Roadway | 06/29/2009 | 06/29/2009 | 12/01/2011 | 22800000 | 0
7301 | Federal Lands Eastern Division | ST. JOHN, VI |  | 0 | 1515785360004 | The primary purpose of this project is to resurface the entire 7.5 miles of North Shore Road along with areas of shoulder reconditioning, drainage improvements, stone masonry edging at selected pull-o | 4R Reconstruction, Added Capacity | 09/28/2009 |  | 12/01/2010 | 1397391.4 | 0
7302 | Federal Lands Eastern Division | ST. THOMAS, VI |  | 0 | 151578LONGBAY | Reconstruct and widen 0.28 miles of Long Bay Road from Veteran's Drive to Centerline Road on St. Thomas, USVI. | 4R Reconstruction, Added Capacity | 11/16/2009 |  |  | 5537155 | 0
7303 | Federal Lands Eastern Division | NOXUBEE, MS |  | 3 | 15B5280NXB001 | This project consists of the rehabilitation of 18.2 miles of Bluff Lake Road, Brooksville-Louisville Road, and Section Line Road in Noxubee and Winston Counties, Mississippi. Bluff Lake Road and Broo | 4R Resurfacing | 06/19/2009 |  | 08/01/2011 | 1437725.56 | 0
7304 | Federal Lands Central Division | APACHE, AZ |  | 01 | 1516040431003 | Near Eagar Arizona, install pavement over a previously constructed gravel road surface on Forest Highway 43 from the West Baldy Parking Area (8.5 miles south of State Highway 260) to the intersection | 4R Resurfacing | 07/06/2009 | 07/06/2009 | 11/01/2009 | 3415149 | 16.2
7305 | Federal Lands Central Division | COCONINO, AZ |  | 01 | 1516043050003 | Design (provide completed plans, drawings and specifications for) the Depot Tour Bus Parking Area at the South Rim Grand Canyon National Park, Arizona (the plans are currently 10% complete). | Preliminary Engineering | 09/16/2009 |  |  | 74377 | 0
7306 | Federal Lands Central Division | NEVADA, CA |  | 04 | 1516061231001 | Remove existing pavement and repave approximately 5 miles of Washington Road from the intersection of SR 20 to a point just south of the town of Washington. | 4R Restoration and Rehabilitation | 05/28/2009 | 06/29/2009 | 11/01/2009 | 4779888.5 | 10.58
7307 | Federal Lands Central Division | EL DORADO, CA |  | 04 | 1516061371004 | On Wentworth Springs Road (in El Dorado County, California) remove the existing pavement and repave approximately 5 miles of roadway from mile post 1.30 to mile post 6. | 4R Restoration and Rehabilitation | 08/07/2009 | 08/10/2009 | 12/01/2009 | 3195420.5 | 10.76
7308 | Federal Lands Central Division | MARIPOSA, CA |  | 19 | 1516063401501 | Remove existing pavement and repave approximately 5.05 miles of roadway, and 2.17 lane miles of paved parking, in Yosemite National Park. The project includes the roadway from Chinquapin intersection | 4R Restoration and Rehabilitation | 06/02/2009 | 06/03/2009 | 11/30/2009 | 8224763.3 | 5.5
7309 | Federal Lands Central Division | INYO, CA |  | 25 | 1516063901102 | Pulverize roadway and overlay with asphalt pavement, and install drainage culverts on approximately 33.3 mile of the Bonnie Claire Road from mile post 7.4 at the junction of Ubehebe Crater Road to mil | 4R Restoration and Rehabilitation | 07/30/2009 | 08/17/2009 | 05/30/2010 | 11311399 | 33.3
7310 | Federal Lands Central Division | DEL NORTE, CA |  | 01 | 1516064710201 | Pulverize existing pavement and overlay with new pavement, and install new draininage ay pavement and drainage structures on approximately 2.18 miles of two-lane roadway between Costal Drive and Klama | 4R Restoration and Rehabilitation | 05/13/2009 | 05/18/2009 | 10/30/2009 | 3102070.45 | 2.1
7311 | Federal Lands Central Division | MONTEZUMA, CO |  | 03 | 1516080301009 | At Mesa Verde National apark in Colorado, remove existing pavement and repave the main entrance road from the Park entrance at Highway 160 to the Park Point Overlook. The project also includes adding | 4R Restoration and Rehabilitation | 06/15/2009 | 06/24/2009 | 08/30/2010 | 11951932 | 19.6
7312 | Federal Lands Central Division | CLEAR CREEK, CO |  | 02 | 1516088012023 | Recondition, regrade and pave approximately seven (7) miles of existing aggregate and chip seal surface on Guanella Pass, near Georgetown, Colorado. This work is near the boundary of Clear Creek and | 4R Reconstruction, Added Capacity | 07/07/2008 | 08/06/2009 | 10/01/2010 | 4600749 | 26.429
7313 | Federal Lands Central Division | RIO GRANDE, CO |  | 03 | 1516088501002 | Recondition and resurface the existing one-way loop road with aggregate (gravel) surfacing. Construct better defined boundaries for existing pullouts, create additional small pullouts where there is | 4R Resurfacing | 08/10/2009 | 08/10/2009 | 09/01/2009 | 354550 | 2.5
7314 | Federal Lands Central Division | SIOUX, NE |  | 06 | 1516310071004 | Design a box culvert drain structure and resurface approximately 1 mile of roadway. | Preliminary Engineering | 09/11/2009 | 09/11/2009 |  | 78976 | 0.3
7315 | Federal Lands Central Division | CLARK, NV |  | 03 | 1516322800109 | Rehabilitate roadway pavement and drainage structures on approximately 17.5 miles of the Northshore Road from the Redstone Parking Area to the North Park Boundary. | 4R Restoration and Rehabilitation | 11/02/2009 |  | 08/29/2010 | 7042962.84 | 17.5
7316 | Federal Lands Central Division | DENVER, CO |  | 01 | 1516350057101 | Develop design drawings and specifications, including environmental studies and clearances, for the replacement of six small bridges in Cibola National Forest in New Mexico state. | Preliminary Engineering | 05/13/2009 | 05/13/2009 | 03/01/2010 | 539949.02 | 0
7317 | Federal Lands Central Division | SANDOVAL, NM |  | 03 | 1516350121006 | Contract modification to existing project between Cuba and LaCueva, NM, to add roadway drainage improvements to protect the roadway and to enhance stream water quality. | Environmental Only | 06/29/2009 | 06/29/2009 | 07/18/2009 | 700000 | 0
7318 | Federal Lands Central Division | DENVER, CO |  | 01 | 1516350121009 | Design services for the development of 100% plan set on project NM 12-1(9) and 70% set plan development on NM PFH12-1(10) for the reconstruction and paving of an existing | Preliminary Engineering | 06/29/2009 | 06/30/2009 | 09/01/2011 | 1138149.98 | 0
7319 | Federal Lands Central Division | MCKENZIE, ND |  | 01 | 1516381701003 | This project involves the removal of the existing asphalt pavement and replacement with new asphalt pavement on 13.8 miles of roadway within the North Unit of Theodore Roosevelt National Park. | 4R Restoration and Rehabilitation | 06/04/2009 | 06/07/2009 | 10/30/2009 | 7371245.5 | 13.8
7320 | Federal Lands Central Division | WARD, ND |  | 01 | 1516383040111 | Recondition and resurface Route 11, Lower Lake Road (at Des Lacs National Wildlife Refuge, in North Dakota) to a uniform width of 22 feet and regravel. Additionally, Lower Lake Parking 1 will be regr | 4R Resurfacing | 07/06/2009 | 07/28/2009 | 08/01/2009 | 901993.33 | 1.03
7321 | Federal Lands Central Division | MCHENRY, ND |  | 01 | 1516383111201 | Reconstruction of two bridges (Willow Creek and Johnson bridges). One bridge location will include a small parking area adjacent to it for canoe access to the river. | Bridge Replacement, No Added Capacity | 09/30/2009 |  | 06/30/2010 | 478239.6 | 0.26
7322 | Federal Lands Central Division | SEVIER, UT |  | 03 | 1516490391003 | Construct asphalt pavement surfacing on a previously constructed gravel surface on Forest Highway 39 from 5.1 miles south of I-70 (the end of the existing pavement) to the Gooseberry Administrative Si | 4R Resurfacing | 06/24/2009 | 07/07/2009 | 09/01/2009 | 1961852 | 10.2
7323 | Federal Lands Central Division | FREMONT, WY |  | 01 | 1516560231003 | Recondition the existing aggregate surfacing and roadbed by scarifying and reshaping to provide for consistent cross slopes and width. The roadway will then be resurfaced with a new aggregate surface | 4R Resurfacing | 09/09/2009 | 08/19/2009 | 10/31/2009 | 959408.75 | 19
7324 | Federal Lands Central Division | CARBON, WY |  | 01 | 1516560261901 | Construction of two (2) small drainiage structures (box culverts) on Wyoming State Route 71, including grading, draining, and paving along the existing alignment to facilitate installation of 2 draina | 4R Reconstruction, No Added Capacity | 06/30/2009 |  | 10/01/2009 | 1059545.25 | 1
7325 | (CFL) NPS | INYO, CA |  | 25, 41, 45 | 1516062008001 | Construct chip seals on routes within Death Valley National Park, Joshua Tree National Park, and Lake Mead National Recreation Area. | 4R Resurfacing | 01/14/2010 |  | 06/22/2010 | 7251506.83 | 14.55
7326 | (CFL) NPS | SHASTA, CA |  | 02 | 1516063201003 | Pulverize the existing pavement and repave approxmately 35 kilometers of roadway on Lassen Park Road in Lassen Volcanic National Park, Shasta County, California. | 4R Restoration and Rehabilitation | 08/26/2009 |  | 11/15/2010 | 6355656.12 | 22
7327 | (CFL) NPS | INYO, CA |  | 25 | 1516063910901 | Pulverize and overlay (repave) approximately 6 miles of roadway on Bonnie CLair Road in Death Valley. Reconstruct the Ubehebe Crater Overlook parking area, including new pavement, curb, gutter and si | 4R Restoration and Rehabilitation | 10/13/2009 |  | 03/19/2010 | 3591890.1 | 6.2
7328 | (CFL) NPS | GRAND, CO |  | 02 | 1516080601005 | Project involves pulverizing the existing pavement and repaving approximately 17 kilometers of roadway, and two campgrounds, on Trail Ridge Road in Rocky Mountain National Park, Grand County, Colorado | 4R Restoration and Rehabilitation | 04/23/2009 | 04/24/2009 | 09/18/2009 | 6884666.4 | 10.787
7329 | (CFL) NPS | PIMA, AZ |  | 01,07,08 | 1516082008002 | In the State of Arizona, construct chip seals surfacing on all routes within Canyon De Chelly, Chiricahua, Fort Bowie, Organ Pipe, Saguaro, Tonto, and Tumacacori National Monuments. | 4R Resurfacing | 09/24/2009 |  | 11/20/2009 | 2704406 | 0.87
7330 | (CFL) NPS | CLARK, NV |  | 03 | 1516322800109 | Pulverize the existing pavement and repave approximately 17.5 miles of the Northshore Road, in Lake Mead National Recreation Area, between mile posts 27.3 and 47.6. | 4R Restoration and Rehabilitation | 11/02/2009 |  | 08/29/2010 | 9700000 | 23.7
7331 | (CFL) NPS | PENNINGTON, SD |  | 01 | 1516460701005 | The project includes the removal of the existing asphalt pavement and replacement with new aspahlt pavement and the installation of new roadway drainage features for 14.5 miles of roadway within the B | 4R Restoration and Rehabilitation | 09/23/2009 |  | 11/15/2010 | 8312957.05 | 14.552
7332 | (CFL) BLM | ALPINE, CA |  | 03 | 1516060660001 | Add a new layer of asphalt to the Indian Creek Access Road, Campground Loop and Boat Parking Lot. | 4R Resurfacing | 12/10/2009 | 12/10/2009 |  | 36442.27 | 0
7333 | (CFL) BLM | MONTEREY, CA |  | 17 | 1516061904101 | Add gravel to 5 miles of various roads and replace the bridge over El Toro Creek with a low water crossing within the Ft. Ord Management Area. | Bridge Replacement, No Added Capacity | 01/21/2010 |  |  | 74219.68 | 5
7334 | (CFL) BLM | MONTEREY, CA |  | 17 | 1516061904301 | Replace 25 culverts in Ft. Ord Management Area | 4R Restoration and Rehabilitation | 01/21/2010 |  |  | 25952.7 | 0
7335 | (CFL) BLM | LAKE, CA |  | 01 | 1516065403001 | Add gravel and pave 2 miles of Mendo Lake Road. | 4R Resurfacing | 01/21/2010 |  |  | 44587.53 | 2
7336 | (CFL) BLM | CHURCHILL, NV |  | 02 | 1516323133001 | Pave 1.4 miles of Sand Mountain Access Road. | 4R Resurfacing | 12/10/2009 | 12/10/2009 |  | 55183.98 | 1.4
7337 | (CFL) BLM | FREMONT, WY |  | 01 | 1516562302001 | Construct gravel surfacing on Hudson Atlantic Road in Wyoming. | 4R Resurfacing | 09/30/2009 |  | 06/30/2010 | 1129765 | 16
7338 | (CFL) BLM | CARBON, WY |  | 01 | 1516563301001 | Construct gravel surfacing on Bridger Pass and Barrel Springs Roads in Wyoming. | 4R Resurfacing | 09/14/2009 | 09/15/2009 | 12/01/2009 | 1505836 | 17.3
7339 | (CFL) BLM | SWEETWATER, WY |  | 01 | 1516564302001 | Construct gravel surfacing on Sand Dunes Recreation Site and White Mountain Petroglphs Roads in Wyoming. | 4R Resurfacing | 02/08/2010 |  | 05/30/2010 | 528043 | 4.3
7340 | (CFL) BLM | FRESNO, CA |  | 20 | 15A6061900601 | Add gravel to 8 miles of road in Panoche Management Area | 4R Resurfacing | 01/21/2010 |  |  | 49264.38 | 8
7341 | (CFL) BLM | LASSEN, CA |  | 04 | 15A6062376001 | Replace the 90 foot portion of the Bizz Johnson Trail Bridge Number 9 that burned in the Devil's Incident Fire in 2000. | Bridge Rehabilitation, No Added Capacity | 01/21/2010 |  |  | 199941.22 | 0
7342 | Federal Lands Western Division | PRINCE OF WALES-OUTER KETCHIKAN, AK |  | 00 | 1517020440008 | In an effort to protect Tongass National Forest's streams and wildlife from impacts from exposed natural occurring acid rock; this project will cleanup affected areas, replace culverts, and buffer the | 0ther | 07/01/2009 | 07/01/2009 | 05/31/2010 | 1766392.81 | 0.944
7343 | Federal Lands Western Division | FLATHEAD, MT |  | 00 | 1517302610023 | The work being performed on this project will reconstruct a portion of the multphase historic Going to the Sun Road project, providing access to Glacier National Park's spectacular scenery and ultimat | 4R Reconstruction, No Added Capacity | 06/08/2009 | 06/08/2009 | 07/01/2011 | 19134081.5 | 2.8
7344 | Federal Lands Western Division | GRAYS HARBOR, WA |  | 06 | 1517532080002 | This project, continuation of phase 1, fully reconstructs the remaining 7 miles of road providing improved access the Olympic National Forest in Washington. | 4R Resurfacing | 07/01/2009 | 07/01/2009 | 11/01/2010 | 4446476 | 5
7345 | (WFL) FS | LEMHI, ID |  | 02 | 1517166030001 | In an effort to improve safe access for visitors to the Challis National Forest, this project will replace three deteriorating bridges on the upper Salmon River Road: Cove Creek, Pine Creek, and Littl | Bridge Replacement, Added Capacity | 07/01/2009 | 07/01/2009 | 12/06/2009 | 330721.81 | 0
7346 | (WFL) FS | COOS, OR |  | 04 | 1517411376001 | This project will repair the Upper Chetco River Bridge stabilizing the foundation and making structural repairs. These repairs will add years to the life of the bridge and improve safety of visitors | 4R Restoration and Rehabilitation | 07/01/2009 | 07/01/2009 |  | 97354.42 | 0.05
7347 | (WFL) FS |  |  | 03, 04 | 1517532009004 | Western Federal Lands Highway Division will provide design support on this project to replace 9 deficient bridges with fabricated modular structures within the Gifford Pinchot National Forest in Washi | Preliminary Engineering | 07/01/2009 | 07/01/2009 |  | 275936.43 | 0
7348 | (WFL) BLM |  |  | 04 | 1517412009002 | This project replaces eleven 40 year old failing culverts with fish passage compliant culverts. This will improve fish passage for federally listed endangered species to Siuslaw River watershed as we | 4R Reconstruction, No Added Capacity | 07/01/2009 | 07/01/2009 |  | 25000 | 0

## Summary Proceed
As Of February 12, 2010
State | # of Projects | Total ARRA Obligations
(CFL) BLM | 10 | 3649235.76
(CFL) NPS | 7 | 44801082.5
(HQFL) IRR | 8 | 7004044
(WFL) BLM | 1 | 25000
(WFL) FS | 3 | 704012.66
Alabama | 128 | 305262553.23
Alaska | 13 | 87262122
Arizona | 159 | 373764361.93
Arkansas | 77 | 160746870
California | 305 | 1264568386
Colorado | 64 | 259366887
Connecticut | 36 | 198497355
Delaware | 27 | 59384859.24
District of Columbia | 11 | 94110324.96
Federal Lands Central Division | 21 | 73242621.02
Federal Lands Eastern Division | 7 | 57864413.71
Federal Lands Western Division | 3 | 25346950.31
Florida | 255 | 768820538
Georgia | 150 | 465797963.17
Hawaii | 13 | 47411763.19
Idaho | 63 | 167579002
Illinois | 497 | 745462751
Indiana | 712 | 474638747.13
Iowa | 213 | 342014303.65
Kansas | 50 | 204181738.28
Kentucky | 35 | 351601297.92
Louisiana | 34 | 298404816.08
Maine | 72 | 123983564.1
Maryland | 97 | 240301414
Massachusetts | 40 | 186429289.58
Michigan | 460 | 709620570.31
Minnesota | 136 | 334199335.82
Mississippi | 68 | 281466458
Missouri | 200 | 480878022.02
Montana | 66 | 161560059
Nebraska | 62 | 166767480
Nevada | 18 | 85196234
New Hampshire | 28 | 118817865.9
New Jersey | 46 | 418420619
New Mexico | 23 | 160193492.69
New York | 303 | 638600167
North Carolina | 294 | 661446395
North Dakota | 118 | 132313095.99
Ohio | 201 | 464229027.11
Oklahoma | 177 | 412575709
Oregon | 229 | 190783729.83
Pennsylvania | 279 | 898083942.95
Puerto Rico | 6 | 17043964.28
Rhode Island | 52 | 121238941.42
South Carolina | 101 | 278031061.84
South Dakota | 27 | 138665528.78
Tennessee | 264 | 525775932
Texas | 282 | 1052196992.67
Utah | 97 | 198618414.51
Vermont | 32 | 85020825.33
Virgin Islands | 3 | 10692498.36
Virginia | 22 | 128875850
Washington | 171 | 427652498.45
West Virginia | 105 | 180230099
Wisconsin | 308 | 443120251.99
Wyoming | 59 | 153393583
Total | 7348 | 17507936912.67