## Notice to Proceed
As Of August 06, 2010
Row | State | County | Urban Area | Cong. District | Project # | Project Description | Improvement Type | Proceed Date | Work Start Date | Estimated Completion Date | Total ARRA Obligations | Length (Miles)
1 | Alabama | MADISON | HUNTSVILLE | 05 | 0001537 | This project constructs the mainline of US-231/431 with overpasses at Max Luther and Sparkman Drive. The mainline will be four and six lanes with a concrete median divider for approximately 1 mile. | New Construction | 08/10/2009 | 08/30/2009 | 06/01/2011 | 21868441.79 | 1.03
2 | Alabama | HOUSTON | DOTHAN | 02 | 0001538 | This project will upgrade the bridge rails to current safety standards for bridges with inventory number 006900 and 006901 over Big Creek on US Highway 231 in Houston County | Pavement Improvement | 05/13/2009 | 06/25/2009 | 04/01/2010 | 195000 | 0.01
3 | Alabama | HOUSTON | DOTHAN | 02 | 0001539 | This project involve the repaving of approximately 6 miles of US Highway 231 from the Florida State line to just north of County Road 93 (Smithville Road) south of Dothan | Pavement Improvement | 05/13/2009 | 06/18/2009 | 04/01/2010 | 2850120.19 | 6.082
4 | Alabama | HENRY |  | 02 | 0001543 | This project involves the repaving of about 3 miles of US Highway 431 from the the south city limit of Headland to just north of State Highway 173 | Pavement Improvement | 10/14/2009 |  | 07/01/2010 | 1693695.94 | 3.06
5 | Alabama | RUSSELL | COLUMBUS (GA) | 03 | 0001546 | This project involves the repaving of 10 miles of US Highway 431 from Old Seale Highway to just south of US Highway 280 in Russell County | Pavement Improvement | 09/25/2009 | 11/06/2009 | 07/01/2010 | 4541092.12 | 10.33
6 | Alabama | MARSHALL |  | 04 | 0001548 | This project involves the repaving and widening of approximately 7 miles of US Highway 431 from the north end of the Tennessee River Bridge to County Road 5 (Cathedral Caverns Highway) just north of G | Pavement Improvement | 09/10/2009 |  | 07/01/2010 | 3837142.57 | 6.66
7 | Alabama | CHAMBERS |  | 03 | 0001553 | This project will improve the curves along SR-1(US-431) from one mile south of SR-147 to south of Sturkie and provide new traffic stripe. | Safety/Traffic Management | 10/22/2009 | 12/11/2009 |  | 229544.17 | 2
8 | Alabama | CLEBURNE |  | 03 | 0001554 | This project involves safety improvements at various curves along US-431 | Safety/Traffic Management | 01/28/2010 |  |  | 748974.66 | 1.96
9 | Alabama | RUSSELL | COLUMBUS (GA) | 03 | 0001555 | This project involves the repaving of US Highway 43 (State Highway 1) from US Highway 80 (State Highway 80) to the north city lilmits of Phenix City in Russell County | Pavement Improvement | 05/27/2010 |  |  | 551860.54 | 1.79
10 | Alabama | COLBERT | FLORENCE | 05 | 0002534 | This project involves the repaving and 2 foot safety widening for about 4 miles of US Highway 72 from west of Cane Creek to east of Dry in Colbert County | Pavement Improvement | 05/15/2009 | 07/02/2009 | 04/10/2010 | 1662887.98 | 3.673
11 | Alabama | LIMESTONE |  | 05 | 0003544 | This project involves the repaving and widening of about 3 miles of US Highway 31 from just south of Cactus Street to Interstate 65 near Athens | Pavement Improvement | 05/04/2009 | 06/22/2009 | 04/01/2010 | 1395000 | 2.655
12 | Alabama | BALDWIN |  | 01 | 0003546 | This project involves the repaving of aproximately 7 miles of the Gulf Shores Parkway from Stapleton to the Bay Minette south city limits | Pavement Improvement | 05/13/2009 | 06/24/2009 | 04/01/2010 | 2999892.9 | 7.38
13 | Alabama | BUTLER |  | 02 | 0003550 | This project involves the repaving and 2 foot widening of approximately 5 miles of US Highway 31 from the Conecuh County line to a bout a mile north of Persimmon Creek of Butler County | Pavement Improvement | 07/23/2009 | 09/16/2009 | 05/01/2010 | 2255932.06 | 5.215
14 | Alabama | LOWNDES |  | 02 | 0003551 | This project involves the repaving and 2 foot widening of approximately 10 miles of US Highway 31 near Fort Deposit from the Junction of State Highway 185 to the Montgomery County line | Pavement Improvement | 08/13/2009 | 09/30/2009 | 06/01/2010 | 3407833.03 | 9.637
15 | Alabama | CONECUH |  | 02 | 0003552 | This project involves the repaving of about 12 miles of US Highway 31 from US Highway 84 to the Butler County Line in Conecuh County | Pavement Improvement | 08/13/2009 | 09/15/2009 | 06/01/2010 | 2704722.58 | 12.127
16 | Alabama | CLARKE |  | 01 | 0005526 | This project involves the repaving of approximately 5 miles of State Highway 5 in Clarke County from US Highway 43 to the Wilcox County Line north of Thomasville | Pavement Improvement | 05/01/2009 | 07/07/2009 | 04/01/2010 | 1619174.16 | 4.795
17 | Alabama | AUTAUGA | MONTGOMERY | 02 | 0006538 | This project involves the repaving and 2 foot widening of 12 miles of US Highway 82 from just west of County Road 40 to State Highway 206 in Pratville | Pavement Improvement | 08/14/2009 | 08/31/2009 | 06/01/2010 | 3850345.25 | 12
18 | Alabama | TUSCALOOSA | TUSCALOOSA | 07 | 0007519 | This project involves the repaving of US Highway 11 from the Greene County Line to just south of the Warrior River Bridge in the Fosters. The project also include the repaving of Holly Springs Road f | Pavement Improvement | 09/16/2009 | 10/13/2009 | 07/01/2010 | 4194899.73 | 9.826
19 | Alabama | GREENE |  | 07 | 0007520 | This project invovles the repaving and widening of 10 miles US Highway 11 from north of Greentrack Road to Tuscaloosa County Line near Knoxville | Pavement Improvement | 09/15/2009 | 10/20/2009 | 07/01/2010 | 3463826.99 | 9.634
20 | Alabama | MACON |  | 03 | 0008554 | This project involves the repaving and widening of 9 miles of US Highway 80 in Macon County from near the junction of State Highway 186 to the Lee County line | Pavement Improvement | 08/14/2009 | 09/29/2009 | 06/01/2010 | 2698634.49 | 9.03
21 | Alabama | MONTGOMERY |  | 03 | 0009509 | This project will add two additional lanes to the existing two lanes to provide a four-lane facility on US Highway 331 from approximately one-half mile south of State Highway 94 to the end of the pres | Pavement Widening | 11/18/2009 |  |  | 18869375.36 | 4.21
22 | Alabama | WILCOX |  | 07 | 0010520 | This project involves the repaving of 2 miles of State Highway 10 (Camden Bypass) from State Highway 28 to State Highway 28 in Camden. Wilcox County | Pavement Improvement | 08/04/2009 | 09/04/2009 | 06/01/2010 | 631951.38 | 1.964
23 | Alabama | CRENSHAW |  | 02 | 0010521 | This project involves the repaving and widening for 10 miles of State Highway 10 from the Butler County line to US Highway 331 in Crenshaw County | Pavement Improvement | 08/12/2009 | 09/04/2009 | 06/01/2010 | 3252048.79 | 9.872
24 | Alabama | CHOCTAW |  | 07 | 0012536 | This project involves repaving approximately 7 miles of US Highway 84 from about 2 miles north of County Road 6 (Bladon Road) to east end of Tombigbee River Bridge in Choctaw County | Pavement Improvement | 03/02/2010 |  |  | 1468712.92 | 6.626
25 | Alabama | CLARKE |  | 07 | 0012537 | This project involves the repaving and widening of 5 miles of US Highway 84 from the east end of the Tombigbee River Bridge to west of County Road 3 in Clarke County | Pavement Improvement | 02/09/2010 |  |  | 2083259.25 | 5.344
26 | Alabama | LAUDERDALE |  | 05 | 0013503 | This project will add two additional lanes to the existing two lanes to ultimately provide a four-lane facility from the end of the present four-lane at Killen to State Highway 64. This project will | Pavement Improvement | 12/02/2009 | 12/15/2009 |  | 10060231.81 | 5.066
27 | Alabama | BULLOCK |  | 02 | 0015515 | This project involves the repaving of a mile of US Highway 29 from State Highway 197 to US Highway 82 in Union Springs | Pavement Improvement | 09/10/2009 | 09/28/2009 | 07/01/2010 | 435883.86 | 1.01
28 | Alabama | ESCAMBIA |  | 01 | 0015516 | This project involves the repaving of over 11 miles of US Highway 29 from 1 mile south of Maye Creek to just south of Smith Creek in Escambia County | Pavement Improvement | 01/26/2010 |  |  | 1911967.31 | 11.42
29 | Alabama | LEE | AUBURN-OPELIKA | 03 | 0015517 | This project involves the repaving of about 2 miles of US Highway 29 from the Macon County Line to Sand Hill Road in Lee County | Pavement Improvement | 07/29/2009 | 09/16/2009 | 05/01/2010 | 921213.28 | 1.86
30 | Alabama | CHOCTAW |  | 07 | 0017525 | This project involves the repaving and widening of approximately 4 miles of State Highway 17 in Chocktaw County from about 1 mile south of County Road 18 to just north of County Road 28 east of Needha | Pavement Improvement | 07/29/2009 | 08/30/2009 | 05/01/2010 | 1278321.13 | 3.571
31 | Alabama | CHOCTAW |  | 07 | 0017526 | This project involves the repaving of 5 miles of State Highway 17 (Mulberry Avenue) from just north of County Road 28 to north of the Butler city limits in Choctaw County | Pavement Improvement | 07/29/2009 | 09/10/2009 | 05/01/2010 | 1288681.05 | 5.541
32 | Alabama | LAMAR |  | 04 | 0017528 | This project involves the repaving of approximately 8 miles of State Highway 17 from about a mile north of County Road 29 to County Road 30 in Sulligent | Pavement Improvement | 09/11/2009 | 11/13/2009 | 07/01/2010 | 6356216.29 | 8.3
33 | Alabama | MARION |  | 04 | 0017529 | This project involves the repaving of approximately 7 miles of State Highway 17 from the Lamar County line to State Highway 4 south of Hamilton in Marion County | Pavement Improvement | 05/04/2009 | 07/06/2009 | 04/01/2010 | 1770059.52 | 7.191
34 | Alabama | SUMTER |  | 07 | 0017530 | This project involves the repaving of 6 miles of State Highway 17 from State Highway 28 to County Road 24 in Sumter County | Pavement Improvement | 09/14/2009 |  | 07/01/2010 | 2721996.1 | 5.97
35 | Alabama | WASHINGTON |  | 01 | 0017531 | This project involves the repaving of 9 miles of State Highway 17 from about 2 miles south of County Road 20 To State Highway 56 in Chatom | Pavement Improvement | 09/28/2009 | 10/13/2009 | 07/01/2010 | 2957542.17 | 9.042
36 | Alabama | PICKENS |  | 04, 07 | 0017532 | This project involves the repaving of 2.5 miles of State Highway 17 from the Carrollton south city limits to just north of the north city limits in Pickens County | Pavement Improvement | 09/21/2009 | 10/13/2009 | 07/01/2010 | 2095405.03 | 2.4
37 | Alabama | LAUDERDALE |  | 05 | 0020510 | This project involves the repaving of approximately 8 miles of State Highway 20 from the Tennessee State line to south of County Road 22 at the Natchez Trace Parkway in Lauderdale County | Pavement Improvement | 09/23/2009 | 10/09/2009 | 07/01/2010 | 2210526.45 | 7.84
38 | Alabama | MONROE |  | 01 | 0021522 | This project involves the repaving of approximately 6 miles of State Highway 21 in Monroe County from the north end of the Litte River Bridge at the Escambia County line to County Road 8 north of Uria | Pavement Improvement | 08/17/2009 | 09/29/2009 | 06/01/2010 | 2193633.16 | 6.245
39 | Alabama | MONROE |  | 01 | 0021523 | This project involves the repaving of approximately 6 miles of State Highway 21 from north of County Road 8 to south of County Road 10 in Monroe County | Pavement Improvement | 08/17/2009 | 09/29/2009 | 06/01/2010 | 2171063.85 | 6.425
40 | Alabama | ESCAMBIA |  | 01 | 0021527 | This project involves the repaving of South Main Street in the town of Atmore from the Florida State line to about 1 mile north | Pavement Improvement | 08/18/2009 | 09/30/2009 | 06/01/2010 | 325434.98 | 0.968
41 | Alabama | CALHOUN |  | 03 | 0021528 | This project involves the repaving of 5 miles of Jacksonville State University Highway from Maxwellborn Road to near Foothills Drive in the town of Piedmont | Pavement Improvement | 09/15/2009 | 01/04/2010 | 07/01/2010 | 1786569.53 | 4.76
42 | Alabama | DALLAS |  | 07 | 0022509 | This project involves the repaving and 2 foot widening of approximately 19 miles of State Highway 22 from State Highway 5 to State Highway 219 in Dallas County southwest of Selma | Pavement Improvement | 08/04/2009 | 09/14/2009 | 06/01/2010 | 4095666.24 | 19.181
43 | Alabama | RANDOLPH |  | 03 | 0022510 | This project will improve the curves along State Highway 22 from 1 mile north of Randolph County Road 17 to the State Line | Pavement Improvement | 10/15/2009 |  |  | 485484.04 | 1
44 | Alabama | LAWRENCE |  | 05 | 0024501 | This project involves the repaving of 5 miles of State Highway 24 from County Road 460 to near County Road 320 in Lawrence County | Pavement Improvement | 10/14/2009 |  | 07/01/2010 | 2887638.92 | 5.03
45 | Alabama | HALE |  | 07 | 0025520 | This project involves repaving and widening fro about 5 miles of State Highway 25 in Hale County from County Road 29 to the Bibb County line | Pavement Improvement | 08/19/2009 | 10/15/2009 | 06/01/2010 | 1811864.63 | 4.534
46 | Alabama | DALE |  | 02 | 0027504 | This project involves the repaving and widening of approximately 10 miles of State Highway 27 in Dale County from east of County Road 59 to the Henry County line | Pavement Improvement | 01/20/2010 | 02/11/2010 |  | 2630054.44 | 9.591
47 | Alabama | COFFEE |  | 02 | 0027505 | This project involves the repaving and widening of approximately 5 miles of State Highway 27 northeast of Enterprise from Indego Place to the Dale County line | Pavement Improvement | 08/04/2009 | 09/30/2009 | 06/01/2010 | 1605503.37 | 5.217
48 | Alabama | WINSTON |  | 04 | 0033502 | This project involves the repaving of 5 miles of State Highway 24 from County Road 460 to near County Road 320 in Lawrence County | Pavement Improvement | 08/18/2009 | 08/31/2009 | 06/01/2010 | 1600500.71 | 4.945
49 | Alabama | JACKSON |  | 05 | 0035509 | This project involves the repaving and 2 foot safety widening for approximately 13 miles of State Highway 35 from State Highway 79 westerly through Woodville to US Highway 72 in Jackson County | Pavement Improvement | 05/04/2009 | 06/29/2009 | 04/01/2010 | 1500000 | 13.29
50 | Alabama | MORGAN | DECATUR | 04,05 | 0036504 | This project involves the repaving and widening of over 2 miles of State Highway 36 (Main Street) from the intersection with US Highway 31 in Hartselle to Interstate 65 | Pavement Improvement | 09/24/2009 |  | 07/01/2010 | 923974.07 | 2.414
51 | Alabama | SHELBY | BIRMINGHAM | 06 | 0038522 | This project involves the repaving of over 6 miles of US-280 from Hugh Daniel Drive to Old US 280 Highway | Pavement Improvement | 05/14/2009 | 06/15/2009 | 04/01/2010 | 6551704.45 | 6.25
52 | Alabama | ESCAMBIA |  | 01, 02 | 0041505 | This project involves the repaving of approximately 10 miles of State Highway 41 from south of County 39 to just south of Interstate 65 in Escambia County | Pavement Improvement | 03/02/2010 |  |  | 3448521.49 | 10.79
53 | Alabama | CLAY |  | 03 | 0049502 | This project involves the repaving of about 8 miles of State Highway 49 fromt the Tallapoosa County line to State Highway 77 near the town of Ashland | Pavement Improvement | 07/21/2009 | 09/11/2009 | 05/01/2010 | 2409572.53 | 7.334
54 | Alabama | TALLAPOOSA |  | 03 | 0049503 | This project involves the resurfacing and traffic stripe at various sites on SR-49. | Safety/Traffic Management | 01/07/2010 | 02/04/2010 |  | 723703.78 | 20
55 | Alabama | BARBOUR |  | 02 | 0051503 | This project involves the repaving and and widening of approximately 10 miles of State Highway 51 in Barbour County from just South of State Highway 239 to the Bullock County line | Pavement Improvement | 08/07/2009 | 09/23/2009 | 06/01/2010 | 2934528.24 | 10.325
56 | Alabama | DALE |  | 02 | 0051504 | This project involves the repaving and widening of 3 miles of State Highway 51 in Dale County from the Coffee County line to US Highway 231 | Pavement Improvement | 01/20/2010 | 02/11/2010 |  | 899945.52 | 3.107
57 | Alabama | BULLOCK |  | 02 | 0051505 | This project involves the repaving and 2 foot widening of 13 miles of State Highway 51 in Bullock County from US Highway 82 to the Russell County line | Pavement Improvement | 01/27/2010 |  |  | 4951093.75 | 13
58 | Alabama | DALE |  | 02 | 0053537 | This project will upgrade the bridge rails to current safety standards for bridges with inventory numbers 005532 and 005533 over Little Claybank Creek and bridges with inventory numbers 005571 and 009 | Bridge Improvement | 05/04/2009 | 06/05/2009 | 04/01/2010 | 155000 | 6.39
59 | Alabama | DALE |  | 02 | 0053538 | This project involves the repaving of about 6.5 miles of US Higway 231 from just south of State Highway 27 north to County Road 2 in Ozark | Pavement Improvement | 05/04/2009 | 06/30/2009 | 04/01/2010 | 2768226.13 | 6.39
60 | Alabama | BLOUNT |  | 04 | 0053541 | This project involves the repaving of approximately 6 miles of US Highway 231 from US Highway 278 to Cullman County | Pavement Improvement | 04/20/2010 |  |  | 1223129.83 | 6.214
61 | Alabama | BLOUNT |  | 04 | 0053542 | This project involves the repaving of about 4 miles of US Highway 231 from State Highway 79 to County Road 26 in Blount County | Pavement Improvement | 04/20/2010 |  |  | 1018632.19 | 3.706
62 | Alabama | ST CLAIR |  | 06 | 0053543 | This project involves the repaving of 7.5 miles of US Highway 231 from just north of Interstate 20 to a couple miles north of Wattsville in Ashville. | Pavement Improvement | 07/16/2009 | 08/22/2009 | 05/01/2010 | 1600829.13 | 7.51
63 | Alabama | COVINGTON |  | 02 | 0055504 | This project involves the repaving of 7 miles of State Highway 55 from US Highway 84 to the North city limits of Red Level | Pavement Improvement | 10/08/2009 |  |  | 4075392.73 | 6.548
64 | Alabama | BUTLER |  | 02 | 0055505 | This project involves the repaving of a little over 1 mile of State Highway 55 from the Conecuh County Line to US Highway 31 in McKenzie | Pavement Improvement | 07/23/2009 | 09/02/2009 | 05/01/2010 | 546999.66 | 1.169
65 | Alabama | HALE |  | 07 | 0060500 | This project involves the repaving and widening of approximately 11 miles of State Highway 60 from State Highway 14 to State Highway 69 near Havana | Pavement Improvement | 04/21/2010 |  |  | 4994006.63 | 11.31
66 | Alabama | DALLAS |  | 07 | 0066502 | This project involves the repaving and 2 foot widening for approximately 5 miles of State Highway 66 from Marengo County line to State Highway 5 in Dallas County | Pavement Improvement | 02/12/2010 |  |  | 1252509.19 | 4.959
67 | Alabama | MARENGO |  | 07 | 0069521 | This project involves the widening of approximately 12 miles of State Highway 69 in Marengo County from US Highway 43 to the Hale County line | Pavement Improvement | 07/23/2009 | 08/25/2009 | 05/01/2010 | 940710.25 | 11.643
68 | Alabama | FRANKLIN |  | 04 | 0069523 | This project involves the repaving of about 4 miles of State Highway 69 from Interstate 65 in Good Hope to the US Highway 31 intersection in Cullman | Pavement Improvement | 07/22/2009 | 09/01/2009 | 05/01/2010 | 1281264.24 | 3.7
69 | Alabama | HALE |  | 07 | 0069525 | This project involves the repaving and extension of culvert pipes to improve roadside safety along 2 milesof State Highway 69 from the Marengo County line to US Highway 80 in Hale County | Pavement Improvement | 07/23/2009 | 08/22/2009 | 05/01/2010 | 486659.58 | 1.994
70 | Alabama | CLARKE |  | 01 | 0069526 | This project involves repaving approximately 9 miles of State Highway 69 from north of County Road 23 (Salt Works Road) to about a mile north of County Road 368 (Dalmation Lane) in Clarke County | Pavement Improvement | 03/02/2010 |  |  | 2227290.66 | 8.781
71 | Alabama | MARENGO |  | 07 | 0069529 | This project involves the repaving of about 12 miles of State Highway 69 in Marengo County from US Highway 43 to the Hale County line | Pavement Improvement | 07/23/2009 | 08/30/2009 | 05/01/2010 | 2904189.23 | 11.643
72 | Alabama | BLOUNT |  | 04 | 0075515 | This project involves the repaving of aprroximately 4 miles of State Highway 75 from from Brooks Lane (County Road 363) in Allgood to 2nd Street (County Road 58) in Oneonta | Pavement Improvement | 09/15/2009 | 10/02/2009 | 07/01/2010 | 1730844.36 | 3.57
73 | Alabama | DE KALB |  | 04 | 0075516 | The project involves the repaving and widening of 4 miles of State Highway 75 (McCurdy Avenue) from about a half mile north of County Road 50 (Traylor Street) in Fyffe to just south of State Highway 3 | Pavement Improvement | 10/06/2009 |  |  | 3208646.19 | 4.03
74 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 0079510 | This project involvesthe repaving of approximately 5 miles of State Highway 79 (Pinson Valley Parkway) from Winewood Road to State Highway 151 just west of Pinson in Jefferson County | Pavement Improvement | 07/21/2009 | 09/02/2009 | 05/01/2010 | 2402325.05 | 5.2
75 | Alabama | PIKE |  | 02 | 0093501 | This project involves the repaving of about 2 miles of State Highway 93 from Us Highway 231 to the North city limits of Brundidge | Pavement Improvement | 08/10/2009 | 09/02/2009 | 06/01/2010 | 840752.4 | 2.25
76 | Alabama | MONTGOMERY | MONTGOMERY | 03 | 0097503 | This project involves the repaving and 2 foot widening of approximately 1 mile State Highway 97 from Crenshaw County line to north of US Highway 31 near Letohatchee | Pavement Improvement | 08/13/2009 | 09/22/2009 | 06/01/2010 | 569032.16 | 1.187
77 | Alabama | WALKER |  | 04 | 0102530 | This project involves the repaving of about 7 miles of State Highway 102 from the Fayette County Line to the intersection with Old Birmingham Highway in Walker County | Pavement Improvement | 02/02/2010 |  |  | 942000 | 6.896
78 | Alabama | GENEVA |  | 02 | 0103508 | This project involves the repaving and widening of 9 miles of State Highway 103 from the Florida State line to State Highway 52 in Slocomb | Pavement Improvement | 11/16/2009 | 12/04/2009 |  | 2513466.31 | 8.933
79 | Alabama | COOSA |  | 03 | 0115503 | This project involves the repaving of about 3 miles of State Highway 115 from State Highway 9 to US Highway 280 | Pavement Improvement | 07/08/2009 | 09/02/2009 | 05/01/2010 | 1163764.15 | 3.19
80 | Alabama | JACKSON |  | 05 | 0117505 | This project involves the repaving of State Highway 117 in Jackson County from the intersection with State Highway 71 north for about 6 miles. | Pavement Improvement | 01/19/2010 |  |  | 1600620.95 | 5.73
81 | Alabama | WALKER |  | 04 | 0118508 | This project involves the repaving of about 4 miles of US Highway 78 in Carbon Hill from 4th Street to Ripley Loop Road. | Pavement Improvement | 09/25/2009 | 10/09/2009 | 07/01/2010 | 1351912.76 | 3.676
82 | Alabama | AUTAUGA |  | 02 | 0123200 | This project involves the repaving of approximatley 3 miles of Autauga County Road 37 from Autauga County Road 24 to the Chilton County Line and is located North of Billingsley, Alabama. | Pavement Improvement | 01/19/2010 | 01/19/2010 |  | 265000 | 2.84
83 | Alabama | WALKER |  | 04 | 0124500 | This project involves the repaving of approximately 10 miles of Old Birmingham Highway from US Highway 78 south to the intersection with State Highway 69 in Walker County. | Pavement Improvement | 02/02/2010 |  |  | 1566988.39 | 10.896
84 | Alabama | FAYETTE |  | 04 | 0129502 | This project involves the repaving of approximately 7 miles of State Highway 129 from US Highway 43 to County Road 49 in Hubbertville | Pavement Improvement | 08/10/2009 | 08/27/2009 | 06/01/2010 | 1679635.45 | 7.26
85 | Alabama | LAUDERDALE |  | 05 | 0133501 | This project involves the repaving of State Highway 133 from State Highway 20 to Magnum Street in the city of Florence | Pavement Improvement | 04/21/2010 |  |  | 5086063.39 | 8.386
86 | Alabama | COLBERT | FLORENCE | 05 | 0133503 | This project involves the repaving of State Highway 133 from near Old Highway 20 (Colbert County Road 22) to Lincoln Avenue just south of Avalon Avenue | Pavement Improvement | 06/23/2010 |  |  | 602754.26 | 2.545
87 | Alabama | BIBB |  | 06 | 0139502 | This project involves the repaving of 7 miles of State Highway 139 from Six Mile Creek to just north of the Shelby County line | Pavement Improvement | 09/10/2009 | 10/08/2009 | 07/01/2010 | 2128141.35 | 7.104
88 | Alabama | TALLADEGA |  | 03 | 0148500 | This project involves the repaving and 2 foot widening of about 2 miles of State Highway 148 from State Highway 21 to the east city limits of Sylacauga | Pavement Improvement | 07/23/2009 | 09/06/2009 | 05/01/2010 | 623949.72 | 1.78
89 | Alabama | CLARKE |  | 01 | 0154501 | This project involves repaving and widening for about 8 miles on State Highway 154 from 1 mile west of County Road 24 to US Highway 43 in Clarke County | Pavement Improvement | 04/21/2010 |  |  | 3534634.11 | 7.6
90 | Alabama | CHILTON |  | 06 | 0155500 | This project involves the repaving and widening of 4 miles of State Highway 155 in Chilton County from near County Road 33 to the Shelby County line | Pavement Improvement | 08/18/2009 | 09/03/2009 | 06/01/2010 | 1675952.78 | 4.076
91 | Alabama | COLBERT | FLORENCE | 05 | 0157514 | This project involves the repaving and the upgrade of bridge rails to current safety standards along State Highway 157 from the lawrence County Line to State Highway 20 in Colbert County | Pavement Improvement | 09/15/2009 | 09/30/2009 | 07/01/2010 | 3612416.49 | 7.495
92 | Alabama | WILCOX |  | 07 | 0162501 | This project involves the repaving of 3 miles State Highway 162 from west of Dixon Creek to west of County Road 28 in Wilcox County | Pavement Improvement | 02/09/2010 |  |  | 649261.27 | 3.141
93 | Alabama | PERRY |  | 07 | 0175500 | This project involves the repaving and widening of State Highway 175 from State Highway 14 near Heiberger to State Highway 5 in Perry County | Pavement Improvement | 09/11/2009 |  | 07/01/2010 | 1730838.95 | 5.382
94 | Alabama | MOBILE | MOBILE | 01 | 0188501 | This project involves the repaving of about 9 miles of State Highway 188 from Franklin Creek to Oddfellows Cemetery in Baldwin County | Pavement Improvement | 01/19/2010 | 02/10/2010 |  | 1279713.65 | 8.67
95 | Alabama | CALHOUN | ANNISTON | 03 | 0192901 | This project provides for grading the road so it can be paved to a four lane roadway from 1500' South of Lake Yahoo to SR-1 (US-431) in Anniston. The project will be partial base and pave wih a bridge | New Construction | 09/21/2009 | 10/09/2009 | 07/01/2011 | 37189383.68 | 2.56
96 | Alabama | GENEVA |  | 02 | 0196500 | This project involves the repaving of Magnolia Avenue from State Highway 52 to State Highway 27 in Geneva | Pavement Improvement | 01/19/2010 |  |  | 582754.07 | 1.69
97 | Alabama | BARBOUR |  | 02 | 0198500 | This project involves the repaving and widening of approximately 2 miles of State Highway 198 in Barbour County from just east of State Highway 239 to State Highway 30 | Pavement Improvement | 02/03/2010 | 02/22/2010 |  | 547493.22 | 1.61
98 | Alabama | BALDWIN |  | 01 | 0210200 | This project involves the repaving of County Road 32 from Sate Highway 59 to County Road 87 in Baldwin County | Pavement Improvement | 05/13/2010 |  |  | 265000 | 7
99 | Alabama | MOBILE | MOBILE | 01 | 0213502 | This project involves the repaving and widening of about 3 miles of State Highway 213 (Shelton Beach Road) from State Highway 158 (Industrial Parkway) to US Highway 43 (Saraland Boulevard) in Saraland | Pavement Improvement | 07/22/2009 | 08/28/2009 | 05/01/2010 | 664616.17 | 2.88
100 | Alabama | BULLOCK |  | 02 | 0223501 | This project involves the repaving and 2 foot widening of a bout a mile of State Highway 223 (Baskin Street) from the Bullock County High School to the junction of US Highway 82 in Union Springs | Pavement Improvement | 09/10/2009 | 09/28/2009 | 07/01/2010 | 390602.39 | 0.75
101 | Alabama | BARBOUR |  | 02 | 0239501 | This project involves the repaving and widening of 2 miles of State Highway 239 from State Highway 51 to State Highway 51 North in Barbour County | Pavement Improvement | 02/03/2010 | 02/22/2010 |  | 542317.97 | 1.916
102 | Alabama | FRANKLIN |  | 04 | 0241501 | This project involves the repaving of about a mile of State Highway 241 from just south of the Marion County line to State Highway 237 in Franklin County | Pavement Improvement | 07/30/2009 | 08/28/2009 | 05/01/2010 | 718021.14 | 1.024
103 | Alabama | LOWNDES |  | 02 | 0263501 | This project involves the repaving and 2 foot widening of approximately 9 miles of State Highway 263 from the Butler County line to State Highway 21 | Pavement Improvement | 01/26/2010 |  |  | 2688166.21 | 8.48
104 | Alabama | WILCOX |  | 07 | 0265500 | This project involves the repaving and safety widening for about 7 miles of State Highway 265 from just north of County Road 51 to State Highway 41 in Wilcox County | Pavement Improvement | 02/09/2010 |  |  | 1697207.27 | 6.83
105 | Alabama | CHEROKEE |  | 03 | 0273500 | The project involves the repaving and widening of approximately 16 miles of State Highway 273 from State Highway 68 in Leesburg to State Highway 35 near Blanche | Pavement Improvement | 08/12/2009 |  | 06/01/2010 | 4016700.1 | 15.836
106 | Alabama | BARBOUR |  | 02 | 0325201 | This project involves the repaving of Barbour County Road 49 from US Highway 82 to Barbour County Road 89 at Springhill | Pavement Improvement | 05/20/2010 |  |  | 265000 | 4.203
107 | Alabama | BULLOCK |  | 02 | 0621200 | This project will completely rebuild the pavement structure (full depth reclamation) down to the subgrade, then the pavement will be widened and repaved approximately 8 miles of Bullock County Road 2 | Pavement Improvement | 10/22/2009 | 11/18/2009 |  | 265000 | 7.61
108 | Alabama | BUTLER |  | 06 | 0707200 | This project involves the repaving and widening of County Road 15 from State Highway 106 to County Road 38 in Butler County | Pavement Improvement | 05/20/2010 |  |  | 265000 | 7.902
109 | Alabama | CALHOUN |  | 03 | 0800216 | This project involves the replacement of a bridge with an inventory number 1001 and its approaches on Prickett Trail (County Road 553) over Tallassechatchee Creek | Pavement Improvement | 05/25/2010 |  |  | 265000 | 0.255
110 | Alabama | CHAMBERS |  | 03 | 0928200 | This project will completely rebuild the pavement structure (full depth reclamation) down to the subgrade, then the pavement will be repaved approximately 5 miles of County Road 267 in Chambers County | Pavement Improvement | 07/27/2009 | 09/02/2009 | 05/01/2011 | 265000 | 5.571
111 | Alabama | CHEROKEE |  | 03 | 1006201 | "This project involves the repaving of approximately 4 miles of Cherokee County Road 71 (Centre Rd.) from 0.6 miles north of Cherokee County Road 59 ( to the Terrapin Creek Bridge south of Centre | Pavement Improvement | 12/29/2009 |  |  | 265000 | 4.2
112 | Alabama | CHOCTAW |  | 07 | 1205201 | This project involves the repaving and widening of County Road 32 from County Road 9 to State Highway 17 in Choctaw County | Pavement Improvement | 05/18/2010 |  |  | 265000 | 6.13
113 | Alabama | CLAY |  | 03 | 1405201 | "This project involves the repaving of approximately 7 miles of Clay County Road 35 (Bluff Springs Road) from the Tallapoosa County Line to the intersection of Clay County Road 132 (Sardis Road) south | Pavement Improvement | 03/02/2010 |  |  | 265000 | 6.9
114 | Alabama | COLBERT | FLORENCE | 05 | 1709200 | This project involves the repaving of County Road 57 from County Road 61 to the Joe Wheeler Highway (State Highway 20) in Tuscumbia | Pavement Improvement | 08/19/2009 | 09/30/2009 | 06/26/2010 | 330972.08 | 2.727
115 | Alabama | COLBERT |  | 05 | 1710201 | This project involves the replacement of a bridge with inventory number 001173 over Rock Creek on Colbert County Road 1 (Maud Rd.) | Other | 08/27/2009 |  |  | 107767.49 | 0.246
116 | Alabama | COLBERT | FLORENCE | 05 | 1717200 | This project involves the repaving of 1 mile of River Road from County Road 48 to Brick School Road in Muscle Shoals | Pavement Improvement | 10/13/2009 |  |  | 135105.43 | 0.893
117 | Alabama | CONECUH |  | 02 | 1818202 | "This project involves the repaving of approximately 4 miles of Conecuh County Road 23 from U.S. Highway 31(N. Jackson Street) northwesterly to Interstate 65 (I-65) north of Castleberry | Pavement Improvement | 11/09/2009 | 12/08/2009 |  | 265000 | 4.16
118 | Alabama | COOSA |  | 03 | 1907200 | This project involves the repaving of County Road 85 from County Road 50 at Kellyton to County Road 86 in Coosa County | Pavement Improvement | 05/18/2010 |  |  | 265000 | 6.2
119 | Alabama | COFFEE |  | 02 | 1E34600 | This project involves the repaving of County Road 709 in Enterprise from State Highway 167 to State Highway 134 | Pavement Improvement | 09/11/2009 | 10/12/2009 | 07/01/2010 | 265000 | 2.589
120 | Alabama | CRENSHAW |  | 02 | 2032200 | "This project involves the widening and repaving of Covington County Road 98 from U.S. Highway 84 to Covington County Road 49 in Covington County. | Pavement Improvement | 10/07/2009 |  |  | 265000 | 1.241
121 | Alabama | CRENSHAW |  | 02 | 2111202 | "This project involves the repaving of approximately 5 miles of Crenshaw County Road 6 (Glenwood Rd./Luverne St.) from the Luverne | Pavement Improvement | 05/18/2010 |  |  | 265000 | 3.963
122 | Alabama | CULLMAN |  | 04 | 2215200 | This project involves the repaving of County Road 1069 from County Road 1043 to County Road 1101 in Cullman County | Pavement Improvement | 05/13/2010 |  |  | 265000 | 6.329
123 | Alabama | DALE |  | 02 | 2304200 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 31 from U.S. Routhe 84/Alabama Route 12 to Dale County Road 43.in Dale County, Alabama. | Pavement Improvement | 05/19/2010 | 06/29/2010 |  | 62917 | 3.969
124 | Alabama | DALE |  | 02 | 2311201 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 73 from Dale County Road 14 to the Henry County Line in Dale County, Alabama. | Pavement Improvement | 05/19/2010 | 06/29/2010 |  | 70257 | 4.432
125 | Alabama | DALE |  | 02 | 2311202 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 14 from Dale County Road 67 to Dale County Road 73 in Dale County, Alabama. | Pavement Improvement | 05/19/2010 | 06/29/2010 |  | 20449 | 1.29
126 | Alabama | DALE |  | 02 | 2315201 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 83 from Dale County Road 62 to Dale County Road 36 in Dale County, Alabama. | Pavement Improvement | 05/19/2010 | 06/29/2010 |  | 51599 | 3.255
127 | Alabama | DALE |  | 02 | 2331200 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 63 from U.S. Routhe 231/Alabama Route 53 to Dale County Road 14.in Dale County, Alabama. | Pavement Improvement | 05/19/2010 | 06/29/2010 |  | 33131 | 2.09
128 | Alabama | DALLAS |  | 07 | 2446200 | This projects involves the repaving and widening of county road 81 from State Highway 22 to State Highway 22 at Valley Grande | Pavement Improvement | 06/01/2010 |  |  | 265000 | 3.627
129 | Alabama | ELMORE |  | 02 | 2601201 | This projects involed paving the shoulder and traffic striping along Rifle Range Road from Redland Road to Mitchell Creek Road | Pavement Improvement | 01/26/2010 |  |  | 259058.2 | 6.61
130 | Alabama | ELMORE |  | 02 | 2606202 | This project involves the repaving andstriping of Main Street from 1st Avenue east to the Eclectic city limits | Pavement Improvement | 02/24/2010 |  |  | 265000 | 1.634
131 | Alabama | ESCAMBIA |  | 01 | 2710200 | "This project involves the widening and repaving of approximately 5 miles of Escambia County Road 17 (Stanley Rd.) from Escambia County Road 27 (Robinsonville Rd.) to Alabama Highway Route 113 | Pavement Improvement | 01/05/2010 | 02/02/2010 |  | 265000 | 4.72
132 | Alabama | ETOWAH |  | 04 | 2810200 | This proeject involves the milling and repaving of Gilley Road from Centre Road to the Cherokee County line | Pavement Improvement | 01/27/2010 |  |  | 265000 | 1.41
133 | Alabama | DE KALB |  | 04 | 2F07600 | This project involves the widening and repaving of County Road 89 from the Fort Payne city limits to County Road 78. | Pavement Improvement | 05/12/2010 |  |  | 265000 | 2.9
134 | Alabama | FRANKLIN |  | 04 | 3000209 | The replacement of the bridge with identification number 001134 and the roadway approaches over Bear Creek located on Franklin County Road 93 in Franklin County, Alabama. | Bridge Replacement | 05/25/2010 |  |  | 265000 | 0.072
135 | Alabama | GENEVA |  | 02 | 3131200 | "This project involves the repaving and widening of approximately 3 miles of Geneva County Road 4 (Goathill Road) from Alabama State Highway 87 to Geneva County Road 120 (Ausley Road) West of Geneva | Other | 11/09/2009 | 12/28/2009 | 04/30/2010 | 265000 | 6.18
136 | Alabama | GREENE |  | 07 | 3200205 | This project involves the replacement of bridge over South Needham Creek on County Road 25 | Pavement Improvement | 05/11/2010 |  |  | 265000 | 0.06
137 | Alabama | HALE |  | 07 | 3314200 | This project involves the widening and resurfacing of County Road 32 from State Highway 69 to State Highway 25 | Pavement Improvement | 04/15/2010 |  |  | 530000 | 6.456
138 | Alabama | HENRY |  | 02 | 3408200 | "This project involves the widening and repaving of Henry County Road 99 from Henry County Road 41 to Henry County Road 107 in Abbeville | Pavement Improvement | 08/21/2009 | 09/09/2009 | 06/01/2010 | 265000 | 1.706
139 | Alabama | HOUSTON |  | 02 | 3500214 | This project will replace the bridge with inventory number 003313 over Cedar Creek on East Cook Road (County Road 438) about a half north of Ed Tolar Road in Houston County | Bridge Replacement | 07/14/2009 | 08/01/2009 | 05/01/2010 | 265000 | 0.038
140 | Alabama | JACKSON |  | 05 | 3621201 | The widening and repaving of Jackson County Road 88 from Alabama Route 71 to the Dekalb County Line in Jackson County, Alabama. | Pavement Improvement | 05/12/2010 |  |  | 265000 | 4.15
141 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 3713200 | Rex Lake Road is currently a 2 lane county road that serves the Barber Motorsports facility and the recently constructed Bass Pro Shop. The project will convert the existing 2 lane to a 4 lane divide | Pavement Improvement | 10/30/2009 |  |  | 5497447.75 | 0.956
142 | Alabama | LAMAR |  | 04 | 3804200 | "This project involves the repaving of approximately 10 miles of Lamar County Road 49 & 20 (Pickens St.) from the Northern Right of Way of the Luxapallila Railroad in Kennedy | Pavement Improvement | 11/04/2009 | 12/03/2009 |  | 265000 | 9.85
143 | Alabama | LAWRENCE |  | 05 | 4000219 | The project involves the replacement of a bridge with the inventory number 003222 on County Road 129 over Pool Creek in Lawrence County | Bridge Replacement | 09/14/2009 | 10/28/2009 | 07/31/2010 | 111054.29 | 0.005
144 | Alabama | LAWRENCE |  | 05 | 4000220 | "This project will replace the bridge for Sandy Creek on Lawrence County Road 150. The bridge has an inventory number of 002345 and wil be replace by a bridge culvert that has 3 barrels that are 10 f | Pavement Improvement | 11/06/2009 |  |  | 153945.71 | 0.006
145 | Alabama | LEE |  | 03 | 4107200 | This project involves the widening and repaving of County Road 401 from County Road 166 to County Road 165 | Pavement Improvement | 05/26/2010 |  |  | 234877.27 | 1.288
146 | Alabama | LOWNDES |  | 02 | 4311200 | This project involves the repaving of County Road 26 from State Highway 21 to west of County Highway 6 | Pavement Improvement | 01/28/2010 |  |  | 265000 | 8.989
147 | Alabama | MACON |  | 03 | 4424203 | This project involves the repaving of County Road 54 from East of the Notasulga city limits to County Road 53 | Pavement Improvement | 01/19/2010 |  |  | 265000 | 2.81
148 | Alabama | MADISON | HUNTSVILLE | 05 | 4500215 | This project will replace a bridge with inventory number 009682 and upgrade the width and safety of the approaching roadway on County Road 50 (Douglass Road) over Douglass Branch approximately a half | Pavement Improvement | 05/27/2010 |  |  | 393737.84 | 0.129
149 | Alabama | MARENGO |  | 07 | 4606201 | The repaving of Marengo County Road 33 from U.S. 43/Alabama Route 13 to Marengo County Road 47 in Marengo County, Alabama. | Pavement Improvement | 05/19/2010 |  |  | 265000 | 4.1
150 | Alabama | MARENGO |  | 04 | 4738200 | This project involves the repaving of County Road 51 from County Road 42 to US Highway 278 (State Highway 74) in Marengo County | Pavement Improvement | 05/19/2010 |  |  | 265000 | 1.59
151 | Alabama | MARSHALL |  | 04 | 4803201 | This project involves repaving County Road 73 (High Point Road) from Old Oneonta Road to Oneonta Cut-off Road | Pavement Improvement | 05/04/2010 |  |  | 196513.15 | 0.767
152 | Alabama | MONROE |  | 01 | 5027200 | This project involves the widening and repaving of County Road 45 from State Highway 21 to County Road 7 | Pavement Improvement | 04/28/2010 |  |  | 265000 | 1.961
153 | Alabama | MORGAN | DECATUR | 04 | 5218200 | This project involves the repaving of South Seneca Drive From the Trinity town limits to Deanna Bridge Highway | Pavement Improvement | 07/01/2009 | 07/02/2009 |  | 49838.24 | 1
154 | Alabama | MORGAN | DECATUR | 04 | 5222200 | This project involves the repaving of less than a mile of Indian Hills Road from Lincoya Circle to Ben Poole Road in the city of Decatur | Pavement Improvement | 07/18/2009 | 08/01/2009 |  | 84137.1 | 1.52
155 | Alabama | MORGAN | DECATUR | 05 | 5226200 | This project involves repaving and striping of Finley Road from State Highway 20 to Gate | Pavement Improvement | 04/22/2010 |  |  | 566265 | 1.69
156 | Alabama | PERRY |  | 07 | 5303200 | This project involves the repaving of about 7 miles of County Road 12 from 2 miles east of State Highway 183 to State Highway 5 in Perry County | Pavement Improvement | 10/13/2009 |  |  | 265000 | 6.91
157 | Alabama | PICKENS |  | 07 | 5422200 | The project involves the milling, repavaing, and striping of County Road 85 from the Sumter County line to State Highway 17 | Pavement Improvement | 01/27/2010 |  |  | 265000 | 4.493
158 | Alabama | PIKE |  | 02 | 5505202 | This project involves the repaving of County Road 2276 from the Crenshaw County line to County Road 2290 and also the repaving of County Road 2290 from County Road 2276 to County Road 2262 near Hender | Pavement Improvement | 07/16/2009 | 08/15/2009 | 05/01/2010 | 265000 | 5.565
159 | Alabama | RANDOLPH |  | 03 | 5605200 | This project involves the widening and repaving of Randolph County Road 82 from the Meadows Bridge (Little Tallapoosa River) to Randolph County Road 87. | Pavement Improvement | 09/28/2009 | 10/22/2009 | 07/31/2010 | 265000 | 5.642
160 | Alabama | RUSSELL |  | 03 | 5704200 | This project will relocate and replace a bridge on Russell County Road 4 over Weolustee Creek north of Pitttsview | Pavement Improvement | 09/30/2009 | 10/09/2009 |  | 265000 | 0.056
161 | Alabama | ST CLAIR |  | 06 | 5824200 | The project involves the repaving of County Road 12 from County Road 6 to State Highway 174 | Pavement Improvement | 05/04/2010 |  |  | 530000 | 7.222
162 | Alabama | LIMESTONE | DECATUR | 05 | 5A20600 | This project involves the widening and repaving of Lucas Ferry Road (County Road 45) from Harris Station Road (County Road 45) to Nuclear Plant Road (County Road 677). | Pavement Improvement | 06/01/2010 | 07/01/2010 |  | 265000 | 2.05
163 | Alabama | SUMTER |  | 07 | 6020200 | "This project involves the repaving and extending the culvert pipes to improve the roadside safety of approximately 2 miles of Sumter County Road 27 from the Mississippi State line south to Sumter Co | Pavement Improvement | 10/16/2009 |  |  | 265000 | 7.01
164 | Alabama | TALLADEGA |  | 03 | 6111200 | This project involves the repaving of Horn's Lake Road (County Road 209) from State Highway 77 to the Clay County line | Pavement Improvement | 06/01/2010 |  |  | 358844.72 | 2.7
165 | Alabama | TALLAPOOSA |  | 03 | 6233200 | "This project includes widening and repaving of approximately 7 milles of Tallapoosa County Road 44 (Dudleyville Road) from Tallapoosa County Road 32 (Denver Road) to the Chambers County Line | Pavement Improvement | 01/07/2010 | 03/01/2010 | 05/31/2010 | 265000 | 7.25
166 | Alabama | TUSCALOOSA | TUSCALOOSA | 07 | 6303200 | This project involves the milling and paving of Hagler Coaling Road (County Road 239) from Serty Boyd Road (County Road 240) to Clements Road (State Highway 566) in Tuscaloosa County | Pavement Improvement | 05/25/2010 |  |  | 1221289 | 5.9
167 | Alabama | TUSCALOOSA | TUSCALOOSA | 07 | 6312200 | The replacement of the bridge and roadway approaches with a triple barrel box bridge culvert with identification number 000864 over Cooley Creek on Tuscaloosa County Road 97 (Eastern Valley Road) near | Pavement Improvement | 06/24/2010 |  |  | 769000 | 0.013
168 | Alabama | WASHINGTON |  | 01 | 6500206 | The replacement of the bridge over the Escatawpa River with a new Precast Bridge in Washington County, Alabama. | Bridge Replacement | 05/27/2010 |  |  | 265000 | 0.098
169 | Alabama | WILCOX |  | 07 | 6617200 | The repaving of Wilcox County Road 29 from Gees Bend Landing to 0.47 mile north of Chilatchee Park Road in Wilcox County, Alabama. | Pavement Improvement | 06/02/2010 |  |  | 265000 | 7.149
170 | Alabama | WINSTON |  | 04 | 6721200 | This project involves the repaving of County Road 14 from County Road 41 to County Road 39 in Winston County | Pavement Improvement | 05/18/2010 |  |  | 265000 | 3.04
171 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 7005600 | This project will realign 3 intersections in the City of Hoover and replace the existing signals. The realignments will improve driver's sight distance and visibility. | Pavement Improvement | 12/15/2009 | 01/12/2010 | 07/01/2010 | 1878317.89 | 0.166
172 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 7020600 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Widening | 05/05/2010 |  |  | 1375027 | 0.6
173 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 7045600 | This project will add a center two way left turn lane to Jefferson Avenue (County Road 18) from the Birmingham City limits to 50th Street. | Other | 02/26/2010 |  |  | 1659402.64 | 1.5
174 | Alabama | JEFFERSON | BIRMINGHAM | 07 | 7045601 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Improvement | 11/12/2009 |  |  | 2624716.25 | 0.75
175 | Alabama | SHELBY | BIRMINGHAM | 06 | 7112604 | This project involves the widening and repaving of County 17 from north of County Road 270 to apprroximately south of Lacey Avenue. This project includes the replacement of the bridge over Beaverdam | Other | 01/29/2010 |  |  | 265000 | 0.48
176 | Alabama | JEFFERSON | BIRMINGHAM | 07 | 7173600 | This project will add dual left turn lanes on East Lake Blvd to SR-79 SB. The improvements will help relieve congestion by allowing more vehicles to make a left turn in a shorter amount of time. | Pavement Widening | 05/26/2010 |  |  | 339737 | 0.17
177 | Alabama | JEFFERSON | BIRMINGHAM | 07 | 7229601 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Widening | 11/09/2009 |  |  | 2900626.44 | 1.4
178 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 7273600 | The repaving of Jefferson County Road 2133 known as Deefoot Parkway from U.S. Route 11/Alabama Route 7 to Interstate 59. | Pavement Improvement | 05/26/2010 |  |  | 265000 | 1.584
179 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 7321600 | This project is for the relocation of utilities that conflict with the construction of Chapel Lane Extension from Al Seier Road to Galleria Boulevard in Birmingham. | Other | 02/25/2010 |  |  | 1659402.64 | 0.75
180 | Alabama | CALHOUN | ANNISTON | 03 | 7400600 | This project involves the repaving of approximately 3 miles of Friendship Road in the city of Oxford from SR-21 to Boiling Spring Road | Pavement Improvement | 07/07/2009 |  |  | 665600 | 7.2
181 | Alabama | CALHOUN | ANNISTON | 03 | 7401601 | This project involves the installation of a new traffic signal at the intersection of Noble Street (County Road 105) and Greenbrier Dear Road (County Road 198) | Safety/Traffic Management | 04/13/2010 |  |  | 65845.55 | 0
182 | Alabama | CALHOUN | ANNISTON | 03 | 7425600 | The project will consist of pole replacement, new traffic lights to upgrade the traffic signal at Bill Robinson Parkway. | Safety/Traffic Management | 04/13/2010 |  |  | 104994.36 | 0
183 | Alabama | CALHOUN | ANNISTON | 03 | 7431600 | This project involves the repaving of Alexandria/Jacksonville Road from Francis Street to South Jacksonville city limits | Pavement Improvement | 04/28/2010 |  |  | 400000 | 1.57
184 | Alabama | CALHOUN | ANNISTON | 03 | 7460600 | This project involves the replacement of a bridge on Eulaton Road (County Road 81), north of State Highway 202 near County Road 109 | Pavement Improvement | 05/11/2010 |  |  | 313175.88 | 0.208
185 | Alabama | MOBILE | MOBILE | 01 | 7507600 | This project will replace a bridge and upgrade the width and safety of the approaching roadway on Michigan Avenue over the CSX railroad in Mobile | Pavement Improvement | 05/06/2010 |  |  | 3304000 | 0.191
186 | Alabama | MOBILE | MOBILE | 01 | 7548600 | This project involves the repaving about a mile of Springhill Avenue from McGregor Avenue to Intersate 65 in the city of Mobile | Pavement Improvement | 08/27/2009 | 09/03/2009 | 07/01/2010 | 312513.08 | 1.3
187 | Alabama | MOBILE | MOBILE | 01 | 7548601 | This project involves the repaving of less than a mile of Springhill Avenue from Interstate 65 to Moffet Road in the city of Mobile | Pavement Improvement | 08/27/2009 | 09/03/2009 | 07/01/2010 | 124363.53 | 0.6
188 | Alabama | MOBILE | MOBILE | 01 | 7552600 | This project involves the repaving of Howells Ferry Road (County Road 605) from Snow Road (County Road 25) to Cody Road (County Road 429) | Pavement Improvement | 01/28/2010 |  |  | 1322100 | 5
189 | Alabama | MOBILE | MOBILE | 01 | 7560600 | This project involves the repaving of about 3 miles of West Main Street from Prichard Avenue to Branch Avenue in the city of Mobile | Pavement Improvement | 06/22/2009 |  |  | 903586.96 | 6.448
190 | Alabama | MOBILE | MOBILE | 01 | 7573600 | This project involves traffic stripe, markings, legends and pavement markers on CR-41 (Celeste Road) from SR-13 (US-43) in Saraland to Lafitte Road. | Safety/Traffic Management | 12/30/2009 | 01/14/2010 |  | 136752.25 | 2.5
191 | Alabama | MACON | MOBILE | 01 | 7597600 | This project involves the repaving and widening of Viaduct Road from east of Mike Box Bridge to Warrior Gulf and from Mike Box Bridge to Southern Ionix. This project also includes the repaving of via | Pavement Improvement | 07/07/2009 |  |  | 535000 | 2
192 | Alabama | MOBILE | MOBILE | 01 | 7599600 | This project involves the repaving of about 1 mile of Baker from Interstate 64 to US Highway 43 north of Mobile | Pavement Improvement | 06/17/2009 |  |  | 248885.83 | 2
193 | Alabama | MOBILE | MOBILE | 01 | 7614600 | This project involves the repaving of McCrary Road (County Road 604) from US Highway 98 (SR-42) to Lott Road (SR-217) | Pavement Improvement | 02/03/2010 |  |  | 699540.66 | 2.9
194 | Alabama | MOBILE | MOBILE | 01 | 7615600 | Mobile County will widen the existing 20 eet width pavement of Half Mile Road 2 feet on each side and then resurface with asphalt the entire 24 feet width from Beverly Road eastwardly approximately 2 | Pavement Improvement | 07/24/2009 | 08/29/2009 | 05/01/2010 | 265000 | 1.837
195 | Alabama | MOBILE | MOBILE | 01 | 7616600 | This project involves the repaving of about 6 miles of the Irvington-Bayou La Batre Highway from State Highway 188 to US Highway 90 in the town of Irvington | Pavement Improvement | 04/29/2010 |  |  | 1609928.14 | 5.74
196 | Alabama | MONTGOMERY | MONTGOMERY | 02 | 7724601 | The existing two-lanes of Perry Hill Road in Montgomery from Interstate 85 to Harrison Road will be widened to provide an undivided four-lane highway. | Pavement Widening | 04/15/2010 |  |  | 1949739.91 | 0.511
197 | Alabama | ELMORE | MONTGOMERY | 02 | 7804601 | This project involves the repaving of Alabama River Parkway (County Road 2) from State Highway 143 to Jackson Lake Road (County Road 60) | Pavement Improvement | 05/05/2010 | 05/20/2010 |  | 464837.88 | 1.69
198 | Alabama | AUTAUGA | MONTGOMERY | 02 | 7812601 | This project involves the repaving of McQueen Smith Road (County Road 75) from East Main Street (County Road 2) to State Highway 14 | Pavement Improvement | 04/21/2010 |  |  | 501165.98 | 1.467
199 | Alabama | AUTAUGA | MONTGOMERY | 02 | 7899600 | This project involves the repaving of Gin Shop Hill Road (County Road 29) from West 4th Street (State Highway 206) to US Highway 82 (State Highway 6) | Pavement Improvement | 04/14/2010 |  |  | 217453.97 | 1.083
200 | Alabama | RUSSELL | COLUMBUS (GA) | 03 | 8007601 | "This project involves the repaving of Russell County Road 28 (Sandfort Road) from the West City Limit of Phenix City | Pavement Improvement | 07/31/2009 |  |  | 542695 | 5.12
201 | Alabama | RUSSELL | COLUMBUS (GA) | 03 | 8018600 | "This project involves the repaving Russell County Road 427 (Opelika Rd.) from Russell County Road 418 (Crawford Rd.) to 22nd Street and Russell County Road 427 (Opelika Road) from Russell County Road | Pavement Improvement | 07/28/2009 |  |  | 294454.37 | 1.82
202 | Alabama | RUSSELL | COLUMBUS (GA) | 03 | 8018601 | This project involves the repaving and striping of Opelika Road (County Road 427) from Cut Rate Road (County Road 296) to south of Stafford Raod (County Road 296) | Pavement Improvement | 12/01/2009 |  |  | 269827.44 | 1.94
203 | Alabama | RUSSELL | COLUMBUS (GA) | 03 | 8041601 | This project involves the repaving and striping of Pierce Road (County Road 427) from US Highway 431/280 in Russell County to Summerville Road in Lee County | Pavement Improvement | 05/11/2010 |  |  | 511097.32 | 1.778
204 | Alabama | ETOWAH | GADSDEN | 04 | 8104600 | This project constructs a new 4 lane roadway approximately 1 mile long between the intersections of Steel Station / Sutton Bridge Roads to I-759. | Pavement Improvement | 12/15/2009 |  |  | 2138433 | 3.36
205 | Alabama | MADISON, MACON | HUNTSVILLE | 05 | 8509601 | This project constructs additional turn lanes on both Wall Triana Highway and US-72 (SR-2) with a signal Modification. | Pavement Improvement | 08/27/2009 |  |  | 738997 | 1.622
206 | Alabama | MORGAN | DECATUR | 05 | 9229600 | This project involves the repaving of Austinville Road SW from Carridale Street to 14 th Street SW and 14th Street SW to Central Parkway in the city of Decatur | Pavement Improvement | 07/08/2009 | 07/09/2009 |  | 121279.93 | 0.66
207 | Alabama | HOUSTON | DOTHAN | 02 | 9412601 | This project involves the repaving of Westgate Parkway from US Highway 84 to US Highway 231 in the city of Dothan | Pavement Improvement | 07/01/2009 | 07/01/2009 |  | 644000 | 4
208 | Alabama | HOUSTON | DOTHAN | 02 | 9412602 | This project involves the repaving of Honeysuckle Road from US Highway 84 to Park Avenue in the city of Dothan | Pavement Improvement | 06/22/2009 | 06/22/2009 |  | 763590 | 5.1
209 | Alabama | HOUSTON | DOTHAN | 02 | 9414601 | This project involves the widening and repaving of Fortner Street (County Road 40) from Brannon Stand Road to Honeysuckle Road | Pavement Improvement | 05/05/2010 |  |  | 105968.88 | 3.05
210 | Alabama | DALE |  | 02 | 9440600 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 75 (Alpha Street) from U.S. Routhe 231/Alabama Route 53 to Dale County Road 112. | Pavement Improvement | 05/19/2010 | 06/29/2010 |  | 26647 | 1.685
211 | Alabama | HOUSTON | DOTHAN | 02 | 9441604 | This project involves the resurfacing of South Brannon Stand Road (CR-59) from 0.06 mile north of SR-52 to 0.30 mile north of CR-40 (Fortner Street). | Pavement Improvement | 01/13/2010 |  |  | 303268.56 | 2.15
212 | Alabama | JEFFERSON | BIRMINGHAM | 06 | 9802918 | This project will improve lane widths and turn lane lengths at selected intersections along Lorna Road. The project will also replace the traffic signals with new equipment. These improvements will | Safety/Traffic Management | 05/19/2010 |  |  | 1246204.81 | 2.9
213 | Alabama | JEFFERSON | BIRMINGHAM | 07 | 9802920 | This project involves the first phase of modification and upgrade to the traffic management center in the city of Birmingham | Safety/Traffic Management | 05/25/2010 |  |  | 660387.5 | 0
214 | Alabama | JEFFERSON | BIRMINGHAM | 06 | CN07908 | This project is the first phase of the Hoover Park Avenue Sidewalks project and involves the addition of sidewalks along Rockview lane from the Rockview Lane/ Park Avenue intersection to the Bluff Par | Safety/Traffic Management | 05/27/2010 |  |  | 79884.75 | 0
215 | Alabama | SHELBY | BIRMINGHAM | 06 | CN07909 | This project involves the addition of sidewalks along Park Avenue in Hoover between Chapel Raod and Farlay Road | Pavement Improvement | 05/27/2010 |  |  | 523634.33 | 0
216 | Alabama | MOBILE, BALDWIN |  | 01 | CN09208 | "This project will repair badly deteriorated pavements at 16 sites located throughout Mobile and Baldwin Counties. The sites are located on various state | Pavement Improvement | 07/27/2009 | 08/29/2009 | 05/01/2010 | 755598.08 | 0
217 | Alabama | MONTGOMERY | MONTGOMERY | 02,03 | CN09906 | This project involves the repaving of various streets in the central business district of Montgomery | Pavement Improvement | 04/29/2010 |  |  | 2156797.86 | 0
218 | Alabama | ELMORE | MONTGOMERY | 02 | CN09908 | This project involves the repaving of the Coosa River Parkway from West Bridge Street to US Highway 231 and the repaving of West Bridge Street from the Coosa River Parkway to North Bridge Street in We | Pavement Improvement | 07/30/2009 | 09/01/2009 | 05/01/2010 | 1207835.61 | 3.459
219 | Alabama | LAUDERDALE |  | 05 | CN10201 | "This project involves the repaving of two different roads. Site 1 is South of Lovelace Crossroads and includes approximately 2 miles of Lauderdale County Road 6 from Lauderdale County Road 219 to Ala | Pavement Improvement | 12/28/2009 |  |  | 265000 | 3.561
220 | Alabama | HOUSTON | DOTHAN | 02 | CN10204 | This project involves the resurfacing of CR-26 (Jordon Avenue) from North ROW SR-12 (US-84) to 0.22 mile east of Glen Lawrence Int. | Pavement Improvement | 01/13/2010 |  |  | 289828.56 | 2.11
221 | Alabama | FAYETTE |  | 04 | CN10208 | This project involves striping various county roads in Fayette County | Safety/Traffic Management | 04/20/2010 |  |  | 265000 | 50.375
222 | Alabama | LAUDERDALE | FLORENCE | 05 | CN10211 | This project involves the repaving of County Road 47 from State Highway 133 to County Road 320 and from County Road 37 to County Road 63 and also the repaving of JC Mauldin Highway from County Road 25 | Pavement Improvement | 05/25/2010 |  |  | 617690 | 5.629
223 | Alabama | BIBB |  | 06 | CN10213 | This project invovles the traffic striping and sign replacement along various county roads in Bibb County | Safety/Traffic Management | 05/23/2010 |  |  | 265000 | 71
224 | Alabama | MARSHALL |  | 04 | CN10214 | This project involves the repaving of Huntsville Road (County Road 414) from Short Creek Bridge ot State Highway 75 | Pavement Improvement | 05/20/2010 |  |  | 58115.61 | 4
225 | Alabama | MADISON | HUNTSVILLE | 05 | CN10215 | The replacement of the bridge with the identification number #2494 over Leslie Branch on Madison County Road 86 (Love Branch Road) near the City of Huntsville, Alabama. | Pavement Improvement | 05/27/2010 |  |  | 425512.9 | 0.216
226 | Alabama | MONTGOMERY | MONTGOMERY | 03 | CN10216 | This project contains two sites listed as follows: Site #1: The repaving of Montgomery County Road 24 known as Cloverdale/Federal Rd. from the Lowndes County Line to US Route 31/Alabama Route 3. Site | Pavement Improvement | 05/13/2010 |  |  | 530000 | 8.02
227 | Alabama | CLEBURNE |  | 03 | CN10217 | This project contains two sites listed as follows: Site #1 :The widening and repaving of Cleburne County Road 34 from US Route 431/ Alabama Route 1 to County Road 13. Site #2: The widening and repa | Pavement Improvement | 05/27/2010 |  |  | 265000 | 3.209
228 | Alabama | COLBERT | FLORENCE | 05 | CN10900 | This project involves the repaving at three different sites in Sheffield. Site #1 is the repaving of Old Jackson Highway from the Tuscumbia city limits to South Montgomery Avenue. Site #2 is South M | Pavement Improvement | 04/28/2009 |  |  | 306788.32 | 1.77
229 | Alabama | MOBILE | MOBILE | 01 | CN10901 | The project involves the restriping of Dead Lake Road from US Highway 43 to Interstate 65 and Radcliff Road from US Highwya 43 to one mile west of Creola city limit | Pavement Improvement | 05/06/2010 | 05/06/2010 |  | 67201.4 | 3.55
230 | Alabama | MOBILE | MOBILE | 01 | CN10902 | This project involves the installation of LED traiffc and pedestrian signals at various intersections in the city of Mobile | Safety/Traffic Management | 04/22/2010 |  |  | 871603.94 | 0
231 | Alabama | COLBERT | FLORENCE | 05 | CN10903 | This project involves the repaving of Gusmus Aveneue from 2nd Street (State Highway 184) to Avalon Avenue, South Broadway Avenue from West 6th Street (County Road 24) to Avalon Avenue and West 6th Str | Pavement Improvement | 04/27/2010 |  |  | 275486.2 | 2.5
232 | Alabama | MORGAN | DECATUR | 04 | CN10905 | This project involves the repaving and striping of portions of Danville Road from Chapel Hill Road to 2nd Street Southwest in the city of Decatur | Pavement Improvement | 04/13/2010 |  |  | 333762.92 | 1.906
233 | Alabama | MORGAN | DECATUR | 04 | CN10906 | This project involves the repaving of 8th Street Southeast from 16th Avenue to Point Mallard Drive and Pont Mallard Drive to Point Mallard Circle in the city of Decatur | Pavement Improvement | 04/14/2010 |  |  | 324082.81 | 2.043
234 | Alabama | MORGAN | DECATUR | 05 | CN10907 | This project involves the repaving and striping of Country Club Road from State Highway 67 to Somerville Road in the city of Decatur | Pavement Improvement | 04/14/2010 |  |  | 147463.47 | 1.08
235 | Alabama | LEE | AUBURN-OPELIKA | 03 | CN10909 | This project involves the repaving of various eligible roads in the city of Auburn | Pavement Improvement | 05/26/2010 |  |  | 1247027.47 | 0
236 | Alabama | MOBILE | MOBILE | 01 | CN10915 | This project involves the purchase of 2 vans for the Association of Retarded Citizens | Other | 10/21/2009 |  |  | 67860 | 0
237 | Alabama | MOBILE | MOBILE | 01 | CN10916 | This project involves sidewalk improvements along State Highway 188 from Alba School to Arnett Street | Transportation Enhancements | 05/06/2010 |  |  | 98976.36 | 1
238 | Alabama | COLBERT | FLORENCE | 05 | CN10918 | This project involves the repaving of North Main Street from 3rd Street to Sheffield city limit and repaving North Cave Street from East Hobson Street to West North Commons Street | Pavement Improvement | 04/28/2010 |  |  | 277689.44 | 1.2
239 | Alabama | LAUDERDALE | FLORENCE | 05 | CN10919 | This project involves the repaving of Hermitage Drive from Royla Avenue to Helton Drive and North Pine Street from North Wood Avenue to Kenneth Court and South Pine Street from West Alabama Street to | Pavement Improvement | 04/27/2010 |  |  | 385824.86 | 0.82
240 | Alabama | MADISON | HUNTSVILLE | 05 | CN10920 | This project involves the repaving of various eligilbe streets in the city of Huntsville | Pavement Improvement | 04/13/2010 |  |  | 2552229.52 | 0
241 | Alabama | MADISON | HUNTSVILLE | 05 | CN10921 | This project involves the repaving of various eligilbe streets in the city of Huntsville | Pavement Improvement | 05/13/2010 |  |  | 1665800.74 | 0
242 | Alabama | MORGAN | DECATUR | 05 | CN10923 | Repaving of Morgan County Route 103 also known as Hayes Street from US Route 31/Alabama Route 3 to Karl Prince Rd. and the repaving of Sparkman Street from Karl Prince Rd. to US Route 31/Alabama Rout | Pavement Improvement | 06/02/2010 |  |  | 253984.88 | 2.321
243 | Alabama | ST CLAIR |  | 06 | I020324 | "This project will convert an existing 4 lane section of interstate to a 6 lane. The completion of this project will tie an existing 6 lane interstate immediately east and immediately west of the pro | Pavement Widening | 10/13/2009 |  | 07/01/2011 | 69572329.45 | 7.87
244 | Alabama | ETOWAH | GADSDEN | 04 | I059342 | Reconstructs a portion of existing concrete Interstate 59 near Gadsden by placing a layer of asphalt on the existing roadway and then placing an 11 inch layer of concrete pavement on the asphalt layer | Pavement Improvement | 05/14/2009 | 06/15/2009 | 04/01/2011 | 47525423.51 | 10.913
245 | Alabama | COLBERT | FLORENCE | 05 | PE09906 | "This project includes improvements to four different repaving sites in Sheffield | Other | 07/01/2009 |  |  | 2056.88 | 2.17
246 | Alabama | MOBILE | MOBILE | 01 | PE09907 | This project involves the adjustment of signal time of various traffic signals in the city of Mobile in order to improve traffic flow | Other | 07/07/2009 |  |  | 149500 | 0
247 | Alabama | COLBERT | FLORENCE | 05 | PE09908 | This project involves the repaving at three different sites in Muscle Shoals. Site #1 is a mile of repaving of Gusmus Avenue between 2nd Street and Avalon Avenue. Site #2 is 1 mile of South Broadway A | Other | 07/07/2009 |  |  | 33359 | 2.5
248 | Alabama | MADISON | HUNTSVILLE | 05 | PE09909 | This project involves the repaving various streets in the city of Huntsville | Other | 07/08/2009 | 07/09/2009 |  | 64974 | 0
249 | Alabama | MADISON | HUNTSVILLE | 05 | PE09910 | This project involves the repaving various streets in the city of Huntsville | Other | 07/08/2009 | 07/09/2009 |  | 150726 | 0
250 | Alabama | MOBILE | MOBILE | 01 | PE09911 | "This project involves the restriping Mobile County Road 917 (Dead Lake Road) from U.S. Highway 43 to Interstate 65 and Mobile County Road 933 (Radcliff Road from U.S. Highway 43 to the Creola | Other | 07/22/2009 |  |  | 15000 | 3.55
251 | Alabama | LAUDERDALE | FLORENCE | 05 | PE09912 | This project involves the repaving at three differenct sites in Florence. Site #1 is the repaving of about a 1 mile section of Hermitage Drive from Royal Avenue to Helton Drive. Site # 2 is the repa | Other | 08/01/2009 | 08/02/2009 |  | 48985 | 0.82
252 | Alabama | MORGAN | DECATUR | 04 | PE09913 | This project involves the repaving of 8th Street SE from 16th Avenue to Point Mallard Drive and Point Mallard Drive to Point Mallard Circle in the city of Decatur | Other | 07/17/2009 | 07/18/2009 |  | 21510 | 2.18
253 | Alabama | MORGAN | DECATUR | 04 | PE09914 | "This project involves the repaving of Country Club Road from Alabama State Highway 67 to Somerville Road in Decatur | Other | 07/17/2009 |  |  | 7761.24 | 1.08
254 | Alabama | MORGAN | DECATUR | 04 | PE09915 | "This project involves the repaving of approximately 4 miles of Morgan County Road 41 (Danville Road) from Morgan County Road 191 (Chapel Hill Rd.) to 2nd Street SW in Decatur | Other | 07/17/2009 | 07/18/2009 |  | 19188 | 1.97
255 | Alabama | MORGAN | DECATUR | 05 | PE09916 | This project involves the repaving of Hayes Street from US Highway 31 to Karl Prince Road and the repaving of Sparkman Street from Karl Prince Road to US Highway 31 in the town of Hartselle | Other | 07/31/2009 |  |  | 9567.09 | 2.4
256 | Alabama | WILCOX |  | 07 | PE10906 | This project involves improvements to the Gees Bend Ferry Terminal Facility | Other | 12/08/2009 |  |  | 153200 | 0
257 | Alabama | LEE | AUBURN-OPELIKA | 03 | PE10907 | This project involves the repaving of various eligible roads in the city of Opelika | Other | 12/16/2009 |  |  | 1101.96 | 0
258 | Alabama | LEE | AUBURN-OPELIKA | 03 | PE10908 | This project involves the repaving of various eligible roads in the city of Auburn | Other | 12/16/2009 |  |  | 3347.53 | 0
259 | Alabama | COLBERT | FLORENCE | 05 | PE10909 | This project involves the repaving of North Main Street from 3rd Street to Sheffield city limit and repaving North Cave Street from East Hobson Street to West North Commons Street | Other | 12/07/2009 |  |  | 27359.78 | 1.2
260 | Alabama | STATEWIDE |  | 03 | SP10904 | This project is to provide funding for an internship for juniors and seniors for careers in the surface transportation industry as provided for by Alabama State University OJT/SS Program. | Other | 05/24/2010 |  |  | 269658 | 0
261 | Alabama | CRENSHAW |  | 02 | TE09900 | This project will add sidewalks to Emment Avenue, Fulton Avenue, U.S. Highway 331 and Sasser Street in Brantley, Alabama in Crenshaw County. | Transportation Enhancements | 01/13/2010 | 02/01/2010 | 12/29/2009 | 250090.5 | 0.9
262 | Alabama | FRANKLIN |  | 04 | TE09901 | This project will add sidewalks to Jackson Avenue in downtown Russelleville, Alabama in Franklin County. | Transportation Enhancements | 02/09/2010 |  |  | 400960 | 0.57
263 | Alabama | ESCAMBIA |  | 01 | TE09904 | This project will add sidewalks along Alco Drive, U.S. Highway 31 and Persimmon Street in downtown Brewton, Alabama in Escambia County. | Transportation Enhancements | 06/01/2010 | 06/14/2010 | 02/16/2010 | 349962.25 | 1.75
264 | Alabama | COVINGTON |  | 02 | TE09906 | "This project involves streetscaping along Alabama State Highway Route 55 (Main Street) in Florala | Transportation Enhancements | 03/24/2010 | 04/08/2010 | 03/05/2010 | 358164 | 0.1
265 | Alabama | MOBILE | MOBILE | 01 | TE09907 | "This project involves the addtion of a sidewalk on University Blvd. from the University Church of Christ to Zeigler Interchange in Mobile | Transportation Enhancements | 02/08/2010 | 03/01/2010 | 05/08/2010 | 100395 | 0.32
266 | Alabama | MONROE |  | 01 | TE09908 | "This project involves the addition of sidewalks along approximately 1 mile of South Mount Pleasant Avenue from Murdock Street to Eagle Point Apartments in Monroeville | Transportation Enhancements | 03/08/2010 | 03/08/2010 | 02/04/2010 | 163200 | 0.78
267 | Alabama | BALDWIN |  | 01 | TE09909 | "This project involves the paving of 2 gravel section of the Hugh Branyon Backcountry Trail | Transportation Enhancements | 04/19/2010 | 04/26/2010 | 04/22/2010 | 377911 | 2.25
268 | Alabama | BALDWIN |  | 01 | TE09910 | "This project will provide a pedestrian connection called the Amber Isle Connection to the Hugh S. Branyon Backcountry Trail in Orange Beach | Transportation Enhancements | 05/06/2010 |  | 05/06/2010 | 304836 | 0.29
269 | Alabama | SHELBY | BIRMINGHAM | 06 | TE09912 | Place Landscaping along Alabama State Route 119 in front of the American Village, in Montevallo, Shelby County, Alabama | Transportation Enhancements | 03/29/2010 | 04/01/2010 | 03/29/2010 | 406918.88 | 0.64
270 | Alabama | TUSCALOOSA | TUSCALOOSA | 07 | TE09913 | Create enhancements to the online Geographical Information System (GIS) computer Tools for research and planning located at 13075 Moundville Archaeological Park in Moundville, | Other | 11/03/2009 | 11/11/2009 | 10/19/2009 | 138650 | 0
271 | Alabama | LOWNDES |  | 02 | TE09915 | "This project involves adding sidewalks to the east side Lowndes County Road 29 in Lowndesboro | Transportation Enhancements | 02/19/2010 | 02/22/2010 | 06/16/2010 | 220000 | 0.69
272 | Alabama | COVINGTON |  | 02 | TE09916 | "This project involves streetscaping (Phase III) of Main Street in Opp | Transportation Enhancements | 06/15/2010 |  |  | 309332 | 0.19
273 | Alabama | CONECUH |  | 02 | TE09921 | "This project will provide pedestrian improvements along Magnolia Avenue | Transportation Enhancements | 03/22/2010 | 03/30/2010 |  | 588209 | 2.08
274 | Alabama | ETOWAH | GADSDEN | 04 | TE09924 | "This project will landscape approximately 1.7 miles of U.S. Highway 431 from Keysburg Road to Bank Street in Glencoe | Transportation Enhancements | 04/13/2010 |  |  | 172500 | 1.49
275 | Alabama | STATEWIDE |  | 01,02,03 | TE09925 | This projects will conduct an Archaeological Survey of the Old Federal Road Statewide to be done byt the University of South Alabama. This project is a research project and is located at the Universi | Other | 01/20/2010 | 02/15/2010 | 10/22/2010 | 48526 | 0
276 | Alabama | MORGAN |  | 05 | TE09927 | "This project involves a Historic Downtown Sidewalk and Canopy Restoration for Hartselle | Transportation Enhancements | 02/17/2010 | 02/22/2010 | 08/25/2010 | 457940 | 0.24
277 | Alabama | BUTLER |  | 02 | TE09928 | "This project involves the addition of sidewalks on U.S. Highway 31 in Georgiana | Transportation Enhancements | 03/15/2010 | 03/15/2010 | 02/18/2010 | 204000 | 0.85
278 | Alabama | DE KALB |  | 04 | TE09929 | "This project involves the addition of sidewalks on Alabama Higway 68 in Crossville | Transportation Enhancements | 02/01/2010 | 04/16/2010 | 08/28/2010 | 503700 | 1.82
279 | Alabama | LOWNDES |  | 02 | TE09930 | "This project involves the addition of sidewalks on Alabama Higway 97 in Hayneville | Transportation Enhancements | 05/07/2010 |  |  | 184092 | 1
280 | Alabama | CALHOUN | ANNISTON | 03 | TE09933 | Construct Project AL 204 Sidewalk- Phase II at Jacksonville State University in Jacksonville, AL. along Alabama Route 204 in Calhoun County, Alabama. | Transportation Enhancements | 04/05/2010 | 04/01/2010 | 05/14/2010 | 77038 | 0.25
281 | Alabama | MOBILE | MOBILE | 01 | TE09935 | This project will add sidewalks to approximately 2 miles of U.S. Highway 43 (Saraland Blvd. N.) from Cleveland Road North to 225 Saraland Blvd. N. ) | Transportation Enhancements | 05/11/2010 | 06/07/2010 | 06/04/2010 | 394885 | 1.2
282 | Alabama | PICKENS |  | 04 | TE09937 | "This project will add sidewalks along 5th Street NW and 2nd Avenue NW from 5th Street Northwest to 7th Street Northwest in Reform | Transportation Enhancements | 04/22/2010 |  |  | 134066 | 0.45
283 | Alabama | MONROE |  | 01 | TE09940 | "This project will add a pedestrian connector between Alabama Southern Community College and Monroe County High School. This Project is located South of Agricultural Road and East of Veterans Drive in | Transportation Enhancements | 04/27/2010 | 05/11/2010 | 03/25/2010 | 387205 | 1.32
284 | Alabama | MONTGOMERY | MONTGOMERY | 03 | TE09945 | Place Landscaping along Alabama Route 271 known as Taylor Road at the Auburn University at Montgomery Campus Property Border with AL -271. | Transportation Enhancements | 04/22/2010 | 05/01/2010 | 06/16/2010 | 12972 | 0.08
285 | Alabama | BARBOUR |  | 02 | TE09946 | This Project involves streetscaping on Main Street in Louisville, Alabama. Barbour County | Transportation Enhancements | 01/20/2010 | 02/15/2010 | 01/05/2010 | 214995 | 0
286 | Alabama | TUSCALOOSA | TUSCALOOSA | 07 | TE09955 | Construct sidewallks along both sides of Coaling Ridge Road and Stephens Loop Road in the Town of Coaling, Alabama. | Transportation Enhancements | 06/08/2010 |  | 12/04/2010 | 848963 | 0
287 | Alabama | SHELBY | BIRMINGHAM | 06 | TE09974 | Construct sidewalks along Ballpark Rd. from Bearden Rd. through Pelham Park to U.S.31 in the City of Pelham in Shelby County, Alabama | Transportation Enhancements | 07/07/2010 |  | 11/02/2010 | 272265.11 | 0
288 | Alaska | DILLINGHAM |  | 00 | 0001260 | Reconstruct 2.8 miles of road from the intersection of Kanakanak Road and Wood River Road to the end of the road at Wood River Landing. Realign the road horizontally and vertically to create improved | Pavement Improvement | 04/16/2010 | 04/17/2010 | 08/31/2010 | 12955259 | 2.8
289 | Alaska | ANCHORAGE | ANCHORAGE | 00 | 0001359 | Increase capacity and improve safety by reconstructing a high-volume intersection at Tudor Road and Lake Otis Boulvard in Anchorage. In addition to dual left-turn lanes at all four corners of the int | Pavement Widening | 04/07/2010 | 04/12/2010 | 10/30/2010 | 5000000 | 0.71
290 | Alaska | NORTHWEST ARCTIC |  | 00 | 0002109 | This project will reconstruct and pave approximately 4,400 lineal feet of Shore Avenue between Lake Street and Crowley Dock Road and armor the tidewater side of the road with a combination of sheet pi | Pavement Improvement | 06/17/2009 | 06/17/2009 | 10/01/2011 | 6500000 | 1.077
291 | Alaska | NOME |  | 00 | 0002185 | Construct drainage improvements and provide dust control on approximately 7,532 linear feet of roads within the City of Nome. The subgrade of the roads will be constructed to prepare for paving and | Pavement Improvement | 06/21/2010 |  | 10/01/2010 | 3588248 | 17
292 | Alaska | SKAGWAY-HOONAH-ANGN |  | 00 | 0003053 | The project will construct a 1,300 foot, two-lane causeway connected to a 6,000 square-foot dock. A pontoon-supported, tidally-operated transfer bridge and ramp will provide roll-on/roll-off access fo | Bridge Improvement | 04/16/2009 | 04/27/2009 | 12/01/2010 | 7700000 | 0.185
293 | Alaska | VALDEZ - CORDOVA |  | 00 | 000S684 | The project will re-pave 7.1 miles of bike and pedestrian path alongside the Richardson Highway between Meals Avenue in downtown Valdez and River Road at the Robe River Subdivision, and improve its sa | Transportation Enhancements | 07/24/2009 | 06/03/2009 | 10/01/2009 | 954770 | 7.6
294 | Alaska | VALDEZ - CORDOVA |  | 00 | 000S685 | Repave 0.95 miles of Blueberry Lake Road in Valdez at the access to the Blueberry Lake Campground. Pave 1,900 feet of roadway within the Blueberry Lake Campground. The project provides improved acce | Pavement Improvement | 07/27/2009 | 06/03/2009 | 10/01/2009 | 1045762 | 0.95
295 | Alaska | SOUTHEAST FAIRBANKS |  | 00 | 000S686 | This project will rehabilitate and resurface the Richardson Highway between MP 265-267 (Delta Junction area), to include its junction of the Alaska Highway and frontage roads. Work includes pulverizi | Pavement Improvement | 05/15/2010 | 05/26/2010 | 08/26/2010 | 3600000 | 1.53
296 | Alaska | KENAI PENINSULA |  | 00 | 0221054 | The project will resurface the driving lanes and shoulder of 16.75 miles of the Sterling Highway between Kalifornsky Beach Road and South Coho Loop Road in the Kenai Peninsula Borough. The project wi | Pavement Improvement | 07/29/2009 | 05/26/2009 | 06/30/2010 | 6756419 | 17
297 | Alaska | KODIAK ISLAND |  | 00 | 0391014 | Resurface 6.4 miles of urban roadway in the City of Kodiak. The project will include replacement of the waterproof membrane on the Buskin River bridge, paint striping, installation of pedestrian cros | Pavement Improvement | 08/06/2009 | 06/02/2009 | 10/01/2009 | 6635651 | 6.95
298 | Alaska | ANCHORAGE | ANCHORAGE | 00 | 0515004 | Resurface 1.837 miles of Jewel Lake Road from its intersection with Dimond Boulevard to its intersection with 63rd Avenue. Upgrade the collapsable, energy-absorbing ends of the guardrails to current | Pavement Improvement | 05/14/2010 | 05/18/2010 | 07/31/2010 | 2280000 | 1.837
299 | Alaska | ANCHORAGE | ANCHORAGE | 00 | 0558007 | This 4.1-mile project will add 4-foot shoulders and new pavement, construct a paved pathway to connect existing pathways at South and North Birchwood Loop, construct a short truck-climbing lane just n | Pavement Improvement | 04/19/2010 | 05/06/2010 | 09/01/2011 | 13059238 | 4.1
300 | Alaska | VALDEZ - CORDOVA |  | 00 | 0750011 | This project will construct a new wayside in the vicinity of Milepost 7 of the Denali Highway. The project includes paved parking, a vault toilet,, litter barrel, table and bench. The project will r | Transportation Enhancements | 09/03/2009 | 05/17/2010 | 07/15/2010 | 441283 | 0
301 | Alaska | KETCHIKAN GATEWAY |  | 00 | 0902034 | Conduct 2nd phase of corrosion protection improvements, consisting of cathodic protection and selected portions of future impressed current protection system for concrete piles and caps of the viaduct | Bridge Improvement | 01/21/2010 | 03/08/2010 | 01/31/2011 | 8591534 | 0.75
302 | Alaska | KETCHIKAN GATEWAY |  | 00 | 0902035 | The project will widen and modify existing sidewalks for approximately 2,040 feet, from Chapmen Street to the existing Viaduct Tunnel to improve pedestrian capacity and safety and achieve Americans wi | Transportation Enhancements | 05/12/2010 | 06/04/2010 | 05/01/2011 | 2200000 | 0.36
303 | Alaska | SKAGWAY-HOONAH-ANGN |  | 00 | 0918007 | This project will rehabilitate 2.2 miles of road in the City of Hoonah linking the city airport and the state ferry terminal. The rehabilitated road will reduce maintenance efforts, improve ride qual | Pavement Improvement | 01/07/2010 | 04/05/2010 | 08/30/2010 | 2016951 | 2.2
304 | Alaska | KETCHIKAN GATEWAY |  | 00 | 0920025 | The project will reconstruct the highway for approximately two miles to provide a paved width of 36' including 12-foot driving lanes and 6-foot shoulders, from the first junction with D-1 Loop Road to | Pavement Improvement | 04/06/2010 | 04/20/2010 | 06/30/2011 | 10014923 | 0
305 | Alaska | JUNEAU |  | 00 | 0933027 | This project will widen and straighten Glacier Highway to a paved width of 30 feet for 4.6 miles between the Amalga Harbor Road and the kayak launch at Eagle Beach. The project will include culvert r | Pavement Improvement | 07/23/2009 | 05/27/2009 | 12/01/2010 | 11273789 | 4.597
306 | Alaska | JUNEAU |  | 00 | 0933036 | The project will rehabilitate and resurface 4.52 miles of driving lanes on Glacier Highway in Juneau, between the Mendenhall Loop road and the Auke Bay Ferry Terminal, not including a segment between | Pavement Improvement | 08/03/2009 | 05/27/2009 | 06/30/2010 | 3416667 | 4.474
307 | Alaska | HAINES |  | 00 | 0956032 | This project will rebuild 0.59 miles of highway between the intersections of Front Street and Union Street including removal and replacement of asphalt, grading and adding material to the subgrade as | Pavement Improvement | 08/12/2009 | 10/19/2009 | 06/30/2010 | 2175989 | 0.59
308 | Alaska | SOUTHEAST FAIRBANKS |  | 00 | 0A11011 | This project will remove the existing truck weigh scale, scale house and associated utilities, and replace them with a new multi-platform scale and a scale house. Site work will include construction | New Construction | 02/09/2010 | 02/23/2010 | 06/15/2011 | 3750000 | 0
309 | Alaska | MATANUSKA-SUSITNA |  | 00 | 0A15026 | This project will resurface 5.8 miles of the Glenn Highway between mileposts 34-42 and replace or repair guardrails including the energy-absorbing, collapsable ends of the guardrails. The project wil | Pavement Improvement | 07/16/2009 | 06/04/2009 | 10/01/2009 | 2037579 | 8
310 | Alaska | MATANUSKA-SUSITNA | ANCHORAGE | 00 | 0A16039 | This project will resurface 15.188 miles of driving lanes, and all ramps and bridges, on the Glenn Highway between Hiland Road and Artillery Road interchanges. Replace or repair guardrails including | Pavement Improvement | 06/12/2009 | 05/26/2002 | 10/01/2009 | 13318636 | 34
311 | Alaska | MATANUSKA-SUSITNA |  | 00 | 0A16040 | This project will resurface 10.03 miles of the Glenn Highway including driving lanes, ramps, interchages and bridges between Mt. View Drive and the Hiland Interchange. Upgrade or replace guardrails i | Pavement Improvement | 05/03/2010 | 05/06/2010 | 08/01/2010 | 11550500 | 10.3
312 | Alaska | MATANUSKA-SUSITNA |  | 00 | 0A41022 | Rehabilitate the driving surface and widen the shoulders of 11.1 miles of roadway on the Parks Highway between Willow Creek and the Kashwitna River including 3 passing zones for northbound traffic an | Pavement Improvement | 10/20/2009 | 10/21/2009 | 09/30/2011 | 25175000 | 11
313 | Arizona | YUMA | YUMA (CA) | 7 | 008A204 | The Arizona Department of Transportation proposes to construct a Chain Link Fence project in Yuma County along I-8; US-95 (16th St) to Araby Rd in YUMA. | Other | 10/08/2009 | 10/19/2009 |  | 321253 | 5.396
314 | Arizona | MARICOPA |  | 7 | 008B200 | The Arizona Department of Transportation proposes a pavement preservation project in Maricopa County, on I-8, from Milepost 121 to Big Horn, east of Gila Bend. | Pavement Improvement | 07/08/2010 |  |  | 1358212 | 13.541
315 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 010B205 | The Arizona Department of Transportation proposes to reconstruct a traffic interchange in Pima County along I-10, from Cienega Creek (milepost 288.4) to Marsh Station (milepost 290.5). Work will incl | Pavement Widening | 07/27/2009 | 09/11/2010 |  | 27635071 | 6.054
316 | Arizona | PINAL |  | 1 | 010C203 | The Arizona Department of Transportation proposes a widen freeway project in Pinal County, on I-10, from I-8 to SR 87. | Pavement Improvement | 07/08/2010 |  |  | 40735939 | 10.426
317 | Arizona | PINAL |  | 1 | 010D204 | The Arizona Department of Transportation proposes to complete a freeway widening project in Pinal County along I-10 from the Town of Picacho to the Picacho Peak traffic interchange. Work will include | Pavement Improvement | 07/29/2009 | 08/14/2009 |  | 17294637.35 | 5.706
318 | Arizona | PIMA | TUCSON | 7 | 010D206 | The Arizona Department of Transportation will construct an ITS Freeway Management System project in Pima County along Interstate 10 from milepost 250.2 to milepost 267.2 and along Interstate 19 toward | New Bridge Construction | 01/28/2010 | 02/18/2010 |  | 4476412.62 | 5.378
319 | Arizona | PIMA |  | 8 | 010E201 | The Arizona Department of Transportation proposes to reconstruct a traffic interchange in Pima County along I-10, from Cienega Creek (milepost 288.4) to Marsh Station (milepost 290.5). Work will incl | Pavement Widening | 07/27/2009 | 07/27/2009 | 09/18/2009 | 10122297 | 0.519
320 | Arizona | PIMA |  | 8 | 010E203 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Pima County along I-10, from Rita Rd to Houghton Rd east of TUCSON a total of 4 miles. | Pavement Improvement | 07/08/2009 | 09/10/2009 |  | 2880496.18 | 3.991
321 | Arizona | PIMA |  | 8 | 010E204 | The Arizona Department of Transportation proposes to replace barbed wire fence in Pima County along I-10; from Vail Rd to Pima/Cochise County Line. | Other | 10/05/2009 | 10/22/2009 |  | 202793 | 16.785
322 | Arizona | PIMA | TUCSON | 8 | 010E205 | The Arizona Department of Transportation proposes a pavement preservation project in Pima County, on I-10, from Houghton Rd to Mountain View TI, approximately 20 miles southeast of Tucson. | Pavement Improvement | 06/03/2010 | 06/23/2010 |  | 4994829 | 5.302
323 | Arizona | COCHISE |  | 8 | 010F201 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Cochise County along I-10 (EB), from East Benson to Johnson Rd (milepost 307.68 to milepost 321.60) to | Pavement Improvement | 06/08/2009 | 07/06/2009 |  | 6685519 | 13.705
324 | Arizona | COCHISE |  | 8 | 010F203 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Cochise County along I-10 (east bound); from Luzena to Bowie. | Pavement Improvement | 07/29/2009 | 08/24/2009 |  | 1556826 | 4.909
325 | Arizona | MARICOPA |  | 3 | 017A207 | The Arizona Department of Transportation proposes to construct a Freeway Widening project in Maricopa County along I-17; SR-74 to Anthem Way in PHOENIX to include Major widening along 5 miles to provi | Pavement Widening | 06/30/2009 | 08/05/2009 |  | 13994094 | 4.831
326 | Arizona | MARICOPA |  | 3 | 017A210 | The Arizona Department of Transportation proposes to construct a Right-of-way fence replacement project in Maricopa County along Interstate 17 (South Bound); from Table Mesa Interchange to Rock Spring | Other | 06/30/2009 | 07/29/2009 |  | 109158.14 | 6.105
327 | Arizona | MARICOPA | PHOENIX, AZ | 4 | 017A211 | The Arizona Department of Transportation proposes a widen roadway project in Maricopa County within the City of Phoenix on SB I-17 beginning at the I-10 stack and extending to Indian School Road. | Pavement Widening | 06/29/2010 |  |  | 1237799 | 0.015
328 | Arizona | SANTA CRUZ |  | 7, 8 | 019A202 | The Arizona Department of Transportation proposes to replace barbed wire fence in Santa Cruz County along I-19; from Rio Rico Rd to Chaves Siding Road north of NOGALES. | Other | 11/04/2009 | 11/16/2010 |  | 371785 | 13.297
329 | Arizona | MOHAVE |  | 2 | 040A208 | The Arizona Department of Transportation proposes to replace barb wire fence in Mohave County along Interstate 40; California State Line to Oatman Hwy Interchange to include Safety. | Other | 08/28/2009 | 09/16/2009 |  | 210600.17 | 44.328
330 | Arizona | MOHAVE |  | 2 | 040B205 | The Arizona Department of Transportation proposes to construct a fence replacement project in Mohave County along Interstate 40; Railroad Ave to Rattlesnake Wash in Kingman, AZ, to include chain link | Other | 06/23/2009 | 07/16/2009 |  | 507115.78 | 4.148
331 | Arizona | COCONINO |  | 1 | 040C202 | The Arizona Department of Transportation proposes to replace barb wire fence in Coconino County along Interstate 40 from State Route 64 (milepost (MP) 166) to Volunteer Wash (MP 188). | Other | 08/10/2009 | 08/24/2009 |  | 362794 | 22.157
332 | Arizona | COCONINO |  | 1 | 040C203 | The Arizona Department of Transportation proposes to construct a pavement preservation project in Coconino County along Interstate 40 from milepost (MP) 150 to MP 190.8. | Pavement Improvement | 08/04/2009 | 08/17/2009 |  | 581676 | 41.121
333 | Arizona | COCONINO |  | 1 | 040D018 | The Arizona Department of Transportation proposes to reconstruct the roadway and alleviate steep grades in Coconino County along Interstate 40 westbound near Walnut Canyon (milepost 205) east of Flag | Pavement Improvement | 06/01/2009 | 06/01/2009 | 05/11/2010 | 7533237 | 0.073
334 | Arizona | APACHE |  | 1 | 040E201 | The Arizona Department of Transportation proposes to construct features that will protect the Dead River Bridge (Bridge #565) in Apache County along Interstate 40 (Eastbound) from the effects of high | Bridge Improvement | 06/25/2009 | 07/07/2009 |  | 151765 | 0.027
335 | Arizona | APACHE |  | 1 | 040E202 | The Arizona Department of Transportation proposes a bridge rehabilitation project in Apache County along Interstate 40 at the Black Creek west of Houck, AZ; project also includes high water protectiv | Bridge Improvement | 06/08/2009 | 07/06/2009 |  | 446667 | 0.036
336 | Arizona | MARICOPA |  | 2 | 060A204 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Maricopa County along US 60, from MP 107.6 to MP 110.2 in WICKENBURG to include Micro Seal. | Pavement Improvement | 08/24/2009 | 10/12/2009 |  | 370011.92 | 2.535
337 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 060B200 | The proposed widen roadway project is located in Maricopa County within the City of Peoria on US 60. The project begins at MP 148.5 and extends to MP 150.3 for a total length of approximately 1.8 mil | Pavement Widening | 06/03/2009 | 06/03/2009 | 06/11/2009 | 8046826.32 | 1.885
338 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 060B201 | The Arizona Department of Transportation proposes to construct a Roadway Widening project in Maricopa County along US-60 (Grand Av); SR-303L to 99th Av to include Road Widening. | Pavement Widening | 11/30/2009 | 01/22/2010 |  | 24112061 | 10.14
339 | Arizona | PINAL | PHOENIX, AZ | 6 | 060C201 | The Arizona Department of Transportation proposes to construct a Gateway graphics project in Pinal County along US 60 at Tomahawk Rd in APACHE JUNCTION (Graphics) to include Gateway graphics. | Transportation Enhancements | 10/05/2009 | 11/19/2009 |  | 349339.19 | 0.21
340 | Arizona | PINAL | PHOENIX, AZ | 6 | 060C202 | The Arizona Department of Transportation proposes to construct a Transportation Enhancement project in Pinal County along US-60 at Goldfield Rd in APACHE JUNCTION to include Gateway graphics. | Transportation Enhancements | 10/05/2009 | 11/19/2009 |  | 361715.74 | 0.235
341 | Arizona | GILA |  | 1 | 060D201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along US-60, Miami City Limits to McMillan Wash. | Pavement Improvement | 06/25/2009 | 08/05/2009 |  | 10118264 | 8.25
342 | Arizona | GILA |  | 1 | 060E202 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along US-60, from Timber Mountain (MP 278.8) to Seneca (MP 286.4). | Pavement Improvement | 05/28/2009 | 07/13/2009 |  | 3652653.74 | 6.822
343 | Arizona | YAVAPAI |  | 1 | 069A206 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Yavapai County along SR-69, I-17 to Big Bug Creek. | Pavement Improvement | 06/10/2009 | 06/26/2009 |  | 2340022.4 | 7.744
344 | Arizona | GRAHAM |  | 1 | 070A202 | The Arizona Department of Transportation proposes to construct a traffic intersection improvement project in Graham County on US-70 @ 8th Avenue in SAFFORD to include pavement and signal improvements. | Pavement Improvement | 08/03/2009 | 08/31/2009 |  | 210664 | 0.159
345 | Arizona | GILA |  | 1 | 073A200 | The Arizona Department of Transportation proposes to construct a Replace Barb Wire Fence project in Gila County along SR 73; Cedar Creek to Canyon Day to include Safety. | Other | 09/08/2009 | 09/21/2009 |  | 324586.89 | 11.42
346 | Arizona | MARICOPA |  | 2 | 074A200 | The Arizona Department of Transportation proposes to construct a Widen Roadway project in Maricopa County along SR-74; MP 19 - New River Rd to include new construction of passing lanes on both eastbou | Pavement Widening | 11/02/2009 | 11/19/2009 |  | 2440925 | 1.427
347 | Arizona | MARICOPA |  | 2 | 074A201 | The Arizona Department of Transportation proposes a widen roadway project in Maricopa County on SR 74 from Milepost 14 to Milepost 16. | Pavement Widening | 07/21/2010 |  |  | 3395000 | 2.001
348 | Arizona | GREENLEE |  | 1 | 075A001 | The Arizona Department of Transportation proposes to construct a transportation enhancement project in Greenlee County along SR 75 in York Valley to include pathways, railings, and retaining walls. | Transportation Enhancements | 10/27/2009 | 11/19/2009 |  | 270508 | 0.51
349 | Arizona | COCHISE |  | 8 | 080A201 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Cochise County along SR-80 through TOMBSTONE. | Pavement Improvement | 06/30/2009 | 08/12/2009 |  | 784285.57 | 0.962
350 | Arizona | COCHISE |  | 8 | 080A202 | The Arizona Department of Transportation proposes to replace fence in Cochise County along SR-80; from Double Adobe Road to the Town of Douglas. | Other | 06/16/2009 | 07/13/2009 |  | 413660.6 | 14
351 | Arizona | SANTA CRUZ |  | 8 | 083A201 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Santa Cruz County along SR-83, near Sonoita from milepost 31.6 to milepost 43.5, a total of 11.9 miles. | Pavement Improvement | 06/16/2009 | 07/06/2009 |  | 2365274.63 | 10.293
352 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 085B200 | The Arizona Department of Transportation proposes to construct a Widen Roadway project in Maricopa County along SR-85; Southern Ave to I-10. | Pavement Widening | 10/06/2009 | 10/22/2009 |  | 11147270.09 | 0.921
353 | Arizona | PIMA |  | 7 | 086A008 | The Arizona Department of Transportation proposes to construct a shoulder widening project in Pima County along SR-86 west Sells from milepost 73.9 to milepost 77.4. | Pavement Improvement | 07/28/2009 | 09/10/2009 |  | 2167459.61 | 3.68
354 | Arizona | PIMA |  | 01 | 086A200 | The Arizona Department of Transportation proposes a widen roadway project in Pima County on SR 86 between milepost 141.1 and the Reservation Boundary, approximately 5 miles west of Robles Junction.? | Pavement Improvement | 06/28/2010 | 07/23/2010 |  | 9000000 | 0.68
355 | Arizona | PIMA | TUCSON | 7 | 086A203 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Pima County along SR-86, from Kinney Road to La Cholla Blvd in TUCSON, a total of 3.1 miles. | Pavement Improvement | 08/05/2009 | 08/27/2009 |  | 2528446.98 | 3.164
356 | Arizona | PIMA | TUCSON | 7 | 086A204 | The Arizona Department of Transportation proposes to perform a bridge deck rehabilitation project in Pima County on SR-86 at the Santa Cruz River in TUCSON. Work will include repair of deteriorating | Bridge Improvement | 07/08/2009 | 07/18/2009 |  | 350000 | 0.049
357 | Arizona | PIMA |  | 7 | 086A205 | The Arizona Department of Transportation proposes to complete the widening of SR-86 in Pima County across Brawley Wash west of TUCSON from milepost 145.69 to milepost 148.3. | Pavement Improvement | 08/03/2009 | 09/01/2009 |  | 1660928.59 | 2.562
358 | Arizona | MARICOPA | PHOENIX, AZ | 5 | 087B205 | The Arizona Department of Transportation proposes a reconstruct roadway project in Maricopa County within the Tonto National Forest on SR 87 between New Four Peaks Road and Dos S Ranch Road. | Pavement Widening | 06/01/2010 | 06/24/2010 |  | 13389170 | 5.565
359 | Arizona | MARICOPA | PHOENIX, AZ | 5 | 087B206 | The Arizona Department of Transportation proposes a reconstruct and repair roadway cut slopes project in Maricopa County within the Tonto National Forest on SR 87 between MP 211.8 and MP 213. | Pavement Improvement | 06/01/2010 | 06/24/2010 |  | 1220985 | 1.235
360 | Arizona | GILA |  | 1 | 087C002 | The Arizona Department of Transportation proposes to construct a Shoulder Widening project in Gila County along SR-87, PAYSON to PINE. | Pavement Improvement | 05/22/2009 | 06/02/2009 |  | 4646791.59 | 1.215
361 | Arizona | GILA |  | 1 | 087C201 | The Arizona Department of Transportation proposes to construct a Replace Barb Wire Fence project in Gila County along SR 87; PAYSON to PINE. | Other | 08/18/2009 | 09/01/2009 |  | 405098 | 12.049
362 | Arizona | COCONINO | FLAGSTAFF | 1 | 089C200 | The Arizona Department of Transportation proposes to construct a pavement preservation project in Coconino County along US 89; Townsend (milepost (MP) 420) to Fernwood (MP 426) north of Flagstaff, AZ. | Pavement Improvement | 05/22/2009 | 06/22/2009 |  | 4783750.62 | 5.119
363 | Arizona | MOHAVE |  | 2 | 093B201 | The Arizona Department of Transportation proposes to construct new southbound travel lanes, creating a divided highway, in Mohave County along US 93, from milepost (MP) 104.1 to MP 106 (Ranch Rd Secti | New Construction | 07/28/2009 | 08/05/2009 | 07/31/2010 | 7522497 | 2.055
364 | Arizona | YUMA | YUMA (CA) | 7 | 095A201 | The Arizona Department of Transportation proposes to construct a widening project in Yuma County along US 95 (16th Street), I-8 to Palms Ave. | Pavement Widening | 08/18/2009 | 09/08/2009 |  | 11349523.66 | 0.709
365 | Arizona | LA PAZ |  | 7 | 095B200 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in La Paz County along US-95, from Peligro (MP 63) to Clarks (MP 80). | Pavement Improvement | 09/28/2009 | 10/13/2009 |  | 9039982 | 28.461
366 | Arizona | YUMA |  | 7 | 095B202 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Yuma County along US 95, from MP 44.3 to MP 312.7. | Pavement Improvement | 08/24/2009 | 09/14/2009 |  | 502307.5 | 9.652
367 | Arizona | LA PAZ |  | 7 | 095C203 | The Arizona Department of Transportation proposes to construct a Passing Lanes project in La Paz County along SR 95 South of Bouse Wash. | Pavement Improvement | 06/30/2009 | 07/27/2009 |  | 1684770.2 | 2.248
368 | Arizona | PIMA | TUCSON | 8 | 0RV0201 | The Town of Oro Valley will perform a pavement preservation project on the following roadways: LaCholla, First, Lamber, Moor,Tan in the Town of Oro Valley. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 1619759 | 0.894
369 | Arizona | MARICOPA | PHOENIX, AZ | 7 | 101A203 | The Arizona Department of Transportation proposes a widen roadway project in Maricopa County, on 99th Avenue between I-10 and Van Buren Street, within the Cities of Avondale and Tolleson. | Pavement Widening | 06/28/2010 | 07/21/2010 |  | 2172000 | 0
370 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 101A204 | The Arizona Department of Transportation proposes to widen Union Hills Road Traffic Interchange in Maricopa County along SR-101L (Aqua Fria Frwy) @ Beardsley Rd/Union Hills Dr in GLENDALE. | New Bridge Construction | 10/26/2009 | 10/26/2009 | 01/01/2012 | 5667374 | 1.213
371 | Arizona | MARICOPA | PHOENIX, AZ | 3 | 101A205 | The Arizona Department of Transportation proposes to construct an auxiliary lane project in Maricopa County, on SR 101L, eastbound between 51st Avenue and 35th Avenue within the City of Phoenix. | Pavement Improvement | 05/13/2010 | 06/07/2010 |  | 2035272.14 | 2.003
372 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 101A206 | The Arizona Department of Transportation proposes to construct an auxiliary lane project in Maricopa County, on SR 101L, southbound between Northern Avenue and Grand Avenue within the City of Peoria. | Pavement Improvement | 05/13/2010 | 06/07/2010 |  | 2186111 | 2.807
373 | Arizona | MARICOPA | PHOENIX, AZ | 2 | 101A207 | The Arizona Department of Transportation proposes an intersection improvement project in Maricopa County, within the City of Peoria on Olive Avenue at the intersection with Agua Fria Freeway (101L). | Pavement Widening | 03/25/2010 | 04/21/2010 |  | 2172403 | 0.358
374 | Arizona | COCONINO |  | 1 | 160A001 | The Arizona Department of Transportation proposes a pavement preservation project in Coconino County along US 160, from the junction of US 89 and US 160 to Van's Trading Post; west of Tuba City, AZ - | Pavement Improvement | 06/01/2009 | 06/11/2009 |  | 3062945 | 8.124
375 | Arizona | NAVAJO |  | 1 | 160A200 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County along US 160, in Kayenta, AZ to Navajo Route 59 - 12.5 miles | Pavement Widening | 05/26/2009 | 06/04/2009 |  | 6451531 | 12.502
376 | Arizona | NAVAJO |  | 1 | 160B200 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County along US 160; from Navajo Route 59 to Dennehotso - 14 miles. | Pavement Improvement | 05/26/2009 | 06/04/2009 |  | 3237003 | 14.003
377 | Arizona | NAVAJO |  | 1 | 180B202 | The Arizona Department of Transportation proposes to replace barb wire fence in Navajo County along US 180, east of Holbrook, AZ; from milepost (MP) 307.3 to 324.9, near the Petrified Forest Road. | Other | 08/05/2009 | 09/08/2009 |  | 579716.79 | 17.393
378 | Arizona | COCHISE | PHOENIX, AZ | 8 | 191A200 | The Arizona Department of Transportation proposes to construct an intersection improvement project in Cochise County along US-191 @ High Street in Sunsites (MP 48.36 to MP 48.94 to include Widen Roadw | Pavement Improvement | 06/16/2009 | 07/20/2009 |  | 484868.83 | 0.581
379 | Arizona | GRAHAM |  | 1 | 191B001 | The Arizona Department of Transportation proposes to construct a transportation enhancement project in Graham County along US 191 from Discovery Blvd. to Relations St. in the Town of Safford. Work wi | Transportation Enhancements | 01/04/2010 | 01/25/2010 |  | 365016 | 1.468
380 | Arizona | COCHISE |  | 08 | 191B200 | The Arizona Department of Transportation proposes to construct a parallel road project in Cochise County on US 191 from Dial Wash to Ten Ranch south of SAFFORD. | New Construction | 06/30/2010 | 07/21/2010 |  | 7425000 | 5.636
381 | Arizona | GREENLEE |  | 1 | 191C202 | The Arizona Department of Transportation proposes an intersection improvement project in Greenlee County along US 191 at Black Hills Rd (Back County Byway) at milepost 159.5. | Pavement Improvement | 07/24/2009 | 09/15/2010 |  | 770888.89 | 0.142
382 | Arizona | GREENLEE |  | 1 | 191C203 | The Arizona Department of Transportation proposes to construct a drainage improvement project in Greenlee County along US-191 (Coronado Trail) at milepost 175 to include Lower Coronado Drainage Improv | Other | 09/28/2009 | 10/19/2009 |  | 409630.3 | 4.747
383 | Arizona | APACHE |  | 1 | 191E202 | The Arizona Department of Transportation proposes a pavement preservation project in Apache County along US 191, from milepost (MP) 427 to MP 436 south of Chinle, AZ. | Pavement Improvement | 06/16/2009 | 07/23/2009 |  | 3171048.9 | 8.381
384 | Arizona | NAVAJO |  | 1 | 260C003 | The Arizona Department of Transportation proposes to construct a Transportation Enhancement project in Navajo County along SR-260; Porter Mtn. Rd to Woodland Rd in PINETOP/LAKESIDE to include Pedestri | Other | 10/28/2009 | 05/03/2010 |  | 627151 | 0.389
385 | Arizona | NAVAJO |  | 1 | 277A201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Navajo County along SR 277, from MP 305.7 to 312.7. | Pavement Improvement | 08/05/2009 | 08/10/2009 |  | 350575.03 | 6.831
386 | Arizona | STATEWIDE |  | 7, 8 | 999A238 | The Arizona Department of Transportation proposes to implement a Pavement Micro Seal project Statewide in various Counties in Southeast Arizona. | Pavement Improvement | 08/24/2009 | 09/16/2009 |  | 1193435.5 | 5.02
387 | Arizona | STATEWIDE |  | 1 | 999A239 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County at various locations. | Pavement Improvement | 08/03/2009 | 08/19/2009 |  | 709240.92 | 5.508
388 | Arizona | GILA |  | 1 | 999A242 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along Globe District Chip Seals to include Chip Seal. | Pavement Improvement | 07/29/2009 | 08/17/2009 |  | 573572.04 | 7.284
389 | Arizona | STATEWIDE |  | 1, 5, 7, 8 | 999A244 | The Arizona Department of Transportation proposes to construct Pipe Liner Inserts (Relining) in VARIOUS Locations Statewide. | Other | 01/05/2010 | 01/20/2010 |  | 2121888 | 9.087
390 | Arizona | PINAL |  | 6 | APJ0200 | The City of Apache Junction, AZ will perform Pavement Preservation along Ironwood Drive from US 60 (Superstition Frwy) to Southern Ave. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 1670913 | 0.773
391 | Arizona | MARICOPA | PHOENIX, AZ | 7 | AVN0206 | The City of Avondale will perform a Preliminary engineering, design and construction along Dysart Rd; I-10 to Indian School Rd in AVONDALE. | Pavement Improvement | 06/23/2009 | 06/23/2009 | 01/29/2010 | 1836835.28 | 0.474
392 | Arizona | MARICOPA | PHOENIX, AZ | 7 | AVN0207 | The City of Avondale will perform a Preliminary engineering, design and construction for along Dysart Rd; Van Buren St to I-10 in AVONDALE. | Other | 06/23/2009 | 06/23/2009 | 01/29/2010 | 48515 | 0.54
393 | Arizona | MARICOPA | PHOENIX, AZ | 7 | BKY0202 | The Town of Buckeye will perform a Pre-engineering/Design and Pavement Rehabilitation and Preservation along Various Locations on Functionally Classified Roads in BUCKEYE. | Pavement Improvement | 06/12/2009 | 06/12/2009 | 01/11/2010 | 1264037 | 0.992
394 | Arizona | MOHAVE |  | 2 | BUL0200 | Bullhead City will perform a pavement preservation project of existing deteriorating asphalt pavement along Miracle Mile in Bullhead City, AZ. | Pavement Improvement | 07/02/2009 | 07/02/2009 |  | 500000 | 1.325
395 | Arizona | COCONINO |  | 1 | CCN0204 | The Coconino County will perform a pavement preservation along Lake Mary Road south of Flagstaff, AZ. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 754012 | 0
396 | Arizona | COCONINO | FLAGSTAFF | 1 | CCN0205 | The Coconino County will perform a pavement preservation project along State Route B40 (Old US 66), from I-40 to City Limits, west of Flagstaff, AZ. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 855903 | 0
397 | Arizona | MARICOPA | PHOENIX, AZ | 3 | CFE0201 | The Town of Carefree, AZ will perform Design and construction of repair and restoration of Cave Creek Road from Scopa Trail to Carefree Eastern Border. | Pavement Improvement | 07/01/2009 | 07/01/2009 |  | 588338 | 4
398 | Arizona | MARICOPA | PHOENIX, AZ | 6 | CHN0014 | The City of Chandler, AZ will construct a Multi-Use Pathway along Paseo Road. | Transportation Enhancements | 07/20/2010 |  |  | 893595 | 1.5
399 | Arizona | MARICOPA | PHOENIX, AZ | 6 | CHN0025 | The City of Chandler, AZ will perform Intersection and Capacity Improvement along Chandler Blvd at Dobson Rd, and on Dobson Rd from Chandler Blvd to Frye Rd. | Pavement Widening | 08/24/2009 | 08/24/2009 |  | 3949421 | 0.5
400 | Arizona | MARICOPA | PHOENIX, AZ | 6 | CHN0211 | The City of Chandler will perform Design and reconstruction of pavement along Price Road; Germann Road to Queen Creek Road in CHANDLER. | Pavement Improvement | 06/30/2009 | 06/30/2009 |  | 2018178 | 1
401 | Arizona | PINAL |  | 1 | CSG0200 | The City of Casa Grande will install intersection traffic signals at the following intersection Peart Road / McCartney Road and Peart Road / Korsten Road in Casa Grande. | Other | 06/18/2009 | 06/18/2009 | 10/16/2009 | 17562 | 0
402 | Arizona | MARICOPA | PHOENIX, AZ | 3 | CVK0201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project along Cave Creek Road from Spur Crossing to the Cave Creek Town Limits in CAVE CREEK, AZ. | Pavement Improvement | 09/09/2009 | 09/09/2009 |  | 614666.87 | 1.5
403 | Arizona | COCHISE |  | 8 | DGS0005 | The City of Douglas will perform a transportation enhancement project which will include a shared use pathway with ADA ramps over a railroad bridge along Paseo de la Amistad. | Transportation Enhancements | 12/29/2009 | 02/01/2010 |  | 537968.41 | 0.2
404 | Arizona | APACHE |  | 1 | EGR0200 | The City of Eager will perform a Pavement Preservation along Main Street; from US-60 to SR-260 in EAGER. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 857370 | 1.6
405 | Arizona | MARICOPA | PHOENIX, AZ | 2 | ELM0202 | The City of El Mirage will perform a Pre-Engineer/Design and Mill and Replace Existing Pavement along Various Locations on Functionally Classified Roadways. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 608600 | 1.5
406 | Arizona | COCONINO | FLAGSTAFF | 1 | FLA0006 | The City of Flagstaff will perform a improvements along State Route B40 in downtown Flagstaff, AZ; the project includes pathway and landscaping improvements. | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 06/11/2010 | 470119 | 0
407 | Arizona | MARICOPA | PHOENIX, AZ | 7 | GBD0200 | The City of Gila Bend will construct Pedestrian and Landscape Improvements along Various Locations along SR-85 (Pima St) in GILA BEND. | Transportation Enhancements | 09/10/2009 | 09/10/2009 |  | 244147 | 0
408 | Arizona | MARICOPA | PHOENIX, AZ | 7 | GBD0203 | The City of Gila Bend will design and construct a carpool lane and transit park & ride lot at the Gila Bend Airport on SR85. | Other | 09/10/2009 | 09/10/2009 | 02/18/2010 | 298862 | 0
409 | Arizona | MARICOPA | PHOENIX, AZ | 2 | GDY0202 | The City of Goodyear will perform a Pre-Engineer/Design to mill, patch and replace pavement along Various Locations on Functionally Classified Roads in GOODYEAR. | Pavement Improvement | 06/23/2009 | 06/23/2009 | 02/18/2010 | 676500 | 2.5
410 | Arizona | GILA |  | 1 | GGI0005 | The Gila County, will perform a Bridge Rehabilitation along Ice House, Bridge and Ice House Wash Bridge and Approaches in GLOBE. | Bridge Replacement | 06/18/2009 | 06/18/2009 |  | 1732990 | 0
411 | Arizona | MARICOPA | PHOENIX, AZ | 6 | GIL0015 | The City of Gilbert will construct Pedestrian bridges across a major Canal within the City. | Transportation Enhancements | 02/22/2010 |  |  | 270000 | 0
412 | Arizona | MARICOPA | PHOENIX, AZ | 6 | GIL0202 | The City of Gilbert will construct Sidewalks, ADA Handicap Ramps, Landscaping & Irrigation in the Heritage District in Downtown GILBERT. | Transportation Enhancements | 09/24/2009 | 08/25/2009 | 06/03/2010 | 421847.85 | 1.3
413 | Arizona | MARICOPA | PHOENIX, AZ | 6 | GIL0203 | The City of Gilbert, AZ will perform Design and Construction of Chip Seal Overlays on various arterial roadways in GILBERT. | Pavement Improvement | 07/06/2009 | 07/06/2009 |  | 4363842 | 15
414 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0201 | The City of Glendale will perform a Pedestrian corridor enhancements along Old Roma Alley in GLENDALE. | Transportation Enhancements | 03/01/2010 | 02/03/2010 | 06/13/2010 | 467549 | 0.1
415 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0211 | The City of Glendale, will perform a Pre-Engineer/Design for pavement overlay along Glendale Ave; 51st Ave to 66th Ave in GLENDALE. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 1677785 | 2
416 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0212 | The City of Glendale will perform a Pre-Engineer/Design and construct pavement surface treatment along Litchfield Rd; Missouri to Northern Ave in GLENDALE. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 638966 | 2
417 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0214 | The City of Glendale will Install thermoplastic pavement markings along 25 Miles on Arterial Streets in GLENDALE. | Pavement Widening | 06/12/2009 | 06/12/2009 | 10/08/2010 | 260923 | 25
418 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0215 | The City of Glendale will install wireless communication devices along Camelback Rd from 47th Ave to 83rd Ave to improve communication with traffic signals. | Safety/Traffic Management | 06/12/2009 | 06/12/2009 |  | 197388 | 4.5
419 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0216 | The City of Glendale will install wireless communication devices along Bethany Home Rd from 63rd Ave to 83rd Ave to improve communication with traffic signals. | Other | 06/23/2009 | 06/23/2009 |  | 13332 | 2.5
420 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0217 | The City of Glendale will install CCTV cameras at various locations on their functionally classified roadways to improve traffic operations and management. | Other | 06/23/2009 | 06/23/2009 |  | 13282 | 0
421 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0218 | The City of Glendale will modernize traffic signals at various locations on functionally classified roadways to improve traffic operations and management. | Other | 06/23/2009 | 06/23/2009 |  | 13512 | 0
422 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GLN0219 | The City of Glendale will install new traffic signal cabinets and controllers at various locations on functionally classified roadways to improve traffic operations and management. | Pavement Improvement | 06/23/2009 | 06/23/2009 |  | 1526104 | 0
423 | Arizona | MARICOPA | PHOENIX, AZ | 7 | GRI0200 | ADOT will perform Design and Construction of Pavement Rehab projects along Various Locations on Functionally Classified Roads within Gila River Indian Community. | Pavement Improvement | 06/23/2009 | 06/23/2009 | 02/16/2010 | 549420.27 | 1.5
424 | Arizona | MARICOPA | PHOENIX, AZ | 4 | GUA0200 | The Town of Guadalupe AZ will perform Replacement of existing street lights to improve safety along Various Roadways in GUADALUPE, AZ | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 634022 | 0
425 | Arizona | PIMA | TUCSON | 7 | IT00200 | The Tohono O'odham Indian Reservation will perform a pavement preservation project along San Xavier Road from Mission to Los Reales on the Tohono O'odham Nation. | Pavement Improvement | 07/09/2009 | 07/09/2009 | 09/30/2011 | 1676996.84 | 0
426 | Arizona | MOHAVE |  | 2 | KNG0202 | The City of Kingman will perform a pavement preservation project along Bank Street Kingman, AZ. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 534294 | 0.5
427 | Arizona | MOHAVE |  | 2 | LHV0003 | The Lake Havasu City will construct a shared use pathway along Magnolia Drive to Acoma Boulevard (Multi-Use Path) in Lake Havasu City, AZ. | Transportation Enhancements | 08/11/2009 | 01/04/2010 | 05/04/2010 | 456051.41 | 0.5
428 | Arizona | MOHAVE |  | 2 | LHV0200 | The Lake Havasu City will install traffic signals at the intersection of South Palo Verde and Acoma in Lake Havasu City, AZ. | Pavement Improvement | 09/09/2009 | 09/09/2009 |  | 264000 | 0
429 | Arizona | LA PAZ |  | 7 | LLA0201 | The LaPaz County will perform a Pavement Preservation project along Salome Road, from US 60 to MP 5.5. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 600000 | 5.5
430 | Arizona | MARICOPA | PHOENIX, AZ | 4 | LPK0201 | The City of Litchfield Park will perform a Pre-Engineer/Design to mill and replace pavement resurfacing/ reconstruction along Various Locations on Functionally Classified Roads in LITCHFIELD PARK. | Pavement Improvement | 06/23/2009 | 06/23/2009 | 02/12/2010 | 485812 | 0.7
431 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0209 | The City of Mesa, AZ will perform Design and Construction of Pavement Preservation and Americans with Disabilities Act (ADA) upgrades along Various Roadways. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 1006459 | 7.5
432 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0210 | The City of Mesa, AZ will perform Design and construction of mill and replace pavement along Various Roadways. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 1321487 | 3.5
433 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0211 | The City of Mesa proposes a pavement preservation project and American with Disabilities Act upgrades in various locations in Mesa, AZ. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 2375826 | 2
434 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0212 | City of Mesa, AZ proposes a pavement preservation project and upgrades to the American with Disabilities Act features in various locations in Mesa, Arizona. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 2015266 | 2
435 | Arizona | MARICOPA | PHOENIX, AZ | 6 | MES0213 | City of Mesa, AZ proposes a pavement preservation project with Americans with Disabilities Act improvements in various locations in Mesa, Arizona. | Pavement Improvement | 08/06/2009 | 08/06/2009 |  | 3516407 | 3
436 | Arizona | MOHAVE |  | 2 | MM00001 | The Mohave County will construct a shared use pathway along the Mohave Wash Pathway (County) from Gordon Drive to Bank Street in Kingman, AZ. | Transportation Enhancements | 11/20/2009 | 07/01/2009 | 08/17/2010 | 386219.78 | 0
437 | Arizona | MOHAVE |  | 2 | MM00200 | The Mohave County will construct a shared use pathway along Mohave Wash Pathway (County) from Bank Street to Northern Avenue in Kingman, AZ. | Transportation Enhancements | 11/20/2009 |  |  | 190744.33 | 0.6
438 | Arizona | MOHAVE |  | 2 | MM00203 | The Mohave County will perform a pavement preservation project along Northern Avenue in Kingman, AZ. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 500000 | 1.5
439 | Arizona | MARICOPA |  | 5 | MMA0201 | Maricopa County, AZ will construct Paved shoulders and add bike lanes along Bush Highway from Usery Pass Rd to Steward Mountain Rd northwest of MESA AZ. | Other | 10/05/2009 | 10/05/2009 | 01/15/2010 | 552383.84 | 4.6
440 | Arizona | MARICOPA | PHOENIX, AZ | 3 | MMA0210 | Maricopa County, will perform Pre-Engineer/Design and construct Asphalt Rubber Overlay along Various Locations on Functionally Classified Roadways in MARICOPA COUNTY. | Pavement Improvement | 06/12/2009 | 06/12/2009 | 12/11/2009 | 6469193 | 31.1
441 | Arizona | PIMA | TUCSON | 8 | MRN0202 | The City of Marana will perform various pavement preservation projects: Rattlesnake Pass (2.5 miles); Tangerine Road, I-10 to Thornydale Road; Moore Road, I-10 to Sandario Road; Sandario Road, Trico R | Pavement Improvement | 06/22/2009 | 06/22/2009 |  | 2769958 | 7.9
442 | Arizona | NAVAJO |  | 1 | NNA0200 | The Navajo County will perform a pavement preservation project along Bourdon Ranch Road from milepost (MP) 6.5 to MP 10.1 in Navajo County. | Pavement Improvement | 06/15/2009 | 06/15/2009 |  | 560883 | 3.5
443 | Arizona | PIMA | TUCSON | 2 | PAS0201 | The Pascua Yaqui Tribe will perform a pavement preservation project along Calle Torim and Ignacio. | Pavement Improvement | 07/14/2009 | 07/14/2009 |  | 429013 | 2.6
444 | Arizona | MARICOPA | PHOENIX, AZ | 2 | PE00205 | Major Arterial mill, overlay and re-striping to 5 general purpose lanes and bike lanes along Beardsley Rd; Lake Pleasant Rd to 83rd Av in PEORIA. | Pavement Widening | 06/08/2009 | 06/08/2009 | 02/05/2010 | 1957210 | 2.4
445 | Arizona | MARICOPA | PHOENIX, AZ | 2 | PE00206 | The City of Peoria will Widen the Beardsley Rd Connection: SR-101L (Agua Fria Fwy) to Beardsley Rd at 83rd Av/Lake Pleasant Pkwy in PEORIA, which will include Advance constructing the Beardsley Road | New Construction | 06/08/2009 | 06/08/2009 | 10/31/2009 | 1471776 | 2
446 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0209 | The City of Phoenix, AZ will perform Design & Construction of Intersection Improvements along 7th St at McDowell Rd in PHOENIX. | Pavement Widening | 07/01/2009 | 07/01/2009 |  | 99999 | 0
447 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0229 | The City of Phoenix, AZ will perform Design & Construction of Removal/Replacement of Existing Americans with Disabilities Act (ADA) Ramps or Construction of New ADA Ramps along Various Locations in PH | Pavement Improvement | 07/07/2009 | 07/07/2009 |  | 1281693 | 0
448 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0230 | The City of Phoenix, AZ will perform Design & Construction of Removal/Replacement of Existing Americans with Disabilities (ADA) Ramps or Construction of New ADA Ramps along Various Locations in PHOENI | Pavement Improvement | 07/07/2009 | 07/07/2009 | 12/16/2009 | 1361950 | 0
449 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0231 | The City of Phoenix, AZ will perform Design & Construction of Bridge Deck Rehabilitations along 11 Locations in PHOENIX. | Bridge Improvement | 07/08/2009 | 07/08/2009 | 01/06/2010 | 1623986 | 0
450 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0232 | The City of Phoenix, AZ will perform Design & Construction of Bridge Joint Rehabilitations along 6 Locations in PHOENIX. | Bridge Improvement | 07/08/2009 | 07/08/2009 |  | 678257 | 0
451 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0233 | The City of Phoenix will design, procure, and install CCTV along various corridors to improve traffic operations and management. | Safety/Traffic Management | 07/08/2009 | 07/08/2009 |  | 755987 | 0
452 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0234 | The City of Phoenix will design, procure and install a fiber optic backbone system along various corridors to improve traffic operations and management. | Safety/Traffic Management | 07/08/2009 | 07/08/2009 |  | 541743 | 0
453 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0235 | The City of Phoenix will design, procure, and install wireless communications devices along various corridors to improve communications facilitating better traffic operations and management. | Safety/Traffic Management | 07/09/2009 | 07/09/2009 |  | 398461 | 0
454 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0236 | The City of Phoenix will perform an inventory, procure, and install traffic control signs along various corridors to aid in the control and management of traffic. | Safety/Traffic Management | 07/09/2009 | 07/09/2009 |  | 2079819 | 0
455 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0237 | The City of Phoenix will perform a Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (North Area). | Pavement Improvement | 07/09/2009 | 07/09/2009 |  | 6798216 | 16
456 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0238 | The City of Phoenix, will perform Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (Central Area). | Pavement Improvement | 07/09/2009 | 07/09/2009 |  | 6716919 | 16
457 | Arizona | MARICOPA | PHOENIX, AZ | 4 | PHX0239 | The City of Phoenix, will perform Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (South Area). | Pavement Improvement | 07/09/2009 | 07/09/2009 |  | 6797577 | 16
458 | Arizona | PIMA | TUCSON | 7 | PPM0161 | The Pima County will perform a transportation enhancement project which consists of new paved shoulders, shared use driveway improvements, and access ramps near the Hohokam Middle School in Pima Count | Other | 07/07/2009 | 07/07/2009 | 09/30/2011 | 404890.96 | 1
459 | Arizona | PIMA | TUCSON | 7 | PPM0214 | The Pima County will perform pavement preservation projects in various locations throughout Pima County. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 09/30/2011 | 1224640.26 | 0
460 | Arizona | PIMA | TUCSON | 7 | PPM0215 | Pima County will complete bridge deck repairs from along Sabino Canyon Rd and Tanque Verde Creek in PIMA COUNTY. | Bridge Improvement | 06/22/2009 | 06/22/2009 | 09/30/2011 | 600000 | 43
461 | Arizona | PIMA | TUCSON | 7 | PPM0218 | The Pima County will perform pavement preservation projects in the La Canadad Area | Pavement Improvement | 07/07/2009 | 07/07/2009 | 09/30/2011 | 818499.94 | 0
462 | Arizona | PIMA | TUCSON | 7 | PPM0219 | The Pima County will perform pavement preservation projects in the Flowing Wells Area | Pavement Improvement | 07/07/2009 | 07/07/2009 | 09/30/2011 | 478600 | 0
463 | Arizona | PIMA | TUCSON | 7 | PPM0220 | The Pima County will perform Countywide Overlay projects in various locations throughout Pima County. | Pavement Improvement | 07/07/2009 | 07/07/2009 | 09/30/2011 | 1308900.06 | 0
464 | Arizona | PIMA | TUCSON | 7 | PPM0221 | The Pima County will perform Countywide Microseal projects in various locations throughout Pima County. | Pavement Improvement | 07/07/2009 | 07/07/2009 | 09/30/2011 | 1531700 | 0
465 | Arizona | PIMA | TUCSON | 7 | PPM0222 | The Pima County will perform Countywide Chipseal projects in various locations throughout Pima County. | Pavement Improvement | 07/07/2009 | 07/07/2009 | 09/30/2011 | 597800 | 0
466 | Arizona | YAVAPAI |  | 1 | PRV0004 | The City of Prescott Valley will perform a Transportation Enhancement project along Bison Lane in PRESCOTT VALLEY to include a shared use pathway. | Other | 08/24/2009 | 08/24/2009 |  | 486218.68 | 0.6
467 | Arizona | YAVAPAI | FLAGSTAFF | 1 | PRV0203 | The City of Prescott Valley will perform a Pavement Preservation along Glassford Hill Road in PRESCOTT VALLEY to include Overlay/ 3" AC. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 1574155 | 0
468 | Arizona | MARICOPA | PHOENIX, AZ | 3 | PVY0202 | The Town of Paradise Valley, AZ will perform Design and construction of pavement resurfacing along Various Roadways in PARADISE VALLEY. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 823174 | 3.7
469 | Arizona | MARICOPA | PHOENIX, AZ | 6 | QCR0205 | The City of Queen Creek, AZ will perform Design and construction of roadway resurfacing and shoulder paving along Various Locations on Rittenhouse Rd in QUEEN CREEK. | Pavement Improvement | 08/11/2009 | 08/11/2009 |  | 972905 | 1.7
470 | Arizona | PIMA |  | 7 | SAH0201 | The Town of Sahuarita will perform a pavement preservation project in Rancho Sahuarita: La Villita to 2 miles north and Traffic signals & signage reflectivity upgrades and Duval Mine Rd: La Canada to | Pavement Improvement | 07/01/2009 | 07/01/2009 |  | 1691785 | 2.6
471 | Arizona | MARICOPA | PHOENIX, AZ | 5 | SCT0200 | The City of Scottsdale, AZ will construct a Shared use pathway along Crosscut Canal, from Thomas Rd to Indian School Rd in SCOTTSDALE to include Shared use pathway and pedestrian bridge. | Other | 11/18/2009 |  |  | 763491 | 0.8
472 | Arizona | MARICOPA | PHOENIX, AZ | 5 | SCT0203 | The City of Scottsdale, AZ will construct a Shared use pathway along Arizona Canal (Sun Circle Trail) at Goldwater Blvd in SCOTTSDALE. | Transportation Enhancements | 09/09/2009 | 12/07/2009 | 08/15/2010 | 337622.87 | 0.1
473 | Arizona | MARICOPA | PHOENIX, AZ | 5 | SCT0206 | The City of Scottsdale will upgraded traffic controllers and cabinets at various locations in the southern area of Scottsdale to improve traffic operations and management. | Safety/Traffic Management | 08/05/2009 | 08/05/2009 | 12/12/2010 | 476615 | 0
474 | Arizona | MARICOPA | PHOENIX, AZ | 5 | SCT0209 | The City of Scottsdale, will perform Pavement Preservation along Various Roadways in the City of Scottsdale. | Pavement Improvement | 09/09/2009 | 09/09/2009 | 09/14/2010 | 4600000 | 10.5
475 | Arizona | NAVAJO |  | 1 | SLW0201 | The Navajo County will perform a Pavement Preservation along Penrod Road in SHOW LOW. | Pavement Improvement | 07/01/2009 | 07/01/2009 |  | 687362 | 4.1
476 | Arizona | MARICOPA | PHOENIX, AZ | 5 | SRI0200 | The Salt River Pima-Maricopa Indian Community, will Design & Construct Pavement Preservation/Chip-Seal along Various Locations on Functionally Classified Roads within Salt River Pima - Maricopa Indian | Pavement Improvement | 08/03/2009 | 08/03/2009 |  | 653910 | 2
477 | Arizona | PIMA | TUCSON | 7 | STC0200 | The City of South Tucson will perform a pavement preservation project along 29th Street; from 12th Avenue to the Union Pacific Railroad in SOUTH TUCSON. | Pavement Improvement | 06/23/2009 | 06/23/2009 |  | 555000 | 0.5
478 | Arizona | GILA |  | 1 | SUP0200 | The Town of Superior will perform a Pavement Preservation along Main Street. | Pavement Improvement | 06/18/2009 | 06/18/2009 | 05/28/2010 | 496574 | 1
479 | Arizona | MARICOPA | PHOENIX, AZ | 2 | SUR0208 | The City of Surprise will perform a Pre-Engineer/Design and construct pavement Reconstruction and ITS Conduit Installation along Bell Rd; Parkview to West City Limit in SURPRISE. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 01/29/2010 | 2797836 | 4.3
480 | Arizona | PIMA |  | 8 | SVS0200 | The City of Sierra Vista will complete transportation enhancement along Snyder Boulevard multi-use path, Avenida del Sol to SR-92 in SIERRA VISTA to include pathways, landscaping, and irrigation. | Other | 08/31/2009 | 09/21/2009 | 01/21/2010 | 454000 | 0.5
481 | Arizona | COCHISE | PHOENIX, AZ | 8 | SVS0204 | The City of Sierra Vista will perform widening, signal upgrades, drainage, improvements, curb, sidewalk, multi-use pathways on South side along Charleston Road. | Other | 06/11/2009 | 06/11/2009 | 12/26/2010 | 2208506 | 1.2
482 | Arizona | GRAHAM |  | 1 | THR0200 | The Town of Thatcher will perform a 2 inch asphalt overlay along Reay Lane in the Town of Thatcher. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 586574 | 2
483 | Arizona | MARICOPA | PHOENIX, AZ | 5 | TMP0202 | The City of Tempe, AZ will construct a Shared Use Pathway along Crosscut Canal from Papago Park to Mouer Park in TEMPE. | Transportation Enhancements | 07/30/2010 |  |  | 823772.07 | 1
484 | Arizona | MARICOPA | PHOENIX, AZ | 5 | TMP0211 | The City of Tempe, AZ will Construct a replacement bridge over the Western Canal along Baseline Rd (Kyrene Rd to Union Pacific Railroad) in TEMPE. | Bridge Replacement | 08/11/2009 | 08/11/2009 | 11/15/2010 | 2136143 | 0.2
485 | Arizona | PIMA | TUCSON | 7 | TUC0051 | The City of Tucson will install, repair or replace deteriorated sidewalks/driveways along South Fourth Avenue in TUCSON. | Other | 09/14/2009 | 09/14/2009 | 06/08/2010 | 358625 | 0.5
486 | Arizona | PIMA | TUCSON | 7 | TUC0073 | The City of Tucson will perform a transportation enhancement project along Fourth Avenue between 17th and 22nd Streets in Tucson to include construction of sidewalks and driveways to meet ADA standard | Transportation Enhancements | 03/01/2010 | 03/01/2010 | 08/27/2010 | 298800 | 0
487 | Arizona | PIMA | TUCSON | 7 | TUC0231 | The City of Tucson will perform pavement preservation projects at various locations within the City of Tucson. | Pavement Improvement | 06/18/2009 | 06/18/2009 | 02/12/2010 | 7376691 | 0
488 | Arizona | PIMA | TUCSON | 7 | TUC0232 | The City of Tucson will complete various pavement preservation projects within the City of Tucson. | New Construction | 09/03/2009 | 09/03/2009 | 07/17/2010 | 3482051 | 0
489 | Arizona | MARICOPA | PHOENIX, AZ | 2 | WBG0200 | The Town of Wickenburg, will perform a Pavement Preservation project along North Vulture Mine Rd; from US 60 to Northern Town Limits in WICKENBURG to include Mill and Replace. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 642619 | 1.6
490 | Arizona | MARICOPA | PHOENIX, AZ | 2 | YTN0200 | The Town of Youngtown will perform a Pre-Engineer/Design to construct, mill and replace pavement resurfacing along Peoria Ave; 111th Ave to 115th Av in YOUNGTOWN. | Pavement Improvement | 06/12/2009 | 06/12/2009 |  | 395711 | 0
491 | Arizona | YUMA | YUMA (CA) | 7 | YUM0200 | The City of Yuma will perform a Transportation Enhancement project in YUMA to include Construction of an interpretative plaza, complete with retaining walls. | Other | 08/01/2009 | 08/01/2010 | 01/01/2011 | 750000 | 0.2
492 | Arizona | YUMA |  | 7 | YYU0031 | The Yuma County will perform a Bridge Replacement project for Red Top Wash Bridge in Yuma. | Bridge Replacement | 03/03/2009 | 11/19/2009 |  | 1325000 | 0
493 | Arizona | YUMA | YUMA (CA) | 7 | YYU0200 | The Yuma County will perform a round-about construction project along Avenue E @ Juan Sanchez Blvd within the New San Luis II POE in YUMA COUNTY. | Pavement Improvement | 09/10/2009 | 09/10/2009 |  | 932000 | 2
494 | Arizona | YAVAPAI |  | 1 | YYV0202 | The Yavapai County will perform a Cold in place recycle; reconstruction along Cornville Rd; from Aspaas Rd to Beaverhead Flat Rd in YAVAPAI COUNTY. | Pavement Improvement | 06/18/2009 | 06/18/2009 |  | 788541 | 3.8
495 | Arkansas | LAWRENCE |  | 01 | ARR1001 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT THE EMBANKMENT AND BRIDGES FOR 9.89 MILES OF THE NEW LOCATION OF HIGHWAY 67 BETWEEN HIGHWAY 230 AND HIGHWAY 63, SOUTH OF HOXIE IN LAWRENCE COUNTY. WORK INC | New Construction | 06/22/2009 | 07/15/2009 | 12/31/2012 | 21094279 | 19.78
496 | Arkansas | PULASKI |  | 02 | ARR1003 | THE PURPOSE OF THIS PROJECT IS TO REPLACE FOUR EXISTING BRIDGE STRUCTURES, RECONSTRUCT APPROACHES ON I-430 AND CONSTRUCT WIDENING TO THE I-630 LOOP RAMP CONNECTIONS AT THE I-430/I-630 INTERCHANGE IN | Bridge Improvement | 07/17/2009 | 07/20/2009 | 11/15/2010 | 15991380 | 0
497 | Arkansas | ST FRANCIS |  | 01 | ARR1004 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.30 MILES OF HIGHWAY 1 BETWEEN THE CITIES OF CALDWELL AND COLT IN ST. FRANCIS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE | Pavement Improvement | 06/15/2009 | 07/07/2009 | 08/21/2009 | 1673191 | 4.3
498 | Arkansas | PHILLIPS |  | 01 | ARR1005 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.36 MILES OF HIGHWAY 49B BETWEEN HIGHWAY 49 AND HIGHWAY 242 IN THE CITY OF HELENA-WEST HELENA, PHILLIPS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, | Pavement Improvement | 06/03/2009 | 07/02/2009 | 07/15/2009 | 391184 | 1.36
499 | Arkansas | MONROE |  | 01 | ARR1006 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.45 MILES OF HIGHWAY 49 FROM HIGHWAY 241 NORTH IN THE VICINITY OF THE CITY OF RICH IN MONROE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, MAINTENANCE | Pavement Improvement | 04/22/2009 | 06/19/2009 | 07/09/2009 | 580419 | 2.45
500 | Arkansas | CRITTENDEN |  | 01 | ARR1007 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 9.63 MILES OF HIGHWAY 79 IN CRITTENDEN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELL | Pavement Improvement | 04/20/2009 | 04/22/2009 | 07/15/2009 | 2139531 | 9.63
501 | Arkansas | LINCOLN |  | 04 | ARR1008 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.39 MILES OF HIGHWAY 425 NORTH AND SOUTH OF STAR CITY IN LINCOLN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, P | Pavement Improvement | 04/17/2009 | 05/04/2009 | 07/06/2009 | 1256575 | 5.39
502 | Arkansas | CHICOT |  | 04 | ARR1010 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.75 MILES OF HIGHWAY 65 BETWEEN THE CITY OF LAKE VILLAGE AND THE CITY OF MCMILLAN CORNER IN CHICOT COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD | Pavement Improvement | 06/03/2009 | 06/30/2009 | 09/14/2009 | 1175182 | 3.73
503 | Arkansas | ASHLEY |  | 04 | ARR1011 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 6.09 MILES OF HIGHWAY 82 EAST OF THE CITY OF CROSSETT IN ASHLEY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUTTERS, MAINTENAN | Pavement Improvement | 06/15/2009 | 06/26/2009 | 09/14/2009 | 1863272 | 6.09
504 | Arkansas | ARKANSAS |  | 01 | ARR1012 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.11 MILES OF SELECTED SECTIONS OF HIGHWAY 79 BETWEEN HIGHWAY 79C AND HIGHWAY 165 NEAR THE CITY OF STUTTGART IN ARKANSAS COUNTY. WORK INCLUDES PAVEMENT | Pavement Improvement | 04/17/2009 | 05/22/2009 | 07/01/2009 | 682688 | 3.11
505 | Arkansas | PIKE |  | 04 | ARR1013 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.06 MILES OF HIGHWAY 70 FROM THE CITY OF KIRBY EAST IN PIKE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEME | Pavement Improvement | 04/22/2009 | 04/30/2009 | 08/10/2009 | 1020068 | 3.06
506 | Arkansas | NEVADA |  | 04 | ARR1014 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.02 MILES OF HIGHWAY 67 FROM THE CITY OF PRESCOTT SOUTH IN NEVADA COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUTTERS, MAINTE | Pavement Improvement | 06/15/2009 | 06/15/2009 | 09/14/2009 | 953699 | 3.02
507 | Arkansas | HEMPSTEAD |  | 04 | ARR1015 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.67 MILES OF HIGHWAY 278 BETWEEN HAZEL STREET AND GREENWOOD STREET IN THE CITY OF HOPE, HEMPSTEAD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD M | Pavement Improvement | 06/08/2009 | 06/08/2009 | 09/14/2009 | 335086 | 1.67
508 | Arkansas | LITTLE RIVER |  | 04 | ARR1016 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.41 MILES OF HIGHWAY 71 BETWEEN THE CITIES OF ASHDOWN AND WILTON IN LITTLE RIVER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENAN | Pavement Improvement | 04/27/2009 | 04/27/2009 | 07/24/2009 | 833726 | 3.41
509 | Arkansas | SEVIER |  | 04 | ARR1017 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.01 MILES OF HIGHWAY 70 FROM THE CITY OF DEQUEEN WEST IN SEVIER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PA | Pavement Improvement | 06/08/2009 | 06/08/2009 | 08/20/2009 | 368943 | 1.01
510 | Arkansas | LAFAYETTE |  | 04 | ARR1018 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.08 MILES OF HIGHWAY 82 EAST AND WEST OF THE RED RIVER IN MILLER AND LAFAYETTE COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH | Pavement Improvement | 04/27/2009 | 05/21/2009 | 08/10/2009 | 607701 | 4.16
511 | Arkansas | HEMPSTEAD |  | 04 | ARR1019 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.45 MILES OF HIGHWAY 278 FROM THE CITY OF OZAN WEST IN HEMPSTEAD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, P | Pavement Improvement | 06/08/2009 | 08/18/2009 | 09/14/2009 | 885084 | 5.45
512 | Arkansas | WASHINGTON |  | 03 | ARR1020 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.78 MILES OF HIGHWAY 412 BETWEEN HIGHWAY 112 AND INTERSTATE 540 IN THE CITY OF SPRINGDALE, WASHINGTON COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, CO | Pavement Improvement | 04/23/2009 | 05/26/2009 | 07/08/2009 | 570814 | 1.78
513 | Arkansas | FRANKLIN |  | 03 | ARR1021 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.09 MILES OF HIGHWAY 22 FROM CHARLESTON EAST IN FRANKLIN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROSION C | Pavement Improvement | 06/15/2009 | 07/27/2009 | 09/14/2009 | 684500 | 3.09
514 | Arkansas | LOGAN |  | 04 | ARR1022 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.77 MILES OF HIGHWAY 22 BETWEEN THE CITIES OF SUBIACO AND MIDWAY IN LOGAN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF T | Pavement Improvement | 04/17/2009 | 04/23/2009 | 05/28/2009 | 691491 | 2.77
515 | Arkansas | SHARP |  | 04 | ARR1023 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.47 MILES OF HIGHWAY 71 SOUTH OF THE CITY OF WALDRON IN SCOTT COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROS | Pavement Improvement | 06/15/2009 | 07/07/2009 | 08/07/2009 | 805350 | 3.47
516 | Arkansas | SEBASTIAN |  | 03 | ARR1024 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.74 MILES OF HIGHWAY 22 FROM INTERSTATE 540 EAST IN THE CITY OF FORT SMITH, SEBASTIAN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAIN | Pavement Improvement | 06/08/2009 | 07/31/2009 | 09/07/2009 | 1021316 | 2.74
517 | Arkansas | POLK |  | 04 | ARR1025 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.65 MILES OF HIGHWAY 71 SOUTH AND NORTH OF HIGHWAY 8 IN THE CITY OF MENA, POLK COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE | Pavement Improvement | 04/27/2009 | 05/29/2009 | 06/24/2009 | 581777 | 1.65
518 | Arkansas | CRAWFORD |  | 03 | ARR1026 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.00 MILES OF HIGHWAY 64 FROM ALMA EAST IN CRAWFORD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROSION CONTROL | Pavement Improvement | 04/20/2009 | 04/20/2009 | 07/24/2009 | 524121 | 2
519 | Arkansas | WHITE |  | 02 | ARR1027 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.67 MILES OF HIGHWAY 167 NORTH OF THE CITY OF BALD KNOB IN WHITE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, P | Pavement Improvement | 06/08/2009 | 07/27/2009 | 09/01/2009 | 1132854 | 3.67
520 | Arkansas | STONE |  | 01 | ARR1028 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.57 MILES OF HIGHWAY 14 EAST OF THE CITY OF MOUNTAIN HOME IN STONE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 04/17/2009 | 05/04/2009 | 05/19/2009 | 438853 | 1.57
521 | Arkansas | WHITE |  | 02 | ARR1029 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.88 MILES OF HIGHWAY 167 FROM THE JACKSON COUNTY LINE NORTH IN WHITE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFI | Pavement Improvement | 06/08/2009 | 07/09/2009 | 09/14/2009 | 862415 | 2.83
522 | Arkansas | WHITE, INDEPENDENCE |  | 01,02 | ARR1030 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.64 MILES OF HIGHWAY 167 FROM THE CITY OF PLEASANT PLAINS SOUTH IN INDEPENDENCE AND WHITE COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING | Pavement Improvement | 04/17/2009 | 05/28/2009 | 06/01/2009 | 862046 | 4.78
523 | Arkansas | CLEBURNE |  | 01 | ARR1031 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.66 MILES OF HIGHWAY 25 FROM GREERS FERRY DAM SOUTH IN THE VICINITY OF THE CITY OF HEBER SPRINGS IN CLEBURNE COUNTY. WORK INCLUDES PAVEMENT REHABILITAT | Pavement Improvement | 04/22/2009 | 07/15/2009 | 08/10/2009 | 648533 | 2.66
524 | Arkansas | INDEPENDENCE |  | 01 | ARR1032 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.14 MILES OF HIGHWAY 69 FROM THE BLACK RIVER WEST IN INDEPENDENCE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 06/03/2009 | 07/06/2009 | 09/14/2009 | 245794 | 1.14
525 | Arkansas | PULASKI |  | 02 | ARR1033 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.10 MILES OF INTERSTATE 40 BETWEEN INTERSTATE 30 AND HIGHWAY 67 IN THE CITY OF NORTH LITTLE ROCK, PULASKI COUNTY. WORK INCLUDES CONCRETE PAVEMENT PATCH | Pavement Improvement | 08/04/2009 | 08/17/2009 | 11/13/2009 | 1892346 | 1.1
526 | Arkansas | LONOKE |  | 01 | ARR1034 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.80 MILES OF HIGHWAY 70 FROM THE PULASKI COUNTY LINE EAST IN LONOKE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, TRENCHING AND SHOULDER PREPARATION, | Pavement Improvement | 04/28/2009 | 04/28/2009 | 06/30/2009 | 467972 | 2.8
527 | Arkansas | HOT SPRING |  | 04 | ARR1035 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.20 MILES OF HIGHWAY 67 FROM THE CITY OF GLEN ROSE SOUTH IN HOT SPRING COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, TRENCHING AND SHOULDER PREPARATIO | Pavement Improvement | 04/17/2009 | 05/05/2009 | 06/17/2009 | 264789 | 1.2
528 | Arkansas | PRAIRIE |  | 01 | ARR1036 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.40 MILES OF HIGHWAY 70 BETWEEN HAZEN AND DEVALLS BLUFF IN PRAIRIE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 04/22/2009 | 04/22/2009 | 06/17/2009 | 993892 | 5.4
529 | Arkansas | LONOKE, PULASKI |  | 02 | ARR1037 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.25 MILES OF HIGHWAY 165 BETWEEN THE CITIES OF NORTH LITTLE ROCK AND SCOTT IN LONOKE AND PULASKI COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD | Pavement Improvement | 06/01/2009 | 06/08/2009 | 09/14/2009 | 1181822 | 11.25
530 | Arkansas | OUACHITA |  | 04 | ARR1038 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.60 MILES OF HIGHWAY 79 BETWEEN THE CITIES OF CAMDEN AND EAST CAMDEN IN OUACHITA COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH | Pavement Improvement | 06/03/2009 | 06/22/2009 | 09/14/2009 | 1294334 | 2.6
531 | Arkansas | DALLAS |  | 04 | ARR1039 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.61 MILES OF HIGHWAY 79 IN DALLAS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEO | Pavement Improvement | 04/17/2009 | 05/07/2009 | 06/24/2009 | 1124559 | 3.61
532 | Arkansas | CLEVELAND |  | 04 | ARR1040 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 9.50 MILES OF HIGHWAY 79 BETWEEN THE CITIES OF KINGLAND AND RISON IN CLEVELAND COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUT | Pavement Improvement | 06/03/2009 | 06/11/2009 | 08/21/2009 | 1354932 | 9.5
533 | Arkansas | CALHOUN |  | 04 | ARR1041 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.12 MILES OF HIGHWAY 167 FROM THE CITY OF HAMPTON SOUTH IN CALHOUN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 04/17/2009 | 05/05/2009 | 06/09/2009 | 1026517 | 4.12
534 | Arkansas | VAN BUREN |  | 02 | ARR1042 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.87 MILES OF HIGHWAY 65 NORTH OF THE CITY OF CLINTON IN VAN BUREN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 06/08/2009 | 08/10/2009 | 09/14/2009 | 1725247 | 5.87
535 | Arkansas | FAULKNER |  | 02 | ARR1043 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.68 MILES OF HIGHWAY 65 NORTH AND SOUTH OF HIGHWAY 25 IN THE CITY OF GREENBRIER, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 04/22/2009 | 07/02/2009 | 08/03/2009 | 778244 | 2.68
536 | Arkansas | YELL |  | 02 | ARR1044 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.90 MILES OF HIGHWAY 10 EAST AND WEST OF THE CITY OF MICKLES IN YELL COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFI | Pavement Improvement | 04/17/2009 | 04/27/2009 | 07/07/2009 | 1092148 | 5.9
537 | Arkansas | POPE |  | 03 | ARR1045 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.64 MILES OF HIGHWAY 7 BETWEEN J STREET AND HIGHWAY 326 IN THE CITY OF RUSSELLVILLE, POPE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 06/04/2009 | 09/04/2009 | 09/14/2009 | 467277 | 1.64
538 | Arkansas | FAULKNER |  | 02 | ARR1046 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 0.37 MILE OF HIGHWAY 65 BETWEEN THE INTERSTATE 40 OFF AND ON RAMPS IN THE CITY OF CONWAY, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD M | Pavement Improvement | 04/22/2009 | 07/02/2009 | 08/05/2009 | 182026 | 0.74
539 | Arkansas | BENTON |  | 03 | ARR1047 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE HIGHWAY 412 FROM HIGHWAY 59 IN THE CITY OF SILOAM SPRINGS TO THE EAST 5.45 MILES IN BENTON COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 06/01/2009 | 06/22/2009 | 08/27/2009 | 2030641 | 5.45
540 | Arkansas | BOONE |  | 03 | ARR1048 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.40 MILES OF HIGHWAY 65 FROM THE MISSOURI STATE LINE SOUTH IN BOONE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC | Pavement Improvement | 04/22/2009 | 05/04/2009 | 07/28/2009 | 2871797 | 7.4
541 | Arkansas | GREENE |  | 01 | ARR1052 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.79 MILES OF HIGHWAY 412 BETWEEN REYNOLDS ROAD AND HIGHWAY 49B IN THE CITY OF PARAGOULD, GREENE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MIL | Pavement Improvement | 06/08/2009 | 08/19/2009 | 09/14/2009 | 770949 | 1.79
542 | Arkansas | MISSISSIPPI |  | 01 | ARR1053 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 0.84 MILE OF HIGHWAY 18 FROM INTERSTATE 55 WEST IN THE CITY OF BLYTHEVILLE, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAI | Pavement Improvement | 04/27/2009 | 04/27/2009 | 05/28/2009 | 348065 | 0.84
543 | Arkansas | CLAY |  | 01 | ARR1054 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.10 MILES OF HIGHWAY 67 BETWEEN HIGHWAY 328 NORTH OF CORNING AND THE MISSOURI STATE LINE IN CLAY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MI | Pavement Improvement | 06/08/2009 | 07/15/2009 | 09/14/2009 | 1098919 | 4.1
544 | Arkansas | MISSISSIPPI |  | 01 | ARR1055 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.10 MILES OF HIGHWAY 140 WEST AND EAST OF HIGHWAY 119Y IN THE CITY OF OSCEOLA, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 04/27/2009 | 05/15/2009 | 06/09/2009 | 452888 | 1.1
545 | Arkansas | LAWRENCE |  | 01 | ARR1056 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE A 0.26 MILE SECTION OF HIGHWAY 412 BETWEEN HIGHWAY 67B NORTH AND HIGHWAY 67B SOUTH IN THE CITY OF WALNUT RIDGE, LAWRENCE COUNTY. WORK INCLUDES PAVEMENT | Pavement Improvement | 06/01/2009 | 08/11/2009 | 09/14/2009 | 125418 | 0.25
546 | Arkansas | RANDOLPH |  | 01 | ARR1057 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.05 MILES OF HIGHWAY 67 FROM HIGHWAY 90 NORTH IN THE THE CITY OF POCAHONTAS, RANDOLPH COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAIN | Pavement Improvement | 04/17/2009 | 05/14/2009 | 08/03/2009 | 174441 | 1.05
547 | Arkansas | POINSETT |  | 01 | ARR1058 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.14 MILES OF HIGHWAY 63 FROM THE CRAIGHEAD COUNTY LINE TO HIGHWAY 69 WEST OF THE CITY OF TRUMANN IN POINSETT COUNTY. WORK INCLUDES PAVEMENT REHABILITAT | Pavement Improvement | 06/01/2009 | 06/04/2009 | 09/14/2009 | 673482 | 2.14
548 | Arkansas | CRAIGHEAD |  | 01 | ARR1059 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.59 MILES OF HIGHWAY 63 BETWEEN HIGHWAY 91 AND HIGHWAY 226 IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK INCLUDES CONCRETE PAVEMENT GRINDING AND P | Pavement Improvement | 05/08/2009 | 06/04/2009 | 10/30/2009 | 1182066 | 3.59
549 | Arkansas | GARLAND |  | 04 | ARR1060 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 0.37 MILE OF HIGHWAY 128 FROM SHADY GROVE ROAD TO NORTH OF HIGHWAY 270 IN THE CITY OF HOT SPRINGS, GARLAND COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADW | Pavement Widening | 09/23/2009 | 10/27/2009 | 06/25/2010 | 1583907 | 0.37
550 | Arkansas | GRANT |  | 04 | ARR1061 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.1 MILES OF HIGHWAY 167 BETWEEN NORTH MILLERVILLE AND THE SHERIDAN BYPASS IN GRANT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN | Pavement Widening | 09/18/2009 | 09/24/2009 | 07/22/2011 | 8819100 | 4.08
551 | Arkansas | SEBASTIAN |  | 03 | ARR1063 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT FOUR MAIN LANE BRIDGES AS PART OF THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49) BETWEEN TAYLOR AVENUE AND HIGHWAY 22 NEAR FT. CHAFFEE IN SEBASTIAN C | New Bridge Construction | 07/06/2009 | 07/09/2009 | 12/30/2010 | 11693084 | 0.66
552 | Arkansas | SEBASTIAN |  | 03 | ARR1064 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 2.69 MILES OF GRADING AND STRUCTURES OF THE NEW LOCATION HIGHWAY 71 BETWEEN CO ROAD 8 AND CUSTER BLVD. NEAR FORT CHAFFEE IN SEBASTIAN COUNTY. WORK WILL INC | New Construction | 10/16/2009 | 10/15/2009 | 09/30/2011 | 10730011 | 5.38
553 | Arkansas | MILLER |  | 04 | ARR1065 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 1.77 MILES OF EMBANKMENT AND MINOR DRAINAGE STRUCTURES FOR THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49) BETWEEN COUNTY ROAD 2 AND DODDRIDGE, SOUTH | New Construction | 08/21/2009 | 09/03/2009 | 06/25/2011 | 6685747 | 1.77
554 | Arkansas | CRAIGHEAD |  | 01 | ARR1066 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 141 AND PARKER ROAD IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK ITEMS INCLUDE TRAFFIC SI | Safety/Traffic Management | 06/08/2009 | 10/20/2009 | 12/18/2009 | 83737 | 0
555 | Arkansas | ARKANSAS |  | 01 | ARR1067 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT APPROXIMATELY 1.30 MILES OF COUNTY ROADS 33 AND 43 NEAR THE CITY OF ALMYRA IN ARKANSAS COUNTY. WORK WILL INCLUDE RECONSTRUCTING THE EXISTING ROADWAY, PAV | Pavement Improvement | 06/15/2009 | 06/26/2009 | 08/14/2009 | 156690 | 1.26
556 | Arkansas | CRITTENDEN |  | 01 | ARR1068 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A WELCOME CENTER AT THE COMMON SECTION OF INTERSTATE 55 AND INTERSTATE 40 IN WEST MEMPHIS, CRITTENDEN COUNTY. WORK ITEMS INCLUDE EARTHWORK, A WELCOME CENTE | Transportation Enhancements | 04/07/2010 | 05/11/2010 | 07/01/2012 | 3830174 | 0
557 | Arkansas | WHITE |  | 02 | ARR2001 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 67B, HIGHWAY 31 AND HIGHWAY 367 INTERSECTION IN THE CITY OF BEEBE IN WHITE COUNTY. WORK ITEMS INCLUDE TRAFFIC S | Safety/Traffic Management | 02/11/2010 | 04/21/2010 | 05/20/2010 | 76337 | 0
558 | Arkansas | VAN BUREN |  | 02 | ARR2002 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 65 AND HIGHWAY 16 EAST IN THE CITY OF CLINTON IN VAN BUREN COUNTY. WORK ITEMS INCLUDE TRAFFIC S | Safety/Traffic Management | 03/25/2010 | 05/06/2010 | 10/08/2010 | 62720 | 0
559 | Arkansas | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2003 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A 2-LANE ROUNDABOUT ON PIKE AVENUE IN NORTH LITTLE ROCK, PULASKI COUNTY. THE WORK WILL ALSO INCLUDE CURBS, GUTTERS, SIDEWALKS, DRAINAGE, LANDSCAPING AND EL | Pavement Widening | 01/11/2010 |  | 12/16/2010 | 1489935 | 0.17
560 | Arkansas | PULASKI |  | 02 | ARR2006 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT TWO CONCRETE. BOX CULVERTS AND APPROACHES ON 0.360 MILE OF COUNTY ROAD 67 IN THE VICINITY OF SHERWOOD IN PULASKI COUNTY. WORK INCLUDES CLEARING AND GRUBBI | Bridge Replacement | 09/17/2009 | 09/17/2009 | 09/01/2010 | 770372 | 0.36
561 | Arkansas | BENTON |  | 03 | ARR2008 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A BRIDGE AND APPROACHES ON APPROXIMATELY 0.47 MILE OF COUNTY ROAD 9 NEAR SILOAM SPRINGS IN BENTON COUNTY. WORK WILL INCLUDE CLEARING, GRADING, DRAINAGE IMP | Bridge Replacement | 11/20/2009 | 02/03/2010 | 05/14/2011 | 1319151 | 0.46
562 | Arkansas | BRADLEY |  | 04 | ARR2009 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT ONE CONCRETE BOX CULVERT AND APPROACHES ON 0.80 MILE OF COUNTY ROAD 2 IN THE VICINITY OF HERMITAGE IN BRADLEY COUNTY. WORK INCLUDES CLEARING AND GRUBBING, | Pavement Improvement | 08/12/2009 | 08/20/2009 | 12/18/2009 | 319946 | 1.6
563 | Arkansas | RANDOLPH |  | 01 | ARR2010 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT ONE BRIDGE LENGTH STRUCTURE AND APPROACHES ON 0.492 MILE OF COUNTY ROAD 48 NEAR POCAHONTAS IN RANDOLPH COUNTY. WORK INCLUDES GRADING, DRAINAGE IMPROVEMENTS, | Bridge Replacement | 06/22/2009 | 07/09/2009 | 12/22/2010 | 1693838 | 0.49
564 | Arkansas | CLARK |  | 01 | ARR2011 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT TWO BRIDGE LENGTH STRUCTURES AND APPROACHES ON 0.72 MILE OF COUNTY ROAD 38 NEAR ASH FLAT IN SHARP COUNTY. WORK WILL INCLUDE EARTHWORK, DRAINAGE IMPROVEMENT | Pavement Improvement | 07/14/2009 | 07/16/2009 | 12/22/2010 | 985359 | 0.72
565 | Arkansas | ST FRANCIS |  | 01 | ARR2012 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 1 AND HIGHWAY 306 IN THE CITY OF COLT IN ST. FRANCIS COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 11/06/2009 | 11/30/2009 | 07/23/2010 | 127341 | 0
566 | Arkansas | WASHINGTON |  | 03 | ARR2013 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 16 AND HIGHWAY 74 IN THE CITY OF ELKINS IN WASHINGTON COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 11/06/2009 | 02/17/2010 | 05/17/2010 | 65247 | 0
567 | Arkansas | CLARK |  | 04 | ARR2014 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL THREE TRAFFIC SIGNALS ON HIGHWAY 67 AT THE INTERSECTIONS OF HENDERSON STREET, HIGHWAY 51 WEST/PINE STREET AND HIGHWAY 51 EAST/CADDO STREET IN TH | Safety/Traffic Management | 11/13/2009 | 01/15/2010 | 07/30/2010 | 203370 | 0
568 | Arkansas | FAULKNER |  | 02 | ARR2016 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 64, ROOSTER ROAD AND LOWER RIDGE ROAD NEAR THE CITY OF CONWAY IN FAULKNER COUNTY. WORK ITEMS IN | Pavement Improvement | 08/19/2009 | 09/14/2009 | 02/05/2010 | 76248 | 0
569 | Arkansas | HEMPSTEAD |  | 04 | ARR2018 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 278, HIGHWAY 29 AND SHOVER ROAD IN THE CITY OF HOPE IN HEMPSTEAD COUNTY. WORK ITEMS INCLUDE TRA | Transportation Enhancements | 12/31/2009 | 06/02/2010 | 07/09/2010 | 113093 | 0
570 | Arkansas | HOWARD |  | 04 | ARR2019 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND INSTALL TRAFFIC SIGNALS ON HIGHWAY 371 AT THE INTERSECTIONS OF HIGHWAY 27/HIGHWAY 278 AND HIGHWAY 980/MAIN STREET IN THE CITY OF NASHVILLE, HOWARD COU | Safety/Traffic Management | 01/14/2010 | 03/23/2010 | 07/09/2010 | 207191 | 0
571 | Arkansas | INDEPENDENCE |  | 01 | ARR2021 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE THE TRAFFIC SIGNALS ON HIGHWAY 167 AT THE INTERSECTIONS OF SOUTHERLAND DRIVE, MYERS AVENUE, LAWRENCE STREET, VIRGINIA DRIVE AND COLLEGE AVENUE IN THE CIT | Safety/Traffic Management | 05/26/2010 |  |  | 220822 | 0
572 | Arkansas | WHITE |  | 02 | ARR2022 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 16 AND HOLMES ROAD INTERSECTION IN THE CITY OF SEARCY IN WHITE COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPM | Safety/Traffic Management | 02/18/2010 | 04/09/2010 | 05/20/2010 | 94063 | 0
573 | Arkansas | CLEBURNE |  | 01 | ARR2023 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 25/124 INTERSECTION IN THE CITY OF QUITMAN IN CLEBURNE COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT, REM | Safety/Traffic Management | 04/14/2010 |  | 11/12/2010 | 165163 | 0
574 | Arkansas | CLARK |  | 04 | ARR2025 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF INTERSTATE 30 AND HIGHWAY 7 IN THE CITY OF CADDO VALLEY IN CLARK COUNTY. WORK ITEMS INCLUDE TRAFFIC SIG | Safety/Traffic Management | 02/11/2010 | 06/29/2010 | 08/20/2010 | 117523 | 0
575 | Arkansas | HOT SPRING |  | 04 | ARR2027 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE TRAFFIC SIGNALS AT THE INTERSECTIONS OF HIGHWAY 270B/3RD STREET, HIGHWAY 270B/HIGHWAY 67, HIGHWAY 67/ASH STREET AND HIGHWAY 9/5TH STREET IN THE CITY OF M | Safety/Traffic Management | 04/27/2010 |  | 11/12/2010 | 288770 | 0
576 | Arkansas | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2029 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 100 AND VESTAL BLVD. INTERSECTION IN THE CITY OF NORTH LITTLE ROCK IN PULASKI COUNTY. WORK ITEMS INCLUDE TRAFFI | Safety/Traffic Management | 02/19/2010 |  | 08/20/2010 | 101867 | 0
577 | Arkansas | BENTON |  | 03 | ARR2030 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 279, HIGHWAY 340 AND HIGHLANDS BLVD. IN THE CITY OF BELLA VISTA IN BENTON COUNTY. WORK ITEMS I | Safety/Traffic Management | 03/05/2010 | 05/17/2010 | 08/20/2010 | 89105 | 0
578 | Arkansas | LINCOLN, DESHA |  | 04 | ARR2031 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 5.39 MILES OF HIGHWAY 65 NORTH AND SOUTH OF THE CITY OF GOULD IN LINCOLN AND DESHA COUNTIES. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, DRAINAGE IMPROVEM | Pavement Widening | 09/18/2009 | 12/10/2009 | 10/05/2012 | 15776865 | 5.39
579 | Arkansas | CRITTENDEN | MEMPHIS (TN-MS) | 01 | ARR2032 | THE PURPOSE OF THIS PROJECT IS TO RELOCATE RAMPS AND CONNECTOR ROUTES TO PROVIDE ACCESS TO THE NEW WELCOME CENTER LOCATED IN THE COMMON AREA OF INTERSTATE 55 AND INTERSTATE 40 IN THE CITY OF WEST MEMP | Transportation Enhancements | 05/26/2010 | 06/16/2010 |  | 6716160 | 0.1
580 | Arkansas | JEFFERSON |  | 04 | ARR2033 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL THREE TRAFFIC SIGNALS ON HIGHWAY 65B AT THE INTERSECTIONS OF CHERRY STREET, HIGHWAYS 79B/365, AND HIGHWAY 79B/UNIVERSITY DRIVE IN THE CITY OF PI | Safety/Traffic Management | 02/18/2010 | 03/25/2010 | 08/20/2010 | 333713 | 0
581 | Arkansas | SEBASTIAN |  | 03 | ARR2036 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 3.02 MILES OF HIGHWAY 22 BETWEEN HIGHWAY 255 AND HIGHWAY 96 IN THE VICINITY OF CENTRAL CITY, SEBASTIAN COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, | Pavement Widening | 06/03/2010 | 06/03/2010 |  | 12021297 | 3.02
582 | Arkansas | POLK |  | 04 | ARR2037 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 1.40 MILES OF A NORTHBOUND PASSING LANE ON HIGHWAY 71 BETWEEN COUNTY ROAD 16 AND HIGHWAY 246 NEAR VANDERVOORT IN POLK COUNTY. WORK WILL INCLUDE PASSING LAN | Pavement Widening | 02/23/2010 | 03/01/2010 | 04/30/2011 | 2015265 | 1.4
583 | Arkansas | SEBASTIAN | FORT SMITH (OK) | 03 | ARR2039 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AND PROVIDE OPERATIONAL IMPROVEMENTS AT THE INTERSECTION OF HIGHWAY 271 AND HARVARD AVENUE IN THE CITY OF FT. SMITH IN SEBASTIA | Pavement Improvement | 03/05/2010 | 03/31/2010 | 08/18/2010 | 191963 | 0.16
584 | Arkansas | WHITE |  | 02 | ARR2041 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A NORTHBOUND AND A SOUTHBOUND PASSING LANE FOR A DISTANCE OF 2.40 MILES ON HWY . 16, BETWEEN THE CITIES OF PANGBURN AND SEARCY IN WHITE COUNTY. WORK WILL A | Pavement Widening | 04/07/2010 | 04/12/2010 |  | 3294666 | 2.4
585 | Arkansas | UNION |  | 04 | ARR2043 | THE PURPOSE OF THIS PROJECT IS TO PROVIDE 3.22 MILES OF BASE AND SURFACING TO COMPLETE WIDENING HIGHWAY 167 BETWEEN CHAMPAGNOLLE ROAD AND HIGHWAY 7 SOUTH IN THE CITY OF EL DORADO, UNION COUNTY. WORK | New Construction | 11/09/2009 | 12/04/2009 | 07/22/2011 | 552587 | 3.22
586 | Arkansas | POPE |  | 03 | ARR2044 | THE PURPOSE OF THIS PROJECT IS TO WIDEN HIGHWAY 247 FROM HIGHWAY 7 EAST 5.26 MILES IN THE VICINITY OF POTTSVILLE, POPE COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN 11' CE | Pavement Widening | 07/07/2010 |  |  | 15252775 | 5.26
587 | Arkansas | FAULKNER |  | 02 | ARR2045 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A 10.10 MILE HIGHWAY 64 BYPASS OF THE CITY OF VILONIA IN FAULKNER COUNTY. WORK INCLUDES BASE, PAVING , EROSION CONTROL, PAVEMENT MARKINGS AND MISCELLANEOUS | New Construction | 04/28/2010 | 06/02/2010 | 12/15/2011 | 23931157 | 10.1
588 | Arkansas | BENTON |  | 03 | ARR2046 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AND PROVIDE INTERSECTION IMPROVEMENTS AT THE INTERSECTION OF HIGHWAY 112 AND HIGHWAY 264 EAST IN THE CITY OF CAVE SPRINGS IN BE | Pavement Widening | 03/09/2010 |  | 06/17/2011 | 684470 | 0
589 | Arkansas | BENTON |  | 03 | ARR2048 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 1.61 MILES OF HIGHWAY 412 BETWEEN THE OKLAHOMA STATE LINE AND WASHINGTON STREET IN SILOAM SPRINGS, BENTON COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADW | Pavement Widening | 01/14/2010 | 02/10/2010 | 11/20/2012 | 7070251 | 1.6
590 | Arkansas | CRAIGHEAD |  | 01 | ARR2049 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 3.55 MILES OF HIGHWAY 226 FROM THE NEW LOCATION OF HIGHWAY 67 TO WEST OF CASH IN CRAIGHEAD COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, FOUR BRIDG | Pavement Widening | 04/16/2010 | 05/04/2010 | 08/31/2012 | 13764995 | 7.56
591 | Arkansas | WASHINGTON, BENTON |  | 03 | ARR2050 | THE PURPOSE OF THIS PROJECT IS TO WIDEN RAMPS AND ADD AUXILIARY LANES AT FOUR INTERCHANGES IN BENTON AND WASHINGTON COUNTIES. IMPROVEMENTS AT A FIFTH INTERCHANGE (PORTER RD.) IN WASHINGTON COUNTY INV | Pavement Widening | 09/29/2009 | 10/12/2009 | 10/01/2010 | 2013305 | 0
592 | Arkansas | FAULKNER | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2052 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A RAILROAD OVERPASS BRIDGE WITH APPROACH EMBANKMENTS ON SALEM ROAD IN THE CITY OF CONWAY, FAULKNER COUNTY. WORK INCLUDES CONSTRUCTING THE RAILROAD OVERPASS | New Bridge Construction | 09/30/2009 | 09/30/2009 | 10/25/2010 | 2360595 | 0.31
593 | Arkansas | CHICOT |  | 04 | ARR2053 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 2.2 MILES OF HIGHWAY 65 BETWEEN FAIRVIEW AND THE LAKE VILLAGE TOURIST INFORMATION CENTER IN CHICOT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4 | Pavement Widening | 02/12/2010 | 02/17/2010 | 11/30/2010 | 6697617 | 2.28
594 | Arkansas | DALLAS |  | 04 | ARR2054 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.44 MILES OF HIGHWAY 167 BETWEEN FORDYCE AND HIGHWAY 273 IN DALLAS COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, FIVE STRUCTURES, DRAINAGE IMPROVEM | Pavement Widening | 01/12/2010 | 01/20/2010 | 10/12/2012 | 19721383 | 4.44
595 | Arkansas | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2055 | THE PURPOSE OF THIS PROJECT IS TO WIDEN BROCKINGTON ROAD BETWEEN HIGHWAY 176 AND MARYLAND AVENUE IN THE CITY OF SHERWOOD, PULASKI COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4 LANES WI | Pavement Widening | 05/04/2010 |  | 11/30/2011 | 4844503 | 0.73
596 | Arkansas | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2056 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 0.851 MILE OF HIGHWAY 107 IN PULASKI COUNTY. WORK INCLUDES GRADING, MINOR DRAINAGE STRUCTURES, PAVING, STORM DRAINS, EROSION CONTROL ITEMS, MAINTENANCE OF TRAF | Pavement Widening | 11/12/2009 | 11/12/2009 | 04/15/2011 | 2669342 | 0.85
597 | Arkansas | GRANT |  | 04 | ARR2057 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.91 MILES OF HIGHWAY 167 BETWEEN THE SALINE RIVER AND NORTH MILLERVILLE IN GRANT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN 11 | Bridge Replacement | 11/13/2009 | 12/01/2009 | 05/10/2013 | 7244745 | 4.91
598 | Arkansas | MILLER |  | 04 | ARR2058 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AN OVERPASS BRIDGE STRUCTURE AND 2.44 MILES OF EMBANKMENT AS PART OF THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49), BETWEEN THE LOUISIANA STATE LINE | New Construction | 01/26/2010 | 04/19/2010 | 12/31/2011 | 6856721 | 2.44
599 | Arkansas | PULASKI |  | 02 | ARR2059 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND WIDEN 1.57 MILES OF HIGHWAY 67 BETWEEN KIEHL AVENUE AND HIGHWAY 440 IN THE CITY OF SHERWOOD, PULASKI COUNTY. WORK INCLUDES WIDENING THE EXISTING ROAD | Pavement Widening | 03/19/2010 | 03/04/2010 | 12/20/2010 | 8516865 | 1.57
600 | Arkansas | CLEBURNE |  | 01 | ARR2060 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.96 MILES OF COUNTY ROAD 79 FROM WILBURN NORTH IN CLEBURNE COUNTY. | Pavement Improvement | 02/19/2010 | 04/06/2010 |  | 287990 | 2.96
601 | Arkansas | HEMPSTEAD |  | 04 | ARR2061 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.83 MILES OF COUNTY ROAD 88 BETWEEN HIGHWAY 78 AND HIGHWAY 174 IN HEMPSTEAD COUNTY. | Pavement Improvement | 03/01/2010 | 03/02/2010 |  | 225622 | 1.83
602 | Arkansas | CRITTENDEN |  | 01 | ARR2062 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 1.0 MILE OF HIGHWAY 118 BETWEEN HIGHWAY 70 AND INTERSTATE 40 IN THE CITY OF WEST MEMPHIS IN CRITTENDEN COUNTY. | Pavement Widening | 02/22/2010 | 04/19/2010 | 11/29/2010 | 2877096 | 0.84
603 | Arkansas | HEMPSTEAD, LAFAYETTE |  | 04 | ARR2063 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 3 NORTHBOUND AND 3 SOUTHBOUND PASSING LANES FOR A DISTANCE OF 7.2 MILES BETWEEN THE CITIES OF HOPE AND LEWISVILLE IN HEMPSTEAD AND LAYFAYETTE COUNTIES. | Pavement Widening | 04/21/2010 | 05/04/2010 | 10/31/2011 | 9452572 | 7.41
604 | Arkansas | INDEPENDENCE |  | 01 | ARR2065 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.54 MILES OF HIGHWAY 167 FROM NORTH OF THE CITY OF PLEASANT PLAINS SOUTH IN INDEPENDENCE COUNTY. | Pavement Improvement | 02/16/2010 | 04/05/2010 |  | 664680 | 1.54
605 | Arkansas | FAULKNER |  | 02 | ARR2066 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.64 MILES OF HIGHWAY 64 BETWEEN INTERSTATE 40 AND SQUIRREL HILL IN FAULKNER COUNTY. | Pavement Improvement | 02/03/2010 | 03/01/2010 |  | 916518 | 2.64
606 | Arkansas | YELL |  | 02 | ARR2067 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT 1.25 MILES OF COUNTY ROAD 88 BETWEEN KINGSTON AND HIGHWAY 28 IN YELL COUNTY. | Pavement Improvement | 04/07/2010 | 04/19/2010 | 09/26/2011 | 208241 | 2.5
607 | Arkansas | FAULKNER |  | 02 | ARR2068 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 60 AND COUNTRY CLUB ROAD IN THE CITY OF CONWAY IN FAULKNER COUNTY. WORK ITEMS INCLUDE TRAFFIC S | Safety/Traffic Management | 06/04/2010 |  |  | 129929 | 0
608 | Arkansas | OUACHITA |  | 04 | ARR2073 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 278 AND COUNTRY CLUB ROAD INTERSECTION IN THE CITY OF CAMDEN IN OUACHITA COUNTY. WORK ITEMS INCLUDE TRAFFIC SIG | Safety/Traffic Management | 07/06/2010 |  |  | 84304 | 0
609 | Arkansas | CRAIGHEAD | JONESBORO | 01 | ARR2075 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 91 AND GEE ST. IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 07/02/2010 |  |  | 82409 | 0
610 | Arkansas | WASHINGTON | FAYETTEVILLE-SPRINGDALE | 03 | ARR2076 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.74 MILES OF HIGHWAYS 71 AND 71B BETWEEN HIGHWAY 156 AND INTERSTATE 540 IN THE CITY OF FAYETTEVILLE, WASHINGTON COUNTY. WORK INCLUDES PAVEMENT REHABIL | Pavement Improvement | 06/25/2010 |  |  | 1042398 | 1.74
611 | Arkansas | BAXTER, MARION |  | 03,04 | ARR2077 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.26 MILES OF HIGHWAY 62 FROM THE TOWN OF GASSVILLE WEST IN BAXTER AND MARION COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GU | Pavement Improvement | 06/25/2010 |  |  | 843706 | 3.26
612 | California | COLUSA, SACRAMENTO, PLACER | SACRAMENTO | 2,4,5 | 000C303 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In Colusa, Placer and Sacramento Counties, at various locations. | Pavement Improvement | 07/02/2009 | 09/18/2009 | 11/01/2010 | 6246659 | 1
613 | California | YOLO, SACRAMENTO, PLACER | SACRAMENTO | 2,4,5 | 000C304 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In Sacramento, El Dorado, Yolo and Placer counties, at various locations. | Safety/Traffic Management | 05/18/2009 | 07/27/2009 | 06/01/2011 | 1810921 | 1
614 | California | TEHAMA, PLUMAS |  | 4 | 000C305 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Tehama and Plumas Counties, as Various Locations. | Pavement Improvement | 06/26/2009 | 07/06/2009 | 12/01/2010 | 2629087 | 1
615 | California | KINGS |  | 20 | 000C306 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Kern and King Counties near Avenal and Devils Den (Sunflower Valley) on State Ro | Pavement Improvement | 07/02/2009 | 07/09/2009 | 12/01/2009 | 3891487 | 1
616 | California | INYO, SAN BERNARDINO |  | 25 | 000C307 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: Shoshone from SR 127 to 0.2 miles E of Chicago Valley in San Bernardino near Baker | Pavement Improvement | 01/28/2010 |  | 07/01/2010 | 1787827 | 5
617 | California | LOS ANGELES | LOS ANGELES, CA | 27,28 | 0053014 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Sun Valley and Sylmar, from Hollywood Way to north of San Fer | Pavement Improvement | 10/12/2009 | 10/22/2009 | 12/01/2010 | 11254618 | 4.9
618 | California | KERN |  | 22 | 0054182 | This is a Safety project by the California Department of Transportation. The project is described as: Near Grapevine, at various locations. | Pavement Improvement | 07/15/2009 | 09/08/2009 | 02/01/2011 | 1651958 | 3.8
619 | California | TEHAMA |  | 2 | 0058336 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In and near Red Bluff, from 5.3 miles south of Adobe Road Overcr | Pavement Improvement | 07/08/2009 | 08/24/2009 | 12/01/2010 | 34239790 | 3.4
620 | California | RIVERSIDE | STATEWIDE | 45 | 0103101 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Construct Bob Hope Drive ext and new interchange | Pavement Widening | 12/10/2009 | 02/03/2010 | 12/01/2011 | 23553000 | 3
621 | California | RIVERSIDE |  | 44 | 0155152 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Riverside County in and near Corona, from Temescal Canyon Road to 0.4 mile south | Pavement Improvement | 06/15/2009 | 06/29/2009 | 12/01/2009 | 851045 | 5
622 | California | SOLANO | SAN FRANCISCO-OAKLAND, CA | 10 | 0802356 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Fairfield, from 0.4 mile west of Route 12 to 0.8 mile east of | Pavement Improvement | 04/28/2009 | 05/18/2009 | 12/01/2009 | 19570134 | 4.7
623 | California | LOS ANGELES | LOS ANGELES, CA | 26,29 | 2101795 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Los Angeles County in and near Pasadena, from State Route 2-A | Pavement Improvement | 09/16/2009 | 11/09/2009 | 05/01/2011 | 341883 | 5.4
624 | California | SANTA CLARA | SAN FRANCISCO-OAKLAND, CA | 15 | 2801119 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In San Jose, from Cypress Avenue Pedestrian Overcrossing to Tant | Pavement Improvement | 07/29/2009 | 09/09/2009 | 01/01/2011 | 11594095 | 2.7
625 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 2801122 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In San Mateo County from Santa Clara County line to San Francisco County | Safety/Traffic Management | 10/08/2009 |  | 10/01/2010 | 1814073 | 27.4
626 | California | SANTA CLARA | SAN JOSE, CA | 15,16 | 2801126 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Ramp Meters at 9 Locations | Safety/Traffic Management | 04/07/2010 |  | 04/01/2011 | 3086456 | 3
627 | California | SANTA CLARA | SAN JOSE, CA | 15,16 | 2801127 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Ramp Meters at 8 Locations | Safety/Traffic Management | 04/28/2010 |  | 04/01/2011 | 3349320 | 3.5
628 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 2801129 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Ramp Meters at 7 Locations | Safety/Traffic Management | 03/08/2010 |  | 04/01/2011 | 4266612 | 7
629 | California | LOS ANGELES | LOS ANGELES, CA | 27,28,30,36 | 4053015 | This is a Design-Build Contract project by the California Department of Transportation. The project is described as: Widen NB I-405 for HOV Lane | Safety/Traffic Management | 06/02/2009 | 06/02/2009 | 04/01/2013 | 189900000 | 10.2
630 | California | SACRAMENTO | SACRAMENTO | 5 | 5002138 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sacramento. The project is described as: Rehabilitate various roadways in Sacramento | Pavement Improvement | 08/26/2009 | 08/27/2009 | 12/01/2009 | 5246052 | 1
631 | California | SACRAMENTO | SACRAMENTO | 5 | 5002140 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sacramento. The project is described as: VARIOUS LOCATIONS W/IN THE CITY OF SACRAMENTO , AC OVERLAYS PHASE I | Pavement Improvement | 08/26/2009 | 09/08/2009 | 12/01/2009 | 2810571 | 1
632 | California | SOLANO | STATEWIDE | 7 | 5003023 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Benicia. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 12/17/2009 | 12/17/2009 | 05/01/2010 | 491800 | 0.2
633 | California | SOLANO | VALLEJO | 7 | 5003024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Benicia. The project is described as: Rehabilitate local street | Pavement Improvement | 10/26/2009 | 09/21/2009 | 11/01/2009 | 291156 | 0.59
634 | California | SANTA CLARA | SAN JOSE, CA | 11,14,15,16 | 5005096 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Jose. The project is described as: Rehabilitate local street | Pavement Improvement | 10/06/2009 | 10/19/2009 | 06/01/2010 | 9302466 | 8.65
635 | California | SANTA CLARA | STATEWIDE | 11,14,15,16 | 5005099 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Jose. The project is described as: Rehabilitate Local Streets. | Pavement Improvement | 05/17/2010 |  | 12/01/2010 | 6116534 | 4.38
636 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5006569 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Angeles. The project is described as: LAX HOSPITALITY ZONE STREET AND SIDEWALK REHABILITATION - PHASE II | Pavement Improvement | 07/06/2009 |  | 12/01/2010 | 7000000 | 3.85
637 | California | LOS ANGELES | LOS ANGELES, CA | 25,27 | 5006571 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: COMMERCE AVE PEDESTRIAN IMPROVEMENTS: THIS IS A PILOT PROJECT TO I | Pavement Improvement | 07/06/2009 |  | 02/01/2010 | 900000 | 0.5
638 | California | LOS ANGELES | LOS ANGELES, CA | 29,31,32,33,34 | 5006577 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES NORTH CENTRAL REGION RESURFACING PROJECT- PHASE II: THIS PROJECT | Pavement Improvement | 07/01/2009 |  | 09/01/2010 | 7275000 | 14
639 | California | LOS ANGELES | LOS ANGELES, CA | 27,30 | 5006578 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES WEST VALLEY REGION RESURFACING PROJECT - PHASE II: THIS PROJECT W | Pavement Improvement | 07/01/2009 |  | 09/01/2010 | 7275000 | 18
640 | California | LOS ANGELES | LOS ANGELES, CA | 25,27,28 | 5006579 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES EAST VALLEY REGION RESURFACING PROJECTS - PHASE II: THIS PROJECT | Pavement Improvement | 07/01/2009 |  | 09/01/2010 | 7275000 | 16
641 | California | LOS ANGELES | LOS ANGELES, CA | 35,36,37,39,46 | 5006580 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES BAY HARBOR REGION RESURFACING PROJECTS - PHASE II: THIS PROJECT W | Pavement Improvement | 07/01/2009 |  | 09/01/2010 | 7275000 | 16.5
642 | California | LOS ANGELES | LOS ANGELES, CA | 25,27,28,29,30,31,32,33,34,35,36,37,39,46 | 5006582 | This is a Transit project by a local agency in the City of Los Angeles. The project is described as: TRANSIT PRIORITY SYSTEM (TPS) AND ATSAC COMMUNICATION SYSTEM REHABILITATION | Safety/Traffic Management | 06/01/2010 |  | 09/01/2012 | 5598697 | 0
643 | California | LOS ANGELES | LOS ANGELES, CA | 25,27,28,29,30,31,32,33,34,35,36,37,39,46 | 5006592 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: THE PROJECT IS TO UPGRADE ROADWAYS GRATES NEAR OR ALONG BIKE PATHS | Safety/Traffic Management | 03/01/2010 |  | 09/01/2012 | 1555275 | 1
644 | California | LOS ANGELES | LOS ANGELES, CA | 35,36,37,39,46 | 5006595 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES BAY HARBOR REGION RESURFACING PROJECTS - PHASE I: THIS PROJECT WI | Pavement Improvement | 07/01/2009 |  | 09/01/2011 | 15588000 | 10.25
645 | California | LOS ANGELES | LOS ANGELES, CA | 36,46 | 5006602 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Los Angeles. The project is described as: HARRY S BRIDGES BLVD RELOCATION/CONSOLIDATION OF STREETS, STREET I | Pavement Improvement | 03/22/2010 |  | 10/01/2011 | 15545200 | 1.11
646 | California | SANTA BARBARA | SANTA BARBARA | 23 | 5007046 | This is a Pavement Resurfacing project by a local agency in the City of Santa Barbara. The project is described as: Overlay and pavement maintenance to streets on Federal list of eligible roads. | Pavement Improvement | 05/24/2010 |  | 07/01/2010 | 2674796 | 1
647 | California | SAN JOAQUIN | STOCKTON | 18 | 5008087 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Stockton. The project is described as: Rehabilitation of 24 streets in the City of Stockton | Pavement Improvement | 10/01/2009 | 10/18/2009 | 09/01/2010 | 6141391 | 14
648 | California | SAN JOAQUIN | STOCKTON | 18 | 5008092 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Stockton. The project is described as: Enhancement of existing roadway. | Transportation Enhancements | 06/01/2010 |  | 01/01/2011 | 894955 | 0.4
649 | California | YUBA | SACRAMENTO | 2 | 5009027 | This is a Traffic Management Engineering project by a local agency in the City of Marysville. The project is described as: Install a new traffic signal, complete pedestrian and landscaping improvemen | Pavement Improvement | 05/18/2010 |  | 12/01/2009 | 43000 | 1
650 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,13 | 5012098 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Oakland. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 02/15/2010 |  | 06/01/2011 | 1118832 | 1
651 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,13 | 5012099 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakland. The project is described as: Rehabilitate local street | Pavement Improvement | 03/01/2010 |  | 06/01/2011 | 3857444 | 5.58
652 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9 | 5012100 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Oakland. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 04/26/2010 |  | 12/01/2010 | 1300000 | 0.5
653 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5014032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alameda. The project is described as: Rehabilitate local street | Pavement Improvement | 08/07/2009 | 08/07/2009 | 12/01/2009 | 1304000 | 1.04
654 | California | EL DORADO | SACRAMENTO | 4 | 5015013 | This is a Pavement Resurfacing project by a local agency in the City of Placerville. The project is described as: Cold Springs Road, from Placerville City Limit to Sleepy Hollow Road: Rehabilitate ro | Pavement Improvement | 11/16/2009 | 11/16/2009 | 11/01/2009 | 415584 | 0.8
655 | California | HUMBOLDT |  | 1 | 5017023 | This is a Pavement Resurfacing project by a local agency in the City of Eureka. The project is described as: Street grind, patch and overlay | Pavement Improvement | 10/29/2009 |  | 10/01/2010 | 665129 | 3.53
656 | California | SANTA CLARA | STATEWIDE | 14,15 | 5019022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clara. The project is described as: Rehabilitate local street | Pavement Improvement | 11/02/2009 | 11/02/2009 | 12/01/2009 | 1110415 | 4.8
657 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5019023 | This is a Traffic Management Engineering project by a local agency in the City of Santa Clara. The project is described as: Install technology improvements | Safety/Traffic Management | 09/28/2009 | 09/28/2009 | 12/01/2009 | 404585 | 1.29
658 | California | SONOMA | SANTA ROSA | 6 | 5022044 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Petaluma. The project is described as: Rehabilitate local street | Pavement Improvement | 09/10/2009 | 09/29/2009 | 12/01/2009 | 561048 | 1.01
659 | California | SONOMA | SANTA ROSA | 6 | 5022045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Petaluma. The project is described as: Rehabilitate Local Streets - Lynch Creek Rd to Dynamic St. | Pavement Improvement | 03/08/2010 |  | 08/01/2010 | 728000 | 0.65
660 | California | CONTRA COSTA | CONCORD | 7,10 | 5024023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Martinez. The project is described as: Rehabilitate local street | Pavement Improvement | 09/14/2009 | 09/14/2009 | 12/01/2009 | 850000 | 4.2
661 | California | CONTRA COSTA | CONCORD | 7 | 5024024 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Martinez. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 03/15/2010 |  | 12/01/2010 | 756299 | 0.6
662 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5025045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: Road repairs: Morrissey Blvd from Soquel Ave to Fairmount | Pavement Improvement | 08/18/2009 | 08/31/2009 | 10/01/2009 | 388682 | 0.2
663 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5025046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: Road repairs: Market St from Water to SR1 | Pavement Improvement | 08/18/2009 | 09/04/2009 | 10/01/2009 | 272211 | 0.5
664 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5025047 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: Road repairs: West Cliff Dr from Almar Blvd to Bay St | Pavement Improvement | 08/18/2009 | 09/28/2009 | 10/01/2009 | 689107 | 1.6
665 | California | VENTURA | OXNARD-VENTURA | 23 | 5026043 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Buena Ventura. The project is described as: Steet Rehab. Olive Street Phase I | Pavement Improvement | 01/05/2010 | 01/06/2010 | 06/01/2010 | 530943 | 1
666 | California | SONOMA | SANTA ROSA | 1,6 | 5027014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Healdsburg. The project is described as: Rehabilitate local street | Pavement Improvement | 09/08/2009 | 09/23/2009 | 10/01/2009 | 500000 | 2.47
667 | California | SONOMA | SANTA ROSA | 1,6 | 5028053 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Rosa. The project is described as: Rehabilitate local street | Pavement Improvement | 09/30/2009 |  | 08/01/2010 | 2855080 | 2.1
668 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5029020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Redwood City. The project is described as: Rehabilitate local street | Pavement Improvement | 09/08/2009 | 09/10/2009 | 10/01/2009 | 736000 | 1.5
669 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5029021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Redwood City. The project is described as: Rehabilitate local street | Pavement Improvement | 11/02/2009 | 11/02/2009 | 03/01/2010 | 523000 | 0.25
670 | California | SOLANO | VALLEJO | 1,7 | 5030048 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Vallejo. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 12/14/2009 | 12/14/2009 | 09/01/2010 | 2207700 | 0.85
671 | California | SOLANO | VALLEJO | 1,7 | 5030049 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Vallejo. The project is described as: Rehabilitate local street | Pavement Improvement | 10/05/2009 | 10/05/2009 | 12/01/2009 | 1020000 | 1.33
672 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5031018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Watsonville. The project is described as: Road repairs: various roadways | Pavement Improvement | 08/13/2009 | 08/17/2009 | 11/01/2009 | 1200000 | 10
673 | California | SOLANO | FAIRFIELD | 10 | 5032022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Suisun City. The project is described as: Rehabilitate local street | Pavement Improvement | 10/07/2009 | 10/13/2009 | 12/01/2009 | 700000 | 0.7
674 | California | SANTA CLARA | SAN JOSE, CA | 11,15,16 | 5034020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Gilroy. The project is described as: Rehabilitate local street | Transportation Enhancements | 01/25/2010 |  | 02/01/2010 | 663000 | 9.4
675 | California | BUTTE | CHICO | 2 | 5037016 | This is a Traffic Management Engineering project by a local agency in the City of Chico. The project is described as: Reconstruct Interchange, improve operations | Pavement Widening | 02/01/2010 |  | 10/01/2010 | 5500000 | 0.6
676 | California | CONTRA COSTA | ANTIOCH-PITTSBURGH | 7,10 | 5038021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Antioch. The project is described as: Rehabilitate local street | Pavement Improvement | 09/14/2009 | 10/01/2009 | 02/01/2010 | 1605000 | 3.2
677 | California | SONOMA |  | 1 | 5039021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cloverdale. The project is described as: Rehabilitate local street | Pavement Improvement | 08/25/2009 | 08/31/2009 | 10/01/2009 | 399868 | 1.6
678 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,13 | 5041033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Leandro. The project is described as: Rehabilitate local street | Pavement Improvement | 09/17/2009 | 09/28/2009 | 12/01/2009 | 1029885 | 0.65
679 | California | NAPA | SAN FRANCISCO-OAKLAND, CA | 1 | 5042049 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Napa. The project is described as: Rehabilitate local street | Pavement Improvement | 09/04/2009 |  | 11/01/2009 | 1600000 | 1.4
680 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5043030 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Rafael. The project is described as: Rehabilitate local street | Pavement Improvement | 09/23/2009 | 10/07/2009 | 11/01/2009 | 1188000 | 3.33
681 | California | TULARE | VISALIA | 21 | 5044051 | This is a Traffic Management Engineering project by a local agency in the City of Visalia. The project is described as: Widening of Ben Maddox Bridge over SR-198 from 5-8 lanes (2 thru lanes each dir | Bridge Improvement | 03/22/2010 |  | 06/01/2011 | 5400000 | 0.79
682 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5045023 | This is a Pavement Resurfacing project by a local agency in the City of Salinas. The project is described as: Reconstruct between Natividad and North Sanborn Roads | Pavement Improvement | 08/31/2009 | 08/31/2009 | 01/01/2010 | 2795487 | 1
683 | California | YOLO |  | 2 | 5046029 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Woodland. The project is described as: CR 102, from East Beamer St to Hanson Wy: Rehabilitate roadway. | Pavement Improvement | 09/21/2009 | 09/21/2009 | 12/01/2009 | 655725 | 1
684 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,13 | 5050036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hayward. The project is described as: Rehabilitate local street | Pavement Improvement | 07/24/2009 | 07/27/2009 | 11/01/2009 | 2037000 | 3.88
685 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5050037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hayward. The project is described as: Rehabilitate local street | Pavement Improvement | 11/20/2009 | 11/30/2009 | 05/01/2010 | 475000 | 2.15
686 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 10,11 | 5053018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Livermore. The project is described as: Rehabilitate local street | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/01/2009 | 1322262 | 1.13
687 | California | ORANGE | LOS ANGELES, CA | 40,47 | 5055155 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Street pavement rehabilitation / reconstruction, including curb ramps, utility adjustment | Pavement Improvement | 04/05/2010 |  | 03/01/2010 | 998183 | 0.67
688 | California | ORANGE | LOS ANGELES, CA | 40,42 | 5055157 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Street pavement rehabilitation / reconstruction, including curb ramps, utility adjustment | Pavement Improvement | 04/26/2010 |  | 03/01/2010 | 539193 | 0.8
689 | California | SOLANO |  | 3,10 | 5056016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Dixon. The project is described as: Rehabilitate local street | Pavement Improvement | 10/19/2009 |  | 11/01/2009 | 300000 | 0.52
690 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 7,9,10 | 5057032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Berkeley. The project is described as: Rehabilitate local street | Pavement Improvement | 09/18/2009 | 09/24/2009 | 06/01/2010 | 1522315 | 0.56
691 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9 | 5057033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Berkeley. The project is described as: Rehabilitate local street | Pavement Improvement | 02/05/2010 |  | 06/01/2010 | 400000 | 0.26
692 | California | RIVERSIDE | SAN BERNARDINO-RIVERSIDE | 44 | 5058079 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Riverside. The project is described as: Install median landscaping | Transportation Enhancements | 12/21/2009 | 12/21/2009 | 02/01/2010 | 348176 | 1
693 | California | STANISLAUS | MODESTO | 18,19 | 5059160 | This is a Pavement Resurfacing project by a local agency in the City of Modesto. The project is described as: Cape and Slurry Various Streets. | Pavement Improvement | 05/24/2010 |  | 11/01/2010 | 2809187 | 30
694 | California | FRESNO | FRESNO | 19,21 | 5060165 | This is a Safety project by a local agency in the City of Fresno. The project is described as: Various traffic signal installation at various location. Consistent with 40 CFR part 93.126, 127, 128, e | Pavement Improvement | 05/07/2010 |  | 06/01/2010 | 291710 | 1
695 | California | FRESNO | FRESNO | 19 | 5060167 | This is a Traffic Management Engineering project by a local agency in the City of Fresno. The project is described as: Traffic signal installation at various location. Consistent with 40 CFR part 93. | Pavement Improvement | 04/02/2010 |  | 04/01/2010 | 300000 | 1
696 | California | FRESNO | FRESNO | 21 | 5060168 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent with 40 CFR part 93.126 | Pavement Improvement | 04/07/2010 |  | 08/01/2010 | 735716 | 2
697 | California | FRESNO | FRESNO | 19 | 5060171 | This is a Safety project by a local agency in the City of Fresno. The project is described as: Various traffic signal installation at various location. Consistent with 40 CFR part 93.126, 127, 128, e | Pavement Improvement | 05/07/2010 |  | 06/01/2010 | 231900 | 1
698 | California | FRESNO | FRESNO | 20 | 5060172 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent with 40 CFR part 93.126, | Pavement Improvement | 04/26/2010 |  | 08/01/2010 | 1551268 | 3
699 | California | ORANGE | LOS ANGELES, CA | 47 | 5063131 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Ana. The project is described as: Roadway Rehabilitation Non-capacity Adding | Pavement Improvement | 01/04/2010 | 01/04/2010 | 06/01/2011 | 634368 | 0.4
700 | California | ORANGE | LOS ANGELES, CA | 47 | 5063132 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Ana. The project is described as: Roadway Rehabilitation Non-capacity Adding | Pavement Improvement | 01/04/2010 | 01/04/2010 | 06/01/2011 | 599048 | 0.5
701 | California | ORANGE | LOS ANGELES, CA | 47 | 5063133 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Ana. The project is described as: Roadway Rehabilitation Non-capacity Adding | Pavement Improvement | 01/04/2010 | 01/04/2010 | 06/01/2011 | 632035 | 0.4
702 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5064061 | This is a Pavement Resurfacing project by a local agency in the City of Pasadena. The project is described as: RESURFACING VARIOUS STREETS WITHIN THE CITY OF PASADENA ON THE SELECT STREET SYSTEM WITH | Pavement Improvement | 04/12/2010 |  | 05/01/2010 | 4331000 | 9.8
703 | California | SANTA CLARA | SAN JOSE, CA | 14,15,16 | 5067014 | This is a Traffic Management Engineering project by a local agency in the City of Los Gatos. The project is described as: Intersection improvements and signal upgrade | Safety/Traffic Management | 07/20/2009 | 01/04/2010 | 10/01/2009 | 453295 | 0.25
704 | California | SANTA CLARA | SAN JOSE, CA | 14,15,16 | 5067015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Gatos. The project is described as: Overlay street Prospect Road (College Ave to Town limit). This inclu | Pavement Improvement | 04/06/2010 |  | 06/01/2010 | 177705 | 0.5
705 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5070018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pomona. The project is described as: STREET IMPROVEMENTS - TOWNE AVENUE (LEXINGTON AVE TO RIVERSIDE DR.) PH | Pavement Improvement | 02/08/2010 |  | 09/01/2009 | 1017000 | 1.25
706 | California | LOS ANGELES | LOS ANGELES, CA | 37 | 5078030 | This is a Pavement Resurfacing project by a local agency in the City of Compton. The project is described as: DEVELOPMENT OF STREET PREVENTIVE PROGRAM. PREVENTIVE MAINTENANCE OF VARIOUS STREETS WITH | Pavement Improvement | 03/30/2010 |  | 09/01/2010 | 583592 | 14
707 | California | LOS ANGELES | LOS ANGELES, CA | 37 | 5078031 | This is a Pavement Resurfacing project by a local agency in the City of Compton. The project is described as: VARIOUS LOCATIONS LOCAL RODS IN THE CITY OF COMPTON.GRINDING AND OVERLAY OF LOCAL ROADS. | Pavement Improvement | 03/30/2010 |  | 06/01/2011 | 2004000 | 4.3
708 | California | SANTA BARBARA | LOMPOC | 24 | 5080021 | This is a Pavement Resurfacing project by a local agency in the City of Lompoc. The project is described as: Street pavement rehabilitation and overlays on V Street, College Avenue, 7th Street, O Str | Pavement Improvement | 09/21/2009 | 09/30/2009 | 10/01/2009 | 682161 | 2.7
709 | California | MERCED | MERCED | 18 | 5085019 | This is a Pavement Resurfacing project by a local agency in the City of Merced. The project is described as: HMA Overlay on 16th St. from G to V St. | Pavement Improvement | 03/03/2010 |  | 05/01/2010 | 1555750 | 2.5
710 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5086029 | This is a Pavement Resurfacing project by a local agency in the City of Monterey. The project is described as: Reconstruct between Fremont and Elorado | Pavement Improvement | 08/31/2009 | 09/14/2009 | 12/01/2009 | 602716 | 1
711 | California | MONTEREY |  | 17 | 5086030 | This is a Safety project by a local agency in the City of Monterey. The project is described as: Del Monte/Figueroa; Traffic signal modifications and curb return/ADA/new bike lane improvements, safe | Safety/Traffic Management | 01/04/2010 | 01/11/2010 | 05/01/2010 | 375000 | 1
712 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5087027 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Pacific Grove. The project is described as: Sidewalk and storm drain improvements | Transportation Enhancements | 11/10/2009 | 11/18/2009 | 03/01/2010 | 303000 | 1
713 | California | MENDOCINO |  | 1 | 5088020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fort Bragg. The project is described as: Grinding, Excavating to 13 feet, replace base rock, asphalt concret | Pavement Improvement | 02/16/2010 |  | 10/01/2009 | 361000 | 0.25
714 | California | MENDOCINO |  | 1 | 5088021 | This is a Pavement Resurfacing project by a local agency in the City of Fort Bragg. The project is described as: Structural digouts, grinding, 2 inch asphalt overlay, and curb ramps installed | Pavement Improvement | 02/22/2010 |  | 10/01/2009 | 567000 | 0.6
715 | California | KINGS | HANFORD | 20 | 5091037 | This is a Pavement Resurfacing project by a local agency in the City of Hanford. The project is described as: City of Hanford, Hanford-Armona Road, From 11th Avenue to Greenbriar Dr; Rehabilitate Roa | Pavement Improvement | 10/12/2009 | 10/12/2009 | 11/01/2009 | 630433 | 1
716 | California | KINGS | HANFORD | 20 | 5091040 | This is a Pavement Resurfacing project by a local agency in the City of Hanford. The project is described as: City of Hanford, 11th Ave. From 3rd St. to Ivy St., Rehabilitate Roadway | Pavement Improvement | 05/31/2010 |  | 08/01/2010 | 497664 | 1
717 | California | LOS ANGELES | LOS ANGELES, CA | 36 | 5093013 | This is a Pavement Resurfacing project by a local agency in the City of Redondo Beach. The project is described as: PRIORITY 1 INGLEWOOD AVE STREET RESURFACING FROM ARTESIA BLVD TO MANHATTAN BEACH BL | Pavement Improvement | 10/12/2009 | 10/19/2009 | 01/01/2010 | 1058000 | 1
718 | California | SOLANO | VACAVILLE | 3,7,10 | 5094049 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Vacaville. The project is described as: Pedestrian Enhancements | Safety/Traffic Management | 06/12/2009 | 06/15/2009 | 11/01/2009 | 260000 | 0.27
719 | California | SOLANO | VACAVILLE | 3,7,10 | 5094052 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Vacaville. The project is described as: Rehabilitate local street | Pavement Improvement | 09/23/2009 | 10/01/2009 | 12/01/2009 | 1376000 | 4.7
720 | California | SOLANO | VACAVILLE | 3,7,10 | 5094053 | This is a Traffic Management Engineering project by a local agency in the City of Vacaville. The project is described as: Install technology improvements | Safety/Traffic Management | 10/30/2009 |  | 01/01/2010 | 320000 | 0
721 | California | PLACER | SACRAMENTO | 4 | 5095013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rocklin. The project is described as: Rehabilitate Sunset Boulevard from Blue Oaks Blvd to Atherton Road. | Pavement Improvement | 09/14/2009 | 09/14/2009 | 11/01/2009 | 1289206 | 1
722 | California | SANTA CLARA | SAN JOSE, CA | 14 | 5100011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palo Alto. The project is described as: Rehabilitate local street | Pavement Improvement | 11/10/2009 | 11/16/2009 | 12/01/2009 | 580000 | 0.6
723 | California | SANTA CLARA | SAN JOSE, CA | 14 | 5100012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palo Alto. The project is described as: Rehabilitate local street | Pavement Improvement | 12/04/2009 | 12/07/2009 | 12/01/2009 | 505000 | 1.7
724 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,10,11,13 | 5101022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasanton. The project is described as: Rehabilitate local street | Pavement Improvement | 09/15/2009 | 10/22/2009 | 06/01/2010 | 1216711 | 1.2
725 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5102034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Mateo. The project is described as: Rehabilitate local street | Pavement Improvement | 08/17/2009 | 08/17/2009 | 11/01/2009 | 1095000 | 4
726 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5107021 | This is a Pavement Resurfacing project by a local agency in the City of Santa Monica. The project is described as: SANTA MONICA BLVD RESURFACING PROJECT PHASE II - MAINTENANCE AND REPAIR TO THE EXIST | Pavement Improvement | 01/05/2010 | 01/05/2010 | 02/01/2010 | 674638 | 0.7
727 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5107022 | This is a Pavement Resurfacing project by a local agency in the City of Santa Monica. The project is described as: STREET RESURFACING CITYWIDE- PAVING ON COLLECTOR AND ARTERIAL STREETS INCLUDING MAIN | Pavement Improvement | 01/04/2010 | 01/05/2010 | 04/01/2010 | 2002183 | 5.5
728 | California | LOS ANGELES | LOS ANGELES, CA | 37,46 | 5108094 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 01/04/2010 | 01/04/2010 | 06/01/2010 | 3028790 | 4.5
729 | California | LOS ANGELES | LOS ANGELES, CA | 37,46 | 5108095 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 01/19/2010 | 01/19/2010 | 06/01/2010 | 229342 | 4.5
730 | California | LOS ANGELES | LOS ANGELES, CA | 37,46 | 5108096 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 01/04/2010 | 01/04/2010 | 06/01/2010 | 487633 | 4.5
731 | California | LOS ANGELES | LOS ANGELES, CA | 37,46 | 5108097 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 12/07/2009 | 12/07/2009 | 06/01/2010 | 634018 | 4.5
732 | California | KERN | BAKERSFIELD | 22 | 5109153 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Hughes Lane: White Lane to Planz Rd; Wible Road: White Lane to | Other | 09/02/2009 | 09/17/2009 | 11/01/2009 | 2040374 | 1.56
733 | California | KERN | BAKERSFIELD | 22 | 5109154 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Mt. Vernon Ave: State Route 178 to University Ave; Resurfacing, | Other | 09/03/2009 | 09/08/2009 | 11/01/2009 | 1772000 | 0.7
734 | California | KERN | BAKERSFIELD | 22 | 5109155 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Ashe Rd: White Lane to Ming Ave; Resurfacing, Reconstruction | Other | 09/02/2009 | 09/17/2009 | 11/01/2009 | 1850000 | 1.12
735 | California | KERN | BAKERSFIELD | 22 | 5109157 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Coffee Road: Friant Kern Canal to Riverlakes Drive - Reconstruc | Pavement Improvement | 04/21/2010 |  | 07/01/2010 | 1710000 | 0.9
736 | California | KERN | BAKERSFIELD | 22 | 5109158 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Ming Avenue: Gosford Road to Ashe Road - Reconstruction Ming Av | Pavement Improvement | 04/22/2010 |  | 07/01/2010 | 4791000 | 1.86
737 | California | YOLO |  | 2 | 5110027 | This is a Safety project by a local agency in the City of Winters. The project is described as: Grant Ave.(SR128), east of Railroad Ave., between Dutton St and Morgan St.: widen to accommodate a cont | Pavement Improvement | 09/01/2009 | 09/08/2009 | 12/01/2009 | 357118 | 1
738 | California | LOS ANGELES | LOS ANGELES, CA | 42 | 5111049 | This is a Safety project by a local agency in the City of Whittier. The project is described as: Santa Gertrudes Avenue at Starbuck Street Traffic Signal Installation. | Safety/Traffic Management | 04/20/2010 |  | 06/01/2010 | 167670 | 1
739 | California | LOS ANGELES | LOS ANGELES, CA | 42 | 5111052 | This is a Safety project by a local agency in the City of Whittier. The project is described as: Painter Avenue Street Light Conversion Project. Conversion of old 6,000 volt series street lighting sy | Other | 03/10/2010 |  | 08/01/2010 | 231430 | 1
740 | California | LOS ANGELES | LOS ANGELES, CA | 42 | 5111056 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Whittier. The project is described as: Intersection of Mar Vista Street and California Avenue. Reconstru | Pavement Improvement | 04/19/2010 |  | 06/01/2010 | 70058 | 1
741 | California | LOS ANGELES | LOS ANGELES, CA | 32 | 5112010 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Azusa. The project is described as: RECONSTRUCTION OF FOOTHILL BLVD. FROM TODD AVE. TO ORANGE AVE. (3,716 | Pavement Improvement | 09/23/2009 | 09/28/2009 | 07/01/2009 | 879841 | 0.7
742 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5113010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Mill Valley. The project is described as: Rehabilitate local street | Pavement Improvement | 10/22/2009 | 10/26/2009 | 08/01/2009 | 286439 | 0.36
743 | California | SONOMA | SANTA ROSA | 1,6 | 5114014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sonoma. The project is described as: Rehabilitate local street | Pavement Improvement | 09/28/2009 | 09/28/2009 | 11/01/2009 | 500000 | 0.53
744 | California | KINGS |  | 20 | 5115019 | This is a Pavement Resurfacing project by a local agency in the City of Lemoore. The project is described as: City of Lemoore, Hanford-Armona Road, From 19th Ave. to SR 41; Overlay Roadway | Pavement Improvement | 10/19/2009 | 10/21/2009 | 12/01/2009 | 435000 | 1
745 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7 | 5117008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hercules. The project is described as: Rehabilitate local street | Pavement Improvement | 10/29/2009 | 10/29/2009 | 12/01/2009 | 577000 | 0.83
746 | California | LOS ANGELES | LOS ANGELES, CA | 32 | 5118014 | This is a Pavement Resurfacing project by a local agency in the City of Covina. The project is described as: STREET OVERLAYS - CITYWIDE | Pavement Improvement | 12/02/2009 | 12/02/2009 | 12/01/2009 | 839828.94 | 2.65
747 | California | VENTURA | OXNARD-VENTURA | 24 | 5121017 | This is a Pavement Resurfacing project by a local agency in the City of Santa Paula. The project is described as: 8th Street from Harvard to Santa Paula Street | Pavement Improvement | 10/14/2009 | 10/14/2009 | 11/01/2009 | 254000 | 1
748 | California | SONOMA | SANTA ROSA | 6 | 5123014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sebastopol. The project is described as: Rehabilitate local street | Pavement Improvement | 11/10/2009 | 11/23/2009 | 12/01/2009 | 595023 | 0.83
749 | California | SANTA CLARA | SAN JOSE, CA | 14 | 5124027 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Mountain View. The project is described as: Rehabilitate local street | Pavement Improvement | 10/05/2009 | 10/05/2009 | 10/01/2009 | 724815 | 0.86
750 | California | INYO |  | 25 | 5125022 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bishop. The project is described as: Replace asphalt paving, cross gutters & ramps. Install new water and | Pavement Improvement | 05/03/2010 | 09/01/2009 | 07/01/2010 | 379440 | 0.2
751 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5126010 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Pinole. The project is described as: Pedestrian Enhancements | Pavement Improvement | 10/22/2009 |  | 04/01/2010 | 214000 | 1
752 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5126012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pinole. The project is described as: Rehabilitate local street | Pavement Improvement | 09/23/2009 |  | 11/01/2009 | 420000 | 0.6
753 | California | CONTRA COSTA | ANTIOCH-PITTSBURGH | 7,10 | 5127023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pittsburg. The project is described as: Rehabilitate local street | Pavement Improvement | 09/25/2009 | 10/19/2009 | 10/01/2009 | 1103000 | 1.02
754 | California | VENTURA | OXNARD-VENTURA | 23,24 | 5129053 | This is a Pavement Resurfacing project by a local agency in the City of Oxnard. The project is described as: Bartolo Square North Street Resurfacing | Pavement Improvement | 05/13/2010 |  | 06/01/2010 | 813147 | 1
755 | California | VENTURA | OXNARD-VENTURA | 23,24 | 5129054 | This is a Traffic Management Engineering project by a local agency in the City of Oxnard. The project is described as: Traffic Signal Improvements, various locations | Safety/Traffic Management | 11/02/2009 | 11/02/2009 | 03/01/2010 | 723230 | 1
756 | California | VENTURA | OXNARD-VENTURA | 23,24 | 5129055 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oxnard. The project is described as: Bartolo Square South Street Resurf. | Pavement Improvement | 10/13/2009 | 10/16/2009 | 03/01/2010 | 923579 | 0.9
757 | California | VENTURA | STATEWIDE | 23 | 5129058 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Oxnard. The project is described as: Route 101 at Rice Ave/Santa Clara Ave Intersection Improvement | Pavement Widening | 11/18/2009 | 02/07/2010 | 06/01/2013 | 5000000 | 1
758 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5130015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alhambra. The project is described as: REHABILITATE POPLAR BOULEVARD FROM FREMONT AVENUE TO CITY BOUNDARY WE | Pavement Improvement | 05/13/2010 |  | 01/01/2010 | 224013 | 0.6
759 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5131015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arcadia. The project is described as: SANTA ANITA AVENUE BETWEEN FOOTHILL BLVD. AND GRANDVIEW AVENUE: STREET | Pavement Improvement | 12/14/2009 | 12/29/2009 | 02/01/2010 | 757000 | 1.1
760 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5131016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arcadia. The project is described as: SANTA ANITA AVENUE BETWEEN LONGDEN AVENUE AND LIVE OAK AVENUE: STREET | Pavement Improvement | 09/29/2009 | 10/01/2009 | 12/01/2009 | 574528.78 | 0.5
761 | California | SOLANO | FAIRFIELD | 7,10 | 5132033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: Rehabilitate local street | Pavement Improvement | 10/11/2009 | 11/12/2009 | 11/01/2009 | 692811 | 0.7
762 | California | SOLANO | FAIRFIELD | 7,10 | 5132034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: Rehabilitate local street | Pavement Improvement | 10/26/2009 | 11/09/2009 | 11/01/2009 | 475372 | 0.8
763 | California | ORANGE | LOS ANGELES, CA | 40 | 5133038 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Fullerton. The project is described as: Rehabilitate 0.35 Miles of roadway on Harbor Blvd | Pavement Improvement | 05/10/2010 |  | 08/01/2010 | 1178639 | 0.35
764 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5135036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Concord. The project is described as: Rehabilitate local street | Pavement Improvement | 10/03/2009 | 10/05/2009 | 12/01/2009 | 1167504 | 1.2
765 | California | CONTRA COSTA | CONCORD | 7,10 | 5135037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Concord. The project is described as: Rehabilitate local street | Pavement Improvement | 09/10/2009 | 09/14/2009 | 11/01/2009 | 584000 | 0.5
766 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5137037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Richmond. The project is described as: Rehabilitate local street and add bicycle lane | Pavement Improvement | 02/10/2010 |  | 11/01/2010 | 1578000 | 0.8
767 | California | SANTA BARBARA | SANTA MARIA | 23 | 5138033 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Maria. The project is described as: Overlay, Phase I (A) E Donovan Rd ? N Carlotti Dr to Suey Rd (B | Pavement Improvement | 04/26/2010 |  | 05/01/2010 | 1657050 | 4.1
768 | California | SANTA BARBARA | SANTA MARIA | 23 | 5138035 | This is a Pavement Resurfacing project by a local agency in the City of Santa Maria. The project is described as: Overlay, Phase II (A) N Railroad Ave ? W Taylor Ave to W Donovan (B) N Western Ave ? | Pavement Improvement | 02/22/2010 |  | 04/01/2010 | 1155603 | 2.6
769 | California | SANTA BARBARA | SANTA MARIA | 23 | 5138037 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Maria. The project is described as: Concrete Project II (A) N Thornburg St ? W Donovan Rd to W Fesler | Transportation Enhancements | 04/07/2010 |  | 05/01/2010 | 301554 | 1
770 | California | SANTA BARBARA | SANTA MARIA | 23 | 5138038 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Maria. The project is described as: Concrete Project III (A) W Taylor St ? N Blosser Rd to N Railroad | Transportation Enhancements | 03/03/2010 |  | 05/01/2010 | 232089 | 1.07
771 | California | BUTTE |  | 2 | 5142030 | This is a Pavement Resurfacing project by a local agency in the City of Oroville. The project is described as: Roadway Rehabilitation / Overlays | Pavement Improvement | 08/31/2009 | 08/28/2009 | 11/01/2009 | 1095000 | 2
772 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5144047 | This is a Safety project by a local agency in the City of Glendale. The project is described as: MONTEREY ROAD NEW TRAFFIC SIGNALS. CONSTRUCT 3 NEW TRAFFIC SIGNALS AT MONTEREY RD./GENEVA ST., MONTERE | Pavement Improvement | 12/07/2009 |  | 07/01/2010 | 616600 | 0.34
773 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5144048 | This is a Pavement Resurfacing project by a local agency in the City of Glendale. The project is described as: STREET REPAIR AND REHABILITATION PROJECT, PHASE VI: PACIFIC AVE. AND ALLEN STREET-THE PR | Pavement Improvement | 03/15/2010 |  | 07/01/2010 | 1235000 | 0.82
774 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5144049 | This is a Traffic Management Engineering project by a local agency in the City of Glendale. The project is described as: SOUTH GLENDALE TYPE 2070 TRAFFIC SIGNAL CONTROLLER CONVERSIONS. REPLACE EXIST | Pavement Improvement | 12/07/2009 |  | 03/01/2010 | 149630 | 1
775 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5144050 | This is a Safety project by a local agency in the City of Glendale. The project is described as: NEW TRAFFIC SIGNAL INSTALLATION AT VARIOUS LOCATIONS. CONSTRUCT 3 NEW TRAFFIC SIGNALS AT CENTRAL AVE./ | Pavement Improvement | 01/26/2010 |  | 07/01/2010 | 639800 | 1
776 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5144051 | This is a Pavement Resurfacing project by a local agency in the City of Glendale. The project is described as: STREET REPAIR AND REHABILITATION PROJECT PHASE I: CHEVY CHASE DR. AND CYPRESS ST.-THE PR | Pavement Improvement | 04/05/2010 |  | 06/01/2010 | 880000 | 1.1
777 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5144052 | This is a Traffic Management Engineering project by a local agency in the City of Glendale. The project is described as: NORTH GLENDALE TYPE 2070 TRAFFIC SIGNAL CONTROLLER CONVERSIONS. REPLACE EXIST | Pavement Improvement | 12/07/2009 |  | 03/01/2010 | 318318 | 1
778 | California | LOS ANGELES | LOS ANGELES, CA | 28 | 5149005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Verne. The project is described as: COMPLETE REHABILITATION OF 1.3 MILE LENGTH OF GOLDEN HILLS ROAD FROM | Pavement Improvement | 09/14/2009 | 09/14/2009 | 10/01/2009 | 598976 | 1.3
779 | California | LOS ANGELES | LOS ANGELES, CA | 28 | 5149006 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of La Verne. The project is described as: Town Center Drive from Foothill Boulevard to White Avenue. Includ | Pavement Improvement | 09/21/2009 | 10/05/2009 | 10/01/2009 | 149433 | 0.25
780 | California | LOS ANGELES | LOS ANGELES, CA | 34 | 5150008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Huntington Park. The project is described as: STREET IMPROVEMENTS AT BISSELL FROM FLORENCE AVE. TO RANDOLPH | Pavement Improvement | 02/08/2010 |  | 12/01/2009 | 1898000 | 2.78
781 | California | ORANGE | MISSION VIEJO | 48 | 5151024 | This is a Pavement Resurfacing project by a local agency in the City of Newport Beach. The project is described as: Pavement rehab. from 44th St. to 22nd St. | Pavement Improvement | 11/09/2009 | 11/09/2009 | 01/01/2010 | 1083924 | 0.95
782 | California | SANTA CLARA | SAN JOSE, CA | 11,15,16 | 5152019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Morgan Hill. The project is described as: Rehabilitate local street | Pavement Improvement | 09/09/2009 | 09/09/2009 | 11/01/2009 | 436941 | 0.6
783 | California | STANISLAUS |  | 19 | 5153030 | This is a Pavement Resurfacing project by a local agency in the City of Oakdale. The project is described as: Curb, gutter, sidewalk, pavement and intersection improvements | Pavement Improvement | 05/05/2010 |  | 10/10/2009 | 360841 | 1
784 | California | SAN JOAQUIN | LODI | 11 | 5154036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lodi. The project is described as: Enhancement of existing roadway | Pavement Improvement | 11/11/2009 |  | 12/01/2010 | 2244461 | 0.62
785 | California | LOS ANGELES | LOS ANGELES, CA | 36 | 5155006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hermosa Beach. The project is described as: 8TH STREET: STREET IMPROVEMENTS BETWEEN PCH & VALLEY DRIVE. INCL | Pavement Improvement | 03/29/2010 |  | 04/01/2010 | 294433 | 0.12
786 | California | LOS ANGELES | LOS ANGELES, CA | 36 | 5155007 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Hermosa Beach. The project is described as: PIER AVENUE IMPROVEMENT PROJECT. MULTI-FACETED PROJECT WHICH | Pavement Improvement | 03/29/2010 |  | 12/01/2009 | 279077 | 0.11
787 | California | MADERA | MADERA | 19 | 5157070 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Madera. The project is described as: Street Rehabilitation/Resurfacing: I St. - North of 2nd to South of Cen | Pavement Improvement | 05/03/2010 |  | 05/01/2010 | 214000 | 0.4
788 | California | MADERA | MADERA | 19 | 5157073 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Madera. The project is described as: Lake Street - Cleveland to Kennedy, reconstruct and widen to 4 lanes wi | Pavement Widening | 10/19/2009 | 10/19/2009 | 12/01/2009 | 1017000 | 0.5
789 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5159014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Anselmo. The project is described as: Rehabilitate local street | Pavement Improvement | 10/20/2009 | 10/20/2009 | 11/01/2009 | 242000 | 0.3
790 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5162017 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Claremont. The project is described as: ARROW HIGHWAY, FROM CITY LIMIT TO CITY.REHABILITATION, RECONSTRUCTIO | Pavement Improvement | 04/05/2010 |  | 03/01/2010 | 895000 | 1.6
791 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5162018 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Claremont. The project is described as: &#9658; LOCATION: THROUGHOUT CITY. &#9658; NATURE OF PROJECT (PRO | Transportation Enhancements | 02/18/2010 |  | 03/01/2010 | 1037000 | 1.51
792 | California | SUTTER | YUBA CITY | 2 | 5163019 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Yuba City. The project is described as: In Yuba City, from Plumas to Shasta, construct signal-phasing modifi | Pavement Improvement | 08/10/2009 | 08/10/2009 | 12/01/2009 | 1900000 | 1
793 | California | SUTTER |  | 2 | 5163023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Yuba City. The project is described as: Yuba City, Live Oak Blvd. and Garden Highway: Rehabilitate roadways, | Pavement Improvement | 04/19/2010 |  | 06/01/2010 | 753627 | 1
794 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5164016 | This is a Pavement Resurfacing project by a local agency in the City of Inglewood. The project is described as: MANCHESTER BOULEVARD CORRIDOR ROADWAY IMPROVEMENT PROJECT. TO PRESERVE AND REHABILITAT | Pavement Improvement | 11/02/2009 | 11/02/2009 | 12/01/2010 | 3200000 | 2.45
795 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5166022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Larkspur. The project is described as: Rehabilitate local street | Pavement Improvement | 10/08/2009 | 10/08/2009 | 11/01/2009 | 236000 | 0.49
796 | California | IMPERIAL |  | 51 | 5167024 | This is a Pavement Resurfacing project by a local agency in the City of Brawley. The project is described as: Asphalt Rehabilitation and Reconstruction of Western Avenue from State Highway 86 to Nort | Pavement Improvement | 03/24/2010 |  | 04/01/2010 | 895000 | 0.8
797 | California | IMPERIAL |  | 51 | 5167025 | This is a Pavement Resurfacing project by a local agency in the City of Brawley. The project is described as: In Brawley Cattle Call Park. From Willard Avenue, Around Park, ending at Willard Avenue. | Transportation Enhancements | 04/05/2010 |  | 06/01/2010 | 152496 | 1
798 | California | IMPERIAL |  | 51 | 5168013 | This is a Pavement Resurfacing project by a local agency in the City of Calexico. The project is described as: Street Rehabilitation of Emmerson Avenue from Highway 98 to Third Street | Pavement Improvement | 03/25/2010 |  | 05/01/2010 | 895000 | 0.78
799 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5171016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Burlingame. The project is described as: Rehabilitate local street | Pavement Improvement | 08/13/2009 | 08/17/2009 | 09/01/2009 | 551000 | 1.2
800 | California | IMPERIAL |  | 51 | 5174007 | This is a Pavement Resurfacing project by a local agency in the City of Holtville. The project is described as: Street Improvements of Rehabilitation and Reconstruction along West side of Holt Avenue | Pavement Improvement | 01/04/2010 | 02/08/2010 | 12/01/2010 | 346000 | 0.11
801 | California | IMPERIAL |  | 51 | 5174008 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Holtville. The project is described as: Replacement of the City of Holtville entrance monument sign locat | Transportation Enhancements | 03/24/2010 |  | 12/01/2009 | 50000 | 0.06
802 | California | IMPERIAL |  | 51 | 5174009 | This is a Pavement Resurfacing project by a local agency in the City of Holtville. The project is described as: Walnut Avenue Rehabilitation between 5th Street (SR 111) and Fourth Street | Pavement Improvement | 12/10/2009 | 12/14/2009 | 12/01/2010 | 317868 | 0.11
803 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5177022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South San Francisco. The project is described as: Rehabilitate local street | Pavement Improvement | 08/10/2009 | 09/14/2009 | 10/01/2009 | 675703 | 0.85
804 | California | ORANGE | LOS ANGELES, CA | 46 | 5181164 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Huntington Beach. The project is described as: Landscaping and Irrigation, fine grading and adjustment o | Transportation Enhancements | 01/12/2010 | 01/12/2010 | 05/01/2010 | 156000 | 0.84
805 | California | ORANGE | LOS ANGELES, CA | 46 | 5181166 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Huntington Beach. The project is described as: Grind pavmt, remove failed roadway, paving of failed areas, o | Pavement Improvement | 03/29/2010 |  | 05/01/2010 | 1120616 | 1.5
806 | California | PLACER | SACRAMENTO | 4 | 5182046 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: Place hot mix asphalt on Junction Boulevard, Woodcreek Oaks Boulevard & Eureka Road. | Pavement Improvement | 08/24/2009 |  | 11/01/2009 | 1006173 | 5
807 | California | PLACER | SACRAMENTO | 4 | 5182048 | This is a Traffic Management Engineering project by a local agency in the City of Roseville. The project is described as: At Douglas & Sierra College Boulevard install E/B & W/B dual left turn lanes, | Other | 08/06/2009 |  | 11/01/2009 | 300000 | 0.1
808 | California | PLACER | SACRAMENTO | 4 | 5182049 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: Place hot mix asphalt bonded wearing course to North Sunrise, Eureka Road & to Junctio | Pavement Improvement | 08/17/2009 |  | 11/01/2009 | 844209 | 1
809 | California | PLACER | SACRAMENTO | 4 | 5182051 | This is a Traffic Management Engineering project by a local agency in the City of Roseville. The project is described as: Install CMS on N/B Sunrise Avenue south of Cirby Way per ITS Master Plan. | Safety/Traffic Management | 09/30/2009 |  | 11/01/2009 | 130630 | 1
810 | California | PLACER | SACRAMENTO | 4 | 5182052 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Roseville. The project is described as: At Sierra College Boulevard & East Roseville Parkway install N/B | Safety/Traffic Management | 09/08/2009 |  | 11/01/2009 | 167123 | 0.1
811 | California | GLENN |  | 4 | 5185005 | This is a Pavement Resurfacing project by a local agency in the City of Orland. The project is described as: Road maintenance | Pavement Improvement | 10/05/2009 | 10/30/2009 | 11/01/2009 | 423181 | 1.07
812 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5191004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hillsborough. The project is described as: Rehabilitate local street | Pavement Improvement | 09/29/2009 | 10/01/2009 | 11/01/2009 | 392000 | 2.3
813 | California | SAN JOAQUIN | TRACY | 11 | 5192028 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Tracy. The project is described as: Reconstruct roadway between Carlton Avenue and 11th Street | Pavement Improvement | 10/08/2009 | 10/26/2009 | 06/01/2010 | 1614306 | 0.5
814 | California | KERN |  | 22 | 5193030 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Taft. The project is described as: 6th St: Kern St to Warren St; Rehabilitation | Pavement Improvement | 02/16/2010 |  | 10/01/2009 | 353343 | 0.26
815 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5194005 | This is a Pavement Resurfacing project by a local agency in the City of King City. The project is described as: Reconstruct between San Lorenzo and Canal Streets | Pavement Improvement | 11/24/2009 |  | 12/01/2009 | 232000 | 1
816 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5196032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Daly City. The project is described as: Rehabilitate local street | Pavement Improvement | 09/21/2009 | 09/28/2009 | 04/01/2010 | 1045000 | 0.8
817 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5196033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Daly City. The project is described as: Rehabilitate local streets | Pavement Improvement | 05/10/2010 |  | 12/31/2010 | 318000 | 0.3
818 | California | FRESNO |  | 20 | 5197018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sanger. The project is described as: Pulverize existing pavement, remix into base, and cap existing street | Pavement Improvement | 04/07/2010 |  | 06/01/2009 | 411045.12 | 0.5
819 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5202014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Fernando. The project is described as: ECONOMIC STIMULUS PROJECT- NORTH BRAND BOULEVARD STREET IMPROVEME | Pavement Improvement | 10/19/2009 | 10/19/2009 | 09/01/2009 | 745000 | 0.58
820 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5204011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Glendora. The project is described as: GRAND AVENUE PAVING PROJECT FROM ARROW HIGHWAY TO FOOTHILL BOULEVARD. | Pavement Improvement | 12/16/2009 | 12/17/2009 | 12/01/2009 | 1266000 | 2
821 | California | FRESNO | FRESNO | 21 | 5208090 | This is a New Construction Roadway project by a local agency in the City of Clovis. The project is described as: Temperance Ave.: Between Gould Canal and Gettysburg; widen from 2 LU to 4 LD. | Pavement Widening | 10/23/2009 | 10/21/2009 | 11/01/2009 | 400000 | 0.75
822 | California | FRESNO | FRESNO | 21 | 5208091 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent wi | Pavement Improvement | 09/20/2009 | 09/20/2009 | 10/01/2009 | 607855 | 0.5
823 | California | FRESNO | FRESNO | 21 | 5208092 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent wi | Pavement Improvement | 09/30/2009 | 09/30/2009 | 10/01/2009 | 350000 | 0.5
824 | California | FRESNO | FRESNO | 21 | 5208093 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes Nees Ave from | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/01/2009 | 400000 | 0.5
825 | California | FRESNO | FRESNO | 21 | 5208095 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Lump-Sum Various AC Overlays/Reconstruction on Eligible Routes. Cons | Pavement Improvement | 05/24/2010 |  | 06/01/2010 | 616177 | 0.5
826 | California | LOS ANGELES | LOS ANGELES, CA | 36 | 5212003 | This is a Pavement Resurfacing project by a local agency in the City of Manhattan Beach. The project is described as: AVIATION BLVD. RESURFACING (MARINE AVE. TO MANHATTAN BEACH BLVD.) --- COLD MILL A | Pavement Improvement | 12/03/2009 | 12/07/2009 | 02/01/2010 | 151414 | 0.5
827 | California | LOS ANGELES | LOS ANGELES, CA | 36 | 5212004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Manhattan Beach. The project is described as: VALLEY DRIVE STREET IMPROVEMENT PROJECT (15TH STREET TO SEPULV | Pavement Improvement | 12/03/2009 | 12/07/2009 | 02/01/2010 | 378837 | 1.3
828 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5213032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sunnyvale. The project is described as: Rehabilitate local street | Bridge Improvement | 08/19/2009 | 09/28/2009 | 11/01/2009 | 1225635 | 0.3
829 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5221009 | This is a Pavement Resurfacing project by a local agency in the City of Beverly Hills. The project is described as: RESURFACING OF APPROXIMATELY 8.1 MILES OF PRINCIPAL ARTERIAL AND MAJOR COLLECTOR ST | Pavement Improvement | 10/26/2009 | 11/02/2009 | 12/01/2010 | 1059000 | 1.1
830 | California | VENTURA | OXNARD-VENTURA | 24 | 5222018 | This is a Pavement Resurfacing project by a local agency in the City of Fillmore. The project is described as: Edge Grinding & Rubberized Asphalt | Pavement Improvement | 01/10/2010 |  | 02/01/2010 | 400000 | 0.82
831 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5225022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Walnut Creek. The project is described as: Rehabilitate local street | Pavement Improvement | 09/09/2009 | 09/10/2009 | 02/01/2010 | 882214 | 0.83
832 | California | KERN | BAKERSFIELD | 20 | 5227036 | This is a Pavement Resurfacing project by a local agency in the City of Delano. The project is described as: 11th Ave from Albany St to High St, 9th Ave from High St to Randolph St, Norwalk St from C | Pavement Improvement | 01/07/2010 | 01/19/2010 | 06/01/2010 | 934745 | 3.42
833 | California | KERN |  | 20 | 5227039 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Delano. The project is described as: 11th Ave from High St. to Randolph St; High St .from Garces Hwy to Ceci | Pavement Improvement | 05/10/2010 |  | 09/01/2010 | 1002581 | 3
834 | California | MERCED |  | 18 | 5230002 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Gustine. The project is described as: Reconstruction of Sidewalks and Ramps in the Downtown area in the C | Transportation Enhancements | 04/21/2010 |  | 02/01/2010 | 207583 | 0.7
835 | California | LOS ANGELES | LOS ANGELES, CA | 29,32 | 5231012 | This is a Pavement Resurfacing project by a local agency in the City of Monterey Park. The project is described as: VARIOUS STREET RESURFACING 2009-01 | Pavement Improvement | 03/15/2010 |  | 06/01/2010 | 1771996 | 3.1
836 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5232009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Corte Madera. The project is described as: Rehabilitate local street | Pavement Improvement | 10/21/2009 | 11/05/2009 | 10/01/2009 | 130773 | 0.77
837 | California | LOS ANGELES | LOS ANGELES, CA | 36 | 5235011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Segundo. The project is described as: Main Street Rehabilitation - Mariposa Avenue to Imperial Highway | Pavement Improvement | 12/08/2009 | 12/10/2009 | 04/01/2010 | 210100 | 0.5
838 | California | ORANGE | LOS ANGELES, CA | 42 | 5237026 | This is a Pavement Resurfacing project by a local agency in the City of Brea. The project is described as: Associated Road - Birch Street to Imperial Highway | Pavement Improvement | 03/15/2010 |  | 03/01/2010 | 483694 | 0.47
839 | California | YOLO | SACRAMENTO | 2 | 5238048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Davis. The project is described as: In Yolo County, rehabilitate various roadways. | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/01/2009 | 732903 | 1
840 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5239014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Cerrito. The project is described as: Rehabilitate local street | Pavement Improvement | 09/21/2009 | 10/01/2009 | 12/01/2009 | 678000 | 1.5
841 | California | LOS ANGELES | LOS ANGELES, CA | 33 | 5240023 | This is a Pavement Resurfacing project by a local agency in the City of Culver City. The project is described as: WASHINGTON BOULEVARD RESURFACING PROJECT BETWEEN HELMS AVENUE AND LA CIENEGA BOULEVAR | Pavement Improvement | 10/14/2009 | 10/23/2009 | 12/01/2009 | 620000 | 0.5
842 | California | LOS ANGELES | LOS ANGELES, CA | 33 | 5240024 | This is a Pavement Resurfacing project by a local agency in the City of Culver City. The project is described as: GRIND AND OVERLAY 3 INCHES OF ASPHALT ON CULVER BOULEVARD FROM COMMONWEALTH AVENUE TO | Pavement Improvement | 10/22/2009 | 10/28/2009 | 11/01/2009 | 172983 | 0.35
843 | California | SAN JOAQUIN | STOCKTON | 11 | 5242021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Manteca. The project is described as: Rehabilitation of 9 streets in the City of Manteca | Pavement Improvement | 10/16/2009 | 10/16/2009 | 10/01/2009 | 1197375 | 4
844 | California | IMPERIAL |  | 51 | 5243006 | This is a Pavement Resurfacing project by a local agency in the City of Calipatria. The project is described as: Street Improvements of Rehabilitation and Reconstruction of North and South Portion of | Pavement Improvement | 02/26/2010 |  | 03/01/2010 | 895000 | 0.64
845 | California | FRESNO |  | 20 | 5245009 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of San Joaquin. The project is described as: Main Street from Arizona Ave. to Placer Ave. Remove and replac | Pavement Improvement | 06/07/2010 |  | 11/01/2009 | 160000 | 0.32
846 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5247015 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Montebello. The project is described as: NEIGHBORHOOD CITYWIDE SIDEWALK REHABILITATION: REMOVAL AND REPLACEM | Transportation Enhancements | 12/01/2009 | 12/08/2009 | 02/01/2010 | 1575904 | 0.7
847 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5248006 | This is a Safety project by a local agency in the City of Soledad. The project is described as: Install new traffic signal at Oak & Front Streets | Safety/Traffic Management | 06/22/2009 | 06/22/2009 | 12/01/2009 | 544891 | 0.12
848 | California | LOS ANGELES | LOS ANGELES, CA | 36 | 5249019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Torrance. The project is described as: CRENSHAW BLVD REHABILITATION, MARICOPA ST TO SEPULVEDA BLVD, CITY OF | Pavement Improvement | 02/19/2010 |  | 09/01/2010 | 1229322 | 2
849 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5250013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: Atlantic Ave work to include pavement improvements, sidewalk, curb ram | Pavement Improvement | 03/11/2010 |  | 02/01/2010 | 444887 | 0.3
850 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5250014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: Martin Luther King Blvd work to include pavement improvements, sidewal | Pavement Improvement | 01/04/2010 | 01/29/2010 | 02/01/2010 | 684580 | 0.47
851 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5250015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: OTIS IMPROVEMENT PROJECT TO INCLUDE PAVEMENT, SIDEWALK, CURB & GUTTER, | Pavement Improvement | 01/04/2010 | 01/29/2010 | 01/01/2010 | 309403 | 0.23
852 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5250016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: IMPERIAL HWY WORK TO INCLUDE PAVEMENT, CURB, GUTTER, CURB RAMPS, RAISE | Pavement Improvement | 03/11/2010 |  | 03/01/2010 | 615603 | 0.5
853 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5253014 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Hawthorne. The project is described as: THE PURPOSE OF THE ALTERATIONS IS TO ENHANCE PUBLIC SAFETY ON A RAIL | Pavement Improvement | 09/30/2009 |  | 01/01/2010 | 35000 | 0.1
854 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5253015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hawthorne. The project is described as: CITYWIDE STREET IMPROVEMENT PROJECT - The work consists of grinding, | Pavement Improvement | 09/20/2009 | 10/15/2009 | 01/01/2010 | 2600000 | 1
855 | California | MERCED |  | 18 | 5254012 | This is a Pavement Resurfacing project by a local agency in the City of Atwater. The project is described as: Shaffer Road - AC Overlay and Partial reconstruction | Pavement Improvement | 12/14/2009 | 01/27/2010 | 10/01/2009 | 568723 | 0.7
856 | California | MERCED |  | 18 | 5254013 | This is a Pavement Resurfacing project by a local agency in the City of Atwater. The project is described as: Juniper Ave. - AC Overlay and Partial reconstruction | Pavement Improvement | 10/05/2009 | 10/05/2009 | 11/01/2009 | 323067.76 | 0.4
857 | California | MERCED |  | 18 | 5256009 | This is a Pavement Resurfacing project by a local agency in the City of Livingston. The project is described as: Project involves road grinding, replacement of asphalt concrete, crack sealing of road | Pavement Improvement | 10/02/2009 | 10/05/2009 | 02/01/2010 | 550803 | 2.62
858 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5257023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South Gate. The project is described as: RECONSTRUCT ATLANTIC AVE AND IMPROVE DRAINAGE FROM FIRESTONE BLVD T | Pavement Improvement | 09/28/2009 | 09/28/2009 | 06/01/2010 | 2620000 | 1.25
859 | California | LOS ANGELES | LOS ANGELES, CA | 32 | 5259018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of West Covina. The project is described as: MAJOR STREET REHABILITATION PROJECT - VARIOUS ARTERIAL STREETS CIT | Pavement Improvement | 11/17/2009 | 11/30/2009 | 12/01/2009 | 2955150 | 8.6
860 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5261006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Atherton. The project is described as: Rehabilitate local street | Pavement Improvement | 07/27/2009 | 07/29/2009 | 08/01/2009 | 463061 | 0.5
861 | California | LOS ANGELES |  | 37 | 5262004 | This is a Pavement Resurfacing project by a local agency in the City of Signal Hill. The project is described as: GRIND AND OVERLAY APPROXIMATELY 12 LANE MILES OF DETERIORATING PAVEMENT ON A MAJOR AR | Pavement Improvement | 09/14/2009 | 09/14/2009 | 11/01/2009 | 500000 | 1.5
862 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5264003 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Colma. The project is described as: Rehabilitate local street | Pavement Improvement | 09/11/2009 | 09/29/2009 | 10/01/2009 | 131000 | 0.5
863 | California | LOS ANGELES | LOS ANGELES, CA | 34 | 5265010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Maywood. The project is described as: SLAUSON AVENUE CORRIDOR IMPROVEMENT PROJECT STREET & MEDIAN IMPROVEMEN | Pavement Improvement | 10/05/2009 | 10/05/2009 | 12/01/2009 | 235000 | 1
864 | California | LOS ANGELES |  | 34 | 5265011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Maywood. The project is described as: ATLANTIC BLVD. SOUTH: PROJECT INCLUDES REMOVAL AND REPLACEMENT OF AC P | Pavement Improvement | 09/21/2009 | 09/21/2009 | 12/01/2009 | 638385 | 0.3
865 | California | ORANGE | LOS ANGELES, CA | 42 | 5266018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Habra. The project is described as: Rehabilitate 0.75 Miles of roadway on Idaho Street | Pavement Improvement | 02/01/2010 | 02/04/2010 | 11/01/2009 | 500000 | 0.75
866 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5267013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Carlos. The project is described as: Rehabilitate local street | Transportation Enhancements | 09/28/2009 | 09/28/2009 | 12/01/2009 | 294870 | 0.75
867 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5268004 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Belmont. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 01/21/2010 |  | 06/01/2011 | 1952194 | 0.2
868 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5268015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Belmont. The project is described as: Rehabilitate local street | Pavement Improvement | 08/31/2009 | 09/09/2009 | 11/01/2009 | 464000 | 0.8
869 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5268016 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Belmont. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 01/01/2010 |  | 06/01/2011 | 2493000 | 0.2
870 | California | ORANGE | LOS ANGELES, CA | 40 | 5269021 | This is a Pavement Resurfacing project by a local agency in the City of Placentia. The project is described as: Rehab and construct asphalt concrete pavement and rubberized asphalt overlay | Pavement Improvement | 03/23/2010 |  | 12/01/2009 | 500000 | 0.53
871 | California | ORANGE | LOS ANGELES, CA | 48 | 5271020 | This is a Pavement Resurfacing project by a local agency in the City of Tustin. The project is described as: Jamboree Rd Pavement Rehab. 2750 feet north of Tustin Ranch Rd to Northern city limit. | Pavement Improvement | 03/29/2010 |  | 04/01/2010 | 813324 | 1.4
872 | California | LOS ANGELES | LOS ANGELES, CA | 34 | 5272009 | This is a Pavement Resurfacing project by a local agency in the City of Bell. The project is described as: BANDINI BOULEVARD FROM EASTERN AVENUE TO 26TH STREET. THE PROJECT CONSISTS IN AC OVERLAY AND | Pavement Improvement | 05/12/2010 |  | 12/01/2009 | 632446 | 0.8
873 | California | LOS ANGELES | LOS ANGELES, CA | 34 | 5272010 | This is a Pavement Resurfacing project by a local agency in the City of Bell. The project is described as: WILCOX AVENUE REHABILITATION FROM GAGE AVENUE TO RANDOLPH AVENUE. THE PROJECT CONSISTS IN AC | Pavement Improvement | 05/12/2010 |  | 12/01/2009 | 507554 | 0.25
874 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5273020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Menlo Park. The project is described as: Rehabilitate local street | Pavement Improvement | 09/03/2009 | 09/04/2009 | 09/01/2009 | 635000 | 1.3
875 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5276022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Gardena. The project is described as: WESTERN AVENUE STREET IMPROVEMENT - REDONDO BEACH BLVD. TO EL SEGUNDO | Pavement Improvement | 12/14/2009 | 12/14/2009 | 06/01/2010 | 916996 | 2
876 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5276023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Gardena. The project is described as: 135TH STREET IMPROVEMENT - CRENSHAW BLVD. TO VERMONT AVE. | Pavement Improvement | 12/14/2009 | 12/14/2009 | 06/01/2010 | 798187 | 2
877 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5277024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfax. The project is described as: Rehabilitate local street | Pavement Improvement | 03/29/2010 |  | 10/01/2009 | 167000 | 0.96
878 | California | KERN |  | 20 | 5281012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Shafter. The project is described as: Lerdo Hwy: Carver St to Driver Rd; Reconstruction, resurfacing and sho | Pavement Improvement | 04/29/2010 |  | 03/01/2010 | 589437 | 1.5
879 | California | RIVERSIDE | INDIA-COACHELLA | 45 | 5282027 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Palm Springs. The project is described as: Install landscaping, gateway park, ped walkwy | Transportation Enhancements | 11/09/2009 | 11/09/2009 | 06/01/2010 | 1850000 | 0.25
880 | California | LOS ANGELES | LOS ANGELES, CA | 46 | 5283006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palos Verdes Estates. The project is described as: PALOS VERDES DRIVE WEST AT BLUFF COVE ROADWAY STABILIZATI | Pavement Improvement | 11/09/2009 | 11/16/2009 | 12/01/2009 | 500000 | 0.05
881 | California | SAN JOAQUIN |  | 11 | 5286012 | This is a Traffic Management Engineering project by a local agency in the City of Ripon. The project is described as: Ehancement of existing roundabout | Pavement Improvement | 11/24/2009 | 12/09/2009 | 03/01/2010 | 202131 | 1
882 | California | KERN |  | 20 | 5287026 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Wasco. The project is described as: Poso Dr: State Route 43 to Griffith Ave; Reconstruction | Pavement Improvement | 10/14/2009 | 10/21/2009 | 04/01/2010 | 937195 | 0.4
883 | California | SACRAMENTO |  | 3 | 5293012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Galt. The project is described as: In Galt, Rehabilitate roadways. | Pavement Improvement | 08/11/2009 |  | 11/01/2009 | 416140 | 1
884 | California | SACRAMENTO |  | 3 | 5293013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Galt. The project is described as: Construct ADA sidewalk repairs in Galt | Pavement Improvement | 09/21/2009 | 09/23/2009 | 11/01/2009 | 300000 | 1
885 | California | MONTEREY |  | 17 | 5295004 | This is a Pavement Resurfacing project by a local agency in the City of Greenfield. The project is described as: Storm drain improvements | Other | 02/03/2010 | 02/16/2010 | 12/01/2009 | 340000 | 1
886 | California | MONTEREY |  | 17 | 5296003 | This is a Pavement Resurfacing project by a local agency in the City of Gonzales. The project is described as: Reconstruct from southerly city limits to 4th Street including sidewalk and bike lanes | Pavement Improvement | 08/12/2009 |  | 12/01/2009 | 171893 | 1
887 | California | SUTTER |  | 2 | 5297006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Live Oak. The project is described as: Rehabilitate Apricot St: N St-Broadway | Pavement Improvement | 10/12/2009 | 10/13/2009 | 12/01/2009 | 205639 | 1
888 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5299011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Millbrae. The project is described as: Rehabilitate local street | Pavement Improvement | 08/31/2009 | 09/08/2009 | 10/01/2009 | 382000 | 0.5
889 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10,11 | 5300008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Brentwood. The project is described as: Rehabilitate local street | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/01/2009 | 1040778 | 1
890 | California | FRESNO |  | 21 | 5301007 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Orange Cove. The project is described as: Center Street: Between Adams and Park; reconstruction. | Pavement Improvement | 09/21/2009 | 09/23/2009 | 11/01/2009 | 200866 | 0.5
891 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7 | 5303013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Pablo. The project is described as: Rehabilitate local street | Pavement Improvement | 09/28/2009 |  | 12/01/2009 | 694000 | 0.85
892 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5304007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Capitola. The project is described as: Road repairs : Capitola Road to Clares | Pavement Improvement | 08/07/2009 | 09/01/2009 | 10/01/2009 | 230000 | 0.3
893 | California | SANTA CLARA | SAN JOSE, CA | 15 | 5306013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Campbell. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 03/22/2010 |  | 02/01/2011 | 2260000 | 0.4
894 | California | SANTA CLARA | SAN JOSE, CA | 14,15,16 | 5306018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Campbell. The project is described as: Rehabilitate local street | Pavement Improvement | 09/21/2009 | 09/21/2009 | 12/01/2009 | 594000 | 0.42
895 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5309013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Altos. The project is described as: Rehabilitate local street | Pavement Improvement | 10/12/2009 | 10/12/2009 | 12/01/2009 | 253000 | 2
896 | California | ORANGE | LOS ANGELES, CA | 40 | 5310031 | This is a Pavement Resurfacing project by a local agency in the City of Buena Park. The project is described as: Rehabilitation of approx 0.53 mi of Knott from La Palma to Crescent, including rehabil | Pavement Improvement | 04/06/2010 |  | 06/01/2010 | 892590 | 0.53
897 | California | ORANGE | LOS ANGELES, CA | 46 | 5312071 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Costa Mesa. The project is described as: Landscape and beautificaion at Fairview Road/I405 Interchange | Transportation Enhancements | 11/02/2009 | 11/02/2009 | 03/01/2010 | 500000 | 2.3
898 | California | ORANGE | LOS ANGELES, CA | 46 | 5312074 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Costa Mesa. The project is described as: Santa Ana Improvement Project,from 17th Street to 22nd Street | Pavement Improvement | 01/20/2010 | 02/02/2010 | 10/01/2010 | 1100000 | 1.25
899 | California | SANTA CLARA | SAN JOSE, CA | 11,15,16 | 5314007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Milpitas. The project is described as: Rehabilitate local street | Pavement Improvement | 09/01/2009 | 09/02/2009 | 12/01/2009 | 771592 | 0.6
900 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5315006 | This is a Pavement Resurfacing project by a local agency in the City of Lakewood. The project is described as: BLOOMFIELD AVENUE IMPROVEMENTS FROM SOUTH CITY LIMIT TO DEL AMO BOULEVARD - RESURFACE PA | Pavement Improvement | 09/08/2009 | 09/08/2009 | 12/01/2009 | 565245.53 | 0.89
901 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5315007 | This is a Pavement Resurfacing project by a local agency in the City of Lakewood. The project is described as: SOUTH STREET IMPROVEMENTS FROM EAST CITY LIMIT TO LAKEWOOD BOULEVARD - RESURFACE PAVEMEN | Pavement Improvement | 09/08/2009 | 09/08/2009 | 12/01/2009 | 1386695.61 | 0.83
902 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5316006 | This is a Pavement Resurfacing project by a local agency in the City of Seaside. The project is described as: Reconstruct between south city limits and Broadway Ave | Pavement Improvement | 09/10/2009 | 09/14/2009 | 12/01/2009 | 669839 | 1
903 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5318025 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cupertino. The project is described as: Rehabilitate local street | Pavement Improvement | 10/05/2009 | 10/07/2009 | 06/01/2010 | 707000 | 0.81
904 | California | ORANGE | LOS ANGELES, CA | 40 | 5319012 | This is a Pavement Resurfacing project by a local agency in the City of La Palma. The project is described as: Orangethorpe Pavement Rehabilitation - Valley View St to Moody St/WCL | Pavement Improvement | 02/16/2010 |  | 12/01/2010 | 500000 | 1
905 | California | SHASTA |  | 2 | 5321015 | This is a Pavement Resurfacing project by a local agency in the City of Anderson. The project is described as: 2.95 miles of Preventative Maintenance on major local streets | Pavement Improvement | 09/03/2009 | 09/21/2009 | 11/01/2009 | 421000 | 2.94
906 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 11,13 | 5322035 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fremont. The project is described as: Rehabilitate local street | Pavement Improvement | 08/24/2009 | 08/24/2009 | 12/01/2009 | 5907000 | 4.28
907 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5324005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Altos Hills. The project is described as: Rehabilitate local street | Pavement Improvement | 07/16/2009 | 07/20/2009 | 08/01/2009 | 316000 | 1.8
908 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5325012 | This is a Pavement Resurfacing project by a local agency in the City of Cerritos. The project is described as: BLOOMFIELD AVENUE, BETWEEN ARTESIA BOULEVARD AND ALONDRA BOULEVARD: PAVEMENT REHABILITA | Pavement Improvement | 02/02/2010 | 02/02/2010 | 06/01/2010 | 1103000 | 1
909 | California | ORANGE | LOS ANGELES, CA | 40 | 5327012 | This is a Pavement Resurfacing project by a local agency in the City of Stanton. The project is described as: Dale St. Rehabilitation - Katella Av to Cerritos Av | Pavement Improvement | 02/25/2010 |  | 12/01/2010 | 363925 | 0.5
910 | California | ORANGE | LOS ANGELES, CA | 47 | 5328063 | This is a Pavement Resurfacing project by a local agency in the City of Garden Grove. The project is described as: To resurface 0.7 miles of Harbor Boulevard (an arterial highway) from Garden Grove t | Pavement Improvement | 03/18/2010 |  | 06/01/2010 | 1000000 | 0.7
911 | California | ORANGE | LOS ANGELES, CA | 40 | 5330014 | This is a Pavement Resurfacing project by a local agency in the City of Cypress. The project is described as: Street Rehabilitation (Valley View, Cerritos to Katella) | Pavement Improvement | 05/03/2010 |  | 06/01/2010 | 544516 | 0.5
912 | California | LOS ANGELES |  | 38 | 5331011 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of La Puente. The project is described as: HACIENDA BLVD. RECONSTRUCTION: RECONSTRUCTION AND/OR OVERLAY OF R | Pavement Improvement | 10/19/2009 | 10/19/2009 | 12/01/2009 | 815592 | 0.9
913 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5331012 | This is a Pavement Resurfacing project by a local agency in the City of La Puente. The project is described as: CITYWIDE OVERLAY PROJECT: OVERLAY OF VARIOUS STREETS CITYWIDE | Pavement Improvement | 11/19/2009 | 11/19/2009 | 01/01/2010 | 247082 | 0.4
914 | California | SANTA CLARA | SAN JOSE, CA | 14,15 | 5332014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Saratoga. The project is described as: Rehabilitate local street | Pavement Improvement | 11/09/2009 | 11/09/2009 | 11/01/2009 | 714000 | 1.3
915 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5336012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Paramount. The project is described as: STREET IMPROVEMENTS IN DOWNEY AVENUE FROM ROSECRANS AVENUE TO GARDEN | Pavement Improvement | 09/08/2009 | 09/08/2009 | 12/01/2009 | 700000 | 0.76
916 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5336013 | This is a Pavement Resurfacing project by a local agency in the City of Paramount. The project is described as: ROSECRANS AVENUE IMPROVEMENTS FROM LA RIVER TO GARFIELD AVENUE - RESURFACE PAVEMENT, CO | Pavement Improvement | 10/12/2009 | 10/12/2009 | 12/01/2009 | 629000 | 0.72
917 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5336014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Paramount. The project is described as: Improvements in Somerset Boulevard from Orange Avenue to LA River an | Pavement Improvement | 02/22/2010 |  | 03/01/2010 | 371000 | 0.47
918 | California | ORANGE | LOS ANGELES, CA | 40,46 | 5338041 | This is a Pavement Resurfacing project by a local agency in the City of Westminster. The project is described as: Brookhurst St Improvements from Hazard Avenue to Bolsa Avenue | Pavement Improvement | 11/02/2009 | 11/02/2009 | 02/01/2010 | 813214 | 0.5
919 | California | SANTA CLARA | SAN JOSE, CA | 14 | 5339001 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Monte Sereno. The project is described as: Rehabilitate local street | Pavement Improvement | 08/10/2009 | 08/17/2009 | 11/01/2009 | 94000 | 0.5
920 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5340012 | This is a Pavement Resurfacing project by a local agency in the City of Santa Fe Springs. The project is described as: RESURFACING AND RECONSTRUCTION OF VARIOUS COMMERCIAL AND INDUSTRIAL STREETS | Pavement Improvement | 01/11/2010 | 01/11/2010 | 10/01/2009 | 528000 | 0.53
921 | California | ORANGE | LOS ANGELES, CA | 46 | 5341028 | This is a Pavement Resurfacing project by a local agency in the City of Fountain Valley. The project is described as: Resurface Warner Ave and Bushard St | Pavement Improvement | 04/05/2010 |  | 03/01/2010 | 619157 | 1
922 | California | KERN | BAKERSFIELD | 20 | 5343002 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of McFarland. The project is described as: W. Perkins Ave: 50 ft east of 3rd St to 320 ft east of 3rd St and | Pavement Improvement | 11/13/2009 |  | 12/01/2009 | 507524 | 0.05
923 | California | LOS ANGELES | LOS ANGELES, CA | 32 | 5345005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Irwindale. The project is described as: GLADSTONE STREET FROM IRWINDALE AVENUE TO THE EAST CITY LIMIT. STREE | Pavement Improvement | 03/15/2010 |  | 11/01/2009 | 500000 | 0.3
924 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5347032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Norwalk. The project is described as: REHABILITATE FRONT STREET FROM SAN ANTONIO DRIVE TO ROSECRANS AVENUE. | Pavement Improvement | 01/04/2010 | 01/04/2010 | 03/01/2010 | 398665 | 0.77
925 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5347033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Norwalk. The project is described as: REHABILITATE FIRESTONE BOULEVARD FROM HOXIE AVENUE TO IMPERIAL HIGHWAY | Pavement Improvement | 04/01/2010 |  | 05/01/2010 | 623000 | 0.91
926 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5347034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Norwalk. The project is described as: REHABILITATE STUDEBAKER ROAD FROM IMPERIAL HIGHWAY TO ALONDRA BOULEVAR | Pavement Improvement | 02/01/2010 |  | 05/01/2010 | 1670498 | 2
927 | California | LOS ANGELES | LOS ANGELES, CA | 50 | 5348016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Bellflower. The project is described as: REHABILITATION OF DOWNEY AVENUE, NORTH CITY LIMIT TO SOUTH CITY LIM | Pavement Improvement | 04/27/2010 |  | 12/01/2009 | 386026 | 0.5
928 | California | LOS ANGELES | LOS ANGELES, CA | 46 | 5349005 | This is a Traffic Management Engineering project by a local agency in the City of Rolling Hills Estates. The project is described as: TRAFFIC SIGNAL MODIFICATION AT PALOS VERDES DRIVE NORTH AND CRENS | Safety/Traffic Management | 02/22/2010 |  | 12/01/2009 | 54439 | 0.1
929 | California | LOS ANGELES | LOS ANGELES, CA | 46 | 5349006 | This is a Safety project by a local agency in the City of Rolling Hills Estates. The project is described as: INSTALL LED INTERNALLY ILLUMINATED STREET NAME SIGNS CITYWIDE | Safety/Traffic Management | 03/01/2010 |  | 12/01/2009 | 65472 | 0.1
930 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5350016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pacifica. The project is described as: Rehabilitate local street | Pavement Improvement | 09/21/2009 | 09/28/2009 | 08/01/2009 | 677000 | 2
931 | California | LOS ANGELES | LOS ANGELES, CA | 38 | 5351017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pico Rivera. The project is described as: BEVERLY BLVD. PAVEMENT REHABILITATION, TRAFFIC SIGNAL MODIFICATION | Pavement Improvement | 05/13/2010 |  | 08/01/2010 | 1960000 | 1.26
932 | California | LOS ANGELES | LOS ANGELES, CA | 42 | 5353005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Walnut. The project is described as: Nogales Street from southerly city limit to Amar. Rehabilitate pavemen | Pavement Improvement | 12/14/2009 | 12/14/2009 | 06/01/2010 | 755431 | 0.5
933 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5355021 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Artesia. The project is described as: SOUTH STREET PEDESTRIAN BIKEWAY AND TRANSIT IMPROVEMENTS. PROJECT PRO | Transportation Enhancements | 11/09/2009 |  | 12/01/2009 | 402866 | 0.5
934 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5357005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Half Moon Bay. The project is described as: Rehabilitate local street | Pavement Improvement | 08/07/2009 | 08/15/2009 | 11/01/2009 | 210000 | 0.5
935 | California | LOS ANGELES | LOS ANGELES, CA | 32 | 5358010 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Rosemead. The project is described as: THE PROJECT CONSISTS IN THE CONSTRUCTION AND UPGRADE OF CURB RAMPS AT | Pavement Improvement | 04/19/2010 |  | 06/01/2010 | 1684000 | 5.15
936 | California | SAN LUIS OBISPO | SAN LUIS OBISPO | 23 | 5359015 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Grover Beach. The project is described as: Fourth Street to the Railroad Tracks (Improve and upgrade lan | Transportation Enhancements | 12/22/2009 |  | 05/01/2010 | 856000 | 0.17
937 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5360008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lawndale. The project is described as: THE PROJECT WILL MAKE VARIOUS STREET IMPROVEMENTS TO ROSECRANS AVENUE | Pavement Improvement | 12/01/2009 | 12/14/2009 | 01/01/2010 | 987000 | 1
938 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5361022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Novato. The project is described as: Rehabilitate local street | Pavement Improvement | 10/19/2009 | 10/19/2009 | 12/01/2009 | 1062000 | 6
939 | California | LOS ANGELES |  | 34 | 5362014 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Commerce. The project is described as: THIS PROJECT IS AT THE INTERSECTION OF GARFIELD AVENUE AND SLAUSON | Pavement Improvement | 11/28/2009 | 09/28/2009 | 11/01/2009 | 500000 | 0.1
940 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5364005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Mirada. The project is described as: Stage Road from Alondra Boulevard to east City Limit. Selective Rec | Pavement Improvement | 02/01/2010 |  | 10/01/2009 | 731019 | 0.8
941 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5365003 | This is a Safety project by a local agency in the City of Temple City. The project is described as: NEW TRAFFIC SIGNAL ON TEMPLE CITY BLVD. AT ELLIS LANE: INSTALLATION OF A NEW SIGNAL. COMPONENTS INC | Safety/Traffic Management | 01/22/2010 |  | 02/01/2010 | 123213 | 1
942 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5365004 | This is a Pavement Resurfacing project by a local agency in the City of Temple City. The project is described as: CITY STREETS OVERLAY PROJECT: GRIND AND OVERLAY OF VARIOUS CITY STREETS | Pavement Improvement | 01/26/2010 |  | 12/01/2009 | 599000 | 0.8
943 | California | LOS ANGELES |  | 26 | 5367006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Dimas. The project is described as: SAN DIMAS AVENUE RECONSTRUCTION, REHABILITATION AND LANDSCAPE MEDIAN | Pavement Improvement | 10/26/2009 | 10/29/2009 | 01/01/2010 | 1085000 | 0.7
944 | California | SISKIYOU |  | 2 | 5371005 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Weed. The project is described as: Rehabilitate 1.63 miles of streets within the City of Weed with asphal | Pavement Improvement | 04/20/2010 |  | 05/01/2010 | 539000 | 1.63
945 | California | LOS ANGELES | LOS ANGELES, CA | 34 | 5373012 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bell Gardens. The project is described as: CITYWIDE STREET REHABILITATION: LOCAL STREET RECONSTRUCTION AN | Pavement Improvement | 11/30/2009 | 11/30/2009 | 01/01/2010 | 414700 | 1
946 | California | LOS ANGELES | LOS ANGELES, CA | 34 | 5373013 | This is a Pavement Resurfacing project by a local agency in the City of Bell Gardens. The project is described as: CITYWIDE STREET OVERLAY: RAC OVERLAY OF STREETS. | Pavement Improvement | 09/16/2009 | 09/16/2009 | 12/01/2009 | 745800 | 0.7
947 | California | CONTRA COSTA | CONCORD | 7,10 | 5375021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasant Hill. The project is described as: Rehabilitate local street | Pavement Improvement | 08/19/2009 | 08/19/2009 | 11/01/2009 | 842000 | 0.71
948 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5376008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Brisbane. The project is described as: Rehabilitate local street | Pavement Improvement | 07/10/2009 |  | 10/01/2009 | 131000 | 0.1
949 | California | ORANGE | LOS ANGELES, CA | 47 | 5377012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Villa Park. The project is described as: This is a pavement rehabilitation project on Santiago Blvd. from Pr | Pavement Improvement | 01/20/2010 |  | 11/01/2009 | 500000 | 2.2
950 | California | LOS ANGELES | LOS ANGELES, CA | 25 | 5378019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palmdale. The project is described as: 2009 ARTERIAL REHABILITATION AND RECONSTRUCTION PROGRAM | Pavement Improvement | 09/16/2009 | 09/16/2009 | 05/01/2010 | 4324000 | 24.58
951 | California | SONOMA | SANTA ROSA | 6 | 5379017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rohnert Park. The project is described as: Rehabilitate local street | Pavement Improvement | 08/13/2009 | 08/27/2009 | 11/01/2009 | 869000 | 3.21
952 | California | SONOMA | SANTA ROSA | 6 | 5383007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cotati. The project is described as: Rehabilitate local street | Pavement Improvement | 11/09/2009 | 11/09/2009 | 01/01/2010 | 500000 | 0.34
953 | California | CONTRA COSTA | CONCORD | 7,10 | 5386009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Clayton. The project is described as: Rehabilitate local street | Pavement Improvement | 08/18/2009 | 08/24/2009 | 10/01/2009 | 355854 | 1.1
954 | California | LOS ANGELES |  | 39 | 5387009 | This is a Pavement Resurfacing project by a local agency in the City of Hawaiian Gardens. The project is described as: NORWALK BOULEVARD FROM CENTRALIA STREET TO SOUTH CITY LIMIT - RESURFACE PAVEMENT | Pavement Improvement | 10/05/2009 | 10/05/2009 | 12/01/2009 | 428060 | 0.56
955 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5388008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Tiburon. The project is described as: Rehabilitate local street | Pavement Improvement | 10/21/2009 | 11/02/2009 | 07/01/2009 | 204000 | 1
956 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5390004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Portola Valley. The project is described as: Rehabilitate local street | Pavement Improvement | 09/18/2009 | 09/24/2009 | 12/01/2009 | 196000 | 0.6
957 | California | VENTURA | THOUSAND OAKS | 23 | 5392040 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Thousand Oaks. The project is described as: Improvements to lane configurations leading to and from the inte | Other | 01/04/2010 | 01/04/2010 | 03/01/2012 | 5196325 | 0.75
958 | California | VENTURA | OXNARD-VENTURA | 24 | 5393020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Camarillo. The project is described as: Annual Pavement Rehab at Various Location | Pavement Improvement | 11/23/2009 |  | 12/01/2010 | 1099966 | 2.45
959 | California | KERN |  | 22 | 5399014 | This is a Traffic Management Engineering project by a local agency in the City of California City. The project is described as: Intersection of Cal City Blvd, Cal City Blvd South, Proctor Blvd, Rands | Safety/Traffic Management | 04/22/2010 |  | 12/01/2009 | 543723 | 1
960 | California | ORANGE | LOS ANGELES, CA | 42 | 5402026 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Yorba Linda. The project is described as: Pavement Rehabilitation on Village Center Drive from Manzanita to | Pavement Improvement | 03/22/2010 |  | 06/01/2010 | 279620 | 1
961 | California | LOS ANGELES | LOS ANGELES, CA | 37 | 5403014 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Carson. The project is described as: BROADWAY IMPROVEMENTS FROM 168TH ST. TO NORTH CITY LIMIT (ALONDRA B | Pavement Improvement | 11/02/2009 | 11/16/2009 | 04/01/2010 | 2000000 | 0.4
962 | California | CONTRA COSTA | CONCORD | 7,10 | 5404020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lafayette. The project is described as: Rehabilitate local street | Pavement Improvement | 08/04/2009 | 08/31/2009 | 10/01/2009 | 744000 | 2.25
963 | California | VENTURA | OXNARD-VENTURA | 24 | 5405050 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Simi Valley. The project is described as: Major Street Rehabilitation, various locations | Pavement Improvement | 08/03/2009 | 08/03/2009 | 10/01/2009 | 1080532 | 2.35
964 | California | VENTURA | OXNARD-VENTURA | 24 | 5405056 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Simi Valley. The project is described as: Major Street Rehabilitation, various locations | Pavement Improvement | 03/22/2010 |  | 06/01/2010 | 1031188 | 1
965 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5409015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Foster City. The project is described as: Rehabilitate local street | Pavement Improvement | 09/14/2009 | 09/14/2009 | 11/01/2009 | 440000 | 0.5
966 | California | ORANGE | LOS ANGELES, CA | 48 | 5410065 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Irvine. The project is described as: Provide landscaping along the recently graded slopes of the Jeffrey | Transportation Enhancements | 02/04/2010 |  | 02/01/2011 | 344109 | 1
967 | California | ORANGE | MISSION VIEJO | 48 | 5410069 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Irvine. The project is described as: Pavement rehabilitation of Red Hill Avenue from Deere to Reynolds. | Pavement Improvement | 02/01/2010 | 02/01/2010 | 04/01/2010 | 2462713 | 0.67
968 | California | LOS ANGELES |  | 36 | 5413010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rancho Palos Verdes. The project is described as: STREET IMPROVEMENTS ON HAWTHORNE BLVD FROM INDIAN PEAK ROA | Pavement Improvement | 10/19/2009 | 10/19/2009 | 01/01/2010 | 1262000 | 4.47
969 | California | CONTRA COSTA | CONCORD | 10 | 5415010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Moraga. The project is described as: Rehabilitate local street | Pavement Improvement | 09/15/2009 | 09/15/2009 | 11/01/2009 | 609000 | 1.1
970 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5417015 | This is a Pavement Resurfacing project by a local agency in the City of La Canada Flintridge. The project is described as: RESURFACING OF VARIOUS CITY STREETS. | Pavement Improvement | 10/15/2009 | 10/15/2009 | 12/01/2009 | 964700 | 2.16
971 | California | LOS ANGELES | LOS ANGELES, CA | 22,25 | 5419020 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Lancaster. The project is described as: RECONSTRUCTION OF THE NORTH HALF OF AVENUE K FROM 50TH TO 52ND ST | Pavement Improvement | 10/19/2009 | 10/26/2009 | 01/01/2010 | 325033 | 0.5
972 | California | LOS ANGELES | LOS ANGELES, CA | 22,25 | 5419021 | This is a Pavement Resurfacing project by a local agency in the City of Lancaster. The project is described as: 2008 STREET REHABILITATION - PHASE II SHALL PERFORM FULL DEPTH RECLAMATION, COLD IN PLA | Pavement Improvement | 09/21/2009 | 09/21/2009 | 01/01/2010 | 2324875 | 3.8
973 | California | LOS ANGELES | LOS ANGELES, CA | 22,25 | 5419023 | This is a Traffic Management Engineering project by a local agency in the City of Lancaster. The project is described as: CONSTRUCTION OF TRAFFIC SIGNALS AND MINOR STREET IMPROVEMENTS AT AVENUE L-8 & | Pavement Improvement | 12/30/2009 | 01/04/2010 | 01/01/2010 | 1339980 | 0.2
974 | California | SAN BERNARDINO | SAN BERNARDINO-RIVERSIDE | 26 | 5420018 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Rancho Cucamonga. The project is described as: On Church street install landscape with irrigation contr | Transportation Enhancements | 06/07/2010 |  | 09/30/2010 | 100000 | 0.2
975 | California | LOS ANGELES | LOS ANGELES, CA | 42 | 5422002 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Habra Heights. The project is described as: REHABILITATION OF ROADWAY, RESTORATION OF STREET SHOULDER, HA | Pavement Improvement | 01/04/2010 | 01/04/2010 | 01/01/2010 | 500000 | 4.16
976 | California | BUTTE |  | 2 | 5425020 | This is a Pavement Resurfacing project by a local agency in the City of Paradise. The project is described as: Roadway Rehabilitation / Overlays | Pavement Improvement | 09/25/2009 | 10/20/2009 | 12/01/2010 | 1498962 | 5.1
977 | California | LAKE |  | 1 | 5427019 | This is a Pavement Resurfacing project by a local agency in the City of Clearlake. The project is described as: Lakeshore Drive to Old Highway 53/Between Rumsey Road and Woodland Drive | Pavement Improvement | 09/10/2009 | 09/21/2009 | 09/01/2009 | 813600 | 1.37
978 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5431006 | This is a Pavement Resurfacing project by a local agency in the City of Westlake Village. The project is described as: This project consists of pavement repair and structural overlay on major arteria | Pavement Improvement | 05/10/2010 |  | 04/01/2010 | 494221 | 1
979 | California | CONTRA COSTA | CONCORD | 10,11 | 5434018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Danville. The project is described as: Rehabilitate local street | Pavement Improvement | 10/08/2009 | 10/19/2009 | 10/01/2011 | 871614 | 2.1
980 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5435016 | This is a Bridge Rehabilitation, Added Capacity project by a local agency in the City of Agoura Hills. The project is described as: WIDENING OF THE REYES ADOBE ROAD OVERCROSSING OF THE 101 FREEWAY FR | Pavement Widening | 10/01/2009 | 10/14/2009 | 08/01/2010 | 690000 | 0.2
981 | California | CONTRA COSTA | CONCORD | 10,11 | 5437022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Ramon. The project is described as: Rehabilitate local street | Pavement Improvement | 10/01/2009 | 10/01/2009 | 03/01/2010 | 1122000 | 0.88
982 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5438008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of East Palo Alto. The project is described as: Rehabilitate local street | Pavement Improvement | 11/04/2009 |  | 02/01/2010 | 421000 | 1.9
983 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5440008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of West Hollywood. The project is described as: SUNSET BLVD FROM WEST CITY BOUNDARY (WEST OF CORY AVE) TO EAST | Pavement Improvement | 01/12/2010 | 01/12/2010 | 12/01/2010 | 1105000 | 1.7
984 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5444013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Orinda. The project is described as: Rehabilitate local street | Pavement Improvement | 10/12/2009 | 10/15/2009 | 12/01/2009 | 318539 | 0.9
985 | California | LOS ANGELES | LOS ANGELES, CA | 25 | 5450047 | This is a Safety project by a local agency in the City of Santa Clarita. The project is described as: TRAFFIC CIRCULATION AND SAFETY IMPROVEMENTS AT NEWHALL AVENUE AND SIERRA HIGHWAY | Pavement Improvement | 10/12/2009 | 10/12/2009 | 12/01/2009 | 282101 | 0.2
986 | California | LOS ANGELES | LOS ANGELES, CA | 25 | 5450048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clarita. The project is described as: ASPHALT ROADWAY REHABILITATION PHASE I | Pavement Improvement | 09/30/2009 | 09/30/2009 | 12/01/2009 | 1297493 | 1.5
987 | California | LOS ANGELES | LOS ANGELES, CA | 25 | 5450050 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clarita. The project is described as: ASPHALT ROADWAY REHABILITATION PHASE II. | Pavement Improvement | 09/30/2009 | 09/30/2009 | 12/01/2009 | 1361858 | 1.5
988 | California | LOS ANGELES | LOS ANGELES, CA | 25 | 5450051 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clarita. The project is described as: BRIDGE REHABILITATION FOR VARIOUS BRIDGES. | Pavement Improvement | 11/30/2009 | 12/09/2009 | 11/01/2009 | 365878 | 0.28
989 | California | ORANGE | MISSION VIEJO | 42 | 5451026 | This is a Pavement Resurfacing project by a local agency in the City of Mission Viejo. The project is described as: Overlay of Portions of Alicia, Trabuco and Olympiad | Pavement Improvement | 01/04/2010 | 01/04/2010 | 01/01/2010 | 898537 | 2.2
990 | California | ORANGE | MISSION VIEJO | 73 | 5454022 | This is a Pavement Resurfacing project by a local agency in the City of Dana Point. The project is described as: Roadway Resurfacing | Pavement Improvement | 03/15/2010 |  | 09/01/2010 | 500000 | 0.83
991 | California | LOS ANGELES | LOS ANGELES, CA | 42 | 5455013 | This is a Pavement Resurfacing project by a local agency in the City of Diamond Bar. The project is described as: PREVENTIVE STREET MAINTENANCE PROGRAM - APPROXIMATELY 10 MILES OF ARTERIAL ROADWAY S | Pavement Improvement | 09/23/2009 | 09/23/2009 | 12/01/2009 | 1763586 | 10
992 | California | SAN JOAQUIN |  | 11 | 5456010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lathrop. The project is described as: Rehabilitate roadway between J Street and Thomsen Road | Pavement Improvement | 11/24/2009 |  | 01/01/2010 | 331377 | 0.42
993 | California | ORANGE | MISSION VIEJO | 48 | 5458014 | This is a Pavement Resurfacing project by a local agency in the City of Laguna Niguel. The project is described as: Construct AC overlay on Aliso Creek Rd. from Alicia Parkway to La Paz Rd. | Pavement Improvement | 02/22/2010 |  | 02/01/2010 | 549010 | 0.5
994 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5462012 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Malibu. The project is described as: MALIBU CANYON ROAD IMPROVEMENTS AND RECONSTRUCTION PROJECT; RECONSTR | Pavement Improvement | 02/01/2010 |  | 03/01/2010 | 452240 | 1.25
995 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5463014 | This is a Traffic Management Engineering project by a local agency in the City of Calabasas. The project is described as: CONNECT ALL TRAFFIC SIGNALS WITHIN THE CITY OF CALABASAS TO THE TRAFFIC MANAG | Other | 04/28/2010 |  | 09/01/2009 | 701000 | 3.95
996 | California | RIVERSIDE | STATEWIDE | 45 | 5464029 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Murrieta. The project is described as: Replace Diamond IC with partial Cloverleaf IC | Bridge Improvement | 12/18/2009 | 12/18/2009 | 04/01/2011 | 9999981 | 1.1
997 | California | ORANGE | MISSION VIEJO | 48 | 5468013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Laguna Hills. The project is described as: Pavement Rehabilitation | Pavement Improvement | 12/07/2009 | 12/14/2009 | 06/01/2010 | 500000 | 0.72
998 | California | ORANGE | MISSION VIEJO | 48 | 5469013 | This is a Pavement Resurfacing project by a local agency in the City of Lake Forest. The project is described as: Trabuco Road Rehabilitation - Lake Forest Dr to South City Limit | Pavement Improvement | 11/30/2009 | 11/30/2009 | 11/01/2009 | 749310 | 1.1
999 | California | NAPA | STATEWIDE | 1,7 | 5470007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of American Canyon. The project is described as: Rehabilitate local street | Pavement Improvement | 11/02/2009 | 11/02/2009 | 09/01/2009 | 320000 | 0.5
1000 | California | SONOMA | SANTA ROSA | 1,6 | 5472012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Windsor. The project is described as: Rehabilitate local street | Pavement Improvement | 08/25/2009 |  | 10/01/2009 | 455547 | 0.75
1001 | California | SONOMA | SANTA ROSA | 1 | 5472014 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Windsor. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 04/01/2010 |  | 08/01/2010 | 245079 | 0.25
1002 | California | SHASTA |  | 2 | 5474013 | This is a Pavement Resurfacing project by a local agency in the City of Shasta Lake. The project is described as: 1.51miles of Preventative Maintenance on major local streets | Pavement Improvement | 10/07/2009 | 10/15/2009 | 12/01/2009 | 409000 | 1.51
1003 | California | SACRAMENTO | SACRAMENTO | 3 | 5475022 | This is a Pavement Resurfacing project by a local agency in the City of Citrus Heights. The project is described as: Fair Oaks Blvd., between Oak Avenue and Old Auburn Road: Minor reconstruction, ove | Pavement Improvement | 09/08/2009 | 09/21/2009 | 12/01/2009 | 1404058 | 1
1004 | California | SACRAMENTO | SACRAMENTO | 3 | 5475024 | This is a Safety project by a local agency in the City of Citrus Heights. The project is described as: Greenback Ln Streetscape: Mariposa-Birdcage | Other | 05/10/2010 |  | 06/01/2010 | 1050028 | 1
1005 | California | ORANGE | MISSION VIEJO | 48 | 5476007 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Laguna Woods. The project is described as: The project involves reconstruction of failed pavement areas, | Pavement Improvement | 10/12/2009 | 10/26/2009 | 06/01/2010 | 500000 | 1.3
1006 | California | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10,11 | 5477003 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakley. The project is described as: Rehabilitate local street | Pavement Improvement | 09/28/2009 | 09/30/2009 | 11/01/2009 | 347491 | 1.3
1007 | California | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10,11 | 5477004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakley. The project is described as: Rehabilitate local street | Pavement Improvement | 09/28/2009 | 09/28/2009 | 11/01/2009 | 294540 | 0.98
1008 | California | ORANGE | MISSION VIEJO | 42 | 5478010 | This is a Pavement Resurfacing project by a local agency in the City of Rancho Santa Margarita. The project is described as: Remove and Replace 3? of asphalt with asphalt rubber hot mix on Alicia Pkw | Pavement Improvement | 04/01/2010 |  | 08/01/2010 | 299291 | 1
1009 | California | SACRAMENTO | SACRAMENTO | 3 | 5479019 | This is a Traffic Management Engineering project by a local agency in the City of Elk Grove. The project is described as: Install ITS components throughout Elk Grove | Safety/Traffic Management | 10/26/2009 | 10/26/2009 | 11/01/2010 | 1000000 | 1
1010 | California | SACRAMENTO | SACRAMENTO | 3 | 5479024 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Elk Grove. The project is described as: Reconstruct I-5 Elk Grove Blvd On-Ramp | Safety/Traffic Management | 09/14/2009 | 09/14/2009 | 07/01/2010 | 187000 | 1
1011 | California | SACRAMENTO | SACRAMENTO | 3 | 5479025 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Elk Grove. The project is described as: Rehabilitate roads in various location in Sacramento County. | Pavement Improvement | 08/28/2009 | 08/28/2009 | 11/01/2009 | 1823001 | 1
1012 | California | SANTA BARBARA | SANTA BARBARA | 23 | 5481007 | This is a Traffic Management Engineering project by a local agency in the City of Goleta. The project is described as: Asphalt overlay (grind and replace) on various FAU streets within the City of Go | Pavement Improvement | 11/19/2009 | 11/23/2009 | 12/01/2009 | 1270736 | 1.7
1013 | California | SACRAMENTO | SACRAMENTO | 3 | 5482007 | This is a New Construction Roadway project by a local agency in the City of Rancho Cordova. The project is described as: International Dr extension and bike/ped bridge | New Construction | 10/20/2009 | 11/03/2009 | 09/01/2011 | 1050000 | 1
1014 | California | SACRAMENTO | SACRAMENTO | 3 | 5482010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rancho Cordova. The project is described as: Coloma Road, from McGregor Dr to Sunrise Blvd: Rehabilitate roa | Pavement Improvement | 07/20/2009 | 08/04/2009 | 02/01/2010 | 1121360 | 1
1015 | California | DEL NORTE |  | 1 | 5901034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: Rehabilitate Oceanview Dr.: Mouth of Smith River Rd. to 1100 ft. S | Pavement Improvement | 08/19/2009 | 08/25/2009 | 10/01/2009 | 245000 | 1.4
1016 | California | DEL NORTE |  | 1 | 5901035 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Del Norte. The project is described as: Improve El Dorado St.: Hamilton Ave. to High School. | Transportation Enhancements | 08/14/2009 | 08/17/2009 | 10/01/2009 | 32000 | 0.19
1017 | California | DEL NORTE |  | 1 | 5901036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: Rehabilitation of Pebble Beach Dr. from Hemlock Ave. to Washington | Pavement Improvement | 08/19/2009 | 08/24/2009 | 10/01/2009 | 200000 | 0.86
1018 | California | DEL NORTE |  | 1 | 5901039 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: El Dorado Street Rehabilitation from Hamilton Ave. to High School | Pavement Improvement | 08/24/2009 | 08/25/2009 | 10/01/2009 | 94000 | 0.19
1019 | California | SISKIYOU |  | 2 | 5902060 | This is a Pavement Resurfacing project by a local agency in the County of Siskiyou. The project is described as: Near Hornbrook Rehab Copco Rd | Pavement Improvement | 08/18/2009 | 08/21/2009 | 11/01/2009 | 1002340 | 3.2
1020 | California | SISKIYOU |  | 2 | 5902061 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Siskiyou. The project is described as: Near Mount Shasta City, along Lake Siskiyou. Construct multi-use tr | Transportation Enhancements | 03/12/2010 |  | 11/01/2010 | 1200000 | 0.1
1021 | California | HUMBOLDT |  | 1 | 5904097 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Rehabilitation and paving | Pavement Improvement | 10/23/2009 | 10/23/2009 | 10/01/2009 | 425795 | 1.02
1022 | California | HUMBOLDT |  | 1 | 5904098 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Rehabilitation and paving | Pavement Improvement | 11/06/2009 |  | 10/01/2009 | 630000 | 0.76
1023 | California | HUMBOLDT |  | 1 | 5904101 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Rehabilitation and paving | Pavement Improvement | 10/06/2009 | 10/06/2009 | 10/01/2009 | 320000 | 0.29
1024 | California | TRINITY |  | 2 | 5905079 | This is a Bridge Rehabilitation, Added Capacity project by a local agency in the County of Trinity. The project is described as: Widen bridge, replace rails, resurface deck, paint. | Bridge Improvement | 01/05/2010 |  | 10/01/2010 | 556248 | 0.3
1025 | California | SHASTA |  | 2 | 5906096 | This is a Pavement Resurfacing project by a local agency in the County of Shasta. The project is described as: 37.7 miles of Preventative Maintenance on major local streets | Pavement Improvement | 07/31/2009 | 09/10/2009 | 12/01/2009 | 2595435 | 42.15
1026 | California | SHASTA | REDDING | 2 | 5906097 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Shasta. The project is described as: Construct East Redding Bike Lanes Phase 1 | Transportation Enhancements | 01/14/2010 |  | 07/01/2010 | 680217 | 2.19
1027 | California | LASSEN |  | 4 | 5907055 | This is a Pavement Resurfacing project by a local agency in the County of Lassen. The project is described as: Asphalt Concrete Overlay and shoulder backing | Pavement Improvement | 09/15/2009 | 09/23/2009 | 11/01/2009 | 777240 | 3.5
1028 | California | TEHAMA |  | 2 | 5908083 | This is a Pavement Resurfacing project by a local agency in the County of Tehama. The project is described as: Overlay of San Benito Avenue | Pavement Improvement | 10/12/2009 | 11/09/2009 | 12/01/2009 | 1170000 | 4.1
1029 | California | MENDOCINO |  | 1 | 5910071 | This is a Pavement Resurfacing project by a local agency in the County of Mendocino. The project is described as: Asphalt Concrete Overlay for designated segment | Pavement Improvement | 05/20/2010 |  | 04/01/2010 | 1900000 | 10.49
1030 | California | BUTTE |  | 2 | 5912082 | This is a Pavement Resurfacing project by a local agency in the County of Butte. The project is described as: Roadway Overlay | Pavement Improvement | 10/19/2009 | 10/05/2009 | 12/01/2009 | 660000 | 3.3
1031 | California | BUTTE |  | 2 | 5912083 | This is a Pavement Resurfacing project by a local agency in the County of Butte. The project is described as: Roadway Overlay | Pavement Improvement | 09/11/2009 | 09/04/2009 | 12/01/2009 | 620000 | 3.3
1032 | California | SIERRA |  | 4 | 5913045 | This is a Scenic or Historic Highway Programs project by a local agency in the County of Sierra. The project is described as: Multimodal travel information facility- visitor center Highway 49 | Transportation Enhancements | 09/28/2009 | 11/04/2009 | 01/01/2010 | 116000 | 0
1033 | California | YUBA |  | 2 | 5916079 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yuba. The project is described as: La Porte Road from Challenge Cutoff Road to west Butte County Line and | Pavement Improvement | 07/01/2009 | 07/16/2009 | 08/01/2009 | 995038 | 1
1034 | California | YUBA |  | 2 | 5916083 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yuba. The project is described as: Rehabilitate various roadways in Yuba County | Pavement Improvement | 10/14/2009 | 11/06/2009 | 10/01/2009 | 1125000 | 1
1035 | California | NEVADA |  | 4 | 5917059 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Nevada. The project is described as: Hirschdale Rd. from I-80 Exit to bridge over Truckee River & Glenshir | Pavement Improvement | 09/21/2009 | 09/21/2009 | 07/01/2010 | 250000 | 1.5
1036 | California | NEVADA |  | 4 | 5917061 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Nevada. The project is described as: Along Penn Valley Dr. - Western Gateway Park to Pleasant Valley Rd./H | Transportation Enhancements | 05/07/2010 |  | 10/01/2010 | 258597 | 0.8
1037 | California | SUTTER |  | 2 | 5918072 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sutter. The project is described as: In Sutter County, rehabilitate various roadways. | Pavement Improvement | 10/19/2009 | 11/16/2009 | 11/01/2009 | 651463 | 1
1038 | California | PLACER |  | 4 | 5919084 | This is a Pavement Resurfacing project by a local agency in the County of Placer. The project is described as: Overlay segments of following roads: Barton Road; Douglas Boulevard; Sierra College Boul | Pavement Improvement | 05/14/2010 |  | 06/01/2010 | 1970962 | 8
1039 | California | PLACER |  | 4 | 5919089 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Placer. The project is described as: Widen Auburn-Folsom Road to four lanes from Placer / Sacramento Count | Pavement Improvement | 12/11/2009 | 01/04/2010 | 10/01/2011 | 2068237 | 6
1040 | California | SONOMA |  | 1,6 | 5920116 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sonoma. The project is described as: Rehabilitate local street | Pavement Improvement | 04/19/2010 |  | 10/01/2010 | 6376000 | 60
1041 | California | NAPA |  | 1 | 5921045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Napa. The project is described as: Rehabilitate local street | Pavement Improvement | 10/19/2009 | 11/09/2009 | 10/01/2009 | 471071 | 3.8
1042 | California | NAPA |  | 1 | 5921046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Napa. The project is described as: Rehabilitate local street | Pavement Improvement | 10/12/2009 | 11/02/2009 | 10/01/2009 | 585917 | 1.1
1043 | California | YOLO | SACRAMENTO | 1,2 | 5922084 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Yolo. The project is described as: Bikeways and rehabilitation: CR 99, 29, 99D | Transportation Enhancements | 08/06/2009 |  | 11/01/2009 | 368568 | 1
1044 | California | YOLO |  | 2 | 5922085 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yolo. The project is described as: Rehabilitate CR 22 Roadway. | Pavement Improvement | 08/19/2009 | 09/17/2009 | 11/01/2009 | 907937 | 1
1045 | California | SOLANO |  | 7,10 | 5923088 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Solano. The project is described as: Rehabilitate local street | Pavement Improvement | 06/25/2009 | 06/29/2009 | 09/01/2009 | 2000000 | 10.4
1046 | California | SOLANO |  | 7,10 | 5923092 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Solano. The project is described as: Construct path, landscaping, historical markers, benches along Cordel | Transportation Enhancements | 01/12/2010 | 02/01/2010 | 11/01/2009 | 800000 | 0.6
1047 | California | SACRAMENTO | SACRAMENTO | 3 | 5924159 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sacramento. The project is described as: In Sacramento County, rehabilitate various roadways. | Pavement Improvement | 08/21/2009 | 09/08/2009 | 10/01/2010 | 10865338 | 1
1048 | California | SACRAMENTO | SACRAMENTO | 3 | 5924161 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Sacramento. The project is described as: ADA sidewalk improvements in Sac. County | Transportation Enhancements | 10/21/2009 | 11/02/2009 | 12/01/2010 | 2973695 | 1
1049 | California | EL DORADO |  | 4 | 5925069 | This is a Pavement Resurfacing project by a local agency in the County of El Dorado. The project is described as: Forni Rd from Ray Lawyer Dr to Placerville Dr: rehabilitate roadways | Pavement Improvement | 08/24/2009 | 08/24/2009 | 10/01/2009 | 633349.32 | 0.7
1050 | California | EL DORADO |  | 4 | 5925071 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of El Dorado. The project is described as: Phase 1B includes reconfig of I/C to a 4-lane tight diamond, const | Transportation Enhancements | 01/19/2010 |  | 09/01/2011 | 5173967 | 1.5
1051 | California | EL DORADO |  | 4 | 5925072 | This is a Pavement Resurfacing project by a local agency in the County of El Dorado. The project is described as: Lotus Rd from Wunschel Ln to State Route 49: rehabilitate roadways | Pavement Improvement | 09/25/2009 | 09/25/2009 | 11/01/2009 | 1717941.85 | 6.57
1052 | California | EL DORADO |  | 4 | 5925073 | This is a Pavement Resurfacing project by a local agency in the County of El Dorado. The project is described as: Malcolm Dixon Rd from Salmon Falls Rd to Green Valley Rd: rehabilitate roadways | Pavement Improvement | 10/06/2009 | 10/06/2009 | 11/01/2009 | 439255 | 2.04
1053 | California | AMADOR |  | 3 | 5926045 | This is a Safety project by a local agency in the County of Amador. The project is described as: Traffic Sign Replacement on various streets throughout the County | Safety/Traffic Management | 02/22/2010 |  | 10/01/2010 | 415881 | 1
1054 | California | MARIN | SAN FRANCISCO-OAKLAND, CA | 6 | 5927068 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Marin. The project is described as: Rehabilitate local street | Pavement Improvement | 10/05/2009 | 10/08/2009 | 12/01/2009 | 1993435 | 3.99
1055 | California | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 7,10 | 5928091 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Contra Costa. The project is described as: Rehabilitate local street | Pavement Improvement | 08/17/2009 | 08/17/2009 | 10/01/2009 | 1945770 | 5.1
1056 | California | SAN JOAQUIN |  | 11 | 5929197 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Resurface roadway between Jack Tone Road and State Route 120 | Pavement Improvement | 10/02/2009 | 10/13/2009 | 12/01/2009 | 892700 | 3.4
1057 | California | SAN JOAQUIN |  | 11 | 5929198 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Resurface roadway between French Camp Road and State Route 120 | Pavement Improvement | 10/12/2009 | 10/30/2009 | 11/01/2009 | 558000 | 2
1058 | California | SAN JOAQUIN |  | 11 | 5929199 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Resurface roadway between Plymouth Road and Alexandria Place | Pavement Improvement | 10/02/2009 | 10/13/2009 | 12/01/2009 | 259100 | 0.6
1059 | California | SAN JOAQUIN | STATEWIDE | 11,18 | 5929200 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Rubberized chip seal of 10 roadways in San Joaquin County | Pavement Improvement | 10/05/2009 | 10/05/2009 | 12/01/2009 | 4168169 | 30
1060 | California | SAN JOAQUIN | STOCKTON | 11 | 5929204 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Joaquin. The project is described as: Rehabilitate roadway between Airport Way and Austin Road | Pavement Improvement | 05/06/2010 |  | 08/01/2010 | 995300 | 4
1061 | California | TUOLUMNE |  | 19 | 5932055 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Tuolumne. The project is described as: County highway J59 Upgrade (HPP project to upgrade existing county | Pavement Improvement | 04/30/2010 |  | 05/01/2010 | 2146000 | 12.5
1062 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9,13 | 5933098 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alameda. The project is described as: Rehabilitate local street | Pavement Improvement | 12/11/2009 |  | 06/01/2010 | 1489903 | 1.65
1063 | California | ALAMEDA | LIVERMORE | 9,13 | 5933099 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alameda. The project is described as: ALTAMONT PASS ROAD- GRANT LN TO LANDFILL ENTR , PAVEMENTS REHAB AND | Pavement Improvement | 10/30/2009 |  | 06/01/2010 | 1200000 | 1.65
1064 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8,12 | 5934147 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 08/19/2009 |  | 02/01/2010 | 1410277 | 0.7
1065 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8,12 | 5934148 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 09/02/2009 |  | 03/01/2010 | 1195042 | 0.63
1066 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8,12 | 5934149 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street/streetscape improvements | Pavement Improvement | 09/14/2009 |  | 09/01/2010 | 2395831 | 0.7
1067 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8,12 | 5934150 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 09/21/2009 |  | 01/01/2010 | 2787467 | 1.2
1068 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8,12 | 5934151 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 08/10/2009 |  | 11/01/2009 | 499662 | 0.08
1069 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8 | 5934152 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 03/01/2010 |  | 04/01/2010 | 2000000 | 0.7
1070 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8,12 | 5934153 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the San Francisco County. The project is described as: Construct ADA compliant curb ramps at various locations | Transportation Enhancements | 02/15/2010 |  | 11/01/2011 | 782592 | 1
1071 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12,14 | 5935054 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Mateo. The project is described as: Rehabilitate local street | Pavement Improvement | 09/25/2009 | 09/29/2009 | 01/01/2010 | 1726000 | 4
1072 | California | SANTA CRUZ | SANTA CRUZ | 17 | 5936076 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Cruz. The project is described as: Road repairs: various roadways | Pavement Improvement | 07/21/2009 | 07/22/2009 | 11/01/2009 | 2132932 | 4.8
1073 | California | SANTA CLARA | SAN JOSE, CA | 11,14,15,16 | 5937132 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Clara. The project is described as: Rehabilitate local street | Pavement Improvement | 07/14/2009 |  | 12/01/2009 | 2684000 | 2.7
1074 | California | SANTA CLARA | SAN JOSE, CA | 11,14,15,16 | 5937133 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Clara. The project is described as: Rehabilitate local street | Pavement Improvement | 08/25/2009 | 09/08/2009 | 12/01/2009 | 959000 | 2.33
1075 | California | MERCED | MERCED | 18 | 5939066 | This is a Pavement Resurfacing project by a local agency in the County of Stanislaus. The project is described as: Various locations | Pavement Improvement | 05/18/2010 |  | 07/01/2010 | 1093567 | 20.4
1076 | California | MADERA |  | 19 | 5941072 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Madera. The project is described as: Avenue 15 - Road 29 to Road 35 alignment | Pavement Improvement | 10/21/2009 | 10/28/2009 | 12/01/2009 | 1868824 | 6
1077 | California | FRESNO | FRESNO | 20 | 5942178 | This is a Pavement Resurfacing project by a local agency in the County of Fresno. The project is described as: AC Overlays on Cedar Avenue btwn Mt. Whitney/Elkhorn, Annadale Ave btwn Riverbend(S)/1.3 | Pavement Improvement | 04/30/2010 |  | 07/01/2010 | 3056173 | 10
1078 | California | SAN BENITO |  | 17 | 5943048 | This is a Pavement Resurfacing project by a local agency in the County of San Benito. The project is described as: On Southside Road from Union Road to Southside Bridge, Roadway Rehabilitation. | Pavement Improvement | 09/08/2009 | 09/28/2009 | 12/01/2009 | 851092 | 3
1079 | California | SAN BENITO |  | 17 | 5943049 | This is a Pavement Resurfacing project by a local agency in the County of San Benito. The project is described as: In San Benito County, on Fairview Road from SR 25 to SR 156. | Pavement Improvement | 04/23/2010 |  | 08/01/2010 | 220000 | 1
1080 | California | SAN BENITO |  | 17 | 5943050 | This is a Pavement Resurfacing project by a local agency in the County of San Benito. The project is described as: In San Benito County, on Union Road from SR 25 to SR 156. | Pavement Improvement | 04/23/2010 |  | 08/01/2010 | 155000 | 1
1081 | California | MONTEREY | SEASIDE-MONTEREY | 17 | 5944095 | This is a Pavement Resurfacing project by a local agency in the County of Monterey. The project is described as: Overlay Espinosa Road between MP .04 and MP 4.72 | Safety/Traffic Management | 08/10/2009 | 08/14/2009 | 12/01/2009 | 2108638 | 4.68
1082 | California | INYO |  | 25 | 5948069 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the County of Inyo. The project is described as: Reconstruct approx 0.5 mi of Barlow and 0.1 miles of Saniger install | Pavement Improvement | 10/01/2009 | 10/06/2009 | 12/01/2009 | 988558 | 2.9
1083 | California | KERN | BAKERSFIELD | 20 | 5950308 | This is a Pavement Resurfacing project by a local agency in the County of Kern. The project is described as: Lerdo Highway: Wildwood Rd to CL (Poplar Ave); Resurfacing, Rehabilitation | Pavement Improvement | 01/05/2010 | 02/02/2010 | 01/01/2010 | 1200000 | 8.1
1084 | California | KERN |  | 22 | 5950310 | This is a Pavement Resurfacing project by a local agency in the County of Kern. The project is described as: Garlock Rd: State Route 395 to 5 miles west; Resurfacing, Rehabilitation | Pavement Improvement | 11/05/2009 |  | 03/01/2010 | 1600000 | 5
1085 | California | KERN |  | 20 | 5950312 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Kern. The project is described as: King Rd: Twisselman Road to County Line Rd; Resurfacing, Rehabilitation | Pavement Improvement | 11/05/2009 | 12/04/2009 | 12/01/2009 | 1200000 | 4.5
1086 | California | SANTA BARBARA |  | 23,24 | 5951124 | This is a Pavement Resurfacing project by a local agency in the County of Santa Barbara. The project is described as: AC Overlay Various Streets and Roads | Pavement Improvement | 06/24/2009 | 07/06/2009 | 12/01/2009 | 1522082.76 | 5
1087 | California | SANTA BARBARA |  | 23,24 | 5951125 | This is a Bridge Rehabilitation, No Added Capacity project by a local agency in the County of Santa Barbara. The project is described as: Seal Cracks in the Bridge decks in Santa Barbara County | Bridge Improvement | 06/24/2009 | 07/13/2009 | 11/01/2009 | 341155 | 1
1088 | California | SANTA BARBARA |  | 23,24 | 5951126 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Barbara. The project is described as: Concrete Sidewalk Installation and Repairs - Various Streets a | Transportation Enhancements | 06/24/2009 | 08/03/2009 | 12/01/2009 | 606000 | 1
1089 | California | SANTA BARBARA |  | 23 | 5951128 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Santa Barbara. The project is described as: Streetscape repair and installation of circulation improvement | Transportation Enhancements | 01/08/2010 |  | 03/01/2010 | 454837 | 1
1090 | California | SANTA BARBARA |  | 24 | 5951130 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Santa Barbara. The project is described as: Streetscape repair and installation of circulation improvement | Transportation Enhancements | 04/16/2010 |  | 05/01/2010 | 300000 | 1
1091 | California | SANTA BARBARA |  | 24 | 5951131 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Santa Barbara. The project is described as: Streetscape repair and installation of circulation improvement | Transportation Enhancements | 02/19/2010 |  | 09/01/2010 | 1330000 | 6
1092 | California | SANTA BARBARA |  | 23 | 5951132 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Barbara. The project is described as: Road Rehabilitation/surface treatment on various roads | Pavement Improvement | 12/08/2009 | 01/04/2010 | 06/01/2010 | 615938 | 1.2
1093 | California | VENTURA | OXNARD-VENTURA | 23,24 | 5952134 | This is a Safety project by a local agency in the County of Ventura. The project is described as: Add new through right-turn lane in both directions on Rose; add new left-turn lane on Rose SB; length | Pavement Widening | 07/20/2009 | 07/10/2009 | 10/01/2009 | 210000 | 0.13
1094 | California | VENTURA | OXNARD-VENTURA | 23,24 | 5952135 | This is a Bridge Rehabilitation, No Added Capacity project by a local agency in the County of Ventura. The project is described as: Bridge Deck Rehab. Various Locations | Pavement Improvement | 07/29/2009 | 07/14/2009 | 10/01/2009 | 487273.54 | 0.24
1095 | California | VENTURA | OXNARD-VENTURA | 24 | 5952138 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Ventura. The project is described as: High Priority on system roads, various locations | Pavement Improvement | 07/10/2009 | 07/10/2009 | 10/01/2009 | 1658662.49 | 4.98
1096 | California | VENTURA | OXNARD-VENTURA | 50 | 5952139 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Ventura. The project is described as: On system roads - Phase A various locations | Pavement Improvement | 08/13/2009 | 08/07/2009 | 11/01/2009 | 2335171 | 10.34
1097 | California | VENTURA | OXNARD-VENTURA | 23,24 | 5952143 | This is a Landscaping and Other Scenic Beautification project by a local agency in the County of Ventura. The project is described as: Pavement Rehabilitation of Katherine Road | Pavement Improvement | 02/23/2010 |  | 08/01/2010 | 280000 | 1.06
1098 | California | LOS ANGELES | LOS ANGELES, CA | 36,38 | 5953595 | This is a Traffic Management Engineering project by a local agency in the County of Los Angeles. The project is described as: TRAFFIC SIGNAL UPGRADES AT WHITTIER BOULEVARD ET. AL. | Safety/Traffic Management | 10/06/2009 | 10/13/2009 | 03/01/2010 | 206821 | 1
1099 | California | LOS ANGELES | LOS ANGELES, CA | 38,42 | 5953596 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: COLIMA RD, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 04/12/2010 |  | 01/01/2011 | 2945874 | 7.36
1100 | California | LOS ANGELES |  | 25 | 5953597 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: ANGELES FOREST HIGHWAY, ET AL. FOR LOS ANGELES COUNTY FAS FUNDS | Pavement Improvement | 04/15/2010 |  | 07/01/2010 | 2655815 | 8.01
1101 | California | LOS ANGELES | LOS ANGELES, CA | 30 | 5953600 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: MULHOLLAND HIGHWAY, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 04/15/2010 |  | 08/01/2010 | 7715128 | 22.5
1102 | California | LOS ANGELES | LOS ANGELES, CA | 39 | 5953603 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: WASHINGTON BL, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 09/18/2009 | 10/30/2009 | 03/01/2010 | 343157 | 0.74
1103 | California | LOS ANGELES | LOS ANGELES, CA | 32,38 | 5953604 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: GRAVES AV, ET AL. - ROADWAY RESURFACING PROJECT | Pavement Improvement | 10/29/2009 | 01/25/2010 | 03/01/2011 | 611989 | 0.85
1104 | California | LOS ANGELES | LANCASTER | 25 | 5953605 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: AVENUE G, ET AL; FOR LOS ANGELES COUNTY FAS FUNDS (PRIORITY #2 F | Pavement Improvement | 04/15/2010 |  | 11/01/2010 | 4694810 | 18.2
1105 | California | LOS ANGELES | LOS ANGELES, CA | 32,38,39 | 5953610 | This is a Safety project by a local agency in the County of Los Angeles. The project is described as: REIS ET AL- BRIDGE BARRIER RAIL REPLACEMENT PROJECT | Bridge Improvement | 11/09/2009 | 01/04/2010 | 05/01/2010 | 229477 | 1
1106 | California | LOS ANGELES |  | 25 | 5953612 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: AVENUE N, ET AL, ROADWAY RESURFACING PROJECT FOR LOS ANGELES COUNTY FAS FUNDS (PRIO | Pavement Improvement | 04/15/2010 |  | 11/01/2010 | 3825347 | 11.97
1107 | California | LOS ANGELES |  | 22 | 5953614 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: GORMAN POST RD, ET AL ROADWAY RESURFACING PROJECT | Pavement Improvement | 04/15/2010 |  | 10/01/2010 | 2755729 | 7.33
1108 | California | LOS ANGELES | LOS ANGELES, CA | 34 | 5953617 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: FIRESTONE BL, ET AL ROADWAY RESURFACING | Pavement Improvement | 11/18/2009 |  | 05/01/2010 | 1713500 | 2.63
1109 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5953618 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: 120TH ST, ET AL; ROADWAY RESURFACING PROJECT | Pavement Improvement | 11/05/2009 | 11/30/2009 | 03/01/2010 | 179041 | 0.27
1110 | California | LOS ANGELES | LOS ANGELES, CA | 37 | 5953619 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: EL SEGUNDO BLVD ET AL. - ROADWAY RESURFACING | Pavement Improvement | 11/05/2009 |  | 04/01/2010 | 760438 | 1.42
1111 | California | LOS ANGELES | LOS ANGELES, CA | 35 | 5953620 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: CRENSHAW BL, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 11/05/2009 |  | 06/01/2010 | 726800 | 1.37
1112 | California | LOS ANGELES | LOS ANGELES, CA | 29 | 5953624 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Los Angeles. The project is described as: Los Angeles River Bike Trail Et Al. (TEA Priority No. 1) | Transportation Enhancements | 02/18/2010 |  | 08/01/2010 | 846465 | 1
1113 | California | LOS ANGELES | LOS ANGELES, CA | 32,38,39,40 | 5953625 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: EMERALD NECKLACE REHABILITATION | Transportation Enhancements | 01/04/2010 |  | 08/01/2010 | 2079200 | 34.62
1114 | California | LOS ANGELES | LOS ANGELES, CA | 28,30,33,34,35,36,37,38,39,46 | 5953626 | This is a Traffic Management Engineering project by a local agency in the County of Los Angeles. The project is described as: TRAFFIC SIGNAL LED INDICATION AND MASS ARM STREET NAME SIGN UPGRADE - PHA | Other | 10/29/2009 |  | 03/01/2011 | 2815738 | 1
1115 | California | LOS ANGELES | LOS ANGELES, CA | 26,29,32,34,38,39,42 | 5953627 | This is a Traffic Management Engineering project by a local agency in the County of Los Angeles. The project is described as: TRAFFIC SIGNAL LED INDICATION AND MASS ARM STREET NAME SIGN UPGRADE - PHA | Other | 10/29/2009 |  | 03/01/2011 | 2861283 | 1
1116 | California | LOS ANGELES | LOS ANGELES, CA | 26 | 5953631 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: Rosemead Bl-Foothill Bl/566 S/o Ardendale Av (Temple City Bounda | Pavement Improvement | 10/13/2009 | 01/11/2010 | 10/01/2011 | 8188693 | 2.1
1117 | California | ORANGE | LOS ANGELES, CA | 48 | 5955068 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Orange. The project is described as: Pavement Rehabilitation of Newport Avenue - Wass St to Hyde Pk Dr | Pavement Improvement | 05/20/2010 |  | 06/01/2010 | 1837401 | 1.86
1118 | California | RIVERSIDE | INDIA-COACHELLA | 45 | 5956179 | This is a Bridge Rehabilitation, Added Capacity project by a local agency in the County of Riverside. The project is described as: Reconstruct ramps and widen overcrossing | Pavement Widening | 02/26/2010 |  | 05/01/2012 | 10415000 | 0.8
1119 | California | RIVERSIDE | SAN BERNARDINO-RIVERSIDE | 44 | 5956187 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Riverside. The project is described as: Ramp modifications | New Construction | 02/19/2010 |  | 12/01/2010 | 3915396 | 0.8
1120 | California | SAN BERNARDINO | STATEWIDE | 43 | 6053080 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of San Bernardino. The project is described as: HOV and lane addition to relieve traffic congestion | Safety/Traffic Management | 10/01/2009 |  | 09/01/2013 | 128116032 | 2.5
1121 | California | SAN DIEGO | SAN DIEGO, CA | 52 | 6066067 | This is a Transit project by a local agency in the City of San Diego. The project is described as: Pedestrian/disabled user facility improvements | Transportation Enhancements | 01/25/2010 |  | 11/01/2011 | 4002427 | 0
1122 | California | SANTA CRUZ | SANTA CRUZ | 17 | 6149062 | This is a Traffic Management Engineering project by a local agency in the County of Santa Cruz. The project is described as: Motorist aide tow trucks to remove incidents. | Safety/Traffic Management | 07/13/2009 | 07/13/2009 | 02/01/2011 | 180000 | 7.03
1123 | California | SANTA CLARA | SAN JOSE, CA | 14,15,16 | 6264044 | This is a Traffic Management Engineering project by a local agency in the County of Santa Clara. The project is described as: The SR 85 Express Lanes project would convert the existing continuous car | Other | 12/04/2009 |  | 07/01/2014 | 3300000 | 24.06
1124 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8 | 6328029 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of San Francisco. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 03/18/2010 |  | 06/01/2011 | 243760 | 1
1125 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8 | 6328030 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of San Francisco. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 02/22/2010 |  | 06/01/2011 | 296197 | 1
1126 | California | SAN DIEGO | SAN DIEGO, CA | 50 | 8051608 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Chula Vista, from north of H Street to north of Route 54; als | Pavement Improvement | 07/24/2009 | 10/05/2009 | 08/01/2010 | 8525838 | 0.9
1127 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9 | 8801058 | This is a Bridge Rehabilitation, No Added Capacity project by the California Department of Transportation. The project is described as: In Oakland, at Fruitvale Avenue Bridge #33-0041. | Pavement Improvement | 06/25/2009 | 07/20/2009 | 06/01/2012 | 9412019 | 0.3
1128 | California | SAN DIEGO | SAN DIEGO, CA | 51 | A905019 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: From I-805 to Otay Mesa Port of Entry | Pavement Widening | 05/08/2009 | 07/01/2009 | 09/01/2012 | 73930886 | 3.4
1129 | California | SONOMA |  | 6 | P001540 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Sonoma County near Fort Ross, from 2.5 miles south of Fort Ross Road to Timber C | Pavement Improvement | 09/10/2009 | 09/11/2009 | 09/01/2010 | 524169 | 7.9
1130 | California | ORANGE | LOS ANGELES, CA | 48 | P001541 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in and near Laguna Beach, from Dana Point/Laguna Beach City limits | Pavement Improvement | 06/12/2009 | 09/09/2009 | 06/01/2010 | 2309355 | 9.5
1131 | California | KERN |  | 22 | P014065 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Kern County near Mojave, from South Junction State Route 58 to 5 miles north of | Pavement Improvement | 06/28/2009 | 07/02/2009 | 10/01/2009 | 5129627 | 24.5
1132 | California | SAN BERNARDINO |  | 41 | P018037 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County, from 0.1 mile west of Route 18/330 Separation to Lakeview | Pavement Improvement | 06/25/2009 | 07/24/2009 | 12/01/2009 | 1360611 | 7.5
1133 | California | SAN BERNARDINO |  | 41 | P018038 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County near Big Bear City, from Snubbing Post Grade Road to 0.6 m | Pavement Improvement | 06/23/2009 | 06/19/2009 | 12/01/2009 | 859022 | 10
1134 | California | SAN BERNARDINO |  | 41 | P018039 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Lucerne Valley, at Cushenbury Creek Bridge #54-394. | Pavement Improvement | 10/12/2009 | 12/01/2009 | 08/01/2011 | 4135127 | 0.7
1135 | California | COLUSA |  | 2 | P020150 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In Williams, from 0.3 mile east to 0.6 mile west of Route 5. | Pavement Improvement | 09/02/2009 | 10/06/2009 | 10/01/2010 | 7088950 | 0.9
1136 | California | YUBA |  | 2 | P020151 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Yuba County near Marysville, from 0.2 miles west of Spring Valley Road to 0.1 mi | Pavement Improvement | 07/22/2009 | 08/13/2009 | 10/01/2010 | 1227430 | 3.2
1137 | California | ALAMEDA, CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 9 | P024030 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: Construct a 2-lane tunnel | Pavement Improvement | 11/20/2009 | 01/13/2010 | 05/01/2014 | 192357000 | 2.2
1138 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9 | P024031 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Realignment of WB Rte 24 to NB Rte 13 | Pavement Improvement | 01/20/2010 |  | 07/01/2010 | 3272686 | 0.1
1139 | California | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 9 | P024032 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Widening and signalization at Kay Street | Pavement Improvement | 01/27/2010 |  | 02/01/2010 | 546921 | 0.1
1140 | California | NAPA |  | 1 | P029105 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Napa County near Calistoga, from 0.2 miles north of Silverado Trail to Lake Coun | Pavement Improvement | 07/21/2009 | 08/17/2009 | 06/01/2010 | 673891 | 10.5
1141 | California | MERCED |  | 18 | P033068 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Merced County in and near Dos Palos, from Fresno County Line to State Route 152; | Pavement Improvement | 06/25/2009 | 07/10/2009 | 12/01/2009 | 1182595 | 19.9
1142 | California | VENTURA | OXNARD-VENTURA | 37 | P034004 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Ventura County in and near Camarillo, from Daily Drive to State Route 118. | Pavement Improvement | 06/26/2009 | 07/12/2009 | 05/01/2011 | 1436883 | 4
1143 | California | PLUMAS |  | 4 | P036086 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Plumas County about 6 miles east of Chester, from 0.8 mile west to 1.2 miles eas | Pavement Improvement | 06/12/2009 | 08/15/2009 | 12/01/2010 | 1739616 | 1.7
1144 | California | ORANGE | LOS ANGELES, CA | 39 | P039021 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In La Habra, from Route 90 to Los Angeles County Line; also on R | Pavement Improvement | 07/17/2009 | 09/21/2009 | 07/01/2011 | 5634488 | 4
1145 | California | FRESNO | FRESNO | 20,21 | P041110 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In Fresno - At McKinley Avenue and Shields Avenue | Pavement Improvement | 08/11/2009 |  | 11/01/2011 | 2954313 | 1.4
1146 | California | SHASTA |  | 2 | P044045 | This is a Safety project by the California Department of Transportation. The project is described as: Near Viola from 2.5 to 1.1 miles west of the Lassen Park entrance. Realign curve, widen shoulder | Safety/Traffic Management | 02/03/2010 |  | 01/01/2012 | 5726722 | 1.4
1147 | California | SAN LUIS OBISPO |  | 22 | P046042 | This is a Safety project by the California Department of Transportation. The project is described as: Near Shandon - at the Shandon Rest Area - rehabilitate Safety Roadside Rest Area | Safety/Traffic Management | 08/12/2009 | 10/06/2009 | 03/01/2012 | 4730488 | 0
1148 | California | EL DORADO |  | 4 | P049143 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near El Dorado, from Ore Court Road to China Hill Road. | Pavement Improvement | 06/26/2009 | 07/07/2009 | 09/01/2011 | 6868710 | 1
1149 | California | SIERRA |  | 4 | P049144 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Sierra County on State Route 49 near Sierraville and Loyalton, from South Juncti | Pavement Improvement | 07/09/2009 | 07/27/2009 | 07/20/2009 | 901956 | 17
1150 | California | TUOLUMNE |  | 4 | P049145 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Tuolumne County in and near Sonora, from 0.2 mile south of Pesce Way to Calavera | Pavement Improvement | 07/02/2009 | 07/20/2009 | 12/01/2009 | 1274809 | 9.1
1151 | California | ORANGE | LOS ANGELES, CA | 39,47 | P057053 | This is a Safety project by the California Department of Transportation. The project is described as: In Orange, Anaheim and Fullerton, from West Orangewood Avenue to the Los Angeles County line at v | Pavement Improvement | 08/09/2009 | 08/05/2009 | 07/01/2011 | 2968914 | 11
1152 | California | SAN BERNARDINO |  | 41 | P062026 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County, from 4.9 miles west to 0.9 miles west of Rio Mesa Drive. | Pavement Improvement | 06/19/2009 | 08/14/2009 | 12/01/2009 | 903988 | 4
1153 | California | ORANGE | LOS ANGELES, CA | 48 | P073086 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in Laguna Niguel, Laguna Hills, Aliso Viejo, Laguna Beach and Irvi | Pavement Improvement | 08/05/2009 | 08/19/2009 | 12/01/2010 | 8790626 | 12.5
1154 | California | SAN DIEGO | SAN DIEGO, CA | 49 | P076024 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: CONSTRUCT 4-LANE HIGHWAY | Pavement Widening | 01/21/2010 |  | 12/01/2013 | 75612901 | 5.8
1155 | California | RIVERSIDE |  | 45 | P078108 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Palo Verde, on 32nd Avenue west of South Randalls Avenue Brid | Pavement Improvement | 08/04/2009 | 09/17/2009 | 05/01/2011 | 1608437 | 0.2
1156 | California | AMADOR | STOCKTON | 4 | P088052 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Amador County in and near Barton, from 0.1 mile west of Wagon Wheel Drive to 0.1 | Pavement Improvement | 06/25/2009 | 07/06/2009 | 12/01/2009 | 995691 | 5.7
1157 | California | AMADOR |  | 4 | P088053 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Amador County near Plasse, from 2 miles west of Tragedy Springs Road to 0.3 mile | Pavement Improvement | 07/10/2009 | 07/10/2009 | 12/01/2009 | 490501 | 6.1
1158 | California | EL DORADO |  | 4 | P089094 | This is a Mitigation of Water Pollution due to Highway Runoff project by the California Department of Transportation. The project is described as: Near Meyers, from Alpine County Line to Route 50. | Pavement Improvement | 07/01/2009 | 09/01/2009 | 01/01/2011 | 16425073 | 8.6
1159 | California | ORANGE | LOS ANGELES, CA | 42 | P090011 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in Brea and Placentia, from Randolph Avenue to 0.1 mile east of Ro | Pavement Improvement | 06/19/2009 | 07/08/2009 | 06/01/2010 | 1768825 | 3
1160 | California | RIVERSIDE, ORANGE | LOS ANGELES, CA | 42,44 | P091127 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Orange County add one lane on eastbound SR-91 from SR-241 to | Pavement Improvement | 09/16/2009 | 11/10/2009 | 11/01/2011 | 47887635 | 5.9
1161 | California | RIVERSIDE |  | 45 | P095020 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: Near Blythe, from 0.4 mile north of Wiley Hill Log Cabin to 0 | Pavement Improvement | 06/26/2009 | 07/12/2009 | 02/01/2010 | 2639700 | 8.3
1162 | California | BUTTE |  | 2,4 | P099519 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: SR 99 Near Biggs - Rio Bonito to SR 162. | Pavement Improvement | 07/07/2009 | 08/01/2009 | 01/01/2011 | 11436484 | 4.6
1163 | California | SUTTER |  | 2 | P099520 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Sutter County, SR 99 near East Nicholas, from Sacramento County | Pavement Improvement | 06/12/2009 | 07/06/2009 | 10/01/2010 | 12195645 | 8.7
1164 | California | MERCED | MERCED | 18 | P099521 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: In Merced County, from north of V Street to Black Rascal Bridge #3 | Pavement Improvement | 10/08/2009 | 10/22/2009 | 04/01/2012 | 29805432 | 1.5
1165 | California | LOS ANGELES | LOS ANGELES, CA | 29 | P134035 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Los Angeles County in Burbank, Glendale and Los Angeles, from Bob Hope Drive Und | Pavement Improvement | 08/06/2009 | 09/03/2009 | 05/01/2011 | 1511500 | 6.4
1166 | California | LASSEN |  | 4 | P139019 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Lassen County about 40 miles north of Susanville, from 7.0 miles north of CDF Fi | Pavement Improvement | 07/14/2009 | 07/27/2009 | 12/01/2010 | 1555196 | 13
1167 | California | MADERA |  | 18,19 | P145029 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: Near Madera, from Avenue 5 1/2 to Avenue 11 1/2. | Pavement Improvement | 06/20/2009 | 06/20/2009 | 05/01/2011 | 10674715 | 6.1
1168 | California | FRESNO |  | 21 | P180053 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near Centerville, from Temperance Avenue to Academy Avenue (Qual | Pavement Improvement | 09/21/2009 | 11/30/2009 | 05/01/2012 | 18369261 | 6.2
1169 | California | MENDOCINO |  | 1 | P222001 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Ukiah, at Russian River Bridge #10-80. | Bridge Replacement | 06/29/2009 | 10/15/2009 | 09/01/2012 | 7903106 | 0.01
1170 | California | RIVERSIDE |  | 45 | P243002 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Riverside County near Idyllwild, from 1.1 miles north of State Routes 74/243 Sep | Pavement Improvement | 07/15/2009 | 07/29/2009 | 12/01/2009 | 1933265 | 12.2
1171 | California | MODOC |  | 4 | P395224 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Modoc County near Alturas, from the Lassen/Modoc County Line to Alturas Overhead | Pavement Improvement | 07/17/2009 | 08/13/2009 | 12/01/2010 | 2358462 | 20.8
1172 | California | SAN BERNARDINO |  | 25 | P395225 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County on US Highway 395 near Kramer Junction, from Federal Priso | Pavement Improvement | 06/26/2009 | 07/10/2009 | 12/01/2009 | 1530677 | 6
1173 | California | MONO |  | 25 | P395226 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Mono County near Hilton Creek, from 0.1 mile north of Crooked Creek Bridge to 0. | Pavement Improvement | 07/03/2009 | 07/23/2009 | 12/01/2009 | 3273458 | 23.5
1174 | California | LOS ANGELES | LOS ANGELES, CA | 34,39 | P710014 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Los Angeles from 0.3 mile south of Firestone Blvd to 0.2 mile | Pavement Improvement | 09/22/2009 | 11/16/2009 | 01/01/2014 | 52602457 | 2.7
1175 | California | MONTEREY |  | 17 | Q101151 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near Salinas, from Central Avenue to Gould Avenue at various loc | Pavement Improvement | 08/14/2009 | 08/31/2009 | 07/01/2010 | 5942549 | 36.9
1176 | California | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 4 | Q101152 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Mateo County in South San Francisco and Brisbane, from Oyster Point Boulevar | Pavement Improvement | 08/14/2009 | 08/19/2009 | 12/01/2010 | 3134512 | 3.1
1177 | California | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 8 | Q101153 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In the City and County of San Francisco on Route 101, Doyle | Pavement Improvement | 04/13/2010 |  | 08/01/2013 | 83281437 | 1.8
1178 | California | MARIN | STATEWIDE | 6 | Q101155 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Construct HOV lanes and bike path | Transportation Enhancements | 10/16/2007 | 08/05/2007 | 10/01/2009 | 2401200 | 1.86
1179 | California | SAN LUIS OBISPO |  | 22 | Q101159 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In and near Atascadero, from Cuesta Grade overhead to north of T | Pavement Improvement | 01/26/2010 |  | 07/01/2012 | 36678522 | 10.6
1180 | California | SANTA CLARA |  | 10,14 | S035007 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Santa Clara County near Los Gatos, from Black Road to the State Route 35 separat | Pavement Improvement | 07/21/2009 | 08/19/2009 | 09/01/2010 | 1421222 | 6.42
1181 | California | KERN | BAKERSFIELD | 22 | S204004 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: In Bakersfield, at Chester Avenue Bridge #50-183. | Bridge Replacement | 07/03/2009 | 08/24/2009 | 08/01/2012 | 15231775 | 1
1182 | California | FRESNO |  | 20 | X019021 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Fresno County on Route 33 near Harris Ranch, from I-5 to 1.7 miles north of Harl | Pavement Improvement | 06/18/2009 | 07/06/2009 | 10/01/2009 | 1519610 | 1
1183 | California | VENTURA, LOS ANGELES |  | 23,24 | X037145 | This is a Safety project by the California Department of Transportation. The project is described as: In Ventura County in and near Oxnard from Wood Road to Mobil Pier Road and in routes 23,33,101,11 | Safety/Traffic Management | 10/15/2009 | 01/01/2010 | 12/01/2011 | 1197345 | 1
1184 | California | LOS ANGELES | LOS ANGELES, CA | 30 | X037146 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles County in Santa Monica from Lincoln Blvd to Palasades pedestrian overcrossing and | Safety/Traffic Management | 10/15/2009 | 11/09/2009 | 07/01/2011 | 1343812 | 1
1185 | California | LOS ANGELES | LOS ANGELES, CA | 34,38,39 | X037147 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles County from Santa Fe Springs to Los Angeles from Valley-View Avenue to Soto Street | Safety/Traffic Management | 09/01/2009 |  | 08/01/2011 | 1472796 | 1
1186 | California | LOS ANGELES | LOS ANGELES, CA | 35,66,37 | X037148 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles and Long Beach, on various routes. | Safety/Traffic Management | 09/01/2009 | 10/17/2009 | 07/01/2011 | 1136232 | 1
1187 | California | MONTEREY |  | 17 | X053022 | This is a Safety project by the California Department of Transportation. The project is described as: Pacific Grove to Castroville, south of Route 1 to Tembladero Slough; also on Route 68 east of Fai | Safety/Traffic Management | 06/29/2009 | 06/29/2009 | 07/01/2010 | 1872022 | 17.1
1188 | Colorado | ADAMS | DENVER, CO | 7 | 002A003 | Resurfaces 2.4 miles of SH 2 from Vasquez to Quebec, adds curb ramps and safety improvements | Pavement Improvement | 04/23/2010 |  |  | 1619093 | 2.485
1189 | Colorado | WASHINGTON |  | 4 | 0061080 | Resurfaces over 9 miles of SH 6 in Washington and Logan Counties | Pavement Improvement | 03/16/2010 |  |  | 4138187 | 9.48
1190 | Colorado | MESA |  | 3 | 0063031 | Enhancement Project: constructs bike and pedestrian trail in Fruita along US 6 | Transportation Enhancements | 09/21/2009 | 09/21/2009 | 01/04/2010 | 433399 | 0.63
1191 | Colorado | EAGLE |  | 2 | 006A043 | Enhancement Project: constructs bike and pedestrian trail to connect Town of Minutrn to Dowd Junction ECO trail | Transportation Enhancements | 09/21/2009 | 09/22/2009 | 11/10/2009 | 282396 | 0.42
1192 | Colorado | SUMMIT |  | 2 | 0091032 | Widens SH 9 to two lanes in each direction and constructs a new pedestrian bridge and a retaining wall. The project will also relocate a bike path and improve drainage north of Breckenridge in Summit | Pavement Widening | 06/04/2009 | 06/04/2009 | 01/07/2010 | 8994331 | 1.55
1193 | Colorado | RIO BLANCO |  | 3 | 0131055 | Reconstructs five miles of SH 13 in asphalt, adds eight-foot shoulders and climbing and passing lanes at Rio Blanco Hill in Rio Blanco County. The improvements will enhance recreational bicycling in t | Pavement Widening | 07/17/2009 | 07/17/2009 | 10/01/2010 | 10439448 | 5.29
1194 | Colorado | JACKSON |  | 03,04 | 0141020 | Asphalt resurfacing of SH 14 east and est of Cameron Pass in Larimer and Jackson counties. | Pavement Improvement | 06/04/2009 | 06/09/2009 | 12/05/2009 | 5432563 | 13.39
1195 | Colorado | JACKSON |  | 3 | 0141021 | Resurfaces and repairs shoulder on 23 miles of SH 14 east of Muddy Pass. | Pavement Improvement | 04/06/2010 |  | 10/31/2010 | 6337976 | 23
1196 | Colorado | CHAFFEE |  | 5 | 0242045 | Resurfaces 12.5 miles of US 24/US 285, north of Johnson Village in Chaffee County, in asphalt. | Pavement Improvement | 05/19/2009 | 07/13/2009 | 11/02/2009 | 3714986 | 12.68
1197 | Colorado | EL PASO |  | 5 | 0243076 | Replaces a structurally deficient bridge over Falcon Creek in Falcon in El Paso County and improves drainage. | Bridge Replacement | 09/16/2009 | 09/16/2009 | 06/23/2010 | 3378144 | 0.8
1198 | Colorado | ELBERT |  | 04,06 | 0243079 | Resurfaces 11 miles of SH 24 west of Limon. | Safety/Traffic Management | 02/26/2010 | 02/26/2010 |  | 6138156 | 11.03
1199 | Colorado | LAS ANIMAS | PUEBLO | 3 | 0251335 | Constructs the Purgatoire River Pedestrian Trail, adds street lights, parking lot paving, curb and gutter, drainage inlets, landscaping and sidewalk along I-25 in Trinidad. | Pavement Improvement | 06/16/2009 | 05/29/2009 | 07/03/2011 | 6572326 | 3
1200 | Colorado | DENVER | DENVER, CO | 1 | 0252402 | Resurfaces approximately three miles of I-25 in Denver from 6th Avenue to 23rd Avenue, in asphalt. | Pavement Improvement | 04/28/2009 | 06/14/2009 | 11/01/2009 | 3436919 | 2
1201 | Colorado | LARIMER | FORT COLLINS | 4 | 0253206 | Improves five miles of roadway surface on I-25 from the Crossroads Interchange at Loveland to SH 392, the Windsor Interchange. | Pavement Improvement | 07/01/2009 | 07/05/2009 | 11/29/2009 | 4727746 | 4.012
1202 | Colorado | LARIMER | FORT COLLINS | 4 | 0253207 | Constructs roundabouts on Crossroads at the I-25 and Crossroads, Loveland interchange to improve mobility and safety. | Safety/Traffic Management | 08/31/2009 | 08/31/2009 | 08/31/2010 | 3000000 | 0.95
1203 | Colorado | WELD |  | 4 | 0342050 | Installs a traffic signal at the intersection of US 34 and Weld County Road 49, west of Kersey. | Safety/Traffic Management | 08/03/2009 | 08/08/2009 |  | 381589 | 0.2
1204 | Colorado | WASHINGTON |  | 4 | 0343030 | Resurfaces 15 miles of SH 34 from Brush to Akron with chipseal. | Pavement Improvement | 02/03/2010 |  |  | 1669000 | 15.2
1205 | Colorado | LARIMER |  | 02,04 | 0361089 | Chip seals 22 miles of US 36 between Lyons and Estes Park to improve the roadway surface condition. | Pavement Improvement | 06/22/2009 | 07/20/2009 | 08/24/2009 | 1472104 | 21.77
1206 | Colorado | BOULDER | BOULDER | 2 | 0361090 | Installs a new traffic signal at the intersection of US 36 and Broadway in Boulder. | Safety/Traffic Management | 07/02/2009 | 08/03/2009 | 10/12/2009 | 352365 | 0.27
1207 | Colorado | LINCOLN | DENVER, CO | 4 | 0405033 | Enhancement Project: Rehabilitate railroad roundhouse in Hugo in Lincoln County, to become a railroad museum. | Transportation Enhancements | 11/18/2009 |  |  | 531670 | 0.24
1208 | Colorado | PUEBLO | PUEBLO | 3 | 0504060 | Resurfaces US 50 east of Pueblo and makes safety improvements | Pavement Improvement | 03/19/2010 |  |  | 5070313 | 11.4
1209 | Colorado | CHAFFEE |  | 5 | 050A009 | Enhancement Project: constructs curb, gutter, sidewalk, and ADA ramps in Salida on US 50 | Transportation Enhancements | 09/03/2009 | 09/18/2009 | 12/17/2009 | 491470 | 0.766
1210 | Colorado | BOULDER | BOULDER | 2 | 052A031 | Replaces the bridge over Boulder Creek on SH 52 at the Boulder - Weld County Line. | Bridge Replacement | 07/16/2009 | 08/31/2009 | 07/12/2010 | 4395465 | 0.511
1211 | Colorado | WELD |  | 4 | 060A013 | Installs a new traffic signal at the intersection of the I-25 exit ramps and frontage roads with SH 60 (Johnstown Exit).. | Safety/Traffic Management | 07/09/2009 | 08/03/2009 | 09/28/2009 | 493383 | 0.17
1212 | Colorado | SAN MIGUEL |  | 3 | 062A013 | Resurface a total of 21.5 miles of SH 62, Dallas Divide in in Ouray and San Migel counties between Placerville and Ridgway, in asphalt and repair embankments. Project includes some work on US 550 at R | Pavement Improvement | 05/12/2009 | 05/12/2009 | 10/02/2009 | 4000000 | 24.9
1213 | Colorado | MESA | GRAND JUNCTION | 3 | 0701197 | Improves safety by widening the acceleration and deceleration lanes at this interchange on I-70 at the Palisade exit in Mesa County. The improvements will upgrade the interchange to current design sta | Pavement Improvement | 06/22/2009 | 09/21/2009 | 12/02/2009 | 1400712 | 1
1214 | Colorado | SUMMIT |  | 2 | 0702283 | Resurfaces 14 miles of I-70 from milepost 190 to 204 as well as the right lane of eastbound I-70 between milepost 180 and 190. Numerous bridges along the I-70 corridor will also be rehabilitated by r | Pavement Improvement | 05/05/2009 | 05/05/2009 | 11/03/2009 | 8000000 | 24
1215 | Colorado | EAGLE |  | 2 | 0702297 | This safety improvement project will construct four roundabouts at the interchange of I-70 in Edwards in Eagle County. | Safety/Traffic Management | 02/26/2010 |  | 11/19/2010 | 8520185 | 0.77
1216 | Colorado | JEFFERSON | DENVER, CO | 7 | 0703350 | Repairs and replaces concrete slabs on I-70 between Kipling Street and Wadsworth Blvd in Wheatridge. | Pavement Improvement | 04/21/2009 | 05/19/2009 | 09/25/2009 | 1732584 | 2.07
1217 | Colorado | EAGLE | DENVER, CO | 2 | 0703353 | Installs various truck parking management components (electronic signs, closed-circuit cameras, power and communications systems), to provide notification during inclement weather. along I-70 between | Safety/Traffic Management | 06/22/2009 | 06/22/2009 | 11/23/2009 | 2203896 | 54.44
1218 | Colorado | ADAMS | DENVER, CO | 7 | 0704217 | Installs cable guardrailin the median of I-70 between Pena Blvd and Tower Road in Aurora to prevent crossover accidents. | Safety/Traffic Management | 06/22/2009 | 07/13/2009 | 09/07/2009 | 294430 | 2.18
1219 | Colorado | ADAMS | DENVER, CO | 7 | 0761200 | Construct two roundabouts on 96th Avenue at the ramps to I-76 in Commerce City. | Safety/Traffic Management | 05/21/2009 | 06/22/2009 | 12/14/2009 | 2222733 | 0.04
1220 | Colorado | ADAMS | DENVER, CO | 7 | 0761201 | Replaces two bridges on I-76 over the Union Pacific Railroad and SH 224 in Commerce City. | Bridge Replacement | 06/02/2009 | 07/06/2009 | 01/17/2011 | 9843607 | 1.043
1221 | Colorado | SEDGWICK |  | 4 | 0762045 | Reconstructs 11 miles of eastbound I-76 in concrete between Sedgwick and the Nebraska state line. | Pavement Improvement | 07/10/2009 | 07/13/2009 | 02/08/2010 | 15570336 | 19.49
1222 | Colorado | GARFIELD |  | 3 | 0821087 | This safety improvement project at the I-70 interchange with US 6 and SH 82 in Glenwood Springs will upgrade traffic signals and improve ramp width and length to benefit both pedestrians and vehicle | Other | 09/03/2009 | 08/03/2009 | 11/24/2009 | 2500000 | 3.02
1223 | Colorado | DOUGLAS | DENVER, CO | 6 | 0852095 | Widens one mile of US 85 to two lanes in each directions with shoulders and a raised median with controlled access on US 85 between Titan Road and Cook Ranch Road in Douglas County. | Pavement Widening | 08/17/2009 | 08/17/2009 | 04/26/2010 | 5400000 | 7.48
1224 | Colorado | DOUGLAS | DENVER, CO | 6 | 0852103 | SANTAFE/C470 INTERCHANGE EA (DEMOS 58, 84, 102), | New Bridge Construction | 05/20/2010 |  |  | 5861928 | 1.9
1225 | Colorado | ARAPAHOE | DENVER, CO | 6 | 088A026 | Replaces the asphalt surface on SH 88, Belleview Avenue, between Santa Fe Drive and Federal Blvd in Littleton. | Pavement Improvement | 04/28/2009 | 05/18/2009 | 06/29/2009 | 431702 | 0.9
1226 | Colorado | DELTA |  | 3 | 092A022 | Reconstructs five miles of SH 92 in asphalt and adds passing lanes and shoulders to improve recreational bicycling between Austin and Hotchkiss in Delta County. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 10/30/2010 | 9284102 | 4.1
1227 | Colorado | GUNNISON |  | 3 | 135A025 | Enhancement Project: constructs bike and pedestrian trail and bridge along SH 135 north of Gunnison | Transportation Enhancements | 03/16/2010 |  |  | 374515 | 0.17
1228 | Colorado | RIO GRANDE |  | 3 | 1602122 | Resurfaces three miles of US 160 west of Del Norte in Rio Grande County, in asphalt. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 07/21/2009 | 1468886 | 3.32
1229 | Colorado | LA PLATA |  | 3 | 1602123 | Relocates the intersection of La Plata County Roads 222 &223 with US 160, east of Durango, and adds auxiliary lanes to improve sight distance. | New Construction | 02/26/2010 | 02/26/2010 | 05/26/2011 | 4300000 | 1.774
1230 | Colorado | RIO GRANDE |  | 3 | 1602125 | Resurfaces with asphalt a second phase of US 160 west to Del Norte in Rio Grande County and constructs ADA ramps. | Pavement Improvement | 03/25/2010 |  | 07/16/2010 | 7523354 | 14
1231 | Colorado | ALAMOSA |  | 3 | 1603027 | Resurfaces six miles of US 160 east of Alamosa in asphalt. | Pavement Improvement | 06/12/2009 | 07/13/2009 | 09/07/2009 | 2736807 | 6.755
1232 | Colorado | LA PLATA |  | 3 | 160A010 | Constructs a new eastbound on-ramp as part of an already scheduled project that will widen US 160 to four lanes and relocate a traffic signal due to the widening east of Durango. | New Construction | 09/03/2009 | 09/03/2009 | 04/15/2010 | 3619600 | 1.49
1233 | Colorado | DOUGLAS | DENVER, CO | 6 | 177A006 | Resurface in asphalt, SH 177, University Avenue in Centennial, from C-470 to Arapahoe. | Pavement Improvement | 05/12/2009 | 05/26/2009 | 09/08/2009 | 1559083 | 2
1234 | Colorado | ARAPAHOE | DENVER, CO | 7 | 2254078 | Phase 1 of project to reconstruct the I-225 / Colfax interchange in Aurora to rebuild the southbound ramp from Colfax to I-225 | Pavement Widening | 11/23/2009 | 11/30/2009 | 05/07/2010 | 1077890 | 0.096
1235 | Colorado | ARAPAHOE | DENVER, CO | 7 | 2254079 | Phase 2 of the reconstruction of the I-55 / Colfax interchange in Aurora, to provide access from I-225 to 17th Avenue. | Pavement Widening | 03/26/2010 |  |  | 11300000 | 0.7
1236 | Colorado | WELD | FORT COLLINS | 4 | 257A007 | Installs a new traffic signal at the intersection fo SH 257 and Garden drive in Windsor. | Safety/Traffic Management | 07/16/2009 | 08/10/2009 | 10/09/2009 | 244422 | 0.16
1237 | Colorado | SAGUACHE |  | 3 | 2852016 | Resurfaces eight miles of US 285, south of Saguache, in asphalt. | Pavement Improvement | 06/12/2009 | 06/12/2009 | 08/28/2009 | 3660211 | 9.48
1238 | Colorado | JEFFERSON | DENVER, CO | 6 | 2854117 | Constructs a grade-separated interchange at Elk Creek Road, new frontage roads and a wildlife crossing underpass. When complete, Elk Creek Rd. will run under US 285. THe project is located in Jefferso | Pavement Widening | 08/26/2009 | 08/26/2009 | 11/24/2010 | 8400000 | 0.664
1239 | Colorado | PARK |  | 5 | 2854120 | Enhancement Project: constructs pedestrian bridge and trail in Fairplay | Transportation Enhancements | 03/11/2010 |  |  | 236000 | 2
1240 | Colorado | BACA |  | 4 | 2871032 | This project will reconstruct US 287 in concrete and improve drainage and shoulder embankments south of Springfield in Baca County. | Pavement Improvement | 10/07/2009 | 10/12/2009 | 10/04/2010 | 12200277 | 8.3
1241 | Colorado | MESA |  | 3 | 340A015 | Installs two new traffic signals west of the I-70 interchange on SH 240 in Fruitia in Mesa County.and makes intersection safety improvements for pedestrians and vehicles. | Pavement Widening | 09/21/2009 | 03/08/2010 |  | 1383153 | 0.89
1242 | Colorado | DOUGLAS | DENVER, CO | 6 | 4701118 | Repairs or replaces concrete slabs on C-470 and resurfaces C-470 in asphalt between Santa Fe Drive and I-25 in Douglas County. Rehabilitates the C-470 bike path between I-70 and I-25 in Jefferson, Ara | Pavement Improvement | 06/16/2009 | 07/09/2009 | 08/13/2010 | 31215789 | 9.243
1243 | Colorado | OURAY |  | 3 | 5502064 | Enhancement Project: constructs wildlife fence and ramps to reduce wildlife collisions along US 550 | Transportation Enhancements | 01/25/2010 | 01/25/2010 |  | 166666 | 8.91
1244 | Colorado | DENVER | DENVER, CO | 1 | C010101 | Replaces the Alameda bridge over I-25 in Denver with one that is wider to accommodate an additional lane ion I-25 in each direction. | Bridge Replacement | 02/11/2010 |  |  | 34447157 | 0.55
1245 | Colorado | DENVER | DENVER, CO | 1 | C010103 | Construct a new interchange at I-70 and Central Park Bvd. in Denver. | New Construction | 01/29/2010 |  | 10/01/2011 | 12000000 | 1.5
1246 | Colorado | PUEBLO | PUEBLO | 3 | C020033 | Enhancement Project: Landscaping and irrigation installation for the Eastern Gateway Landscape Project located at the intersection of SH 50 B and SH 47 in Pueblo. | Transportation Enhancements | 02/08/2010 | 04/01/2010 |  | 381424 | 0
1247 | Colorado | WELD | FORT COLLINS | 4 | C030035 | Resurfaces Weld County Road 74 from Weld County Road 13 to SH 357 in asphalt. | Pavement Improvement | 08/24/2009 | 08/24/2009 | 09/18/2009 | 459627 | 0
1248 | Colorado | LARIMER | FORT COLLINS | 4 | C060049 | Enhancement Project: Constructs a bicycle/pedestrian underpass under SH 392 in Windsor. | Transportation Enhancements | 07/28/2009 | 08/12/2009 | 09/16/2009 | 496000 | 0.369
1249 | Colorado | LARIMER | FORT COLLINS | 4 | C060050 | Resurfaces Larimer County Road 17 between Berthoud and Fort Collins in asphalt. | Pavement Improvement | 07/28/2009 | 08/03/2009 | 10/19/2009 | 3542373 | 0
1250 | Colorado | ARAPAHOE | DENVER, CO | 6 | C100028 | Enhancement Project: Construct an extension to the bicycle and pedestrain bridge over I-25 south of Dry Creek Road to extend over Inverness Drive in Arapahoe County. | Transportation Enhancements | 11/18/2009 | 11/18/2009 | 07/19/2010 | 708947 | 0
1251 | Colorado | ADAMS | DENVER, CO | 7 | C120018 | Construct an underpass of Pecos Street under the railroad tracks, south of I-76 in Adams County. | Pavement Improvement | 12/16/2009 | 01/04/2010 | 10/31/2011 | 4450000 | 0
1252 | Colorado | PROWERS |  | 4 | C170006 | Enhancement Project: Designs and constructs a transportation museum in Lamar in Prowers County. | Transportation Enhancements | 06/05/2010 |  |  | 330750 | 0
1253 | Colorado | LA PLATA |  | 3 | C200006 | Enhancement Project: constructs shared use path along CR 501 in Bayfield | Transportation Enhancements | 08/24/2009 | 08/24/2009 | 12/07/2009 | 220341 | 0
1254 | Colorado | BENT |  | 4 | C290007 | Enhancement Project: Historic restoration through Town Square in Las Animas in Bent County, install streetscaping, sidewalks and landscaping. | Transportation Enhancements | 03/17/2010 |  |  | 121000 | 0
1255 | Colorado | CLEAR CREEK |  | 2 | C510023 | Enhancement Project: constructs asphalt recreation trail from Bakerville to Loveland Basin in Clear Creek County along I70 | Transportation Enhancements | 05/07/2010 | 06/09/2010 |  | 903635 | 0
1256 | Colorado | STATEWIDE |  | 4 | HQ00023 | Provides on the job training to construction workers to develop construction skills | Other | 01/01/2010 | 01/01/2010 | 01/01/2012 | 250000 | 0
1257 | Colorado | JEFFERSON | DENVER, CO | 02,07 | M040017 | Enhancement Project: Construct a bicycle and pedestrian trail on the south side of the West 86th Parkway in Arvada to connect the exisitng trails. | Transportation Enhancements | 10/13/2009 | 10/22/2009 | 12/21/2009 | 300000 | 0
1258 | Colorado | JEFFERSON | DENVER, CO | 7 | M040019 | This project widens 74TH AVE from KIPLING to CARR to accommodate bike lanes and add sidewalks. | Transportation Enhancements | 05/03/2010 |  |  | 287157 | 0
1259 | Colorado | LA PLATA |  | 3 | M065003 | Enhancement Project: constructs sidewalks along US 160 business route in Bayfield | Transportation Enhancements | 08/20/2009 | 08/24/2009 | 10/13/2009 | 200000 | 0.11
1260 | Colorado | LARIMER | FORT COLLINS | 4 | M070002 | Enhancement Project: Construct bicycle and pedestrian improvements on Main Street in Berthoud. | Transportation Enhancements | 06/23/2010 |  |  | 134000 | 0.01
1261 | Colorado | PUEBLO | PUEBLO | 3 | M086056 | Enhancement Project:: Pedestrian trail replacement and streetscape on Northern Avenue from Vinewood Lane to Prairie Avenue in Pueblo. | Transportation Enhancements | 04/01/2010 |  |  | 165000 | 0
1262 | Colorado | PUEBLO | PUEBLO | 3 | M086058 | Constructs Veteran's memorial pedestrian bridge in Gateway Park at corner of Grand Avenue and S. Main Street in Pueblo | Transportation Enhancements | 03/23/2010 |  |  | 600000 | 0
1263 | Colorado | BOULDER | STATEWIDE | 2 | M110065 | Enhancement Project: constructs pedestrian access ramps at various intersections in Boulder to meet Americans with Disability (ADA) requirements. | Transportation Enhancements | 09/08/2009 | 09/14/2009 | 11/09/2009 | 757624 | 0
1264 | Colorado | BOULDER | BOULDER | 2 | M110066 | Enhancement Project: Constructs bike/pedestrian crossing treatments including medians, striping, flashing beacons and signage at the Folsom Street and Spruce Street intersection in Boulder. | Transportation Enhancements | 09/08/2009 | 09/08/2009 | 12/08/2009 | 318270 | 0
1265 | Colorado | WELD | FORT COLLINS | 4 | M190003 | Resurfaces in asphalt 4th Avenue(Weld County Road 74) in Severance 2.5 miles west of Weld County Road 25 | Pavement Improvement | 09/28/2009 | 09/28/2009 | 11/30/2009 | 838000 | 0
1266 | Colorado | EL PASO | COLORADO SPRINGS | 5 | M240121 | Widens Woodmen Rd. and constructs a new interchange at Academy Blvd.in Colorado Springs including construction of sidewalks and a bike path. | Pavement Widening | 09/18/2009 | 09/24/2009 | 11/15/2011 | 35031818 | 0
1267 | Colorado | LOGAN |  | 4 | M256012 | Enhancement Project: improves sidewalks and ADA ramps along 7th Street in Sterling | Transportation Enhancements | 06/01/2010 |  | 07/28/2010 | 211000 | 0
1268 | Colorado | DENVER | DENVER, CO | 1 | M320064 | Enhancement Project: Striping and singage on various designated bikeways on the streets of Denver. | Transportation Enhancements | 10/22/2009 | 10/26/2009 | 06/30/2010 | 250000 | 0
1269 | Colorado | ADAMS | DENVER, CO | 2 | M356024 | Enhancement Project: replace existing 4' sidewalks with 8' sidewalks to serve as a bike and pedestrain train on Bradburn Blvd from 73rd Avenue to Turnpike Drive in Westminster. | Transportation Enhancements | 07/23/2009 | 07/27/2009 | 09/30/2009 | 260000 | 0
1270 | Colorado | WELD | BOULDER | 2 | M400004 | Enhancement Project: Construct bike pathes on the north and south sides of Leon Wurl Parkway in Erie from Bonanza Drive east to I-25. | Transportation Enhancements | 10/12/2009 | 10/19/2009 | 02/16/2010 | 607066 | 0
1271 | Colorado | BOULDER | BOULDER | 2 | M400005 | Enhancement Project: constructs bike lanes on East County Line Road from SH7 to Erie Parkway in Erie | Transportation Enhancements | 03/15/2010 |  |  | 433000 | 0
1272 | Colorado | LARIMER |  | 4 | M405013 | Enhancement Project: constructs Fall River Trail/Path in Estes Park | Transportation Enhancements | 10/05/2009 | 10/08/2009 | 12/15/2009 | 140012 | 0.73
1273 | Colorado | WELD | STATEWIDE | 4 | M415011 | Enhancement Project: Construct bicycle and pedestrian improvements on the US 85 service road in Evans. | Transportation Enhancements | 02/18/2010 | 03/22/2010 |  | 160000 | 0
1274 | Colorado | WELD | FORT COLLINS | 4 | M415012 | Resurfaces 37th Street in Evans in asphalt | Pavement Improvement | 09/08/2009 | 09/08/2009 | 10/16/2009 | 354000 | 0
1275 | Colorado | GARFIELD |  | 3 | M535004 | Enhancement Project: constructs a pedestrian bridge over I-70 along Devereux Rd in Glenwood Springs | Transportation Enhancements | 09/11/2009 | 09/15/2009 | 06/01/2010 | 50200 | 0
1276 | Colorado | GRAND |  | 2 | M560002 | Enhancement Project:: Beautification and drainage improvements at the Grand Lake Welcome Center in Grand Lake, Grand County. | Transportation Enhancements | 03/23/2010 |  | 06/15/2010 | 169000 | 0
1277 | Colorado | ROUTT |  | 3 | M615002 | Enhancement Project: improves and extends sidewalks in Hayden | Transportation Enhancements | 04/24/2010 | 07/12/2010 |  | 256000 | 0.25
1278 | Colorado | JEFFERSON | DENVER, CO | 7 | M760030 | Constructs new bike path from Rooney Rd to Indiana St along US 6 and C470 | Transportation Enhancements | 03/04/2010 | 03/15/2010 | 06/29/2010 | 92000 | 0
1279 | Colorado | LARIMER | FORT COLLINS | 4 | M830047 | Intersection improvements at SH 34 and Wilson in Loveland. | Safety/Traffic Management | 09/14/2009 | 09/14/2009 | 11/11/2009 | 250000 | 0
1280 | Colorado | BOULDER | BOULDER | 2 | M835002 | Enhancement Project: streetscape enhancements and recostruction of Main Street (US 36) in Lyons between 3rd and 5th Avenues to include paving, curb and gutter, landscaping and pedestrian amenities. | Transportation Enhancements | 09/28/2009 | 10/12/2009 | 12/09/2009 | 689000 | 0.294
1281 | Colorado | BOULDER | BOULDER | 2 | M935001 | Enhancement Project: Construct sidewalks on SH 119 between Eldora and @nd in Nederland to connect to the RTD parking. | Transportation Enhancements | 09/08/2009 |  |  | 385000 | 2
1282 | Colorado | ADAMS | DENVER, CO | 2 | M945001 | This project is reconstructing concrete on HURON ST from 104TH TO 112TH. | Pavement Improvement | 04/16/2010 |  | 03/18/2011 | 3903974 | 0
1283 | Colorado | LINCOLN |  | 4 | R100157 | The project will ireconstruct to concrete pavement 8.7 miles of US 40/US 287 (mileposts 413-422 approximately) south of Hugo in Lincloln County. | Pavement Improvement | 06/02/2009 | 06/02/2009 | 03/09/2010 | 12248750 | 8.7
1284 | Colorado | ADAMS | DENVER, CO | 02,06 | R600340 | Installs ramp metering systems on I-25, US 36, and C470 in various locations | Safety/Traffic Management | 05/19/2009 | 06/01/2009 | 08/24/2009 | 259460 | 0.18
1285 | Colorado | BOULDER | DENVER, CO | 02,07 | R600343 | Replaces traffic signals at the intersection of US6, SH 58 and SH 93 in Golden and at the SH 128 and Simms intersection in Broomfield. | Safety/Traffic Management | 06/04/2009 | 07/20/2009 | 11/02/2009 | 862403 | 4.38
1286 | Colorado | JEFFERSON | DENVER, CO | 7 | R600346 | Resurface in asphalt approximately three miles of US 40, Colfax Avenue, between Kipling Street and Sheridan Blvd in Lakewood. | Pavement Improvement | 05/01/2009 | 06/01/2009 | 10/04/2009 | 2231905 | 2.829
1287 | Colorado | STATEWIDE |  | 4 | SW00837 | This grant provides on the job training to construction workers to develop construction skills. | Other | 03/29/2010 | 03/29/2010 |  | 210000 | 0
1288 | Connecticut | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 0001315 | The project involves the reconstruction and lengthening of the existing AMTRAK bridge over Route 1, as well as the rehabilitation of a portion of Route 1 in the Town of Branford | Bridge Replacement | 08/13/2009 | 08/13/2009 | 03/09/2014 | 70815491 | 0
1289 | Connecticut | HARTFORD | SPRINGFIELD-CHICOPEE-HOLYOKE (MA) | 01 | 0005105 | This project will extend the life of the bridge along Route 5 over Interstate 91 in the Town of Enfield by replacing the existing deteriorated deck, bridge supports, and piers. | Bridge Improvement | 06/22/2009 | 06/22/2009 | 12/13/2010 | 6730000 | 0
1290 | Connecticut | STATEWIDE |  | 01,02,03,04,05 | 000R418 | The State of Connecticut will replace overhead sign supports on multiple state highways | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 12/01/2010 | 5975600 | 0
1291 | Connecticut | HARTFORD |  | 01 | 000R430 | The State of Connecticut will install and revise traffic control signals at various intersections throughout District 1 | Safety/Traffic Management | 07/27/2009 | 07/27/2009 | 08/10/2010 | 1362070 | 0
1292 | Connecticut | STATEWIDE |  | 02 | 000R442 | The State of Connecticut will install and revise traffic control signals at various intersections in District 2 to improve safety | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 09/01/2010 | 328970 | 0
1293 | Connecticut | STATEWIDE |  | 02 | 000R444 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 to improve safety | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 09/01/2010 | 1872080 | 0
1294 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 000R447 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 to improve safety | Safety/Traffic Management | 08/10/2009 | 08/03/2009 | 05/17/2010 | 186176 | 0.01
1295 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 000R449 | The State of Connecticut will install and revise traffic control signals at various intersections in District 3 | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 05/17/2010 | 339748 | 0
1296 | Connecticut | STATEWIDE |  | 05,01 | 000R453 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 4 | Safety/Traffic Management | 12/11/2009 | 05/04/2010 | 07/14/2010 | 788940 | 0
1297 | Connecticut | STATEWIDE |  | 03,04 | 000R514 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 05/17/2010 | 1073963 | 0
1298 | Connecticut | STATEWIDE |  | 05,01 | 000R538 | This project consists of the replacement of bridge deck joints within District 4 | Bridge Improvement | 07/24/2009 | 08/03/2009 | 01/26/2010 | 5734200 | 32.26
1299 | Connecticut | NEW HAVEN | WATERBURY | 03 | 000R596 | This project consists of pavement milling and resurfacing of the travel lanes, new line striping, rumble strips, and NOVACHIPTM Surface treatment that provides improved skid, wear, and rutting resiste | Pavement Improvement | 10/16/2009 | 10/16/2009 | 05/17/2010 | 3932474 | 5.88
1300 | Connecticut | STATEWIDE |  | 01,02,03,04,05 | 000R597 | The State of Connecticut will conduct crack sealing and crack filling along major highways including Route 8, I-84, I-91, I-95, and I-384. This effort will help extend the lifetime of the pavements o | Pavement Improvement | 10/01/2009 | 10/01/2009 | 11/14/2009 | 2204907 | 22.27
1301 | Connecticut | STATEWIDE |  | 01 | 000R598 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists through District 1. | Safety/Traffic Management | 08/31/2009 | 09/08/2009 | 09/30/2009 | 139004.1 | 0
1302 | Connecticut | STATEWIDE |  | 02 | 000R599 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 2. | Safety/Traffic Management | 09/01/2009 | 10/05/2009 | 10/19/2009 | 129480 | 0
1303 | Connecticut | STATEWIDE |  | 03, 04 | 000R600 | The State of Connecticut will install epoxy pavement markings and Interstae lines for safey of motorists through District 3. | Safety/Traffic Management | 09/01/2009 | 09/20/2009 | 10/14/2009 | 220000 | 0
1304 | Connecticut | STATEWIDE |  | 05, 01 | 000R601 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 4 | Safety/Traffic Management | 09/02/2009 | 09/08/2009 | 05/17/2010 | 47428 | 0
1305 | Connecticut | STATEWIDE |  | 05,01 | 000R602 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 4 | Safety/Traffic Management | 05/01/2010 | 05/01/2010 | 07/01/2010 | 268791 | 0
1306 | Connecticut | STATEWIDE |  | 03, 04 | 000R603 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 3 | Safety/Traffic Management | 04/05/2010 | 04/05/2010 | 06/18/2009 | 500296 | 0
1307 | Connecticut | STATEWIDE |  | 01 | 000R604 | The State of Connecticut will install epoxy pavement markings and Interste lines for safety of motorists throughout District 1. | Safety/Traffic Management | 10/16/2009 | 10/25/2009 | 11/10/2009 | 331473 | 0
1308 | Connecticut | STATEWIDE |  | 02 | 000R605 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 2. | Safety/Traffic Management | 10/06/2009 | 10/19/2009 | 11/04/2009 | 400835 | 0
1309 | Connecticut | FAIRFIELD | DANBURY (NY) | 05 | 000R606 | TOWN CENTER PEDESTRIAN AND STREETSCAPE ENHANCEMENTS, TOWN OF NEW FAIRFIELD | Transportation Enhancements | 05/24/2010 | 05/20/2010 | 09/16/2010 | 259754 | 0.13
1310 | Connecticut | STATEWIDE |  | 01 | 000R630 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES, AND INTERSECTIONS WITHIN DISTRICT 1 | Safety/Traffic Management | 07/07/2010 | 07/07/2010 | 09/28/2010 | 232525 | 0
1311 | Connecticut | STATEWIDE |  | 02 | 000R631 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES AND INTERSECTIONS WITHIN DISTRICT 2 | Safety/Traffic Management | 06/07/2010 | 06/07/2010 | 09/15/2010 | 196355 | 0
1312 | Connecticut | STATEWIDE | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 000R632 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES, AND INTERSECTIONS IN DISTRICT 3 | Safety/Traffic Management | 06/18/2010 | 07/06/2010 | 09/09/2010 | 415669 | 0
1313 | Connecticut | STATEWIDE |  | 05, 01 | 000R633 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES, AND INTERSECTIONS IN DISTRICT 4 | Safety/Traffic Management | 07/15/2010 | 07/15/2010 | 10/16/2010 | 174071 | 0
1314 | Connecticut | WINDHAM |  | 02 | 0012138 | This project will involve the installation of sidewalks on Rte 12 from SR647 to School St and from RR avenue to Academy Hill Rd in Plainfield | Transportation Enhancements | 04/28/2010 | 05/05/2010 | 09/01/2010 | 813543 | 1.2
1315 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0015103 | This project will provide for median deck repairs on the bridge carrying Route 15 (Merritt Parkway) over Reservoir Avenue in the Town of Trumbull | Bridge Improvement | 06/15/2009 | 06/18/2009 | 07/29/2011 | 1299200 | 0
1316 | Connecticut | TOLLAND |  | 02 | 0031118 | This project involves the installation of sidewalks on Main St from Paden Rd to 1000 feet north of Rte 275 in Coventry | Transportation Enhancements | 06/03/2010 | 06/28/2010 | 10/25/2010 | 569350 | 0
1317 | Connecticut | NEW LONDON | NEW LONDON-NORWICH | 02 | 0032183 | INTERSECTION IMPROVEMENTS AT ROUTE 32, LATHROP RD., AND MAPLE RD., TOWN OF WATERFORD | Pavement Improvement | 06/01/2010 | 06/01/2010 | 09/28/2010 | 625632 | 0.2
1318 | Connecticut | NEW HAVEN |  | 02 | 0032184 | The State of Connecticut will resurface Route 2 in Eastbound and Westbound directions from Colchester to Lebanon | Pavement Improvement | 10/28/2009 | 10/28/2009 | 11/11/2009 | 3802792 | 0.02
1319 | Connecticut | WINDHAM |  | 02 | 0089118 | This project involves the reconstruction of the existing bridge superstructure, including new steel girders and a concrete deck. Additional improvements to the approach pavement and drainage will als | Bridge Improvement | 07/03/2009 | 07/13/2009 | 08/03/2010 | 1272600 | 0
1320 | Connecticut | HARTFORD | HARTFORD | 01 | 0091103 | Pavement preservation will be conducted by the State of Connecticut along Interstate 91 from West Street in the Town of Rocky Hill to Route 3 in the Town of Wethersfield. Scope of work includes resur | Pavement Improvement | 10/01/2009 | 10/14/2009 | 11/18/2009 | 4748987 | 4.08
1321 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150192 | This project involves the resurfacing of the pavement, along with other bridge and safety improvements, along a section of Route 15 (Merritt Parkway) from Congress Street to Morehouse Highway | Pavement Improvement | 06/15/2009 | 06/18/2009 | 07/29/2011 | 24969945 | 44.06
1322 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150193 | This project will provide for the replacement of the existing Route 15 (Merritt Parkway) bridge over the Mill River in the Town of Fairfield. | Bridge Replacement | 06/15/2009 | 06/18/2009 | 07/29/2011 | 10994400 | 0.02
1323 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150194 | This project involves the resurfacing of the pavement, along with other bridge and safety improvements, along a section of Route 15 (Merritt Parkway) from Morehouse Highway to Route 8 | Pavement Improvement | 06/15/2009 | 06/18/2009 | 07/29/2011 | 33481455 | 10.73
1324 | Connecticut | MIDDLESEX | HARTFORD | 01 | 0912132 | I-91 PAVEMENT PRESERVATION TOWNS OF CROMWELL AND ROCKY HILL | Pavement Improvement | 06/01/2010 | 06/01/2010 | 07/31/2010 | 2920879 | 3.62
1325 | Connecticut | MIDDLESEX | MERIDEN-NEW HAVEN | 02 | 0952111 | This project consists of replacing the bridge deck joints on the Baldwin Bridge on I95 over the Connecticut River | Bridge Improvement | 07/27/2009 | 07/27/2009 | 11/17/2009 | 2851300 | 0
1326 | Connecticut | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1002105 | RESURFACING OF FORD AND BEAVER ST. ANSONIA | Pavement Improvement | 07/19/2010 | 07/19/2010 | 09/01/2010 | 550935 | 0
1327 | Connecticut | LITCHFIELD |  | 01 | 1005102 | HILLCREST DR. CRACK SEALING AND 1' OVERLAY TOWN OF BARKHAMSTED | Pavement Improvement | 07/08/2010 | 07/12/2010 | 09/05/2010 | 121000 | 0
1328 | Connecticut | HARTFORD | HARTFORD | 01 | 1007105 | In the Town of Berlin, Episcopal Road will be reconstructed and paved from Deming Road to Rowley Street to improve road and dainage. | Pavement Improvement | 04/05/2010 | 04/12/2010 | 06/12/2010 | 498786 | 0.51
1329 | Connecticut | FAIRFIELD | DANBURY (NY) | 05 | 1009111 | THIS PROJECT INCLUDES THE MILLING AND PAVING OF HAWLEYVILLE ROAD, TOWN OF BETHEL | Pavement Improvement | 07/16/2010 | 07/19/2010 | 09/16/2010 | 509563 | 1.5
1330 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1015118 | Congress Street Bridge (Phase1 - Partial Demolition), City of Bridgeport | Bridge Replacement | 01/21/2010 | 03/08/2010 | 06/29/2010 | 600400 | 0
1331 | Connecticut | HARTFORD | HARTFORD | 01 | 1017106 | THIS PROJECT INVOLVES MIX STREET RECONSTRUCTION AND NORMALIZATION OF INTERSECTION WITH MALBY STREET, BRISTOL | Pavement Improvement | 06/28/2010 | 06/28/2010 | 01/04/2011 | 1065600 | 0.51
1332 | Connecticut | FAIRFIELD | DANBURY (NY) | 05 | 1018108 | THE STATE OF CONNECTICUT WILL COMPLETE A PAVING PROJECT THAT INCLUDES THE MILLING AND PAVING GRAY'S BRIDGE RD, BROOKFIELD | Pavement Improvement | 07/01/2010 | 07/01/2010 |  | 413600 | 0
1333 | Connecticut | FAIRFIELD | DANBURY (NY) | 05 | 1034114 | MILLING AND PAVING OF WHITE STREET, FRANKLIN STREET, AND FRANKLIN STREET EXT. CITY OF DANBURY | Pavement Improvement | 05/27/2010 | 05/27/2010 | 08/24/2010 | 1593000 | 0
1334 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1035103 | Replacement of Staircases & Railings at Noroton Heights RR Station, Town of Darien | Transportation Enhancements | 05/20/2010 | 05/20/2010 | 11/16/2010 | 479170 | 0
1335 | Connecticut | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1036001 | THIS PROJECT INCLUDES THE MILLING AND OVERLAY OF ELIZABETH STREET, TOWN OF DERBY | Pavement Improvement | 07/14/2010 | 07/14/2010 | 08/27/2010 | 700576 | 0
1336 | Connecticut | MIDDLESEX | HARTFORD | 02 | 1041104 | THIS PROJECT INCLUDES THE RESURFACING OF HADDAM NECK RD, EAST HAMPTON | Pavement Improvement | 05/12/2010 | 05/24/2010 | 07/24/2010 | 185033 | 0.682
1337 | Connecticut | HARTFORD | HARTFORD | 01 | 1042118 | PAVEMENT REHABILIATION OF PORTIONS OF MAIN STREET AND SCHOOL ST., TOWN OF EAST HARTFORD | Pavement Improvement | 07/19/2010 | 07/19/2010 | 10/27/2010 | 2047715 | 0
1338 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1050106 | Various intersection improvements will be completed at the Black Rock Turnpike and Commerce Drive in Fairfield | Other | 04/19/2010 | 04/19/2010 | 04/19/2011 | 1124920 | 0
1339 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1056112 | PAVEMENT RECONSTRUCTION AND OVERLAY OF FIELD POINT ROAD, DEARFIELD DR, BROOKSIDE DR, WEST ELM ST., RAILROAD AVE, PROSPECT ST AND HORSENECK LN., GREENWICH | Pavement Improvement | 05/06/2010 | 05/09/2010 | 06/23/2010 | 958712 | 2.35
1340 | Connecticut | LITCHFIELD |  | 05 | 1073104 | WHITE WOOD ROAD OVERLAY , TOWN OF LITCHFIELD | Pavement Improvement | 06/24/2010 | 07/12/2010 | 08/24/2010 | 149723 | 0
1341 | Connecticut | HARTFORD | HARTFORD | 01 | 1076120 | In the Town of Manchester, a new traffic control signal will be installed at the interesection of Slater Street and the Best Buy driveways to improve safety and traffic flow to and from exisiting stor | Safety/Traffic Management | 09/08/2009 | 04/01/2010 | 05/15/2010 | 252300 | 0
1342 | Connecticut | HARTFORD | HARTFORD | 01 | 1076124 | In the Town of Manchester, pavement preservation will be conducted along Buckland Hills Road by repaving from Buckland Street eastward to Deming Street. | Pavement Improvement | 11/05/2009 | 04/01/2010 | 06/29/2010 | 2509498 | 0
1343 | Connecticut | TOLLAND |  | 02 | 1077107 | IN THE TOWN OF MANSFIELD, PAVING OF MANSFIELD CITY ROAD WILL BE COMPLETED | Pavement Improvement | 07/06/2010 | 07/06/2010 | 10/13/2010 | 269036 | 0
1344 | Connecticut | HARTFORD | HARTFORD | 05 | 1088109 | This project work inlcudes the milling and overlaying of Corbin Avenue, East Street, and Stanley Street in the city of New Britain | Pavement Improvement | 07/06/2010 | 07/06/2010 | 12/14/2010 | 1734651 | 3.35
1345 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1089102 | THIS PROJECT INCLUDES PAVEMENT RESURFACING OF OLD NORWALK ROAD, FARM ROAD, WEST ROAD AND WEED ROAD, IN THE TOWN OF NEW CANAAN | Pavement Improvement | 06/21/2010 | 06/21/2010 | 08/05/2010 | 830200 | 2.81
1346 | Connecticut | FAIRFIELD | DANBURY (NY) | 05 | 1090103 | In the Town of New Fairfield, the park and ride lot will be repaved for an improved surface. | Pavement Improvement | 10/13/2009 | 10/13/2009 | 10/21/2009 | 220000 | 4.25
1347 | Connecticut | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1092133 | This project will provide for the reconstruction of Quinnipiac Avenue, including pavement, drainage and sidewalks, from south of Ferry Street to Clifton Street in the City of New Haven. | Pavement Improvement | 03/22/2010 | 04/01/2010 | 11/27/2011 | 6503800 | 0.789
1348 | Connecticut | NEW LONDON | NEW LONDON-NORWICH | 02 | 1094106 | The project will complete roadway improvements to Montauk Avenue in New London | Pavement Improvement | 06/15/2010 | 06/15/2010 | 09/12/2010 | 807572 | 0.83
1349 | Connecticut | LITCHFIELD | DANBURY (NY) | 05 | 1095114 | This project includes the completion of milling and paving Boardman Road and Grove Street in the town of New Milford | Pavement Improvement | 06/16/2010 | 06/17/2010 | 09/13/2010 | 1043944 | 1.9
1350 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1102109 | THIS PROJECT INCLUDES THE RESURFACING AND PAVING OF DR. MARTIN LUTHER KING JR. DR. BELDEN HILL RD., BUTLER ST. HARBOR AVE., IN THE CITY OF NORWALK | Pavement Improvement | 06/21/2010 | 06/21/2010 | 09/30/2010 | 1449934 | 0
1351 | Connecticut | MIDDLESEX | HARTFORD | 01 | 1112001 | THE VENDOR WILL COMPLETE THE PAVEMENT PRESERVATION OF BARTLETT ST, COLLINS HILL RD, HIGH ST, ISINGLASS AND JOBS POND ROAD IN PORTLAND | Pavement Improvement | 05/10/2010 | 06/14/2010 | 07/14/2010 | 234180 | 8.27
1352 | Connecticut | HARTFORD | HARTFORD | 01 | 1118003 | In the Town of Rocky Hill, pavement preservation will be conducted along Old Main Street by repaving from Glastonbury Avenue extending 50 feet south of the bridge over Goff Brook | Pavement Improvement | 07/29/2009 | 08/10/2009 | 10/18/2009 | 1262839 | 0
1353 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1126108 | THIS PAVEMENT REHABILITATION PROJECT WILL INCLUDE THE PAVING AND REHABILITATION OF CONSTITUTION BLVD. SOUTH IN THE CITY OF SHELTON | Pavement Improvement | 04/28/2010 | 05/05/2010 | 09/01/2010 | 453730 | 0
1354 | Connecticut | HARTFORD | HARTFORD | 01 | 1132104 | In the Town of South Windsor, beginning at the Manchester Town Line and extending north, approximately 4400 feet of Buckland Road will be resurfaced. | Pavement Improvement | 10/02/2009 | 10/02/2009 | 12/30/2009 | 1137602 | 0
1355 | Connecticut | LITCHFIELD | HARTFORD | 05 | 1140001 | Pavement rehabilitaition will be completed on Old Northfield Road in Thomaston | Pavement Improvement | 06/21/2010 | 07/07/2010 | 09/18/2010 | 183556 | 0.322
1356 | Connecticut | LITCHFIELD |  | 05 | 1143109 | THIS PAVEMENT PROJECT INCLUES THE MILLING AND OVERLAYING OF LITCHFIELD ST., WINTHROP ST. AND WATER ST., IN THE CITY OF TORRINGTON | Pavement Improvement | 06/17/2010 | 06/17/2010 | 09/14/2010 | 1015286 | 0
1357 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1157001 | THE VENDOR WILL COMPLETE THE PAVEMENT PRESERVATION OF OLD HYDE ROAD IN THE TOWN OF WESTON | Pavement Improvement | 07/12/2010 | 07/12/2010 | 08/03/2010 | 260600 | 0
1358 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1158001 | THIS PAVEMENT PRESERVATION PROJECT INCLUDES THE PAVING OF CROSS HIGHWAY, LONG LOTS RD., AND NEWTOWN TPKE, IN THE TOWN OF WESTPORT | Pavement Improvement | 03/29/2010 | 03/29/2010 | 05/03/2010 | 838040 | 0
1359 | Connecticut | HARTFORD | HARTFORD | 01 | 1164106 | In the Town of Windsor, pavement preservation will be conducted by along Day Hill Road by milling and paving from Blue Hills Avenue to Great Pond Drive. This will include new drainage and curbing. | Pavement Improvement | 09/28/2009 | 10/01/2009 | 11/29/2009 | 891700 | 0
1360 | Connecticut | NEW LONDON | NEW LONDON-NORWICH | 02 | 3953001 | IN THE TOWNS OF EAST LYME,MONTVILLE AND WATERFORD THIS PROJECT WILL INCLUDE THE PAVEMENT PRESERVATION OF I-395. | Pavement Improvement | 05/14/2010 | 05/14/2010 | 07/28/2010 | 4134146 | 5.6
1361 | Connecticut | FAIRFIELD | DANBURY (NY) | 05 | 6034007 | This project consists of the replacement of the Backus Avenue Bridge in the city of Danbury | Bridge Improvement | 03/29/2010 | 03/29/2010 | 10/25/2010 | 1055328 | 0.049
1362 | Connecticut | FAIRFIELD | WATERBURY | 03 | 6080004 | The purpose of this project is to replace the Longmeadow Road Bridge in the Town of Middlebury | Bridge Replacement | 04/01/2010 | 04/01/2010 | 05/26/2011 | 167700 | 0
1363 | Connecticut | NEW LONDON |  | 02 | 6085002 | THE PURPOSE OF THIS PROJECT IS TO REPAIR THE BRIDGE ON OLD COLCHESTER RD.IN THE TOWN OF MONTVILLE | Bridge Improvement | 03/24/2010 | 04/05/2010 | 05/19/2011 | 1067200 | 0.094
1364 | Connecticut | NEW HAVEN | WATERBURY | 03 | 6087005 | This project consists of the rehabilitation of the Rubber Avenue Bridge, number 03713, town of Naugatuck | Bridge Improvement | 04/12/2010 | 04/12/2010 | 11/08/2010 | 1168891 | 0
1365 | Connecticut | LITCHFIELD |  | 05 | 6099012 | THE PURPOSE OF THIS PROJECT IS INSTALL A MEMBRANE AND OVERLAY BRIDGE #5207 ON LOWER RD IN NORTH CANAAN | Bridge Improvement | 07/06/2010 | 07/06/2010 | 09/03/2010 | 336939 | 0.04
1366 | Connecticut | LITCHFIELD |  | 05 | 6119002 | THIS PROJECT CONSISTS OF PAINTING JUDDS BRIDGE IN THE TOWN OF ROXBURY | Other | 07/20/2010 | 07/20/2010 | 11/26/2010 | 233104 | 0.03
1367 | Connecticut | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 6158006 | This project will provide rehabilitation of th existing Hales Road bridge over Metro North RR in the Town of Westport. Construction will include complete replacement of the bridge superstructure and | Bridge Improvement | 08/28/2009 | 09/28/2009 | 07/28/2010 | 4192758 | 0
1368 | Connecticut | HARTFORD | HARTFORD | 02 | H011002 | This project will include the completing the reconstruction of Town Farms Road and Post Office Road in Enfield | Pavement Improvement | 05/03/2010 | 05/03/2010 | 10/27/2011 | 3746137 | 1.2
1369 | Connecticut | NEW LONDON | NEW LONDON-NORWICH | 02 | H018011 | This project will include streetscape improvements for Mystic within the town of Stonington | Transportation Enhancements | 05/17/2010 | 05/17/2010 | 11/12/2010 | 544172 | 0.34
1370 | Connecticut | NEW LONDON | NEW LONDON-NORWICH | 02 | H018012 | This project will provide for streetscape type improvements along Route 1 in the Town of Stonington from the Mystic Bridge easterly to Willow Street. The work includes new curbing, sidewalks, decorti | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 05/01/2010 | 905760 | 0.11
1371 | Connecticut | HARTFORD | HARTFORD | 01 | H135002 | In the Town of Southington, the Linear Park multi-use trail will be constructed along an abandoned rail line from West Main Street to the Cheshire Town line. | Transportation Enhancements | 01/14/2010 | 01/20/2010 | 04/01/2011 | 1902990 | 1.9
1372 | Connecticut | LITCHFIELD |  | 01 | PEDS124 | In the City of Torrington, the Still River Greenway multi-use path will be extended 1.8 miles from Princewoods Road north to Harris Drive. | Transportation Enhancements | 07/07/2009 | 07/07/2009 | 11/11/2009 | 900000 | 0
1373 | Connecticut | HARTFORD | HARTFORD | 05 | PEDS125 | THE PROJECT WILL INCLUDE CONNECTING THE BURLINGTON TRAIL TO THE FARMINGTON TRAIL IN THE TOWNS OF BURLINGTON AND FARMINGTON | Transportation Enhancements | 07/06/2010 | 07/20/2010 | 10/05/2010 | 305600 | 0
1374 | Connecticut | HARTFORD | HARTFORD | 01 | PEDS130 | THE PROJECT WILL INCLUDE THE REPAIR AND IMPROVEMENT OF SECTIONS OF THE I-84 /I-384 MULTI USE TRAIL IN EAST HARFORD AND MANCHESTER | Transportation Enhancements | 05/21/2010 | 05/21/2010 | 08/25/2010 | 766866 | 2.6
1375 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009009 | This project will remove and replace hot-mix surface, hot mix patching, and profile improvements at one location in New Castle County. | Pavement Improvement | 05/20/2009 | 05/20/2009 | 10/01/2009 | 4223809.38 | 4.94
1376 | Delaware | SUSSEX |  | 00 | 2009010 | This project will remove and replace hot-mix surface, hot-mix patching, and curb ramp upgrades at two locations in Sussex County. | Pavement Improvement | 06/03/2009 | 06/08/2009 | 10/01/2009 | 866353.32 | 3.519
1377 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009011 | This project replaces the concrete median barrier on I-95 between SR 7 interchange and SR 72 overpass. | Pavement Improvement | 08/13/2009 | 08/13/2009 | 01/01/2010 | 1712689.38 | 4.89
1378 | Delaware | SUSSEX, KENT |  | 00 | 2009012 | This project will improve the long-term condition of the roadway by paving and rehabilitating at various locations | Pavement Improvement | 04/24/2009 | 04/24/2009 | 06/01/2010 | 7716353.22 | 1
1379 | Delaware | NEW CASTLE |  | 00 | 2009014 | This project will improve the long-term condition of the roadway by milling, hot-mix patching, and overlaying at 2 locations in New Castle County. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 11/01/2009 | 1240215.51 | 2.63
1380 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009015 | This project will improve the long-term condition of the roadway by milling, hot-mix patching and overlaying at 4 locations in Wilmington. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 12/01/2009 | 3511837.46 | 1
1381 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009016 | This project will improve the long-term condition of the roadway by milling, patching and overlayin at 3 locations in New Castle County. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 1289897.07 | 1
1382 | Delaware | SUSSEX |  | 00 | 2009017 | This project will construct a permanent berth for the historic Lightship Overfalls, listed in the National Register of Historic Places. | Transportation Enhancements | 03/09/2010 | 03/15/2010 | 06/15/2010 | 400000 | 0.06
1383 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009018 | This project involves the rehabilitation of interstate bridges 1-800, 1-831, 1-802, 1-809, 1-811, 1-815, 1-819N, 1-826N and 1-826S. This work includes: replacing expansion joints, joint seals, compre | Bridge Improvement | 05/04/2009 | 05/04/2009 | 04/10/2010 | 2655281.89 | 1
1384 | Delaware | SUSSEX |  | 00 | 2009019 | This project involves the Boardwalk restoration - approximately 52,795 square foot section from the Henlopen Hotel to Rehoboth Avenue and the 24,300 square foot section from Laurel Street to Prospect | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 06/01/2010 | 5585854.53 | 0.05
1385 | Delaware | STATEWIDE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009020 | This project involves various intersections with different scope of works, variously involving new signal installations, reconstruction of aging infrastructure, pedestrian signal enhancements, upgrade | Other | 04/21/2009 | 04/21/2009 | 08/01/2009 | 1554380.95 | 1
1386 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009021 | This project will complete an over 4 mile loop recreational trail and will be a segment in an overall cross-county greenway trail system. | Transportation Enhancements | 05/18/2009 | 05/18/2009 | 09/11/2010 | 704339.79 | 0.05
1387 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009022 | This project in the New Castle Industrial Track Rail Trail covers 4.75 miles of corridor running north from Delaware Street in New Castle, across Boulden Boulevard, then crossing the the Christina Riv | Transportation Enhancements | 08/31/2009 | 08/31/2009 | 12/01/2009 | 1013567.13 | 0.51
1388 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009023 | This project includes miscellaneous work at Bridge 1-701, 703, 703A, 704 and 705. Work includes the replacement of bearings, expansion joints, painting of structural steel, repair of spalled concrete | Other | 05/04/2009 | 05/04/2009 | 12/01/2010 | 134734.73 | 1
1389 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009024 | This project involves the rehabilwork at Bridge 1-792 and 829. Work includes the replacement of bearings, expansion joints, painting of structural steel, repair of spalled concrete and replacement of | Other | 04/28/2009 | 04/28/2009 | 12/01/2010 | 176065.92 | 1
1390 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009025 | This project involves the rehabilitation of interstate bridges 1-804, 1-805, 1-810, 1-811 and 1-812. This work includes cleaning and painting the steel beams,diaphragms and bearings. | Bridge Improvement | 05/08/2009 | 05/08/2009 | 04/01/2010 | 2349396.55 | 1
1391 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009026 | This streetscape improvement project is along Old Lancaster Pike from Valley Road to Errickson Drive. Improvements include; new sidewalks, upgrades to curb ramps, drainage modifications, decrotive cro | Transportation Enhancements | 05/07/2009 | 05/07/2009 | 12/01/2010 | 2880690.94 | 0.38
1392 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009027 | This project on Route 52 / Old Kennett Pike would replace current temporary traffic calming features with permanent ones. This work would improve safety for motorists and pedestrians. | Transportation Enhancements | 09/29/2009 | 09/29/2009 | 09/04/2010 | 1976610.33 | 0.65
1393 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009028 | This project will replace non-standard guardrail, guardrail components and end treatments as required for all state-maintained roads in New Castle County. | Safety/Traffic Management | 10/21/2009 | 10/21/2009 | 08/30/2012 | 630798.38 | 1
1394 | Delaware | STATEWIDE |  | 00 | 2009029 | This project will repaint existing pavement markings statewide. | Safety/Traffic Management | 08/31/2009 | 08/31/2009 | 06/01/2010 | 1264126.57 | 107.41
1395 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | 2009030 | This project involves the rehabilitation of interstate bridges 1-676, 1- 717, 1-719, 1-720, 1-738, 1-739 and 1-740. Work includes the replacement of bearings, expansion seal and/or joints, painting of | Bridge Improvement | 05/04/2009 | 05/04/2009 | 12/26/2010 | 4183921.19 | 1
1396 | Delaware | KENT | DOVER | 00 | 2009031 | This project will build the first phase of a DART Dover Transit Center on five acres on Water Street between Queen and West Streets. | Other | 12/08/2009 | 12/08/2009 | 03/08/2011 | 3602365 | 0.11
1397 | Delaware | KENT | DOVER | 00 | 2009033 | This project will rotomill, patch, and 2" hot-mox overlay at 3 locations, including miscellaneous concrete work (curb ramps) in Kent County. | Pavement Improvement | 09/29/2009 | 11/09/2009 | 06/01/2010 | 1228420.75 | 1
1398 | Delaware | NEW CASTLE |  | 0 | 2010012 | "Project includes improvements to 3 intersections in the Newark area. The improvements include extension of left turn lanes to assist traffic during the I-95 Newark toll plaza project, and other incid | Safety/Traffic Management | 03/23/2010 | 04/26/2010 | 05/15/2010 | 1050384.84 | 0.01
1399 | Delaware | KENT | DOVER | 00 | K356011 | This project improves saftey by channelizing the median at the intersection of SR 10 and Sorghum Mill Road to accommodate eastbound and westbound SR 10 left-turns. | Safety/Traffic Management | 06/17/2009 | 07/20/2009 | 11/01/2009 | 218880.81 | 0.15
1400 | Delaware | NEW CASTLE | WILMINGTON (NJ-MD-PA) | 00 | N024001 | This project will elevate the roadway, improve shoulders, underground utilities, pave and restripe the hot mix pavement on Market Street from "A" Street to just north of the Market/Walnut St split. | Pavement Improvement | 04/22/2009 | 04/22/2009 | 09/01/2011 | 13001108.13 | 1
1401 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | N056038 | This project entails constructing two highway speed EZ Pass Lanes in both the Northbound and Southbound directions of the Newark Toll Plaza located on I-95 near the DE/MD State Line. | New Construction | 04/17/2009 | 04/17/2009 | 12/01/2011 | 40804555.85 | 2.6
1402 | Delaware | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 00 | N059036 | This project will mill and resurface southbound I-95 from the Wilmington Viaduct to just south of the SR 141 interchange. | Pavement Improvement | 04/24/2009 | 04/24/2009 | 12/01/2009 | 2670167.53 | 2.83
1403 | Delaware | NEW CASTLE | WILMINGTON (NJ-MD-PA) | 00 | N397001 | "This project will replace the existing corrugated metal pipes with a double cell precast concrete box culvert. It also will reconstruct the roadway approaches, place guardrail as required, and place | Bridge Replacement | 04/06/2010 | 04/07/2010 | 09/25/2010 | 872610.47 | 0.023
1404 | Delaware | NEW CASTLE |  | 00 | N438002 | This project will expand the park & ride on along SR 299, west of SR 1. | Other | 06/05/2009 | 06/05/2009 | 01/01/2010 | 932672.49 | 0.29
1405 | Delaware | SUSSEX |  | 00 | S020003 | This project will involve hot-mix patching and 3 1/2" overlay at one location in Sussex County. | Pavement Improvement | 07/08/2009 | 07/20/2009 | 10/01/2009 | 1523946.62 | 5.09
1406 | Delaware | SUSSEX |  | 00 | S584003 | This project improves the railroad crossing at SR 404 and Newton Road by installing automatic gates, updating the cantilever lights and controller, and replace pre-cast concrete surface. | Other | 06/08/2009 | 10/19/2009 | 04/01/2010 | 362333.6 | 1
1407 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 1108027 | REPLACEMENT OF THE NEW YORK AVENUE BRIDGE WHICH CROSSES OVER METRO, AMTRACK AND CSX RAILROAD TRACKS | Bridge Improvement | 09/22/2009 |  |  | 25823004.7 | 0.1
1408 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 1300015 | CONSTRUCTION WILL INCLUDE SIDEWALK, CURB AND GUTTER, PAVING T, NEW STREETLIGHTS, TRAFFIC SIGNALS, SAFETY IMPROVEMENTS AND LANDSCAPING ALONG PENNSYLVANIA AVENUE FROM THE SOUSA BRIDGE TO SOUTHERN AVENUE | Pavement Improvement | 11/18/2009 |  |  | 18392820.99 | 1.4
1409 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 3000050 | THIS PROJECT IS MAINLY TO REPAVE THE ROADWAY; ALSO MINOR IMPROVEMENTS WILL BE DONE ALONG VARIOUS ROADWAYS WITHIN THE HISTORIC DUPONT CIRCLE BUSINESS DISTRICT | Pavement Improvement | 11/12/2009 |  |  | 5383959.4 | 0.48
1410 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 3105006 | RECONSTRUCT/RESURFACE ROADWAY, SIDEWALK, CURB, GUTTER AND WHEELCHAIR RAMPS. UPGRADE STREETLIGHT AND TRAFFIC SIGNALS. REPLACE WATER MAIN AND LANDSCAPING .ALONG 18TH STREET, FROM FLORIDA AVENUE TO MASSA | Pavement Improvement | 11/15/2009 |  |  | 5526764.7 | 0.53
1411 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 3207003 | REPLACEMENT OF THE EASTERN AVENUE BRIDGE THAT CROSSES OVER KENNILWORTH AVENUE | Bridge Improvement | 11/13/2009 |  |  | 4499569.75 | 0.1
1412 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 3207004 | REPLACEMENT OF THE EASTERN AVENUE BRIDGE THAT CROSSES OVER KENNILWORTH AVENUE | Pavement Improvement | 11/13/2009 |  |  | 6101847.25 | 0.1
1413 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 4116001 | RECONSTRUCT THE ROADWAY AND ADD NEW SIDEWALKS ALONG WESTERN AVENUE FROM CHESTNUT STREET TO OREGON AVENUE IN NORTHWEST DC | Pavement Improvement | 01/26/2010 |  |  | 2622528.44 | 0.52
1414 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888323 | THE WORK WILL INCLUDE UPGRADING OF STREETLIGHTS, WHEELCHAIR RAMPS, PLANTING TREES AS WELL AS REPAIRING SIDEWALKS AND GUTTERS AND AND REPAVING THE ROADWAY. THIS WORK WILL OCCUR ALONG 25 BLOCKS OF TH | Safety/Traffic Management | 08/10/2009 | 09/17/2009 |  | 6611873.89 | 1.36
1415 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888327 | INSTALL BATTERY BACKUP POWER SUPPLY FOR CRITICAL TRAFFIC LIGHTS THROUGHOUT THE CITY TO PROVIDE UP TO 8 HOURS OF POWER. | Safety/Traffic Management | 01/01/2010 |  |  | 1751131.58 | 0
1416 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888328 | REPAVING OF SECTIONS OF THE INTERSTATE HIGHWAY IN DC | Pavement Improvement | 04/24/2009 | 04/24/2009 |  | 1000000 | 14.14
1417 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888329 | IMPROVE STREETLIGHTS ALONG THE DALECARLIA PARKWAY AND BLADENSBURG ROAD | Safety/Traffic Management | 04/24/2009 | 04/24/2009 |  | 4845806.11 | 12.64
1418 | District of Columbia | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) | 00 | 8888332 | IMPROVE PEDESTRIAN FACILITIES THAT SERVICE NEIGHBORHOOD SCHOOLS | Transportation Enhancements | 01/07/2010 | 01/07/2010 |  | 2593767.6 | 0
1419 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA001 | This Okaloosa County project will improve safety at the existing intersection of State Road 85 South and State Road 123, near the Northwest Florida Regional airport, by providing a flyover ramp for mo | Pavement Widening | 12/05/2000 | 12/05/2000 | 06/30/2012 | 29688055 | 1.241
1420 | Florida | SANTA ROSA | PENSACOLA | 01 | ARRA002 | This Santa Rosa County project will widen the existing two-lane roadway to four with bike lanes and sidewalks to improve safety and relieve congestion. | Pavement Widening | 04/02/2001 | 04/02/2001 | 01/19/2012 | 6948432 | 0.984
1421 | Florida | BAY | PANAMA CITY | 02 | ARRA004 | Bay County is building a new bridge over Grand Lagoon for vehicles and pedestrians to improve safety and relieve congestion on Thomas Drive in Panama City Beach. | Bridge Improvement | 09/28/2009 | 09/28/2009 | 03/22/2011 | 13502328 | 0.822
1422 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA005 | Barrier walls and culverts will be installed on this Leon County safety improvement project to allow wildlife to pass under the road and improve driver safety along this roadway. | Transportation Enhancements | 08/18/2009 | 08/18/2009 | 09/17/2010 | 3281480 | 1.074
1423 | Florida | FRANKLIN |  | 02 | ARRA006 | Franklin County will construct approximately 2,500 feet of five-foot wide sidewalk along Bluff Road in Apalachicola to improve pedestrian safety. | Transportation Enhancements | 11/16/2009 | 11/16/2009 | 04/11/2010 | 116145 | 0.737
1424 | Florida | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17,19,20,21,22,23 | ARRA007 | The City of Hallandale Beach will improve pedestrian safety by installing brick pavers and stamped concrete crosswalks at various locations on West Hallandale Beach Boulevard. | Transportation Enhancements | 02/03/2010 | 02/08/2010 | 05/10/2010 | 234531 | 1.937
1425 | Florida | MARTIN | FORT PIERCE-STUART | 16,23 | ARRA010 | FDOT will build a new high level bridge over the south fork of the St. Lucie River and the Okeechobee Waterway between Palm City and Stuart to ease congestion and provide faster evacuation from the co | New Bridge Construction | 08/19/2009 | 08/19/2009 |  | 72238911 | 1.42
1426 | Florida | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17,19,20,21,22,23 | ARRA011 | The City of Wilton Manors will replace deteriorating pavement, build new sidewalks and bike lanes and plant landscaping to enhance N.E. 15th Avenue. | Transportation Enhancements | 03/16/2010 | 03/16/2010 | 06/16/2010 | 185900 | 0.01
1427 | Florida | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17,19,20,21,22,23 | ARRA012 | The City of Fort Lauderdale will improve pedestrian safety by building paved parking, adding sidewalks, installing pedestrian lighting and enhancing landscaping at various locations on NW 7 Street, NW | Transportation Enhancements | 06/15/2010 |  | 09/30/2010 | 500000 | 1.154
1428 | Florida | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17,19,20,21,22,23 | ARRA013 | The City of Deerfield Beach will improve access to the west entrance of the Deerfield Beach train station that serves Tri-Rail (commuter) and Amtrak customers by building a sidewalk and a pedestrian p | Transportation Enhancements | 12/07/2009 | 01/04/2010 | 05/04/2010 | 359765 | 0
1429 | Florida | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17,19,20,21,22,23 | ARRA014 | The City of Pembroke Pines will build new sidewalks at several locations along Pembroke Road and 196th Avenue to provide pedestrian access between major roads, subdivisions , schools, shops and to pro | Transportation Enhancements | 12/07/2009 | 12/14/2009 | 04/30/2010 | 526915 | 0.986
1430 | Florida | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17,19,20,21,22,23 | ARRA017 | The City of Lighthouse Point will build sidewalks and install pedestrian lighting to improve safety on N.E. 44 Street. | Transportation Enhancements | 01/18/2010 | 01/26/2010 | 06/30/2010 | 160000 | 0.212
1431 | Florida | INDIAN RIVER | VERO BEACH | 15 | ARRA018 | Indian River County will plant additional landscaping to enhance the median of 58th Avenue for 3.05 miles from Oslo Road to 16th Avenue in southern Indian River County. | Transportation Enhancements | 01/04/2010 | 01/06/2010 | 04/16/2010 | 277648 | 3.05
1432 | Florida | MARTIN | FORT PIERCE-STUART | 16,23 | ARRA019 | Martin County will provide access for bicyclists and pedestrians by building a one mile-long shared-use path from S.E. Grafton Avenue to Seabranch Preserve State Park south of Stuart. | Transportation Enhancements | 04/26/2010 | 04/26/2010 | 06/15/2010 | 187500 | 0.931
1433 | Florida | ST LUCIE | FORT PIERCE-STUART | 16,23 | ARRA020 | The City of Port St. Lucie will add 0.6 miles of sidewalk to improve pedestrian safety on the east side of California Boulevard from Heatherwood Boulevard to Fairway Isles. | Transportation Enhancements | 01/21/2010 | 02/01/2010 | 03/31/2010 | 73189 | 0.611
1434 | Florida | PALM BEACH | WEST PALM BEACH | 16,19,22,23 | ARRA021 | Palm Beach County will provide safe access for bicyclists and pedestrians on the eastern levee of the South Florida Water Management drainage canal in the City of Palm Beach Gardens and unincorporated | Transportation Enhancements | 03/01/2010 | 03/08/2010 | 09/04/2010 | 750000 | 0
1435 | Florida | ST LUCIE | FORT PIERCE-STUART | 16,23 | ARRA022 | FDOT will improve safety for motorists by replacing the 56-year old structurally deficient Juanita Street Bridge over Taylor Creek in Fort Pierce, as well as improve bicyclist and pedestrian safety by | Bridge Improvement | 04/05/2010 |  |  | 1155082 | 0.102
1436 | Florida | ST LUCIE | FORT PIERCE-STUART | 16,23 | ARRA023 | The City of Port St. Lucie will improve a 2.3-mile segment of Westmoreland by rebuilding the road using a new type of pavement that will wear longer and reduce the need for repairs. | Pavement Improvement | 12/31/2009 | 12/31/2009 | 05/28/2010 | 1023808 | 2.396
1437 | Florida | ST LUCIE | FORT PIERCE-STUART | 16,23 | ARRA024 | The City of Fort Pierce will rebuild 13th Street from Orange Avenue to Avenue D using a new type of pavement that will last longer and reduce the need for repairs, reduce flooding by installing a new | Pavement Improvement | 05/31/2010 | 05/31/2010 | 09/01/2010 | 879800 | 0.3
1438 | Florida | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16,19,22,23 | ARRA025 | The Village of Wellington will repave and add street lights to improve 5.4 miles of Forest Hill Boulevard. | Pavement Improvement | 01/12/2010 | 01/12/2010 | 12/31/2011 | 5221287 | 7.254
1439 | Florida | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16,19,22,23 | ARRA026 | The Village of Royal Palm Beach will improve two miles of Royal Palm Beach Boulevard by adding sidewalks for pedestrians and resurfacing the road using a new type of pavement that will last longer and | Pavement Improvement | 04/05/2010 | 04/12/2010 | 05/15/2010 | 2578922 | 4.051
1440 | Florida | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16,19,22,23 | ARRA027 | The City of Riviera Beach will replace deteriorating pavement on 3.3 miles of A1A from U.S. 1 at Blue Heron Boulevard north to Burnt Bridge on Singer Island. | Pavement Improvement | 01/12/2010 |  | 12/31/2011 | 4067290 | 6.688
1441 | Florida | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16,19,22,23 | ARRA028 | FDOT will restore vehicle traffic by replacing the Tequesta Drive Bridge over the North Fork of the Loxahatchee River. The bridge was recently closed due to its unsafe condition. | Pavement Improvement | 10/28/2009 | 11/18/2009 | 08/05/2010 | 2689633 | 0.23
1442 | Florida | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16,19,22,23 | ARRA029 | The City of Boynton Beach will improve 0.6 miles of Seacrest Boulevard by adding street lights and resurfacing the road using a new type of pavement that will last longer and reduce the need for repai | Pavement Improvement | 01/12/2010 | 01/12/2010 | 03/24/2011 | 1161276 | 0.671
1443 | Florida | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16,19,22,23 | ARRA030 | Palm Beach County will improve 14.7 miles of Military Trail between Clint Moore Road in Boca Raton and Lake Worth Road in Lake Worth by resurfacing the existing pavement and improve pedestrian safety | Pavement Improvement | 07/19/2010 |  |  | 6857120 | 14.664
1444 | Florida | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16,19,22,23 | ARRA031 | FDOT will build a new four-lane bridge between Hillsboro Boulevard/ State Road 810 in Deerfield Beach (Broward County) and S.W. 18th Street in Boca Raton (Palm Beach County), crossing over local stree | Pavement Widening | 10/29/2009 | 10/29/2009 |  | 2574095 | 0.234
1445 | Florida | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16,19,22,23 | ARRA032 | FDOT will replace aging underground sewer and water lines, add sidewalks, curbs, drainage and resurface .316 miles of Southeast 3rd Street in Belle Glade. | Pavement Improvement | 01/12/2010 | 03/24/2010 |  | 960943 | 0.316
1446 | Florida | MARTIN | FORT PIERCE-STUART | 16,23 | ARRA033 | Martin County will add a southbound right-turn lane at the intersection of State Road 707 and N.W. Wright Boulevard to ease congestion just north of the Roosevelt Bridge over the St. Lucie River in St | Pavement Improvement | 05/24/2010 | 05/24/2010 | 08/25/2010 | 137172 | 0.122
1447 | Florida | MARTIN | FORT PIERCE-STUART | 16,23 | ARRA034 | Martin County is replacing the deteriorating pavement on one mile of Baker Road from U.S. 1 to Savannah Road in northeastern Martin County. | Pavement Improvement | 10/05/2009 | 10/12/2009 | 12/01/2009 | 250000 | 1.011
1448 | Florida | MARTIN | FORT PIERCE-STUART | 16,23 | ARRA035 | Martin County will improve nine miles of County Road 609 from State Road 710 north of Indiantown north to County Road 714 by replacing aging pavement. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 03/01/2010 | 2100000 | 9
1449 | Florida | INDIAN RIVER | VERO BEACH | 15 | ARRA036 | FDOT will resurface County Road 507 from the Fellsmere city limits north 3.09 miles to the Indian River/Brevard County line to extend the life of the road. | Pavement Improvement | 11/16/2009 | 11/16/2009 | 05/04/2010 | 651192 | 6.362
1450 | Florida | PASCO |  | 05,09 | ARRA037 | In Pasco County, this project widens 2.8 miles of U.S. 41 from the existing two lanes to a four-lane divided road with medians and turn lanes to reduce congestion. | Pavement Widening | 07/01/2009 | 07/15/2009 | 06/01/2011 | 14697106 | 2.841
1451 | Florida | ALACHUA |  | 03,06 | ARRA038 | In the City of Alachua, in northern Alachua County, a sidewalk and bike lane will be built along Northwest County Road 235A from U.S. 441 to Santa Fe High School which will improve the safety of stude | Transportation Enhancements | 08/20/2009 | 08/20/2009 | 06/15/2012 | 67963 | 1
1452 | Florida | ALACHUA |  | 03,06 | ARRA039 | In Alachua County, a concrete sidewalk will be built along the north side of Southwest Eighth Avenue between Southwest 75th Street (Tower Road) and end of the road which will provide a safer place for | Transportation Enhancements | 08/20/2009 | 08/20/2009 | 06/15/2012 | 90926 | 1
1453 | Florida | LEVY |  | 05,06 | ARRA040 | In Levy County, bike lanes will be built along both sides of State Road 320 from Manatee Springs State Park to U.S. 19 to improve recreational options for campers at the state park as well as provide | Transportation Enhancements | 08/20/2009 | 08/20/2009 | 06/15/2012 | 1666886 | 5.784
1454 | Florida | PUTNAM |  | 03,07 | ARRA041 | In Bradford County, a 12-foot wide, 4-mile long multi-use trail will be built along the old abandoned railroad line along State Road 100 from the Clay County line to County Road 315 to provide recreat | Transportation Enhancements | 10/12/2009 | 10/12/2009 | 06/15/2012 | 1165746 | 4.366
1455 | Florida | ALACHUA | GAINESVILLE | 03,06 | ARRA042 | In Gainesville, an off-road bicycle path will be built on the abandoned railroad property alongside West Sixth Street from Southeast Second Avenue to Northwest 16th Avenue for recreation and those who | Transportation Enhancements | 08/04/2009 | 08/04/2009 | 06/15/2012 | 434867 | 1.54
1456 | Florida | ALACHUA | GAINESVILLE | 03,06 | ARRA043 | In Gainesville, Northeast Eighth Avenue will be repaved between North Main Street (State Road 329) and Northeast Boulevard to improve the road surface. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/15/2012 | 113575 | 0.311
1457 | Florida | ALACHUA |  | 03,06 | ARRA045 | To promote economic development in the western area of Alachua County, a southbound turn lane will be added to U.S. 41 just south of Newberry onto Southwest 30th Avenue. | Safety/Traffic Management | 08/20/2009 | 08/20/2009 | 06/15/2012 | 443275 | 0.001
1458 | Florida | ALACHUA | GAINESVILLE | 03,06 | ARRA046 | In Gainesville, North Main Street (County Road 329) will be reconstructed from four to two lanes with a center turn between Northwest Eighth and 16th avenues which will increase safety. It will also b | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 943082 | 1.681
1459 | Florida | MIAMI-DADE |  | 17,18,20,21,25 | ARRA047 | Cash toll collections will be replaced with all-electronic tolling on a 21-mile segment of Florida?s Turnpike located between State Road 836 in Miami and County Line Road in Miramar.? The project will | Pavement Improvement | 09/30/2009 | 09/30/2009 | 10/19/2011 | 22000000 | 12
1460 | Florida | ALACHUA |  | 03,06 | ARRA048 | Southwest 122nd Street in Alachua County will be resurfaced and a five-foot paved shoulder added south of Archer Road (State Road 24) to Southwest 89th Avenue which will improve safety. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 402913 | 0.343
1461 | Florida | BAKER |  | 04 | ARRA049 | In Glen St. Mary, County Road 125 will be resurfaced from U.S. 90 to Glen Haven Lane and the culverts will be upgraded to make the roadway a safer route to drive. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 589224 | 1.556
1462 | Florida | BRADFORD |  | 06 | ARRA050 | In Bradford County, Northwest County Road 229 between State Road 16 and Northwest 55th Avenue will be repaved to improve the road surface. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 726641 | 2
1463 | Florida | CLAY |  | 03,06 | ARRA051 | In St. Johns County, County Road 214 will be resurfaced between State Road 100 and County Road 315C to improve the ride. | Pavement Improvement | 08/07/2009 | 08/07/2009 | 06/15/2012 | 1513929 | 6.584
1464 | Florida | COLUMBIA |  | 04 | ARRA052 | In western Columbia County, County Road 250 (Lake Jeffery Road) will be widened from 10 to 12-foot lanes and resurfaced from Interstate 75 to the Suwannee County line to improve the road surface. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 1134339 | 2.9
1465 | Florida | COLUMBIA |  | 04 | ARRA053 | In Lake City, County Road 129 (Northwest Lake Jeffery Road) will be resurfaced between U.S. 90 and the CSX Railroad and a crosswalk added at Parkview Baptist Church to provide additional safety on a b | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 391522 | 0.664
1466 | Florida | DIXIE |  | 02 | ARRA054 | In Cross City, the intersection of U.S. 19 (State Road 55) and County Road 351A will be improved by widening the intersection to allow log trucks and larger vehicles to safely turn. The road also will | Safety/Traffic Management | 08/20/2009 | 08/20/2009 | 06/15/2012 | 415337 | 0.1
1467 | Florida | MADISON |  | 04 | ARRA055 | In Madison County, County Road 53 between Interstate 10 and Southeast Roger Sink Road will be resurfaced to improve the ride. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/15/2012 | 855844 | 1.899
1468 | Florida | PUTNAM |  | 03,07 | ARRA056 | St. Johns Avenue will be resurfaced between State Road 19 and Palm Avenue which will improve the roadway for traffic headed toward downtown Palatka. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/15/2012 | 274088 | 1.176
1469 | Florida | PUTNAM |  | 03,07 | ARRA057 | Moseley Avenue in Palatka will be resurfaced from U.S. 17 to State Road 100 and the sidewalks will be repaired and made handicap-accessible to provide a safer ride for motorists and a safer way for pe | Pavement Improvement | 12/15/2009 | 12/15/2009 | 07/05/2010 | 356253 | 1.61
1470 | Florida | PUTNAM |  | 03,07 | ARRA058 | In Pomona Park in southern Putnam County, a new concrete sidewalk will be built between U.S. 17 and Cisco Road to provide a safer path for pedestrians. | Transportation Enhancements | 08/04/2009 | 08/04/2009 | 06/15/2012 | 136772 | 3.835
1471 | Florida | PUTNAM |  | 03,07 | ARRA059 | In Putnam County, two culverts will be replaced on Silver Lake Drive over Devall Branch and Two Mile Creek with new concrete culverts to improve the drainage in the area. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/15/2012 | 453008 | 3.44
1472 | Florida | PUTNAM |  | 03,07 | ARRA060 | In western Putnam County, a concrete sidewalk and asphalt bike path will be built along a section of County Road 315 to improve safety for pedestrians and bicyclists. | Transportation Enhancements | 08/04/2009 | 08/04/2009 | 06/15/2012 | 333013 | 2.082
1473 | Florida | SUWANNEE |  | 02 | ARRA061 | A two mile section of County Road 252 in eastern Suwannee County, between the Columbia County line and County Road 137, will be widened from 10 to 12-foot lanes and repaved to improve the road surface | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 886333 | 1.915
1474 | Florida | ST JOHNS |  | 07 | ARRA062 | In St. Johns County, West King Street (County Road 214) between County Road 13 and 13A will have several culverts or pipes replaced and extended to help with drainage issues. | Pavement Improvement | 11/23/2009 | 11/23/2009 | 10/17/2010 | 342033 | 3.946
1475 | Florida | ST JOHNS |  | 07 | ARRA063 | In St. Johns County, West King Street (County 214) will be widened to improve safety and the road resurfaced between County 13 and 13A to improve the ride. | Pavement Improvement | 11/23/2009 | 11/23/2009 | 10/17/2010 | 729621 | 7.891
1476 | Florida | GILCHRIST |  | 06 | ARRA064 | In Gilchrist County, County Road 341 will be repaved between State Road 26 and the Levy County line to improve the road surface. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/15/2012 | 262290 | 1.482
1477 | Florida | HAMILTON |  | 04 | ARRA065 | In Hamilton County, County Road 135 between White Springs and Southeast 177th Court will be repaved to improve the road surface.. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/15/2012 | 791978 | 2.9
1478 | Florida | LAFAYETTE |  | 02 | ARRA066 | In Lafayette County, County Road 354 from U.S. 27 to County Road 361 will be repaved to improve the road surface. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/15/2012 | 499567 | 2.707
1479 | Florida | LEVY |  | 05,06 | ARRA067 | In Levy County, County Road 40 will be repaved between Park Street in Inglis and the Marion County line to improve the road surface and make it safer. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 806973 | 7.413
1480 | Florida | NASSAU |  | 04 | ARRA068 | In Nassau County, County Road 2 will be resurfaced between County Road 121 and the Georgia line and the Agricultural Inspection Station ramps will be repaved to improve safety for motorists. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 337858 | 1.381
1481 | Florida | PUTNAM |  | 03,07 | ARRA069 | In Crescent City in southern Putnam County, a new concrete sidewalk will be built along East Grand Rondo from Central Street to County Road 308 to provide a safer route for pedestrians. | Transportation Enhancements | 08/04/2009 | 08/04/2009 | 06/15/2012 | 91669 | 0.1
1482 | Florida | TAYLOR |  | 02 | ARRA070 | In Taylor County, County Road 14 will be resurfaced between U.S. 221 in Shady Grove and the Madison County line to provide a safer road. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 964362 | 3.063
1483 | Florida | UNION |  | 04 | ARRA071 | County Road 231 in Union County will be resurfaced between the Department of Corrections Reception and Medical Center and the Bradford County line to improve the ride. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/15/2012 | 458012 | 1.009
1484 | Florida | CLAY | JACKSONVILLE | 03,06 | ARRA072 | In Clay County, Peoria Road (County Road 224A) will be widened to provide a center turn lane from College Drive (County Road 224) to Moody Road to improve traffic flow. An intersection improvement wil | Safety/Traffic Management | 08/04/2009 | 08/04/2009 | 06/15/2012 | 829429 | 0.241
1485 | Florida | CLAY | JACKSONVILLE | 03,06 | ARRA073 | In Orange Park, an additional right turn lane will be added to Kingsley Avenue at U.S. 17 to increase the amount of traffic that can turn onto U.S. 17. | Safety/Traffic Management | 08/07/2009 | 08/07/2009 | 06/15/2012 | 390148 | 0.001
1486 | Florida | CLAY | JACKSONVILLE | 03,06 | ARRA074 | Four lanes on Knight Boxx Road (County Road 220B) in Orange Park in Clay County will be resurfaced from Blanding Boulevard (State Road 21) to County Road 220 to provide a safer ride. | Pavement Improvement | 08/07/2009 | 08/07/2009 | 06/15/2012 | 479970 | 1.206
1487 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA075 | In Jacksonville, for Alta Drive and New Berlin Road, the existing pavement will be resurfaced and paved shoulders added to improve the road surface between Zoo Parkway (State Road 105) and State Road | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 3853102 | 2.012
1488 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA076 | Ninth Street in Jacksonville Beach will be improved by repairing the existing drainage system and resurfacing between Osceola Avenue and First Street. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 4177278 | 1.5
1489 | Florida | NASSAU | JACKSONVILLE | 04 | ARRA077 | In Fernandina Beach, North 14th Street will be resurfaced between Atlantic Avenue and Pogy Place. The bridge railing will be replaced at Egans Creek Bridge to make the crossing safer for motorists, pe | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 520379 | 1.76
1490 | Florida | NASSAU | JACKSONVILLE | 04 | ARRA078 | North Eighth Street in Fernandina Beach between Dade Street and the Port of Fernandina will be repaved to improve the road surface. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 06/15/2012 | 68619 | 0.464
1491 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA079 | In St. Augustine, West King Street or County Road 214 will be resurfaced between County Road 13 and Palmer Avenue to provide a safer road. | Pavement Improvement | 11/23/2009 | 11/23/2009 | 10/17/2010 | 1505182 | 14.979
1492 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA080 | To improve capacity and safety at the Interstate 95/State Road 207 interchange in St. Johns County, the northbound and southbound ramps will be widened and a turn lane will be added for westbound traf | Safety/Traffic Management | 07/22/2009 | 07/22/2009 | 06/15/2012 | 630135 | 0.001
1493 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA081 | In St. Augustine, concrete sidewalks will be provided along Del Monte, Varella and Durbin Creek Boulevard to increase safety for pedestrians. | Transportation Enhancements | 08/20/2009 | 08/20/2009 | 06/15/2012 | 396926 | 5.968
1494 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA082 | North of St. Augustine, a new traffic signal system along County Road 210 and Racetrack Road between U.S. 1 and County Road 16A will improve traffic flow along county roads. | Safety/Traffic Management | 08/20/2009 | 08/20/2009 | 06/15/2012 | 313387 | 16.16
1495 | Florida | CITRUS |  | 05 | ARRA083 | In Citrus County, a new multi-use path is being built along U.S. 19 in Crystal River between NW 19th Street and W. State Park Street to provide an area for both bicyclists and pedestrians to travel sa | Transportation Enhancements | 09/04/2009 | 09/14/2009 | 01/04/2010 | 170000 | 0.477
1496 | Florida | CITRUS |  | 05 | ARRA084 | In Citrus County, this project repaves 2.4 miles of Fort Island Trail from North Palm Springs Terrace to U.S. 19/Suncoast Boulevard to improve the road surface. | Pavement Improvement | 12/14/2009 | 12/14/2009 | 03/13/2010 | 328560 | 1.461
1497 | Florida | CITRUS |  | 05 | ARRA085 | In Citrus County, this project repaves 1.5 miles of Ozello Trail from U.S. 19 to Winterset Avenue to improve the road surface. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 02/27/2010 | 180711 | 1.455
1498 | Florida | CITRUS |  | 05 | ARRA086 | In Citrus County, to enhance the ride ability of the roadway, this project resurfaces 2.7 miles of Croft Ave. from State Road 44 to north of Harley Street. | Pavement Improvement | 11/09/2009 | 11/11/2009 | 02/08/2010 | 388134 | 2.726
1499 | Florida | CITRUS |  | 05 | ARRA087 | In Citrus County, this project repaves one mile of Turner Camp Road from Ella Avenue to Twin Lakes Drive to improve the road surface. | Pavement Improvement | 11/12/2009 | 11/18/2009 | 02/09/2010 | 149100 | 1.53
1500 | Florida | CITRUS |  | 05 | ARRA088 | In Citrus County, this project repaves six miles of Cardinal Street from U.S. 19 to County Road 491 (Lecanto Highway) to improve the road surface. | Pavement Improvement | 12/14/2009 | 01/18/2010 | 06/15/2010 | 709410 | 6.151
1501 | Florida | CITRUS |  | 05 | ARRA089 | In Citrus County, this project resurfaces 2.5 miles of County Road 491 from State Road 44 to County Road 486 due to the poor condition of the road. | Pavement Improvement | 11/22/2009 | 11/22/2009 | 02/19/2010 | 503100 | 2.515
1502 | Florida | INDIAN RIVER | VERO BEACH | 15 | ARRA090 | FDOT will improve 2.69 miles of Barber Street in Sebastian by repaving the road and installing a new drainage system. | Pavement Improvement | 11/16/2009 | 11/16/2009 |  | 1806847 | 2.686
1503 | Florida | CITRUS |  | 05 | ARRA091 | In Citrus County, due to the poor condition of the road, this project resurfaces 6.8 miles of County Road 491 from Pine Ridge Boulevard to State Road 200. | Pavement Improvement | 01/04/2010 | 01/13/2010 | 04/03/2010 | 777534 | 7.018
1504 | Florida | CITRUS |  | 05 | ARRA093 | In Citrus County, this project repairs approximately 200 feet of the Withlapopka Causeway shoulders to prevent further erosion along the canal. | Pavement Improvement | 03/29/2010 | 04/05/2010 | 06/12/2010 | 594050 | 0.216
1505 | Florida | CITRUS |  | 05 | ARRA094 | In Citrus County, this project repaves 5.6 miles of County Road 480 (Stagecoach Road) from County Road 491 (Lecanto Highway) to County Road 581 (Pleasant Grove Road) to improve the road surface. | Pavement Improvement | 11/09/2009 | 11/10/2009 | 03/06/2010 | 1042656 | 5.722
1506 | Florida | CITRUS |  | 05 | ARRA095 | In Citrus County, this project adds a new traffic signal and a right turn lane on State Road 44 at the Citrus County Landfill to ease access and minimize backups at the entrance to the landfill. | Pavement Improvement | 09/15/2009 | 01/11/2010 | 06/12/2010 | 584357 | 0.577
1507 | Florida | CITRUS |  | 05 | ARRA096 | In Citrus County, this project repaves 2.4 miles of Grover Cleveland Boulevard from Tedna Terrace to County Road 491 to improve the road surface. | Pavement Improvement | 12/07/2009 | 12/17/2009 | 03/06/2010 | 259860 | 2.403
1508 | Florida | CITRUS |  | 05 | ARRA097 | In Citrus County, this project repaves 1.6 miles of Halls River Road from the Halls River Bridge to Fishbowl Drive to improve the road surface. | Pavement Improvement | 11/30/2009 | 12/14/2009 | 02/28/2010 | 121292 | 1.067
1509 | Florida | HERNANDO |  | 05 | ARRA099 | In eastern Hernando County, this project resurfaces 1.8 miles of Cortez Blvd (State Road 50) between U.S. 98 and the railroad tracks to the east to provide a safer ride. | Pavement Improvement | 08/15/2009 | 08/31/2009 | 11/12/2009 | 737444 | 1.844
1510 | Florida | INDIAN RIVER | VERO BEACH | 15 | ARRA100 | FDOT will resurface 3.5 miles of 20th Avenue from Oslo Road to State Road 60 in Vero Beach to extend the life of the road. | Pavement Improvement | 12/11/2009 | 12/11/2009 |  | 2271526 | 5.543
1511 | Florida | HERNANDO |  | 05 | ARRA101 | In Hernando County, this project repaves 2.2 miles of Mariner Boulevard from Maderia Street to Augustine Road to improve the road surface. | Pavement Improvement | 01/04/2010 | 01/17/2010 | 04/23/2010 | 814015 | 2.204
1512 | Florida | HERNANDO |  | 05 | ARRA102 | In Hernando County, this project repaves 0.6 miles of Spring Hill Drive from Pinehurst Drive to Deltona Boulevard to improve the road surface. | Pavement Improvement | 10/08/2009 | 10/08/2009 | 12/07/2009 | 277591 | 0.657
1513 | Florida | HERNANDO |  | 05 | ARRA103 | In Hernando County, this project repaves 1.5 miles of Deltona Boulevard from State Road 50 to Northcliffe Boulevard to improve the road surface. | Pavement Improvement | 10/15/2009 | 10/15/2009 | 12/04/2009 | 248011 | 1.489
1514 | Florida | HERNANDO |  | 05 | ARRA104 | In Hernando County, this project repaves 2.5 miles of Deltona Boulevard from Spring Hill Drive to Philatelic Drive to improve the road surface. | Pavement Improvement | 02/14/2010 | 02/14/2010 | 06/04/2010 | 466945 | 2.508
1515 | Florida | HERNANDO |  | 05 | ARRA105 | In Hernando County, this project repaves 2.8 miles of Spring Hill Drive from Mariner Boulevard to Deltona Boulevard to improve the road surface. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 03/15/2010 | 893110 | 3.038
1516 | Florida | HERNANDO |  | 05 | ARRA106 | In Hernando County, due to the poor condition of the road, this project replaces 2.1 miles of the asphalt surface on Burwell Rd. (County Road 575) and widens the 10-foot lanes to 12-foot lanes from St | Pavement Improvement | 10/22/2009 | 10/22/2009 | 12/11/2009 | 270715 | 2.049
1517 | Florida | HERNANDO |  | 05 | ARRA107 | In Hernando County, due to the poor condition of the road, this project resurfaces 3.8 miles of Citrus Way and widens the 11-foot lanes to 12-foot lanes from Ft. Dade Avenue to south of Centralia Road | Pavement Improvement | 01/05/2010 | 01/06/2010 | 06/18/2010 | 762757 | 3.826
1518 | Florida | HERNANDO |  | 05 | ARRA108 | In Hernando County, this project repaves 1.4 miles of Yontz Road from U.S. 98 to Howell Avenue to improve the road surface. | Pavement Improvement | 12/15/2009 | 12/15/2009 | 01/14/2010 | 276140 | 1.433
1519 | Florida | HERNANDO |  | 05 | ARRA109 | In Hernando County, this project repaves one mile of North Avenue from Howell Avenue to Ponce de Leon Boulevard to improve the road surface. | Pavement Improvement | 02/28/2010 | 03/01/2010 | 05/28/2010 | 241465 | 0.743
1520 | Florida | HERNANDO |  | 05 | ARRA110 | In Hernando County, 20 miles of the asphalt surface of the Suncoast Trail is being replaced due to the poor condition of the trail. | Transportation Enhancements | 08/31/2009 | 09/21/2009 | 04/27/2010 | 759000 | 0
1521 | Florida | HILLSBOROUGH | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,11,12 | ARRA113 | In Hillsborough County, this project will add new lighting, landscaping and brick sidewalks for safety purposes on 56th Street from Temple Heights Road to east of 98th Avenue. | Transportation Enhancements | 10/19/2009 | 11/23/2009 | 06/11/2010 | 348298 | 0.146
1522 | Florida | PASCO |  | 05,09 | ARRA124 | In Pasco County, this project builds a new three mile, eight-foot wide trail from Congress Street to Starkey Boulevard to accommodate bicyclists and pedestrians. | Transportation Enhancements | 01/27/2010 | 02/08/2010 | 07/22/2010 | 616243 | 0
1523 | Florida | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,10,11 | ARRA129 | In Pinellas County, this project converts the existing southbound lane of East Avenue to a trail for pedestrians and bicyclists to travel safely between Drew Street and Turner Street. | Transportation Enhancements | 10/19/2009 | 10/19/2009 | 07/21/2010 | 313596 | 0.001
1524 | Florida | MIAMI-DADE | MIAMI-HIALEAH, FL | 17,18,20,21,25 | ARRA134 | This project is the final and largest section of the 12-part Palmetto Expressway (State Road 826) Improvement Program which consists of major construction along a 16-mile corridor. | Pavement Widening | 11/13/2009 | 11/25/2009 |  | 89175975 | 2.979
1525 | Florida | ST LUCIE | FORT PIERCE-STUART | 16,23 | ARRA135 | FDOT is widening 4.35 miles of State Road 70 in western St. Lucie County to a four-lane, divided highway and adding shoulders for safety on this major cross-state business and evacuation route. | Pavement Widening | 07/27/2009 | 08/03/2009 | 06/30/2012 | 15795655 | 4.356
1526 | Florida | BROWARD | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,19,20,21,22,23 | ARRA136 | FDOT will build a new four-lane bridge between Hillsboro Boulevard/ State Road 810 in Deerfield Beach (Broward County) and S.W. 18th Street in Boca Raton (Palm Beach County), crossing over local stree | Pavement Widening | 10/29/2009 | 10/29/2009 | 07/13/2012 | 38349338 | 0.46
1527 | Florida | GULF |  | 02 | ARRA137 | This pedestrian safety project includes sidewalk and landscape improvements in the City of Port St. Joe in Gulf County. | Transportation Enhancements | 10/23/2009 | 11/02/2009 | 06/28/2010 | 343118 | 0.297
1528 | Florida | HOLMES |  | 01 | ARRA138 | This project will repair the existing sidewalk and construct additional sidewalk near Bonifay Middle School to improve pedestrian safety in Holmes County. | Transportation Enhancements | 07/29/2009 | 07/29/2009 | 07/28/2010 | 89021 | 0.239
1529 | Florida | WASHINGTON |  | 01 | ARRA139 | The City of Chipley will construct approximately 900 feet of five-foot wide sidewalk along State Road 77 to improve pedestrian safety in Washington County. | Transportation Enhancements | 10/06/2009 | 10/06/2009 | 02/18/2010 | 49923 | 0.172
1530 | Florida | GADSDEN |  | 02 | ARRA140 | Five-foot wide sidewalks along various streets within the city limits of Midway will be constructed to improve pedestrian safety in Gadsden County. | Transportation Enhancements | 08/18/2009 | 08/18/2009 | 04/17/2010 | 463754 | 1.35
1531 | Florida | GADSDEN | TALLAHASSEE | 02 | ARRA141 | A five-foot wide sidewalk along State Road 267 in the City of Quincy has been constructed to improve pedestrian safety in Gadsden County. | Transportation Enhancements | 08/18/2009 | 08/18/2009 | 04/17/2010 | 79110 | 0.272
1532 | Florida | FRANKLIN |  | 02 | ARRA142 | Franklin County will construct approximately 1,600 feet of five-foot wide sidewalk along Franklin Boulevard to improve pedestrian safety. | Transportation Enhancements | 11/09/2009 | 11/09/2009 | 02/07/2010 | 53321 | 0.139
1533 | Florida | JACKSON |  | 02 | ARRA143 | Jackson County will construct a five-foot wide sidewalk along Riverforest Road to improve pedestrian safety. | Transportation Enhancements | 10/15/2009 | 10/15/2009 | 03/30/2010 | 42024 | 0.538
1534 | Florida | COLLIER | NAPLES | 14,25 | ARRA144 | Build a second two-lane bridge next to the existing Jolley Bridge to give drivers a four-lane bridge that connects Marco Island to U.S. 41 and reduces congestion during heavy travel times. | New Bridge Construction | 09/10/2009 | 09/21/2009 | 10/03/2011 | 27659767 | 0.783
1535 | Florida | POLK | LAKELAND | 05,12,15 | ARRA145 | Construct a new two-lane road to provide a direct connection between State Road 33 and the Pace Road Interchange at the Polk Parkway for easy access to the new University of South Florida Polytechnic | New Construction | 12/29/2009 | 01/06/2010 | 02/28/2012 | 37049661 | 0
1536 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA147 | Construct Metro Extension (State Road 739), a new six-lane road that connects U.S. 41 and Six Mile Cypress Parkway in Lee County and relieves heavy traffic on U.S. 41. It will also serve as an alterna | New Construction | 04/29/2009 | 07/25/2009 | 03/10/2012 | 34820398 | 2.772
1537 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA148 | Widen U.S. 301 in Sarasota from four to six lanes to relieve roadway congestion. Improvements to drainage and sidewalks will also enhance safety in the area. | Pavement Widening | 09/02/2009 | 09/16/2009 | 08/28/2011 | 9699352 | 2.007
1538 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA149 | Install communications devices at 88 intersections throughout Manatee County and connect them to the Manatee Traffic Management Center to improve traffic congestion and emergency response times. | Safety/Traffic Management | 09/30/2009 | 10/13/2009 | 06/29/2011 | 6106640 | 0
1539 | Florida | CHARLOTTE |  | 13,14,16 | ARRA151 | Replace the old Cape Haze Drive bridge over Amberjack Cove Waterway in Charlotte County with a new bridge with wider lanes, shoulders and sidewalks. | Pavement Improvement | 09/09/2009 | 11/02/2009 | 06/01/2010 | 1087247 | 0.241
1540 | Florida | CHARLOTTE | PUNTA GORDA | 13,14,16 | ARRA152 | Construct intersection improvements at State Road 776/Coliseum Boulevard in Charlotte County, including new turn lanes and traffic signals to move traffic more efficiently through this area. | Pavement Improvement | 09/29/2009 | 09/29/2009 | 07/05/2010 | 549865 | 0.207
1541 | Florida | CHARLOTTE |  | 13,14,16 | ARRA153 | Add two new right turn lanes on Veterans Boulevard to improve traffic flow at the Murdock Circle intersection in Charlotte County. | Pavement Improvement | 09/29/2009 | 09/29/2009 | 07/05/2010 | 231333 | 0.01
1542 | Florida | CHARLOTTE |  | 13,14,16 | ARRA154 | Lengthen the left turn lane on State Road 776 at the Oriole Boulevard intersection to improve traffic movement through the intersection in Charlotte County. | Pavement Improvement | 09/29/2009 | 09/29/2009 | 07/05/2010 | 100009 | 0.172
1543 | Florida | DE SOTO |  | 13 | ARRA155 | Pave five miles of County Road 760 from County Road 769 to U.S. 17 in Desoto County to improve the road surface. | Pavement Improvement | 09/16/2009 | 10/24/2009 | 07/08/2010 | 1503716 | 3.17
1544 | Florida | GLADES |  | 16 | ARRA156 | Pave County Road 720 in Glades County from the Hendry County line to five miles west to improve the road surface. | Pavement Improvement | 09/15/2009 | 11/25/2009 | 08/11/2010 | 2341524 | 5
1545 | Florida | HARDEE |  | 13 | ARRA157 | Resurface Main Street (County Road 664) in the city of Bowling Green from Doc Coil Road to east of U.S.17 to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 09/21/2009 | 10/24/2009 | 05/03/2010 | 743800 | 3.5
1546 | Florida | HENDRY |  | 16,23 | ARRA158 | Pave County Road 832 in Hendry County from State Road 29 to nine miles east to improve the road surface. | Pavement Improvement | 07/28/2009 | 09/15/2009 | 08/30/2010 | 1595142 | 9
1547 | Florida | HIGHLANDS |  | 16 | ARRA159 | Resurface Memorial Drive (County Road 17A) in Highlands County from Sebring Parkway to Manatee Drive to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 09/15/2009 | 10/20/2009 | 05/07/2010 | 365737 | 2.268
1548 | Florida | HIGHLANDS |  | 16 | ARRA160 | Resurface County Road 621 in Highlands County from U.S. 27 to Crocket Road to improve the surface of this heavily traveled road. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 03/07/2010 | 206501 | 0.6
1549 | Florida | HARDEE |  | 13 | ARRA161 | Add sidewalks along West Main Street from Booker T. Washington Avenue to Chester Avenue in the City of Bowling Green to improve safety. | Transportation Enhancements | 09/21/2009 | 01/18/2010 | 03/20/2010 | 73702 | 0
1550 | Florida | DE SOTO |  | 13 | ARRA162 | Construct a sidewalk along Dr. Martin Luther King, Jr. Street from Booker T. Washington Avenue to U.S. 17 to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 09/16/2009 | 11/22/2009 | 02/01/2010 | 87008 | 0
1551 | Florida | HENDRY |  | 16,23 | ARRA163 | Construct a new sidewalk along State Road 29 from the RV park to the post office in the Felda community in Hendry County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 09/09/2009 | 09/09/2009 | 03/28/2010 | 431911 | 2.077
1552 | Florida | OKEECHOBEE |  | 16 | ARRA164 | Add sidewalks along Southwest 7th Avenue, Southwest 9th Street and Southwest 11th Avenue in the City of Okeechobee to improve pedestrian safety. | Transportation Enhancements | 09/21/2009 | 02/15/2010 | 04/23/2010 | 164379 | 0
1553 | Florida | POLK |  | 05,12,15 | ARRA165 | Design and build a 12-foot wide paved trail between State Road 17 and 4th Street as an extension of the existing Lake Wales Trail, improving the connectivity of walking trails in Polk County. | Transportation Enhancements | 09/10/2009 | 12/07/2009 | 03/01/2010 | 136678 | 0
1554 | Florida | POLK |  | 05,12,15 | ARRA166 | Build a 12-foot wide paved trail connecting the existing Fort Fraser Trail just south of the University of South Florida/Polk State College to the Circle B Bar Reserve located on S.R. 540 to improve t | Transportation Enhancements | 09/10/2009 | 09/29/2009 | 03/01/2010 | 457968 | 0
1555 | Florida | CHARLOTTE | PUNTA GORDA | 13,14,16 | ARRA167 | Construct a paved pathway from Retta Esplande to Olympia Avenue in Punta Gorda to connect parks, schools, and the riverfront and give walkers and bicyclists a recreational route for exercise. | Transportation Enhancements | 02/01/2010 | 02/08/2010 | 06/01/2010 | 424017 | 0
1556 | Florida | COLLIER | NAPLES | 14,25 | ARRA168 | Construct a paved pathway along Bald Eagle Drive on Marco Island to connect the town center, residential areas, and schools and give walkers and bicyclists a recreational route for exercise. | Transportation Enhancements | 08/19/2009 | 08/24/2009 | 01/24/2010 | 380719 | 1.185
1557 | Florida | HIGHLANDS |  | 16 | ARRA169 | Resurface Kenilworth Boulevard from Lakeview Drive to Persimmon Avenue to improve the surface of this heavily traveled road in Highlands County. | Pavement Improvement | 09/15/2009 | 10/20/2009 | 05/07/2010 | 156946 | 0.4
1558 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA170 | Add landscaping along State Road 789 through the coastal city of Long Boat Key to enhance the roadway features of this beach community. | Transportation Enhancements | 09/30/2009 | 10/22/2009 | 06/15/2010 | 232667 | 4.557
1559 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA171 | Add landscaping along State Road 789 through the coastal city of Bradenton Beach to enhance the roadway features of this beach community. | Transportation Enhancements | 09/30/2009 | 10/22/2009 | 06/15/2010 | 127041 | 0.902
1560 | Florida | HIGHLANDS |  | 16 | ARRA172 | Resurface County Road 17 (S. Main Street) in the town of Lake Placid from Poinsettia Street to West Interlake Boulevard to improve the surface of this heavily traveled road. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 03/05/2010 | 205921 | 0.499
1561 | Florida | MANATEE |  | 11,13 | ARRA173 | Add sidewalks along Gulf Front Park from Palm Avenue to Willow Avenue in the City of Anna Maria to improve safety. | Transportation Enhancements | 09/16/2009 | 11/09/2009 | 12/12/2009 | 19458 | 0
1562 | Florida | HIGHLANDS |  | 16 | ARRA174 | Resurface Home Avenue from Sebring Parkway to State Road 17 (North Gate Drive) to improve the surface of this heavily traveled road in Highlands County. | Pavement Improvement | 09/15/2009 | 10/20/2009 | 05/07/2010 | 52186 | 0.168
1563 | Florida | MANATEE |  | 11,13 | ARRA176 | Add sidewalks along North Bay Boulevard from Hibiscus Street to North Shore Drive in the City of Anna Maria to improve safety. | Transportation Enhancements | 09/16/2009 | 11/09/2009 | 12/10/2009 | 42716 | 0
1564 | Florida | MANATEE |  | 11,13 | ARRA177 | Add sidewalks along Gulf Drive from Spring Avenue to Pine Avenue in the City of Anna Maria to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 11/09/2009 | 12/12/2009 | 6973 | 0
1565 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA178 | Replace a short bridge in Lee County on Cortez Boulevard near Fort Myers High School with a new bridge that has sidewalks. | Pavement Improvement | 10/28/2009 | 12/06/2009 | 01/28/2010 | 247843 | 0.001
1566 | Florida | MANATEE |  | 11,13 | ARRA179 | Add sidewalks along North and South Gulf Drive from 57th Street to 84th Street in the City of Holmes Beach to improve safety. | Transportation Enhancements | 09/16/2009 | 09/29/2009 | 12/02/2009 | 9998 | 1.203
1567 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA180 | Construct a new culvert on Carrel Road to replace an older, rough-riding surface. | Pavement Improvement | 11/23/2009 | 01/18/2010 | 03/23/2010 | 94960 | 0.001
1568 | Florida | MANATEE |  | 11,13 | ARRA181 | Add sidewalks along Holmes Boulevard from 54th Street to 66th Street in the City of Holmes Beach to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 09/28/2009 | 12/02/2009 | 22942 | 0
1569 | Florida | MANATEE |  | 11,13 | ARRA182 | Add sidewalks along Palm Drive from 66th Street to 85th Street in the City of Holmes Beach to improve safety. | Transportation Enhancements | 09/16/2009 | 09/29/2009 | 12/02/2009 | 10445 | 0
1570 | Florida | MANATEE |  | 11,13 | ARRA183 | Add sidewalks along 85th Street from Gulf Drive to Marina Drive in the City of Holmes Beach to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 09/29/2009 | 12/02/2009 | 11335 | 0
1571 | Florida | MANATEE |  | 11,13 | ARRA184 | Add sidewalks along 21st Avenue from 26th Street West to 27th Street West in Bradenton to improve safety. | Transportation Enhancements | 09/16/2009 | 09/30/2009 | 12/02/2009 | 8534 | 0
1572 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA185 | Add sidewalks along 27th Street from 22nd Avenue West to 23rd Avenue West in Bradenton to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 09/30/2009 | 12/02/2009 | 21180 | 0
1573 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA186 | Add sidewalks along 23nd Avenue from 26th Street West to 27th Street West in Bradenton to improve safety. | Transportation Enhancements | 09/16/2009 | 09/30/2009 | 12/02/2009 | 7135 | 0
1574 | Florida | MANATEE |  | 11,13 | ARRA187 | Add sidewalks along 21st Avenue from 30th Street West to 34th Street West in Bradenton to improve pedestrian safety. | Transportation Enhancements | 09/16/2009 | 09/30/2009 | 12/02/2009 | 53233 | 0
1575 | Florida | HIGHLANDS |  | 16 | ARRA189 | Add sidewalks along Thunderbird Road from Lotus Avenue to Red Pine Drive in the City of Sebring to improve pedestrian safety. | Transportation Enhancements | 09/15/2009 | 01/04/2010 | 04/09/2010 | 115031 | 0
1576 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA190 | Add paved shoulders that will be designated bike lanes on Buckingham Road from State Road 82 to Neal Road in Lee County to enhance safe riding for cyclists. | Pavement Improvement | 01/14/2010 | 02/16/2010 | 06/14/2010 | 293630 | 1.8
1577 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA191 | Add a second left turn lane on Daniels Parkway westbound at Bell Tower Boulevard in Lee County to improve traffic flow at the intersection. | Pavement Improvement | 03/01/2010 | 03/10/2010 | 09/27/2010 | 502272 | 0.443
1578 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA192 | Add a bicycle lane on Summerlin Road in Lee County at the toll plaza to give walkers, runners, and bicyclists a connection to the Sanibel causeway bridge. | Transportation Enhancements | 02/08/2010 | 02/08/2010 | 09/06/2010 | 319262 | 0
1579 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA193 | Add two new right turn lanes on Sunshine Boulevard at Lee Boulevard in Lee County to move traffic more efficiently at the intersection. | Pavement Improvement | 01/14/2010 | 01/20/2010 | 06/13/2010 | 553432 | 0.014
1580 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA194 | Construct a left turn on Homestead Road South in Lee County at the Milwaukee Boulevard to move traffic more efficiently though the intersection. | Safety/Traffic Management | 09/16/2009 | 09/17/2009 | 01/15/2010 | 70579 | 0.2
1581 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA195 | Rehabilitate the Crescent Avenue bridge and the North Bay Boulevard bridge in the coastal city of Anna Maria Island to extend the use of the bridges by many years. | Pavement Improvement | 09/22/2009 | 10/13/2009 | 09/10/2010 | 648398 | 0.001
1582 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA196 | Resurface Pine Avenue in the city of Anna Maria from Gulf Drive to Bay Boulevard to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 09/16/2009 | 11/16/2009 | 01/11/2010 | 80949 | 0.504
1583 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA197 | Resurface Gulf Drive in the city of Anna Maria from Willow Avenue to Pine Avenue to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 09/16/2009 | 11/16/2009 | 01/11/2010 | 126369 | 0.276
1584 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA199 | Add landscaping and sidewalks along State Road 789/Gulf Drive from south of 2nd Street to north of 5th Street to improve the safety and enhance the roadway features of this beach community. | Transportation Enhancements | 09/30/2009 | 10/22/2009 | 04/26/2010 | 315087 | 0.371
1585 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA200 | Add pedestrian crosswalks to the intersections of East Bay Drive and Gulf Drive in the city of Holmes Beach to improve safety. | Transportation Enhancements | 09/16/2009 | 11/16/2009 | 12/16/2009 | 20221 | 0.002
1586 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA201 | Beach Boulevard, (U.S. 90/State Road 212) in Duval County will be widened from four to six lanes for 1? miles between Hodges Boulevard and San Pablo Road in order to complete the six-lane section betw | Pavement Widening | 06/10/2009 | 06/10/2009 | 06/15/2012 | 15180617 | 2.76
1587 | Florida | CLAY |  | 03,06 | ARRA202 | In Clay County, a new overpass for Plantation Oaks Boulevard traffic will separate the higher speed and volume of traffic on State Road 23, making it safer and more efficient. | Pavement Widening | 06/16/2009 | 06/16/2009 | 11/03/2012 | 8404994 | 0.1
1588 | Florida | NASSAU |  | 04 | ARRA203 | In Nassau County, State Road A1A (State Road 200) will be widened from two to four lanes for six miles between Griffin and Stratton roads to improve traffic flow within the corridor. | Pavement Widening | 06/16/2009 | 06/16/2009 | 06/16/2012 | 29838311 | 7.89
1589 | Florida | CHARLOTTE |  | 13,14,16 | ARRA204 | Lengthen two left turn lanes on southbound U.S. 41 in Charlotte County to improve traffic flow at the Midway Boulevard intersection. | Pavement Improvement | 09/30/2009 | 03/15/2010 | 06/07/2010 | 165765 | 0.1
1590 | Florida | CHARLOTTE |  | 13,14,16 | ARRA205 | Add a left turn lane at Murdock Circle westbound at U.S. 41 to improve traffic movement in this area. | Pavement Improvement | 09/30/2009 | 03/24/2010 | 06/04/2010 | 180803 | 0.1
1591 | Florida | FLAGLER |  | 07 | ARRA206 | This project in Flagler County will extend the Lehigh Trail and Bike Path by adding 12-foot wide paths and two bridges which benefits trail users and increases safety. | Transportation Enhancements | 02/05/2010 | 02/15/2010 | 09/22/2010 | 859595 | 2.718
1592 | Florida | FLAGLER |  | 07 | ARRA207 | This project in the City of Palm Coast fixes the bridge over Club House Waterway and includes better guardrails. | Bridge Improvement | 02/28/2010 | 02/28/2010 | 08/25/2010 | 741882 | 0.034
1593 | Florida | MARION | OCALA | 03,05,06,08 | ARRA208 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/06/2009 | 11/30/2009 | 03/26/2010 | 335281 | 1.517
1594 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA209 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 01/11/2010 | 01/21/2010 | 04/21/2010 | 182075 | 2.291
1595 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA210 | RESURFACING NORTH RIVERSIDE DR FROM SAND PINE RD TO US 192 (0002.950 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 02/23/2010 | 03/05/2010 | 06/13/2010 | 225374 | 2.95
1596 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA211 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 01/25/2010 | 02/03/2010 | 05/05/2010 | 318511 | 2.773
1597 | Florida | LAKE | LADY LAKE | 03,05,06,08 | ARRA212 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 01/22/2010 | 02/01/2010 | 06/15/2010 | 1704807 | 8.551
1598 | Florida | FLAGLER |  | 07 | ARRA213 | This project replaces a bridge on County Road 305 in Flagler County and includes guardrail improvements. | Pavement Improvement | 02/05/2010 | 06/14/2010 | 12/22/2010 | 804600 | 0.01
1599 | Florida | MARION | OCALA | 03,05,06,08 | ARRA214 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/06/2009 | 11/10/2009 | 03/06/2010 | 47971 | 0.839
1600 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA215 | This project fixes a drainage pipe at Hall Road in the Town of Malabar in Brevard County. | Safety/Traffic Management | 03/25/2010 | 03/25/2010 | 06/12/2010 | 18375 | 0.225
1601 | Florida | MARION | OCALA | 03,05,06,08 | ARRA216 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/10/2009 | 11/16/2009 | 03/13/2010 | 139256 | 0.922
1602 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA217 | This project in the City of Melbourne will resurface the road, improve storm water drainage, make turn lanes safer, fix sidewalks and upgrade pedestrian crossings. | Pavement Improvement | 02/16/2010 | 02/22/2010 | 06/22/2010 | 609034 | 1.277
1603 | Florida | MARION | OCALA | 03,05,06,08 | ARRA218 | This turn lane project in the City of Ocala will improve safety and traffic flow and reduce traffic congestion at intersections. | Safety/Traffic Management | 12/03/2009 | 12/07/2009 | 10/03/2010 | 1152877 | 1.058
1604 | Florida | MARION | OCALA | 03,05,06,08 | ARRA219 | This repaving project in Marion County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/05/2009 | 11/09/2009 | 03/24/2010 | 980253 | 3.363
1605 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA220 | This project in Brevard County will provide a safer environment for pedestrians with a new asphalt sidewalk on which to walk. | Transportation Enhancements | 03/24/2010 | 03/24/2010 | 04/23/2010 | 41550 | 0.713
1606 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA221 | This repaving project in the City of Palm Bay will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 01/13/2010 | 01/15/2010 | 06/13/2010 | 909183 | 1.98
1607 | Florida | MARION | OCALA | 03,05,06,08 | ARRA222 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/06/2009 | 11/10/2009 | 03/06/2010 | 97672 | 0.707
1608 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA223 | This repaving project in Brevard County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 01/28/2010 | 01/28/2010 | 04/28/2010 | 291064 | 0.793
1609 | Florida | MARION | OCALA | 03,05,06,08 | ARRA224 | This repaving project in Marion County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 11/23/2009 | 12/14/2009 | 07/12/2010 | 4837445 | 10.849
1610 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA225 | This resurfacing project in the City of Satellite Beach will improve the condition of the existing pavement and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 12/16/2009 | 12/21/2009 | 03/22/2010 | 137098 | 0.275
1611 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA226 | This resurfacing project in the City of Titusville will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 11/16/2009 | 12/07/2009 | 02/26/2010 | 51251 | 0.285
1612 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA227 | This resurfacing project in Brevard County will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 03/25/2010 | 03/25/2010 | 05/24/2010 | 681252 | 1.681
1613 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA228 | This resurfacing project in Brevard County will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 02/17/2010 | 02/17/2010 | 05/08/2010 | 338018 | 1.018
1614 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA229 | This project fixes a drainage pipe at Atz Road in the Town of Malabar in Brevard County. | Safety/Traffic Management | 03/25/2010 | 03/25/2010 | 06/12/2010 | 4775 | 0.23
1615 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA230 | This project fixes storm water drainage problems on Riverside Drive in Brevard County. | Safety/Traffic Management | 03/31/2010 | 03/31/2010 | 04/30/2010 | 24830 | 0.067
1616 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA231 | This repaving project in the City of Palm Bay will improve the road surface. | Pavement Improvement | 11/17/2009 | 11/17/2009 | 04/23/2010 | 698396 | 1.251
1617 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA232 | This resurfacing project in the City of Titusville will improve the condition of the existing pavement as well as provide better guardrails. | Pavement Improvement | 11/16/2009 | 12/07/2009 | 02/26/2010 | 125916 | 0.68
1618 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA233 | This resurfacing project in Brevard County will improve the condition of the road and upgrade pedestrian crossings. | Pavement Improvement | 01/28/2010 | 01/28/2010 | 05/28/2010 | 526893 | 1.699
1619 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA234 | This resurfacing project in Brevard County will improve the condition of the existing pavement, provide better traffic signals and sensors, and enhance safety by upgrading pedestrian crossings. | Pavement Improvement | 02/23/2010 | 02/23/2010 | 05/14/2010 | 742561 | 1.949
1620 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA235 | This resurfacing project in Lake County will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 02/01/2010 | 02/11/2010 | 03/28/2010 | 19030 | 0.256
1621 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA236 | This resurfacing project in Brevard County will improve the condition of the existing pavement and enhance safety by upgrading pedestrian crossings. | Pavement Improvement | 02/17/2010 | 02/17/2010 | 05/08/2010 | 548243 | 0.995
1622 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA237 | This resurfacing project in Lake County will improve the condition of the pavement and enhance safety by upgrading pedestrian crossings. | Pavement Improvement | 01/18/2010 | 01/28/2010 | 04/28/2010 | 156704 | 1.269
1623 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA238 | This resurfacing project in the City of Cape Canaveral will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 02/02/2010 |  | 02/08/2011 | 181563 | 0.998
1624 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA239 | This resurfacing project in the Town of Malabar in Brevard County will improve the condition of the area where a paved driveway meets a road. | Pavement Improvement | 03/25/2010 | 03/25/2010 | 06/12/2010 | 9525 | 0.103
1625 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA240 | This resurfacing project in Brevard County will improve the condition of the existing pavement, provide better traffic signals and controls, and enhance safety by providing upgraded pedestrian crossin | Pavement Improvement | 01/28/2010 | 01/28/2010 | 03/14/2010 | 49243 | 0.161
1626 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA241 | This resurfacing project in the Town of Malabar in Brevard County will improve the condition of the area where a paved driveway meets a road. | Pavement Improvement | 03/25/2010 | 03/25/2010 | 06/12/2010 | 10525 | 0.071
1627 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA242 | This project in the City of Cocoa will improve drainage along School Street, fix sidewalks and upgrade pedestrian crossings. | Safety/Traffic Management | 03/02/2010 | 03/02/2010 | 06/30/2010 | 142678 | 0.247
1628 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA243 | This project in the City of Cocoa Beach will resurface the road, improve storm water drainage, fix sidewalks and upgrade pedestrian crossings. | Pavement Improvement | 10/22/2009 | 11/02/2009 | 08/29/2010 | 262282 | 0.409
1629 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA244 | This resurfacing project in Brevard County will improve the condition of the existing pavement, provide better traffic signals and controls, and enhance safety by providing upgraded pedestrian crossin | Pavement Improvement | 01/28/2010 | 01/28/2010 | 05/28/2010 | 374332 | 1
1630 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA245 | This resurfacing project in the Town of Malabar in Brevard County will improve the condition of the area where a paved driveway meets a road. | Pavement Improvement | 03/25/2010 | 03/25/2010 | 06/12/2010 | 9775 | 0.001
1631 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA246 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 01/25/2010 | 02/03/2010 | 03/21/2010 | 18837 | 0.116
1632 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA247 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 01/22/2010 | 02/01/2010 | 06/01/2010 | 209728 | 2.276
1633 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA248 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 01/11/2010 | 01/21/2010 | 05/21/2010 | 617617 | 4.896
1634 | Florida | LAKE | LADY LAKE | 03,05,06,08 | ARRA249 | This resurfacing project in Lake County will fix the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 01/11/2010 | 01/21/2010 | 04/21/2010 | 127208 | 0.3
1635 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA250 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 01/18/2010 | 01/18/2010 | 04/28/2010 | 152316 | 1.854
1636 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA251 | This resurfacing project in Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 11/24/2009 | 12/07/2009 | 03/08/2010 | 880639 | 2.16
1637 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA252 | This resurfacing project in the City of Oviedo will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 12/11/2009 | 12/11/2009 | 06/12/2010 | 996399 | 1.791
1638 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA253 | This State Road 434 project in the City of Winter Springs will provide turn lanes to help reduce traffic congestion. | Pavement Improvement | 01/26/2010 | 01/26/2010 | 04/26/2010 | 163034 | 0.05
1639 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA254 | The Rinehart Road project in the City of Lake Mary includes resurfacing which will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 11/19/2009 | 11/20/2009 | 03/12/2010 | 711850 | 2.09
1640 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA255 | The Howell Branch Road resurfacing project in Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 11/02/2009 | 11/02/2009 | 02/24/2010 | 505154 | 0.745
1641 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA256 | The International Parkway resurfacing project within the City of Lake Mary will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 02/23/2010 | 03/01/2010 | 06/21/2010 | 360507 | 1.139
1642 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA257 | The State Road 419 project in the City of Winter Springs will provide turn lanes to reduce traffic congestion. | Pavement Improvement | 12/01/2009 | 12/01/2009 | 05/24/2010 | 414724 | 0.001
1643 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA258 | The West 25th Street resurfacing project is Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 12/07/2009 | 12/17/2009 | 06/01/2010 | 1453600 | 1.164
1644 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA259 | The 8th Street resurfacing project on a local road in the City of Holly Hill will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 01/27/2010 | 02/01/2010 | 03/13/2010 | 29962 | 0.11
1645 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA260 | The Taylor Creek Bridge project in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 06/01/2010 | 06/01/2010 | 02/25/2011 | 2750000 | 0.049
1646 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA261 | The Campo Way Bridge project located in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 04/09/2010 | 04/12/2010 | 10/08/2010 | 378044 | 0.333
1647 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA262 | The Harrell Road Bridge project located in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 04/02/2010 | 04/05/2010 | 10/31/2010 | 642520 | 0.457
1648 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA263 | The Thorpe Road Bridge project located in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 05/10/2010 | 05/10/2010 | 11/05/2010 | 412423 | 1.005
1649 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA264 | The Lake Underhill Road resurfacing project in Orange County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 04/01/2010 | 04/12/2010 | 11/28/2010 | 2334323 | 1.508
1650 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA265 | The Downtown Orlando Intelligent Transportation System (ITS) project will use underground fiber optic cable and video detection equipment to upgrade the regional computerized signal system which will | Safety/Traffic Management | 02/03/2010 | 02/03/2010 | 08/31/2010 | 3154100 | 0
1651 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA266 | RESURFACING CLARKE ROAD FROM SILVER STAR ROAD TO CLARCONA-OCOEE ROAD (0002.516 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 02/04/2010 | 03/01/2010 | 05/30/2010 | 1157652 | 2.516
1652 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA267 | The Morse Boulevard resurfacing project in Orange County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 01/07/2010 | 02/08/2010 | 06/28/2010 | 240757 | 0.87
1653 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA268 | The General Rees Avenue resurfacing project in Orange County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 04/01/2010 | 04/12/2010 | 12/08/2010 | 975019 | 0.074
1654 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA269 | The Dean Road resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 04/01/2010 | 04/05/2010 | 09/02/2010 | 1186807 | 1.864
1655 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA270 | The Kaley Street resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 04/01/2010 | 04/05/2010 | 09/02/2010 | 396048 | 1.31
1656 | Florida | OSCEOLA | ORLANDO | 08,12,15 | ARRA271 | The Buenaventura Boulevard resurfacing project in Osceola County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 12/22/2009 | 12/22/2009 | 04/07/2010 | 2040113 | 2.573
1657 | Florida | OSCEOLA | ORLANDO | 08,12,15 | ARRA272 | The John Young Parkway resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 12/22/2009 | 12/22/2009 | 03/12/2010 | 1789329 | 1.494
1658 | Florida | OSCEOLA | ORLANDO | 08,12,15 | ARRA273 | The Neptune Road resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 12/22/2009 | 12/22/2009 | 02/08/2010 | 206970 | 0.491
1659 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA274 | The County Road 4139 resurfacing project in the City of Lake Helen will be constructed by Volusia County and will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 02/12/2010 | 02/22/2010 | 06/22/2010 | 300000 | 3.794
1660 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA275 | The Riverside Drive resurfacing project in the City of New Smyrna Beach will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 11/19/2009 | 11/23/2009 | 04/17/2010 | 284059 | 0.839
1661 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA276 | The Canal View Boulevard resurfacing project in Port Orange will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 01/06/2010 | 01/11/2010 | 04/12/2010 | 108813 | 0.939
1662 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA277 | The Lake Washington Road resurfacing project in the City of Melbourne will extend the usable life of the highway and enhance safety. | Pavement Improvement | 02/16/2010 | 02/22/2010 | 06/22/2010 | 418400 | 1.046
1663 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA278 | The Sykes Creek Parkway resurfacing project in Brevard County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 03/25/2010 | 03/25/2010 | 06/08/2010 | 381058 | 1.437
1664 | Florida | HILLSBOROUGH | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,11,12 | ARRA279 | The I-4/Selmon Expressway Connector is a new toll road that will connect Interstate 4 to the Selmon Expressway and provide commercial trucks direct access to the Port of Tampa improving the efficient | New Construction | 07/01/2009 | 07/08/2009 | 02/01/2015 | 105025353 | 0.913
1665 | Florida | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,10,11 | ARRA280 | In Pinellas County, to reduce congestion, this project removes the traffic signals on U.S. 19 between Whitney Road and State Road 60 and replaces them with two new interchanges at Belleair Road and Se | Pavement Widening | 06/29/2009 | 08/20/2009 | 10/01/2014 | 44990142 | 2.643
1666 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA281 | This project widens Interstate 95 from Malabar Road to Palm Bay Road in Brevard County, making this section of I-95 three lanes in both directions. | Pavement Widening | 10/01/2009 | 10/01/2009 | 11/26/2010 | 21165476 | 4.173
1667 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA282 | The U.S. 27 project will add two new lanes, making this a six-lane, divided highway from just north of Lake Louisa Road to Cluster Oaks Drive in the City of Clermont. | Pavement Widening | 10/14/2009 | 10/14/2009 | 10/14/2011 | 20412470 | 3.837
1668 | Florida | MARION | OCALA | 03,05,06,08 | ARRA283 | This project will transform Baseline Road, which is primarily a two-lane highway, into a four-lane, divided highway near Ocala in Marion County. | Pavement Widening | 09/11/2009 | 09/11/2009 | 11/20/2010 | 27003841 | 5.704
1669 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA284 | The State Road 50 project in the City of Winter Garden will widen this roadway more than three miles to a six-lane divided roadway. | Pavement Widening | 09/23/2009 | 09/23/2009 | 07/15/2011 | 18455641 | 3.056
1670 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA285 | The State Road 434 project in the City of Altamonte Springs will make this section of the road a six-lane, divided highway, which is consistent to the rest of State Road 434 in this area. | Pavement Widening | 09/30/2009 | 09/30/2009 | 07/27/2010 | 4686478 | 0.713
1671 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA288 | Resurface Tenth Street in the city of Palmetto from 8th Avenue to 14th Avenue to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 02/01/2010 | 04/29/2010 | 09/30/2010 | 76106 | 0.512
1672 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA289 | Resurface Cattlemen Road in Sarasota County from Bahia Vista to south of Fruitville Road to improve the surface of this heavily traveled road. | Pavement Improvement | 02/18/2010 | 02/18/2010 | 06/30/2010 | 395068 | 1.9
1673 | Florida | OKEECHOBEE |  | 16 | ARRA290 | Replace the bridge at 43rd Avenue in the city of Okeechobee to improve the safety of motorists. | Pavement Improvement | 09/21/2009 | 10/24/2009 | 10/29/2010 | 1201547 | 0.001
1674 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA291 | Resurface Sumter Boulevard in North Port from City Center Boulevard to Hansard Avenue. The project also includes the widening of a bridge and new turn lanes to move traffic more efficiently. | Pavement Improvement | 03/22/2010 | 04/14/2010 | 04/06/2011 | 1448068 | 0.267
1675 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA292 | Install new traffic signals, ramps and asphalt crosswalks at the intersections at Venice Avenue and Harbor Drive in Sarasota County to improve the safety of the area. | Pavement Improvement | 01/11/2010 | 03/31/2010 | 10/01/2010 | 332747 | 0.571
1676 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA293 | Construct improvements to State Road 758 (Siesta Drive) between Siesta Bridge and Henson Bayou Bridge to correct a drainage problem along this entrance onto Siesta Key. | Pavement Improvement | 03/24/2010 | 05/03/2010 | 09/30/2010 | 1053068 | 0.502
1677 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA294 | Resurface Venice Avenue in Sarasota County from Ramsey Road to Jacaranda Boulevard to improve the deteriorated surface of this busy road. | Pavement Improvement | 04/21/2010 | 04/26/2010 | 08/31/2010 | 816068 | 1.016
1678 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA295 | Resurface University Parkway in Manatee County from U.S. 41 to U.S. 301 to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 04/09/2010 | 04/14/2010 | 08/31/2010 | 753068 | 0.051
1679 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA296 | Resurface University Parkway from U.S. 301 to I-75 to improve the deteriorated surface of this heavily traveled road. This is a joint project by Manatee and Sarasota counties. | Pavement Improvement | 05/04/2010 | 05/11/2010 | 09/30/2010 | 1112836 | 0
1680 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA297 | Resurface University Parkway from U.S. 301 to I-75 to improve the deteriorated surface of this heavily traveled road. This is a joint project by Manatee and Sarasota counties. | Pavement Improvement | 05/04/2010 | 05/11/2010 | 09/30/2010 | 1143956 | 5.089
1681 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA303 | This trail project in Brevard County will create a safe environment for pedestrian and bicyclists. | Transportation Enhancements | 01/06/2010 | 01/16/2010 | 05/06/2010 | 317660 | 0
1682 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA304 | This project fixes a drainage pipe at Atz Road in the Town of Malabar in Brevard County. | Safety/Traffic Management | 03/25/2010 | 03/25/2010 | 06/12/2010 | 20105 | 0.293
1683 | Florida | FLAGLER |  | 07 | ARRA305 | The Downtown Streetscape project within the City of Flagler Beach will include sidewalks, better lighting and accessibility for all pedestrians. | Transportation Enhancements | 02/26/2010 | 03/01/2010 | 09/27/2010 | 1012628 | 0.519
1684 | Florida | LAKE | LEESBURG-EUSTIS | 03,05,06,08 | ARRA306 | The Lois Drive Bridge project in Lake County replaces an outdated bridge that causes some vehicles to "bottom out" when they cross. | Pavement Improvement | 12/17/2009 | 12/17/2009 | 10/05/2010 | 2071200 | 0.044
1685 | Florida | MARION | OCALA | 03,05,06,08 | ARRA307 | This sidewalk project in Marion County will provide a safer environment for pedestrians and will upgrade pedestrian crossings. | Transportation Enhancements | 10/16/2009 | 10/26/2009 | 02/23/2010 | 456707 | 0
1686 | Florida | MARION | OCALA | 03,05,06,08 | ARRA308 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrians. | Pavement Improvement | 11/06/2009 | 11/30/2009 | 05/27/2010 | 988939 | 1.02
1687 | Florida | ORANGE | ORLANDO | 03,07,08,24 | ARRA309 | The Pine Hills Road/Silver Streetscape project in Orange County will provide a safer environment for pedestrians and bicyclists and enhance the renovation of Evans High School. | Transportation Enhancements | 04/09/2010 | 04/12/2010 | 09/08/2010 | 366132 | 0.576
1688 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA310 | The Cross Seminole County Trail project will repair the Howell Creek Trestle Bridge which is a vital part of the Seminole County trail system. | Transportation Enhancements | 12/07/2009 | 12/07/2009 | 04/25/2010 | 450866 | 0
1689 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA311 | The International Parkway resurfacing project in the City of Lake Mary will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 02/23/2010 | 03/01/2010 | 06/21/2010 | 391353 | 1.17
1690 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA312 | This State Road 434 project in the City of Winter Springs will provide safer conditions for making right turns at this intersection. | Pavement Improvement | 12/01/2009 | 12/01/2009 | 05/20/2010 | 168461 | 0.064
1691 | Florida | SUMTER |  | 05 | ARRA313 | This repaving project in Osceola County will improve the road surface and upgrade pedestrian crossings. | Pavement Improvement | 11/24/2009 | 01/11/2010 | 05/11/2010 | 661988 | 3.785
1692 | Florida | SUMTER |  | 05 | ARRA314 | This sidewalk project in Marion County will provide a safer environment for pedestrians and bicyclists as well as upgraded pedestrian crossings. | Pavement Improvement | 11/24/2009 | 01/11/2010 | 06/10/2010 | 1020860 | 7.425
1693 | Florida | SUMTER |  | 05 | ARRA315 | The Lake Panasoffkee Pedestrian Trail, located in Sumter County, will provide a safe environment with a new, five-foot wide, concrete sidewalk for pedestrians and bicyclists. | Transportation Enhancements | 12/10/2009 | 01/11/2010 | 04/10/2010 | 299590 | 0
1694 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA316 | The Dunn Avenue project in Daytona Beach will extend this road and includes a bridge over I-95. | New Construction | 02/12/2010 | 03/01/2010 | 08/03/2011 | 5581933 | 0.612
1695 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA318 | The 8th Street resurfacing project in the City of Holly Hill will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 02/03/2010 | 02/08/2010 | 03/20/2010 | 18402 | 0.129
1696 | Florida | MIAMI-DADE | MIAMI-HIALEAH, FL | 17,18,20,21,25 | ARRA319 | This project reconstructs almost three miles of the US 1 corridor known as the 18-mile stretch between Florida City and Key Largo. | Pavement Improvement | 11/16/2004 | 11/16/2004 |  | 18433884 | 2.86
1697 | Florida | MONROE |  | 18,25 | ARRA323 | This project will provide maintenance and repairs to the Palm Drive Bridge in Monroe County. The project will replace the bridge deck and railings. | Bridge Improvement | 11/19/2009 | 11/30/2009 | 02/01/2010 | 136053 | 0.013
1698 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA324 | This project will resurface the existing roadway, upgrade sidewalks, signing and pavement markings, replace signals and landscape. This project will enhance mobility for the community. | Pavement Improvement | 06/01/2010 |  |  | 3955017 | 0.743
1699 | Florida | MONROE |  | 18,25 | ARRA325 | This project will provide maintenance and repairs to the Geiger Creek bridge. These repairs will maintain a higher level of service. | Bridge Improvement | 02/11/2010 | 02/17/2010 |  | 914056 | 0.125
1700 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA328 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/16/2010 | 02/16/2010 | 05/12/2011 | 162382 | 0.833
1701 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA329 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/16/2010 | 02/16/2010 | 05/12/2011 | 239094 | 0.8
1702 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA330 | This project will repave roadways throughout the Town of Cutler Bay. This project will enhance the ride for users of the town's roadway network. | Pavement Improvement | 01/04/2010 | 02/12/2010 | 07/20/2010 | 207376 | 1.563
1703 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA331 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Transportation Enhancements | 12/01/2009 | 12/01/2009 | 05/30/2010 | 126959 | 0
1704 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA332 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Transportation Enhancements | 12/01/2009 | 12/14/2009 | 06/12/2010 | 172408 | 0
1705 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA333 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Safety/Traffic Management | 03/01/2010 | 03/01/2010 | 03/01/2011 | 458965 | 0
1706 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA334 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Safety/Traffic Management | 03/01/2010 | 03/01/2010 | 03/01/2011 | 274051 | 0
1707 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA335 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Safety/Traffic Management | 03/01/2010 | 03/01/2010 | 01/16/2011 | 184655 | 0
1708 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA338 | This project will resurface 1.50 miles of road and add new markings, guardrails and sidewalk improvements. | Pavement Improvement | 02/25/2010 | 02/25/2010 |  | 120875 | 4.561
1709 | Florida | MONROE |  | 18,25 | ARRA340 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 02/22/2010 | 03/03/2010 | 07/30/2010 | 136680 | 0.4
1710 | Florida | MONROE |  | 18,25 | ARRA341 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 02/22/2010 | 03/03/2010 | 07/30/2010 | 126347 | 0.228
1711 | Florida | MONROE |  | 18,25 | ARRA342 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 02/05/2010 | 02/05/2010 | 07/02/2010 | 50828 | 0.07
1712 | Florida | MONROE |  | 18,25 | ARRA343 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 02/05/2010 | 02/05/2010 | 07/02/2010 | 31172 | 0.25
1713 | Florida | MONROE |  | 18,25 | ARRA345 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 02/05/2010 | 02/05/2010 | 02/28/2011 | 174050 | 0.556
1714 | Florida | MONROE |  | 18,25 | ARRA346 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 02/05/2010 | 02/05/2010 | 02/28/2011 | 32635 | 0.08
1715 | Florida | MONROE |  | 18,25 | ARRA347 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 05/18/2010 | 05/18/2010 |  | 67985 | 0.08
1716 | Florida | MONROE |  | 18,25 | ARRA348 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 02/05/2010 | 02/05/2010 | 02/25/2011 | 467900 | 0.63
1717 | Florida | MONROE |  | 18,25 | ARRA349 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 05/18/2010 | 05/18/2010 |  | 48726 | 0.255
1718 | Florida | MONROE |  | 18,25 | ARRA350 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 05/18/2010 | 05/18/2010 |  | 187035 | 0.27
1719 | Florida | MONROE |  | 18,25 | ARRA351 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 06/02/2010 | 03/02/2010 | 03/31/2011 | 234574 | 0.31
1720 | Florida | MONROE |  | 18,25 | ARRA353 | The United Street corridor project in the City of Key West will repave the existing roadway, restripe the surface, and construct new sidewalks and curbs. This project will enhance safety for the motor | Pavement Improvement | 06/02/2010 |  |  | 418466 | 0.266
1721 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA354 | The Village of Biscayne Park will construct median curbs and an irrigation system. The project will enhance pedestrian safety. | Transportation Enhancements | 09/16/2009 | 10/15/2009 | 12/13/2009 | 74073 | 0.527
1722 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA355 | The Village of El Portal will resurface and enhance drainage at intersections. The project will enhance roadway safety for the traveling public. | Pavement Improvement | 09/16/2009 |  | 01/15/2010 | 56641 | 0.261
1723 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA356 | The City of Virginia Gardens will construct new drainage inlets at intersections, and perform pavement resurfacing and restriping. This project will enhance safety for the traveling public. | Pavement Improvement | 09/16/2009 |  | 01/05/2010 | 37260 | 0.3
1724 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA357 | Larger drainage pipes will be installed under US 29 in the Town of Century as part of an overall community drainage improvement project in Escambia County. | Pavement Improvement | 08/18/2009 | 08/18/2009 | 12/30/2009 | 498123 | 0.134
1725 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA359 | This project will provide sidewalk enhancements along selected corridor. This project will increase pedestrian safety. | Transportation Enhancements | 12/08/2009 | 01/05/2010 | 03/25/2010 | 112000 | 0
1726 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA360 | This project will provide illuminated signs throughout various locations in Miami-Dade County to enhance driving conditions. | Safety/Traffic Management | 01/10/2010 | 01/25/2010 | 07/23/2010 | 298700 | 0
1727 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA361 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists. | Safety/Traffic Management | 11/12/2009 | 11/12/2009 | 06/01/2010 | 126922 | 0
1728 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA362 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists and pedestrians. | Safety/Traffic Management | 11/30/2009 | 12/07/2009 | 07/13/2010 | 103244 | 0
1729 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA363 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists. | Safety/Traffic Management | 03/03/2010 | 03/08/2010 | 03/03/2011 | 295442 | 0
1730 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA364 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 10/19/2009 | 10/19/2009 | 04/17/2010 | 60661 | 0.26
1731 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA365 | This project will renovate sidewalks, curbs, pavement, pavement markings and upgrade signage. These enhancements will help maintain a higher level of service. | Pavement Improvement | 02/08/2010 | 03/02/2010 | 06/30/2010 | 217949 | 0.097
1732 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA366 | This project will add new drainage, lighting, sidewalk, curbs, pavement, pavement markings, signage and signalization. These enhancements will help maintain a higher level of service. | Pavement Improvement | 02/08/2010 | 02/15/2010 | 08/31/2010 | 944899 | 0.524
1733 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA367 | This project will add new drainage, lighting, sidewalk, curbs, pavement, pavement markings, signage and signalization. These enhancements will help maintain a higher level of service. | Pavement Improvement | 02/08/2010 | 03/01/2010 | 08/31/2010 | 886643 | 0.501
1734 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA368 | This project will add new drainage, lighting, sidewalk, curb, pavement, pavement markings, signage and signalization. These enhancements will help maintain a high level of service. | Pavement Improvement | 02/08/2010 | 03/15/2010 | 08/31/2010 | 993385 | 0.465
1735 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA369 | This project will renovate sidewalks, curbs, pavement, pavement markings and upgrade signage. These enhancements will help maintain a higher level of service. | Pavement Improvement | 02/08/2010 | 03/02/2010 | 06/30/2010 | 278218 | 1.488
1736 | Florida | JACKSON |  | 02 | ARRA370 | The City of Marianna will repave Milton Avenue to improve the road surface and driving quality in Jackson County. | Pavement Improvement | 12/03/2009 | 12/18/2009 | 05/29/2010 | 219017 | 0.086
1737 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA371 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 01/04/2010 | 01/04/2010 | 01/04/2011 | 176529 | 1.002
1738 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA372 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 01/04/2010 | 01/04/2010 | 01/04/2011 | 236847 | 0.511
1739 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA373 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/26/2010 | 263409 | 0.513
1740 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA374 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/26/2010 | 314525 | 0.786
1741 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA375 | This project will resurface the roadway. This will enhance driving quality by improving the road surface. | Pavement Improvement | 01/04/2010 | 01/04/2010 | 01/04/2011 | 295481 | 0.553
1742 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA376 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/08/2010 | 02/08/2010 | 05/04/2011 | 259743 | 1.512
1743 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA377 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/08/2010 | 02/08/2010 | 05/04/2011 | 36691 | 0.183
1744 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA378 | This project will resurface the roadway. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/08/2010 | 02/08/2010 | 05/04/2011 | 168559 | 0.516
1745 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA379 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/08/2010 | 02/08/2010 | 05/04/2011 | 209756 | 0.498
1746 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA380 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/16/2010 | 02/16/2010 | 05/12/2011 | 375554 | 1.5
1747 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA381 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/08/2010 | 02/08/2010 | 05/04/2011 | 139682 | 1.028
1748 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA382 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 03/01/2010 | 03/02/2010 | 01/16/2011 | 436190 | 0.922
1749 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA384 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 03/01/2010 | 03/02/2010 | 01/16/2011 | 215712 | 1.48
1750 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA385 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/22/2010 | 02/22/2010 | 12/19/2010 | 249415 | 1.027
1751 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA386 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/22/2010 | 02/22/2010 | 12/19/2010 | 351470 | 1
1752 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA387 | This project will resurface the roadway. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/22/2010 | 02/22/2010 | 12/19/2010 | 237328 | 1.524
1753 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA388 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/22/2010 | 02/22/2010 | 12/19/2010 | 96610 | 0.504
1754 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA389 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/22/2010 | 02/22/2010 | 12/19/2010 | 261261 | 1.524
1755 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA390 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 02/22/2010 | 02/22/2010 | 12/19/2010 | 371321 | 0.83
1756 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA391 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 04/21/2010 | 04/30/2010 | 02/24/2011 | 157697 | 0.5
1757 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA392 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 04/21/2010 | 04/30/2010 | 02/24/2011 | 125194 | 0.503
1758 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA393 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 04/21/2010 | 04/30/2010 | 02/24/2011 | 460235 | 0.99
1759 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA394 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 03/01/2010 | 03/01/2010 | 08/28/2010 | 269767 | 0.498
1760 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA395 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 03/01/2010 | 03/01/2010 | 08/28/2010 | 138492 | 0.04
1761 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA396 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 04/26/2010 | 04/26/2010 | 02/21/2011 | 741164 | 1.38
1762 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA397 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses a | Pavement Improvement | 11/30/2009 | 11/30/2009 | 07/30/2010 | 155885 | 0.311
1763 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA398 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses a | Pavement Improvement | 02/08/2010 | 02/08/2010 | 08/08/2010 | 144508 | 0.16
1764 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA399 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses a | Pavement Improvement | 01/26/2010 | 01/26/2010 | 07/26/2010 | 190280 | 0.826
1765 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA400 | This Leon County project will add a left turn lane and a traffic signal on Meridian Road at Ox Bottom Road to improve traffic operations and safety. | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 03/22/2010 | 831252 | 0.325
1766 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA401 | The City of Homestead will install streetlight poles. Streetlights along the corridor will enhance the safety of all roadway users. | Safety/Traffic Management | 12/01/2009 | 12/07/2009 | 05/31/2010 | 1345064 | 6.127
1767 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA402 | This new project involves the installation of decorative lighting along the Ludlam Drive Bike Path in the City of Miami Springs. The project will provide better visibility for pedestrians. | Safety/Traffic Management | 02/11/2010 | 02/12/2010 | 07/16/2010 | 319569 | 2
1768 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA404 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 02/25/2010 | 05/14/2010 | 05/28/2010 | 29707 | 0.191
1769 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA405 | This project will provide lighting enhancements for the City of Homestead. Streetlights along this corridor will enhance safety for all roadway users. | Safety/Traffic Management | 04/01/2010 | 04/01/2010 | 06/01/2010 | 230754 | 0.903
1770 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA406 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 02/25/2010 | 05/14/2010 |  | 80946 | 0.255
1771 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA407 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 02/25/2010 | 05/14/2010 | 05/28/2010 | 46214 | 0.137
1772 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA408 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 02/25/2010 | 05/14/2010 | 05/28/2010 | 84323 | 0.506
1773 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA409 | The City of South Miami will enhance sections of Sunset Drive by resurfacing, reconstructing sidewalks, upgrading drainage, and installing median landscaping and irrigation. This project will create a | Pavement Improvement | 11/30/2009 | 11/30/2009 | 03/30/2010 | 253166 | 0.219
1774 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA410 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 01/06/2010 | 01/06/2010 | 05/06/2010 | 13204 | 0.119
1775 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA411 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 01/06/2010 | 01/06/2010 | 05/06/2010 | 40834 | 0.16
1776 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA414 | The City of North Miami Beach will improve safety for motorists by repairing the underside of the bridge deck. | Bridge Improvement | 06/02/2010 |  |  | 250000 | 0.016
1777 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA415 | This project will repave the existing roadway. This project will enhance safety and mobility. | Pavement Improvement | 03/09/2010 | 03/10/2010 | 03/31/2011 | 611940 | 0.424
1778 | Florida | MONROE |  | 18,25 | ARRA418 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 02/05/2010 | 02/05/2010 | 07/16/2010 | 146521 | 0.394
1779 | Florida | MONROE |  | 18,25 | ARRA419 | The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians. | Transportation Enhancements | 02/05/2010 | 02/05/2010 |  | 170422 | 0.447
1780 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA424 | This project will repave roadways throughout the Town of Cutler Bay. This project will enhance the ride for users of the town's roadway network. | Pavement Improvement | 01/04/2010 | 01/27/2010 | 07/20/2010 | 220740 | 1.682
1781 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA425 | This project will repave roadways throughout the Town of Cutler Bay. This project will enhance the ride for users of the town's roadway network. | Pavement Improvement | 01/04/2010 | 03/22/2010 | 07/20/2010 | 156107 | 1.112
1782 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA426 | This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network. | Pavement Improvement | 01/04/2010 | 03/05/2010 | 07/20/2010 | 148088 | 1.232
1783 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA428 | This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network. | Pavement Improvement | 01/04/2010 | 02/04/2010 | 07/20/2010 | 48228 | 0.45
1784 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA432 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Pavement Improvement | 02/25/2010 | 02/25/2010 |  | 351528 | 1
1785 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA435 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 01/06/2010 | 01/06/2010 | 05/06/2010 | 17488 | 0.12
1786 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA436 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 01/06/2010 | 01/06/2010 | 05/06/2010 | 30971 | 0.5
1787 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA440 | This project will repave the existing roadway and repair existing pavement markings. This project will enhance safety and mobility. | Pavement Improvement | 10/06/2009 | 02/11/2010 | 05/25/2010 | 317175 | 0.501
1788 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA441 | The City of West Miami will construct four traffic-calming devices at various locations. This project will reduce the speed of traffic and improve pedestrian safety. | Safety/Traffic Management | 09/14/2009 | 10/20/2009 |  | 21064 | 0.013
1789 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA442 | The City of West Miami will construct four traffic-calming devices at various locations. This project will reduce the speed of traffic and improve pedestrian safety. | Safety/Traffic Management | 09/14/2009 | 10/14/2009 |  | 30996 | 0.13
1790 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA444 | This project will repave the existing roadway and repair existing pavement markings. This project will enhance safety and mobility. | Transportation Enhancements | 10/06/2009 | 11/18/2009 |  | 186171 | 0.47
1791 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA445 | This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network. | Pavement Improvement | 01/04/2010 | 02/19/2010 | 07/20/2010 | 160745 | 1.708
1792 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA446 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 11/23/2009 | 11/23/2009 | 07/22/2010 | 32243 | 1
1793 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA447 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 11/23/2009 | 11/23/2009 | 07/22/2010 | 20300 | 1.174
1794 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA448 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 11/23/2009 | 11/23/2009 | 07/22/2010 | 55948 | 0.504
1795 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA449 | This project involves widening 0.8 miles of a three-lane roadway to five lanes. This project will ease congestion and provide interconnectivity. | Pavement Widening | 01/15/2010 | 01/15/2010 |  | 776997 | 1.017
1796 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA450 | This project will provide sidewalk enhancements and increase pedestrian safety. | Transportation Enhancements | 01/04/2010 | 01/05/2010 | 06/20/2010 | 456640 | 0.707
1797 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA451 | This project will provide new construction of a new raised landscaped median, new turning bays for left turn movements and new curb bump outs at intersections to provide for improved bus access. This | Pavement Improvement | 03/18/2010 | 04/05/2010 | 12/22/2010 | 1036796 | 0.408
1798 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA455 | This project will repave the existing roadway. This project will enhance safety and mobility. | Pavement Improvement | 12/08/2009 | 01/15/2010 | 06/21/2010 | 813438 | 0.752
1799 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA456 | This project will resurface the existing roadway, upgrade sidewalks, signing and pavement markings, replace signals and landscape. This project will enhance mobility for the community. | Pavement Improvement | 05/27/2010 |  |  | 510979 | 0.297
1800 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA457 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 10/19/2009 | 10/19/2009 | 04/17/2010 | 88847 | 1.014
1801 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA458 | The City of Fort Walton Beach will repave Yacht Club Drive to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 12/10/2009 | 12/10/2009 | 04/30/2010 | 438108 | 1.304
1802 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA459 | The City of Fort Walton Beach will repave Wright Parkway to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 12/10/2009 | 12/10/2009 | 04/30/2010 | 152726 | 1.191
1803 | Florida | CALHOUN |  | 02 | ARRA460 | This safety project will provide roadway striping on city streets in the City of Blountstown to provide safer travel on roads that have little or no existing striping in Calhoun County. | Safety/Traffic Management | 12/14/2009 | 12/24/2009 | 04/13/2010 | 80384 | 3.125
1804 | Florida | GADSDEN |  | 02 | ARRA461 | This safety project will provide roadway striping on rural roads in Gadsden County to provide safer travel on roads that have little or no existing striping. | Safety/Traffic Management | 05/03/2010 | 05/11/2010 | 06/15/2010 | 500000 | 0
1805 | Florida | GADSDEN | TALLAHASSEE | 02 | ARRA462 | This safety project will provide roadway striping on roads in Gadsden County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 03/22/2010 | 04/01/2010 | 06/15/2010 | 268359 | 0
1806 | Florida | GULF |  | 02 | ARRA463 | Gulf County will repave County Road 30A to improve the road surface and driving quality. | Pavement Improvement | 01/28/2010 | 01/28/2010 | 04/30/2010 | 273078 | 0.3
1807 | Florida | HOLMES |  | 01 | ARRA464 | This safety project will provide roadway striping on rural roads in Holmes County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 11/06/2009 | 11/12/2009 | 03/01/2010 | 547215 | 16.647
1808 | Florida | LIBERTY |  | 02 | ARRA465 | Liberty County will install guardrail at several locations on county roads to improve the safety of the traveling public. | Safety/Traffic Management | 11/17/2009 | 11/30/2009 | 03/04/2010 | 266006 | 0
1809 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA467 | Okaloosa County will replace drainage pipes and existing failing pavement on Hollywood Boulevard in Fort Walton Beach to improve the road surface and driving quality. | Pavement Improvement | 11/19/2009 | 12/01/2009 | 05/15/2010 | 1271467 | 0.187
1810 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA468 | The City of Destin will add bus stops, public parking and landscaping, improve sidewalks, and replace existing failing pavement on Scenic Highway to improve pedestrian safety and travel in Okaloosa Co | Pavement Improvement | 10/06/2009 | 10/19/2009 | 08/24/2010 | 760955 | 0.771
1811 | Florida | WAKULLA |  | 02 | ARRA469 | This safety project will provide roadway striping on rural roads in Wakulla County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 10/13/2009 | 11/02/2009 | 10/11/2009 | 64707 | 19.785
1812 | Florida | WALTON | FORT WALTON BEACH | 01,02 | ARRA470 | Walton County will construct a pedestrian bridge over Big Redfish Lake along County Road 30A to improve pedestrian safety. | Transportation Enhancements | 01/07/2010 | 01/17/2010 | 05/18/2010 | 467007 | 0.001
1813 | Florida | WASHINGTON |  | 01 | ARRA471 | This safety project will provide roadway striping on rural roads in Washington County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 11/04/2009 | 11/14/2009 | 03/15/2010 | 449539 | 11.46
1814 | Florida | WASHINGTON |  | 01 | ARRA472 | Washington County will repave State Park Road to improve the road surface and driving quality. | Pavement Improvement | 12/07/2009 | 12/17/2009 | 05/22/2010 | 261575 | 1.035
1815 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA473 | This project involves the design of a traffic circle that will be used as a traffic calming device and improvements at crosswalks. This project will enhance safety and mobility. | Pavement Improvement | 02/19/2010 | 02/19/2010 | 06/18/2010 | 409310 | 0.178
1816 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA474 | This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network. | Pavement Improvement | 01/26/2010 | 02/19/2010 | 06/18/2010 | 160500 | 0.01
1817 | Florida | MONROE |  | 18,25 | ARRA476 | This project will provide intersection realignment, resurfacing of roadway, new striping, signage and emergency signalization. | Pavement Improvement | 02/05/2010 | 02/08/2010 |  | 87000 | 0.133
1818 | Florida | MONROE |  | 18,25 | ARRA478 | This project will enhance the Sombrero Beach Road extension by installing storm water facilities, renovating the bike path, installing streetlights, and widening, resurfacing and restriping the road. | Pavement Improvement | 01/11/2010 | 01/27/2010 |  | 1010000 | 0.26
1819 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA479 | This project will repave approximately 0.9 miles of Harbor Drive to improve the ride for the users of this roadway. | Pavement Improvement | 10/19/2009 | 10/19/2009 | 04/19/2010 | 108566 | 0.912
1820 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA480 | This project will install lighting along approximately 0.4 mile of the project corridor providing better visibility to the users of this roadway. | Safety/Traffic Management | 10/19/2009 | 10/19/2009 | 04/19/2010 | 153021 | 0.497
1821 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA482 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 07/09/2010 |  |  | 132034 | 0.21
1822 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA484 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/16/2010 | 02/16/2010 | 11/18/2010 | 584666 | 2
1823 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA485 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 04/07/2010 | 04/19/2010 | 04/19/2011 | 1280249 | 2.51
1824 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA486 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 04/07/2010 | 04/19/2010 | 09/16/2010 | 259496 | 1.54
1825 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA487 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/16/2010 | 02/16/2010 | 11/18/2010 | 554999 | 1.32
1826 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA488 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/16/2010 | 02/16/2010 | 11/18/2010 | 212168 | 0.509
1827 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA489 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/16/2010 | 02/16/2010 | 11/18/2010 | 234036 | 2.039
1828 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA490 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists. | Safety/Traffic Management | 03/29/2010 | 03/29/2010 | 11/09/2010 | 248710 | 1.003
1829 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA491 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 03/01/2010 | 03/01/2010 | 12/01/2010 | 471766 | 2.976
1830 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA492 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/23/2010 | 03/01/2010 | 12/01/2010 | 469453 | 1.762
1831 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA493 | The Village of Pinecrest will repave two miles of road. This project will enhance mobility for users of this roadway. | Pavement Improvement | 12/25/2009 | 01/04/2010 | 03/12/2010 | 252822 | 2.042
1832 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA494 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 03/29/2010 | 03/29/2010 |  | 419806 | 2.77
1833 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA495 | The project will repave the existing roadway. This project will enhance mobility for users of this roadway. | Pavement Improvement | 12/25/2009 | 01/19/2010 | 03/12/2010 | 187587 | 1.331
1834 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA496 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/23/2010 | 03/01/2010 | 12/01/2010 | 323897 | 1.989
1835 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA497 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/23/2010 | 03/01/2010 | 12/01/2010 | 566110 | 2.001
1836 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA498 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/23/2010 | 03/01/2010 | 12/01/2010 | 162411 | 1.212
1837 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA499 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/23/2010 | 03/01/2010 | 10/02/2010 | 643535 | 2.004
1838 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA500 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 02/23/2010 | 03/01/2010 | 10/12/2010 | 307073 | 1.009
1839 | Florida | CALHOUN |  | 02 | ARRA501 | Guardrail will be installed on several county roads in Calhoun County to improve the safety of the traveling public. | Safety/Traffic Management | 07/29/2009 | 07/29/2009 | 07/28/2010 | 146938 | 6.302
1840 | Florida | CALHOUN |  | 02 | ARRA502 | This safety project will provide roadway striping on rural roads in Calhoun County to provide safer travel on roads that had little or no existing striping. | Safety/Traffic Management | 07/29/2009 | 07/29/2009 | 07/28/2010 | 214699 | 9.656
1841 | Florida | WAKULLA |  | 02 | ARRA503 | Crosswalks and sidewalks were constructed along State Road 363 to improve pedestrian safety in the City of St. Marks. | Transportation Enhancements | 08/18/2009 | 08/18/2009 | 04/17/2010 | 33236 | 0.097
1842 | Florida | GADSDEN |  | 02 | ARRA504 | Five-foot wide sidewalks along various streets within the city limits of Gretna will be constructed to improve pedestrian safety in Gadsden County . | Transportation Enhancements | 08/18/2009 | 08/18/2009 | 04/17/2010 | 348058 | 0.777
1843 | Florida | HOLMES |  | 01 | ARRA505 | This pedestrian safety project in Holmes County will include the construction of a 600-foot sidewalk in the Town of Noma. | Transportation Enhancements | 07/29/2009 | 07/29/2009 | 07/28/2010 | 37574 | 0.117
1844 | Florida | HOLMES |  | 01 | ARRA506 | This pedestrian safety project in Holmes County will include the construction of a 900-foot sidewalk in the Town of Esto. | Transportation Enhancements | 07/29/2009 | 07/29/2009 | 07/28/2010 | 74566 | 0.336
1845 | Florida | JEFFERSON |  | 02,04 | ARRA507 | Existing deficient pavement on North Salt Road in Jefferson County will be replaced to improve the road surface and driving quality. | Safety/Traffic Management | 08/18/2009 | 08/18/2009 | 05/17/2010 | 735371 | 4.889
1846 | Florida | JACKSON |  | 02 | ARRA508 | A five-foot wide sidewalk along State Road 69 will be constructed in the City of Grand Ridge to improve pedestrian safety in Jackson County. | Transportation Enhancements | 07/29/2009 | 07/29/2009 | 07/28/2010 | 133913 | 0.255
1847 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA509 | A five-foot wide sidewalk along State Road 285 has been constructed in the City of Niceville to improve pedestrian safety in Okaloosa County. | Transportation Enhancements | 07/29/2009 | 07/29/2009 | 07/28/2010 | 155764 | 0.858
1848 | Florida | WALTON | FORT WALTON BEACH | 01,02 | ARRA510 | A five-foot wide sidewalk along Live Oak Avenue will be constructed in the City of DeFuniak Springs to improve pedestrian safety in Walton County. | Transportation Enhancements | 07/29/2009 | 07/29/2009 | 07/28/2010 | 164295 | 2.196
1849 | Florida | WALTON | FORT WALTON BEACH | 01,02 | ARRA511 | Walton County will repave County Road 30A to improve the road surface and driving quality. | Pavement Improvement | 01/07/2010 | 01/17/2010 | 05/12/2010 | 1028522 | 1.17
1850 | Florida | JACKSON |  | 02 | ARRA512 | The City of Marianna in Jackson County will repave College Street to improve the road surface and driving quality. | Pavement Improvement | 10/19/2009 | 10/19/2009 | 05/13/2010 | 187993 | 0.589
1851 | Florida | WALTON | FORT WALTON BEACH | 01,02 | ARRA513 | The City of Freeport will construct a five-foot wide sidewalk along State Road 20 to improve pedestrian safety in Walton County. | Transportation Enhancements | 11/09/2009 | 11/09/2009 | 11/12/2009 | 49132 | 0.114
1852 | Florida | WAKULLA | TALLAHASSEE | 02 | ARRA514 | This project will improve safety for motorists by providing a left turn lane onto Russell Drive north of the City of Crawfordville. | Pavement Widening | 08/18/2009 | 08/18/2009 | 04/17/2010 | 200184 | 0.214
1853 | Florida | JACKSON |  | 02 | ARRA515 | This Jackson County project consists of installing sidewalk along Caverns Road to increase pedestrian safety to Marianna High School. | Transportation Enhancements | 10/15/2009 | 10/15/2009 | 06/28/2010 | 507379 | 1.631
1854 | Florida | JACKSON |  | 02 | ARRA516 | This Jackson County project consists of restriping cross-walks and replacing failing sidewalks to improve pedestrian safety in the City of Marianna. | Safety/Traffic Management | 10/15/2009 | 10/15/2009 | 04/27/2010 | 216183 | 0.068
1855 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA517 | The City of Tallahassee will construct approximately 2,300 feet of sidewalk along Idlewild Drive to improve pedestrian safety in Leon County. | Transportation Enhancements | 03/04/2010 | 03/04/2010 | 11/19/2010 | 309486 | 0.413
1856 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA518 | The City of Tallahassee will construct approximately 1,800 feet of sidewalk along Lucy Street to improve pedestrian safety in Leon County. | Transportation Enhancements | 03/03/2010 | 03/03/2010 | 09/20/2010 | 102282 | 0.353
1857 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA519 | This City of Tallahassee project will reconstruct curb ramps and pedestrian signal features to improve pedestrian safety in the community. | Transportation Enhancements | 03/29/2010 | 03/29/2010 | 09/21/2010 | 174865 | 1.081
1858 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA520 | The City of Tallahassee will construct approximately 1,600 feet of sidewalk along Joe Louis Street to improve pedestrian safety in Leon County. | Transportation Enhancements | 03/03/2010 | 03/03/2010 | 11/19/2010 | 412769 | 0.427
1859 | Florida | OKALOOSA | FORT WALTON BEACH | 01,02 | ARRA521 | The City of Fort Walton Beach will repave Country Club Avenue to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 12/10/2009 | 12/10/2009 | 04/30/2010 | 142948 | 0.85
1860 | Florida | GADSDEN | TALLAHASSEE | 02 | ARRA522 | Gadsden County will repave Glades Road to improve the road surface and driving quality. | Pavement Improvement | 12/14/2009 | 12/24/2009 | 02/10/2010 | 384409 | 1.84
1861 | Florida | GADSDEN |  | 02 | ARRA523 | Gadsden County will repave South Main Street to improve the road surface and driving quality. | Pavement Improvement | 03/16/2010 | 03/26/2010 | 06/22/2010 | 123790 | 0.25
1862 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA524 | Leon County will construct approximately 4,700 feet of sidewalk along Dempsey Mayo Road to improve pedestrian safety. | Transportation Enhancements | 01/19/2010 | 01/19/2010 | 03/22/2010 | 174287 | 0.906
1863 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA525 | Leon County will repair the existing sidewalk and construct additional sidewalk along Perkins Road to improve pedestrian safety in the City of Tallahassee. | Transportation Enhancements | 11/23/2009 | 11/23/2009 | 03/22/2010 | 18728 | 0.076
1864 | Florida | LEON | TALLAHASSEE | 02,04 | ARRA526 | Leon County will construct approximately one mile of sidewalk along Velda Dairy Road to improve pedestrian safety. | Transportation Enhancements | 04/13/2010 | 04/13/2010 | 07/16/2010 | 306023 | 1.729
1865 | Florida | OKALOOSA |  | 01,02 | ARRA527 | Okaloosa County will construct a five-foot sidewalk along Brookmeade Drive to improve pedestrian safety in the City of Crestview. | Transportation Enhancements | 12/16/2009 | 12/21/2009 | 04/11/2010 | 81455 | 0.373
1866 | Florida | FRANKLIN |  | 02 | ARRA528 | Franklin County will construct approximately 2,700 feet of five-foot wide sidewalk along Pine Avenue to improve pedestrian safety. | Transportation Enhancements | 11/09/2009 | 11/09/2009 | 04/11/2010 | 98746 | 0.227
1867 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA529 | Escambia County will repave Dog Track Road to improve the road surface and driving quality. | Pavement Improvement | 10/13/2009 | 10/19/2009 | 06/30/2010 | 256347 | 1.125
1868 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA530 | Escambia County will repave Old Palafox Road from East Roberts Boulevard to Nine Mile Road to improve the road surface and driving quality in the City of Pensacola. | Pavement Improvement | 10/13/2009 | 10/19/2009 | 08/19/2010 | 428777 | 2.182
1869 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA531 | Escambia County will repave Old Palafox Road from Memory Lane to Nine Mile Road to improve the road surface and driving quality in the City of Pensacola. | Pavement Improvement | 10/29/2009 | 11/02/2009 | 10/08/2010 | 1210430 | 4.342
1870 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA532 | Escambia County will repave Copter Road to improve the road surface and driving quality. | Pavement Improvement | 10/13/2009 | 10/19/2009 | 05/31/2010 | 284103 | 0.428
1871 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA533 | Along with pedestrian safety improvements, Escambia County will repave "W" Street to improve the road surface and driving quality. | Pavement Improvement | 10/13/2009 | 10/19/2009 |  | 1645399 | 3.081
1872 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA534 | Escambia County will repave Dog Track Road from Blue Angel Parkway to US 98 to improve the road surface and driving quality. | Pavement Improvement | 10/13/2009 | 10/19/2009 | 08/19/2010 | 474210 | 2.084
1873 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA535 | Escambia County will repave East Johnson Avenue to improve the road surface and driving quality. | Pavement Improvement | 10/13/2009 | 10/19/2009 | 06/30/2010 | 243267 | 0.845
1874 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA536 | Escambia County will repave Beulah Road to improve the road surface and driving quality. | Pavement Improvement | 04/20/2010 | 04/26/2010 | 08/23/2010 | 650716 | 1.35
1875 | Florida | ESCAMBIA | PENSACOLA | 01 | ARRA537 | Escambia County will construct a five-foot wide sidewalk along Broad Street to improve pedestrian safety. | Transportation Enhancements | 10/13/2009 | 10/19/2009 | 04/12/2010 | 143690 | 0.468
1876 | Florida | MANATEE |  | 11,13 | ARRA538 | Add Sidewalks along Gulf Front Park from Maple Street to Oak Street in the City of Anna Maria to improve safety for pedestrians in the area. | Transportation Enhancements | 09/16/2009 | 11/09/2009 | 12/12/2009 | 6981 | 0
1877 | Florida | LIBERTY |  | 02 | ARRA541 | Liberty County will construct approximately one mile of sidewalk along County Road 12 leading to Tolar Elementary School to improve pedestrian safety in the City of Bristol. | Transportation Enhancements | 12/02/2009 | 12/07/2009 | 05/15/2010 | 220000 | 0.809
1878 | Florida | WAKULLA | TALLAHASSEE | 02 | ARRA542 | This project will improve safety for motorists by providing a left turn lane onto Aaron Strickland Road north of the City of Crawfordville. | Pavement Widening | 02/01/2010 | 02/15/2010 | 05/28/2010 | 174680 | 0.287
1879 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA543 | Add a new sidewalk along Cape Coral Parkway from Agualinda Boulevard to 16th Place in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 11/17/2009 | 11/23/2009 | 05/31/2010 | 102495 | 0.846
1880 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA545 | Add a new sidewalk along Nicholas Parkway from State Road 78 to Santa Barbara Boulevard in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 11/17/2009 | 03/29/2010 | 10/31/2010 | 271934 | 1.344
1881 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA546 | Add a new sidewalk along Beach Parkway from Surfside Boulevard to Chiquita Boulevard in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 11/17/2009 |  |  | 402282 | 1.935
1882 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA547 | This State Road 40 project in the City of Ormond Beach will provide an eight-foot wide bike/pedestrian trail in a residential community. | Transportation Enhancements | 03/01/2010 | 03/01/2010 | 07/29/2010 | 179057 | 0.969
1883 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA549 | On the southeast side of Jacksonville, State Road 9B, a new four-lane highway, will relieve congestion on the heavily traveled U.S. 1 and Old St. Augustine Road corridors. | New Construction | 02/05/2010 | 02/05/2010 | 11/01/2012 | 64627225 | 3.593
1884 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA550 | On the southeast side of Jacksonville, State Road 9B, a new four-lane highway, will relieve congestion on the heavily traveled U.S. 1 and Old St. Augustine Road corridors. | New Construction | 02/05/2010 | 02/05/2010 | 11/01/2012 | 11431433 | 0.501
1885 | Florida | CITRUS |  | 05 | ARRA551 | In Citrus County, this project repaves 2.4 miles of Independence Highway from State Road 44 to U.S. 41 to improve the road surface. | Pavement Improvement | 04/04/2010 | 04/06/2010 | 06/19/2010 | 424145 | 2.412
1886 | Florida | HERNANDO |  | 05 | ARRA552 | In Hernando County, due to the poor condition of the road, this project resurfaces 1.6 miles of County Road 574 from California Street to Broad Street (U.S. 41). | Pavement Improvement | 05/21/2010 |  | 08/26/2010 | 567500 | 1.595
1887 | Florida | HERNANDO |  | 05 | ARRA553 | In Hernando County, this project repaves 2.5 miles of the asphalt surface of County Road 541 from Mountain View Blvd. to State Road 50 to improve the road surface. | Pavement Improvement | 06/01/2010 | 06/01/2010 | 11/28/2010 | 1281011 | 2.45
1888 | Florida | LEE |  | 14 | ARRA555 | Widen Interstate 75 from Colonial Boulevard to State Road 82 in Southwest Florida from four to six lanes to move daily traffic and commerce more efficiently. | Pavement Widening | 12/15/2009 | 12/21/2009 | 10/14/2011 | 10054054 | 1.536
1889 | Florida | GADSDEN |  | 02 | ARRA557 | SIDEWALK CITY OF GRETNA FOURTH STREET SIDEWALK 2009 ECONOMIC STIMULUS (0000.285 MILES) IN GADSDEN COUNTY, FLORIDA. | Transportation Enhancements | 03/08/2010 | 03/08/2010 |  | 39763 | 0.285
1890 | Florida | HENDRY |  | 16,23 | ARRA558 | WIDEN/RESURFACE EXIST LANES CR 832 (KERI ROAD) FROM SR 29 TO 13.1 MILES E OF SR 29 (0013.100 MILES) IN HENDRY COUNTY, FLORIDA. | Pavement Improvement | 02/11/2010 | 05/10/2010 | 06/08/2011 | 2428516 | 13.1
1891 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA559 | RESURFACING HABEN BLVD FROM US 301 TO US 41 (0001.044 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 01/18/2010 | 01/18/2010 | 10/24/2010 | 822744 | 1.044
1892 | Florida | HOLMES |  | 01 | ARRA560 | SIDEWALK SR 79 SIDEWALKS PHASE II 2009 ECONOMIC STIMULUS (0000.433 MILES) IN HOLMES COUNTY, FLORIDA. | Transportation Enhancements | 02/17/2010 | 02/17/2010 |  | 85241 | 0.433
1893 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA561 | RESURFACING BRENTWOOD DRIVE FROM FEC RAILROAD TO DERBYSHIRE ROAD (0001.478 MILES) IN VOLUSIA COUNTY, FLORIDA. | Pavement Improvement | 06/04/2010 | 06/14/2010 |  | 131931 | 1.478
1894 | Florida | MARION | OCALA | 03,05,06,08 | ARRA563 | RESURFACING SE LAKE WEIR AVENUE FROM SE 31ST STREET TO S OF SE 38TH STREET (0000.564 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 06/16/2010 |  |  | 180914 | 0.564
1895 | Florida | MANATEE | SARASOTA-BRADENTON | 11,13 | ARRA565 | Resurface State Road 64 (Manatee Avenue) from 12th East to 15th Street West to improve the surface of this heavily traveled road. | Pavement Improvement | 02/09/2010 | 02/09/2010 | 03/16/2011 | 1083242 | 1.321
1896 | Florida | LIBERTY |  | 02 | ARRA566 | SIDEWALK CR 12 SIDEWALK PHASE II 2009 ECONOMIC STIMULUS (0000.358 MILES) IN LIBERTY COUNTY, FLORIDA. | Transportation Enhancements | 03/23/2010 | 03/23/2010 |  | 67848 | 0.358
1897 | Florida | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,10,11 | ARRA567 | BIKE PATH/TRAIL NORTH BAY TRAIL (1ST ST) FROM 30TH AVE N TO 54TH AVE N IN PINELLAS COUNTY, FLORIDA. | Transportation Enhancements | 05/12/2010 | 05/12/2010 | 04/23/2011 | 1026823 | 0
1898 | Florida | CITRUS |  | 05 | ARRA568 | RESURFACING CR490(HOMOSASSA TRL) FROM US 19 TO SR 44 (0006.184 MILES) IN CITRUS COUNTY, FLORIDA. | Pavement Improvement | 05/09/2010 | 05/09/2010 | 08/14/2010 | 842437 | 6.184
1899 | Florida | HERNANDO |  | 05 | ARRA569 | RESURFACING WISCON RD FROM SR 50 TO US 41 (0004.224 MILES) IN HERNANDO COUNTY, FLORIDA. | Pavement Improvement | 05/23/2010 | 05/23/2010 | 07/07/2010 | 978000 | 4.224
1900 | Florida | HIGHLANDS |  | 16 | ARRA570 | RESURFACING SPARTA ROAD FROM SR 66 TO ORDAY ROAD (0001.400 MILES) IN HIGHLANDS COUNTY, FLORIDA. | Pavement Improvement | 03/10/2010 | 03/29/2010 | 02/02/2011 | 377300 | 1.4
1901 | Florida | COLLIER | NAPLES | 14,25 | ARRA571 | BRIDGE REHABILITATION MOORINGLINE DRIVE AT BRIDGE #030125 (0000.001 MILES) IN COLLIER COUNTY, FLORIDA. | Pavement Improvement | 02/17/2010 |  |  | 540512 | 0.001
1902 | Florida | MARION | OCALA | 03,05,06,08 | ARRA572 | SIDEWALK DOWNTOWN OCALA BIKE/PED IMPROVEMENTS BROADWAY & SW 1ST AVE IN MARION COUNTY, FLORIDA. | Transportation Enhancements | 05/18/2010 | 06/15/2010 | 06/30/2010 | 300000 | 0
1903 | Florida | MARION | OCALA | 03,05,06,08 | ARRA573 | RESURFACING NW/SW 27TH AVENUE FROM SW 20TH STREET TO NW OLD BLITCHTON ROAD (0001.994 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 06/16/2010 |  |  | 826232 | 1.994
1904 | Florida | SUMTER |  | 05 | ARRA574 | RESURFACING CR 470 FROM LAKE PANASOFKEE OUTF ALL CANAL TO SR 44 (0004.642 MILES) IN SUMTER COUNTY, FLORIDA. | Pavement Improvement | 06/01/2010 | 06/15/2010 |  | 1131759 | 4.642
1905 | Florida | SUMTER |  | 05 | ARRA575 | RESURFACING CR 476 E FROM US 301 TO SR 471 (0003.163 MILES) IN SUMTER COUNTY, FLORIDA. | Pavement Improvement | 06/01/2010 | 06/15/2010 |  | 860380 | 3.163
1906 | Florida | VOLUSIA | DAYTONA BEACH | 03,07,24 | ARRA581 | SIDEWALK SR40 MULTI-USE TRAIL (PHASE II) OLD TOMOKA RD TO BREAKAWAY TRAILS (0001.120 MILES) IN VOLUSIA COUNTY, FLORIDA. | Transportation Enhancements | 05/21/2010 | 06/14/2010 | 11/11/2010 | 196059 | 1.12
1907 | Florida | SUWANNEE |  | 02 | ARRA583 | BIKE PATH/TRAIL SR 49 (US 129) FR:WM.GUY LEMMON MEM.PARK TO SR 20 (US 27) (0002.706 MILES) IN SUWANNEE COUNTY, FLORIDA. | Transportation Enhancements | 06/25/2010 |  |  | 648374 | 2.706
1908 | Florida | SUWANNEE |  | 02 | ARRA584 | WIDEN/RESURFACE EXIST LANES CR 252 FROM US 129 TO CR 137 (0008.493 MILES) IN SUWANNEE COUNTY, FLORIDA. | Pavement Improvement | 07/06/2010 |  |  | 3468585 | 8.493
1909 | Florida | JACKSON |  | 02 | ARRA585 | SIDEWALK OLD SPANISH TRAIL FROM LOCKEY AVE TO 3RD AVE (0001.760 MILES) IN JACKSON COUNTY, FLORIDA. | Transportation Enhancements | 06/15/2010 |  |  | 327459 | 1.76
1910 | Florida | BAY | PANAMA CITY | 02 | ARRA587 | RESURFACING 11TH STREET RESURFACING (0001.925 MILES) IN BAY COUNTY, FLORIDA. | Pavement Improvement | 07/19/2010 |  |  | 1000000 | 1.925
1911 | Florida | JEFFERSON |  | 02,04 | ARRA589 | RESURFACING NORTH SALT ROAD PHASE II RESURFACING (0000.939 MILES) IN JEFFERSON COUNTY, FLORIDA. | Pavement Improvement | 04/20/2010 | 04/20/2010 | 09/17/2010 | 176301 | 0.939
1912 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA593 | SIDEWALK WEST CASTILLO DRIVE FROM: SR 5 (US 1) TO: SR 5A/SAN MARCO AVE. (0000.277 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Transportation Enhancements | 04/08/2010 | 04/08/2010 | 06/16/2012 | 208705 | 0.277
1913 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA594 | TRAFFIC OPS IMPROVEMENT SR 207 @ SR 312 (0000.013 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Safety/Traffic Management | 04/08/2010 | 04/08/2010 | 06/16/2012 | 1142386 | 0.013
1914 | Florida | NASSAU | JACKSONVILLE | 04 | ARRA595 | TRAFFIC OPS IMPROVEMENT SR A1A/SR 200 @ BLACKROCK ROAD (0000.001 MILES) IN NASSAU COUNTY, FLORIDA. | Safety/Traffic Management | 03/31/2010 | 04/08/2010 | 06/16/2012 | 794513 | 0.001
1915 | Florida | CLAY | JACKSONVILLE | 03,06 | ARRA596 | WIDEN/RESURFACE EXIST LANES CR 220 FROM: CR 209 TO: BLANDING BLVD. (0003.078 MILES) IN CLAY COUNTY, FLORIDA. | Pavement Improvement | 03/30/2010 | 03/30/2010 | 06/16/2012 | 1626653 | 3.078
1916 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA597 | RESURFACING 9TH STREET FROM: OSCEOLA AVENUE TO: ST. JOHNS C/L (0000.182 MILES) IN DUVAL COUNTY, FLORIDA. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 05/01/2011 | 1145116 | 0.182
1917 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA598 | RESURFACING OLD DIXIE HIGHWAY FROM: SR 312 TO: SR 207 (0000.227 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Pavement Improvement | 04/08/2010 | 04/08/2010 | 06/16/2012 | 365061 | 0.227
1918 | Florida | NASSAU | JACKSONVILLE | 04 | ARRA599 | SIDEWALK CR 107 BLACKROCK RD FROM: WINDSOR DRIVE TO: HERRON ISLES PKWAY (0001.611 MILES) IN NASSAU COUNTY, FLORIDA. | Transportation Enhancements | 06/16/2009 | 06/16/2009 | 05/01/2011 | 399893 | 1.611
1919 | Florida | CLAY | JACKSONVILLE | 03,06 | ARRA600 | RESURFACING MOODY AVENUE FROM: DRS. LAKE ROAD TO: PE0RIA (0001.880 MILES) IN CLAY COUNTY, FLORIDA. | Pavement Improvement | 03/30/2010 | 03/30/2010 | 06/16/2012 | 960317 | 1.88
1920 | Florida | DUVAL | JACKSONVILLE | 03,04,06 | ARRA601 | RESURFACING CAHOON AVENUE FROM: DEVOE STREET TO: CANNON STREET (0000.297 MILES) IN DUVAL COUNTY, FLORIDA. | Pavement Improvement | 03/31/2010 | 04/08/2010 | 06/16/2012 | 197795 | 0.297
1921 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA602 | BRIDGE-REPAIR/REHABILITATION CR 214 BRIDGE OVER I-95 (0000.044 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Bridge Improvement | 04/08/2010 | 04/08/2010 | 06/16/2012 | 230365 | 0.044
1922 | Florida | CLAY | JACKSONVILLE | 03,06 | ARRA603 | TRAFFIC OPS IMPROVEMENT SR 224/KINGSLEY AVE. FROM: PLAINFIELD AVENUE TO: SMITH STREET (0000.438 MILES) IN CLAY COUNTY, FLORIDA. | Safety/Traffic Management | 03/30/2010 | 03/30/2010 | 06/16/2012 | 139857 | 0.438
1923 | Florida | ST JOHNS | JACKSONVILLE | 07 | ARRA604 | RESURFACING CR 13B/FRUIT COVE RD FROM: SR 13 TO: SR 13 (0002.381 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Pavement Improvement | 04/08/2010 | 04/08/2010 | 06/16/2012 | 1042928 | 2.381
1924 | Florida | ALACHUA | GAINESVILLE | 03,06 | ARRA607 | SIDEWALK SR 121/NW 34TH ST. SR 222/NW 39TH AVE/MP5.86 TO NW 55TH BLVD /MP7.730 IN ALACHUA COUNTY, FLORIDA. | Transportation Enhancements | 08/04/2009 | 08/04/2009 | 06/15/2012 | 243958 | 1.87
1925 | Florida | OKEECHOBEE |  | 16 | ARRA608 | SIDEWALK OKEECHOBEE SIDEWALKS AT VARIOUS LOCATIONS IN OKEECHOBEE COUNTY, FLORIDA. | Transportation Enhancements | 02/22/2010 | 04/14/2010 | 10/31/2010 | 292072 | 0
1926 | Florida | DE SOTO |  | 13 | ARRA609 | BRIDGE-ROUTINE MAINTENANCE CR 761 (CR 769) AT BRIDGE #040004 (0000.090 MILES) IN DESOTO COUNTY, FLORIDA. | Pavement Improvement | 02/18/2010 | 05/04/2010 | 02/08/2011 | 410965 | 0.09
1927 | Florida | HARDEE |  | 13 | ARRA610 | SIDEWALK 4TH STREET FROM US 17 TO SCHOOL HOUSE RD IN HARDEE COUNTY, FLORIDA. | Transportation Enhancements | 05/04/2010 | 05/04/2010 | 10/21/2010 | 136253 | 0
1928 | Florida | DE SOTO |  | 13 | ARRA611 | SIDEWALK POLK STREET FROM MAGNOLIA STREET TO HICKORY STREET IN DESOTO COUNTY, FLORIDA. | Transportation Enhancements | 05/04/2010 | 05/04/2010 | 10/21/2010 | 54484 | 0
1929 | Florida | GLADES |  | 16 | ARRA612 | BIKE PATH/TRAIL VANCE WHIDDEN PARK IN GLADES COUNTY, FLORIDA. | Transportation Enhancements | 04/13/2010 | 04/13/2010 | 10/30/2010 | 257500 | 0
1930 | Florida | LEE | FORT MYERS-CAPE | 14 | ARRA613 | ADD LANES & REHABILITATE PVMNT I-75 FROM S OF SR 82 TO S OF LUCKETT ROAD (0001.529 MILES) IN LEE COUNTY, FLORIDA. | Pavement Widening | 03/25/2010 | 04/09/2010 | 07/13/2011 | 8980155 | 1.529
1931 | Florida | PASCO |  | 05,09 | ARRA614 | SIDEWALK US 301/98 (SR35/700) FROM DADE CITY AVE TO US 98 BYPASS (0001.098 MILES) IN PASCO COUNTY, FLORIDA. | Transportation Enhancements | 06/08/2010 | 06/14/2010 |  | 560740 | 1.098
1932 | Florida | HARDEE |  | 13 | ARRA615 | LIGHTING US 17 (SOUTHBOUND) FROM MAIN STREET TO HARDEE STREET (0000.491 MILES) IN HARDEE COUNTY, FLORIDA. | Transportation Enhancements | 02/17/2010 | 04/13/2010 |  | 369410 | 0.491
1933 | Florida | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA616 | PEDESTRIAN/WILDLIFE OVERPASS LEGACY TRAIL AT US 41 (0000.100 MILES) IN SARASOTA COUNTY, FLORIDA. | Transportation Enhancements | 03/30/2010 |  |  | 3015846 | 0.1
1934 | Florida | HENDRY |  | 16,23 | ARRA619 | SIDEWALK NW/NE EUCALYPTUS BLVD FROM COWBOY WAY TO COLLINSWOOD PKWY IN HENDRY COUNTY, FLORIDA. | Transportation Enhancements | 07/13/2010 |  |  | 210771 | 0
1935 | Florida | FRANKLIN |  | 02 | ARRA620 | SIDEWALK OAK STREET SIDEWALKS (0000.506 MILES) IN FRANKLIN COUNTY, FLORIDA. | Transportation Enhancements | 04/14/2010 | 04/14/2010 | 09/11/2010 | 171172 | 0.506
1936 | Florida | MARION | OCALA | 03,05,06,08 | ARRA623 | SIDEWALK MARION OAKS TRAIL FROM SW 63RD TERRACE TO SW 31ST AVENUE IN MARION COUNTY, FLORIDA. | Transportation Enhancements | 06/04/2010 | 06/08/2010 |  | 266125 | 0
1937 | Florida | BREVARD | MELBOURNE-COCOA | 15,24 | ARRA624 | SIDEWALK COGAN DRIVE SIDEWALK FROM TORRENCE AVENUE TO BABCOCK STREET (0000.950 MILES) IN BREVARD COUNTY, FLORIDA. | Transportation Enhancements | 06/07/2010 | 06/14/2010 |  | 71905 | 0.95
1938 | Florida | FLAGLER |  | 07 | ARRA625 | RESURFACING PALM COAST PARKWAY FROM OLD KINGS ROAD TO PALM HARBOR PARKWAY IN FLAGLER COUNTY, FLORIDA. | Pavement Improvement | 05/16/2010 | 05/16/2010 | 07/15/2010 | 258117 | 1.818
1939 | Florida | FLAGLER |  | 07 | ARRA626 | SIDEWALK BELLE TERRE PKWAY MULTI USE PATH FROM PINE GROVE TO PINE LAKES PKWY IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 06/10/2010 | 06/11/2010 |  | 319809 | 1.936
1940 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA627 | SIDEWALK NORTH LOCKWOOD BLVD FROM ASHLAND TRAIL TO CR 426 IN SEMINOLE COUNTY, FLORIDA. | Transportation Enhancements | 06/09/2010 | 06/28/2010 |  | 390077 | 0
1941 | Florida | SEMINOLE | ORLANDO | 03,07,24 | ARRA628 | RESURFACING RINEHART ROAD FROM CR 46-A TO TOWNE CENTER BLVD. IN SEMINOLE COUNTY, FLORIDA. | Pavement Improvement | 06/18/2010 |  |  | 261601 | 0.796
1942 | Florida | CITRUS |  | 05 | ARRA629 | RESURFACING US 19 (SR 55) FROM NW SNUG HARBOR RD TO W CORNFLOWER DR (0007.476 MILES) IN CITRUS COUNTY, FLORIDA. | Pavement Improvement | 06/06/2010 | 06/06/2010 |  | 2912023 | 7.476
1943 | Florida | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17,18,20,21,25 | ARRA631 | FLEXIBLE PAVEMENT RECONSTRUCT. WEST 36 AVENUE FROM WEST 76 STREET TO WEST 84 STREET (0000.498 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 06/28/2010 | 06/28/2010 |  | 594030 | 0.498
1944 | Florida | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09,10,11 | ARRA636 | INTERSECTION IMPROVEMENT US 19 (SR 55) FROM S OF MCCORMICK DR TO N OF ENTERPRISE RD (0000.957 MILES) IN PINELLAS COUNTY, FLORIDA. | Safety/Traffic Management | 05/27/2010 |  |  | 3359263 | 0.957
1945 | Florida | ALACHUA |  | 03,06 | ARRA637 | RESURFACING SR 200 (US 301) FROM NE 76TH PLACE TO SR 24 (0011.838 MILES) IN ALACHUA COUNTY, FLORIDA. | Pavement Improvement | 06/07/2010 |  |  | 3737345 | 11.838
1946 | Georgia | MUSCOGEE | COLUMBUS (AL) | 2, 3 | 0000099 | This is an enhancement project in Muscogee County. The project construction consists of the construction of a 10 to 12 foot multi use trail beginning at Columbus State University and extending northe | Transportation Enhancements | 09/23/2009 | 09/28/2009 | 05/15/2011 | 663681 | 12
1947 | Georgia | LANIER |  | 1 | 0000310 | This is a safety improvment project in Lanier County on SR 11/US 129. The project will realign on new location SR 11/US 129 and SR 31, 122/ US 221 to create two 90 degree intersections with SR 37 to | Pavement Widening | 07/27/2009 | 08/03/2009 | 06/30/2010 | 1887702.04 | 1.05
1948 | Georgia | DOUGLAS | ATLANTA | 13 | 0000424 | This project consists of reconstructing the existing intersection of SR 5 and Rose Avenue, located just north of I-20 in Douglas County. The existing intersection has an undesirable scissor-type confi | Safety/Traffic Management | 07/27/2009 | 08/18/2009 | 04/07/2011 | 2589555.28 | 0.2
1949 | Georgia | GORDON |  | 9 | 0000683 | This project is a bridge replacement project is Gordon and Murray counties. The bridge is located on County Road 134/County Line Road over Polecat Creek on the Gordon and Murray county line. Also, t | Bridge Replacement | 07/27/2009 | 09/17/2009 | 05/31/2013 | 1439870.03 | 0.61
1950 | Georgia | NEWTON | ATLANTA | 8 | 0000842 | This project is an intersection improvement project in Newton County. This project will widen SR 162/Salem Road 6 ft. symmetrically to provide a north bound left turn lane. In addition, County Road | Safety/Traffic Management | 11/03/2009 | 11/17/2009 | 12/31/2010 | 820632.7 | 0.32
1951 | Georgia | MILLER |  | 2 | 0001361 | This project is a bridge replacement project in Miller County. The construction proposes to construct a new 160' x 44' concrete bridge on SR 91 over Dry Creek at the existing bridge site. The roadway | Bridge Replacement | 10/23/2009 | 11/05/2009 | 11/30/2010 | 1956969.84 | 0.32
1952 | Georgia | TATTNALL |  | 12 | 0001364 | This project is a bridge replacement on S.R. 56/Nail Bridge @ the Ohoopee River, 2 miles west of Reidsville in Tattnall County. The project length is 0.41 miles. | Bridge Replacement | 07/28/2009 | 08/31/2009 | 09/30/2010 | 2831014.42 | 0.41
1953 | Georgia | CLAY |  | 2 | 0001369 | This project will replace the structurally deficient bridge in Clay County on County Road 76 over Drag Nasty Creek with a new 180' x 28' reinforced concrete bridge. The existing approaches consist of | Bridge Replacement | 07/06/2009 | 07/31/2009 | 02/28/2010 | 1155383.5 | 0.32
1954 | Georgia | GLYNN | BRUNSWICK | 1 | 0001558 | This project is the construction of safety turn lanes on SR 520 in Brantley and Glynn Counties. The project begins just west of the Brantley/Glynn County Line at its intersection with County Road 580 | Safety/Traffic Management | 11/23/2009 | 04/23/2010 | 12/31/2010 | 4775607.92 | 11.41
1955 | Georgia | DOUGHERTY | ALBANY | 2 | 0001562 | This project is a safety improvement project in Dougherty County. This project consists of median opening improvements on SR 300/US 19 from the Mitchell County line to the Worth County line. At 25 l | Safety/Traffic Management | 02/03/2010 | 05/13/2010 | 09/30/2011 | 7998375.83 | 18.23
1956 | Georgia | BARTOW | ATLANTA | 11 | 0001574 | "This project is a safety improvement located on SR 3/US 41 in Bartow County. The project begins approximately at the Cobb/Bartow County line and extends north to the SR 293 Connector in Bartow Count | Safety/Traffic Management | 08/18/2009 | 09/16/2009 | 05/31/2011 | 11263039.7 | 15.15
1957 | Georgia | FLOYD | ROME | 11 | 0001575 | This project is a safety improvement that will construct turn lanes on SR 53 in Floyd County. The project will construct left and right turn lanes at fifteen intersections and four median crossovers | Safety/Traffic Management | 11/30/2009 | 12/01/2009 | 09/30/2011 | 7015514.31 | 9.93
1958 | Georgia | RICHMOND | AUGUSTA (SC) | 10 | 0001794 | This project is a road widening in Richmond County. The project consists of the widening and reconstruction of Alexander Drive from Washington Road (SR 28) to Riverwatch Parkway (SR 104) in the City | Pavement Widening | 01/12/2010 | 03/12/2010 | 12/31/2012 | 8115912.6 | 0.87
1959 | Georgia | UNION |  | 9 | 0001918 | This project is a safety intersection improvement in Union County. SR 11/US 129 in Union County is a rural arterial route that currently consists of one southbound lane and one northbound lane. This | Safety/Traffic Management | 03/23/2010 | 06/03/2010 | 09/30/2011 | 1932273.38 | 0.6
1960 | Georgia | DE KALB | ATLANTA | 4 | 0002406 | This is a sidewalk construction project in Dekalb County. This project includes construction of sidewalks on both sides of SR 12/US 278/Covington Highway from SR 154/Memorial Drive to County Road 518 | Transportation Enhancements | 07/27/2009 | 08/25/2009 | 08/31/2010 | 870414.3 | 1.58
1961 | Georgia | HENRY | ATLANTA | 13, 3 | 0002638 | This project is a roadway widening project in Henry County. The project is located on Eagle's Landing Parkway, 0.4 miles east of the I-75 interchange in Henry County. This project will continue the | Pavement Widening | 08/31/2009 | 09/29/2009 | 02/27/2012 | 23370448.45 | 2.6
1962 | Georgia | CANDLER |  | 12 | 0002734 | This is a bridge replacement project in Candler County. The project is a bridge replacement on County Road 203/Glisson Road at Wolfe Creek. The existing bridge was constructed in 1955 and is structu | Bridge Replacement | 08/26/2009 | 11/18/2009 | 09/30/2011 | 1207275.12 | 0.49
1963 | Georgia | CANDLER |  | 12 | 0002841 | This project is a bridge replacement in Candler County. The project will replace the bridge on County Road 223/Portal Highway at Little Stocking Head Creek, 5 miles north of Metter. The existing bri | Bridge Replacement | 07/28/2009 | 09/21/2009 | 12/31/2010 | 968761.6 | 0.35
1964 | Georgia | CANDLER |  | 12 | 0002842 | This project will replace two bridges in Bulloch and Candler counties. The project will replace the bridge on County Road 223/Portal Highway at Big Branch and the bridge on County Road 223/Portal Hig | Bridge Replacement | 07/28/2009 | 09/21/2009 | 12/31/2010 | 2288929.57 | 0.78
1965 | Georgia | CARROLL |  | 3 | 0003083 | This project is a bridge replacement project on County Road 837 in Carroll County. This project replaces the existing structurally deficient bridge over Big Indian Creek with a 320 ft. x 30 ft. conc | Bridge Replacement | 03/02/2010 | 03/29/2010 | 04/30/2011 | 1847683.25 | 0.39
1966 | Georgia | FULTON | ATLANTA | 6 | 0003769 | This project is an intersection improvement in Fulton County. The project will reconstruct the intersection on County Road 85/Kimball Bridge Road at County Road 103/Waters Road. The construction wil | Pavement Improvement | 12/01/2009 |  | 10/31/2010 | 849092.42 | 0.2
1967 | Georgia | FULTON | ATLANTA | 5 | 0004393 | This is a transportation enhancement project in Atlanta, Fulton County. This project proposes to improve accessibility, mobility and safety by connecting to a bike and pedestrian system that is plann | Transportation Enhancements | 06/18/2010 |  | 07/01/2011 | 1926137.3 | 0.69
1968 | Georgia | GWINNETT | ATLANTA | 7 | 0004456 | This is a new roadway construction project in Gwinnett County. This proposed project will connect to the existing intersection of McGinnis Ferry Road and Satellite Boulevard, with only minor improvem | New Construction | 09/03/2009 | 09/11/2009 | 09/30/2011 | 20412160.25 | 2.67
1969 | Georgia | CLAYTON | ATLANTA | 13 | 0004633 | This is a transportation enhancement project in Jonesboro in Clayton County. This project includes enhancements to pedestrian safety and improved near term traffic flow. The project will also addres | Transportation Enhancements | 04/09/2010 | 03/23/2010 | 06/30/2011 | 3329993 | 0.87
1970 | Georgia | CLINCH |  | 1 | 0006534 | This project is a transportation enhancement in Clinch County. The historic Homerville Railroad Depot, also known as Station 11, will be restored to its original architectural style to the extent pos | Transportation Enhancements | 10/08/2009 | 11/09/2009 | 04/10/2015 | 490753 | 0
1971 | Georgia | WASHINGTON |  | 12 | 0006562 | This project is a transportation enhancement in Washington County and the City of Sandersville. The project will provide new 5-ft sidewalks along Sun Hill Road, providing pedestrian access to Kaolin | Transportation Enhancements | 06/15/2010 |  | 12/31/2011 | 433724 | 1.57
1972 | Georgia | MUSCOGEE | COLUMBUS (AL) | 2 | 0006597 | This project is a transportation enhancement in Columbus, Muscogee County. This project consists of streetscape improvements on Veterans Pkwy SR 1/US 27 beginning at 8th Street and extending northerl | Transportation Enhancements | 11/12/2009 | 01/25/2010 | 05/15/2015 | 1250000 | 0.65
1973 | Georgia | PIKE |  | 3 | 0006600 | "This project constructs a walking trail in Molena, in Pike County. Construction includes the aesthetic revitalization of a portion of Georgia Highway 109 east of the Georgia Highway 18 intersection. | Transportation Enhancements | 09/29/2009 | 10/21/2009 | 05/15/2011 | 97307 | 0.1
1974 | Georgia | HENRY | ATLANTA | 13 | 0006647 | This project is an enhancement project in Henry County. This project will construct the Reeves Creek Trail and Greenway, a bicycle and pedestrian trail along the Reeves Creek in the City of Stockbrid | Transportation Enhancements | 04/30/2010 |  | 12/31/2011 | 1100000 | 0
1975 | Georgia | FULTON | ATLANTA | 5 | 0006683 | This project is a safety and operational improvement project in Fulton County and the City of Atlanta. This project consists of corridor and intersection improvements on SR 141/Peachtree Road from th | Pavement Improvement | 02/04/2010 | 03/15/2010 | 06/30/2012 | 10052474.59 | 1.33
1976 | Georgia | GWINNETT | ATLANTA | 4, 7 | 0006825 | The proposed project along Buford Highway in Gwinnett County will upgrade signal equipment and install fiber optic interconnect to allow for Intelligent Transporation Systems (ITS). Installation of IT | Safety/Traffic Management | 09/18/2009 | 01/11/2010 | 10/28/2011 | 1195798.89 | 11.01
1977 | Georgia | GWINNETT | ATLANTA | 7 | 0006829 | This project, in Gwinnett County, includes the design of fiber optic communications cable and closed-circuit television (CCTV) cameras along Sugarloaf Parkway from Peachtree Industrial Boulevard in Du | Safety/Traffic Management | 09/18/2009 | 01/25/2010 | 10/28/2011 | 1384553.27 | 12.3
1978 | Georgia | HENRY | ATLANTA | 3 | 0006840 | This project is a transportation enhancement in Henry County. The proposed project will construct sidewalks and sidewalk improvements in the Tanger Boulevard area of the city of Locust Grove. | Transportation Enhancements | 05/07/2010 |  | 03/15/2012 | 938000 | 0
1979 | Georgia | COBB | ATLANTA | 11 | 0006869 | This project is new roadway construction in Cobb County. The project consists of the construction of Big Shanty Road Connector (SR 401) from Barrett Lakes Boulevard to George Busbee Parkway for a tot | New Construction | 01/05/2010 | 02/19/2010 | 04/30/2012 | 9087183.44 | 1.88
1980 | Georgia | COWETA | ATLANTA | 3 | 0006956 | This project is the replacement of a structurally deficient bridge in Coweta County. This project will replace the bridge on County Road 41 over the CSX Railroad, 2.0 miles northeast of Newnan, Georg | Bridge Replacement | 01/05/2010 | 01/15/2010 | 10/31/2010 | 1345078.64 | 0.4
1981 | Georgia | COWETA | ATLANTA | 3 | 0006957 | This project is the replacement of a structurally deficient bridge in Coweta County. This project will replace the bridge on County Road 130 over White Oak Creek, 3.5 miles northeast of Moreland, Geo | Bridge Replacement | 01/05/2010 | 02/15/2010 | 11/30/2010 | 1055465.1 | 0.25
1982 | Georgia | DE KALB | ATLANTA | 4, 5 | 0007130 | This project is a transportation enhancement in Dekalb County. The project will construct streetscape designs and intersection improvements along SR 154/Memorial Drive from SR 155/Candler Road to Mou | Transportation Enhancements | 07/23/2009 | 09/28/2009 | 05/31/2012 | 4539202.25 | 3.4
1983 | Georgia | DE KALB | ATLANTA | 4 | 0007131 | This project is the construction of intersection and pedestrian safety improvements in DeKalb County. This project is on SR 10/Memorial Drive and begins at Woodcroft Road and ends at Goldsmith Road. | Transportation Enhancements | 12/22/2009 | 03/08/2010 | 12/31/2011 | 2716982.02 | 3.47
1984 | Georgia | BALDWIN |  | 12 | 0008065 | This project is a transportation enhancement in Baldwin County. Phase II of the Milledgeville downtown streetscape proposes to construct new sidewalks, ADA compliant access, new and reconstructed str | Transportation Enhancements | 05/17/2010 |  | 11/01/2011 | 750000 | 0.3
1985 | Georgia | JACKSON |  | 10 | 0008066 | This project is a transportation enhancement in Banks and Jackson Counties and in the City of Maysville. This project is the second phase of the Maysville Downtown Streetscape. Project construction | Transportation Enhancements | 04/15/2010 |  | 12/31/2011 | 355914 | 0.7
1986 | Georgia | BURKE |  | 12 | 0008080 | This project is a transportation enhancement in Burke County. The project will provide sidewalks and landscaping along State Route 56 from the intersection of Myrick Street along State Route 56 to Ba | Transportation Enhancements | 04/30/2010 |  | 12/31/2011 | 725000 | 0.2
1987 | Georgia | DECATUR |  | 2 | 0008113 | This project provides streetscape improvements in downtown Bainbridge in Decatur County. The Bainbridge Central Business District is well defined on the north by Calhoun Street and on the south by Sh | Transportation Enhancements | 09/29/2009 | 11/09/2009 | 07/01/2011 | 591411.23 | 0.36
1988 | Georgia | DE KALB | ATLANTA | 5 | 0008115 | This project is a transportation enhancement in Dekalb County. Deepdene Park will be rehabilitated. The Mead at the east end and the West Lawn at the west end of Deepdene Park will have the open, pas | Transportation Enhancements | 01/05/2010 |  | 05/07/2011 | 1137182.6 | 0.4
1989 | Georgia | DE KALB | ATLANTA | 3, 4 | 0008119 | This project is a transportation enhancement in DeKalb and Rockdale Counties. This project involves clearing, grading, and installing a 10' to 12' wide concrete trail from MLK High School on Snapfinge | Transportation Enhancements | 01/25/2010 |  | 05/07/2011 | 664629 | 1.6
1990 | Georgia | FAYETTE | ATLANTA | 3 | 0008126 | The project will provide pedestrian improvements within the City of Fayetteville in Fayette County along Lee Street. This will include construction of a 5 foot sidewalk with a 2 foot grass buffer and | Transportation Enhancements | 09/23/2009 | 11/02/2009 | 03/26/2015 | 337500 | 0.59
1991 | Georgia | FULTON | ATLANTA | 5 | 0008131 | This is an enhancement project in Fulton County, city of Atlanta. Streetscape improvements within the Farlie Poplar historic district along: 1) Walton Street: between Centennial Olympic Park Drive a | Transportation Enhancements | 05/27/2010 |  | 12/01/2011 | 723515.63 | 0.21
1992 | Georgia | HARALSON |  | 11 | 0008157 | This project is a transportation enhancement in the City of Buchanan in Haralson County. The project will construct sidewalks, curb and gutter, seatwalls, lighting, street furniture and landscaping a | Transportation Enhancements | 10/09/2009 | 02/16/2010 | 04/11/2015 | 438000 | 0.2
1993 | Georgia | HENRY | ATLANTA | 3 | 0008159 | This project is a transportation enhancement in Henry County. The proposed project will provide a trailhead facility. The project will be constructed on two city owned parcels adjacent to Cleveland | Transportation Enhancements | 10/01/2009 | 03/15/2010 | 04/03/2015 | 241204.1 | 0.91
1994 | Georgia | MUSCOGEE | COLUMBUS (AL) | 2 | 0008185 | This is a transportation enhancement project in Muscogee County. This project will provide streetscape and beautification along SR 1/Veteran's Parkway in Columbus from 10th Street to SR 22 Spur. The | Transportation Enhancements | 11/12/2009 | 01/25/2010 | 05/15/2015 | 1071732.27 | 0.4
1995 | Georgia | PAULDING | ATLANTA | 11 | 0008188 | The project will provide a trailhead facility adjacent to downtown Dallas in Paulding County, on an approximate 1 acre site at the intersection of South Main Street and Hardee Street. The trailhead w | Transportation Enhancements | 09/17/2009 | 12/01/2009 | 06/01/2011 | 625000 | 0.06
1996 | Georgia | SCHLEY |  | 2 | 0008198 | This project is a transportation enhancement in Schley County. The project will construct sidewalks on three locations in Ellaville: 1) east side of Hill Street between West Buena Vista Street and | Transportation Enhancements | 10/08/2009 | 01/18/2010 | 05/14/2011 | 66997.38 | 0.64
1997 | Georgia | SPALDING | ATLANTA | 3 | 0008235 | This project will provide traffic signal upgrades in Spalding County. This project will upgrade traffic signal in the City of Griffin at the 12 locations. The signals on Poplar St. between 6th and | Safety/Traffic Management | 02/22/2010 | 04/08/2010 | 03/28/2012 | 1236651.85 | 1.3
1998 | Georgia | SPALDING | ATLANTA | 3 | 0008236 | This project will provide traffic signal upgrades in Spalding County. This project will upgrade traffic signals at the following intersections: 1) College St. @ 6th St. 2) Hill St. @ Chappell S | Safety/Traffic Management | 02/22/2010 | 04/27/2010 | 03/28/2012 | 326933.55 | 0
1999 | Georgia | COWETA | ATLANTA | 3 | 0008544 | This is an interchange lighting project in Coweta County. This project shall install 38 High Mast Lighting Towers at two existing interchanges along Interstate 85 in Coweta County. Currently, no road | New Construction | 05/10/2010 |  | 12/31/2010 | 1109521.11 | 0.8
2000 | Georgia | MITCHELL |  | 2 | 0009112 | This is a transportation enhancement project in Mitchell County. This project will improve the streetscape along East Broad Street/ GA S. R. 97/112 in downtown Camilla. Construction includes the dem | Transportation Enhancements | 01/28/2010 | 04/12/2010 | 10/07/2011 | 500000 | 0.1
2001 | Georgia | WALKER | CHATTANOOGA (TN) | 9 | 0009317 | This project is a roadway maintenance repaving project in Walker County. This project is the milling and resurfacing of County Road 704/McFarland Avenue from Rossville City limits to SR 1/US 27 for a | Pavement Improvement | 03/02/2010 | 03/03/2010 | 06/30/2010 | 463539.06 | 1.64
2002 | Georgia | WALKER | CHATTANOOGA (TN) | 9 | 0009328 | This project is a transportation enhancement project in Walker County in the City of Chickamauga. This project will construct sidewalks at several locations in the City of Chickamauga. Sidewalks will | Transportation Enhancements | 06/23/2010 |  | 05/15/2011 | 1102000 | 3.31
2003 | Georgia | GWINNETT | ATLANTA | 7 | 0009344 | This project is an intersection improvement in Gwinnett County. The purpose of this project is to improve the operating characteristics of the intersection of SR 8 (Lawrenceville Highway) and Pleasan | Safety/Traffic Management | 08/28/2009 | 09/16/2009 | 06/30/2011 | 9328483.55 | 0.21
2004 | Georgia | GWINNETT | ATLANTA | 4, 7 | 0009345 | The project is an intersection improvement in Gwinnett County. This project will improve the operation characteristics of the intersection of SR 8 (Lawrenceville Highway) and Beaver Ruin Road/Arcado | Safety/Traffic Management | 08/05/2009 | 11/02/2009 | 06/30/2011 | 6285053.8 | 1.1
2005 | Georgia | CATOOSA | CHATTANOOGA (TN) | 9 | 0009346 | This project is a safety intersection improvement project in Catoosa County. This project consists of reconstructing the existing left turns lanes on SR 2 from a Type A median crossover to a Type B. | Safety/Traffic Management | 07/27/2009 | 08/26/2009 | 09/30/2010 | 1531013.32 | 0.22
2006 | Georgia | FULTON | ATLANTA | 5 | 0009347 | This is a transportation enhancement project in Atlanta, Fulton County. This project will construct sidewalk improvements, including the replacement and upgrading of existing sidewalks along portions | Transportation Enhancements | 07/09/2010 |  | 12/31/2011 | 4001548.18 | 0.8
2007 | Georgia | FULTON | ATLANTA | 5 | 0009348 | This project is a safety improvement in Fulton County. The proposed project will provide traffic signals at five key intersections in Midtown Atlanta. This project will provide a safer pedestrian an | Pavement Improvement | 01/12/2010 |  | 12/31/2010 | 1344853 | 0
2008 | Georgia | COBB | ATLANTA | 6 | 0009349 | This project will modify the interchange of SR 120/Roswell Road and SR 120 Alternate (formerly SR 120 Loop) in Cobb County. This project is located in the City of Marietta. The proposed project will | Pavement Improvement | 08/18/2009 | 09/01/2009 | 06/30/2011 | 7573857.03 | 0.75
2009 | Georgia | COBB | ATLANTA | 11 | 0009350 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 809/Corner Road. The construction will con | Pavement Improvement | 08/19/2009 | 09/24/2009 | 04/30/2011 | 1242339.86 | 1.6
2010 | Georgia | GWINNETT | ATLANTA | 7 | 0009351 | This project is a road widening construction project in Gwinnett County. The project will widen and reconstruct the existing two lanes of SR 20 to accommodate 4 lanes beginning approximately 800 feet | Pavement Improvement | 09/08/2009 | 10/28/2009 | 12/31/2011 | 11545667.54 | 2.65
2011 | Georgia | COBB | ATLANTA | 11 | 0009352 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 784/Hadaway Road. The construction will co | Pavement Improvement | 08/19/2009 | 09/24/2009 | 04/30/2011 | 956562.38 | 0.4
2012 | Georgia | COBB | ATLANTA | 11 | 0009353 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 55/Mars Hill Church Road. The construction | Pavement Improvement | 08/19/2009 | 09/24/2009 | 04/30/2011 | 884562.14 | 0.4
2013 | Georgia | FAYETTE | ATLANTA | 3 | 0009355 | This project will upgrade existing traffic signal equipment and pedestrian facilities for S.R. 314 and S.R. 54 at various intersections in Fayette County. The intersections are as follows: 1) SR 3 | Safety/Traffic Management | 07/20/2009 | 10/26/2009 | 02/28/2010 | 175877.47 | 1.2
2014 | Georgia | FULTON | ATLANTA | 6 | 0009357 | This project is a safety project in Fulton County in the City of Roswell. This project will upgrade existing traffic signal equipment and pedestrian facilities at various locations on Pine Grove Road | Safety/Traffic Management | 02/05/2010 | 06/01/2010 | 10/31/2010 | 250129.91 | 1.6
2015 | Georgia | FULTON | ATLANTA | 6 | 0009358 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations on SR 961/Old Alabama Road in the City of Roswell, Fulton County. The intersections are | Safety/Traffic Management | 07/17/2009 | 10/12/2009 | 07/31/2010 | 766858.65 | 3
2016 | Georgia | DE KALB | ATLANTA | 4, 6 | 0009359 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations in DeKalb County on Chamblee Tucker Road, Clairmont Road, & New Peachtree Road. The int | Safety/Traffic Management | 07/20/2009 | 09/22/2009 | 05/31/2010 | 1161968.65 | 0
2017 | Georgia | DE KALB | ATLANTA | 4 | 0009360 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations on Briarcliff Road & Shallowford Road in Dekalb County. The intersections are as follow | Safety/Traffic Management | 07/20/2009 | 11/04/2009 | 07/31/2010 | 892693.87 | 1.8
2018 | Georgia | DE KALB | ATLANTA | 4, 6 | 0009361 | This project will upgrade the existing traffic signal equipment and pedestrian facilities at various locations on Chamblee Dunwoody Road and NorthShallowford Road in DeKalb County. The intersections | Safety/Traffic Management | 07/20/2009 | 02/01/2010 | 12/31/2010 | 1855080.7 | 0
2019 | Georgia | DE KALB | ATLANTA | 4 | 0009362 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at 21 locations on LaVista Rd, Northlake Pkwy, & Henderson Mill Rd in Dekalb County at the following intersec | Safety/Traffic Management | 07/20/2009 | 05/11/2010 | 12/31/2010 | 1984055.69 | 0
2020 | Georgia | COBB | ATLANTA | 13 | 0009363 | This project consists of the upgrade of the traffic signals at 4 locations on SR 139/Mableton Parkway and 1 location on County Road 2570/Old Alabama Road in Cobb County. Pedestrian improvements will | Safety/Traffic Management | 07/20/2009 | 11/02/2009 | 07/31/2010 | 453645.6 | 1.9
2021 | Georgia | COLUMBIA | AUGUSTA (SC) | 10 | 0009365 | This project is the replacement of the existing bridge over Euchee Creek on SR 223, 2.2 miles northwest of Grovetown, in Columbia County. The project will widen and correct the structural deficiencie | Bridge Replacement | 11/02/2009 | 02/24/2010 | 12/31/2010 | 2397388.95 | 0.22
2022 | Georgia | ATKINSON |  | 1 | 0009366 | This project is located approximately four miles northwest of Pearson, Georgia in Atkinson County. This project will construct a bridge replacement over Pudding Creek along County Road 42/Antioch Chur | Bridge Replacement | 07/28/2009 | 08/10/2009 | 06/30/2010 | 1528744.92 | 0.43
2023 | Georgia | FULTON | ATLANTA | 6 | 0009367 | This project is a bridge replacement on CR 85/Kimball Bridge Road two miles southeast of Alpharetta in Fulton County. The project is 0.554 miles long, consisting of removal of the existing Big Creek B | Bridge Replacement | 12/04/2009 | 01/21/2010 | 09/30/2011 | 4232229.95 | 0.2
2024 | Georgia | CHATHAM | SAVANNAH | 1 | 0009380 | This project is a safety improvement in Chatham County in downtown Savannah. This project consists of upgrading pedestrian countdown signal heads at multiple intersections. | Safety/Traffic Management | 03/19/2010 | 06/28/2010 | 05/31/2011 | 450217.07 | 0
2025 | Georgia | CHATHAM | SAVANNAH | 1 | 0009381 | This project is a safety improvement in Chatham County in downtown Savannah. The project will install audible push buttons at 50 signalized intersections. The push buttons emit an audible signal to | Safety/Traffic Management | 03/19/2010 | 06/28/2010 | 05/31/2011 | 274621.76 | 0
2026 | Georgia | CHATHAM | SAVANNAH | 1 | 0009382 | This project is a safety improvement in Chatham County in downtown Savannah. This project consists of replacing existing signal heads at eleven signalized intersections along 27th Street, from Montgo | Safety/Traffic Management | 03/19/2010 | 06/28/2010 | 05/31/2011 | 70548.86 | 1.2
2027 | Georgia | CHATHAM | SAVANNAH | 1 | 0009385 | This project is a safety improvement in Chatham County in the City of Savannah. This project consists of installing an emergency vehicle GPS pre-emption system assembly at existing signalized interse | Safety/Traffic Management | 03/19/2010 | 06/28/2010 | 05/31/2011 | 1403176.23 | 0
2028 | Georgia | COWETA | ATLANTA | 3 | 0009419 | This project is an intersection improvement in Coweta County. The project will realign the intersection of SR 16/Wells Street at County Road 157/Broad Street & Luther Bailey Road. The project will c | Safety/Traffic Management | 10/06/2009 | 10/15/2009 | 09/30/2010 | 1017617.62 | 0.38
2029 | Georgia | COFFEE |  | 1 | 0009421 | This project will replace the structurally deficient bridge on SR 135/US 221 over Tiger Creek in Coffee County. The existing 108 X 24' bridge was constructed in 1947 and will be replaced with a new 1 | Bridge Replacement | 09/24/2009 | 10/29/2009 | 08/31/2010 | 1332580.3 | 0.3
2030 | Georgia | PIERCE |  | 1 | 0009422 | This is an intersection improvement project in Pierce County. This project will realign the intersection of SR 203/Strickland Street and County Road 309/Old Alma Road and with County Road 236 to impr | Pavement Improvement | 09/28/2009 | 01/11/2010 | 06/30/2010 | 1067196.42 | 0.36
2031 | Georgia | BARROW | ATLANTA | 7 | 0009423 | This project is a maintenance resurfacing project in Barrow County to repave local roadways. The Barrow resurfacing program includes four roadways: 1) Carl Bethlehem Road from SR 81 to SR 11; 2) Smi | Pavement Improvement | 01/21/2010 | 02/01/2010 | 07/31/2010 | 1114345.5 | 8.59
2032 | Georgia | BARTOW | ATLANTA | 11 | 0009424 | This project is a maintenance resurfacing project in Bartow County to repave local roadways. The Bartow resurfacing program includes two roadways: 1) Red Top Mountain Road from 0.24 miles east of I- | Pavement Improvement | 01/19/2010 | 03/16/2010 | 06/30/2010 | 198099.28 | 1.86
2033 | Georgia | CHEROKEE | ATLANTA | 6 | 0009425 | This project is a maintenance resurfacing project in Cherokee County to repave local roadways. The Cherokee resurfacing program includes a single roadway 1) East Cherokee Drive from 0.16 miles north | Pavement Improvement | 02/02/2010 | 04/27/2010 | 06/30/2010 | 247148 | 1.54
2034 | Georgia | CLAYTON | ATLANTA | 13, 5 | 0009426 | This project is a maintenance resurfacing project in Clayton County to repave local roadways. The Clayton resurfacing program includes three roadways: 1) Flint River Road from Glenwoods Drive to Kend | Pavement Improvement | 02/24/2010 | 03/29/2010 | 06/30/2010 | 1006267.26 | 3.88
2035 | Georgia | COWETA | ATLANTA | 3 | 0009427 | This project is a maintenance resurfacing project in Coweta County to repave local roadways. The Coweta resurfacing program includes three roadways: 1) Poplar Road from I-85 to Yeager Road and from | Pavement Improvement | 02/04/2010 | 05/25/2010 | 07/31/2010 | 895998.01 | 8.62
2036 | Georgia | DOUGLAS | ATLANTA | 13, 3 | 0009428 | This project is a maintenance resurfacing project in Douglas County to repave local roadways. The Douglas resurfacing program includes three roadways: 1) Liberty Road from North Helton Road to Libert | Pavement Improvement | 02/24/2010 | 04/12/2010 | 06/30/2010 | 862108.92 | 4.46
2037 | Georgia | FAYETTE | ATLANTA | 3 | 0009429 | This project is a maintenance resurfacing project in Fayette County to repave local roadways. The Fayette resurfacing program includes five roadways: 1) SR 85 Connector from SR 85 to Woods Road; 2) H | Pavement Improvement | 02/05/2010 | 05/17/2010 | 07/31/2010 | 856264.2 | 7.46
2038 | Georgia | FORSYTH | ATLANTA | 7, 9 | 0009430 | This project is a maintenance resurfacing project in Forsyth County to repave local roadways. The Forsyth resurfacing program includes seven roadways: 1) Old Atlanta Road from James Burgess Road to | Pavement Improvement | 01/19/2010 | 03/31/2010 | 07/31/2010 | 1694628.62 | 9.37
2039 | Georgia | HENRY | ATLANTA | 13, 3 | 0009431 | This project is a maintenance resurfacing project in Henry County to repave local roadways. The Henry resurfacing program includes two roadways: 1) Thurman Road from East Atlanta Road to Rex Road; | Pavement Improvement | 02/03/2010 | 04/21/2010 | 07/31/2010 | 792128.21 | 3.2
2040 | Georgia | ROCKDALE | ATLANTA | 4 | 0009432 | This project is a maintenance resurfacing project in Rockdale County to repave local roadways. The Rockdale resurfacing program includes four roadways: 1) Sigman Road from Gees Mill Road to Old Covi | Pavement Improvement | 02/11/2010 | 02/25/2010 | 06/30/2010 | 1402825.66 | 12.27
2041 | Georgia | WALTON | ATLANTA | 7 | 0009433 | This project is a maintenance resurfacing project in Walton County to repave local roadways. The Walton program includes four roadways: 1) Old Monroe Highway from Pannell Road to Nunnally Shoals Roa | Pavement Improvement | 02/05/2010 | 04/07/2010 | 07/31/2010 | 1853284.14 | 15.38
2042 | Georgia | FAYETTE | ATLANTA | 3 | 0009452 | This project is the construction of the widening and improvement of SR 74 in Fayette County, from SR 85 to Cooper Circle Road (approximately 1.85 miles south of Crosstown Drive) for a total length of | Pavement Widening | 10/26/2009 | 11/17/2009 | 12/31/2011 | 15925376.13 | 3
2043 | Georgia | TROUP |  | 3 | 0009453 | This project will construct phase two of the South LaGrange Loop, a new roadway in Troup County. The roadway will be a bypass around the southern portion of the City of LaGrange. The limits extend f | New Construction | 11/06/2009 | 11/23/2009 | 12/31/2011 | 20310819.69 | 4.15
2044 | Georgia | CLARKE | ATHENS | 10 | 0009454 | This project is a roadway maintenance repaving project in Clarke County. This project is the milling and resurfacing of County Road 470/MAIN ST from County Road 134/ATHENS ROAD to OGLETHORPE COUNTY L | Pavement Improvement | 02/05/2010 | 04/29/2010 | 07/31/2010 | 252814.38 | 1.5
2045 | Georgia | CLARKE | ATHENS | 10 | 0009455 | This project is a roadway maintenance repaving project in Clarke County. This project is the milling and resurfacing of County Road 140/OLD ELBERTON from County Road 477/VOYLES ROAD to MADISON COUNTY | Pavement Improvement | 02/05/2010 | 04/29/2010 | 07/31/2010 | 244377.32 | 1.87
2046 | Georgia | CLARKE | ATHENS | 10 | 0009456 | This project is a roadway maintenance repaving project in Clarke County. This project is the milling and resurfacing of County Road 120/SMOKEY ROAD from NOWHERE ROAD to HELICAN SPRINGS ROAD for a tot | Pavement Improvement | 02/05/2010 | 04/29/2010 | 07/31/2010 | 316558.9 | 2.45
2047 | Georgia | ELBERT |  | 10 | 0009457 | This project is a roadway maintenance repaving project in Elbert County. This project is the milling and resurfacing of County Road 307/THIRTEEN FORKS ROAD from SR 77 to HART COUNTY LINE for a total | Pavement Improvement | 01/19/2010 | 04/06/2010 | 07/31/2010 | 417073.4 | 4.13
2048 | Georgia | FRANKLIN |  | 10 | 0009458 | This project is a roadway maintenance repaving project in Franklin County. This project is the milling and resurfacing of County Road 418/County Road 419/BOLD SPRINGS ROAD from SR 106 to SR 59; EXC S | Pavement Improvement | 02/03/2010 | 04/22/2010 | 07/31/2010 | 567285.65 | 6.84
2049 | Georgia | HABERSHAM |  | 10 | 0009459 | This project is a roadway maintenance repaving project in Habersham County. This project is the milling and resurfacing of County Road 387/DEMOREST/MT AIRY ROAD from SR 385/US 442 to SR 365 for a tot | Pavement Improvement | 01/19/2010 | 04/19/2010 | 06/30/2010 | 344243.77 | 1.25
2050 | Georgia | HALL | GAINESVILLE | 9 | 0009460 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 367/West Ridge Road from County Road 751/Athens Street to SR 11 for a | Pavement Improvement | 03/02/2010 | 04/16/2010 | 06/30/2010 | 104556.73 | 0.42
2051 | Georgia | HALL | GAINESVILLE | 9 | 0009461 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 367/County Road 1098/West Ridge Road from SR 11 to SR 53 Connector fo | Pavement Improvement | 03/02/2010 | 04/16/2010 | 06/30/2010 | 170353.92 | 1.04
2052 | Georgia | HALL | GAINESVILLE | 9 | 0009462 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 621/Wade Orr Road from SR 13 to County Road 685/Hog Mountain Road for | Pavement Improvement | 03/02/2010 | 04/16/2010 | 06/30/2010 | 202789.52 | 1.1
2053 | Georgia | HALL | GAINESVILLE | 9 | 0009463 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 451/Memorial Park Drive from SR 369 to SR 13 for a total project leng | Pavement Improvement | 03/02/2010 | 04/16/2010 | 06/30/2010 | 280211.17 | 1.6
2054 | Georgia | HART |  | 10 | 0009464 | This project is a roadway maintenance repaving project in Hart County. This project is the milling and resurfacing of County Road 505/LIBERTY CHURCH ROAD from SR 172 to ELBERT COUNTY LINE for a total | Pavement Improvement | 01/19/2010 | 04/06/2010 | 07/31/2010 | 224830.73 | 2.38
2055 | Georgia | JACKSON |  | 10 | 0009465 | This project is a roadway maintenance repaving project in Jackson County. This project is the milling and resurfacing of County Road 426/WAYNE POULTRY from OLD GAINESVILLE HWY to VALENTINE PKY for a | Pavement Improvement | 02/05/2010 | 03/30/2010 | 06/30/2010 | 599728.4 | 2.8
2056 | Georgia | LUMPKIN |  | 9 | 0009466 | This project is a roadway maintenance repaving project in Lumpkin County. This project is the milling and resurfacing of County Road 134/DAMASCUS CHURCH ROAD from SR 9/US 19 to WHITE COUNTY LINE for | Pavement Improvement | 01/21/2010 | 04/14/2010 | 07/31/2010 | 320381.4 | 3.24
2057 | Georgia | MADISON |  | 10 | 0009467 | This project is a roadway maintenance repaving project in Madison County. This project is the milling and resurfacing of County Road 394/LEXINGTON ROAD from SR 72 to OGLETHORPE COUNTY LINE for a tota | Pavement Improvement | 01/19/2010 | 04/01/2010 | 06/30/2010 | 168458.15 | 1.63
2058 | Georgia | RABUN |  | 10 | 0009468 | This project is a roadway maintenance repaving project in Rabun County. This project is the milling and resurfacing of OLD 441 from south of County Road 218 to City Street 514 and from City Street 50 | Pavement Improvement | 02/01/2010 | 03/29/2010 | 07/31/2010 | 1200300 | 10
2059 | Georgia | STEPHENS |  | 10 | 0009469 | This project is a roadway maintenance repaving project in Stephens County. This project is the milling and resurfacing of County Road 538/BROOKHAVEN CIR from County Road 43/E SILVER SHOALS ROAD to SR | Pavement Improvement | 02/01/2010 | 05/19/2010 | 07/31/2010 | 818568.25 | 6.34
2060 | Georgia | TOWNS |  | 10 | 0009470 | This project is a roadway maintenance repaving project in Towns County. This project is the milling and resurfacing of County Road 172/GUM LOG ROAD from west of WINCHESTER CREEK ROAD to BARNARD ROAD | Pavement Improvement | 01/19/2010 | 04/02/2010 | 07/31/2010 | 137441.08 | 1.4
2061 | Georgia | UNION |  | 9 | 0009471 | This project is a roadway maintenance repaving project in Union County. This project is the milling and resurfacing of County Road 341/OLD BLUE RIDGE HWY from County Road 117 to LITTLE YOUNGCANE CREE | Pavement Improvement | 01/19/2010 | 04/02/2010 | 07/31/2010 | 291527.23 | 2.57
2062 | Georgia | WHITE |  | 9 | 0009472 | This project is a roadway maintenance repaving project in White County. This project is the milling and resurfacing of County Road 68/HULSEY ROAD from SR 75 to SR 11/US 129 for a total project length | Pavement Improvement | 01/21/2010 | 04/14/2010 | 07/31/2010 | 160571.73 | 1.3
2063 | Georgia | BALDWIN |  | 12 | 0009473 | This project is a roadway maintenance repaving project in Baldwin County. This project is the milling and resurfacing of City Street 701/BLANDY ROAD from SR 49 to SR 22 for a total project length of | Pavement Improvement | 01/29/2010 | 03/13/2010 | 06/30/2010 | 250760.21 | 1.96
2064 | Georgia | BALDWIN |  | 12 | 0009474 | This project is a roadway maintenance repaving project in Baldwin County. This project is the milling and resurfacing of County Road 69/BROWNS CROSSING ROAD from SR 49 to SR 22 for a total project le | Pavement Improvement | 01/21/2010 | 03/01/2010 | 06/30/2010 | 375845.04 | 3.64
2065 | Georgia | HANCOCK |  | 12 | 0009475 | This project is a roadway maintenance repaving project in Hancock County. This project is the milling and resurfacing of County Road 180/POWELLTON AVE from HAMILTON ST to SPARTA CITY LIMITS for a tot | Pavement Improvement | 02/03/2010 |  | 06/30/2010 | 79918 | 0.57
2066 | Georgia | JEFFERSON |  | 12 | 0009476 | This project is a roadway maintenance repaving project in Jefferson County. This project is the milling and resurfacing of City Street 561/MIDVILLE ROAD from SR 4 to SR 24 for a total project length | Pavement Improvement | 02/03/2010 | 03/12/2010 | 06/30/2010 | 122923 | 0.8
2067 | Georgia | JEFFERSON |  | 12 | 0009477 | This project is a roadway maintenance repaving project in Jefferson County. This project is the milling and resurfacing of County Road 59/QUAKER ROAD from SR 17 to SR 80 for a total project length of | Pavement Improvement | 02/03/2010 | 03/12/2010 | 06/30/2010 | 182928.4 | 1.5
2068 | Georgia | JOHNSON |  | 12 | 0009478 | This project is a roadway maintenance repaving project in Johnson County. This project is the milling and resurfacing of County Road 203/BAY SPRINGS CHURCH ROAD from SR 26 to MT OLIVE CHURCH ROAD for | Pavement Improvement | 01/29/2010 | 04/19/2010 | 06/30/2010 | 282374.28 | 2.88
2069 | Georgia | LAURENS |  | 8 | 0009479 | This project is a roadway maintenance repaving project in Laurens County. This project is the milling and resurfacing of City Street 768/ROBERSON ST from SR 19/US 80 to City Street 770/KNOX ST for a | Pavement Improvement | 02/01/2010 | 06/08/2010 | 06/30/2010 | 36263.5 | 0.23
2070 | Georgia | LAURENS |  | 8 | 0009480 | This project is a roadway maintenance repaving project in Laurens County. This project is the milling and resurfacing of County Road 526/OLD MACON ROAD from EVERGREEN ROAD to WILKINSON COUNTY LINE fo | Pavement Improvement | 02/01/2010 | 06/08/2010 | 06/30/2010 | 355156.5 | 4.21
2071 | Georgia | MCDUFFIE |  | 10 | 0009481 | This project is a roadway maintenance repaving project in McDuffie County. This project is the milling and resurfacing of City Street 663/RAILROAD STREET from SR 17 to SR 223 for a total project leng | Pavement Improvement | 02/01/2010 | 04/21/2010 | 06/30/2010 | 99825.8 | 0.67
2072 | Georgia | MCDUFFIE |  | 10 | 0009482 | This project is a roadway maintenance repaving project in McDuffie County. This project is the milling and resurfacing of County Road 309/HAPPY VALLEY ROAD from SR 17 to County Road 297/SAND HILL ROA | Pavement Improvement | 02/01/2010 | 04/21/2010 | 06/30/2010 | 167945.6 | 1.16
2073 | Georgia | OGLETHORPE |  | 10 | 0009483 | This project is a roadway maintenance repaving project in Oglethorpe County. This project is the milling and resurfacing of County Road 77/WOLFSKIN ROAD from County Road 240 to CLARKE COUNTY LINE for | Pavement Improvement | 01/21/2010 | 03/30/2010 | 06/30/2010 | 107337.25 | 0.69
2074 | Georgia | RICHMOND | AUGUSTA (SC) | 12 | 0009484 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 1509/KEYSVILLE ROAD from SR 88 to BURKE COUNTY LINE for a total p | Pavement Improvement | 01/29/2010 | 03/01/2010 | 06/30/2010 | 352489.8 | 3.1
2075 | Georgia | SCREVEN |  | 12 | 0009485 | This project is a roadway maintenance repaving project in Screven County. This project is the milling and resurfacing of County Road 243/E OGEECHEE ST from SR 73 to SYLVANIA CITY LIMITS for a total p | Pavement Improvement | 01/29/2010 | 03/17/2010 | 06/30/2010 | 238589.18 | 1
2076 | Georgia | WARREN |  | 12 | 0009486 | This project is a roadway maintenance repaving project in Warren County. This project is the milling and resurfacing of County Road 174/FIVE POINTS JEWELL ROAD from SR 16 to SR 123 for a total projec | Pavement Improvement | 02/01/2010 | 04/21/2010 | 06/30/2010 | 67348.6 | 0.54
2077 | Georgia | WASHINGTON |  | 12 | 0009487 | This project is a roadway maintenance repaving project in Washington County. This project is the milling and resurfacing of County Road 446/RIDGE ROAD from SR 88 to SR 15 for a total project length o | Pavement Improvement | 02/03/2010 |  | 06/30/2010 | 210576.75 | 1.99
2078 | Georgia | WILKES |  | 10 | 0009488 | This project is a roadway maintenance repaving project in Wilkes County. This project is the milling and resurfacing of City Street 612/ANDREWS DRIVE from SR 17/US 78BU to SR 47 for a total project l | Pavement Improvement | 02/05/2010 | 05/05/2010 | 06/30/2010 | 278344.41 | 2.13
2079 | Georgia | BUTTS |  | 8 | 0009489 | This project is a roadway maintenance repaving project in Butts County. This project is the milling and resurfacing of County Road 296/BROWNLEE ROAD from SR 36 to County Road 136 at the Monroe County | Pavement Improvement | 02/05/2010 | 04/07/2010 | 07/31/2010 | 594810.55 | 6.63
2080 | Georgia | DOOLY |  | 2 | 0009490 | This project is a roadway maintenance repaving project in Dooly County. This project is the milling and resurfacing of County Road 320/ELKO ROAD from HOUSTON COUNTY LINE to SR 7 for a total project l | Pavement Improvement | 01/21/2010 | 05/11/2010 | 06/30/2010 | 123366.19 | 1.2
2081 | Georgia | JONES |  | 8 | 0009491 | This project is a roadway maintenance repaving project in Jones County. This project is the milling and resurfacing of County Road 292/BOWEN HILL ROAD from County Road 107/SMITH ROAD to SR 49 for a t | Pavement Improvement | 01/29/2010 | 02/27/2010 | 07/31/2010 | 455141.41 | 3.9
2082 | Georgia | LAMAR |  | 3 | 0009492 | This project is a roadway maintenance repaving project in Lamar County. This project is the milling and resurfacing of County Road 214/HIGH FALLS PARK from SR 36 to MONROE COUNTY LINE for a total pro | Pavement Improvement | 02/01/2010 | 03/09/2010 | 07/31/2010 | 475528.99 | 4.42
2083 | Georgia | MACON |  | 2 | 0009493 | This project is a roadway maintenance repaving project in Macon County. This project is the milling and resurfacing of County Road 282/DRAYTON ROAD from County Road 22/TWIN CHURCHS ROAD to Dooly Coun | Pavement Improvement | 02/01/2010 | 04/30/2010 | 07/31/2010 | 483690.95 | 5.05
2084 | Georgia | PIKE |  | 3 | 0009494 | This project is a roadway maintenance repaving project in Pike County. This project is the milling and resurfacing of County Road 161/KINGS ROAD from SR 109 to UPSON COUNTY LINE for a total project l | Pavement Improvement | 02/05/2010 | 06/08/2010 | 07/31/2010 | 471915.7 | 3.93
2085 | Georgia | PULASKI |  | 8 | 0009495 | This project is a roadway maintenance repaving project in Pulaski County. This project is the milling and resurfacing of County Road 198/BURNT BRIDGE from SR 26 to SR 230 for a total project length o | Pavement Improvement | 01/21/2010 | 05/12/2010 | 06/30/2010 | 381684.08 | 4.1
2086 | Georgia | TROUP |  | 3 | 0009496 | This project is a roadway maintenance repaving project in Troup County. This project is the milling and resurfacing of County Road 407/BARTLEY ROAD from SHOEMAKER ROAD to SR 1 for a total project len | Pavement Improvement | 02/03/2010 | 03/12/2010 | 07/31/2010 | 911631.44 | 8.35
2087 | Georgia | TWIGGS |  | 8 | 0009497 | This project is a roadway maintenance repaving project in Twiggs County. This project is the milling and resurfacing of County Road 193/SGODA-HUBER ROAD from SR 87 to County Road 185/RIGGINS MILL ROA | Pavement Improvement | 02/05/2010 | 02/19/2010 | 07/31/2010 | 787351.56 | 4.78
2088 | Georgia | UPSON |  | 3 | 0009498 | This project is a roadway maintenance repaving project in Upson County. This project is the milling and resurfacing of County Road 421/BARNESVILLE ROAD from SR 74 to LAMAR COUNTY LINE for a total pro | Pavement Improvement | 01/21/2010 | 02/17/2010 | 07/31/2010 | 655167.98 | 5.27
2089 | Georgia | BAKER |  | 2 | 0009499 | This project is a roadway maintenance repaving project in Baker County. This project is the milling and resurfacing of County Road 122/PRETORIA ROAD from SR 91 to DOUGHERTY COUNTY LINE for a total pr | Pavement Improvement | 02/03/2010 | 05/12/2010 | 07/31/2010 | 647641.2 | 7.49
2090 | Georgia | BEN HILL |  | 8 | 0009500 | This project is a roadway maintenance repaving project in Ben Hill County. This project is the milling and resurfacing of County Road 254/OSIERFIELD from SR 206 to IRWIN COUNTY LINE for a total proje | Pavement Improvement | 01/19/2010 | 04/07/2010 | 06/30/2010 | 91427.93 | 1.09
2091 | Georgia | BERRIEN |  | 1 | 0009501 | This project is a roadway maintenance repaving project in Berrien County. This project is the milling and resurfacing of County Road 359/WYCLIFF ROBERTS ROAD from SR 158 to County Road 238/GLADYS ROA | Pavement Improvement | 01/19/2010 | 03/25/2010 | 07/31/2010 | 458782.43 | 6.87
2092 | Georgia | COLQUITT |  | 8 | 0009502 | This project is a roadway maintenance repaving project in Colquitt County. This project is the milling and resurfacing of City Street 759/City Street 1025/WEST BLVD from SR 33/US 319 to City Street 7 | Pavement Improvement | 02/01/2010 | 06/07/2010 | 06/30/2010 | 315921.17 | 1.93
2093 | Georgia | COOK |  | 1 | 0009503 | This project is a roadway maintenance repaving project in Cook County. This project is the milling and resurfacing of County Road 247/MASSEE POST ROAD from BOONE ROAD to LONNIE GRIMSLEY ROAD for a to | Pavement Improvement | 01/21/2010 | 06/14/2010 | 06/30/2010 | 163291.52 | 1.53
2094 | Georgia | DOUGHERTY | ALBANY | 2 | 0009504 | This project is a roadway maintenance repaving project in Dougherty County. This project is the milling and resurfacing of WEST OAKRIDGE DRIVE from OLD PRETORIA ROAD to LOCKETT STATION for a total pr | Pavement Improvement | 01/21/2010 | 04/26/2010 | 06/30/2010 | 605627.45 | 3.2
2095 | Georgia | GRADY |  | 2 | 0009506 | This project is a roadway maintenance repaving project in Grady County. This project is the milling and resurfacing of County Road 315/17TH AVE from SR 93/SR 111 to 0.30 MI east of SR 38/US 84 for a | Pavement Improvement | 02/05/2010 | 06/03/2010 | 07/31/2010 | 59611.55 | 0.46
2096 | Georgia | LEE | ALBANY | 2 | 0009507 | This project is a roadway maintenance repaving project in Lee County. This project is the milling and resurfacing of County Road 227/PINEWOOD ROAD from KINCHAFOONEE CREEK to County Road 229/BRONWOOD | Pavement Improvement | 02/04/2010 | 05/28/2010 | 07/31/2010 | 119556.7 | 1.16
2097 | Georgia | LEE |  | 2 | 0009508 | This project is a roadway maintenance repaving project in Lee County. This project is the milling and resurfacing of County Road 231/NORTH PHILEMA ROAD from SR 32 to County Road 232/NEW YORK ROAD for | Pavement Improvement | 02/04/2010 | 05/28/2010 | 07/31/2010 | 404408.7 | 4.68
2098 | Georgia | LOWNDES | VALDOSTA | 1 | 0009509 | This project is a roadway maintenance repaving project in Lowndes County. This project is the milling and resurfacing of County Road 779/HOWELL ROAD from County Road 1274/STATENVILLE to SR 7/PERIMETE | Pavement Improvement | 01/21/2010 | 03/25/2010 | 06/30/2010 | 218636.5 | 1.95
2099 | Georgia | LOWNDES | VALDOSTA | 1, 2 | 0009510 | This project is a roadway maintenance repaving project in Lowndes County. This project is the milling and resurfacing of County Road 782/MORVEN ROAD from SR 122 to BROOKS COUNTY LINE for a total proj | Pavement Improvement | 02/04/2010 | 03/30/2010 | 07/31/2010 | 413676.16 | 4.06
2100 | Georgia | MILLER |  | 2 | 0009511 | This project is a roadway maintenance repaving project in Miller County. This project is the milling and resurfacing of County Road 189/GRADY COBB ROAD from SHINGLER ROAD to THREE NOTCH ROAD for a to | Pavement Improvement | 02/03/2010 | 05/24/2010 | 07/31/2010 | 378553 | 3.97
2101 | Georgia | MITCHELL |  | 2 | 0009512 | This project is a roadway maintenance repaving project in Mitchell County. This project is the milling and resurfacing of County Road 275/RIVER ROAD from SR 65 to County Road 11/SLASH ROAD for a tota | Pavement Improvement | 02/05/2010 | 06/03/2010 | 07/31/2010 | 689910.75 | 7.35
2102 | Georgia | RANDOLPH |  | 2 | 0009513 | This project is a roadway maintenance repaving project in Randolph County. This project is the milling and resurfacing of County Road 161/LOWER SHELLMAN from SR 41 to TERRELL COUNTY LINE for a total | Pavement Improvement | 02/05/2010 | 05/19/2010 | 07/31/2010 | 328228.1 | 4.16
2103 | Georgia | TIFT |  | 8 | 0009514 | This project is a roadway maintenance repaving project in Tift County. This project is the milling and resurfacing of County Road 418/OLD UNION ROAD from SOUTHWELL BLVD to OMEGA-ELDORADO ROAD for a t | Pavement Improvement | 01/21/2010 | 03/15/2010 | 07/31/2010 | 397608.84 | 4.35
2104 | Georgia | WORTH |  | 8 | 0009515 | This project is a roadway maintenance repaving project in Worth County. This project is the milling and resurfacing of County Road 415/PHILLIP CAUSEY ROAD from SR 33 to County Road 412/SUMNER ROAD fo | Pavement Improvement | 02/11/2010 | 05/13/2010 | 07/31/2010 | 371356.1 | 5.48
2105 | Georgia | BULLOCH |  | 12 | 0009516 | This project is a roadway maintenance repaving project in Bulloch County. This project is the milling and resurfacing of County Road 577/DENMARK-NEVILS ROAD from County Road 584/GROVELAND ROAD to SR | Pavement Improvement | 01/21/2010 | 04/08/2010 | 06/30/2010 | 349280.3 | 2.52
2106 | Georgia | CAMDEN |  | 1 | 0009517 | This project is a roadway maintenance repaving project in Camden County. This project is the milling and resurfacing of County Road 141/HARRIETTS BLUFF ROAD from DEEP CREEK to CHEMICAL PLANT for a to | Pavement Improvement | 02/01/2010 | 03/22/2010 | 07/31/2010 | 470681.91 | 3.73
2107 | Georgia | EFFINGHAM |  | 12 | 0009518 | This project is a roadway maintenance repaving project in Effingham County. This project is the milling and resurfacing of County Road 307/CLYO-KILDARE ROAD from SR 21 to north of PR 443 for a total | Pavement Improvement | 02/04/2010 | 05/05/2010 | 07/31/2010 | 1134122.8 | 10.257
2108 | Georgia | EVANS |  | 12 | 0009519 | This project is a roadway maintenance repaving project in Evans County. This project is the milling and resurfacing of County Road 233/OLD HWY 250 from TATTNALL CO LINE to County Road 204/SUNBURY ROA | Pavement Improvement | 01/19/2010 | 07/01/2010 | 07/31/2010 | 810587.86 | 5.81
2109 | Georgia | TATTNALL |  | 12 | 0009520 | This project is a roadway maintenance repaving project in Tattnall County. This project is the milling and resurfacing of County Road 509/OLD HWY 250 from SR 73/US 301 to EVANS COUNTY LINE for a tota | Pavement Improvement | 01/19/2010 | 07/01/2010 | 07/31/2010 | 563837.92 | 3.89
2110 | Georgia | TOOMBS |  | 12 | 0009521 | This project is a roadway maintenance repaving project in Toombs County. This project is the milling and resurfacing of County Road 335/THOMPSON POND ROAD from SR 292 to VIDALIA CITY LIMITS for a tot | Pavement Improvement | 02/11/2010 | 03/31/2010 | 06/30/2010 | 310057.25 | 1.4
2111 | Georgia | WAYNE |  | 1 | 0009522 | This project is a roadway maintenance repaving project in Wayne County. This project is the milling and resurfacing of County Road 392/SUNSET BLVD from SR 169 to north of SR 38/US 84 for a total proj | Pavement Improvement | 01/21/2010 | 05/24/2010 | 06/30/2010 | 309230.77 | 1.5
2112 | Georgia | CHATTOOGA |  | 11 | 0009523 | This project is a roadway maintenance repaving project in Chattooga County. This project is the milling and resurfacing of County Road 329/GORE-SUBLIGNA ROAD from SR 1/US 27 to County Road 29/JOHNSTO | Pavement Improvement | 02/04/2010 | 05/13/2010 | 07/31/2010 | 484286.75 | 4.29
2113 | Georgia | FLOYD | ROME | 11 | 0009524 | This project is a roadway maintenance repaving project in Floyd County. This project is the milling and resurfacing of City Street 1124/BROAD STREET from SR 1/US 27 to COOSA RIVER for a total project | Pavement Improvement | 02/05/2010 | 06/06/2010 | 06/30/2010 | 244519.69 | 0.75
2114 | Georgia | FLOYD | ROME | 11 | 0009525 | This project is a roadway maintenance repaving project in Floyd County. This project is the milling and resurfacing of City Street 642/Charlton Street from SR 1/US 27 to County Road 1050/Division Str | Pavement Improvement | 03/11/2010 |  | 06/30/2010 | 155682.11 | 1.01
2115 | Georgia | GORDON |  | 11 | 0009526 | This project is a roadway maintenance repaving project in Gordon County. This project is the milling and resurfacing of County Road 483/CRAIGTOWN ROAD from SR 225 to SR 3/US 41 for a total project le | Pavement Improvement | 01/19/2010 | 02/03/2010 | 06/30/2010 | 214540.03 | 2.45
2116 | Georgia | GORDON |  | 11 | 0009527 | This project is a roadway maintenance repaving project in Gordon County. This project is the milling and resurfacing of County Road 483/NEWTOWN CHURCH ROAD from SR 225 to County Road 21/NEWTOWN ROAD | Pavement Improvement | 02/05/2010 | 04/06/2010 | 06/30/2010 | 129508.14 | 1.13
2117 | Georgia | PAULDING | ATLANTA | 11 | 0009528 | This project is a roadway maintenance repaving project in Paulding County. This project is the milling and resurfacing of County Road 467/DALLAS NEBO ROAD from SR 61 to County Road 472/FROG ROAD for | Pavement Improvement | 01/19/2010 |  |  | 386427.16 | 3.01
2118 | Georgia | CLAYTON | ATLANTA | 13 | 0009530 | This project is a roadway maintenance repaving project in Clayton County. This project is the milling and resurfacing of County Road 1351/REX ROAD from SR 42 to I-675 for a total project length of 0. | Pavement Improvement | 02/05/2010 | 04/19/2010 | 06/30/2010 | 173139.47 | 0.66
2119 | Georgia | TURNER |  | 8 | 0009531 | This project is a roadway maintenance repaving project in Turner County. This project is the milling and resurfacing of County Road 249/WARWICK HWY from east of County Road 96/OAK GROVE to County Roa | Pavement Improvement | 01/19/2010 | 04/07/2010 | 06/30/2010 | 122983.42 | 1.58
2120 | Georgia | COBB | ATLANTA | 11, 13, 6 | 0009532 | This project is a roadway maintenance repaving project in Cobb County. This project is the milling and resurfacing of County Road 1720/Windy Hill from County Road 1154/Powers Ferry Road to SR 3/US 41 | Pavement Improvement | 02/24/2010 | 04/27/2010 | 06/30/2010 | 762015.68 | 1.57
2121 | Georgia | NEWTON | ATLANTA | 8 | 0009536 | "The proposed safety project is located in Newton County. This project will replace the intersection of Turner Lake Road and Clark Street currently controlled by a traffic signal with a roundabout. T | New Construction | 04/29/2010 | 05/13/2010 | 11/30/2010 | 775622.42 | 0.8
2122 | Georgia | CATOOSA | CHATTANOOGA (TN) | 9 | 0009540 | This project is a roadway maintenance repaving project in Catoosa County. This project is the milling and resurfacing of County Road 382/LAFAYETTE STREET from SR 151 to SR 3/US 41 for a total project | Pavement Improvement | 02/01/2010 | 03/31/2010 | 06/30/2010 | 129324.93 | 1.78
2123 | Georgia | WASHINGTON |  | 12 | 0009598 | This project is an intersection improvement in Washington County. This project consists of intersection improvements on State Route 15 at Matthews Road in the City of Tennille. The project begins at | Safety/Traffic Management | 01/19/2010 | 04/06/2010 | 09/30/2011 | 2883272.29 | 0.59
2124 | Georgia | APPLING |  | 1 | 0009603 | This project will replace two bridges in Appling County. The replacement of the bridges at SR 4/US 1 at Blackwater Creek and Sweetwater Creek will be constructed in conjunction with a roadway widenin | Bridge Replacement | 01/06/2010 | 01/20/2010 | 08/31/2012 | 1080619.77 | 1
2125 | Georgia | NEWTON | ATLANTA | 7, 8 | 0009604 | This project is a roadway widening project in Newton County. The project is to widen SR 142 from south of SR 12/US 278 to CR 72/Industrial Boulevard. The project ties to I-20 at the SR 142 interchan | Pavement Widening | 01/12/2010 | 03/01/2010 | 10/31/2012 | 12419891.91 | 1.11
2126 | Georgia | APPLING |  | 1 | 0009605 | This project is a roadway widening project in Appling County. The project will widen and reconstruct US 1/SR 4 from the Bacon County line north to SR 15. From the Bacon County line to CR 493, the US | Pavement Widening | 01/06/2010 | 01/20/2010 | 08/31/2012 | 36711343.28 | 9.1
2127 | Georgia | RICHMOND | AUGUSTA (SC) | 10 | 0009610 | This project is a safety project in Augusta/Richmond County. This project will upgrade traffic signal equipment and upgrade pedestrian accomodations at the following intersections in the City of Augu | Safety/Traffic Management | 06/25/2010 |  | 07/31/2011 | 2823816.02 | 1.04
2128 | Georgia | COLUMBIA | AUGUSTA (SC) | 10 | 0009621 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 164/FLOWING WELLS ROAD from County Road 573/WHEELER ROAD to SR 10 | Pavement Improvement | 06/14/2010 |  | 06/30/2011 | 268472.77 | 1.46
2129 | Georgia | COLUMBIA | AUGUSTA (SC) | 10 | 0009622 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 221/SOUTH OLD BELAIR ROAD from SR 383 to SR 232 for a total proje | Pavement Improvement | 06/14/2010 |  | 06/30/2011 | 533037.11 | 3.29
2130 | Georgia | COLUMBIA | AUGUSTA (SC) | 10 | 0009623 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 1236/EVANS-TO-LOCKS ROAD from SR 104 to SR 28 for a total project | Pavement Improvement | 06/14/2010 |  | 06/30/2011 | 444962.35 | 2.59
2131 | Georgia | COLUMBIA | AUGUSTA (SC) | 10 | 0009624 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 176/OLD EVANS RD from SR 104 to the CSX Railroad Crossing (Crossi | Pavement Improvement | 06/14/2010 |  | 06/30/2011 | 377151.43 | 0.59
2132 | Georgia | COLUMBIA | AUGUSTA (SC) | 10 | 0009625 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of SR 28 from County Road 1236/EVANS-TO-LOCKS ROAD to SAVANNAH RIVER for a total | Pavement Improvement | 06/14/2010 |  | 06/30/2011 | 694049.06 | 3.92
2133 | Georgia | BUTTS |  | 8 | 0009632 | This project will construct pasing lanes on State Route 42 in Butts County. The project will construct two passing lanes along a 3.08-mile stretch of SR 42/US 23 between the cities of Jackson and Jen | New Construction | 03/08/2010 | 03/31/2010 | 12/31/2011 | 8034673.67 | 3.079
2134 | Georgia | TERRELL |  | 2 | 0009634 | This project is a bridge replacement on a county road in Terrell County. Project construction will replace the structurally deficient bridge at Sasser-Herod Road 164, over Chickasawhatchee Creek. T | Bridge Replacement | 01/21/2010 | 02/15/2010 | 09/30/2011 | 1143296.85 | 0.55
2135 | Georgia | TERRELL |  | 2 | 0009635 | This project is a bridge replacement on a county road in Terrell County. Project construction will replace the structurally deficient bridge at CR 164/Sasser-Herod Road over Brantley Creek. The exist | Bridge Replacement | 01/21/2010 | 02/15/2010 | 09/30/2011 | 960229.2 | 0.47
2136 | Georgia | CHEROKEE | ATLANTA | 6 | 0009636 | The proposed project will provide sidewalks with curb and gutter drainage, lighting, benches, trash receptacles, thermoplastic striping at cross walks, and bicycle parking. The project limits include | Transportation Enhancements | 06/08/2010 |  |  | 965323.8 | 0.63
2137 | Georgia | COBB | ATLANTA | 6 | 0009638 | This project is a roadway widening project in Cobb County. The project will widen SR 120/Roswell Road from SR 120 Alternate to Bridgegate Drive. The initial 22% of the project is located within the | Pavement Improvement | 02/05/2010 | 03/08/2010 | 12/31/2012 | 10195880.63 | 1.82
2138 | Georgia | DE KALB | ATLANTA | 4 | 0009641 | This project will construct a new roadway in DeKalb County. The project consists of extending the existing Lithonia Industrial Boulevard on new location between South Stone Mountain Lithonia Road to | Pavement Widening | 03/11/2010 | 03/17/2010 | 09/30/2012 | 18666021.45 | 1.33
2139 | Georgia | PAULDING | ATLANTA | 11 | 0009642 | This project will replace a structurally deficient bridge on County Road 467 in Paulding County. Construction will replace the bridge and approaches on County Road 467/Bakers Bridge Road over Sweetwa | Bridge Replacement | 03/02/2010 | 03/17/2010 | 05/31/2011 | 2195289.94 | 0.43
2140 | Georgia | SPALDING | ATLANTA | 3 | 0009680 | This project consists of road resurfacing on East McIntosh Road beginning at Old Atlanta Road and extending to North Hill Street. | Pavement Improvement | 03/19/2010 | 05/12/2010 | 08/31/2010 | 258279.36 | 1.32
2141 | Georgia | SPALDING | ATLANTA | 3 | 0009682 | This project consists of road resurfacing on Old Atlanta Road beginning at the Griffin City limits and extending to the Henry County line. | Pavement Improvement | 03/19/2010 | 05/12/2010 | 08/31/2010 | 660446.03 | 5.25
2142 | Georgia | SPALDING | ATLANTA | 3 | 0009683 | This project consists of road resurfacing at the following locations: on Old Atlanta Road from an asphalt joint north of Beatty Street to Griffin City limits, on West Popular Street from New Orleans S | Pavement Improvement | 03/19/2010 | 05/12/2010 | 08/31/2010 | 205197.73 | 1.65
2143 | Georgia | TIFT |  | 8 | 0009686 | This project is the replacement of a structurally deficient bridge in Tift County. Construction will replace the bridge on County Road 411/Salem Church Road at Ty Ty Creek with a new reinforced concr | Bridge Replacement | 03/02/2010 | 03/04/2010 | 04/30/2011 | 2362947.56 | 0.76
2144 | Georgia | PUTNAM |  | 10 | 0009687 | This project is the widening and reconstruction of US 441 (SR 24) in Putnam County beginning just north of CR 245/Cay Road and ending at US 129/SR 44 at the Eatonton Bypass for a distance of 8.3 miles | Pavement Widening | 03/19/2010 | 04/20/2010 | 05/31/2012 | 34550070.72 | 8.3
2145 | Georgia | CATOOSA | CHATTANOOGA (TN) | 9 | 0009693 | This project is a roadway maintenance repaving project in Catoosa County. This project is the milling and resurfacing of County Road 171/Poplar Springs Rd from County Road 390/Three Notch Rd to SR 15 | Pavement Improvement | 05/27/2010 |  | 09/30/2010 | 602847.97 | 3.5
2146 | Georgia | BROOKS |  | 2 | 0009701 | This project is a bridge replacement project in Brooks County. The proposed project consists of the replacement of a narrow and structurally deficient bridge on CR 305 over Pride Branch. The existin | Bridge Replacement | 03/02/2010 | 03/22/2010 | 04/30/2011 | 1821022.77 | 0.379
2147 | Georgia | FULTON | ATLANTA | 6 | 0009704 | This project is an operational and safety improvement in Fulton County. This project is located at the intersection of S.R. 140/Holcomb Bridge Road and Barnwell Road/C.R. 107 in Roswell. Currently, S | Pavement Improvement | 03/19/2010 | 06/28/2010 | 05/31/2011 | 271111.43 | 0.1
2148 | Georgia | BIBB | MACON | 8 | 0009827 | This project is an Interstate widening project in Bibb County. This project will widen I-75 from two to three 12-foot travel lanes in each direction between Pierce Avenue and Arkwright Road. The proj | Pavement Widening | 06/15/2010 |  | 05/31/2013 | 31068949.25 | 3.3
2149 | Georgia | COBB | ATLANTA | 11 | 0010124 | This project is an operational improvement in Cobb County. This project will construct additional turning capacity at the Wade Green Road exit on I-75. This project will help alleviate congestion at | Pavement Improvement | 06/08/2010 |  | 10/31/2010 | 663237.12 | 0.4
2150 | Georgia | COOK |  | 1 | 0011061 | This project is a bridge replacement in Cook County. This project will replace the structurally deficient bridge on SR 7/US 41 over Giddens Mill Creek with a new reinforced concrete bridge. The exis | Bridge Replacement | 09/24/2009 | 09/24/2009 | 09/30/2010 | 2215295.17 | 0.209
2151 | Georgia | PIKE |  | 3 | 0051034 | This project is a safety intersection improvement in Pike County. The purpose of this project is to improve the safety and operation by realigning the intersection of SR 18/SR 109 and SR 74. Current | Pavement Improvement | 09/30/2009 | 10/29/2009 | 07/31/2010 | 1401078.13 | 0.52
2152 | Georgia | CHEROKEE | ATLANTA | 6 | 0057017 | This is a bridge replacement project in Cherokee County. This project will replace a narrow and structurally deficient bridge on Howell Bridge Road (CR 107) over Sharp Mountain Creek, 2 miles southwe | Bridge Replacement | 10/26/2009 | 11/30/2009 | 12/31/2010 | 1443800 | 0.13
2153 | Georgia | COLQUITT |  | 8 | 0071028 | This project will replace the structurally deficient bridge on CR 186/Hagin Still Road over the Ochlockonee River in Colquitt County. The bridge is located southeast of the city of Doerun. The 140'x | Bridge Replacement | 09/24/2009 | 09/28/2009 | 08/31/2010 | 1235527.02 | 0.23
2154 | Georgia | FULTON | ATLANTA | 6 | 00SW004 | This project will construct sidewalks on Holcomb Bridge Road in Fulton County. The construction proposes to add 5' sidewalks 2' behind the back of the existing curb on both sides of Holcomb Bridge Ro | Transportation Enhancements | 11/16/2009 |  | 08/31/2010 | 1258115.94 | 0.49
2155 | Georgia | MUSCOGEE | COLUMBUS (AL) | 2 | 00TS047 | This project is a safety and operational improvement in the City of Columbus in Muscogee County. This project is the installation of fiber optic communications cable and closed circuit television (CC | Safety/Traffic Management | 02/11/2010 |  | 06/30/2011 | 1034304.2 | 0
2156 | Georgia | MUSCOGEE | COLUMBUS (AL) | 2 | 00TS048 | This project is a safety and operational improvement in the City of Columbus in Muscogee County. The Columbus Regional Traffic Control Center (TCC) will provide the core communications and infrastruc | Safety/Traffic Management | 02/11/2010 |  | 06/30/2011 | 689336.84 | 0
2157 | Georgia | DOUGHERTY | ALBANY | 2 | 0133005 | This project is a roadway widening in Dougherty County. This project widens and reconstructs SR 234/Gillionville Road from Eight Mile Road to Lockett Station Road. The existing two lane roadway wil | Pavement Widening | 08/19/2009 | 09/25/2009 | 09/30/2011 | 7651900.03 | 2.17
2158 | Georgia | PAULDING | ATLANTA | 11 | 0181070 | This is an intersection safety project in Paulding County. This intersection improvement is located 8.2 miles southwest of the City of Dallas on SR 61 at the intersection with County Road 472 and Cou | Pavement Improvement | 03/02/2010 | 05/11/2010 | 12/31/2010 | 1441955.14 | 0.55
2159 | Georgia | TERRELL |  | 2 | 0291032 | This project is the reconstruction and rehabilitation of SR 49 in Terrell County north of the city of Dawson. The project limits begin at the junction with SR 45 and continue for 3.14 miles. SR 49 cur | Pavement Improvement | 02/04/2010 | 02/11/2010 | 04/30/2011 | 3960447.86 | 2.98
2160 | Georgia | WILKINSON |  | 8 | 0540019 | This project is the construction of the North Gordon Bypass, a new roadway, from SR 57 at the Twiggs/Wilkinson County Line to SR 243 at Lake Tchucoloako. The total length of project is 7.2 miles. The | New Construction | 09/01/2009 | 10/26/2009 | 07/31/2012 | 33387811.03 | 7.2
2161 | Georgia | CHATHAM | SAVANNAH | 12 | 0641049 | This is a bridge replacement project in Chatham County. This project will replace the US 17/SR 25 bridge over Norfolk Southern Railroad approximately 5.5 miles north of Savannah in Port Wentworth. T | Bridge Replacement | 07/27/2009 | 07/28/2009 | 05/31/2012 | 4231018.62 | 0.23
2162 | Georgia | BIBB | MACON | 8 | 0661036 | This project will construct auxiliary lanes on SR 87 in Bibb County. The project will reconstruct SR 87/US 23 from an existing four-lane roadway with a 40-ft depressed median with rural shoulders to | Pavement Improvement | 09/24/2009 | 11/12/2009 | 04/30/2011 | 8359335.95 | 2.12
2163 | Georgia | GWINNETT | ATLANTA | 7 | 0852176 | This project is the construction of an Advanced Traffic Management System along Interstate 85 in Gwinnett County. The proposed project involves the installation of fiber optic cable and High Density | Safety/Traffic Management | 09/18/2009 | 01/09/2010 | 10/31/2010 | 2164670.45 | 4.91
2164 | Georgia | GWINNETT | ATLANTA | 7 | 0998001 | This project will rehabilitate and improve the safety at the bridge over I-85 and widening of SR 324 approaching the bridge in Gwinett County. This project replaces the two-lane bridge on Gravel Spri | Bridge Replacement | 09/04/2009 | 10/02/2009 | 05/31/2012 | 11912476 | 0.8
2165 | Georgia | HENRY | ATLANTA | 3 | 1631020 | This project is an intersection improvement in Henry County. The project will install signalization of a stop condition intersection and the addition of left and right turn lanes to SR 81 at the inte | Safety/Traffic Management | 01/08/2010 | 01/20/2010 | 11/05/2010 | 696071.31 | 0.25
2166 | Georgia | CLAYTON | ATLANTA | 13, 5 | 6751001 | This project will install the NaviGAtor system along I-675 from I-75 to I-285 in Clayton, Dekalb and henry Counties. Included in the project will be two changeable message signs, vehicle detection co | Safety/Traffic Management | 08/18/2009 | 08/18/2009 | 12/31/2010 | 1894362.88 | 10.7
2167 | Georgia | DOUGLAS | ATLANTA | 13 | 7532950 | This project is a bridge replacement in Douglas County. The proposed project consists of replacing the existing structurally deficient bridge (48.43 Suff. Rating) along County Road 815/Anneewakee Roa | Bridge Replacement | 09/24/2009 | 10/23/2009 | 12/31/2010 | 1876015.68 | 0.419
2168 | Georgia | DE KALB | ATLANTA | 4 | 9014024 | This project is a culvert replacement in Dekalb County. The proposed project will replace the existing box culvert and wooden pedestrian bridge on SR 155/Candler Road at Shoal Creek with a larger con | Bridge Replacement | 09/23/2009 | 11/12/2009 | 03/31/2011 | 1394072.48 | 0.26
2169 | Georgia | FULTON | ATLANTA | 5 | 9161001 | The proposed project would replace the existing Mitchell Street Bridge located over CSX Railroad between Techwood Drive and Spring Street. The existing bridge is in need of replacement due to inadequa | Bridge Replacement | 01/05/2010 | 03/29/2010 | 05/31/2012 | 8559194.8 | 0.578
2170 | Georgia | DOUGLAS | ATLANTA | 13 | 9398001 | This project is the construction of intersection improvements on Kings Highway at Central Church Road in Douglas County. The project will provide a separate left turn bay for westbound movements onto | Safety/Traffic Management | 09/18/2009 | 11/12/2009 | 04/30/2011 | 778753.72 | 0.33
2171 | Georgia | BULLOCH |  | 12 | M003694 | This project is a maintenance construction project in Bulloch County. This project is the resurfacing of SR 26. This section of SR 26 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 01/19/2010 |  | 10/31/2010 | 2055114.84 | 10.81
2172 | Georgia | ROCKDALE | ATLANTA | 4 | M003836 | This is a maintenance construction project in Rockdale County. This project is the milling and resurfacing of SR 162 from the Newton County Line to County Road 666/Dogwood Drive. This section of SR | Pavement Improvement | 07/17/2009 | 08/13/2009 | 05/31/2010 | 594191.33 | 2.39
2173 | Georgia | EFFINGHAM |  | 12 | M003841 | This project is a maintenance construction project in Effingham County. This project is the resurfacing of SR 26. This section of SR 26 needs resurfacing because the existing pavement is deterioratin | Pavement Improvement | 01/12/2010 | 06/16/2010 | 08/31/2010 | 1238031.3 | 5.39
2174 | Georgia | JACKSON |  | 10 | M003862 | This project is a maintenance construction project in Jackson County. This project is the resurfacing of SR 82. This section of SR 82 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 07/20/2009 | 01/15/2010 | 05/31/2010 | 1009579.73 | 6.2
2175 | Georgia | QUITMAN |  | 2 | M003896 | This project is a maintenance construction project in Quitman and Randolph Counties. This project is the milling and resurfacing of SR 50. This section of SR 50 needs resurfacing because the existing | Pavement Improvement | 06/19/2009 | 01/15/2010 | 03/31/2010 | 2423843.86 | 11.26
2176 | Georgia | COFFEE |  | 1 | M003897 | This is a maintenance construction project in Coffee County. This project is the milling and resurfacing of SR 31/US 441 from SR 135 to City Street 787/McNeal Drive. This section of SR 31 needs resur | Pavement Improvement | 07/06/2009 | 08/26/2009 | 04/30/2010 | 665267.93 | 2.4
2177 | Georgia | DOUGHERTY | ALBANY | 2 | M003898 | This project is a maintenance construction project in Dougherty County. The project is the milling and resurfacing of SR 133 from SR 91 to the Lee County Line. This section of SR 133 needs resurfacin | Pavement Improvement | 06/19/2009 | 07/30/2009 | 01/31/2010 | 224974.26 | 1.07
2178 | Georgia | MADISON |  | 10 | M003906 | This is a maintenance construction project in Madison County. The project is the resurfacing of SR 98 from SR 8/US 29 to SR 72. Ths section of SR 98 needs resurfacing because the existing pavement is | Pavement Improvement | 06/25/2009 | 07/25/2009 | 03/31/2010 | 825383.1 | 7.4
2179 | Georgia | TOWNS |  | 10 | M003907 | This is a maintenance construction project in Towns County. The project is the milling and rsurfacing of SR 75 from SR 2 to the North carolina State Line. This section of SR 75 needs resurfacing beca | Pavement Improvement | 06/19/2009 | 08/17/2009 | 03/31/2010 | 498265.27 | 3.4
2180 | Georgia | HALL | GAINESVILLE | 9 | M003908 | This is a maintenance construction project in Hall County. The project is the resurfacing of SR 283 from SR 60 to SR 52/Dahlonega Highway. This section of SR 283 needs resurfacing because the existin | Pavement Improvement | 06/25/2009 | 08/24/2009 | 04/30/2010 | 1289894.36 | 9.3
2181 | Georgia | MONTGOMERY |  | 1, 12 | M003909 | This project is a maintenance construction project in Jeff Davis and Montgomery Counties. This project is the resurfacing of SR 135. This section of SR 135 needs resurfacing because the existing pave | Pavement Improvement | 07/17/2009 | 01/29/2010 | 05/31/2010 | 3147915.33 | 18.57
2182 | Georgia | CHATHAM | SAVANNAH | 12 | M003910 | This project is a maintenance construction project in Chatham County. This project is the milling and resurfacing of SR 307. This section of SR 307 needs resurfacing because the existing pavement is | Pavement Improvement | 06/30/2009 | 02/10/2010 | 04/30/2010 | 1311565.27 | 5.94
2183 | Georgia | CHATHAM | SAVANNAH | 12 | M003911 | This project is a maintenance construction project in Chatham County. This project is the milling and resurfacing of SR 30. This section of SR 30 needs resurfacing because the existing pavement is de | Pavement Improvement | 06/30/2009 | 02/10/2010 | 04/30/2010 | 182427.84 | 0.98
2184 | Georgia | BACON |  | 1 | M003914 | This project is a maintenance construction project in Bacon County. This project is the milling and resurfacing of SR 32. This section of SR 32 needs resurfacing because the existing pavement is dete | Pavement Improvement | 06/30/2009 | 12/17/2009 | 03/31/2010 | 1152581.33 | 4.56
2185 | Georgia | CHARLTON |  | 1 | M003916 | This is a maintenance construction project in Charlton County. The project is the resurfacing of SR 4/US 1 from north of SR 4 to the Ware County Line. This section of SR 4 needs resurfacing because t | Pavement Improvement | 06/25/2009 | 07/13/2009 | 04/30/2010 | 4132510.48 | 11.73
2186 | Georgia | CHARLTON |  | 1 | M003917 | This is a maintenance construction project in Charlton County. This project is the resurfacing of SR 40 Connector from SR 40 to SR 4. This section of SR 40 Connector needs resurfacing because the exis | Pavement Improvement | 06/25/2009 | 07/13/2009 | 04/30/2010 | 197452.66 | 1.33
2187 | Georgia | WALKER |  | 9 | M003920 | This project is a maintenance construction project in Walker County. This project is the milling and resurfacing of SR 1 Businesss. This section of SR 1 Business needs resurfacing because the existin | Pavement Improvement | 07/06/2009 | 09/10/2009 | 04/30/2010 | 721762.53 | 3.34
2188 | Georgia | BARTOW |  | 11 | M003921 | This is a maintenance construction project in Bartow County. This project is the milling and resurfacing of SR 3 from south of Peachtree Street to north of MLK Jr. Drive in Cartersville. This sectio | Pavement Improvement | 06/25/2009 | 08/18/2009 | 04/30/2010 | 745586.75 | 1.63
2189 | Georgia | CHEROKEE | ATLANTA | 6 | M003923 | This project is a maintenance construction project in Cherokee County. This project is the resurfacing on SR 140. This section of SR 140 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 06/25/2009 | 09/08/2009 | 03/31/2010 | 1762634.82 | 10.61
2190 | Georgia | SUMTER |  | 2 | M003932 | This is a maintenance construction project in Sumter County. This project is the milling and resurfacing of SR 27 West from SR 27 to SR 3/US 19 in Americus. This section of SR 27 West needs resurfaci | Pavement Improvement | 06/25/2009 | 08/02/2009 | 12/31/2009 | 593223.49 | 2.13
2191 | Georgia | SUMTER |  | 2 | M003933 | This is a maintenance construction project in Sumter County. This project is the milling and resurfacing of SR 27 from SR 3/US 19 to SR 27 West/SR 30 in Americus. This section of SR 27 needs resurfac | Pavement Improvement | 06/25/2009 | 08/02/2009 | 12/31/2009 | 616798.09 | 2.136
2192 | Georgia | RICHMOND | AUGUSTA (SC) | 12 | M003935 | This project is a maintenance construction project in Richmond County. This project is the milling and resurfacing of SR 28. This section of SR 28 needs resurfacing because the existing pavement is d | Pavement Improvement | 10/26/2009 | 03/21/2010 | 06/30/2010 | 1295804.9 | 2.72
2193 | Georgia | DODGE |  | 8 | M003938 | This is a maintenance construction project in Dodge County. This project is the milling and resurfacing of SR 117 from south of Front Street to Sugar Creek Bridge. This section of SR 117 needs resurf | Pavement Improvement | 06/22/2009 | 07/09/2009 | 03/31/2010 | 2273844.08 | 13.62
2194 | Georgia | JEFFERSON |  | 12 | M003941 | This project is a maintenance construction project in Jefferson County. This project is the milling and resurfacing of SR 4. This section of SR 4 needs resurfacing because the existing pavement is de | Pavement Improvement | 10/26/2009 | 04/29/2010 | 08/31/2010 | 3438984.42 | 13.61
2195 | Georgia | FULTON | ATLANTA | 6 | M003942 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 9 from the Chattahoochee River to Marietta Highway. This section of SR 9 needs resurfaci | Pavement Improvement | 06/25/2009 | 08/02/2009 | 04/30/2010 | 296801.5 | 1.21
2196 | Georgia | FULTON | ATLANTA | 5 | M003943 | This is a maintenance construction project in Clayton and Fulton Counties. This project is the milling and resurfacing of SR 3/US 19 from Interstate 285 to City Street 3096/Cleveland Avenue. This sec | Pavement Improvement | 06/26/2009 | 07/07/2009 | 03/31/2010 | 936941.23 | 4.17
2197 | Georgia | FULTON | ATLANTA | 6 | M003945 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 9 from Abernathy Road to the Chattahoochee River. This section of SR 9 needs resurfacing | Pavement Improvement | 06/25/2009 | 08/02/2009 | 04/30/2010 | 1558771.05 | 5.2
2198 | Georgia | DE KALB | ATLANTA | 4, 7 | M003946 | This project is a maintenance construction project in DeKalb and Gwinnett Counties. This project is the milling and resurfacing of SR 10. This section of SR 10 needs resurfacing because the existing | Pavement Improvement | 08/14/2009 | 04/16/2010 | 08/29/2010 | 3210565.33 | 3.83
2199 | Georgia | FULTON | ATLANTA | 13 | M003947 | This project is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 14 Spur. This section of SR 14 Spur needs resurfacing because the existing pavem | Pavement Improvement | 08/07/2009 | 03/05/2010 | 06/30/2010 | 894468.65 | 1.61
2200 | Georgia | FULTON | ATLANTA | 5 | M003948 | This is a maintenance construction project in Fulton County. This project is the resurfacing of SR 139 from West Whitehall Street to County Road 4176/Cascade Avenue. This section of SR 139 needs resu | Pavement Improvement | 06/19/2009 | 08/11/2009 | 03/31/2010 | 515323.56 | 1.21
2201 | Georgia | FULTON | ATLANTA | 5 | M003949 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 54 from north of I-285 to University Avenue. This section of SR 54 needs resurfacing bec | Pavement Improvement | 08/07/2009 | 09/01/2009 | 06/30/2010 | 1249406.17 | 5.87
2202 | Georgia | FULTON | ATLANTA | 13 | M003950 | This project is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 92. This section of SR 92 needs resurfacing because the existing pavement is det | Pavement Improvement | 06/25/2009 | 09/23/2009 | 03/31/2010 | 938806.6 | 3.83
2203 | Georgia | HALL | GAINESVILLE | 9 | M003957 | This project is a maintenance construction project in Hall County. This project is the resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 06/25/2009 | 09/10/2009 | 04/30/2010 | 1151859.25 | 3
2204 | Georgia | DAWSON |  | 9 | M003958 | This project is a maintenance construction project in Dawson County. This project is the resurfacing of SR 53. This section of SR 53 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 06/25/2009 | 11/19/2009 | 03/31/2010 | 1179956.15 | 6.8
2205 | Georgia | HABERSHAM |  | 10 | M003959 | This project is a maintenance construction project in Habersham County. This project is the resurfacing of SR 384. This section of SR 384 needs resurfacing because the existing pavement is deteriorat | Pavement Improvement | 06/25/2009 | 11/02/2009 | 03/31/2010 | 645925.17 | 4.2
2206 | Georgia | FRANKLIN |  | 10 | M003960 | This is a maintenance construction project in Franklin County. This project is the resurfacing of SR 51 from SR 59 to County Road 168/Hale Crossing Road. This section of SR 51 needs resurfacing becau | Pavement Improvement | 06/25/2009 | 08/25/2009 | 03/31/2010 | 1045067.2 | 9.9
2207 | Georgia | WHITE |  | 10, 9 | M003961 | This is a maintenance construction project in Habersham and White Counties. The project is the resurfacing of SR 356 from SR 17 in White County to SR 197 in Habersham County. This section of SR 356 n | Pavement Improvement | 06/25/2009 | 07/20/2009 | 04/30/2010 | 1804857.39 | 10.83
2208 | Georgia | FORSYTH | ATLANTA | 9 | M003964 | This project is a maintenance construction project in Forsyth County. This project is the milling and resurfacing of SR 9. This section of SR 9 needs resurfacing because the existing pavement is dete | Pavement Improvement | 06/25/2009 | 09/30/2009 | 03/31/2010 | 1996234.06 | 9.8
2209 | Georgia | STEPHENS |  | 10 | M003965 | This project is a maintenance construction project in Banks, Franklin and Stephens Counties. This project is the resurfacing of SR 63. This section of SR 63 needs resurfacing because the existing pav | Pavement Improvement | 07/21/2009 | 09/08/2009 | 05/31/2010 | 1911803.7 | 12.63
2210 | Georgia | BANKS |  | 10 | M003966 | This project is a maintenance construction project in Banks County. This project is the resurfacing of SR 164. This section of SR 164 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 06/25/2009 | 11/04/2009 | 04/30/2010 | 794418.78 | 4.8
2211 | Georgia | CHEROKEE | ATLANTA | 11, 6 | M003967 | This is an Interstate 575 maintenance construction project in Cobb and Cherokee Counties. This project is the milling and resurfacing of I-575/SR 417 from I-75 in Cobb County to the Etowah River in C | Pavement Improvement | 06/25/2009 | 07/13/2009 | 05/31/2010 | 19597484.47 | 19.79
2212 | Georgia | MARION |  | 2 | M003968 | This is a maintenance construction project in Marion County. This project is the milling and resurfacing of SR 137 from City Street 505/McDuffie Street to the Taylor County line. This section of SR 1 | Pavement Improvement | 06/25/2009 | 09/09/2009 | 04/30/2010 | 1407634.2 | 10.53
2213 | Georgia | CRAWFORD |  | 2 | M003969 | This is a maintenance construction project in Crawford and Peach Counties. The project is the milling and resurfacing of SR 7 from SR 96 in Peach County to SR 22/US 80 in Crawford County. This sectio | Pavement Improvement | 07/17/2009 | 08/06/2009 | 04/30/2010 | 2363595.66 | 14.37
2214 | Georgia | SCHLEY |  | 2 | M003970 | This project is a maintenance construction project in Schley and Sumter Counties. This project is the milling and resurfacing of SR 153. This section of SR 153 needs resurfacing because the existing | Pavement Improvement | 06/25/2009 | 02/11/2010 | 04/30/2010 | 1433599.39 | 8.1
2215 | Georgia | HENRY | ATLANTA | 3 | M003971 | This is a maintenance construction project in Henry County. This project is the milling and resurfacing of SR 155 from the Spalding County line to SR 20/SR 81. This section of SR 155 needs resurfacin | Pavement Improvement | 06/25/2009 | 08/04/2009 | 04/30/2010 | 2069902.16 | 8.8
2216 | Georgia | JASPER |  | 8 | M003972 | This project is a maintenance construction project in Jasper County. This project is the milling and resurfacing of SR 83. This section of SR 83 needs resurfacing because the existing pavement is dete | Pavement Improvement | 06/25/2009 | 08/31/2009 | 04/30/2010 | 1864482.29 | 12.79
2217 | Georgia | RICHMOND | AUGUSTA (SC) | 10, 12 | M003973 | This project is a maintenance construction project in Richmond County. This project is the milling and resurfacing of SR 4. This section of SR 4 needs resurfacing because the existing pavement is det | Pavement Improvement | 08/20/2009 | 10/20/2009 | 06/30/2010 | 4028596.8 | 10.2
2218 | Georgia | JASPER |  | 8 | M003974 | This is a maintenance construction project in Jasper County. This project is the milling and resurfacing of SR 16 from the Butts County line to SR 11 South. This section of SR 16 needs resurfacing be | Pavement Improvement | 06/25/2009 | 08/03/2009 | 04/30/2010 | 1457250.93 | 8.95
2219 | Georgia | PUTNAM |  | 10 | M003975 | This project is a maintenance construction project in Putnam County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is dete | Pavement Improvement | 06/19/2009 | 09/28/2009 | 04/30/2010 | 1702197.71 | 8.3
2220 | Georgia | TWIGGS |  | 8 | M003976 | This project is a maintenance construction project in Bleckley, Laurens and Twiggs Counties. This project is the concrete slab replacement of I-16/SR 404. This slab replacement of I-16 is needed becau | Pavement Improvement | 11/19/2009 | 02/02/2010 | 05/31/2011 | 22299110.14 | 15.32
2221 | Georgia | CHATHAM | SAVANNAH | 1, 12 | M003977 | This project is an interstate resurfacing project in Bryan and Chatham counties on I-95. This section of I-95 needs resurfacing because the existing pavement is deteriorating. I-95/SR 405 was last res | Pavement Improvement | 01/21/2010 | 06/01/2010 | 12/31/2010 | 8428494.63 | 11.7
2222 | Georgia | WARE |  | 1 | M003978 | This is a maintenance construction project in Ware County. This project is the milling and resurfacing of SR 4 Business/US 1 from south of County Road 341/Short Street to north of County Road 255/Smi | Pavement Improvement | 06/25/2009 | 07/20/2009 | 04/30/2010 | 1064995.62 | 5.79
2223 | Georgia | EFFINGHAM |  | 12 | M003979 | This project is a maintenance construction project in Effingham County. This project is the resurfacing of SR 17. This section of SR 17 needs resurfacing because the existing pavement is deterioratin | Pavement Improvement | 06/30/2009 | 09/15/2009 | 04/30/2010 | 741328.89 | 4.12
2224 | Georgia | CHARLTON |  | 1 | M003980 | This project is a maintenance construction project in Brantley and Charlton Counties. This project is the resurfacing of SR 23. This section of SR 23 needs resurfacing because the existing pavement is | Pavement Improvement | 07/06/2009 | 02/17/2010 | 04/30/2010 | 3681244.89 | 23.15
2225 | Georgia | BRYAN |  | 1 | M003981 | This project is a maintenance construction project in Bryan County. This project is the resurfacing of SR 25. This section of SR 25 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 08/20/2009 | 11/19/2009 | 06/30/2010 | 1623997.7 | 4.28
2226 | Georgia | ROCKDALE | ATLANTA | 4 | M003983 | This is a maintenance construction project in Rockdale County. This project is the resurfacing of SR 20 from County Road 435/Sigman Road to SR 138. This section of SR 20 needs resurfacing because the | Pavement Improvement | 06/25/2009 | 07/08/2009 | 04/30/2010 | 292742.36 | 1.34
2227 | Georgia | ROCKDALE | ATLANTA | 3, 4 | M003984 | This project is a maintenance construction project in Rockdale County. This project is the resurfacing of SR 20. This section of SR 20 needs resurfacing because the existing pavement is deteriorating | Pavement Improvement | 08/07/2009 | 09/08/2009 | 06/30/2010 | 2403218.15 | 6.99
2228 | Georgia | DE KALB | ATLANTA | 4 | M003985 | This project is a maintenance construction project in DeKalb County. This project is the resurfacing of SR 236/LaVista Road. This section of SR 236 needs resurfacing because the existing pavement is | Pavement Improvement | 08/17/2009 | 09/08/2009 | 06/30/2010 | 976902.07 | 2.4
2229 | Georgia | COBB | ATLANTA | 11 | M003986 | This project is a maintenance construction project in Cobb County. This project is the resurfacing of SR 360. This section of SR 360 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 08/07/2009 | 04/11/2010 | 06/30/2010 | 501006.53 | 2.97
2230 | Georgia | BIBB | MACON | 8 | M003987 | This project is a maintenance construction project in Bibb County. This project is the resurfacing of SR 87. This section of SR 87 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 01/21/2010 | 03/16/2010 | 08/31/2010 | 2263901.33 | 14.46
2231 | Georgia | BIBB | MACON | 8 | M003988 | This project is a maintenance construction project in Bibb County. This project is the resurfacing of SR 49. This section of SR 49 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 01/21/2010 | 03/16/2010 | 08/31/2010 | 66326.32 | 0.27
2232 | Georgia | WEBSTER |  | 2 | M003989 | This project is a maintenance construction project in Marion and Webster Counties. This project is the resurfacing of SR 41. This section of SR 41 needs resurfacing because the existing pavement is d | Pavement Improvement | 07/20/2009 | 04/05/2010 | 05/31/2010 | 1817639.78 | 12.57
2233 | Georgia | TAYLOR |  | 2 | M003990 | This project is a maintenance construction project in Crawford and Taylor Counties. This project is the resurfacing of SR 128. This section of SR 128 needs resurfacing because the existing pavement i | Pavement Improvement | 06/25/2009 | 03/01/2010 | 04/30/2010 | 2088691.24 | 14.09
2234 | Georgia | HARRIS |  | 3 | M003991 | This is a maintenance construction project in Harris County. This project is the resurfacing of SR 18 from SR 219 to SR 1/US 27. This section of SR 18 needs resurfacing because the existing pavement | Pavement Improvement | 06/25/2009 | 08/06/2009 | 04/30/2010 | 1676696.76 | 11.48
2235 | Georgia | GREENE |  | 10 | M003992 | This is a maintenance construction project in Greene County. The project is the resurfacing of SR 44 from the Putnam County line to SR 12. This section of SR 44 needs resurfacing because the existing | Pavement Improvement | 06/19/2009 | 08/11/2009 | 04/30/2010 | 2465038.45 | 11.45
2236 | Georgia | RICHMOND | AUGUSTA (SC) | 12 | M003993 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 56 Spur. This section of SR 56 Spur needs resurfacing because the existing pavement is det | Pavement Improvement | 11/30/2009 | 04/12/2010 | 09/30/2010 | 3576406.9 | 6.58
2237 | Georgia | NEWTON |  | 8 | M003994 | This project is a maintenance construction project in Newton County. This project is the resurfacing of SR 142. This section of SR 142 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 01/05/2010 | 02/01/2010 | 08/31/2010 | 1219852.67 | 8.3
2238 | Georgia | JASPER |  | 8 | M003995 | This project is a maintenance construction project in Jasper County. This project is the resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 01/21/2010 | 03/03/2010 | 08/31/2010 | 1495888.73 | 8.6
2239 | Georgia | LOWNDES | VALDOSTA | 1, 2 | M003998 | This project is an interstate resurfacing project in Lowndes County. This project is the milling and resurfacing of I-75/SR 401. This section of I-75 needs resurfacing because the existing pavement i | Pavement Improvement | 01/14/2010 | 04/26/2010 | 12/31/2010 | 19860872.58 | 18.05
2240 | Georgia | BRYAN |  | 1 | M004000 | This project is a maintenance construction project in Bryan County. This project is the resurfacing of SR 30/US 280. This section of SR 30 needs resurfacing because the existing pavement is deteriora | Pavement Improvement | 07/20/2009 | 09/16/2009 | 05/31/2010 | 2039028.08 | 8.85
2241 | Georgia | WHEELER |  | 1, 12 | M004001 | This project is a maintenance construction project in Montgomery and Wheeler Counties. This project is the resurfacing of SR 30. This section of SR 30 needs resurfacing because the existing pavement | Pavement Improvement | 07/17/2009 | 10/09/2009 | 05/31/2010 | 1904208.01 | 11.52
2242 | Georgia | WHEELER |  | 1 | M004003 | This project is a maintenance construction project in Wheeler County. This project is the resurfacing of SR 126. This section of SR 126 needs resurfacing because the existing pavement is deterioratin | Pavement Improvement | 07/20/2009 | 04/07/2010 | 05/31/2010 | 1795111.71 | 12.09
2243 | Georgia | WILKES |  | 10 | M004006 | This project is a maintenance construction project in Lincoln and Wilkes Counties. This project is the resurfacing of SR 47. This section of SR 47 needs resurfacing because the existing pavement is d | Pavement Improvement | 09/21/2009 | 04/22/2010 | 07/31/2010 | 2458228.56 | 15.69
2244 | Georgia | EMANUEL |  | 12 | M004011 | This project is a maintenance construction project in Emmanuel County. This project is the resurfacing of SR 297. This section of SR 297 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 01/29/2010 | 06/08/2010 | 08/31/2010 | 1869884.29 | 9.93
2245 | Georgia | RICHMOND | AUGUSTA (SC) | 10 | M004012 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 104. This section of SR 104 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 11/23/2009 | 06/02/2010 | 06/30/2010 | 151609.12 | 0.45
2246 | Georgia | RICHMOND | AUGUSTA (SC) | 10 | M004013 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 104 East. This section of SR 104 East needs resurfacing because the existing pavement is d | Pavement Improvement | 11/23/2009 | 06/02/2010 | 06/30/2010 | 144882.58 | 0.44
2247 | Georgia | FRANKLIN |  | 10 | M004014 | This projects provides maintenance construction on I-85 in Franklin and Hart Counties. This project is the milling and resurfacing of I-85/SR 403 from south of SR 17 in Franklin County to the South C | Pavement Improvement | 09/03/2009 | 04/12/2010 | 07/31/2010 | 6116052.98 | 7.12
2248 | Georgia | HALL | GAINESVILLE | 9 | M004015 | This project is a maintenance construction project in Hall County. This project is the removal of selected concrete slabs on SR 365. The reason for removal and replacement of the selected concrete sl | Pavement Improvement | 07/29/2009 | 11/12/2009 | 05/31/2010 | 2273178.2 | 7.97
2249 | Georgia | HOUSTON | WARNER ROBINS | 8 | M004020 | This project is a maintenance construction project in Houston County. This project is the milling and resurfacing of SR 127. This section of SR 127 needs resurfacing because the existing pavement is | Pavement Improvement | 01/19/2010 | 02/19/2010 | 08/31/2010 | 125682.43 | 0.75
2250 | Georgia | HOUSTON | WARNER ROBINS | 8 | M004021 | This project is a maintenance construction project in Houston County. This project is the resurfacing of SR 11 Business. This section of SR 11 Business needs resurfacing because the existing pavement | Pavement Improvement | 08/17/2009 | 04/05/2010 | 04/30/2010 | 850102.43 | 4.5
2251 | Georgia | PULASKI |  | 8 | M004025 | This project is a maintenance construction project in Pulaski County. This project is the resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 11/23/2009 |  | 09/30/2010 | 1689883.06 | 10.58
2252 | Georgia | MERIWETHER |  | 3 | M004027 | This project is a maintenance construction project in Meriwether County. This project is the resurfacing of SR 85. This section of SR 85 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 12/04/2009 | 06/01/2010 | 09/30/2010 | 1712474.03 | 11.1
2253 | Georgia | DOOLY |  | 2 | M004028 | This project is a maintenance construction project in Dooly County. This project is the resurfacing of SR 27. This section of SR 27 needs resurfacing because the existing pavement is deteriorating. S | Pavement Improvement | 11/23/2009 |  | 09/30/2010 | 1863860.66 | 11.76
2254 | Georgia | FAYETTE | ATLANTA | 3 | M004029 | This project is a maintenance construction project in Fayette County. This project is the resurfacing of SR 85. This section of SR 85 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 11/19/2009 | 06/07/2010 | 09/30/2010 | 2125652.41 | 9.88
2255 | Georgia | BIBB | MACON | 8 | M004030 | This project is a maintenance construction project in Bibb County. This project is the milling and resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deter | Pavement Improvement | 11/19/2009 | 05/18/2010 | 08/31/2010 | 1272250 | 5.33
2256 | Georgia | COWETA | ATLANTA | 3 | M004031 | This project is a maintenance construction project in Coweta County. This project is the resurfacing of SR 154. This section of SR 154 needs resurfacing because the existing pavement is deteriorating | Pavement Improvement | 11/24/2009 | 04/30/2010 | 09/30/2010 | 1622334.38 | 8.36
2257 | Georgia | UPSON |  | 3 | M004032 | This project is a maintenance construction project in Lamar and Upson Counties. This project is the resurfacing of SR 36. This section of SR 36 needs resurfacing because the existing pavement is dete | Pavement Improvement | 11/19/2009 |  | 10/07/2010 | 2538255 | 15.03
2258 | Georgia | LAMAR |  | 3, 8 | M004033 | This project is a maintenance construction project in Lamar and Monroe Counties. This project is the resurfacing of SR 7. This section of SR 7 needs resurfacing because the existing pavement is deter | Pavement Improvement | 11/19/2009 | 06/22/2010 | 09/30/2010 | 2262804.83 | 15
2259 | Georgia | SPALDING | ATLANTA | 3 | M004034 | This project is a maintenance construction project in Spalding County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is d | Pavement Improvement | 01/05/2010 |  | 06/30/2010 | 1283058 | 4.09
2260 | Georgia | HOUSTON | WARNER ROBINS | 8 | M004035 | This project is a maintenance construction project in Houston County. This project is the milling and resurfacing of SR 247. This section of SR 247 needs resurfacing because the existing pavement is | Pavement Improvement | 01/19/2010 | 02/19/2010 | 08/31/2010 | 1296822.32 | 8.57
2261 | Georgia | PEACH |  | 2 | M004036 | This project is a maintenance construction project in Peach County. This project is the milling and resurfacing of SR 247 Connector. This section of SR 247 Connector needs resurfacing because the exi | Pavement Improvement | 01/20/2010 | 04/19/2010 | 07/31/2010 | 545808.33 | 3.01
2262 | Georgia | BUTTS |  | 8 | M004037 | This project is a maintenance construction project in Butts County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is dete | Pavement Improvement | 01/05/2010 | 04/19/2010 | 06/30/2010 | 378541.95 | 1.34
2263 | Georgia | JONES |  | 8 | M004038 | This project is a maintenance construction project in Jones County. This project is the resurfacing of SR 44. This section of SR 44 needs resurfacing because the existing pavement is deteriorating. S | Pavement Improvement | 01/21/2010 | 02/26/2010 | 10/31/2010 | 2265748.5 | 14.58
2264 | Georgia | TAYLOR |  | 2 | M004039 | This project is a maintenance construction project in Taylor County. This project is the resurfacing of SR 22. This section of SR 22 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 01/05/2010 | 03/01/2010 | 08/31/2010 | 1023496 | 6.18
2265 | Georgia | BRANTLEY |  | 1 | M004040 | This project is a maintenance construction project in Brantley County. This project is the resurfacing of SR 520. This section of SR 520 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 08/07/2009 | 05/03/2010 | 06/30/2010 | 956222.95 | 3.5
2266 | Georgia | DOUGLAS | ATLANTA | 13 | M004047 | This project is a maintenance construction project in Douglas County. This project is the milling and resurfacing of 1.7 miles of SR 92 from Durelee Lane/City Street 597 to Malone Street/City street | Pavement Improvement | 05/27/2010 |  | 03/31/2011 | 534883.45 | 1.73
2267 | Georgia | GWINNETT | ATLANTA | 7 | M004052 | This project is a maintenance construction project in Gwinnett County. This project is the milling and resurfacing of 5.8 miles of SR 20 from west of Peachtree Industrial Boulevard/County Road 1954 t | Pavement Improvement | 05/21/2010 |  | 03/31/2011 | 1812083.31 | 5.8
2268 | Georgia | WHEELER |  | 1 | M004078 | This is a maintenance construction project in Telfair and Wheeler counties. This project is the resurfacing of SR 19. This section of SR 19 needs resurfacing because the existing pavement is deterior | Pavement Improvement | 03/19/2010 |  | 01/31/2011 | 804196.34 | 19.16
2269 | Georgia | CHEROKEE | ATLANTA | 6 | M004079 | This project is a maintenance construction project in Cherokee County. This project is the resurfacing of 4.7 miles of SR 369 from SR 20 to the Forsyth County line. This section of SR 369 needs res | Pavement Improvement | 05/27/2010 | 06/27/2010 | 03/31/2011 | 1041773.67 | 4.72
2270 | Hawaii | HONOLULU | HONOLULU | 1 | 0001036 | Install and Upgrade traffic signals, including ADA improvements, signs, markings and interconnects (Komo Mai St & Hoomalu St, Waiakamilo Rd & McNeil St, N Beretania St & Aala St, Kiluea Ave, Lanikuha | Safety/Traffic Management | 12/21/2009 | 12/21/2009 | 08/03/2011 | 3670845.6 | 0
2271 | Hawaii | HONOLULU | HONOLULU | 1 | 0001045 | Provide auxiliary power needed to support critical operations during prolonged power outages due to emergencies. | Safety/Traffic Management | 04/30/2010 |  | 07/28/2010 | 270774 | 0
2272 | Hawaii | HONOLULU |  | 1 | 0011250 | Upgrade the Farrington Highway and Makakilo Separation structures over the H-1 freeway to better resist earthquake damage. (Farrington Hwy Separation) | Bridge Improvement | 07/13/2009 | 07/13/2009 | 01/04/2010 | 834579.19 | 0
2273 | Hawaii | HONOLULU | HONOLULU | 1 | 0011262 | Install longitudinal dowels into concrete sections, repair and smoothen concrete pavement at two major locations on the Interstate Route H-1 freeway from MP 2.4 to 3.46 and MP 24.9 to 26.4. | Pavement Improvement | 01/29/2010 | 12/15/2009 | 08/15/2011 | 6350000 | 0
2274 | Hawaii | HAWAII |  | 2 | 0192059 | Remove and dispose of lead-based paint and rust from steel members and paint them. Work also includes repairing/replacing steel members that need repair work. (Kukaiau Bridge MP33.6, Kuwaikahi Bridge | Bridge Improvement | 09/08/2009 | 09/08/2009 | 04/07/2011 | 4301949.3 | 14.2
2275 | Hawaii | MAUI |  | 2 | 0311011 | Extend the life of the pavement and provide a smooth surface in areas that are starting to show distress by removal of the top layer and repaving. | Pavement Improvement | 08/31/2009 | 10/30/2009 | 02/23/2010 | 2979480 | 0
2276 | Hawaii | MAUI |  | 2 | 0321009 | Replace and/or modify the existing bridge girders to provide additional clearance. | Bridge Improvement | 04/02/2010 | 07/12/2010 | 06/02/2010 | 1922456 | 0
2277 | Hawaii | MAUI |  | 2 | 0360010 | Extending the life of the pavement and provide a smooth surface in areas that are starting to show distress by providing a surface seal. | Pavement Improvement | 08/26/2009 | 09/18/2009 | 10/29/2009 | 526005.59 | 3.32
2278 | Hawaii | MAUI |  | 2 | 0460014 | Resurface and reconstruct damaged areas of the pavement. Safety (including guardrail and shoulder improvements) and ADA improvements could be included. | Pavement Improvement | 08/26/2009 | 09/21/2009 | 10/22/2009 | 2688406 | 1.96
2279 | Hawaii | MAUI |  | 2 | 0470006 | Extend the life of the pavement and provide a smooth surface in areas that are starting to show distress by removal of the top pavement layer and repaving. | Pavement Improvement | 08/26/2009 | 10/30/2009 | 10/29/2009 | 1031504.87 | 5.79
2280 | Hawaii | MAUI |  | 2 | 0480003 | Resurface and reconstruct damaged areas of the pavement. Safety (including guardrail and shoulder improvements) on Farrington Avenue (2.44 miles) and Puupeela Avenue (1.21 miles) | Pavement Improvement | 12/10/2009 | 01/04/2010 | 03/16/2009 | 5403802 | 3.65
2281 | Hawaii | KAUAI |  | 2 | 0561052 | Reconstruct weakened pavement areas, cold plane, resurface, adjust utility boxes, & install guardrails, pavement markings, & traffic signs on Kuhio Hwy, Rte 56, between MP 9.0 and MP 10.0. | Pavement Improvement | 07/20/2009 | 07/24/2009 | 10/13/2009 | 1021416 | 1
2282 | Hawaii | KAUAI |  | 2 | 0583001 | Reconstruct weakened pavement areas, remove existing surface and repave, adjust utilities, and install guardrails, pavement markings, and traffic signs on Maalo Road, Route 583 | Pavement Improvement | 07/20/2009 | 07/30/2009 | 09/29/2009 | 729083 | 1
2283 | Hawaii | HONOLULU | HONOLULU | 2 | 0831042 | Replace existing South Punaluu Stream Bridge with new concrete bridge. | Bridge Replacement | 08/26/2009 | 08/26/2009 | 09/01/2011 | 15298509.74 | 0
2284 | Hawaii | HAWAII |  | 2 | 1880001 | Construction of a new 1.6 mile, 2 lane, Ane Keohokalole Highway from Palani Road to Puohulihuli Street, reconstruction of 0.4 miles of the existing roadway from Puohulihuli Street to the West Hawaii C | New Construction | 03/29/2010 | 03/29/2010 | 01/20/2012 | 33815615.08 | 0
2285 | Hawaii | MAUI |  | 2 | 3190001 | Remove the existing pavement surface on Ohukai Road between Hukulii Place and Hoalike Street and install new pavement. Utility covers will be adjusted and the road will be restriped. | Pavement Improvement | 04/12/2010 | 06/07/2010 | 05/21/2010 | 409557.75 | 0
2286 | Hawaii | MAUI |  | 2 | 3405002 | Reconstruction and beautification of Market Street from Kahawai Street to Makuhau Road. Install drainage system, street lights, landscaping and irrigation. | Pavement Improvement | 11/27/2009 | 01/19/2010 | 12/01/2010 | 2421989.55 | 0.17
2287 | Idaho | IDAHO |  | 1 | 4110137 | This project will add a climbing lane up the Whitebird Grade by widening 2.6 miles of US-95 in Idaho County. | Pavement Widening | 03/03/2009 | 03/03/2009 | 09/30/2011 | 4129008 | 2.619
2288 | Idaho | IDAHO |  | 1 | 4110138 | This project includes the complete removal and replacement of pavement and base on 12 miles of US-95 north of Grangeville in Idaho County. | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 3570710 | 9.059
2289 | Idaho | KOOTENAI |  | 1 | 5110137 | This project is to reconstruct the last 3.2 mile segment of US-95 in the City of Hayden in Kootenai County | Pavement Widening | 06/02/2009 | 06/02/2009 | 09/30/2011 | 8983795 | 4.46
2290 | Idaho | BANNOCK | POCATELLO | 2 | 7261100 | This project will repair or replace critical elements of the Custer Street Bridge in Bannock County. Improvements to the bridge deck and girders will extend the surface life of the structure and maint | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 327077 | 0
2291 | Idaho | GEM |  | 1 | 8001100 | This project will reconstruct and overlay 0.1 miles of Main Street and provide handicap accessible sidewalks in the City of Emmett, Gem County. | Pavement Improvement | 09/22/2009 | 09/22/2009 | 09/30/2011 | 627100 | 0.129
2292 | Idaho | BONNER |  | 1 | A001222 | This project will replace the Dover Bridge, an aging and deficient bridge, on US-95 in Bonner County. | New Bridge Construction | 04/22/2009 | 04/22/2009 | 09/30/2011 | 28542897 | 1.66
2293 | Idaho | CLEARWATER |  | 1 | A002352 | This project will widen and pave 4 miles of State Highway 11 in Clearwater County between the cities of Wieppe and Pierce. | Pavement Improvement | 02/28/2010 | 02/28/2010 | 09/30/2011 | 4178863 | 4.114
2294 | Idaho | BANNOCK |  | 2 | A007806 | This project will upgrade 31 miles of Southbound I-15 in Bannock County by laying an asphalt overlay, seal coat, and fog coat over the existing pavement. The project will also include deck repair at f | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 3379041 | 5
2295 | Idaho | BANNOCK |  | 2 | A007840 | This project will upgrade 31 miles of Northbound I-15 in Bannock County by laying an asphalt overlay, seal coat, and fog coat over the existing pavement. The project will also include deck repair at f | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 3640781 | 5
2296 | Idaho | FREMONT |  | 2 | A008624 | This project will add passing lanes in a mountainous area near Henry's Lake by widening 6.4 miles of US-20. | Pavement Widening | 04/22/2009 | 04/22/2009 | 09/30/2011 | 2351499 | 6.37
2297 | Idaho | CANYON, PAYETTE |  | 1 | A008955 | This project will repair the concrete pavement to provide a smooth driving surface on 5 miles of I-84 in Payette and Canyon Counties The project also includes repair and replacement of deficient guar | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 8613611 | 5.03
2298 | Idaho | JEFFERSON |  | 2 | A009387 | This project will reconstruct 1.7 miles of SH-48 in Rigby including new curb & gutter and handicap accessible sidewalks to the high school. | Pavement Widening | 04/22/2009 | 04/22/2009 | 09/30/2011 | 4281084 | 1.71
2299 | Idaho | IDAHO, LEWIS |  | 1 | A009795 | This project will repair the bridge deck and seal the driving surface on the bridge crossing Lawyers Creek on US-95 on the county line between Idaho and Lewis County. | Bridge Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 145748 | 0.173
2300 | Idaho | CLEARWATER |  | 1 | A009796 | This project will repair the bridge deck and preserve the driving surface with skid resistance aggregate and epoxy on State Highway 7 in the City of Orofino in Clearwater County. | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 275369 | 0.049
2301 | Idaho | CLEARWATER |  | 1 | A009797 | This project will repair the bridge deck and seal the driving surface on the bridge crossing the North Fork Clearwater River on State Highway 7 in Clearwater County. | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 63558 | 0
2302 | Idaho | ADA |  | 1 | A010489 | This project consists of constructing continuous sidewalk, to be in complliance with the Americans with Disabilities Act, on the east and west sides of a 0.3 mile section of West 8th Street in the Cit | Transportation Enhancements | 05/28/2009 | 05/28/2009 | 09/30/2011 | 147294 | 0.454
2303 | Idaho | ADA | BOISE CITY | 1 | A010537 | This project takes place at 7 locations throughout Ada County and will overlay a total of 11 miles of existing roadways including handicap accessible sidewalk ramps. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 2573684 | 12.51
2304 | Idaho | BANNOCK | POCATELLO | 2 | A010584 | This project will add one additional lane by widening 1.2 miles of congested urban interstate from the Chubbuck Interchange on I-86 to the Pocatello Creek Interchange on I-15 in Bannock County. | Pavement Improvement | 04/22/2009 | 04/22/2009 | 09/30/2011 | 10138499 | 1.2
2305 | Idaho | TWIN FALLS |  | 2 | A010917 | This project will eliminate traffic congestion in Twin Falls by constructing a new 5.1 mile long, 4-lane US-93 bypass, around the west side of the city. | New Construction | 04/22/2009 | 04/22/2009 | 09/30/2011 | 22045265 | 5.07
2306 | Idaho | LATAH |  | 1 | A011031 | This project will add passing lanes in the Moscow Mountain area by widening 1.3 miles of US 95 in Latah County. | Pavement Widening | 04/22/2009 | 04/22/2009 | 09/30/2011 | 3606204 | 1.338
2307 | Idaho | BINGHAM |  | 2 | A011097 | This project will mill and overlay Bergener, Bridge and Judicial Streets from the Snake river Bridge to Main Street in the City of Blackfoot | Pavement Improvement | 02/17/2010 | 02/17/2010 | 09/30/2011 | 1036492 | 2.286
2308 | Idaho | LATAH |  | 1 | A011558 | This project will add a thin lift overlay on 6.2 miles of State Highway 9 in Latah County. | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 1636769 | 6.222
2309 | Idaho | CANYON |  | 1 | A011584 | This project is to realign and reconstruct the west leg of the intersection of Franklin and 21st Avenue in the City of Caldwell in Canyon County. The project includes curb, gutter and handicap accecs | Pavement Widening | 11/30/2009 | 11/30/2009 | 09/30/2011 | 1273513 | 0.132
2310 | Idaho | BONNEVILLE, JEFFERSON |  | 2 | A011673 | This project will improve user operating conditions on an 8.5 mile segment of I-15 in Bonneville County by leveling the pavement, adding a plantmix overlay, and finishing with a seal coat and fog coat | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/30/2011 | 1615624 | 8.475
2311 | Idaho | KOOTENAI | COEUR D ALENE | 1 | A011867 | This project will widen and completely reconstruct 0.5 miles of Hanley Avenue between Government Way and a new roundabout on 4th Street in the City of Dalton Gardens in Kootenai County. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 499706 | 0.49
2312 | Idaho | NEZ PERCE | LEWISTON | 1 | A011917 | This project will seal coat the existing pavement and provide a skid resistant surface on 14 miles of local streets throughout the City of Lewiston. | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 696964 | 0
2313 | Idaho | BANNOCK | POCATELLO | 2 | A011918 | This project will remove and replace existing bridge joints on Gould Street Bridge in the City of Pocatello and improve pavement markings along the roadway. | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 347185 | 0.229
2314 | Idaho | STATEWIDE |  | 2 | A011919 | This project funded the purchase of one van for public transportation in Pocatello. | Other | 11/30/2009 | 11/30/2009 | 09/30/2011 | 24000 | 0
2315 | Idaho | BONNEVILLE | IDAHO FALLS | 2 | A011920 | This project will seal coat the existing pavement and provide a skid resistant surface on 5.6 miles of local streets throughout Idaho Falls. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 09/30/2011 | 721474 | 5.598
2316 | Idaho | ADA |  | 1 | A011922 | This project takes place at 16 locations throughout Ada County and will overlay a total of 20 miles of existing roadways to improve operating conditions, preserve structural capacity, and extend the u | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 3067819 | 20.38
2317 | Idaho | ADA |  | 1 | A011924 | This project will improve the network for pedestrians throughout Ada County by improving existing sidewalks, pedestrian ramps, and curb & gutter sections at up to 122 intersections within the cities o | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 374109 | 0
2318 | Idaho | ADA | BOISE CITY | 2 | A011925 | This project will construct a pedestrian bridge across the Boise River east of Veterans Memorial Parkway. | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 581560 | 0
2319 | Idaho | ADA | BOISE CITY | 2 | A011926 | This project will improve the network for pedestrians within Downtown Boise by improving existing sidewalks, pedestrian ramps, and curb and gutter sections at up to 49 intersections so they are in con | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 480288 | 0
2320 | Idaho | ADA | BOISE CITY | 1 | A011932 | This project will provde aesthetically pleasing landscaping to the newly constructed Ten Mile Interchange on I-84 in Canyon County. | Transportation Enhancements | 06/16/2009 | 06/16/2009 | 09/30/2011 | 862962 | 1
2321 | Idaho | BOUNDARY |  | 1 | A011935 | This project will overlay 3 miles of Deep Creek Loop, a two lane roadway, in Boundary County to provide a safer traveling surface and prolong the life of the asphalt. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 498000 | 10.557
2322 | Idaho | SHOSHONE |  | 1 | A011936 | This project will overlay the existing pavement to improve roadway surface smoothness and will provide stormwater drainage pathways on 0.8 mile of Nine Mile Road in Shoshone County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 387140 | 2.273
2323 | Idaho | BENEWAH |  | 1 | A011937 | This project will pave the existing gravel roadway on 1.3 miles of the Benewah Creek Road corridor in Benewah County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 389163 | 1.64
2324 | Idaho | SHOSHONE |  | 1 | A011938 | This project will include repair of the existing pavement with a new pavement overlay on a 0.5 mile long segment in the City of Wallace in Shoshone County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 259369 | 0.912
2325 | Idaho | CLEARWATER |  | 1 | A011939 | This project includes a pavement seal coat on 14 miles of Cavendish Road in Clearwater County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 485989 | 14.345
2326 | Idaho | CLEARWATER |  | 1 | A011940 | This project will pave on top of existing gravel roadway on 0.8 miles of Musselshell Road in Clearwater County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 496343 | 1.5
2327 | Idaho | CLEARWATER |  | 1 | A011941 | This project will increase the life of the pavement on 2.6 miles of roadway in the City of Orofino in Clearwater County by adding asphalt leveling and a seal coat to provide skid resistance. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 255850 | 6.3
2328 | Idaho | IDAHO |  | 1 | A011942 | This project will remove and replace the pavement and aggregate base on 0.7 mile of local road in the City of Cottonwood, Idaho County, to improve the driving surface and extend the life of the pavem | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 599573 | 0.722
2329 | Idaho | PAYETTE |  | 1 | A011943 | This project will improve traffic flow and pedestrian safety near local schools in the City of Fruitland in Payette County with a pavement overlay, installing handicap accessible sidewalks, and improv | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 454325 | 1.108
2330 | Idaho | CANYON |  | 1 | A011944 | This project in Canyon County will repair the existing pavement and add a new asphalt overlay on a 1.5 mile segment of Notus Road from State Highway 19 to Red Top Road. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 514147 | 2
2331 | Idaho | GEM |  | 1 | A011945 | This project consists of an asphalt overlay on a 4 mile segment of the Ola Highway in Gem County to increase pavement longevity, improve the ride quality, and provide a safer road surface for the trav | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 526147 | 7
2332 | Idaho | ADAMS |  | 1 | A011946 | This project will overlay 1.6 miles and sealcoat 1.2 miles of Indian Valley Road in Adams County to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 519047 | 7.07
2333 | Idaho | LINCOLN |  | 2 | A011947 | This project will overlay 1.7 miles and sealcoat 2.9 miles of 600 West Road in Lincoln County to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 537112 | 4.561
2334 | Idaho | CASSIA |  | 2 | A011948 | This project will remove and recycle the existing pavement and gravel base on 1.2 miles of Old Highway 81 South Road in Cassia County to provide a safe and durable driving surface. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 534583 | 3.468
2335 | Idaho | TWIN FALLS |  | 2 | A011949 | This project will improve 0.2 mile of Center Street in the City of Kimberly, Twin Falls County, by removing the deteriorated roadway, constructing a new base, and laying new pavement. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 360354 | 0.37
2336 | Idaho | CAMAS |  | 2 | A011950 | This project in the City of Fairfield, Camas County, will repair areas of distressed pavement, install an overlay, and perform minor storm drainage improvements at intersections along 0.6 mile of Sold | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 472440 | 0.61
2337 | Idaho | BANNOCK | POCATELLO | 2 | A011951 | This project will remove and recycle the existing pavement and gravel base on a 1.2 mile segment of Mink Creek Road in Bannock County and will include both minor widening and an overlay. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 528990 | 1.933
2338 | Idaho | CARIBOU |  | 2 | A011952 | This project will improve the roadway and increase safety by adding new pedestrian crossing lights, replacing drainage structures, and adding a pavement overlay on 0.4 mile of local road in the City o | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 357615 | 0.426
2339 | Idaho | POWER |  | 2 | A011953 | This project will remove and recycle the existing pavement and gravel base on a 1 mile section of South Pleasant Valley Road in Power County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 526136 | 2.029
2340 | Idaho | BANNOCK |  | 2 | A011954 | This project will repair and overlay 0.4 mile of local roadway pavement and provide a new pedestrian crossing with crossing lights to improve user operating conditions on East Main Street in the City | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 275235 | 0.419
2341 | Idaho | FREMONT |  | 2 | A011955 | This project will seal coat the existing pavement and provide a skid resistant surface on a 4.5 mile segment of the Teton Highway in Fremont County. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 280879 | 4.543
2342 | Idaho | CUSTER |  | 2 | A011956 | This project in Custor County will repair a 3.1 mile segment of Trail Creek Road and extend the pavement life by adding a thin overlay to the pavement. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 620677 | 2
2343 | Idaho | FREMONT |  | 2 | A011957 | This project will repair and overlay 0.5 mile of pavement on Main Street in City of St.Anthony, Fremont County and will include minor drainage improvements, replacement of traffic signal detection loo | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 613643 | 1.41
2344 | Idaho | CLARK |  | 2 | A011958 | This project will replace the asphalt gutter with a concrete gutter and will overlay the roadway to improve user operating conditions on a 0.5 mile segment of Main Street in the City of Dubois, Clark | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/30/2011 | 411206 | 0.865
2345 | Idaho | STATEWIDE |  | 2 | A011960 | This project will provide for curation and management of artifacts including consolidation of the Hatwaii archaeological collection. This project will develop public outreach on archaeological displa | Transportation Enhancements | 06/16/2009 | 06/16/2009 | 09/30/2011 | 162960 | 0
2346 | Idaho | BOISE |  | 1 | A011961 | This project is to construct a wildlife/game crossing under US-21 in Boise County. | New Bridge Construction | 06/16/2009 | 06/16/2009 | 09/30/2011 | 1066088 | 0
2347 | Idaho | FREMONT |  | 2 | A011963 | This project is a study to determine a solution to numerous wildlife/vehicle collisions on US-20 in Fremont County. | Other | 10/28/2009 | 10/28/2009 | 09/30/2011 | 624680 | 20
2348 | Idaho | STATEWIDE |  | 2 | A011964 | This project will construct 940 handicap ramps in Districts 1, 2, & 3 in accordance with the requirements of the Americans with Disabilities Act. It will be split into five separate projects for cons | Other | 06/16/2009 | 06/16/2009 | 09/30/2011 | 198811 | 0
2349 | Idaho | KOOTENAI |  | 2 | A011976 | This project is to repair 10 structures on Interstate 90 between Post Falls and the Washington State border in Kootenai County. These structures will have the top of the deck removed and replaced with | Bridge Improvement | 11/30/2009 | 11/30/2009 | 09/30/2011 | 4129411 | 4.6
2350 | Idaho | KOOTENAI |  | 1 | A011979 | This project will construct 89 handicap ramps in the Coeur D'Alene area of District 1, in Benewah, Kootenai and Shoshone Counties, in accordance with the requirements of the Americans with Disabilitie | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 608508 | 0
2351 | Idaho | BONNER |  | 1 | A011980 | This project will construct 90 handicap ramps in the Sandpoint area of District 1, in Bonner County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 775240 | 0
2352 | Idaho | LATAH |  | 1 | A011981 | This project will construct 132 handicap ramps in the northern area of District 2, in Latah County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 986942 | 0
2353 | Idaho | IDAHO |  | 1 | A011982 | This project will construct 80 handicap ramps in the southern area of District 2, in Idaho County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 539505 | 0
2354 | Idaho | CANYON, GEM, PAYETTE, ADA |  | 1,2 | A011983 | This project will construct 127 handicap ramps in District 3, in Canyon, Gem, & Payette Counties, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 11/30/2009 | 11/30/2009 | 09/30/2011 | 458018 | 0
2355 | Idaho | KOOTENAI, SHOSHONE |  | 1 | A011986 | This project is to repair 9 structures on Interstate 90 between Post Falls and the Montana State border in Kootenai & Shoshone Counties. These structures will have the top of the deck removed and repl | Bridge Improvement | 02/03/2010 | 02/03/2010 | 09/30/2011 | 4127214 | 30.783
2356 | Idaho | STATEWIDE |  | 2 | A012206 | This project will construct handicap ramps in Districts 5 and 6 in accordance with the requirements of the Americans with Disabilities Act. It will be split into two separate projects for constructi | Other | 02/03/2010 | 02/03/2010 | 09/30/2011 | 157528 | 0
2357 | Idaho | ADA | BOISE CITY | 1 | A012207 | This project will construct 248 handicap ramps in Ada County in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 02/28/2010 | 02/28/2010 | 09/30/2011 | 730250 | 0
2358 | Idaho | ADA | BOISE CITY | 1 | A012208 | This project takes place at 9 locations throughout Ada County and will overlay a total of 7 miles of existing roadways to improve operating conditions, preserve structural capacity, and extend the use | Other | 02/28/2010 | 02/28/2010 | 09/30/2011 | 1330271 | 7.19
2359 | Idaho | ADA | BOISE CITY | 2 | A012209 | This project will improve the network for pedestrians and people with disabilities in Downtown Boise by improving existing sidewalks and 55 pedestrian ramps at up to 14 intersections so they are in co | Transportation Enhancements | 02/03/2010 | 02/03/2010 | 09/30/2011 | 179400 | 0
2360 | Idaho | STATEWIDE |  | 2 | A012218 | This project will construct 68 handicap ramps in the Cities of Rigby and Salmon of District 6 in accordance with the requirements of the Americans with Disabilities Act in Lemhi and Jefferson County. | Transportation Enhancements | 05/24/2010 | 05/24/2010 | 09/30/2011 | 528616 | 0
2361 | Idaho | BONNEVILLE | IDAHO FALLS | 2 | A012227 | This project will seal coat the existing pavement and provide a skid resistant surface on 4.9 miles of local streets throughout Idaho Falls. | Pavement Improvement | 02/03/2010 | 02/03/2010 | 09/30/2011 | 535404 | 4.732
2362 | Idaho | CANYON, ADA |  | 1 | A012260 | This project provides funding for a statewide training program for returning disabled veterans. Vetrans will be trained to drive trucks and obtain a CDL license or become a certified flagger with mar | Other | 07/01/2010 | 07/01/2010 | 06/30/2011 | 99330 | 0
2363 | Idaho | STATEWIDE |  | 1 | A012262 | This project provides funding for construction safety training for minority, women, Native American and other disadvantaged individuals working on transportation related construction projects in Idaho | Other | 04/20/2010 | 04/20/2010 | 09/30/2010 | 55448 | 0
2364 | Idaho | ADA | BOISE CITY | 2 | C009818 | This project, in the City of Boise, the existing I-84 Vista Interchange will be reconstructed into a Single Point Urban Interchange. | Pavement Widening | 04/22/2009 | 04/22/2009 | 09/30/2011 | 24029318 | 1.2
2365 | Illinois | WHITESIDE |  | 14 | 000S617 | This project will extend the pavement life by resurfacing a section of US 30 near the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 05/11/2009 | 05/26/2009 | 08/30/2009 | 782424.21 | 2.33
2366 | Illinois | WINNEBAGO | ROCKFORD | 16 | 000S618 | This project will extend the pavement life by resurfacing a section of US 20 Business Route in the city of Freeport (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/26/2009 | 10/30/2009 | 389189.69 | 1.35
2367 | Illinois | HENRY |  | 14 | 000S619 | This project will extend the pavement life by resurfacing 12 miles of US 6 between the cities of Geneseo and Atkinson (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/26/2009 | 10/30/2009 | 2817253.31 | 29.28
2368 | Illinois | STEPHENSON |  | 16 | 000S620 | This project will extend the pavement life by resurfacing sections of US 20 and IL 26 near the city of Freeport (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 05/26/2009 | 09/30/2009 | 1837174.95 | 6.42
2369 | Illinois | WINNEBAGO | ROCKFORD | 16 | 000S628 | This project will extend the pavement life by resurfacing a section of IL 2 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 04/30/2009 | 05/26/2009 | 10/30/2009 | 1105192.12 | 16.94
2370 | Illinois | STATEWIDE |  | 15,17,18,19 | 000S630 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 7 (Southeast Illinois). | Safety/Traffic Management | 04/28/2009 | 06/22/2009 | 12/30/2009 | 745277.15 | 0
2371 | Illinois | STATEWIDE |  | 1,2,3,4,5,6,7,8,9,10,11,13,14 | 000S631 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 1 (Northeast Illinois). | Safety/Traffic Management | 04/23/2009 | 05/12/2009 | 07/30/2010 | 868438.5 | 0
2372 | Illinois | STATEWIDE |  | 11,14,15 | 000S633 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 3 (East-Central Illinois). | Safety/Traffic Management | 07/30/2009 | 08/10/2009 | 07/30/2010 | 520517.77 | 0
2373 | Illinois | STATEWIDE |  | 17,18 | 000S634 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout District 4 (West-Central Illinois) | Safety/Traffic Management | 05/06/2009 | 05/16/2009 | 07/30/2010 | 539505.75 | 0
2374 | Illinois | STATEWIDE |  | 15,17,18,19 | 000S637 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 7 (Southeast Illinois). | Safety/Traffic Management | 05/06/2009 | 07/28/2009 | 07/30/2010 | 343186.98 | 0
2375 | Illinois | STATEWIDE |  | 12,15,19 | 000S639 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 9 (Southern Illinois). | Safety/Traffic Management | 05/06/2009 | 08/31/2009 | 07/30/2010 | 477059.89 | 0
2376 | Illinois | STATEWIDE |  | 1,2,3,4,5,6,7,8,9,10,11,13,14 | 000S640 | This project consists of improving safety by upgrading guardrail terminals to current standard throughout IDOT District 1 (Northeast Illinois). | Safety/Traffic Management | 04/30/2009 | 06/23/2009 | 11/30/2009 | 817169.16 | 0
2377 | Illinois | STATEWIDE |  | 17,18 | 000S644 | This project consists of improving safety by upgrading guardrail terminals to current standard throughout District 4 (West-Central Illinois) | Safety/Traffic Management | 04/28/2009 | 05/08/2009 | 12/30/2009 | 721808.89 | 0
2378 | Illinois | STATEWIDE |  | 12,15,19 | 000S645 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 9 (Southern Illinois). | Safety/Traffic Management | 04/28/2009 | 05/21/2009 | 12/30/2009 | 683695.91 | 0
2379 | Illinois | MONTGOMERY |  | 19 | 000S646 | This project will extend the pavement life by resurfacing various streets in Nokomis, Il in Montgomery County (West-Central Illinois). | Pavement Improvement | 04/30/2009 | 05/03/2010 | 07/30/2010 | 943914.97 | 3.27
2380 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 000S647 | This project will extend the pavement life by resurfacing DesPlaines Avenue from 26th to 31st Street in the Village of Riverside in Cook County. (Northeastern Illinois). | Pavement Improvement | 04/28/2009 | 05/18/2009 | 08/30/2009 | 345016.9 | 0.51
2381 | Illinois | STATEWIDE |  | 11,14,15 | 000S648 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 3 (East-Central Illinois). | Safety/Traffic Management | 07/30/2009 | 08/24/2009 | 12/30/2009 | 1031644.46 | 0
2382 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,2,3,13 | 000S649 | This project will extend the pavement life by resurfacing numerous roadway sections in Southern Cook County (Northeastern Illinois) | Pavement Improvement | 06/01/2009 | 06/23/2009 | 09/30/2009 | 911289.06 | 0
2383 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 3,4,5,7 | 000S650 | This project will extend the pavement life by resurfacing numerous roadway sections in Central Cook County (Northeastern Illinois) | Pavement Improvement | 06/01/2009 | 06/29/2009 | 11/30/2009 | 1573740.6 | 0
2384 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 6,8,9,10 | 000S651 | This project will extend the pavement life by resurfacing numerous roadway sections in Northern Cook County (Northeastern Illinois) | Pavement Improvement | 06/01/2009 | 06/05/2009 | 10/30/2009 | 1022357.4 | 0
2385 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 2,11,13 | 000S652 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Kane County (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/22/2009 | 09/30/2009 | 453708.18 | 0
2386 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 000S653 | This project will extend the pavement life by resurfacing numerous roadway sections in Will County (Northeastern Illinois). | Pavement Improvement | 06/02/2009 | 06/15/2009 | 10/30/2009 | 1397082.45 | 0
2387 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 6,13,14 | 000S654 | This project will extend the pavement life by resurfacing numerous roadway sections in DuPage County (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/15/2009 | 11/30/2009 | 2302963.54 | 0
2388 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 8,16 | 000S655 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout McHenry County (Northeastern Illinois). | Pavement Improvement | 06/02/2009 | 06/09/2009 | 09/30/2009 | 623454.17 | 0
2389 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 8,10 | 000S656 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Lake County (Northeastern Illinois). | Pavement Improvement | 06/02/2009 | 06/12/2009 | 11/30/2009 | 2512642.94 | 0
2390 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 8,10 | 000S657 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Lake County (Northeastern Illinois). | Pavement Improvement | 07/30/2009 | 08/12/2009 | 11/30/2009 | 2010293.64 | 0
2391 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 000S658 | This project will substantially improve the roadway, traffic congestion and safety by constructing a new interchange to replace the old interchange in Troy, Illinois (Southwest Illinois) | Pavement Improvement | 08/05/2009 | 08/17/2009 | 07/30/2012 | 24594122.19 | 0.01
2392 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 000S659 | This project will improve safety and operations by removal of old ramp structures and extention of existing ramps and other roadway improvements on I-94/90 from Hubbard's Cave to I-290 in the City of | Pavement Improvement | 05/20/2009 | 06/15/2009 | 11/30/2009 | 13055933.04 | 1.18
2393 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 000S660 | This project will extend the pavement life by milling, patching and resurfacing 2 miles of Dempster Street from US 41 to McCormick Blvd in Skokie and Chicago Avenue to Judson Avenue in Evanston in Coo | Pavement Improvement | 06/01/2009 | 06/14/2009 | 11/30/2009 | 1564125.3 | 2.07
2394 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 000S662 | This project will extend the pavement life by resurfacing 3.04 miles of Touhy Ave from Northwest highway to Central Avenue in the Village of Niles and Cities of Chicago and Park Ridge in Cook County, | Pavement Improvement | 06/01/2009 | 06/12/2009 | 09/30/2009 | 2188300.77 | 3.18
2395 | Illinois | MCDONOUGH |  | 17 | 000S680 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on CH 23 over Jack Creek at Toulon which is approximately 30 miles northwest of the City of | Pavement Improvement | 07/30/2009 | 08/10/2009 | 11/30/2009 | 1873371.59 | 10.57
2396 | Illinois | HENDERSON |  | 17 | 000S681 | This project will extend the pavement life by providing for surface improvements at 2 locations on US Route 34 near the City of Gulfport and the Mississippi River (West-Central Illinois) | Pavement Improvement | 08/11/2009 | 08/13/2009 | 09/30/2009 | 616368.16 | 4.38
2397 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 000S685 | This project will extend the pavement life by resurfacing 3.0 miles on US Route 6 in Channahon and Rockdale (Northeast Illinois). | Pavement Improvement | 10/29/2009 | 04/30/2010 | 08/30/2010 | 1807031.55 | 3.94
2398 | Illinois | MARSHALL |  | 18 | 000S802 | This project will extend the pavement life by resurfacing and adding safety improvements to 15 miles of Illinois Routes 89 and 17 in Marshall and Putnam Counties (West-Central Illinois). | Pavement Improvement | 04/21/2010 | 04/22/2010 | 10/30/2010 | 700000 | 13.93
2399 | Illinois | STATEWIDE |  | 18 | 0011106 | On The Job Training/ Supportive Services Program | Other | 05/01/2010 | 05/03/2010 | 06/30/2011 | 1189635 | 0
2400 | Illinois | FULTON |  | 17 | 0022070 | This project will extend the pavement life by providing for 7.21 miles pavement repairs and resurfacing on Illinois Route 78 approximately 20 miles west of Peoria (West-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/11/2009 | 09/30/2009 | 2133958.28 | 7.54
2401 | Illinois | PEORIA |  | 18 | 0022071 | This project will extend the pavement life by providing for 3.06 miles of pavement repairs and resurfacing on Ilinois Route 78 west of Peoria (West-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/08/2009 | 08/30/2009 | 1022359.09 | 3.06
2402 | Illinois | FULTON |  | 17 | 0022072 | This project will extend the pavement life by providing for 9.2 miles of pavement repairs and resurfacing on Illinois Route 78 aproximately 20 miles west of Peoria (West-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/01/2009 | 09/30/2009 | 1722288.36 | 9.19
2403 | Illinois | STARK |  | 18 | 0022075 | This project will extend the pavement life by resurfacing 9.7 miles of Illinois Route 78 approximately 20 miles northwest of Peoria (West-Central Illinois) | Pavement Improvement | 07/30/2009 | 08/03/2009 | 12/30/2009 | 2461526.75 | 19.36
2404 | Illinois | CLINTON |  | 19 | 0027038 | This project will substantially improve the roadway by constructing a new bridge over Lost Creek on Sand Ridge Road near Ferrin, Illinois (Southwest Illinois) | Bridge Replacement | 07/27/2009 | 09/14/2009 | 10/30/2009 | 50000 | 0.2
2405 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0031030 | This project will extend the bridge life by milling, resurfacing and repairing the bridge deck and making other roadway improvements on Winnetka Rd. over the North branch of the Chicago River in Cook | Bridge Improvement | 03/16/2010 | 04/02/2010 | 10/30/2010 | 213277 | 0.03
2406 | Illinois | BOONE |  | 16 | 0032106 | This project will extend the pavement life by resurfacing sections of Poplar Grove Road in Boone County (Northwest Illinois). | Pavement Improvement | 09/15/2009 | 10/07/2009 | 10/30/2009 | 398954 | 10.78
2407 | Illinois | DE WITT |  | 15 | 0039027 | This project will enhance safety by upgrading signs to current standards throughout DeWitt County (East-Central Illinois). | Safety/Traffic Management | 06/01/2010 | 06/01/2010 | 07/30/2011 | 49556 | 0
2408 | Illinois | DE WITT |  | 15 | 0039028 | Preliminary engineering for the prepaation of a sign inventory in DeWitt county, 09-00000-00-SG | Other | 08/10/2009 | 08/10/2009 | 10/30/2010 | 32550 | 0
2409 | Illinois | DOUGLAS |  | 15 | 0041093 | This project consists of providing engineering design for a future township bridge improvement over the Kaskaskia River (East-Central Illinois). | Other | 09/30/2009 | 11/01/2009 | 12/30/2010 | 63525 | 0.01
2410 | Illinois | DOUGLAS |  | 15 | 0041094 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE OVER SCATTERING FORK, SECTION 07-03122-01-EG | Other | 09/30/2009 | 10/01/2009 | 07/30/2010 | 20000 | 0.02
2411 | Illinois | DOUGLAS |  | 15 | 0041095 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE OVER THE KASKASKIA RIVER NEAR FLICKLIN, SECTION 09-05123-01EG | Other | 09/30/2009 | 11/01/2009 | 12/30/2010 | 107005 | 0
2412 | Illinois | DOUGLAS |  | 15 | 0041096 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE CARRYING TR 218 OVER BRUSHY FORK, DOUGLAS COUNTY SECTION 07-08119-01-EG | Other | 09/30/2009 | 10/05/2009 | 10/30/2010 | 52019 | 0.03
2413 | Illinois | DOUGLAS |  | 15 | 0041097 | This project will enhance safety by upgrading signs to current standards throughout Douglas County (East-Central Illinois). | Safety/Traffic Management | 04/15/2010 | 04/15/2010 | 04/30/2011 | 72420 | 0
2414 | Illinois | KANKAKEE |  | 11 | 0041130 | This project will extend the pavement life by resurfacing 7.9 miles of IL 17 in western Kankakee County (East-Central Illinois). | Pavement Improvement | 04/23/2009 | 05/26/2009 | 08/30/2009 | 1744277.41 | 8.1
2415 | Illinois | EDWARDS |  | 19 | 0047032 | This project will substantially improve the roadway by constructing a new bridge over Bear Creek on County Highway 4 near Samsville in Edwards County (Southeast Illinois). | Bridge Replacement | 03/01/2010 | 04/30/2010 | 06/30/2010 | 165067 | 0.01
2416 | Illinois | HAMILTON |  | 19 | 0065051 | This project will extend the pavement life by resurfacing numerous roadway sections in Whtie County. (Southern Illinois) | Pavement Improvement | 02/22/2010 | 05/01/2010 | 05/30/2010 | 264944 | 0.01
2417 | Illinois | JO DAVIESS |  | 16 | 0065104 | This project will extend the pavement life by resurfacing 5.3 miles on Stagecoach Trail near the city of Warren (Northwest Illinois). | Pavement Improvement | 10/27/2009 | 05/17/2010 | 12/30/2010 | 375743 | 9.34
2418 | Illinois | SANGAMON |  | 18 | 0067079 | This project will extend the pavement life by milling and resurfacing a portion of Jefferson Street in the City of Springfield (West-Central Illinois). | Pavement Improvement | 04/23/2009 | 04/30/2009 | 09/30/2009 | 836639.67 | 2.88
2419 | Illinois | CASS |  | 18 | 0067080 | This project will substantially improve the roadway by reconstructing two box culverts and repairing another one on Illinois Route 125 near Bluff Springs (West-Central Illinois) | Pavement Improvement | 05/04/2009 | 05/05/2009 | 05/30/2010 | 2135489.09 | 2.7
2420 | Illinois | IROQUOIS |  | 15 | 0071115 | This project will extend pavement life by resurfacing 4.2 miles of IL 54 near the city of Thawville (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 07/20/2009 | 10/30/2009 | 880320.15 | 4.57
2421 | Illinois | LOGAN |  | 18 | 0071116 | This project will extend the pavement life by resurfacing a portion of Illinois Route 54 northeast of Mt. Pulaski in Logan County (West-Central Illinois). | Pavement Improvement | 04/23/2009 | 05/14/2009 | 09/30/2009 | 1442589.51 | 6.89
2422 | Illinois | CARROLL |  | 16 | 0077103 | This project will extend the pavement life by resurfacing sections of County Highways 4 and 25 in Carroll County (Northwest Illinois). | Pavement Improvement | 09/11/2009 | 09/24/2009 | 10/30/2009 | 309728 | 20.56
2423 | Illinois | JEFFERSON |  | 19 | 0081059 | This project will extend the pavement life by resurfacing 1.32 miles of County Highway 42/43 in Jefferson County.(Southern Illinois) | Pavement Improvement | 03/01/2010 | 05/03/2010 | 06/30/2010 | 413197 | 1.24
2424 | Illinois | JERSEY |  | 17 | 0083047 | This project will improve safety by replacing an existing bridge over Otter Creek near Fieldon, Illinois (Southwest Illinois) | Bridge Replacement | 03/01/2010 | 06/01/2010 | 07/30/2010 | 240596 | 0.01
2425 | Illinois | EDGAR |  | 15 | 0091071 | This project will extend the pavement life by resurfacing 4.5 miles of Illinois 16 approximately 25 miles southeast of Champaign (East-Central Illinois) | Pavement Improvement | 12/08/2009 | 03/30/2010 | 08/30/2010 | 2074958.81 | 29.06
2426 | Illinois | KNOX |  | 17 | 0095126 | This project will substantially improve the roadway by constructing a new bridge over Finch Creek on County Highway 16 east of Galesburg (West-Central Illinois) | Bridge Replacement | 08/03/2009 | 08/17/2009 | 11/30/2009 | 255000 | 0.02
2427 | Illinois | KNOX |  | 17 | 0095133 | This project will substantially improve the roadway by constructing a new bridge over Swab Run Creek in eastern Knox County, approximately 20 miles southeast of Galesburg (West-Central Illinois) | Bridge Replacement | 12/17/2009 | 05/17/2010 | 06/30/2010 | 141848 | 0.01
2428 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 00D1691 | This project will substantially improve mobility by constructing a new prefabricated pedestrian bridge over Buffalo Creek & construct a 0.14 mile shared use path between Dundee Road & Glendale Rd in t | Transportation Enhancements | 09/15/2009 | 10/05/2009 | 05/30/2010 | 271795 | 0
2429 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 00D1701 | This project will provide for pedestrain safety by improving the sidewalk, pedestrain lighting and signage adjacent to Roosevelt Road in Westchester, (Northeastern Illinois) | Transportation Enhancements | 09/10/2009 | 09/17/2009 | 05/30/2010 | 268960 | 0.7
2430 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 00D1710 | This project will provide for pedestrian safety by constructing a new Pedestrain path from Three Oaks Road through Cary Grove Park to District 26 Cary Jr High School (Northeast Illinois). | Transportation Enhancements | 01/26/2010 | 04/01/2010 | 09/30/2010 | 623500 | 0
2431 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 9 | 00D1779 | This project will provide for pedestrian safety by removing an existing pedestrian path and constructing a new path with lighting and landscaping from Lee St. north for 1.08 miles in the Evanston Lake | Transportation Enhancements | 06/29/2010 |  | 06/30/2010 | 598867 | 0
2432 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 9 | 00D1795 | This project consists of a safety and traffic enhancement by installing 1.63 miles of new lighting and streetscape improvements on Miner Street, Oakton Street and Lee Street corridors in Des Plaines, | Transportation Enhancements | 12/10/2009 | 03/16/2010 | 10/30/2010 | 800000 | 0
2433 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 00D1809 | This project will enhance the roadway by installing landscape improvements of select medians, embankments, planting of trees, shrubs, and flowers, on 4.1 miles of Harlem Avenue from 191st St. to 159th | Transportation Enhancements | 03/01/2010 | 03/01/2010 | 08/30/2010 | 851389 | 0.6
2434 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 00D1810 | This project will substantially improve the roadway by reconstructing a section IL 137 by providing new asphalt pavement and other roadway improvements in Winthrop Harbor. (Northeast Illinois) | Transportation Enhancements | 03/23/2010 | 04/05/2010 | 06/30/2011 | 2008500 | 0.13
2435 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 00D2131 | This project consists of a substantial transportation improvement by construction of a new concrete bicycle and pedestrian path and other associated improvements between the cities of Rock Island and | Transportation Enhancements | 11/18/2009 | 05/10/2010 | 05/30/2009 | 446000 | 0
2436 | Illinois | STEPHENSON |  | 16 | 00D2139 | This project will substantially improve pedestrian safety by constructing a new pedestrian bridge over the Pecatonic River in the city of Freeport and repair of a timber bridge in Stephenson County (N | Transportation Enhancements | 12/22/2009 | 03/01/2010 | 10/30/2011 | 1928000 | 0
2437 | Illinois | LEE |  | 14 | 00D2140 | This project will improve pedestrian and bicycle safety by constructing a multi-use path, sidewalks and other related items at Howell Park in the city of Dixon (Northwest Illinois). | Transportation Enhancements | 04/07/2010 | 04/07/2010 | 08/30/2010 | 341481 | 0
2438 | Illinois | LA SALLE |  | 11 | 00D3058 | This project will substantially improve pedestrian trafficabilty by constructing sidewalk and two bridges near Riverfront Park in the city of Marseilles (East-Central Illinois). | Transportation Enhancements | 06/01/2010 | 07/06/2010 | 06/30/2010 | 207303 | 0
2439 | Illinois | GRUNDY |  | 11 | 00D3059 | This project will improve safety by installing lighting and signing along IL 113 in the village of Diamond (East-Central Illinois). | Transportation Enhancements | 05/12/2010 |  | 08/30/2010 | 301413 | 1
2440 | Illinois | STARK |  | 18 | 00D4102 | This project will enhance safety and aesthetics by reconstructing sidewalks and installing lighting at the instersection of Illinois Routes 17 and 91 in Stark County (West-Central Illinois). | Transportation Enhancements | 05/04/2010 | 07/19/2010 | 09/30/2010 | 208400 | 0.23
2441 | Illinois | PEORIA | PEORIA | 18 | 00D4103 | This project will enhance pedestrian safety by constructing sidewalks and replacing curb and gutter along 0.75 mile of Pfeiffer Road in Bartonville, Peoria County (West-Central Illinois). | Transportation Enhancements | 05/18/2010 | 05/28/2010 | 08/30/2010 | 478925 | 0.75
2442 | Illinois | MCLEAN |  | 15 | 00D5090 | This project will provide for pedestrian and bicycle safety by constructing a 4-mile multi-use path on the southwest side of Bloomington (Central Illinois). | Transportation Enhancements | 05/18/2010 | 05/20/2010 | 08/30/2010 | 1440000 | 0
2443 | Illinois | SANGAMON |  | 18 | 00D6089 | This project consists of substantial transportation improvement by constructing new pavement with concrete pavers, new sidewalks, decorative lighting, and planting beds on Capital Avenue between 5th | Transportation Enhancements | 03/18/2010 | 03/18/2010 | 08/30/2010 | 1796318 | 0.16
2444 | Illinois | SANGAMON |  | 18 | 00D6090 | This project will substantially improve the community by providing a new bicycle and pedestrian path in Sangamon County(West-Central Illinois) | Transportation Enhancements | 06/29/2010 |  | 07/30/2012 | 2352126 | 0
2445 | Illinois | MACON |  | 17 | 00D7036 | This project will provide landscaping for the Farm Progress Grounds in Decatur (Southeast Illinois). | Transportation Enhancements | 10/29/2009 | 04/12/2010 | 05/30/2010 | 74400 | 0
2446 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 00D8131 | This project will add new sidewalk, replace broken curb and gutter add lighting o the streets and adjust the stop lights to operate more efficiently on various streets throughout the city of East St. | Transportation Enhancements | 12/10/2009 | 05/11/2010 | 10/30/2010 | 800000 | 0
2447 | Illinois | GALLATIN |  | 19 | 00D9084 | This project will enhance pedestrian and bicycle accommodations by constructing a bike trail accessing the Gallatin County Visitors Center in Gallatin County (Southern Illinois). | Transportation Enhancements | 04/28/2010 | 04/28/2010 | 10/30/2010 | 586100 | 0
2448 | Illinois | SALINE |  | 19 | 00D9094 | This project will enhance pedestrian and bicycle accommodations by constructing a bike trail connection between the cities of Eldorado and Harrisburg (Southern Illinois). | Transportation Enhancements | 04/23/2010 | 04/23/2010 | 05/30/2011 | 939900 | 0
2449 | Illinois | SALINE |  | 19 | 00D9096 | LAND ACQUISITION FOR THE CONSTRUCTION OF A BIKE/PED TRAIL TO CONNECT ELDORADO TO HARRISBURG, SECTION 06-00082-00-BT | Transportation Enhancements | 09/14/2009 |  | 10/30/2009 | 22500 | 0
2450 | Illinois | MCDONOUGH |  | 17 | 0109052 | This project will extend the structure life by providing new exterior paint on two county highway bridges in McDonough County (West-Central Illinois). | Bridge Improvement | 04/06/2010 | 04/16/2010 | 06/30/2010 | 77947 | 0.02
2451 | Illinois | MCLEAN |  | 15 | 0113029 | This project will provide for pedestrian safety by constructing a 1.13 mile multi-use bike trail in Chenoa, approximately 25 miles north of Bloomington (East-Central Illinois) | Transportation Enhancements | 08/04/2009 | 08/07/2009 | 10/30/2009 | 10685.46 | 0
2452 | Illinois | MASON |  | 18 | 0125018 | This project consists of a safety and traffic enhancement by upgrading pavement markings on various routes throughout Mason County (West-Central Illinois). | Safety/Traffic Management | 04/15/2010 | 06/01/2010 | 05/30/2010 | 80010 | 0
2453 | Illinois | POPE |  | 19 | 0132130 | This project will extend the pavement life by milling, patching and resurfacing 3.61 miles of IL145 in Pope county, Illinois (Southern Illinois). | Pavement Improvement | 06/02/2009 | 07/01/2009 | 08/30/2009 | 985175.18 | 3.75
2454 | Illinois | PEORIA |  | 18 | 0143050 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on County Highway 15 over Spoon River approximately 30 miles northwest of Peoria (West-Centr | Bridge Improvement | 09/08/2009 | 09/28/2009 | 07/30/2010 | 379741 | 0.02
2455 | Illinois | PULASKI |  | 12 | 0153030 | This project will substantially improve the roadway by constructing a new bridge over Pulaski Slough on Morris Road in Pulaski County, Illinois (Southern Illinois Illinois) | Bridge Replacement | 08/27/2009 | 09/21/2009 | 10/30/2009 | 157081 | 0.02
2456 | Illinois | SANGAMON |  | 18 | 0167058 | This project will extend the pavement life by resurfacing a portion of a Sangamon County road near Springfield (West-Central Illinois). | Pavement Improvement | 10/14/2009 | 10/12/2009 | 03/30/2010 | 1573224.1 | 11.2
2457 | Illinois | SANGAMON |  | 18 | 0167059 | This project will substantially improve the roadway by constructing a new intersection and signals along with other roadway improvements at Village Center Drive and Business 55 in Sherman (West-Centra | Pavement Improvement | 04/19/2010 | 06/01/2010 | 07/30/2010 | 280212 | 0.01
2458 | Illinois | LA SALLE |  | 11 | 0169103 | This project will extend the pavement life by resurfacing 3.6 miles of US 52 near the city of Troy Grove (East-Central Illinois). | Pavement Improvement | 04/23/2009 | 05/27/2009 | 09/30/2009 | 682587.86 | 3.63
2459 | Illinois | DE KALB |  | 14 | 0174118 | This project will substantially improve the roadway by constructing a new bridge over Big Indian Creek on County Highway 6 in Dekalb County (East-Central Illinois). | Bridge Replacement | 07/30/2009 | 08/10/2009 | 12/30/2009 | 314054 | 10.02
2460 | Illinois | STARK |  | 18 | 0175023 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on CH 23 over Jack Creek at Toulon which is approximately 30 miles northwest of the City of | Bridge Replacement | 09/15/2009 | 09/16/2009 | 10/30/2009 | 184642 | 0.01
2461 | Illinois | TAZEWELL | PEORIA | 18 | 0179032 | This project will enhance safety by widening the pavement to accommodate left and right turn lanes into Tazewell County facilities on Illinois Route 9 approximately 10 miles south of Peoria (West-Cent | Pavement Improvement | 12/14/2009 | 04/26/2010 | 07/30/2010 | 420000 | 0.01
2462 | Illinois | DE KALB |  | 14 | 0179106 | This project will extend the pavement life by resurfacing 3 miles of South 1st Street in Dekalb County (East-Central Illinois). | Pavement Improvement | 02/24/2010 | 05/18/2010 | 05/30/2010 | 572363 | 3.31
2463 | Illinois | UNION |  | 12 | 0181048 | This project will substantially improve the roadway by replacing the existing bridge carrying Kratzinger Hollow Rd over Green Creek near Jonesboro, Illinois (Southern Illinois) | Bridge Replacement | 03/10/2010 | 05/06/2010 | 06/30/2010 | 115000 | 0.01
2464 | Illinois | LEE |  | 14 | 0185103 | This project will extend the pavement life by resurfacing sections of Ambot Road and Walton Road in Lee County (Northwest Illinois). | Pavement Improvement | 12/09/2009 | 05/11/2010 | 07/30/2010 | 433493 | 6.35
2465 | Illinois | WARREN |  | 17 | 0187038 | This project consists of a safety and traffic enhancement by upgrading roadway signs throughout Warren County (West-Central Illinois) | Safety/Traffic Management | 12/14/2009 | 12/24/2009 | 11/30/2010 | 295543 | 0
2466 | Illinois | BUREAU |  | 18 | 0188120 | This project will extend pavement life by resurfacing 2 miles of County Highway 8 in Bureau County (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 09/08/2009 | 09/30/2009 | 292800 | 4
2467 | Illinois | OGLE |  | 16 | 0189108 | This project will extend the pavement life by resurfacing sections of Freeport Road in Ogle County (Northwest Illinois). | Pavement Improvement | 07/30/2009 | 08/24/2009 | 09/30/2009 | 574019 | 21.47
2468 | Illinois | WINNEBAGO |  | 16 | 0201027 | This project consists of improving safety by upgrading guardrail to current standards throughout Winnebago County (Northwest Illinois). | Safety/Traffic Management | 10/29/2009 | 11/09/2009 | 12/30/2009 | 328676 | 0
2469 | Illinois | MERCER |  | 17 | 0206116 | This project will prepare for a drainage improvement project on County Highway 4 in Henry County (West-Central Illinois). | Other | 10/27/2009 | 10/27/2009 | 03/30/2010 | 67683 | 1.31
2470 | Illinois | MERCER |  | 17 | 0206117 | This project will extend the pavement life by resurfacing and replacing culverts along a section of County Highway 4 in Mercer County (West-Central Illinois). | Pavement Improvement | 04/20/2010 | 04/30/2010 | 08/30/2010 | 286259 | 1.31
2471 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 2 | 0209003 | This item provides construction engineering service for inspection and oversight for the improvement of I-94 from Martin Luther King Drive to 159th Street in Chicago, Cook County. | Other | 04/30/2009 | 04/30/2009 | 07/30/2011 | 2714990 | 9
2472 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 4,6,7 | 0209004 | This item provides design engineering services for the development of plans and specifications for the construction of I-290 from Thorndale Ave to Grand Ave; I-290 from I-88 to I-94/90 and I-355 from | Other | 05/18/2009 | 05/18/2009 | 05/30/2011 | 4224528 | 14
2473 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1 | 0209005 | This item provides construction engineering service for inspection and oversight of the project on I-57 to replace 7 bridge decks in Cook and Will Counties (Northeast Illinois) | Other | 05/15/2009 | 05/15/2009 | 02/28/2010 | 1300000 | 0
2474 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 7 | 0209006 | This item provides construction engineering service for inspection and oversight of the ramp modification project on I-94/90 from Hubbard's Cave to I-290 and the bridge deck replacement project at 26t | Other | 05/07/2009 | 05/07/2009 | 02/28/2011 | 1189458 | 0
2475 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 5 | 0209007 | This item provides construction engineering service for inspection and oversight of the project for bridge improvement I-90/94 in Chicago (Northeast Illinois) | Other | 05/11/2009 | 05/11/2009 | 12/30/2010 | 702536 | 0
2476 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0209008 | This item provides construction engineering service for inspection and oversight of the project to resurface 159th Street in Homer Glen (Northeast Illinois) | Other | 06/02/2009 | 06/02/2009 | 02/28/2010 | 852053 | 30
2477 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 2 | 0209009 | This item provides construction engineering service for inspection and oversight of the project to resurface Burnham Avenue in Calumet City (Northeast Illinois) | Other | 05/05/2009 | 05/05/2009 | 02/28/2010 | 605580 | 0
2478 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0209010 | This item provides construction engineering service for inspection and oversight of the project to resurface Lemont Road in Lemont (Northeast Illinois) | Other | 04/30/2009 | 04/30/2009 | 12/30/2012 | 710068 | 0
2479 | Illinois | STATEWIDE |  | 1,2,3,4,5,6,7,8,9,10,11,13,14,16 | 0209013 | This item provides preliminary engineering services for the development of projects in the District 1 area (Northeast Illinois) | Other | 06/02/2009 | 06/02/2009 | 12/30/2011 | 4000000 | 0
2480 | Illinois | STATEWIDE |  | 14,16,17 | 0209014 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 05/15/2009 | 05/15/2009 | 12/30/2012 | 400000 | 0
2481 | Illinois | STATEWIDE |  | 14,16,17 | 0209015 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 05/15/2009 | 05/15/2009 | 12/30/2012 | 300000 | 0
2482 | Illinois | STATEWIDE |  | 14,16,17 | 0209016 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 05/12/2009 | 05/12/2009 | 12/30/2012 | 300000 | 0
2483 | Illinois | STATEWIDE |  | 17,18 | 0209017 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 4 (West-Central Illinois). | Other | 06/02/2009 | 06/02/2009 | 12/30/2011 | 1700000 | 0
2484 | Illinois | STATEWIDE |  | 11,15 | 0209018 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 5 (East-Central Illinois). | Other | 05/18/2009 | 05/18/2009 | 12/30/2012 | 500000 | 0
2485 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 0209019 | This project will ensure quality infrastructure by providing engineering oversight during construction of a highway interchange on Interstate 55/70 in Madison County (Southwest Illinois). | Other | 06/25/2009 | 06/25/2009 | 05/30/2012 | 2313381 | 0
2486 | Illinois | STATEWIDE |  | 12,17,19 | 0209020 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 05/20/2009 | 05/20/2009 | 05/30/2012 | 500000 | 0
2487 | Illinois | STATEWIDE |  | 12,17,19 | 0209021 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 06/11/2009 | 06/11/2009 | 05/30/2012 | 500000 | 0
2488 | Illinois | STATEWIDE |  | 12,19,17 | 0209022 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 05/15/2009 | 05/15/2009 | 05/30/2012 | 500000 | 0
2489 | Illinois | STATEWIDE |  | 12,17,19 | 0209023 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 05/15/2009 | 05/15/2009 | 05/30/2012 | 500000 | 0
2490 | Illinois | STATEWIDE |  | 12,15,19 | 0209024 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 05/18/2009 | 05/18/2009 | 12/30/2011 | 300000 | 0
2491 | Illinois | STATEWIDE |  | 12,19 | 0209025 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 05/18/2009 | 05/18/2009 | 05/30/2011 | 300000 | 0
2492 | Illinois | STATEWIDE |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19 | 0209026 | This project provides Quality Assurance on pavement resurfacing on projects statewide in Illinois | Other | 05/29/2009 | 05/29/2009 | 05/30/2012 | 300000 | 0
2493 | Illinois | TAZEWELL | PEORIA | 17,18 | 0209027 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 4 (West-Central Illinois). | Other | 06/26/2009 | 06/26/2009 | 12/30/2011 | 1599947 | 0
2494 | Illinois | HENRY |  | 17 | 0239102 | This project will extend the pavement life by resurfacing sections of County Highways 39 and 24 in Henry County (Northwest Illinois). | Pavement Improvement | 03/01/2010 | 06/01/2010 | 06/30/2010 | 497682 | 3.46
2495 | Illinois | BUREAU |  | 11 | 0242114 | This project will extend pavement life by providing a surface treatment on 9.5 miles of County Highway 16 in Bureau County (East-Central Illinois). | Pavement Improvement | 09/09/2009 | 09/09/2009 | 09/30/2009 | 128800 | 28.38
2496 | Illinois | BUREAU |  | 11 | 0244101 | This project will extend pavement life by providing a surface treatment on 7.8 miles of County Highway 9 in Bureau County (East-Central Illinois). | Pavement Improvement | 09/09/2009 | 09/15/2009 | 09/30/2009 | 83792 | 12.78
2497 | Illinois | KENDALL |  | 14 | 0281101 | This project will extend the pavement life by resurfacing a section of County Highway 19 in Kendall County (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 10/05/2009 | 10/30/2009 | 361760 | 3.05
2498 | Illinois | GRUNDY |  | 11 | 0287106 | This project will substantially improve the roadway by constructing a new bridge over the Mazon River on County Highway C29 in Grundy County (East-Central Illinois). | Bridge Replacement | 03/01/2010 | 07/06/2010 | 11/30/2010 | 333347 | 0.01
2499 | Illinois | MCLEAN |  | 15 | 0294108 | This project will extend the pavement life by providing for 13.05 miles of pavement removal and resurfacing on Old U.S. Route 66 north of Bloomington (East-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/26/2009 | 10/30/2009 | 3075370.29 | 16.77
2500 | Illinois | LIVINGSTON, GRUNDY |  | 11 | 0298103 | This project will extend pavement life by resurfacing 7 miles of Old US 66 between the cities of Dwight and Gardener (East-Central Illinois). | Pavement Improvement | 05/11/2009 | 06/15/2009 | 10/30/2009 | 1984380.56 | 14.28
2501 | Illinois | STEPHENSON |  | 16 | 0301058 | This project will extend the pavement life by resurfacing a section of US 20 in western Stephenson County (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 07/27/2009 | 11/30/2009 | 1655501.24 | 5.86
2502 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0303042 | This project will extend the pavement life by resurfacing 5.21 miles on IL 173 from Lake County Line to US 12 in the Villages of Fox Lake and Richmond (Northeastern Illinois) | Pavement Improvement | 04/30/2009 | 05/18/2009 | 08/30/2009 | 1861530.67 | 5.46
2503 | Illinois | WINNEBAGO | ROCKFORD | 16 | 0303043 | This project will extend the pavement life by resurfacing a section of IL 251 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 04/23/2009 | 05/26/2009 | 10/30/2009 | 498240.41 | 2.96
2504 | Illinois | WINNEBAGO | ROCKFORD | 16 | 0303044 | This project will extend the pavement life by resurfacing sections of IL 251 in the city of Loves Park (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/11/2009 | 09/30/2009 | 963894.35 | 3.18
2505 | Illinois | JERSEY |  | 17 | 0304042 | This project will extend the pavement life by milling, patching and resurfacing Grafton, Illinois (Southwest Illinios). | Pavement Improvement | 05/11/2009 | 05/26/2009 | 11/30/2009 | 2671744.35 | 8.36
2506 | Illinois | JERSEY, MADISON | ST. LOUIS (MO)-IL | 19 | 0304043 | This project will extend the pavement life by milling, patching and resurfacing near Alton, Illinois (Southwest Illinios). | Pavement Improvement | 05/04/2009 | 05/26/2009 | 11/30/2009 | 2024824.77 | 6.56
2507 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0305038 | This project will substantially improve the roadway by reconstructing a section of Palatine Rd by widening the road, providing new asphalt pavement and other roadway improvements in Palatine (Northeas | Other | 04/28/2010 | 04/28/2010 | 05/30/2011 | 5178416 | 0.8
2508 | Illinois | MCHENRY |  | 16 | 0305041 | This project will extend the pavement life by milling, patching, resurfacing and striping 2.34 miles on US 14 from Bunker Hill Rd to Park Lane Dr in unincorporated McHenry | Pavement Improvement | 05/06/2009 | 05/26/2009 | 09/30/2009 | 631892.25 | 2.35
2509 | Illinois | ROCK ISLAND |  | 17 | 0308035 | This project will extend the pavement life by resurfacing 4.4 miles of IL 81 near the city of Cambridge (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/27/2009 | 06/30/2010 | 4426093.1 | 4.41
2510 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 0310130 | Construction of two new structures carrying IL Route 255 over Humbert Road in Godfrey, IL (Southwest Illinois) | Pavement Widening | 07/16/2009 | 09/14/2009 | 10/30/2011 | 4891714.12 | 0.77
2511 | Illinois | SCHUYLER |  | 18 | 0310131 | This project will extend the pavement life by resurfacing a portion of US Route 67 near Rushville (West-Central Illinois). | Pavement Improvement | 04/17/2009 | 04/23/2009 | 10/30/2009 | 3703886.22 | 9.86
2512 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0310132 | This project will extend the pavement life by resurfacing 3.5 miles of US 67 near the city of Milan (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/20/2009 | 10/30/2009 | 3631151.19 | 3.48
2513 | Illinois | CASS |  | 18 | 0310134 | This project will extend the pavement life by resurfacing and updating guardrail to a portion of US Route 67 from Beardstown to 3 miles north of Meredosia (West-Central Illinois). | Pavement Improvement | 05/04/2009 | 05/04/2009 | 09/30/2009 | 2509608.49 | 9.96
2514 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0311037 | This project will extend the pavement life by resurfacing 4.1 miles on US Route 34 in the City of Downers Grove (Northeast Illinois). | Pavement Improvement | 04/28/2009 | 05/01/2009 | 10/30/2009 | 2682617.34 | 3.37
2515 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0311039 | This project will extend the pavement life by resurfacing 2.09 miles on US Route 34 in Napreville (Northeast Illinois). | Pavement Improvement | 10/16/2009 |  | 07/30/2010 | 1420191.7 | 4.3
2516 | Illinois | MCDONOUGH |  | 17 | 0315055 | This project will extend the pavement life by providing surface improvements on a 0.57 mile section of U.S. Route 136 in Macomb (West-Central Illinois) | Pavement Improvement | 07/30/2009 | 08/10/2009 | 11/30/2009 | 633140.85 | 1.14
2517 | Illinois | OGLE |  | 16 | 0316035 | This project will extend the pavement life by resurfacing a section of US 52 and IL 26 near the city of Polo (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 05/18/2009 | 07/30/2009 | 363285.85 | 1.27
2518 | Illinois | MCLEAN |  | 11 | 0317080 | This project will extend the pavement life by providing for 7.3 miles of pavement repairs and resurfacing on U.S. Route 24 north of Bloomington (East-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/04/2009 | 08/30/2009 | 1696469.4 | 7.28
2519 | Illinois | DOUGLAS, PIATT |  | 15 | 0323026 | This project will extend the pavement life by providing for 9.6 miles of pavement removal and resurfacing on U.S. Route 36 south of Champaign (East-Central Illinois) | Pavement Improvement | 04/23/2009 | 05/06/2009 | 09/30/2009 | 2479001.73 | 9.78
2520 | Illinois | COLES |  | 15 | 0325051 | This project will extend the bridge life by replacing the bridge deck and making other bridge improvements at the intersection of US Route 45 and Illinois Route 16 in Mattoon (Southeast Illinois). | Bridge Improvement | 02/24/2010 | 03/08/2010 | 11/30/2010 | 2866803.69 | 0.04
2521 | Illinois | GRUNDY |  | 11 | 0326077 | This project will extend the pavement life by resurfacing 10.9 miles of IL 47 near the city of Mazon (East-Central Illinois). | Pavement Improvement | 06/08/2009 | 08/17/2009 | 10/30/2009 | 2339080.53 | 11.02
2522 | Illinois | LIVINGSTON, GRUNDY |  | 11 | 0326078 | This project will extend the pavement life by resurfacing 15.6 miles of IL 47 between the cities of Dwight and Saunemin (East-Central Illinois). | Pavement Improvement | 06/02/2009 | 06/08/2009 | 05/30/2010 | 3899088.32 | 15.49
2523 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0326079 | This project will extend the pavement life by milling, patching, resurfacing and striping 3.55 miles on US 30/IL 47 from US 30/IL 56 to Kendall County lines in the Village of Sugar Grove (Northeaster | Pavement Improvement | 05/18/2009 | 05/26/2009 | 08/30/2009 | 1955152.42 | 5.87
2524 | Illinois | MARION |  | 19 | 0327043 | This project consists of 2.61 miles of resurfacing which will extend the pavement life by milling, patching and resurfacing in Marion County, Illinois (Southwest Illinios). | Pavement Improvement | 05/04/2009 | 05/13/2009 | 09/30/2009 | 794759.98 | 2.72
2525 | Illinois | IROQUOIS |  | 15 | 0329106 | This project will extend the pavement life by resurfacing a section of County Highway 10 in Iroquois County (East-Central Illinois). | Pavement Improvement | 02/22/2010 | 04/13/2010 | 06/30/2010 | 645683 | 5.7
2526 | Illinois | WILL |  | 11 | 0330050 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on us Route 45 over Forked Creek 2.1 miles south of Manhattan Monee Road (Northeast Illinoi | Bridge Improvement | 05/11/2009 | 07/13/2009 | 09/30/2009 | 248217.04 | 0.01
2527 | Illinois | WILL |  | 11 | 0330051 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 45/52 over south Branch of Forked Creek 0.5 miles south of Joliet Road near Pe | Bridge Improvement | 05/11/2009 | 07/13/2009 | 09/30/2009 | 247208.82 | 0.01
2528 | Illinois | KANKAKEE |  | 11 | 0330052 | This project will extend the pavement life by resurfacing a section of IL 17 near the city of Aroma (East-Central Illinois). | Pavement Improvement | 06/01/2009 | 08/03/2009 | 09/30/2009 | 2994021.65 | 4.3
2529 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 04 | 0330053 | This project will extend the pavement life by resurfacing 1.66 miles of Mannheim Rd in theVillages of Hillside, Melrose Park, and Stone Park, (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/08/2009 | 10/30/2009 | 1585675.63 | 1.43
2530 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0330054 | This project will extend the pavement life by resurfacing 1.22 miles of US 12/45 from Prospect Avenue to Walnut Avenue in the City of DesPlaines in Cook County. (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/15/2009 | 09/30/2009 | 735694.24 | 1.14
2531 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0330055 | This project will extend the pavement life by resurfacing 1.20 miles of US 12/45 from US 12 (Rand Rd) to Walnut Avenue within the City of DesPlaines in Cook County. (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/15/2009 | 09/30/2009 | 912549.95 | 3.21
2532 | Illinois | SALINE |  | 19 | 0331048 | This project will substantially improve mobility by constructing a new four lane roadway and new bridge over west Harrisburg drainage ditch which will rerout a protion of IL13 around Harrisburg, Illin | New Construction | 06/01/2009 | 07/13/2009 | 08/30/2011 | 14183910.09 | 5.5
2533 | Illinois | JACKSON |  | 12 | 0331050 | This project will substantially improve the roadway by constructing a new bridge over Mud Creek on IL 13 in Jackson County, Illinois (Southern Illinois) | Bridge Replacement | 10/22/2009 | 11/02/2009 | 10/30/2011 | 1865415.6 | 0.04
2534 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0332091 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on IL 1 over Trim Creek 1 mile south of Beecher (Northeast Illinois). | Pavement Improvement | 05/11/2009 | 06/23/2009 | 07/30/2010 | 665725.4 | 0.01
2535 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0334018 | This project will extend the pavement life by milling, patching and resurfacing 1.13 miles on US Rt. 12 (Main St) from Wisconsin State Line to IL 73 (Kenosha Rd) in the Village of Richmond (Northeaste | Pavement Improvement | 06/01/2009 | 06/22/2009 | 09/30/2009 | 453639.51 | 1.12
2536 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 0335011 | This project will extend the pavement life by resurfacing 3.91 miles on IL 176 between Nish Rd and IL 31in the Villages of Crystal Lake and Prairie Grove (Northeastern Illinois) | Pavement Improvement | 04/28/2009 | 05/11/2009 | 08/30/2009 | 1288150.05 | 3.89
2537 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0335012 | This project will extend the pavement life by milling, patching, resurfacing and striping 1.44 miles on IL 60 from IL 21(Milwaukee Ave) to west of I-94(Tri-State Tollway) in the Villages of Libertyvil | Pavement Improvement | 06/01/2009 | 06/19/2009 | 11/30/2009 | 970128.99 | 1.7
2538 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0335013 | This project will extend the pavement life by milling, patching and resurfacing 2.96 miles on IL Rt 176 and IL 60/83 from west of Thorngate Dr to IL 60/83 and from IL 176 to Midlothian Rd in Mundelein | Pavement Improvement | 10/23/2009 | 04/14/2010 | 06/30/2010 | 1216777.6 | 5.96
2539 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0338036 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL 59 at four structures in West Chicago (Northeast Illinois). | Bridge Improvement | 05/04/2009 | 06/01/2009 | 10/30/2009 | 1070936.11 | 1.99
2540 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0338037 | This project will improve safety and traffic operations by reconstructing the intersection of IL 59 and US Route 30 in Plainfield (Northeast Illinois) | Pavement Improvement | 06/16/2009 | 06/19/2009 | 05/30/2011 | 7903047.94 | 0.01
2541 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0338038 | This project will extend the pavement life by resurfacing 5.80 miles on IL 59 in West Chicago (Northeast Illinois). | Pavement Improvement | 10/28/2009 | 03/17/2010 | 08/30/2010 | 4021444.39 | 12.58
2542 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0338039 | This project will extend the pavement life by milling, patching and resurfacing 2.45 miles on IL Rt 59/Hough street from IL 22 to Lake-Cook Rd in Barrington (Northeastern Illinois). | Pavement Improvement | 10/27/2009 | 04/12/2010 | 07/30/2010 | 1115282.72 | 5
2543 | Illinois | FORD |  | 15 | 0340103 | This project will substantially improve the roadway by constructing new bridges over creeks on County Highway 26 southwest of the city of Paxton (East-Central Illinois). | Bridge Replacement | 09/08/2009 | 09/23/2009 | 05/30/2010 | 319891 | 0.02
2544 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 0341045 | This project will extend the pavement life by resurfacing 1.43 miles of Touhy Avenue (IL 72) from Lee Street to the DesPlaines River Road in the Villages of Des Plaines and Rosemont in Cook County. (N | Pavement Improvement | 04/23/2009 | 05/12/2009 | 08/30/2009 | 1312389.16 | 1.7
2545 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0341046 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL 72 over I-90 in Gilberts in Northeastern Illinois | Bridge Improvement | 06/01/2009 | 06/08/2009 | 09/30/2009 | 725497.89 | 0.01
2546 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0341047 | This project will extend the pavement life by milling, patching and resurfacing 0.98 miles of Il 72 in the Village of Hoffman Estates in Cook County. (Northeastern Illinois). | Pavement Improvement | 08/07/2009 | 08/14/2009 | 10/30/2009 | 1231439.52 | 2.12
2547 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0347021 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on Il 38 over Kress Creek in West Chicago (Northeast Illinois). | Pavement Improvement | 05/04/2009 | 05/26/2009 | 08/30/2009 | 383598.44 | 0.01
2548 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0348042 | This project will extend the bridge life by partial and full depth patching of the bridge deck, bridge deck overlay, joint repair, and making other roadway improvements to the IL 43 bridge over Stoney | Bridge Improvement | 06/01/2009 | 06/22/2009 | 10/30/2009 | 692294.91 | 0.01
2549 | Illinois | KENDALL |  | 14 | 0349013 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on US Rt. 30 over River St in Montgomery (Northeastern Illinois) | Bridge Improvement | 04/23/2009 | 06/25/2009 | 08/30/2009 | 445859.2 | 0.02
2550 | Illinois | KENDALL, KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0349014 | This project will extend the pavement life by milling, resurfacing and striping 2.78 miles on US Rt.30 from IL Rt 47 to Orchard Rd in the Village of Montgomery (Northeastern Illinois) | Pavement Improvement | 05/18/2009 | 05/26/2009 | 08/30/2009 | 1019192.72 | 3.54
2551 | Illinois | LIVINGSTON |  | 15 | 0349114 | This project will substantially improve the roadway by replacing two bridges on County Highway 10 north of Weston in Livingston County (East-Central Illinois). | Bridge Replacement | 03/02/2010 | 04/01/2010 | 08/30/2010 | 623639 | 0.02
2552 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0350029 | This project will extend the pavement life by resurfacing 1.69 miles of IL 50 (Cicero Avenue) from IL 19 (Irving Road) to I-94 in the City of Chicago. | Pavement Improvement | 04/23/2009 | 05/11/2009 | 09/30/2009 | 1558990.02 | 3.06
2553 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0350030 | This project will extend the pavement life by resurfacing 2.92 miles of US 41/IL 50 from Foster Street to Touhy Avenue in Lincolnwood in Cook County (Northeastern Illinois). | Pavement Improvement | 04/30/2009 | 05/18/2009 | 10/30/2009 | 2265153.23 | 2.91
2554 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0350031 | This project will extend pavement life by resurfacing 0.847 miles of US 41 from Old Orchard Road to Central Avenue in the Villages of Skokie and Wilmette in Cook County (Northeastern Illinois). | Pavement Improvement | 05/04/2009 | 05/26/2009 | 08/30/2009 | 651426.3 | 0.82
2555 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0350032 | This project will extend the life of the pavement by resurfacing 1.512 miles of Cicero Avenue (IL 50) from 34th Street to 46th Street and drainage improvements at IL 50 under I-55 within Cicero & Chic | Pavement Improvement | 07/27/2009 | 09/15/2009 | 10/30/2009 | 1382759.2 | 1.46
2556 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0351018 | This project will substantially improve the roadway by reconstructing 1.92 miles of US 6 (159th street) from I-294 (Tri-State Tollway) to IL 1 (Halsted Street) in Harvey and Markham in Cook County. (N | Pavement Improvement | 06/11/2009 | 06/12/2009 | 07/30/2011 | 18834039.42 | 2.33
2557 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0351019 | This project will extend the pavement life by resurfacing 4.78 miles on IL 7 in Homer Glen (Northeast Illinois). | Pavement Improvement | 05/21/2009 | 06/09/2009 | 11/30/2009 | 1557324.92 | 5.18
2558 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0351020 | This project will extend the pavement life by milling, patching and resurfacing 2.59 miles of US 6 / IL 7 (159th St) from Will-Cook Rd to US 45 in the Village of Orland Park in Cook County. (Northeas | Pavement Improvement | 05/21/2009 | 06/09/2009 | 10/30/2009 | 808496.85 | 2.98
2559 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0352010 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL Rt 137 over Des Plaines River in Libertyville (Northeastern Illinois) | Bridge Improvement | 04/30/2009 | 05/06/2009 | 09/30/2009 | 604593.79 | 0.01
2560 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0352012 | This project will extend the pavement life by milling, patching, resurfacing, curb and gutter 2.52 miles on IL 137 from Martin Luther King Dr to west of US Rt. 41 in the Village of North Chicago (Nort | Pavement Improvement | 06/01/2009 | 06/23/2009 | 10/30/2009 | 2380101.15 | 2.51
2561 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0353014 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on US 30 over IL 394 in the Village of Ford Heights in Cook County. (Northeastern Illinois). | Bridge Improvement | 09/08/2009 | 04/16/2010 | 11/30/2010 | 3441423.77 | 0.02
2562 | Illinois | WOODFORD |  | 18 | 0358102 | This project will substantially improve the roadway by replacing multiple drainage structures on and reconstructing 2.26 miles of County Highway 1 approximately 25 miles northeast of Peoria (West-Cent | Pavement Improvement | 07/24/2009 | 08/17/2009 | 07/30/2010 | 466776 | 6
2563 | Illinois | KANE, COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0360010 | This project will extend the pavement life by milling, patching and resurfacing 1.95 miles on IL 25 (Dundee ave) from I-90(Northwest Tollway) to IL 72(Higgins Rd) in the Villages of Dundee and Elgin ( | Pavement Improvement | 06/11/2009 | 06/18/2009 | 11/30/2009 | 1762847.87 | 2.03
2564 | Illinois | WOODFORD |  | 18 | 0367105 | Thie project will extend the pavement life by resurfacing a 2.5 mile section of County Highway 23 east of Peoria (West-Central Illinois) | Pavement Improvement | 12/03/2009 | 04/19/2010 | 06/30/2010 | 302173 | 3.12
2565 | Illinois | MARSHALL |  | 18 | 0369106 | This project will extend the pavement life by resurfacing 2 miles of County Highway 1 in Marshall County, approximately 25 miles northeast of Peoria (West-Central Illinois) | Pavement Improvement | 12/09/2009 | 05/20/2010 | 05/30/2010 | 267610 | 2
2566 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0370007 | This project will extend the pavement life by resurfacing 1.52 miles Western Avenue from 87th to 99th Street. (Northeastern Illinois). | Pavement Improvement | 04/28/2009 | 04/28/2009 | 10/30/2009 | 1501596.82 | 1.84
2567 | Illinois | PEORIA |  | 18 | 0386105 | This project will extend the pavement life by resurfacing 3.3 miles of Kickapoo-Edwards Road just west of Peoria (West-Central Illinois) | Pavement Improvement | 12/03/2009 | 04/14/2010 | 05/30/2010 | 129720 | 3.27
2568 | Illinois | LEE |  | 11 | 0391018 | This project will extend the pavement life by patching 19 miles of Interstate 39 trhough Lee County (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 05/26/2009 | 08/30/2009 | 1158619.72 | 19.23
2569 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0391026 | This project will extend the bridge life by deck patching, placement of permanent protective shielding and other roadway improvements on 39th Street (Perhing Road) over S. Racine Avenue and Norfolk an | Bridge Improvement | 04/28/2009 | 05/26/2009 | 08/30/2009 | 242959.67 | 0.01
2570 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 0392007 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 26th Street and Frontage Road B over the Franklin Connector which connects Stevenson Expr | Bridge Improvement | 04/23/2009 | 07/20/2009 | 11/30/2010 | 5754169.45 | 0.02
2571 | Illinois | MCDONOUGH |  | 17 | 0415107 | This project will extend the pavement life by resurfacing 0.5 miles of County Highway 13 in McDonough County (West-Central Illinois). | Pavement Improvement | 03/02/2010 | 03/12/2010 | 05/30/2010 | 132000 | 0.51
2572 | Illinois | HENDERSON |  | 17 | 0418113 | This project will improve the roadway by providing new concrete pavement on a section of County Highway 15 in Henderson County (West-Central Illinois). | Pavement Improvement | 03/30/2010 | 04/09/2010 | 06/30/2010 | 229282 | 3
2573 | Illinois | HANCOCK |  | 17 | 0428103 | This project will extend the pavement life by resurfacing a portion Hancock County Highway 11 from Basco, IL to five miles west of Basco (West-Central Illinois). | Pavement Improvement | 09/10/2009 | 09/18/2009 | 12/30/2009 | 476459 | 10
2574 | Illinois | MCDONOUGH |  | 17 | 0436107 | This project will extend the pavement life by resurfacing 0.5 miles of County Highway 1 in McDonough County (West-Central Illinois). | Pavement Improvement | 03/08/2010 | 03/18/2010 | 05/30/2010 | 132000 | 1.02
2575 | Illinois | SCHUYLER |  | 18 | 0454104 | This project will substantially improve the roadway by constructing a new bridge over Dutchmans Creek on County Highway 8 near Browning in Schuyler County (West-Central Illinois). | Bridge Replacement | 05/18/2010 |  | 08/30/2010 | 243160 | 0.01
2576 | Illinois | TAZEWELL |  | 18 | 0467106 | This project will extend the pavement life by resurfacing 3 miles of Allentown Rd approximately 10 miles southeast of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 | 04/20/2010 | 06/30/2010 | 446467 | 2.84
2577 | Illinois | TAZEWELL |  | 18 | 0468102 | This project will extend the pavement life by resurfacing 7 blocks of Minier Avenue in Minier, southeast of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 | 04/21/2010 | 05/30/2010 | 155000 | 0.6
2578 | Illinois | TAZEWELL |  | 18 | 0470107 | This project will extend the pavement life by providing for 1.4 miles of resurfacing on Dee Mack Road east of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 | 05/01/2010 | 05/30/2010 | 320000 | 3
2579 | Illinois | MCLEAN |  | 15 | 0478106 | This project will substantially improve 0.74 mile of County Highway 29 by providing new concrete pavement and other roadway improvements north of Bloomington (East-Central Illinois) | Pavement Improvement | 07/24/2009 | 08/06/2009 | 01/30/2010 | 1066520 | 0.02
2580 | Illinois | MCLEAN |  | 11 | 0494102 | This project will extend the pavement life by providing for 2.42 miles pavement repairs and resurfacing on Horse Farm Road in LeRoy, southeast of Bloomington (East-Central Illinois) | Pavement Improvement | 09/08/2009 | 09/14/2009 | 11/30/2009 | 510000 | 4.84
2581 | Illinois | VERMILION |  | 15 | 0496106 | This project will substantially improve the roadway by constructing a new bridge on County Highway 14 over the Middle Branch approximately 50 miles northeast of Champaign (East-Central Illinois) | Bridge Replacement | 12/07/2009 | 03/15/2010 | 09/30/2010 | 505094 | 0.01
2582 | Illinois | WINNEBAGO |  | 16 | 0505024 | This project will extend the pavement life and improve drainage by resurfacing and replacing culverts along a section of IL 75 in the city of Rockton (Northwest Illinois). | Pavement Improvement | 02/24/2010 | 05/25/2010 | 10/30/2010 | 1839708.69 | 11.32
2583 | Illinois | VERMILION |  | 15 | 0513103 | This project will extend the pavement life with 10.4 miles of pavement repairs on Chicago Street approximately 20 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 04/23/2009 | 06/11/2009 | 09/30/2009 | 844802.75 | 9.72
2584 | Illinois | BOONE |  | 16 | 0525115 | This project will extend the pavement life by resurfacing 5.4 miles of US 20 near the city of Belvidere (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/11/2009 | 10/30/2009 | 1628442.77 | 5.45
2585 | Illinois | CHAMPAIGN |  | 15 | 0531108 | This project will substantially improve the roadway by reconstructing and widening County Highway 18 south of Champaign (East-Central Illinois) | Pavement Improvement | 12/10/2009 | 04/05/2010 | 10/30/2010 | 597211 | 13.92
2586 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0535001 | This project will extend the pavement life by milling, patching anfd resurfacing 6.59 miles on IL 60/83 between IL Rt 20(Belvidere Rd) and IL 176 in the Villages of Mundelein, Ivanhoe, Volo and Round | Pavement Improvement | 06/01/2009 | 06/20/2009 | 05/30/2010 | 2092946.58 | 6.88
2587 | Illinois | PIATT |  | 15 | 0535102 | This project will extend the pavement life by resurfacing a section of Shady Rest Road approximately 15 miles west of Champaign (East-Central Illinois) | Pavement Improvement | 12/22/2009 | 03/29/2010 | 08/30/2010 | 276697 | 1.56
2588 | Illinois | DE WITT |  | 15 | 0543105 | This project will substantially improve the roadway by constructing a new bridge on Parnell Road over Salt Creek approximately 25 miles south of Bloomington (East-Central Illinois) | Bridge Improvement | 12/14/2009 | 03/15/2010 | 08/30/2010 | 6413 | 0.01
2589 | Illinois | MACON |  | 18 | 0548103 | This project will substantially improve the roadway by replacing a new bridge over Lake Fork Creek on County Highway 58 west of Maroa (West-Central Illinois) | Bridge Replacement | 12/14/2009 | 04/19/2010 | 06/30/2010 | 328230 | 0.01
2590 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0556233 | This project will address noise issues with the construction of noise walls along I-55 in Romeoville and Planfield (Northeast Illinois) | Transportation Enhancements | 09/14/2009 |  | 05/30/2011 | 8546818.35 | 6.57
2591 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0556234 | This project will address noise issues with the construction of noise walls along I-55 in Joliet and Planfield (Northeast Illinois) | Transportation Enhancements | 10/07/2009 | 10/17/2009 | 05/30/2011 | 8162557.2 | 7.93
2592 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0556238 | Not in FMIS | Pavement Improvement | 05/18/2010 | 06/01/2010 | 11/30/2010 | 3500000 | 0.02
2593 | Illinois | LOGAN |  | 18 | 0559102 | This project will extend the bridge life by rehabilitating the bridge deck and making other improvements on County Highway 2 two miles north of Lincoln (West-Central Illinois). | Bridge Improvement | 04/09/2010 | 04/28/2010 | 08/30/2010 | 368344 | 0.01
2594 | Illinois | LEE |  | 14 | 0561029 | This project will substantially improve the roadway by constructing new bridges over creeks on IL 2 near Sauk Valley College (Northwest Illinois). | Bridge Replacement | 12/08/2009 | 04/05/2010 | 11/30/2010 | 1959537.75 | 0.03
2595 | Illinois | WHITESIDE |  | 16 | 0565003 | This project will extend the pavement life by resurfacing 2.9 miles of IL 136 near the city of Fulton (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 05/18/2009 | 10/30/2009 | 1284750.45 | 3.21
2596 | Illinois | DE KALB |  | 14 | 0567098 | This project will extend the pavement life by resurfacing 5.3 miles of IL 38 east of the city of Dekalb (East-Central Illinois). | Pavement Improvement | 06/01/2009 | 07/06/2009 | 09/30/2009 | 1910449.89 | 10.6
2597 | Illinois | MASON |  | 18 | 0567115 | This project will extend the pavement life by providing a surface treatment on a section of County Highway 20 near Forest City in Mason County (West-Central Illinois). | Pavement Improvement | 08/27/2009 | 09/08/2009 | 09/30/2009 | 229661 | 3.83
2598 | Illinois | DE KALB |  | 14 | 0567126 | This project will extend the pavement life by resurfacing 2.2 miles of IL 38 in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 08/11/2009 | 08/31/2009 | 07/30/2010 | 1828069.3 | 4.34
2599 | Illinois | FRANKLIN |  | 12 | 0572149 | This project will extend the pavement life by milling, rubblizing, patching and resurfacing 8.68 miles of Interstate 57 in Franklin County Illinois (Southern Illinios). | Pavement Improvement | 04/28/2009 | 07/13/2009 | 08/30/2009 | 8982883.85 | 8.68
2600 | Illinois | COLES |  | 15 | 0574128 | This project will extend the pavement life by resurfacing a portion of Interstate 57 from south of Arcola to Mattoon (Southeast Illinois). | Pavement Improvement | 05/20/2009 | 06/09/2009 | 08/30/2010 | 21590042.78 | 10.87
2601 | Illinois | CASS |  | 18 | 0575312 | This project will substantially improve the roadway by constructing a new bridge over Middle Creek on County Highway 12 near Newmansville (West-Central Illinois). | Bridge Replacement | 04/15/2010 | 06/01/2010 | 08/30/2010 | 212157 | 0.01
2602 | Illinois | COOK |  | 01 | 0577277 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 112th Place over I-57 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 06/01/2009 | 06/04/2009 | 11/30/2009 | 2814816.26 | 0.01
2603 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0577278 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 103rd Street over I-57 in Chicago. (Northeastern Illinois). | Bridge Improvement | 05/04/2009 | 06/01/2009 | 11/30/2009 | 2035725.16 | 0.01
2604 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0577279 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on North Peotone/Joliet Road over I-57in Peotone (Northeast Illinois). | Bridge Improvement | 05/11/2009 | 07/20/2009 | 09/30/2009 | 416872.79 | 0.01
2605 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0577280 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the 115th Street over I-57 in Chicago, Cook County. (Northeastern Illinois). | Bridge Improvement | 04/23/2009 | 05/11/2009 | 11/30/2009 | 2912304.47 | 0.01
2606 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577281 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 125th Street over I-57 in Calumet Township. (Northeastern Illinois). | Bridge Improvement | 04/28/2009 | 05/24/2009 | 11/30/2009 | 1563214.81 | 0.01
2607 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577282 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 111th Street over I-57 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 06/01/2009 | 04/01/2010 | 09/30/2010 | 2934155.15 | 0.01
2608 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577283 | This project will extend the bridge life by repairing the bridge deck and new deck overlay to 0.06 miles of the 167th Street bridge over I-57 in the Cities of Oark Park and Country Club Hills in Cook | Bridge Improvement | 06/22/2009 | 07/17/2009 | 10/30/2009 | 605420.7 | 0.01
2609 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0577285 | This project will extend the pavement life by milling, patching and resurfacing 7.2 miles of I-57 from the Will Co Line to 175th St in the Villages of Country Cub Hills, Matteson, Bremen, and Richton | Pavement Improvement | 10/23/2009 | 03/26/2010 | 08/30/2010 | 11790438.23 | 14.48
2610 | Illinois | BUREAU |  | 11 | 0587024 | This project will extend the pavement life by resurfacing 6.2 miles of IL 92 between the cities of Ohio and Walnut (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 06/01/2009 | 08/30/2009 | 1872317.64 | 5.91
2611 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 0592052 | This project will extend the pavement life by milling, patching and resurfacing 1.78 miles in St. Clair County, IL (Southwest Illinois) | Pavement Improvement | 05/11/2009 | 05/15/2009 | 10/30/2009 | 945485.07 | 1.78
2612 | Illinois | PIKE |  | 18 | 0598102 | This project will extend the pavement life by resurfacing a 3.57 mile section of County Highway 2 from Baylis to New Salem in Pike County (West-Central Illinois). | Pavement Improvement | 04/01/2010 | 04/28/2010 | 06/30/2010 | 452500 | 3.06
2613 | Illinois | SCOTT |  | 18 | 0605107 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on County Highway 3 over Wolf Run Creek northwest of Bluffs (West-Central Illinois). | Bridge Improvement | 04/27/2010 |  | 06/30/2010 | 162350 | 0.01
2614 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0607078 | This project will extend the pavement life by resurfacing 1.11 miles on US Routes 52/30/6 in Joliet (Northeast Illinois). | Pavement Improvement | 05/11/2009 | 05/21/2009 | 08/30/2009 | 592221.76 | 1.16
2615 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0607079 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 30 over Hickory Creek in Joliet (Northeast Illinois). | Bridge Improvement | 05/11/2009 | 06/15/2009 | 09/30/2009 | 328811.26 | 0.01
2616 | Illinois | HENRY |  | 14 | 0611014 | This project will extend the pavement life by resurfacing 4 miles of IL 92 in the city of Rock Island (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/08/2009 | 08/30/2009 | 648677.93 | 2.34
2617 | Illinois | HENRY |  | 17 | 0611015 | This project will extend the pavement life by resurfacing a section of IL 81 near the city of Andover (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/11/2009 | 08/30/2009 | 384371.34 | 0.72
2618 | Illinois | MASON |  | 18 | 0614030 | This project will extend the pavement life by milling, patching, and resurfacing a portion of Illinois Route 78 from Havana to Saidora (West-Central Illinois). | Pavement Improvement | 04/30/2009 | 05/08/2009 | 11/30/2009 | 5267344.26 | 13.61
2619 | Illinois | MCDONOUGH |  | 17 | 0618003 | This project will extend pavement life by providing for 6.8 miles of surface improvements on IL Rte. 41 east of the City of Macomb which is approximately 50 miles west of the City of Peoria (West-Cent | Pavement Improvement | 07/30/2009 | 08/13/2009 | 11/30/2009 | 1475854.58 | 12.68
2620 | Illinois | FULTON |  | 17 | 0630006 | This project will extend the pavement life by providing for 4.84 miles of pavement repairs and resurfacing on IL Route 100 near the City of Bryant which is approximately 35 miles southwest of the Cit | Pavement Improvement | 04/28/2009 | 05/04/2009 | 08/30/2009 | 898945.73 | 4.97
2621 | Illinois | WILL |  | 11 | 0631015 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on IL 102 over Rayns Creek southeast of Wilmington (Northeast Illinois). | Bridge Improvement | 04/28/2009 | 06/08/2009 | 09/30/2009 | 238149.41 | 0.01
2622 | Illinois | HENRY |  | 14 | 0638010 | This project will extend the pavement life by resurfacing a section of US 6 in the city of Geneseo (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/26/2009 | 08/30/2009 | 622510.03 | 2.29
2623 | Illinois | HENRY |  | 14 | 0638013 | This project will substantially improve the roadway by constructing a new bridge over Hennepin Canal on IL 82 near the city of Geneseo (Northwest Illinois). | Bridge Replacement | 12/08/2009 | 04/05/2010 | 11/30/2010 | 1512229 | 0.02
2624 | Illinois | COLES |  | 15 | 0642123 | This project will substantially improve the roadway by constructing a new section of roadway near Mattoon (Southeast Illinois). | New Construction | 07/22/2009 | 08/10/2009 | 10/30/2010 | 307906 | 2.26
2625 | Illinois | STARK |  | 18 | 0643204 | This project will extend the pavement life by providing for 3.4 miles of pavement repair and resurfacing on IL Route 17 at Toulon which is approximately 30 miles northwest of the City of Peoria ( West | Pavement Improvement | 07/30/2009 | 08/03/2009 | 09/30/2009 | 514445.45 | 6.94
2626 | Illinois | CHRISTIAN |  | 19 | 0645112 | This project will extend the pavement life by resurfacing and other improvements on approximately six miles of County Highway 1 near Vanderville (West-Central Illinois). | Pavement Improvement | 04/27/2010 | 06/01/2010 | 08/30/2010 | 420098 | 9.19
2627 | Illinois | WHITESIDE |  | 17 | 0646069 | This project will extend the pavement life by resurfacing a section of IL 40 in the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 05/04/2009 | 09/08/2009 | 11/30/2009 | 1094176.41 | 1.25
2628 | Illinois | MARSHALL, STARK |  | 18 | 0646070 | This project will extend the pavement life by providing for 4.43 miles of pavement repair and resurfacing on IL Route 40 and IL Route 17 approximately 25 miles north of the City of Peoria (West-Centra | Pavement Improvement | 07/30/2009 | 08/10/2009 | 10/30/2009 | 1167478.32 | 8.07
2629 | Illinois | JO DAVIESS |  | 16 | 0650008 | This project will improve drainage by replacing 2 culverts on IL 78 in Jo Daviess County. | Bridge Improvement | 03/03/2010 | 05/03/2010 | 09/30/2010 | 646110.45 | 0.03
2630 | Illinois | LA SALLE, PUTNAM |  | 18 | 0653028 | This project will extend the pavement life by resurfacing 6.5 miles of IL 18 between the cities of Magnolia and Lostant (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 06/22/2009 | 09/30/2009 | 1273129.8 | 12.13
2631 | Illinois | SANGAMON |  | 18 | 0662063 | This project will substantially improve the roadway by reconstructing the intersection of IL Route 4 and Monroe/Old Jacksonville Rd. by providing new pavement and other roadway improvements in Springf | Pavement Improvement | 03/01/2010 | 04/15/2010 | 05/30/2011 | 2174000 | 3.37
2632 | Illinois | CUMBERLAND |  | 15 | 0662102 | This project will extend the pavement life by resurfacing and other improvements on FAS Route 662 in Cumberland County (Southeast Illinois). | Pavement Improvement | 04/09/2010 | 04/20/2010 | 08/30/2010 | 252088 | 1.2
2633 | Illinois | WARREN |  | 17 | 0665013 | This project will extend the pavement life by providing for 5.08 miles of pavement repair and resurfacing along IL Route 116 near the City of Roseville which is approximately 60 miles west of the City | Pavement Improvement | 07/27/2009 | 08/10/2009 | 10/30/2009 | 1085914.56 | 10.12
2634 | Illinois | KNOX, FULTON |  | 17 | 0665014 | This project provides for 8.3 miles of pavement repairs and resurfacing, extending the pavement life, on Illinois Route 116 near the City of St. Augustine which is approximately 40 miles west of the C | Pavement Improvement | 07/27/2009 | 08/06/2009 | 11/30/2009 | 2493135.9 | 14.56
2635 | Illinois | WOODFORD |  | 18 | 0673024 | This project will extend the pavement life by resurfacing of 5.90 miles of IL Routes 116 and 117 near the west city limits of the City of Roanoke which is approximately 20 mile east of the City of Peo | Pavement Improvement | 04/28/2009 | 05/07/2009 | 10/30/2009 | 2223904.2 | 6.12
2636 | Illinois | COLES |  | 15 | 0674111 | This project will substantially improve the roadway by replacing a box culvert on Fish Hatchery Road near Paradise (Southeast Illinois). | Bridge Improvement | 05/21/2009 | 06/17/2009 | 07/30/2009 | 162702.01 | 0.01
2637 | Illinois | EDGAR |  | 15 | 0678106 | This project will substantially improve the roadway by reconstructing and resurfacing a section of County Highway 21, approximately 50 miles southeast of Champaign (East-Central Illinois) | Pavement Improvement | 12/17/2009 | 07/19/2010 | 06/30/2010 | 336991 | 2.71
2638 | Illinois | LIVINGSTON |  | 15 | 0681037 | This project wil substantially improve the roadway by reconstructing a section of IL 116 in the village of Cullom. | Pavement Improvement | 04/30/2009 | 06/22/2009 | 05/30/2010 | 3082325.23 | 0.89
2639 | Illinois | LIVINGSTON |  | 15 | 0681038 | This project will extend the pavement life by resurfacing the road and replacing curb and gutter in the village of Saunemin (East-Central Illinois). | Pavement Improvement | 04/07/2010 | 05/06/2010 | 06/30/2011 | 650000 | 0.65
2640 | Illinois | HANCOCK |  | 17 | 0685028 | This project will extend the pavement life by resurfacing a portion of Illinois Route 9 in Hancock County from Dallas City to LaHarpe (West-Central Illinois). | Pavement Improvement | 04/28/2009 | 05/11/2009 | 10/30/2009 | 3754838.97 | 13.28
2641 | Illinois | CRAWFORD |  | 15 | 0696107 | This project will substantially improve the roadway by constructing a new bridge over Bennett Creek on County Highway 6 near Robinson in Crawford County (Southeast Illinois). | Bridge Replacement | 12/28/2009 | 05/10/2010 | 07/30/2010 | 202507 | 0.2
2642 | Illinois | VERMILION |  | 15 | 0697030 | This project will extend the life of the roadway by providing for 6.5 miles of pavement repairs, resurfacing, and bridge deck repairs on Illinois Route 9 in Vermilion County at the Indiana border (Eas | Pavement Improvement | 05/15/2009 | 06/15/2009 | 10/30/2009 | 2085502.67 | 6.63
2643 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 0701184 | This project will extend the pavement life by milling, patching and resurfacing 3. 67 miles of Interstate 55/70 from Canteen Creek to just north of Il 157. In addition this project will include brid | Pavement Improvement | 02/22/2010 | 03/29/2010 | 08/30/2010 | 9577498.24 | 7.26
2644 | Illinois | JASPER |  | 19 | 0704138 | This project will substantially improve the roadway by reconstructing a section of County Highway 6 near Gila in Jasper County (Southeast Illinois). | Pavement Improvement | 08/03/2009 | 08/11/2009 | 10/30/2009 | 299807 | 3.5
2645 | Illinois | CHAMPAIGN |  | 15 | 0709024 | This project will extend the pavement life by providing for 3.8 miles of pavement repairs and resurfacing on U.S. Route 136 north of Champaign (East-Central Illinois) | Pavement Improvement | 05/04/2009 | 05/29/2009 | 08/30/2009 | 956727.74 | 3.8
2646 | Illinois | VERMILION |  | 15 | 0711010 | This project will extend the life of the roadway by providing for 7.6 miles of pavement repairs, resurfacing, and culvert replacement on Illinois Route 119 in Vermilion County at the Indian border (Ea | Pavement Improvement | 05/06/2009 | 05/18/2009 | 10/30/2009 | 1935511.91 | 7.78
2647 | Illinois | EFFINGHAM |  | 19 | 0711108 | This project will extend the pavement life by adding new shoulders and resurfacing a portion of County Highway 25 south of Altamont (Southeast Illinois) | Pavement Improvement | 09/16/2009 | 10/07/2009 | 12/30/2009 | 361611 | 8
2648 | Illinois | FAYETTE |  | 19 | 0712106 | This project will substantially improve the roadway by replacing and repairing several culverts on County Highway 24 in Fayette County (Southeast Illinois). | Bridge Improvement | 08/24/2009 | 09/08/2009 | 12/30/2009 | 410144 | 6.24
2649 | Illinois | SHELBY |  | 19 | 0713111 | This project will substantially improve the roadway by reconstructing a section of Michigan and Logan Streets by providing new concrete pavement and other roadway improvements in Tower Hill (Southeast | Pavement Improvement | 12/10/2009 | 03/09/2010 | 08/30/2010 | 487714 | 0.82
2650 | Illinois | MONTGOMERY |  | 19 | 0721219 | This project will substantially improve the roadway by reconstructing a new bridge over East Fork of Shoal Creek on County Highway 8 near Filmore (West-Central Illinois) . | Bridge Replacement | 12/14/2009 |  | 08/30/2010 | 368721 | 0.01
2651 | Illinois | CHAMPAIGN |  | 15 | 0725005 | This project will extend the pavement life by resurfacing 0.9 miles of Illinois Route 10 in Champaign (East-Central Illinois). | Pavement Improvement | 03/15/2010 | 04/12/2010 | 06/30/2010 | 702614.72 | 2
2652 | Illinois | FRANKLIN |  | 12 | 0726058 | This project will extend the pavement life by milling, patching and resurfacing 6.58 miles of IL 148 in Franklin County, Illinois (Southern Illinios). | Pavement Improvement | 04/28/2009 | 06/08/2009 | 09/30/2009 | 2446918.04 | 13.45
2653 | Illinois | WINNEBAGO | ROCKFORD | 16 | 0734042 | This project will extend the pavement life by resurfacing a section of IL 251 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/26/2009 | 08/30/2009 | 318933.82 | 0.63
2654 | Illinois | GREENE |  | 17 | 0738107 | This project will improve roadway quality by milling and resurfacing County Highway 10 in Greene County (Southwest Illinois). | Pavement Improvement | 03/19/2010 | 05/17/2010 | 05/30/2010 | 323927 | 1.5
2655 | Illinois | MACON |  | 17 | 0741094 | This project will extend the pavement life by resurfacing a portion of Illinois Route 105 through the City of Decatur (Southeast Illinois). | Pavement Improvement | 04/30/2009 | 05/27/2009 | 10/30/2009 | 2385691.68 | 3.05
2656 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0741096 | This project will extend the structural life by completing repairs on the viaducts carrying Interstate 74 over IL 92 in the city of Moline (Northwest Illinois). | Bridge Improvement | 04/30/2009 | 05/11/2009 | 08/30/2009 | 756407.74 | 0.02
2657 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0741097 | This project will extend the pavement life by resurfacing a section of Interstate 74 and completing bridge repairs on several structures in the city of Moline (Northwest Illinois). | Pavement Improvement | 04/30/2009 | 05/11/2009 | 10/30/2010 | 11402089.34 | 5.75
2658 | Illinois | PIATT |  | 15 | 0741098 | This project will extend the pavement life by providing for 12.6 miles of pavement repairs and resurfacing on Illinois Route 105 west of Decatur (East-Central Illinois) | Pavement Improvement | 04/30/2009 | 05/20/2009 | 10/30/2009 | 2921806.75 | 12.66
2659 | Illinois | HENRY |  | 17 | 0742127 | This project will substantially improve the roadway by constructing new bridges over Opheim Road on Interstate 74 and other roadway improvements north of the city of Woodhull (Northwest Illinois). | Bridge Improvement | 12/08/2009 | 04/05/2010 | 11/30/2010 | 3537466.75 | 0.6
2660 | Illinois | MCLEAN |  | 11 | 0744238 | This project will extend the pavement life by providing for 4.24 miles of pavement repairs and resurfacing on Interstate 74 in Bloomington (East-Central Illinois) | Pavement Improvement | 04/28/2009 | 05/04/2009 | 08/30/2010 | 7205166.81 | 4.61
2661 | Illinois | PEORIA |  | 18 | 0744239 | This project will extend the pavement life by providing for 6.12 miles of pavement removal and resurfacing on a section of Interstate 74 approximately 7 miles west of the City of Peoria (West-Central | Pavement Improvement | 04/28/2009 | 04/29/2009 | 11/30/2009 | 7970484.99 | 5.72
2662 | Illinois | TAZEWELL |  | 18 | 0744240 | This project will extend the pavement life by providing for 6.41 miles of pavement repairs, resurfacing, and other improvements to Interstate 74 just east of Peoria (West-Central Illinois) | Pavement Improvement | 05/11/2009 | 05/26/2009 | 11/30/2009 | 7872358.65 | 6.73
2663 | Illinois | ADAMS |  | 17 | 0745079 | This project will extend the pavement life by resurfacing a portion of Illinois Route 104 to the east from Quincy (West-Central Illinois). | Pavement Improvement | 04/28/2009 | 05/18/2009 | 11/30/2009 | 4666894.14 | 5.78
2664 | Illinois | CHAMPAIGN, PIATT |  | 15 | 0745158 | This project will extend the pavement life by providing for 4.6 miles of pavement repairs, resurfacing, safety improvements on Interstate 74 west of Champaign (East-Central Champaign) | Pavement Improvement | 05/06/2009 | 05/28/2009 | 10/30/2009 | 3374493.73 | 10.95
2665 | Illinois | MOULTRIE, DOUGLAS |  | 15 | 0749022 | This project will extend the pavement life by resurfacing and adding shoulders to Illinois Route 133 through Arthur, Douglas County (East-Central Illinois). | Transportation Enhancements | 04/09/2010 | 05/10/2010 | 08/30/2010 | 88000 | 1.14
2666 | Illinois | MORGAN |  | 18 | 0753036 | This project will extend the pavement life by resurfacing a portion of Illinois Route 104 near Waverly (West-Central Illinois). | Pavement Improvement | 04/30/2009 | 07/27/2009 | 11/30/2009 | 2118638.78 | 2.1
2667 | Illinois | CALHOUN |  | 17 | 0754113 | This project will extend the pavement life by milling, patching and resurfacing of County Highway 1 from the Village of Hardin city limits to Lincoln Valley Road in Calhoun County, Illinois (Southwest | Pavement Improvement | 12/29/2009 | 06/01/2010 | 05/30/2010 | 157888 | 0.64
2668 | Illinois | SHELBY |  | 19 | 0766005 | This project will extend the pavement life by resurfacing a portion of Illinois Route 32 west of Oblong (Southeast Illinois). | Pavement Improvement | 04/23/2009 | 04/30/2009 | 10/30/2009 | 2075179.07 | 13
2669 | Illinois | CUMBERLAND |  | 15 | 0773008 | This project will extend the pavement life by resurfacing a portion of Illinois Route 121 in Greenup (Southeast Illinois). | Pavement Improvement | 04/23/2009 | 05/18/2009 | 09/30/2009 | 1464670 | 5.18
2670 | Illinois | BOND |  | 19 | 0777114 | This project will extend the pavement life by resurfacing Sorento Road from New Douglas road to Crane Road in Sorento, Illinois (Southwest Illinois). | Pavement Improvement | 11/03/2009 | 03/01/2010 | 05/30/2010 | 215000 | 5.65
2671 | Illinois | CLINTON |  | 19 | 0778106 | This project will improve driving quality by milling and resurfacing County Highway 14 in Clinton County (Southwest Illinois). | Pavement Improvement | 03/01/2010 | 06/02/2010 | 05/30/2010 | 327104 | 4.24
2672 | Illinois | MADISON |  | 19 | 0778107 | This project will extend the pavement life by resurfacing St. Rose Road from the city of Highland to the Clinton County line in Madison County (Southwest Illinois). | Pavement Improvement | 05/10/2010 | 05/12/2010 | 06/30/2010 | 173639 | 3.11
2673 | Illinois | BOND |  | 19 | 0779105 | Planning and design engineering to replace the bridge carrying North Pokey Road over Indian Creek in Bond County, IL (Southwest Illinois) | Other | 02/18/2010 | 02/18/2010 | 12/30/2010 | 66520 | 0.01
2674 | Illinois | CRAWFORD |  | 15 | 0781030 | This project will extend the pavement life by resurfacing a portion of Illinois Route 33 west of Oblong (Southeast Illinois). | Pavement Improvement | 05/11/2009 | 05/26/2009 | 07/30/2010 | 6162844.79 | 2.52
2675 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 0788004 | This project will substantially improve the roadway by reconstructing a section of Illinois Route 3 by providing new pavement and other roadway improvements in Venice (Southwest Illinois). | New Construction | 06/16/2009 | 10/12/2009 | 08/30/2011 | 3732615.13 | 1.26
2676 | Illinois | WASHINGTON |  | 19 | 0788112 | This project will improve driving quality by patching, resurfacing, and upgrading pavement markings along County Highway 24 near Hoyleton, Illinois (Southwest Illinois). | Pavement Improvement | 03/01/2010 | 07/06/2010 | 07/30/2010 | 340000 | 4
2677 | Illinois | CLAY |  | 19 | 0801230 | Preliminary engineering for a structure replacement over Laws Creek east of Ingram in Clay County. Section 09-00082-00-BR | Other | 06/19/2009 | 06/22/2009 | 04/30/2010 | 47000 | 0
2678 | Illinois | CLAY |  | 19 | 0801231 | This project will substantially improve the roadway by constructing a new bridge over Laws Creek on East Dundas Lane near Ingraham(Southeast Illinois). | Bridge Replacement | 04/19/2010 | 05/20/2010 | 09/30/2010 | 230366 | 0.01
2679 | Illinois | RICHLAND |  | 19 | 0801232 | This project will extend the pavement life by resurfacing and other improvements on East Dundas Lane near Dundas (Southeast Illinois). | Pavement Improvement | 04/21/2010 | 05/07/2010 | 05/30/2010 | 229556 | 1.19
2680 | Illinois | BUREAU |  | 11 | 0802064 | This project will extend the pavement life by resurfacing 7.5 miles of Interstate 80 near the city of Seatonville (East-Central Illinois). | Pavement Improvement | 05/21/2009 | 06/08/2009 | 10/30/2009 | 3681905.14 | 7.36
2681 | Illinois | LA SALLE |  | 11 | 0803130 | This project will extend the pavement life by resurfacing 30 miles of Interstate 80 in LaSalle County (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 05/17/2009 | 08/30/2009 | 1174180.11 | 29.99
2682 | Illinois | GRUNDY |  | 11 | 0803131 | This project will extend the pavement life by providing a surface treatment on 6.3 miles of Interstate 80 in western Grundy County (East-Central Illinois). | Pavement Improvement | 05/11/2009 | 06/15/2009 | 07/30/2009 | 1500910.6 | 6.3
2683 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0805071 | This project will extend the pavement life by resurfacing 6.125 miles of I-80 from 80th Ave to I-290 in the Tinley Park, Country Club Hills, and Hazel Crest. (Northeastern Illinois). | Pavement Improvement | 10/27/2009 | 04/05/2010 | 08/30/2010 | 15821320 | 13.11
2684 | Illinois | LAWRENCE |  | 15 | 0805108 | This project will extend the pavement life by widening and resurfacing 3.5 miles of County Highway 9 in Lawrence County (Southeast Illinois). | Pavement Improvement | 03/01/2010 | 04/29/2010 | 07/30/2010 | 284790 | 3.59
2685 | Illinois | CLARK |  | 15 | 0832013 | This project will extend the pavement life by providing a surface treatment on a seven mile section of IL Route 49 from Casey to the Cumberland County Line (Southeastl Illinois). | Pavement Improvement | 03/10/2010 | 06/01/2010 | 06/30/2010 | 398631.93 | 14
2686 | Illinois | CHAMPAIGN |  | 15 | 0836028 | This project will extend the pavement life by providing for 5.7 miles of pavement removal and resurfacing on Illinois Route 49 southeast of Champaign (East-Central Illinois) | Pavement Improvement | 05/06/2009 | 05/11/2009 | 08/30/2009 | 1083541.33 | 5.98
2687 | Illinois | WILL |  | 11 | 0840061 | This project will extend the pavement life by resurfacing 3.33 miles on IL 50north of Peotone (Northeast Illinois). | Pavement Improvement | 04/28/2009 | 05/05/2009 | 09/30/2009 | 1455187.96 | 4.11
2688 | Illinois | IROQUOIS |  | 15 | 0840062 | This project will extend the pavement life by resurfacing 10.7 miles of IL 49 near the city of Crescent City (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 06/08/2009 | 10/30/2009 | 2099137.03 | 10.8
2689 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0840063 | This project will extend the pavement life by resurfacing 2.06 miles on IL 50 in Monee/Peotone (Northeast Illinois). | Pavement Improvement | 10/16/2009 | 04/12/2010 | 06/30/2010 | 1043819.08 | 2.9
2690 | Illinois | GRUNDY |  | 11 | 0846019 | This project will extend the pavement life by resurfacing 6.4 miles of IL 53 near the city of Gardener (East-Central Illinois). | Pavement Improvement | 04/28/2009 | 06/13/2009 | 10/30/2009 | 1812639.8 | 6.3
2691 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0852011 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 52 over Jackson Creek 4 miles southeast of IL 53 (Northeast Illinois). | Pavement Improvement | 04/28/2009 | 06/09/2009 | 08/30/2009 | 284688.53 | 0.01
2692 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0856025 | This project will extend the pavement life by resurfacing 2.65 miles on IL 7 in Joliet and Crest Hill (Northeast Illinois). | Pavement Improvement | 10/23/2009 | 06/22/2010 | 07/30/2010 | 1739465.28 | 9.42
2693 | Illinois | PERRY |  | 12 | 0865106 | This project will extend the pavement life by resurfacing approximately 1 mile of Old DuQuoin Rd in DuQuoin. (Southern Illinois) | Pavement Improvement | 02/22/2010 | 05/01/2010 | 05/30/2010 | 249928 | 2.88
2694 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0866007 | This project will substantially improve the roadway by resurfacing 4.41 miles, widening, installing traffic signals and drainage improvements on IL 83 from Wisconsin State line to Petite Lake Rd in th | Pavement Improvement | 08/24/2009 | 09/08/2009 | 05/30/2011 | 13773780.98 | 9.24
2695 | Illinois | FRANKLIN |  | 12 | 0869036 | This project will improve safety by replacing an existing bridge on IL 34 near Benton, Illinois (Southern Illinois) | Bridge Replacement | 02/24/2010 | 05/03/2010 | 11/30/2010 | 730800.14 | 0.04
2696 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 0870011 | This project will extend the pavement life by resurfacing 1.06 miles on IL 53 in the City of Lombard (Northeast Illinois). | Pavement Improvement | 04/30/2009 | 05/18/2009 | 08/30/2009 | 460059.01 | 0.99
2697 | Illinois | WHITE |  | 19 | 0877013 | This project will substantially improve the roadway by constructing a new bridge over a tributary of Can Creek on IL 141 in White County, Illinois (Southern Illinois) | Bridge Replacement | 12/10/2009 | 01/18/2010 | 11/30/2010 | 785603.3 | 0.2
2698 | Illinois | WHITESIDE |  | 17 | 0881018 | This project will extend the pavement life by resurfacing 7.9 miles of Interstate 88 near the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 05/11/2009 | 05/26/2009 | 10/30/2009 | 3874419.56 | 8.45
2699 | Illinois | JOHNSON |  | 19 | 0885040 | This project will extend the pavement life by milling, patching and resurfacing 8.46 miles of IL 146 in Johnson County, Illinois (Southern Illinios). | Pavement Improvement | 06/02/2009 | 06/25/2009 | 08/30/2009 | 1557257.01 | 8.78
2700 | Illinois | WHITE |  | 15 | 0887108 | Grade slopes and place riprap to prevent erosion for 0.55 miles on County Highway 7 in White County, Illinois (Southern Illinois) | Pavement Improvement | 09/09/2009 | 10/08/2009 | 10/30/2009 | 234834.84 | 2
2701 | Illinois | WHITE |  | 15 | 0887109 | Grade slopes and place riprap to prevent erosion for 0.26 miles on County Highway 7 in White County, Illinois (Southern Illinois) | Pavement Improvement | 12/10/2009 | 12/15/2009 | 05/30/2010 | 66757 | 0.45
2702 | Illinois | GALLATIN |  | 15 | 0888122 | This project will extend the pavement life by resurfacing 4.48 of County Highway 3 in Gallatin Coutny, Illinois (Southern Illinois). | Pavement Improvement | 07/30/2009 | 11/09/2009 | 10/30/2009 | 190041 | 9
2703 | Illinois | SALINE |  | 19 | 0898107 | This project will extend the pavement life by resurfacing Harco Road from IL 13 to Brushy Creek Road in Saline County (Southern Illinois). | Pavement Improvement | 12/17/2009 |  | 07/30/2010 | 286154 | 4.39
2704 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0904117 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the Sayre Avenue Bridge over I-90 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 04/23/2009 | 06/08/2009 | 09/30/2010 | 2925184.16 | 0.01
2705 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0904118 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the Central Avenue Bridge over I-90 in the City of Chicago, Cook County. (Northeastern Il | Bridge Improvement | 04/28/2009 | 05/18/2009 | 11/30/2009 | 2788874.83 | 0.01
2706 | Illinois | JACKSON |  | 12 | 0915102 | This project will extend the pavement life by milling, patching and resurfacing 1.57 miles of Grand Tower Road in Jackson County, Illinois (Southern Illinios). | Pavement Improvement | 07/30/2009 | 08/27/2009 | 10/30/2009 | 382828 | 1.59
2707 | Illinois | UNION |  | 12 | 0926112 | This project will extend the pavement life by resurfacing St. Johns Road from the city of Dongola to IL127 in Union County (Southern Illinois). | Pavement Improvement | 04/12/2010 | 05/11/2010 | 06/30/2010 | 106915 | 5.68
2708 | Illinois | MASSAC |  | 19 | 0931110 | This project will extend the pavement life by resurfacing 1.35 miles of County Highway 11 in Massac County, Illinois (Southern Illinois). | Pavement Improvement | 09/10/2009 | 10/05/2009 | 10/30/2009 | 176112 | 2.7
2709 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0943416 | This project will extend the pavement life by resurfacing 6.97 miles of I-94 (Bishop Ford Expressway) from Martin Luther King Drive to 130th Street (south of Dolton Avenue) in Chicago in Cook County. | Pavement Improvement | 05/07/2009 | 05/18/2009 | 08/30/2010 | 14472368.3 | 5.26
2710 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0943417 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on I-94 over the Little Calumet River and Greenwood Ave. Additionally, the project will sub | Pavement Improvement | 04/29/2009 | 05/11/2009 | 05/30/2010 | 12851659.7 | 4.29
2711 | Illinois | ALEXANDER |  | 12 | 0946107 | This project will extend the pavement life by resurfacing 3.99 miles of Miller City Road in Alexander County, Illinois (Southern Illinois). | Pavement Improvement | 07/30/2009 | 09/09/2009 | 10/30/2009 | 184896 | 8
2712 | Illinois | WHITESIDE |  | 17 | 1225115 | This project will extend the pavement life by resurfacing sections of Albany Road in western Whiteside County (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 10/12/2009 | 11/30/2009 | 505781 | 9.18
2713 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 1238009 | This project will extend the pavement life by resurfacing 2.83 miles on IL 176 from Midlothian to IL 21 in the Villages of Libertyville and Mundelein (Northeastern Illinois) | Pavement Improvement | 10/21/2009 | 04/12/2010 | 07/30/2010 | 1118020.07 | 7.28
2714 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 1238010 | This project will extend the pavement life by resurfacing 1.17 miles on IL 176 from IL Rt. 21 to St. Mary's Rd in the Village of Libertyville (Northeastern Illinois). This project will also improve b | Pavement Improvement | 10/23/2009 | 04/05/2010 | 08/30/2010 | 858704.64 | 2.93
2715 | Illinois | PUTNAM |  | 18 | 1254110 | This project will extend the pavement life by resurfacing 2 miles of County Highway 16 in Putnam County (West-Central Illinois). | Pavement Improvement | 04/07/2010 | 04/19/2010 | 05/30/2010 | 137702 | 1.92
2716 | Illinois | LAKE, COOK, MCHENRY |  | 08 | 1270004 | This project will extend the pavement life by milling, patching and resurfacing 4.25 miles on Lake-cook Rd from Kane, McHenry, cook county line to Old Hart Rd in Barrington Hills (Northeastern Illinoi | Pavement Improvement | 12/07/2009 |  | 06/30/2010 | 994906.9 | 9.06
2717 | Illinois | KANKAKEE |  | 11 | 1299109 | This project will extend pavement life by resurfacing a section of County Highway 7 in northern Kankakee County (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 09/14/2009 | 09/30/2009 | 431841 | 6.56
2718 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1319001 | This project will extend the pavement life by 1.45 miles of resurfacing of Ballard Rd from Rand Rd easterly to Greenwood Ave in the Villages of DesPlaines, Glenview, Niles, Park Ridge, Cook County (No | Pavement Improvement | 10/28/2009 | 04/19/2010 | 06/30/2010 | 753728.33 | 3.78
2719 | Illinois | KANKAKEE |  | 11 | 1323114 | This project will extend the pavement life by resurfacing 7 miles of IL 115 near the city of Kankakee (East-Central Illinois). | Pavement Improvement | 04/23/2009 | 06/08/2009 | 10/30/2009 | 1380976.3 | 9.8
2720 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1332015 | This project will extend the pavement life by resurfacing 3.27 miles of IL 43 (Oakton St) from South DesPlaines Road to US 14 (Caldwell Ave) in Park Ridge & Niles in Cook County. (Northeastern Illinoi | Pavement Improvement | 06/01/2009 | 06/11/2009 | 11/30/2009 | 3101154.93 | 3.27
2721 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1340009 | This project will extend the pavement life by resurfacing 0.8 miles of Touhy Ave from IL50 to US41 and from Lawndale Ave to Kimball Ave in Village of Lincolnwood, Cook County (Northeastern Illinois). | Pavement Improvement | 10/28/2009 | 06/07/2010 | 06/30/2010 | 623113.94 | 2.26
2722 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 1363004 | This project will extend the pavement life by resurfacing 0.98 miles of Gunnison St. from IL 43 (Harlem Ave) to Nagle Ave in Chicago and the Village of Harwood Heights in Cook County (Northeastern Ill | Pavement Improvement | 11/03/2009 | 04/09/2010 | 06/30/2010 | 885374.8 | 2
2723 | Illinois | LA SALLE |  | 11 | 1365112 | This project will extend the pavement life by resurfacing 5 miles of County Highway 33 in LaSalle County (East-Central Illinois). | Pavement Improvement | 02/19/2010 |  | 06/30/2010 | 675633 | 6.03
2724 | Illinois | PEORIA | PEORIA | 18 | 1380106 | This project will extend the pavement life by providing for 3.4 miles of pavement repairs and resurfacing of Illinois Route 91 just north of Peoria (West-Central Illinois). | Pavement Improvement | 07/30/2009 | 08/17/2009 | 11/30/2009 | 1225314.17 | 6.98
2725 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 04 | 1395003 | This project will extend the pavement life by resurfacing 1.40 miles of Chicago Avenue from Lake St to Thatcher Rd in Melrose Park & Maywood in Cook County. (Northeastern Illinois). | Pavement Improvement | 04/23/2009 | 05/04/2009 | 08/30/2009 | 717530.88 | 1.47
2726 | Illinois | FULTON |  | 17 | 1458103 | This project will extend the pavement life by resurfacing a section of County Highway 6 near the City of Canton, approximately 25 miles southwest of Peoria (West-Central Illinois) | Pavement Improvement | 02/19/2010 | 04/27/2010 | 07/30/2010 | 488725 | 2
2727 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1459004 | This project will extend the pavement life by resurfacing 2.95 miles of 26th Street from IL 43 to IL 50 in Berwyn & Cicero in Cook County. (Northeastern Illinois). | Pavement Improvement | 04/28/2009 | 05/18/2009 | 09/30/2009 | 1271977.9 | 3.11
2728 | Illinois | TAZEWELL |  | 18 | 1464103 | This project wil extend the pavement life by providing for 0.41 mile of pavement removal and resurfacing on Locast Street in Delavan, south of Peoria (West-Central Illinois). | Pavement Improvement | 09/14/2009 | 07/06/2010 | 09/30/2009 | 125000 | 0.68
2729 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1467006 | This project will extend the pavement life by milling, patching and resurfacing 0.55 miles on 31st Street from IL 171 to DesPlaines Avenue and also on 31st St. from Golfview Rd to IL 171 in the Villag | Pavement Improvement | 04/28/2009 | 05/25/2009 | 07/30/2009 | 254965.07 | 0.62
2730 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1467007 | This project will extend the pavement life by milling, patching and resurfacing 3.61 miles of 31st St from Wolf Rd to IL 171 in the Villages of Westchester, Brookfield, LaGrange Park. (Northeastern I | Pavement Improvement | 09/09/2009 | 11/07/2009 | 07/30/2010 | 1894284.84 | 7.38
2731 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 1488004 | This project will extend the pavement life with 2.58 miles of milling, resurfacing, patching, curb & gutter, pavement marking & detector loops on 47th St from DuPage County line to East Ave, Cook Coun | Pavement Improvement | 10/21/2009 | 04/05/2010 | 08/30/2010 | 1335494.34 | 6.06
2732 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 1527012 | This project will substantially improve the roadway network by constructing four new bridges and rehabilitation of an existing bridge. Two of the new bridges are located at IL Rt 25/Dunham and IL Rt 2 | New Construction | 07/27/2009 | 08/18/2009 | 05/30/2011 | 1100000 | 0
2733 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1566002 | This project will extend the life of the pavement by surface removal, pavement patching, guardrail removal and replacement, pavement marking on 2.46 miles of 95th st from IL 171 (Archer Ave) to US 45 | Pavement Improvement | 05/06/2009 | 05/18/2009 | 08/30/2009 | 780486.71 | 2.54
2734 | Illinois | MASON |  | 18 | 1595103 | FAS 1595 (CH 19) - 4 miles southwest of Mason City at Sleepy Hollow Ditch-Bridge replacement. PE - Phase I | Other | 11/06/2009 | 11/06/2009 | 07/30/2010 | 26681 | 0.01
2735 | Illinois | MORGAN |  | 18 | 1614104 | This project will extend the pavement life by resurfacing a portion of County Highway 32 in Morgan County and adding lighting at an intersection for a safety improvement near Jacksonville (West-Centra | Pavement Improvement | 09/08/2009 | 09/08/2009 | 11/30/2009 | 328970 | 3.89
2736 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 1618001 | This project will extend the life of the pavement by resurfacing 0.72 miles of 175th Street from Governor's Highway to the intersection of 175th Street and Dixie Hwy in the Village of Homewood in Cook | Pavement Improvement | 05/06/2009 | 07/15/2009 | 08/30/2009 | 240159.29 | 0.75
2737 | Illinois | CLARK |  | 15 | 1660105 | This project will substantially improve the roadway by reconstructing a new structure over Hawks Creek one mile west of Dennison in Clark County (Southeast Illinois) | Bridge Improvement | 04/27/2010 | 06/07/2010 | 07/30/2010 | 349298 | 0.02
2738 | Illinois | CRAWFORD |  | 15 | 1697104 | FAS 1697 (CH 8) - 2 miles SE of Hardinville over Honey Creek (170 ft) PE I & II - bridge replacement | Other | 05/19/2010 | 05/19/2010 | 12/30/2010 | 26891 | 0.01
2739 | Illinois | ADAMS |  | 17 | 1721002 | This project will extend the pavement life by patching and resurfacing a portion Interstate 172 around Quincy, Illinois (West-Central Illinois). | Pavement Improvement | 05/04/2009 | 05/12/2009 | 08/30/2010 | 14584587.03 | 9.41
2740 | Illinois | CLINTON |  | 19 | 1784105 | This project will extend the pavement life by milling, patching and resurfacing 5.5 miles of County Highway 5 near Centralia, Illinois (Southwest Illinios). | Pavement Improvement | 08/12/2009 | 10/01/2009 | 12/30/2009 | 70000 | 11.04
2741 | Illinois | MARION |  | 19 | 1790103 | This project will extend the pavement life by milling, patching and resurfacing County Highway 32 from Jefferson Road to I-57 in Marion County, Illinois (Southwest Illinios). | Pavement Improvement | 08/05/2009 | 08/17/2009 | 10/30/2009 | 367987 | 4.53
2742 | Illinois | WABASH |  | 19 | 1819107 | This project will extend the pavement life by resurfacing a portion of Goodson Orchard Road in Wabash County (Southeast Illinois). | Pavement Improvement | 01/04/2010 | 04/14/2010 | 06/30/2010 | 147866 | 3.25
2743 | Illinois | MONROE |  | 12 | 1858103 | This project will extend the pavement life by providing a surface treatment on 2.18 miles of County Highway 12 from IL156 to County Highway 6 near Valmeyer, Illinois (Southwest Illinois) | Pavement Improvement | 08/25/2009 | 08/31/2009 | 09/30/2009 | 149789 | 4.18
2744 | Illinois | RANDOLPH |  | 12 | 1870108 | This project will extend the pavement life by resurfacing Wine Hill Road from Welge Road to County Highway 5 near Steelville, Illinois (Southwest Illinois). | Pavement Improvement | 12/14/2009 | 05/03/2010 | 06/30/2010 | 405449 | 2.92
2745 | Illinois | FRANKLIN |  | 12 | 1881114 | This project will extend the pavement life by resurfacing approximately 3.75 miles of Park Street Road in Franklin County.(Southern Illinois) | Pavement Improvement | 02/22/2010 | 05/01/2010 | 06/30/2010 | 352969 | 3.72
2746 | Illinois | WILLIAMSON |  | 12 | 1887106 | This project will extend the pavement life by resurfacing Saraville Road from Crab Orchard road to Ewing Road in Williamson County, Illinois (Southern Illinois). | Pavement Improvement | 12/17/2009 | 04/01/2010 | 06/30/2010 | 377444 | 2.8
2747 | Illinois | JACKSON |  | 12 | 1908001 | This project will extend the pavement life by milling, patching and resurfacing 7.8 miles of IL 151 in Jackson County, Illinois (Southern Illinios). | Pavement Improvement | 04/28/2009 | 05/12/2009 | 10/30/2009 | 2103336.12 | 7.84
2748 | Illinois | POPE |  | 19 | 1930119 | This project will extend the pavement life by resurfacing Bay City Road from IL Route 146 south for 4.3 miles in Pope County (Southern Illinois). | Pavement Improvement | 04/12/2010 | 05/10/2010 | 06/30/2010 | 180207 | 4
2749 | Illinois | STEPHENSON |  | 16 | 2051001 | This project will extend the pavement life by resurfacing 3 miles of Winneshiek Road in Stephenson County (Northwest Illinois). | Pavement Improvement | 03/08/2010 | 06/22/2010 | 05/30/2010 | 393026 | 3.17
2750 | Illinois | MARSHALL |  | 18 | 2370114 | This project will extend the pavement life by providing for 7.0 miles of removal and replacement of roadway surface on IL Route 26 near the City of Lacon which is approximately 25 miles north of the C | Pavement Improvement | 04/28/2009 | 05/08/2009 | 08/30/2009 | 1390284.14 | 7.01
2751 | Illinois | ADAMS |  | 17 | 2592102 | This project will extend the pavement life by resurfacing six miles of Adams County Highway near Loraine (West-Central Illinois). | Pavement Improvement | 07/30/2009 | 08/24/2009 | 10/30/2009 | 527967 | 12
2752 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 2612002 | This project will extend the bridge life by adding a new deck overlay, new joints, repairing the backwall of the north abutment and making other roadway improvements on Lemont Road over Des Plaines Ri | Bridge Improvement | 04/28/2009 | 05/28/2009 | 01/30/2010 | 4556823.83 | 0.01
2753 | Illinois | MOULTRIE |  | 15 | 2660101 | This project will substantially improve the roadway by reconstructing a section of County Highway 19 near Sullivan in Moultrie County (Southeast Illinois). | Pavement Improvement | 09/09/2009 | 09/16/2009 | 10/30/2009 | 262058 | 2.54
2754 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2697005 | This project will extend the bridge life by bridge deck patching and overlay on Willow Springs Road over the DesPlaines River and I&M Canal in the Village of Willow Springs in Cook County. (Northeaste | Bridge Improvement | 06/01/2009 | 06/15/2009 | 11/30/2009 | 4877955.21 | 0.01
2755 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 2706103 | This project will extend the pavement life by milling, patching and resurfacing 1.63 miles on IL Rt 43 (Waukegan Rd) from IL Rt 60 to Gage Lane in the Villages of Lake Forest and Lake Bluff (Northeast | Pavement Improvement | 10/23/2009 | 04/13/2010 | 07/30/2010 | 956788.18 | 3.3
2756 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 2711016 | This project will extend the pavement life by resurfacing 3.24 miles on IL Rt 131 from IL Rt 120 to just south of IL Rt 137 in the City of North Chicago (Northeastern Illinois) | Pavement Improvement | 05/06/2009 | 05/18/2009 | 09/30/2009 | 2702720.33 | 3.09
2757 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 2714010 | This project will extend the pavement life by resurfacing 0.55 miles of 25th Avenue from Belmont Ave to Addison Street in the Village of Franklin Park in Cook County. (Northeasern Illinois). | Pavement Improvement | 06/01/2009 | 10/13/2009 | 08/30/2009 | 404669.38 | 0.5
2758 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2719001 | This project will extend the pavement life by milling, patching and resurfacing 0.74 miles of East Avenue between 47th and 55th Streets in Summit (Northeastern Illinois). | Pavement Improvement | 06/01/2009 | 06/25/2009 | 09/30/2009 | 347208.07 | 1
2759 | Illinois | MACOUPIN |  | 17 | 2729105 | This project will extend the pavement life by resurfacing and other improvements on County Highway 3 at IL Route 4 east in Macoupin County (West-Central Illinois). | Pavement Improvement | 04/12/2010 | 05/17/2010 | 08/30/2011 | 598281 | 0.41
2760 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 2759003 | This project will extend the pavement life by resurfacing 1.29 miles of DesPlaines Avenue from Randolph Street to Roosevelt Road in Forrest Park in Cook Co. (Northeastern Illinois). | Pavement Improvement | 04/28/2009 | 05/04/2009 | 09/30/2009 | 919906.65 | 1.34
2761 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2759004 | This project will extend pavement life by resurfacing 1.038 miles of Des Plaines Avenue from Roosevelt Road to Cermak Road within the Village of Forest Park in Cook County (Northeastern Illinois). | Pavement Improvement | 10/28/2009 |  | 06/30/2010 | 767570.71 | 2.14
2762 | Illinois | WAYNE |  | 19 | 2821108 | This project will substantially improve the roadway by replacing the bridge over Martin Creek on County Highway 7 near Geff in Wayne County (Southeast Illinois) | Bridge Improvement | 03/15/2010 | 04/06/2010 | 07/30/2010 | 342153 | 0.01
2763 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 2831002 | This project will extend the bridge life by making full depth deck repairs, structural repairs, deck overlay, and other roadway improvements to the Kedzie Avenue bridge over the Cal-Sag Channel in Rob | Bridge Improvement | 10/23/2009 | 03/22/2010 | 08/30/2010 | 1297670.06 | 0.03
2764 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 2843006 | This project will extend the life of the pavement by resurfacing 1.07 miles of Dixie Highway just north of 183rd Street to Governor's Highway in Village of Homewood, Cook County (Northeastern Illinois | Pavement Improvement | 06/02/2009 | 07/02/2009 | 10/30/2009 | 490712.28 | 1.08
2765 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 2907002 | This project will extend the pavement life by resurfacing 1.15 miles of State Street from 60th Street to 69th Street within the City of Chicago in Cook County. (Northeastern, Illinois). | Pavement Improvement | 10/16/2009 | 04/12/2010 | 07/30/2010 | 1074300 | 1.44
2766 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 2943016 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements to the Burnham Avenue bridge over State Street, Indiana Harbor Beltway and CSX Railroad and | Bridge Improvement | 05/04/2009 | 05/06/2009 | 10/30/2009 | 5439185.65 | 0.01
2767 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 3033001 | This project will provide for pedestrian & bicyclist safety by constructing the DuPage River Bike & Pedestrian Trail from IL Route 59 & Riverview Park to the Prairie Creek Development in the Plainfiel | Transportation Enhancements | 06/01/2010 | 06/01/2010 | 10/30/2010 | 1574949 | 0
2768 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 3523006 | This project will extend the pavement life by milling, patching and resurfacing 2.6 miles on US 12 from 3rd Avenue to US 12/45 and along Rand Rd from Des Plaines River Road to Lundgren Ave in Des Plai | Pavement Improvement | 06/02/2009 | 06/13/2009 | 10/30/2009 | 1927842.05 | 2.22
2769 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 3592005 | This project will extend the pavement life by milling, patching and resurfacing 0.94 mile of Brainard Avenue from Burnham Ave to the Indiana State line in the Village of Burnham in Cook County. (North | Pavement Improvement | 06/01/2009 | 06/23/2009 | 09/30/2009 | 365144.42 | 1.08
2770 | Illinois | KANKAKEE |  | 11 | 4068002 | This project will extend the pavement life by resurfacing various roads in the village of Manteno (East-Central Illinois). | Pavement Improvement | 05/20/2010 |  | 10/30/2010 | 246398 | 0.35
2771 | Illinois | MORGAN |  | 18 | 4097005 | Transportation enhancement and road improvements necessary for Downtown Plaza improvements in Jacksonville, IL * | Transportation Enhancements | 03/15/2010 | 03/16/2010 | 05/30/2011 | 1356600 | 0
2772 | Illinois | CASS |  | 18 | 5002021 | This project will extend the pavement life by resurfacing a portion of Cass County Highway 7 from western edge of Beardstown for five miles to the west (West-Central Illinois). | Pavement Improvement | 09/15/2009 | 10/19/2009 | 11/30/2009 | 170449 | 1.46
2773 | Illinois | BOONE |  | 16 | 5004010 | This project will extend the pavement life by resurfacing a section of Newburg Road and other roadway improvements in the city of Belvidere (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/23/2009 | 11/30/2009 | 500000 | 5.6
2774 | Illinois | FRANKLIN |  | 12 | 5005011 | This project will substantially improve the roadway by reconstructing a section of North DuQuoin Street by providing new concrete pavement and other roadway improvements from McFall St. to the Interst | Pavement Improvement | 04/12/2010 | 05/03/2010 | 05/30/2011 | 229732 | 0.72
2775 | Illinois | FULTON |  | 17 | 5007022 | This project will extend the pavement life by providing for pavement repairs and resurfacing on Elm Street and Walnut Street in the City of Canton, approximately 25 miles southwest of Peoria (West-Cen | Pavement Improvement | 09/08/2009 | 09/18/2009 | 10/30/2009 | 261842 | 2.25
2776 | Illinois | FULTON |  | 17 | 5007023 | This project will provide for pedestrian safety by constructing 6 blocks of new concrete sidewalk along the north side of Ash Street in the City of Canton, approximately 25 miles southwest of Peoria ( | Safety/Traffic Management | 09/22/2009 | 09/22/2009 | 12/30/2009 | 200586 | 1.72
2777 | Illinois | JACKSON |  | 12 | 5008024 | This project will substantially improve mobility by constructing the missing section that connects Marion Street together by providing new concrete pavement, curb and gutter and sidewalk in the city o | New Construction | 09/10/2009 | 09/23/2009 | 08/30/2010 | 372283 | 0
2778 | Illinois | JACKSON |  | 12 | 5008025 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Carbondale, Illinois (Southern Illinois). | Pavement Improvement | 07/30/2009 | 08/03/2009 | 11/30/2009 | 455000 | 0.62
2779 | Illinois | WHITE |  | 19 | 5010010 | This project will extend the pavement life by resurfacing numerous roadway sections in the village of Carmi, Illinois (Southern Illinois). | Pavement Improvement | 10/27/2009 | 05/10/2010 | 12/30/2009 | 164004 | 0.74
2780 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011263 | This project will extend the pavement life by resurfacing and repair broken curb and gutter on Lindenthal Ave. from Washington st. to Poplar St. in the City of Highland, IL (Southwest Illinois). | Pavement Improvement | 08/03/2009 | 08/24/2009 | 09/30/2009 | 201250 | 0.44
2781 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011267 | Preliminary engineering for the milling and resurfacing of Madison Ave. in Edwardsville. Section 09-00099-00-RS | Other | 06/18/2009 | 06/22/2009 | 04/30/2010 | 34000 | 2
2782 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011268 | This project consists of milling and resurfacing along Madison Avenue in Edwardsville, Illinois (Southwest Illinois). Other improvements include constructing curbs, sidewalks, and ramps compliant wit | Pavement Improvement | 05/25/2010 | 06/07/2010 | 06/30/2010 | 242784 | 0.51
2783 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011269 | This project consists of patching, resurfacing, and widening of Fosterburg Road in Alton, Illinois (Southwest Illinois) Additionally, the construction of a culvert will improve roadway drainage. | Pavement Improvement | 03/01/2010 | 03/29/2010 | 06/30/2010 | 369000 | 0.5
2784 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011270 | This project will extend the pavement life by milling, patching and resurfacing .25 miles of Ostle Dr. from Newport Dr. to Waverly Dr. in Collinsville, Illinois (Southwest Illinios). | Pavement Improvement | 09/23/2009 | 09/23/2009 | 05/30/2010 | 165000 | 0.27
2785 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011271 | This project will extend the pavement life by milling, patching and resurfacing Main St. from Shamrock Ave. to Lakeside Ave. in the city of East Alton, Illinois (Southwest Illinios). | Pavement Improvement | 09/23/2009 | 09/23/2009 | 06/30/2010 | 400000 | 0.5
2786 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011272 | This project will improve driving quality by resurfacing and upgrading pavement markings along Glen Carbon Road in the Village of Glen Carbon, Illinois (Southwest Illinois). | Pavement Improvement | 04/27/2010 | 04/27/2010 | 06/30/2010 | 270991 | 1.05
2787 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011274 | This project will extend the pavement life by resurfacing Maryville Road from St. Clair Ave. to Terminal Ave. in Granite City, Illinois (Southwest Illinois). | Pavement Improvement | 12/29/2009 | 07/05/2010 | 06/30/2010 | 337912 | 0.46
2788 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011275 | This project will enhance pedestrian safety by constructing a 10 wide pedestrian walkway with concrete barrier on Ohio Ave. from IL Route 203 to Old Madison Road in the City of Madision, St. Clair Cou | Safety/Traffic Management | 05/03/2010 | 05/10/2010 | 06/30/2010 | 140238 | 0.18
2789 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011276 | Preliminary engineering for the resurfacing of West Main Street (Glen Carbonn Road) in the village of Glen Carbon. Section 09-00018-01-RS | Other | 06/18/2009 | 06/22/2009 | 10/30/2009 | 26905 | 2
2790 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011277 | Project consists of concrete pavement widening, construction of concrete curb and gutter and installation of storm sewer along Frank Scott Parkway West from Belleville West Parkway to Concordia Church | Pavement Improvement | 09/10/2009 | 09/21/2009 | 05/30/2010 | 640000 | 4.12
2791 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011278 | This project will extend the pavement life by milling, patching and resurfacing Broadway Ave. from Klein Ave. to State Street in city of Venice (Southwest Illinois). | Pavement Improvement | 05/03/2010 | 05/12/2010 | 06/30/2010 | 256952 | 0.6
2792 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011279 | Construct new sidewalk, Replace broken sidewalk and upgrade sidewalk/street crossings to accommodate those with disabilities along Monroe St. from St. Louis St. to Marner Park in the city of Lebanon, | Safety/Traffic Management | 09/14/2009 | 10/05/2009 | 04/30/2010 | 261747 | 1.47
2793 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011280 | This project will extend the pavement life by milling, patching and resurfacing of 9th street from Airline Drive to north of Old Edwardsville Road in the city of Wood River, IL (Southwest Illinois). | Pavement Improvement | 04/29/2010 | 05/03/2010 | 06/30/2010 | 260412 | 1.43
2794 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011284 | This project will substantially improve the roadway by reconstructing a section of North DuQuoin Street by providing new concrete pavement and other roadway improvements from McFall St. to the Interst | Pavement Improvement | 05/25/2010 |  | 07/30/2010 | 264319 | 0.13
2795 | Illinois | MONROE | ST. LOUIS (MO)-IL | 12 | 5011285 | This project consists of patching and resurfacing 0.35 miles of Palmer Road in the City of Columbia, Illinois (Southwest Illinois). Additionally, wider shoulders will improve safety. | Pavement Improvement | 03/02/2010 | 05/24/2010 | 06/30/2010 | 233597 | 0.46
2796 | Illinois | MONROE | ST. LOUIS (MO)-IL | 12 | 5011286 | This roadway widening project includes 0.27 miles of resurfacing and the addition of a new right turn lane from Maeystown Road onto IL 156 in Waterloo, Illinois (Southwest Illinois) Additionally, new | Pavement Improvement | 03/02/2010 | 04/26/2010 | 06/30/2010 | 220000 | 0.26
2797 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011287 | This project will extend the pavement life by milling, patching and resurfacing 1.36 miles of Doris Ave. from Range Lane to Jerome Lane in the city of Cahokia, IL (Southwest Illinois). | Pavement Improvement | 03/18/2010 | 03/18/2010 | 07/30/2010 | 327200 | 1.4
2798 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011290 | This project will extend the pavement life by milling, patching and resurfacing Pontoon Rd from Breckenridge Ln. to IL111 in Pontoon Beach, Illinois(Southwest Illinios). | Pavement Improvement | 08/25/2009 | 08/25/2009 | 05/30/2010 | 279500 | 1.55
2799 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011291 | This project will improve safety by providing pedestrians a signal to stop traffic and safely cross Monroe St. in the city of Lebenon. (Southwest Illinois) | Safety/Traffic Management | 04/23/2010 | 04/23/2010 | 05/30/2010 | 42832 | 0.01
2800 | Illinois | MADISON | ST. LOUIS (MO)-IL | 19 | 5011292 | This project will extend the pavement life by milling, patching and resurfacing .44 miles of Frontage Road from Harvestyme Lane to clara Dr. in Troy, Illinois (Northwest Illinios). | Pavement Improvement | 10/29/2009 | 01/26/2010 | 05/30/2010 | 134750 | 0.54
2801 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011293 | This project will extend the pavement life by resurfacing 6th street from IL 143 to Rohm Place in the city of Wood River, Illinois(Southwest Illinois). | Pavement Improvement | 12/22/2009 | 03/23/2010 | 05/30/2010 | 255300 | 0.59
2802 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011294 | This project will extend the pavement life by resurfacing, replace broken curb and gutter and sidewalks on Church Road from IL Route 157 to 50th St. in Centreville, IL (Southwest Illinois) . | Pavement Improvement | 05/03/2010 | 05/03/2010 | 08/30/2010 | 448019 | 1.24
2803 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011295 | This project will extend the pavement life by milling, patching and resurfacing of 17th street from Russell Ave. to East Broadway Ave. in the city of East St. Louis (Southwest Illinois). | Pavement Improvement | 05/03/2010 | 05/03/2010 | 07/30/2010 | 441427 | 0.78
2804 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011296 | This project consists of milling and resurfacing on a section of Union Hill Road in the City of Fairview Heights, Illinois (Southwest Illinois). Other improvements include constructing new sidewalks | Pavement Improvement | 03/01/2010 | 03/08/2010 | 07/30/2010 | 307200 | 0.44
2805 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011297 | This project will substantially improve the roadway by reconstructing a section of Concordia Church Road from IL route 158 to Frank Scott Parkway by providing new full depth bituminous pavement and ot | New Construction | 06/30/2010 |  | 11/30/2010 | 907252 | 0.93
2806 | Illinois | MADISON | ST. LOUIS (MO)-IL | 12 | 5011300 | This project enhances the aesthetics of th eroadway by planting trees along IL Route 3 from Rock Road to 20th Street in Granite City, Madison County (Southwest Illinois). | Transportation Enhancements | 05/18/2010 |  | 05/30/2010 | 19640 | 0.66
2807 | Illinois | MARION |  | 19 | 5012017 | This project will extend the pavement life by resurfacing Brookside Ave. from 15th street to 17th street in Wamac, Illinois (Southwest Illinois). | Pavement Improvement | 11/18/2009 | 04/19/2010 | 05/30/2010 | 41880 | 0.13
2808 | Illinois | MARION |  | 19 | 5012018 | Replace broken sidewalk and upgrade sidewalk/street crossings to accommodate those with disabilities at various locations along US Route 51 between Mcbriarty st. and Pearct St in Central City, Illinoi | Safety/Traffic Management | 03/10/2010 | 04/04/2010 | 06/30/2010 | 41370 | 1.54
2809 | Illinois | MARION |  | 19 | 5012019 | This project will extend the pavement life by milling, patching and resurfacing various streets in the City of Centralia, Illinois (Southwest Illinois). | Pavement Improvement | 05/07/2010 | 05/03/2010 | 07/30/2010 | 427484 | 1.11
2810 | Illinois | COLES |  | 15 | 5013016 | This project will extend the pavement life by resurfacing numerous roadway sections in the City of Charleston (Southeast Illinois). | Pavement Improvement | 09/10/2009 | 10/21/2009 | 11/30/2009 | 340000 | 0
2811 | Illinois | COLES |  | 15 | 5013017 | This project will extend the pavement life by resurfacing numerous roadway sections in Charleston, Coles County (Southeast Illinois). | Pavement Improvement | 06/29/2010 |  | 06/30/2010 | 319711 | 1.35
2812 | Illinois | RANDOLPH |  | 12 | 5014009 | This project will extend the pavement life by resurfacing numerous roadway sections in the City of Chester, Illinois (Southwest Illinois). | Pavement Improvement | 01/13/2010 | 04/28/2010 | 05/30/2010 | 253416 | 0.73
2813 | Illinois | DE WITT |  | 15 | 5015004 | This project will extend the pavement life by resurfacing 5 blocks of Washington Street in Clinton, approximately 25 miles south of Bloomington (East-Central Illinois) | Pavement Improvement | 10/15/2009 | 06/15/2010 | 08/30/2010 | 218724 | 0.31
2814 | Illinois | VERMILION |  | 15 | 5016037 | This project will extend the pavement life by resurfacing a section of Denmark Road in Danville, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 12/10/2009 | 03/30/2010 | 07/30/2010 | 700000 | 2.88
2815 | Illinois | VERMILION |  | 15 | 5016038 | This project will substantially improve Voorhees Street by constructing a new bridge over the CSX railroad and providing 0.8 mile of resurfacing in Danville, approximately 30 miles east of Champaign ( | Pavement Improvement | 12/14/2009 | 04/05/2010 | 10/30/2010 | 700000 | 1
2816 | Illinois | VERMILION |  | 15 | 5016039 | This project will extend the pavement life by resurfacing 0.8 mile of Main Street in Westville, approximately 35 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 01/08/2010 | 04/19/2010 | 06/30/2010 | 217531 | 0.99
2817 | Illinois | DE KALB |  | 14 | 5017040 | This project will extend the pavement life by resurfacing a section of Fairview Drive in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 08/12/2009 | 09/03/2009 | 10/30/2009 | 565839.09 | 2.92
2818 | Illinois | DE KALB |  | 16 | 5017041 | This project will substantially improve the roadway by reconstructing the intersection of Plank Road and Lindgren Road in the city of Sycamore (East-Central Illinois). | Pavement Improvement | 03/19/2010 | 04/19/2010 | 09/30/2010 | 472000 | 0.2
2819 | Illinois | DE KALB |  | 14 | 5017042 | This project will substantially improve the roadway by constructing a new intersection at Dresser Road and Normal Road in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 03/19/2010 | 04/19/2010 | 08/30/2010 | 402000 | 0.01
2820 | Illinois | LEE |  | 14 | 5018015 | This project will substantially improve the roadway by reconstructing a section of Hennepin Avenue by providing new concrete intersections, pavement and other roadway improvements in Dixon (Northwest | Pavement Improvement | 02/24/2010 | 04/28/2010 | 09/30/2010 | 482180 | 0.2
2821 | Illinois | PERRY |  | 12 | 5019007 | This project will extend the pavement life by milling, patching and resurfacing 0.55 miles of Cole Street from Division St. to Line St. in the city of DuQuoin, Illinois (Southern Illinois). | Pavement Improvement | 10/22/2009 | 11/16/2009 | 12/30/2010 | 201632 | 0.52
2822 | Illinois | EFFINGHAM |  | 19 | 5021025 | This project will substantially improve the roadway by constructing a section of Veterans Drive by providing new concrete pavement in Effingham (Southeast Illinois). | Pavement Improvement | 12/17/2009 | 03/08/2010 | 09/30/2010 | 374589 | 0.1
2823 | Illinois | WAYNE |  | 19 | 5022012 | This project will substantially improve the roadway by constructing a new box culvert over a branch of Pond Creek on East 4th Street in Fairfield, Wayne County (Southeast Illinois). | Bridge Replacement | 05/19/2010 | 06/03/2010 | 08/30/2010 | 163973 | 0.01
2824 | Illinois | CLAY |  | 19 | 5023010 | This project will substantially improve the roadway by reconstructing a section of Worthey Steet by providing new concrete pavement and other roadway improvements in Flora, Clay County (Southeast Ill | Pavement Improvement | 04/29/2010 | 05/03/2010 | 09/30/2010 | 153840 | 0.25
2825 | Illinois | STEPHENSON |  | 16 | 5024026 | This project will extend the pavement life and complete other roadway improvements by resurfacing and sidewalk improvements to numerous sections of streets in the city of Freeport (Northwest Illinois) | Pavement Improvement | 10/07/2009 | 10/13/2009 | 06/30/2010 | 685351 | 3.2
2826 | Illinois | KNOX |  | 17 | 5025043 | This project will substantially improve the roadway by reconstructing and providing additional roadway improvements for a 1/4 mile section of Carl Sandburg Drive in the City of Galesburg (West-Central | Pavement Improvement | 07/27/2009 | 07/30/2009 | 10/30/2009 | 249852 | 0.72
2827 | Illinois | KNOX |  | 17 | 5025044 | This project will improve a section of Knox Street by providing a new surface, sidewalks, and drainage improvements in the City of Galesburg (West-Central Illinois) | Pavement Improvement | 08/05/2009 | 08/05/2009 | 11/30/2009 | 471959 | 1.34
2828 | Illinois | KNOX |  | 17 | 5025046 | This project will improve a 1/2 mile section of South Seminary Street by providing a new surface, sidewalks, and drainage improvements in the City of Galesburg (West-Central Illinois) | Pavement Improvement | 10/20/2009 | 10/30/2009 | 05/30/2010 | 279099 | 1.02
2829 | Illinois | KNOX |  | 17 | 5025047 | This project will substantially improve the roadway by reconstructing 0.25 miles of State Street in the City of Galesburg, Knox County (West-Central Illinois). | Pavement Improvement | 02/24/2010 | 02/19/2010 | 06/30/2010 | 44000 | 0.01
2830 | Illinois | HENRY |  | 14 | 5026011 | This project will extend the pavement life by providing a surface treatment on numerous roadway sections in the city of Geneseo (Northwest Illinois). | Pavement Improvement | 08/27/2009 | 05/03/2010 | 05/30/2010 | 196006 | 0
2831 | Illinois | SALINE |  | 19 | 5027012 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Harrisburg. (Southern Illinois) | Pavement Improvement | 03/01/2010 | 04/27/2010 | 06/30/2010 | 298243 | 0.45
2832 | Illinois | WILLIAMSON |  | 12 | 5029011 | This project consists of improving safety by upgrading traffic signs to current standard throughout the village of Energy, Illinois (Southern Illinois). | Safety/Traffic Management | 11/13/2009 | 11/13/2009 | 10/30/2010 | 20614 | 0
2833 | Illinois | VERMILION |  | 15 | 5031008 | This project will extend the pavement life by resurfacing 0.8 mile of North Market Street in Hoopeston, approximately 50 miles northeast of Champaign (East-Central Illinois) | Pavement Improvement | 12/28/2009 | 04/05/2010 | 09/30/2010 | 180428 | 0.87
2834 | Illinois | MORGAN |  | 18 | 5032028 | This project will extend the pavement life by resurfacing a portion of the Village of South Jacksonville's East Vandalia Road (West-Central Illinois). | Pavement Improvement | 09/10/2009 | 10/27/2009 | 07/30/2010 | 105111 | 0.88
2835 | Illinois | MORGAN |  | 18 | 5032029 | This project will extend the pavement life by resurfacing and other improvements on Lafayette Street in Jacksonville, Morgan County (West-Central Illinois). | Pavement Improvement | 04/12/2010 | 05/10/2010 | 07/30/2010 | 603111 | 0.9
2836 | Illinois | JERSEY |  | 19 | 5033009 | – This project will provide for pedestrian accommodations by constructing a sidewalk along Fairgrounds Ave. from Cemetery Road to June Street and along June Street from Fairgrounds Ave. to East Carpen | Safety/Traffic Management | 04/29/2010 | 06/24/2010 | 07/30/2010 | 194560 | 1.04
2837 | Illinois | LA SALLE |  | 11 | 5036025 | This project will extend the pavement life by resurfacing a section of Richard Moyle Sr. Highway in the city of Oglesby (East-Central Illinois). | Pavement Improvement | 09/09/2009 | 09/09/2009 | 09/30/2009 | 110314 | 2.06
2838 | Illinois | LA SALLE |  | 11 | 5036026 | This project will extend the pavement life and improve pedestrian safety by resurfacing and reconstructing sidewalks for numerous roadway sections in the city of Peru (East-Central Illinois). | Pavement Improvement | 09/15/2009 | 10/01/2009 | 12/30/2009 | 258667 | 1.66
2839 | Illinois | LA SALLE |  | 11 | 5036027 | This project will extend the pavement life by resurfacing various streets in the city of LaSalle (East-Central Illinois). | Pavement Improvement | 02/24/2010 | 04/19/2010 | 06/30/2010 | 292651 | 0
2840 | Illinois | LOGAN |  | 18 | 5038013 | This project will extend the pavement life by resurfacing College Street from 8th to 11th and State St. from Kickapoo St to 4th Street in Lincoln (West-Central Illinois). | Pavement Improvement | 06/01/2010 |  | 07/30/2010 | 390507 | 1.31
2841 | Illinois | MCDONOUGH |  | 17 | 5040009 | This project will substantially improve the roadway by reconstructing a section of Ward Street with new concrete pavement and other roadway improvements in the City of Macomb which is approximately 60 | Pavement Improvement | 08/03/2009 | 08/19/2009 | 08/30/2010 | 376800 | 1.02
2842 | Illinois | MCDONOUGH |  | 17 | 5040010 | This project will substantially improve the roadway by reconstructing a section of Ward Street with new concrete pavement and other roadway improvements, including sidewalk, in the City of Macomb appr | Pavement Improvement | 10/23/2009 | 11/02/2009 | 08/30/2010 | 229517 | 0.26
2843 | Illinois | WILLIAMSON |  | 12 | 5041022 | LAND ACQUISITION FOR THE WIDENING OF MORGAN AVE. FROM CORBON ST. TO NORTH RUSSELL ST IN MARION, SECTION 08-00105-00-FP | Other | 08/26/2009 | 08/26/2009 | 10/30/2009 | 90000 | 0
2844 | Illinois | COLES |  | 15 | 5042018 | This project will extend the pavement life by resurfacing numerous roadway sections and sidewalks in Mattoon, Coles County (Southeast Illinois). | Pavement Improvement | 04/21/2010 | 05/26/2010 | 07/30/2010 | 553262 | 0
2845 | Illinois | LA SALLE |  | 11 | 5044011 | This project will extend the pavement life by widening and resurfacing a section of West Main Street in the city of Mendota (East-Central Illinois). | Pavement Improvement | 02/24/2010 | 03/24/2010 | 09/30/2010 | 219962 | 0.62
2846 | Illinois | MASSAC |  | 19 | 5045008 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Metropolis, Illinois (Southern Illinois). | Pavement Improvement | 09/09/2009 | 10/05/2009 | 10/30/2009 | 196066 | 0
2847 | Illinois | MASSAC |  | 19 | 5045009 | This project will enhance pedestrian and bicycle accommodations by constructing a bike trail from Fort Massac State Park to Strawberry Road in Massac County (Southern Illinois). | Transportation Enhancements | 04/12/2010 | 05/10/2010 | 05/30/2012 | 2092088 | 0
2848 | Illinois | WARREN |  | 17 | 5046007 | This project will extend the pavement life by resurfacing 0.60 mile of North Main Street in Monmouth, west of Galesburg (West-Central Illinois) | Pavement Improvement | 09/09/2009 | 09/21/2009 | 12/30/2009 | 297669 | 1.1
2849 | Illinois | GRUNDY |  | 11 | 5047008 | This project will extend the pavement life and complete other roadway improvements by resurfacing numerous roadway sections in the city of Morris (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 09/28/2009 | 10/30/2009 | 360796 | 0
2850 | Illinois | WABASH |  | 15 | 5048020 | This project will extend the pavement life by resurfacing a portion of 3rd Street in Mt. Carmel (Southeast Illinois). | Pavement Improvement | 10/16/2009 | 10/26/2009 | 12/30/2009 | 241438 | 1.52
2851 | Illinois | JEFFERSON |  | 19 | 5049023 | This project will substantially improve the roadway by reconstructing a section of North Davidson Ave from Illinois Route 15 north approx. 1 mile by providing new concrete pavement and other roadway i | Pavement Improvement | 04/22/2010 | 05/22/2010 | 07/30/2010 | 492101 | 0.3
2852 | Illinois | JACKSON |  | 12 | 5050013 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Murphysboro, Illinois (Southern Illinois). | Pavement Improvement | 12/10/2009 | 03/04/2010 | 06/30/2010 | 262974 | 0.7
2853 | Illinois | RICHLAND |  | 19 | 5051011 | This project will substantially improve the roadway by reconstructing a section of Butler Street by providing new concrete pavement and other roadway improvements in Olney, Richland County (Southeast | Pavement Improvement | 04/29/2010 | 06/15/2010 | 09/30/2010 | 261069 | 0.25
2854 | Illinois | LA SALLE |  | 11 | 5052026 | This project will extend the pavement life by resurfacing various streets in the city of Ottawa (East-Central Illinois). | Pavement Improvement | 02/19/2010 | 04/21/2010 | 07/30/2010 | 504448 | 0
2855 | Illinois | CHRISTIAN |  | 17 | 5053006 | This project will substantially improve the roadway by reconstructing a section of Chestnett Street by providing new concrete pavement and other roadway improvements in Pana (West-Central Illinois). | Pavement Improvement | 06/10/2010 |  | 07/30/2010 | 124843 | 0.17
2856 | Illinois | HENRY |  | 17 | 5053012 | This project will extend the pavement life and improve pedestrian safety by resurfacing numerous roadway sections and construction of sidewalks in the city of Kewanee (Northwest Illinois). | Pavement Improvement | 10/16/2009 | 05/03/2010 | 05/30/2010 | 391527 | 1.14
2857 | Illinois | EDGAR |  | 15 | 5054008 | This project will extend the pavement life by resurfacing 1 block of Crawford Street in Paris, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 10/14/2009 | 06/14/2010 | 05/30/2010 | 47395 | 0.14
2858 | Illinois | EDGAR |  | 15 | 5054009 | This project will extend the pavement life by resurfacing 4 blocks of Wood Street and Court Street in Parkis, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 12/09/2009 | 04/01/2010 | 06/30/2010 | 227164 | 0.25
2859 | Illinois | KENDALL |  | 14 | 5055001 | This project will extend pavement life by resurfacing a section of Center Street in the city of Plano (East-Central Illinois). | Pavement Improvement | 10/16/2009 | 04/15/2010 | 05/30/2010 | 323440 | 1.21
2860 | Illinois | LIVINGSTON |  | 15 | 5056017 | This project will extend pavement life by resurfacing a section of Deerfield Road in the city of Pontiac (East-Central Illinois). | Pavement Improvement | 09/15/2009 | 10/01/2009 | 12/30/2009 | 221422 | 2.02
2861 | Illinois | BUREAU |  | 11 | 5057006 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Princeton (East-Central Illinois). | Pavement Improvement | 10/08/2009 | 04/19/2010 | 07/30/2010 | 226889 | 0
2862 | Illinois | ADAMS |  | 17 | 5058030 | This project will extend the pavement life by resurfacing numerous roadway sections in Quicy in Adams County (West-Central Illinois). | Pavement Improvement | 03/02/2010 |  | 08/30/2010 | 1000000 | 0
2863 | Illinois | CHAMPAIGN |  | 15 | 5059013 | This project will extend the pavement life by resurfacing approximately 1.5 miles of Flessner Avenue and Pacesetter Drive in Rantoul, north of Champaign (East-Central Illinois) | Pavement Improvement | 09/15/2009 | 09/15/2009 | 06/30/2010 | 363886 | 1.47
2864 | Illinois | CRAWFORD |  | 15 | 5060008 | This project will substantially improve the roadway by constructing a section of North Allen Street by providing new concrete pavement and other roadway improvements in Robinson (Southeast Illinois). | Pavement Improvement | 12/17/2009 | 04/08/2010 | 08/30/2010 | 206350 | 0.08
2865 | Illinois | OGLE |  | 16 | 5061013 | This project will extend the pavement life and improve pedestrian safety by resurfacing and improving sidewalk on sections of Lincoln Highway and 4th Avenue in the city of Rochelle (Northwest Illinois | Pavement Improvement | 06/17/2010 |  | 06/30/2010 | 320082 | 0.42
2866 | Illinois | WHITESIDE |  | 17 | 5062027 | This project will extend the pavement life and improve pedestrian safety by resurfacing the roadway and replacing the sidewalk for a section of 12th Avenue in the city of Rock Falls (Northwest Illinoi | Pavement Improvement | 02/24/2010 | 06/03/2010 | 08/30/2010 | 291000 | 0.93
2867 | Illinois | MARION |  | 19 | 5064014 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Salem, Illinois (Southwest Illinois). | Pavement Improvement | 09/14/2009 | 09/14/2009 | 09/30/2009 | 219353 | 0
2868 | Illinois | MARION |  | 19 | 5064015 | This project will extend the pavement life by resurfacing South Marion Street from East Lake street to the County Fairgrounds in the city of Salem (Southwest Illinois) | Pavement Improvement | 05/04/2010 |  | 05/30/2010 | 19877 | 0.24
2869 | Illinois | BUREAU |  | 18 | 5065006 | This project will extend the pavement life and improve pedestrian safety by resurfacing and reconstructing sidewalks for a section of St. Paul Street in the city of Spring Valley (East-Central Illinoi | Pavement Improvement | 07/24/2009 | 08/01/2009 | 10/30/2009 | 163278 | 0.38
2870 | Illinois | LA SALLE |  | 11 | 5066014 | This project will extend the pavement life by resurfacing a section of Oakley Avenue in the city of Streator (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 10/05/2009 | 06/30/2010 | 437897 | 1.52
2871 | Illinois | CHRISTIAN |  | 19 | 5067017 | This project will extend the pavement life by resurfacing and other improvements on Spresser Street in Taylorville, Christian County (West-Central Illinois). | Pavement Improvement | 04/19/2010 | 06/07/2010 | 07/30/2010 | 345641 | 2.28
2872 | Illinois | FAYETTE |  | 19 | 5068024 | This project will substantially improve the roadway by reconstructing a section of Coles Street by providing new concrete pavement and other roadway improvements in Vandalia (Southeast Illinois). | Pavement Improvement | 12/14/2009 | 04/22/2010 | 07/30/2010 | 210978 | 0.26
2873 | Illinois | IROQUOIS |  | 15 | 5069005 | This project will extend the pavement life and improve pedestrian safety by resurfacing the roadway and replacing the sidewalks on sections of 5th Street, 8th Street, and Elm Street in the city of Wat | Pavement Improvement | 03/03/2010 | 04/16/2010 | 06/30/2010 | 171000 | 1.14
2874 | Illinois | FRANKLIN |  | 12 | 5071014 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of West Frankfort. (Southern Illinois). | Pavement Improvement | 02/22/2010 | 03/22/2010 | 06/30/2010 | 247911 | 1.19
2875 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074081 | This project will substantially improve the roadway by reconstructing a section of 30th Street in the city of Rock Island (Northwest Illinois). | Pavement Improvement | 03/03/2010 | 04/22/2010 | 09/30/2010 | 877027 | 0.95
2876 | Illinois | ROCK ISLAND |  | 17 | 5074082 | This project will extend the pavement life by resurfacing a section of First Street in the city of Coal Valley (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/28/2009 | 10/30/2009 | 174439 | 2.2
2877 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074083 | This project will substantially improve the roadway by reconstructing a section of 5th Avenue and other roadway improvements in the city of Moline (Northwest Illinois). | Pavement Improvement | 03/01/2010 | 04/19/2010 | 05/30/2011 | 967284 | 0.15
2878 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074084 | This project will extend the pavement life by resurfacing a section of 12th Avenue in the city of East Moline (Northwest Illinois). | Pavement Improvement | 03/03/2010 | 04/05/2010 | 07/30/2010 | 473631 | 1.5
2879 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074085 | This project will extend the pavement life by resurfacing a section of 221st Street in Rock Island County (Northwest Illinois). | Pavement Improvement | 03/03/2010 | 06/24/2010 | 07/30/2010 | 555482 | 3.63
2880 | Illinois | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074086 | This project will extend the pavement life by resurfacing a section of 10th Street in the city of Silvis (Northwest Illinois). | Pavement Improvement | 03/03/2010 | 04/22/2010 | 06/30/2010 | 351636 | 1.56
2881 | Illinois | DE KALB |  | 14 | 5076007 | This project will extend the pavement life by resurfacing a section of Railroad Street in the city of Sandwich (East-Central Illinois). | Pavement Improvement | 03/10/2010 | 07/12/2010 | 05/30/2010 | 196883 | 0.51
2882 | Illinois | BOND |  | 19 | 5078007 | This project will extend the pavement life by resurfacing South Fourth Street from US 40 to Franklin street in the city of Greenville (Southwest Illinois) | Pavement Improvement | 06/17/2010 | 07/19/2010 | 10/30/2010 | 210373 | 1.01
2883 | Illinois | UNION |  | 12 | 5080004 | This project will extend the pavement life by milling, patching and resurfacing 0.7 miles ofHeacock Street in the village of Jonesboro, Illinois (Southern Illinios). | Pavement Improvement | 10/22/2009 | 11/02/2009 | 12/30/2010 | 207003.22 | 0.73
2884 | Illinois | SANGAMON |  | 19 | 5082008 | LAND ACQUISITION FOR THE RECONSTRUCTION OF GORDON DRIVE FROM RAMBLEWOOD TO MAU DRIVE IN CHATHAM, SECTION 06-00028-00-WR | Other | 09/29/2009 |  | 11/30/2009 | 58000 | 0.53
2885 | Illinois | SANGAMON |  | 19 | 5082009 | This project will extend culvert and roadway life by extending the length of the culvert and adding an additional culvert along with drainage improvements on Gordon Drive over Grindstone Creek in Chat | Bridge Improvement | 03/23/2010 | 03/23/2010 | 08/30/2010 | 442000 | 0.01
2886 | Illinois | PERRY |  | 12 | 5084003 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Pickneyville. (Southern Illinois) | Pavement Improvement | 02/22/2010 | 05/01/2010 | 06/30/2010 | 165274 | 0.52
2887 | Illinois | PIATT |  | 15 | 5090001 | This project will extend the life of the roadway by replaceing a culvert on Buchanan Street in Monticello, Piatt County (East-Central Illinois). | Bridge Improvement | 03/01/2010 | 04/19/2010 | 06/30/2010 | 142064 | 0.1
2888 | Illinois | KANKAKEE |  | 15 | 5092004 | This project wil substantially improve the roadway by reconstructing a section of Burns Road West in the city of Bourbonnais. | New Construction | 08/04/2009 | 09/14/2009 | 07/30/2010 | 1875750 | 2.02
2889 | Illinois | PEORIA | PEORIA | 18 | 5093139 | This project consists of providing engineering design for a future highway improvement on Northmoor Road in the city of Peoria (West-Central Illinois). | Other | 07/16/2009 | 07/16/2009 | 09/30/2009 | 173272 | 0
2890 | Illinois | TAZEWELL | PEORIA | 18 | 5093140 | This project will extend the pavement life by removing existing pavement and resurfacing 0.91 mile of Parkway Drive in Pekin, just south of Peoria (West-Central Illinois) | Pavement Improvement | 10/28/2009 | 04/26/2010 | 12/30/2009 | 432276 | 2.3
2891 | Illinois | TAZEWELL | PEORIA | 18 | 5093141 | This project will extend the pavement life by providing for pavement removal and resurfacing on North Main Street in Morton, just east of Peoria (West-Central Illinois) | Pavement Improvement | 10/28/2009 | 06/01/2010 | 07/30/2010 | 212838 | 0.62
2892 | Illinois | PEORIA | PEORIA | 18 | 5093142 | This project will extend the pavement life by provide for pavement removal and resurfacing of a 0.51 mile section of Heading Avenue in West Peoria (West-Central Illinois) | Pavement Improvement | 09/25/2009 | 09/29/2009 | 09/30/2009 | 60800 | 1.04
2893 | Illinois | PEORIA | PEORIA | 18 | 5093143 | This project will extend the pavement life by resurfacing a 0.5 mile section of Garfield Avenue in Bartonville, just south of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 | 04/26/2010 | 06/30/2010 | 80564 | 0.49
2894 | Illinois | PEORIA | PEORIA | 18 | 5093144 | This project will extend the pavement life by providing for 0.39 mile of pavement removal and resurfacing on North Prospect Road in Peoria (West-Central Illinois) | Pavement Improvement | 09/25/2009 | 10/05/2009 | 10/30/2009 | 84714 | 0.94
2895 | Illinois | TAZEWELL | PEORIA | 18 | 5093145 | This project will extend the pavement life by providing for 0.38 mile of pavement removal and resurfacing on Fischer Avenue just south of Peoria (West-Central Illinois) | Pavement Improvement | 09/14/2009 | 09/23/2009 | 09/30/2009 | 69558 | 0.8
2896 | Illinois | TAZEWELL | PEORIA | 18 | 5093146 | This project will extend the pavement life by providing for 0.64 mile of pavement removal and resurfacing on Highview Road in East Peoria (West-Central Illinois) | Pavement Improvement | 08/04/2009 | 09/01/2009 | 09/30/2009 | 263249 | 1.16
2897 | Illinois | TAZEWELL | PEORIA | 18 | 5093147 | This project will extend the pavement life by providing for 3 blocks of pavement repairs and resurfacing in South Pekin, just south of Peoria (West-Central Illinois) | Pavement Improvement | 10/28/2009 | 04/19/2010 | 12/30/2009 | 106397 | 2.98
2898 | Illinois | TAZEWELL | PEORIA | 18 | 5093148 | This project will extend the pavement life by resurfacing 1 mile of Hillcrest Drive and Wilmor Road in the City of Washington, east of Peoria (West-Central Illinois) | Pavement Improvement | 12/14/2009 | 04/21/2010 | 05/30/2010 | 168113 | 1.13
2899 | Illinois | PEORIA | PEORIA | 18 | 5093149 | This project will extend the pavement life by resurfacing 0.5 miles of Truitt Avenue in Peoria County (West-Central Illinois). | Pavement Improvement | 02/19/2010 | 04/07/2010 | 06/30/2010 | 181366 | 0.77
2900 | Illinois | PEORIA | PEORIA | 18 | 5093153 | This project will substantially improve the roadway by reconstructing a section of Northmoor Road by providing new pavement and other roadway improvements in Peoria (West-Central Illinois). | Pavement Improvement | 03/08/2010 | 05/27/2010 | 11/30/2010 | 1939728 | 0.32
2901 | Illinois | DE KALB |  | 16 | 5094001 | This project will extend the pavement life by resurfacing numerous streets in the city of Genoa (East-Central Illinois). | Pavement Improvement | 09/08/2009 | 09/28/2009 | 11/30/2009 | 162552 | 1.78
2902 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099087 | This project will extend the pavement life by resurfacing a section of West Riverside Boulevard in the city of Rockford (Northwest Illinois). | Pavement Improvement | 12/15/2009 | 05/03/2010 | 08/30/2010 | 406820 | 0.44
2903 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099088 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Rockford (Northwest Illinois). | Pavement Improvement | 10/29/2009 | 05/03/2010 | 06/30/2010 | 926000 | 2.13
2904 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099090 | This project will extend the pavement life by resurfacing a section of Mill Road in the city of Cherry Valley (Northwest Illinois). | Pavement Improvement | 12/15/2009 | 05/03/2010 | 05/30/2010 | 48250 | 0.18
2905 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099091 | This project will widen and install traffic signals at the intersection of Ralston Road and Blue Bonnet Drive in Winnebago County (Northwest Illinois). | Pavement Improvement | 02/24/2010 | 05/27/2010 | 09/30/2010 | 703838 | 0.01
2906 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099092 | This project will extend the pavement life by resurfacing a section of Westfield Road in the city of Winnebago (Northwest Illinois). | Pavement Improvement | 09/15/2009 | 09/21/2009 | 10/30/2009 | 66750 | 1
2907 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099093 | This project will extend the pavement life by resurfacing sections of Willowbrook Road in Winnebago County (Northwest Illinois). | Pavement Improvement | 02/24/2010 | 05/24/2010 | 10/30/2009 | 188490 | 2
2908 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099094 | This project will extend the pavement life by resurfacing a section of McDonald Road in the city of Roscoe (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/14/2009 | 09/30/2009 | 92618.33 | 1
2909 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099095 | This project will extend the pavement life by resurfacing sections of Windsor Road and Riverside Boulevard in the city of Loves Park (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/21/2009 | 10/30/2009 | 455689.36 | 1.52
2910 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099096 | This project will extend the pavement life by resurfacing sections of Machesney Road and Mitchell Road in the village of Machesney Park (Northwest Illinois). | Pavement Improvement | 02/24/2010 | 05/18/2010 | 05/30/2010 | 195140 | 1.72
2911 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099097 | This project will extend the pavement life and improve safety by resurfacing the road and replacing the sidewalk on Longwood Street in the city of Rockford (Northwest Illinois). | Pavement Improvement | 02/24/2010 | 05/03/2010 | 08/30/2010 | 535479 | 0.32
2912 | Illinois | WINNEBAGO | ROCKFORD | 16 | 5099098 | This project will extend the pavement life of two roadways by resurfacing sections of Alpine Road, West State Street, and South Central Avenue in the city of Rockford (Northwest Illinois). | Pavement Improvement | 02/24/2010 | 05/03/2010 | 10/30/2010 | 1290143 | 1.86
2913 | Illinois | MACON |  | 17 | 5169042 | This project will extend the bridge life by repairing various bridge piers and making other bridge improvements on Garfield Bridge in the City of Decatur (Southeast Illinois). | Bridge Improvement | 08/03/2009 | 08/10/2009 | 11/30/2009 | 792000 | 0.02
2914 | Illinois | MACON |  | 17 | 5169043 | This project will substantially improve the roadway by constructing a new section of Fletcher Park Boulevard by providing new concrete pavement in Mt.Zion (Southeast Illinois). | New Construction | 12/14/2009 | 03/31/2010 | 10/30/2010 | 1229600 | 0.57
2915 | Illinois | MACON |  | 18 | 5169044 | This project will substantially improve the roadway by constructing two new bridges over Stevens Creek and the Tributary on County Highway 20 near Forsyth in Macon County (Southeast Illinois). | Bridge Replacement | 04/19/2010 | 06/07/2010 | 12/30/2010 | 480000 | 0.02
2916 | Illinois | MACON |  | 18 | 5169045 | This project will substantially improve the roadway by constructing a new bridge over Stevens Creek on MacArthur near Decatur in Macon County (Southeast Illinois). | Bridge Replacement | 03/19/2010 | 04/12/2010 | 05/30/2011 | 447408 | 0.01
2917 | Illinois | CHAMPAIGN |  | 15 | 5181040 | This project will substantially improve the roadway by widening 1.5 miles of Windsor Road in Urbana to 4 lanes and providing for other roadway and safety improvements (East-Central Illinois) | Pavement Widening | 06/05/2009 | 07/13/2009 | 06/30/2011 | 2150000 | 2.71
2918 | Illinois | CHAMPAIGN |  | 15 | 5181044 | This project will substantially improve the north leg of the 1st Street and Windsor Street intersection with concrete widening and other roadway improvements in Champaign (East-Central Illinois) | Pavement Improvement | 08/01/2009 | 08/01/2009 | 11/30/2009 | 750000 | 1.53
2919 | Illinois | CHAMPAIGN |  | 15 | 5181045 | This project consists of providing engineering design for a future highway improvement on Prospect Avenue in the city of Savoy (East-Central Illinois). | Other | 08/26/2009 | 09/01/2009 | 08/30/2010 | 305000 | 0.88
2920 | Illinois | CHAMPAIGN |  | 15 | 5181046 | This project will extend the pavement life by resurfacing 1.25 miles of Kirby Avenue in Champaign (East-Central Illinois) | Pavement Improvement | 12/10/2009 | 06/09/2010 | 08/30/2010 | 1160459 | 1.07
2921 | Illinois | JO DAVIESS |  | 16 | 5206004 | This project will extend the pavement life by resurfacing a section of 2nd Street in the city of East Dubuque (Northwest Illinois). | Pavement Improvement | 03/08/2010 | 04/26/2010 | 06/30/2010 | 88354 | 0.1
2922 | Illinois | MCLEAN |  | 11 | 5227046 | This project will substantially improve the roadway by reconstructing, widening, and adding other roadway improvements to 0.5 mile of Hamilton Road in Bloomington. | Pavement Improvement | 12/15/2009 | 03/01/2010 | 06/30/2011 | 834472 | 0.1
2923 | Illinois | MCLEAN |  | 15 | 5227050 | This project will provide safety enhancements by installing traffic signals at the intersection of Hershey Road and College Avenue in Bloomington (East-Central Illinois) | Safety/Traffic Management | 12/10/2009 | 03/17/2010 | 05/30/2010 | 200000 | 0.01
2924 | Illinois | MCLEAN |  | 15 | 5227051 | This project will extend the pavement life by resurfacing 1 mile of Ireland Grove Road in Bloomington (East-Central Illinois) | Pavement Improvement | 12/03/2009 | 04/06/2010 | 10/30/2010 | 470000 | 0.93
2925 | Illinois | MCLEAN |  | 11 | 5227053 | This project will substantially improve 1 block of Virginia Avenue by reconstructing the roadway with concrete pavement, adding other roadway improvements, and replacing the structure over Sugar Creek | Bridge Replacement | 12/14/2009 | 04/05/2010 | 10/30/2010 | 1414977 | 0.01
2926 | Illinois | WINNEBAGO |  | 16 | 5291011 | This project will extend the pavement life by resurfacing a section of East Union Street in the city of Rockton (Northwest Illinois). | Pavement Improvement | 09/08/2009 | 09/10/2009 | 10/30/2009 | 279191.55 | 1.84
2927 | Illinois | HENRY | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5789005 | This project will extend the pavement life by resurfacing a section of US 6 near the city of Colona (Northwest Illinois). | Pavement Improvement | 04/28/2009 | 05/07/2009 | 08/30/2009 | 289996.23 | 1.06
2928 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 7 | 6000201 | This project will extend the pavement life and provide for pedestrian safety by resurfacing, repairing sidewalk, improving traffic signals and streetscaping of Congress Parkway from Wells St. to Michi | Pavement Improvement | 04/07/2010 |  | 05/30/2012 | 9000000 | 0.48
2929 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,3,4,7 | 6000284 | This project will extend the pavement life by resurfacing numerous roadway sections in the Far South area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 07/09/2009 | 08/03/2009 | 12/30/2009 | 5419055 | 10
2930 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,3,4,7 | 6000285 | This project will extend the pavement life by resurfacing numerous roadway sections in the South area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 07/08/2009 | 08/03/2009 | 12/30/2009 | 11128315 | 22
2931 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,3,4,7 | 6000286 | This project will extend the pavement life by resurfacing numerous roadway sections in the Central area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 07/08/2009 | 07/07/2009 | 12/30/2009 | 7026785 | 12
2932 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 1,3,4,7 | 6000287 | This project will extend the pavement life by resurfacing numerous roadway sections in the North area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 07/01/2009 | 07/07/2009 | 12/30/2009 | 10101000 | 18
2933 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 7 | 6000292 | This project will extend the pavement life by milling, patching and resurfacing Chicago Ave. from Laramie Ave to Grand Ave, in the City of Chicago, IL (Northeastern Illinois). | Pavement Improvement | 11/04/2009 | 03/23/2010 | 11/30/2011 | 5753000 | 2.87
2934 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 7 | 6000293 | This project will extend the pavement life by resurfacing LaSalle Dr from Clark St. to Lake Shore Dr. (Northeast Illinois) | Pavement Improvement | 04/05/2010 | 06/10/2010 | 09/30/2010 | 13100002 | 0.41
2935 | Illinois | LA SALLE |  | 11 | 6120001 | This project will extend the pavement life by resurfacing a section of IL 178 near the city of Utica (East-Central Illinois). | Pavement Improvement | 04/23/2009 | 05/21/2009 | 08/30/2009 | 290585.59 | 0.78
2936 | Illinois | KANKAKEE |  | 11 | 6176002 | This project will substantially improve the roadway by reconstructing a section of Armour Road in the city of Bourbonnais (East-Central Illinois). | Pavement Improvement | 06/01/2009 | 04/05/2010 | 07/30/2010 | 3926224.7 | 1.25
2937 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 8003322 | This project will substantially improve the roadway by reconstructing Cemetary Rd between Washington St and Tri-State Parkway in the Village of Gurnee (Northeastern Illinois) | Pavement Improvement | 09/15/2009 | 11/01/2009 | 11/30/2010 | 7218540 | 2.94
2938 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 8003516 | This project will extend the pavement life by milling, patching and resurfacing 0.16 miles of Ridgewood Rd. in Riverside, Illinois (Northeastern Illinois) | Pavement Improvement | 03/01/2010 | 06/14/2010 | 05/30/2010 | 180000 | 0.13
2939 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 8003593 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to Madison Street in Villa Park (Northeast Illinois). | Safety/Traffic Management | 10/19/2009 | 11/09/2009 | 06/30/2010 | 260479 | 0.9
2940 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 8003809 | This project will substantially improve the roadway by reconstructing a section of Wright Blvd by widening the road, providing new pavement and other roadway improvements in the Village of Schaumburg, | Pavement Improvement | 03/03/2010 | 03/26/2010 | 05/30/2010 | 752264 | 0.86
2941 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 8003870 | This project will substantially improve the roadway by reconstructing a section of Wilmot Rd between Gordon Terrace and Deerfield Rd in the Village of Deerfield (Northeastern Illinois) by widening the | Pavement Improvement | 06/12/2009 | 08/01/2009 | 11/30/2009 | 1445773 | 2
2942 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 8003888 | This project will provide for pedestrian/bicycle safety by constructing a new shared use path adjacent to Washington Street in Naperville (Northeast Illinois). | Transportation Enhancements | 08/18/2009 | 08/31/2009 | 05/30/2010 | 1623500 | 0
2943 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003067 | This project will extend the life of the pavement by resurfacing Lawndale Ave from 47th St to Ogden Ave in Lyons in Cook County. | Pavement Improvement | 12/07/2009 | 04/12/2010 | 06/30/2010 | 600000 | 0.73
2944 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003176 | This project will extend the pavement life by resurfacing 0.99 miles of East Ave from Cermak Rd to Roosevelt Rd in Berwyn. (Northeastern Illinois). | Pavement Improvement | 12/10/2009 | 04/01/2010 | 04/30/2010 | 720000 | 0.97
2945 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003193 | This project will extend the pavement life by resurfacing, pavement markings, removing and replacing curb, gutter and sidewalks to assist persons with disabilities. This project is located on Deaan St | Pavement Improvement | 08/07/2009 | 09/21/2009 | 11/30/2009 | 313727 | 2.01
2946 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003199 | This project will extend the pavement life by milling, patching and resurfacing Wilson St from Randall Rd to Raddant Rd in the city of Batavia (Northeastern Illinois) | Pavement Improvement | 07/15/2009 | 07/15/2009 | 08/30/2009 | 848647.3 | 5.14
2947 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003218 | This project will extend the pavement life by resurfacing 0.51 miles of 63rd Street from LaGrange Rd to East Ave in Hodgkins in Cook County. (Northeastern Illinois). | Pavement Improvement | 11/10/2009 | 11/10/2009 | 05/30/2010 | 400000 | 0.52
2948 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003224 | This project will extend the pavement life by milling, patching, resurfacing and striping McDonald Rd from Burlington Rd to Kendall Rd in the village of Campton Hills (Northeastern Illinois) | Pavement Improvement | 07/01/2009 | 08/24/2009 | 11/30/2009 | 391000 | 2.97
2949 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003225 | This project will extend the pavement life by milling, patching, resurfacing and striping on Summit St from Dundee Ave to Hiawatha Drive in the city of Elgin (Northeastern Illinois) | Pavement Improvement | 08/26/2009 | 09/21/2009 | 12/30/2009 | 933840 | 1.2
2950 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003252 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Farnsworth Ave from Reckinger Rd to Molitor Rd in the City of Aurora (Northeastern Illinois) | Pavement Improvement | 07/09/2009 | 08/24/2009 | 10/30/2009 | 637000 | 1.83
2951 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003254 | This project will extend the pavement life by milling, patching and resurfacing 0.93 mile of Addison Road in the Village of Villa Park, DuPage County (Northeastern Illinois). | Pavement Improvement | 02/22/2010 | 05/03/2010 | 06/30/2010 | 916300 | 1.09
2952 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003278 | This project will extend the pavement life by milling, patching and resurfacing 0.98 miles of Central Park Ave. in Evergreen Park, Illinois (Northeastern Illinois) | Pavement Improvement | 03/03/2010 |  | 07/30/2010 | 500000 | 1
2953 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003292 | This project will extend the pavement life by resurfacing Blackhawk Trail from Plainfield Rd. to Wolf Rd. in the village of Indian Head Park, Cook County (Northeastern Illinois). | Pavement Improvement | 09/22/2009 | 10/07/2009 | 11/30/2009 | 350000 | 1.72
2954 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003299 | This project will extend the pavement life by resurfacing, installing relief sewer, patching, curb & gutter, sidewalks, water main replacement on Sheridan Rd. from South Blvd to Main St. in the city o | Pavement Improvement | 08/27/2009 | 09/10/2009 | 06/30/2010 | 1320000 | 1.22
2955 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003301 | This project will extend the pavement life by resurfacing and side walk repairs to accommodate people with disabilties on Washington St from Williams St to Main St in in the Village of Carpentersville | Pavement Improvement | 09/08/2009 | 09/21/2009 | 10/30/2009 | 160000 | 0.84
2956 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003302 | This project will extend the pavement life by resurfacing 1.11 miles of Prairie Ave from 47th St to Burlington Ave, curb & gutter replacement, patching & sanitary sewer replacement all located in the | Pavement Improvement | 12/10/2009 | 01/25/2010 | 06/30/2010 | 930000 | 1.12
2957 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003303 | This project will extend the pavement life by resurfacing 0.53 miles of Brainard Ave. from Harding Ave. to 31st St. in LaGrange Park, Cook County (Northeastern Illinois). | Pavement Improvement | 08/07/2009 | 09/01/2009 | 11/30/2009 | 319989 | 1
2958 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003304 | This project will extemd the pavement life by resurfacing 0.68 miles of Irving Park Rd. from Madison Dr. to Bartlett Rd. in the village of Streamwood, Cook County (Northeastern Illinois). | Pavement Improvement | 09/09/2009 | 09/28/2009 | 11/30/2009 | 465000 | 1.68
2959 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003305 | This project will extend the pavement life by resurfacing 0.7 miles of 10th St./Wilmette Ave. from Sheridan Road to Lake Avenue in Wilmette, Cook County (Northeastern Illinois). | Pavement Improvement | 12/10/2009 | 04/20/2010 | 06/30/2010 | 360000 | 0.7
2960 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003306 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Sundown Rd from McLean Bvld to IL 31 in the Village of South Elgin (Northeastern Illinois) | Pavement Improvement | 10/16/2009 | 05/03/2010 | 06/30/2010 | 976000 | 0.99
2961 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 17 | 9003307 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements and repairs to the structure carrying Old Willow Road over the Middle Fork of the north bran | Bridge Improvement | 12/22/2009 | 04/05/2010 | 06/30/2010 | 100000 | 0.02
2962 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003308 | This project will extend the pavement life by milling, patching and resurfacing 0.73 miles of Pfingsten Rd. in Northbrook, Illinois (Northeastern Illinois) | Pavement Improvement | 03/03/2010 | 07/12/2010 | 05/30/2010 | 660937 | 1.5
2963 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003309 | This project will extend the pavement life by resurfacing 1.47 miles of Overlook Drive from Waukegan Road to Golf Road, in the Village of Golf in Cook County (Northeastern Illinois). | Pavement Improvement | 09/10/2009 | 11/07/2009 | 12/30/2009 | 252000 | 1.72
2964 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003311 | This project will extend the pavement life by resurfacing on Bull Valley Rd from Shelby Court to Valley Hill Rd in the Village of Bull Valley (Northeastern Illinois) | Pavement Improvement | 10/16/2009 | 05/03/2010 | 12/30/2009 | 262105 | 5.06
2965 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003313 | This project will substantially improve the roadway by reconstructing a section of US 14 at E. Main Street by providing new pavement and other roadway improvements in the City of Cary (Northeast Illin | Pavement Improvement | 06/08/2010 |  | 08/30/2010 | 262000 | 0.1
2966 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003315 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on Algonquin Rd between Plum Tree Rd and US 14 in the Village of F | Pavement Improvement | 10/16/2009 | 05/04/2010 | 06/30/2010 | 262105 | 0.85
2967 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003316 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement of 1.22 miles onKaneville Rd from Randall Rd to IL Rt 38 in the Village of Geneva(Northeastern Il | Pavement Improvement | 12/14/2009 | 05/24/2010 | 06/30/2010 | 1064509 | 2.5
2968 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003317 | This project will extend the pavement life by resurfacing on Wondermere Rd from Greenwood Rd to Thompson Rd in the Village of Greenwood (Northeastern Illinois) | Pavement Improvement | 09/15/2009 | 09/22/2009 | 10/30/2009 | 262105 | 3.33
2969 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003318 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on State St from IL Rt 72 to north of Keyes Ave in Hampshire (Nort | Pavement Improvement | 12/16/2009 | 06/08/2010 | 06/30/2010 | 659972 | 1.6
2970 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003319 | This project will extend the pavement life by resurfacing 0.44 miles of 9th Ave from Roosevelt Rd to Bataan Drive in the Village of Maywood in Cook County (Northeastern Illinois). | Pavement Improvement | 10/08/2009 | 04/12/2010 | 05/30/2010 | 561900 | 1.32
2971 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003320 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings and detector loop replacement on Douglas Rd between Montgomery Rd a | Pavement Improvement | 12/16/2009 | 04/26/2010 | 06/30/2010 | 800773 | 1.34
2972 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003321 | This project will extend the pavement life by resurfacing Lehigh Ave from Oakton Street to Lincoln Avenue in the Village of Morton Grove in Cook County (Northeastern Illinois). | Pavement Improvement | 10/29/2009 | 05/10/2010 | 05/30/2010 | 356937 | 0.78
2973 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003322 | This project will extend the pavement life by resurfacing Montrose Ave from east of Cumberland Ave to Canfield Ave in the Village of Norridge in Cook County (Northeastern Illinois). | Pavement Improvement | 09/21/2009 | 11/01/2009 | 12/30/2009 | 368200 | 0.49
2974 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003323 | This project will extend the pavement life by resurfacing on Prairie St from west of US Rt 30/IL Rt 47 to Gordon Rd in the Village of Sugar Grove (Northeastern Illinois) | Pavement Improvement | 12/22/2009 | 04/26/2010 | 06/30/2010 | 632379 | 3.84
2975 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003324 | This project will extend the pavement life by resurfacing 0.51 miles of Westchester Blvd from Canterbury St to Roosevelt Rd in the Village of Westchester in Cook County (Northeastern Illinois). | Pavement Improvement | 10/08/2009 | 11/01/2009 | 05/30/2010 | 532235 | 1.53
2976 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003326 | This project will extend the pavement life by resurfacing 1.2 miles of Central Rd from Huber Lane to Harlem Avenue in Glenview in Cook County (Northeastern Illinois). | Pavement Improvement | 09/08/2009 | 10/05/2009 | 12/30/2009 | 720000 | 2.88
2977 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003327 | This project will extend the pavement life by resurfacing Division St. from 25th Ave to 14th Ave in Melrose Park in Cook County (Northeastern Illinois). | Pavement Improvement | 11/06/2009 | 05/08/2010 | 06/30/2010 | 548540 | 1.01
2978 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003329 | This project will extend the life of the pavement by resurfacing 0.90 miles of Dundee Ave from Lake Cook Rd. to IL Route 59 in Barrington, Cook County (Northeastern Illinois). | Pavement Improvement | 10/29/2009 | 05/03/2010 | 05/30/2010 | 308000 | 0.9
2979 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003332 | The project consists of improving safety by installing traffic signals and resurfacing the intersection at Chicago-Heights Glenwood Rd and Holbrook Rd in the Village of Glenwood, Illinois (Northeaster | Safety/Traffic Management | 01/26/2010 | 03/01/2010 | 08/30/2010 | 393800 | 0.01
2980 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003333 | This project consists of improving safety by installing street lighting along Broadway Ave in the City of Harvey, Illinois (Northeastern Illinois) | Safety/Traffic Management | 04/19/2010 |  | 07/30/2010 | 408345 | 0.54
2981 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003334 | This project consists of improving safety by installing street lighting along 138th St in the Village of Riverdale, Illinois (Northeastern Illinois) | Safety/Traffic Management | 03/08/2010 | 06/10/2010 | 07/30/2010 | 389800 | 1.26
2982 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003335 | This project consists of improving safety by installing street lighting along Bernice Rd in the City of Lansing, Illinois (Northeastern Illinois) | Safety/Traffic Management | 01/08/2010 |  | 06/30/2010 | 430000 | 1.35
2983 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 2 | 9003336 | This project consists of improving safety by installing emergency vehicle pre-emption equipment at 13 various intersections in the Village of Dolton, Illinois (Northeastern Illinois) | Safety/Traffic Management | 03/03/2010 |  | 07/30/2010 | 240000 | 0
2984 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003337 | This project will extend the pavement life by milling, patching and resurfacing 0.99 miles of East End Ave. in Chicago Heights, Illinois (Northeastern Illinois) | Pavement Improvement | 01/08/2010 |  | 06/30/2010 | 1086526 | 1.02
2985 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003338 | This project will substantially improve the roadway by reconstructing a section of Western Ave by providing new concrete pavement and other roadway improvements in Blue Island, Illinois (Northeastern | Pavement Improvement | 03/10/2010 | 05/03/2010 | 07/30/2010 | 445000 | 0.03
2986 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003340 | This project will substantially improve the roadway by widening IL 43 from 243 ft north of 71st Street for 0.329 miles to the north in the Village of Bridgeview in Cook County (Northeastern Illinois). | Pavement Improvement | 01/20/2010 | 03/15/2010 | 06/30/2010 | 500000 | 0.01
2987 | Illinois | GRUNDY | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003341 | This project will improve safety by installing lighting on Ridge Road and McEvilly Road in the village of Minooka (East-Central Illinois). | Safety/Traffic Management | 05/11/2010 |  | 06/30/2010 | 169800 | 1.22
2988 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003342 | This project will extend the pavement life by patching and resurfacing 173rd St/Elm Dr. in Hazel Crest, Illinois (Northeastern Illinois) | Pavement Improvement | 02/16/2010 | 04/01/2010 | 10/30/2010 | 483420 | 0.63
2989 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003343 | This project will enhance the roadway by installing 1.4 miles of tree planting, sidewalk improvements, pedestrian signals and lighting and signing along 95th St. (US 12/20) from 76th Avenue 88th St. i | Safety/Traffic Management | 05/12/2010 | 06/14/2010 | 11/30/2010 | 745693 | 1.45
2990 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003344 | This project will extend the pavement life by milling, patching and resurfacing Madison St. in the Village of Bellwood, Illinois (Northeastern Illinois) | Pavement Improvement | 02/24/2010 | 04/09/2010 | 06/30/2010 | 303200 | 0.51
2991 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003345 | This project will extend the life of the pavement by resurfacing N. Oak Ave from W Bartlett Ave to US 20 & resurfacing W. Bartlett Ave from IL 59 to Western Ave, Cook County (Northeastern Illinois). | Pavement Improvement | 12/14/2009 | 12/17/2009 | 07/30/2010 | 1435000 | 1.74
2992 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003349 | This project will extend the life of the pavement by resurfacing Thatcher Ave. from Central Ave. to Chicago Ave. in the village of River Forest, Cook County (Northeastern Illinois). | Pavement Improvement | 08/07/2009 | 09/01/2009 | 10/30/2009 | 428200 | 0.98
2993 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003352 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on Ringwood Rd between Spring Grove Rd and Johnsburg Rd in the vill | Pavement Improvement | 10/26/2009 | 05/03/2010 | 06/30/2010 | 262105 | 2.44
2994 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003353 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 0.90 miles on Ridge Rd between Deerwood Trail and IL Rt 120 in t | Pavement Improvement | 10/27/2009 | 10/27/2009 | 06/30/2010 | 262105 | 2.88
2995 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003354 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 1.27 miles on Valley View Rd between Crystal Lake Rd and IL Rt 1 | Pavement Improvement | 09/09/2009 | 09/28/2009 | 10/30/2009 | 262105 | 3.9
2996 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003355 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 1.40 miles on Ringwood Rd between McCullom Lake Rd and Devonshir | Pavement Improvement | 10/27/2009 | 10/27/2009 | 06/30/2010 | 262105 | 6.28
2997 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003356 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of on East Wonder Lake Rd between McCullom Lake Rd and Burnard Mill | Pavement Improvement | 12/10/2009 | 05/03/2010 | 05/30/2010 | 262105 | 1.61
2998 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003357 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Huntington Dr North from Stonegate Rd to Hanson Rd in the Village of Algonquin (Northeastern I | Pavement Improvement | 09/08/2009 | 09/21/2009 | 10/30/2009 | 262105 | 2.07
2999 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003358 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement including handicap ramps on 1.0 mile on Kreutzer Rd from Smith Rd to Northwestern Railroad tracks | Pavement Improvement | 09/14/2009 | 09/24/2009 | 10/30/2009 | 262105 | 0.88
3000 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003359 | This project will extend the life of the pavement by resurfacing Fullerton Ave. from Webster St. to 76th Ave. in Elmwood Park, Cook County (Northeastern Illinois). | Pavement Improvement | 08/07/2009 | 09/01/2009 | 11/30/2009 | 303000 | 1
3001 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003360 | This project will provide for pedestrian safety by constructing a sidewalk extension adjacent to Manhattan Road in the Village of Manhattan, Will County (Northeastern Illinois). | Safety/Traffic Management | 03/01/2010 | 05/03/2010 | 06/30/2010 | 100000 | 0.35
3002 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003361 | This project will extend the pavement life by resurfacing 0.81 miles on 135th Street in Romeoville (Northeast Illinois). | Pavement Improvement | 12/08/2009 | 04/05/2010 | 06/30/2010 | 415000 | 2.02
3003 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003362 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to Rathje Road in Peotone (Northeast Illinois). | Safety/Traffic Management | 12/17/2009 | 05/01/2010 | 05/30/2010 | 58000 | 0.23
3004 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003363 | This project will extend the pavement life by resurfacing on Sauk Trail in Frankfort (Northeast Illinois). | Pavement Improvement | 12/08/2009 | 04/15/2010 | 06/30/2010 | 190000 | 1
3005 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003364 | This project will extend the pavement life by resurfacing 99th St. from Oak Park Avenue to Ridgeland Avenue in Chicago Ridge in Cook County (Northeastern Illinois). | Pavement Improvement | 08/19/2009 | 10/03/2009 | 12/30/2009 | 353526 | 0.28
3006 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 3 | 9003366 | This project will enhance mobility by constructing a 10-foot wide asphalt pedestrian path for the Stony Creek Trail from Austin Ave to Mansfield Ave in Oak Lawn, Cook County (Northeastern Illinois). | Transportation Enhancements | 03/31/2010 | 03/31/2010 | 06/30/2010 | 373860 | 0
3007 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003367 | This project consists of improving safety by installing street lighting along Sauk Trail in the City of Lansing, Illinois (Northeastern Illinois) | Safety/Traffic Management | 03/16/2010 |  | 08/30/2010 | 351000 | 0.89
3008 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003368 | This project will extend the life of the pavement by resurfacing Green Bay Rd. from Park Ave to Scott Ave in Glencoe in Cook County (Northeastern Illinois). | Pavement Improvement | 12/10/2009 | 05/10/2010 | 06/30/2010 | 570587 | 1.28
3009 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003369 | This project will extend the pavement life by resurfacing on Barreville Rd from north village limits to Ames Rd in the Village of Prairie Grove (Northeastern Illinois) | Pavement Improvement | 12/28/2009 |  | 01/30/2010 | 262105 | 0.72
3010 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003370 | This project will improve safety by lighting 0.5 miles of US Route 30 in Mokena (Northeast Illinois) | Safety/Traffic Management | 11/19/2009 | 04/20/2010 | 05/30/2010 | 258742 | 0.03
3011 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003371 | This project will extend the pavement life by resurfacing 0.5 miles on Gaylord Road in Crest Hill (Northeast Illinois). | Pavement Improvement | 09/08/2009 | 09/11/2009 | 10/30/2009 | 153241 | 1.53
3012 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003372 | This project will extend the pavement life by resurfacing 0.7 miles of 167th Street from 88th Ave to Hobart Ave in Orland Hills, Cook County (Northeastern Illinois). | Pavement Improvement | 04/19/2010 | 05/10/2010 | 07/30/2010 | 275000 | 0.71
3013 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003373 | This project will extend the pavement life by resurfacing on 151st Street in Homer Glen (Northeast Illinois). | Pavement Improvement | 09/08/2009 | 09/28/2009 | 10/30/2009 | 366000 | 3
3014 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003374 | This project will extend the life of the pavement by resurfacing 0.80 miles of Tower Road from Hibbard Road to Sheridan Road excluding Green Bay Road & Sheridan Road intersections, minor curb repair a | Pavement Improvement | 10/29/2009 |  | 05/30/2009 | 420000 | 0.49
3015 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003375 | This project will extend the pavement life by milling, patching and resurfacing 0.49 miles of Laramie Ave. in Oak Forest, Illinois (Northeastern Illinois) | Pavement Improvement | 03/19/2010 | 04/26/2010 | 06/30/2010 | 297000 | 0.5
3016 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003376 | This project will extend the life of the pavement by resurfacing 0.97 miles of Main St. from IL 50 to Crawford Avenue in Skokie in Cook County (Northeastern Illinois). | Pavement Improvement | 12/28/2009 | 04/01/2010 | 06/30/2010 | 788937 | 1
3017 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003377 | This project will improve mobility and safety by installing traffic signals & interconnections at the intersection of 127th St & Timberline Drive in Lemont in Cook County (Northeastern Illinois). | Safety/Traffic Management | 12/08/2009 | 04/01/2010 | 06/30/2010 | 300000 | 0.01
3018 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003378 | This project will provide for pedestrian safety by removal & replacement of existing sidewalk with ADA ramps, and new curb & gutter along Roberts Road from 97th st to 111th St. and along 111th St from | Safety/Traffic Management | 10/29/2009 | 03/15/2010 | 06/30/2010 | 363000 | 6.94
3019 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003379 | This project will extend the pavement life by milling, patching and resurfacing 0.48 miles of Flossmoor Rd. in Flossmoor, Illinois (Northeastern Illinois) | Pavement Improvement | 03/30/2010 | 04/21/2010 | 06/30/2010 | 185000 | 0.47
3020 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003380 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to IL 59 in Naperville (Northeast Illinois). | Safety/Traffic Management | 01/04/2010 | 04/21/2010 | 07/30/2010 | 900000 | 3.16
3021 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003381 | This project will extend the pavement life by patching and resurfacing Church Road in the Village of Beecher, Will County (Northeastern Illinois). | Pavement Improvement | 12/29/2009 | 03/01/2010 | 06/30/2010 | 100000 | 1
3022 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003382 | This project will extend the life of the pavement by resurfacing 0.28 miles of Franklin Ave from Ruby St to Rose St / 25th St in Franklin Park in Cook County (Northeastern Illinois). | Pavement Improvement | 09/21/2009 | 09/21/2009 | 05/30/2010 | 503000 | 0.54
3023 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003383 | This project will extend the pavement life by resurfacing on Drauden Road in Plainfield (Northeast Illinois). | Pavement Improvement | 12/08/2009 | 04/06/2010 | 05/30/2010 | 210000 | 0.99
3024 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003384 | This project will extend the pavement life by milling, patching and resurfacing 0.78 miles of 135th St. in Crestwood, Illinois (Northeastern Illinois) | Pavement Improvement | 04/14/2010 | 05/17/2010 | 07/30/2010 | 225000 | 1.01
3025 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003385 | This project will improve mobility by constructing a sidewalk adjacent to Harlem Ave between 119th St and 131st St., on McCarthy Road between 76th Ave and 123rd St., and on 135th St. from Ridgeland to | Safety/Traffic Management | 05/10/2010 | 06/22/2010 | 08/30/2010 | 265303 | 2.07
3026 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003386 | This project will extend the pavement life by milling, patching and resurfacing Burlington Ave from Brainard Ave to Kensington Ave in Lagrange, Illinois (Northeastern Illinois) | Pavement Improvement | 02/22/2010 | 06/07/2010 | 06/30/2010 | 166900 | 0.27
3027 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003387 | This project will extend the pavement life by resurfacing Central Ave from 70th Place to a point 1200 feet south of 73rd St in Bedford Park in Cook County (Northeastern Illinois). | Pavement Improvement | 02/08/2010 |  | 08/30/2010 | 500000 | 1.01
3028 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003389 | This project will extend the pavement life by resurfacing 1.10 miles on Thomas Dillon Drive in Channahon (Northeast Illinois). | Pavement Improvement | 10/23/2009 | 04/27/2010 | 12/30/2009 | 189000 | 1.12
3029 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003390 | This project will enhance mobility by constructing a 0.4 mile multi-use path on the east side of 104th Ave from 167th St to 163rd Place in the Village of Orland Park, Cook County (Northeastern Illinoi | Transportation Enhancements | 04/29/2010 | 05/09/2010 | 08/30/2010 | 263547 | 0
3030 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003391 | This project will extend the pavement life by milling, patching and resurfacing 0.51 mile of Clarendon Hills Road in the Village of Willowbrook, DuPage County (Northeastern Illinois). | Pavement Improvement | 05/12/2010 | 06/09/2010 | 05/30/2010 | 215813 | 0.5
3031 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003392 | This project will provide for pedestrian safety by constructing a new sidewalks adjacent to Harlem Ave, 107th St, and Ridgeland Ave in Worth, Illinois (Northeastern Illinois) | Safety/Traffic Management | 04/08/2010 | 05/26/2010 | 07/30/2010 | 449000 | 0.83
3032 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003393 | This project will extend the pavement life by milling, patching and resurfacing 0.49 miles of Kostner Ave. in Crestwood, Illinois (Northeastern Illinois) | Pavement Improvement | 03/03/2010 | 04/15/2010 | 06/30/2010 | 212000 | 1
3033 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003394 | This project will extend the pavement life by resurfacing 0.39 miles of 34th St. from Union Ave to Holeman Ave in South Chicago Heights, Cook County (Northeastern Illinois). | Pavement Improvement | 02/02/2010 | 04/26/2010 | 07/30/2010 | 369316 | 0.37
3034 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003395 | This project will improve mobility by constructing 1.0 miles of sidewalk on the east side of Kedzie Ave from 153rd St to 159th St. in the City of Markham, Cook County (Northeastern Illinois). | Safety/Traffic Management | 05/24/2010 | 05/24/2010 | 06/30/2010 | 246647 | 2.64
3035 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003396 | This project will extend the pavement life by resurfacing on Wallin Drive in Plainfield (Northeast Illinois). | Pavement Improvement | 12/08/2009 | 04/06/2010 | 05/30/2010 | 280000 | 1.01
3036 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003397 | This project will extend pavement life by milling, patching and resurfacing an eight block section of Janes Avenue in the City of Woodridge (Northeastern Illinois). | Pavement Improvement | 03/02/2010 |  | 06/30/2010 | 505356 | 2
3037 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 5 | 9003399 | This project will extend the life of the bridge carrying Whitehall Ave over Addison Creek by removing existing superstructure & replace with wide flange steel beam & concrete deck & roadway improvemen | Bridge Improvement | 03/31/2010 | 03/31/2010 | 07/30/2010 | 553200 | 0.2
3038 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003400 | This project will extend the pavement life by milling, patching and resurfacing 1.02 mile of Lies Road in the Village of Carol Stream, DuPage County (Northeastern Illinois). | Pavement Improvement | 02/19/2010 | 05/03/2010 | 07/30/2010 | 809000 | 1.01
3039 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003403 | This project will extend the pavement life by milling and resurfacing Powis Road from North Avenue to Smith Road in the City of West Chicago (Northeastern Illinois). | Pavement Improvement | 06/10/2010 |  | 06/30/2010 | 246019 | 1.15
3040 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003405 | This project will extend the pavement life by milling and resurfacing Joliet Street from IL Route 59 to Geneva Street in the City of West Chicago (Northeastern Illinois). | Pavement Improvement | 05/18/2010 | 06/28/2010 | 08/30/2010 | 441800 | 2.08
3041 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003408 | This project will extend the pavement life by milling and resurfacing 1.21 miles of Bruce Road and 163rd Street in the City of Lockport (Northeastern Illinois). | Pavement Improvement | 03/01/2010 | 06/09/2010 | 06/30/2010 | 415000 | 1.88
3042 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003410 | This project will extend the pavement life by milling, patching and resurfacing 1.02 mile of St. Charles Road in the City of Elmhurst (Northeastern Illinois). | Pavement Improvement | 02/22/2010 | 05/03/2010 | 06/30/2010 | 419988 | 0.51
3043 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003412 | This project will substantially improve the roadway by reconstruction a section of First Street from Myrtle Avenue to Clara Place in the City of Elmhurst (Notheastern Illinois). | Pavement Improvement | 04/29/2010 |  | 06/30/2010 | 310000 | 0.73
3044 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003417 | This project will extend the pavement life by milling and resurfacing 1.13 miles of Park Boulevard and Lambert Road in the Village of Glen Ellyn, DuPage County (Northeastern Illinois). | Pavement Improvement | 05/20/2010 |  | 07/30/2010 | 626553 | 1.09
3045 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003418 | This project will enhance mobility by constructing a new sidewalk on Governors Highway from Sauk Trail to Maple Ave, from Poplar Ave to north Maple Ave, from 400 feet south of Sauk Trail to Sauk Trail | Safety/Traffic Management | 06/08/2010 |  | 05/30/2010 | 106823 | 0.63
3046 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003419 | This project consists of improving safety and traffic enhancement by 0.78 miles of traffic signal modernization on US Rt 14 from Dole Ave to Devonshire Lane/Kieth Ave in Crystal Lake (Northeastern Ill | Safety/Traffic Management | 12/03/2009 | 03/02/2010 | 07/30/2010 | 262105 | 0.77
3047 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003420 | This project will extend the pavement life with 3.0 miles of concrete pavement patching, asphalt overlay, shoulder rehabilitation, new pipe underdrains, sidewalk removal & replacement on E. Frontage R | Pavement Improvement | 09/21/2009 | 10/01/2009 | 07/30/2010 | 3780000 | 7.89
3048 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003421 | This project will extend the pavement life by milling, patching and resurfacing 1.1 miles of St. Charles Road from Illinois Route 53 to Grace Street in the Village of Lombard, DuPage County (Northeast | Pavement Improvement | 05/26/2010 | 06/29/2010 | 08/30/2010 | 47063 | 1.48
3049 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003422 | This project will extend the pavement life by milling, patching and resurfacing 127th St from 80th Ave to 123rd St and 121st St from Southwest Highway to 80th Ave in Palos Park, Illinois (Northeastern | Pavement Improvement | 02/24/2010 |  | 06/30/2010 | 395000 | 0.64
3050 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003423 | This project will extend the pavement life by milling, patching and resurfacing 0.76 miles of Gilbert Ave. in Western Springs, Illinois (Northeastern Illinois) | Pavement Improvement | 03/01/2010 | 03/17/2010 | 06/30/2010 | 672700 | 0.78
3051 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003424 | This project will extend the pavement life by resurfacing numerous roadway sections in DuPage County (Northeastern Illinois). | Pavement Improvement | 12/08/2009 | 05/10/2010 | 07/30/2010 | 531535 | 1.1
3052 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003425 | This project will extend the pavement life by resurfacing 1.09 miles on Gardield Street in Hinsdale (Northeast Illinois) | Pavement Improvement | 12/09/2009 | 04/05/2010 | 11/30/2010 | 1539000 | 1.01
3053 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003426 | This project will extend the pavement life by milling, patching and resurfacing 187th St. from Dixie Highway to Riegel Rd in Homewood, Illinois (Northeastern Illinois) | Pavement Improvement | 03/03/2010 | 04/12/2010 | 06/30/2010 | 236000 | 0.66
3054 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003428 | This project will extend the pavement life by milling, patching and resurfacing 139th St. from Crawford Ave to Coopers Grove Rd in Robbins, Illinois (Northeastern Illinois) | Pavement Improvement | 01/08/2010 | 05/01/2010 | 08/30/2010 | 935000 | 2.42
3055 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003429 | This project will extend the pavement life by milling, patching and resurfacing 0.69 miles of Woodlawn Ave. in Ford Heights, Illinois (Northeastern Illinois) | Pavement Improvement | 01/08/2010 | 03/01/2010 | 07/30/2010 | 550000 | 1.36
3056 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003430 | This project will provide for pedestrian safety by constructing a new sidewalks adjacent to Algonquin Rd from Seymour Ave to Mt. Prospect Rd. in Des Plaines, Illinois (Northeastern Illinois) | Safety/Traffic Management | 02/24/2010 | 04/05/2010 | 07/30/2010 | 200000 | 0.7
3057 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003431 | This project will extend the pavement life by resurfacing University Parkway from Crawford Avenue to Steger-Monee Road in the Village of University Park, Will County (Northeastern Illinois). | Pavement Improvement | 03/31/2010 | 05/31/2010 | 07/30/2010 | 372807 | 2.42
3058 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003436 | This project will extend the pavement life by resurfacing 0.91 miles on Boughton Road in Bolingbrook (Northeast Illinois). | Pavement Improvement | 10/01/2009 | 10/12/2009 | 12/30/2009 | 660000 | 3.21
3059 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003438 | This project consists of improving safety by upgrading traffic signals on Schmidt Road at the intersection with Remington Boulevard in the Village of Bolingbrook, Will County (Northeastern Illinois). | Safety/Traffic Management | 01/26/2010 | 01/26/2010 | 06/30/2010 | 320000 | 0.01
3060 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003439 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of on Oak St between Crystal Lake Rd and Burr St in the village of | Pavement Improvement | 03/02/2010 | 03/02/2010 | 06/30/2010 | 262105 | 0.72
3061 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003440 | This project will extend the pavement life by resurfacing on Shick Road in Bloomingdale (Northeast Illinois). | Pavement Improvement | 10/29/2009 | 04/15/2010 | 07/30/2010 | 1482917 | 0.93
3062 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003442 | This project will extend the pavement life by milling, patching and resurfacing Edina Blvd. from 21st street to Shiloh Blvd. (Northeast Illinios). | Pavement Improvement | 03/02/2010 |  | 05/30/2010 | 181244 | 0.48
3063 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003443 | This project will extend the pavement life by resurfacing Old Barrington Road from Cuba Rd to IL 22 in the City of North Barrington (Northeastern Illinois). | Pavement Improvement | 03/02/2010 | 04/27/2010 | 06/30/2010 | 224212 | 1.02
3064 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003445 | This project will substantially extend the pavement life by resurfacing, landscaping and improve safety and traffic enhancement by upgrading pavement markings of on Raffel Rd from Il Rt 120 Banford R | Pavement Improvement | 12/10/2009 | 05/03/2010 | 06/30/2010 | 262105 | 0.25
3065 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003449 | This project will extend the pavement life by milling, patching and resurfacing 0.48 miles on Garfield St from McKinley St to Old Orchard Rd in Harvard (Northeastern Illinois). | Pavement Improvement | 12/07/2009 | 03/15/2010 | 03/30/2010 | 262105 | 0.45
3066 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003452 | This project will extend the pavement life by milling, patching and resurfacing Deerpath Rd near Deer Park, Illinois (Northeast Illinios). | Pavement Improvement | 03/02/2010 | 04/27/2010 | 05/30/2010 | 102045 | 0.42
3067 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003454 | This project will extend the pavement life by milling, patching and resurfacing Telegraph Rd near Bannnockburn, Illinois (Northeast Illinios). | Pavement Improvement | 03/02/2010 | 05/15/2010 | 06/30/2010 | 266000 | 1
3068 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003456 | This project will extend the pavement life by resurfacing a four block section of Laurel Ave in the City of Highland Park (Northeast Illinois). | Pavement Improvement | 03/02/2010 | 05/03/2010 | 06/30/2010 | 108500 | 0.37
3069 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003457 | This project will extend the pavement life by milling, patching and resurfacing Sheridan Rd near Highwood, Illinois (Northeast Illinios). | Pavement Improvement | 03/10/2010 |  | 06/30/2010 | 476700 | 1.18
3070 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003458 | This project will extend the pavement life by milling, patching and resurfacing Deerpath Drive near Lindenhurst, Illinois (Northeast Illinios). | Pavement Improvement | 03/01/2010 | 05/03/2010 | 05/30/2010 | 149100 | 0.52
3071 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003459 | This project will extend the pavement life by milling, patching and resurfacing Saunders Road near Riverwood, Illinois (Northeast Illinios). | Pavement Improvement | 03/02/2010 | 04/28/2010 | 06/30/2010 | 331128 | 1.45
3072 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003461 | Village of Wauconda will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of pavement | Pavement Improvement | 02/19/2010 | 06/01/2010 | 05/30/2010 | 220500 | 1.45
3073 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003462 | This project will extend the pavement life by milling, patching and resurfacing Jackson Street near Waukegan, Illinois (Northeast Illinios). | Pavement Improvement | 03/15/2010 |  | 07/30/2010 | 661320 | 2.6
3074 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003465 | This project will extend the pavement life by milling and resurfacing various roadway sections in the City of Joliet (Northeastern Illinois). | Pavement Improvement | 05/03/2010 | 05/03/2010 | 07/30/2010 | 1194419 | 0
3075 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003466 | This project will extend the pavement life by resurfacing 3.65 miles on River Road near Wilmington (Northeast Illinois). | Pavement Improvement | 12/28/2009 | 04/05/2010 | 07/30/2010 | 1260000 | 3.7
3076 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003475 | This project will extend the pavement life by milling, patching and resurfacing Chapel Hill Rd near Johnsburg, Illinois (Northeast Illinois). | Pavement Improvement | 05/12/2010 | 06/14/2010 | 06/30/2010 | 262105 | 2
3077 | Illinois | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003476 | This project will extend the pavement life by milling, patching and resurfacing Rawson Bridge Rd near Port Barrington, Illinois (Northeast Illinios). | Pavement Improvement | 04/29/2010 | 04/30/2010 | 06/30/2010 | 214981 | 0.01
3078 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003478 | This project consists of improving safety and traffic enhancement by installing street lighting along IL Route 113 from Center Road to Mitchell Street in the City of Braidwood (Northeastern Illinois). | Safety/Traffic Management | 06/17/2010 |  | 07/30/2010 | 68000 | 0.25
3079 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003486 | This project will extend the pavement life by milling and resurfacing various roadway sections in the Village of New Lenox, Will County (Northeastern Illinois). | Pavement Improvement | 04/19/2010 | 05/26/2010 | 06/30/2010 | 241889 | 0
3080 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003489 | This project will extend pavement life by resurfacing 0.4 miles of Devon Avenue from Higgins Rd to I-294 in the Village of Rosemont in Cook County (Northeastern Illinois). | Pavement Improvement | 03/31/2010 | 03/31/2010 | 06/30/2010 | 503200 | 0.36
3081 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 6 | 9003490 | This project will extend pavement life by resurfacing numerous roadway sections in DuPage County including Gary Ave, Naperville Rd, Lemont Rd, Ferry Rd and Diehl Rd. (Northeastern Illinois) | Pavement Improvement | 03/19/2010 |  | 08/30/2010 | 4066500 | 0
3082 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003500 | This project will extend the pavement life by resurfacing 0.5 miles of Montrose Ave from Sayre Ave to Forest Preserve Ave in the Village of Harwood Heights, Cook County (Northeastern Illinois). | Pavement Improvement | 04/09/2010 |  | 05/30/2010 | 332990 | 0.48
3083 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003505 | This project will extend the pavement life by resurfacing 0.4 miles of Ridgeland Ave from Roosevelt Rd to Garfield St., and 1.0 miles from Division St. to North Ave in Oak Park, Cook County (Northeast | Pavement Improvement | 04/09/2010 | 04/30/2010 | 06/30/2010 | 533231 | 0.92
3084 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003513 | This project will provide for pedestrian safety by replacing sidewalks along Kankakee Street from Baltimore Street to Kankakee River Drive in the City of Wilmington (Northeastern Illinois). | Safety/Traffic Management | 01/13/2010 | 01/13/2010 | 05/30/2010 | 80000 | 0.8
3085 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003515 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to County Line Road in Burr Ridge (Northeast Illinois). | Safety/Traffic Management | 01/08/2010 | 04/01/2010 | 06/30/2010 | 84200 | 0.55
3086 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 9 | 9003522 | This project will enhance the roadways by supplying, delivering & installing 324 native trees on Cicero Avenue, Crawford Avenue, Devon Avenue, Lincoln Avenue, Pratt Avenue, Touhy Avenue & McCormick Av | Transportation Enhancements | 04/21/2010 |  | 06/30/2010 | 140300 | 0
3087 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003525 | This project will extend the pavement life by milling, patching and resurfacing 173rd St from Old Brennan Highway to Cicero Ave. in Country Club Hills, Illinois (Northeastern Illinois) | Pavement Improvement | 03/29/2010 | 04/16/2010 | 05/30/2010 | 295000 | 0.36
3088 | Illinois | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003526 | This project will extend the pavement life by resurfacing Raven Road from Seil Road to Valencia Drive in the Village of Shorewood, Will County (Northeastern Illinois). | Pavement Improvement | 04/19/2010 | 05/12/2010 | 06/30/2010 | 105000 | 0.35
3089 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003528 | This project will provide for pedestrian safety by constructing a new Pedestrain path and bridge adjacent to Thornmeadow Rd. in Riverwoods, (Northeast Illinois). | Bridge Improvement | 05/18/2010 |  | 09/30/2010 | 1066350 | 0.25
3090 | Illinois | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003529 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to IL Route 72 in West Dundee, IL , (Northeast Illinois). | Transportation Enhancements | 05/07/2010 |  | 08/30/2010 | 133630 | 0.13
3091 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003537 | This project will extend the pavement life by milling, patching and resurfacing 0.63 miles of Orchard Dr. in Park Forest, Illinois (Northeastern Illinois) | Pavement Improvement | 03/30/2010 | 05/05/2010 | 06/30/2010 | 409000 | 0.67
3092 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003547 | This project will improve aesthetics by streetscaping 0.47 miles of US 41 including lighting, sidewalk repair, curb and gutter repair and resurfacing in Skokie, Illinois (Northeastern Illinois) | Transportation Enhancements | 04/15/2010 |  | 08/30/2010 | 790336 | 0.49
3093 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003549 | This project will improve aesthetics by planting trees and streetscaping along various routes including Roberts Rd, 111th St, Kean Ave, and 103rd St in Palos Hills, Illinois (Northeastern Illinois). | Transportation Enhancements | 03/25/2010 | 03/17/2010 | 06/30/2010 | 200000 | 5.79
3094 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003550 | This project will extend the pavement life by milling, patching and resurfacing Batavia Road in the City of Warrenville (Norteastern Illinois). | Pavement Improvement | 02/19/2010 | 04/15/2010 | 06/30/2010 | 690000 | 1.15
3095 | Illinois | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003574 | This project will improve safety by installing 0.31 miles of new lighting along Burnham Ave from Brainard Ave north to Burnham Ave bridge in Burnham, Cook County (Northeastern Illinois). | Safety/Traffic Management | 03/31/2010 | 03/31/2010 | 06/30/2010 | 347000 | 0.08
3096 | Illinois | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003576 | This project consists of improving safety and traffic enhancement by installing street lighting at the intersection of IL Route 83 and Plainfield Road in the Village of Willowbrook, DuPage County (Nor | Safety/Traffic Management | 05/18/2010 |  | 07/30/2010 | 185403 | 0.01
3097 | Illinois | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003640 | This project will extend the pavement life by milling, patching and resurfacing on FAU 184 (Hawthorne Dr) from Cedar Lake Road to Rollins Rd in Round Lake Beach (Northeast-Illinois) | Pavement Improvement | 03/29/2010 | 05/03/2010 | 06/30/2010 | 147000 | 0.95
3098 | Illinois | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 9251010 | This project will extend the pavement life by milling, patching and resurfacing in Belleville, Illinois (Southwestwest Illinios). | Pavement Improvement | 05/11/2009 | 06/03/2009 | 08/30/2009 | 170311.96 | 0.7
3099 | Indiana | DUBOIS |  | 09 | 0003610 | This project will add turn lanes, widen the intersection, and install a new signal at SR 56 and Dubois County Rd 500W. | Safety/Traffic Management | 06/18/2009 | 08/03/2009 | 06/30/2010 | 104062.22 | 0.01
3100 | Indiana | ELKHART |  | 03 | 0013180 | This project will improve drainage by replacing the structure on SR 15 over a branch of Preston Miles' ditch in Elkhart County. | Pavement Improvement | 06/18/2009 | 07/14/2009 | 10/23/2009 | 1115122.65 | 0.01
3101 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0014130 | This project will improve drainage by replacing the structure on US 41 over Jane Feddeler Ditch in Lake County. | Pavement Improvement | 05/13/2009 | 06/24/2009 | 08/31/2009 | 576957.31 | 0.01
3102 | Indiana | SULLIVAN |  | 08 | 0100974 | This project is a bridge rehabilitation where the wearing surface of the deck will be removed and repalced on SR 154 at the bridge over Turman Creek, 2.17 miles W of SR 63 in Sullivan county. | Bridge Improvement | 03/24/2010 | 04/24/2010 | 11/30/2010 | 591309.71 | 0.01
3103 | Indiana | VANDERBURGH | EVANSVILLE (KY) | 08 | 0101271 | This is a road reconstruction project that will widen the road on Oak Hill Rd from US 41 to 0.32 mi N of SR 62 at Pigeon Creek in Vanderburgh county. This is Phase one of a multi-phase improvement to | Pavement Improvement | 01/28/2010 | 02/26/2010 | 06/30/2011 | 4962901.25 | 3
3104 | Indiana | HENRY |  | 06 | 0101426 | This project will improve the surface and rebuild sections of the bridge on SR 109 over I-70 in Henry County. | Bridge Improvement | 07/15/2009 | 07/15/2009 | 10/29/2010 | 1773465.75 | 0.01
3105 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0101500 | This project will improve drainage by replacing the structure on US 6 over Kiefer Ditch in Elkhart County. | Pavement Improvement | 09/09/2009 |  | 10/01/2010 | 531512.95 | 0.1
3106 | Indiana | NOBLE |  | 03 | 0101530 | This project will add turn lanes and imrpove the intersection at US 33 and SR 109 in Noble County. | Pavement Widening | 06/22/2009 | 08/31/2009 | 11/20/2009 | 376701.01 | 0.1
3107 | Indiana | GIBSON |  | 08 | 0173058 | This project will plant wildflowers and native vegetation along US 41at US 41 and Gibson County Road 550. | Transportation Enhancements | 07/21/2009 | 08/24/2009 | 08/01/2010 | 94456.25 | 0.67
3108 | Indiana | LAKE, STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0196049 | This project will replace the pavement on US 41 in Lake County from 1 mile south of US12/US20 to north of US12/20 and includes sewer replacement and modernization to provide a new road. | Pavement Improvement | 05/05/2010 | 05/18/2010 | 10/01/2010 | 2322827 | 1.01
3109 | Indiana | WHITE |  | 04 | 0200067 | This project will improve drainage by replacing the structure over Swygman ditch on US 24 in White County. | Safety/Traffic Management | 11/17/2009 | 01/15/2010 | 04/30/2010 | 48172 | 0.1
3110 | Indiana | WHITE |  | 04 | 0200071 | This project will improve drainage by replacing the structure on US 24 over Winters ditch in White County. | Safety/Traffic Management | 11/17/2009 | 01/15/2010 | 04/30/2010 | 75432 | 0.1
3111 | Indiana | UNION |  | 06 | 0200195 | This project will repair and restore the pavement and replace signs on US 27 from the Ohio State line north 3.6 miles in Union county. | Safety/Traffic Management | 04/15/2009 | 08/05/2009 | 02/10/2012 | 29179.07 | 3.56
3112 | Indiana | FOUNTAIN |  | 08 | 0200364 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Safety/Traffic Management | 06/17/2009 | 07/16/2009 | 08/31/2010 | 37743.16 | 0.02
3113 | Indiana | SHELBY, JOHNSON |  | 05,04,06 | 0200539 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | Safety/Traffic Management | 05/12/2009 | 07/22/2009 | 07/11/2011 | 26276.41 | 11.55
3114 | Indiana | STATEWIDE |  | 05,04,07 | 0200606 | This project will extend the traffic management system of closed circuit TV used for traffic management in Indianapolis. | Safety/Traffic Management | 06/11/2009 | 07/16/2009 | 11/15/2010 | 3592423.77 | 18.42
3115 | Indiana | ALLEN |  | 03 | 0200884 | This project will add lanes to SR 1 from I-69 in Allen County to Tonkel Road. | Pavement Widening | 06/01/2009 | 07/15/2009 | 08/13/2011 | 396605.83 | 0.1
3116 | Indiana | ADAMS |  | 06 | 0200890 | This project will improve drainage by replacing the small drainage structure on US 27 over Swartz ditch, 2.9 miles north of SR 218 in Adams County. | Pavement Improvement | 01/21/2010 | 06/22/2010 | 10/30/2010 | 688464.51 | 0.1
3117 | Indiana | WELLS |  | 06 | 0200894 | This project will improve drainage by replacing the small drainage structure on SR 301 over Vera Cruz Sewer, 0.6 miles north of SR 116 in Wells County. | Pavement Improvement | 08/20/2009 | 05/03/2010 | 08/21/2010 | 240955.15 | 0.01
3118 | Indiana | WABASH |  | 05 | 0200919 | This project will improve drainage by replacing the small drainage structure on SR 13 over Sharp ditch , 1.8 miles north of US 24 in Wabash County. | Pavement Improvement | 04/17/2009 | 06/10/2009 | 08/07/2009 | 397717.32 | 0.01
3119 | Indiana | ALLEN |  | 03 | 0200932 | This is a bridge rehabilitation project, on SR 101 on the bridge over Maumee River, 1.08 miles N of US 24 in Allen county , where the deck surface is removed and replaced to extend the life of the b | Bridge Improvement | 12/11/2009 | 03/18/2010 | 08/21/2010 | 741966.05 | 0.01
3120 | Indiana | DE KALB |  | 03 | 0200934 | This project will replace the existing bridge with a new wider structure for Dekalb county road 11A over I-69, 2.8 miles S of SR 8. | Bridge Improvement | 11/18/2009 | 04/01/2010 | 11/30/2010 | 3177881.13 | 0.01
3121 | Indiana | MONROE | BLOOMINGTON | 09 | 0200987 | This is a trail project to proviide facilities for pedestrians and bicycles project in the city of Bloomington Jackson Creek Trail in Monroe county. This is phase one of a multi phase project and use | Transportation Enhancements | 02/22/2010 | 03/31/2010 | 07/16/2010 | 374753.06 | 0.612
3122 | Indiana | BENTON |  | 01 | 0201203 | This project will improve the surface and rebuild sections of the bridge on US 41 over KB&S Railroad and US 52 in Benton County. | Bridge Replacement | 04/29/2009 | 05/11/2009 | 11/15/2009 | 1738096.18 | 0.04
3123 | Indiana | BENTON |  | 01 | 0201204 | This project will improve the surface and rebuild sections of the bridge on US 41 over KB&S Railroad and US 52 in Benton County. | Bridge Replacement | 04/29/2009 | 05/11/2009 | 11/15/2009 | 1153115.9 | 0.04
3124 | Indiana | CLINTON |  | 04 | 0201213 | This project will improve the surface and rebuild sections of the bridge on SR 75 over Kilmore Creek in Clinton County. | Bridge Improvement | 05/27/2009 | 06/15/2009 | 08/31/2009 | 438235.02 | 0.01
3125 | Indiana | OHIO |  | 09 | 0201245 | This project will improve the surface and rebuild sections of the bridge on SR 56 over Laughery Creek in Ohio County. | Bridge Improvement | 05/16/2009 | 07/31/2009 | 08/01/2011 | 5184952.26 | 0.18
3126 | Indiana | DUBOIS |  | 09 | 0242029 | This project will add turn lanes, widen the intersection, and install a new signal at SR 56 and Dubois County Rd 500W. | Pavement Widening | 06/18/2009 | 08/03/2009 | 06/30/2010 | 639905.85 | 0.01
3127 | Indiana | DE KALB, ALLEN | FORT WAYNE | 03 | 0300084 | This project will improve sections and extend the life of I-69 from 0.86 miles North of SR 1 to 9.87 miles North of SR 1 with a pavement surface overlay. | Pavement Improvement | 08/18/2009 | 08/24/2009 | 10/31/2009 | 2476953.36 | 8.68
3128 | Indiana | DE KALB |  | 03 | 0300092 | This project will improve safety and extend the life of the bridge(s) on County Road 68 over I-69 in DeKalb County. | Bridge Improvement | 04/02/2009 | 04/13/2009 | 08/31/2009 | 438945.26 | 0.1
3129 | Indiana | DE KALB |  | 03 | 0300093 | This project will improve safety and extend the life of the bridge(s) on County Road 60 over I-69 in DeKalb County. | Bridge Improvement | 04/02/2009 | 04/13/2009 | 08/31/2009 | 307586.66 | 0.1
3130 | Indiana | GREENE |  | 08 | 0300556 | This project will build a new bridge over Richland Creek on SR54, 1.32 miles E US 231 in Green county, east of Bloomfield to improve drainage and load carrying capacity. | New Bridge Construction | 03/24/2010 | 04/28/2010 | 11/05/2011 | 667110.13 | 0.01
3131 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300758 | This is a safety project, at 121st Street and US 41 in Hammond, Lake county, to modernize the traffic signals . | Safety/Traffic Management | 05/05/2010 | 05/18/2010 | 10/01/2010 | 69253.48 | 0.01
3132 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300759 | This is a safety project, at 119st Street and US 41 in Hammond, Lake county, to modernize the traffic signals in conjunction with the street modernization project. | Safety/Traffic Management | 05/05/2010 | 05/18/2010 | 10/01/2010 | 60730.15 | 0.01
3133 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300760 | This is a safety project ,at 117th Street at US 41 in Lake Co perform Traffic Signals Modernization work in conjunction with the ARRA street modernization contract. | Safety/Traffic Management | 05/05/2010 | 05/18/2010 | 10/01/2010 | 41911.33 | 0.35
3134 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300761 | This is a Safety project,at US 12/20 (Indianapolis Blvd.)/114th Street (Sec V); to perform Traffic Signals Modernization work. | Safety/Traffic Management | 05/05/2010 | 05/18/2010 | 10/01/2010 | 107604.5 | 0.04
3135 | Indiana | STEUBEN |  | 03 | 0300942 | This project will rebuild the US 20 and I-69 interchange in Steuben county to improve traffic flow. | Pavement Widening | 06/01/2009 | 06/12/2009 | 10/15/2010 | 3676824.73 | 0.69
3136 | Indiana | MARSHALL |  | 02 | 0301057 | This project will improve safety and extend the life of the bridge(s) on SR 10 over Clarence Baker Ditch in Marshall County. | Bridge Improvement | 04/17/2009 | 06/08/2009 | 11/22/2009 | 214456.84 | 0.01
3137 | Indiana | KOSCIUSKO |  | 03 | 0301140 | This is a Reconstruction (no added capacity) project, at SR 19 - Branch of Armey Ditch, 11.1 miles N of US 30; to perform Small Structure Replacement work. | Pavement Improvement | 12/30/2009 |  | 08/13/2010 | 339672.7 | 0.1
3138 | Indiana | ALLEN |  | 03 | 0301152 | This is a Small Structure project, at Over Dennis Ditch, 1.7 miles N of Lafayette Center interchange; to perform Pipe Lining work. | Other | 04/14/2010 |  | 10/02/2010 | 191162.7 | 0.1
3139 | Indiana | PARKE |  | 08 | 0322001 | This project will improve drainage by repairing pipes in Parke County 3 miles South of SR 234. | Pavement Improvement | 07/22/2009 | 09/11/2009 | 08/30/2010 | 679684.15 | 0.13
3140 | Indiana | JEFFERSON |  | 09 | 0400133 | This project will replace and restore the pavement on Michigan Road in Jefferson County near the Town of Madison. | Pavement Improvement | 07/15/2009 | 09/09/2009 | 06/07/2010 | 1233716 | 0.75
3141 | Indiana | MONROE | BLOOMINGTON | 09 | 0400322 | This project will improve the surface and rebuild sections of the bridge on SR 37 over the abandoned Railroad, 3.5 miles South of SR 45 in Monroe County. | Bridge Improvement | 05/13/2009 | 06/12/2009 | 06/26/2010 | 697938.5 | 0.01
3142 | Indiana | MONROE | BLOOMINGTON | 09 | 0400324 | This project will improve the surface and rebuild sections of the bridge on SR 37 over the abandoned Railroad, 3.5 miles South of SR 45 in Monroe County. | Bridge Improvement | 05/13/2009 | 06/12/2009 | 06/26/2010 | 671638.17 | 0.01
3143 | Indiana | OWEN |  | 08 | 0400568 | This project will correct a slide condition along SR 243 south of the Owen / Putnam County line. | Pavement Improvement | 07/22/2009 | 09/24/2009 | 09/30/2010 | 472233.66 | 0.07
3144 | Indiana | GRANT, HUNTINGTON |  | 05 | 0400614 | This project will improve sections and extend the life of I-69 from 1.84 mi S of Huntington Co Ln to 1.55 mi South of SR 124 with a pavement surface overlay. | Pavement Improvement | 07/07/2009 | 08/12/2009 | 10/24/2009 | 2117715.38 | 7.32
3145 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0400711 | This is a reconstruction project, at Cline Ave from Ridge Rd to 45th St., to perform intersection improvements adding turn lanes for better traffic flow and safety. | Pavement Improvement | 04/15/2010 | 04/27/2010 | 05/31/2011 | 4056240.33 | 0.86
3146 | Indiana | TIPPECANOE |  | 04 | 0400997 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 1288872.55 | 0.01
3147 | Indiana | TIPPECANOE |  | 04 | 0400999 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 624811.28 | 0.12
3148 | Indiana | TIPPECANOE |  | 04 | 0401000 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 1193676.61 | 0.12
3149 | Indiana | TIPPECANOE, BENTON |  | 01,04 | 0401007 | This project will improve sections and extend the life of US 52 in Benton county from SR 352 to US 231 with a asphalt preventive maintenance surface overlay. | Pavement Improvement | 03/24/2009 | 04/15/2009 | 11/15/2009 | 3823682.05 | 11.34
3150 | Indiana | JAY |  | 06 | 0401105 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge over Perry-Oakley Ditch, 1.09 miles N of US 27; to perform Bridge Rehabilitation Or Repair work. | Bridge Improvement | 03/25/2010 | 05/10/2010 | 10/30/2010 | 211009.77 | 0.1
3151 | Indiana | JACKSON |  | 09 | 0401139 | This project will improve the surface and rebuild sections of the bridge on SR 258 over White River in Jackson County. | Bridge Improvement | 06/05/2009 | 06/08/2009 | 10/16/2009 | 996973.79 | 0.01
3152 | Indiana | STARKE |  | 02 | 0401149 | This is a Small Structure project, at SR 39 - 1.25 miles N of E jct of SR 10; to perform Pipe Lining work. | Other | 04/14/2010 | 06/08/2010 | 06/30/2010 | 43144.02 | 0.01
3153 | Indiana | STARKE |  | 02 | 0401150 | This is a Small Structure project, at SR 39 - 2.25 miles N of E jct of SR 10; to perform Pipe Lining work. | Other | 04/14/2010 | 06/08/2010 | 06/30/2010 | 37500.99 | 0.01
3154 | Indiana | DE KALB, ALLEN | FORT WAYNE | 03 | 0401216 | This project will improve drainage by repairing pipes on I-69 from 0.86 miles North of SR 1 to 9.87 miles North of SR 1 in Allen and Dekalb Counties. | Pavement Improvement | 08/18/2009 | 08/24/2009 | 10/31/2009 | 976353.5 | 8.68
3155 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0401287 | This project will beautify the roadside by planting native grasses and wildflowers along US 52 near the SR 443 bridge and Happy Hollow Road in West Lafayette. | Transportation Enhancements | 06/09/2009 | 07/01/2009 | 06/30/2011 | 44866 | 0.01
3156 | Indiana | LAWRENCE |  | 04 | 0426013 | This project will improve sections and extend the life of US 50 from SR 37 to "E" street in Bedford, Lawrence county with a preventive maiantenance asphalt overlay. | Pavement Improvement | 03/23/2009 | 04/20/2009 | 08/29/2009 | 976603.3 | 1.77
3157 | Indiana | KNOX |  | 08 | 0431065 | This project will plant wildflowers and native vegetation along SR 67 south of Bruceville in Knox County. | Transportation Enhancements | 07/21/2009 | 08/24/2009 | 08/01/2010 | 37869.1 | 0.28
3158 | Indiana | ALLEN |  | 03 | 0452010 | This project will add lanes to SR 1 from I-69 in Allen County to Tonkel Road. | Pavement Widening | 06/01/2009 | 07/15/2009 | 08/13/2011 | 10767689.43 | 1.85
3159 | Indiana | STARKE |  | 02 | 0500283 | This project will improve sections and extend the life of SR 39 in Starke County with a pavement surface overlay. | Pavement Improvement | 08/18/2009 | 08/29/2009 | 11/15/2009 | 1341695.75 | 7.11
3160 | Indiana | TIPPECANOE |  | 04 | 0500597 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 24555851.35 | 0.12
3161 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0500819 | This project will build a new the bike and pedestrian facilities on Tracy Trail from Summerfield Park to Craig Park in the Greenwood area in Johnson county. | Transportation Enhancements | 12/16/2009 | 03/22/2010 | 10/29/2010 | 829013 | 0.01
3162 | Indiana | VANDERBURGH | EVANSVILLE (KY) | 08 | 0500938 | This project will plant wildflowers and native vegetation along I-164 at I-164 and SR 62 in Vanderburgh County. | Transportation Enhancements | 07/21/2009 | 08/21/2009 | 08/01/2010 | 59674.25 | 0.17
3163 | Indiana | VIGO | TERRE HAUTE | 08 | 0500965 | This project will replace and restore the pavement on Brown Avenue, from Wabash Avenue to Locust Street, in Vigo County. | Pavement Widening | 09/15/2009 | 10/06/2009 | 06/30/2010 | 1536019.28 | 0.38
3164 | Indiana | BOONE | INDIANAPOLIS | 04 | 0501249 | This is a Maintenance Resurfacing project, at I-65 to I 465; to perform asphalt resurface, Functional work. | Pavement Improvement | 02/19/2010 |  | 10/30/2010 | 2849967.08 | 4.13
3165 | Indiana | GREENE |  | 08 | 0565014 | This project will replace a large culvert with a new bridge on SR54 as part of contract SB-30551 reconstruction project at the bridge over Ritter Ditch, East of US 231 in Greene County. | Pavement Widening | 03/24/2010 | 04/28/2010 | 11/05/2011 | 923845.75 | 0
3166 | Indiana | CLAY |  | 08 | 0600085 | This project will improve sections and extend the life of SR 246 from SR 159 to SR 157 in Clay County with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 05/11/2009 | 06/30/2009 | 815449.39 | 6.62
3167 | Indiana | DELAWARE | MUNCIE | 06 | 0600233 | This project will improve sections and extend the life of Sr 3 with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 06/02/2009 | 08/07/2009 | 1318336.68 | 10.94
3168 | Indiana | HOWARD | KOKOMO | 05 | 0600338 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Construction | 06/01/2009 | 07/10/2009 | 06/15/2011 | 8918680.32 | 2
3169 | Indiana | STARKE |  | 02 | 0600501 | This project repairs a drainage pipe on SR 39 , 1.48 miles south of SR 8 in Starke county by re-lining the culver instead of replacing it. | Other | 04/14/2010 | 06/08/2010 | 06/30/2010 | 37500.99 | 0.01
3170 | Indiana | HOWARD | KOKOMO | 05 | 0600566 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Bridge Construction | 06/01/2009 | 07/10/2009 | 06/15/2011 | 1734801.49 | 0.01
3171 | Indiana | MONROE | BLOOMINGTON | 04,09 | 0600605 | This project will improve sections and extend the life of SR 48 from Curry Pike to E of SR 37 in Bloomington with a pavement surface overlay. | Pavement Improvement | 04/15/2009 | 05/08/2009 | 08/02/2009 | 512986.83 | 0.56
3172 | Indiana | MARION | INDIANAPOLIS | 04 | 0600651 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | New Construction | 05/26/2009 | 06/23/2009 | 11/15/2010 | 9669603.35 | 0.01
3173 | Indiana | MARION | INDIANAPOLIS | 04 | 0600653 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | Bridge Replacement | 05/26/2009 | 06/23/2009 | 11/15/2010 | 2431747.71 | 0.07
3174 | Indiana | MARION | INDIANAPOLIS | 04 | 0600654 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | Bridge Replacement | 05/26/2009 | 06/23/2009 | 11/15/2010 | 2457379.37 | 0.01
3175 | Indiana | MONROE, BROWN |  | 09 | 0600667 | This is a project repairs drainage pipes under SR 46 in various locations in Seynour district by relining the old culverts instead of replacing them. | Safety/Traffic Management | 03/01/2010 | 03/26/2010 | 07/30/2010 | 144294.15 | 15
3176 | Indiana | MONTGOMERY |  | 04 | 0600803 | This project will improve drainage by replacing the structure on US 231, 3 miles South of the South junction with SR 32 in Montgomery County. | Pavement Improvement | 03/24/2009 | 05/18/2009 | 06/13/2009 | 45853.99 | 0.2
3177 | Indiana | OWEN |  | 08 | 0621004 | This is a bridge replacement at the bridge over Meadow Brook Creek on US 231 south of SR 46 in Owen county to replace a deficient bridge | Bridge Replacement | 04/09/2010 |  | 09/17/2010 | 620500 | 0.01
3178 | Indiana | SHELBY, JOHNSON |  | 05,06,04 | 0684011 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | Pavement Widening | 05/12/2009 | 07/22/2009 | 07/11/2011 | 13291723.99 | 11.28
3179 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0710027 | This proejct will extend the pavement life on SR 23 in St Joseph county from SR 933 to Campeau St ; by doing asphalt resurface preventive maintenance work. | Pavement Improvement | 02/22/2010 | 03/29/2010 | 07/31/2010 | 874458 | 2.19
3180 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710031 | This project will improve sections and extend the life of US 20 in East Chicago with a pavement surface overlay. | Pavement Improvement | 06/17/2009 | 07/21/2009 | 09/30/2009 | 1659673.58 | 2.56
3181 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710034 | This project will improve the pavement on SR 149 from the junstion of SR 130 to the junction of US 20. | Pavement Improvement | 04/08/2009 | 05/04/2009 | 11/13/2009 | 1362731.25 | 5.13
3182 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0710040 | This project will improve sections and extend the life of SR-23 from SR 4 to Olive Street in St Joseph County with a pavement surface overlay. | Pavement Improvement | 06/05/2009 | 08/14/2009 | 11/01/2009 | 1593244.25 | 11.79
3183 | Indiana | PULASKI |  | 02 | 0710042 | This project will improve sections and extend the life of US 35 from SR 14 to SR 10 in Pulaski County with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 05/18/2009 | 10/16/2009 | 1407322.75 | 10.03
3184 | Indiana | CASS |  | 02 | 0710043 | This project will improve sections and extend the life of US 24 from the north junction with US 35 to the south junction with US 35 and on SR 29 from US 24 to Burlington Ave. near Logansport in Cass C | Pavement Improvement | 03/23/2009 | 05/11/2009 | 07/31/2009 | 1651219.54 | 1.61
3185 | Indiana | ST JOSEPH |  | 02 | 0710044 | This is a Maintenance Resurfacing project , From Georgia St in Walkerton to US 31 to perform asphalt resurface, Functional work. | Pavement Improvement | 03/04/2010 |  | 08/31/2010 | 3085070.82 | 9.24
3186 | Indiana | JASPER |  | 01 | 0710046 | This project will extend the pavement lief on SR 10 - from SR 110 to US 231 by doing asphalt resurface preventive maintenance work. | Pavement Improvement | 04/08/2010 | 04/23/2010 | 06/18/2010 | 647470.4 | 6.21
3187 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710053 | This project will improve sections and extend the life of US 30 in Lake County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/02/2009 | 11/15/2009 | 3318981.34 | 5.39
3188 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710054 | This project will improve sections and extend the life of US 41 from US 231 to 77th Ave with a pavement surface overlay. | Pavement Improvement | 08/27/2009 | 09/04/2009 | 10/31/2009 | 1812338.2 | 3.99
3189 | Indiana | LAKE |  | 01 | 0710058 | This project will improve sections and extend the life of SR 53 from 93rd Ave to South of 73rd Ave with a pavement surface overlay. | Pavement Improvement | 05/13/2009 | 08/03/2009 | 10/16/2009 | 1148579.81 | 2.43
3190 | Indiana | LAWRENCE |  | 04 | 0710074 | This project will stop erosion and correct a slide occurring on the west side of US 50 south of the East Fork White River Bridge in lawrence County. | Safety/Traffic Management | 06/04/2009 | 07/23/2009 | 08/14/2009 | 162684 | 0.1
3191 | Indiana | ALLEN |  | 03 | 0710107 | This project will improve safety and extend the life of the bridge(s) on Hursh Road over I-69 in Allen County. | Bridge Improvement | 04/02/2009 | 04/13/2009 | 08/31/2009 | 277824.96 | 0.01
3192 | Indiana | DAVIESS |  | 08 | 0710108 | This is a preventive maintenance resurfacing project, on SR 57 - From 1.32 miles North of junction of US 50/US 150 to the sounth junction of SR 58 to do a thin asphalt resurface to extend the life of | Pavement Improvement | 11/18/2009 | 02/25/2010 | 10/01/2010 | 3659182.17 | 38.32
3193 | Indiana | JASPER |  | 01 | 0710115 | This project will extend the service life of the pavement on I-65, 2 mile north of US 321 to north of SR 14 in Jasper county with a preventive maintenance resurfacing project. | Pavement Improvement | 09/15/2009 | 10/22/2009 | 08/20/2010 | 3009802.03 | 9.75
3194 | Indiana | HUNTINGTON |  | 05 | 0710141 | This project will improve safety and extend the life of the bridge(s) on I-69 over Wabash River in Huntington County. | Bridge Improvement | 05/13/2009 | 07/07/2009 | 10/31/2009 | 1452773.4 | 0.04
3195 | Indiana | DE KALB |  | 03 | 0710144 | This project will install new cable barrier in the median along I-69 in Dekalb County to prevent crossover head-on collisions. | Safety/Traffic Management | 05/16/2009 | 08/05/2009 | 10/31/2009 | 378646.31 | 4.32
3196 | Indiana | VIGO, HENDRICKS, MORGAN |  | 08 | 0710147 | This project will install new cable barrierin the median on I-70 in Vigo, Hendricks, and Morgan Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 06/10/2009 | 07/23/2009 | 09/12/2009 | 1157982.31 | 4.48
3197 | Indiana | HENDRICKS, MARION |  | 04,07 | 0710148 | This project will install new cable barrier in the median along I-74 in Hendricks and Marion Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 04/29/2009 | 06/04/2009 | 07/31/2009 | 560763.13 | 7.78
3198 | Indiana | CLARK, SHELBY, JOHNSON, JACKSON |  | 05,06,04,09 | 0710150 | This project will install new cable guardrail in the median along I-65 in Johnson and Shelby Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 06/15/2009 | 06/26/2009 | 10/31/2009 | 3843690.33 | 89.63
3199 | Indiana | FLOYD |  | 09 | 0710151 | This project will install new cable guardrailin the median along I-64 in Floyd County to prevent crossover head-on collisions. | Safety/Traffic Management | 06/15/2009 | 06/26/2009 | 10/31/2009 | 360552.55 | 9.84
3200 | Indiana | CLARK, FLOYD |  | 09 | 0710152 | This project will install new cable guardrail in the median along I-265 in Clark and Floyd Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 06/15/2009 | 06/26/2009 | 10/31/2009 | 545978.63 | 12.03
3201 | Indiana | MARION | INDIANAPOLIS | 07 | 0710163 | This project will improve sections and extend the life of I-465 in Marion county with a pavement surface overlay from 3.23 miles North of I-74 to 5.12 miles North of I-74. | Pavement Improvement | 06/16/2009 | 07/30/2009 | 11/15/2009 | 1500500 | 1.9
3202 | Indiana | SWITZERLAND |  | 09 | 0710169 | This project will improve sections and extend the life of SR 56 from Oday Road to Rio Vista Lane in Switzerland county with a pavement surface overlay. | Pavement Improvement | 10/07/2009 | 05/11/2010 | 08/13/2010 | 2096135.96 | 21.05
3203 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0710203 | This is a Safety project, at Parkside School sidewalk - This is a 2006 Safe Routes to School (SRTS) project that beyond the avaialbe funding of the SRTS program that will provide sidewalks to Parkside | Safety/Traffic Management | 11/30/2009 | 04/26/2010 | 06/19/2010 | 159604.78 | 0.01
3204 | Indiana | GREENE |  | 08 | 0710285 | This project will extend the pavement life on SR 157 from north of US 231 to the jct with SR 48 in Greene county by doing asphalt resurface with 2 layers | Pavement Improvement | 10/14/2009 | 10/21/2009 | 11/15/2009 | 475438.35 | 2.41
3205 | Indiana | DAVIESS, KNOX |  | 08 | 0710390 | This project will improve sections and extend the life of SR 58 from SR 67 to SR 57 in Knox and Daviess Counties with a pavement surface overlay. | Pavement Improvement | 03/23/2009 | 07/08/2009 | 09/20/2009 | 886582.9 | 6.39
3206 | Indiana | MONTGOMERY |  | 04 | 0710394 | This project will improve sections and extend the life of US 231 from just north of US 136 in Crawfordsville to 1/2 mile north of I-74 in Montgomery County with a pavement surface overlay. | Pavement Improvement | 06/03/2009 | 06/23/2009 | 11/06/2009 | 3436551.55 | 3.13
3207 | Indiana | SCOTT, JACKSON |  | 09 | 0710432 | This project will improve sections and extend the life of US 31 from SR 56 to SR 250 in Jackson and Scott Counties with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 04/03/2009 | 11/16/2009 | 1526188.61 | 12.97
3208 | Indiana | STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01,02 | 0710470 | This project will install new signal loop detectors to improve traffic flow at 5 intersection along US 30 in Northwest Indiana | Safety/Traffic Management | 04/14/2009 | 05/29/2009 | 08/31/2009 | 369390.8 | 0.02
3209 | Indiana | HANCOCK, MADISON |  | 05,06 | 0710492 | This project will improve sections and extend the life of SR 9 in Hancock and Madison Counties with a pavement surface overlay. | Pavement Improvement | 06/02/2009 | 07/10/2009 | 08/28/2009 | 1556750 | 10.81
3210 | Indiana | JENNINGS |  | 09 | 0710502 | This project will improve sections and extend the life of SR 3 from South junction with SR 7 South of Vernon to US 50 with a pavement surface overlay. | Pavement Improvement | 05/13/2009 | 06/20/2009 | 08/31/2009 | 528503.93 | 1.58
3211 | Indiana | STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01,02 | 0710510 | This project will install new signal loop detectors to improve traffic flow at 5 intersection along US 30 in Northwest Indiana | Safety/Traffic Management | 04/29/2009 | 05/18/2009 | 08/31/2009 | 283823.5 | 0.02
3212 | Indiana | HANCOCK |  | 05 | 0710541 | This project will improve sections and extend the life of US 40 with a pavement surface overlay. | Pavement Improvement | 06/02/2009 | 06/27/2009 | 08/07/2009 | 820500 | 3.12
3213 | Indiana | MIAMI |  | 05 | 0710581 | This project will improve the surface and rebuild sections of the bridge on US 31 over the abandoned CSX Railroad, 1 miles South of US 50 in Ohio County. | Bridge Replacement | 04/17/2009 | 04/22/2009 | 06/26/2010 | 308238.35 | 0.01
3214 | Indiana | MIAMI |  | 05 | 0710582 | This project will improve the surface and rebuild sections of the bridge on US 31 over the abandoned CSX Railroad, 1 miles South of US 50 in Ohio County. | Bridge Replacement | 04/17/2009 | 04/22/2009 | 06/26/2010 | 729284.5 | 0.01
3215 | Indiana | CLINTON, BOONE |  | 04 | 0710622 | This project will improve sections and extend the life of I-65 with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 04/20/2009 | 10/31/2009 | 4275408.99 | 9.78
3216 | Indiana | LAWRENCE |  | 04 | 0710650 | This project will patch deteriorated pavement areas and seal cracks on SR 37 near Mitchell. | Pavement Improvement | 03/31/2009 | 05/05/2009 | 09/18/2009 | 398694.16 | 8.01
3217 | Indiana | JOHNSON | INDIANAPOLIS | 06,04 | 0710670 | This project will improve sections and extend the life of US 31 from SR 252 to Youngs Creek Bridge in Johnson county with a pavement surface overlay. | Pavement Improvement | 08/18/2009 | 03/24/2010 | 08/13/2010 | 1569905.69 | 12.57
3218 | Indiana | WASHINGTON |  | 09 | 0710694 | This project will improve sections and extend the life of SR 56 in Washington County with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 04/02/2009 | 08/01/2009 | 989946.05 | 9.87
3219 | Indiana | KNOX |  | 08 | 0710700 | This is a Maintenance Resurfacing project, at US 50 - 6.08 miles W of SR 241 to 1.88 miles E of SR 241; to perform PCCP Cleaning and Sealing Joints work. | Pavement Improvement | 10/23/2009 | 04/01/2010 | 08/28/2010 | 648462.9 | 7.86
3220 | Indiana | LAWRENCE |  | 04 | 0710823 | This project will improve sections and extend the life of SR 54 from SR 58 to SR 37 with a pavement surface overlay. | Pavement Improvement | 07/07/2009 | 05/10/2010 | 11/01/2010 | 650211.09 | 10.47
3221 | Indiana | WARRICK |  | 08 | 0710824 | This project will improve sections and extend the life of SR 61 from 0.8 Mi. N of SR 62 to S of SR 68 in Warrick County with a pavement surface overlay. | Pavement Improvement | 03/19/2009 | 04/28/2009 | 12/18/2009 | 1531554.06 | 10.13
3222 | Indiana | STEUBEN |  | 03 | 0710833 | This project will improve sections and extend the life of SR 1 in Steuben County with a pavement surface overlay. | Pavement Improvement | 06/05/2009 | 08/19/2009 | 10/31/2009 | 1451671.15 | 12.92
3223 | Indiana | PIKE |  | 08 | 0710835 | This project will improve sections and extend the life of SR 56 from South junction with SR 61 to SR 257 in Pike county with a preventive maintenance pavement surface overlay. | Pavement Improvement | 06/16/2009 | 09/08/2009 | 06/30/2010 | 1297838.15 | 8.31
3224 | Indiana | ELKHART | ELKHART-GOSHEN | 02,03 | 0710839 | This is a Maintenance Resurfacing project, From 5.49 miles W of SR 15 -W jct (Middleton Run Rd), to 0.10 miles W of SR 13; to perform asphalt resurface, Functional work. | Pavement Improvement | 04/26/2010 | 05/17/2010 | 10/01/2010 | 3807660.75 | 11.89
3225 | Indiana | CASS |  | 02 | 0710840 | This is a Safety project, at SR-218 1163' E of CR 600E (EB) 24+64 and 70' E of Maple Street (WB) 25+11; to perform New Flasher Installation work. | Safety/Traffic Management | 02/22/2010 | 03/12/2010 | 04/30/2010 | 12654.7 | 0.47
3226 | Indiana | HARRISON | LOUISVILLE (KY)-IN | 09 | 0710884 | This project will extend the bridge life by repainting bridge beams at I-64 over Blue River and Blue Road in Harrison County. | Bridge Improvement | 06/19/2009 | 02/19/2010 | 08/28/2010 | 446999.59 | 0.01
3227 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0710886 | This project will improve sections and extend the life of SR 19 near the I-80/I-90 Toll Road in Elkhart Co. with a pavement surface overlay. | Pavement Improvement | 06/05/2009 | 07/16/2009 | 10/02/2009 | 1838664.06 | 2.79
3228 | Indiana | ELKHART | ELKHART-GOSHEN | 02,03 | 0710888 | This project will extend the life of the pavement on SR 19 from I-80/90 Toll Road to the Michigan state line by resurfcing the road with 2 lays of asphalt overlay. | Pavement Improvement | 04/08/2010 | 06/11/2010 | 10/08/2010 | 1876577.13 | 1.69
3229 | Indiana | MONTGOMERY |  | 04 | 0710917 | This project will upgrade and improve the traffic signals at US 231 and the SR 32/ SR 47 junction in Montgomery County. | Safety/Traffic Management | 06/09/2009 | 06/30/2009 | 06/27/2009 | 25048.8 | 0.02
3230 | Indiana | BLACKFORD |  | 06 | 0710921 | This project will improve sections and extend the life of SR 26 from 0.84 mile East of SR 3(Little Lick Creek) to SR 167 with a pavement surface overlay. | Pavement Improvement | 06/02/2009 | 08/24/2009 | 11/13/2009 | 871676.31 | 7.14
3231 | Indiana | JAY |  | 06 | 0710928 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge over Limberlost Creek, 2.37 miles N of US 27, East of Bryant; to perform Bridge Deck Reconstruction & Widening work. | Bridge Improvement | 03/25/2010 | 05/10/2010 | 10/30/2010 | 1011571.33 | 0.01
3232 | Indiana | GRANT |  | 05 | 0710933 | This project will improve sections and extend the life of SR 26 from SR 13 to I-69 with a pavement surface overlay. | Pavement Improvement | 08/27/2009 | 09/15/2009 | 10/16/2009 | 1236669.07 | 14.42
3233 | Indiana | HOWARD | KOKOMO | 05 | 0710943 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Bridge Construction | 06/01/2009 | 07/10/2009 | 06/15/2011 | 774131.29 | 0.01
3234 | Indiana | CARROLL, HOWARD |  | 02,05 | 0710948 | This project will improve sections and extend the life of SR 22 from SR 29 to 11.48 miles East of SR 29 with a pavement surface overlay. | Pavement Improvement | 06/16/2009 | 08/07/2009 | 11/13/2009 | 1766853.95 | 11.51
3235 | Indiana | HARRISON |  | 09 | 0711000 | This project will move the Historic Rothrock Mill bridge from it's current location to storage for preservation purposes. | Transportation Enhancements | 06/19/2009 | 07/13/2009 | 08/15/2009 | 41802.09 | 0.01
3236 | Indiana | WHITE |  | 04 | 0711020 | This project will improve sections and extend the life of US 24 with a pavement surface overlay. | Pavement Improvement | 04/15/2009 | 05/30/2009 | 07/31/2009 | 394030 | 1.35
3237 | Indiana | KOSCIUSKO |  | 03 | 0711022 | This project will improve sections and extend the life of SR 15 with a pavement surface overlay. | Pavement Improvement | 03/24/2009 | 05/01/2009 | 07/17/2009 | 315308.54 | 0.99
3238 | Indiana | NOBLE, STATEWIDE |  | 03 | 0711024 | This project will improve sections and extend the life of SR 9 with a pavement surface overlay. | Pavement Improvement | 03/31/2009 | 05/26/2009 | 10/31/2009 | 555377.21 | 1.83
3239 | Indiana | ORANGE |  | 09 | 0800005 | This project will improve drainage by repairing pipes at SR 145, between 1.6 Miles North TO 9.8 Miles North of SR 164 in Orange County. | Pavement Improvement | 04/13/2009 | 05/14/2009 | 10/30/2009 | 258979.75 | 8.18
3240 | Indiana | DUBOIS |  | 09 | 0800006 | This project will improve sections and extend the life of SR 164 with a pavement surface overlay. | Pavement Improvement | 04/30/2009 | 06/08/2009 | 09/18/2009 | 173051.83 | 0.93
3241 | Indiana | POSEY |  | 08 | 0800086 | This project will improve sections and extend the life of SR 62 from IL/IN State line to 1.96 miles East of SR 69 with a pavement surface overlay. | Pavement Improvement | 07/23/2009 | 03/23/2010 | 11/10/2010 | 1571712.39 | 8.76
3242 | Indiana | DUBOIS |  | 08,09 | 0800122 | This is a Maintenance Resurfacing project, at SR 56 - Jct with SR 257 to the W jct of US 231; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 03/19/2010 | 07/01/2010 | 1257820.69 | 10.12
3243 | Indiana | LAWRENCE |  | 04 | 0800125 | This project will improve sections and extend the life of US 50 from 4.09 miles East of SR 37 to junction with SR 446 with a pavement surface overlay. | Pavement Improvement | 07/07/2009 | 05/10/2010 | 11/01/2010 | 688431.96 | 5.56
3244 | Indiana | ALLEN |  | 03 | 0800142 | This is a Small Structure project, at Over the ditch at the Interchange, 0.15 miles N of I-469 S jct; to perform Pipe Lining work. | Other | 04/14/2010 |  | 10/02/2010 | 593401.65 | 0.01
3245 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0800158 | This project will improve sections and extend the life of US-6 from SR 19 to SR 15 in Elkhart County with a pavement surface overlay. | Pavement Improvement | 06/03/2009 | 07/08/2009 | 10/09/2009 | 979865.66 | 6.97
3246 | Indiana | HUNTINGTON |  | 05 | 0800162 | This project will improve sections and extend the life of US 41 in Huntington County with a pavement surface overlay | Pavement Improvement | 07/06/2009 | 08/19/2009 | 10/23/2009 | 2202419 | 8.8
3247 | Indiana | WABASH, WHITLEY |  | 03,05 | 0800176 | This is a Maintenance Resurfacing project, at SR 114 - From 1.66 miles E of SR 13 (EEL River) to SR 105; to perform asphalt resurface, Functional work. | Pavement Improvement | 12/10/2009 | 04/09/2010 | 08/13/2010 | 1890052.25 | 7.39
3248 | Indiana | WAYNE |  | 06 | 0800177 | This project will improve sections and extend the life of SR 227 from CSX R/R to US 27 with a pavement surface overlay. | Pavement Improvement | 07/22/2009 | 08/20/2009 | 11/20/2009 | 488200 | 2.87
3249 | Indiana | WAYNE |  | 06 | 0800191 | This project will improve sections and extend the life of US 27 from. 1.12 miles North of I-70 at East fork of Whitewater River to 5.71 miles North of I-70 at Fountain Circle with a pavement surface o | Pavement Improvement | 07/22/2009 | 08/20/2009 | 11/20/2009 | 895000.12 | 3.96
3250 | Indiana | ALLEN | FORT WAYNE | 03 | 0800196 | This project will improve lighting on I-69 at Airport Expressway in Allen County. | Safety/Traffic Management | 07/10/2009 | 08/18/2009 | 11/30/2009 | 71877.05 | 0.76
3251 | Indiana | HENRY |  | 06 | 0800200 | This project is road surface treatment for US 36 in Greenfield District, from 3.67 miles west of State Road 3 to west ramps of State Road 3. | Pavement Improvement | 08/25/2009 | 09/04/2009 | 10/16/2009 | 527700 | 3.59
3252 | Indiana | JAY |  | 06 | 0800203 | This project will improve sections and extend the life of US 27 in the Town of Portland with a pavement surface overlay. | Pavement Improvement | 07/07/2009 | 08/20/2009 | 10/15/2009 | 674602.4 | 5.16
3253 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0800219 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge # 12-64-05413-A (WBL) over Burns Ditch (0.94 miles W of SR 249); to perform Bridge Maintenance And Repair work. | Bridge Improvement | 03/23/2010 |  | 07/15/2011 | 1816152.27 | 0.01
3254 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0800220 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge # 12-64-05413-A (EBL) over Burns Ditch (0.94 miles W of SR 249); to perform Bridge Maintenance And Repair work. | Bridge Improvement | 03/23/2010 |  | 07/15/2011 | 1116423.97 | 0.01
3255 | Indiana | STATEWIDE |  | 04 | 0800237 | This project will extend the bridge life by repainting bridge beams at various locations in Crawfordsville. | Bridge Improvement | 04/25/2009 | 05/28/2009 | 09/30/2009 | 435708.8 | 0.01
3256 | Indiana | GRANT |  | 05 | 0800260 | This project will improve sections and extend the life of US 35 from 1.65 miles East of SR 15 (10th St) to 0.24 miles East of I-69 and on SR 22 with a pavement surface overlay. | Pavement Improvement | 06/16/2009 | 08/26/2009 | 10/24/2009 | 743435.3 | 7.2
3257 | Indiana | JACKSON |  | 09 | 0800389 | This project will patch deteriorated pavement areas and seal cracks on US 31 4.11 mi. N of SR 250 in Jackson County. | Pavement Improvement | 03/26/2009 | 06/09/2009 | 07/15/2009 | 146826.45 | 0.96
3258 | Indiana | JASPER |  | 02,01 | 0800434 | This project will improve sections and extend the life of SR 10 with a pavement surface overlay. | Pavement Improvement | 04/09/2009 | 05/12/2009 | 06/26/2009 | 332090.99 | 7.99
3259 | Indiana | MARSHALL | SOUTH BEND (MI) | 02 | 0800438 | This project will improve sections and extend the life of SR 17 with a pavement surface overlay. | Pavement Improvement | 04/16/2009 | 09/08/2009 | 11/01/2009 | 292790.44 | 1.68
3260 | Indiana | STARKE |  | 02 | 0800439 | This project will improve sections and extend the life of SR 23 with a pavement surface overlay. | Pavement Improvement | 04/16/2009 | 07/10/2009 | 11/06/2009 | 241745.43 | 6.48
3261 | Indiana | JASPER |  | 01,04 | 0800440 | This project will improve sections and extend the life of SR 16 with a pavement surface overlay. | Pavement Improvement | 04/16/2009 | 05/18/2009 | 06/30/2009 | 474528.03 | 14.4
3262 | Indiana | KOSCIUSKO |  | 03 | 0800475 | This project will improve sections and extend the life of SR 25 with a pavement surface overlay. | Pavement Improvement | 03/24/2009 | 05/01/2009 | 07/17/2009 | 164391.63 | 0.57
3263 | Indiana | BARTHOLOMEW | COLUMBUS | 09 | 0800516 | This project will add turn lanes, nodernize the signal, and widen the intersection at SR 11and Bartholomw county Road 450S. | Safety/Traffic Management | 05/06/2009 | 06/01/2009 | 08/15/2010 | 41055.8 | 0.01
3264 | Indiana | MARION | INDIANAPOLIS | 07 | 0800517 | This project will install fiber optic lines from the Indianapolis Traffic Management Center to downtown Indianapolis to improve the closed circuit TV system used for traffic management. | Safety/Traffic Management | 06/11/2009 | 06/29/2009 | 05/28/2010 | 714614.44 | 7.62
3265 | Indiana | SPENCER |  | 09 | 0800753 | This project will improve sections and extend the life of SR 245 from junction with SR 70 to 3.50 miles South of SR 162 with a pavement surface overlay. | Pavement Improvement | 07/23/2009 | 03/01/2010 | 11/01/2011 | 640303.87 | 9.03
3266 | Indiana | SPENCER |  | 09 | 0800766 | This project will improve sections and extend the life of SR 161 from Ky State Line to SR 66 with a pavement surface overlay. | Pavement Improvement | 07/23/2009 | 03/01/2010 | 11/01/2011 | 1807885.98 | 8.29
3267 | Indiana | GIBSON |  | 08 | 0800817 | This project will improve sections and extend the life of SR 168 from US 41 to SR 57 with a pavement surface overlay. | Pavement Improvement | 07/23/2009 | 08/26/2009 | 05/31/2010 | 1478864.47 | 9.4
3268 | Indiana | POSEY |  | 08 | 0800821 | This project will improve sections and extend the life of SR 69 from 2.48 miles South of West junction with SR 66 to 0.1 miles North of I-64 with a pavement surface overlay. | Pavement Improvement | 07/09/2009 | 08/06/2009 | 08/01/2010 | 1307218.59 | 8.84
3269 | Indiana | TIPPECANOE, WHITE | LAFAYETTE-WEST LAFAYETTE | 04 | 0800831 | This project will improve sections and extend the life of SR 43 in Tippecanoe & White Counties with a pavement surface overlay | Pavement Improvement | 04/09/2009 | 08/20/2009 | 07/31/2009 | 466983.08 | 4.76
3270 | Indiana | WELLS, ALLEN |  | 03,06 | 0800939 | This is a Maintenance Resurfacing project, at From 2.44 miles N of US 224 (CR850N, Ossian, Wells Co) to I-469 (Allen Co); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/18/2010 |  | 11/06/2010 | 1417133.2 | 6.04
3271 | Indiana | WAYNE |  | 06 | 0800962 | This project will extend the bridge life by repainting bridge beams at I-70 in Wayne County. | Bridge Improvement | 08/20/2009 | 09/16/2009 | 11/24/2009 | 335618 | 0.01
3272 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0800967 | This is a pavement resurfacing project on SR15, 2 miles north of US 20 to SR 120 in Bristol in Elkhart county that will lay 2 lays of asphalt to extend the life of the pavement, | Pavement Improvement | 04/26/2010 | 05/17/2010 | 10/01/2010 | 466215.25 | 1.86
3273 | Indiana | NOBLE, DE KALB |  | 03 | 0800974 | This is a Maintenance Resurfacing project, at US 6 - From SR 3 E jct (Kendallville) to I-69; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 05/17/2010 | 10/31/2010 | 2499046.86 | 12.02
3274 | Indiana | WHITLEY, HUNTINGTON |  | 03,05 | 0800975 | This project will improve sections and extend the life of US 24 in Huntington county from 1.66 Miles east of SR 9 est junction (Meridian Rd) to 0.75 miles east of SR 114 with a preventive maintenance | Pavement Improvement | 07/07/2009 | 09/08/2009 | 10/23/2009 | 2710401.31 | 10.64
3275 | Indiana | ALLEN | FORT WAYNE | 03 | 0800984 | This project will improve sections and extend the life of US 24 in Allen County with a pavement surface overlay | Pavement Improvement | 03/25/2009 | 08/17/2009 | 09/03/2009 | 666979.75 | 4.18
3276 | Indiana | WELLS |  | 06 | 0800986 | This is a Maintenance Resurfacing project, at SR 116 N jct to 2.44 miles N of US 224 (CR 850 N); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 03/24/2010 | 06/07/2010 | 08/28/2010 | 1098409.91 | 7.47
3277 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0810040 | This is a Safety project, at US 231 - at Parrish Avenue, Comm No 01-045-388; to perform Traffic Signals, New Or Modernized work. | Safety/Traffic Management | 01/05/2010 | 01/29/2010 | 05/31/2010 | 103748.5 | 0.01
3278 | Indiana | LAGRANGE |  | 03 | 0810097 | This is a Maintenance Resurfacing project, at E US 20 - From 0.20 miles E of SR 9 to 4.28 miles E of SR 3 (Lagrange/Steuben Co Line).; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/29/2009 |  | 10/31/2010 | 1384101 | 11.35
3279 | Indiana | JAY, ADAMS |  | 06 | 0810099 | This is a Maintenance Resurfacing project, at Jct of SR 18/67 (Jay Co) to 1.04 miles S of SR 124 (Adams Co).; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 04/13/2010 | 05/04/2010 | 08/14/2010 | 1229805.85 | 13.05
3280 | Indiana | MIAMI, WABASH, HUNTINGTON |  | 05 | 0810100 | This is a Maintenance Resurfacing project, at SR 19 (Miami Co) to SR 5 (Huntington Co).; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/15/2009 | 04/14/2010 | 10/01/2010 | 2840212.5 | 25.45
3281 | Indiana | STATEWIDE |  | 01,02,04 | 0810108 | This project will improve the pavement markings in the LaPorte Area. | Safety/Traffic Management | 04/16/2009 | 06/15/2009 | 11/12/2009 | 217958.7 | 0.01
3282 | Indiana | WARRICK |  | 08 | 0810123 | This project will improve drainage by repairing pipes at I-64, 1 mile East of SR 161 in Warrick County. | Pavement Improvement | 05/12/2009 | 06/10/2009 | 11/15/2009 | 117802.99 | 0.01
3283 | Indiana | CRAWFORD, WARRICK |  | 08 | 0810124 | This project will improve drainage by repairing pipes at I-64 from 5 miles East of I-164 to 1 mile West of SR 66 in Crawford and Warren Counties. | Pavement Improvement | 05/12/2009 | 06/10/2009 | 11/15/2009 | 139519.02 | 0.03
3284 | Indiana | WHITLEY |  | 03,05 | 0810228 | This is a Maintenance Resurfacing project, at SR 114 - From SR 105 to SR 9; to perform asphalt resurface, Functional work. | Pavement Improvement | 12/16/2009 | 04/08/2010 | 10/22/2010 | 1909280.99 | 7.89
3285 | Indiana | STEUBEN |  | 03 | 0810240 | This project will mitigate the environmental impacts of relocating a stream as part of the US 20 curve correction project, adding 370' of stream length, creating a floodplain and planting native veget | Other | 06/18/2009 | 08/24/2009 | 06/30/2010 | 92975 | 0.01
3286 | Indiana | WARREN |  | 08 | 0810254 | This project will extend the bridge life by repainting bridge beams at SR 55 over Big Pine Creek in Warren County. | Bridge Improvement | 09/01/2009 | 10/08/2009 | 11/15/2009 | 253700.68 | 0.01
3287 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0810342 | This project will improve sections and extend the life of US-31 from Youngs Creek Bridge to Westview Dr in Johnson County with a pavement surface overlay. | Pavement Improvement | 04/16/2009 | 05/14/2009 | 07/31/2009 | 694983.4 | 0.65
3288 | Indiana | TIPPECANOE, CLINTON |  | 04 | 0810387 | This project will improve drainage by repairing pipes at I-64 in Posey, Spencer and Vanderburgh Counties. | Pavement Improvement | 05/22/2009 | 06/15/2009 | 06/30/2009 | 253803.9 | 1.97
3289 | Indiana | PUTNAM |  | 08 | 0810388 | This project will improve sections and extend the life of SR 243 in Putnam County with a pavement surface overlay. | Pavement Improvement | 05/13/2009 | 06/09/2009 | 07/01/2009 | 650934.62 | 4.01
3290 | Indiana | JEFFERSON |  | 09 | 0810390 | This project will improve sections and extend the life of US 421 in Jefferson County with a pavement surface overlay | Pavement Improvement | 05/22/2009 | 06/24/2009 | 10/09/2009 | 596194.04 | 7.9
3291 | Indiana | JEFFERSON |  | 09 | 0810391 | This project will improve sections and extend the life of SR 57 in Jefferson County with a pavement surface overlay. | Pavement Improvement | 05/22/2009 | 06/25/2009 | 07/31/2009 | 211151.98 | 2.59
3292 | Indiana | MONROE, BROWN |  | 09 | 0810411 | This project will improve sections and extend the life of SR 46 from SR 446 to SR 135 with a pavement surface overlay. | Pavement Improvement | 05/13/2009 | 06/16/2009 | 08/31/2009 | 1784927.67 | 22.21
3293 | Indiana | JACKSON |  | 09 | 0810412 | This project will improve sections and extend the life ofS R-258 from SR 58 to Elm St in Jackson County with a pavement surface overlay. | Pavement Improvement | 06/01/2009 | 08/04/2009 | 11/13/2009 | 1224335.79 | 12.34
3294 | Indiana | JENNINGS, JEFFERSON |  | 09 | 0810413 | This project will improve sections and extend the life of SR 7 from 1.52 miles North of Clifty Creek Drive to SR 3 with a pavement surface overlay. | Pavement Improvement | 05/09/2009 | 08/13/2009 | 11/13/2009 | 1696103.37 | 14.97
3295 | Indiana | JENNINGS, JEFFERSON |  | 09 | 0810414 | This project will improve sections and extend the life of SR 250 from SR-3 to SR-7 with a pavement surface overlay. | Pavement Improvement | 10/07/2009 | 03/10/2010 | 06/30/2010 | 696378.04 | 9.94
3296 | Indiana | DEARBORN |  | 06,09 | 0810415 | This project will improve sections and extend the life of SR-46 from SR 1 to US 52 in Dearborn County with a pavement surface overlay. | Pavement Improvement | 07/28/2009 | 08/28/2009 | 10/16/2009 | 513103.76 | 5.3
3297 | Indiana | FULTON |  | 02,05 | 0810431 | This project will improve sections and extend the life of US 31 from the Fulton/Miami County Line to Old US 31 with a pavement surface overlay. | Pavement Improvement | 06/09/2009 | 07/14/2009 | 07/18/2009 | 487095.33 | 3.8
3298 | Indiana | STARKE |  | 02 | 0810432 | This project will improve sections and extend the life of US 35 through the town of Knox with a pavement surface overlay. | Pavement Improvement | 06/17/2009 | 07/18/2009 | 07/31/2009 | 323005.7 | 2.61
3299 | Indiana | FOUNTAIN |  | 08 | 0810453 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Pavement Improvement | 06/17/2009 | 07/16/2009 | 08/31/2010 | 568694.99 | 1.02
3300 | Indiana | STATEWIDE |  | 01,02,04 | 0810532 | This project will improve pavement markings in the LaPorte Area. | Safety/Traffic Management | 06/19/2009 | 07/06/2009 | 09/11/2009 | 318376 | 0.01
3301 | Indiana | CARROLL |  | 02 | 0810598 | This project will construct canal boat support facilities for the Wabash and Erie Canal in the City of Delphi. | Transportation Enhancements | 06/19/2009 | 11/10/2009 | 05/22/2010 | 401437.39 | 0.01
3302 | Indiana | WHITE |  | 04 | 0818022 | This project will improve the surface and rebuild sections of the bridge on US 421 over Little Monon Creek in White County. | Bridge Replacement | 03/21/2009 | 04/16/2009 | 08/28/2009 | 668112.1 | 0.01
3303 | Indiana | MADISON | ANDERSON | 06 | 0887013 | This project will add turn lanes and widen the intersection at SR 32 and Rangeline Road in Madison County. | Pavement Improvement | 07/08/2009 | 08/24/2009 | 07/31/2010 | 1920915 | 0.12
3304 | Indiana | SHELBY |  | 06 | 0900008 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | New Bridge Construction | 05/12/2009 | 07/22/2009 | 07/11/2011 | 252212.4 | 0.01
3305 | Indiana | POSEY, VANDERBURGH, SPENCER |  | 04 | 0900048 | This project will improve drainage by repairing pipes at I-64 in Posey, Spencer and Vanderburgh Counties. | Pavement Improvement | 05/12/2009 | 06/10/2009 | 11/15/2009 | 727204.41 | 45.01
3306 | Indiana | DUBOIS |  | 09 | 0900049 | This is a Facilities for Pedestrians and Bicycles project, at Jasper Multi-Use Path - Ph 2; from W 20th St to 30th St; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 11/23/2009 | 03/17/2010 | 07/15/2010 | 436161.45 | 0.01
3307 | Indiana | TIPPECANOE |  | 04 | 0900079 | This project will improve sections and extend the life of US 52 in West Lafayette with a pavement surface overlay. | Pavement Improvement | 06/03/2009 | 06/15/2009 | 11/28/2009 | 3816213.94 | 5.5
3308 | Indiana | LA PORTE |  | 02 | 0900082 | This is a Maintenance Resurfacing project, at US 35 - from Severs Rd to East Jct with US 20; to perform asphalt resurface, Functional work. | Pavement Improvement | 10/08/2009 | 10/15/2009 | 08/13/2010 | 1681597.77 | 4.12
3309 | Indiana | SHELBY |  | 06 | 0900083 | This project will build a new road from Amos Road to McKay Road in Shelby County. | New Construction | 08/11/2009 |  | 09/01/2010 | 1925233.13 | 0.763
3310 | Indiana | NEWTON |  | 01 | 0900084 | This project will improve sections and extend the life of US 41 in Newton County with a pavement surface overlay. | Pavement Improvement | 06/09/2009 | 07/17/2009 | 08/28/2009 | 1973246.73 | 11.88
3311 | Indiana | MARSHALL |  | 02 | 0900086 | This project will improve sections and extend the life of SR 106 in Marshall County with a pavement surface overlay. | Pavement Improvement | 06/17/2009 | 09/09/2009 | 10/16/2009 | 517285 | 5.26
3312 | Indiana | MARSHALL |  | 02 | 0900087 | This project will improve sections and extend the life of US 6 in Marshall County with a pavement surface overlay | Pavement Improvement | 06/17/2009 | 09/02/2009 | 10/02/2009 | 418872.18 | 5.41
3313 | Indiana | DEARBORN |  | 06 | 0900092 | This project will improve sections and extend the life of old US 52 on Old US-52 from IR-74 to West Harrison Corporate Limitswith a pavement surface overlay. | Pavement Improvement | 07/27/2009 | 08/21/2009 | 11/03/2009 | 310752.1 | 2.42
3314 | Indiana | DEARBORN |  | 09 | 0900093 | This project will improve sections and extend the life of York Ridge Road from SR-1 to North Dearborn Road with a pavement surface overlay. | Pavement Improvement | 11/23/2009 | 03/04/2010 | 06/30/2010 | 650901.55 | 7.44
3315 | Indiana | DEARBORN |  | 09 | 0900095 | This project will improve sections and extend the life of North Hogan Road from SR 350 to Hogan Road in Dearborn County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/16/2009 | 10/09/2009 | 234751.67 | 11.89
3316 | Indiana | DEARBORN |  | 09 | 0900096 | This project will improve sections and extend the life of North Dearborn from Ripley county line to SR1 in Dearborn County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/16/2009 | 10/09/2009 | 142476.7 | 7.56
3317 | Indiana | VIGO | TERRE HAUTE | 08 | 0900119 | This project will replace and restore the pavement on US-40, at Brown Blvd, Terre Haute, in Vigo County. | Pavement Widening | 09/15/2009 | 10/06/2009 | 06/30/2010 | 83633.1 | 0.1
3318 | Indiana | VIGO | TERRE HAUTE | 08 | 0900122 | This project will improve drainage by repairing pipes at I-70, .10 mile East of SR 46 in Vigo County. | Safety/Traffic Management | 06/25/2009 | 07/01/2009 | 08/15/2009 | 626338.95 | 0.1
3319 | Indiana | HAMILTON, HENDRICKS, MARION, BOONE | INDIANAPOLIS | 04,07 | 0900129 | This project will install traffic cameras on I-465, I-65, I-70 and I-74. | Other | 06/11/2009 | 08/05/2009 | 05/28/2010 | 475935 | 23.11
3320 | Indiana | TIPPECANOE |  | 04 | 0900133 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 1408413.79 | 0.01
3321 | Indiana | TIPPECANOE |  | 04 | 0900134 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 530746.71 | 0.01
3322 | Indiana | TIPPECANOE |  | 04 | 0900135 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 734550.61 | 0.01
3323 | Indiana | TIPPECANOE |  | 04 | 0900136 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 893652.86 | 0.01
3324 | Indiana | DEARBORN | CINCINNATI | 09 | 0900144 | This project will improve sections and extend the life of SR 148 from SR-48 to Maple Street with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 03/22/2010 | 07/16/2010 | 827466.29 | 9.17
3325 | Indiana | JEFFERSON |  | 09 | 0900145 | This project will improve sections and extend the life of SR 56 from East Junction of SR-62 to Crooked Creek Bridgewith a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 03/05/2010 | 07/16/2010 | 595391.45 | 2.56
3326 | Indiana | RIPLEY |  | 09 | 0900146 | This is a Maintenance Resurfacing project, at Jefferson/Ripley CL to US-50; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 04/12/2010 |  | 11/15/2010 | 1010697.88 | 12.57
3327 | Indiana | JACKSON |  | 09 | 0900147 | This is a Maintenance Resurfacing project, at SR 235 - to US-50; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/07/2009 | 11/02/2009 | 11/15/2009 | 747276.8 | 7.53
3328 | Indiana | DEARBORN |  | 09 | 0900159 | This project will improve sections and extend the life of Ridge Ave. from Decker Ave to Robinson Avenue with a pavement surface overlay. | Pavement Improvement | 07/15/2009 | 08/07/2009 | 09/30/2009 | 79526.63 | 0.42
3329 | Indiana | STARKE |  | 02 | 0900176 | This project will improve sections and extend the life of SR 10 in Starke County with a pavement surface overlay. | Pavement Improvement | 08/20/2009 | 09/21/2009 | 11/15/2009 | 1655345.65 | 6.81
3330 | Indiana | VIGO | TERRE HAUTE | 08 | 0900177 | This is a Reconstruction (no added capacity) project, at 7th Street and Springhill Road; to perform Intersect. Improv. W/ Added Turn Lanes work. | Pavement Improvement | 04/08/2010 | 04/23/2010 | 08/28/2010 | 991533.27 | 0.01
3331 | Indiana | LAKE, PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900211 | This project will patch deteriorated pavement areas and seal cracks on I-94 from 1.5 mi. E of I-65 to SR 249 in Lake and Porter Counties. | Pavement Improvement | 07/22/2009 | 08/31/2009 | 11/13/2009 | 907112.68 | 15.76
3332 | Indiana | CARROLL, CASS |  | 02 | 0900218 | This is a Maintenance Restoration & Rehabilitation project, at SR 25 - from SR 218 in Delphi to Logansport; to perform Crack Sealing work. | Pavement Improvement | 01/22/2010 | 05/20/2010 | 06/30/2010 | 153095.8 | 20.26
3333 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900219 | This project will patch deteriorated pavement areas and seal cracks on US 20 from SR 912 to Bridge St. in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 101851.5 | 9.88
3334 | Indiana | WASHINGTON |  | 09 | 0900229 | This is a Maintenance Resurfacing project, at SR-135 to 1.4 miles W Pekin; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/06/2010 | 04/12/2010 | 06/30/2010 | 1148707.4 | 6.14
3335 | Indiana | WASHINGTON |  | 09 | 0900231 | This is a Maintenance Resurfacing project, at East of Jim Day Road to Washington /Scott CL; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/06/2010 | 06/24/2010 | 09/30/2010 | 1894683.26 | 10.88
3336 | Indiana | DECATUR, FRANKLIN |  | 06 | 0900232 | This is a Maintenance Resurfacing project, at 0.7 miles E of US-421 to the Batesville CL; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/06/2010 | 04/14/2010 | 07/15/2010 | 1833545.88 | 13.63
3337 | Indiana | JOHNSON |  | 05,04,06 | 0900238 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | New Bridge Construction | 05/12/2009 | 07/22/2009 | 07/11/2011 | 242787.2 | 0.01
3338 | Indiana | DECATUR |  | 06 | 0900260 | This is a Maintenance Resurfacing project, at I-74 to Seymour District/Greenfield District Line; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/07/2010 |  | 11/15/2010 | 1248345.2 | 6.02
3339 | Indiana | PERRY |  | 09 | 0900296 | This project will improve safety and extend the life of the bridge(s) on County Road 211 over I-64 in Perry County. | Bridge Improvement | 07/07/2009 | 09/17/2009 | 06/30/2010 | 419566 | 0.214
3340 | Indiana | KNOX |  | 08 | 0900297 | This project will improve safety and extend the life of the bridge(s) on US 41 over Main Street in Knox County. | Bridge Improvement | 07/10/2009 |  | 07/31/2010 | 345750.5 | 0.122
3341 | Indiana | KNOX |  | 08 | 0900298 | This project will improve safety and extend the life of the bridge(s) on US 41 over Main Street in Knox County. | Bridge Improvement | 07/10/2009 |  | 07/31/2010 | 309249.5 | 0.122
3342 | Indiana | GREENE |  | 08 | 0900299 | This project will improve safety and extend the life of the bridge(s) on SR 157 over White River in Green County. | Bridge Improvement | 07/24/2009 | 09/22/2009 | 06/30/2010 | 961859.92 | 0.742
3343 | Indiana | OWEN |  | 08 | 0900300 | This project will improve safety and extend the life of the bridge(s) on US 231 over Fish Creek in Owen County. | Bridge Improvement | 07/24/2009 | 09/22/2009 | 06/30/2010 | 621795 | 0.225
3344 | Indiana | HUNTINGTON |  | 05 | 0900301 | This project will improve safety and extend the life of the bridge(s) on SR 124 over Brock Creek in Huntington County. | Bridge Improvement | 07/07/2009 | 08/21/2009 | 10/30/2009 | 271400.3 | 0.68
3345 | Indiana | HUNTINGTON |  | 05 | 0900302 | This project will improve safety and extend the life of the bridge(s) on County Road 300 South over I-69 in Huntington County. | Bridge Improvement | 07/07/2009 | 08/21/2009 | 10/30/2009 | 421012.07 | 0.208
3346 | Indiana | BARTHOLOMEW |  | 09 | 0900303 | This project will improve safety and extend the life of the bridge(s) on US 31 over Little Sand Creek in Bartholomew County. | Bridge Improvement | 10/09/2009 | 04/05/2010 | 10/31/2010 | 675666.07 | 0.108
3347 | Indiana | BARTHOLOMEW |  | 09 | 0900304 | This project will improve safety and extend the life of the bridge(s) on SR 46 over the abandoned Railroad in Bartholomew County. | Bridge Improvement | 10/09/2009 | 04/05/2010 | 10/31/2010 | 660012.93 | 0.01
3348 | Indiana | BROWN |  | 09 | 0900305 | This project will improve safety and extend the life of the bridge(s) on SR 45 over Beanblossom Creek in Brown County. | Bridge Improvement | 07/07/2009 | 06/07/2010 | 10/29/2010 | 517603 | 0.125
3349 | Indiana | BROWN |  | 09 | 0900306 | This project will improve safety and extend the life of the bridge(s) on SR 45 over Beanblossom Creek in Brown County. | Bridge Improvement | 07/07/2009 | 06/07/2010 | 10/29/2010 | 468003 | 0.01
3350 | Indiana | DECATUR |  | 06 | 0900307 | This project will improve safety and extend the life of the bridge(s) on SR 3 over Clifty Creek in Decatur County. | Bridge Improvement | 07/07/2009 | 03/10/2010 | 11/19/2010 | 760685.65 | 0.01
3351 | Indiana | RIPLEY |  | 09 | 0900308 | This project will improve safety and extend the life of the bridge(s) on US 50 over Laughery Creek in Ripley County. | Bridge Improvement | 08/18/2009 | 03/10/2010 | 11/19/2010 | 730256.8 | 0.01
3352 | Indiana | SCOTT |  | 09 | 0900309 | This project will improve safety and extend the life of the bridge(s) on SR 3 over the abandoned Railroad in Scott County. | Bridge Improvement | 07/24/2009 | 04/01/2010 | 09/20/2010 | 520602.25 | 0.217
3353 | Indiana | VERMILLION |  | 08 | 0900310 | This project will improve safety and extend the life of the bridge(s) on SR 63 over Brouiletts Creek in Vermillion County. | Bridge Improvement | 08/18/2009 | 04/09/2010 | 10/15/2010 | 775788 | 0.421
3354 | Indiana | WARREN |  | 08 | 0900311 | This project will improve safety and extend the life of the bridge(s) on SR 263 over Redwood Creek in Warren County. | Bridge Improvement | 07/17/2009 | 09/10/2009 | 07/18/2010 | 654751.5 | 0.15
3355 | Indiana | VERMILLION |  | 08 | 0900312 | This project will improve safety and extend the life of the bridge(s) on SR 71 over Little Vermillion River in Vermillion County. | Bridge Improvement | 08/18/2009 | 04/09/2010 | 10/15/2010 | 455103 | 0.15
3356 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900314 | This project will patch deteriorated pavement areas and seal cracks on I-65 from SR 2 to US 231 in Lake County. | Pavement Improvement | 07/22/2009 | 08/31/2009 | 11/13/2009 | 584240.48 | 7.38
3357 | Indiana | STARKE, PORTER, MARSHALL, LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02,01 | 0900315 | This project will patch deteriorated pavement areas and seal cracks on US 30 from the Lake/Porter County Line to SR 17 in LaPorte, Marshall, Porter and Starke Counties. | Pavement Improvement | 07/22/2009 | 08/31/2009 | 11/13/2009 | 196608.48 | 50.08
3358 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900316 | This project will patch deteriorated pavement areas and seal cracks on US 30 from US 41 to SR 55 in Lake County. | Pavement Improvement | 07/22/2009 | 08/31/2009 | 11/13/2009 | 106560.48 | 5.71
3359 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900317 | This project will patch deteriorated pavement areas and seal cracks on I-94 from SR 249 to SR 49 in Porter County. | Pavement Improvement | 07/22/2009 | 08/31/2009 | 11/13/2009 | 68160.48 | 7.08
3360 | Indiana | LA PORTE | MICHIGAN CITY | 02 | 0900318 | This project will patch deteriorated pavement areas and seal cracks on I-94 from US 35 to the Michigan State Line in LaPorte County. | Pavement Improvement | 07/22/2009 | 08/31/2009 | 11/13/2009 | 55680.48 | 5.85
3361 | Indiana | BARTHOLOMEW | COLUMBUS | 06 | 0900321 | This project will improve sections and extend the life of 25th St. from CR 350 E to SR 9 with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/09/2009 | 11/15/2009 | 496214.92 | 4.3
3362 | Indiana | PARKE |  | 08 | 0900322 | This project will improve the surface and rebuild sections of the bridge on SR 47 at Turkey Run in Parke County. | Bridge Improvement | 07/11/2009 | 09/16/2009 | 11/15/2009 | 303605.25 | 0.317
3363 | Indiana | WARREN |  | 08 | 0900323 | This project will improve the surface and rebuild sections of the bridge on US 136 at the Wabash River in Warren County. | Bridge Improvement | 07/07/2009 | 09/10/2009 | 09/30/2009 | 471268.58 | 0.935
3364 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900327 | This project will patch deteriorated pavement areas and seal cracks on US 231 from SR 912 to Bridge St. in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 22020.5 | 6.3
3365 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900329 | This project will patch deteriorated pavement areas and seal cracks on SR 2 from Cline Ave. to SR 53 in Porter County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 60440.5 | 13.4
3366 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900331 | This project will patch deteriorated pavement areas and seal cracks on US 41 from Huehn St. to 0.25 mi.. N. of Sheffield Ave. in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 32000.5 | 2.57
3367 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900333 | This project will patch deteriorated pavement areas and seal cracks on US 12 from W. of Calumet Ave. to the Illinois State Line. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 30625.5 | 1.31
3368 | Indiana | HOWARD |  | 05 | 0900334 | This project will improve sections and extend the life of Howard County Road 200N from 1350 East to the county line with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 26460.37 | 0.01
3369 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900335 | This project will patch deteriorated pavement areas and seal cracks on US 12 from Schrage Ave. to the lift bridge S. of Riley Road in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 89218 | 1.45
3370 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900336 | This project will improve the surface and rebuild sections of the bridge on SR 912 over I-80 in Lake County. | Bridge Improvement | 09/14/2009 | 05/03/2010 | 06/30/2010 | 298381.48 | 0.01
3371 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900337 | This project will improve the surface and rebuild sections of the bridge on SR 912 over I-80 in Lake County. | Bridge Improvement | 09/14/2009 | 05/03/2010 | 06/30/2010 | 300423.28 | 0.01
3372 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900339 | This project will patch deteriorated pavement areas and seal cracks on US 20 from SR 249 to US 20/I-94 in Porter County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 59680.5 | 3.54
3373 | Indiana | HOWARD |  | 02 | 0900340 | This project will improve sections and extend the life of Howard County Road 200W from County Road 200North to County Road 325 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 81387.28 | 1.2
3374 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900341 | This project will improve the surface and rebuild sections of the bridge on US 41 over Brown Ditch in Lake County. | Bridge Improvement | 09/14/2009 | 10/12/2009 | 10/31/2009 | 27193.25 | 0.88
3375 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900342 | This project will patch deteriorated pavement areas and seal cracks on SR 312 from US 41 to Parrish Ave. in Lake County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 32000.25 | 3.56
3376 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900343 | This project will improve the surface and rebuild sections of the bridge on US 41 over Brown Ditch in Lake County. | Bridge Improvement | 09/14/2009 | 10/12/2009 | 10/31/2009 | 23371.25 | 0.88
3377 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900344 | This project will patch deteriorated pavement areas and seal cracks on US 31 from US 20 to the Michigan State Line in St. Joseph County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 75952.75 | 3.84
3378 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900345 | This project will improve the surface and rebuild sections of the bridge on US 41 over Singleton Ditch in Lake County. | Bridge Improvement | 09/14/2009 | 10/12/2009 | 10/31/2009 | 23371.25 | 0.94
3379 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900346 | This project will improve the surface and rebuild sections of the bridge on US 41 over Singleton Ditch in Lake County. | Bridge Improvement | 09/14/2009 | 10/12/2009 | 10/31/2009 | 23371.25 | 0.94
3380 | Indiana | MARSHALL | SOUTH BEND (MI) | 02 | 0900347 | This project will patch deteriorated pavement areas and seal cracks ON US 6 from 0.5 mi. W of SR 106 to 0.5 mi. E of SR 106 in Marshall County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 27450.25 | 4.14
3381 | Indiana | JENNINGS |  | 09 | 0900348 | This project will improve the surface and rebuild sections of the bridge on US 50 at Vernon Fork Muscatatuck River in Jennings County. | Bridge Improvement | 09/17/2009 | 06/10/2010 | 07/31/2010 | 280871.8 | 0.01
3382 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900349 | This project will patch deteriorated pavement areas and seal cracks on US 12 from SR 249 to SR 149 bridge in Porter County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 20400.25 | 1.98
3383 | Indiana | HARRISON |  | 09 | 0900350 | This project will improve the surface and rebuild sections of the bridge on SR 135 at Lick Run Creek in Harrison County. | Bridge Improvement | 07/20/2009 | 08/20/2009 | 09/26/2009 | 495227.43 | 0.122
3384 | Indiana | BARTHOLOMEW |  | 06 | 0900351 | This project will improve the surface and rebuild sections of the bridge on I-65 over Driftwood River in Bartholomew County. | Bridge Improvement | 08/18/2009 | 05/27/2010 | 10/01/2010 | 606321.7 | 0.01
3385 | Indiana | BARTHOLOMEW |  | 06 | 0900352 | This project will improve the surface and rebuild sections of the bridge on I-65 over Driftwood River in Bartholomew County. | Bridge Improvement | 08/18/2009 | 05/27/2010 | 10/01/2010 | 436878.3 | 0.01
3386 | Indiana | KNOX |  | 08 | 0900353 | This project will improve the surface and rebuild sections of the bridge on US 50 over Wabash River in Knox County. | Bridge Improvement | 07/15/2009 | 08/14/2009 | 10/15/2009 | 52897.74 | 0.01
3387 | Indiana | LA PORTE | MICHIGAN CITY | 02 | 0900354 | This project will patch deteriorated pavement areas and seal cracks on SR 212 from US 12 to US 20 in LaPorte County. | Pavement Improvement | 07/22/2009 | 08/10/2009 | 11/13/2009 | 32000.5 | 3.36
3388 | Indiana | KNOX |  | 08 | 0900355 | This project will improve the surface and rebuild sections of the bridge on US 50 over Wabash River in Knox County. | Bridge Improvement | 07/15/2009 | 08/14/2009 | 10/15/2009 | 52307.59 | 0.01
3389 | Indiana | LAWRENCE |  | 08 | 0900356 | This project will improve the surface and rebuild sections of the bridge on US 50 over White River in Lawrence County. | Bridge Improvement | 07/15/2009 | 08/14/2009 | 10/15/2009 | 41930.71 | 0.93
3390 | Indiana | WAYNE |  | 06 | 0900357 | This project will improve sections and extend the life of Arba Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 04/19/2010 | 06/04/2010 | 350293.36 | 3.58
3391 | Indiana | LAWRENCE |  | 08 | 0900358 | This project will improve the surface and rebuild sections of the bridge on US 50 over White River in Lawrence County. | Bridge Improvement | 07/15/2009 | 08/14/2009 | 10/15/2009 | 40828.81 | 0.93
3392 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900363 | This project will extend the bridge life by repainting bridge beams at I-64 over SR 111 & Main Street in Floyd County. | Bridge Improvement | 10/29/2009 | 01/04/2010 | 09/25/2010 | 929831.88 | 0.02
3393 | Indiana | CASS |  | 02 | 0900364 | This is a Maintenance Restoration & Rehabilitation project, at SR 25 - from Logansport to SR 16; to perform Crack Sealing work. | Pavement Improvement | 01/22/2010 | 05/20/2010 | 06/30/2010 | 31270.8 | 11.42
3394 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900365 | This project will extend the bridge life by repainting bridge beams at I-64 over Southern Railroad in Floyd County. | Bridge Improvement | 10/29/2009 | 01/04/2010 | 09/25/2010 | 871470.52 | 0.02
3395 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900366 | This project will extend the bridge life by repainting bridge beams at I-64 over SR 111 & Main Street in Floyd County. | Bridge Improvement | 10/29/2009 | 01/04/2010 | 09/25/2010 | 1430958.6 | 0.02
3396 | Indiana | NEWTON |  | 01 | 0900367 | This is a Maintenance Restoration & Rehabilitation project, at US 41 - from SR 114 to SR 14; to perform Crack Sealing work. | Pavement Improvement | 01/22/2010 | 05/20/2010 | 06/30/2010 | 40500.8 | 5.31
3397 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0900368 | This project will extend the bridge life by repainting bridge beams at I-65 at Riverside Drive & Market Street in Clark County. | Bridge Improvement | 08/03/2009 | 09/23/2009 | 11/01/2009 | 570539.54 | 0.648
3398 | Indiana | JASPER |  | 01 | 0900369 | This is a Maintenance Restoration & Rehabilitation project, at US 231 - from SR 14 to CR 600N; to perform Crack Sealing work. | Pavement Improvement | 01/22/2010 | 05/20/2010 | 06/30/2010 | 22750.8 | 5.05
3399 | Indiana | MARSHALL |  | 02 | 0900371 | This is a Maintenance Restoration & Rehabilitation project, at US 31 - from SR 110 to 0.1mi S of SR 10; to perform Crack Sealing work. | Pavement Improvement | 01/22/2010 | 05/20/2010 | 06/30/2010 | 88638.8 | 4.73
3400 | Indiana | VANDERBURGH | EVANSVILLE (KY) | 08 | 0900384 | This is a Facilities for Pedestrians and Bicycles project, at Greenway bike/ped trail from Franklin St to Maryland St (Sect 3-C2); to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 04/01/2010 | 06/01/2010 | 06/15/2011 | 1892569 | 0.01
3401 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0900406 | This project will upgrade and improve the traffic signals at various locations in the town of Westfield. | Safety/Traffic Management | 11/23/2009 | 12/21/2009 | 03/01/2010 | 65210.2 | 0.01
3402 | Indiana | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900423 | This is a Maintenance Resurfacing project, at SR 4 - On Maple Avenue from Monroe Street (SR4) to Rose Street; to perform Surface Treatment work. | Pavement Improvement | 01/08/2010 | 04/05/2010 | 06/01/2010 | 97094.97 | 0.3
3403 | Indiana | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900424 | This is a Maintenance Resurfacing project, at City of LaPorte on Park Street from Norfolk/Southern RR to McClung Road; to perform Surface Treatment work. | Pavement Improvement | 01/08/2010 | 04/05/2010 | 06/01/2010 | 50971.96 | 0.27
3404 | Indiana | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900425 | This is a Maintenance Resurfacing project, at 1st Street from Central Avenue to J Street (SR 2); to perform Surface Treatment work. | Pavement Improvement | 01/08/2010 | 04/05/2010 | 06/01/2010 | 63481.47 | 0.32
3405 | Indiana | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900426 | This is a Maintenance Resurfacing project, at 1st Street from J Street (SR 2) to Indiana Avenue (US 35); to perform Surface Treatment work. | Pavement Improvement | 01/08/2010 | 04/05/2010 | 06/01/2010 | 219215.5 | 0.58
3406 | Indiana | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900427 | This is a Maintenance Resurfacing project, at Street from 10th Street to 18th Street; to perform Surface Treatment work. | Pavement Improvement | 01/08/2010 | 04/05/2010 | 06/01/2010 | 97874.83 | 0.5
3407 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900429 | This is a Maintenance Resurfacing project, at 73rd Avenue from Clark Street to I-65 overpass; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 |  | 07/31/2010 | 708954.07 | 3.5
3408 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900430 | This is a Maintenance Resurfacing project, at Madison Street/Harrison Street from US 30 to 53rd Avenue; to perform Surface Treatment work. | Pavement Improvement | 01/15/2010 | 03/30/2010 | 06/30/2010 | 327191.87 | 3.61
3409 | Indiana | CRAWFORD |  | 09 | 0900434 | This project will improve drainage by repairing pipes at I-64 in Crawford County. | Pavement Improvement | 07/16/2009 | 08/31/2009 | 06/01/2010 | 1605682 | 11.28
3410 | Indiana | VANDERBURGH |  | 08 | 0900436 | This project will improve drainage by repairing pipes at SR 66 in Crawford County. | Other | 07/06/2009 | 08/31/2009 | 10/15/2009 | 735970.32 | 3.99
3411 | Indiana | MARSHALL |  | 02 | 0900441 | This project will complete the restoration of the Bremen Train Depot. | Transportation Enhancements | 12/16/2009 |  | 10/31/2010 | 289960.37 | 0.01
3412 | Indiana | MARSHALL |  | 02 | 0900442 | This project will improve the Marshall County Historical Museum. | Transportation Enhancements | 01/08/2010 |  | 10/31/2010 | 393189.06 | 0.01
3413 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900443 | This is a Historic Preservation project to update and preserve the streetscape on at Central Ave. from 119th to 116th and on Oliver St, from 119th to 117th in the town of Whiting, Lake county. | Transportation Enhancements | 01/14/2010 | 04/13/2010 | 06/30/2010 | 264180.25 | 0.63
3414 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900448 | This project will replace the bridge deck on SR 23 over Mishawaka Ave in St Joseph County. | Bridge Improvement | 08/18/2009 | 10/09/2009 | 05/15/2010 | 730528.5 | 0.146
3415 | Indiana | FOUNTAIN |  | 04 | 0900449 | This project will improve safety and extend the life of the bridge(s) on SR 341 over Coal Creek in Fountain County. | Bridge Improvement | 07/17/2009 | 09/10/2009 | 07/18/2010 | 357212.5 | 0.71
3416 | Indiana | PARKE |  | 08 | 0900450 | This project will improve safety and extend the life of the bridge(s) on US 41 over Big Raccoon Creek in Parke County. | Bridge Improvement | 07/07/2009 | 04/07/2010 | 07/31/2010 | 795594.75 | 0.384
3417 | Indiana | WABASH |  | 05 | 0900451 | This project will improve safety and extend the life of the bridge(s) on Sr 13 over Paw Paw Creek in Wabash County. | Pavement Improvement | 07/07/2009 | 08/05/2009 | 10/30/2009 | 144530.47 | 0.42
3418 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900452 | This project will improve safety and extend the life of the bridge(s) on SR 4 over Rock Run Creek in Elkhart County. | Bridge Improvement | 08/18/2009 | 09/14/2009 | 10/23/2009 | 121166.6 | 0.44
3419 | Indiana | ADAMS |  | 06 | 0900453 | This project will improve safety and extend the life of the bridge on SR 218 over Wagley Farlow Ditch in Adams County by removing and replacing the wearing surface of the deck. | Bridge Improvement | 07/07/2009 | 09/03/2009 | 10/30/2009 | 326688.84 | 0.03
3420 | Indiana | JASPER |  | 01 | 0900469 | This project will improve sections and extend the life of County Road 900North from 200 west to 300 east in Jasper County with a pavement surface overlay. | Pavement Improvement | 12/31/2009 | 04/14/2010 | 06/05/2010 | 469658 | 5.04
3421 | Indiana | JASPER |  | 02 | 0900470 | This project will improve sections and extend the life of County Road 400West from Northern County limits to intersection at SR 10 in Jasper County with a pavement surface overlay. | Pavement Improvement | 12/31/2009 | 04/14/2010 | 06/05/2010 | 575812.67 | 6.67
3422 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900472 | This is a Maintenance Resurfacing project, at Kennedy Avenue from the Toll Road to Michigan Avenue; to perform Surface Treatment work. | Pavement Improvement | 01/19/2010 | 03/25/2010 | 06/09/2010 | 363065.78 | 2
3423 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900473 | This is a Landscaping project, at E Columbus Drive from Cline Avenue to Main Street; to perform Landscaping work. | Transportation Enhancements | 03/26/2010 | 04/02/2010 | 06/15/2010 | 99538.87 | 0.9
3424 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900474 | This is a Safety project, at E Columbus Drive from Cline Avenue to Main Street; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 03/26/2010 | 04/02/2010 | 06/15/2010 | 329757.93 | 0.9
3425 | Indiana | MARSHALL |  | 02 | 0900493 | This project will improve sections and extend the life of 9A Road from SR 31 to King Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 04/21/2010 | 07/02/2010 | 16159.25 | 0.733
3426 | Indiana | MARSHALL |  | 02 | 0900496 | This project will improve sections and extend the life of Lincoln Highway from King Road to Fir Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/06/2009 | 06/30/2010 | 566060.81 | 5.91
3427 | Indiana | MARSHALL |  | 02 | 0900500 | This project will improve sections and extend the life of 4th Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 04/21/2010 | 07/02/2010 | 5861.81 | 0.254
3428 | Indiana | MARSHALL |  | 02 | 0900501 | This project will improve sections and extend the life of King Road from Plymouth-Goshen Trail to 4th Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 04/21/2010 | 07/02/2010 | 78275.02 | 3.697
3429 | Indiana | MARSHALL |  | 02 | 0900502 | This project will improve sections and extend the life of Plymouth-Goshen Trail from Linden Road to King Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 04/21/2010 | 07/02/2010 | 17565.74 | 0.733
3430 | Indiana | MARSHALL |  | 02 | 0900514 | This project will improve sections and extend the life of Lincoln Highway from Fir Road to Elm Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/06/2009 | 06/30/2010 | 81746.03 | 1.042
3431 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900518 | This is a Maintenance Resurfacing project, at Wisconsin St. from Old Ridge Road to 10th Street; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 05/10/2010 | 06/05/2010 | 350540.74 | 0.97
3432 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900520 | This is a New Construction Roadway project, at Lake Park Avenue from Ridge Road (37th Ave) to Old Ridge Road; to perform Surface Treatment work. | New Construction | 01/08/2010 | 06/28/2010 | 06/30/2010 | 193772.83 | 0.92
3433 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900521 | This is a Maintenance Resurfacing project, at 3rd Street from S LaSalle St to Main Street; to perform Surface Treatment work. | Pavement Improvement | 10/13/2009 | 11/05/2009 | 11/21/2009 | 282412.76 | 1.5
3434 | Indiana | BROWN |  | 09 | 0900535 | This project will improve sections and extend the life of Gatesville Rd. from SR 135 to Salt Cree with a pavement surface overlay. | Pavement Improvement | 11/23/2009 | 05/03/2010 | 07/01/2010 | 381688.28 | 6.33
3435 | Indiana | BROWN |  | 09 | 0900536 | This project will improve sections and extend the life of Christiansburg Rd. Rd from SR 135 S to Bells with a pavement surface overlay. | Pavement Improvement | 11/23/2009 | 05/03/2010 | 07/01/2010 | 247456.61 | 4.06
3436 | Indiana | KNOX |  | 08 | 0900537 | This project will improve sections and extend the life of Bicknell Slab Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/24/2009 | 11/30/2009 | 539391.24 | 8.03
3437 | Indiana | KNOX |  | 08 | 0900538 | This project will improve sections and extend the life of Sixth St in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/08/2009 | 11/30/2009 | 142978.5 | 1.53
3438 | Indiana | KNOX |  | 08 | 0900539 | This project will improve sections and extend the life of Sixth Street Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/24/2009 | 11/30/2009 | 196066.53 | 2.9
3439 | Indiana | DAVIESS |  | 08 | 0900540 | This project will improve sections and extend the life of Cannelburt Rd in Daviess County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/18/2009 | 11/30/2009 | 313718.95 | 3.2
3440 | Indiana | GREENE |  | 08 | 0900541 | This is a Maintenance Resurfacing project, at NW 11th St to NW 5th St; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 06/01/2010 | 08/31/2010 | 70314.86 | 0.43
3441 | Indiana | GIBSON |  | 08 | 0900542 | This is a Maintenance Resurfacing project, at 12th St to Main St; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 06/01/2010 | 08/31/2010 | 127834.08 | 0.73
3442 | Indiana | GREENE |  | 08 | 0900543 | This is a Maintenance Resurfacing project, at 5th St to 12th St; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 06/01/2010 | 08/31/2010 | 68407.98 | 1.03
3443 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0900545 | This is a Maintenance Resurfacing project, at Kopp Lane from Hallmark Blvd to Eastern Blvd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 |  | 04/07/2010 | 109600 | 0.72
3444 | Indiana | SPENCER |  | 09 | 0900546 | This project will improve sections and extend the life of Old SR 245 with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 09/25/2009 | 11/30/2009 | 582496.64 | 3.89
3445 | Indiana | DAVIESS |  | 08 | 0900547 | This project will improve the traffic signs in Daviess County. | Safety/Traffic Management | 09/01/2009 | 01/18/2010 | 12/31/2009 | 321489 | 0.01
3446 | Indiana | PERRY |  | 09 | 0900548 | This project will improve sections and extend the life of French Ridge Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/14/2009 | 11/30/2009 | 478205.43 | 5.15
3447 | Indiana | PERRY |  | 09 | 0900549 | This project will improve sections and extend the life of Leopold Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/14/2009 | 11/30/2009 | 549249.41 | 6.9
3448 | Indiana | MARSHALL |  | 02 | 0900550 | This project will improve sections and extend the life of South Michigan St. in Marshall County with a pavement surface overlay | Pavement Improvement | 09/11/2009 | 04/21/2010 | 07/02/2010 | 292820.96 | 4.283
3449 | Indiana | MARSHALL |  | 02 | 0900551 | This project will improve sections and extend the life of Miami Highway from SR 106 to the county line in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 04/21/2010 | 07/02/2010 | 42123.04 | 2.039
3450 | Indiana | WHITE |  | 04 | 0900554 | This is a Maintenance Resurfacing project, at North Main Street from TP&W railroad tracks N 2,665 feet; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 02/22/2010 | 03/31/2010 | 07/01/2010 | 268352.11 | 0.5
3451 | Indiana | WHITE |  | 04 | 0900555 | This is a Maintenance Resurfacing project, at North Illinois Street from TP&W railroad N 2,660 feet; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 02/22/2010 | 03/31/2010 | 07/01/2010 | 206935.48 | 0.4
3452 | Indiana | MARSHALL |  | 02 | 0900556 | This project will improve sections and extend the life of Monterey Rd with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 04/21/2010 | 07/02/2010 | 36552.76 | 1.687
3453 | Indiana | ALLEN |  | 03 | 0900558 | This is a Small Structure project, at I-69 & I-469 Interchange Ramp"D",Pipe #7, EB to SB I-69, 0.18 Miles S. of I-469; to perform Pipe Lining work. | Other | 04/14/2010 |  | 10/02/2010 | 44401.65 | 0.1
3454 | Indiana | CARROLL |  | 02 | 0900560 | This project will improve sections and extend the life of Road 600S with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 05/18/2010 | 06/30/2010 | 558472.41 | 5.52
3455 | Indiana | CARROLL |  | 02 | 0900561 | This project will improve sections and extend the life of Road 75W in Carroll County with a pavement surface overlay. | Pavement Improvement | 10/14/2009 | 04/02/2010 | 10/15/2009 | 271533.7 | 1.75
3456 | Indiana | CASS |  | 02 | 0900562 | This project will improve sections and extend the life of Road 700E with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/18/2009 | 10/12/2009 | 708918.62 | 5.5
3457 | Indiana | CASS |  | 02 | 0900563 | This project will improve sections and extend the life of Road 400S in Cass County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/18/2009 | 10/12/2009 | 53499.41 | 0.5
3458 | Indiana | CASS |  | 02 | 0900564 | This project will improve sections and extend the life of Road 200E in Cass County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 05/18/2010 | 06/30/2010 | 330703.46 | 3
3459 | Indiana | SPENCER |  | 09 | 0900566 | This project will improve sections and extend the life of Old SR 45 in Spencen County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 09/25/2009 | 11/30/2009 | 387969.28 | 3.79
3460 | Indiana | SPENCER |  | 09 | 0900567 | This project will improve sections and extend the life of Fulda Shortcut Rd with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 09/25/2009 | 11/30/2009 | 220751.47 | 4.18
3461 | Indiana | SPENCER |  | 09 | 0900568 | This project will improve sections and extend the life of Road 800 E in Spencer County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 09/25/2009 | 11/30/2009 | 121839.45 | 2.28
3462 | Indiana | MONTGOMERY |  | 04 | 0900572 | This project will replace and restore the pavement on Nucor Road in Crawfordsville. | Pavement Improvement | 09/03/2009 | 08/03/2009 | 11/15/2009 | 588659.98 | 5.86
3463 | Indiana | GIBSON |  | 08 | 0900573 | This project will improve sections and extend the life of Road 350 E in Gibson County with a pavement surface overlay | Pavement Improvement | 09/01/2009 | 09/15/2009 | 11/30/2009 | 482102.74 | 5.3
3464 | Indiana | MONTGOMERY |  | 04 | 0900574 | This project will replace and restore the pavement on Old SR 55 in Wingate. | Pavement Improvement | 09/03/2009 | 08/03/2009 | 11/15/2009 | 963868.51 | 10.92
3465 | Indiana | GIBSON |  | 08 | 0900575 | This project will improve sections and extend the life of Road 550 E in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 11/30/2009 | 400716.23 | 3.51
3466 | Indiana | GIBSON |  | 08 | 0900576 | This project will improve sections and extend the life of Road 350 S in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 11/30/2009 | 225187.43 | 2.62
3467 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900577 | This project will improve sections and extend the life of CR 50 S/Old Boonville HWY in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/06/2009 | 11/30/2009 | 201964.34 | 2.1
3468 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900578 | This project will improve sections and extend the life of Road 350S/Vann Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/06/2009 | 11/30/2009 | 366914.3 | 3.9
3469 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900579 | This project will improve sections and extend the life of Road 25w/Yankeetown Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/06/2009 | 11/30/2009 | 59422.22 | 0.7
3470 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900580 | This project will improve sections and extend the life of Old SR 66 in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/06/2009 | 11/30/2009 | 142584.85 | 1.8
3471 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900581 | This project will improve sections and extend the life of CR 800N/Elberfeld Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/16/2009 | 11/30/2009 | 120251.19 | 1.1
3472 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0900582 | This project will improve sections and extend the life of Rd 1100S/North Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/16/2009 | 11/30/2009 | 121332.76 | 1.7
3473 | Indiana | HENDRICKS | INDIANAPOLIS | 04 | 0900584 | This is a Maintenance Restoration & Rehabilitation project, at US 40 - In Plainfield from the East end of the Bridge over White Lick Creek to Carr Rd; to perform Road Reconstruction work. | Pavement Improvement | 09/18/2009 | 10/05/2009 | 11/12/2010 | 2391134.09 | 1.08
3474 | Indiana | KNOX |  | 08 | 0900585 | This project will improve sections and extend the life of 2nd St in Knox County with a pavement surface overlay | Pavement Improvement | 09/15/2009 | 10/30/2009 | 11/30/2009 | 107323.67 | 0.625
3475 | Indiana | MADISON |  | 06 | 0900599 | This project will improve sections and extend the life of Old SR 132 in Madison County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/16/2009 | 10/30/2009 | 333962.38 | 5.22
3476 | Indiana | MADISON |  | 06 | 0900605 | This project will restore the pavement on Madison County Road 600 W with a new surface course. | Pavement Improvement | 09/14/2009 | 09/22/2009 | 10/30/2009 | 340821.51 | 3.83
3477 | Indiana | NOBLE |  | 03 | 0900606 | This project will improve sections and extend the life of Northport Rd. from SR 9 to Angling Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/23/2009 | 10/31/2009 | 321091.35 | 2.85
3478 | Indiana | MADISON |  | 06 | 0900607 | This project will improve sections and extend the life of Madison County Road 100E with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/16/2009 | 10/30/2009 | 89002.34 | 1.08
3479 | Indiana | MADISON |  | 06 | 0900608 | This project will improve sections and extend the life of 8th St. in Madison County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/16/2009 | 10/30/2009 | 271010.78 | 4.33
3480 | Indiana | SHELBY |  | 05 | 0900609 | This project will improve sections and extend the life of Shelby County Road 400E on the east side of Shelbyville with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/26/2009 | 11/02/2009 | 744886.72 | 0.01
3481 | Indiana | PUTNAM |  | 08 | 0900610 | This project will replace and restore the pavement on Indiana Street in Greencastle. | Pavement Improvement | 09/01/2009 | 09/18/2009 | 11/15/2009 | 80137.74 | 0.54
3482 | Indiana | FOUNTAIN |  | 08 | 0900612 | This project will improve sections and extend the life of N Perry St in Fountain County with a pavement surface overlay | Pavement Improvement | 09/01/2009 | 09/29/2009 | 11/15/2009 | 260458.14 | 0.52
3483 | Indiana | HAMILTON |  | 05 | 0900613 | This is a Maintenance Resurfacing project, at From SR 32 to SR 47 in Washington & Adams Townships IN; to perform Pavement, Other work. | Pavement Improvement | 11/23/2009 |  | 05/28/2010 | 448756.77 | 6.07
3484 | Indiana | RUSH |  | 06 | 0900614 | This project will replace and restore the pavement on County Road 800E, from CR-100N to CR-1200N, in Rush County. | Pavement Improvement | 09/01/2009 | 11/16/2009 | 10/30/2009 | 111562.88 | 0.99
3485 | Indiana | RUSH |  | 06 | 0900615 | This project will replace and restore the pavement on County Road 800E, from CR-600N to CR-900N, in Rush County. | Pavement Improvement | 09/01/2009 | 11/16/2009 | 10/30/2009 | 254079.22 | 3
3486 | Indiana | HANCOCK |  | 05 | 0900616 | This project will replace and restore the pavement on County Road 1050E, from US-40 to SR-650N, in Hancock County. | Pavement Improvement | 09/01/2009 | 10/13/2009 | 10/30/2009 | 433578.85 | 5.69
3487 | Indiana | HANCOCK |  | 06 | 0900617 | This project will replace and restore the pavement on County Road 600E, from US-40 to SR-234, in Hancock County. | Pavement Improvement | 09/01/2009 | 10/13/2009 | 10/30/2009 | 565804.64 | 6.11
3488 | Indiana | LAWRENCE |  | 04 | 0900624 | This project will improve sections and extend the life of Main St/Hoosier Ave with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/19/2009 | 11/30/2009 | 258595.55 | 0.28
3489 | Indiana | SULLIVAN |  | 08 | 0900626 | This project will improve sections and extend the life of CR 925N/CR 450W/CR 1100 N with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/07/2009 | 11/30/2009 | 586794.18 | 8.54
3490 | Indiana | SULLIVAN |  | 08 | 0900628 | This project will improve sections and extend the life of Old US 41 in Sullivan County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/07/2009 | 11/30/2009 | 294187.65 | 4.2
3491 | Indiana | MADISON |  | 06 | 0900635 | This project will restore the pavement on Madison County Road 1100 N with a new surface course. | Pavement Improvement | 09/14/2009 | 09/22/2009 | 10/30/2009 | 215901.65 | 4
3492 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900637 | This is a Safety project, at Hausfledt Lane at CSX Railroad Crossing; to perform Railroad Protection work. | Safety/Traffic Management | 01/06/2010 |  | 05/13/2010 | 471428 | 0.04
3493 | Indiana | MADISON |  | 06 | 0900638 | This project will restore the pavement on Madison County Road 1100 N with a new surface course. | Pavement Improvement | 09/14/2009 | 09/22/2009 | 10/30/2009 | 414216.26 | 5.5
3494 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900639 | This project will improve the traffic signals on Market Street from State St to Vincennes Street. | Safety/Traffic Management | 02/01/2010 | 02/08/2010 | 05/14/2010 | 327809.26 | 1.3
3495 | Indiana | TIPTON |  | 05 | 0900642 | This project will improve sections and extend the life of Division Rd. from US 31 to SR 1 with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 10/30/2009 | 529938.85 | 4.96
3496 | Indiana | TIPTON |  | 05 | 0900643 | This project will improve sections and extend the life of South Ash St. from SR 28 to Railroad with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 10/30/2009 | 44947.05 | 1.008
3497 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900644 | This project will improve traffic signals from Spring Street to State Street in New Albany, Floyd county. | Safety/Traffic Management | 02/01/2010 | 02/08/2010 | 05/14/2010 | 277980.07 | 1.3
3498 | Indiana | HOWARD |  | 05 | 0900647 | This project will improve sections and extend the life of Howard County Road 1350 East from CR 200 North to CR 400 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 177353.25 | 2
3499 | Indiana | HOWARD |  | 05 | 0900648 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 1000 East to County Road 1200 East with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 110474.26 | 2
3500 | Indiana | CARROLL |  | 02 | 0900650 | This project will improve sections and extend the life of Road 300 W in Carroll County with a pavement surface overlay. | Pavement Improvement | 10/14/2009 | 04/02/2010 | 10/15/2009 | 135196.57 | 1.17
3501 | Indiana | CARROLL |  | 02 | 0900651 | This project will improve sections and extend the life of Bicycle Rd with a pavement surface overlay. | Pavement Improvement | 10/14/2009 | 04/02/2010 | 10/15/2009 | 430230.38 | 3.94
3502 | Indiana | CARROLL |  | 02 | 0900652 | This project will improve sections and extend the life of Road 100N in Carroll County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/20/2009 | 06/15/2010 | 12797.61 | 0.12
3503 | Indiana | CARROLL |  | 02 | 0900655 | This project will improve sections and extend the life of Road 700W in Carroll County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/20/2009 | 06/15/2010 | 314863.21 | 6.11
3504 | Indiana | CARROLL |  | 02 | 0900656 | This project will improve sections and extend the life of Meridian Rd in Carroll County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/20/2009 | 06/15/2010 | 418889.95 | 3.01
3505 | Indiana | CASS |  | 02 | 0900657 | This project will replace and restore the pavement on Loganspot Road, from Longtree to SR-1100E, in Cass County. | Pavement Improvement | 09/01/2009 | 09/18/2009 | 10/12/2009 | 641031.41 | 7.5
3506 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900660 | This is a Maintenance Resurfacing project, at Southeastern Avenue from Columbia to 175th St.; to perform Surface Treatment work. | Pavement Improvement | 01/06/2010 |  | 09/30/2010 | 668918.21 | 1.33
3507 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900661 | This is a Maintenance Resurfacing project, at 45th Avenue from Kennedy to Kleinman; to perform Surface Treatment work. | Pavement Improvement | 01/20/2010 |  | 09/30/2010 | 340503.85 | 1.23
3508 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900663 | This is a Maintenance Resurfacing project, at Main Street from Wood Ave to Chase St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 01/05/2010 | 06/01/2010 | 06/30/2010 | 356171.53 | 2.49
3509 | Indiana | MARSHALL |  | 02 | 0900671 | This project will improve sections and extend the life of 9A Road from city limits to SR 31 in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/06/2009 | 06/30/2010 | 98051.42 | 1.142
3510 | Indiana | MARSHALL |  | 02 | 0900672 | This project will improve sections and extend the life of Plymouth-Goshen Trail from city limits to Lilac Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 04/21/2010 | 07/02/2010 | 21436.96 | 0.02
3511 | Indiana | JASPER |  | 01 | 0900673 | This is a Maintenance Resurfacing project, at CR 700 S from 1200W to 3315' West of CR 900W; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 12/31/2009 | 04/14/2010 | 06/05/2010 | 242489.4 | 2.41
3512 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900674 | This is a Maintenance Resurfacing project, at Kennedy Avenue from Main Street to Junction Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 01/06/2010 |  | 08/15/2010 | 254248.74 | 1.47
3513 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900675 | This is a Maintenance Resurfacing project, at 77th Avenue from US 41 to Austin Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 01/06/2010 |  | 08/15/2010 | 164673.77 | 1.23
3514 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900676 | This is a Maintenance Resurfacing project, at Lincolnwood Avenue/Old Lincoln Highway from US 30 to 77th Ave.; to perform Surface Treatment work. | Pavement Improvement | 01/06/2010 |  | 08/15/2010 | 104863.39 | 0.8
3515 | Indiana | HOWARD |  | 05 | 0900681 | This project will improve sections and extend the life of Howard County 850 East from County Road 200 North to County Road 400 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 115921.11 | 2
3516 | Indiana | HOWARD |  | 05 | 0900682 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 700 West to County Road 710 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 7795.4 | 0.14
3517 | Indiana | HOWARD |  | 05 | 0900683 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 750 West to County Road 800 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 27403.93 | 0.5
3518 | Indiana | HOWARD |  | 05 | 0900684 | This project will improve sections and extend the life of Howard County Road 1150W from CR 400 North to CR 600 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 101305.36 | 2
3519 | Indiana | HOWARD |  | 05 | 0900685 | This project will improve sections and extend the life of Howard County Road 750W from SR 22 to County Road 200 North with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 66850.74 | 1
3520 | Indiana | HOWARD |  | 05 | 0900686 | This project will improve sections and extend the life of Howard County Road 750W with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 130543.23 | 2.2
3521 | Indiana | HOWARD |  | 05 | 0900687 | This project will improve sections and extend the life of Howard County Road 750 West from County Road 220 South to Russiaville town limits with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 78336.75 | 1.5
3522 | Indiana | HOWARD |  | 05,04 | 0900688 | This project will improve sections and extend the life of Howard County Road 600 South from County Road 800 West to County Road 870 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 36345.43 | 0.8
3523 | Indiana | HOWARD |  | 05 | 0900689 | This project will improve sections and extend the life of Howard County Road 220 South from County Road 750 West to County Road 766 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 8010.89 | 0.13
3524 | Indiana | HOWARD |  | 05 | 0900690 | This project will improve sections and extend the life of Howard County Road 750 West from Russioville Town limits to County Road 500 South with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 38789.21 | 0.7
3525 | Indiana | HOWARD |  | 05 | 0900691 | This project will improve sections and extend the life of Howard County Road 250 South from from County Road 600 West to County Road 750 West with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 89909.8 | 1.5
3526 | Indiana | CLAY |  | 08 | 0900692 | This project will replace and restore the pavement on Bowling Green Poland Road, from SR-46 to SR-42, in Clay County. | Pavement Improvement | 09/01/2009 | 09/30/2009 | 11/15/2009 | 632977.1 | 6.72
3527 | Indiana | WARREN |  | 08 | 0900693 | This project will replace and restore the pavement on Monroe Street, from Franklin Street to South 3rd Street, in Warren County. | Pavement Improvement | 09/01/2009 | 09/22/2009 | 11/15/2009 | 324468.42 | 1.17
3528 | Indiana | VIGO | TERRE HAUTE | 08 | 0900694 | This project will replace and restore the pavement on Cotton Drive from Singhurst Street to SR-159, in Vigo County. | Pavement Improvement | 09/02/2009 | 10/15/2009 | 11/15/2009 | 207440.79 | 0.75
3529 | Indiana | VIGO | TERRE HAUTE | 08 | 0900695 | This project will replace and restore the pavement on Rio Grande Avenue, from Baldwin Street to Twin Beach Street, in Vigo County. | Pavement Improvement | 09/02/2009 | 10/15/2009 | 11/15/2009 | 224772.74 | 2.355
3530 | Indiana | PUTNAM |  | 08 | 0900696 | This project will improve sections and extend the life of Walnut Road from the West Greencastle City Limits to West County Line Road in Putnam County with a pavement surface overlay. | Pavement Improvement | 09/03/2009 | 09/22/2009 | 11/15/2009 | 940215 | 8
3531 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900697 | This is a preventive maintenance resurfacing project, at CR17 from North of CR18 to South of Verdant road in elkhart county to extend the service life of the pavement. | Pavement Improvement | 12/16/2009 |  | 08/15/2010 | 192260.32 | 0.6
3532 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900698 | This is a Maintenance Resurfacing project, at CR 17 from 900' N of Verdant to SR 120; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 |  | 08/15/2010 | 636681.05 | 1.8
3533 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900699 | This is a Maintenance Resurfacing project, at CR 17 from CR 6 to CR 4; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 |  | 08/15/2010 | 257651.21 | 1
3534 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0900700 | This is a Maintenance Resurfacing project, at CR 45 from Fenmore Ave to CR 13; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 |  | 08/15/2010 | 150244.13 | 2.1
3535 | Indiana | VIGO | TERRE HAUTE | 08 | 0900701 | This project will replace and restore the pavement on Rosedale Road, from Rio Grande Avenue to Lambert Street, in Vigo County. | Pavement Improvement | 09/02/2009 | 10/15/2009 | 11/15/2009 | 357154.43 | 3.71
3536 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0900702 | This is a Facilities for Pedestrians and Bicycles project, at SR 3 from Water St. to Park St.; to perform Enhancement work. | Transportation Enhancements | 12/31/2009 | 03/08/2010 | 10/01/2010 | 634688.66 | 0.04
3537 | Indiana | VERMILLION |  | 08 | 0900704 | This project will replace and restore the pavement on Main Street, from 50' North of the RR tracks to North of the City limits, in Vermillion County. | Pavement Improvement | 09/11/2009 | 10/05/2009 | 11/15/2009 | 293482.42 | 0.568
3538 | Indiana | POSEY |  | 08 | 0900709 | This is a Maintenance Resurfacing project, at SR 62 to Middle Mt Vernon Rd.; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 03/30/2010 | 08/31/2010 | 203274.03 | 2.1
3539 | Indiana | POSEY |  | 08 | 0900710 | This is a Maintenance Resurfacing project, at Creamery Rd to SR 66; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 03/30/2010 | 08/31/2010 | 451941.97 | 4.9
3540 | Indiana | POSEY |  | 08 | 0900711 | This project will improve sections and extend the life of Springfield Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/30/2009 | 735695.82 | 9.3
3541 | Indiana | STARKE |  | 02 | 0900712 | This project will improve sections and extend the life of Road 210 in Starke County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/01/2009 | 11/07/2009 | 102677.15 | 1.3
3542 | Indiana | STARKE |  | 02 | 0900713 | This project will improve sections and extend the life of Road 625E in Starke County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/01/2009 | 11/07/2009 | 90035.31 | 1.2
3543 | Indiana | STARKE |  | 02 | 0900714 | This project will improve sections and extend the life of Toto Rd in Starke County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/01/2009 | 11/07/2009 | 603557.12 | 8.3
3544 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900716 | This is a Maintenance Resurfacing project, at 101st(Joliet St.) from US 41 to Parish Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 02/22/2010 |  | 09/30/2010 | 255425.56 | 1.15
3545 | Indiana | NOBLE |  | 03 | 0900717 | This project will improve sections and extend the life of County Road 600West from US 6 to county road 1200 north in Noble County with a pavement surface overlay. | Pavement Improvement | 09/10/2009 | 09/16/2009 | 09/30/2009 | 138858.13 | 4.8
3546 | Indiana | NOBLE |  | 03 | 0900718 | This project will improve sections and extend the life of Baseline Road from SR 3 to county road 1200 East in Noble County with a pavement surface overlay. | Pavement Improvement | 09/10/2009 | 09/16/2009 | 09/30/2009 | 35086.24 | 1.5
3547 | Indiana | SHELBY |  | 06 | 0900720 | This project will improve the surface and rebuild sections of the bridge on County Road 900 South over Big Blue River in Shelby County. | Bridge Improvement | 09/15/2009 | 04/09/2010 | 07/30/2010 | 60502.5 | 0.01
3548 | Indiana | BOONE |  | 04 | 0900721 | This project will improve sections and extend the life of Elizaville Road from the Lebanon City Limits to County Road 500 East in Boone County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/05/2009 | 11/15/2009 | 536583.48 | 6.5
3549 | Indiana | BOONE |  | 05,04 | 0900722 | This project will improve sections and extend the life of County Road 1200East from County Road 300 South to SR 32 in Boone County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/05/2009 | 11/15/2009 | 79749.5 | 3
3550 | Indiana | BOONE |  | 04 | 0900723 | This project will improve sections and extend the life of County Road 400East from County Road 300 South to SR 32 in Boone County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/05/2009 | 11/15/2009 | 254577.56 | 2.9
3551 | Indiana | BOONE |  | 04 | 0900724 | This project will improve sections and extend the life of County Road 25West from the Hendricks County Line to County Road 250 South in Boone County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/05/2009 | 11/15/2009 | 425591.25 | 5.6
3552 | Indiana | KNOX |  | 08 | 0900727 | This project will improve sections and extend the life of Bicknell-Oaktown Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/24/2009 | 11/30/2009 | 70107.97 | 1.28
3553 | Indiana | KNOX |  | 08 | 0900728 | This project will improve sections and extend the life of Hart Street Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/24/2009 | 11/30/2009 | 365159.72 | 5.37
3554 | Indiana | WARREN |  | 08 | 0900735 | This project will improve sections and extend the life of River Rd in Warren County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/15/2009 | 193054.36 | 0.11
3555 | Indiana | WARREN |  | 08 | 0900736 | This project will improve sections and extend the life of Independence Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/15/2009 | 532282.63 | 5.53
3556 | Indiana | WARREN |  | 08 | 0900737 | This project will improve sections and extend the life of Rd 300N in Warren County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/15/2009 | 1341777.4 | 13.43
3557 | Indiana | NOBLE |  | 03 | 0900738 | This project will improve sections and extend the life of Angling Road from Northport Road to Kendallville City Limits in Noble County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/03/2009 | 10/16/2009 | 260092.09 | 3
3558 | Indiana | CLINTON |  | 04 | 0900739 | This is a Maintenance Resurfacing project, at Old SR 28 to Mulberry City limits; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/25/2010 | 06/30/2010 | 578218.02 | 5.8
3559 | Indiana | NOBLE |  | 03 | 0900740 | This project will improve sections and extend the life of Albion Road from US 33 to the Albion City Line in Noble County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/03/2009 | 10/16/2009 | 549995.39 | 7
3560 | Indiana | SHELBY |  | 06 | 0900741 | This project will improve the surface and rebuild sections of the bridge on County Road 900 South over Big Blue River in Shelby County. | Bridge Improvement | 09/15/2009 | 04/09/2010 | 07/30/2010 | 42424.5 | 0.01
3561 | Indiana | CLINTON |  | 04 | 0900742 | This is a Maintenance Resurfacing project, at SR 38 to Kelly Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/25/2010 | 06/30/2010 | 274643.69 | 5
3562 | Indiana | CLINTON |  | 04 | 0900743 | This is a Maintenance Resurfacing project, at CR 100 N to CR 600 N.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/25/2010 | 06/30/2010 | 415432.94 | 3.5
3563 | Indiana | LA PORTE |  | 02 | 0900745 | This is a Maintenance Resurfacing project, at CR 500 W from SR 2 to Johnson Rd.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 01/08/2010 | 03/30/2010 | 05/15/2010 | 481582.56 | 3.7
3564 | Indiana | JACKSON |  | 09 | 0900771 | This is a Maintenance Resurfacing project, at CR 150 N/100 N/50N from SR 11 to US 50; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 10/22/2009 | 11/15/2009 | 322891.51 | 6.65
3565 | Indiana | JACKSON |  | 09 | 0900772 | This project will improve the pavement from county road 300 north to county road 100 west. | Pavement Improvement | 02/20/2010 | 03/25/2010 | 07/01/2010 | 172031.99 | 2.99
3566 | Indiana | JACKSON |  | 09 | 0900775 | This is a Maintenance Resurfacing project, at 300 N from CR 800 E to CR 850 E; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 03/25/2010 | 06/15/2010 | 45111.96 | 0.5
3567 | Indiana | POSEY |  | 08 | 0900778 | This project will improve sections and extend the life of Lower New Harmony Rd with a pavement surface overlay. | Other | 09/01/2009 | 09/25/2009 | 11/30/2009 | 24773.9 | 1
3568 | Indiana | POSEY |  | 08 | 0900779 | This project will improve sections and extend the life of O'Donnel Rd/Brittle Bank Rd in Posey County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/30/2009 | 108116.7 | 0.4
3569 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900780 | This is a Maintenance Resurfacing project, at Co Road 30 - Basher Road from Reliance Rd to US 33.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/30/2009 |  | 08/06/2010 | 187317.05 | 1.48
3570 | Indiana | POSEY |  | 08 | 0900781 | This project will improve sections and extend the life of Main street (Old SR 69) with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/25/2009 | 11/30/2009 | 10641.65 | 1.2
3571 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900782 | This is a preventive maintenance resurfacing project, on 8th Street from College Avenue to Lincoln Ave in Goshen to extend the pavement surface life. | Pavement Improvement | 11/30/2009 |  | 08/06/2010 | 229199.95 | 1.41
3572 | Indiana | GIBSON |  | 08 | 0900783 | This project will improve sections and extend the life of Embree St in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 09/30/2009 | 142835.79 | 0.689
3573 | Indiana | GIBSON |  | 08 | 0900784 | This project will improve sections and extend the life of Makemson Ave in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 09/30/2009 | 15214.16 | 0.133
3574 | Indiana | GIBSON |  | 08 | 0900785 | This project will improve sections and extend the life of Seminary St in Gibson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/15/2009 | 09/30/2009 | 34381.58 | 0.294
3575 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0900786 | This is a Maintenance Resurfacing project, at Lincoln Avenue from Indiana Avenue to Chicago Ave.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 08/06/2010 | 94565.25 | 0.229
3576 | Indiana | GREENE |  | 08 | 0900794 | This is a Maintenance Resurfacing project, at 5th Street to 4th St.; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 06/01/2010 | 08/31/2010 | 57510.94 | 0.5
3577 | Indiana | JACKSON |  | 09 | 0900796 | This project will improve the pavement on county road 500 south from SR 39 to 830 East. | Pavement Improvement | 02/20/2010 | 03/25/2010 | 07/01/2010 | 228007.19 | 3.81
3578 | Indiana | RUSH |  | 06 | 0900797 | This project will improve sections and extend the life of County Road 715West from SR 44 to BAse Road in Rush County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 10/14/2009 | 11/14/2009 | 171299.93 | 2.36
3579 | Indiana | JACKSON |  | 09 | 0900798 | This project will improve the pavement 0n 600 south from 830 east to 1025 east. | Pavement Improvement | 02/20/2010 | 03/25/2010 | 07/01/2010 | 98526.76 | 1.59
3580 | Indiana | FAYETTE |  | 06 | 0900799 | This project will improve sections and extend the life of Veterans Memorial Highway from SR 121 to SR 1 in Fayette County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 10/14/2009 | 11/13/2009 | 96258.85 | 0.95
3581 | Indiana | KOSCIUSKO |  | 03 | 0900802 | This project will improve sections and extend the life of old US 30 from the west county line to 350W in Kosciusko county with a preventive maintenance asphalt overlay. | Pavement Improvement | 09/14/2009 | 10/07/2009 | 07/16/2010 | 724922.92 | 8
3582 | Indiana | KOSCIUSKO |  | 03 | 0900803 | This project will improve sections and extend the life of Old US 30 from current US 30 to the east County line road in Kosciusko county | Pavement Improvement | 09/14/2009 | 10/07/2009 | 07/16/2010 | 768649.19 | 8
3583 | Indiana | JACKSON |  | 09 | 0900806 | This project will improve the pavement on county road 850 east from 410 north to 200 north. | Pavement Improvement | 02/20/2010 | 03/25/2010 | 07/01/2010 | 135130.33 | 2.22
3584 | Indiana | JACKSON |  | 09 | 0900807 | This is a Maintenance Resurfacing project, at CR 200 N from US 50 to Bridge 91 over White River; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 03/25/2010 | 06/15/2010 | 55956.1 | 0.87
3585 | Indiana | JENNINGS |  | 09 | 0900809 | This project will improve the pavement on county road 150 south from SR 7 to county road 250 east. | Pavement Improvement | 02/22/2010 | 04/29/2010 | 07/01/2010 | 67492.94 | 0.58
3586 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900810 | This is a Maintenance Resurfacing project, at Roosevelt Road from Vale Park Road to LaPorte Ave.; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/01/2010 | 07/01/2010 | 616651.4 | 1.77
3587 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900811 | This is a Maintenance Resurfacing project, at Calumet Avenue from GT&W RR (CN RR) to Vale Park Rd.; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/01/2010 | 07/01/2010 | 324633.03 | 1.15
3588 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900812 | This is a Maintenance Resurfacing project, at Joliet Road from SR 130 to Hayes Leonard Road (SR 150W); to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/01/2010 | 07/01/2010 | 203117.59 | 1.15
3589 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900813 | This is a Safety project, at Valparaiso High School - Campbell St. at Vale Park Rd. & John Glenn Dr. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 03/05/2010 | 05/12/2010 | 07/01/2010 | 21309.27 | 0.01
3590 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900814 | This is a Safety project, at Ben Franklin Middle School - Campbell St. at Ridgeland Ave N & Haas St. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 03/05/2010 | 05/12/2010 | 07/01/2010 | 7046.65 | 0.01
3591 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900815 | This is a Safety project, at Northview Elementary School-Campbell St at Roane Ln N & Roseland Terrace S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 03/05/2010 | 05/12/2010 | 07/01/2010 | 12526.98 | 0.01
3592 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900816 | This is a Safety project, at Parkview Elementary School-Roosevelt Rd. at Oak St N & Chicago St. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 03/05/2010 | 05/12/2010 | 07/01/2010 | 9563.13 | 0.01
3593 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900817 | This is a Safety project, at Thomas Jefferson Middle School-Roosevelt Rd. at Glendale Blv. N & Illinois St. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 03/05/2010 | 05/12/2010 | 07/01/2010 | 9563.13 | 0.01
3594 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900818 | This is a Safety project, at Central Elementary School - Morgan Blvd at Erie St.; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 03/05/2010 | 05/12/2010 | 07/01/2010 | 8947.99 | 0.01
3595 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900819 | This is a Scenic or Historic Highway Programs project, at Indiana Ave. between Lafayette St. & Washington St.; Lafayette-SR 130 to Indiana, to perform Enhancement work. | Transportation Enhancements | 04/06/2010 | 04/23/2010 | 06/30/2010 | 258791.1 | 0.01
3596 | Indiana | JENNINGS |  | 09 | 0900823 | This is a Maintenance Resurfacing project, at CR 265 W/300 W from CR 70 S to US 50; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 |  | 06/01/2010 | 63535.97 | 0.87
3597 | Indiana | JENNINGS |  | 09 | 0900824 | This is a Maintenance Resurfacing project, at CR 300 N from SR 3 to CR 600 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 |  | 06/01/2010 | 235630.92 | 4.48
3598 | Indiana | DUBOIS |  | 09 | 0900825 | This project will improve sections and extend the life of Jasper-Dubois Rd with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 11/30/2009 | 748081.44 | 6.94
3599 | Indiana | DUBOIS |  | 09 | 0900826 | This project will improve sections and extend the life of Rd 1100S in Dubois County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 11/30/2009 | 439834.62 | 5.33
3600 | Indiana | JENNINGS |  | 09 | 0900833 | This project will extend the life of the pavement on CR 350 N from CR 75 W to 90 E in Jenning county by doing asphalt resurface as Preventive Maintenance work. | Pavement Improvement | 02/22/2010 |  | 06/01/2010 | 96059.05 | 1.65
3601 | Indiana | JENNINGS |  | 09 | 0900834 | This project will improve the pavement on CR 500 North from SR 3 to Base Road. | Pavement Improvement | 02/22/2010 | 04/29/2010 | 07/01/2010 | 153070.05 | 1.5
3602 | Indiana | JENNINGS |  | 09 | 0900835 | This project will improve the pavement on CR 550 East/ 600 East from county road 150 south to US 50. | Pavement Improvement | 02/22/2010 | 04/29/2010 | 07/01/2010 | 282003.6 | 5.23
3603 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900840 | This is a Maintenance Resurfacing project, at Oak Hill Road from US 20 to SR 49; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 04/07/2010 | 05/28/2010 | 201906.9 | 1.1
3604 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900841 | This is a Maintenance Resurfacing project, at Waverly Road from I-94 bridge abutment to US 12; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 04/08/2010 | 05/28/2010 | 203620.12 | 1.1
3605 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900842 | This is a Maintenance Resurfacing project, at Meridian Road, from US 6 to CR 1050 N; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/01/2010 | 06/01/2010 | 265346.52 | 2.5
3606 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900843 | This is a Maintenance Resurfacing project, at CR 700N from Swanson road to Willowcreek Rd.; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/01/2010 | 06/01/2010 | 97424.24 | 0.74
3607 | Indiana | PORTER |  | 01 | 0900844 | This is a Maintenance Resurfacing project, at North Calumet Road, from US 6 to Chesterton Town Limits; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 03/22/2010 | 07/01/2010 | 275142.94 | 1.23
3608 | Indiana | PORTER |  | 01 | 0900846 | This is a Maintenance Resurfacing project, at Division Road from SR 49 to 0.5 mi E of SR 49; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 | 05/25/2010 | 06/30/2010 | 107519.21 | 0.5
3609 | Indiana | PORTER |  | 01 | 0900848 | This is a Maintenance Resurfacing project, at CR 250W from Kankakee River to SR 8; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 | 05/25/2010 | 07/01/2010 | 286233.96 | 2.52
3610 | Indiana | PORTER |  | 01 | 0900849 | This is a Maintenance Resurfacing project, at Division Road from CR 400E to CR 575 E; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 | 05/25/2010 | 07/02/2010 | 189763.8 | 1.76
3611 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900851 | This is a Maintenance Resurfacing project, at Samuelson Road from 750 ft. South of Indiana Toll Road to Portage Ave.; to perform Surface Treatment work. | Pavement Improvement | 01/15/2010 | 04/13/2010 | 06/01/2010 | 162562.74 | 1.05
3612 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900852 | This is a Maintenance Resurfacing project, at Central Avenue from Bridge over Willowcreek to Elm St.; to perform Surface Treatment work. | Pavement Improvement | 01/15/2010 | 04/13/2010 | 06/01/2010 | 156007.61 | 0.83
3613 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900853 | This is a Maintenance Resurfacing project, at Swanson Road from CR 700N to US 6; to perform Surface Treatment work. | Pavement Improvement | 01/15/2010 | 04/13/2010 | 06/01/2010 | 221096.56 | 0.94
3614 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900855 | This is a Landscaping project, at Intersection of Willowcreek Rd & Country Side Pk Entrance on US 6 - Landscaping; to perform Landscaping work. | Transportation Enhancements | 01/15/2010 | 04/05/2010 | 05/15/2010 | 85522.5 | 0.01
3615 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900856 | This is a Maintenance Resurfacing project, at Fir Road from McKinley Avenue to Spur line of Railroad; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 |  | 09/30/2010 | 64603.59 | 0.85
3616 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900857 | This is a Maintenance Resurfacing project, at McKinley Avenue (US 20) from Division Street to Home St.; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 |  | 09/30/2010 | 304493.53 | 1.29
3617 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900858 | This is a Safety project, at SR 933 - City Wide Traffic Signal Modernization; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 12/31/2009 | 02/01/2010 | 09/30/2010 | 312367.16 | 0.01
3618 | Indiana | LAKE |  | 01 | 0900860 | This is a Safety project, at Various roadways within the town of Winfield; to perform Signing work. | Safety/Traffic Management | 02/22/2010 | 04/13/2010 | 04/30/2010 | 37189.59 | 0.01
3619 | Indiana | LAKE |  | 01 | 0900862 | This is a Maintenance Resurfacing project, at Randolph Street from 129th Avenue to 123rd Ave.; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 |  | 07/31/2010 | 98462.18 | 0.88
3620 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900864 | This is a Maintenance Resurfacing project, at Twyckenham Drive from Rockne Drive to South Bend Avenue (SR 23); to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 10/21/2009 | 04/05/2010 | 07/15/2010 | 174928.66 | 0.706
3621 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900865 | This is a Maintenance Resurfacing project, at Western Avenue from Walnut Street to Chapin St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 08/30/2010 | 238542.75 | 0.4
3622 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900866 | This is a Maintenance Resurfacing project, at McKinley Avenue from 500ft East of Ironwood Drive to Preston Dr.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 10/21/2009 | 04/05/2010 | 07/15/2010 | 145765.73 | 0.638
3623 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900867 | This is a Maintenance Resurfacing project, at Western Avenue from Lombardy Drive to Albert Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 10/21/2009 | 04/05/2010 | 07/15/2010 | 114693.34 | 0.278
3624 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900868 | This is a Maintenance Resurfacing project, at Edison Road from Ironwood Drive to Hickory Rd.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 08/30/2010 | 229667.43 | 0.952
3625 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900869 | This is a Maintenance Resurfacing project, at Ireland Road from East of Miami Street to Ironwood Dr.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 10/21/2009 | 04/05/2010 | 07/15/2010 | 222483.43 | 0.866
3626 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900870 | This is a Maintenance Resurfacing project, at Portage Avenue from 370' N of Cleveland Road to Appaloosa Ln.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 10/21/2009 | 04/05/2010 | 07/15/2010 | 86365.36 | 0.489
3627 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900871 | This is a Maintenance Resurfacing project, at Ireland Road from St. Joseph Street to High St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 08/30/2010 | 128937.28 | 0.492
3628 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900872 | This is a Maintenance Resurfacing project, at Portage Avenue from Elwood Avenue to Lathrop St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 08/30/2010 | 241847.6 | 1.05
3629 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900873 | This is a Maintenance Resurfacing project, at Lincolnway W from Chapin Street to Olive St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 08/30/2010 | 391219.1 | 1.356
3630 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900874 | This is a Maintenance Resurfacing project, at Main Street from Chippewa Street to Sample St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 10/21/2009 | 04/05/2010 | 07/15/2010 | 414470.8 | 1.991
3631 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900876 | This is a Safety project, at Sample Street and Mayflower Road Intersection; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 02/22/2010 |  | 06/15/2010 | 32073.75 | 0.01
3632 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900877 | This is a Safety project, at Angela Avenue and North Shore Drive Intersection; to perform Traffic Signal Maintenance work. | Safety/Traffic Management | 02/22/2010 |  | 06/15/2010 | 28890 | 0.01
3633 | Indiana | JENNINGS |  | 09 | 0900885 | This is a Maintenance Resurfacing project, at CR 800 W from 825 S to SR 250; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 |  | 06/01/2010 | 88976.43 | 1.47
3634 | Indiana | JENNINGS |  | 09 | 0900886 | This is a Maintenance Resurfacing project, at CR 825 S from CR 800 W to CR 900 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 |  | 06/01/2010 | 96791.11 | 1.13
3635 | Indiana | JENNINGS |  | 09 | 0900889 | This project will improve the pavement on County Road 90 west/95 west from county road 115 to Base Road. | Pavement Improvement | 02/22/2010 | 04/29/2010 | 07/01/2010 | 94768.93 | 0.95
3636 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0900890 | This is a Maintenance Resurfacing project, at County Road 10 - John Weaver Parkway from CR 10 to CR 6; to perform Resurface over Asphalt Pavement work. | Pavement Improvement | 01/21/2010 | 04/27/2010 | 08/31/2010 | 427674.32 | 2.25
3637 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0900891 | This is a Maintenance Resurfacing project, at Beardsley Ave from Nappanee St to 100' W of Beech St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/21/2010 | 04/27/2010 | 08/31/2010 | 51041.18 | 1.19
3638 | Indiana | OHIO |  | 09 | 0900897 | This is a Maintenance Resurfacing project, at Cass Union Rd from Aberdeen Rd/SR 56 to SR 262; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/05/2010 | 06/30/2010 | 396132.6 | 6.6
3639 | Indiana | OHIO |  | 09 | 0900898 | This is a Maintenance Resurfacing project, at Hartford pike from Woods Ridge Road to Nelson Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/08/2010 | 06/30/2010 | 176815.7 | 1.7
3640 | Indiana | OHIO |  | 09 | 0900899 | This is a Maintenance Resurfacing project, at Nelson Rd from Hartford Pike to Rising Sun Limits; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/08/2010 | 06/30/2010 | 550595.47 | 3.7
3641 | Indiana | MORGAN |  | 04 | 0900900 | This project will improve sections and extend the life of Centenary Rd. from Henderson Ford Road to 1 mile South of SR 144 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 277355.96 | 3.4
3642 | Indiana | MORGAN |  | 04 | 0900901 | This project will improve sections and extend the life of old SR 37 from Martinsville City Limits to SR 37 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 111468.8 | 1.7
3643 | Indiana | MORGAN |  | 04 | 0900902 | This project will improve sections and extend the life of Paragon Rd. from SR 67 to SR 37 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 286593.27 | 5.7
3644 | Indiana | WELLS |  | 06 | 0900904 | This is a Maintenance Resurfacing project, at Lancaster St from Adams St to Bond St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 11/11/2009 | 06/12/2010 | 62063.86 | 1
3645 | Indiana | WELLS |  | 06 | 0900905 | This is a Maintenance Resurfacing project, at Western Ave from Decker Dr.; to Midway St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 11/11/2009 | 06/12/2010 | 40637.19 | 0.4
3646 | Indiana | WELLS |  | 06 | 0900906 | This is a Maintenance Resurfacing project, at Midway St from Western Ave.; to W Washington St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 11/11/2009 | 06/12/2010 | 116576.12 | 0.25
3647 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900911 | This is a project, at Joliet Street (93rd Avenue) at US 41; to perform Storm Sewer Repair Or Replacement work. | Other | 03/04/2010 | 05/26/2010 | 07/31/2010 | 378584.97 | 0.01
3648 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900915 | This is a Safety project, at SR 933 - Various locations City wide; to perform Sign Modernization (Series Of Units) work. | Safety/Traffic Management | 12/31/2009 |  | 09/30/2010 | 68709.01 | 0.01
3649 | Indiana | MORGAN |  | 04 | 0900916 | This project will improve sections and extend the life of Rueben Dr. from Old SR 37 to SR 37 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 33596.3 | 0.5
3650 | Indiana | MORGAN |  | 04 | 0900917 | This project will improve sections and extend the life of Rob Hill Rd fROM SR 39 TO SR 67 with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 244217.24 | 3.4
3651 | Indiana | MORGAN |  | 04 | 0900918 | This project will improve sections and extend the life of Blue Bluff Rd. from Centerton Rd. to Bridge with a pavement surface overlay. | Pavement Improvement | 11/23/2009 |  | 08/30/2010 | 92905.41 | 1.2
3652 | Indiana | SCOTT |  | 09 | 0900923 | This is a Maintenance Resurfacing project, at Third St. from Cherry St. to Montgomery St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 02/24/2010 | 04/16/2010 | 07/25/2010 | 65948.04 | 0.562
3653 | Indiana | SCOTT |  | 09 | 0900929 | This is a Maintenance Resurfacing project, at Montgomery St from Main St to Third St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 02/24/2010 | 04/16/2010 | 07/25/2010 | 80048.13 | 0.18
3654 | Indiana | JENNINGS |  | 09 | 0900930 | This project will improve the pavement on county road 500 east from county road 560 north to the county line. | Pavement Improvement | 02/22/2010 | 04/29/2010 | 07/01/2010 | 344662.67 | 6.14
3655 | Indiana | JENNINGS |  | 09 | 0900931 | This project will improve the pavement on Base Road/ County Road 20 West near North Vernon. | Pavement Improvement | 02/22/2010 | 04/29/2010 | 07/01/2010 | 162550.61 | 3.09
3656 | Indiana | JENNINGS |  | 09 | 0900932 | This is a Maintenance Resurfacing project, at CR-115S from CR-75W to Vernon; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 |  | 06/01/2010 | 64914.15 | 0.01
3657 | Indiana | JENNINGS |  | 09 | 0900935 | This project will improve sections and extend the life of Greensburg Street from US 50 to Woodlaen Drive in Jennings County with a pavement surface overlay. | Pavement Improvement | 11/23/2009 | 03/08/2010 | 07/15/2010 | 51747.6 | 0.44
3658 | Indiana | FOUNTAIN |  | 04 | 0900937 | This is a Maintenance Resurfacing project, at US 41 to SR 341; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 04/20/2010 | 07/15/2010 | 485757.43 | 3
3659 | Indiana | FOUNTAIN |  | 04 | 0900938 | This is a Maintenance Resurfacing project ,at SR 341 to Fountain/Montgomery County Line; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 04/20/2010 | 07/15/2010 | 283668.99 | 5
3660 | Indiana | FOUNTAIN |  | 08 | 0900939 | This is a Maintenance Resurfacing project, at Covington City Limits to US 41; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 04/20/2010 | 07/15/2010 | 954086.16 | 7.8
3661 | Indiana | SCOTT |  | 09 | 0900940 | This is a Maintenance Resurfacing project, at Main St from Lake Rd to Montgomery St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 02/24/2010 | 04/16/2010 | 07/25/2010 | 175719.49 | 1.5
3662 | Indiana | JEFFERSON |  | 09 | 0900941 | This project will improve sections and extend the life of Michigan Road from West Street to Green Road in Jefferson County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/17/2009 | 11/15/2009 | 164209.29 | 1.89
3663 | Indiana | CASS |  | 02 | 0900944 | This project will improve the traffic signs in the town of Galveston in Cass County. | Safety/Traffic Management | 09/15/2009 | 10/26/2009 | 11/30/2009 | 41888.73 | 0.01
3664 | Indiana | CASS |  | 02 | 0900945 | This project will improve the traffic signs in the town of Royal Center in Cass County. | Safety/Traffic Management | 09/15/2009 | 10/26/2009 | 11/30/2009 | 5221.19 | 0.01
3665 | Indiana | CASS |  | 02 | 0900946 | This project will improve the traffic signs in the town of Walton in Cass County. | Safety/Traffic Management | 09/15/2009 | 10/26/2009 | 11/30/2009 | 10075.69 | 0.01
3666 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900948 | This project will improve sections and extend the life of Patterson Rd from Watkins St to Kenilworth Rd with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 74686.15 | 0.7
3667 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900949 | This project will improve sections and extend the life of Beech Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 79231.77 | 0.75
3668 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900950 | This project will improve sections and extend the life of Timothy Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 53897.15 | 0.5
3669 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900952 | This project will improve sections and extend the life of Tamarach Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 396092.45 | 3.6
3670 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900953 | This project will improve sections and extend the life of Kern Rd in St Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 170869.44 | 1.9
3671 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900954 | This project will improve sections and extend the life of Oak Rd from New Rd to Roosevelt Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 195944.75 | 2
3672 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900955 | This project will improve sections and extend the life of Walkerton Trail from 0.01 MI S of Georgia St to 0.1 MI S of SR 23 with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 95534.15 | 0.8
3673 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900956 | This project will improve sections and extend the life of Main St in Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 30644.32 | 0.12
3674 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900957 | This project will improve sections and extend the life of Washington St in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 24899.42 | 0.1
3675 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900958 | This project will improve sections and extend the life of Patterson Rd from 0.04 MI E of Beeckler Court to Watkins St with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 21998.43 | 0.09
3676 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900959 | This project will improve sections and extend the life of Walkerton Trail in St. Joseph county from Spruce Rd to 0.1 MI S of Georgia St with a preventive maintenance pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 132570.87 | 0.05
3677 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900960 | This project will improve sections and extend the life of Mayflower Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 26719.91 | 0.3
3678 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900961 | This project will improve sections and extend the life of Sumption Trail in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 46175.6 | 0.8
3679 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900962 | This project will improve sections and extend the life of Oak Rd from Roosevelt Rd to Kern Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 56716.64 | 1
3680 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900963 | This project will improve sections and extend the life of Beech Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 10/01/2009 | 06/30/2010 | 149295.99 | 3.2
3681 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900964 | This project will improve traffic signs in Walkerton in St Joseph County. | Safety/Traffic Management | 09/15/2009 | 03/15/2010 | 06/30/2010 | 50414.87 | 0.01
3682 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900965 | This project will improve the traffic signs in North Liberty in St Joseph County. | Safety/Traffic Management | 09/15/2009 | 03/15/2010 | 06/30/2010 | 38045.14 | 0.01
3683 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900966 | This project will improve the signs in New Carlisle in St Joseph County. | Safety/Traffic Management | 09/15/2009 | 03/15/2010 | 06/30/2010 | 48885.14 | 0.01
3684 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900967 | This project will improve the traffic signs in Lakeville in St Joseph County. | Safety/Traffic Management | 09/15/2009 | 03/15/2010 | 06/30/2010 | 35355.85 | 0.01
3685 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900968 | This project will improve the traffic signs in St Joseph County. | Safety/Traffic Management | 09/15/2009 | 03/15/2010 | 06/30/2010 | 148249.03 | 0.01
3686 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900969 | This is a Maintenance Resurfacing project, at Morse Street from 149th to Lowell Corp Limits; to perform Surface Treatment work. | Pavement Improvement | 01/11/2010 | 05/18/2010 | 06/30/2010 | 536728.84 | 3.36
3687 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900970 | This is a Maintenance Resurfacing project, at Cedar Lake Road form 121st to 133rd; to perform Surface Treatment work. | Pavement Improvement | 01/12/2010 | 04/23/2010 | 06/30/2010 | 262314.46 | 1.64
3688 | Indiana | PIKE |  | 08 | 0900982 | This is a Maintenance Resurfacing project, at E Old SR 64 - SR 257 to CR 1100E; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 05/04/2010 | 08/31/2010 | 250364.52 | 3.7
3689 | Indiana | PIKE |  | 08 | 0900983 | This is a Maintenance Resurfacing project, at CR 500E to SR 257; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 05/04/2010 | 08/31/2010 | 105812.74 | 1.56
3690 | Indiana | PERRY |  | 09 | 0900987 | This is a trail construction project for pedestrians and bicycles at Tell City Riverfront, 1,800' south of Washington St to 3,400' north of the plaza in Tell City in Perry county using enhancement fun | Transportation Enhancements | 12/18/2009 | 05/19/2010 | 08/31/2010 | 434981.44 | 1.01
3691 | Indiana | DE KALB |  | 03 | 0900988 | This project will improve sections and extend the life of Dekalb County Road 48 with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/06/2009 | 10/31/2010 | 231953.6 | 1.6
3692 | Indiana | SCOTT |  | 09 | 0900991 | This is a Maintenance Resurfacing project, at Elm St from Lake Rd to SR 56; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 02/24/2010 | 04/16/2010 | 07/25/2010 | 104350.1 | 1
3693 | Indiana | DE KALB |  | 03 | 0900993 | This project will improve sections and extend the life of Wayne Street from Cedar Street to Walnut Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 09/30/2009 | 146655.49 | 0.77
3694 | Indiana | MARION | INDIANAPOLIS | 07 | 0900994 | This is a Maintenance Resurfacing project, at Arlington Ave. from 38th St. to 56th St.; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 | 03/01/2010 | 06/30/2010 | 1643950 | 2
3695 | Indiana | SCOTT |  | 09 | 0900995 | This is a Maintenance Resurfacing project, at Beechwood and Allen St. from SR 56 to US 31; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 02/24/2010 | 04/16/2010 | 07/25/2010 | 36599.39 | 0.46
3696 | Indiana | DE KALB |  | 03 | 0900996 | This project will improve sections and extend the life of N. Commerce Drive in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 09/30/2009 | 38650.93 | 0.21
3697 | Indiana | DE KALB |  | 03 | 0900997 | This project will improve sections and extend the life of Center Street from US 6 to Rope Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 09/30/2009 | 52189.49 | 0.48
3698 | Indiana | DE KALB |  | 03 | 0900998 | This project will improve sections and extend the life of Rope Street from Center Street to SR 427 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 09/30/2009 | 74286.14 | 0.47
3699 | Indiana | DE KALB |  | 03 | 0900999 | This project will improve sections and extend the life of Walnut Street from Albright Street to SR 39 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 09/30/2009 | 44769.41 | 0.25
3700 | Indiana | DE KALB |  | 03 | 0901000 | This project will improve sections and extend the life of Walnut Street from Center Street to Wayne Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 09/04/2009 | 09/30/2009 | 46943.69 | 0.25
3701 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901004 | This is a Maintenance Resurfacing project, at Colfax Street from Belshaw Road to 231st Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 12/16/2009 | 04/20/2010 | 06/04/2010 | 608420.42 | 4.9
3702 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901005 | This is a Maintenance Resurfacing project, at 231st Avenue from Monon Road to Colfax St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 12/16/2009 | 04/20/2010 | 06/04/2010 | 300548.26 | 2.85
3703 | Indiana | SCOTT |  | 09 | 0901021 | This is a Maintenance Resurfacing project, at Cherry St. from US 31 to Third St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 02/24/2010 | 04/16/2010 | 07/25/2010 | 40358.15 | 0.61
3704 | Indiana | SCOTT |  | 09 | 0901022 | This is a Maintenance Resurfacing project, at Wardell St from US 31 to Third St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 02/24/2010 | 04/16/2010 | 07/25/2010 | 79478.37 | 0.61
3705 | Indiana | HOWARD |  | 05 | 0901023 | This project will improve sections and extend the life of County Road 400North from County Road 850 East to County Road 900 East in Howard County with a pavement surface overlay. | Transportation Enhancements | 09/14/2009 | 09/24/2009 | 11/13/2009 | 42341.78 | 0.5
3706 | Indiana | PERRY |  | 09 | 0901024 | This is a Maintenance Resurfacing project, at Gerald Rd (CR 10) to SR 70; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 04/14/2010 | 08/31/2010 | 376584 | 3.9
3707 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901026 | This project will improve sections and extend the life of New Market Road from SR 3 to Zimmerman Road in Clark County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/29/2009 | 04/30/2010 | 202273.16 | 3.1
3708 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901027 | This project will improve sections and extend the life of Camp Creek-Bethlehem Road from Flint Road to Bethlehem New Washington in Clark County with a pavement surface overlay. | Pavement Improvement | 08/20/2009 | 09/29/2009 | 11/13/2009 | 202814.25 | 3.07
3709 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901029 | This project will improve sections and extend the life of Charlestown-Memphis Road from US 31 to SR 160 in Clark County with a pavement surface overlay. | Pavement Improvement | 10/09/2009 | 10/30/2009 | 04/30/2010 | 307001.48 | 5.9
3710 | Indiana | HOWARD |  | 05 | 0901030 | This project will improve sections and extend the life of County Road 750West from County Road 300 North to County Road 400 North in Howard County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 65574.31 | 1
3711 | Indiana | HOWARD |  | 05 | 0901031 | This project will improve sections and extend the life of County Road 100North from County Road 400 East to County Road 500 East in Howard County with a pavement surface overlay. | Pavement Improvement | 09/14/2009 | 09/24/2009 | 11/13/2009 | 75481.89 | 1
3712 | Indiana | HAMILTON |  | 05 | 0901032 | This is a Maintenance Resurfacing project, at 146th St from Hamilton/Boone County line to Ditch Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 05/14/2010 | 06/18/2010 | 308907.44 | 3.05
3713 | Indiana | WAYNE |  | 06 | 0901036 | This project will improve sections and extend the life of Salisbury Road from Nolands Fork Road to Williamsburg Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/13/2009 | 163791.8 | 0.65
3714 | Indiana | WAYNE |  | 06 | 0901037 | This project will improve sections and extend the life of 37th Street from Hodgin Road to US 40 in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/20/2009 | 544186.16 | 1.14
3715 | Indiana | WAYNE |  | 06 | 0901038 | This project will improve sections and extend the life of Industries Road from Williamsburg Pike to Union Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/06/2009 | 219725.43 | 0.61
3716 | Indiana | FULTON |  | 02 | 0901039 | This project will improve sections and extend the life of Southway 31 in Fulton County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 11/25/2009 | 115530.27 | 1.1
3717 | Indiana | FULTON |  | 02 | 0901040 | This is a Maintenance Resurfacing project, at Old US 31 N from CR 350N to SR 110; to perform Surface Treatment work. | Pavement Improvement | 10/14/2009 |  | 06/30/2010 | 449932.91 | 4.7
3718 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901041 | This is a Maintenance Resurfacing project, at Greenwood Avenue between SR 231 and SR 55; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 12/16/2009 | 04/14/2010 | 06/01/2010 | 253502.62 | 2.56
3719 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901042 | This is a Maintenance Resurfacing project, at Court Street from the North side of Town Square to 121st. St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 12/16/2009 | 04/14/2010 | 06/01/2010 | 435566.77 | 1.28
3720 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901043 | This is a Maintenance Resurfacing project, at 49th Avenue from Broadway to Grant; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 03/31/2010 | 06/01/2010 | 336330.85 | 0.75
3721 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901044 | This is a Maintenance Resurfacing project, at 15th Avenue from I-65 to Martin Luther King Dr.; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 04/06/2010 | 06/01/2010 | 232517.79 | 0.65
3722 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901045 | This is a Maintenance Resurfacing project, at 35th Avenue from Broadway to Martin Luther King Dr.; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 03/31/2010 | 06/01/2010 | 401067.83 | 0.93
3723 | Indiana | FULTON |  | 02 | 0901046 | This is a preventive maintenanc eresurfacing project, at Olson Road from CR 700 W to SR 17 in Fulton county to provide 1 inch of asphalt to extend the pavement life. | Pavement Improvement | 10/14/2009 |  | 06/30/2010 | 206332.77 | 3.5
3724 | Indiana | FULTON |  | 02 | 0901047 | This project will improve sections and extend the life of Wabash Ave with a pavement surface overlay. | Pavement Improvement | 09/11/2009 |  | 11/25/2009 | 108235.99 | 1.6
3725 | Indiana | FULTON |  | 02 | 0901048 | This is a Maintenance Resurfacing project, at CR 550 S from CR 1200 W(Fulton/Pulaski Co Line) to SR 17; to perform Surface Treatment work. | Pavement Improvement | 10/14/2009 |  | 06/30/2010 | 167279.28 | 2.8
3726 | Indiana | FULTON |  | 02 | 0901049 | This is a Maintenance Resurfacing project, at CR 600 S from SR 25 to CR 250 E; to perform Surface Treatment work. | Pavement Improvement | 10/14/2009 |  | 06/30/2010 | 163888.4 | 2.8
3727 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901050 | This project will improve sections and extend the life of Engle Road from St John Road to Floyd County in Clark County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/27/2009 | 04/30/2010 | 107832.81 | 1.22
3728 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901051 | This is a Maintenance Resurfacing project, at Hibernia Rd. from SR 62 to Charlestown Bethlehem Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/13/2009 | 10/20/2009 | 11/13/2009 | 104312.85 | 1.43
3729 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901052 | This project will improve sections and extend the life of Marble Hill Road from SR 62 to Gill Road in Clark County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/29/2009 | 04/30/2010 | 145544.3 | 1.72
3730 | Indiana | JEFFERSON |  | 09 | 0901057 | This is a Maintenance Resurfacing project, at Old State Rd 62 from US 421 to SR 62; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/13/2009 | 10/26/2009 | 11/15/2009 | 135612.23 | 1.97
3731 | Indiana | RUSH |  | 06 | 0901059 | This is a Maintenance Resurfacing project, at Main Street from CR 800 to the RR Tracks at the town limit; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/13/2009 | 05/28/2010 | 06/25/2010 | 357838.25 | 1.34
3732 | Indiana | JACKSON |  | 09 | 0901060 | This project will improve the pavement with a preventive maintenance resurface on Base Road/County Road 25 East from White River to SR 2 in Jackson county. | Pavement Improvement | 02/20/2010 | 03/25/2010 | 07/01/2010 | 488093.28 | 5.67
3733 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901062 | This project will improve sections and extend the life of Martinsburg Knob Road from Borden Greenville Road to Washington County in Clark County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/08/2009 | 11/13/2009 | 197357.5 | 3.69
3734 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901063 | This project will improve sections and extend the life of New Hope Church Road from Bethlehem Road to Jefferson County in Clark County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/29/2009 | 04/30/2010 | 83118.28 | 1.1
3735 | Indiana | GRANT |  | 05 | 0901065 | This is a Maintenance Resurfacing project, at 38th Street from 460 feet E of Adams Street/SR 15 to S Todd Street to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 581950.94 | 1.68
3736 | Indiana | GRANT |  | 05 | 0901066 | This is a Maintenance Resurfacing project, at Adams Street from 29th street to 26th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 90479.78 | 0.35
3737 | Indiana | GRANT |  | 05 | 0901067 | This is a Maintenance Resurfacing project, at Nebraska Street from 26th Street to 23rd Street to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 462130.86 | 1.48
3738 | Indiana | JACKSON |  | 05 | 0901068 | This is a Maintenance Resurfacing project, at Adams Street from Railroad Tracks S of 11th Street to 3rd St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 216594.89 | 0.58
3739 | Indiana | GRANT |  | 05 | 0901069 | This is a Maintenance Resurfacing project, at Washington Street from 38th street to Wabash Ave.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 11/12/2009 | 07/02/2010 | 989056.12 | 2.67
3740 | Indiana | GRANT |  | 05 | 0901070 | This project will improve sections and extend the life of Kem Road from Miller Avenue to Wabash Avenue in Grant County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/13/2009 | 10/31/2009 | 246551.96 | 1.03
3741 | Indiana | MARION | INDIANAPOLIS | 07 | 0901071 | This is a Maintenance Resurfacing project, at Allisonville Rd from Fall Creek Rd to 46th St.; to perform Partial 3-R work. | Pavement Improvement | 11/24/2009 |  | 06/30/2010 | 239371.27 | 0.05
3742 | Indiana | MARION | INDIANAPOLIS | 07 | 0901072 | This is a Maintenance Resurfacing project, at 62nd St from Keystone Ave to Allisonville Rd.; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 | 03/15/2010 | 06/30/2010 | 521300 | 1.3
3743 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901073 | This is a Maintenance Resurfacing project, at State St from I-265 to Green Valley Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 04/09/2010 | 06/19/2010 | 265600 | 0.73
3744 | Indiana | MONROE | BLOOMINGTON | 09 | 0901074 | This is a Maintenance Resurfacing project, at Old SR 37 S, from SR 37 to Rogers St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 03/29/2010 | 07/30/2010 | 181380.86 | 0.95
3745 | Indiana | MONROE | BLOOMINGTON | 09 | 0901076 | This is a preventive maintenance resurfacing project, at Old SR 37 N in Monroe county , from Whisnand Rd to Wylie Rd. to extend the life of the pavement. | Pavement Improvement | 11/23/2009 | 04/08/2010 | 07/30/2010 | 330820.04 | 2.34
3746 | Indiana | MONROE | BLOOMINGTON | 09 | 0901077 | This is a Maintenance Resurfacing project, at Monroe Dam Rd, from SR 37 to Strain Ridge Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/29/2010 | 07/30/2010 | 117238.04 | 0.773
3747 | Indiana | MONROE | BLOOMINGTON | 04 | 0901078 | This is a Maintenance Resurfacing project, at Rockport Road from Victor Pike to May Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 04/06/2010 | 07/30/2010 | 403313.71 | 3.128
3748 | Indiana | MONROE | BLOOMINGTON | 09 | 0901079 | This is a Maintenance Resurfacing project, at Fairfax Road, from Pointe Rd to Dillman Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 04/05/2010 | 07/30/2010 | 695947.21 | 4.72
3749 | Indiana | MARION | INDIANAPOLIS | 07 | 0901080 | This is a Bridge Replacement (no added capacity) project, at Bridge over Lick Creek in Sarah Bolton Park; to perform Bridge Replacement, Special work. | Bridge Replacement | 02/22/2010 |  | 09/03/2010 | 341363.39 | 0.01
3750 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901081 | This is a preventive maintenance resurfacing project, at Greenfield Avenue (formerly SR 238) in Hamilton county to extend the pavement life. | Pavement Improvement | 12/31/2009 |  | 06/30/2010 | 311055.35 | 2.88
3751 | Indiana | MARION | INDIANAPOLIS | 07 | 0901082 | This is a Maintenance Resurfacing project, at Emerson Ave from 38th St to 56th St.; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 | 03/18/2010 | 09/30/2010 | 1490522 | 2
3752 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901083 | This is a Maintenance Resurfacing project, at Paoli Pike from Hilltop Rd to 267 feet W of Boe Creek Dr.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 03/31/2010 | 05/22/2010 | 293500 | 1.97
3753 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901084 | This is a Maintenance Resurfacing project, at Georgetown-Greenville Road from Church Rd.; to Harrison St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/25/2009 | 04/08/2010 | 06/12/2010 | 363000 | 6.5
3754 | Indiana | GRANT |  | 05 | 0901086 | This project will improve sections and extend the life of Garthwaite Road in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 100685.68 | 1.12
3755 | Indiana | GRANT |  | 05 | 0901087 | This project will improve sections and extend the life of County Road 300South from County Road 300 West to SR 37 in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 218205.79 | 3
3756 | Indiana | GRANT |  | 05 | 0901088 | This project will improve sections and extend the life of County Road 600East from SR 18 to County Road 700 North in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 467332.26 | 6.76
3757 | Indiana | GRANT |  | 05 | 0901089 | This project will improve sections and extend the life of County Road 200North from County Road 300 East to County Road 600 East in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 218843.62 | 3
3758 | Indiana | GRANT |  | 05 | 0901090 | This project will improve sections and extend the life of County Road 400East from Walnut Creek to County Road 200 South in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 98260.27 | 1.5
3759 | Indiana | GRANT |  | 05 | 0901091 | This project will improve sections and extend the life of County Road 950East from Matthews Town Limits to SR 26 in Grant County with a pavement surface overlay. | Pavement Improvement | 09/02/2009 | 10/01/2009 | 11/07/2009 | 224068.95 | 2.27
3760 | Indiana | MARSHALL |  | 02 | 0901093 | This project will improve sections and extend the life of Olive Trail from 13th Road to Overmyer Drive in Marshall County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 04/21/2010 | 07/02/2010 | 66651.01 | 3.709
3761 | Indiana | BLACKFORD |  | 06 | 0901096 | This project will improve sections and extend the life of Wabash Avenue from Kickapoo Street to Park Avenue in Blackford County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/12/2009 | 10/30/2009 | 73667.35 | 0.3
3762 | Indiana | DE KALB |  | 03 | 0901097 | This project will improve sections and extend the life of County Road 40 from SR 1 to State Line in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/01/2009 | 10/30/2009 | 270802.5 | 3.4
3763 | Indiana | DE KALB |  | 03 | 0901098 | This project will improve sections and extend the life of Auburn Drive from Diehl Drive to Wayne Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/06/2009 | 10/31/2009 | 153639.84 | 1.42
3764 | Indiana | DE KALB |  | 03 | 0901099 | This project will improve sections and extend the life of Main Street from Gates Cove to County Road 36 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 09/01/2009 | 10/06/2009 | 10/31/2009 | 153688.07 | 1.42
3765 | Indiana | HENDRICKS | INDIANAPOLIS | 04 | 0901100 | This is a Maintenance Resurfacing project, at From 2500 N. Dan Jones to approx. 3000 S. Dan Jones Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 02/22/2010 | 05/01/2010 | 1094800 | 4.2
3766 | Indiana | HENDRICKS | INDIANAPOLIS | 04 | 0901101 | This is a Safety project, at CR 200 N & Ronald Reagan Pkwy.; to perform Traffic Signals, New Or Modernized work. | Safety/Traffic Management | 10/23/2009 | 11/16/2009 | 06/30/2010 | 169869.75 | 0.01
3767 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901102 | This is a Maintenance Resurfacing project, at Wiggins St. to just south of Robinison St.; to perform Resurface over Asphalt Pavement work. | Pavement Improvement | 11/23/2009 | 05/18/2010 | 06/30/2010 | 272515.74 | 0.53
3768 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901106 | This is a Facilities for Pedestrians and Bicycles project, at New trail from Clarendon Dr. to Edgewater Dr. paralled to Carrigan Rd.; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 05/18/2010 |  | 11/15/2010 | 1251268.75 | 0.305
3769 | Indiana | MARION | INDIANAPOLIS | 07 | 0901110 | This is a Bridge Rehabilitation (no added capacity) project, at Emerson Ave. over CSX Railroad; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 12/30/2009 | 02/22/2010 | 07/31/2010 | 426709.45 | 0.028
3770 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901112 | This is a Maintenance Resurfacing project, between Battleground Town limits & Tyler Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/05/2010 | 03/19/2010 | 06/30/2010 | 252086.24 | 0.04
3771 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901113 | This is a Maintenance Resurfacing project, at Ridge Road from Colfax Avenue to Grant St.; to perform Surface Treatment work. | Pavement Improvement | 01/13/2010 | 04/30/2010 | 06/30/2010 | 967860.55 | 2.99
3772 | Indiana | DAVIESS |  | 08 | 0901122 | This is a Maintenance Resurfacing project, at NW 21st St to Front St.; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 06/18/2010 | 08/31/2010 | 70629.65 | 0.76
3773 | Indiana | DAVIESS |  | 08 | 0901123 | This is a Maintenance Resurfacing project, at US 50 to W Main St.; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 06/18/2010 | 08/31/2010 | 44229.41 | 0.38
3774 | Indiana | DAVIESS |  | 08 | 0901124 | This is a Maintenance Resurfacing project, at Jackson St to Wykoff Ln.; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 06/18/2010 | 08/31/2010 | 40996.12 | 0.38
3775 | Indiana | DAVIESS |  | 08 | 0901125 | This is a Maintenance Resurfacing project, at Field Ave to NW 21st St.; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 06/18/2010 | 08/31/2010 | 45965.07 | 0.51
3776 | Indiana | SCOTT |  | 09 | 0901126 | This is a Maintenance Resurfacing project, at Leota Rd from Boatman Rd to US 31; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/29/2010 | 05/31/2010 | 156789.65 | 2.2
3777 | Indiana | MARION | INDIANAPOLIS | 07 | 0901127 | This is a Maintenance Restoration & Rehabilitation project, at 56th St. from Boy Scout Rd. to Ciato Rd.; to perform Pavement, Other work. | Pavement Improvement | 04/01/2010 |  | 08/15/2010 | 233325 | 0.5
3778 | Indiana | MARION | INDIANAPOLIS | 07 | 0901128 | This is a Bridge Rehabilitation (no added capacity) project, at Westfield Blvd. over White River; to perform Bridge Deck Overlay work. | Bridge Improvement | 12/30/2009 | 02/22/2010 | 07/31/2010 | 348011.01 | 0.096
3779 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901129 | This is a Maintenance Resurfacing project, at Edwardsville-Galena Rd from Oaks Road to Bridge over Little Indian Creek; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 04/16/2010 | 05/05/2010 | 191300 | 3.6
3780 | Indiana | WASHINGTON |  | 09 | 0901130 | This is a Maintenance Resurfacing project at Washington Blvd from Mulberry St. to Market St. to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/30/2009 | 11/02/2009 | 11/30/2009 | 52646.81 | 0.34
3781 | Indiana | MARION | INDIANAPOLIS | 08 | 0901131 | This is a Maintenance Resurfacing project, at Tibbs Ave. from 16th St. to Lafayette Rd.; to perform Partial 3-R work. | Pavement Improvement | 12/31/2009 |  | 08/16/2010 | 361104.1 | 1.2
3782 | Indiana | MARION | INDIANAPOLIS | 07 | 0901132 | This is a Maintenance Resurfacing project, at Thompson Rd. from Emerson Ave. to Franklin Rd.; to perform Partial 3-R work. | Pavement Improvement | 02/22/2010 |  | 08/16/2010 | 1199315.16 | 3.4
3783 | Indiana | MARION | INDIANAPOLIS | 07 | 0901133 | This is a Maintenance Resurfacing project, at Southeastern Ave. from Raymond St. to Sheridan Ave.; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 |  | 10/04/2010 | 1275406.63 | 0.08
3784 | Indiana | MARION | INDIANAPOLIS | 07 | 0901134 | This is a Maintenance Resurfacing project, at Sam Jones Parkway from I-465 to I-70; to perform Partial 3-R work. | Pavement Improvement | 12/31/2009 |  | 08/16/2010 | 727847.17 | 1.3
3785 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901136 | This is a Maintenance Resurfacing project, at Central Avenue from Benton Street to County Line Rd.; to perform Surface Treatment work. | Pavement Improvement | 01/19/2010 | 04/06/2010 | 06/09/2010 | 486985.59 | 3
3786 | Indiana | LA PORTE |  | 02 | 0901137 | This is a Maintenance Resurfacing project, at Wozniak Road from SR 2 to CR 400 N; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 01/06/2010 | 04/06/2010 | 05/15/2010 | 1094730.38 | 7.3
3787 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901138 | This is a Reconstruction (no added capacity) project, at Summit, Between Wirtz Road and Jennings Place; to perform Other Type Project (Miscellaneous) work. | Pavement Improvement | 02/25/2010 | 06/13/2010 | 07/01/2010 | 166804.2 | 0.01
3788 | Indiana | PULASKI |  | 02 | 0901139 | This project will improve sections and extend the life of County Road 500S outh from Market Street to county road 1050 west in Pulaski County with a pavement surface overlay. | Pavement Improvement | 12/31/2009 |  | 08/27/2010 | 104611.01 | 3.86
3789 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901140 | This is a Maintenance Resurfacing project, at Wabash Avenue from Calumet Road to Waverly Rd.; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/15/2010 | 07/01/2010 | 105466.09 | 0.6
3790 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901141 | This is a Maintenance Resurfacing project, at 11th Street from CR 1100 N to Porter Ave.; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/15/2010 | 07/01/2010 | 133054.67 | 0.91
3791 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901142 | This is a Maintenance Resurfacing project, at Porter Avenue from 15th St. to 23rd St.; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/15/2010 | 07/01/2010 | 84335.06 | 0.52
3792 | Indiana | WASHINGTON |  | 09 | 0901145 | This is a Maintenance Resurfacing project, at SR 135 - Market St. from Washington Blvd to Alpine St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/30/2009 | 11/02/2009 | 11/30/2009 | 91557.87 | 0.72
3793 | Indiana | MARION | INDIANAPOLIS | 07 | 0901148 | This is a Maintenance Resurfacing project, at Raymond St. from Shelby St. to Southeastern Ave.; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 |  | 10/04/2010 | 2847684.79 | 3.6
3794 | Indiana | MARION | INDIANAPOLIS | 07 | 0901149 | This is a Bridge Rehabilitation (no added capacity) project, at Holt Rd. bridge over Big Eagle Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 12/03/2009 | 06/01/2010 | 09/30/2010 | 822708.1 | 0.068
3795 | Indiana | MARION | INDIANAPOLIS | 07 | 0901151 | This is a Maintenance Resurfacing project, at Franklin Way/Rd. from 21st St. to 30th St.; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 |  | 10/04/2010 | 465877.43 | 1
3796 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901152 | This is a Bridge Rehabilitation (no added capacity) project, at Cumberland Rd. over White River; to perform Bridge Deck Overlay work. | Bridge Improvement | 02/22/2010 | 06/01/2010 | 09/01/2010 | 425380.09 | 0.095
3797 | Indiana | MARION | INDIANAPOLIS | 05 | 0901153 | This is a Maintenance Resurfacing project, at Walnut St. from Southport Rd. to Stop 10 Rd.; to perform Resurface PCC Pavement (Partial 3/R Standards) work. | Pavement Improvement | 01/13/2010 |  | 08/16/2010 | 161969.95 | 0.542
3798 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901154 | This is a Maintenance Resurfacing project, at Lantern Rd. from South St. to Lantern Wood Dr.; to perform Pavement, Other work. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 119679.34 | 0.75
3799 | Indiana | WABASH |  | 05 | 0901155 | This project will improve sections and extend the life of County Road 250South from Old Sr 15 to America Road in Wabash County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 05/06/2010 | 06/18/2010 | 441936.72 | 4.94
3800 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901156 | This is a Maintenance Resurfacing project, at Hague Rd. from 96th St. to 116th St.; to perform Pavement, Other work. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 204318.61 | 2
3801 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901157 | This is a Maintenance Resurfacing project, at Cumberland Rd. from 121st St. to 141st St.; to perform Pavement, Other work. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 189960.09 | 2
3802 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901159 | This is a Maintenance Resurfacing project, at Cumberland Rd. from 106th St. to High Point Ridge; to perform Pavement, Other work. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 118730.32 | 0.8
3803 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901160 | This is a Maintenance Resurfacing project, at Brooks School Rd. from 96th St. to 116th St.; to perform Pavement, Other work. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 137666.98 | 2
3804 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901162 | This is a Maintenance Resurfacing project, at 106th St. from Hague Rd. to Cumberland Rd.; to perform Pavement, Other work. | Pavement Improvement | 11/19/2009 |  | 08/07/2010 | 243841.66 | 2
3805 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901163 | This is a Maintenance Resurfacing project, at Hazel Dell Blvd. (see project listing for full description); to perform Partial 3-R work. | Pavement Improvement | 03/05/2010 | 03/30/2010 | 09/07/2010 | 1671831.15 | 2.1
3806 | Indiana | MARION | INDIANAPOLIS | 07 | 0901165 | This is a Maintenance Restoration & Rehabilitation project, at 75th St.-Pennsyl. St. to College Ave. & sign repl. fr. Spring Mill to College Ave.; to perform Road Rehabilitation work. | Pavement Improvement | 12/16/2009 |  | 06/01/2010 | 91196 | 0.6
3807 | Indiana | BLACKFORD |  | 06 | 0901166 | This project will improve sections and extend the life of Park Avenue from Gilkey Ave to Mill Street in Blackford County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 11/03/2009 | 05/29/2010 | 143863.5 | 1.5
3808 | Indiana | MARION | INDIANAPOLIS | 07 | 0901167 | This is a Maintenance Resurfacing project, at Elmwood Ave. from E. of Emerson Ave. to W. of Arlington Ave.; to perform Pavement, Other work. | Pavement Improvement | 12/31/2009 | 05/11/2010 | 06/30/2010 | 115088.25 | 1.1
3809 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901168 | This is a Maintenance Resurfacing project, at Greensburg Rd. from 510 East to 450 E; to perform Pavement, Other work. | Pavement Improvement | 12/16/2009 | 04/19/2010 | 05/14/2010 | 102996.8 | 0.8
3810 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901169 | This is a Maintenance Resurfacing project, at Morgantown Rd. from CR 600N to Fairview Rd.; to perform Pavement, Other work. | Pavement Improvement | 12/16/2009 | 04/19/2010 | 05/14/2010 | 292854.81 | 3.88
3811 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901170 | This is a Maintenance Resurfacing project, at CR 144 from CR 500N to Bargersville City limits; to perform Pavement, Other work. | Pavement Improvement | 12/16/2009 | 04/19/2010 | 05/14/2010 | 193734.92 | 2.29
3812 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901171 | This is a Maintenance Resurfacing project, at County Road 800 N - Olive Branch Rd. from 400 West to SR 135; to perform Pavement, Other work. | Pavement Improvement | 12/16/2009 | 04/19/2010 | 05/14/2010 | 84675.38 | 0.85
3813 | Indiana | MORGAN | INDIANAPOLIS | 04 | 0901172 | This is a Maintenance Resurfacing project, at Mann Rd. from Landersdale Rd. to the Marion County Line; to perform Partial 3-R work. | Pavement Improvement | 12/31/2009 | 04/15/2010 | 08/30/2010 | 128564 | 1.26
3814 | Indiana | DELAWARE | MUNCIE | 03 | 0901173 | This is a Maintenance Resurfacing project, at McGallliard Rd. from Wheeling Ave. to Riverside Ave.; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 | 07/02/2010 | 10/01/2010 | 863097.34 | 1.55
3815 | Indiana | DELAWARE | MUNCIE | 06 | 0901174 | This is a Maintenance Resurfacing project,at Tillotson Ave from Riverside Ave to SR 332/McGalliard Rd.; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 | 06/24/2010 | 10/01/2010 | 769371.87 | 1.27
3816 | Indiana | WAYNE |  | 06 | 0901175 | This project will improve sections and extend the life of Kepler Road from Jacksonburg Road to Washington Road in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/06/2009 | 257959.04 | 1.88
3817 | Indiana | WAYNE |  | 06 | 0901176 | This project will improve sections and extend the life of Pottershop Road from Abington to US 27 in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/23/2009 | 10/23/2009 | 62448.04 | 0.16
3818 | Indiana | WAYNE |  | 06 | 0901177 | This is a Maintenance Resurfacing project, at SR 38 - Centerville Road (S-8189) from SR 38 to We Oler Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/18/2009 | 05/18/2010 | 06/04/2010 | 574791.59 | 4.44
3819 | Indiana | WAYNE |  | 06 | 0901178 | This project will improve sections and extend the life of Jacksonburg Road from Swoveland Road to SR 38 in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/23/2009 | 11/13/2009 | 155774.29 | 1
3820 | Indiana | WAYNE |  | 06 | 0901179 | This project will improve sections and extend the life of Pottershop Road from Pennville Road to Abington in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 06/04/2010 | 59092.13 | 0.27
3821 | Indiana | WAYNE |  | 06 | 0901180 | This project will improve sections and extend the life of Pennville Road from Fayette County line to US 40 in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/06/2009 | 794659.49 | 6.77
3822 | Indiana | WAYNE |  | 06 | 0901181 | This project will improve sections and extend the life of Centerville Road from I-70 to SR 38 with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/12/2009 | 11/13/2009 | 221065 | 1.52
3823 | Indiana | WAYNE |  | 06 | 0901182 | This project will improve sections and extend the life of South L Street in Wayne County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 09/21/2009 | 11/25/2009 | 736150 | 1.52
3824 | Indiana | MARION | INDIANAPOLIS | 07 | 0901183 | This proejct will extend the life of the bridge by doing bridge maintenance and repair on the deck on Keystone Avenue bridge over Fall Creek in Marion county. | Bridge Improvement | 02/22/2010 | 04/05/2010 | 07/31/2010 | 647694.28 | 0.1
3825 | Indiana | HANCOCK |  | 05 | 0901188 | This is a Bridge Rehabilitation (no added capacity) project, at I 70 - 5.75 mi W of SR 9; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 10/09/2009 |  | 08/13/2010 | 407780 | 0.196
3826 | Indiana | JACKSON |  | 09 | 0901198 | This is a Maintenance Resurfacing project, at 300 N from CR 100 W to White River; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 03/25/2010 | 06/15/2010 | 205666.14 | 3.22
3827 | Indiana | JEFFERSON |  | 09 | 0901200 | This is a Maintenance Resurfacing project, at Deputy Pike from SR 7 to SR 3; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 07/31/2010 | 937456 | 13.1
3828 | Indiana | DE KALB |  | 03 | 0901201 | This project will replace existing sidewalks and place new sidewalks in St. Joe, Indiana . | Safety/Traffic Management | 09/15/2009 | 10/26/2009 | 05/27/2010 | 111590.35 | 0.36
3829 | Indiana | DE KALB |  | 03 | 0901203 | This project will improve sections and extend the life of Dekalb County Road 35 with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/06/2009 | 10/31/2010 | 143137.9 | 5.3
3830 | Indiana | CLAY |  | 08 | 0901208 | This is a Maintenance Resurfacing project, at I-70 - From Center Point to Harmony; to perform Partial 3-R work. | Pavement Improvement | 12/16/2009 | 03/18/2010 | 06/30/2010 | 823382.98 | 8
3831 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901209 | This project will resurface the County Road 350N between Morehouse Road And West Lafayette City Limits in Tippecanoe County. | Pavement Improvement | 04/10/2010 | 06/21/2010 | 06/30/2010 | 91523 | 0.26
3832 | Indiana | MARION | INDIANAPOLIS | 04 | 0901210 | This is a Maintenance Resurfacing project, at Mooresville Rd from Raceway Rd to West Newton; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 | 04/05/2010 | 08/09/2010 | 829554.42 | 2.4
3833 | Indiana | MARION | INDIANAPOLIS | 07 | 0901211 | This is a Maintenance Resurfacing project, at Mooresville Rd from Southport Rd to High School Rd.; to perform Partial 3-R work. | Pavement Improvement | 11/23/2009 | 04/05/2010 | 08/09/2010 | 273333.59 | 0.04
3834 | Indiana | CASS |  | 02 | 0901212 | This is a Maintenance Resurfacing project, at SR 29 - Burlington Avenue from Clinton Street to Cliff Dr.; to perform Surface Treatment work. | Pavement Improvement | 02/23/2010 | 03/15/2010 | 06/02/2010 | 392699.46 | 0.94
3835 | Indiana | CASS |  | 02 | 0901213 | This is a Maintenance Resurfacing project, at Main Street from Coles Street to US24/35; to perform Surface Treatment work. | Pavement Improvement | 02/23/2010 | 03/15/2010 | 06/02/2010 | 179608.77 | 1.6
3836 | Indiana | MONROE | BLOOMINGTON | 09 | 0901216 | This is a Maintenance Resurfacing project, at Woodyard Rd from Curry Pike to Vernal Pike; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/24/2010 | 04/06/2010 | 07/30/2010 | 125979.18 | 1.31
3837 | Indiana | MONROE | BLOOMINGTON | 09 | 0901218 | This is a Maintenance Resurfacing project, at Old SR 37 South, from Rogers St to Rhorer Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/24/2010 | 04/06/2010 | 07/30/2010 | 357964.17 | 1.67
3838 | Indiana | MONROE | BLOOMINGTON | 09 | 0901220 | This is a Maintenance Resurfacing project, at That Road, from SR 37 to Rogers St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/24/2010 | 04/06/2010 | 07/30/2010 | 163852.75 | 1.36
3839 | Indiana | MARION | INDIANAPOLIS | 05 | 0901224 | This is a Maintenance Resurfacing project, at Southport Rd. from Sherman Dr. to Gray Rd.; to perform Partial 3-R work. | Pavement Improvement | 02/22/2010 |  | 08/16/2010 | 286848.1 | 0.4
3840 | Indiana | KOSCIUSKO |  | 03 | 0901227 | This is a Maintenance Resurfacing project, from 0.15 miles W of SR 19 to 0.1 miles W of SR 13; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 03/24/2010 | 03/26/2010 | 10/01/2010 | 7934392.25 | 19.63
3841 | Indiana | MARION | INDIANAPOLIS | 07 | 0901228 | This is a Maintenance Resurfacing project, at Lynhurst Dr from Kentucky Ave to I-70; to perform Partial 3-R work. | Pavement Improvement | 12/31/2009 |  | 08/16/2010 | 211864.21 | 1.2
3842 | Indiana | MARION | INDIANAPOLIS | 04 | 0901229 | This is a preventive maintenance resurfacing project, at Mendenhall Rd from Camby Rd to SR 67 in Marion county to extend the service life of the pavement. | Pavement Improvement | 11/23/2009 | 04/05/2010 | 08/09/2010 | 338289.39 | 1.2
3843 | Indiana | MARION | INDIANAPOLIS | 07 | 0901230 | This is a Maintenance Resurfacing project, at Meridian St. from Thompson Rd. to I-465; to perform Partial 3-R work. | Pavement Improvement | 02/22/2010 |  | 08/16/2010 | 599699.62 | 0.6
3844 | Indiana | MARION | INDIANAPOLIS | 07 | 0901231 | This is a Maintenance Resurfacing project, at 38th St from German Church Rd to Carroll Rd.; to perform Partial 3-R work. | Pavement Improvement | 02/22/2010 | 05/11/2010 | 06/30/2010 | 237451.28 | 1
3845 | Indiana | MARION | INDIANAPOLIS | 05 | 0901233 | This is a Maintenance Resurfacing project, at Arlington Ave. from Shelbyville Rd.; to Thompson Rd. to perform Partial 3-R work. | Pavement Improvement | 02/22/2010 |  | 08/16/2010 | 618488.12 | 1.3
3846 | Indiana | MARION | INDIANAPOLIS | 05,07 | 0901234 | This is a Maintenance Resurfacing project, at Carroll Rd from 46th St to 56th St.; to perform Partial 3-R work. | Pavement Improvement | 03/05/2010 |  | 06/30/2010 | 310676.88 | 1
3847 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901235 | This is a Maintenance Resurfacing project, at 116th St from 0.35 mi E. of Eller Rd to 2.4 mi W of I-69; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 |  | 07/31/2010 | 157808.07 | 0.02
3848 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901236 | This is a Maintenance Resurfacing project, at Towne Rd from 96th St to 116th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 07/31/2010 | 140876.94 | 2.05
3849 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901237 | This is a Maintenance Resurfacing project, at 146th St from Ditch Rd to Springmill Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 | 05/14/2010 | 06/11/2010 | 113419.92 | 0.98
3850 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901238 | This is a Maintenance Resurfacing project, at Cumberland Rd from 96th St to 106th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 07/31/2010 | 86502.98 | 1.02
3851 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901239 | This is a preventive maintenance resurfacing project, at Olio Rd from the bridge over Geist Reservoir to 126th St. in Hamilotn county to extendthe service life of the pavement. | Pavement Improvement | 12/16/2009 |  | 07/31/2010 | 393619.79 | 1.02
3852 | Indiana | HANCOCK | INDIANAPOLIS | 05 | 0901240 | This is a Maintenance Resurfacing project, at CR 600W from CR 500N to CR 650N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 215724.58 | 1.47
3853 | Indiana | HANCOCK | INDIANAPOLIS | 05 | 0901241 | This is a Maintenance Resurfacing project, at CR 300N from CR 700W to CR 800W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 89072.4 | 1
3854 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901242 | This is a Safety project, at SR 51 - SR 51(Lincoln St) at 10th St (SR 51); to perform Traffic Signals, New Or Modernized work. | Safety/Traffic Management | 01/05/2010 | 02/01/2010 | 05/31/2010 | 80714 | 0.01
3855 | Indiana | STEUBEN |  | 03 | 0901243 | This is a Maintenance Resurfacing project, at County Highway 1100 W - CR-475S from Lagrange County line to CR-500S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 154670.93 | 0.8
3856 | Indiana | STEUBEN |  | 03 | 0901244 | This is a Maintenance Resurfacing project, at CR 500 S from CR 475 S to SR 327; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 61689.4 | 0.7
3857 | Indiana | STEUBEN |  | 03 | 0901245 | This is a Maintenance Resurfacing project, at N SR 327 - CR 500 N from SR-327 to CR 900 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 45702.26 | 0.5
3858 | Indiana | STEUBEN |  | 03 | 0901246 | This is a Maintenance Resurfacing project, at CR 900 W from CR 500 N to Orland Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 13826.59 | 0.1
3859 | Indiana | STEUBEN |  | 03 | 0901247 | This is a Maintenance Resurfacing project, at Orland Road from CR 900 W to CR 800 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 101475.56 | 1
3860 | Indiana | STEUBEN |  | 03 | 0901248 | This is a Maintenance Resurfacing project, at CR 800 W from Orland Rd (N Junction) to Orland Rd.; (S Junction) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 12872.56 | 0.1
3861 | Indiana | STEUBEN |  | 03 | 0901249 | This is a Maintenance Resurfacing project, at Orland Rd from CR 800 W to CR 675 N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 160441.5 | 1.4
3862 | Indiana | STEUBEN |  | 03 | 0901250 | This is a Maintenance Resurfacing project, at Kimble Rd from CR 550 W to Orland Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 27577.22 | 0.35
3863 | Indiana | STEUBEN |  | 03 | 0901252 | This is a Maintenance Resurfacing project, at Fox Lake Rd from Menges Rd to CR 200 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 259152.5 | 2.1
3864 | Indiana | STEUBEN |  | 03 | 0901253 | This is a Maintenance Resurfacing project, at CR 200 W from Fox Lake Rd to US 20; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 6615.8 | 0.3
3865 | Indiana | STEUBEN |  | 03 | 0901254 | This is a Maintenance Resurfacing project, at Menges Rd from Waymire Rd to Fox Lake Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 55508.97 | 0.7
3866 | Indiana | STEUBEN |  | 03 | 0901255 | This is a Maintenance Resurfacing project, at Waymire Rd from Menges Rd to CR 150W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 117311.16 | 1.3
3867 | Indiana | STEUBEN |  | 03 | 0901256 | This is a Maintenance Resurfacing project, at E SR 120 - Van Guilder Road from SR-120; to North Baker St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/15/2009 | 04/08/2010 | 05/27/2010 | 139414.16 | 1.6
3868 | Indiana | JAY |  | 06 | 0901271 | This is a Maintenance Restoration & Rehabilitation project, at N Charles Ave from W Water Street to SR 67; to perform Pavement, Other work. | Pavement Improvement | 12/04/2009 |  | 06/25/2010 | 49493.52 | 0.5
3869 | Indiana | JAY |  | 06 | 0901272 | This is a Maintenance Resurfacing project, at Lincoln Street from N Franklin Street to US 27 (Meridian Street); to perform Pavement, Other work. | Pavement Improvement | 11/23/2009 |  | 06/25/2010 | 19926.5 | 0.17
3870 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901278 | This is a Maintenance Resurfacing project, at Whiteland Rd from CR 75W to the New Whiteland City limits; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 04/13/2010 | 05/14/2010 | 94201.01 | 0.77
3871 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901279 | This is a Maintenance Resurfacing project, at Smokey Row Rd from CR 500W to SR 135; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 04/13/2010 | 05/14/2010 | 208365.43 | 2
3872 | Indiana | JOHNSON | INDIANAPOLIS | 04 | 0901280 | This is a Maintenance Resurfacing project, at Stones Crossing Rd from CR 500W to CR 600W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 04/13/2010 | 05/14/2010 | 96502.04 | 1.03
3873 | Indiana | WARRICK | EVANSVILLE (KY) | 08 | 0901281 | This is a trail project for pedestrians and bicycles on the Rivertown Trail Phase IIA at Old Lock and Dam to Belle Rive Drive in Newburgh in Warrick county using enhancement funds | Transportation Enhancements | 03/08/2010 | 03/15/2010 | 10/01/2010 | 870394.97 | 0.01
3874 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901283 | This is a Facilities for Pedestrians and Bicycles project, at 106th St from Penns Pkwy to Rangeline Rd/ College Ave fr I-465 to 105th St.; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 04/01/2010 |  | 08/31/2010 | 219450 | 2.18
3875 | Indiana | KOSCIUSKO |  | 03 | 0901284 | This is a Maintenance Resurfacing project, at Country Club Rd from Country Club Dr S to Hackleman St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 10/28/2009 | 08/01/2010 | 144895.43 | 0.99
3876 | Indiana | KOSCIUSKO |  | 03 | 0901285 | This is a Maintenance Resurfacing project, at Harrison St from Sheridan St to Dubois Dr.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 10/28/2009 | 08/01/2010 | 49582.91 | 0.32
3877 | Indiana | KOSCIUSKO |  | 03 | 0901286 | This is a Maintenance Resurfacing project, at Winona Ave from 200' E of Bronson St to McKinley St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 10/28/2009 | 08/01/2010 | 110450.99 | 0.72
3878 | Indiana | KOSCIUSKO |  | 03 | 0901287 | This is a Maintenance Resurfacing project, at Rozella Rd from Brookview Ave to SR 15; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/14/2009 | 10/28/2009 | 08/01/2010 | 53202.99 | 0.6
3879 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901288 | This is a Facilities for Pedestrians and Bicycles project, at Along 146th St from Cherry Tree Rd to River Rd.; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 04/01/2010 |  | 06/30/2010 | 139680.25 | 1.29
3880 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901289 | This is a Maintenance Resurfacing project, at 234th St from the Cicero Corp limits to Overdorf Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 07/30/2010 | 231896.38 | 1.78
3881 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901290 | This is a Maintenance Resurfacing project, at Olio Rd from 126th St to 136th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 05/12/2010 | 06/30/2010 | 274126.63 | 1
3882 | Indiana | ALLEN |  | 03 | 0901299 | This is a Maintenance Resurfacing project, at Carroll Road from US 33 to Hand Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 03/29/2010 | 08/21/2010 | 328987.49 | 4.35
3883 | Indiana | ALLEN |  | 03 | 0901300 | This is a Maintenance Resurfacing project, at Ferguson Rd from Bluffton Road to Winchester Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 03/29/2010 | 08/21/2010 | 168670.29 | 1.88
3884 | Indiana | ALLEN |  | 03 | 0901301 | This is a Maintenance Resurfacing project, at Yellow River Road from Hadley Road to O'Day Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 03/29/2010 | 08/21/2010 | 53412.55 | 0.62
3885 | Indiana | ALLEN |  | 03 | 0901302 | This is a Maintenance Resurfacing project, at O'Day Road from Yellow River Road to US 33; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 03/29/2010 | 08/21/2010 | 364136.36 | 4.81
3886 | Indiana | ALLEN |  | 03 | 0901303 | This is a Maintenance Resurfacing project, at Dawkins Road from Doyle Road to Main Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 03/29/2010 | 08/21/2010 | 1145781.91 | 9.07
3887 | Indiana | DELAWARE | MUNCIE | 06 | 0901313 | This project will extedn the life of the road by performing perventive maiantenance resurfacing on Albany St from Miller St to CR 50S in Delaware county. | Pavement Improvement | 03/11/2010 |  | 08/15/2010 | 52371 | 0.25
3888 | Indiana | DELAWARE | MUNCIE | 06 | 0901314 | This project will resurface the County Road 600W from SR 332 to Lone Beech Bridge in Delaware County. | Pavement Improvement | 04/13/2010 |  | 07/30/2010 | 333564.5 | 0.1
3889 | Indiana | DELAWARE | MUNCIE | 06 | 0901315 | This is a Maintenance Resurfacing project, at Old SR 67 (Fuson Rd) from SR 67 to Cowan Rd; to perform Partial 3-R work. | Pavement Improvement | 02/22/2010 |  | 08/15/2010 | 413942.07 | 1.8
3890 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901316 | This is a Maintenance Resurfacing project, at Hart Street from 81st Street N to US 30; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/19/2010 | 05/31/2010 | 579254.81 | 2.1
3891 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901317 | This is a Maintenance Resurfacing project, at Calumet Avenue from US 30 N to intersection of Main Street; to perform Surface Treatment work. | Pavement Improvement | 01/05/2010 | 04/19/2010 | 05/31/2010 | 17629.06 | 2.03
3892 | Indiana | HUNTINGTON |  | 05 | 0901323 | This project will improve sections and extend the life of County Road 900North from SR 9 to county road 600 east in Huntington County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/29/2009 | 06/12/2010 | 564063.47 | 7.14
3893 | Indiana | HUNTINGTON |  | 05 | 0901324 | This project will improve sections and extend the life of County Road 300West from county road 1200 south to county road 300 south in Huntington County with a pavement surface overlay. | Pavement Improvement | 09/15/2009 | 10/29/2009 | 06/12/2010 | 680700.92 | 9.01
3894 | Indiana | HUNTINGTON |  | 05 | 0901325 | This project will improve sections and extend the life of County Road 800North from county road 1000 west to SR 9 in Huntington County with a pavement surface overlay. | Pavement Improvement | 10/14/2009 | 10/28/2009 | 06/12/2010 | 657672 | 9.04
3895 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901336 | This is a Maintenance Resurfacing project, at Kern Road from York Road to Ironwood Road to; perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 02/22/2010 |  | 10/30/2010 | 97803.8 | 0.5
3896 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901337 | This is a Maintenance Resurfacing project, at Fir Road from Day Road to Brick Road (exluding intersections); to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 195575.51 | 2.7
3897 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901338 | This is a Maintenance Resurfacing project, at Miami Road from Roosevelt Road to 0.7 miles south of Orchard Heights Drive; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 52748.56 | 0.6
3898 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901339 | This is a Maintenance Resurfacing project, at Adams Road from Ironwood Road to Gumwood Road ;to perform Surface Treatment, Microsurface work. | Pavement Improvement | 03/01/2010 |  | 10/30/2010 | 217468.35 | 2
3899 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901340 | This is a Maintenance Resurfacing project, at Ironwood Road from Auten Road to State Line Road; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 | 05/20/2010 | 08/15/2010 | 127678.25 | 1
3900 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901341 | This is a Maintenance Resurfacing project, at Portage Road from 0.4 miles north of Bendix Drive to IN/MI State Line; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 259988.33 | 1.6
3901 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901342 | This is a Maintenance Resurfacing project, at Ireland Road from SR 23 to Locust Road; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 153261.06 | 2
3902 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901343 | This is a Maintenance Resurfacing project, at Brick Road from Gumwood Road to Fir Road; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 | 06/15/2010 | 10/30/2010 | 134892.94 | 1
3903 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901344 | This is a Maintenance Resurfacing project, at Ash Road from SR 933 to Elsie Avenue; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 199887.4 | 1.4
3904 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901345 | This is a Maintenance Resurfacing project, at Ironwood Road from Douglas Road to indiana Toll Road; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 84988.69 | 0.5
3905 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901346 | This is a Maintenance Resurfacing project, at Mayflower Road from the UAB, 0.3 miles north of Sumption Trail, to SR 23; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 33113.49 | 0.5
3906 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901347 | This is a Maintenance Resurfacing project, at Locust Road from Madison Road to Jackson Road to; perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 262227.2 | 2.9
3907 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901348 | This is a Maintenance Resurfacing project, at I-80 - Juniper Road from 0.3 miles north of Douglas Rd. to Cleveland Road; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 64125.26 | 0.7
3908 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901351 | This is a Maintenance Resurfacing project, at Beech Road from 0.5 miles S of Harrison road to .07 miles S of Adams St.; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 78529.76 | 0.5
3909 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901352 | This is a Maintenance Resurfacing project, at Grant Road from US 20/US31 By-Pass to Mayflower Road; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 60090.72 | 0.8
3910 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901353 | This is a Safety project, at County wide (urban areas only) sign replacement; to perform Safety Revisions work. | Safety/Traffic Management | 12/16/2009 | 02/12/2010 | 07/31/2010 | 171299.73 | 0.01
3911 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901354 | This project will improve roadway safety in the town of Osceola. | Safety/Traffic Management | 12/16/2009 | 02/12/2010 | 07/31/2010 | 36517.01 | 0.01
3912 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901355 | This is a Maintenance Resurfacing project, at Edison Road from Quince Road to Sundown Road; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 209393.94 | 2.1
3913 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901356 | This is a Maintenance Resurfacing project, at Township 23 North, Range 4 West; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 05/10/2010 | 06/30/2010 | 319191.83 | 1.57
3914 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901357 | This is a Maintenance Resurfacing project, at Beech Road from Ireland Road to 0.5 miles S of Harrison Road; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 03/01/2010 |  | 10/30/2010 | 44624.46 | 1
3915 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901358 | This is a Maintenance Resurfacing project, at Beech Road from SR 933 to .07 miles south of Adams Street; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 04/14/2010 | 08/15/2010 | 36104.42 | 0.26
3916 | Indiana | JAY |  | 06 | 0901362 | This is a Maintenance Resurfacing project, at CR 200 S from Blaine Pike to Boundry Pike; to perform Pavement, Other work. | Pavement Improvement | 10/13/2009 | 05/18/2010 | 07/30/2010 | 218336.18 | 2.08
3917 | Indiana | JAY |  | 06 | 0901365 | This is a Maintenance Resurfacing project, at CR 300 N from Pennville LIMITS TO US 27; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 06/18/2010 | 07/30/2010 | 771313.38 | 9.132
3918 | Indiana | JAY |  | 06 | 0901366 | This is a Maintenance Resurfacing project, at CR 400 S from CR 1150 W to SR 1; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/13/2009 | 05/18/2010 | 07/30/2010 | 262370.35 | 2.47
3919 | Indiana | JAY |  | 06 | 0901367 | This is a Maintenance Resurfacing project, at CR 1150 W from Dunkirk to CR 900 S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 07/13/2010 | 07/30/2010 | 341424.82 | 3.82
3920 | Indiana | JAY |  | 06 | 0901374 | This is a Maintenance Restoration & Rehabilitation project, at West Water Street from Western City Limit to US 27 (Meridian Street); to perform Patch And Rehab Bituminous Pavement work. | Pavement Improvement | 12/30/2009 |  | 06/28/2010 | 122489.15 | 1.5
3921 | Indiana | JAY |  | 06 | 0901375 | This is a Maintenance Restoration & Rehabilitation project, at W. High Street from N. Middle Street to US 27 (Meridian Street); to perform Patch And Rehab Bituminous Pavement work. | Pavement Improvement | 12/30/2009 |  | 06/28/2010 | 59967.54 | 0.37
3922 | Indiana | JAY |  | 06 | 0901379 | This project will patch and restore and overlay North Wayne St from SR 26 to East Votaw Street in Portland, Jay county to extend the life of the pavement. | Pavement Improvement | 12/30/2009 |  | 06/25/2010 | 48108.38 | 0.49
3923 | Indiana | RUSH |  | 06 | 0901384 | This is a Maintenance Resurfacing project, at CR 800 E from Glenwood to CR 250 N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/13/2009 | 11/04/2009 | 10/30/2009 | 126196.38 | 1.32
3924 | Indiana | RUSH |  | 06 | 0901386 | This is a Maintenance Resurfacing project, at CR 800 E from Orange Pike to Glenwood; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/13/2009 | 03/17/2010 | 07/30/2010 | 235660.1 | 2.67
3925 | Indiana | RUSH |  | 06 | 0901388 | This is a Maintenance Resurfacing project, at Fort Wayne from E. 3rd St to E. 11th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/13/2009 | 03/19/2010 | 06/25/2010 | 173432.25 | 0.9
3926 | Indiana | RUSH |  | 06 | 0901390 | This is a Maintenance Resurfacing project, at Conard-Harcourt Way from SR 3 to E. 11th Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 10/13/2009 | 03/19/2010 | 06/25/2010 | 172800.26 | 0.84
3927 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0901409 | This is a Maintenance Resurfacing project, at From 1.90 Miles West of SR 15 to SR 15; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 03/23/2010 |  | 08/13/2010 | 416461.5 | 1.87
3928 | Indiana | MIAMI, FULTON |  | 02,05 | 0901410 | This is a Maintenance Resurfacing project, at SR 19 - From US 24 to 0.25 miles S of SR 14 (South limits of Akron); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/15/2009 | 04/05/2010 | 10/08/2010 | 2060566.8 | 18.9
3929 | Indiana | NOBLE, ELKHART | ELKHART-GOSHEN | 03 | 0901411 | This is a Maintenance Resurfacing project, at From jct. US 33/SR 13 to 0.17 miles E of SR 5; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 03/23/2010 | 04/12/2010 | 07/31/2010 | 1000723.6 | 5.47
3930 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901416 | This is a Safety project, at Edwardsville-Galena Rd from Old Vincennes Rd to Country Trace Lane; to perform Pavement Markings work. | Safety/Traffic Management | 02/22/2010 | 04/16/2010 | 05/15/2010 | 67033.9 | 0.38
3931 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901418 | This is a Safety project, at Old Vincennes Rd from Partridge Place to Pebble Creek Dr; to perform Pavement Markings work. | Safety/Traffic Management | 02/22/2010 | 04/16/2010 | 05/15/2010 | 37535.3 | 0.84
3932 | Indiana | STARKE |  | 02 | 0901428 | This is a Facilities for Pedestrians and Bicycles project, at Former Erie RR right of way between North Judson and Town of Ora in Starke Co; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 04/01/2010 | 05/18/2010 | 10/15/2011 | 1028182.99 | 6.25
3933 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901439 | This is a Maintenance Resurfacing project, at Between CR 800 S & US 52; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/05/2010 | 03/18/2010 | 06/30/2010 | 148123.9 | 0.683
3934 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901441 | This is a Maintenance Resurfacing project, at Between CR 510 S & CR 430 S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 04/21/2010 | 05/29/2010 | 194622.29 | 0.867
3935 | Indiana | DE KALB |  | 03 | 0901449 | This is a Maintenance Resurfacing project, at Main St from Ensley Ave to North St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/23/2010 | 04/12/2010 | 08/15/2010 | 449968.35 | 0.95
3936 | Indiana | FOUNTAIN |  | 08 | 0901455 | This is a Facilities for Pedestrians and Bicycles project, at Covington Circle Trail - Ph II; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 02/24/2010 | 03/23/2010 | 07/10/2010 | 718659 | 3.1
3937 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901458 | This is a Maintenance Resurfacing project, at From Union Township line to Old US 231; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/16/2009 | 04/21/2010 | 05/29/2010 | 137332.84 | 1.02
3938 | Indiana | PULASKI |  | 02 | 0901465 | This is a trail project on an abandoned RR right of way for pedestrians and bicycles at rail banked corridor along US 35 between Star City and north of Royal Center in Cass/Pulaski Co's using enhancem | Transportation Enhancements | 12/31/2009 | 03/15/2010 | 11/19/2010 | 2263793 | 15.69
3939 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0901466 | This is a Maintenance Resurfacing project, at Beverly Drive from Eaton Avenue to US 12 (Mt. Baldy); to perform Surface Treatment work. | Pavement Improvement | 01/08/2010 | 04/01/2010 | 06/01/2010 | 271350.65 | 3.73
3940 | Indiana | GRANT |  | 05 | 0901468 | This is a preventive maintenance resurfacing project, on North "D" Street from 1st to 10th Streetin Gas City, Grant county to extend the service llife of the pavement. | Pavement Improvement | 04/01/2010 | 05/11/2010 | 06/26/2010 | 229014.71 | 1.01
3941 | Indiana | GRANT |  | 05 | 0901469 | This is a Maintenance Resurfacing project, at 5th Street from South "H" Street to North "D" Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 05/11/2010 | 06/26/2010 | 187492.59 | 0.78
3942 | Indiana | GRANT |  | 05 | 0901470 | This is a Maintenance Resurfacing project, at South "D" Street from 1st to 3rd Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 05/11/2010 | 06/26/2010 | 45567.92 | 0.21
3943 | Indiana | GRANT |  | 05 | 0901471 | This is a preventive maintenance resurfacing project, at 3rd Street from South "H" Street to SR 22 in Gas City, Grant county. | Pavement Improvement | 04/01/2010 | 05/11/2010 | 06/26/2010 | 133434.1 | 0.51
3944 | Indiana | GRANT |  | 05 | 0901472 | This is a Maintenance Resurfacing project, at 7th Street from SR 22 to North "D" Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 05/11/2010 | 06/26/2010 | 48849.7 | 0.25
3945 | Indiana | DE KALB |  | 03 | 0901473 | This is a trail project for pedestrians and bicycles on the over 6500 feet of side walks on Ralph Sechler Dr., Spencer St, School St, Hart St and other streets in the town of St Joe, and is Phase 3 of | Transportation Enhancements | 01/06/2010 | 03/01/2010 | 08/15/2010 | 313344.36 | 0.36
3946 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0901480 | This is a Facilities for Pedestrians and Bicycles project, at New York Street from 9th St to 12th Street in Elkhart, Elkart county. This 1 of 3 projects top provide pedestrian facilities under contrac | Transportation Enhancements | 11/30/2009 | 04/26/2010 | 06/19/2010 | 42812.57 | 0.23
3947 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0901481 | This is a Facilities for Pedestrians and Bicycles project, at 11th St from New York Ave to East Burdick St in Elkhart, Elkhart county. This 1 of 3 projects to provide pedestrian facilites under contra | Transportation Enhancements | 11/30/2009 | 04/26/2010 | 06/19/2010 | 37792.17 | 0.14
3948 | Indiana | ADAMS |  | 06 | 0901482 | This is a preventive maintenance resurfacing project, at Piqua Rd from East of Monroe St to CR 700E (State Line) in Adams county; to perform asphalt resurface, Preventive Maintenance work. This 1 of | Pavement Improvement | 04/13/2010 |  | 08/14/2010 | 598945.33 | 7.07
3949 | Indiana | ADAMS |  | 06 | 0901483 | This is a pavement preventive maintenance resurfacing project, at CR 1200 S from CR 500 E to CR 700 E (State Line) in Adams county to perform Chip Seal work that will extend the life of the road. This | Pavement Improvement | 04/13/2010 |  | 08/14/2010 | 39410.22 | 1.93
3950 | Indiana | ADAMS |  | 06 | 0901484 | This is a preventive maintenance resurfacing project, at CR 100 E (High St ) from north of US 33 to north of abandoned RR (City Limits) in Adams county to perform asphalt resurface to extend the lif | Pavement Improvement | 04/13/2010 |  | 08/14/2010 | 92446.35 | 1.04
3951 | Indiana | ADAMS |  | 06 | 0901485 | This is a preventive maintenance resurfacing project, at CR 500 E (Old SR 116) from CR 1200 South to CR 1100 South to perform Chip Seal work to extend the life of the pavement. This 1 of 5 proejcts | Pavement Improvement | 04/13/2010 |  | 08/14/2010 | 21866.55 | 1.05
3952 | Indiana | ADAMS |  | 06 | 0901486 | This is a preventive maintenance resurfacing project, on County Road 1050/1100 from south of Hale St (Town Limits) to County Road 500East in Adams county to perform, Chip Seal work to extend the life | Pavement Improvement | 04/13/2010 |  | 08/14/2010 | 124734.75 | 6.2
3953 | Indiana | WAYNE |  | 06 | 0901487 | This is a Maintenance Resurfacing project,at Centerville Rd from 900 feet S of Temple Dr,N 3.38 miles to the S ramp to I-70 ;to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/18/2009 | 03/25/2010 | 06/11/2010 | 1011110.45 | 3.41
3954 | Indiana | DE KALB |  | 03 | 0901494 | This is a Maintenance Resurfacing project, at Quincy Street from N. Peters St to N. 2nd St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 05/18/2010 | 06/30/2010 | 171935.7 | 0.7
3955 | Indiana | DE KALB |  | 03 | 0901495 | This project will extend the pavement life with a preventive maintenance resurfacing project on South Rd from N. 2nd St to 0.1 mile E of Taylor Rd. in Garrett, Dekalb county. | Pavement Improvement | 04/01/2010 | 05/18/2010 | 06/30/2010 | 74456 | 0.56
3956 | Indiana | ALLEN |  | 03 | 0901496 | This is a Maintenance Resurfacing project, at Woodburn Road from Hetrick Road to State Road 101 (Main St.) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/06/2010 |  | 10/30/2010 | 157574.85 | 0.5
3957 | Indiana | ALLEN |  | 03 | 0901497 | This is a Maintenance Resurfacing project, at Woodburn Road from State Road 101 (Fahlsing Rd.) to Brobst Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/06/2010 |  | 10/30/2010 | 56120.75 | 0.5
3958 | Indiana | ALLEN |  | 03 | 0901498 | This is a Maintenance Resurfacing project, at Bull Rapids Rd from SR 101 (Main St.) to 0.33 mile N of Ash St (City limits) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/06/2010 |  | 10/30/2010 | 100975.18 | 0.7
3959 | Indiana | HANCOCK | INDIANAPOLIS | 05 | 0901502 | This is a Maintenance Resurfacing project, at CR 300 N from CR 300 W to CR 200 W, 0.50 miles N of I-70; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 10/01/2010 | 94439.29 | 1
3960 | Indiana | HANCOCK | INDIANAPOLIS | 05 | 0901503 | This is a Maintenance Resurfacing project, at CR 300 N from CR 400 W to CR 300 W, 0.5 miles N of I-70; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 10/01/2010 | 92327.76 | 1
3961 | Indiana | LA PORTE | MICHIGAN CITY | 02 | 0901505 | This is a Preventive Maintenance Resurfacing project, at Coolspring Avenue from Roeske Avenue (Michigan City Corp Limit) to Johnson Road in Laprot county to extend the life of the pavement.. | Pavement Improvement | 02/24/2010 | 04/15/2010 | 07/01/2010 | 329390.4 | 0.6
3962 | Indiana | MONROE | BLOOMINGTON | 09 | 0901506 | This is a Maintenance Resurfacing project, at S. Walnut St from Wylie to Country Club to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 | 03/12/2010 | 06/26/2010 | 707045.75 | 1.69
3963 | Indiana | MADISON | ANDERSON | 06 | 0901517 | This is a Maintenance Resurfacing project, at Pendleton Ave from High St to Reformatory Rd; to perform Surface Treatment work. | Pavement Improvement | 12/31/2009 |  | 07/30/2010 | 142600 | 0.76
3964 | Indiana | MADISON | ANDERSON | 08 | 0901518 | This is a Maintenance Resurfacing project, at Harrison St from 3rd St to Norfolk Southern RR crossing; to perform Surface Treatment work. | Pavement Improvement | 01/06/2010 |  | 06/30/2010 | 200150 | 0.92
3965 | Indiana | MADISON | ANDERSON | 06 | 0901519 | This is a Maintenance Resurfacing project, at CR 50 W from SR 38 to Anderson C L; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 10/01/2010 | 281629.13 | 4.1
3966 | Indiana | MADISON | ANDERSON | 06 | 0901521 | This is a Maintenance Resurfacing project, at CR 100 W from SR 128 to CR 1100 N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 10/01/2010 | 221297.08 | 3.1
3967 | Indiana | MADISON | ANDERSON | 06 | 0901522 | This is a Maintenance Resurfacing project, at CR 1100 N from SR 9 to CR 100 E; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 10/01/2010 | 56177.6 | 1.1
3968 | Indiana | MADISON | ANDERSON | 06 | 0901523 | This is a Maintenance Resurfacing project, at CR 1100 N from CR 200 W to CR 100 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 10/01/2010 | 83358 | 1.1
3969 | Indiana | MADISON | ANDERSON | 06 | 0901524 | This is a Maintenance Resurfacing project, at New Columbus Ave from CR 600S to CR 400S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 10/01/2010 | 169100.19 | 2.1
3970 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901529 | This is a Maintenance Resurfacing project, at Cumberland Rd from Field Dr to Allisonville Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 06/30/2010 | 140643.69 | 0.97
3971 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901530 | This is a Maintenance Resurfacing project, at Boden Rd between SR 38 and Greenfield Ave to; perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 07/31/2010 | 157126.25 | 2.08
3972 | Indiana | HAMILTON | INDIANAPOLIS | 05 | 0901531 | This is a Maintenance Resurfacing project, at Little Chicago Rd between SR 38 and Carrigan Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 07/31/2010 | 219004 | 1.65
3973 | Indiana | NOBLE |  | 03 | 0901533 | This is a Maintenance Resurfacing project, at Diamond St from Main St to Sherman St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/21/2010 | 08/31/2010 | 236868.67 | 0.61
3974 | Indiana | NOBLE |  | 03 | 0901535 | This is a Maintenance Resurfacing project, at Mitchell St from Weston Ave to Orchard St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/21/2010 | 08/31/2010 | 104251.51 | 0.47
3975 | Indiana | NOBLE |  | 03 | 0901538 | This is a Maintenance Resurfacing project, at Iddings St from Main St to Town St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/21/2010 | 08/31/2010 | 42310.1 | 0.28
3976 | Indiana | MONROE | BLOOMINGTON | 09 | 0901540 | This is a Maintenance Resurfacing project, at Business SR 37 from Old SR 37 North; to SR 37 to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 | 05/07/2010 | 07/30/2010 | 359234.4 | 1.764
3977 | Indiana | NOBLE |  | 03 | 0901542 | This is a Maintenance Resurfacing project, at Fair St from Wayne St to US 6; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/21/2010 | 08/31/2010 | 69979.72 | 0.28
3978 | Indiana | CLARK | LOUISVILLE (KY)-IN | 09 | 0901547 | This is a Maintenance Resurfacing project, at Old SR 62 - Brown Station Way from Randolph Avenue to Silver Creek; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 03/30/2010 | 06/30/2010 | 627143 | 1.8
3979 | Indiana | NOBLE |  | 03 | 0901551 | This is a Maintenance Resurfacing project, at Main St from High St to US 6 to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/21/2010 | 08/31/2010 | 9602.4 | 0.07
3980 | Indiana | ALLEN | FORT WAYNE | 03 | 0901552 | This is a Maintenance Resurfacing project, at Hartzell Rd from RR tracks (approx. 1600' south of Rose Ave) to Rose Ave; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 06/03/2010 | 07/30/2010 | 36964.34 | 0.3
3981 | Indiana | ALLEN | FORT WAYNE | 03 | 0901553 | This is a Maintenance Resurfacing project, at Rose Ave; from Green St. to Linden Rd to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 06/03/2010 | 07/30/2010 | 45610.65 | 0.61
3982 | Indiana | ALLEN | FORT WAYNE | 03 | 0901554 | This is a Maintenance Resurfacing project, at Landin Rd from N River Rd to Maysville Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 06/03/2010 | 07/30/2010 | 272228.08 | 1.89
3983 | Indiana | ALLEN | FORT WAYNE | 03 | 0901555 | This is a Maintenance Resurfacing project, at New Haven Ave from Meyer Rd to SR 930; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 06/03/2010 | 07/30/2010 | 89825.99 | 0.73
3984 | Indiana | ALLEN | FORT WAYNE | 03 | 0901556 | This is a Maintenance Resurfacing project, at Rose Ave from Hartzell Rd to Landin Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 06/03/2010 | 07/30/2010 | 55547.51 | 0.58
3985 | Indiana | ALLEN | FORT WAYNE | 03 | 0901557 | This is a preventive maintenance resurfacing project on Minnich Rd from Seiler Rd to SR 930 in Fort wayne , Allen county to extend the service life of the road. | Pavement Improvement | 11/23/2009 | 05/26/2010 | 06/26/2010 | 166342.1 | 1.15
3986 | Indiana | ALLEN | FORT WAYNE | 03 | 0901558 | This is a Maintenance Resurfacing project, at Summit St from Bensman Ave to Linden Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 06/03/2010 | 07/30/2010 | 59087.48 | 0.48
3987 | Indiana | ALLEN | FORT WAYNE | 03 | 0901559 | This is a Maintenance Resurfacing project, at Lincoln Hwy from 365' E of Green St; to City Limits (1320' W of Doyle St) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 06/03/2010 | 07/30/2010 | 120619.5 | 1.1
3988 | Indiana | HENDRICKS | INDIANAPOLIS | 04 | 0901561 | This project will resurface the County Road 100N from Richfield Drive to Kinross Drive in Hendricks County. | Pavement Improvement | 04/10/2010 | 05/05/2010 | 07/30/2010 | 215983.5 | 1.5
3989 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901563 | This project is a preventive maintenance resurfacing project, on Old US Hwy 231 - From County Road 500 South to County Road 350 South in Tippecanoe county to extend the life of the pavement. | Pavement Improvement | 12/16/2009 | 04/21/2010 | 05/29/2010 | 238671.89 | 1.443
3990 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901571 | This is a Maintenance Resurfacing project, at 45th Street from State Line east to Highland Line; to perform Surface Treatment work. | Pavement Improvement | 12/16/2009 | 04/06/2010 | 06/01/2010 | 559573.26 | 2.4
3991 | Indiana | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0901600 | This is a Maintenance Resurfacing project, at Schultz Road from CR 600W to CR 400W; to perform Surface Treatment work. | Pavement Improvement | 11/23/2009 | 11/24/2009 | 12/01/2009 | 287065.77 | 2.12
3992 | Indiana | LA PORTE | MICHIGAN CITY | 02 | 0901619 | This proejct replaces and repairs storm sewers, at Michigan Blvd from US 12 to Carroll Avenue in Michigan City, LaPorte county to correct and improve drainage of the road. | Other | 05/05/2010 | 06/18/2010 | 09/01/2010 | 1735143.59 | 1.86
3993 | Indiana | CRAWFORD |  | 09 | 0901627 | This is a Maintenance Resurfacing project, at SR 164 to SR 56; to perform Surface Treatment, Ultrathin Bonded Wearing Course work. | Pavement Improvement | 04/09/2010 | 06/07/2010 | 07/31/2010 | 1838564.73 | 13.67
3994 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901628 | This is a Maintenance Resurfacing project, at From US 52 to SR 38; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/05/2010 | 03/19/2010 | 06/30/2010 | 269162.73 | 0.696
3995 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901629 | This is a Maintenance Resurfacing project, at Between SR 26 and US 52; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 04/20/2010 | 07/31/2010 | 1359216 | 1.62
3996 | Indiana | ALLEN | FORT WAYNE | 03 | 0901631 | This is a Maintenance Resurfacing project, at Aboite Center Rd from West Hamilton Rd to Homestead Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 06/26/2010 | 117466.77 | 1.26
3997 | Indiana | ALLEN | FORT WAYNE | 03 | 0901632 | This is a Maintenance Resurfacing project, at Bass Road from W Co Ln Road to Scott Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 06/26/2010 | 230737.53 | 3.26
3998 | Indiana | ALLEN | FORT WAYNE | 03 | 0901633 | This is a preventive maintenance resurfacing project on Covington Road from West County Line Road to Braemar Drivein Allen county to extend the service life of the pavement. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 06/26/2010 | 234296.18 | 1.87
3999 | Indiana | ALLEN | FORT WAYNE | 03 | 0901634 | This is a Maintenance Resurfacing project, at West Hamilton Road frm US 24 to Bass Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 06/26/2010 | 570440.24 | 5.63
4000 | Indiana | ALLEN | FORT WAYNE | 03 | 0901635 | This is a Maintenance Resurfacing project, at Leesburg Road from Kroemer Road to Beineke Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 04/01/2010 | 06/26/2010 | 69613.18 | 1.02
4001 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901636 | This project will improve the traffic signs in the town of Indian Village. | Safety/Traffic Management | 12/16/2009 | 02/12/2010 | 07/31/2010 | 3169.67 | 0.01
4002 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901637 | This project will improve the traffic signs in the town of Roseland. | Safety/Traffic Management | 12/16/2009 | 02/12/2010 | 07/31/2010 | 23814.19 | 0.01
4003 | Indiana | MARION | INDIANAPOLIS | 07 | 0901648 | This is a Maintenance Resurfacing project, at US 36 - From Pendleton Pike to 79th St; to perform Pavement, Other work. | Pavement Improvement | 04/01/2010 |  | 08/13/2010 | 268699.99 | 2.32
4004 | Indiana | MARION | INDIANAPOLIS | 05 | 0901649 | This is a Maintenance Resurfacing project, at Carroll Rd. from 75th St. to 79th St.; to perform Pavement, Other work. | Pavement Improvement | 01/13/2010 |  | 07/10/2010 | 199647.76 | 0.5
4005 | Indiana | DEARBORN | CINCINNATI | 09 | 0901652 | This is a Maintenance Resurfacing project, at Nowlin Avenue from Rand Aven. to Meadowcreek Drive; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 04/02/2010 | 06/25/2010 | 139653.6 | 0.01
4006 | Indiana | HENDRICKS |  | 04 | 0901655 | This is a Facilities for Pedestrians and Bicycles project, at From SR 267 to CR 300 N and from Ronald Reagan Pkwy; to Raceway Rd to perform Enhancement work. | Transportation Enhancements | 04/13/2010 | 04/26/2010 | 11/15/2010 | 3334104.27 | 0.01
4007 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901656 | This is a Maintenance Resurfacing project, at Liverpool Road from New Jersey Street to Deep River; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 01/19/2010 | 05/10/2010 | 09/15/2010 | 464343.79 | 0.23
4008 | Indiana | MIAMI, FULTON |  | 02,05 | 0901663 | This project will build a trail for pedestrians and bicycles on Nickel Plate Trail: from Lovers Lane north of Peru im Miami county to Wabash Road in Rochester in Fulton County. | Transportation Enhancements | 02/22/2010 | 03/19/2010 | 10/15/2010 | 4413712.7 | 17
4009 | Indiana | MONROE | BLOOMINGTON | 09 | 0901685 | This project builds new sidewalks in 17 locations in Bloomington, Monroe county using enhancement funds. | Other | 02/22/2010 | 03/15/2010 | 05/14/2010 | 324415 | 1.2
4010 | Indiana | JEFFERSON |  | 09 | 0901686 | This is a Landscaping project, at Madison Riverfront Dev-Phase 2: Bankstab, Scenic, Docking; to perform Landscaping work. | Transportation Enhancements | 02/18/2010 | 03/16/2010 | 12/15/2010 | 915468.75 | 0.01
4011 | Indiana | ELKHART |  | 03 | 0901687 | This is a trail project for pedestrians and bicycles project on the Pumpkinvine Trail and is Phase 5C located from 1300' south of CR 22 to US 20 in Elkhart county using enhancement funds. | Transportation Enhancements | 03/04/2010 | 04/05/2010 | 08/20/2010 | 1088731.18 | 0.04
4012 | Indiana | MARION | INDIANAPOLIS | 07 | 0901689 | This is a Maintenance Resurfacing project, at 34th St from Arlington Avenue to Shadeland Avenue; to perform Partial 3-R work. | Pavement Improvement | 04/07/2010 |  | 10/31/2010 | 408277.59 | 1
4013 | Indiana | MARION | INDIANAPOLIS | 05 | 0901690 | This is a Maintenance Resurfacing project, at Davis Rd from Vandergriff Rd to Troy Ave; to perform Partial 3-R work. | Pavement Improvement | 04/01/2010 |  | 11/01/2010 | 191427.53 | 0.7
4014 | Indiana | MARION | INDIANAPOLIS | 05,07 | 0901691 | This is a Maintenance Resurfacing project, at Edgewood Ave from Shelbyville Rd to Five Points Rd; to perform Partial 3-R work. | Pavement Improvement | 04/01/2010 |  | 11/01/2010 | 583175.71 | 1.3
4015 | Indiana | MARION | INDIANAPOLIS | 05,07 | 0901692 | This is a Maintenance Resurfacing project, at Five Points Rd from Shelbyville Rd to Southeastern Ave; to perform Partial 3-R work. | Pavement Improvement | 04/01/2010 |  | 11/01/2010 | 547726.16 | 4.3
4016 | Indiana | MARION | INDIANAPOLIS | 07 | 0901693 | This proejct will place muliple lays of asphalt to increase strength and extend the life of the pavement on Harding St from Morris St to Oliver Ave in Marion county. | Pavement Improvement | 04/07/2010 | 07/09/2010 | 08/02/2010 | 332158.38 | 0.5
4017 | Indiana | MARION | INDIANAPOLIS | 04 | 0901694 | This project rebuilds the pavement with multi-lays of asphalt on Lafayette Rd from 71st St to County Line Rd in Indianapolis, Marion county. | Pavement Improvement | 04/10/2010 | 05/11/2010 | 09/11/2010 | 1930481.6 | 3.6
4018 | Indiana | MARION | INDIANAPOLIS | 07 | 0901695 | This is a Maintenance Resurfacing project, at Morris St from Lynhurst Dr to Westbrook Ave; to perform Partial 3-R work. | Pavement Improvement | 04/01/2010 |  | 07/01/2010 | 210149 | 0.5
4019 | Indiana | MARION | INDIANAPOLIS | 05 | 0901697 | This is a Maintenance Resurfacing project, at Senour St from Thompson Rd to Troy Ave; to perform Partial 3-R work. | Pavement Improvement | 04/01/2010 |  | 11/01/2010 | 242614.61 | 2
4020 | Indiana | MARION | INDIANAPOLIS | 07 | 0901712 | This is a Bridge Rehabilitation (no added capacity) project, at Mann Rd over Dollar Hide Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 04/01/2010 | 05/17/2010 | 10/31/2010 | 276920.99 | 0.1
4021 | Indiana | MARION | INDIANAPOLIS | 07 | 0901713 | This is a Bridge Rehabilitation (no added capacity) project, at Emerson Avenue over Brookside Creek; to perform Bridge Rehabilitation Or Repair work. | Bridge Improvement | 04/01/2010 | 05/17/2010 | 10/31/2010 | 264201.27 | 0.1
4022 | Indiana | MARION | INDIANAPOLIS | 04 | 0901714 | This is a Bridge Rehabilitation (no added capacity) project, at Country Club Rd over Cox Ditch; to perform Bridge Deck Overlay work. | Bridge Improvement | 04/01/2010 | 04/12/2010 | 10/31/2010 | 248146.66 | 0.1
4023 | Indiana | MARION | INDIANAPOLIS | 04 | 0901716 | This is a Bridge Rehabilitation (no added capacity) project, at Bridgeport Rd over White Lick Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 04/01/2010 | 04/12/2010 | 10/31/2010 | 247883.69 | 0.1
4024 | Indiana | MARION | INDIANAPOLIS | 04 | 0901717 | This is a Bridge Rehabilitation (no added capacity) project, at Bridgeport Rd over Salem Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 04/01/2010 | 04/12/2010 | 10/31/2010 | 152878.34 | 0.1
4025 | Indiana | MARION | INDIANAPOLIS | 04 | 0901718 | This is a Bridge Rehabilitation (no added capacity) project, at Bridgeport Rd over Shiloh Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 04/01/2010 | 04/12/2010 | 10/31/2010 | 103559.57 | 0.1
4026 | Indiana | ALLEN | FORT WAYNE | 03 | 0901722 | This is a Maintenance Resurfacing project, at Liberty Mills Road frm W Co Ln Road to Amber Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/31/2010 | 08/14/2010 | 216179.98 | 1.79
4027 | Indiana | ALLEN | FORT WAYNE | 06 | 0901723 | This is a Maintenance Resurfacing project, at Muldoon Road frm Ferguson Road to Winchester Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/31/2010 | 08/14/2010 | 99462.66 | 1.32
4028 | Indiana | ALLEN | FORT WAYNE | 03 | 0901724 | This is a Maintenance Resurfacing project, at Smith Road from Airport Expressway to 120 feet N of Knoll Road (N&S Railroad); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/31/2010 | 08/14/2010 | 182986.38 | 2.41
4029 | Indiana | ALLEN | FORT WAYNE | 03 | 0901725 | This is a Maintenance Resurfacing project, at Wallen Road frm Huguenard Road to Hanauer Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/31/2010 | 08/14/2010 | 64261.09 | 0.93
4030 | Indiana | ALLEN | FORT WAYNE | 03 | 0901726 | This is a Maintenance Resurfacing project, at Washington Center Road frm O'Day Road to Kroemer Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/31/2010 | 08/14/2010 | 137575.49 | 1.79
4031 | Indiana | ALLEN | FORT WAYNE | 06 | 0901727 | This is a Maintenance Resurfacing project, at Winchester Road frm Ferguson Road to Lower Huntington Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/31/2010 | 08/14/2010 | 155975.24 | 1.97
4032 | Indiana | ALLEN | FORT WAYNE | 03 | 0901728 | This is a Maintenance Resurfacing project, at Yohne Road frm Branstrator Rd to Smith Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 11/23/2009 | 03/31/2010 | 08/14/2010 | 181322.14 | 2.53
4033 | Indiana | MARION | INDIANAPOLIS | 07 | 0901731 | This is a Bridge Rehabilitation (no added capacity) project, at 56th St over Indian Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 04/01/2010 | 05/17/2010 | 10/31/2010 | 182156.01 | 0.1
4034 | Indiana | MARION | INDIANAPOLIS | 07 | 0901733 | This is a Bridge Rehabilitation (no added capacity) project, at Mann Road over Mann Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 04/01/2010 | 05/17/2010 | 10/31/2010 | 237870.92 | 0.1
4035 | Indiana | ADAMS |  | 06 | 0901734 | This is a Special Bridge project, on the CF&E Railroad over the St Marys River in Adams County, to replace a steel girder to provide an improved rail line for economic development to an industrial are | Bridge Improvement | 03/05/2010 | 03/23/2010 | 08/28/2010 | 2535947.75 | 0.05
4036 | Indiana | MADISON | ANDERSON | 06 | 0901738 | This is a preventive maintenance resurfacing project on West 38th St from Raible Ave to Oakwood Blvd in Anderson, in Madison county to extend the service life of the road. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 128458.58 | 0.4
4037 | Indiana | MADISON | ANDERSON | 06 | 0901739 | This is a Maintenance Resurfacing project, at W 25th St from Raible Ave to Park Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 72248.85 | 1
4038 | Indiana | MADISON | ANDERSON | 06 | 0901740 | This is a Maintenance Resurfacing project, at Raible Ave from W 38th St to W 30th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 97332.64 | 0.7
4039 | Indiana | MADISON | ANDERSON | 06 | 0901741 | This is a Maintenance Resurfacing project, at Park Rd from W 53rd St to W 25th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 174964.32 | 2
4040 | Indiana | MADISON | ANDERSON | 06 | 0901742 | This is a Maintenance Resurfacing project, at Main St from 53rd St to 65th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 69697.33 | 1
4041 | Indiana | MADISON | ANDERSON | 06 | 0901743 | This is a Maintenance Resurfacing project, at Lindberg Rd from Alexandria Pike to Rangeline Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 176131.43 | 2.02
4042 | Indiana | MADISON | ANDERSON | 06 | 0901744 | This is a Maintenance Resurfacing project, at E 38th St from SR 9/Scatterfield Rd to Rangeline Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 70076.86 | 1
4043 | Indiana | MADISON | ANDERSON | 06 | 0901745 | This is a Maintenance Resurfacing project, at Cross St from SR 9/Scatterfield Rd to Rangeline Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 120762.71 | 1.4
4044 | Indiana | MADISON | ANDERSON | 06 | 0901746 | This is a Maintenance Resurfacing project, at Columbus Ave from 53rd St to 67th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 97353.17 | 1.1
4045 | Indiana | MADISON | ANDERSON | 06 | 0901747 | This is a Maintenance Resurfacing project, at Alexandria Pike from University Blvd. to SR 9/Scatterfield Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 144770.45 | 1.8
4046 | Indiana | MADISON | ANDERSON | 06 | 0901748 | This is a Maintenance Resurfacing project, at W 53rd St from CSX Railroad Crossing to Layton Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 |  | 10/01/2010 | 127703.66 | 1.6
4047 | Indiana | FLOYD |  | 09 | 0901750 | This is a Maintenance Resurfacing project, at Scottsville Rd from Martin Road to the Clark County line; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 04/23/2010 | 05/05/2010 | 368400 | 4.33
4048 | Indiana | ADAMS |  | 06 | 0901754 | This is a part of a special project, at the CF&E Railroad crossing on US 27, south of Adams St in Adams county to improve an old railroad crossing to imporve the rail line for an idustiral area. T | Bridge Improvement | 03/05/2010 | 03/23/2010 | 08/28/2010 | 110127.25 | 0.02
4049 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901756 | This is a Safety project, at Approx 70 signalized intersections within Lafayette; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 12/31/2009 | 02/18/2010 | 07/31/2010 | 610929.22 | 0.1
4050 | Indiana | RIPLEY |  | 09 | 0901757 | This is a Bridge Rehabilitation (no added capacity) project, at SR 48 - SR 48 over Laughery Creek, 1.70 miles E of SR 229; to perform Bridge Deck Replacement work. | Bridge Improvement | 12/30/2009 | 03/15/2010 | 09/17/2010 | 523689.1 | 0.01
4051 | Indiana | ALLEN | FORT WAYNE | 03 | 0901776 | This is a Facilities for Pedestrians and Bicycles project, at Covington Rd Trail: from Sycamore Hills Dr to Scott Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 01/06/2010 | 03/18/2010 | 08/14/2010 | 526956.1 | 0.6
4052 | Indiana | GRANT |  | 03 | 0901777 | This is a trail construction project, for the Cardinal Greenway Trail: from Troy Ave to CR 400 Wrian Facilities work in th city of Marion in Grant county using enhancement funds | Transportation Enhancements | 01/06/2010 | 04/27/2010 | 09/01/2010 | 426913.5 | 2
4053 | Indiana | RANDOLPH |  | 06 | 0901781 | This is a Maintenance Resurfacing project, at From the Little Mississinewa River to the Ohio State Line; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 04/07/2010 |  | 08/14/2010 | 157759.01 | 0.92
4054 | Indiana | ALLEN | FORT WAYNE | 03 | 0901783 | This is a Facilities for Pedestrians and Bicycles project, at Covington Rd Trail: from Eggeman Rd to Sycamore Hills Dr; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 02/22/2010 | 03/18/2010 | 08/14/2010 | 571950.6 | 0.45
4055 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901785 | This is a Maintenance Resurfacing project, at Vermillion Drive/127th Street from Cline Avenue E to Fairbanks Avenue; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 01/11/2010 |  | 06/30/2010 | 251128.26 | 0.84
4056 | Indiana | ALLEN | FORT WAYNE | 03 | 0901786 | This is a Maintenance Resurfacing project, at W Jefferson Blvd from 725' SW of Lutheran Hospital Ent. to 500'. NE of Illinois; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/08/2010 | 03/29/2010 | 06/26/2010 | 993909.84 | 3.95
4057 | Indiana | ALLEN | FORT WAYNE | 03 | 0901787 | This is a Maintenance Resurfacing project, at Wayne St from Broadway to Coombs St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 | 03/29/2010 | 05/27/2010 | 388452.81 | 1.34
4058 | Indiana | ALLEN | FORT WAYNE | 03 | 0901788 | This is a Maintenance Resurfacing project, at Berry St from Broadway to Coombs St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 | 03/29/2010 | 05/27/2010 | 344029.58 | 1.35
4059 | Indiana | ALLEN | FORT WAYNE | 03 | 0901789 | This is a Maintenance Resurfacing project, at Washington Blvd from Broadway to Clay St to; perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 | 03/29/2010 | 05/27/2010 | 226716.37 | 0.82
4060 | Indiana | ALLEN | FORT WAYNE | 03 | 0901790 | This is a Maintenance Resurfacing project, at Jefferson Blvd from Calhoun St to Clay St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 | 03/29/2010 | 05/27/2010 | 92395.17 | 0.33
4061 | Indiana | WAYNE |  | 06 | 0901793 | This is a trail project on the Cardinal Greenway & Main St, Randolph, Losantville, IN- Cardinal & Davis Meyersin Wayne county using enhancement funds. | Transportation Enhancements | 04/06/2010 |  | 04/15/2011 | 1712258.77 | 0.01
4062 | Indiana | WAYNE |  | 06 | 0901795 | This is a Facilities for Pedestrians and Bicycles project, at Cardinal Greenway & Martindale Creek, Wayne County, Economy IN; to perform Enhancement work. | Transportation Enhancements | 02/22/2010 |  | 09/30/2010 | 323246.65 | 0.01
4063 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901796 | This is a Maintenance Resurfacing project, at Randolph Street from 109th Avenue to 101st Avenue; to perform Surface Treatment work. | Pavement Improvement | 01/27/2010 |  | 06/01/2010 | 52157.06 | 1
4064 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901797 | This is a Maintenance Resurfacing project, at 109th Avenue from Colorado Street to Randolph Street; to perform Surface Treatment work. | Pavement Improvement | 01/27/2010 |  | 06/01/2010 | 43702.15 | 3
4065 | Indiana | MONROE | BLOOMINGTON | 09 | 0901808 | This is a Safety project, at Intersection of 4th St and College Ave; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 03/23/2010 | 04/14/2010 | 08/15/2010 | 205727.96 | 0.01
4066 | Indiana | MONROE | BLOOMINGTON | 09 | 0901809 | This is a Safety project, at Intersection of 4th St and Walnut St; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 03/23/2010 | 04/14/2010 | 08/15/2010 | 180669.42 | 0.01
4067 | Indiana | ALLEN | FORT WAYNE | 03 | 0901810 | This is a Maintenance Resurfacing project, at Diebold Rd from Clinton St to SR 1; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/21/2010 | 59876.24 | 0.65
4068 | Indiana | ALLEN | FORT WAYNE | 03 | 0901811 | This is a Maintenance Resurfacing project, at Hosler Rd frm Tonkel Rd to Halter Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 05/12/2010 | 08/21/2010 | 230827.03 | 2.2
4069 | Indiana | ALLEN | FORT WAYNE | 03 | 0901812 | This is a Maintenance Resurfacing project, at Hursh Rd frm Auburn Rd to Tonkel Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/21/2010 | 149410.35 | 1.78
4070 | Indiana | ALLEN | FORT WAYNE | 03 | 0901813 | This is a Maintenance Resurfacing project, at Union Chapel Rd frm Corbin Rd to Coldwater Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/21/2010 | 83395.37 | 0.5
4071 | Indiana | ALLEN | FORT WAYNE | 03 | 0901814 | This is a Maintenance Resurfacing project, at Union Chapel Rd frm Coldwater Rd to Auburn Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 05/12/2010 | 08/21/2010 | 147343.03 | 0.97
4072 | Indiana | ALLEN | FORT WAYNE | 03 | 0901815 | This is a Maintenance Resurfacing project, at Union Chapel Rd frm Tonkel Rd to 160' W of Old Union Chapel; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 05/12/2010 | 08/21/2010 | 160550.17 | 2
4073 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901818 | This is a Maintenance Resurfacing project, at Central Avenue from I-65 to MLK Drive; to perform Surface Treatment work. | Pavement Improvement | 04/09/2010 |  | 09/30/2010 | 199796.63 | 1.34
4074 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901820 | This is a Maintenance Resurfacing project, at 35th Avenue from Chase Street to Grant Street; to perform Surface Treatment work. | Pavement Improvement | 04/09/2010 |  | 09/30/2010 | 124879.84 | 0.73
4075 | Indiana | MADISON | ANDERSON | 06 | 0901823 | This is a Maintenance Resurfacing project, at CR 200E from SR 32 to CR 800N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 07/17/2010 | 08/15/2010 | 643595.68 | 8.1
4076 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901824 | This is a Maintenance Resurfacing project, at Old Hobart Road from Miller Avenue to US 20; to perform Surface Treatment work. | Pavement Improvement | 04/09/2010 |  | 09/30/2010 | 158855.2 | 0.68
4077 | Indiana | ALLEN | FORT WAYNE | 03 | 0901825 | This is a Maintenance Resurfacing project, at E State Blvd: from Anthony Blvd to Hobson Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 | 04/01/2010 | 06/26/2010 | 386584.6 | 0.88
4078 | Indiana | ALLEN | FORT WAYNE | 03 | 0901826 | This is a Maintenance Resurfacing project, at E State Blvd from Hobson Rd to Coliseum Blvd (SR 930); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 12/31/2009 | 04/01/2010 | 06/26/2010 | 221536.04 | 0.52
4079 | Indiana | MARION | INDIANAPOLIS | 07 | 0901828 | This is a trail project for pedestrians and bicycles ont the Trail along 71st St from Eagle Creek North gate to Twelve Oaks Blvd on Indianapolis west side in Marion county | Transportation Enhancements | 04/23/2010 |  | 10/31/2010 | 920711.46 | 0.84
4080 | Indiana | ALLEN | FORT WAYNE | 03 | 0901831 | This is a Facilities for Pedestrians and Bicycles project, at NYC Rail to Trail: Wallen Rd to Till Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 02/23/2010 | 03/23/2010 | 08/28/2010 | 609068.95 | 0.49
4081 | Indiana | ALLEN | FORT WAYNE | 03 | 0901833 | This is a preventive maintenance resurfacing project, at East Rudisill Blvd from Calhoun St to South Anthony Blvd Fort Wayne, Allen county to perform asphalt resurface to extend the life of the stree | Pavement Improvement | 12/31/2009 | 03/18/2010 | 06/26/2010 | 452791.05 | 1.05
4082 | Indiana | ALLEN | FORT WAYNE | 03 | 0901834 | This is a project provide for pedestrians and bicycles on West Rudisill Blvd from Broadway to Calhoun Street in Fort Wayne in Allen county using enhancement money. This is 1 of 2 projects under cont | Transportation Enhancements | 12/31/2009 | 03/18/2010 | 06/26/2010 | 181481.68 | 1.05
4083 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901835 | This is a Maintenance Resurfacing project, at Samuelson Road from Robbins Road to 750 Ft South of Indiana Toll Rd; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 | 05/25/2010 | 07/01/2010 | 116754.84 | 0.7
4084 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901836 | This is a Safety project, at Various intersections on Campbell St., Calumet Ave, Silhavy and LaPorte Ave; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 12/31/2009 | 01/21/2010 | 07/01/2010 | 78205.25 | 0.01
4085 | Indiana | DELAWARE | MUNCIE | 06 | 0901837 | This is a Maintenance Resurfacing project, at Nebo Rd from SR 332 to River Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 | 05/12/2010 | 08/15/2010 | 288668.66 | 2.2
4086 | Indiana | ALLEN | FORT WAYNE | 03 | 0901839 | This is a Maintenance Resurfacing project, at Doyle Rd frm Dawkins Rd to Edgerton Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/21/2010 | 38690.33 | 0.5
4087 | Indiana | ALLEN | FORT WAYNE | 03 | 0901840 | This is a Maintenance Resurfacing project, at Halter Rd frm St Joe Rd to Cedar St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/21/2010 | 48803.59 | 0.52
4088 | Indiana | ALLEN | FORT WAYNE | 06 | 0901841 | This is a Maintenance Resurfacing project, at Wayne Trace frm Tillman Rd to 450' S of Philley Ave (Ft Wayne City Limits); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/21/2010 | 160321.72 | 1.65
4089 | Indiana | ALLEN | FORT WAYNE | 03 | 0901842 | This is a Maintenance Resurfacing project, at Wheelock Rd frm Flutter Rd to St Joe Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/21/2010 | 192333.57 | 1.78
4090 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0901848 | This is a Maintenance Resurfacing project, at Old US 33 from Ash Road to SR 19; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 |  | 08/15/2010 | 746837.44 | 3.1
4091 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0901849 | This is a Maintenance Resurfacing project, at CR 30 from CR 13 to CR 15; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 02/22/2010 |  | 08/15/2010 | 104403.54 | 1
4092 | Indiana | ALLEN | FORT WAYNE | 03 | 0901850 | This is a Facilities for Pedestrians and Bicycles project, at Covington Rd Trail: Beal Taylor Ditch to Eggeman Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 02/22/2010 | 03/19/2010 | 08/14/2010 | 436132 | 0.17
4093 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0901867 | This is a Maintenance Resurfacing project, at Bypass Road from West Lexington to 550 feet west of Nappanee; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/08/2010 | 05/06/2010 | 07/01/2010 | 134487.51 | 0.49
4094 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0901868 | This is a Maintenance Resurfacing project, at Old US 20 from Oak Manor Place to Bypass Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/08/2010 | 05/06/2010 | 07/01/2010 | 66618.64 | 0.36
4095 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0901869 | This is a Maintenance Resurfacing project, at Lexington Avenue from Bypass Road to 370' W of 22nd St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/08/2010 | 05/06/2010 | 07/01/2010 | 89873.85 | 0.46
4096 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 0901870 | This is a Maintenance Resurfacing project, at County Road 13 - Jeanwood from 100' N of East Lake Drive N to C.R. 6; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 01/06/2010 | 06/25/2010 | 08/01/2010 | 135481.25 | 1.08
4097 | Indiana | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901871 | This is a Safety project, at Intersection of Pearl St. and Elm St.; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 03/23/2010 | 04/20/2010 | 06/16/2010 | 140777.04 | 0.01
4098 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901877 | This is a Maintenance Resurfacing project, at Bremen Highway from Ireland Road to US 20 By-Pass; to perform Surface Treatment work. | Pavement Improvement | 02/22/2010 | 05/11/2010 | 09/30/2010 | 159068.51 | 0.45
4099 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0901878 | This is a Reconstruction (no added capacity) project, at Middlebury St: from Main St to Zollinger Rd; to perform Other Roadside Maintenance work. | Pavement Improvement | 02/22/2010 |  | 08/06/2010 | 200657.27 | 0.89
4100 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0901879 | This is a PreventiveMaintenance Resurfacing project, at Dierdorff Rd (CR 27) from CR 40 to Kercher Rd in Elkhart county that will exend the life of the pavement. | Pavement Improvement | 02/22/2010 | 07/02/2010 | 08/06/2010 | 119720.51 | 1.01
4101 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 0901880 | This is a Maintenance Resurfacing project, at Clinton St: from 410' West of Tanglewood Dr to Green Rd; to perform Other Roadside Maintenance work. | Pavement Improvement | 02/22/2010 |  | 08/06/2010 | 149362.28 | 0.57
4102 | Indiana | ALLEN |  | 06 | 0901914 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge # 268 over St Mary's River on Bostick Rd (Pedestrian); to perform Bridge Maintenance And Repair work. | Bridge Improvement | 04/10/2010 | 05/21/2010 | 10/30/2010 | 1226709.6 | 0.04
4103 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901915 | This is a Maintenance Resurfacing project, at 93rd Ave.- Cline to Marquette, Deodor to Hart St and White Oak to W of Columbia; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 04/01/2010 |  | 08/01/2010 | 320852.9 | 2.77
4104 | Indiana | VIGO | TERRE HAUTE | 08 | 0901923 | This is a Maintenance Resurfacing project, at From US 41 to 7th St; to perform Partial 3-R work. | Pavement Improvement | 04/01/2010 | 06/21/2010 | 07/30/2010 | 79737.73 | 0.4
4105 | Indiana | ALLEN | FORT WAYNE | 03 | 0901926 | This is a Facilities for Pedestrians and Bicycles project, at Fort Wayne Rivergreenway Maintenance-Boardwalk decking & Bridge hand Rails; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 01/06/2010 | 03/15/2010 | 06/26/2010 | 292076.01 | 0.39
4106 | Indiana | MARION | INDIANAPOLIS | 05 | 0901930 | This is a Maintenance Resurfacing project, at Carroll Rd from 79th St to 86th St; to perform asphalt resurface, Functional work. | Pavement Improvement | 04/01/2010 |  | 08/13/2010 | 320862.52 | 1
4107 | Indiana | MARION | INDIANAPOLIS | 05 | 0901931 | This is a Maintenance Resurfacing project, at Carroll Rd from Pendleton Pike to 75th St; to perform asphalt resurface, Functional work. | Pavement Improvement | 04/01/2010 |  | 08/13/2010 | 93740.04 | 0.2
4108 | Indiana | ALLEN | FORT WAYNE | 03 | 0901939 | This project is a preventive naintenance resurfacing project on Bluffton Road from Liberty Dr to Old Trail Road in Allen county to extend the service life of the pavement. | Pavement Improvement | 02/22/2010 | 06/01/2010 | 06/26/2010 | 162361.58 | 0.51
4109 | Indiana | ALLEN | FORT WAYNE | 03 | 0901944 | This is a Maintenance Resurfacing project, at N River Rd from Corporate Limits (1,500' W of Landin Rd) to 570' Wof Landin Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 |  | 08/14/2010 | 33559.5 | 0.18
4110 | Indiana | ALLEN | FORT WAYNE | 03 | 0901945 | This is a preventive maintenance project which will extend the service life of the road, on Moeller Rd from West of Quail Creek Blvd to the city limits west of Woodland Dr in Allen county. | Pavement Improvement | 04/01/2010 |  | 08/14/2010 | 54444.16 | 0.41
4111 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901946 | This project will upgrade the traffic signals on Kossuth Street at 16th Street And 18th Street in Tippecanoe County. | Safety/Traffic Management | 05/21/2010 | 06/24/2010 | 08/31/2010 | 18680.5 | 0.1
4112 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901947 | This project will upgrade the traffic signals at 26th Street And Earl/hedgewood in Tippecanoe County. | Safety/Traffic Management | 05/21/2010 | 06/24/2010 | 08/31/2010 | 53988.5 | 0.1
4113 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901948 | This project will upgrade the traffic signals at 36th Street And At Shenandoah in Tippecanoe County. | Safety/Traffic Management | 05/21/2010 | 06/24/2010 | 08/31/2010 | 50718 | 0.1
4114 | Indiana | RANDOLPH |  | 06 | 0901950 | This proejct clears the right of way in preparation for a major road reconstruction project on Parcels 17 and 35 to remove and demolish buildings on SR 32 in Randolf county on the east side of Winches | Other | 03/24/2010 | 03/30/2010 | 04/15/2010 | 21812.5 | 0.22
4115 | Indiana | ALLEN | FORT WAYNE | 03 | 0901954 | This is a Facilities for Pedestrians and Bicycles project, at NYC Rail to Trail: Till Rd to 0.4 miles N of Till Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 02/22/2010 | 04/01/2010 | 08/28/2010 | 536636.34 | 0.4
4116 | Indiana | DELAWARE | MUNCIE | 06 | 0901981 | This is a Safety project, at Madison St at 29th St and 26th St; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 04/27/2010 | 05/25/2010 | 06/25/2010 | 193786.4 | 0.01
4117 | Indiana | ALLEN | FORT WAYNE | 03 | 0901995 | This is a Maintenance Resurfacing project, at North River Rd from Landin Rd to I-469; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/14/2010 | 130462.93 | 1.45
4118 | Indiana | ALLEN | FORT WAYNE | 03 | 0901996 | This is a Maintenance Resurfacing project, at Thomas Rd from RR Xing 3100' North of Illinois Rd to Bass Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/14/2010 | 65176.02 | 0.37
4119 | Indiana | ALLEN | FORT WAYNE | 06 | 0901997 | This is a Maintenance Resurfacing project, at Monroeville Road from US 27 to Marion Center Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/14/2010 | 105193.65 | 1.31
4120 | Indiana | ALLEN | FORT WAYNE | 03 | 0901998 | This is a Maintenance Resurfacing project, at Scott Road from RR Crossing 725' South of Seegar Blvd to Bass Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/14/2010 | 41976.39 | 0.35
4121 | Indiana | ALLEN | FORT WAYNE | 03 | 0901999 | This is a Maintenance Resurfacing project, at Knoll Road from Smith Road to Ardmore Avenue; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/14/2010 | 76433.88 | 1
4122 | Indiana | ALLEN | FORT WAYNE | 03 | 0902000 | This is a Maintenance Resurfacing project, at Seiler Road from Adams Center Road to Green Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 04/01/2010 | 06/09/2010 | 08/14/2010 | 225029.23 | 2.48
4123 | Indiana | ALLEN | FORT WAYNE | 03 | 0902180 | This is a Safety project, at Guardrail upgrades to various bridges in Northeast Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 04/01/2010 | 05/07/2010 | 08/21/2010 | 229133 | 1
4124 | Indiana | ALLEN | FORT WAYNE | 03 | 0902181 | This is a Safety project, at Guardrail upgrades to various bridges in Northwest Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 04/01/2010 | 05/06/2010 | 08/21/2010 | 138060.43 | 1
4125 | Indiana | ALLEN | FORT WAYNE | 06 | 0902182 | This is a Safety project, at Guardrail upgrades to various bridges in Southeast Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 04/01/2010 | 06/03/2010 | 08/21/2010 | 115688.08 | 1
4126 | Indiana | ALLEN | FORT WAYNE | 03 | 0902183 | This is a Safety project, at Guardrail upgrades to various bridges in Southwest Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 04/01/2010 | 05/05/2010 | 08/21/2010 | 122498.96 | 1
4127 | Indiana | RANDOLPH |  | 06 | 1004017 | This project will replace the bridge on SR 32 over Sparrow Creek in Randolph County.. | Bridge Replacement | 05/13/2009 | 07/29/2009 | 11/20/2009 | 867750 | 0.01
4128 | Indiana | WHITE |  | 04 | 1441044 | This is a Maintenance Resurfacing project, at From 4th St, 1.02 miles W of E jct with US 231, to E jct with US 231; to perform asphalt resurface, Functional work. | Pavement Improvement | 05/19/2010 | 07/06/2010 | 10/31/2010 | 2538720.28 | 0.99
4129 | Indiana | STARKE |  | 02 | 1475040 | This project will improve drainage by replacing the structure on US 35 ofer Laramore Ditch in Starke County. | Pavement Improvement | 06/04/2009 | 08/04/2009 | 11/01/2009 | 793700 | 0.01
4130 | Indiana | LA PORTE |  | 02 | 1477002 | This is a Safety project, at US 35 - At Schultz Rd, 0.14 mile N of I-80/90 Underpass; to perform Sight Distance Improvement work. | Safety/Traffic Management | 10/08/2009 | 10/15/2009 | 08/13/2010 | 909249.18 | 0.27
4131 | Indiana | MARION | INDIANAPOLIS | 07 | 1531031 | This is a Bridge Replacement (capacity added) project, at Bridge over Little Buck Creek, 1.16 miles S of I-465; to perform Bridge Replacement, Other Construction work. | Bridge Replacement | 02/20/2010 | 03/15/2010 | 08/02/2011 | 3105889 | 0.11
4132 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 1621002 | This project will add turn lanes and improve the intersection of US 19 and county road 42 in Elkhart County. | Pavement Widening | 08/18/2009 | 04/01/2010 | 06/30/2010 | 812909 | 0.01
4133 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 1810014 | This is a Reconstruction (no added capacity) project, at SR 15 - Over Wolf Lake Drain, 2.65 miles N of US 33; to perform Small Structure, Replacement work. | Pavement Improvement | 10/14/2009 |  | 10/01/2010 | 479931.03 | 0.01
4134 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 1941018 | This project will improve and widen intersections along SR 8 and SR 49 in Porter County. | Safety/Traffic Management | 08/27/2009 | 10/22/2009 | 06/29/2010 | 1947964 | 0.93
4135 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | 2127112 | This project will widn US 6 in Elkhart County with the installation of sidewalks along the North side of the road and a wider median. | Pavement Widening | 07/17/2009 | 03/03/2010 | 10/22/2010 | 4949108 | 0.94
4136 | Indiana | WHITLEY |  | 03 | 2192034 | This is a Reconstruction (no added capacity) project, at US 33 - At Clingerman Avenue, 0.5 mile N of SR 205; to perform Curve Correction work. | Pavement Improvement | 09/08/2009 | 10/21/2009 | 06/18/2010 | 302904 | 0.1
4137 | Indiana | ELKHART | ELKHART-GOSHEN | 02 | 2195026 | This project will construct a median left turn lane on US 33 near US 20 in Dunlap, Elkhart County. New pavement, drainage structures, signals and signs will be placed and a bridge widened. | New Construction | 03/27/2009 | 07/23/2009 | 10/07/2011 | 10667478.72 | 5.42
4138 | Indiana | UNION |  | 06 | 2493013 | This project will repair and restore the pavement and replace signs on US 27 from the Ohio State line north 3.6 miles in Union county. | Pavement Widening | 04/15/2009 | 08/05/2009 | 02/10/2012 | 9345892.93 | 3.58
4139 | Indiana | GRANT |  | 05 | 3227023 | This project will improve the sight distance at SR 26 and county road 750 south in Grant County. | Pavement Improvement | 07/07/2009 | 08/21/2009 | 11/13/2009 | 986682.26 | 0.2
4140 | Indiana | FULTON |  | 02 | 3325007 | This project will replace the bridge on SR 17 over Starr Ditch in Fulton County. | Bridge Replacement | 04/17/2009 | 07/06/2009 | 11/14/2009 | 556948.74 | 0.01
4141 | Indiana | HANCOCK | INDIANAPOLIS | 07 | 3630005 | This is a trail project for pedestrians and bicycles on the Pennsy Trail from just East of German Church Road to Mt. Comfort Road ( Hancock county road 600 W) using enhanacment funds. | Transportation Enhancements | 03/04/2010 | 03/31/2010 | 11/15/2010 | 1641150 | 2
4142 | Indiana | HENDRICKS |  | 04 | 3632005 | This project will improve the surface and rebuild sections of the bridge on US 40 over White Lick Creek in Hendricks County. | Pavement Improvement | 03/24/2009 | 04/20/2009 | 11/24/2009 | 2847000 | 0.01
4143 | Indiana | SULLIVAN |  | 08 | 3677012 | This project will improve the intersection on SR 54 and add turn lanes at County Road 50 South, 1 mile West of SR 159. | Pavement Improvement | 05/08/2009 | 07/14/2009 | 04/17/2010 | 793449.25 | 0.11
4144 | Indiana | ADAMS |  | 06 | 3801006 | This is a Bridge Replacement (no added capacity) project, at Bridge over Smith-Shoemaker Ditch, 2.1 miles E of US 27; to perform Bridge Replacement work. | Bridge Replacement | 03/23/2010 | 05/10/2010 | 10/16/2010 | 684476.62 | 0.01
4145 | Indiana | SCOTT |  | 09 | 4072004 | This project will replace the bridge on SR 356 over Town Creek in Scott County. | Bridge Replacement | 03/19/2009 | 04/07/2009 | 10/31/2009 | 627953.34 | 0.2
4146 | Indiana | FOUNTAIN |  | 08 | 4223005 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Pavement Improvement | 06/17/2009 | 07/16/2009 | 08/31/2010 | 3270050.51 | 1.02
4147 | Indiana | BARTHOLOMEW | COLUMBUS | 09 | 4303009 | This project will add turn lanes, nodernize the signal, and widen the intersection at SR 11and Bartholomw county Road 450S. | Pavement Improvement | 05/06/2009 | 06/01/2009 | 08/15/2010 | 1202944.2 | 0.01
4148 | Indiana | CLINTON |  | 04 | 4312005 | This project will improve the sight distance at SR 75 and county road 700 north in Clinton County. | Safety/Traffic Management | 06/03/2009 | 06/24/2009 | 11/15/2009 | 1206807.56 | 0.86
4149 | Indiana | MORGAN |  | 04 | 4455005 | This project will replace and restore the pavement on SR 42 in Morgan County from Monrovia to Martinsville. | Pavement Improvement | 06/04/2009 | 07/07/2009 | 11/20/2010 | 7339345 | 11.96
4150 | Indiana | STARKE |  | 02 | 4475002 | This project will improve drainage by replacing the structure over Cannon ditch on SR 8 in Starke County | Pavement Improvement | 08/19/2009 | 09/29/2009 | 10/31/2009 | 346456.39 | 0.01
4151 | Indiana | FOUNTAIN |  | 04 | 4923003 | This project will improve the surface and rebuild sections of the bridge on SR 341 over I-74 in Fountain County. | Bridge Improvement | 03/23/2009 | 04/03/2009 | 07/31/2009 | 1220119 | 0.01
4152 | Indiana | HENRY |  | 06 | 5133003 | This is a Bridge New Construction project, at 5.36 miles N of US 40; to perform New Br, Precast 3 Sided Culvert work. | New Bridge Construction | 03/23/2010 | 05/18/2010 | 10/30/2010 | 404395.98 | 0.228
4153 | Indiana | HENRY |  | 06 | 5133004 | This project replaces a old small drainage culvert on SR 103, 4 miles north of US 40 in Henry county. | Pavement Improvement | 03/23/2010 | 05/18/2010 | 10/30/2010 | 425503.02 | 0.239
4154 | Indiana | ST JOSEPH |  | 02 | 5171008 | This project will improve drainage by replacing the structure on SR 331 over Madison Township Ditch in St. Joseph County. | Pavement Improvement | 03/24/2009 | 06/01/2009 | 08/29/2009 | 688526.05 | 0.01
4155 | Indiana | MIAMI |  | 05 | 5252007 | This project will improve drainage by replacing the structure on SR 16 over Washonis Creek in Miami County. | Pavement Improvement | 09/08/2009 | 10/19/2009 | 09/03/2010 | 397020.7 | 0.1
4156 | Indiana | JEFFERSON |  | 09 | 5639005 | This project will improve the sight distance at SR 250 and Scott Ridge Road in Jefferson County. | Safety/Traffic Management | 05/08/2009 | 07/17/2009 | 09/25/2009 | 681704.39 | 0.01
4157 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 8571960 | This is a Reconstruction (no added capacity) project, at US 41 - At 93rd Ave, 1.9 miles N of US 231; to perform Intersection Improvement work. | Pavement Improvement | 06/30/2009 | 07/28/2009 | 10/31/2009 | 2083424.57 | 0.01
4158 | Indiana | ELKHART |  | 03 | 9031815 | This project will improve drainage by replacing the structure on SR 19 over Fisher-Gordon Ditch in Elkhart County. | Pavement Improvement | 05/18/2009 | 07/22/2009 | 10/09/2009 | 552259.39 | 0.1
4159 | Indiana | HARRISON |  | 09 | 9032075 | This project will improve drainage by replacing a pipe on SR 11 on the East side of Elizabeth. | Pavement Improvement | 07/09/2009 | 07/31/2009 | 10/17/2009 | 272187.22 | 0.01
4160 | Indiana | HUNTINGTON |  | 05 | 9301060 | This project will improve drainage by replacing the structure on SR 5 over Loon Creek in Huntington County. | Pavement Improvement | 08/14/2009 | 09/15/2009 | 10/23/2009 | 498659 | 0.01
4161 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 9381900 | This is a road reconstruction project that will completly reconstruct the road and add lanes to increase the capacity of the road on Miami St from Kern Rd to Jackson Rd in St Joseph county. | Pavement Widening | 04/22/2010 | 05/03/2010 | 10/15/2010 | 1891030.49 | 1.04
4162 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9610820 | This project will replace the bridge on SR 312 over the Indiana Harbor Canal in Lake County. | Bridge Replacement | 06/18/2009 | 07/06/2009 | 10/31/2009 | 2153446.87 | 0.01
4163 | Indiana | STEUBEN |  | 03 | 9803670 | This project will rebuild the US 20 and I-69 interchange in Steuben county to improve traffic flow. | Bridge Replacement | 06/01/2009 | 06/12/2009 | 10/15/2010 | 1994588.32 | 0.49
4164 | Indiana | ST JOSEPH | SOUTH BEND (MI) | 02 | 9901720 | This project will replace the bridge on Locust Road over US 20 in St Joseph County. | Bridge Replacement | 06/03/2009 | 06/16/2009 | 09/18/2009 | 3054373.82 | 0.09
4165 | Indiana | PORTER |  | 01 | 9901740 | This project will replace the bridge on SR 49 over Pleasant Township Ditch in Porter County. | Bridge Replacement | 05/13/2009 | 06/26/2009 | 10/31/2009 | 758632.98 | 0.01
4166 | Indiana | MARTIN |  | 08 | 9903160 | This is a Reconstruction (no added capacity) project, at 3.38 miles E of SR 650; to perform Small Structure Replacement work. | Pavement Improvement | 03/24/2010 | 04/14/2010 | 07/31/2010 | 698972.94 | 0.1
4167 | Indiana | FRANKLIN |  | 06 | 9924012 | This is a Bridge Replacement (no added capacity) project, at Bridge #94 over E Fork Blue Creek, carrying Blue Creek; to perform Br Repl, Comp.Cont.Pres.Conc. I-Beam work. | Bridge Replacement | 04/01/2010 | 04/12/2010 | 10/01/2010 | 829328.76 | 0.01
4168 | Indiana | KOSCIUSKO |  | 03 | 9943052 | This is a Bridge New Construction project, at Bridge over Waubee Drain, 3.39 miles S of US 6; to perform New Bridge, Other Construction work. | New Bridge Construction | 02/20/2010 | 03/26/2010 | 09/25/2010 | 647849.2 | 0.01
4169 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9945111 | This is a trail project for pedestrians and bicycles and is the Phase 1 of the Bike Network in Crown Point, Lake county using enhancement funds. | Transportation Enhancements | 02/24/2010 | 03/22/2010 | 10/15/2010 | 899763.55 | 0.01
4170 | Indiana | WHITE |  | 04,02 | 9991027 | This project builds a new trail for pedestrians and bicycle, at Tioga Bridge as a bike/ped crossing over Lake Freeman and Tippecanoe River in White county. | Transportation Enhancements | 01/19/2010 | 03/22/2010 | 10/15/2010 | 1060488 | 0.01
4171 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999193 | This project will extend the bridge life by repainting bridge beams at SR 49 over US 30 and SR 2 in Porter County. | Bridge Improvement | 05/13/2009 | 06/30/2009 | 09/03/2009 | 372762.88 | 0.01
4172 | Indiana | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999194 | This project will extend the bridge life by repainting bridge beams at Calumet Ave over SR 49 and US 6 in Porter County. | Bridge Improvement | 05/13/2009 | 06/30/2009 | 09/09/2009 | 347985.54 | 0.01
4173 | Indiana | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999228 | This project will upgrade and modernize the traffic signal at US 41 and 93rd Avenue in Lake County. | Safety/Traffic Management | 06/30/2009 | 07/28/2009 | 10/31/2009 | 115269.08 | 0.01
4174 | Indiana | TIPPECANOE |  | 04 | 9999231 | This project will add turn lanes and improve the intersection of SR 25 at county road 575 west and county road 500 west in Tippecanoe County. | Pavement Widening | 04/15/2009 | 05/04/2009 | 10/31/2009 | 1383518.57 | 1.12
4175 | Indiana | JACKSON |  | 09 | 9999235 | This project will improve sections and extend the life of SR 11 from SR 250 to US 50 in Jackson County with a pavement surface overlay. | Pavement Improvement | 09/11/2009 | 09/28/2009 | 11/30/2009 | 1129575.55 | 8.01
4176 | Indiana | TIPPECANOE |  | 04 | 9999236 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 06/15/2009 | 08/04/2009 | 10/31/2011 | 1025634.93 | 0.01
4177 | Indiana | MARION | INDIANAPOLIS | 07 | 9999241 | This is a Bridge Rehabilitation (no added capacity) project, at 21st Street over Big Eagle Creek; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 12/03/2009 | 06/01/2010 | 09/30/2010 | 546435.69 | 0.064
4178 | Indiana | HOWARD | KOKOMO | 02 | A600560 | This project is the 4th phase of a road reconstruction project that will totally reconstruct the pavement and add travel lanes on Dixon Road from Sycamore to Judson in Kokomo, Howard county. | Pavement Widening | 04/15/2010 | 05/05/2010 | 08/31/2012 | 2107988 | 1.207
4179 | Indiana | ELKHART | ELKHART-GOSHEN | 03 | A710953 | This is a Bridge Rehabilitation (no added capacity) project, at Indiana Ave historic bridge, on Indiana Ave where it crosses Elkhart River; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 05/12/2010 | 06/05/2010 | 10/15/2010 | 479577.57 | 0.03
4180 | Indiana | MONROE | BLOOMINGTON | 09 | A901422 | This is a Facilities for Pedestrians and Bicycles project, at B-Line Trail phase 2; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 04/21/2010 | 05/17/2010 | 06/29/2011 | 2057179.92 | 2.4
4181 | Indiana | BARTHOLOMEW | COLUMBUS | 09 | G195003 | This is a Maintenance Restoration & Rehabilitation project, at 17th St from US 31 to Central Ave; to perform Road Reconstruction work. | Pavement Improvement | 01/13/2010 | 02/08/2010 | 10/31/2011 | 1661117 | 1
4182 | Indiana | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | L720015 | This project will build a new bridge on US 52 over the Norfolk Southern Railroad, 2 miles South of SR 25 in Tippecanoe County. | New Bridge Construction | 06/05/2009 | 08/20/2009 | 11/30/2010 | 5791766.4 | 0.01
4183 | Iowa | POTTAWATTAMIE | OMAHA (NE)-IA | 5 | 000R001 | This project will provide grading, drainage, paving, electrical and lighting for an intermodal facility owned by the Iowa Interstate Railroad in Council Bluffs. The facility is located northeast of th | Other | 02/11/2010 | 04/05/2010 | 12/01/2010 | 2000000 | 0
4184 | Iowa | FAYETTE |  | 1 | 000R002 | This project will replace track ballast and ties on 14 miles of D&W Railroad track between Dewar and Oelwein to improve operational efficiency and safety. | Other | 01/06/2010 | 05/03/2010 | 12/01/2010 | 764200 | 0
4185 | Iowa | CLINTON |  | 1 | 000R003 | This ARRA project will construct part of a new rail based industrial park being developed by the Clinton Regional Development Corporation. Rail construction includes: construction of a 10,000 feet pas | New Bridge Construction | 02/23/2010 | 02/23/2010 | 12/01/2010 | 2090186.83 | 0
4186 | Iowa | LEE |  | 2 | 000R004 | This project will upgrade the electrical components of the swing span railroad bridge over the Mississippi River between Keokuk, Iowa and Hamilton, Illinois. The project updates the electrical system | Transportation Enhancements | 02/23/2010 |  | 12/01/2010 | 120900 | 0
4187 | Iowa | PAGE |  | 5 | 0022044 | This project will provide an improved driving surface by widening and resurfacing 2.0 miles of Iowa Highway 2 from W State Street to S 16th Street in Clarinda with hot-mix asphalt. | Pavement Improvement | 03/30/2009 | 04/06/2009 | 11/01/2009 | 848817 | 1.9
4188 | Iowa | DAVIS |  | 2 | 0028035 | This project will provide an improved driving surface by widening and resurfacing with hot-mix asphalt 4.9 miles of Iowa Highway 2/US Highway 63 through Bloomfield from the west junction of these hig | Pavement Improvement | 06/29/2009 | 07/20/2009 | 07/01/2010 | 3651402.77 | 5
4189 | Iowa | PLYMOUTH |  | 5 | 0031075 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 3/South Dakota 50 over the Big Sioux River 0.5 miles North and 1.7 miles West of We | Bridge Replacement | 03/06/2009 | 03/30/2009 | 11/01/2009 | 1842961 | 0
4190 | Iowa | BUENA VISTA |  | 5 | 0032053 | This project will replace a bridge, which is in poor condition and narrow with a new bridge. The bridge is on Iowa 3 over Brooke Creek 6.1 miles West of US 71 or approximately 10 miles Northwest of S | Bridge Replacement | 07/31/2009 | 04/19/2010 | 11/01/2010 | 782441 | 0
4191 | Iowa | POLK | DES MOINES | 3 | 0064152 | This project will reconstruct and widen approximately 900 feet of 111th Street south and west of the intersection with US Highway 6 (Hickman Road) in the City of Clive. The project will include concr | Pavement Improvement | 01/05/2010 |  | 12/01/2010 | 586698 | 0.25
4192 | Iowa | WEBSTER, CALHOUN |  | 4 | 0074017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 11.7 miles of Iowa Highway 7 from 0.5 miles west of the Calhoun County Line to US Highway 1 | Pavement Improvement | 03/26/2009 | 04/13/2009 | 12/01/2009 | 5364499 | 11.9
4193 | Iowa | OSCEOLA |  | 5 | 0092021 | This project will improve the driving surface by applying an unbonded portland cement concrete overlay on approximately 8.6 miles of Iowa Highway 9 from just west of Polk Avenue to just east of Tanage | Pavement Improvement | 03/30/2009 | 05/04/2009 | 11/01/2009 | 4865289 | 8.8
4194 | Iowa | POLK | DES MOINES | 3 | 0132615 | Polk County is constructing a 0.4 mile extension of Adventureland Drive NW. The project will widen Adventureland Drive NW from a 2-lane roadway to a 4-lane roadway with median, sidewalk, and left-tur | Pavement Improvement | 09/14/2009 | 09/22/2009 | 12/01/2010 | 706977 | 0.3
4195 | Iowa | STORY | AMES | 4 | 0155662 | This project is in the city of Ames on George W. Carver Avenue from Stange Road to Bloomington Road. The project consists of one inch of hot-mix asphalt stress relief course and six inches of concret | Pavement Improvement | 09/28/2009 | 10/12/2009 | 12/01/2010 | 717794 | 0.9
4196 | Iowa | STORY | AMES | 4 | 0155664 | This project is in the city of Ames on Lincoln Way from Hickory Drive to just past Marshall Avenue. The project consists of milling the existing surface, patching problem areas, resurfacing with hot- | Pavement Improvement | 08/27/2009 | 09/18/2009 | 12/01/2010 | 530759.85 | 0.3
4197 | Iowa | STORY | AMES | 4 | 0155665 | This project will provide for the construction of .6 miles of the Skunk River Trail that will run along the west side of South Skunk River from just south of East 13th Street in South River Valley Par | Transportation Enhancements | 08/27/2009 | 09/18/2009 | 12/01/2010 | 175728 | 0.6
4198 | Iowa | STORY | AMES | 4 | 0155668 | This project consists of milling and resurfacing with asphalt 0.44 miles of roadway along Duff Avenue from 7th Street N. to 13th Street in Ames, Iowa. | Pavement Improvement | 01/14/2010 |  | 12/01/2010 | 504231 | 0.44
4199 | Iowa | WAPELLO |  | 2 | 0161017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 5.3 miles of Iowa Highway 16 from US Highway 34 to north city | Pavement Improvement | 04/01/2009 | 04/06/2009 | 12/01/2009 | 1837373 | 5.5
4200 | Iowa | DAVIS, WAPELLO, VAN BUREN |  | 2 | 0161018 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 0.16 miles of Iowa Highway 16 from north city limit of Eldon t | Pavement Improvement | 04/01/2009 | 04/06/2009 | 12/01/2009 | 1450974.35 | 4.3
4201 | Iowa | CALHOUN |  | 4 | 0203083 | Grading of relocated US 20 in Iowa, from the east Sac County line to County Road N-33 in Calhoun County, 2.6 miles. | New Construction | 03/01/2010 | 04/12/2010 | 12/01/2010 | 2874975.12 | 4.2
4202 | Iowa | CHICKASAW |  | 4 | 0241017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 6.75 miles of Iowa Highway 24 from east city limit of New Hamp | Pavement Improvement | 04/03/2009 | 04/20/2009 | 11/01/2009 | 3200829 | 7.8
4203 | Iowa | CHICKASAW, WINNESHIEK |  | 4 | 0241020 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 6 miles of Iowa Highway 24 from the west city limit of Lawler | Pavement Improvement | 04/03/2009 | 04/20/2009 | 11/01/2009 | 2566288 | 6.3
4204 | Iowa | CASS |  | 5 | 0285612 | This project replaces the bridge supports, which are in very poor condition, to extend the service life of the bridge. The bridge is located on Nishna Street over an unnamed creek just South of 29th | Bridge Improvement | 10/12/2009 | 11/02/2009 | 12/01/2009 | 92520 | 0
4205 | Iowa | CASS |  | 5 | 0285613 | This project is in Atlantic, Iowa on South Olive Street from East 14th Street to East 22nd Street. The project consists of pavement rehabilitation which will provide a smoother ride and improved drai | Pavement Improvement | 01/21/2010 |  | 12/01/2010 | 175000 | 0.5
4206 | Iowa | FREMONT |  | 5 | 0291068 | This project will replace two bridges, which are in poor condition, with new bridges. The bridges are on Interstate 29 over Plum Creek 0.5 miles South of Exit #20, or approximately 28 miles South of C | Bridge Replacement | 03/06/2009 | 03/30/2009 | 11/01/2009 | 2173992 | 0
4207 | Iowa | FREMONT |  | 5 | 0291069 | This project will replace two bridges, which are in poor condition with new bridges. The bridges are on Interstate 29 over County Road J24 at Exit #20, approximately 27 miles South of Council Bluffs. | Bridge Replacement | 03/06/2009 | 03/30/2009 | 11/01/2009 | 2797514 | 0
4208 | Iowa | FREMONT |  | 5 | 0291075 | On Interstate 29 in Fremont County Iowa, from 1.5 mile north of county road J-26 north to 1.5 mile north of county road J-24, a nine-inch concrete overlay will be placed on the northbound lanes and a | Pavement Improvement | 03/06/2009 | 03/30/2009 | 11/01/2009 | 11189757 | 4.2
4209 | Iowa | MILLS |  | 5 | 0292054 | This project will replace two bridges, which are in poor condition, with new bridges. The bridges are on Interstate 29 over St. Mary’s Creek 1 mile South of Exit #42, or approximately 5 miles South of | Bridge Replacement | 03/06/2009 | 03/23/2009 | 11/01/2009 | 1726111 | 0
4210 | Iowa | MILLS |  | 5 | 0292065 | On Interstate 29 in Mills County, Iowa, from 3 miles north of the north junction with US Highway 34 to the Pottawattamie County line, a nine-inch concrete overlay will be placed on the northbound lane | Pavement Improvement | 03/06/2009 | 03/23/2009 | 11/01/2009 | 11742272 | 6
4211 | Iowa | MONONA, HARRISON |  | 5 | 0295100 | The Iowa DOT is reconstruction of I-29 from Exit 95, which services Little Sioux, Iowa, to Exit 112, which services Onawa, Iowa. The project includes the reconstruction of the grade and Portland Ceme | Pavement Improvement | 04/23/2009 | 05/04/2009 | 11/01/2010 | 42253362 | 18.1
4212 | Iowa | MONONA |  | 5 | 0296167 | This project provides for a six inch hot-mix asphalt overlay on the north and southbound lanes of Interstate 29 in Monona County, Iowa, from just north of Iowa 175 north to the Woodbury County line. | Pavement Improvement | 06/29/2009 | 07/31/2009 | 09/01/2010 | 22401042 | 13.5
4213 | Iowa | MONONA |  | 5 | 0296182 | This project will replace a bridge, which is in poor condition with a new bridge. The bridge is on Interstate 29 southbound over Robinson Creek approximately 3.5 miles South of Exit#127 near Sloan. | Bridge Replacement | 03/06/2009 | 06/22/2009 | 11/01/2009 | 1169819 | 0
4214 | Iowa | TAMA |  | 3 | 0306151 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 11.9 miles of US Highway 30 from just east of M Avenue to Iow | Pavement Improvement | 06/26/2009 | 07/17/2009 | 07/01/2010 | 4065922 | 11.9
4215 | Iowa | CLARKE |  | 5 | 0351105 | This project will replace two bridges, which are in poor condition and have inadequate clearance over Interstate 35, with new bridges. The bridges are on US 34 over Interstate 35 in Osceola. | Bridge Replacement | 03/06/2009 | 04/01/2009 | 11/01/2009 | 1736085 | 0
4216 | Iowa | CLARKE |  | 5 | 0351111 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of the southbound lanes of I-35. The project begins approximately one mile north of Exit 22, which services Van Wert, Iowa, and e | Pavement Improvement | 03/30/2009 | 04/07/2009 | 11/01/2009 | 15304219 | 9.5
4217 | Iowa | CLARKE |  | 5 | 0351112 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of the northbound lanes of I-35. The project begins approximately one mile north of Exit 22, which services Van Wert, Iowa, and e | Pavement Improvement | 08/06/2009 | 04/05/2010 | 11/01/2010 | 8471001 | 9.5
4218 | Iowa | CLARKE |  | 5 | 0351116 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of US Highway 34 at the interchange of I-35 and US Highway 34; Exit 33 which services Osceola, Iowa. The project is approximately | Bridge Replacement | 03/06/2009 | 04/01/2009 | 11/01/2009 | 1626415 | 0.4
4219 | Iowa | WARREN |  | 4 | 0352337 | This project provides for a four inch hot-mix asphalt overlay on the north and southbound lanes of Interstate 35 in Warren County Iowa, from the Clarke County line north to 2 miles south of Iowa 92 ne | Pavement Improvement | 04/13/2009 | 05/05/2009 | 11/01/2009 | 17007987 | 11.3
4220 | Iowa | CLAYTON |  | 1 | 0523031 | This project includes performing cracking and seating of the existing portland cement concrete pavement and then applying a hot-mix asphalt overlay on approximately 9.0 miles of US Highway 52 from jus | Pavement Improvement | 08/17/2009 | 08/24/2009 | 09/01/2010 | 3746694 | 9
4221 | Iowa | CLAYTON |  | 1 | 0523032 | This project will resurface eight miles of US 52 from Guttenberg to Garnavillo with six inches of hot-mix asphalt to improve pavement condition. | Pavement Improvement | 08/17/2009 | 08/24/2009 | 09/01/2010 | 3439573 | 7.5
4222 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 0587631 | In Bettendorf, Iowa on 23rd Street from Grant Street to Central Avenue. This project will be constructed in three stages to minimize impact on residents in the area. The street will be graded and pa | Pavement Improvement | 05/29/2009 | 06/08/2009 | 12/01/2009 | 739272 | 0.32
4223 | Iowa | LEE |  | 2 | 0611122 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 03/06/2009 | 04/08/2009 | 11/01/2009 | 126319 | 0
4224 | Iowa | LEE |  | 2 | 0611124 | The project is part of the grading of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-Pass. This project is for the grading of the new alignment which will be | New Construction | 03/06/2009 | 04/01/2009 | 09/01/2010 | 8245240 | 2.2
4225 | Iowa | LEE |  | 2 | 0611129 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 03/06/2009 | 04/06/2009 | 11/01/2009 | 549102 | 0
4226 | Iowa | LEE |  | 2 | 0611132 | The project is part of the grading of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-Pass. This project is for the grading of the new alignment which will be | New Construction | 03/06/2009 | 04/06/2009 | 09/01/2010 | 4912339 | 1.7
4227 | Iowa | LEE |  | 2 | 0611162 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 03/06/2009 | 04/06/2009 | 11/01/2009 | 251777 | 0
4228 | Iowa | LEE |  | 2 | 0611165 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 03/06/2009 | 03/18/2009 | 11/01/2009 | 295767.6 | 0
4229 | Iowa | MAHASKA |  | 3 | 0633078 | This project will mill, widen, and resurface 9 miles of US 63 from New Sharon south to 210th Street North with five inches of hot-mix asphalt to improve pavement condition and safety. The widening wi | Pavement Improvement | 07/17/2009 | 07/17/2009 | 07/01/2010 | 7406627 | 9.2
4230 | Iowa | DECATUR, CLARKE |  | 5 | 0691038 | This project will widen and resurface 31 miles of US 69 from Osceola south to Interstate 35 west of Davis City with three inches of hot-mix asphalt to improve pavement condition and safety. | Pavement Improvement | 04/01/2009 | 04/21/2009 | 11/01/2009 | 4892118.84 | 33
4231 | Iowa | POLK | DES MOINES | 3 | 0694092 | This project will mill 1.5 inches and resurface with 4.5 inches of hot-mix asphalt on US 69 from Iowa 160 (Oralabor Road) north1.7 miles to First Street in Ankeny to improve pavement condition. | Pavement Improvement | 10/02/2009 | 05/03/2010 | 12/01/2010 | 1000000 | 1.69
4232 | Iowa | PAGE, MONTGOMERY |  | 5 | 0711030 | This project will widen and resurface 17 miles of US 71 from Iowa 2 near Clarinda north to the intersection with US 34 north of Villisca with three inches of hot-mix asphalt to improve pavement condit | Pavement Improvement | 03/30/2009 | 04/14/2009 | 11/01/2009 | 6189082 | 17.2
4233 | Iowa | SAC, CARROLL |  | 5 | 0715068 | This project will mill and replace two inches of the existing hot mix asphalt surface on approximately 12 miles of US 71 from just north of Carroll to the junction of Iowa 175 in Auburn to improve pav | Pavement Improvement | 04/20/2009 | 05/21/2009 | 11/01/2009 | 1395963.34 | 10.5
4234 | Iowa | POLK |  | 3 | 0747603 | This multi-use path will be constructed as an alternative mode of transportation in the city of Bondurant, in Polk county. The path is along Second Street from 450 ft west of Mallard Point Circle NW | Transportation Enhancements | 08/26/2009 | 08/26/2009 | 12/01/2010 | 389313.69 | 0.779
4235 | Iowa | BOONE |  | 4 | 0750627 | This project consistes of two roadways in Boone, Iowa: South Marshall Street from Hancock Drive to Crestwood Drive and Industrial Park Road from Linn Street to Argo Street. Both projects consist of p | Pavement Improvement | 01/29/2010 | 04/01/2010 | 12/01/2010 | 473410 | 0.6
4236 | Iowa | JOHNSON | IOWA CITY | 2 | 0801600 | This project is in Iowa City, Iowa on Hawkins Drive from the University of Iowa Hospital to Carver Hawkeye Arena. The project consists of pavement rehabilitation and widening which will provide a smo | Pavement Improvement | 02/11/2010 | 02/01/2010 | 12/01/2010 | 200000 | 0.4
4237 | Iowa | JOHNSON | IOWA CITY | 2 | 0806285 | Construction of a recreational trail in Iowa City along IA 1 (N. Dodge Street) from Act Circle NE to Northgate Dr., 0.64 miles. The project includes construction of a pedestrian bridge over Interstat | Transportation Enhancements | 03/19/2010 | 04/19/2010 | 12/01/2010 | 1252603 | 0.63
4238 | Iowa | POTTAWATTAMIE |  | 5 | 0921059 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 92 over Keg Creek approximately 2.7 miles West of Treynor. | Bridge Replacement | 03/20/2009 | 04/06/2009 | 11/01/2009 | 1142159 | 0
4239 | Iowa | POTTAWATTAMIE |  | 5 | 0921060 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 92 over Middle Silver Creek approximately 0.1 miles West of Treynor. | Bridge Replacement | 03/20/2009 | 04/06/2009 | 11/01/2009 | 1279850 | 0
4240 | Iowa | DES MOINES |  | 2 | 0977632 | This project is in Burlington, Iowa on Mt. Pleasant Street from U.S. 61 to Osborn Street. The project consists of milling the existing surface down to the concrete subbase and paving two and a half i | Pavement Improvement | 09/03/2009 | 09/14/2009 | 12/01/2010 | 1364054.71 | 1.5
4241 | Iowa | LINN | CEDAR RAPIDS | 2 | 1001061 | IA 922/U.S. Business Route 151 (1st Avenue) and Collins Road will be widened in Cedar Rapids, Iowa. The project will start at 40th Steet Dr. SE for 1.3 miles ending at Tama Street SE. Widening will | Pavement Widening | 12/16/2009 | 04/19/2010 | 12/01/2010 | 2832566 | 0.273
4242 | Iowa | CLINTON |  | 1 | 1040602 | Camanche, Iowa on Washington Boulevard from US 67 to 22nd Avenue. The project consists of pavement rehabilitation which will provide a smoother ride and improved drainage. | Pavement Improvement | 01/15/2010 | 04/28/2010 | 12/01/2010 | 168623 | 0.6
4243 | Iowa | WARREN | DES MOINES | 4 | 1105603 | Carlisle, Iowa on South 1st Street from Highway 5 to School Street. The project consists of pavement rehabilitation which will provide a smoother ride and improved drainage. Better accommodations fo | Pavement Improvement | 02/24/2010 |  | 12/01/2010 | 446670 | 0.3
4244 | Iowa | CARROLL |  | 5 | 1125612 | Carroll, Iowa on Clark Street from extended Anthony Street to 7th Street. The project consists of milling the existing surface and resurfacing with hot-mix asphalt. The three and a half inch overlay | Pavement Improvement | 12/08/2009 |  | 12/01/2010 | 808258 | 0.7
4245 | Iowa | DUBUQUE |  | 1 | 1147603 | Cascade, Iowa on Tyler Street Northeast from 1st Avenue to just past Macomber Road. The project consists of milling the existing surface and resurfacing with three-inches of hot-mix asphalt providing | Pavement Improvement | 12/23/2009 | 06/04/2010 | 12/01/2010 | 64456 | 0.7
4246 | Iowa | BLACK HAWK |  | 1 | 1185641 | This project consists of replacing the pavement of multiple roadways in Cedar Falls, Iowa: State Street from East 2nd Street to East 4th Street, East 2nd Street from Main Street to State Street and Ea | Pavement Improvement | 10/19/2009 | 04/01/2010 | 12/01/2010 | 700000 | 0.43
4247 | Iowa | BLACK HAWK |  | 1 | 1185642 | This two phase Trail widening and resurfacing project is located along the North and South sides of the Cedar River in the city of Cedar Falls in Blackhawk County. Phase I, North Riverside Trail , ru | Transportation Enhancements | 10/15/2009 |  | 12/01/2010 | 207500 | 1.939
4248 | Iowa | CHEROKEE |  | 5 | 1272618 | Cherokee, Iowa on North River Road from the city limits to the River Road Bridge. The project consists of a four inch hot-mix asphalt overlay with mail box turnouts and driveway/intersection fillets | Pavement Improvement | 06/16/2009 | 07/20/2009 | 12/01/2009 | 180000 | 0.9
4249 | Iowa | MONONA, WOODBURY |  | 5 | 1412041 | To improve safety and winter driving conditions this project will grade four miles along Iowa 141. The project starts at the Woodbury and Monona County Line just southeast of Smithland and ends 4 mil | Pavement Improvement | 03/27/2009 | 04/20/2009 | 11/01/2009 | 2271717 | 2.7
4250 | Iowa | CLINTON |  | 1 | 1415619 | Clinton County is extending 19th Avenue, approximately 1.9 miles, in the city of Clinton, Iowa, from Mill Creek Parkway east to Springdale Drive. The project is a new 4-lane Portland Cement Concrete | Pavement Improvement | 12/23/2009 | 05/17/2010 | 12/01/2010 | 815053 | 0.35
4251 | Iowa | BUCHANAN |  | 1 | 1503058 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 150 over Bear Creek approximately 3.3 mile South of Independence. | Bridge Replacement | 03/06/2009 | 03/26/2009 | 12/01/2009 | 983635 | 0
4252 | Iowa | JOHNSON | IOWA CITY | 2 | 1557634 | This project is the construction of the .3 mile extension of 1st Avenue Trail along the west side of 1st Avenue from Country Club Drive north to Oakdale Blvd. in the city of Coralville in Johnson Coun | Transportation Enhancements | 02/23/2010 | 05/17/2010 | 12/01/2010 | 382549 | 0.289
4253 | Iowa | POLK | DES MOINES | 3 | 1631080 | This project involves improvements at the intersection of Iowa Highway 163 and NE 75th Street in Pleasant Hill in Polk County, including the addition of portland cement concrete turn lanes and signal | Safety/Traffic Management | 06/16/2009 | 06/22/2009 | 12/01/2009 | 750000 | 0.3
4254 | Iowa | POTTAWATTAMIE | OMAHA (NE)-IA | 5 | 1642657 | The city of Council Bluffs, Iowa, is reconstructing College Road from US Highway 6 southeast and west to Valley View Drive. The project will replace approximately 0.96 miles of the existing roadway w | Pavement Improvement | 08/10/2009 | 08/10/2009 | 12/01/2010 | 2163357 | 1.5
4255 | Iowa | POTTAWATTAMIE | OMAHA (NE)-IA | 5 | 1642658 | The city of Council Bluffs, Iowa is repairing the transverse joints on 35th Street from Nebraska Avenue to 23rd Avenue. The project will extend the life of the existing Portland Cement Concrete (PCC) | Pavement Improvement | 12/02/2009 | 04/12/2010 | 12/01/2010 | 478467.01 | 3
4256 | Iowa | POTTAWATTAMIE |  | 5 | 1642659 | The new construction of a Bicycle Pedestrian Trail along the east side of 13th Street between Avenue A and Avenue H in the city of Council Bluffs in Pottawattamie county. This project will increase s | Transportation Enhancements | 10/15/2009 | 10/26/2009 | 12/01/2010 | 200000 | 0.51
4257 | Iowa | POTTAWATTAMIE | OMAHA (NE)-IA | 5 | 1642660 | For the reconstruction and improvement of multipule segments of a series of bicycle and pedestrian trails connecting the city of Council Bluffs urban and rural areas in Pottawattamie county. The spe | Transportation Enhancements | 02/08/2010 | 04/14/2010 | 12/01/2010 | 471030 | 8.54
4258 | Iowa | RINGGOLD |  | 5 | 1691038 | This project is located on US 169 in Ringgold County from the intersection with Iowa 2 in Mount Ayr north 13 miles to the Union County line. The project will recycle three inches of the existing pave | Pavement Improvement | 07/10/2009 | 04/05/2010 | 07/01/2010 | 4382345 | 12.9
4259 | Iowa | UNION |  | 5 | 1692021 | This project is located on US 169 in Union County, starting in Afton and proceeding south approximately 9 miles to the Union/Ringgold county line near Shannon City. The project will recycle three inc | Pavement Improvement | 07/10/2009 | 04/05/2010 | 07/01/2010 | 3373398 | 8.7
4260 | Iowa | UNION |  | 5 | 1710609 | Creston, Iowa on East Prairie Street from Cherry Street to Mulberry Street. The project consists of a two inch hot-mix asphalt overlay which will provide a smoother ride on the roadway. The Poplar St | Pavement Improvement | 08/27/2009 | 09/10/2009 | 12/01/2010 | 62778 | 0.1
4261 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 1827659 | This project consists of a number of different sections on multiple roadways in Davenport, Iowa: Jersey Ridge Road, Northwest Boulevard, Division Street, Locust Street, and Rockingham Road in three lo | Pavement Improvement | 06/08/2009 | 07/20/2009 | 12/01/2009 | 1183107 | 2.477
4262 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 1827660 | The City of Davenport will patch the existing pavement at the intersection of Eastern Avenue and 53rd Street and Pine Street from 53rd Street to Northwest Boulevard to improve pavement conditions. Th | Pavement Improvement | 06/11/2009 | 06/17/2009 | 12/01/2009 | 800000 | 0
4263 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 1827661 | This project will consist of constructing a new raised median along US Highway 67 from Iowa Street to Gaines Street and along US Highway 61 from Gaines Street to Marquette Street in the City of Davenp | Pavement Improvement | 01/26/2010 | 04/19/2010 | 12/01/2010 | 267842.79 | 0.9
4264 | Iowa | CLINTON |  | 1 | 1855613 | De Witt, Iowa on 11th Street from 6th Avenue to Humeston Road. The roadway will be milled and overlaid with two inches of hot-mix asphalt which will provide a smoother ride. Selected sidewalk ramps a | Pavement Improvement | 06/01/2009 | 06/17/2009 | 12/01/2009 | 201885 | 0.49
4265 | Iowa | POLK | DES MOINES | 3 | 1945753 | Des Moines, Iowa on 6th Avenue from University Avenue to the Des Moines River Bridge. The roadway will be milled and problem areas will be patched as necessary. Traffic signal loops will be replaced | Pavement Improvement | 05/27/2009 | 07/26/2009 | 12/01/2009 | 497395.63 | 0.9
4266 | Iowa | WARREN | DES MOINES | 3 | 1945754 | Des Moines, Iowa on Fleur Drive/Blue Street from Beardsley Street to Southwest 9th Street. The existing roadway surface will be milled before being overlaid with five inches of asphalt. The five inc | Pavement Improvement | 05/27/2009 | 06/15/2009 | 12/01/2009 | 496951 | 1.2
4267 | Iowa | POLK | DES MOINES | 3 | 1945755 | Des Moines, Iowa on McKinley Avenue from Fleur Drive to South Union Street. The existing roadway surface will be milled and the traffic signal loop detectors will be replaced before being overlaid wi | Pavement Improvement | 08/17/2009 | 09/29/2009 | 12/01/2010 | 339405 | 1.5
4268 | Iowa | POLK | DES MOINES | 3 | 1945756 | This project is in the city of Des Moines on Southeast 5th Street from East County Line Road to East Army Post Road. Three inches of hot-mix asphalt will be placed to improve driving quality and saf | Pavement Improvement | 08/17/2009 | 09/14/2009 | 12/01/2010 | 467340 | 1
4269 | Iowa | POLK | DES MOINES | 3 | 1945757 | This project is in the city of Des Moines on McKinley Avenue from South Union Street to Southeast 5th Street. The project consists of widening and placement of a 10-inch portland cement concrete surf | Pavement Improvement | 08/17/2009 | 04/01/2010 | 12/01/2010 | 1286228 | 0.3
4270 | Iowa | POLK | DES MOINES | 3 | 1945758 | In Polk county, the city of Des Moines will improve safety, driving quality, and capacity through portland cement concrete pavement widening with hot-mix asphalt resurfacing along Army Post Road fro | Pavement Improvement | 12/07/2009 | 04/05/2010 | 12/01/2010 | 1000000 | 0.2
4271 | Iowa | POLK | DES MOINES | 3 | 1945759 | The construction of the Principal Riverwalk multi-purpose trail extensions run along the West side of Des Moines River from Grand Avenue south to Walnut Street and from Court Avenue south to Vine Stre | Transportation Enhancements | 10/06/2009 | 12/02/2009 | 12/01/2010 | 2849000 | 0.2
4272 | Iowa | DUBUQUE | DUBUQUE (IL) | 1 | 2100646 | The city of Dubuque, Iowa, is purchasing the right-of-way for the construction of a new roadway to be known as the Southwest Arterial. The roadway will connect US highway 20 to US Highway 61. The pro | Other | 09/10/2009 | 09/10/2009 | 12/01/2010 | 2909534 | 6.2
4273 | Iowa | DUBUQUE |  | 1 | 2160609 | This project replaces the bridge supports, which are in poor condition, to extend the service life of the bridge. The project also improves the aesthetics of the bridge to blend with the 1st Street i | Bridge Improvement | 12/07/2009 | 03/31/2010 | 12/01/2010 | 156901 | 0
4274 | Iowa | BENTON |  | 3 | 2186045 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on US 218 over Pratt Creek approximately 7.5 miles West of Vinton. | Bridge Replacement | 03/06/2009 | 04/20/2009 | 11/01/2009 | 1048906 | 0
4275 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | 2290609 | In Scott county, the city of Eldridge will improve safety and mobility with hot-mix asphalt widening along 1st Street north of Trails Road and south of Fisher Court for .24 miles. | Pavement Improvement | 10/13/2009 | 10/21/2009 | 12/01/2010 | 140000 | 3.1
4276 | Iowa | SCOTT |  | 1 | 2290610 | This project provides for the design and engineering of a multi-use trail that will run along the east side of County Road Y-64 from north of the city limits of Eldridge to south of the city limits of | Other | 12/08/2009 | 12/08/2009 | 12/01/2010 | 90152.21 | 0
4277 | Iowa | JEFFERSON |  | 2 | 2465617 | The city of Fairfield, Iowa is reconstructing Kirkwood Avenue from 5th Street east to 2nd Street which has deteriorated beyond maintenance repairs. The 0.23 mile long project replaces the old roadway | Pavement Improvement | 06/24/2009 | 08/31/2009 | 12/01/2009 | 283500 | 0.2
4278 | Iowa | LEE |  | 2 | 2697618 | In Lee county, the city of Fort Madison will improve traffic management, safety, mobility, and carrying capacity. These enhancements will be made with structural improvements to pavement and the addit | Pavement Improvement | 06/01/2009 | 06/01/2009 | 12/01/2010 | 550000 | 0.01
4279 | Iowa | POLK | DES MOINES | 3 | 3125607 | In Polk county, the city of Grimes will improve driving quality, capacity, and safety along South James Street, beginning south of 6th Street and ending north of Urbandale approximately 2.0 miles. Th | Pavement Improvement | 08/10/2009 | 08/24/2009 | 12/01/2010 | 1000000 | 2.2
4280 | Iowa | POWESHIEK |  | 3 | 3127622 | In Poweshiek county, the city of Grinnell will improve driving quality and safety through hot-mix asphalt resurfacing with milling along two sections of road; one along 8th Avenue from West Street (I | Pavement Improvement | 07/06/2009 | 09/10/2009 | 12/01/2009 | 196400 | 1
4281 | Iowa | IDA |  | 5 | 3650603 | In Ida county, the city of Ida Grove will improve driving quality and safety by patching Moorehead Avenue, from 2nd Street to Ohio Street (Iowa 59), with portland cement concrete before placing a ho | Pavement Improvement | 06/01/2009 | 09/08/2009 | 12/01/2009 | 200000 | 0
4282 | Iowa | WARREN |  | 4 | 3680612 | The City of Indianola will improve approximately ¾ of a mile of North Y Street between Iowa Highway 92 and West Euclid Avenue by replacing the existing granular surface with a new concrete pavement. | Pavement Improvement | 06/12/2009 | 06/12/2009 | 12/01/2009 | 494331 | 0.73
4283 | Iowa | JOHNSON | IOWA CITY | 2 | 3715643 | In Johnson county, the city of Iowa City will improve driving quality and safety through hot-mix asphalt resurfacing with milling along South Riverside Drive (Old Highway 218) beginning south of High | Pavement Improvement | 08/24/2009 | 09/01/2009 | 12/01/2010 | 600000 | 1.6
4284 | Iowa | POLK | DES MOINES | 3 | 3827611 | This project will involve widening of the existing pavement on approximately 0.8 miles of Northwest 86th Street from Chamberry Boulevard to Northwest 62nd Avenue in the City of Johnston. The new conc | Pavement Improvement | 01/26/2010 | 04/01/2010 | 12/01/2010 | 1144528 | 0.8
4285 | Iowa | MARION |  | 3 | 4040606 | In Marion county, the city of Knoxville will improve driving quality and safety through hot-mix asphalt resurfacing with milling along two sections of road. One along South Roche Street from Robinson | Pavement Improvement | 06/11/2009 | 10/05/2009 | 12/01/2009 | 296950 | 0.688
4286 | Iowa | SCOTT |  | 1 | 4252601 | This project provides preliminary and final design engineering for the Mississippi River Trail (MRT) that will run along U.S. Highway 67 from the Eastern most city limits of Bettendorf to the Northern | Other | 12/08/2009 | 12/08/2009 | 12/01/2010 | 214190 | 0
4287 | Iowa | DELAWARE |  | 1 | 4682621 | In Delaware county, the city of Manchester will improve driving quality and safety through hot-mix asphalt resurfacing along East Main Street from Brewer Street to Bailey Drive. | Pavement Improvement | 11/03/2009 | 05/05/2010 | 12/01/2010 | 210309 | 0.37
4288 | Iowa | JACKSON |  | 1 | 4742615 | In Jackson county, the city of Maquoketa will enhance safety and drainage with improvements to portland cement concrete curb and gutter along North Main Street from Grove Street to Quarry Street. Imp | Pavement Improvement | 05/29/2009 | 07/22/2009 | 12/01/2009 | 244514 | 0.4
4289 | Iowa | LINN |  | 2 | 4775620 | Marion, Iowa intends to improve North 35th Street from Tower Terrace Road to Indian Creek Road. Improvements will include patching of the existing roadway pavement and grading and construction of bic | New Construction | 01/27/2010 | 03/22/2010 | 12/01/2010 | 1274994 | 0.686
4290 | Iowa | LINN |  | 2 | 4775621 | Marion, Iowa intends to reconstruct North 10th Street from Indian Creek Road to Tower Terrace Road. Reconstruction will include intersection modifications, pavement widening, culvert replacement, tra | Pavement Improvement | 01/27/2010 | 04/05/2010 | 12/01/2010 | 1228500 | 0.7
4291 | Iowa | LINN |  | 2 | 4775622 | Marion, Iowa will improve the Central Business District between North 10th Street from 7th Avenue to 8th Avenue. Construction includes updating traffic signals and lighting to improve safety and prov | Safety/Traffic Management | 02/25/2010 | 06/07/2010 | 12/01/2010 | 280000 | 0.66
4292 | Iowa | LINN |  | 2 | 4775623 | Marion, Iowa intends to improve the intersection of Armar Drive and Highway 100. Intersection modifications will include traffic signal upgrades and concrete paving/widening. | Safety/Traffic Management | 02/25/2010 |  | 12/01/2010 | 450000 | 0
4293 | Iowa | LINN |  | 2 | 4775624 | Marion, Iowa intends to improve the safety at the intersection of South 22nd Street and Highway 100 by installing new traffic signals, adding left turn lanes and extending existing left turn lanes. | Pavement Improvement | 02/25/2010 |  | 12/01/2010 | 371360 | 0
4294 | Iowa | MARSHALL |  | 4 | 4797612 | In Marshall county, the city of Marshalltown will improve driving quality and safety by resurfacing along Iowa Avenue West, for 70 feet west of Parker Avenue to 648 feet east of south 6th street, wit | Pavement Improvement | 09/09/2009 | 09/24/2009 | 12/01/2010 | 449376.89 | 3
4295 | Iowa | MUSCATINE |  | 2 | 5330619 | In Muscatine county, the city of Muscatine will improve road safety, drainage, capacity and driving quality. Improvements will be obtained through replacement of portland cement concrete pavement, ce | Pavement Improvement | 06/18/2009 | 08/10/2009 | 12/01/2009 | 733544 | 0.6
4296 | Iowa | STORY |  | 4 | 5405607 | In Story county, the city of Nevada will improve the driving surface, and extend the service life of the pavement along W 4th Street, at U.S. Highway 30 heading north 1.0 mile to 1st Street, by resur | Pavement Improvement | 05/27/2009 | 08/10/2009 | 12/01/2009 | 245333 | 0.98
4297 | Iowa | JASPER |  | 3 | 5482611 | This project is on East 31st Street North and North 19th Avenue East from 1st Avenue east to East 19th Street in Newton. The project will improve the driving surface and extend the service life of th | Pavement Improvement | 09/21/2009 | 09/23/2009 | 06/06/2010 | 620472 | 1.91
4298 | Iowa | JOHNSON |  | 2 | 5557614 | This project will improve traffic flow and safety on Iowa 965 in North Liberty by constructing traffic signals at its intersection with Cherry Street. | Safety/Traffic Management | 02/24/2010 | 04/27/2010 | 12/01/2010 | 285000 | 0
4299 | Iowa | WARREN | DES MOINES | 4 | 5587602 | This project will improve access to new development by converting an existing three-way “T” intersection of Colonial Parkway and Iowa Highway 28 within the City of Norwalk into a four-way intersection | Pavement Improvement | 03/15/2010 | 05/11/2010 | 12/01/2010 | 300000 | 0.3
4300 | Iowa | WAPELLO |  | 2 | 5825637 | This project will increase capacity, improve safety and mobility along Lake Road in the city of Ottumwa in Wapello County. The project begins at the city limits along Lake Road and heads north for | Pavement Improvement | 06/15/2009 | 10/05/2009 | 12/01/2009 | 632498 | 1.5
4301 | Iowa | WAPELLO |  | 2 | 5825638 | In Wapello county, the city of Ottumwa will conduct structural enhancements including hot-mix asphalt resurfacing and portland cement concrete patching along .74 miles of roadway on Madison Avenue f | Pavement Improvement | 06/15/2009 | 10/05/2009 | 12/01/2009 | 361255.93 | 1
4302 | Iowa | MARION |  | 3 | 5947613 | In Marion county, the city of Pella will replace deteriorating pavement on Independence Street heading south along Oskaloosa Street to southeast 9th Street. Smoother longer lasting pavement will be p | Pavement Improvement | 06/01/2009 | 06/01/2009 | 12/01/2010 | 323163 | 1
4303 | Iowa | DALLAS |  | 4 | 5970610 | This project will be rehabilitating the pavement along three roadways within the City of Perry totaling approximately 0.96 miles: Park Street from 1st Avenue to the east edge of Violet Hill Cemetery, | Pavement Improvement | 05/21/2009 | 06/22/2009 | 12/01/2009 | 269251.35 | 0.9
4304 | Iowa | SCOTT |  | 1 | 6247601 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 0.75 miles of Lost Grove Road in the City of Princeton from US Highway 67 west 3960 feet. | Pavement Improvement | 03/29/2010 |  | 12/01/2010 | 249820 | 0.8
4305 | Iowa | BLACK HAWK | WATERLOO | 1 | 6342600 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 1.1 miles of County Route D-22/ Dubuque Road from the west to | Pavement Improvement | 07/10/2009 | 08/17/2009 | 12/01/2009 | 750000 | 1.131
4306 | Iowa | WOODBURY |  | 5 | 6890606 | The City of Sergeant Bluff will reconstruct approximately 0.3 miles of South Lewis Boulevard from 1st Street to Topaz Drive. The new concrete driving surface will improve ride quality and reduce main | Pavement Improvement | 06/08/2009 | 08/03/2009 | 12/01/2009 | 537483.46 | 0.29
4307 | Iowa | SIOUX | SIOUX CITY (NE-SD) | 5 | 7055621 | This project will be rehabilitating the pavement along three roadways within the City of Sioux Center totaling 0.65 miles: 2nd Avenue from 4th Street SW to 3rd Street NW, 3rd Street NE from 1st Avenue | Pavement Improvement | 05/18/2009 | 09/10/2009 | 12/01/2009 | 370399 | 0.65
4308 | Iowa | WOODBURY | SIOUX CITY (NE-SD) | 5 | 7057662 | The City of Sioux City will reconstruct and widen approximately ½ mile of South Martha Street from Stone Avenue to Gordon Drive. The new concrete driving surface will improve ride quality and capacit | Pavement Improvement | 06/25/2009 | 06/12/2009 | 12/01/2009 | 792853 | 0.47
4309 | Iowa | WOODBURY | SIOUX CITY (NE-SD) | 5 | 7057663 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on five sections of roadway within the City of Sioux City totaling 12.5 blocks: 3rd Street from Water Street | Pavement Improvement | 06/09/2009 | 06/29/2009 | 12/01/2009 | 495533 | 0.88
4310 | Iowa | CLAY |  | 5 | 7170619 | The city of Spencer Iowa is reconstructing West 11th Street from Grand Avenue west to 7th Avenue West, approximately 0.5 miles. The existing Portland Cement Concrete (PCC) roadway will be removed and | Pavement Improvement | 03/08/2010 | 04/05/2010 | 12/01/2010 | 217026 | 0.5
4311 | Iowa | JOHNSON |  | 2 | 7855606 | This project will replace existing deteriorated pavement with new full-depth portland cement concrete pavement patches on Sunset Street from Koser Avenue to Highland Drive and Melrose Avenue from Suns | Pavement Improvement | 01/29/2010 | 06/09/2010 | 12/01/2010 | 50000 | 0
4312 | Iowa | POLK | DES MOINES | 3 | 7875632 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 1 mile of Iowa 100th Street from Douglas Avenue to Hickman Road in Urbandale. | Pavement Improvement | 01/21/2010 |  | 12/01/2010 | 1200000 | 0.99
4313 | Iowa | BLACK HAWK | WATERLOO | 1 | 8155708 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on four sections of roadway within the City of Waterloo totalling 1.93 miles: Broadway Street from Donald St | Pavement Improvement | 05/22/2009 | 07/20/2009 | 12/01/2009 | 1431482.09 | 1.9
4314 | Iowa | BLACK HAWK | WATERLOO | 1 | 8155709 | This project provides for construction of a bicycle and pedestrian trail on the south bank of the Cedar River from West 6th Street to West 18th Street in the city of Waterloo in Blackhawk County. Thi | Transportation Enhancements | 01/26/2010 |  | 12/01/2010 | 517197 | 1.069
4315 | Iowa | BREMER |  | 1 | 8190623 | This project will upgrade traffic signals on Highway 3 (Bremer Avenue) in Waverly, Iowa at the following intersections; 15th Street West, 10th Street West, 6th Street West, 4th Street West, 1st Street | Safety/Traffic Management | 12/23/2009 | 04/12/2010 | 12/01/2010 | 394998 | 0
4316 | Iowa | POLK | DES MOINES | 3 | 8477610 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 1.6 miles of 73rd Street from Center Street to Hickman Road i | Pavement Improvement | 06/16/2009 | 07/08/2009 | 12/01/2010 | 538000 | 1.6
4317 | Iowa | ADAIR |  | 5 | C001071 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on 200th street over the West Fork of the Middle Nodaway River 0.5 miles East of Bridgewate | Bridge Replacement | 06/17/2009 | 06/30/2009 | 12/01/2009 | 312195 | 0.1
4318 | Iowa | ADAMS |  | 5 | C002054 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2.8 miles of County Route N26 from the town of Nodaway | Pavement Improvement | 08/24/2009 | 08/24/2009 | 12/01/2010 | 217179 | 2.8
4319 | Iowa | APPANOOSE |  | 2 | C004077 | This project consists of applying a hot mix asphalt overlay at two locations in Appanoose County. One location is approximately 2.8 miles on County Route T14 from Iowa Highway 2 to just north of the | Pavement Improvement | 07/08/2009 | 09/21/2009 | 12/01/2009 | 581000 | 3.3
4320 | Iowa | APPANOOSE |  | 2 | C004078 | This project provides for construction of a box culvert extension over Ham Creek on the south side of county road J18 east of Honey Creek Resort State Park, north of Rathbun Lake in Appanoose county. | Transportation Enhancements | 07/08/2009 | 07/20/2009 | 06/01/2009 | 150000 | 0.26
4321 | Iowa | APPANOOSE |  | 2 | C004079 | For the new construction of a 7 mile multi-use trail on the northern border of Rathbun Lake in Appanoose County. The trail will serve as an alternative mode of transportation from county road J18 to | Transportation Enhancements | 08/31/2009 | 08/31/2009 | 12/01/2010 | 1146787.5 | 8.294
4322 | Iowa | BENTON |  | 3 | C006078 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 5.7 miles of County Route | Pavement Improvement | 08/24/2009 | 09/21/2009 | 12/01/2010 | 888727 | 5.5
4323 | Iowa | BLACK HAWK |  | 1 | C007116 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 2.8 miles of County Route | Pavement Improvement | 06/11/2009 | 09/28/2009 | 12/01/2009 | 778935.38 | 3.5
4324 | Iowa | BOONE |  | 4 | C008053 | The project is located on Boone County Route R-21 which is also known as Nature Road. Boone County is placing Hot Mix Asphalt Resurfacing over Cold In-Place Recycling of the existing asphalt surface | Pavement Improvement | 05/13/2009 | 08/31/2009 | 12/01/2009 | 558263 | 6.5
4325 | Iowa | BREMER |  | 1 | C009061 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 3.6 miles of County Route | Pavement Improvement | 07/20/2009 | 09/14/2009 | 12/01/2009 | 650000 | 3.5
4326 | Iowa | BUCHANAN |  | 1 | C010067 | This project will improve the driving surface and extend the life of the pavement by applying an unbonded concrete overlay on approximately 6.8 miles of County Route D22 from County Route V65 to Golf | Pavement Improvement | 05/13/2009 | 05/26/2009 | 12/01/2009 | 1730000 | 7
4327 | Iowa | BUENA VISTA |  | 5 | C011067 | This project will improve the driving surface and extend the life of the pavement by applying an unbonded concrete overlay on approximately 1.6 miles of 600th Street (East Milwaukee Road) from Geising | Pavement Improvement | 05/14/2009 | 05/26/2009 | 12/01/2009 | 717251 | 1.5
4328 | Iowa | CALHOUN |  | 4 | C013079 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 12 miles of County Route D15 from the Sac/Calhoun Count | Pavement Improvement | 08/24/2009 | 09/21/2009 | 12/01/2010 | 2000000 | 12
4329 | Iowa | CARROLL |  | 5 | C014124 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 7 miles of County Route N41 from US Highway 30 to Count | Pavement Improvement | 05/20/2009 | 07/06/2009 | 12/01/2009 | 1000000 | 9.9
4330 | Iowa | CARROLL |  | 5 | C014126 | For the reconstruction of a 13.5 mile segment of the Sauk Rail Trail from the city of Maple River Junction, which is just north of Highway 30, in Carroll County through the city of Breda towards the c | Transportation Enhancements | 09/24/2009 | 04/13/2010 | 06/12/2010 | 1000000 | 12.9
4331 | Iowa | CASS |  | 5 | C015050 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 6.4 miles of County Route G35 from County Route N28 to | Pavement Improvement | 07/02/2009 | 07/06/2009 | 12/01/2009 | 1500000 | 6.5
4332 | Iowa | CEDAR |  | 2 | C016078 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 4.1 miles of County Route | Pavement Improvement | 08/17/2009 | 06/18/2010 | 12/01/2010 | 773396 | 4.5
4333 | Iowa | CERRO GORDO |  | 4 | C017059 | This project includes performing cracking and seating of the existing concrete pavement and then doing a hot mix asphalt overlay. The work will be done on County Route B30 from the city of Mason City | Pavement Improvement | 05/28/2009 | 09/08/2009 | 12/01/2009 | 1009770.74 | 4.5
4334 | Iowa | CHEROKEE |  | 5 | C018054 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 3 miles of County Route M | Pavement Improvement | 05/27/2009 | 09/02/2009 | 12/01/2009 | 500000 | 3
4335 | Iowa | CLARKE |  | 5 | C020071 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2 miles of County Route H45 at three separate locations | Pavement Improvement | 07/10/2009 | 09/08/2009 | 12/01/2009 | 748000 | 1
4336 | Iowa | CLINTON |  | 1 | C023082 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 10.7 miles of County Route | Pavement Improvement | 06/03/2009 | 08/03/2009 | 12/01/2009 | 524593 | 6
4337 | Iowa | CRAWFORD |  | 5 | C024088 | The project is located on Crawford County Route (CCR) M55 (330th Street) and CCR E53 (S Avenue). Crawford County is replacing the existing Portland Cement Concrete roadway surface with a new Portland | Pavement Improvement | 05/14/2009 | 06/22/2009 | 12/01/2009 | 1391865.1 | 6.8
4338 | Iowa | DALLAS |  | 4 | C025075 | The project is located on Dallas County Route (DCR) R16 (R Avenue). Dallas County is replacing the existing Portland Cement Concrete roadway surface with a new Portland Cement Concrete roadway surfac | Pavement Improvement | 06/03/2009 | 07/08/2009 | 12/01/2009 | 726674 | 4.2
4339 | Iowa | DECATUR |  | 5 | C027042 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 1.9 miles of County Route J14 from Interstate 35 to US | Pavement Improvement | 07/01/2009 | 09/08/2009 | 12/01/2009 | 368000 | 2
4340 | Iowa | DELAWARE |  | 1 | C028067 | This project will provide an improved driving surface, extension of the life of the pavement, and improved site drainage by applying a hot mix asphalt overlay with cold-in-place recycling and the repl | Pavement Improvement | 05/21/2009 | 07/27/2009 | 12/01/2009 | 525953 | 3
4341 | Iowa | DICKINSON |  | 5 | C030037 | This project will improve the driving surface and enhance safety by applying an unbonded concrete overlay and doing necessary shoulder work on approximately 4.2 miles of County Route M27 from 190th St | Pavement Improvement | 06/11/2009 | 07/16/2009 | 12/01/2009 | 1417702 | 4.2
4342 | Iowa | DICKINSON |  | 5 | C030039 | This project provides for resurfacing and renovation of various segments of Spine and Poyzer Trails in the cities of Milford, Arnolds Park, Okoboji, Spirit Lake, and Orleans in Dickinson County. The | Transportation Enhancements | 01/11/2010 | 05/04/2010 | 12/01/2010 | 186365 | 8.54
4343 | Iowa | DUBUQUE |  | 1 | C031061 | This project involves replacement of four bridges along Farley Road from Aitchison Road to the City of Cascade. | Bridge Replacement | 02/18/2010 | 03/22/2010 | 12/01/2010 | 506011 | 0.54
4344 | Iowa | EMMET |  | 4 | C032038 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2.9 miles of County Route N22 from County Route A17 to | Pavement Improvement | 05/21/2009 | 07/17/2009 | 12/01/2009 | 470749.42 | 2.9
4345 | Iowa | EMMET |  | 4 | C032039 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2 miles of Emmet County Route A22 (170th Ave.) from the Dickinson/Emmet County line east to the Es | Pavement Improvement | 05/21/2009 | 07/17/2009 | 12/01/2009 | 597840 | 3.3
4346 | Iowa | FAYETTE |  | 1 | C033106 | This project consists of applying a concrete overlay on Fayette County Route V68 (W Ave.) from U.S. Highway 18 northerly to 3rd St. in the city of Waucoma. The project also includes a concrete overla | Pavement Improvement | 05/21/2009 | 05/28/2009 | 12/01/2009 | 1920000 | 8
4347 | Iowa | FLOYD |  | 4 | C034077 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 7.5 miles of Floyd County Route B60 (270th St.) from the Cerro Gordo/Floyd County line east to Ind | Pavement Improvement | 05/15/2009 | 06/30/2009 | 12/01/2009 | 1268424.36 | 7.4
4348 | Iowa | FRANKLIN |  | 4 | C035057 | This project will improve safety along approximately ¾ mile of Franklin County Route S56 (Timber Ave.) from Iowa Highway 3 north to 155th St. on the south limits of the city of Hansell. The existing | Pavement Improvement | 05/20/2009 | 09/21/2009 | 12/01/2009 | 210459.95 | 1
4349 | Iowa | GRUNDY |  | 3 | C038085 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2 miles of Grundy County Route T19 (F Ave.) from 1st Street in the city of Wellsburg north, past U | Pavement Improvement | 05/21/2009 | 06/01/2009 | 12/01/2009 | 530000 | 2.5
4350 | Iowa | GRUNDY |  | 3 | C038086 | This project provides for construction of the East Lake Trail on the east side of Grundy County Lake located SW of interchange U.S. Highway 20 & County Road T-55 (Union Ave.) which is just SW of the c | Transportation Enhancements | 12/02/2009 | 12/02/2009 | 12/01/2010 | 433008.94 | 0.78
4351 | Iowa | GUTHRIE |  | 5 | C039052 | This project provides for resurfacing and construction of 5.7 miles of the Raccoon River Valley Trail from Clay Street in the city of Panora to the Trailhead in the city of Yale both in Guthrie county | Transportation Enhancements | 06/04/2009 | 06/04/2009 | 12/01/2010 | 782454.72 | 5.34
4352 | Iowa | HAMILTON |  | 4 | C040052 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road R27 over the Boone River 5 miles North of Webster City. | Bridge Replacement | 05/11/2009 | 05/26/2009 | 12/01/2009 | 600000 | 0.1
4353 | Iowa | HANCOCK |  | 4 | C041096 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 3.4 miles of Hancock County Route B20 (285th St./Quail Ave./290th St.) from Hancock County Route R | Pavement Improvement | 05/28/2009 | 07/30/2009 | 12/01/2009 | 356466.18 | 3.5
4354 | Iowa | HARDIN |  | 4 | C042064 | This project will provide an improved driving surface and reduce future roadway maintenance on Hardin County Route S56 from Iowa Highway 175 northerly to Hardin County Route D35 in Steamboat Rock. Th | Pavement Improvement | 05/21/2009 | 06/01/2009 | 12/01/2009 | 699400 | 4.5
4355 | Iowa | HARRISON |  | 5 | C043068 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Harrison County Route F32 from U.S. Highway 30 in Woodbine east 4.6 miles | Pavement Improvement | 01/08/2010 | 05/10/2010 | 12/01/2010 | 1020000 | 4.1
4356 | Iowa | HENRY |  | 2 | C044064 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5.8 miles of Henry County Route J20 (Salem Road) from Ash Avenue in the city of Hillsboro easterly | Pavement Improvement | 06/08/2009 | 09/07/2009 | 12/01/2009 | 1138000 | 5
4357 | Iowa | HOWARD |  | 4 | C045059 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5 miles of Howard County Route V26 (Jade Ave.) from Iowa Highway 9 north to Howard County Route A2 | Pavement Improvement | 05/21/2009 | 05/26/2009 | 12/01/2009 | 960000 | 5
4358 | Iowa | IDA |  | 5 | C047045 | The project is located on Ida County Route (ICR) M15 (240th Street). Ida County is replacing the existing Portland Cement Concrete (PCC) roadway surface with a new PCC roadway surface which includes | Pavement Improvement | 07/02/2009 | 08/03/2009 | 12/01/2009 | 500000 | 1.47
4359 | Iowa | IOWA |  | 3 | C048056 | This project will provide an improved driving surface and reduce future roadway maintenance on Iowa County Route F67 (325th St.) from Iowa County Route V52 (H Ave.) easterly to North Knoll Ridge St. i | Pavement Improvement | 06/16/2009 | 06/18/2009 | 12/01/2009 | 773396 | 6.5
4360 | Iowa | JACKSON |  | 1 | C049046 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 1.3 miles of Jackson County Route Y53 (Hurstville Road) from Pershing Road in the city of Maquoke | Pavement Improvement | 07/20/2009 | 08/06/2009 | 12/01/2009 | 167439 | 2.6
4361 | Iowa | JACKSON |  | 1 | C049047 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2.6 miles of Jackson County Route D55 (300th St.) from ¼ mile east of U.S. Highway 61 east to 400 | Pavement Improvement | 07/20/2009 | 08/06/2009 | 12/01/2009 | 400000 | 2.5
4362 | Iowa | JASPER |  | 3 | C050087 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5.2 miles of Jasper County Route T38 from Mahaska/Jasper County line north to the Skunk River Brid | Pavement Improvement | 07/02/2009 | 09/14/2009 | 12/01/2009 | 850142 | 5.1
4363 | Iowa | JEFFERSON |  | 2 | C051043 | This project will replace a narrow bridge with a new bridge. The bridge is on County Road V64/Douds Road over Lick Creek approximately 3 miles South of Libertyville. | Bridge Replacement | 12/11/2009 | 04/12/2010 | 12/01/2010 | 347681 | 0.1
4364 | Iowa | JOHNSON |  | 2 | C052090 | This project will reconstruct approximately 0.8 miles of Johnson County Route F12 (120th St.) and 1.1 miles of Iowa Highway 965 near the city of Swisher. County Route F12 will be rebuilt from 925 fee | Pavement Improvement | 12/29/2009 | 04/19/2010 | 12/01/2010 | 556302 | 0.6
4365 | Iowa | JOHNSON |  | 2 | C052093 | This project consists of applying a concrete overlay on Johnson County Route W64 (Oak Crest Hill Road) from the Washington/Johnson County line northerly to the south city limit of Hills (approximately | Pavement Improvement | 12/14/2009 | 05/04/2010 | 12/01/2010 | 556302 | 0.8
4366 | Iowa | JOHNSON |  | 2 | C052094 | This project provides for construction of the 1.5 mile extension of Dubuque Street Trail along Dubuque Street (County Road W-66) from West Overlook Road northwest to 275th Street just southeast of th | Transportation Enhancements | 08/17/2009 | 09/07/2009 | 12/01/2009 | 252000 | 1.3
4367 | Iowa | JONES |  | 1 | C053066 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Jones County Route E34 (Fairview Rd.) from Quaker Ln. (just east of the ci | Pavement Improvement | 10/16/2009 | 04/08/2010 | 12/01/2010 | 863137 | 2.8
4368 | Iowa | KEOKUK |  | 3 | C054082 | This project will improve drainage along and under Keokuk County Route V5G by replacing multiple pipe culverts under the 2.8 miles of roadway from Iowa Highway 149 to Iowa Highway 78 in the city of Ol | Pavement Improvement | 08/24/2009 | 05/06/2010 | 12/01/2010 | 380278 | 11.2
4369 | Iowa | KOSSUTH |  | 4 | C055128 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 10 miles of Kossuth County Route R14 (240th Ave.) from U.S. Highway 18 (near the city of Wesley) n | Pavement Improvement | 07/28/2009 | 08/03/2009 | 12/01/2009 | 1428688 | 11
4370 | Iowa | LINN |  | 2 | C057102 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Linn County Route W45 (Troy Mills Rd.) from just north of Linn County Rout | Pavement Improvement | 05/20/2009 | 08/24/2009 | 12/01/2009 | 896785 | 2.7
4371 | Iowa | LOUISA |  | 2 | C058039 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 12.6 miles of Louisa County Route X99 from just east of the Iowa River Bridge (near the city of Wa | Pavement Improvement | 07/02/2009 | 09/14/2009 | 12/01/2009 | 1300000 | 12.5
4372 | Iowa | LUCAS |  | 3 | C059045 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 0.9 miles of Albia Road (475th Lane) in the city of Chariton from S. 5th Street southeasterly to U | Pavement Improvement | 10/21/2009 | 10/27/2009 | 12/01/2009 | 399000 | 1
4373 | Iowa | MADISON |  | 4 | C061083 | This project will provide an improved driving surface by applying an asphalt overlay to various locations on Madison County Route G4R (Cumming Road) between Quail Ridge Trail (approximately 6 miles no | Pavement Improvement | 06/03/2009 | 09/21/2009 | 12/01/2009 | 569170 | 3.5
4374 | Iowa | MAHASKA |  | 3 | C062066 | This project will replace the existing deteriorating pavement with new concrete pavement on approximately 2.2 miles of Osburn Avenue from Iowa Highway 23 to Iowa Highway 92 in Mahaska County. The new | Pavement Improvement | 06/02/2009 | 08/31/2009 | 12/01/2009 | 852647 | 2.1
4375 | Iowa | MARION |  | 3 | C063096 | This project will provide an improved driving surface by applying an asphalt overlay on Marion County Route G71 from Iowa Highway 5 southeasterly to the approximately ¼ mile north of 2nd Street in the | Pavement Improvement | 05/01/2009 | 05/07/2009 | 12/01/2009 | 314043 | 5
4376 | Iowa | MARION |  | 3 | C063097 | This project will provide an improved driving surface by applying an asphalt overlay on Marion County Route G76 from 1.5 miles east of Marion County Route S45 (southeast of the city of Melcher-Dallas) | Pavement Improvement | 05/01/2009 | 05/08/2009 | 12/01/2009 | 311651 | 1.5
4377 | Iowa | MARSHALL |  | 4 | C064109 | Marshall County will resurface 3.5 miles of County Road E-67 with new asphalt between Underwood and Yates Avenue west of the City of Gilman. This project will improve driving quality by providing a mo | Pavement Improvement | 05/14/2009 | 05/25/2009 | 12/01/2009 | 781815.52 | 3.5
4378 | Iowa | MILLS |  | 5 | C065074 | This project provides for reconstruction of two segments of the Wabash Trace Nature Trail through and near the cities of Silver City and Malvern both in Mills County. The first segment begins southea | Transportation Enhancements | 03/09/2010 | 05/24/2010 | 12/01/2010 | 547526.9 | 2.77
4379 | Iowa | MITCHELL |  | 4 | C066039 | Mitchell County will overlay 2 miles of County Road A-23 with new concrete between Walnut Avenue and Addison Avenue northeast of the City of McIntire. This project will improve driving quality and sig | Pavement Improvement | 05/21/2009 | 09/14/2009 | 12/01/2009 | 400000 | 2
4380 | Iowa | MONONA |  | 5 | C067062 | The project is located on Monona County Road (MCR) E60. Monona County is improving the existing gravel roadway with a drainage system and new gravel surface. The project is located approximately 3.6 | Pavement Improvement | 05/26/2009 | 07/06/2009 | 12/01/2009 | 456691.22 | 1.7
4381 | Iowa | MONROE |  | 3 | C068063 | Monroe County will widen and resurface 1.6 miles of County Road H-35 with new asphalt south of the City of Albia. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 06/16/2009 | 09/14/2009 | 12/01/2009 | 624000 | 1.6
4382 | Iowa | MONTGOMERY |  | 5 | C069039 | Montgomery County will overlay 1.7 miles of County Road H-54 with new concrete east of the City of Colburg to Iowa Highway 48. This project will improve driving quality and significantly extend the li | Pavement Improvement | 11/23/2009 |  | 12/01/2010 | 405610 | 2.2
4383 | Iowa | MUSCATINE |  | 2 | C070049 | Muscatine County will resurface 2.5 miles of County Road F-70 with new asphalt between County Road X-54 and Iowa Highway 38 north of the City of Muscatine. Four inches of the existing asphalt road wil | Pavement Improvement | 07/17/2009 | 10/26/2009 | 12/01/2009 | 733544 | 2.5
4384 | Iowa | PALO ALTO |  | 4 | C074092 | Palo Alto County will widen and resurface 2 miles of County Road N-20 with new asphalt between the northern city limits of Ruthven and the intersection of County Road B-25 and 355th Avenue. This proje | Pavement Improvement | 05/20/2009 | 09/22/2009 | 12/01/2009 | 659874 | 2
4385 | Iowa | PLYMOUTH |  | 5 | C075120 | Plymouth County will resurface 3 miles of County Road C-12 with new asphalt between County Road K-22 and County Road K-30 east of the City of Craig. Three inches of the existing asphalt road will be r | Pavement Improvement | 06/01/2009 | 06/01/2009 | 12/01/2009 | 375000 | 3
4386 | Iowa | PLYMOUTH |  | 5 | C075121 | Plymouth County will resurface 1 mile of County Road K-30 with new asphalt between County Road C-12 and 100th Street north of the City of Craig. Three inches of the existing asphalt road will be recyc | Pavement Improvement | 06/05/2009 | 06/01/2009 | 12/01/2009 | 125000 | 1
4387 | Iowa | PLYMOUTH |  | 5 | C075122 | Plymouth County will replace 5.4 miles of County Road K-22 with new concrete between the Woodbury County border and County Road C-60 north of the City of Sioux City. This project will improve driving | Pavement Improvement | 11/20/2009 | 04/07/2010 | 12/01/2010 | 1189278 | 5.5
4388 | Iowa | POLK | DES MOINES | 3 | C077168 | Polk County will resurface 5.7 miles of Northwest/Northeast 118th Avenue with new asphalt between Northwest Sheldahl Drive and U.S. Highway 69 east of the City of Polk City. This project will improve | Pavement Improvement | 05/06/2009 | 05/14/2009 | 12/01/2009 | 1950000 | 5.5
4389 | Iowa | POLK |  | 3 | C077169 | Polk County will resurface 3.5 miles of various city roads with new asphalt. Locations include Northwest 110th Avenue between Iowa Highway 17 and Northeast 121st Street northwest of the City of Des Mo | Pavement Improvement | 05/06/2009 | 05/14/2009 | 12/01/2009 | 418779 | 3.5
4390 | Iowa | POWESHIEK |  | 3 | C079041 | Poweshiek County will resurface 2.7 miles of County Road F-62 with new asphalt between the Jasper County border and Iowa Highway 146 west of the City of Searsboro. Four inches of the existing asphalt | Pavement Improvement | 07/06/2009 | 09/21/2009 | 12/01/2009 | 619700 | 3
4391 | Iowa | RINGGOLD |  | 5 | C080049 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road P64 over a tributary to Lotts Creek 3.7 miles Southwest of Kellerton. | Bridge Replacement | 08/12/2009 | 08/14/2009 | 12/01/2010 | 312555 | 0
4392 | Iowa | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 1 | C082039 | Scott County will resurface 5.1 miles of County Road Y-48 with new asphalt between Iowa Highway 22 and County Road F-65 west of the City of Davenport. This project will improve driving quality by prov | Pavement Improvement | 05/26/2009 | 06/18/2009 | 12/01/2009 | 2100000 | 4
4393 | Iowa | SCOTT |  | 1 | C082042 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road F33/St. Ann’s Road over Mason Creek approximately 3 miles Northwest of Long | Bridge Replacement | 09/21/2009 | 10/02/2009 | 12/01/2010 | 299524.5 | 0
4394 | Iowa | SCOTT |  | 1 | C082044 | The project is for the replacement of a Reinforced Concrete Box (RCB) Culvert, Single Box, by Scott County. The existing RCB Culvert had deteriorated, and the structure no longer serves the drainage | New Bridge Construction | 09/21/2009 | 09/26/2009 | 12/01/2010 | 134516 | 0.09
4395 | Iowa | SCOTT |  | 1 | C082046 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road Y48/Maysville Road over Hickory Creek approximately 1.5 miles Southeast of M | Bridge Replacement | 09/28/2009 | 03/24/2010 | 06/01/2010 | 288203.93 | 0.02
4396 | Iowa | SHELBY |  | 5 | C083046 | Shelby County will resurface 5.6 miles of County Road F-58 with new asphalt between Maple Road and County Road M-47 south of the City of Harlen. This project will improve driving quality by providing | Pavement Improvement | 08/17/2009 | 08/24/2009 | 12/01/2010 | 1400000 | 5.6
4397 | Iowa | SIOUX |  | 5 | C084130 | Sioux County will resurface 4.9 miles of County Road L-14 with new asphalt between U.S. Highway 18 and the Lyon County border north of the City of Boyden. Three inches of the existing asphalt road wil | Pavement Improvement | 05/18/2009 | 07/27/2009 | 12/01/2009 | 1052216 | 5
4398 | Iowa | SIOUX |  | 5 | C084132 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Harrison Avenue over a small stream 1 mile east and 3.5 miles South of Maurice. | Bridge Replacement | 05/18/2009 | 08/03/2009 | 12/01/2009 | 330396.12 | 0.01
4399 | Iowa | STORY |  | 4 | C085102 | Story County will resurface 4 miles of County Road E-29 with new asphalt between U.S. Highway 65 and the Marshall County border north of the City of Colo. This project will improve driving quality by | Pavement Improvement | 05/20/2009 | 07/20/2009 | 12/01/2009 | 858307 | 4
4400 | Iowa | TAMA |  | 3 | C086074 | Tama County will resurface 9.8 miles of various county roads south of the City of Tama with new asphalt. Locations include County Road E-69 between Iowa Highway 146 and U.S. Highway 63, and County Roa | Pavement Improvement | 06/17/2009 | 08/03/2009 | 12/01/2009 | 966635.42 | 10
4401 | Iowa | TAYLOR |  | 5 | C087037 | This project will install longitudinal subdrains along both sides of the existing roadway for Taylor County Road N44 from the Missouri State Line north for 4.3 miles to Taylor County Road J55. The su | Pavement Improvement | 01/12/2010 |  | 12/01/2010 | 201766 | 3.5
4402 | Iowa | TAYLOR |  | 5 | C087038 | This project will install longitudinal subdrains along both sides of the existing roadway for Taylor County Road P14 from the Missouri State Line north for 2.7 miles to Taylor County Road J55 and on T | Pavement Improvement | 01/12/2010 |  | 12/01/2010 | 152496 | 3.5
4403 | Iowa | UNION |  | 5 | C088040 | Union County will resurface 3 miles of County Road P-33 with new asphalt between County Road H-17 and Adair-Union Street north of the City of Creston. This project will improve driving quality by prov | Pavement Improvement | 05/12/2009 | 05/19/2009 | 12/01/2009 | 437751 | 3
4404 | Iowa | VAN BUREN |  | 2 | C089057 | Van Buren County will remove the top three inches of existing pavement on County Road V-64 and resurface it with new asphalt between Iowa Highway 16 and the Jefferson-Van Buren County line west of the | Pavement Improvement | 05/14/2009 | 06/03/2009 | 12/01/2009 | 320993 | 3.4
4405 | Iowa | WAPELLO |  | 2 | C090060 | Wapello County will resurface 3.8 miles of various county roads near the City of Ottumwa with new asphalt. Locations include County Road H-21 between Blackhawk Road and County Road H-27, and County Ro | Pavement Improvement | 05/15/2009 | 05/08/2009 | 12/01/2009 | 423752 | 12.5
4406 | Iowa | WARREN |  | 4 | C091081 | Warren County will resurface 3.2 miles of County Road S-23 with new asphalt between County Road G-24 and Iowa Highway 5 west of the City of Hartford. This project will improve driving quality by provi | Pavement Improvement | 05/18/2009 | 06/08/2009 | 12/01/2009 | 576146 | 3.2
4407 | Iowa | WASHINGTON |  | 2 | C092075 | Washington County will overlay 4.2 miles of County Road W-64 with new concrete between 160th Street and Iowa Highway 22 east of the City of Riverside. This project will improve driving quality and sig | Pavement Improvement | 05/14/2009 | 08/24/2009 | 12/01/2009 | 732691 | 5.6
4408 | Iowa | WEBSTER |  | 4 | C094082 | This project will repair a bridge, which is in poor condition, by replacing the bridge deck. The bridge is on County Road C66 over Lizard Creek 5 miles West of Clare. | Bridge Improvement | 07/01/2009 | 07/20/2009 | 12/01/2009 | 350000 | 0.06
4409 | Iowa | WEBSTER |  | 4 | C094083 | Webster County will resurface 2.4 miles of County Road D-14 with new asphalt between U.S. Highway 169 and County Road P-56 north of the City of Wahkonsa. This project will improve driving quality by p | Pavement Improvement | 02/11/2010 |  | 12/01/2010 | 934867 | 2.5
4410 | Iowa | WINNEBAGO |  | 4 | C095055 | Winnebago County will resurface 3.7 miles of County Road R-60 with new asphalt between U.S. Highway 69 and the southern city limits of Scarville. This project will improve driving quality by providing | Pavement Improvement | 05/13/2009 | 06/15/2009 | 12/01/2009 | 532664.81 | 3.7
4411 | Iowa | WINNESHIEK |  | 4 | C096101 | Winneshiek County will overlay 2.2 miles of County Road V-68 with new concrete between the Fayette County border and Iowa Highway 24 in the City of Jackson Junction. This project will improve driving | Pavement Improvement | 05/21/2009 | 05/28/2009 | 12/01/2009 | 664000 | 2.2
4412 | Iowa | WOODBURY |  | 5 | C097107 | This project will mill and place three and a half inches of hot-mix asphalt for 1.6 miles of Correctionville Road from Sioux City’s city limits to just past Buchanan Ave. The project will create a sm | Pavement Improvement | 05/26/2009 | 07/14/2009 | 12/01/2009 | 639833 | 1.8
4413 | Iowa | WOODBURY |  | 5 | C097108 | This project will mill and place four inches of pavement on county road L-37 for approximately 10.7 miles from near Danbury, IA to county road D-38. The project will improve pavement condition and sa | Pavement Improvement | 06/02/2009 | 08/24/2009 | 12/01/2009 | 500000 | 10
4414 | Iowa | WORTH |  | 4 | C098050 | This project places a concrete overlay on a bridge deck to extend the service life of the bridge. The bridge is located on 410th Street over the Shell Rock River 1.5 miles east of Kensett. | Bridge Improvement | 08/12/2009 | 04/14/2010 | 12/01/2010 | 48418 | 0.03
4415 | Iowa | WORTH |  | 4 | C098051 | This project places a concrete overlay on a bridge deck to extend the service life of the bridge. The bridge is located on 495th Street over the Shell Rock River approximately 1 mile West and 2.5 mil | Bridge Improvement | 08/12/2009 | 04/14/2010 | 12/01/2010 | 32696 | 0.02
4416 | Kansas | SEDGWICK | WICHITA | 04 | 1351209 | This project will reconstruct the I-135/KTA/47th St. interchange and 47th St from Broadway to Lulu St in the city of Wichita. This work will improve traffic capacity, operation and safety on these ro | Pavement Widening | 08/20/2009 | 08/20/2009 | 02/24/2011 | 17131901.18 | 0.001
4417 | Kansas | WYANDOTTE | KANSAS CITY (MO) | 03 | 4353359 | This project will widen and reconstruct Woodend Avenue to provide additional turn lanes in the city of Edwardsville in Wyandotte County. This work will improve traffic capacity, operations, and safe | Pavement Improvement | 03/01/2010 | 03/01/2010 | 09/14/2011 | 775000 | 0.001
4418 | Kansas | RILEY |  | 02 | A041003 | This project will construct a 4-Lane Freeway Section on K-18 in Riley County with an interchange at K-114. This work will improve traffic capacity, operation and safety along K-18. | Pavement Widening | 02/10/2010 | 02/10/2010 | 12/31/2012 | 64118465.74 | 3.866
4419 | Kansas | SEDGWICK | WICHITA | 04 | A100604 | This project will reconstruct 47th Street from Lulu Street to Hydraulic Avenue in the city of Wichita from a 4-lane to 5-lane roadway. This reconstruction will increase both capacity and safety relat | Pavement Improvement | 06/07/2010 | 06/07/2010 | 05/06/2011 | 650000 | 0
4420 | Kansas | STATEWIDE |  | 04 | A116910 | This project will provide skill training for women and minorities in highway construction work in central Kansas for Federal Fiscal Year 2010. | Other | 09/24/2009 | 09/24/2009 |  | 224600 | 0
4421 | Kansas | OSAGE |  | 02 | A120102 | This project will replace an abandoned RR bridge with a pedestrian bridge that is part of the KANZA Rails to Trails Conservancy trail network in Osage Co. This work will improve safety for trails use | Transportation Enhancements | 06/01/2010 | 06/01/2010 | 10/19/2010 | 956867.52 | 0.001
4422 | Kansas | GOVE |  | 01 | A153401 | This project will replace the pavement on K-23, provide a 28 ft. roadway and replace guardrail as warranted to improve safety along K-23 in Gove County. | Pavement Improvement | 02/23/2009 | 02/23/2009 | 09/06/2010 | 3823789.37 | 8
4423 | Kansas | GOVE |  | 01 | A153402 | This project will replace the pavement on K-23, provide a 28 ft. roadway and replace guardrail as warranted to improve safety along K-23 in Gove County. | Pavement Improvement | 03/25/2010 | 03/25/2010 | 08/15/2010 | 4500749.94 | 9.6
4424 | Kansas | STATEWIDE |  | 01 | A181001 | The project will improve defects in approximately 42 bridges along the NKCR route in northwest Kansas and rehabilitate the approach track to these bridges as warranted. | Safety/Traffic Management | 03/15/2010 | 04/19/2010 | 09/30/2010 | 343825.05 | 0
4425 | Kansas | REPUBLIC |  | 01 | A181201 | This project construct 2000 ft. of siding and a new switch into the Nesika Energy Plant in the city of Scandia that will enable the Nesika Energy Plant to ship by rail and access national markets for | Safety/Traffic Management | 04/19/2010 | 04/19/2010 | 07/02/2010 | 351392.51 | 0
4426 | Kansas | SEDGWICK | WICHITA | 04 | A181401 | This project will add 7,200 ft. of rail siding/pass track that will improve rail traffic flow and increase operation efficiency for elevators outside the city of Wichita. | Safety/Traffic Management | 04/26/2010 | 04/26/2010 | 06/12/2010 | 967820 | 0
4427 | Kansas | RENO |  | 01 | A183901 | This project will construct storage tracks at the Siemens Nachelle Facility in the city of Hutchinson that will enable the company to ship by rail and provide for a more efficient operation. | Safety/Traffic Management | 03/03/2010 |  | 02/22/2012 | 844800 | 0
4428 | Kansas | COMANCHE |  | 01 | C421801 | This project will replace a bridge on County Road 155, 1.0 mile West of Coldwater in Comanche County - improving structural and/or safety concerns. | Bridge Replacement | 11/01/2009 | 11/01/2009 | 05/05/2010 | 320027.86 | 0
4429 | Kansas | COWLEY |  | 04 | C422001 | This project will provide a 2 inch asphalt overlay on County Road 164 from Udall to County Road 18 in Cowley County, improving rideability and surface condition. | Pavement Improvement | 08/14/2009 | 08/14/2009 | 11/03/2009 | 877500 | 0
4430 | Kansas | ELLIS |  | 01 | C422801 | This project will replace a bridge 5.6 miles South and 0.8 miles West of the city of Walker in Ellis County - improving structural and/or safety concerns. | Bridge Replacement | 10/28/2009 | 11/16/2009 | 05/24/2010 | 491587.92 | 0
4431 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | C424801 | This project will replace a bridge on 143rd Street over Captain Creek in Johnson County - improving structural and/or safety concerns. | Bridge Replacement | 03/01/2010 | 03/01/2010 | 09/27/2010 | 798718.53 | 0
4432 | Kansas | DICKINSON |  | 01 | C447801 | This project will replace a bridge on Old US Highway 40, 3.5 miles West of Highway 15 in Dickinson County - improving structural and/or safety concerns. | Pavement Improvement | 01/01/2010 | 01/11/2010 | 11/05/2010 | 644400 | 0
4433 | Kansas | SHAWNEE | TOPEKA | 02 | C448901 | This project is a storm sewer and culvert project on NorthWest 46th Street Between US Highway 75 and NorthWest Fielding Road in Shawnee County that will improve drainage. | Pavement Widening | 03/01/2010 | 03/10/2010 | 11/05/2010 | 2203448.42 | 0
4434 | Kansas | ATCHISON |  | 02 | C453901 | This project will replace a bridge 4.0 miles North and 4.4 miles East of the city of Shannon in Atchison County - improving structural and/or safety concerns. | Bridge Replacement | 11/18/2009 | 11/18/2009 | 09/10/2010 | 216000 | 0
4435 | Kansas | WABAUNSEE |  | 01 | C454901 | This project will replace a bridge 5.0 miles East and 0.9 miles North of Eskridge in Wabaunsee County - improving structural and/or safety concerns. | Bridge Replacement | 03/30/2010 | 03/30/2010 | 06/07/2011 | 353424.91 | 0
4436 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | C455101 | This project will redeck a bridge 1.4 miles East of the city of Jarbalo in Leavenworth County - improving surface conditions. | Bridge Replacement | 09/01/2009 | 09/01/2009 | 02/08/2011 | 399943.07 | 0
4437 | Kansas | BARBER |  | 01 | C455201 | This project will replace a bridge 2.0 miles East of the city of Hazelton on Rural Secondary Route 1381 - improving structural and/or safety concerns. | Bridge Replacement | 11/02/2009 | 11/19/2009 | 04/12/2011 | 292272 | 0
4438 | Kansas | POTTAWATOMIE |  | 02 | C455301 | This project will rehabilitate a bridge 2.0 miles North of the city of Manhattan Over the Big Blue River in Pottawatomie County - improving structural and/or safety concerns. | Bridge Replacement | 12/17/2009 | 12/17/2009 | 04/12/2011 | 478800 | 0
4439 | Kansas | ROOKS |  | 01 | C455401 | This project resurfaces 2.6 Miles of Rural Secondary Route 916 and 1729 in the City of Woodston in Rooks County - improving surface conditions. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 02/08/2011 | 310000 | 0
4440 | Kansas | HARPER |  | 04 | C455501 | This project will provide a 4-inch overlay on NE 160th Road (Rural Secondary Route 641) near the city of Conway Springs in Harper County - improving surface conditions. | Pavement Improvement | 03/02/2010 | 03/02/2010 | 03/08/2011 | 510000 | 0
4441 | Kansas | KINGMAN |  | 04 | C455601 | This project will provide a 2-inch overlay on Rural Secondary Route 1704 (vicinity of US-54 South) in Kingman County - improving surface conditions. | Pavement Improvement | 11/23/2009 | 06/03/2010 | 04/12/2011 | 369381.39 | 0
4442 | Kansas | RICE |  | 01 | C455701 | This project will provide a 2-inch mill (removal of exiting pavement) and asphalt overlay on Main Street ( Rural Secondary Route 983) in the city of Bushton in Rice County - improving surface conditio | Pavement Improvement | 02/19/2010 | 02/19/2010 | 05/09/2011 | 367000 | 0
4443 | Kansas | BUTLER |  | 04 | C455801 | This project will rehabilitate a bridge 1.5 miles West of the city of Benton and 1.7 miles North over the White Water Creek in Butler County - improving structural and/or safety concerns. | Pavement Improvement | 03/01/2010 | 03/01/2010 | 09/13/2010 | 687750 | 0
4444 | Kansas | RENO |  | 01 | C455901 | This project will provide an asphalt overlay on 4th Avenue (Rural Secondary Route-636) from K-14 E to K-96 4th Avenue Interchange in Hutchinson in Reno County - improving surface conditions. | Pavement Improvement | 12/02/2009 | 06/18/2010 | 04/12/2011 | 517593 | 0
4445 | Kansas | HARVEY |  | 04 | C456001 | This project will replace a bridge on Kansas Avenue, 1.1 miles North and 0.5 miles East of Newton, in Harvey County - improving structural and/or safety concerns. | Bridge Replacement | 04/16/2010 | 04/16/2010 | 07/11/2011 | 575000 | 0
4446 | Kansas | BARTON |  | 01 | C456101 | This project will provide a maintenance resurfacing of Rural Secondary Route 462 from Great Bend West city limits West to NorthWest 60th Avenue in Great Bends in Barton County - improving surface cond | Pavement Improvement | 03/08/2010 | 03/30/2010 | 03/08/2011 | 560000 | 0
4447 | Kansas | ANDERSON |  | 02 | C456201 | This project will rehabilitate a bridge on Rural Secondary Route1389 4.0 miles South and 1.7 miles East of the city of Harris in Anderson County - improving structural and/or safety concerns. | Bridge Improvement | 07/31/2009 | 07/31/2009 | 05/17/2011 | 55586.45 | 0
4448 | Kansas | CHAUTAUQUA |  | 04 | C456301 | This project will provide a 2.5-inch asphalt overlay on Independence Road (Rural Secondary Route 97) for 3.5 Miles in Chautauqua County - improving surface conditions. | Pavement Improvement | 08/27/2009 |  | 01/04/2011 | 442596.26 | 0
4449 | Kansas | FRANKLIN |  | 02 | C456501 | This project will provide a 2-inch asphalt overlay on John Brown Road (Rural Secondary Route 1066/259) Between Kentucky Road and Florida in Franklin County - improving surface conditions. | Pavement Improvement | 08/27/2009 | 08/27/2009 | 01/04/2011 | 485468.4 | 0
4450 | Kansas | GREENWOOD |  | 04 | C456601 | This project will provide a 2-inch asphalt overlay on Rural Secondary Route 291 from the city of Hamilton to the city of Virgil in Greenwood County - improving surface conditions. | Pavement Improvement | 10/22/2009 | 10/22/2009 | 01/04/2011 | 490000 | 0
4451 | Kansas | ELK |  | 04 | C456701 | This project will provide an asphalt resurfacing of Kansas Street in the city of Longton from US Highway 160 to 6th Street - improving surface conditions. | Pavement Improvement | 08/07/2009 | 11/11/2009 | 01/04/2011 | 120751.89 | 0
4452 | Kansas | LINCOLN |  | 01 | C456801 | This project will provide grading and drainage structure work on Rural Secondary Route 394 (3.5 miles North of K-18 North of the city of Beverly) in Lincoln County - improving structural and drainage | Pavement Improvement | 03/01/2010 | 03/01/2010 | 04/12/2011 | 111629.38 | 0
4453 | Kansas | ELLSWORTH |  | 01 | C456901 | This project will provide an asphalt overlay on Low Road from the city of Ellsworth to the city of Kanopolis in Ellsworth County - improving surface conditions. | Pavement Improvement | 01/11/2010 | 01/11/2010 | 03/08/2011 | 493000 | 0
4454 | Kansas | MORRIS |  | 01 | C457001 | This project will provide a bridge rehabilitation (to include abutment, deck repair, and patching on the Bridge Over Rock Creek, 0.3 Miles North of the city of Dunlap, in Morris County - improving sur | Bridge Replacement | 03/11/2010 | 03/11/2010 | 04/12/2011 | 218500 | 0
4455 | Kansas | MARION |  | 01 | C457101 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on Cedar Street from Hudson North to US-56 in the city of Marion in Marion County - improving surface conditions. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 05/09/2011 | 168000 | 0
4456 | Kansas | MITCHELL |  | 01 | C457201 | This project will provide crack repair and an asphalt overlay of Rural Secondary Routes 466 and 1029 south of the city of Glen Elder - improving surface conditions. | Pavement Improvement | 03/25/2010 | 03/25/2010 | 02/08/2011 | 465350 | 0
4457 | Kansas | WASHINGTON |  | 01 | C457301 | This project will provide grading and resurfacing of Rural Secondary Route 1100 through the city of Hanover from K-234 in Washington County - improving surface deficiencies and conditions. | Pavement Improvement | 04/26/2010 | 04/26/2010 | 04/12/2011 | 351000 | 0
4458 | Kansas | SALINE |  | 01 | C457401 | This project will replace a bridge on Kipp Road 0.1 miles North and 0.5 miles East of the city of Kipp in Saline County - improving structural and/or safety concerns. | Bridge Replacement | 01/01/2010 | 02/01/2010 | 03/08/2011 | 315000 | 0
4459 | Kansas | HAMILTON |  | 01 | C457501 | This project will provide a 3 inch overlay for 2 miles of Rural Secondary Road 308 from US Highway 50 south for 2 miles in Hamilton County -- improving surface conditions. | Pavement Improvement | 04/26/2010 |  | 09/05/2011 | 370307.4 | 0
4460 | Kansas | SCOTT |  | 01 | C457901 | This project will provide a 4-inch overlay of Federal Aid Secondary route 1898 2 miles West of K-95 Highway in Scott County - improving surface conditions. | Pavement Improvement | 08/18/2009 | 08/18/2009 | 02/08/2011 | 461897.23 | 0
4461 | Kansas | NEOSHO |  | 02 | C458001 | This project will provide grading, surfacing, and bridge work on Rural Secondary Route 168 East of Shaw Road for 3.5 miles in Neosho County - improving surface and structural conditions. | Pavement Improvement | 03/15/2010 | 03/15/2010 | 09/27/2010 | 500000 | 0
4462 | Kansas | SEDGWICK | WICHITA | 04 | C458101 | This project will provide milling and asphalt overlay on Rock Road from Oak Knoll 5.5 miles North of 63rd Street South in Wichita area in Sedgwick County - improving surface conditions. | Pavement Improvement | 05/20/2010 | 06/21/2010 | 04/12/2011 | 1316216.22 | 0
4463 | Kansas | SEDGWICK | WICHITA | 04 | C458401 | This project will provide a mill and overlay to 295th Street in Sedgwick County west from 21st Street to 61st Street north - improving surface condition | Pavement Improvement | 05/20/2010 | 06/14/2010 | 09/06/2011 | 724500 | 0
4464 | Kansas | STATEWIDE |  | 02 | K507010 | This project will provide skill training for women and minorities in highway construction work in northeast Kansas for Federal Fiscal Year 2010. | Other | 11/03/2009 | 11/03/2009 |  | 200402 | 0
4465 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | K825107 | This project will add two lanes, reconstruct the 95th Street interchange and add noise walls to selected section in the city of Overland Park. This work will improve traffic capacity, operation and s | Pavement Widening | 06/05/2009 | 06/05/2009 | 01/10/2012 | 31966458.83 | 1.841
4466 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | K825111 | This project will add two lanes & reconstruct US-69 and widen I-35 in the city of Overland Park. This work will improve traffic capacity, operation and safety on US-69 and I-35. | Pavement Widening | 06/26/2001 | 06/26/2001 | 01/11/2012 | 51977795.54 | 1.137
4467 | Kansas | MCPHERSON |  | 01 | K825301 | This project will construct a 4-Lane partial access controlled improvement with a bypass at the city of Inman. This work will improve traffic capacity, operation and safety along K-61. | Pavement Widening | 05/06/2009 | 05/06/2009 | 11/23/2011 | 36046133.16 | 7.43
4468 | Kansas | MCPHERSON |  | 01 | K825302 | This project will construct a 4-Lane partial access controlled improvement. This work will improve traffic capacity, operation and safety along K-61. | Pavement Widening | 05/06/2009 | 05/06/2009 | 11/23/2011 | 36839656.44 | 7.06
4469 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | K921806 | This project will extend operation of the Operation Green Light System to improve intersection traffic signal coordination on regional arterial routes in the bi-state Kansas City Metropolitan area. I | Other | 07/28/2009 | 07/28/2009 | 07/04/2011 | 1000000 | 0
4470 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N037301 | This project will widen College Blvd from 4 to 6 lanes from Pflumm Road to US-69 in Overland Park in Johnson County - improving both capacity and safety. | Pavement Widening | 06/25/2009 |  | 09/08/2009 | 1000000 | 0
4471 | Kansas | BUTLER | WICHITA | 04 | N039001 | This project will improve Andover Road to 5 lanes with a center turn lane, curb and gutter, and a 10-ft bide/ped sidewalk from Harry Street to 1100 Feet South of US-54 in the city of Andover in Butler | Pavement Widening | 09/18/2009 | 09/18/2009 | 07/09/2010 | 1234800 | 0
4472 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N046701 | This project will widen 87th Street from 4 to 6 lanes from Renner Blvd. to Ridgeview Road in the city of Lenexa in Johnson County - improving capacity and safety. | Pavement Widening | 12/07/2009 | 12/15/2009 | 09/10/2010 | 3000000 | 0
4473 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N047801 | This project will reconstruct the existing 127th Street from 2 lanes to 4 lanes from Mur-Len to Black Bob in the city of Olathe in Johnson County - improving both capacity and safety. | Pavement Widening | 02/16/2010 |  | 02/03/2011 | 3500000 | 0
4474 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N047901 | This project will remove and replace curb and sidewalks, mill and overlay, and replace traffic loops on 103rd Road from State Line Road to Mission Road in the city of Leawood in Johnson County - impro | Pavement Improvement | 06/07/2010 | 06/07/2010 | 09/05/2011 | 925305.34 | 0
4475 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N048001 | This project will convert 4-lane cross section to 3-lane, install sidewalks & curbs, mill and resurface Roe Avenue from West 63rd Street North to Shawnee Mission Parkway in the city of Mission in John | Pavement Improvement | 03/29/2010 | 03/29/2010 | 08/16/2010 | 921921 | 0
4476 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N048101 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on College Blvd From Benson Street to Nall Avenue in the city of Overland Park in Johnson County - improving surface | Pavement Improvement | 10/06/2009 | 10/06/2009 | 07/02/2010 | 2800000 | 0
4477 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N048201 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on Merriam Drive from Johnson Drive to Shawnee Mission Parkway in the city of Merriam in Johnson County -- improving | Pavement Improvement | 06/15/2010 |  | 07/20/2010 | 150000 | 0
4478 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N048301 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on Merriam Drive From 57th Street to Antioch Road in the city of Merriam in Johnson County -- improving surface cond | Pavement Improvement | 06/16/2010 |  | 07/28/2010 | 299236.84 | 0
4479 | Kansas | WYANDOTTE | KANSAS CITY (MO) | 03 | N048501 | This project will remove and replace curbs, inlets, guardrails, concrete medians and rehabilitate the pavement on State Avenue from 69th Street to 47th Street - improving surface conditions, drainage, | Pavement Improvement | 01/19/2010 | 03/15/2010 | 05/09/2011 | 4568618.34 | 0
4480 | Kansas | SEDGWICK | WICHITA | 04 | N048701 | This project will replace 148-ft bridge with flood wall across Chisholm Creek N of 49th Street N of Broadway Avenue in the city of Park city in Sedgwick County. | Bridge Replacement | 02/02/2010 | 02/04/2010 | 05/09/2011 | 1596946.71 | 0
4481 | Kansas | SEDGWICK | WICHITA | 04 | N048801 | This project will provide a full-depth reconstruction of the roadway to the bottom of the base, adding 7 inches of pavement, and striping of West Grand Ave. from Meridian Ave. to North Main Street in | Pavement Improvement | 08/12/2009 | 04/05/2010 | 05/09/2011 | 797723.03 | 0
4482 | Kansas | WYANDOTTE | KANSAS CITY (MO) | 03 | N049001 | This is a roadway reconstruction project with curb and gutter, storm drainage, and sidewalks on South 138th Street From Metro Avenue North to Kansas in the city of Bonner Springs in Wyandotte County - | New Construction | 04/01/2010 | 04/01/2010 | 05/09/2011 | 158362.69 | 0
4483 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N049101 | This project will provide improvements (signals, raised medians, markings, etc.) to the existing Intersection of US56 and Old 56 Highway in the city of Gardner in Johnson County - improving safety. | Pavement Improvement | 03/01/2010 | 03/01/2010 | 05/09/2011 | 422833.76 | 0
4484 | Kansas | SEDGWICK | WICHITA | 04 | N049701 | This project will provide a mill (removal of existing pavement) and overlay of Broadway-Central to 12th Street in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 04/12/2010 |  | 04/25/2011 | 486000 | 0
4485 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N049801 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on 55th Street from Merriam Drive to Switzer Road in the city of Merriam in Johnson County -- improving surface con | Pavement Improvement | 06/17/2010 |  | 08/05/2010 | 50000 | 0
4486 | Kansas | SEDGWICK | WICHITA | 04 | N049901 | This project will resurface Madison Avenue Between K-15 and Rock Road in the city of Derby in Sedgwick County - improving surface conditions. | Pavement Improvement | 05/05/2010 | 05/05/2010 | 03/08/2011 | 409069.73 | 0
4487 | Kansas | SEDGWICK | WICHITA | 04 | N050001 | This project will provide concrete pavement replacement on Hillside from 9th Street to 12 Street in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 12/01/2009 | 12/01/2009 | 04/25/2011 | 864000 | 0
4488 | Kansas | SEDGWICK | WICHITA | 04 | N050101 | This project will provide concrete pavement replacement on Washington from 1st Street to Central Avenue in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 01/11/2010 | 01/11/2010 | 04/25/2011 | 432000 | 0
4489 | Kansas | SEDGWICK | WICHITA | 04 | N050201 | This project will reconstruct the existing 2-lane asphalt mat to a 5-lane road (including sidewalks, signals, and drainage) on Maize Road from Pawnee Avenue to Kellogg in the city of Wichita in Sedgwi | New Construction | 02/01/2010 |  | 06/08/2011 | 3530657.13 | 0
4490 | Kansas | SEDGWICK | WICHITA | 04 | N050301 | This project will reconstruct the existing 2-lane facility to a 3-lane road (including sidewalks and drainage) on Hydraulic Avenue from Harry Street to Kellogg in city of Wichita in Sedgwick County - | New Construction | 02/08/2010 |  | 10/01/2010 | 2910519.3 | 0
4491 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | N050501 | This project will provide a mill (removal of existing pavement) and overlay (to include curbs, sidewalks, ADA ramps, repairing bridge approaches on 83rd Street from Hedge Lane Terrace to Monticello Te | Pavement Improvement | 05/17/2010 | 05/17/2010 | 05/11/2011 | 164760.7 | 0
4492 | Kansas | SEDGWICK | WICHITA | 04 | N051401 | This project will be providing surfacing improvements to Harry Street from Greenwich Road to 127th Street in the City of Wichita -- improving rideability and safety. | New Construction | 05/10/2010 | 05/10/2010 | 09/05/2011 | 999836.86 | 0
4493 | Kansas | FORD |  | 01 | T032501 | This project will construct a pedestrian/bike path along US-50 from 14th Street East to 6th Avenue in Dodge City in Ford County. | Transportation Enhancements | 05/14/2010 | 05/14/2010 | 07/26/2011 | 460000 | 0
4494 | Kansas | NEOSHO |  | 02 | T033101 | This project will provide improvements to downtown Erie, KS along Main St from Fourth St, north to State St, then west on State St to US Highway 59, to include brick paver accents, curb and gutter, li | Transportation Enhancements | 10/16/2009 | 10/16/2009 | 11/03/2010 | 632470.42 | 0
4495 | Kansas | GREENWOOD |  | 04 | T033401 | Restore part of the interior and exterior and establish a transportation museum/welcome center in the former bus depot of the Greenwood Hotel at 300 N Main | Transportation Enhancements | 09/10/2009 | 09/10/2009 | 01/04/2011 | 1155186.65 | 0
4496 | Kansas | FRANKLIN |  | 02 | T033801 | This project will rehabilitate six railroad trestles, in various stages of disrepair, on the Midland Railway track located between Montana and Pawnee Roads in Franklin County. | Transportation Enhancements | 02/03/2010 | 02/03/2010 | 10/04/2010 | 293609 | 0
4497 | Kansas | DOUGLAS | LAWRENCE | 03 | T033901 | This project will remove an existing asphalt overlay, provide restoration of historic brick streets and reconstruction of four intersections on New York Street from 9th Street to 12th Street in Lawren | Transportation Enhancements | 12/21/2009 | 12/21/2009 | 10/04/2010 | 703341.7 | 0
4498 | Kansas | RILEY |  | 02 | T034001 | Restore portions of interior of the historic Isaac Goodnow house in Manhattan, KS including stabilization work on the stairs & interior walls & surface restoration with historically appropriate plaste | Transportation Enhancements | 11/19/2009 | 11/19/2009 | 10/04/2010 | 114519 | 0
4499 | Kansas | RICE |  | 01 | T034101 | This project will install 2 brick masonry Welcome Portal Signs on the north & south entrances to the city on Broadway (K-14, K-96) with landscaping & a concrete walkway along the west side of Broadway | Transportation Enhancements | 04/09/2010 | 04/09/2010 | 12/02/2010 | 69390 | 0
4500 | Kansas | STEVENS |  | 01 | T034201 | Project to provide new sidewalks w/ brick pavers, lighting, raised planters, ADA ramps, crosswalks, landscaping, irrigation, fence, benches & trash cans along Main St (US Hwy 56) from 5th to 7th St & | Transportation Enhancements | 11/20/2009 | 11/20/2009 | 10/04/2010 | 1255179.41 | 0.001
4501 | Kansas | WYANDOTTE | KANSAS CITY (MO) | 03 | T034401 | This project will provide streetscape improvements from the Kansas Highway 7 off ramp, along Front Street (Kansas Highway 32) to Elm Street, in Bonner Springs, Kansas, and will include decorative stre | Transportation Enhancements | 12/14/2009 | 12/14/2009 | 11/03/2010 | 245428.5 | 0
4502 | Kansas | MIAMI |  | 02 | T034501 | Project will include concrete & concrete paver sidewalk surface w/ retaining wall, trash cans, bike rack, lighting, signing, pavement markings and landscape improvements to downtown Osawatomie, KS alo | Transportation Enhancements | 01/14/2010 | 01/14/2010 | 10/04/2010 | 649940 | 0
4503 | Kansas | FRANKLIN |  | 02 | T034601 | This project will provide lighting along the Prairie Spirit Rail Trail between 5th and 23rd Streets a distance of up to approximately 11,300 linear feet, in Ottawa, KS, with the installation of L.E.D | Transportation Enhancements | 02/08/2010 | 02/08/2010 | 11/03/2010 | 153500 | 0
4504 | Kansas | DOUGLAS | LAWRENCE | 02 | T034701 | This project will remove an existing six-foot asphalt path and construct a ten-foot concrete path on the south side of Clinton Parkway from east of Wakarusa Drive to K-10 highway in Lawrence, Kansas. | Transportation Enhancements | 12/18/2009 | 12/18/2009 | 10/04/2010 | 800750 | 0
4505 | Kansas | SEDGWICK | WICHITA | 04 | T034801 | This project will construct a concrete ped/bike path from 111th St, along the Mulvane Sports Complex (MSC), then connect to existing path & another path section from 111th St south along Webb Road to | Transportation Enhancements | 10/19/2009 | 10/19/2009 | 10/04/2010 | 159588.58 | 0
4506 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | T035001 | This project will construct a 1.3 mile extension of the South Indian Creek Trail, from Southdowns Park, to Hampton Park & an extension of 159th St trail to connect to Chisholm Trail Jr High, & include | Transportation Enhancements | 01/26/2010 | 01/26/2010 | 12/02/2010 | 593025.55 | 0
4507 | Kansas | HARVEY |  | 04 | U000401 | This project will provide resurface and rehabilitation on the Main Street Bridge in Halstead in Harvey County - improving structural and surface conditions. | Bridge Improvement | 05/10/2010 | 05/10/2010 | 06/28/2010 | 166170.95 | 0
4508 | Kansas | DOUGLAS | LAWRENCE | 03 | U204101 | This project will be a reconstruction of the Intersection of North 2nd Street and Locust Street in the City of Lawrence in Douglas County - improving surface condition and safety. | Safety/Traffic Management | 07/20/2009 | 07/28/2009 | 10/13/2010 | 2000000 | 0
4509 | Kansas | JOHNSON | KANSAS CITY (MO) | 03 | U214201 | This project will remove and replace concrete approach lanes, provide a mill (removal of existing pavement) and overlay, and make ADA modifications on US-56 to 47th Street on US-169 (Rainbow BLVD) in | Pavement Improvement | 03/15/2010 | 03/15/2010 | 06/01/2011 | 1053559.52 | 0
4510 | Kansas | JOHNSON | KANSAS CITY (MO) | 02 | U223201 | This project will provide a variable mill (removal of existing pavement) and overlay on RS-348 (Nelson/ West 8th Street) From RailRoad to Morgan Street in the city of Edgerton in Johnson County - impr | Pavement Improvement | 10/22/2009 | 10/24/2009 | 03/08/2011 | 156618.71 | 0
4511 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223401 | This project will provide a surface overlay, aggregate shoulders, pavement markings, storm sewer improvements on 147th Street from South of Cottonwood Drive North to 4H Road in the city of Lansing in | Pavement Improvement | 10/01/2009 | 10/01/2009 | 03/08/2011 | 250509.62 | 0
4512 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223501 | This project will provide a pedestrian signal on US Highway 24 at NorthStar Drive in the city of Tonganoxie in Leavenworth County - improving safety. | Pavement Improvement | 10/12/2009 | 10/12/2009 | 11/09/2009 | 23800 | 0
4513 | Kansas | JEFFERSON |  | 02 | U223601 | This project will provide an overlay to Jefferson Street from Walnut to City Limits in the city of Oskaloosa in Jefferson County - improving surface conditions. | Pavement Improvement | 11/02/2009 | 11/02/2009 | 11/09/2009 | 30801.32 | 0
4514 | Kansas | DONIPHAN |  | 02 | U223701 | This project will provide surfacing and culvert work (replacing the Reinforced Concrete Bridge) on Old US-36 (RS-2128) just west of Elm Street in the city of Highland in Doniphan County - improving su | Pavement Improvement | 11/18/2009 | 11/18/2009 | 04/12/2011 | 219300 | 0
4515 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223901 | This project will provide storm sewer improvements on 4th Street at K-7/73and Spruce K-92 in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 11/02/2009 | 11/02/2009 | 04/12/2011 | 224885.43 | 0
4516 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U224001 | This project will provide storm sewer improvements on 5th Ave and Doniphan in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 11/02/2009 | 11/02/2009 | 04/12/2011 | 89586 | 0
4517 | Kansas | LEAVENWORTH | KANSAS CITY (MO) | 02 | U224101 | This project will provide storm sewer improvements on 10th Street and Wellington in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 11/02/2009 | 11/02/2009 | 04/12/2011 | 124435 | 0
4518 | Kansas | POTTAWATOMIE |  | 02 | U224201 | This project will provide realignment of the intersection, surfacing, adding double left-turn lanes, and upgrading the traffic signals at the Intersection of US 24 and McCall Road in the city of Manha | Safety/Traffic Management | 02/15/2010 | 02/15/2010 | 06/13/2011 | 1000000 | 0
4519 | Kansas | RUSSELL |  | 01 | U224301 | This project will provide a reconstruction of US 281 Highway (Fossil Street) from East 9th to Union Pacific RR in the city of Russell in Russell County - improving surface conditions. | Pavement Improvement | 03/01/2010 | 03/01/2010 | 04/12/2011 | 313787.44 | 0
4520 | Kansas | WALLACE |  | 01 | U224401 | This project will provide a mill (removal of existing pavement) and overlay on Highway K-27 from North Front Street to Third Street in the city of Sharon Springs in Wallace County - improving surface | Pavement Improvement | 05/06/2010 | 06/21/2010 | 04/12/2011 | 127664.51 | 0
4521 | Kansas | PAWNEE |  | 01 | U224501 | This project will provide a 1-inch mill (removal of existing pavement) and 2 inch overlay on Northeast Trail Street from the US-56 junction east to 11th Street in the city of Larned in Pawnee County - | Pavement Improvement | 03/11/2010 | 03/11/2010 | 07/11/2011 | 227520.87 | 0
4522 | Kansas | BARTON |  | 01 | U224601 | This project will provide grading and concrete pavement surfacing on US 281 (Main Street) from 3rd Street to the RailRoad Tracks in the city of Hoisington in Barton County - improving surface conditio | Pavement Improvement | 03/02/2010 | 03/02/2010 | 07/11/2011 | 494498 | 0.234
4523 | Kansas | RENO |  | 01 | U224701 | This project will provide a bridge replacement on 4th Ave. over Monroe Street in the city of Hutchinson in Reno County - improving structural concerns. | Bridge Replacement | 02/01/2010 | 03/08/2010 | 05/09/2011 | 485436.18 | 0
4524 | Kansas | BARTON |  | 01 | U224801 | This project will provide a reconstruction of McKinley Street in the city of Great Bends in Barton County - improving structural and surface conditions. | Pavement Improvement | 03/22/2010 | 03/22/2010 | 05/17/2010 | 488000 | 0
4525 | Kansas | PRATT |  | 01 | U224901 | This project will provide a 4-inch mill (removal of existing pavement) and overlay between the railroad crossing at US-281 and Maple Street and the north city limits of the city of Pratt in Pratt Coun | Pavement Improvement | 01/21/2010 | 03/20/2010 | 06/06/2011 | 123857.41 | 0
4526 | Kansas | BUTLER |  | 04 | U225001 | This project will provide an asphalt overlay on 6th Avenue and Boyer Avenue from K-254 to Metcalf Road in the city of El Dorado in Butler County - improving surface conditions. | Pavement Improvement | 03/15/2010 | 03/15/2010 | 11/22/2010 | 750000 | 0
4527 | Kansas | SUMNER |  | 04 | U225201 | This project will provide culvert replacement and surfacing work at the Hillside Street Bridge over the Rock Island Slough in the city of Wellington in Sumner County - improving drainage and surface c | New Bridge Construction | 04/05/2010 | 04/05/2010 | 08/09/2010 | 297434.82 | 0
4528 | Kansas | MONTGOMERY |  | 04 | U225301 | This project will provide an asphalt overlay on 4th Avenue (RS-809) from US 75 to Wood Street in the city of Caney in Montgomery County - improving surface conditions. | Pavement Improvement | 08/07/2009 | 10/12/2009 | 01/04/2011 | 124884.01 | 0
4529 | Kansas | BOURBON |  | 02 | U225401 | This project will provide an asphalt overlay and curb work on SW National Street from Linker Street to Wall Street in the city of Fort Scott in Bourbon County - improving surface conditions. | Pavement Improvement | 10/01/2009 | 10/06/2009 | 01/04/2011 | 228180 | 0
4530 | Kansas | MIAMI |  | 02 | U225501 | This project will provide an asphalt overlay on 8th Street from the North City Limits to Main Street in the city of Osawatomie in Miami County - improving surface conditions. | Pavement Improvement | 10/30/2009 | 10/30/2009 | 11/13/2009 | 88146.75 | 0
4531 | Kansas | CRAWFORD |  | 02 | U225601 | This project will provide an asphalt overlay on Broadway Street from Centennial to Williams in the city of Pittsburg in Crawford County - improving surface conditions. | Pavement Improvement | 08/27/2009 | 08/27/2009 | 01/04/2011 | 229353.5 | 0
4532 | Kansas | CHASE |  | 01 | U225701 | This project will provide an asphalt overlay on 5th Street from West of Cedar Street to State Street in the city of Concordia in Cloud County - improving surface conditions. | Pavement Improvement | 02/11/2010 | 03/01/2010 | 06/07/2011 | 425283 | 0
4533 | Kansas | FORD |  | 01 | U225901 | This project will provide expansion joint replacement on the bridge on 14th Ave. over the Arkansas River in the city of Dodge City - improving structural conditions. | Bridge Replacement | 05/03/2010 | 05/03/2010 | 07/11/2011 | 99000 | 0
4534 | Kansas | LABETTE |  | 02 | U226001 | This project will provide intersection improvements at US 59 and Flynn Drive in the city of Parsons in Labette County - improving safety and economic development associated with the Flynn Industrial P | Safety/Traffic Management | 03/17/2010 | 03/17/2010 | 06/07/2011 | 386348.68 | 0
4535 | Kansas | GRAY |  | 01 | U226101 | This project provide concrete pavement on US-50 from Fifth Street east for 2.5 blocks in the city of Cimarron in Gray County - improving surface conditions. | Pavement Improvement | 05/24/2010 | 06/09/2010 | 05/10/2011 | 802002 | 0.959
4536 | Kansas | MARION |  | 01 | U226301 | This project will provide an asphalt overlay on Ash Street 1st Street to 3rd Street in the city of Hillsboro in Marion County - improving surface conditions. | Pavement Improvement | 01/26/2010 | 01/26/2010 | 06/07/2011 | 348269.01 | 0
4537 | Kansas | OSAGE |  | 02 | U226401 | This project will provide a mill (removal of existing pavement) and overlay and curb & gutter work on US-56 from the South City Limit to Santa Fe Avenue West on K-31 in the city of Burlingame in Osage | Pavement Improvement | 03/15/2010 | 03/15/2010 | 06/07/2010 | 493465 | 0
4538 | Kansas | SHERMAN |  | 01 | U226501 | This project will provide roadway reconstruction/surfacing of K-27/US- 24 Business North of I-70 in the city of Goodland in Sherman County - improving structural and surface conditions. | Pavement Improvement | 06/02/2010 | 06/02/2010 | 09/06/2011 | 570599.16 | 0
4539 | Kansas | HODGEMAN |  | 01 | U226601 | This project will provide a mill (removal of existing pavement) and overlay on RS226 in the city of Hanston in Hodgeman County - improving surface conditions. | Pavement Improvement | 01/29/2010 | 04/12/2010 | 05/10/2011 | 105747.48 | 0
4540 | Kansas | PHILLIPS |  | 01 | U226801 | This project will provide reconstruction of the intersection at State Street and 2nd Street in the city of Phillipsburg in Phillips County -- improving surface condition and safety. | Pavement Improvement | 02/02/2010 | 02/02/2010 | 06/07/2011 | 318200 | 0
4541 | Kansas | DONIPHAN |  | 02 | U226901 | This project will provide a mill (removal of existing pavement) and overlay on RS-2163 (Locust) from Last Chance to the North City Limits in the city of Troy in Doniphan County - improving surface con | Pavement Improvement | 03/29/2010 | 03/29/2010 | 05/10/2011 | 726600.1 | 0
4542 | Kansas | WOODSON |  | 02 | U227001 | This project will provide an asphalt overlay on US-75 from the South City Limits 700 feet North in the city of Yates Center in Woodson County - improving surface conditions. | Pavement Improvement | 03/26/2010 | 03/26/2010 | 06/07/2011 | 345778 | 0
4543 | Kentucky | EDMONSON |  | 02 | 0051031 | WIDENING OF 2.4 MILES OF EXISTING KY 101 ROADWAY IN EDMONSON COUNTY BETWEEN RHODA AND CHALYBEATE, BEGINNING AT MILEPOINT 0.485 AND EXTENDING TO MILEPOINT 2.85. | Pavement Improvement | 10/30/2009 | 04/07/2010 | 12/01/2010 | 4330000 | 2.365
4544 | Kentucky | FAYETTE |  | 6 | 0114004 | CONSTRUCTION OF NEWTOWN PIKE ROADWAY EXTENSION FROM MAIN STREET TO VERSAILLES ROAD IN LEXINGTON, KENTUCKY. | New Construction | 07/10/2009 | 07/10/2009 | 12/01/2010 | 11100000 | 0.519
4545 | Kentucky | FAYETTE | LEXINGTON-FAYETTE | 06 | 0114005 | UTILITY RELOCATION FUNDING FOR THE CONSTRUCTION OF NEWTOWN PIKE ROADWAY EXTENSION FROM MAIN STREET TO VERSAILLES ROAD IN LEXINGTON, KENTUCKY. | Other | 12/08/2009 |  |  | 1000000 | 0.519
4546 | Kentucky | CLINTON |  | 01 | 0139002 | PHASE I OF THE CONSTRUCTION OF THE ALBANY BYPASS IN CLINTON COUNTY; (BRIDGE AND CULVERT SECTION) BEGINNING AT BATES DELK ROAD AND EXTENDING NORTHWARD 1.53 MILES TO 450 FEET SOUTH OF CHURNTOP ROAD. | New Construction | 03/24/2010 |  | 05/31/2011 | 3182233.6 | 1.534
4547 | Kentucky | BREATHITT |  | 5 | 0151065 | RECONSTRUCTION AND RELOCATION OF KY 15 ROADWAY FROM KY-15 AT JACKSON, KENTUCKY TO A POINT 0.43 MILES NORTH OF KY 15 IN BREATHITT COUNTY. | Pavement Improvement | 10/30/2009 | 02/03/2010 | 05/01/2012 | 11373292.84 | 0.43
4548 | Kentucky | BREATHITT |  | 5 | 0151066 | RECONSTRUCTION AND RELOCATION OF KY 15 ROADWAY FROM 0.43 MILES NORTH OF KY 15 AT JACKSON, KENTUCKY TO 0.31 MILES SOUTH OF STILL HOUSE HOLLOW IN BREATHITT COUNTY. | Pavement Improvement | 05/21/2009 | 05/21/2009 | 02/01/2011 | 23059255.94 | 1.7
4549 | Kentucky | LETCHER |  | 5 | 0151067 | CONSTRUCTION OF LEFT TURN LANE ON KY-15 AT THE END OF EXISTING WHITESBURG BYPASS WEST OF WHITESBURG, KENTUCKY IN LETCHER COUNTY. | Safety/Traffic Management | 05/20/2009 | 05/20/2009 | 07/30/2010 | 1600000 | 0.27
4550 | Kentucky | MONROE |  | 1 | 0159006 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-90 ROADWAY FROM 0.34 MILES SOUTH OF BUSHONG ROAD MILEPOINT 12.75 AND EXTENDING NORTHERLY TO 0.68 MILES SOUTH OF CYCLONE ROAD AT MILEPOINT 17.45 IN MONROE C | Pavement Improvement | 05/04/2009 | 05/04/2009 | 11/15/2011 | 6804972.87 | 4.7
4551 | Kentucky | LYON, CALDWELL |  | 1 | 0242066 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-24 EAST BOUND AND WEST BOUND LANES FROM 0.5 MILE EAST OF KY-293 AT MILEPOINT 45.133 IN LYON COUNTY TO KY-139 AT MILEPOINT 65.300 IN CALDWELL COUNTY. | Pavement Improvement | 04/03/2009 | 04/03/2009 | 11/09/2009 | 12226812 | 20.167
4552 | Kentucky | CAMPBELL | CINCINNATI (OH) | 4 | 0272109 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF US 27 ROADWAY FROM SOUTH OF KY-154 AT MILEPOINT 1.9 TO CAMPBELL COUNTY PARK AT MILEPOINT 5.0 IN CAMPBELL COUNTY. | Pavement Widening | 05/04/2009 | 05/04/2009 | 11/30/2011 | 29120000 | 3.2
4553 | Kentucky | KENTON | CINCINNATI (OH) | 4 | 0273013 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF 12TH STREET ROADWAY FROM I-75 TO SCOTT STREET IN COVINGTON, KENTUCKY IN KENTON COUNTY. | Pavement Improvement | 05/22/2009 | 05/22/2009 | 11/01/2011 | 7586554 | 0.47
4554 | Kentucky | KENTON | CINCINNATI (OH) | 4 | 0273014 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF 12TH STREET ROADWAY FROM I-75 TO SCOTT STREET IN COVINGTON, KENTUCKY IN KENTON COUNTY. | Pavement Improvement | 07/02/2009 | 07/02/2009 | 07/01/2011 | 2175306 | 0.22
4555 | Kentucky | HARDIN | RADCLIFF-ELIZABETHTOWN | 2 | 0401068 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-144 ROADWAY TO PROVIDE HORIZONTAL AND VERTICAL REALIGNMENT OF EXISTING ROADWAY BETWEEN MILEPOINTS 0.8 TO MILEPOINT 1.1 JUST WEST OF KY-1500 AT VINE GROVE, | Safety/Traffic Management | 09/16/2009 | 09/16/2009 | 06/30/2010 | 223819.4 | 0.3
4556 | Kentucky | HARDIN | RADCLIFF-ELIZABETHTOWN | 02 | 0401071 | Safety improvements along KY 220 between milepoint 13.2 to milepoint 13.3 in Hardin county, Kentucky at the southeast intersection of KY 220 and KY 1600 in Rineyville, Kentucky. | Safety/Traffic Management | 02/23/2010 | 05/19/2010 | 08/30/2010 | 1334814.95 | 0.1
4557 | Kentucky | JEFFERSON |  | 3 | 0655098 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-65 IN JEFFERSON COUNTY FROM FERN VALLEY ROAD AT MILEPOINT 128.13 TO MILEPOINT 131.89. | Pavement Improvement | 07/02/2009 | 07/02/2009 | 12/15/2010 | 18000000 | 3.16
4558 | Kentucky | TRIGG |  | 1 | 0801075 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF US 68/KY 80 ROADWAY BETWEEN MILEPOINT 0.243 TO MILEPOINT 8.284 IN THE LAND BETWEEN THE LAKES AREA OF TRIGG COUNTY. | Pavement Widening | 04/30/2009 | 04/30/2009 | 11/15/2010 | 30000000 | 7.791
4559 | Kentucky | CLINTON |  | 01 | 1271100 | RECONSTRUCTION OF 3.5 MILES OF US 127 IN CLINTON COUNTY BEGINNING AT THE ALBANY BYPASS AND EXTENDING NORTH TO KY 90. | Pavement Improvement | 11/19/2009 | 03/10/2010 | 10/01/2011 | 17105774.45 | 4.24
4560 | Kentucky | WASHINGTON |  | 2 | 1501096 | CONSTRUCTION OF NEW SPRINGFIELD NORTHWEST BYPASS FROM KY 555 TO US 150 NORTHWEST OF SPRINGFIELD, KENTUCKY. | New Construction | 05/05/2009 | 05/05/2009 | 06/01/2011 | 13821653.83 | 3.475
4561 | Kentucky | ROCKCASTLE |  | 05 | 1501097 | RECONSTRUCTION OF 6 MILES OF US 150 IN ROCKCASTLE COUNTY BEGINNING AT BRODHEAD, KY AND EXTENDING EAST TO US 461 AT MT. VERNON, KY. | Pavement Improvement | 10/29/2009 | 02/08/2010 | 12/01/2011 | 24088172.4 | 6.31
4562 | Kentucky | NELSON |  | 02 | 1501098 | RECONSTRUCTION/RELOCATION OF 3 MILES OF US 31E IN NELSON COUNTY NORTH OF BARDSTOWN, KY BEGINNING AT KY 509 AND EXTENDING NORTH TO WHITESIDE DRIVE. | Pavement Improvement | 12/29/2009 | 04/01/2010 | 07/31/2011 | 7314802.28 | 3.07
4563 | Kentucky | ROCKCASTLE, LINCOLN |  | 6 | 1501099 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF APPROXIMATELY 7.2 MILES OF US-150 ROADWAY FROM CRAB ORCHARD, KENTUCKY IN LINCOLN COUNTY TO BRODHEAD, KENTUCKY IN ROCKCASTLE COUNTY. | Pavement Improvement | 04/07/2009 | 04/07/2009 | 12/01/2010 | 25748598 | 14.3
4564 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 2641164 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-264 IN LOUISVILLE, KENTUCKY FROM NEWBURG ROAD AT MILEPOINT 13.710 TO BRECKINRIDGE LANE AT MILEPOINT 18.410 IN JEFFERSON COUNTY. | Pavement Improvement | 09/04/2009 | 09/04/2009 | 06/15/2010 | 12078000 | 5.7
4565 | Kentucky | JEFFERSON |  | 3 | 2641166 | PAVEMENT REHABILITATION TO MILL 1"" OF EXISTING PAVEMENT AND TO RESURFACE WITH THIN OVERLAY ON I-264 EAST BOUND & WEST BOUND FROM MILEPOINT 22.61 TO I-71 AT MILEPOINT 22.97. | Pavement Improvement | 07/01/2009 | 05/03/2010 | 06/30/2010 | 301574.28 | 0.36
4566 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 2652023 | REPAIR AND GRIND EXISTING PAVEMENT ON I-265 IN JEFFERSON COUNTY FROM MILEPOINT 18.8 NEAR EXIT 19 AND EXTENDING NORTH TO MILEPOINT 23.4 NEAR EXIT 23. | Pavement Improvement | 12/30/2009 | 04/07/2010 | 10/31/2010 | 3846696.7 | 4.56
4567 | Kentucky | MARION |  | 2 | 3000786 | CONSTRUCTION OF A NEW ROADWAY CONNECTOR FROM THE INTERSECTION OF THE US-68/LEBANON NORTHERN BYPASS (KY 2154) AND EXTENDING SOUTHEAST TO INDUSTRIAL DRIVE IN LEBANON, KENTUCKY IN MARION COUNTY, BEING AP | New Construction | 04/07/2009 | 04/07/2009 | 07/01/2010 | 4000000 | 1.3
4568 | Kentucky | JEFFERSON |  | 3 | 3001339 | CONSTRUCTION OF PEDESTRIAN AND SAFETY IMPROVEMENTS INCLUDING SIDEWALKS, LANDSCAPING, AND SIGNAL IMPROVEMENTS ALONG US 60A (EASTERN PARKWAY) AT 3RD STREET IN LOUISVILLE, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 07/02/2009 | 07/02/2009 | 06/01/2010 | 2888182.29 | 0.2
4569 | Kentucky | BULLITT | LOUISVILLE (IN) | 02 | 3001343 | PAVEMENT REHABILITATION TO MILL AND GRIND EXISTING PAVEMENT, AND RESURFACE KY-1526 (KNOB CREEK ROAD) FROM KY-44 TO OLD BROOKS HILL ROAD (KY 2672) IN BULLITT COUNTY BEING APPROXIMATELY 4.9 MILES IN LEN | Pavement Improvement | 10/01/2009 | 05/17/2010 | 05/31/2010 | 465996 | 4.9
4570 | Kentucky | BULLITT | LOUISVILLE (IN) | 02 | 3001344 | PAVEMENT REHABILITATION TO MILL AND GRIND EXISTING PAVEMENT, AND RESURFACE KY 1526 (BELLS MILL ROAD) FROM KY 44 TO KY 61 IN BULLITT COUNTY BEING APPROXIMATELY 3.9 MILES IN LENGTH. | Pavement Improvement | 10/01/2009 | 05/17/2010 | 05/31/2010 | 482930 | 3.972
4571 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001346 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 06/07/2010 | 11/15/2010 | 334859.25 | 0
4572 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001348 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 06/10/2010 | 09/01/2010 | 242528 | 0
4573 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001349 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 80234 | 0
4574 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001350 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 06/25/2010 | 11/01/2010 | 87373 | 0
4575 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001351 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 06/17/2010 | 11/15/2010 | 131098 | 0
4576 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001352 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 05/26/2010 | 11/15/2010 | 152185 | 0
4577 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001353 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 05/19/2010 | 11/01/2010 | 129008 | 0
4578 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001354 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 05/28/2010 | 11/15/2010 | 85662.5 | 0
4579 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001355 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 74302.8 | 0
4580 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001356 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 99687.5 | 0
4581 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001357 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 81290 | 0
4582 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001358 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 06/23/2010 | 11/01/2010 | 116726.5 | 0
4583 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001359 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 05/19/2010 | 08/19/2010 | 121005.5 | 0
4584 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001360 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 05/04/2010 | 11/15/2010 | 107651.5 | 0
4585 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001361 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 05/11/2010 | 11/01/2010 | 101035 | 0
4586 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001362 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 02/05/2010 | 06/01/2010 | 11/15/2010 | 105259 | 0
4587 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001364 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 06/28/2010 | 11/15/2010 | 119438 | 0
4588 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001365 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 06/29/2010 | 11/01/2010 | 94298.38 | 0
4589 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001366 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 111650 | 0
4590 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001367 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 05/18/2010 | 11/01/2010 | 109219 | 0
4591 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001368 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 77550 | 0
4592 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001369 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 46530 | 0
4593 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001370 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 |  | 11/15/2010 | 76450 | 0
4594 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001371 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 64075 | 0
4595 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001372 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 |  | 11/15/2010 | 121731.5 | 0
4596 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001373 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 06/23/2010 | 11/01/2010 | 97702 | 0
4597 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001374 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 06/22/2010 | 11/01/2010 | 113327.5 | 0
4598 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001375 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 05/12/2010 | 11/15/2010 | 115516.5 | 0
4599 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001376 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 05/17/2010 | 11/15/2010 | 109659 | 0
4600 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001377 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 05/19/2010 | 11/15/2010 | 106975 | 0
4601 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001378 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 79446.4 | 0
4602 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001379 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 84946.84 | 0
4603 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001380 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 |  | 11/15/2010 | 108751.5 | 0
4604 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001381 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 06/07/2010 | 11/15/2010 | 91714.81 | 0
4605 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001382 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 06/11/2010 | 09/01/2010 | 144523.28 | 0
4606 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001383 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 05/03/2010 | 11/15/2010 | 901784.8 | 0
4607 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001384 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 02/05/2010 | 06/14/2010 | 11/01/2010 | 855189.41 | 0
4608 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001385 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1710) | Pavement Improvement | 02/05/2010 | 05/10/2010 | 11/15/2010 | 667518.39 | 0
4609 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001386 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1711) | Pavement Improvement | 02/05/2010 | 06/14/2010 | 11/01/2010 | 668473.67 | 0
4610 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001387 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1712) | Pavement Improvement | 02/05/2010 | 06/03/2010 | 09/01/2010 | 548090.19 | 0
4611 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001388 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1713) | Pavement Improvement | 02/05/2010 | 05/11/2010 | 08/31/2010 | 488400 | 0
4612 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 02,03 | 3001389 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1714) | Pavement Improvement | 02/05/2010 | 06/17/2010 | 08/31/2010 | 593010.17 | 0
4613 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 3001390 | RECONSTRUCTION OF APPROXIMATELY 1,443 HANDICAP RAMPS AND 1,570 FEET OF SIDEWALKS IN THE CITY OF JEFFERSONTOWN, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 02/05/2010 |  | 11/15/2010 | 1338238 | 0
4614 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 3001391 | The Jefferson County- Louisville Metro Government will construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the city of Louisville (KIPDA ID # 1671). | Transportation Enhancements | 02/05/2010 | 05/17/2010 | 11/15/2010 | 157126.53 | 0
4615 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 3001392 | PAVEMENT REHABILITATION BY MILLING THE EXISTING SURFACE, AND REPLACING WITH A MINIMUM OF 1.5 INCHES OF ASPHALT SURFACE TO EXTEND THE PAVEMENT LIFE OF PLANTSIDE DRIVE FROM BLUEGRASS PARKWAY TO KY 1819 | Pavement Improvement | 02/05/2010 | 06/02/2010 | 10/01/2010 | 279550.67 | 0
4616 | Kentucky | OLDHAM | LOUISVILLE (IN) | 04 | 3001393 | CONSTRUCT 1,400 FEET OF SIDEWALK ALONG NORTH SIDE OF KY 22 FROM KY 329 TO KY 329 BYPASS, AND CONSTRUCT 400 FEET OF SIDEWALK ALONG KY 146 FROM FLOYDSBURG ROAD TO THE NEW CRESTWOOD ELEMENTARY SCHOOL, IN | Transportation Enhancements | 02/05/2010 |  | 10/15/2010 | 114211.81 | 0
4617 | Kentucky | OLDHAM | LOUISVILLE (IN) | 04 | 3001394 | INSTALL GUARDRAILS ALONG ROADWAYS AT VARIOUS LOCATIONS IN OLDHAM COUNTY KENTUCKY. | Safety/Traffic Management | 02/05/2010 |  | 11/15/2010 | 58115.4 | 0
4618 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 3001395 | Streetscape project in Jefferson county, Kentucky in downtown Louisville, Kentucky along Second Street for improvements to traffic intersections, sidewalks, accessibility/mobility, landscaping, lighti | Transportation Enhancements | 03/09/2010 |  |  | 2400000 | 0
4619 | Kentucky | FAYETTE | LEXINGTON-FAYETTE | 06 | 3003243 | Transportation Enhancement project in Fayette county, Kentucky at Lexington, Kentucky for the construction of Legacy Trail Phase I from Berea road at Ironworks Pike to Newtown Pike at Citation Bouleva | Transportation Enhancements | 03/03/2010 | 03/18/2010 | 08/31/2010 | 3275371.5 | 6.4
4620 | Kentucky | FAYETTE | LEXINGTON-FAYETTE | 06 | 3003244 | Transportation Enhancement project at Fayette county, Kentucky in Lexington, Kentucky for the construction of Legacy Trail phase 2 from Citation Boulevard to Loudon Avenue. | Transportation Enhancements | 03/03/2010 | 03/18/2010 | 08/31/2010 | 2004632.5 | 2.1
4621 | Kentucky | FAYETTE | LEXINGTON-FAYETTE | 06 | 3003245 | Transportation Enhancement project in Fayette county, Kentucky at Lexington, Kentucky for the construction of the downtown streetscape project to improve mobility along Vine street from South Broadway | Pavement Improvement | 02/05/2010 | 04/05/2010 | 08/20/2010 | 1295000 | 0
4622 | Kentucky | BARREN |  | 2 | 3013012 | CONSTRUCTION OF NEW GLASGOW OUTER LOOP ROADWAY FROM US-68 TO THE LOUIE B. NUNN PARKWAY EAST OF GLASGOW, KENTUCKY. | New Construction | 05/21/2009 | 05/21/2009 | 04/01/2011 | 15678931 | 1.2
4623 | Kentucky | DAVIESS |  | 2 | 3023014 | RECONSTRUCTION AND RELOCATION OF THE EXISTING EAST US-60 BYPASS AT OWENSBORO, KENTUCKY (EAST COUNTY CORRIDOR) BEGINNING AT REID ROAD AND EXTENDING NORTHEAST TO EXISTING US 60 EAST OF OWENSBORO, KENTUC | Pavement Improvement | 07/02/2009 | 07/02/2009 | 02/15/2013 | 33943657.92 | 2.2
4624 | Kentucky | NELSON |  | 02 | 3025006 | Transportation Enhancement project in Nelson county, Kentucky at Bardstown, Kentucky for Phase I and Phase II construction of streetscape improvements including sidewalks, curb ramps, and widening the | Transportation Enhancements | 03/25/2010 |  |  | 2539000 | 0
4625 | Kentucky | BULLITT | LOUISVILLE (IN) | 02 | 5116024 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-61 ROADWAY FROM SOUTH OF JOHN HARPER HIGHWAY (BROOKS ROAD MILEPOINT 19.33) TO THE EXISTING 4-LANE SECTION SOUTH OF CARDINAL AVENUE AT MILEPOINT 210.5 IN BU | Pavement Widening | 05/04/2009 | 05/04/2009 | 05/15/2010 | 6055912.18 | 0.72
4626 | Kentucky | NELSON |  | 2 | 5121010 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-245 ROADWAY FROM MILEPOINT 6.5 AT INTERSECTION OF KY-332 NORTH OF BARDSTOWN AND EXTENDING NORTHWEST TO MILEPOINT 7.6 TO THE FLAGET HOSPITAL SITE IN BARDSTO | Pavement Widening | 05/20/2009 | 05/20/2009 | 07/15/2010 | 4627074 | 1.193
4627 | Kentucky | WHITLEY |  | 5 | 5147019 | ASPHALT SURFACING FOR THE RECONSTRUCTED SECTION OF KY 92 ROADWAY FROM CORNBREAD BRANCH NEAR OLD JELLICO ROAD AT MILEPOINT 4.4 AND EXTENDING EAST TO BRIER CREEK BRIDGE AT MILEPOINT 8.4 IN WHITLEY COUNT | Pavement Improvement | 05/01/2009 | 07/13/2009 | 06/30/2010 | 6020000 | 5.5
4628 | Kentucky | MCCREARY |  | 05 | 5147020 | RECONSTRUCTION AND RELOCATION OF KY 92 ROADWAY BETWEEN MILEPOINT 16.6 TO MILEPOINT 21.5 IN MCCREARY COUNTY. | Pavement Improvement | 10/30/2009 | 02/22/2010 | 08/15/2011 | 14670000 | 4.9
4629 | Kentucky | KNOX, WHITLEY |  | 5 | 5155009 | CONSTRUCTION OF A NEW ROADWAY CONNECTOR FROM KY-6 AT WOODBINE IN WHITLEY COUNTY EXTENDING NORTHEAST TO THE CORBIN BYPASS IN KNOX COUNTY, BEING APPROXIMATELY 1.2 MILES IN LENGTH. | New Construction | 05/01/2009 | 05/01/2009 | 09/01/2010 | 4790000 | 0
4630 | Kentucky | OLDHAM | LOUISVILLE (IN) | 04 | 5162019 | CONSTRUCT 1,644 FEET OF SIDEWALKS, WHICH WILL BE 4 FEET IN WIDTH WITH FIVE-FOOT PASSING AREAS TO MEET ADA STANDARDS, ALONG THE SOUTH SIDE OF KY 146 FROM DOGWOOD LANE EXTENDING WEST TO FOLEY AVENUE IN | Transportation Enhancements | 02/05/2010 | 06/10/2010 | 11/01/2010 | 107994.85 | 0.31
4631 | Kentucky | GALLATIN |  | 4 | 5170014 | SAFETY IMPROVEMENTS, REHABILITATION OF PAVEMENT, AND CONSTRUCT NEW BRIDGE DECK WITH BARRIER WALLS ON EXISTING US 127 BIG SUGAR BRIDGE BETWEEN MILEPOINT 3.88 TO MILEPOINT 3.98 IN GALLATIN COUNTY. | Bridge Improvement | 04/03/2009 | 04/03/2009 | 08/13/2009 | 463846.59 | 0.1
4632 | Kentucky | MADISON |  | 6 | 5192004 | CONSTRUCTION OF LEFT TURN LANES AT THE US25 AND KY1156 INTERSECTION AT RICHMOND, KENTUCKY IN MADISON COUNTY. | Safety/Traffic Management | 06/30/2009 | 06/30/2009 | 06/18/2010 | 910000 | 0.02
4633 | Kentucky | FRANKLIN |  | 6 | 5196010 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF APPROXIMATELY 2.3 MILES OF US 421 ROADWAY FROM EXISTING US-60/KY 676 INTERCHANGE TO 1600 FEET EAST OF CHENAULT INDUSTRIAL ROAD IN FRANKLIN COUNTY. | Pavement Widening | 05/04/2009 | 05/04/2009 | 08/26/2010 | 9934478.4 | 1.79
4634 | Kentucky | KNOTT |  | 05 | 5339006 | CONSTRUCT LEFT TURN LANE AND IMPROVE SIGHT DISTANCE ON KY 160 AT THE INTERSECTION OF KY 3391 NEAR THE KNOTT COUNTY CENTRAL HIGH SCHOOL IN KNOTT COUNTY, KENTUCKY. | Safety/Traffic Management | 12/30/2009 | 03/16/2010 | 08/15/2010 | 1641000 | 0.236
4635 | Kentucky | HENDERSON | EVANSVILLE (IN) | 01 | 7970012 | Provide safety improvements by widening of us 41a at Henderson, Kentucky in Henderson County between milepoint 14.48 to 14.68 to construct two-way left turn lane. | Pavement Improvement | 11/20/2009 | 03/19/2010 | 08/14/2010 | 1173502.07 | 0.2
4636 | Kentucky | HENDERSON |  | 01 | 7997004 | Provide safety improvement by widening of Watson lane at us 41a at Henderson, Kentucky in Henderson County between milepoint 1.098 to 1.167 to accommodate two approach lanes and one receiving lane. | Pavement Improvement | 11/19/2009 | 03/03/2010 | 06/04/2010 | 305561.03 | 0.069
4637 | Kentucky | BOONE | CINCINNATI (OH) | 04 | 8200009 | RECONSTRUCTION OF 1.6 MILES OF KY 237 IN BOONE COUNTY FROM US 42 AT GUN POWDER BEGINNING AT MILEPOINT 1.581 AND EXTENDING NORTHWEST TO WOODCREEK DRIVE NEAR MILEPOINT 3.166. | Pavement Widening | 05/10/2010 |  | 05/01/2012 | 5731742.27 | 1.605
4638 | Kentucky | FAYETTE | LEXINGTON-FAYETTE | 06 | 8591002 | PHASE 1B OF THE WIDENING OF 0.7 MILES OF LIBERTY ROAD/TODDS ROAD IN LEXINGTON, KENTUCKY BEGINNING AT THE INTERSECTION OF MAN O'WAR BLVD AND EXTENDING EAST TO FOREST HILL DRIVE. | Pavement Improvement | 10/30/2009 | 03/22/2010 | 09/15/2010 | 470000 | 0.696
4639 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 8723011 | EXTENDING EXISTING BLANKENBAKER PARKWAY (KY 913) AS 5 LANE ROADWAY IN JEFFERSON COUNTY FROM THE BLANKENBAKER ACCESS ROAD TO TAYLORSVILLE ROAD (KY 155). | Pavement Widening | 11/20/2009 | 02/08/2010 | 07/15/2011 | 6000700 | 0.6
4640 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 8724018 | INSTALLATION OF BICYCLE LANES ALONG TAYLORSVILLE ROAD BETWEEN MCMAHAN BOULEVARD AND HURSTBOURNE PARKWAY IN LOUISVILLE, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 02/05/2010 | 06/15/2010 | 11/15/2010 | 65998.05 | 1.582
4641 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 8738031 | The Jefferson County- Louisville Metro Government will construct new sidewalks to meet ADA (American Disabilities Act) compliance along the east side of the Preston Highway from Gilmore Lane to Kremer | Transportation Enhancements | 02/05/2010 |  | 11/01/2010 | 111265 | 0.358
4642 | Kentucky | JEFFERSON | LOUISVILLE (IN) | 03 | 8893001 | WIDEN EXISTING ROADS (NO ADDITIONAL TRAVEL LANES), ADD SIDEWALKS, CONSTRUCT DRAINAGE IMPROVEMENTS, AND INSTALL LANDSCAPING ALONG MAIN STREET FROM KY 1819 (WATTERSON TRAIL) TO THE WESTERN CITY LIMIT AN | Pavement Improvement | 02/05/2010 |  | 09/15/2010 | 171676.11 | 0.108
4643 | Kentucky | GRAYSON |  | 2 | 9001011 | PAVEMENT REHABILITATION OF THE EASTBOUND LANES OF THE WESTERN KENTUCKY PARKWAY IN GRAYSON COUNTY FROM 0.9 MILES EAST OF CROW HOLLOW ROAD BRIDGE, BEGINNING AT MILEPOINT 114.9 AND EXTENDING EAST TO THE | Pavement Improvement | 05/20/2009 | 05/20/2009 | 09/13/2009 | 1100000 | 2.15
4644 | Louisiana | CADDO |  | 4 | 0021021 | This project will build 3.2 miles of new interstate highway from US 71(S) to LA 2. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas State Line in | New Construction | 11/16/2009 | 11/16/2009 | 08/28/2011 | 7698891.02 | 3.153
4645 | Louisiana | WASHINGTON |  | 1 | 002S613 | These Washington Parish projects near Bogalusa will replace four existing structurally deficient timber bridges located on Burt Road and Claiborne Street. | Bridge Replacement | 08/03/2009 | 08/05/2009 | 03/28/2010 | 1688814.46 | 0
4646 | Louisiana | JEFFERSON | NEW ORLEANS | 2 | 0105370 | This project is Phase 2 of 2 for the imporvement of the existing Interstate 10/Causeway Blvd interchange. The project includes the construction of new flyover ramps to improve the flow of traffic bet | Pavement Widening | 08/04/2009 | 11/09/2009 | 01/21/2012 | 56194317.5 | 0.38
4647 | Louisiana | ASCENSION | BATON ROUGE | 03 | 0302505 | This project will construct a sidewalk near East Ascension High School in the city of Gonzales to provide pedestrian access to parks, businesses, civic facilities as well as Bayou Francois in Ascensio | Transportation Enhancements | 03/22/2010 | 03/22/2010 | 06/14/2010 | 483410.01 | 0.511
4648 | Louisiana | ASCENSION | BATON ROUGE | 6 | 0309511 | This project includes patching deteriorated pavement and placing an asphalt overlay along LA 73 in Ascension Parish from US61(N) to the East Baton Rouge Parish Line. | Pavement Improvement | 06/05/2010 |  | 08/14/2010 | 1569712.77 | 2.88
4649 | Louisiana | ASSUMPTION | HOUMA | 3 | 0409500 | This project will construct left turn lanes on LA 1 to turn onto LA 1247 in Assumption Parish, LA. | Pavement Improvement | 05/21/2010 | 05/21/2010 | 07/02/2010 | 242031.22 | 0.59
4650 | Louisiana | BOSSIER | SHREVEPORT | 4 | 0809508 | This project will rebuild 2.1 miles of pavement on Stockwell Road in Bossier Parish. | Pavement Improvement | 07/15/2010 |  | 09/30/2010 | 1495468.41 | 2.1
4651 | Louisiana | CADDO | SHREVEPORT | 4 | 0905504 | This project will build 4.6 miles of new interstate highway from Mira-Myrtis Road to LA 168. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas Sta | Pavement Improvement | 05/18/2009 | 05/18/2009 | 08/11/2010 | 34301108.98 | 4.66
4652 | Louisiana | CADDO | SHREVEPORT | 4 | 0909507 | This project will remove the deteriorated asphalt, make repairs,and place a new asphalt overlay Woolworth Road from Colquitt Road to the Shreveport City Limits in Caddo Parish. | Pavement Improvement | 07/15/2010 |  |  | 757497.19 | 0
4653 | Louisiana | CALCASIEU | LAKE CHARLES | 7 | 1008534 | This project will rehabilitate approximately 9.6 miles of Intetstate 210 from the east end of the Calcasieu River Bridge to Interstate 10 on the east side of Lake Charles in Calcasieu Parish. The fir | Pavement Improvement | 11/09/2009 | 11/09/2009 | 09/10/2010 | 20649009.09 | 9.58
4654 | Louisiana | CALCASIEU | LAKE CHARLES | 07 | 1009516 | The City of Lake Charles will repair 2 miles of Broad Street from Entreprise to Interstate 210 by placing new asphalt on the exisitng pavement in Calcasieu Parish. | Pavement Improvement | 07/07/2010 |  | 09/15/2010 | 1751513.23 | 2.236
4655 | Louisiana | CALCASIEU | LAKE CHARLES | 07 | 1009517 | The City of Lake Charles will repair approximately a half mile of West McNesse Street from Weaver Street to Nelson Street and 2 miles of the pavement on Weaver Street from Sale Street to Ham Reid Stre | Pavement Improvement | 06/08/2010 |  | 12/12/2010 | 3098682.64 | 0
4656 | Louisiana | CALCASIEU | LAKE CHARLES | 07 | 1009521 | The City of Lake Charles will repair 1 mile of pavement by placing new asphalt on the existing pavement from Hodge Street to 7th Street in Calcasieu Parish. | Pavement Improvement | 06/08/2010 |  | 07/26/2010 | 664989.67 | 0
4657 | Louisiana | CALCASIEU | LAKE CHARLES | 07 | 1009522 | This project will remove the existing pavement and construct 1.25 miles of new concrete pavement on the 5 lane segment of LA 14 from LA 3092 to LA 3186 in Calcasieu Parish. | Pavement Improvement | 07/30/2010 |  |  | 4110507.91 | 0
4658 | Louisiana | IBERIA |  | 3 | 1104011 | This project will build a new bridge on US 90 at LA 85 in Iberia Parish as part of the upgrading of US 90 to become part of I-49 from Lafayette to New Orleans. | New Construction | 03/01/2009 | 03/03/2009 | 09/06/2012 | 29929858.86 | 1.17
4659 | Louisiana | CATAHOULA |  | 5 | 1308502 | This project is located at the northern and southern city limits of Sicily Island in Catahoula Parish along LA 15 and will providie landscaping along the reconstructed section of LA 15 through Sicily | Transportation Enhancements | 07/11/2009 | 07/11/2009 | 09/12/2009 | 177680.83 | 0.231
4660 | Louisiana | CONCORDIA |  | 5 | 1508500 | This project will remove approximately 7 miles of the deteriorated pavement along US 425 and place new asphalt from US 65 to Foules in Concordia and Catahoula Parishes. | Pavement Improvement | 09/12/2009 | 09/12/2009 | 12/05/2009 | 1908201.98 | 0.266
4661 | Louisiana | DE SOTO |  | 4 | 1602501 | This project will establish a trailhead with informational signage and parking area for automobiles and bicycles along LA 191 (approx. 650? south of the intersection of US 84 and LA 191) in the Toled | Transportation Enhancements | 07/15/2010 |  |  | 267435.84 | 0.02
4662 | Louisiana | EAST BATON ROUGE | BATON ROUGE | 6 | 1704507 | This project located near Central, LA in East Baton Rouge Parish includes clearing, removing trees and buildings and placing soil, and two new bridges over Beaver Bayou for the new Central Thruway fro | New Construction | 03/01/2010 | 03/31/2010 | 07/18/2011 | 7928611.19 | 0
4663 | Louisiana | EAST BATON ROUGE |  | 6 | 1709503 | The project is located in Baton Rouge and consists of widening Interstate-10 from four to six lanes from the Seigen Lane Interchange to the Highland Road Interchange. | Pavement Widening | 03/01/2009 | 03/10/2009 | 01/02/2013 | 69605000 | 2
4664 | Louisiana | EAST BATON ROUGE | BATON ROUGE | 6 | 1709523 | This project consists of constructing the Central Thruway which will be a concrete roadway in East Baton Rouge Parish from Florida Blvd. to the South end of Sullivan Rd. | Pavement Improvement | 06/14/2010 |  | 12/11/2010 | 1591471.18 | 0.01
4665 | Louisiana | EVANGELINE |  | 3 | 2002502 | These Evangeline Parish projects on Red Fox Lane and 1st Street in Chataignier will replace the existing deficient timber bridges with a new concrete box culvert and a new concrete bridge. | Bridge Replacement | 06/22/2009 | 06/22/2009 | 01/09/2010 | 644400.04 | 0
4666 | Louisiana | JACKSON |  | 5 | 2508503 | This Jackson Parish project will place new asphalt along 6 miles of the existing two lanes on US 167 lanes from Quitman to the Lincoln Parish line. | Pavement Improvement | 08/01/2009 | 08/01/2009 | 01/16/2010 | 2964005.33 | 6.06
4667 | Louisiana | JEFFERSON | NEW ORLEANS | 2 | 2602528 | This Jefferson Parish project will remove the deteriorated pavement and place new asphalt along approximately 0.34 miles of Lapalco Boulevard beginning at Manhattan Boulevard and ending at Bayou Fatma | Pavement Improvement | 08/04/2010 |  | 09/29/2010 | 1233867.36 | 0
4668 | Louisiana | LAFAYETTE | LAFAYETTE | 07 | 2808504 | This project will stabilize the roadway base and resurface the roadway on LA 733 from the junction at US 167 to the junction at LA 92. This project is located in Lafayette Parish. | Pavement Improvement | 06/15/2010 |  |  | 1947176 | 4.426
4669 | Louisiana | LAFAYETTE | LAFAYETTE | 3 | 2809507 | This Lafayette Parish project includes removing the exisiting deteriorated pavement, repairs, and placing new asphalt and shoulders along approximately 2 miles of LA 724 from Althea Drive to US 90. | Pavement Improvement | 06/19/2010 | 06/19/2010 | 08/14/2010 | 1232187.36 | 1.948
4670 | Louisiana | LAFAYETTE | LAFAYETTE | 7 | 2809508 | This project will construct an addditional westbound left-turn lane at Pinhook and Carmel (LA 94) in Lafayette, LA. | Pavement Widening | 06/02/2010 |  | 06/30/2010 | 246604.16 | 0.001
4671 | Louisiana | LAFAYETTE | LAFAYETTE | 7 | 2809511 | This Lafayette Parish project will remove the deteriorated pavement, make repairs, and place new asphalt at the intersection of University Avenue (LA 182) and Cameron (US 90). | Pavement Improvement | 07/06/2010 |  | 11/30/2010 | 2503458.6 | 0
4672 | Louisiana | LAFAYETTE | LAFAYETTE | 7 | 2809513 | This Lafayette Parish project will remove the deteriorated pavement, make repairs, and place new asphalt at the intersection of North University (LA 182) at Cameron (US 90). | Pavement Improvement | 07/06/2010 |  | 10/26/2010 | 187586.23 | 0.157
4673 | Louisiana | LAFAYETTE | LAFAYETTE | 3 | 2809519 | This Lafayette Parish project will build a traffic roundabout at the intersection of Bonin Road and Milton Avenue (LA 92). | New Construction | 06/05/2010 |  | 07/31/2010 | 570987.84 | 0
4674 | Louisiana | LAFOURCHE |  | 3 | 2909501 | This Lafourche Parish project will construct a new vertical lift bridge with concrete towers to replace the existing deficient pontoon bridge. The new bridge will be constructed on a realigned section | Bridge Replacement | 05/20/2009 | 05/20/2009 | 02/15/2012 | 37067216.83 | 0.57
4675 | Louisiana | LAFOURCHE | HOUMA | 3 | 2909504 | This project provides for the placement of new asphalt and new roadway striping along the existing 2 lane highway of LA 1 from just south of US 90 to Mathews in Lafourche Parish. The roadway will hav | Pavement Improvement | 06/17/2010 |  | 09/09/2010 | 1961153.54 | 2.45
4676 | Louisiana | LAFOURCHE | HOUMA | 3 | 2909505 | Turn lanes will be installed at intersection of LA 1 and LA 308 in Lafourche Parish. | Pavement Improvement | 06/27/2010 |  | 07/25/2010 | 487429.56 | 0.001
4677 | Louisiana | LAFOURCHE | HOUMA | 3 | 2909506 | The project consists of repairs and new ashpalt on the following streets in Lafourche Parish: Audubon Ave. (S. Acadia - Erwin Dr.), Menard St. (Audubon - Goode St.), Ridgefield Road (LA 1 - Plantation | Pavement Improvement | 05/19/2010 | 05/19/2010 | 08/12/2010 | 1367241.87 | 3.5
4678 | Louisiana | LAFOURCHE | HOUMA | 3 | 2909507 | New lighting and signs will be installed along LA 1 in the Town of Lockport in Lafourche Parish. | Safety/Traffic Management | 05/26/2010 | 05/26/2010 | 07/14/2010 | 101586.9 | 0.001
4679 | Louisiana | LAFOURCHE | HOUMA | 3 | 2909513 | This project consists of a new 6 foot bike and walking path in the city of Thibodaux from Bayou Lane to LA 648 (Percy Brown Rd.) in Lafourche Parish. The project will provide pedestrian access to a m | Transportation Enhancements | 05/18/2010 | 05/18/2010 | 07/20/2010 | 208727.45 | 0.001
4680 | Louisiana | LIVINGSTON | BATON ROUGE | 6 | 3207500 | This project consists of the removal of existing concrete sidewalks and replacement with decorative concrete pavers and is located on LA 15 (Range Road) from East Railroad Avenue and LA 1032 (Centervi | Transportation Enhancements | 07/14/2010 |  |  | 396535.58 | 0.163
4681 | Louisiana | LIVINGSTON | BATON ROUGE | 6 | 3207506 | This project provides for pavement repair and new asphalt along portions of LA 1024 in Livingston Parish. | Pavement Improvement | 03/30/2010 | 03/30/2010 | 08/31/2010 | 2336000 | 5.44
4682 | Louisiana | LIVINGSTON | BATON ROUGE | 6 | 3209505 | This Design-Build project consists of widening the mainline of I-12 in Denham Spring, LA from four lanes to six lane from Pete's Hwy. to Juban Interchange in the eastbound direction, and from the Amit | New Construction | 03/09/2009 | 11/08/2009 | 09/06/2012 | 16688313.05 | 2.08
4683 | Louisiana | ORLEANS | NEW ORLEANS | 1 | 3602513 | This project consists of the reconstruction of the existing roadway with new concrete pavement on Fleur De Lis Blvd from from Veterans Memorial Blvd to North of 30th St in Orleans Parish. | Pavement Improvement | 11/11/2009 | 12/10/2009 | 10/17/2010 | 7238577.42 | 0
4684 | Louisiana | OUACHITA |  | 7 | 3701525 | This Ouachita Parish project on Caples Road will replace the existing deficient timber bridge over Longs Creek with a new concrete bridge. | Bridge Replacement | 07/31/2009 | 07/31/2009 | 02/05/2010 | 577623.46 | 0
4685 | Louisiana | OUACHITA |  | 5 | 3701526 | This Ouachita Parish project on Sam Head Road will replace the existing deficient timber bridge over Bogaloosa Creek with a new concrete bridge. | Bridge Replacement | 07/31/2009 | 07/31/2009 | 02/05/2010 | 326869.34 | 0
4686 | Louisiana | OUACHITA | MONROE | 5 | 3709503 | This Ouchita Parish project will widen Oliver Road from two lanes to three lanes and place new asphalt pavement, beginning at LA 840-6 to Tower Drive. The project will also fill a 7 foot deep ditch a | Pavement Improvement | 07/14/2010 |  |  | 1749886.62 | 0
4687 | Louisiana | OUACHITA | MONROE | 5 | 3709504 | This work will repair and place new asphalt and striping along approximately 5.4 miles of the following streets in Ouachita Parish: Crosely St. - between Cypress and Black Bayou Canal. Downing Pines | Pavement Improvement | 06/28/2010 |  | 09/27/2010 | 1959694.07 | 4.21
4688 | Louisiana | OUACHITA | MONROE | 5 | 3709505 | This project will reconstruct and place new asphalt on Good Hope Road from LA 616 (Arkansas Road) to T. John Road in Ouachita Parish. | Pavement Improvement | 06/09/2010 |  | 07/21/2010 | 740224.97 | 0.777
4689 | Louisiana | OUACHITA | MONROE | 6 | 3709506 | This project will place new asphalt of Dellwood Drive in the town of Richwood (Ouachita Parish) from US 165 to Blackwood Drive. | Pavement Improvement | 07/14/2010 |  |  | 462291.29 | 0.538
4690 | Louisiana | OUACHITA | MONROE | 5 | 3709507 | This project will place new ashpalt on Louisiana Avenue in Ouachita Parish from Wallace Dean Road to Wallace Road. | Pavement Improvement | 06/09/2010 |  | 07/21/2010 | 235618.75 | 0.25
4691 | Louisiana | OUACHITA | MONROE | 5 | 3709508 | This project in Ouachita Parish will place new asphalt pavement on Vancil Road from LA 838 to US 80. | Pavement Improvement | 06/09/2010 |  | 07/21/2010 | 746224.96 | 1.184
4692 | Louisiana | OUACHITA | MONROE | 5 | 3709509 | This project will plalce new asphalt on Hadley Street in Ouachita Parish from Nutland Road to approximately 0.5 miles west. | Pavement Improvement | 07/15/2010 |  |  | 419774.71 | 0.482
4693 | Louisiana | OUACHITA | MONROE | 5 | 3709512 | Riverside Dr. (Park Ave. to Louisville Ave.) - Repair roadway and place new asphalt from Bres St. to Louisville. Washington St.- (Walnut to North 14 th St.) Remove deteriorated concrete and replace | Pavement Improvement | 07/30/2010 |  |  | 683497.16 | 0.88
4694 | Louisiana | OUACHITA | MONROE | 5 | 3709513 | The City of Monroe will place new asphalt on approximately 1.4 miles of Riverside Drive from Park Avenue to Louisiville in Ouachita Parish. | Pavement Improvement | 07/15/2010 |  |  | 690402.2 | 0.001
4695 | Louisiana | PLAQUEMINES | NEW ORLEANS | 3 | 3809500 | This project will widen the roadway and place new asphalt along portions of Woodland Hwy (LA 406) in Plaquemines Parish. | Pavement Widening | 06/01/2010 | 06/01/2010 | 07/20/2010 | 1190336.45 | 1.858
4696 | Louisiana | RAPIDES | ALEXANDRIA | 5 | 4003530 | This project will construct sidewalks in the Town of Woodworth along Castor Plunge Road from Mason Rue Drive to Langston Drive, US 165 from Castor Plunge Road to a point approximately 1700' south of C | Transportation Enhancements | 06/12/2010 |  | 08/07/2010 | 405814.16 | 0.2
4697 | Louisiana | RAPIDES | ALEXANDRIA | 05 | 4008508 | This project will remove and upgrade with new impacts attenuator in four sites in Alexandria, LA. The locations of the sites are I-49 (2 sites), US 167 (1 site)), and US 71 (1 site). | Safety/Traffic Management | 05/10/2010 | 05/10/2010 | 06/28/2010 | 308975.34 | 0
4698 | Louisiana | ST BERNARD | NEW ORLEANS | 3 | 4409500 | This St. Bernard Parish project will improve drainage on LA 46 near Fortification Canal and ends at Paris Road. | Pavement Improvement | 07/15/2010 |  |  | 2235726.96 | 1.25
4699 | Louisiana | ST CHARLES | NEW ORLEANS | 3 | 4502500 | This project will construct a bike and walking path on the St. Charles Parish West Bank Mississippi River levee between Davis Drive in Luling to Elm Street in Hahnville. | Transportation Enhancements | 09/08/2009 | 09/08/2009 | 11/10/2009 | 1761764.79 | 0
4700 | Louisiana | ST CHARLES | NEW ORLEANS | 3 | 4508502 | This poject will place new asphalt along 1.4 miles of LA 3127 in Saint Charles Parish between Log mile 9.7 and Interstate 310 in St. Charles Parish. | Pavement Improvement | 01/25/2010 | 02/24/2010 | 03/08/2010 | 861400.98 | 1.21
4701 | Louisiana | ST MARTIN |  | 3 | 5003501 | This St. Martin Parish project in the City of Breaux Bridge on Refinery Road will replace the existing deficient timber bridge over Bayou Teche with a new concrete bridge. | Bridge Replacement | 06/15/2009 | 06/15/2009 | 07/05/2010 | 1969198.58 | 0
4702 | Louisiana | ST TAMMANY | SLIDELL | 1 | 5204528 | This St. Tammany Parish project will improve access at the LA 59 and Interstate 12 interchange by providing new turn lanes on LA 59 and widening of the ramp onto I-12. | Pavement Improvement | 08/22/2009 | 08/22/2009 | 01/09/2010 | 3246189.24 | 0.53
4703 | Louisiana | ST TAMMANY | MANDEVILLE-COVINGTON | 1 | 5208511 | This project located in the City of Covington, LA in St. Tammany Parish involve milling and overlaying the asphalt section of the roadway and cleaning and sealing the joints and cracks in the concrete | Pavement Improvement | 05/14/2010 | 05/14/2010 | 07/09/2010 | 859363.28 | 1.595
4704 | Louisiana | ST TAMMANY | SLIDELL | 1 | 5209503 | This St. Tammany Parish project located near Pearl River will widen the existing I-59 exit and entrance ramps and portions of LA 1090 at I-59. The project will provide additional turn lanes at the ex | Pavement Improvement | 09/08/2009 | 09/08/2009 | 10/20/2009 | 1402699.82 | 0.44
4705 | Louisiana | ST TAMMANY | MANDEVILLE-COVINGTON | 1 | 5209504 | This St. Tammany Parish project will improve traffic operations by constructing turn lanes and widening ramps at the US 11/I-12 interchange in Slidell, LA. | Pavement Improvement | 09/25/2009 | 09/25/2009 | 05/13/2010 | 5620179.56 | 1.43
4706 | Louisiana | ST TAMMANY | MANDEVILLE-COVINGTON | 1 | 5209505 | This St. Tammany Parish project is located in Covington and will construct an additional left turn lane for Northbound US 190 traffic turning onto westbound Park Drive. | Pavement Widening | 07/15/2010 |  |  | 517173.63 | 0.38
4707 | Louisiana | ST TAMMANY | SLIDELL | 1 | 5209506 | This St. Tammansy Parish project located in Slidell will construct a right turn lane from LA 1090 on to Brownswitch Road. | Pavement Improvement | 06/24/2010 |  |  | 817013.29 | 0.194
4708 | Louisiana | ST TAMMANY | SLIDELL | 1 | 5209507 | This St. Tammany Parish project located in Slidell will convert the existing intersection of LA 1091 and Brownswitch Road into a traffic roundabout. | Pavement Widening | 06/24/2010 |  |  | 1260101.2 | 0.11
4709 | Louisiana | ST TAMMANY | MANDEVILLE-COVINGTON | 1 | 5209508 | This project is located in the Covington/ Madisonville area of St. Tammany Parish. The project will construct additional left and right turn lanes at LA 21 and Brewster Road. | Pavement Widening | 07/30/2010 |  |  | 1513701.82 | 0
4710 | Louisiana | ST TAMMANY | SLIDELL | 1 | 5209509 | This St. Tammany Parish project is located in Slidell and includes widening LA 433 to provide additional right turn lanes onto I-10 and Voters Road. | Pavement Widening | 07/29/2010 |  |  | 1824168.37 | 0
4711 | Louisiana | ST TAMMANY | SLIDELL | 1 | 5209528 | This project in Slidell, LA in St. Tammany Parish will overlay LA 433 from 3.4 Mi South of US 190 to 1.06 Mi North US 11. This project is joint with federal project number ERP1(149)(150)(151) & ARR-52 | Pavement Improvement | 07/29/2010 |  |  | 1916541.4 | 6.46
4712 | Louisiana | ST TAMMANY | SLIDELL | 1 | 5209529 | This project in Slidell, LA in St. Tammany Parish will overlay LA 1090 from 0.15 Mi North of US 190 to the I-59 Ramps. This project is joint with federal project number ERP1(149)(150)(151) & ARR-5209( | Pavement Improvement | 07/29/2010 |  |  | 991470.86 | 4.3
4713 | Louisiana | TANGIPAHOA |  | 1 | 5302508 | The Tangipahoa Parish project in the City of Hammond on J.W. Davis Road will replace the existing deficient timber bridge over a canal with a concrete bridge. | Bridge Replacement | 06/29/2009 | 06/29/2009 | 05/03/2010 | 1110196.58 | 0
4714 | Louisiana | TANGIPAHOA |  | 1 | 5302509 | This Tangipahoa Parish project on Little Italy Road will replace the existing deficient timber bridge over a creek with a concrete bridge. | Bridge Replacement | 06/29/2009 | 06/29/2009 | 03/01/2010 | 509169.94 | 0
4715 | Louisiana | TANGIPAHOA |  | 1 | 5302510 | This project in Tangipahoa Parish on Bennett Road will replace the existing deficient concrete bridge over Natalbany Creek with a new concrete bridge. | Bridge Replacement | 07/09/2009 | 07/09/2009 | 03/11/2010 | 673130.77 | 0
4716 | Louisiana | TANGIPAHOA |  | 1 | 5302511 | This project in Tangipahoa Parish on Cooper Road will replace the existing deficient timber bridge over Cooper Creek with a new concrete bridge. | Bridge Replacement | 07/09/2009 | 07/09/2009 | 03/11/2010 | 473393.56 | 0
4717 | Louisiana | TERREBONNE | HOUMA | 3 | 5509505 | This Terrebonne Parish project will repair and place new asphalte along approximately 5.4 miles of the following streets: Alma Street, Country Drive, Klondyke Road, Southdown Mandalay Road, Westside B | Pavement Improvement | 06/04/2010 |  | 07/23/2010 | 965547.61 | 4.51
4718 | Louisiana | TERREBONNE | HOUMA | 3 | 5509507 | This project in Terrebonne Parish will construct turn lanes at the following 10 intersections: Bayou Gardens at West Park, Corporate Dr. at MLK Blvd., Corporate Dr. at West Tunnel Blvd., Coteau Rd. at | Pavement Improvement | 06/02/2010 | 06/02/2010 | 12/29/2010 | 1084116.71 | 0.001
4719 | Louisiana | ORLEANS | NEW ORLEANS | 2 | 6033009 | This Orleans Parish project consists of reconstructing and widening of Earhart Boulevard from Hamilton St to Fern St. | Pavement Improvement | 11/11/2009 | 01/04/2010 | 08/31/2011 | 12622195.91 | 0
4720 | Louisiana | WEST BATON ROUGE | BATON ROUGE | 6 | 6109503 | In West Baton Rouge Parish, a ramp will be added to the LA 1 northbound acceleeration lane at Emily Drive. | Pavement Widening | 04/20/2010 | 04/26/2010 | 06/01/2010 | 396890.86 | 0.24
4721 | Louisiana | WEST CARROLL |  | 5 | 6204500 | This West Carroll Parish project on Lingo Loop Road will replace the existing deficient timber bridge over Mill Bayou with a new concrete bridge. | Bridge Replacement | 08/05/2009 | 08/05/2009 | 03/17/2010 | 400743.18 | 0.157
4722 | Louisiana | WEST CARROLL |  | 5 | 6204501 | This West Carroll Parish project on Wood Road will ieplace the existing deficient timber bridge over Alligator Bayou with a new concrete bridge. | Bridge Replacement | 08/05/2009 | 08/05/2009 | 03/17/2010 | 385020.95 | 0
4723 | Louisiana | RAPIDES | ALEXANDRIA | 5 | 7869002 | Susek Drive is an existing two lane roadway in the northeast portion of Pineville, Louisiana in Rapides Parish. 2.2 miles of the roadway is to be reconstructed to two 12 foot lanes with curbs. The pro | Pavement Improvement | 09/14/2009 | 09/14/2009 | 10/19/2010 | 9171690.55 | 0.151
4724 | Louisiana | STATEWIDE |  | 6 | 9909526 | This project will replace the existing navigational radar systems on both the Plaquemine/Sunshine Ferry and the St. Francisville/New Roads Ferry with a modern systems that will provide a safer operati | Other | 01/25/2010 |  | 06/24/2010 | 300000 | 0
4725 | Louisiana | STATEWIDE |  | 5 | 9909527 | This Iberville Parish project will replace the existing main engine reduction gears on the M/V Ascension and will provide improved vessel speed and reliability. | Other | 03/15/2010 |  | 04/26/2010 | 305832.75 | 0
4726 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1048 | This Orelans Parish project consists of removing deteriorated pavement and placing new asphalt and striping on Leon C Simon Dr from London Ave Canal to Elysian Fields Ave. in New Orleans. | Transportation Enhancements | 11/20/2009 | 12/03/2009 | 04/05/2011 | 95456.18 | 0
4727 | Louisiana | ORLEANS | NEW ORLEANS | 1 | ERP1050 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Mirabeau Ave from St. Bernard Ave to Elysian Fields Ave. in New Orlea | Transportation Enhancements | 11/20/2009 | 12/03/2009 | 04/05/2011 | 607341.22 | 0
4728 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1051 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Filmore Ave from St. Bernard Ave to Elysian Fields Ave. in New Orlean | Transportation Enhancements | 11/20/2009 | 12/03/2009 | 04/05/2011 | 662825 | 0
4729 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1052 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on St. Bernard Ave from I-610 to Filmore Ave. in New Orleans. | Transportation Enhancements | 11/20/2009 | 12/03/2009 | 04/05/2011 | 531334.23 | 0
4730 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1053 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Paris Ave from I-610 to Mirabeau Ave. in New Orleans. | Transportation Enhancements | 11/20/2009 | 12/03/2009 | 04/05/2011 | 560927.71 | 0
4731 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1054 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Elysian Fields from Lakeshore Dr to US 90 in New Orleans. | Transportation Enhancements | 11/20/2009 | 12/03/2009 | 04/05/2011 | 1003155.45 | 0
4732 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1056 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Carrolton Avenue at I-10 and Claiborne Avenue (US 90) in the City of New Orleans. | Transportation Enhancements | 01/08/2010 | 01/08/2010 | 05/24/2011 | 524008.22 | 0
4733 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1057 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Carrolton Avenue at Claiborne (US 90) and St. Charles Avenues in the City of New Orleans. | Transportation Enhancements | 01/08/2010 | 01/08/2010 | 05/24/2011 | 814586.6 | 0
4734 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1063 | This Orleans Parish project will construct sidewalks on Nashville from Claiborne to Tchoupitoulas in New Orleans. | Transportation Enhancements | 10/06/2009 | 10/06/2009 | 04/24/2010 | 974814.24 | 0
4735 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1067 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Lasalle St. from Poydras St. to Tulane Ave. in New Orleans, LA. The project will overlay the street and add | Transportation Enhancements | 10/12/2009 | 11/03/2009 | 08/08/2010 | 438287.63 | 0
4736 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1068 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Gravier St. from Loyola Ave. to St. Peters St. in New Orleans, LA. | Transportation Enhancements | 10/12/2009 | 11/03/2009 | 08/08/2010 | 22036.72 | 0
4737 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1069 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Common St. from Loyola Ave. to St. Peters St. in New Orleans, LA. The project will overlay the street and p | Transportation Enhancements | 10/12/2009 | 11/03/2009 | 08/08/2010 | 776930.93 | 0
4738 | Louisiana | ORLEANS | NEW ORLEANS | 1 | ERP1071 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Magazine St. from Canal St. to US 90 Hwy. in New Orleans, LA. The project will overlay the street and parki | Transportation Enhancements | 10/12/2009 | 11/03/2009 | 08/08/2010 | 270462.51 | 0
4739 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1072 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Camp St.. from Canal St. to US 90 Hwy. in New Orleans, LA. The project will overlay the street and parking | Transportation Enhancements | 10/12/2009 | 11/03/2009 | 08/08/2010 | 334956.83 | 0
4740 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1075 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Loyola Ave. from Canal Street to US 90 Hwy. in New Orleans, LA. The project will overlay the street and par | Transportation Enhancements | 10/12/2009 | 11/03/2009 | 08/08/2010 | 1607566.25 | 0
4741 | Louisiana | ORLEANS | NEW ORLEANS | 2 | ERP1076 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Poydras St. from Lasalle St. to Loyola Ave. in New Orleans, LA. The project will overlay the street. T | Transportation Enhancements | 10/12/2009 | 11/03/2009 | 08/08/2010 | 3772.32 | 0
4742 | Louisiana | ST BERNARD | NEW ORLEANS | 3 | ERP1084 | This project will provide for the construction of sidewalks on Mehle Avenue in the city of Arabi (St. Bernard Parish) from LA 46 to LA 39. | Transportation Enhancements | 02/01/2010 | 02/15/2010 | 06/29/2010 | 103019.91 | 0
4743 | Louisiana | ST BERNARD | NEW ORLEANS | 3 | ERP1120 | This project will provide for the construction of sidewalks on Rowley Boulevard in the city of Arabi (St. Bernard Parish) from LA 46 to LA 39. | Transportation Enhancements | 02/01/2010 | 02/15/2010 | 06/29/2010 | 164364.32 | 0
4744 | Louisiana | ST BERNARD | NEW ORLEANS | 3 | ERP1122 | This project will provide for the construction of sidewalks on Cougar Drive in the city of Arabi (St. Bernard Parish) from Benjamin Street to Genet Drive. | Transportation Enhancements | 02/01/2010 | 02/15/2010 | 06/29/2010 | 238095.66 | 0
4745 | Louisiana | ST BERNARD | NEW ORLEANS | 3 | ERP1124 | This project will provide for the construction of sidewalks on East Genie Street in the city of Chalmette (St. Bernard Parish) from Golden Drive to Palmisano Boulevard. | Transportation Enhancements | 02/01/2010 | 02/15/2010 | 06/29/2010 | 158820.61 | 0
4746 | Louisiana | ST BERNARD | NEW ORLEANS | 3 | ERP1125 | This project will provide for the construction of sidewalks on Packenham Drive in the city of Chalmette ( St. Bernard Parish) from North Derbigny Street to West Genie Street. | Transportation Enhancements | 02/01/2010 | 02/15/2010 | 06/29/2010 | 125304.41 | 0
4747 | Louisiana | STATEWIDE |  | 4 | LA03003 | This project will provide four informational kiosks in the towns of Vivian, Plain Dealing, Sarepta, and Homer in Caddo, Bossier, Webster, Claiborne Parishes. | Transportation Enhancements | 08/18/2009 | 08/18/2009 | 04/27/2010 | 204285.98 | 0.001
4748 | Maine | ANDROSCOGGIN |  | 2 | 1001700 | Lisbon, Sabattus, Rt 9. Reconstruction of 6.75 miles of Route 9 beginning 0.33 of a mile northerly of Route 196 and extending northeasterly 6.75 miles to the Maine Turnpike Overpass. Work involves g | Pavement Improvement | 08/11/2009 | 08/11/2009 | 07/31/2011 | 9646830.99 | 6.75
4749 | Maine | CUMBERLAND |  | 1 | 1015800 | Portland, Veranda Street Bridge, Replacement of Veranda Street Overpass Bridge over Canadian Railroad | Bridge Improvement | 05/06/2009 | 05/06/2009 | 02/28/2010 | 1420227.32 | 0
4750 | Maine | HANCOCK |  | 2 | 1107200 | Ellsworth, Route 1A. Reconstruction of 2.67 miles of Route 1A beginning at the Rabbit Road and extending southeasterly 2.67 miles to 0.15 of a mile northerly of the Old Bangor Road. Work includes gra | Pavement Improvement | 08/05/2009 | 08/05/2009 | 06/30/2011 | 6406557.4 | 2.67
4751 | Maine | CUMBERLAND | PORTLAND | 1 | 1184400 | Portland, Bayside Trail. This project will design an extension of the Portland Trails system through the Bayside area of Portland along the abandoned Union Branch Rail Line extending from the Eastern | Transportation Enhancements | 08/11/2009 | 08/11/2009 | 09/30/2009 | 800000 | 0
4752 | Maine | WALDO |  | 2 | 1267600 | Lincolnville, Knights Hill Culvert Replacement on Route 52 over Meservy Brook | Bridge Improvement | 05/21/2009 | 05/21/2009 | 10/12/2009 | 255000 | 0
4753 | Maine | ANDROSCOGGIN |  | 2 | 1273700 | Auburn, Joline Drive Intersection Improvement with a signal at the intersection of Center Street, Joline Street, and Stetson Street | Safety/Traffic Management | 05/28/2009 | 05/28/2009 | 12/31/2009 | 567134.95 | 0
4754 | Maine | ANDROSCOGGIN |  | 2 | 1277700 | Turner, Route 117. Reconstruction of 2.39 miles of Route 117 including grading, paving, drainage and guardrail improvements. | Pavement Improvement | 07/22/2009 | 07/22/2009 | 09/20/2009 | 2789003.76 | 2.39
4755 | Maine | ANDROSCOGGIN |  | 2 | 1305900 | Auburn, Joline Drive. Reconstruction of 0.18 of a mile beginning at Center Street and extending westerly to Turner Street. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 11/30/2009 | 379538 | 0.18
4756 | Maine | ANDROSCOGGIN |  | 2 | 1306100 | Lewiston, Russell Street. Reconstruction of 0.51 miles beginning at the convergence of the ramps to Main Street, extending easterly to Robinson Gardens. This project will include construction of left | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/11/2009 | 2106788.41 | 0.51
4757 | Maine | YORK |  | 1 | 1308500 | Biddeford, Route 111. Highway resurfacing beginning at Main Street (Route 9) and extending westerly 0.97 of a mile to 0.10 of a mile easterly of Marshall Avenue. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 583688.73 | 0.97
4758 | Maine | YORK |  | 1 | 1308600 | Biddeford, Route 9. Highway resurfacing beginning at Parkside and extending 0.95 of a mile to Alfred Street. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 429553.62 | 0.95
4759 | Maine | CUMBERLAND |  | 1 | 1310400 | Portland, Auburn Street. Intersection improvement with signal located at the intersection of Auburn Street and Lyseth Moore Drive. | Safety/Traffic Management | 07/02/2009 | 07/02/2009 | 12/31/2009 | 253396.5 | 0
4760 | Maine | YORK |  | 1 | 1311100 | Saco, North Street. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile northerly of Park Street and extending 1.00 mile to 0.34 of a mile southerly of Hillview Avenue. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 253205.96 | 1
4761 | Maine | YORK |  | 1 | 1334100 | Biddeford-Kennebunk, Eastern Trail, Construct a bicycle/pedestrian trail from Rt. 111 in Biddeford to Route 35 in Kennebunk. | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 07/31/2010 | 1437316 | 0
4762 | Maine | CUMBERLAND |  | 1 | 1480600 | Portland, Cumberland Avenue. Highway resurfacing beginning at Franklin Arterial and extending 0.29 of a mile to Elm Street. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 09/30/2009 | 141419.15 | 0.29
4763 | Maine | CUMBERLAND |  | 1 | 1480700 | Westbrook, Eisenhower Drive. Highway resurfacing beginning at Saco Street and extending 0.88 of a mile to Spring Street. Includes shoulder resurfacing. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 08/31/2009 | 570450.54 | 0.87
4764 | Maine | YORK |  | 1 | 1480800 | Saco, Beach Street-Ferry Road. Pave a 3/4" hot mix asphalt overlay beginning at North Street and extending 1.11 miles to Pine Ridge Road. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 224904.49 | 1.11
4765 | Maine | CUMBERLAND |  | 1 | 1480900 | Falmouth, Brook Road. Pave a 1 1/4" hot mix asphalt overlay beginning at the Westbrook town line and extending 0.74 of a mile to the Leighton Road. The project will include drainage and the installa | Pavement Improvement | 05/28/2009 | 05/28/2009 | 08/31/2009 | 497817.38 | 0.48
4766 | Maine | CUMBERLAND |  | 1 | 1481100 | Portland, Westbrook Street. Pave a 1 1/4" hot mix asphalt overlay beginning at the Westbrook town line and extending 0.89 miles to Congress Street. Project includes alteration of 24 catch basins and | Pavement Improvement | 06/16/2009 | 06/16/2009 | 09/30/2009 | 267978.85 | 0.89
4767 | Maine | SAGADAHOC |  | 1 | 1511450 | Interstate I-295 Northbound, Brunswick to Gardiner. This project involves reconstruction of the roadway including grinding and rubblizing the existing concrete roadway, grading and paving, drainage a | Pavement Improvement | 03/03/2009 | 03/03/2009 | 10/10/2009 | 33500000 | 23.88
4768 | Maine | KENNEBEC |  | 1 | 1511460 | Interstate I-295 Northbound, Topsham to Gardiner. This project involves building the crossovers from the northbound lanes to the southbound lanes as part of the traffic detour for the I-295 northboun | Safety/Traffic Management | 03/30/2009 | 03/30/2009 | 10/06/2009 | 1751386.05 | 0
4769 | Maine | LINCOLN |  | 1 | 1561300 | Damariscotta, Salt Bay Steel Culvert Bridge Replacement over Oyster Creek, located on Belvedere Road at the Damariscotta-Nobleboro town line. | Bridge Replacement | 05/29/2009 | 05/29/2009 | 10/08/2009 | 511591.54 | 0
4770 | Maine | KENNEBEC |  | 1 | 1561400 | Hallowell, Second Street Bridge Rehabilitation over Maine Central Railroad. Replace existing deck and repair concrtete bridge abutments and retaining walls. | Bridge Replacement | 05/05/2009 | 05/05/2009 | 03/30/2010 | 1232549 | 0
4771 | Maine | PENOBSCOT |  | 2 | 1562700 | Township 2 Region 8, Lincoln Spur Bridge Deck Replacement located over Interstate 95 northbound and southbound. Replace existing deck and install new safety barriers. | Bridge Improvement | 04/24/2009 | 04/24/2009 | 10/11/2009 | 1344424.7 | 0
4772 | Maine | HANCOCK |  | 2 | 1568900 | Sullivan, Route 1. Intersection Improvements including construction of a bypass lane located at the intersection of Route 1 and the Ashville Road. | Safety/Traffic Management | 06/24/2009 | 06/24/2009 | 08/31/2009 | 316313.74 | 0
4773 | Maine | OXFORD |  | 2 | 1571600 | Lovell, Main Street. Pave a 3/4" hot mix asphalt overlay beginning 0.82 of a mile north of Christian Hill Road and extending northerly 1.66 miles to 0.12 of a mile south of West Lovell Road. | Pavement Improvement | 04/14/2009 | 04/14/2009 | 10/09/2009 | 319487.96 | 1.66
4774 | Maine | CUMBERLAND |  | 1 | 1571900 | Sebago, Sebago Road. Pave a 3/4" hot mix asphalt overlay beginning at Shore Road and extending northerly 0.90 miles to 0.17 of a mile northerly of Woodland Road. | Pavement Improvement | 04/14/2009 | 04/14/2009 | 10/09/2009 | 263701.29 | 0.91
4775 | Maine | CUMBERLAND |  | 1 | 1572000 | Standish, Route 114. Pave a 3/4" hot mix asphalt overlay eginning 0.16 of a mile north of Route 35 and extending northerly 6.50 miles to 0.94 of a mile south of the Standish-Sebago town line. | Pavement Improvement | 04/14/2009 | 04/14/2009 | 10/09/2009 | 1121709.23 | 6.5
4776 | Maine | KENNEBEC |  | 2 | 1573700 | Clinton, Baker Street. Pave a 3/4" hot mix asphalt overlay beginning at Route 11 and extending northerly 1.16 miles. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/05/2009 | 411142.34 | 1.16
4777 | Maine | SOMERSET |  | 2 | 1573900 | Fairfield, Route 23. Pave a 3/4" hot mix asphalt overlay beginning at Route 201 and extending northerly 0.65 of a mile to 0.19 of a mile northerly of Pishon Ferry Road. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 109143.83 | 0.65
4778 | Maine | KENNEBEC |  | 2 | 1574600 | Oakland, Fairfield Street. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile northerly of Greeley Street and extending northerly 0.85 of a mile to 0.30 of a mile northerly of Municipal Dri | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/06/2009 | 153247.97 | 0.85
4779 | Maine | KENNEBEC |  | 2 | 1574700 | Oakland, Pleasant Street. Pave a 3/4" hot mix asphalt overlay beginning at Oak Street and extending easterly 0.37 of a mile to Route 11. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 84886.84 | 0.37
4780 | Maine | KENNEBEC |  | 1 | 1575000 | Randolph, Route 9. Pave a 3/4" hot mix asphalt overlay beginning 0.05 of a mile westerly of the Chelsea-Randolph town line and extending easterly 3.67 miles to 0.10 of a mile easterly of the Augusta- | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/05/2009 | 601652.04 | 3.59
4781 | Maine | KENNEBEC |  | 2 | 1575700 | Waterville, Oak Street. Pave a 3/4" hot mix asphalt overlay beginning at Main Street and extending easterly 0.46 of a mile to College Avenue. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/05/2009 | 117408.17 | 0.46
4782 | Maine | FRANKLIN |  | 2 | 1576500 | Eustis, Route 27. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile south of Route 16 and extending northerly 1.26 miles. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 09/30/2009 | 226899.25 | 1.26
4783 | Maine | SOMERSET |  | 2 | 1577000 | Jackman, Route 6. Pave a 3/4" hot mix asphalt overlay beginning 2.19 miles westerly of the Long Pond Twp town line and extending easterly 2.19 miles. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 608120.69 | 2.19
4784 | Maine | PISCATAQUIS |  | 2 | 1577400 | Sapling Township., Rockwood Road. Pave a 3/4" hot mix asphalt overlay beginning 0.05 of a mile westerly of the Sapling Township-Big Moose Township town line and extending easterly 6.10 miles to 0.46 | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 1112301.88 | 6.1
4785 | Maine | SOMERSET |  | 2 | 1579000 | Palmyra, Ell Hill Road. Pave a 3/4" hot mix asphalt overlay beginning at Somerset Avenue and extending northerly 6.27 miles to 0.03 of a mile northerly of Ford Hill Road. | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/10/2009 | 1178865.74 | 6.27
4786 | Maine | AROOSTOOK |  | 2 | 1579700 | Caswell, Van Buren Road. Pave a 3/4" hot mix asphalt overlay beginning 0.29 of a mile southerly of the Hamlin town line and extending northerly 5.69 miles to 1.18 miles southerly of Albert Cyr Road. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/08/2009 | 1588813.43 | 5.62
4787 | Maine | ANDROSCOGGIN |  | 2 | 1581400 | Auburn, Turner Street. Pave a 3/4" hot mix asphalt overlay beginning at Center Street and extending northerly 1.08 miles to 0.30 of a mile southerly of Mount Auburn Avenue. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 07/31/2009 | 381205.93 | 1.08
4788 | Maine | KENNEBEC |  | 1 | 1583000 | Gardiner, Water Street. Pave a 3/4" hot mix asphalt overlay beginning at Cobbossee Avenue and extending easterly 1.10 miles to Route 201. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/09/2009 | 278105.84 | 1.1
4789 | Maine | KENNEBEC |  | 1,2 | 1583100 | Litchfield, Route 9. Pave a 3/4" hot mix asphalt overlay beginning 0.17 of a mile westerly of the Huntington Hill Road and extending easterly 3.99 miles to 0.06 of a mile westerly of the Bog Hill Roa | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/09/2009 | 714525.86 | 4.01
4790 | Maine | KENNEBEC |  | 2 | 1583200 | Oakland, Route 11. Grind and remove 1 1/4" of existing pavement and replace with a 1 1/4" hot mix asphalt overlay beginning at Route 23 and extending northerly 4.46 miles to 0.01 of a mile northerly | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/11/2009 | 844096.65 | 4.46
4791 | Maine | KENNEBEC |  | 1 | 1584000 | West Gardiner, Lewiston Road. Pave a 1 1/4" hot mix asphalt overlay beginning 0.42 of a mile westerly of the I-95 Exit 102 On-ramp and extending easterly 1.69 miles to 0.11 of a mile westerly of the | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/09/2009 | 722543.79 | 1.69
4792 | Maine | SOMERSET |  | 2 | 1584300 | Fairfield, Norridgewock Road. Grind and remove 1 1/4" of the existing pavement and replace with a 1 1/4" hot mix asphalt overlay beginning 1.87 miles west of Routes 104/139 and extending westerly 4.75 | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2009 | 988920.78 | 4.75
4793 | Maine | FRANKLIN |  | 2 | 1584900 | New Sharon, Route 27. Pave a 3/4" hot mix asphalt overlay beginning 0.38 of a mile southerly of York Hill Road and extending northerly 2.65 miles to Route 2. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/10/2009 | 511207.78 | 2.65
4794 | Maine | PENOBSCOT |  | 2 | 1585100 | Bangor, Broadway. Pave a 3/4" hot mix asphalt overlay beginning at the Interstate 95 southbound Exit 185 ramps and extending northerly 0.65 of a mile to Grandview Avenue. | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/08/2009 | 185816.55 | 0.56
4795 | Maine | PENOBSCOT |  | 2 | 1585300 | Bangor, Hogan Road. Grind and remove 1 1/4" of existing asphalt and replace with a 1 1/4" of hot mix asphalt overlay beginning 0.10 miles southerly of the intersection of Mt. Hope and extending north | Pavement Improvement | 07/08/2009 | 07/08/2009 | 08/31/2009 | 451562.08 | 1.24
4796 | Maine | WASHINGTON |  | 2 | 1586200 | East Machias, Route 1. Pave a 3/4" hot mix asphalt overlay beginning 0.37 of a mile northerly of Chase Mills Road and extending northerly 1.00 mile to 0.47 of a mile northerly of the Whiting town lin | Pavement Improvement | 07/21/2009 | 07/21/2009 | 06/30/2010 | 249231.28 | 1
4797 | Maine | SOMERSET |  | 2 | 1587500 | Pittsfield, Park Street. Grind and remove 1 1/4" of existing asphalt and replace with a 1 1/4" hot mix asphalt overlay beginning at North Main Street and extending northerly 0.19 of a mile to Somerse | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/10/2009 | 58907.85 | 0.19
4798 | Maine | ANDROSCOGGIN |  | 2 | 1588200 | Auburn, Route 202. Pave a 3/4" hot mix asphalt overlay beginning at Minot Avenue and extending northerly 0.68 of a mile to Lisbon Street. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 07/31/2009 | 279516.49 | 0.68
4799 | Maine | ANDROSCOGGIN |  | 2 | 1588500 | Auburn, Minot Avenue. Pave a 3/4" hot mix asphalt overlay beginning at High Street and extending northerly 0.51 of a mile to Court Street. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 07/31/2009 | 214358.35 | 0.51
4800 | Maine | CUMBERLAND |  | 1 | 1589100 | Interstate I-295 Southbound, Freeport. Work involves replacing culvert underneath I-295 Exit 22 on and off ramps. | Bridge Improvement | 07/07/2009 | 07/07/2009 | 10/31/2009 | 143100 | 0.06
4801 | Maine | CUMBERLAND |  | 1 | 1590100 | Portland, Forest Avenue. Grind and remove 1 1/4" existing asphalt and replace with 1 1/4" hot mix asphalt beginning at Warren Avenue and extending northerly 1.15 miles to Castine Avenue. | Pavement Improvement | 06/16/2009 | 06/16/2009 | 09/30/2009 | 677796.29 | 0.98
4802 | Maine | CUMBERLAND |  | 1 | 1590300 | Interstate I-295 Southbound, Portland. Paving 0.42 miles beginning 0.13 of a mile north of the Washington Avenue Southbound on-ramp. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 08/31/2009 | 84242 | 0.42
4803 | Maine | LINCOLN |  | 1 | 1591800 | Edgecomb, Route 1. Pave a 3/4" hot mix asphalt overlay beginning 0.08 of a mile northerly of Eddy Road and extending northerly 1.02 miles to 0.05 of a mile northerly of Cochran Road. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2009 | 519451.66 | 1.02
4804 | Maine | SOMERSET |  | 2 | 1593200 | Caratunk, Route 201. Pave a 3/4" hot mix asphalt overlay beginning 3.74 miles southerly of the The Forks Plantation town line and extending northerly 3.77 miles. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 598207 | 3.77
4805 | Maine | FRANKLIN |  | 2 | 1593300 | Farmington, Route 2. Grind and remove 1 1/4" of existing pavement and replace with 1 1/4" of hot mix as[halt beginning 500 feet west of the bridge to Prescott Street; Route 2/4/27 intersection to Hil | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/10/2009 | 495279.15 | 2.87
4806 | Maine | SOMERSET |  | 2 | 1593600 | Moose River, Route 201. Pave a 3/4" hot mix asphalt overlay beginning 0.26 of a mile northerly of Sandy Stream Road and extending northerly 13.65 miles to the Canadian border. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 2226123.37 | 13.65
4807 | Maine | SOMERSET |  | 2 | 1594100 | West Forks Plantation., Route 201. Pave a 3/4" hot mix asphalt overlay beginning 0.16 of a mile southerly of the Parlin Pond Township town line and extending northerly 13.62 miles to 2.60 miles north | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/10/2009 | 2189119.98 | 13.62
4808 | Maine | PENOBSCOT |  | 2 | 1594300 | Bangor, Broadway (Route 15). Pave a 3/4" hot mix asphalt overlay beginning 325' easterly of the I-95 northbound Exit 185 ramps and extending northerly 0.23 of a mile to the I-95 southbound Exit 185 r | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/08/2009 | 89609.23 | 0.23
4809 | Maine | PENOBSCOT |  | 2 | 1594800 | Hampden, Route 202. Pave a 3/4" hot mix asphalt overlay beginning at Western Avenue and extending northerly 4.02 miles to the Interstate 395 Exit 2 eastbound ramps. | Pavement Improvement | 04/13/2009 | 04/13/2009 | 10/08/2009 | 1262169.22 | 4.02
4810 | Maine | PENOBSCOT |  | 2 | 1595300 | Interstate I-95 Southbound, Mattamiscontis Township to Howland. 10.37 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2009 | 4259760.87 | 10.37
4811 | Maine | PENOBSCOT |  | 2 | 1595400 | Interstate I-95 Southbound, Township 2 Region 8 NWP to Mattamiscontis Township. 7.06 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/06/2009 | 2608466.57 | 7.06
4812 | Maine | HANCOCK |  | 2 | 1669600 | Deer Isle-Sedgwick Bridge Substructure Rehabilitation over Eggemoggin Reach, located on the Deer Isle-Sedgwick town line. Repair bridge tower piers. | Bridge Improvement | 09/16/2009 | 09/16/2009 | 10/31/2010 | 10094550.21 | 0
4813 | Maine | KNOX |  | 1 | 1674500 | South Thomaston, Spruce Head Bridge Replacement on Island Road. | Bridge Replacement | 08/19/2009 | 08/19/2009 | 05/31/2010 | 2196049.9 | 0
4814 | Maine | PENOBSCOT |  | 2 | 1677500 | Interstate I-95 Southbound, Howland to Old Town. 15.6 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2010 | 4513576.77 | 15.6
4815 | Maine | AROOSTOOK |  | 02 | 1681910 | Interstate I-95 Northbound - highway resurfacing beginning 2.86 miles north of the Oakfield/Smryna town line and extends northerly 13.64 miles to the Canadian border. | Pavement Improvement | 02/04/2010 | 05/15/2010 | 10/31/2010 | 6918467.9 | 0
4816 | Maine | PENOBSCOT |  | 2 | 1682200 | Interstate I-95 Southbound, Township 2 Region 9 NWP to Township 2 Region 8 NWP. 8.22 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 04/08/2009 | 04/08/2009 | 10/07/2010 | 2542725 | 8.22
4817 | Maine | WASHINGTON |  | 2 | 1698300 | Lubec, Route 189. Pave a 1-1/4" hot mix asphalt overlay beginning at the intersection of Route 1 and extending easterly approximately 6.7 miles. | Pavement Improvement | 07/21/2009 | 07/21/2009 | 06/30/2010 | 3294190.47 | 11.19
4818 | Maine | CUMBERLAND |  | 1 | 1700800 | South Portland-Portland, Long Creek Watershed. Pavement treatment on Maine Mall Road designed to enhance treatment of stormwater runoff in an urban impaired stream watershed as recommended by the Lon | Other | 06/29/2009 | 06/29/2009 | 12/31/2009 | 1685245 | 0
4819 | Maine | STATEWIDE |  | 1 | 1736501 | On the Job Training/Support Services to fund apprenticeships and training centers for underrepresented or disadvantaged people pursuing careers in transportation, engineering or construction. | Other | 04/28/2010 | 04/29/2010 | 09/30/2010 | 351409 | 0
4820 | Maine | WALDO |  | 2 | 1763400 | Rehabilitation of the Maine State Ferry Service's pier structure and the Islesboro and Lincolnville locations. | Other | 11/19/2009 | 11/20/2009 | 12/30/2011 | 1300000 | 0
4821 | Maine | PISCATAQUIS |  | 2 | A001000 | Dover-Foxcroft, Route 15. Reconstruction of 1.29 miles of Route 15 including drainage, paving, re-alignment of side roads, guardrail and safety improvements. | Pavement Improvement | 07/20/2009 | 07/20/2009 | 06/30/2010 | 2889444.44 | 1.29
4822 | Maryland | HARFORD |  |  | 0003125 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This project is in Ha | Pavement Improvement | 05/17/2010 | 05/17/2010 |  | 1152250 | 0
4823 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 5 | 0003134 | Maryland State Highway will be replacing the deteriorated Berwyn Creek concrete bridge deck with a new deck under their bridge system preseveration program. | Bridge Improvement | 03/18/2010 | 03/18/2010 |  | 671987 | 0
4824 | Maryland | ANNE ARUNDEL |  | 1 | 000A368 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/22/2009 | 09/29/2009 | 11/01/2011 | 4612024 | 0
4825 | Maryland | CALVERT |  | 1 | 000A369 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/05/2009 | 05/14/2009 | 11/01/2011 | 5117038 | 0
4826 | Maryland | CHARLES |  | 5 | 000A370 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 04/29/2009 | 05/20/2009 | 11/01/2011 | 4612050 | 0
4827 | Maryland | ST MARYS |  | 5 | 000A371 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 | 06/11/2009 | 12/01/2011 | 6140665 | 0
4828 | Maryland | ANNE ARUNDEL |  | 5 | 000A373 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 07/16/2009 | 10/15/2009 | 12/01/2011 | 6688533 | 0
4829 | Maryland | STATEWIDE |  | 4,5,6,8 | 000A375 | This is a signalization project. Signals and Reconstructs in District 3. This contract is required for routine capital signal improvement efforts in District 3. | Safety/Traffic Management | 08/20/2009 | 09/30/2009 |  | 5287442 | 0
4830 | Maryland | CECIL |  | 1 | 000A379 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/09/2009 | 09/20/2009 | 12/01/2011 | 3408022 | 0
4831 | Maryland | KENT |  | 1 | 000A380 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 | 06/15/2009 | 11/01/2011 | 2306012 | 0
4832 | Maryland | QUEEN ANNES |  | 1 | 000A381 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 | 06/09/2009 | 12/01/2011 | 3828006 | 0
4833 | Maryland | TALBOT |  | 1 | 000A382 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/05/2009 | 06/10/2009 | 11/01/2011 | 2288019 | 0
4834 | Maryland | STATEWIDE |  | 1,2,3,4,5,6,7,8 | 000A385 | This project will improve interstate lighting and enhance safety at various interchanges. | Safety/Traffic Management | 01/16/2010 | 02/26/2010 |  | 8061776 | 0
4835 | Maryland | STATEWIDE |  | 1 | 000A386 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Dorchester, Somerset, Wicomico, and Worcester Coun | Pavement Improvement | 06/24/2009 | 10/05/2009 | 06/01/2012 | 3088800 | 0
4836 | Maryland | STATEWIDE |  | 4,5,6,8 | 000A387 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Montgomery and Prince George’s Counties. This work | Transportation Enhancements | 06/16/2009 | 07/22/2009 | 07/01/2012 | 3612818 | 0
4837 | Maryland | STATEWIDE |  | 1,2,3,6,7 | 000A388 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Baltimore and Harford Counties. This work will add | Transportation Enhancements | 06/23/2009 | 08/11/2009 | 06/01/2011 | 2623097 | 0
4838 | Maryland | STATEWIDE |  | 1,2,3,5 | 000A389 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Anne Arundel, Calvert, Charles, and St. Mary’s Cou | Transportation Enhancements | 07/14/2009 | 08/03/2009 | 06/01/2011 | 2904467 | 0
4839 | Maryland | STATEWIDE |  | 3,6,7 | 000A390 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Carroll, Frederick, and Howard Counties. This work | Transportation Enhancements | 07/16/2009 | 07/27/2009 | 06/01/2011 | 1987656 | 0
4840 | Maryland | DORCHESTER |  | 1 | 000A395 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. Various locations in | Pavement Improvement | 03/11/2009 | 03/30/2009 | 12/01/2010 | 2903015 | 0
4841 | Maryland | SOMERSET |  | 1 | 000A396 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Somerset County that will enhance pavement life and provide | Pavement Improvement | 03/11/2009 | 03/30/2009 | 12/01/2010 | 3106037 | 0
4842 | Maryland | WICOMICO |  | 1 | 000A397 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Wicomico County that will enhance pavement life and provide | Pavement Improvement | 04/08/2009 | 06/28/2009 | 12/01/2010 | 2773001 | 0
4843 | Maryland | WORCESTER |  | 1 | 000A398 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Worcester County that will enhance pavement life and provid | Pavement Improvement | 03/11/2009 | 05/10/2009 | 12/01/2010 | 3606058 | 0
4844 | Maryland | STATEWIDE |  | 1 | 000A400 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Dorchester, Somerset, Wicomico, and Worcester Counties. The work may als | Safety/Traffic Management | 06/09/2009 | 12/16/2009 | 12/01/2011 | 379808 | 0
4845 | Maryland | STATEWIDE |  | 1 | 000A401 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Caroline, Cecil, Kent, Queen Anne’s and Talbot Counties. The work may al | Safety/Traffic Management | 06/09/2009 |  | 01/01/2012 | 299042 | 0
4846 | Maryland | STATEWIDE |  | 4,5,6,8 | 000A402 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Montgomery County and Prince George’s Counties. The work may also includ | Safety/Traffic Management | 06/03/2009 |  | 12/01/2011 | 468485 | 0
4847 | Maryland | STATEWIDE |  | 1,2,3,6,7 | 000A403 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Baltimore and Harford Counties. The work may also include installation o | Safety/Traffic Management | 05/20/2009 | 12/01/2009 | 01/01/2012 | 441541 | 0
4848 | Maryland | STATEWIDE |  | 1,2,3,5 | 000A404 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Anne Arundel, Calvert, Charles, and St Mary’s Counties Counties. The wor | Safety/Traffic Management | 05/20/2009 | 06/08/2009 | 12/01/2011 | 597345 | 0
4849 | Maryland | STATEWIDE |  | 3,6,7 | 000A405 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Carroll, Frederick, and Howard Counties. The work may also include instal | Safety/Traffic Management | 05/21/2009 | 09/14/2009 | 01/01/2012 | 580636 | 0
4850 | Maryland | ALLEGANY |  | 6 | 000A406 | This project involves resurfacing and pavement preservation of various locations in Allegheny County. The project will improve ride and improve deterirating sections of the highway. Work will be dod | Pavement Improvement | 06/09/2009 | 07/17/2009 | 01/30/2012 | 3471080 | 0
4851 | Maryland | BALTIMORE |  | 1,2,3,6,7 | 000A407 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 10/07/2009 |  |  | 5112046 | 0
4852 | Maryland | BALTIMORE |  | 1,2,3,6,7 | 000A408 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 10/07/2009 | 03/23/2010 |  | 5412023 | 0
4853 | Maryland | CARROLL |  | 6 | 000A409 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/18/2009 | 07/06/2009 | 12/01/2011 | 2958005 | 0
4854 | Maryland | HARFORD |  | 1,2,6 | 000A410 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/09/2009 | 08/05/2009 | 12/01/2011 | 5812006 | 0
4855 | Maryland | MONTGOMERY |  | 4,6,8 | 000A411 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 | 06/15/2009 | 12/01/2011 | 5076015 | 0
4856 | Maryland | MONTGOMERY |  | 4,6,8 | 000A412 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/27/2009 | 07/16/2009 | 12/01/2011 | 5736006 | 0
4857 | Maryland | PRINCE GEORGES |  | 4,5,8 | 000A413 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/15/2009 | 10/09/2009 | 12/01/2011 | 5066050 | 0
4858 | Maryland | PRINCE GEORGES |  | 4.5 | 000A414 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 | 06/29/2009 | 12/01/2011 | 5876063 | 0
4859 | Maryland | WASHINGTON |  | 6 | 000A415 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/20/2009 | 07/17/2009 | 12/01/2011 | 3078053 | 0
4860 | Maryland | FREDERICK |  | 6 | 000A416 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 05/21/2009 | 06/29/2009 | 12/01/2011 | 7026051 | 0
4861 | Maryland | GARRETT |  | 6 | 000A417 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/09/2009 | 08/03/2009 | 12/01/2011 | 2623007 | 0
4862 | Maryland | HOWARD |  | 3,7 | 000A418 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. At some locations, i | Pavement Improvement | 05/18/2009 | 07/26/2009 | 12/01/2011 | 6372010 | 0
4863 | Maryland | STATEWIDE |  | 1,2,3,4,5,6,7,8 | 000A419 | This project will repair concrete pavement and curb at Truck Weigh/Inspection Stations due to severely cracked roadway surface. Project will also improve geometric and drainage. This is a statewide | Pavement Improvement | 06/09/2009 | 07/28/2009 | 07/01/2012 | 1344595 | 0
4864 | Maryland | CAROLINE |  | 1 | 000A420 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 06/09/2009 | 06/22/2009 | 12/01/2011 | 2516042 | 0
4865 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 4.5 | 000A421 | Maryland State Highway will clean and paint ten bridges in Prince George's County as part of its bridge system preservation program. This project will extend the life of the existing bridges. | Bridge Improvement | 03/11/2009 | 05/18/2009 | 06/01/2010 | 1789806 | 0
4866 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 4,5,8 | 000A422 | Cleaning and painting bridges for longer service life on US 1, MD201, MD202, MD212 and MD500 | Bridge Improvement | 03/30/2009 | 05/11/2009 | 05/01/2010 | 1742046 | 0
4867 | Maryland | STATEWIDE |  | 1,2,3,6,7 | 000A423 | This project will improve safety for the travelling public. Maryland State Highway will rehabilitate existing substandard traffic barrier at various locations in Baltimore and Harford Counties. InB | Safety/Traffic Management | 06/10/2009 | 07/13/2009 | 01/01/2011 | 833976 | 0
4868 | Maryland | STATEWIDE |  | 1,2,3,5 | 000A424 | Maryland State Highway will upgrade guard rails at various locations in Anne Arundel, Calvert, Charles and St. Mary's Counties. This project will will improve safety for the travelling public. In An | Safety/Traffic Management | 06/15/2009 | 06/29/2009 | 01/01/2011 | 833976 | 0
4869 | Maryland | STATEWIDE |  | 3,6,7 | 000A425 | This project will improve safety for motorists by upgrading existing guardrails at various locations in Garrett, Washington, Carroll, Frederick and Howard Counties. | Safety/Traffic Management | 06/09/2009 | 08/24/2009 | 01/01/2011 | 1904760 | 0
4870 | Maryland | STATEWIDE |  | 4,5,6,8 | 000A426 | This project will improve safety for motorists by upgrading existing guardrails at various locations in Montgomery and prince George's Counties. | Safety/Traffic Management | 06/15/2009 | 08/17/2009 | 01/01/2011 | 852738 | 0
4871 | Maryland | STATEWIDE |  | 1,2,3,4,5,6,7,8 | 000A427 | This project will install and upgrade signing at various locations. This project will improve safety of motorist. | Safety/Traffic Management | 03/16/2009 | 07/01/2009 | 04/01/2012 | 5922034 | 0
4872 | Maryland | STATEWIDE |  | 1 | 000A428 | Maryland State Highway will install new median traffic barrier and rehabilitate non-compliance traffic barrier on approximately 17 mile section of US50 in Dorchester, Somerset, Wicomico and Worcester | Safety/Traffic Management | 06/15/2009 | 01/04/2010 | 01/01/2011 | 1615969 | 0
4873 | Maryland | STATEWIDE |  | 1 | 000A429 | Maryland State Highway will rehabilitate existing substandard traffic barrier at various locations in Cecil (along 17 miles of US40), Queen Anne's (along 15.5 miles of US50) and Talbot (along 21 miles | Safety/Traffic Management | 07/13/2009 | 07/27/2009 | 01/01/2011 | 2283767 | 0
4874 | Maryland | STATEWIDE |  | 1,2,3,5,6,7 | 000A430 | This contract will provide for upgrades to camera video detection for the traffic control timing of the different phases of operation. It will install traffic detection at signalized intersections in | Safety/Traffic Management | 06/16/2009 | 06/30/2009 | 07/01/2011 | 1824752 | 0
4875 | Maryland | STATEWIDE |  | 1,2,3,4,5,6,7,8 | 000A431 | This project is for dynamic message signs deployment to ncrease CHART's (Maryland State's traffic operation's center) information dissemmation capibilities. | Safety/Traffic Management | 07/28/2009 | 04/07/2010 | 08/01/2012 | 3756551 | 0
4876 | Maryland | STATEWIDE |  | 3,4,5,6,7,8 | 000A432 | This project will install battery backups and other signal improvements throughout the state districts. | Safety/Traffic Management | 10/21/2009 | 03/17/2010 | 08/31/2011 | 5580749 | 0
4877 | Maryland | STATEWIDE |  | 3,4,5,6,7,8 | 000A433 | This contract will provide for upgrades to camera video detection for the traffic control timing of the different phases of operation. | Safety/Traffic Management | 06/25/2009 | 07/13/2009 | 08/01/2011 | 1672809 | 0
4878 | Maryland | STATEWIDE |  | 1,2,3,5,6 | 000A434 | This project will install battery backups and other signal improvements throughout the state districts. | Safety/Traffic Management | 08/13/2009 | 09/07/2009 | 09/01/2011 | 5296976 | 0
4879 | Maryland | STATEWIDE |  | 1,2,3,6,7 | 000A443 | This project will install containerized trees and seedlings at various locations including, but not limited to 34 sites throughout Baltimore, | Transportation Enhancements | 07/13/2009 | 09/10/2009 | 09/30/2011 | 367839 | 0
4880 | Maryland | STATEWIDE |  | 1,2,3,4,5,6,7,8 | 000A445 | This project will install sign lighting system at various locations to improve safety for motorists. | Safety/Traffic Management | 08/25/2009 | 09/02/2009 | 09/01/2011 | 2541339 | 0
4881 | Maryland | STATEWIDE |  | 1,2,3,5 | 000A446 | This project will install and establish trees at various locations in Anne Arundel, Calvert, Charles and Saint Mary Counties. This work involves the removal of dead or invasive species, as well as, | Transportation Enhancements | 12/23/2009 |  |  | 245907 | 0
4882 | Maryland | STATEWIDE |  | 1 | 000A447 | This project will plant trees and bare root seedlings at various locations including, but not limited to 25 sites throughout Caroline, Dorchester, Kent, Queen Anne’s, Talbot, Wicomico and Worcester Co | Transportation Enhancements | 10/07/2009 | 11/09/2009 | 09/01/2011 | 251958 | 0
4883 | Maryland | STATEWIDE |  | 4,5,6,8 | 000A448 | This project will install and establish reforestation trees and shrubs at various locations throughout Prince Georges's and Montgomary Counties. Project will remove dead or invasive plants and install | Transportation Enhancements | 08/05/2009 | 09/29/2009 | 08/01/2010 | 221260 | 0
4884 | Maryland | FREDERICK | FREDERICK | 6 | 000A452 | This project, located in Frederick County, is for vegetation management, invasive species removal, and installation, care, and establishment of reforestation and landscape plantings in the interchange | Transportation Enhancements | 08/05/2009 | 01/07/2010 | 08/01/2011 | 496980 | 0.28
4885 | Maryland | HOWARD |  |  | 000A455 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Howard County that will enhance pavement life and provide s | Pavement Improvement | 04/22/2010 | 04/22/2010 |  | 2993000 | 0
4886 | Maryland | BALTIMORE | BALTIMORE,MD | 2 | 000A481 | This project involves traffic signal reconstruction in Baltimore County at MD7, MD157 and MD7. | Safety/Traffic Management | 10/14/2009 | 10/28/2009 | 11/30/2011 | 1720765 | 0
4887 | Maryland | ANNE ARUNDEL | BALTIMORE,MD | 2,3 | 000A486 | This project involves traffic signal reconstruction in Anne Arundel County at MD 2 and MD210. | Safety/Traffic Management | 11/25/2009 | 01/04/2010 | 12/31/2011 | 1621285 | 0
4888 | Maryland | CALVERT |  |  | 000A487 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. The project is for re | Pavement Improvement | 05/12/2010 | 05/12/2010 |  | 983003 | 0
4889 | Maryland | HARFORD |  |  | 000A488 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Harford County that will enhance pavement life and provide | Pavement Improvement | 12/22/2009 | 05/17/2010 |  | 1148888 | 0
4890 | Maryland | FREDERICK |  |  | 000A494 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Frederick County that will enhance pavement life and provid | Pavement Improvement | 04/12/2010 | 04/12/2010 |  | 2406346 | 0
4891 | Maryland | WASHINGTON |  |  | 000A499 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Washington County that will enhance pavement life and provi | Pavement Improvement | 04/27/2010 | 04/27/2010 |  | 2255715 | 0
4892 | Maryland | SOMERSET |  |  | 000A500 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Somerset County that will enhance pavement life and provide | Pavement Improvement | 04/05/2010 | 04/05/2010 |  | 620800 | 0
4893 | Maryland | BALTIMORE |  |  | 000A505 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Baltimore County that will enhance pavement life and provid | Pavement Improvement | 04/01/2010 | 04/01/2010 |  | 7430500 | 0
4894 | Maryland | STATEWIDE |  | 05 | 000A526 | This project will clean and paint 12 bridges on various routes in Anne Arndel, Calvert, Charles, and St Mary's Counties. These processes will extend the life of the structures. | Bridge Improvement | 01/21/2010 |  |  | 1800277 | 0
4895 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) |  | 000A529 | Maryland State Highway will mill, resurface, line stripe, and install guardrail on I-95/I495 from MD 5 to South of D'Arcy Road and MD 4 to South of Old Marlboro Road. | Pavement Improvement | 04/20/2010 |  |  | 4105745 | 0
4896 | Maryland | ALLEGANY |  | 6 | 0682033 | Maryland State Highway will perfrom patching and install a new layer that will enhance pavement life and provide smoother surface. In addition, the project will enhance safety by upgrading guradrails | Pavement Improvement | 06/08/2009 | 07/07/2009 | 12/01/2009 | 3889716 | 3.42
4897 | Maryland | STATEWIDE |  | 6 | 0682034 | Maryland State Highway will Maryland State Highway will either replace guardrails not meeting the current standards or repair them or install new guardrails as needed. This project will improve safety | Safety/Traffic Management | 04/20/2009 | 05/11/2009 | 12/01/2009 | 1251301 | 9.4
4898 | Maryland | STATEWIDE |  | 6 | 0682035 | Maryland State Highway will replace existing substandard weatherized traffic barrier along the roadside and median with galvanized traffic barrier on 17 mile section of Interstate 68 (from west of Hil | Safety/Traffic Management | 07/07/2009 | 08/10/2009 | 01/01/2011 | 3675603 | 17
4899 | Maryland | ALLEGANY |  | 6 | 0682036 | This project will establish turfgrass in selected bare and eroded areas on MD 36 to Garrett County Line. | Transportation Enhancements | 08/25/2009 | 09/14/2009 | 11/30/2009 | 417474 | 3.23
4900 | Maryland | FREDERICK |  | 6 | 0703055 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. In addition, the proj | Pavement Improvement | 06/15/2009 | 08/12/2009 | 10/01/2009 | 3550530 | 6.86
4901 | Maryland | BALTIMORE |  | 6 | 0832214 | Maryland State Highway will improve sections of Interstate 83 (from MOunt Carmel Road to PA State line) and associated ramps in Baltimore County by removing few inches of existing roadway and adding | Pavement Improvement | 06/24/2009 | 07/13/2009 | 08/01/2010 | 4637947 | 2.8
4902 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 5 | 0952267 | This project includes work to remove invasive species and install reforestation and landscape plantings along roadsides and within median and quadrant sections of the US 50 / I-495/95 Interchange, loc | Transportation Enhancements | 08/13/2009 | 10/22/2009 | 10/01/2011 | 638968 | 0
4903 | Maryland | STATEWIDE |  | 3,5 | 0953182 | Lanscaping using invasive plant control and native plant establishment on I-95 from I-495 to MD212 and from MD109 to MD100. Invasive plant species will be removed and native meadow plants will be pla | Transportation Enhancements | 04/29/2009 | 05/11/2009 | 06/01/2011 | 414357 | 0
4904 | Maryland | ALLEGANY |  | 01 | 1015005 | This project in Allegheny County will widen the roadway to a minium 18' width, perfrom surface overlay, construct two retaining walls to minimize grading impacts, and complete drainage improvements on | Pavement Improvement | 02/16/2010 | 04/01/2010 |  | 3057478 | 0
4905 | Maryland | GARRETT |  | 6 | 1016006 | Maryland State Highway will resurface at various locations in Allegany County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Improvement | 07/23/2009 | 08/24/2009 | 02/01/2010 | 947460 | 0.79
4906 | Maryland | FREDERICK |  | 6 | 1051025 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. The project is locate | Pavement Improvement | 06/09/2009 | 07/27/2009 | 11/01/2009 | 2386657 | 10.2
4907 | Maryland | FREDERICK |  | 6 | 1074009 | This project will improve roadway characterstics (geometrics improvements) in Frederick County at Fingerboard Rd and Ijamsville Rd/Big Woods Rd toimprove safety. | Pavement Improvement | 04/23/2009 | 07/24/2009 | 03/01/2010 | 1768873 | 0.3
4908 | Maryland | HOWARD | BALTIMORE,MD | 3,7 | 1091062 | Maryland State Highway will resurface in Howard County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Improvement | 08/14/2009 | 09/09/2009 | 05/01/2010 | 3865394 | 2.63
4909 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 5 | 1194004 | This a bridge replacement project in Prince George's County. | Bridge Replacement | 10/07/2009 | 06/25/2010 | 12/31/2010 | 1461126 | 0
4910 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 3 | 1251034 | Baltimore City will resurface Orleans Street from Central Avenue to Wolfe Street for pavement preservation. This project will include updating sidewalks, traffic barriers, storm drains, and roadway l | Pavement Improvement | 08/03/2009 | 08/03/2009 | 07/01/2010 | 7082521 | 0
4911 | Maryland | CECIL | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 1251044 | Maryland State Highway is correcting inadequate drainage then resurfacing and restriping the roadway on the southern approach to Big Elk Creek. | Pavement Improvement | 02/18/2010 |  |  | 403461 | 0
4912 | Maryland | HARFORD | ABERDEEN-HAVRE DE GRACE-BEL AIR |  | 1257001 | Maryland State Highway will mill and resurface the existing roadway, repair existing drainage, upgrade the existing traffic barrier and end treatments, and then restripe the roadway on MD 462 from MD | Pavement Improvement | 01/12/2010 | 07/08/2010 |  | 610784 | 0
4913 | Maryland | CECIL |  | 1 | 1266003 | This project, located in Cecil County, is for the construction of a 121’ x 77’ expansion of the ride sharing facility at MD 222 and Blythedale Road.This carpool lot in Cecil County has reached 85% cap | Pavement Widening | 06/22/2009 | 07/13/2009 | 12/01/2009 | 330214 | 0
4914 | Maryland | STATEWIDE |  | 1 | 1271048 | This project will eradicate or control invasive plants on US 301 in Queen Anne's, Kent and Cecil Counties from US50/301 split to the Delaware line. Native meadow plants will be planted in place of in | Transportation Enhancements | 06/15/2009 | 07/16/2009 | 07/01/2011 | 115953 | 0
4915 | Maryland | DORCHESTER |  | 1 | 1301141 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with the new layer that will enhance pavement life and provide smoother surface. This project is | Pavement Improvement | 06/15/2009 | 09/09/2009 | 10/01/2009 | 1245512 | 4.49
4916 | Maryland | TALBOT |  | 1 | 1301142 | Maryland State Highway will improve sections of US 50 (from MD 662B to MD 309) in Talbot County by removing few inches of existing roadway and adding a new pavement layer that will wear longer and min | Pavement Improvement | 07/06/2009 | 07/20/2009 | 08/01/2010 | 3454391 | 4.09
4917 | Maryland | GARRETT |  | 6 | 2011027 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. In addition, the pr | Pavement Improvement | 06/15/2009 | 08/17/2009 | 03/01/2010 | 1383637 | 1.58
4918 | Maryland | GARRETT |  | 6 | 2011028 | This project will resurface US219 from .15 Miles North of MD 42 to Bumble Bee Rd to enhance roadway life and improve ride. | Pavement Improvement | 03/11/2009 | 03/25/2009 | 10/01/2009 | 1742518 | 2.17
4919 | Maryland | GARRETT |  | 6 | 2061022 | Maryland State Highway will resurface MD135 from Chestnut Grove Road to Lee Road in Garrett County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 04/01/2009 | 05/09/2009 | 02/01/2010 | 2227223 | 3.26
4920 | Maryland | WASHINGTON |  | 6 | 2211014 | This project will add a right turn lane on MD65 at MD63 (lower vertical crest) to facilitate traffic movement and improve safety. | Pavement Improvement | 09/03/2009 | 09/29/2009 | 06/30/2010 | 688709 | 0.15
4921 | Maryland | CARROLL |  | 6 | 2341039 | Maryland State Highway is doing this project in Carroll County. It is a geometric improvement project that involves the construction of separate left turn and deceleration lanes, traffic signal upgra | Pavement Improvement | 10/07/2009 | 10/20/2009 | 06/30/2010 | 1498087 | 0
4922 | Maryland | CARROLL |  | 6 | 2371018 | Ramp widening (geometric improvement) at MD27 at MD140 ramps. This project will improve safety. | Pavement Improvement | 09/11/2009 | 09/28/2009 | 06/30/2010 | 742980 | 0.23
4923 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 4 | 2451032 | MD 410 to wayne Avenue - Traffic Signal Reconstruction for safety. | Safety/Traffic Management | 12/23/2009 | 01/11/2010 |  | 1103573 | 0
4924 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 4.8 | 2491025 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD650 from Milestone Drive to Venice Drive to enhance roadway life and smoothness. | Pavement Improvement | 03/03/2009 | 03/16/2009 | 02/01/2010 | 2149158 | 1.17
4925 | Maryland | STATEWIDE | WASHINGTON (DC-MD-VA) | 8 | 2491026 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD650 from MD410 to Holton Lane to enhance roadway life and smoothness. | Pavement Improvement | 09/29/2009 | 11/18/2009 |  | 1444164 | 0.83
4926 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) |  | 2491027 | Maryland State Highway will widen and resurface MD 650 from the DC line to MD 140 to enhance the pavement life, provide higher degree of safety, and provide smoother ride surface. | Pavement Improvement | 03/18/2010 | 04/19/2010 |  | 1893497 | 0
4927 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 5 | 2511062 | Maryland State will perfrom patching, removal of surface (as needed) and resurface US 1 from MD410 to Albion Road to enhance roadway life, safety and smoothness. | Pavement Improvement | 03/02/2010 | 04/30/2010 | 06/30/2010 | 839177 | 0.52
4928 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 4 | 2541010 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD214 from Cindy lane to Brightseat Road to enhance roadway life, safety and smoothness. | Pavement Improvement | 06/24/2009 | 09/29/2009 | 08/01/2010 | 1925417 | 1.98
4929 | Maryland | FREDERICK |  | 6 | 2707175 | Maryland State will perfrom patching, removal of surface (as needed) and resurface Northbound I270 from Structure 1007901 Bennett Creek to Structure 1007801 MD 80 to enhance roadway life, safety and s | Pavement Improvement | 03/26/2009 | 05/11/2009 | 09/01/2009 | 921645 | 1.26
4930 | Maryland | CAROLINE |  | 1 | 3001045 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 06/09/2009 | 06/23/2009 | 01/01/2010 | 918268 | 2.47
4931 | Maryland | CAROLINE |  | 1 | 3001046 | Maryland State Highway will widen 1.3 mile section of MD 404 in Caroline County. The project will add two westbound lanes, aa 34 foot median and will reconstruct existing lanes. Project will add lef | Pavement Widening | 09/09/2009 | 09/28/2009 |  | 2437935 | 1.32
4932 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 2 | 3009010 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Hilton Street from Frederick Avenue to Mulberry Street to enhance roadway life and smoot | Pavement Improvement | 07/15/2009 | 07/13/2009 | 12/01/2009 | 928143 | 0
4933 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 2 | 3019006 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Park Heights Avenue from NorthernPArkway to Garrison Bulevard to enhance roadway life an | Pavement Improvement | 10/15/2009 | 10/05/2009 |  | 1619916 | 0
4934 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 2 | 3200001 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Frankford Avenue from Sinclair Lane to Moravia Park Drive to enhance roadway life and sm | Pavement Improvement | 07/06/2009 | 07/06/2009 | 12/01/2009 | 1340347 | 0
4935 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 7 | 3206005 | Baltimore City will rehabilitate (make it to last longer) Argonne Drive Bridge. | Bridge Improvement | 01/10/2010 | 02/15/2010 |  | 6528294 | 0
4936 | Maryland | WORCESTER |  | 01 | 3311012 | Maryland State Highway will resurface MD 528 from 9th Street to 28th Street in Ocean City to eenhance the pavement life and provide smoother ride surface. | Pavement Improvement | 04/02/2010 | 04/22/2010 |  | 832716 | 0
4937 | Maryland | BALTIMORE CITY | BALTIMORE,MD | 2 | 3341002 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Northern Parkway from Falls Road to Park Heights Avenue to enhance roadway life and smoo | Pavement Improvement | 06/22/2009 | 07/15/2009 | 05/01/2010 | 7572091 | 0
4938 | Maryland | HARFORD |  | 1 | 3631001 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 06/22/2009 | 07/28/2009 | 12/01/2009 | 1289267 | 2.14
4939 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 8 | 4952276 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In ad | Pavement Improvement | 07/16/2009 | 08/03/2009 | 06/01/2010 | 8941712 | 3.92
4940 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 4,5 | 5008021 | This project will add second left turn lane on Southbound MD410 at MD 500 to facilitate traffic movement and reduce congestions and enhance safety. | Pavement Improvement | 01/08/2010 | 02/01/2010 |  | 1120639 | 0.5
4941 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 4,5 | 5008022 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. This p | Pavement Improvement | 10/14/2009 | 03/09/2010 | 03/31/2010 | 1921697 | 1.12
4942 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 8 | 5010013 | Maryland State Highway is doing this project in Montgomery County. It is a geometric improvement that will extend left tun lanes on MD 28, as well as add another turning lane on MD 28. The project i | Pavement Improvement | 10/14/2009 | 12/07/2009 | 09/30/2010 | 1028309 | 0
4943 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 8 | 5018026 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 06/09/2009 | 07/16/2009 | 12/01/2011 | 3434916 | 1.76
4944 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 5 | 5019021 | MAryland State Highway will be replacing the deteriorating concrete bridge decks on MD 201 ND and MD 201 SB with new decks as part of its bridge system preservation program. | Bridge Improvement | 02/22/2010 | 03/15/2010 |  | 5878653 | 0
4945 | Maryland | MONTGOMERY | WASHINGTON (DC-MD-VA) | 8 | 5035004 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 08/11/2009 | 10/11/2009 | 03/01/2010 | 1865847 | 1.54
4946 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 8 | 5067010 | This project will replace existing deteriorating pavement surface ( MD 212, Riggs Road from Washington D.C. line to Sargent Road) in Prince George's County with new pavement surface. It will also mak | Pavement Improvement | 10/23/2009 | 11/06/2009 | 09/30/2010 | 1835894 | 0.93
4947 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 5 | 5067011 | This project will improve safety at MD212 at Allview Drive/Evans Trail by making Geometric improvements. | Pavement Improvement | 09/22/2009 | 11/02/2009 |  | 1250441 | 0
4948 | Maryland | PRINCE GEORGES | WASHINGTON (DC-MD-VA) |  | 5096001 | Maryland State Highway will replace the deteriorating concrete bridge deck on Forestville Raod over I-95 with a new deck as part of its bridge sytem preservation program. | Bridge Improvement | 05/05/2010 | 06/17/2010 |  | 1720857 | 0
4949 | Maryland | BALTIMORE | BALTIMORE,MD |  | 6956346 | Maryland State Highway will replace the deteriorated bridge at I-695 over MD 26 (Liberty Road) with a new one as part of its bridge system preservation program. | Bridge Replacement | 02/08/2010 | 04/01/2010 |  | 21923532 | 0
4950 | Maryland | ALLEGANY | CUMBERLAND (WV) | 06 | 7509004 | Maryland State Highway Will reconstruct Maryland Avenue from Jefferson Street to Short Street in Allegany County. | Pavement Improvement | 10/08/2009 | 11/15/2009 |  | 498000 | 0
4951 | Massachusetts | BRISTOL | FALL RIVER (RI) | 3,4 | 001S899 | The project includes the construction of a new interchange (Exit 8 1/2) on Route 24 in Freetown and construction of new access roadways east to the proposed Fall River Executive Park and west to South | Pavement Improvement | 11/30/2009 | 11/30/2009 |  | 32053618 | 0
4952 | Massachusetts | PLYMOUTH | TAUNTON | 4, 9 | 001S917 | This project will resurface Route 18/28 from Bridgewater Center to the Middleborough Rotary (intersection of Route 44) and make drainage improvements. | Pavement Improvement | 04/23/2009 |  |  | 2842051 | 0
4953 | Massachusetts | BERKSHIRE |  | 1 | 001S918 | The project will begin at the Adams/Cheshire town boundary (MM 66.3) and will end just north of Commonwealth Avenue (MM 67.8) for a project length of approximately 1.5 miles. MassHighway will resurfac | Pavement Improvement | 04/23/2009 |  |  | 2199456 | 1.5
4954 | Massachusetts | BARNSTABLE | HYANNIS | 10 | 001S919 | This project will resurface Route 6 (Scenic Highway) from the intersection with Nightingale Pond Road to just east of the intersection with Bourndale Road in the Town of Bourne. | Pavement Improvement | 04/23/2009 |  |  | 1756160 | 2.41
4955 | Massachusetts | BRISTOL | NEW BEDFORD | 4 | 001S920 | Resurface Route 6 from west of the Dartmouth town line (milemarker 20.9±) to the Fall River city line (milemarker 16.3±), a distance of approximately 4.6 miles. | Pavement Improvement | 04/30/2009 |  |  | 5074035 | 4.65
4956 | Massachusetts | WORCESTER |  | 1 | 001S921 | In the Town of Barre, this project will resurface Route 122 and a section of Rte 62. The state highway section of the project begins just west of Pleasant Street (milemarker 48.265) and proceeds weste | Pavement Improvement | 05/14/2009 |  |  | 2268246 | 0
4957 | Massachusetts | BARNSTABLE |  | 10 | 001S922 | In Barnstable: Perform resurfacing and related work on the state-owned sections of Route 6A, from milemarker 8.12 to milemarker 16.56, a distance of approximately 8.5 miles. Also included in the proj | Pavement Improvement | 07/02/2009 |  |  | 3150634 | 8.43
4958 | Massachusetts | MIDDLESEX |  | 7 | 001S923 | This project will resurface a section of Route 2 in Lincoln. Work includes guardrail, painting and signage. | Pavement Improvement | 05/14/2009 |  |  | 1596500 | 3.05
4959 | Massachusetts | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 5 | 001S924 | This project will resurface Route 2 in Concord from Walden to the Sudbury town line and from Nine Acre Corner road to Elm Street. Work includes guardrail, painting and signage. | Pavement Improvement | 05/07/2009 |  |  | 4313468 | 1.05
4960 | Massachusetts | BRISTOL | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 3 | 001S925 | Mill and resurface Route 6 in Swansea from the Somerset town line to the Rehoboth town line. Work on this project also includes the repair of frost heaves and the reconstruction of existing sidewalks. | Pavement Improvement | 04/23/2009 |  |  | 4159044 | 5.5
4961 | Massachusetts | BARNSTABLE |  | 10 | 001S926 | Mill and resurface Route 6A in Dennis from the Yarmouth Town Line to the Brewster Town Line, a distance of approximately 4.3 miles. | Pavement Improvement | 06/25/2009 |  |  | 1611976 | 4.28
4962 | Massachusetts | NORFOLK |  | 9 | 001S927 | This is a Pavement Preservation Project for Route 24 in Avon and Stoughton. | Pavement Improvement | 07/31/2009 |  |  | 5718302.23 | 4
4963 | Massachusetts | WORCESTER |  | 1 | 001S932 | Mill and resurface Route 32 (Main Street) from the Ware/New Braintree town line (milemarker 22.383) to just past the New Braintree/Hardwick town line (milemarker 23.38), a distance of approximately 1 | Pavement Improvement | 05/14/2009 |  |  | 657048 | 0.94
4964 | Massachusetts | FRANKLIN | FITCHBURG-LEOMINSTER | 1 | 001S933 | In Gill and Wendell: Work under this project will consist of milling the existing paved surface and repaving with 2" of HMA modified top course material. Work will also include repairs/upgrades to gua | Pavement Improvement | 04/30/2009 |  |  | 3590569 | 0
4965 | Massachusetts | HAMPSHIRE |  | 1 | 001S934 | This project takes place in a number of locations between Westfield and Easthampton. The project will consist of milling the existing paved surface of Route 5 & 10 and repaving with 2" of HMA modified | Pavement Improvement | 05/21/2009 |  |  | 3891211 | 0
4966 | Massachusetts | WORCESTER |  | 3 | 001S935 | This project will commence at Route 140 in Shrewsbury and continue in a westerly direction to Massasoit Road in Worcester, a distance of approximately 3.5 miles. | Pavement Improvement | 11/27/2009 |  |  | 2775064 | 3.23
4967 | Massachusetts | FRANKLIN |  | 1 | 001S936 | The focus of the Northfield Street Improvement Project is to reconstruct sidewalks on Main Street and Parker Avenue in Northfield from a point north of the intersection with River Street continuing no | Transportation Enhancements | 05/07/2009 |  |  | 1100620 | 0
4968 | Massachusetts | BERKSHIRE | PITTSFIELD | 1 | 001S937 | In Lenox: Reconstruction of State Highway from the Route 7 intersection north for approximately 1.25 miles to the end of the State Highway just south of the intersection with Route 183. Included in th | Pavement Improvement | 06/25/2009 |  |  | 3670203.6 | 1.3
4969 | Massachusetts | NANTUCKET |  | 10 | 001S941 | This project in Nantucket consists of the mill and resurface of Milestone Road from just west of rotary that intersects Orange Street, Sparks Avenue, and Old South Road, to just east of rotary that in | Pavement Improvement | 05/21/2009 |  |  | 4748670 | 0
4970 | Massachusetts | HAMPSHIRE |  | 1 | 001S942 | The purpose of this project is to resurface portions of Route 9 in Belchertown and Ware. Work will also include repairs/upgrades to guardrail end treatments as needed and new pavement markings. Beche | Pavement Improvement | 05/21/2009 |  |  | 4699691 | 0
4971 | Massachusetts | BERKSHIRE |  | 1 | 001S945 | The proposed scope for this project consists of micro-milling Route 8 shoulders and partially into travel lanes, installing a stress absorbing interlayer (SAMI) over the travel lanes, and applying a h | Pavement Improvement | 05/14/2009 |  |  | 1265387 | 0
4972 | Massachusetts | PLYMOUTH |  | 9 | 001S946 | In Brockton: Reconstruct Route 27, Pleasant Street, West Street and Westgate Mall Road. Work includes minor widening, geometric improvements, new traffic signals and interconnection of signalized int | Pavement Improvement | 07/30/2009 |  |  | 2811883 | 0
4973 | Massachusetts | BERKSHIRE |  |  | 001S947 | This project proposes to resurface Route 7 in New Ashford and Lanesborough with hot-mix asphalt, and would also include repairing/improving the drainage system, resetting guardrail, upgrading guardrai | Pavement Improvement | 05/07/2009 |  |  | 2406702 | 0
4974 | Massachusetts | WORCESTER | WORCESTER, MA-CT | 3, 5 | 001S949 | The proposed work under this project consists of bridge reconstruction, widening, guardrail installation and all other work on Water Street from its intersection with Bolton Street and Harris Street t | Bridge Replacement | 09/10/2009 |  |  | 3514426 | 0
4975 | Massachusetts | WORCESTER | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 5 | 001S952 | Resurface Route 2 in Harvard and Littleton from the vicinity of the Littleton Road Bridge to the Boxborough town line, a distance of approximately 4.4 miles. Work includes minor box widening to extend | Pavement Improvement | 04/30/2009 |  |  | 5175866 | 4.55
4976 | Massachusetts | HAMPSHIRE |  | 1 | 001S953 | The project involves roadway and sidewalk rehabilitation on town-owned Elm Street in the Town of Hatfield, and includes coldplaning, roadway reclamation, hot mix asphalt paving, replacement of sidewal | Pavement Improvement | 07/09/2009 |  |  | 975700 | 0
4977 | Massachusetts | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 6 | 001S954 | The proposed expansion of the Newburyport Park & Ride facility will add 105 parking spaces. Work will include the construction of a soil nail retaining wall, upgrades to the existing lighting, as well | Safety/Traffic Management | 08/13/2009 |  |  | 3958204 | 0
4978 | Massachusetts | HAMPDEN |  | 2 | 001S955 | This project consists of demolishing and replacing the Red Bridge Road Bridge over the Utilities Canal in Wilbraham. The new bridge will be a superstructure replacement constructed on an improved alig | Bridge Improvement | 07/23/2009 |  |  | 1838194 | 0
4979 | Massachusetts | WORCESTER | FITCHBURG-LEOMINSTER | 1 | 001S961 | The Project limits are Route 2 in Westminster from Wyman Road/Village Inn Road (Exit 26), easterly into Fitchburg, to the Junction of Route 31 in Fitchburg, a distance of approximately 2.6 miles. The | Pavement Improvement | 08/07/2009 |  |  | 7485002 | 2.26
4980 | Massachusetts | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 1, 2 | 001S962 | This multi-use recreational rail trail project starts at Ferry Street in Easthampton and ends at Earle Street in Northampton, for a total length of 4,400 Meters. It links the Manhan Bike Trail in Eas | Transportation Enhancements | 09/03/2009 |  |  | 4211726.4 | 0
4981 | Massachusetts | MIDDLESEX |  | 5 | 001S964 | The Town of Westford is proposing to widen approximately 3,000 feet of Littleton Road (Route 110). The existing cross section contains one lane in each direction with an additional left turn lane for | Pavement Improvement | 08/06/2009 |  |  | 2955042.35 | 0
4982 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8, 9 | 001S965 | This project will make safety and mobility improvements at four major intersections along the Dorchester Avenue corridor; Andrews Square, Glover's Corner, Fields Corner and Peabody Square. Improvemen | Pavement Improvement | 11/17/2009 |  |  | 15127198 | 0
4983 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8 | 001S966 | Work consists of resurfacing and related work in various locations in the city Boston | Pavement Improvement | 01/28/2010 |  |  | 3695619 | 0
4984 | Massachusetts | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 1 | 001S967 | The purpose of this project is to improve access to the Jackson Street School by constructing new sidewalks, constructing a new access ramp to the nearby bikepath, installing 4' chain link fence at sc | Transportation Enhancements | 10/01/2009 | 10/01/2009 |  | 613114 | 0
4985 | Massachusetts | WORCESTER |  | 1 | 001S995 | The scope of work for the proposed project is to reconstruct Athol Richmond Road in the Town of Royalston from Elm Avenue in Royalston to the New Hampshire state border. The length of the roadway is a | Pavement Improvement | 11/27/2009 |  |  | 1000000 | 0
4986 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8 | 002S015 | MassHighway proposes to construct the North Bank Bridge over the MBTA Commuter Rail tracks providing a bicycle/pedestrian connection from East Cambridge to City Square Charlestown and the Boston Harbo | Transportation Enhancements | 11/30/2009 |  |  | 29176615 | 0
4987 | Massachusetts | BERKSHIRE |  |  | 002S022 | This project proposes to utilize pavement preservation techniques to resurface approximately 11.4 miles of various Federal-Aid eligible roadways (NHS and non-NHS) in North Adams. | Pavement Improvement | 01/14/2010 |  |  | 2972254 | 0
4988 | Massachusetts | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) |  | 002S026 | This project proposes to reconstruct Bridge Street (Route 1A) from the Beverly Salem Bridge to Washington Street. The project includes, sidewalks, curbing, trees and pavement markings. | Pavement Improvement | 12/17/2009 |  |  | 7234415 | 0
4989 | Massachusetts | WORCESTER |  | 2 | 002S034 | This Footprint Road project in Southbridge involves milling and resurfacing, selected full-depth construction and minor box widening to provide a uniform width. (3.25 mi) | Pavement Improvement | 12/10/2009 |  |  | 2000290 | 0
4990 | Massachusetts | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) |  | 002S053 | Fiber optic connectivity at three locations. Dist 4 via Rte 2 to MBTA Alewife station in Cambridge, Newton rest area on Rte 128 to MBTA riverside station, MEMA bunker to MTA toll plaza in Framingham | Safety/Traffic Management | 12/17/2009 | 12/17/2009 |  | 1400000 | 0
4991 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) |  | 002S055 | Upgrade of the TOC and BTD video systems to IP based virtual matrix switching system. | Safety/Traffic Management | 12/10/2009 | 12/10/2009 |  | 1000000 | 0
4992 | Massachusetts | SUFFOLK |  |  | 002S056 | The design of communication equipment at five locations to increase bandwidth and allow for single CCTV connections for viewing for the City of Boston. | Safety/Traffic Management | 12/10/2009 | 12/10/2009 |  | 402958 | 0
4993 | Massachusetts | PLYMOUTH | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 9 | 002S072 | The purpose of this project is to reconstruct North Street from Pleasant Street to Village Gate Drive. The project will involve full depth reconstruction of North Street with approximately a four foot | Pavement Improvement | 01/21/2010 |  |  | 1026713 | 0
4994 | Massachusetts | PLYMOUTH | HYANNIS | 4 | 002S073 | The purpose of this project is to rehabilitate the existing pavement surface on Routes 6 & 28 in Wareham from just east of Mogan Way easterly to the Wareham/Bourne Town Line. | Pavement Improvement | 01/28/2010 |  |  | 603016 | 0
4995 | Massachusetts | BRISTOL | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 4 | 002S074 | The work for the Route 24 bridge over Bedford Street shall consist of reconstructing the bridge and approach wearing surface; replacing the reinforced concrete deck slab; extending the proposed deck a | Bridge Improvement | 01/28/2010 |  |  | 3067718 | 0
4996 | Massachusetts | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 2 | 002S075 | The work consists of the landscape improvements along the side slopes and embankments along I-91, from Broad Street to State Street; the design of an irrigation system; and sidewalk and landscaping im | Transportation Enhancements | 02/18/2010 |  |  | 1460945 | 0
4997 | Massachusetts | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 9 | 002S076 | This project involves the installation of a new fully actuated traffic signal system with appropriate phasing and timing for peak hour demands, including an exclusive pedestrian phase, to improve safe | Safety/Traffic Management | 02/04/2010 |  |  | 938075 | 0
4998 | Massachusetts | HAMPSHIRE |  | 1 | 002S077 | Work under this project will consist of micromilling 1.5” from the existing paved surface and repaving with a 1.5” asphalt standard top course and a 0.75" paver placed friction course. Work will also | Pavement Improvement | 02/11/2010 |  |  | 1846293 | 0
4999 | Massachusetts | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 2 | 002S079 | Project will consist of milling and resurfacing Burnett Road from New Lombard Road (near the Turnpike entrance) to the Ludlow Town Line for a total length of 1.7 miles. | Pavement Improvement | 01/21/2010 |  |  | 1165889 | 0
5000 | Massachusetts | WORCESTER |  | 1 | 002S080 | The project limits are Route 140 in Gardner from 1000 feet north of Route 101 and continuing 1.6 miles north to Stone Street. The project consists of milling and resurfacing, and related work. | Pavement Improvement | 02/11/2010 |  |  | 1874120 | 0
5001 | Massachusetts | HAMPSHIRE |  | 1 | 002S081 | This project begins at the Westhampton Town Line and proceeds north-westerly for 3.08 miles to the intersection of South Street. The roadway currently exhibits potholes, alligator and block cracking, | Pavement Improvement | 02/11/2010 |  |  | 2435594 | 0
5002 | Massachusetts | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 1 | 002S088 | This project consists of resurfacing Westfield Road (Rte 202) from the Westfield City Line at Old County Road to Ashley Road for a total length of approximately 2.1 miles. | Pavement Improvement | 02/18/2010 |  |  | 1211241 | 0
5003 | Massachusetts | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Various | 002S089 | The proposed Nonantum Road project will narrow the roadway to two 11-foot travel lanes for most of the stretch between Galen Street in Watertown and the Brook Street/North Beacon Street intersection | Pavement Improvement | 03/11/2010 |  |  | 6360344 | 0
5004 | Massachusetts | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8 | 002S092 | This project will reconstruct Washington Street, including traffic signal upgrades, landscaping and sidewalks/wheelchair ramps. | Pavement Improvement | 03/18/2010 |  |  | 1258737 | 0
5005 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8 | 002S099 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 01/28/2010 |  |  | 3786018 | 0
5006 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8 | 002S100 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 02/04/2010 |  |  | 3745027 | 0
5007 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8 | 002S101 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 02/04/2010 |  |  | 2965713 | 0
5008 | Massachusetts | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 8 | 002S102 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 02/04/2010 |  |  | 3384433 | 0
5009 | Massachusetts | NORFOLK | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 2 | 002S103 | The purpose of this project is to improve traffic safety and operations for motorists and pedestrians. The proposed improvements for Pulaski Boulevard include widening the roadway, rehabilitating the | Pavement Improvement | 01/28/2010 |  |  | 9871571.3 | 0
5010 | Massachusetts | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 9 | 002S104 | This is a State Highway resurfacing project including new pavement, guardrail, painting and signage. | Pavement Improvement | 01/21/2010 |  |  | 1880221 | 0
5011 | Massachusetts | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 6 | 002S107 | The project includes realignment and signal installation at the following locations; Walnut Street at I-95 Southbound Ramps and Colonial Golf Club Site Drive (Exit 43); Walnut Street at I-95 Northboun | Pavement Improvement | 03/11/2010 |  |  | 5815090.75 | 0
5012 | Massachusetts | WORCESTER | WORCESTER, MA-CT | 2 | 002S114 | The Project extends along Route 146 in Uxbridge, from just north of the Chocolog Road interchange, northerly about 4.4 miles to the Douglas Town Line, then continuing another 0.3± miles in Douglas to | Pavement Improvement | 03/04/2010 |  |  | 9122436.5 | 0
5013 | Michigan | INGHAM |  | 8 | 0833038 | 1.25 miles of roadway reconstruction of North Williamston Road from Sherwood Road to the city limits of Williamston in Ingham County. This project includes tree removals and drainage improvements. | Other | 03/23/2009 | 03/26/2009 | 08/21/2009 | 23000 | 1.25
5014 | Michigan | INGHAM |  | 8 | 0833039 | 2.0 miles of pavement resurfacing of North Williamston Road from Sherwood Road to Haslett Road just north of the city of Williamston in Ingham County. This project will improve pavement rideability a | Pavement Improvement | 03/23/2009 | 03/26/2009 | 08/21/2009 | 200000 | 1.999
5015 | Michigan | ALCONA |  | 1 | 0901004 | MDOT will resurface 5 miles of US-23 from Everett Rd to Black River Rd in the vicinity of Ossineke. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 05/05/2011 | 3269612.6 | 9.832
5016 | Michigan | ALCONA |  | 1 | 0901005 | MDOT will resurface 4.5 miles of M-72 from M-65 to west of O'Donnell Rd in the Huron National Forest. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/16/2009 | 07/16/2009 | 10/10/2009 | 1248007.56 | 4.31
5017 | Michigan | ALCONA |  | 1 | 0901006 | The Alcona County Road Commission will resurface 2.5 miles of East Black River Rd from US-23 to Lakeshore Rd east of the village of Lost Lake Woods. This will improve the driving quality by making th | Other | 07/09/2009 | 07/09/2009 | 05/05/2011 | 331618 | 2.949
5018 | Michigan | ALGER |  | 1 | 0902006 | This pavement project in Alger County will improve the drive quality and make the road smoother. | Pavement Improvement | 05/14/2009 | 06/01/2009 | 09/30/2009 | 93591 | 4.901
5019 | Michigan | ALGER |  | 1 | 0902007 | This pavement project in Alger County will improve the drive quality and make the road smoother. | Pavement Improvement | 05/14/2009 | 06/01/2009 | 09/30/2009 | 93591 | 5.039
5020 | Michigan | ALGER |  | 1 | 0902008 | This pavement project on Rock River Road in the Village of Chatham will improve the drive quality and make the road smoother. | Pavement Improvement | 05/14/2009 | 06/01/2009 | 09/30/2009 | 27765.54 | 1.519
5021 | Michigan | ALLEGAN |  | 6 | 0903321 | MDOT will resurface 7 miles of I-196, from 71st Street to 118th Avenue in Allegan County, just north of South Haven. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 12/31/2010 | 19688061.42 | 13.961
5022 | Michigan | ALLEGAN | HOLLAND | 6 | 0903322 | MDOT is installing median cable guardrail on 7 miles of I-196, from 71st Street to 118th Avenue in Allegan County, just north of South Haven, to improve safety. | Safety/Traffic Management | 04/02/2009 | 04/02/2009 | 12/31/2010 | 666797.08 | 6.98
5023 | Michigan | ALLEGAN |  | 6 | 0903323 | MDOT will renovate the Glenn Rest Area on I-196 in Allegan County, to improve convenience and service to stopping motorists. | Other | 04/02/2009 | 04/02/2009 | 05/30/2011 | 2040721.74 | 0.939
5024 | Michigan | ALLEGAN |  | 6 | 0903324 | MDOT will make repairs on the bridge carrying I-196 over 71st Street in Allegan County, just north of South Haven, to make the bridge last longer. | Bridge Replacement | 04/02/2009 | 04/02/2009 | 05/30/2011 | 395635.34 | 0
5025 | Michigan | ALLEGAN |  | 6 | 0903327 | "The City of Allegan will resurface 2.3 miles of Babylon Road from River Street to M-40 in the city. This will improve the driving quality by making the road smoother. | Other | 08/12/2009 | 09/22/2009 | 10/24/2009 | 120000 | 2.305
5026 | Michigan | ALLEGAN |  | 6 | 0903333 | "The Allegan County Road Commisssion will resurface 4.2 miles of 109th Avenue from 48th Street to 56th Street, in the southwest part of Allegan County. | Pavement Improvement | 10/06/2009 | 10/11/2009 | 11/13/2009 | 838743 | 4.209
5027 | Michigan | ALPENA |  | 1 | 0904009 | The Alpena County Road Commission resurface 3 miles of Leer Rd from Mellon Rd to Carr Rd in south of the village of Posen. This will improve the driving quality by making the road smoother. | Pavement Improvement | 12/28/2009 | 06/09/2010 | 07/02/2010 | 309392 | 3.013
5028 | Michigan | ANTRIM |  | 1 | 0905006 | MDOT will resurface 1.4 miles of M-88 from South Eckhardt Rd to South Central Lake in the vicinity of Bellaire. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 09/11/2011 | 650439.76 | 1.361
5029 | Michigan | ANTRIM |  | 1 | 0905007 | MDOT will resurface 12 miles of M-66 from US-131 west to Lillac Creek in the vicinity of Mancelona. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 03/03/2011 | 539878.21 | 11.977
5030 | Michigan | ARENAC |  | 1 | 0906004 | West of the City of Pinconning on M-65/Maple Ridge Road southeast quadrant and on M-61/I-75 southwest quadrant, there was the improvement to the park and ride lot to encourage ridesharing and reduce t | Other | 04/02/2009 | 04/02/2009 | 12/01/2010 | 78116.25 | 0
5031 | Michigan | ARENAC |  | 1 | 0906005 | Repairs will be made at the US-23 bridge over Big Creek North of the City of Standish to make the bridge last longer. | Bridge Improvement | 04/03/2009 | 04/03/2009 | 10/02/2009 | 61671.16 | 0
5032 | Michigan | BARAGA |  | 1 | 0907010 | This paving of road and shoulders and installed rumble strips project on US-41 south of the City of L'Anse will improve safety and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/21/2011 | 179863.05 | 1.503
5033 | Michigan | BARAGA |  | 1 | 0907011 | This paving of road and shoulders and installed rumble strips project south of the City of L'Anse will improve safety and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/20/2011 | 1799533.59 | 11.355
5034 | Michigan | BAY | BAY CITY | 1,5 | 0909009 | There is 52.76 miles of shoulder widening within the Cities of Standish, Omer, and Augres to improve mobility and reduce congestion. | Transportation Enhancements | 04/23/2009 | 04/23/2009 | 03/31/2010 | 3849069.51 | 52.875
5035 | Michigan | BAY | BAY CITY | 5 | 0909012 | Bay City is perfoming 0.19 miles of roadway realignment and intersection modifications on Marquette Avenue to improve safety. | Pavement Improvement | 06/02/2009 | 08/24/2009 | 06/01/2010 | 480000 | 0.486
5036 | Michigan | BAY | BAY CITY | 5 | 0909018 | Within Bay City, MDOT will replace I-75 from Squaconning Creet to Hotchkiss to improve safety and increase mobility. | Pavement Improvement | 09/03/2009 | 09/03/2009 | 09/19/2013 | 15825489.51 | 3.687
5037 | Michigan | BAY |  | 5 | 0909019 | Within Bay City, MDOT will replace I-75 from Squaconning Creet to Hotchkiss to improve safety and increase mobility. | Bridge Improvement | 01/25/2010 | 02/09/2010 | 09/19/2013 | 2613680.91 | 0
5038 | Michigan | BAY | BAY CITY | 5 | 0909020 | Within Bay City, MDOT will replace M-84 over Squaconning Creek and Dutch Creek to improve safety and increase mobility. | Bridge Replacement | 04/13/2009 | 04/13/2009 | 09/19/2013 | 3060406.05 | 0
5039 | Michigan | BAY | SAGINAW | 5 | 0909021 | This is reconstructing 4.49 miles on 6 bridges to improve safety and increase capacity. | Pavement Widening | 01/28/2003 | 01/28/2003 | 09/19/2013 | 13120368.56 | 3.261
5040 | Michigan | BERRIEN | BENTON HARBOR | 6 | 0911332 | "The City of St. Joseph will resurface 0.13 miles of Park St. from Lake Boulevard to Main Street in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/13/2009 | 09/08/2009 | 07/27/2011 | 210060.39 | 0.134
5041 | Michigan | BERRIEN | BENTON HARBOR | 6 | 0911335 | MDOT is installing median cable guardrail on 18 miles of I-94, from US-12 to I-94 BL near Bridgeman in Berrien County, just south of the Benton Harbor - St. Joseph metropolitan area, to improve safety | Safety/Traffic Management | 05/29/2009 | 05/29/2009 | 06/25/2010 | 3239999.4 | 36.096
5042 | Michigan | BERRIEN | BENTON HARBOR | 6 | 0911351 | "The Berrien County Road Commisssion will resurface 1.8 miles of Glenlord Road from I-94 BL to Cleveland Avenue and from Lincoln to M-139, through Stevensville and Shoreham, on the south side of the B | Pavement Improvement | 06/30/2009 | 08/03/2009 | 08/12/2009 | 75559.85 | 3.538
5043 | Michigan | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0911352 | "The Berrien County Road Commisssion will resurface 4 miles of Range Line Rd. from Walton Road north, between Buchanan and Berrien Springs in Berrrien County. This will improve the driving quality by | Pavement Improvement | 06/30/2009 | 07/14/2009 | 07/17/2009 | 68534.59 | 4.044
5044 | Michigan | BERRIEN |  | 6 | 0911353 | "The Berrien County Road Commisssion will resurface sections of Coloma Road and Range Line Road totalling 5 miles in northwest and southern Berrrien County. This will improve the driving quality by m | Pavement Improvement | 06/30/2009 | 07/20/2009 | 08/10/2009 | 91004.42 | 5.044
5045 | Michigan | BERRIEN |  | 6 | 0911354 | "The Berrien County Road Commisssion will resurface sections of Red Arrow Highway, Warren Woods Road and Shawnee Road totalling 4.2 miles in the southern part of Berrrien County. This will improve th | Pavement Improvement | 06/30/2009 | 08/03/2009 | 08/13/2009 | 89165.81 | 4.221
5046 | Michigan | BERRIEN |  | 6 | 0911355 | "The Berrien County Road Commisssion will resurface sections of Hagar Shore, Blue Star Highway and Paul Avenue totalling 5.5 miles in the northwest corner of Berrrien County. This will improve the dr | Pavement Improvement | 06/30/2009 | 07/20/2009 | 08/10/2009 | 77153.97 | 4.828
5047 | Michigan | BERRIEN | BENTON HARBOR | 6 | 0911359 | "The Berrien County Road Commisssion will resurface 8 miles of Pipestone Road, Nickerson Avenue, Sodius Parkway and Red Arrow Highway in the area south and east of the Benton Harbor - St. Joseph metro | Pavement Improvement | 01/14/2010 | 07/13/2010 |  | 616054 | 7.982
5048 | Michigan | BERRIEN |  | 6 | 0911363 | "The City of Watervliet will resurface 0.41 miles of East St. Joseph Avenue from M-140 to Lewis in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/02/2010 |  | 08/15/2010 | 153914.67 | 0.414
5049 | Michigan | BERRIEN |  | 6 | 0911364 | "The village of Baroda will resurface 0.21 miles of Hills Road. from the village limits to 1st Street in the village. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/05/2010 | 04/12/2010 | 06/04/2010 | 70000 | 0.214
5050 | Michigan | BERRIEN |  | 6 | 0911368 | "The Berrien County Road Commisssion will resurface 0.46 miles of Cleveland Avenue from Rocky Weed Rd. northward near Stevensville, just south of the Benton Harbor - St. Joseph metropolitan area. Thi | Pavement Improvement | 02/24/2010 | 07/06/2010 |  | 182226.5 | 0.462
5051 | Michigan | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0911373 | MDOT will resurface 0.31 miles of US-12 BR, from Grant Street to the St. Joseph River in Niles. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 06/04/2010 | 366569.67 | 0.603
5052 | Michigan | BRANCH |  | 7 | 0912010 | "The Branch County Road Commisssion will resurface 5.5 miles of Jonesville Road from Fremont Road to the Hillsdale County Line, east of Coldwater. This will improve the driving quality by making the | Pavement Improvement | 06/04/2009 | 08/01/2009 | 09/30/2009 | 85200 | 5.462
5053 | Michigan | BRANCH |  | 7 | 0912011 | "The Branch County Road Commisssion will resurface 3.6 miles of North Fremont Road from Corless Road to US-12, just east of Coldwater. This will improve the driving quality by making the road smoothe | Pavement Improvement | 06/04/2009 | 08/01/2009 | 09/30/2009 | 35365.93 | 3.606
5054 | Michigan | BRANCH |  | 6,7 | 0912012 | "The Branch County Road Commisssion will resurface 5.6 miles of Burr Oak Road from Bronson city limits to the St. Joseph County Line, in Branch County. This will improve the driving quality by making | Pavement Improvement | 06/04/2009 | 07/27/2009 | 09/23/2009 | 79182.79 | 5.629
5055 | Michigan | BRANCH |  | 7 | 0912013 | "The Branch County Road Commisssion will resurface sections of Dunks Rd., Creamery Rd. and Railroad Rd. totalling 6.1 miles in the northwest corner of the county. This will improve the driving qualit | Pavement Improvement | 06/04/2009 | 08/01/2009 | 09/30/2009 | 85500 | 6.086
5056 | Michigan | BRANCH |  | 7 | 0912014 | The Branch County Road Commisssion will resurface 5.6 miles of Orland Road and Southern Road, from Rierson Road to Dewsenberry Road, in the southwest part of the county. This will improve the driving | Pavement Improvement | 06/09/2009 | 07/16/2009 | 08/03/2009 | 57378 | 5.565
5057 | Michigan | BRANCH |  | 7 | 0912015 | "The Branch County Road Commisssion will resurface 4 miles of Marshall Road from Newton Road to Girard Rd, just north of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/24/2009 | 09/23/2009 | 08/13/2010 | 68699 | 4.036
5058 | Michigan | BRANCH |  | 7 | 0912016 | "The Branch County Road Commisssion will repair one mile of Marshall Road from Newton Road to State Rd, just north of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/29/2009 | 09/22/2009 | 09/30/2009 | 13055 | 1.004
5059 | Michigan | BRANCH |  | 7 | 0912018 | "The City of Coldwater will repair various sections of W. Pearl Street totalling 8.9 miles in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/13/2009 | 09/22/2009 | 10/12/2009 | 52633 | 8.982
5060 | Michigan | BRANCH |  | 7 | 0912019 | "The Branch County Road Commisssion will resurface 2.5 miles of River road from Garfield Road to US-12 and from US-12 to Narrows Road, in the city of Coldwater. This will improve the driving quality | Pavement Improvement | 08/13/2009 | 08/27/2009 | 10/05/2009 | 47550.54 | 2.516
5061 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913222 | "The City of Battle Creek will resurface 1 mile of Beckley Road from Helmer Road to Stone Jug Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/04/2009 | 09/15/2009 | 07/27/2011 | 189291.44 | 1.012
5062 | Michigan | CALHOUN | BATTLE CREEK | 6,7 | 0913223 | "The City of Battle Creek will resurface 1 mile of Capital Avenue SW from Beckley Road to the city limits. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/04/2009 | 09/15/2009 | 10/29/2009 | 246674.85 | 1.001
5063 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913224 | "The City of Battle Creek will resurface 1.7 miles of Jackson Street from M-37 to Bedford Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/04/2009 | 09/15/2009 | 10/29/2009 | 361852.38 | 1.692
5064 | Michigan | CALHOUN |  | 7 | 0913225 | The Calhoun County Road Commission is building sidewalks and ADA ramps on 1.5 miles of M-96 from Columbia Avenue to I-94 BL in the city of Battle Creek, to improve pedestrian mobility and safety. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/25/2009 | 268455.06 | 1.463
5065 | Michigan | CALHOUN |  | 7 | 0913229 | The Calhoun County Road Commission will resurface 3 miles ofN Drive N from 12 Mile Road to 15 Mile Road, east of Battle Creek. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/27/2011 | 441159.36 | 2.976
5066 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913231 | The Calhoun County Road Commission will resurface 1.9 miles of Bellevue Road from Verona Road to McAllister, in the Battle Creek urbanized area. This will improve the driving quality by making the ro | Pavement Improvement | 09/02/2009 | 10/16/2009 | 07/27/2011 | 272481.98 | 1.869
5067 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913232 | The Calhoun County Road Commission will resurface 0.6 miles of Beadle Lake Road from B Drive N to Division Drive, in the Battle Creek urbanized area. This will improve the driving quality by making t | Pavement Improvement | 09/17/2009 | 09/30/2009 | 07/27/2011 | 167331.71 | 0.6
5068 | Michigan | CALHOUN |  | 7 | 0913233 | "The City of Marshall will resurface 0.56 miles of North Kalamazoo Avenue from Brewer Street to Linden Street in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/23/2009 | 10/01/2009 | 11/15/2009 | 122215.07 | 0.559
5069 | Michigan | CALHOUN | BATTLE CREEK | 7 | 0913234 | "The City of Springfield will resurface 1.3 miles of Harmonia Road from M-37 to Evergreen in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/28/2009 | 09/08/2009 | 07/27/2011 | 330773 | 1.344
5070 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914019 | The Cass County Road Commission will resurface 1.8 miles of Ironwood Drive from Redfield Street to Bell Road, in the Niles urbanized area. This will improve the driving quality by making the road smo | Pavement Improvement | 07/09/2009 | 07/19/2010 | 07/30/2010 | 40360 | 1.76
5071 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914020 | The Cass County Road Commission will resurface 0.2 miles of Redfield Road from Adamsville Road to Mason Township, in the Niles urbanized area. This will improve the driving quality by making the road | Pavement Improvement | 07/09/2009 | 07/19/2010 | 07/30/2010 | 12150 | 0.192
5072 | Michigan | CASS |  | 6 | 0914021 | The Cass County Road Commission will resurface 0.5 miles of Matthews Street from Dailey Road to Cherry Grove Road, in the Dowagiac urbanized area. This will improve the driving quality by making the | Pavement Improvement | 07/07/2009 | 10/01/2009 | 10/31/2009 | 50000 | 0.503
5073 | Michigan | CASS |  | 6 | 0914022 | The Cass County Road Commisssion will resurface 3.7 miles of Decatur Road from M-60 to Kelsey Lake Road, near Cassopolis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 08/31/2009 | 09/15/2009 | 87279.15 | 3.717
5074 | Michigan | CASS |  | 6 | 0914023 | The Cass County Road Commisssion will resurface 3 miles of Brownsville Street from M-62 to Crooked Creek Road,south of Cassopolis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/30/2009 | 08/31/2009 | 09/15/2009 | 73916 | 2.962
5075 | Michigan | CASS |  | 6 | 0914024 | "The Cass County Road Commission will resurface various sections of Pine Lake, Monette and Dailey Streets totalling 7.3 miles in the southwest part of the county. This will improve the driving quality | Pavement Improvement | 06/30/2009 | 08/31/2009 | 09/15/2009 | 77650 | 2.64
5076 | Michigan | CASS |  | 6 | 0914025 | The Cass County Road Commisssion will resurface 1.7 miles of Indian Lake Road fromCrystal Springs to Smith Lake Road, between Niles and Dowagiac. This will improve the driving quality by making the r | Pavement Improvement | 06/30/2009 | 08/31/2009 | 09/15/2009 | 32041 | 1.716
5077 | Michigan | CASS |  | 6 | 0914026 | "The Cass County Road Commission will resurface various sections of Marcellus Highway totalling 0.9 miles in thenorth part of the county. This will improve the driving quality by making the road smoot | Pavement Improvement | 06/30/2009 | 08/31/2009 | 09/15/2009 | 82515.97 | 3.845
5078 | Michigan | CASS |  | 6 | 0914027 | The Cass County Road Commission will resurface 0.18 miles of Middle Crossing Road from Yaw Street to the city limits, in the Dowagiac urbanized area. This will improve the driving quality by making t | Pavement Improvement | 07/08/2009 | 08/02/2010 | 08/27/2010 | 20000 | 0.18
5079 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914031 | The Cass County Road Commission will resurface 1.4 miles of Huntly Road from Holly Street to Barron Lake Road, in the Niles urbanized area. This will improve the driving quality by making the road sm | Pavement Improvement | 07/20/2009 | 08/31/2009 | 09/15/2009 | 27500 | 1.36
5080 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914032 | The Cass County Road Commission will resurface 2.7 miles of Beebe Road from US-12 to Runkle Road and from Redfield Street to US-12, in the Niles urbanized area. This will improve the driving quality | Pavement Improvement | 07/20/2009 | 08/31/2009 | 09/15/2009 | 61948 | 2.798
5081 | Michigan | CASS |  | 6 | 0914033 | The Cass County Road Commisssion will resurface 4 miles of Dewey Lake Street from M-51 to Glenwood road, in the northeast part of the county. This will improve the driving quality by making the road | Pavement Improvement | 07/20/2009 | 07/19/2010 | 07/30/2010 | 75947 | 3.959
5082 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 0914034 | The Cass County Road Commission will resurface 2.5 miles of Pine Lake Road from M-60 to Anderson Road, in the Niles urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/21/2009 | 08/31/2009 | 09/15/2009 | 31578 | 1.584
5083 | Michigan | CHEBOYGAN |  | 1 | 0916011 | MDOT will resurface 1.2 miles of US-23 from M-27 to the Little Black River in the village of Cheboygan. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/27/2009 | 05/27/2009 | 09/18/2009 | 751019.75 | 1.172
5084 | Michigan | CHEBOYGAN |  | 1 | 0916013 | One and a quarter miles of Trowbridge Rd will be resurfaced from the Sturgeon River bridge to South Straights Hwy in the Village of Wolverine. This will improve the driving quality by making the road | Pavement Improvement | 12/10/2009 | 05/12/2010 | 06/11/2010 | 15298 | 1.258
5085 | Michigan | CHEBOYGAN |  | 1 | 0916014 | Four tenths of a mile of South Straights Hwy will be resurfaced from Cedar St to the north village limits of the Village of Wolverine. This will improve the driving quality by making the road smoothe | Pavement Improvement | 12/10/2009 | 05/12/2010 | 06/11/2010 | 58321.06 | 0.408
5086 | Michigan | CLARE |  | 4 | 0918007 | There will be 5.41 miles of paved pathway in the village of Farwell on the Pere Marquette Rail Trail for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 04/02/2009 | 04/02/2009 | 04/30/2010 | 804661.79 | 5.409
5087 | Michigan | CLINTON | LANSING | 8 | 0919009 | Near the city of Bath in Clinton County, MDOT will improve the driving surface of 6.5 miles of I-96 with a concrete restoration project. | Pavement Improvement | 05/01/2009 | 05/01/2009 | 06/16/2011 | 1706751.76 | 16.097
5088 | Michigan | CLINTON |  | 8 | 0919010 | Near the City of Dewitt, The Clinton County Road Commission is resurfacing 1 mile of West Alward Road from US-127BR to Williams Road to improve driving quality and make the road smoother. | Pavement Improvement | 08/03/2009 | 08/11/2009 | 09/18/2009 | 163735.7 | 1.004
5089 | Michigan | CLINTON | LANSING | 8 | 0919011 | In the city of Dewitt, over 1/2 mile of West Main Street will be resurfaced from Norris Road to Scott Street to improve ride quality and make the roadway smoother. Improvements include new sidewalk t | Pavement Improvement | 08/03/2009 | 08/24/2009 |  | 190414.02 | 0.602
5090 | Michigan | CLINTON | LANSING | 8 | 0919012 | Near the city of Dewitt, The Clinton County Road Commission is resurfacing 1 mile of East Clark Road from US-127BR to Wood Road to improve driving quality and make the road smoother. | Pavement Improvement | 08/03/2009 | 08/19/2009 | 09/18/2009 | 287307.25 | 1.003
5091 | Michigan | CLINTON |  | 8 | 0919013 | Close to the villages of Hubbardston and Pewamo, the Clinton county Road Commission will improve 4 miles of pavement on West Colony Road from the West Clinton County Line to Tallman Road. | Pavement Improvement | 06/02/2009 | 06/22/2009 | 07/11/2009 | 65955.65 | 3.945
5092 | Michigan | CLINTON |  | 8 | 0919014 | In Bath Township, the Clinton County Road Commission will resurface 1/2 mile of East Clark Road from Webster Road to the east to improve driving quality and make the road smoother. | Pavement Improvement | 08/14/2009 | 09/01/2009 | 09/18/2009 | 134651.7 | 0.5
5093 | Michigan | CLINTON | LANSING | 7,8 | 0919015 | MDOT is reconstructing nearly 7 miles of I-96 in Clinton and Eaton Counties to improve driver mobility and make the roadway safer and smoother. This project is the 5000th Recovery Act project and is | Pavement Improvement | 06/24/2009 | 06/24/2009 | 03/01/2012 | 44933102.11 | 15.835
5094 | Michigan | CLINTON |  | 8 | 0919021 | 4 miles of East Colony Road is being resurfaced north of St. Johns to make the roadway smoother and improve ride quality. | Pavement Improvement | 08/05/2009 | 08/11/2009 | 08/31/2009 | 68354.97 | 4.013
5095 | Michigan | CRAWFORD |  | 1 | 0920009 | The Crawford County Road Commission will resurface 1.7 miles of South Wakely Bridge Rd from M-72 to The Au Sable River in the Huron National Forest near Grayling. This will improve the driving qual | Pavement Improvement | 09/03/2009 | 09/21/2009 | 10/30/2009 | 195116.35 | 1.664
5096 | Michigan | CRAWFORD |  | 1 | 0920010 | MDOT will resurface 2.4 miles of M-93 from Camp Grayling to M-72 in the vicinity of Grayling. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/13/2009 | 05/13/2009 | 06/25/2010 | 385568.05 | 2.606
5097 | Michigan | CRAWFORD |  | 1 | 0920013 | MDOT will resurface 5 miles of I-75 from south of the NYC RR to north of M-93 in the vicinity of Grayling. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/02/2009 | 06/02/2009 | 05/05/2011 | 3332348.34 | 5.319
5098 | Michigan | DELTA |  | 1 | 0921011 | This intersection project at US-2 and US-41 in the City of Rapid River will increase safety and improve the pavement condition which will make for a smoother ride. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/18/2010 | 1510991.51 | 1.165
5099 | Michigan | DELTA |  | 1 | 0921014 | This pavement project on County Road 513 in Delta County will improve the drive quality and make the road smoother. | Pavement Improvement | 08/19/2009 | 01/04/2010 | 10/31/2010 | 244861 | 11.418
5100 | Michigan | DICKINSON |  | 1 | 0922007 | This Center Left-Turn lane project on M-95 in Sagola will improve safety and increase mobility. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 10/18/2010 | 373621.01 | 0.363
5101 | Michigan | DICKINSON |  | 1 | 0922008 | This pavement project on Balsam Street in the City of Kingsford will improve the drive quality and make the road smoother. | Pavement Improvement | 09/01/2009 | 09/28/2009 | 10/20/2009 | 222475.03 | 0.497
5102 | Michigan | EATON | LANSING | 7 | 0923010 | In Eaton County just outside of city of Lansing limits , 2.41 miles of Creyts Road is to be resurfaced from Lansing Road to I-496. This work will improve driving quality and make the road smoother. | Pavement Improvement | 06/29/2009 | 07/13/2009 | 10/30/2009 | 667891.65 | 2.414
5103 | Michigan | EATON | LANSING | 7 | 0923012 | In the City of Grand Ledge, just over 1/4 miles of Brookside Drive from Timbercreek Street to South Street will be reconstructed to improve rideability and make the roadway smoother. | Pavement Improvement | 07/31/2009 | 08/03/2009 | 09/14/2009 | 205654.6 | 0.349
5104 | Michigan | EATON | LANSING | 7 | 0923013 | In the City of Grand Ledge, 1/4 miles of Timber Creek Drive from Saginaw highway to Brookside Drive will be reconstructed to improve rideabilty and make the roadway smoother. | Pavement Improvement | 07/31/2009 | 08/03/2009 | 09/14/2009 | 188445.44 | 0.284
5105 | Michigan | EATON |  | 7 | 0923015 | In the City of Eaton Rapids, MDOT is working on building a streetscape project on South Clinton Trail and South Main Street (State Routes M-99 & M-50) The work will be from just west of Hallawood Lan | Pavement Improvement | 06/17/2009 | 06/17/2009 | 09/20/2012 | 2220411.77 | 1.385
5106 | Michigan | EATON |  | 7 | 0923016 | The City of Eaton Rapids in Eaton County will beautify its downtown by building this streetscape. The streetscape will include new brick pavers, lighting, decorative sidewalk and and additional lands | Transportation Enhancements | 06/10/2009 | 06/10/2009 | 09/20/2012 | 853534.7 | 0.397
5107 | Michigan | EATON | LANSING | 7 | 0923017 | In Eaton County just outside of city of Lansing limits , 1/2 mile of Creyts Road is to be resurfaced from Saginaw highway to the north. This work will improve driving quality and make the road smooth | Pavement Improvement | 10/07/2009 | 07/23/2010 | 05/31/2010 | 117146 | 0.499
5108 | Michigan | EMMET |  | 1 | 0924008 | The Emmet County Road Commission will resurface three quarters of a mile of Mitchell Rd from Division Rd east 3900 ft in the vicinity of Petoskey. This will improve the driving quality by making the | Pavement Improvement | 06/15/2009 | 06/15/2009 | 10/19/2009 | 155000 | 0.654
5109 | Michigan | EMMET |  | 1 | 0924009 | The Emmet County Road Commission will resurface 2.3 miles of W Conway Rd from Heydey St to Clayton Rd in Little Traverse Township. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/01/2009 | 05/01/2009 | 11/15/2009 | 350165.87 | 2.331
5110 | Michigan | GENESEE |  | 4,5 | 0925015 | Just west of the city of Flint, MDOT will repair M-13 over Mistequay Creek to make the bridge last longer. | Bridge Improvement | 04/02/2009 | 04/02/2009 | 04/01/2011 | 187661.7 | 0
5111 | Michigan | GENESEE |  | 4,5 | 0925016 | Just west of the city of Flint, MDOT will repair 12.2 miles of M-13 to extend the service life of the existing pavement. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 01/15/2011 | 5394215.94 | 12.395
5112 | Michigan | GENESEE |  | 5,10 | 0925018 | Within the City of Fenton, MDOT will resurface parking lot on US-23 to improve the quality of the parking surface and extend the life of the road pavement. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 12/31/2010 | 94674.25 | 0
5113 | Michigan | GENESEE | FLINT | 5 | 0925021 | The MDOT will design roadway and bridge improvements to I-475 from the I-75 and I-69 interchange south of Flint north 6.6 miles. | Other | 05/14/2009 | 05/14/2009 | 12/31/2009 | 825251.03 | 14.929
5114 | Michigan | GENESEE | FLINT | 5 | 0925023 | Near the city of Flint, MDOT is upgrading 1.16 miles of pavement on Pasadena Avenue from I-75 to the Flint city limits, Genesee County. This will improve the ride quality of the road. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 07/30/2010 | 1536295 | 1.087
5115 | Michigan | GENESEE | FLINT | 5 | 0925024 | There will be 1.10 miles of pavement repair on Clio Road from Pierson Road to Carpenter Road to improve safety and increase mobility. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 08/15/2010 | 1385335 | 0.997
5116 | Michigan | GENESEE |  | 5 | 0925032 | Genesee County is resurfacing 0.99 miles on Irish Road from Richfield Road northerly to Carpenter Road to improve the driving quality by making the road smoother. | Pavement Improvement | 06/23/2009 | 06/23/2009 | 08/15/2010 | 624753 | 0.925
5117 | Michigan | GENESEE | FLINT | 5 | 0925038 | Genesee County will repair the pavement of 0.83 miles on Morrish Road from I-69 to the Canadian National Railway railroad tracks in the city of Swartz Creek to improve the driving quality of the road. | Pavement Improvement | 07/02/2009 | 07/02/2009 | 08/15/2010 | 252303.31 | 0.918
5118 | Michigan | GENESEE | FLINT | 5 | 0925041 | In the City of Fenton in Genesee County there is 1.16 miles of resurfacing on Silver Parkway from Owen Road to Silver Lake Road to improve the driving quality by making the road smoother. | Pavement Improvement | 10/23/2009 | 10/26/2009 | 10/30/2010 | 1180758.17 | 0.912
5119 | Michigan | GENESEE | FLINT | 5 | 0925046 | In the city of Flint there is 0.95 miles of road reconstruction on Kettering Gateway from I-69 to Chevrolet Avenue to improve the driving quality by making the road smoother. | Pavement Improvement | 08/18/2009 | 08/18/2009 | 05/27/2011 | 2315955.02 | 0.64
5120 | Michigan | GENESEE | FLINT | 5 | 0925054 | In Genesee County, MDOT will perform a Design Build reconstruction of 4 bridge structures on I-475 from the south interchange to I-69 including Hill road and Bristol Road over I-475 and I-475 over Map | Pavement Improvement | 09/18/2009 | 09/18/2009 | 02/01/2012 | 20037904.5 | 14.929
5121 | Michigan | GLADWIN |  | 1 | 0926009 | The County of Gladwin is resurfacing 2.02 miles of roadway to improve the driving quality of the Knox Road from Shock Road easterly to Dundas Road. | Pavement Improvement | 09/02/2009 | 10/05/2009 | 11/07/2009 | 387200 | 1.987
5122 | Michigan | GOGEBIC |  | 1 | 0927008 | This pavement project on US-2 in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 05/01/2009 | 05/01/2009 | 10/18/2010 | 1843722.08 | 16.204
5123 | Michigan | GOGEBIC |  | 1 | 0927014 | This pavement and guardrail project on US-45 in Gogebic County will improve the safety and ride quality of the road. | Pavement Improvement | 08/13/2009 | 08/13/2009 | 10/18/2010 | 1905797.08 | 12.415
5124 | Michigan | GRAND TRAVERSE |  | 4 | 0928008 | East 8th St in Traverse City will be resurfaced for over a half mile from garfield to Woodmere St. This will improve the driving quality by making the road smoother. | Other | 10/19/2009 | 04/12/2010 | 06/23/2010 | 210000 | 0.605
5125 | Michigan | GRAND TRAVERSE |  | 4 | 0928010 | The Grand Traverse County Road Commission will place new pavement markings at various locations on county roads in the county to provide more visible markings. | Safety/Traffic Management | 10/08/2009 | 05/18/2010 | 06/18/2010 | 277500 | 1.434
5126 | Michigan | GRAND TRAVERSE |  | 4 | 0928011 | The Grand Traverse County Road Commission will place new pavement symbols at various locations on county roads in the county to provide safer roadways. | Safety/Traffic Management | 08/13/2009 | 09/18/2009 | 07/30/2010 | 90692.15 | 1.434
5127 | Michigan | GRAND TRAVERSE |  | 4 | 0928012 | The Grand Traverse County Road Commission will resurface 3.2 miles of karlin Rd from M-137 to Nessen Rd south of the village of Green Lake. This will improve the driving quality by making the road sm | Pavement Improvement | 12/17/2009 | 06/01/2010 | 07/02/2010 | 404957.82 | 3
5128 | Michigan | GRATIOT |  | 4 | 0929208 | Near the city of Alma there will be 4.05 miles of resurfacing on Lumberjack Road from M-46 northerly to North County Line Road to improve driving quality by making the road smoother. | Other | 12/22/2009 | 04/27/2010 | 08/13/2010 | 446327 | 4.057
5129 | Michigan | GRATIOT |  | 4 | 0929210 | The city of Alma is resurfacing 8.92 miles on M-46 from the Gratiot/Montcalm County line easterly to west of US-127BR to improve driving quality by making the road smoother. | Pavement Improvement | 09/21/2009 | 09/21/2009 | 01/21/2011 | 1648382.16 | 8.92
5130 | Michigan | HILLSDALE |  | 7 | 0930012 | 5.29 miles of South Waldron Road from Territorial Road northerly to Prattville Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness through the community | Pavement Improvement | 05/28/2009 | 06/30/2009 | 08/27/2009 | 69889.47 | 5.291
5131 | Michigan | HILLSDALE |  | 7 | 0930013 | 2.75 miles of Church Road from Waldon Road to US-127 will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness east of the city of Hillsdale, Hillsdale County. | Pavement Improvement | 05/28/2009 | 06/29/2009 | 09/17/2009 | 44312.91 | 2.754
5132 | Michigan | HILLSDALE |  | 7 | 0930014 | 2.91 miles of North Adams Road from the Village of Jonesville to Mimes Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness in Hillsdale County. | Pavement Improvement | 05/28/2009 | 06/11/2009 | 08/27/2009 | 93387.72 | 2.914
5133 | Michigan | HILLSDALE |  | 7 | 0930015 | 3.0 miles of North Adam Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, South of the City of Jackson in Hillsdale County. | Pavement Improvement | 05/28/2009 | 06/01/2009 | 08/27/2009 | 91506.45 | 3.004
5134 | Michigan | HILLSDALE |  | 7 | 0930016 | 3 miles of East Bacon Road will have a Chip and Seal treatment from Peterson Road to Osseo Road east of the village of Hillsdale, Hillsdale County. The work will preserve the pavement life and improv | Pavement Improvement | 05/28/2009 | 06/29/2009 | 09/17/2009 | 83859 | 2.993
5135 | Michigan | HILLSDALE |  | 7 | 0930017 | 5 miles of South Allen Road from Bankers Road to US-12 will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness. This proejct is located just west of the city of | Pavement Improvement | 06/02/2009 | 06/29/2009 | 08/27/2009 | 93791.85 | 4.96
5136 | Michigan | HOUGHTON |  | 1 | 0931007 | This paving project on US-41 east of the City of Houghton will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 06/22/2009 | 353754.39 | 2.046
5137 | Michigan | HOUGHTON |  | 1 | 0931008 | This pavement project on US-41 in Houghton County will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/18/2010 | 328382.32 | 2.654
5138 | Michigan | HOUGHTON |  | 1 | 0931009 | This shoulder paving and guardrail installation project on M-26 in Houghton County will serve cyclists, joggers and other non-motorized users and will improve safety. | Transportation Enhancements | 04/02/2009 | 04/02/2009 | 08/18/2009 | 176732.89 | 2.443
5139 | Michigan | HOUGHTON |  | 1 | 0931010 | This paving project on M-26 in the Village of Lake Linden will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/18/2010 | 472359 | 2.577
5140 | Michigan | HOUGHTON |  | 1 | 0931014 | This pavement project on Erickson Drive in the Houghton Urban Area will improve the drive quality and make the road smoother. | Pavement Improvement | 08/31/2009 | 09/23/2009 | 10/15/2009 | 90000 | 0.45
5141 | Michigan | HOUGHTON |  | 1 | 0931015 | This pavement project on 6th Street in the City of Larium will improve the drive quality and make the road smoother. | Pavement Improvement | 08/31/2009 | 09/23/2009 | 10/15/2009 | 115000 | 0.361
5142 | Michigan | HOUGHTON |  | 1 | 0931017 | This pavement project on Sharon Ave. in the Houghton Urban Area will improve the drive quality and make the road smoother. | Pavement Improvement | 09/01/2009 | 09/22/2009 | 10/15/2009 | 88521.77 | 0.48
5143 | Michigan | HURON |  | 10 | 0932213 | North of Sebewaing, MDOT is upgrading 3.6 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 04/14/2009 | 04/14/2009 | 03/31/2011 | 140515.08 | 3.588
5144 | Michigan | HURON |  | 10 | 0932214 | West of Port Austin, MDOT is upgrading 4.8 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 04/16/2009 | 04/16/2009 | 03/31/2011 | 293993.36 | 4.886
5145 | Michigan | HURON |  | 10 | 0932219 | There will be 2.68 miles of resurfacing on Atwater Road from Parisville Road easterly to west of Ruth Road to improve the driving quality of the road by making the road smoother. | Pavement Improvement | 07/22/2009 | 08/29/2009 | 09/30/2009 | 355560.72 | 2.94
5146 | Michigan | HURON |  | 5,10 | 0932220 | Near the city of Sebewaing there are 16.28 miles sidewalk improvements on M-25 from south of Huron Line Road northeasterly to south of Myers Road, from south of Orchard Street northerly to south of De | Transportation Enhancements | 05/29/2009 | 05/29/2009 | 03/31/2010 | 324906.28 | 3.793
5147 | Michigan | INGHAM | LANSING | 8 | 0933024 | Near the community of Haslett MI, just over 1/4 miles of Marsh Road will be resurfaced from Baker Street to the north Ingham County Line. This project will improve rideabilty and make the roadway smo | Pavement Improvement | 07/02/2009 | 07/27/2009 | 07/31/2009 | 86778.25 | 0.34
5148 | Michigan | INGHAM |  | 8 | 0933025 | Between the cities of Leslie and Eaton Rapids in Ingham County, 6.0 miles of Bellevue Road will have Chip and Seal treatment to preserve pavement life and improve pavement rideabilty. | Pavement Improvement | 05/05/2009 | 07/07/2009 | 07/31/2009 | 93999.72 | 6.149
5149 | Michigan | INGHAM |  | 8 | 0933026 | South of Mason in Ingham County, Barnes Road will have Chip and Seal treatment from South College Road to South Meridian Road to preserve pavement life and improve pavement rideability. This project | Pavement Improvement | 05/05/2009 | 07/20/2009 | 07/24/2009 | 93999.85 | 6.474
5150 | Michigan | INGHAM | LANSING | 8 | 0933028 | 0.95 miles of South Washington Road from West Jolly Road to Miller Road will be resurfaced in the City of Lansing. Improvements include ADA sidewalk ramp upgrades for increased pedestrian access and | Pavement Improvement | 08/05/2009 | 08/05/2009 |  | 322116.67 | 0.948
5151 | Michigan | INGHAM | LANSING | 8 | 0933029 | In the City of East Lansing, 1 mile of East Mount Hope Avenue will be reconstructed along the southern limits of the city. The new roadway will improve rideablity and improve drainage features. | Pavement Improvement | 07/22/2009 | 07/29/2009 | 10/02/2009 | 681220 | 1.471
5152 | Michigan | INGHAM |  | 8 | 0933030 | West of the Village of Stockbridge, 4.75 miles of Morton and Heeney Roads will have Chip and Seal treatment to preserve pavement life and improve rideability. | Pavement Improvement | 05/21/2009 | 07/20/2009 | 07/24/2009 | 62576.43 | 4.079
5153 | Michigan | INGHAM | LANSING | 8 | 0933032 | 0.45 miles of Michigan Avenue from US-127 to Friendship Court will be resurfaced in the City of Lansing. Improvements include concrete curb & gutter and sidewalk replacement. The work will improve r | Pavement Improvement | 08/05/2009 | 08/17/2009 | 09/21/2009 | 447851.38 | 0.788
5154 | Michigan | INGHAM | LANSING | 8 | 0933034 | Near Williamston in Ingham county, MDOT will resurface about 8 miles of I-96 to improve driving quality by making the road smoother. | Pavement Improvement | 05/28/2009 | 05/28/2009 | 12/31/2011 | 3259504.55 | 17.302
5155 | Michigan | INGHAM | LANSING | 8 | 0933036 | In the community of Holt in Ingham County, 1.37 miles of West Holt Road from Heatherton Drive to Thornburn Street will be resurfaced to improve rideabilty and make the roadway smoother. | Pavement Improvement | 07/07/2009 | 09/01/2009 | 11/15/2009 | 725374.31 | 1.329
5156 | Michigan | INGHAM | LANSING | 8 | 0933037 | Near the community of Haslett MI, 1/2 miles of Marsh Road will be resurfaced from Tihart Road to just north of Franklin Street in Ingham County. This project will improve rideabilty and make the road | Pavement Improvement | 09/21/2009 | 10/01/2009 | 05/31/2010 | 484059.58 | 0.789
5157 | Michigan | IONIA |  | 3 | 0934011 | The MDOT will resurface 4 miles of M-66 near the City of Ionia. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 12/31/2010 | 894993.66 | 3.902
5158 | Michigan | IONIA |  | 3 | 0934014 | The City of Ionia will resurface over a half mile of West Adams Street from M-66 to Jackson Street in the City of Ionia. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 08/31/2009 |  | 259520.75 | 0.691
5159 | Michigan | ISABELLA |  | 4 | 0937007 | Within the City of Mt. Pleasant, MDOT will repair 4.85 miles of US-127 south of the Blanchard Road interchange to extend the service life of the existing road as well as make repairs to the bridge to | Pavement Improvement | 04/28/2009 | 04/28/2009 | 09/19/2011 | 10666736.82 | 10.526
5160 | Michigan | ISABELLA |  | 4 | 0937012 | The City of Rosbush is reconstructing 3.00 miles on Vernon Road from Winn Road easterly to Vandecar Road and from Lincoln Road easterly to Mission Road to improve driving quality by making the road sm | Pavement Improvement | 10/05/2009 | 10/09/2009 | 11/06/2009 | 472051 | 3.004
5161 | Michigan | JACKSON |  | 7 | 0938221 | In Jackson County, the County Road Commission will reconstruct East Michigan Avenue from Fox Road to Gillett's Lake Road to improve driving quality by making the road smoother. | Pavement Improvement | 08/04/2009 | 08/17/2009 |  | 624776.04 | 0.755
5162 | Michigan | JACKSON | JACKSON | 7 | 0938222 | In the city of Jackson, Jackson County, the city will resurface 1/2 mile of Ganson Street from Cooper Street to East Avenue. The project will include sidewalk repairs and new ADA ramps to improve ped | Pavement Improvement | 08/26/2009 | 09/08/2009 |  | 284951.27 | 0.461
5163 | Michigan | JACKSON | JACKSON | 7 | 0938223 | In the city of Jackson, Jackson County, the city will resurface 1/2 mile of West Morrell Street from Brown Street to West Avenue. The project will improve driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 09/08/2009 |  | 328692.09 | 0.502
5164 | Michigan | JACKSON | JACKSON | 7 | 0938224 | In the city of Jackson, Jackson County, the city will reconstruct just under 1/2 mile of North Jackson Street from Glick Highway to Ganson Street to improve driving quality by making the road smoother | Pavement Improvement | 12/23/2009 | 04/05/2010 | 07/30/2010 | 533236.53 | 0.371
5165 | Michigan | JACKSON | JACKSON | 7 | 0938241 | In Jackson County, the County Road Commission will resurface Springport Road from Shirley Drive to Airport Road to improve just over a mile of road to improve drive quality by making the road smoother | Pavement Improvement | 02/03/2010 | 05/05/2010 |  | 617319.23 | 1.273
5166 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939011 | MDOT will reconstruct the interchange of I-94 at Westnedge Avenue to a new design and will reconstruct and add a lane in each direction to 1.9 miles of I-94, between Oakland Drive and Lovers Lane, in | Pavement Widening | 04/07/2009 | 04/07/2009 | 12/31/2012 | 47911594.23 | 5.516
5167 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939012 | "The City of Portage will resurface 1.6 miles of E. Centre Avenue from Portage Road to Westnedge Avenue in the Kalamazoo urbanized area. This will improve the driving quality by making the road smooth | Pavement Improvement | 06/22/2009 | 07/08/2009 | 07/27/2011 | 900000 | 1.612
5168 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939013 | "The City of Portage will resurface 0.75 miles of E. Kilgore Road from Westnedge Avenue to Grand Elk RR in the Kalamazoo urbanized area. This will improve the driving quality by making the road smooth | Pavement Improvement | 06/30/2009 | 07/20/2009 | 07/27/2011 | 647541.67 | 0.743
5169 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939015 | The Kalamazoo County Road Commisssion will resurface 2.6 miles of S Avenue from Sprinkle Road to 29th Street, in the Kalamazoo urbanized area. This will improve the driving quality by making the road | Pavement Improvement | 07/31/2009 | 08/24/2009 | 07/27/2011 | 940291.84 | 2.579
5170 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939016 | The Kalamazoo County Road Commisssion will resurface 1 mile of S. 8th Street from R Avenue to Q Avenue, in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoot | Pavement Improvement | 08/03/2009 | 08/24/2009 | 07/27/2011 | 320496.79 | 1.001
5171 | Michigan | KALAMAZOO |  | 6 | 0939017 | The Kalamazoo County Road Commisssion will resurface 1 mile of N. 12th Street from D Avenue to C Avenue, in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoo | Pavement Improvement | 08/03/2009 | 08/24/2009 | 07/27/2011 | 395590.35 | 1.005
5172 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939022 | "The City of Kalamazoo will resurface 1.15 miles of E. Cork Street from Westnedge Avenue to Lovers Lane in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/10/2009 | 09/21/2009 |  | 493397.75 | 1.151
5173 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939023 | "The City of Kalamazoo will resurface 0.6 miles of Reed Street from Burdick Avenue to Portage Avenue in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/10/2009 | 09/21/2009 |  | 194445.25 | 0.606
5174 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939024 | "The City of Kalamazoo will resurface 0.4 miles of S. Burdick Street from Cork Street to Crescent in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/10/2009 | 09/21/2009 |  | 179661.5 | 0.434
5175 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939025 | "The City of Kalamazoo will resurface 1.1 miles of Lovers Lane from Cork Street to Kilgore Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/10/2009 | 09/21/2009 |  | 254334.05 | 1.073
5176 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939026 | "The City of Kalamazoo will resurface 0.25 miles of N. Edwards Street from South Street to Kalamazoo Avenue in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/15/2009 | 09/22/2009 | 05/14/2010 | 330192.5 | 0.252
5177 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 0939032 | "The village of Schoolcraft will resurface 1 mile of E. Eliza Street from west village limits to 14th Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 10/20/2009 | 10/21/2009 | 06/18/2010 | 222339.04 | 0.987
5178 | Michigan | KALKASKA |  | 1,4 | 0940007 | The Kalkaska County Road Commission will resurface 5 miles of County Highway 612 from the east county line to Blue Lake Rd and Darke to Rogers Rd . This will improve the driving quality by making the | Pavement Improvement | 12/18/2009 | 06/07/2010 | 06/11/2010 | 321701.47 | 4.687
5179 | Michigan | KENT | GRAND RAPIDS | 3 | 0941141 | The City of Wyoming will resurface one mile of Prairie Parkway from Byron Center to Burlingame Avenue in the City of Wyoming. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/13/2009 | 07/13/2009 | 09/30/2009 | 461140.4 | 1
5180 | Michigan | KENT | GRAND RAPIDS | 3 | 0941142 | The City of Wyoming will resurface two miles of Burlingame Avenue from 52 Street to 36th Street in the City of Wyoming. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/13/2009 | 07/13/2009 | 09/30/2009 | 848806.13 | 2.03
5181 | Michigan | KENT | GRAND RAPIDS | 3 | 0941143 | The City of Walker will resurface a half mile of Veteran's Memorial Drive from Riverbend to Maynard Avenue in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/02/2009 | 07/06/2009 | 08/31/2009 | 107983.75 | 0.499
5182 | Michigan | KENT | GRAND RAPIDS | 3 | 0941144 | The City of Walker will resurface 0.1 of a mile of Three Mile Road from Alpine Avenue to the I-196 exit ramp in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/29/2009 | 07/15/2009 | 08/31/2009 | 269634.14 | 0.13
5183 | Michigan | KENT | GRAND RAPIDS | 3 | 0941146 | The Kent County Road Commission will resurface two and three quarters of a mile of 5 Mile Road from Gavin Lake Road to Lincoln Lake Road in Kent County. This will improve the driving quality by makin | Pavement Improvement | 08/14/2009 | 09/14/2009 | 09/25/2009 | 672341.54 | 2.745
5184 | Michigan | KENT | GRAND RAPIDS | 3 | 0941147 | The MDOT will make repairs to the bridges at US-131and Pine Island Drive, Post Road, and 10 Mile Rd to make the bridges last longer. | Bridge Improvement | 04/23/2009 | 04/23/2009 | 12/31/2010 | 1665033.25 | 0
5185 | Michigan | KENT | GRAND RAPIDS | 2 | 0941149 | The City of Grand Rapids will resurface a half mile of Leonard Street from Nixon Street to Collingsdale Avenue in the City of Walker. This will improve the driving quality by making the road smoother | Pavement Improvement | 06/30/2009 | 07/13/2009 | 06/15/2011 | 1292485 | 0.535
5186 | Michigan | KENT | GRAND RAPIDS | 3 | 0941150 | The City of Grandville will resurface 0.2 of a mile of Potomac Avenue from 44th Street to Century Center in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/22/2009 | 09/14/2009 | 09/30/2009 | 69678.74 | 0.224
5187 | Michigan | KENT | GRAND RAPIDS | 2,3 | 0941151 | The City of Grandville will resurface 0.2 of a mile of Kenowa Avenue from the south City limits to Stonehenge Drive in the City of Grandville. This will improve the driving quality by making the road | Pavement Improvement | 07/22/2009 | 09/14/2009 | 09/30/2009 | 76696 | 0.17
5188 | Michigan | KENT | GRAND RAPIDS | 3 | 0941152 | The City of Grandville will resurface 0.4 of a mile of 44th Street from Potomac Avenue to Rivertown Parkway in the City of Grandville. This will improve the driving quality by making the road smoothe | Pavement Improvement | 07/22/2009 | 09/14/2009 | 09/30/2009 | 79502 | 0.373
5189 | Michigan | KENT | GRAND RAPIDS | 3 | 0941153 | The City of Grandville will resurface 0.1 of a mile of 44th Street from Kenowa Avenue to the I-196 ramp in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/22/2009 | 09/14/2009 | 09/30/2009 | 79502 | 0.114
5190 | Michigan | KENT | GRAND RAPIDS | 3 | 0941156 | The City of East Grand Rapids will resurface a 0.3 miles of Lake Drive from the west city limits to Plymouth Road in the City of East Grand Rapids. This will improve the driving quality by making t | Pavement Improvement | 07/30/2009 | 08/03/2009 | 10/31/2009 | 332036 | 0.33
5191 | Michigan | KENT | GRAND RAPIDS | 3 | 0941158 | The Kent County Road Commission will resurface over 1.5 miles of Patterson Avenue from 44th Street to M-37 in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/11/2009 | 08/13/2009 | 05/15/2010 | 1100000 | 1.596
5192 | Michigan | KENT | GRAND RAPIDS | 3 | 0941159 | The Kent County Road Commission will resurface two and half miles of 84th Street from Cherry Valley Avenue to Whitneyville Avenue in Kent County. This will improve the driving quality by making the r | Pavement Improvement | 07/17/2009 | 08/04/2009 | 10/31/2009 | 608150.43 | 2.508
5193 | Michigan | KENT | GRAND RAPIDS | 3 | 0941162 | The City of East Grand Rapids will resurface a quarter of a mile of Breton Avenue from the norht city limits to Burton Street in East Grand Rapids. This will improve the driving quality by making the | Pavement Improvement | 08/03/2009 | 08/10/2009 | 06/11/2010 | 300000 | 0.251
5194 | Michigan | KENT | GRAND RAPIDS | 3 | 0941166 | The MDOT will make repairs to the bridge at M-57 over the White Pine Trail north of Grand Rapids to make the bridge last longer. | Bridge Improvement | 05/28/2009 | 05/28/2009 | 12/31/2010 | 532283.83 | 0
5195 | Michigan | KENT |  | 2,3 | 0941172 | The MDOT is deploying ITS technology on M-6 at I-196, I-96 and at M-11 and M-6 in Kent County, Grand Rapids area to improve mobility and reduce congestion | Safety/Traffic Management | 06/15/2009 | 06/15/2009 | 01/01/2011 | 823158.18 | 46.718
5196 | Michigan | KENT | GRAND RAPIDS | 3 | 0941176 | The MDOT is integrating ITS technoligies on US-131, I-96 and I-196 at 31 locations around Kent County in the Grand Rapids area to improve mobility and reduce congestion. | Safety/Traffic Management | 06/23/2009 | 06/23/2009 | 07/15/2012 | 280000 | 0
5197 | Michigan | KENT |  | 3 | 0941177 | The MDOT will make repairs to the bridge at M-11 over the Grand River in the City of Walker to make the bridge last longer. | Bridge Improvement | 06/23/2009 | 06/23/2009 | 12/31/2010 | 737053.64 | 0
5198 | Michigan | KENT | GRAND RAPIDS | 3 | 0941179 | The City of Grand Rapids will beautify Madison Avenue and Hall Street in the vicinity of Adams St and in the vicinity of Jefferson Ave by building this streetscape. | Pavement Improvement | 10/15/2009 | 11/16/2009 | 09/30/2012 | 744772.43 | 1.373
5199 | Michigan | KENT | GRAND RAPIDS | 3 | 0941187 | The MDOT will widen almost 4 miles of I-196 freeway from the Grand River East to Fuller Avenue in the Grand Rapids area to improve mobility and reduce congestion | Pavement Widening | 08/18/2009 | 08/18/2009 | 12/30/2011 | 33341155.4 | 13.09
5200 | Michigan | KENT | GRAND RAPIDS | 3 | 0941188 | The MDOT will replace 2 miles of I-196 freeway lighting from the Grand River East to Fuller Avenue in the Grand Rapids area to improve driver visibility. | Pavement Improvement | 08/18/2009 | 08/18/2009 | 06/01/2011 | 650996.74 | 3.876
5201 | Michigan | KENT | GRAND RAPIDS | 3 | 0941189 | The MDOT will replace the I-196 bridges over Lafayette Avenue in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 09/30/2009 | 09/30/2009 | 06/01/2011 | 2587985.19 | 0
5202 | Michigan | KENT | GRAND RAPIDS | 3 | 0941190 | The MDOT will replace the Coit Avenue bridge over I-196 in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 08/18/2009 | 08/18/2009 | 06/01/2011 | 2508509.56 | 0
5203 | Michigan | KENT |  | 2 | 0941203 | The City of Kent City will resurface 0.2 miles of South Main Street from Ball Creek Road to M-46/17 Mile Road in the City of Kent City. This will improve the driving quality by making the road smooth | Pavement Improvement | 06/22/2010 | 07/06/2010 | 09/10/2010 | 70000 | 0.161
5204 | Michigan | KENT | GRAND RAPIDS | 3 | 0941206 | The Kent County Road Commission will resurface one and a half miles of Leonard Street from M-44 to Crahen Street in Grand Rapids Township. This will improve the driving quality by making the road smo | Pavement Improvement | 01/14/2010 | 06/14/2010 | 07/30/2010 | 484620 | 1.494
5205 | Michigan | KENT | GRAND RAPIDS | 3 | 0941211 | The City of Grand Rapids will resurface 0.2 miles of Lake Drive from Cherry Street to Fuller Avenue in the City of Grand Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/21/2009 | 04/19/2010 | 06/30/2010 | 230000 | 0.212
5206 | Michigan | KEWEENAW |  | 1 | 0942131 | This pavement project on Eagle Harbor Road in Keweenaw County will improve the drive quality and make the road smoother. | Other | 01/14/2010 | 06/10/2010 | 07/01/2010 | 164462 | 3.51
5207 | Michigan | LAKE |  | 2 | 0943229 | The Lake County Road Commission will resurface 5 miles of South Hawkins Rd from US-10 south in the vicinity of Reed City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/02/2009 | 08/03/2009 | 08/27/2009 | 91940 | 4.987
5208 | Michigan | LAKE |  | 2 | 0943230 | The Lake County Road Commission will resurface 6 miles of W Star Lake Drive around Star Lake in the Manistee National Forest southwest of the village of Baldwin. This will improve the driving qualit | Pavement Improvement | 06/02/2009 | 08/03/2009 | 08/27/2009 | 93367 | 6.047
5209 | Michigan | LAKE |  | 2 | 0943231 | The Lake County Road Commission will resurface 5 miles of E 92nd St and S BroadwayRd from S Forman to 96th and from 72nd to 92nd St in the Manistee National Forest. This will improve the driving qua | Pavement Improvement | 06/02/2009 | 08/03/2009 | 08/27/2009 | 89005 | 4.797
5210 | Michigan | LAKE |  | 2 | 0943232 | The Lake County Road Commission will resurface 4 miles of West 52nd St from the Baldwin Village limits westward. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/04/2009 | 08/03/2009 | 08/27/2009 | 73501 | 3.629
5211 | Michigan | LAPEER |  | 10 | 0944088 | In the city of Fenton, MDOT is resurfacing existing car pool lots at the US-23 exit to Silver Lake Road, on M-24 north of Barnes Lake Road, on M-90 between Brush Street and Baldwin Avenue, and on M-24 | Pavement Improvement | 04/17/2009 | 04/17/2009 | 12/31/2010 | 61652.35 | 0
5212 | Michigan | LAPEER |  | 10 | 0944089 | Within the City of North Branch, MDOT will resurface parking lot on M-90 to improve the quality of the parking surface and extend the life of the road pavement. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 12/31/2010 | 22729.22 | 0
5213 | Michigan | LAPEER |  | 10 | 0944092 | The city of Lapeer will reconstruct 0.31miles on N Saginaw Street to improve the driving quality by making the road smoother. | Other | 02/10/2010 | 04/05/2010 | 08/13/2010 | 240000 | 0.215
5214 | Michigan | LEELANAU |  | 4 | 0945329 | MDOT will resurface 16.5 miles of M-72 from the Village of Empire to Bugai Rd. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/09/2009 | 06/09/2009 | 05/05/2011 | 932630.33 | 16.401
5215 | Michigan | LEELANAU |  | 4 | 0945330 | The MDOT will construct a passing relief lane on M-72 from Cedar Run Rd to Goodrick Rd west of Traverse City. This will allow safer driving operations on M-72. | Pavement Widening | 06/30/2009 | 06/30/2009 | 03/03/2011 | 1409246.4 | 1.124
5216 | Michigan | LEELANAU |  | 4 | 0945332 | The Leelanau County Road Commission will resurface 1.5 miles of County Road 651 from Hohnke Rd to M-22 in the vicinity of Empire. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/18/2009 | 08/18/2009 | 11/12/2009 | 271725 | 1.585
5217 | Michigan | LIVINGSTON |  | 8 | 0947010 | 8.3 miles of resurfacng of US-23 from I-96 to M-59 just north of Brighton in Livingston County. This project will provide for improved rideability and increased pavement smoothness. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 02/09/2010 | 3118815.4 | 16.563
5218 | Michigan | LIVINGSTON |  | 8 | 0947011 | A new Carpool lot will be constructed at Burkhart Road just west of M-59 near the I-96 Interchange west of Howell. This lot will encourage ridesharing and reduce the number of cars on the roadway. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/30/2009 | 163471.09 | 0.02
5219 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947012 | MDOT will improve mobility and reduce congestion with installation of an Intelligent Transportation System (ITS) along I-96 from the city of Fowlerville easterly to the Oakland/Livingston County line | Safety/Traffic Management | 06/15/2009 | 06/15/2009 | 12/31/2010 | 533441.41 | 69.774
5220 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947015 | This project will provide for 1.5 miles of pavement resurfacing on East Grand River Avenue from Lake Chemung to 1/3 of a mile east of Hughes Road between the cities of Howell and Brighton in Livingsto | Pavement Improvement | 09/18/2009 | 09/22/2009 | 06/30/2010 | 1199887.3 | 1.517
5221 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947016 | This project will provide for 0.40 miles of pavement resurfacing on Main Street from Third Avenue to Grand River Avenue in the city of Brighton, Livingston County. This will provide for improved pave | Pavement Improvement | 09/21/2009 | 10/13/2009 |  | 254732.5 | 0.402
5222 | Michigan | LIVINGSTON |  | 8 | 0947018 | This project will provide for 2 miles of pavement resurfacing on Old US-23 from Dean Road to Faussett, north of the city of Brighton in Livingston County. This will provide for improved pavement ride | Pavement Improvement | 01/14/2010 | 05/10/2010 |  | 442597.03 | 2.056
5223 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947020 | This project will provide for 1.1 miles of pavement resurfacing on North Michigan Avenue from Grand River Avenue to M-59 in the city of Howell, Livingston County. This will provide for improved pavem | Pavement Improvement | 10/07/2009 | 10/16/2009 | 11/14/2009 | 310163.14 | 1.104
5224 | Michigan | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 8 | 0947021 | 1/3 of a mile of Walnut Street is being resurfaced from Maple Street to Clinton Street in the City of Howell, Livingston County to make the roadway smoother and improve ride quality. | Pavement Improvement | 10/07/2009 | 10/16/2009 | 11/14/2009 | 106000 | 0.349
5225 | Michigan | MACKINAC |  | 1 | 0949011 | This pavement and Rumble Strip project on US-2 in Mackinac County will improve safety and make the road smoother. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/18/2010 | 2541340.8 | 6.012
5226 | Michigan | MACOMB | DETROIT,MI | 12 | 0950035 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of 12 Mile Road in Macomb County. | Pavement Improvement | 07/27/2009 | 08/03/2009 | 09/30/2009 | 550876.16 | 0.465
5227 | Michigan | MACOMB |  | 10,12 | 0950036 | Resurfacing to maintain the pavement condition and improve ride quality of ramps at I-94 at 9 Mile Road, 10 Mile Road, and 23 Mile Road, and on M-19 in the city of St. Clair Shores by MDOT. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 04/01/2011 | 519873.41 | 0.897
5228 | Michigan | MACOMB | DETROIT,MI | 12 | 0950037 | Resurfacing to maintain the pavement condition and improve ride quality of Ten Mile Road in Eastpointe. | Pavement Improvement | 08/04/2009 | 08/15/2009 | 11/30/2009 | 319522.67 | 0.505
5229 | Michigan | MACOMB | DETROIT,MI | 12 | 0950038 | One mile of resurfacing to maintain the pavement condition and improve ride quality of 10 Mile Road in East Pointe and Center Line. | Pavement Improvement | 08/04/2009 | 08/15/2009 | 11/30/2009 | 469171.03 | 0.839
5230 | Michigan | MACOMB |  | 10 | 0950040 | Resurfacing to maintain the pavement condition and improve ride quality of M-19 near Richmond by MDOT. | Pavement Improvement | 05/29/2009 | 05/29/2009 | 04/01/2011 | 2211673.36 | 4.112
5231 | Michigan | MACOMB |  | 10 | 0950041 | Three miles of microsurfacing to preserve the pavement condition and improve ride quality of North Avenue and 26 Mile Road in Macomb County. | Pavement Improvement | 09/08/2009 | 09/16/2009 | 10/30/2009 | 293071.55 | 3.321
5232 | Michigan | MACOMB | DETROIT,MI | 12 | 0950045 | 2 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along 15 Mile Road in Sterling Heights by MDOT. | Pavement Improvement | 09/10/2009 | 09/14/2009 | 06/30/2010 | 2089235.2 | 2.226
5233 | Michigan | MACOMB | DETROIT,MI | 12 | 0950046 | Two and a half miles of resurfacing to maintain the pavement condition and improve ride quality of M-3 in Mount Clemens by MDOT. | Pavement Improvement | 07/09/2009 | 07/09/2009 | 04/01/2011 | 4306667.77 | 1.705
5234 | Michigan | MACOMB | DETROIT,MI | 10 | 0950051 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Schoenherr Road in Macomb County. | Pavement Improvement | 10/06/2009 | 10/14/2009 | 11/01/2009 | 282091.8 | 1.002
5235 | Michigan | MACOMB | DETROIT,MI | 10 | 0950058 | 2 mile application of a preventive maintenace treatment to improve safety, smoothness, and extend the service life of the existing pavement on Washington Street in New Baltimore by MDOT. | Pavement Improvement | 12/23/2009 | 05/12/2010 | 05/28/2010 | 300000 | 2.094
5236 | Michigan | MACOMB | DETROIT,MI | 12 | 0950059 | 2 miles of resurfacing to maintain the pavement condition and improve ride quality of 14 Mile Road in Sterling Heights. | Pavement Improvement | 02/02/2010 | 04/21/2010 | 07/31/2010 | 1480150.97 | 0.94
5237 | Michigan | MACOMB | DETROIT,MI | 12 | 0950060 | Resurfacing to maintain the pavement condition and improve ride quality of 14 Mile Road in Clinton. | Pavement Improvement | 02/02/2010 | 04/21/2010 | 07/31/2010 | 1141735.24 | 1.37
5238 | Michigan | MANISTEE |  | 2 | 0951308 | The Mainistee County Road Commission will resurface 4 miles of Stronach Rd from M-55 to Eastlake Rd in the vicinity of the Village of Eastlake in the Manistee National Forest. This will improve the d | Pavement Improvement | 09/17/2009 | 09/26/2009 | 11/01/2009 | 362028 | 3.564
5239 | Michigan | MANISTEE |  | 2 | 0951309 | The Mainistee County Road Commission will resurface 1 miles of Stronach Rd from US-31 to Grant south of the the City of Manistee. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/17/2009 | 09/26/2009 | 11/01/2009 | 80000 | 0.927
5240 | Michigan | MARQUETTE |  | 1 | 0952006 | This pavement project on US-41 in the City of Marquette will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 |  | 514103.68 | 2.056
5241 | Michigan | MARQUETTE |  | 1 | 0952007 | This pavement resurfacing and rumble strip project on US-41 in the City of Marquette will improve safety and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/18/2010 | 474775.03 | 1.93
5242 | Michigan | MARQUETTE |  | 1 | 0952009 | This roundabout project in Marquette County at the intersection of US-41/M-28 and Front Street will improve safety. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 10/21/2011 | 3260244.55 | 4.224
5243 | Michigan | MARQUETTE |  | 1 | 0952014 | This paving project on County Road 557 in Marquette County will improve the drive quality and make the road smoother. | Pavement Improvement | 09/28/2009 | 06/21/2010 | 08/01/2010 | 652694.59 | 2.207
5244 | Michigan | MARQUETTE |  | 1 | 0952016 | This pavement project on Champion Street in the City of Marquette will improve the drive quality and make the road smoother. | Pavement Improvement | 08/28/2009 | 09/08/2009 | 08/15/2010 | 465000 | 0.36
5245 | Michigan | MARQUETTE |  | 1 | 0952020 | This pavement project on M-94 in Marquette County will improve the drive quality and make the road smoother. | Pavement Improvement | 08/04/2009 | 08/04/2009 |  | 730059.32 | 9.499
5246 | Michigan | MARQUETTE |  | 1 | 0952025 | This pavement project on M-28 BR in the City of Ishpeming will improve the drive quality and make the road smoother. | Pavement Improvement | 05/11/2009 | 05/11/2009 |  | 440452.63 | 3.901
5247 | Michigan | MASON |  | 2 | 0953021 | MDOT will resurface 0.5 miles of US-10 at Dowland St in the vicinity of the Lake Michigan Car Ferry in Ludington. This will improve the driving quality by making the road smoother and provide better | Pavement Improvement | 06/04/2009 | 06/04/2009 | 05/05/2011 | 369730.05 | 0.47
5248 | Michigan | MASON |  | 2 | 0953024 | The City of Ludington will design improvements to 0.2 miles of South Williams St from Ludington Ave to Filer St in Ludington so as to improve the driving quality by making the road smoother. | Other | 08/18/2009 | 08/25/2009 | 06/25/2010 | 13248 | 0.144
5249 | Michigan | MECOSTA |  | 4 | 0954007 | The MDOT will resurface 2 miles of US-131BR/M-20 from US-131 east to Northland Drive near the City of Big Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 03/30/2010 | 440527.94 | 3.63
5250 | Michigan | MECOSTA |  | 4 | 0954008 | The MDOT will resurface 2 miles of US-131BR/M-20 from US-131 east to Northland Drive near the City of Big Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 03/30/2010 | 810015.65 | 4.356
5251 | Michigan | MECOSTA |  | 4 | 0954009 | The MDOT will make repairs to the bridge at Old State Road over US-131 near the Village of Stanwood to make the bridge last longer. | Bridge Improvement | 05/21/2009 | 05/21/2009 | 12/31/2010 | 597081.11 | 0
5252 | Michigan | MECOSTA |  | 4 | 0954010 | The Mecosta County Road Commission will resurface 20 Mile Road from 60th Ave to 50th Ave west of the Village of Barryton. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/24/2009 | 10/01/2009 | 11/14/2009 | 87420.72 | 1.008
5253 | Michigan | MECOSTA |  | 4 | 0954011 | Improvements will be made to guard rail on Arthur Road from 10th Avenue to Costabella Road west of the Village of Lake Isabella to improve safety. | Pavement Improvement | 06/24/2009 | 10/01/2009 | 11/14/2009 | 122015 | 1.002
5254 | Michigan | MECOSTA |  | 4 | 0954012 | The Mecosta County Road Commission will resurface Pierce Road from front St to 110th Ave in the village of Stanwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/24/2009 | 10/01/2009 | 11/14/2009 | 233284 | 7.333
5255 | Michigan | MIDLAND |  | 1,4,5 | 0956007 | Within the cities of Midland, Auburn and Bay, MDOT will be upgrading 16 bridge decks on US-10 from Sturgeon Road easterly to I-75 and on M-20/US-10BR from Saginaw Road easterly to Waldo Road to make t | Bridge Improvement | 05/29/2009 | 05/29/2009 | 04/11/2011 | 277823.6 | 0
5256 | Michigan | MIDLAND |  | 4 | 0956009 | The city of Midland will resurface 2.8 miles on Gordonville Road to improve the driving quality by making the road smoother. | Pavement Improvement | 07/24/2009 | 07/24/2009 | 10/30/2009 | 470000 | 9.392
5257 | Michigan | MIDLAND |  | 4 | 0956010 | In the city of Midland there is 17.20 miles of resurfacing on Smith Crossing Road, Freeland Road, Pine River Road, Nine Mile Road, Shepherd Road, Gordonville Road, Jefferson Road, Prairie Road, Eastma | Pavement Improvement | 07/30/2009 | 07/30/2009 | 10/30/2009 | 441633 | 8.757
5258 | Michigan | MIDLAND |  | 4 | 0956011 | The city of Midland will resurface 4.16 miles on M-20 from west of Meridian Road easterly to east of Vance Road to improve the driving quality by making the road smoother. | Pavement Improvement | 09/29/2009 | 09/29/2009 | 02/01/2012 | 1870540.38 | 4.015
5259 | Michigan | MISSAUKEE |  | 4 | 0957004 | The Missaukee Couth Road Commission willl resurface 5.5 miles of Falmouth/Hildebrand/Cadilac/Lucas Rds between M-66 and Dikerson Rd in the vicinity of Cadilac. This will improve the driving quality b | Pavement Improvement | 10/12/2009 | 10/19/2009 | 06/12/2010 | 277931.16 | 5.53
5260 | Michigan | MONROE | MONROE | 15 | 0958011 | 0.39 miles of pavement resurfacing on West 7th Street from Telegraph Road to Union Street in the city of Monroe, Monroe County. This project will improve pavement rideability and increase pavement sm | Pavement Improvement | 09/17/2009 | 10/05/2009 | 11/01/2009 | 154753.89 | 0.78
5261 | Michigan | MONROE | MONROE | 15 | 0958012 | 0.17 miles of pavement resurfacing on Riverview Avenue from Scottwood Street to Maywood Street in the city of Monroe, Monroe County. This project will improve pavement rideability and increase paveme | Pavement Improvement | 09/15/2009 | 09/28/2009 | 11/15/2009 | 184262.69 | 0.173
5262 | Michigan | MONTCALM |  | 4 | 0959004 | The MDOT will resurface seven and a half miles of M-91 from north of Colby Rd to north of Kedalville Rd near the village of Lakeview. This will improve the driving quality by making the road smoothe | Pavement Improvement | 06/22/2009 | 04/02/2009 | 11/14/2009 | 406541.43 | 7.455
5263 | Michigan | MONTCALM |  | 4 | 0959008 | The Moncalm County Road Commission will resurface South Youngman Rd from M-57 to Harlow Rd east of Greenville. This will improve the driving quality by making the road smoother. | Pavement Widening | 08/12/2009 | 08/13/2009 | 09/18/2009 | 94878.93 | 0.757
5264 | Michigan | MONTCALM |  | 4 | 0959009 | The MDOT will resurface seven miles of M-57 from Berridge Rd to east of M-66 near the City of Greenville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/26/2009 | 07/01/2009 | 03/30/2010 | 874005.49 | 7.053
5265 | Michigan | MONTCALM |  | 4 | 0959010 | The MDOT will resurface six miles of M-46 from US-131 to west of Amble Rd near the village of Lakeview. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/04/2009 | 06/04/2009 | 03/30/2010 | 746003.4 | 5.945
5266 | Michigan | MONTCALM |  | 4 | 0959011 | The Montcalm County Road Commission will resurface South Vickeryville Rd from Stanton Rd to Sidney Rd. near the village of Stanton. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/17/2009 | 09/22/2009 | 10/30/2009 | 440419.07 | 2.689
5267 | Michigan | MUSKEGON |  | 2 | 0961134 | The MDOT will make repairs to the bridge at Fruitport Rd over I-96 and the bridge at Russell Rd over US-31in Muskegon County to make the bridges last longer. | Bridge Improvement | 05/14/2009 | 05/14/2009 | 09/21/2011 | 1366446.88 | 0
5268 | Michigan | MUSKEGON |  | 2 | 0961135 | The MDOT will build a roundabout at M-37 and M-46 intersection and resurface M-37 from M-46 to Moon Rd for 2 miles west of the village of Casanovia to improve safety and road smoothness. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 06/01/2012 | 3570121.65 | 3.977
5269 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961138 | The City of Muskegon will resurface a half mile of Laketon Ave from Peck St to Wood St. This will improve driving quality by making the road smoother. | Pavement Improvement | 07/27/2009 | 08/18/2009 | 11/15/2009 | 800000 | 0.504
5270 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961139 | The City of Whitehall will resurface 3 tenths of a mile of Mears Ave from Lincoln Rd to Misco Drive. This will improve driving quality by making the road smoother. Needed utility work will also be d | Pavement Improvement | 09/03/2009 | 09/08/2009 | 10/16/2009 | 200000 | 0.285
5271 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961140 | The City of Montague will resurface a block of Old Channel Trail from Dowling St to Church St. This will improve driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 09/02/2009 | 09/30/2009 | 36539.31 | 0.073
5272 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961141 | The City of Montegue will resurface a one tenth of a mile of Dowling St from Meade St to Ferry St. This will improve driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 09/02/2009 | 12/31/2010 | 50000 | 0.111
5273 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961142 | The City of Muskegon will resurface 0.4 mile of Summit Ave from west of Henry St to Coolidge Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 08/31/2009 | 09/08/2009 | 12/31/2010 | 178180.36 | 0.355
5274 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961143 | The City of Norton Shores will resurface 0.8 miles of Pontaluna Rd Grand Haven Rd to Wood Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 08/25/2009 | 09/08/2009 | 12/31/2010 | 503211 | 0.769
5275 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0961150 | The City of North Muskegon will resurface 0.6 miles of Ruddiman Drive from Center St to Whitehall Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 02/16/2010 | 04/27/2010 | 05/28/2010 | 200000 | 0.599
5276 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963182 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Crooks Road in Oakland County. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 11/15/2009 | 802000 | 1.145
5277 | Michigan | OAKLAND | DETROIT,MI | 9,12 | 0963183 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Campbell Road in Madison Heights and Royal Oak. | Pavement Improvement | 05/14/2009 | 07/27/2009 | 11/29/2009 | 1153712.67 | 0.99
5278 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963184 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Orchard Lake Road in Oakland County. | Pavement Improvement | 07/31/2009 | 08/18/2009 | 10/23/2009 | 415000 | 1.012
5279 | Michigan | OAKLAND |  | 9 | 0963185 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Square Lake Road in Bloomfield Township by MDOT. | Pavement Improvement | 05/15/2009 | 05/15/2009 | 05/05/2011 | 5680132.89 | 2.563
5280 | Michigan | OAKLAND | DETROIT,MI | 12 | 0963196 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of 10 Mile Road in Oakland County. | Pavement Improvement | 08/10/2009 | 08/13/2009 | 10/09/2009 | 512000 | 0.536
5281 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963197 | Resurfacing to maintain the pavement condition and improve ride quality of Rochester Road in Clawson. | Pavement Improvement | 07/31/2009 | 08/17/2009 | 10/02/2009 | 350000 | 0.51
5282 | Michigan | OAKLAND | DETROIT,MI | 9,10 | 0963199 | 5.6 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along M-59 in Rochester Hills by MDOT. | Pavement Widening | 06/02/2009 | 06/02/2009 | 09/19/2012 | 56520048.71 | 11.892
5283 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963208 | 2 miles of resurfacing to maintain the pavement condition and improve ride quality of M-59 in Pontiac. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 06/30/2012 | 10981306.51 | 6.259
5284 | Michigan | OAKLAND | DETROIT,MI | 12 | 0963209 | Resurfacing to maintain the pavement condition and improve ride quality of East Progress Drive in Madison Heights by MDOT. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 12/15/2010 | 410072.35 | 0.832
5285 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963211 | Two miles of resurfacing to maintain the pavement condition and improve ride quality of Orchard Lake Road in Oakland County. | Pavement Improvement | 09/03/2009 | 09/08/2009 | 06/15/2010 | 1749000 | 2.095
5286 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963212 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Crooks Road in Oakland County. | Pavement Improvement | 08/28/2009 | 09/10/2009 | 06/15/2010 | 879000 | 1.235
5287 | Michigan | OAKLAND | DETROIT,MI | 11 | 0963215 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Novi Road in Novi. | Pavement Improvement | 09/10/2009 | 09/16/2009 | 11/02/2009 | 827000 | 1.004
5288 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963220 | 2 miles of concrete pavement repairs to maintain the pavement condition and improve ride quality of Halsted Road in Farmington Hills. | Pavement Improvement | 07/22/2009 | 07/22/2009 | 09/25/2010 | 1199136.89 | 1.622
5289 | Michigan | OAKLAND | DETROIT,MI | 11 | 0963224 | Resurfacing to maintain the pavement condition and improve ride quality of Nine Mile Road in Novi. | Pavement Improvement | 09/24/2009 | 10/03/2009 | 06/15/2010 | 328000 | 1.026
5290 | Michigan | OAKLAND | DETROIT,MI | 11 | 0963225 | Three miles of resurfacing to maintain the pavement condition and improve ride quality of Meadowbrook Road in Novi. | Pavement Improvement | 09/24/2009 | 10/03/2009 | 06/15/2010 | 340000 | 1
5291 | Michigan | OAKLAND | DETROIT,MI | 9,11 | 0963226 | Resurfacing to maintain the pavement condition and improve ride quality of Nine Mile Road in Novi. | Pavement Improvement | 09/24/2009 | 10/03/2009 | 06/15/2010 | 340000 | 1.038
5292 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963239 | Bridge replacement to improve safety and maintain mobility of Opdyke Road over M-59 in Pontiac by MDOT. | Bridge Improvement | 08/18/2009 | 08/18/2009 | 12/31/2010 | 2808245.99 | 0
5293 | Michigan | OAKLAND | DETROIT,MI | 9 | 0963240 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Cass Avenue in Pontiac by MDOT. | Pavement Improvement | 07/09/2009 | 07/09/2009 | 05/05/2011 | 1832013.03 | 1.183
5294 | Michigan | OAKLAND | DETROIT,MI | 9,12 | 0963264 | One mile of resurfacing to maintain the pavement condition and improve ride quality of John R Road in Troy. | Pavement Improvement | 02/04/2010 | 04/01/2010 | 07/02/2010 | 837000 | 1.028
5295 | Michigan | OCEANA |  | 2 | 0964332 | The MDOT will make repairs to the bridge at Taylor Rd over US-131 in Oceana County to make the bridge last longer. | Bridge Improvement | 05/29/2009 | 05/29/2009 | 03/31/2011 | 670924.26 | 0
5296 | Michigan | OCEANA |  | 2 | 0964340 | The Oceana County Rd Commission will resurface 3 miles of West Shelby Rd from 52nd Ave to 40th Ave west of the Village of Shelby. This will improve the driving quality of the raodway | Other | 02/26/2010 | 05/03/2010 | 05/28/2010 | 446345 | 3.026
5297 | Michigan | OGEMAW |  | 1 | 0965009 | MDOT will repair 10.6 miles of I-75 from the south Ogemaw County line to Cook Rd and from Ski Park Rd to the north county linein Ogemaw County to extend the service life of the existing roadway. | Pavement Improvement | 12/30/2008 | 12/30/2008 | 06/18/2009 | 897731.5 | 11.057
5298 | Michigan | OGEMAW |  | 1 | 0965010 | MDOT will design repairs to drainage culverts along I-75 in Ogemaw County to improve drainage and extend the life of the roadway drainage structures. | Other | 04/23/2009 | 04/23/2009 |  | 9046.69 | 10.034
5299 | Michigan | OGEMAW |  | 1 | 0965011 | MDOT will fix drainage culverts along I-75 in Ogemaw County to improve drainage and extend the life of the roadway drainage structures. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 06/01/2010 | 1105824.92 | 10.034
5300 | Michigan | ONTONAGON |  | 1 | 0966008 | This paving project on M-64 from Silver City to The City of Ontonagon will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2009 | 04/02/2009 | 10/18/2010 | 2576015.29 | 11.84
5301 | Michigan | OSCEOLA |  | 4 | 0967010 | MDOT will design the resurfacing of 2 miles of US-10 from the west county line of Osceola to the US-131 interchange in the vicinity of Reed City. This will improve the driving quality by making the | Other | 04/29/2009 | 04/29/2009 |  | 46696.66 | 1.89
5302 | Michigan | OSCEOLA |  | 4 | 0967011 | MDOT will resurface 2 miles of US-10 from the west county line of Osceola to the US-131 interchange in the vicinity of Reed City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 03/03/2011 | 1255464.1 | 1.89
5303 | Michigan | OSCEOLA |  | 4 | 0967015 | The Osceola County Road Commission will resurface 4 and a quarter miles of 200th Ave from 20 Mile Rd to the county line in the vicinity of the village of Tustin. This will improve the driving quality | Other | 07/29/2009 | 10/27/2009 | 07/31/2010 | 146233 | 4.263
5304 | Michigan | OSCODA |  | 1 | 0968003 | The Oscoda County Road Commission will replace the bridge on Waterwheel Court over Big Creek to improve safety and increase mobility. | Bridge Replacement | 09/23/2009 | 03/17/2010 | 08/30/2010 | 87616.5 | 0.309
5305 | Michigan | OTSEGO |  | 1 | 0969014 | MDOT will resurface 5 miles of M-32 from east of Krys Rd to Turtle Lake Rd east of Gaylord. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 10/08/2009 | 385285.55 | 9.855
5306 | Michigan | OTSEGO |  | 1 | 0969016 | The Otsego County Road Commission will reconstruct 1.5 miles of Charles Brink Rd from E of Championship Dr to Opal Lake Rd in the vicinity of Otsego Lake. This will improve the driving quality by mak | Other | 09/18/2009 | 09/21/2009 | 11/13/2009 | 331098 | 1.565
5307 | Michigan | OTTAWA | HOLLAND | 2 | 0970019 | Almost 2 miles of Lakewood Blvd from River Ave to 120th Ave will be resurfaced in Holland Township. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/25/2009 | 07/01/2009 | 07/31/2009 | 580277.36 | 1.704
5308 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 0970020 | Five miles of 48th Ave will be resurfaced near the City of Hudsonville and in Georgetown Township from Chicago Drive to Bauer Rd. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/26/2009 | 07/01/2009 | 08/14/2009 | 1145923.48 | 4.672
5309 | Michigan | OTTAWA |  | 2 | 0970022 | The City of Holland will resurface almost 2 miles of Lakewood Blvd from River Ave to 120th Ave. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/26/2009 | 07/01/2009 | 08/14/2009 | 440912.71 | 1.965
5310 | Michigan | OTTAWA |  | 2 | 0970024 | The MDOT will make repairs to the I-196 bridges over 48th St near the City of Grandville to make the bridges last longer. | Bridge Improvement | 04/28/2009 | 04/28/2009 | 12/31/2010 | 618074.05 | 0
5311 | Michigan | OTTAWA |  | 2 | 0970026 | The MDOT will resurface 6 miles of I-96 from M-104 to 68th Ave in the vicinity of Spring Lake. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 04/01/2011 | 1558066.92 | 11.106
5312 | Michigan | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0970034 | The Ottawa County Road Commission will resurface 2 miles of Lake michigann Dr from Lakeshore Ave to US-31. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/23/2009 | 07/30/2009 | 09/11/2009 | 344045.35 | 1.96
5313 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 0970037 | The MDOT will resurface 1 mile of I-196 BL from US-31 east to the Macatawa River near the City of Holland. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/09/2009 | 06/09/2009 | 03/30/2010 | 358122.14 | 1.355
5314 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 0970038 | The MDOT will resurface 9 miles of I-196 from 64th Ave to Kenowa Ave near Hudsonville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/10/2009 | 06/10/2009 | 03/30/2010 | 2406902.54 | 13.499
5315 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 0970039 | The MDOT will resurface 11 miles of M-45 from US-31 east to 68th Ave near the city of Grand Haven. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/10/2009 | 06/10/2009 | 03/30/2010 | 1428909.36 | 11.095
5316 | Michigan | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0970040 | The City of Grand Haven will resurface three quarters of a mile of Robbins Rd from just east of US-31 to Beechtree St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 09/22/2009 | 09/25/2009 |  | 230691 | 0.721
5317 | Michigan | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0970041 | The City of Spring Lake will resurface 0. 2 miles of West Springlake Rd from Smith's Bridge to Bayberry Dr. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/26/2009 | 09/08/2009 | 10/31/2009 | 200000 | 0.22
5318 | Michigan | OTTAWA |  | 2 | 0970044 | The MDOT will resurface a half mile of US-31 south bound from the Grand River bascule bridge to 3rd St including M-104 in the city of Ferrysburg. This will improve the driving quality by making the r | Pavement Improvement | 07/10/2009 | 07/10/2009 | 06/30/2010 | 264725.75 | 0.905
5319 | Michigan | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 2 | 0970051 | The City of Spring Lake will resurface 0. 2 miles of Jackson St at Exchange St and at West Savidge (M-104). This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/19/2010 | 04/05/2010 | 06/25/2010 | 183407.05 | 0.162
5320 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 0970053 | The MDOT will make repairs to the I-96 bridge over west bound M-11 near the City of Grand Rapids to make the bridge last longer. | Bridge Improvement | 02/16/2010 | 03/02/2010 | 12/31/2010 | 239412.06 | 0
5321 | Michigan | ROSCOMMON |  | 1,4 | 0972006 | The MDOT is upgrading the guard rail along 17.5 miles of US-127 in Roscommon County from Snow Bowl Rd north to I-75 to improve safety. | Safety/Traffic Management | 04/02/2009 | 04/02/2009 | 07/10/2009 | 232098.65 | 30.285
5322 | Michigan | SAGINAW | SAGINAW | 4 | 0973027 | In the city of Saginaw, MDOT is making repairs on M-46 to make the bridge last longer. | Bridge Improvement | 05/11/2009 | 05/11/2009 | 12/31/2010 | 984609.01 | 0
5323 | Michigan | SAGINAW | SAGINAW | 5 | 0973028 | Within the city of Saginaw, MDOT will reconstruct 1.20 miles of M-13 to improve the driving quality by making the road smoother. | Pavement Improvement | 05/29/2009 | 05/29/2009 | 09/19/2012 | 5609565.18 | 1.258
5324 | Michigan | SAGINAW | SAGINAW | 5 | 0973030 | The City of Saginaw is resurfacing 1.48 miles on Outer Drive to improve driving quality by making the road smoother. | Pavement Improvement | 08/14/2009 | 08/17/2009 | 11/13/2009 | 1844073 | 1.484
5325 | Michigan | SAGINAW |  | 4 | 0973033 | The City of Chesaning is resurfacing 7 miles on S Hemlock Road to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 80000 | 10.75
5326 | Michigan | SAGINAW |  | 4 | 0973034 | The Saginaw County Road Commission is resurfacing 5.105 miles on Ditch Road south of Chesaning to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 80716.1 | 5.105
5327 | Michigan | SAGINAW |  | 4,5 | 0973035 | The City of Frankenmuth is resurfacing 5.03 miles on S Dehmel Road to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 80000 | 4.949
5328 | Michigan | SAGINAW |  | 4,5 | 0973036 | The City of Bridgeport is resurfacing 5.37 miles on Busch Rd & Moorish Rd to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 85000 | 5.348
5329 | Michigan | SAGINAW |  | 4 | 0973037 | The Saginaw County Road Commission is resurfacing 3.9 miles on Fergus Road from Sharon Rd to Bishop Rd near the Village of St. Charles to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 67368.88 | 3.943
5330 | Michigan | SAGINAW |  | 4 | 0973038 | In Tittabawassee Township there is 5 miles of resurfacing on Mackinaw Rd & Lawndale Rd to improve driving quality by making the road smoother. | Pavement Improvement | 07/07/2009 | 07/13/2009 | 08/27/2009 | 80000 | 4.996
5331 | Michigan | SAGINAW | SAGINAW | 5 | 0973041 | In the city of Saginaw there will be 0.98 miles reconstruction on East Genesee Avenue from Franklin Street to Janes Street to improve the driving quality and make the road smoother. | Pavement Improvement | 12/22/2009 | 03/08/2010 | 09/18/2012 | 934074 | 0.427
5332 | Michigan | SAGINAW | SAGINAW | 5 | 0973042 | The city of Saginaw will beautify 0.45 miles along W Genesee Avenue. | Transportation Enhancements | 12/22/2009 | 03/08/2010 | 09/18/2012 | 510000 | 0.427
5333 | Michigan | SAGINAW | SAGINAW | 5 | 0973051 | The city of Saginaw will reconstruct 0.51 miles on North Woodbridge Street from Houghton Avenue to Davenport Avenue to improve the driving quality by making the road smoother. | Other | 02/01/2010 | 04/26/2010 | 10/23/2010 | 400000 | 0.555
5334 | Michigan | SAGINAW | SAGINAW | 4,5 | 0973053 | There is 15.39 miles of resurfacing on M-46 from Towerline Road easterly to west of M-15 and on M-84 from M-58 (State Street) northerly to north of Pierce Road to improve the driving quality by making | Pavement Improvement | 09/16/2009 | 09/16/2009 | 02/01/2012 | 3374881.08 | 15.434
5335 | Michigan | SANILAC |  | 10 | 0974004 | North of Port Sanilac, MDOT is upgrading 6.8 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 05/29/2009 | 05/29/2009 | 03/31/2010 | 402983.46 | 6.824
5336 | Michigan | SCHOOLCRAFT |  | 1 | 0975013 | This shoulder paving project on County Road 498 in Schoolcraft County will improve safety. | Pavement Improvement | 05/11/2009 | 07/27/2009 | 09/30/2009 | 91271 | 3.958
5337 | Michigan | SCHOOLCRAFT |  | 1 | 0975014 | This shoulder paving project on Thunder Lake Road in Schoolcraft County will improve safety. | Pavement Improvement | 05/11/2009 | 08/17/2009 | 11/15/2009 | 91680 | 10.314
5338 | Michigan | SCHOOLCRAFT |  | 1 | 0975016 | This shoulder paving project on County Road 436 in Schoolcraft County will improve safety. | Pavement Improvement | 09/01/2009 | 09/16/2009 | 09/30/2010 | 94000 | 2.998
5339 | Michigan | SHIAWASSEE |  | 8 | 0976208 | Near the city of Perry in Shiawausee county, MDOT will improve the driving surface of nearly 8 miles of I-96 with a resurfacing project. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 06/16/2011 | 3682328.68 | 15.748
5340 | Michigan | SHIAWASSEE |  | 4 | 0976211 | 0.2 of a mile of pavement resurfacing of East King Street from North Dewey Street to North Gould Street, in the city of Owosso, Shiawausee County. This project will improve pavement rideability and i | Pavement Improvement | 08/28/2009 | 10/02/2009 | 11/01/2009 | 100000 | 0.25
5341 | Michigan | SHIAWASSEE |  | 4 | 0976212 | 0.14 miles of pavement resurfacing of North Park Street from M-21 to Mason Street, in the city of Owosso, Shiawausee County. This project will improve pavement rideability and increase pavement smoot | Pavement Improvement | 08/28/2009 | 10/02/2009 | 11/01/2009 | 100000 | 0.135
5342 | Michigan | SHIAWASSEE |  | 4 | 0976213 | 0.24 miles of pavement resurfacing on Maple Street from M-71 to Main Street near the City of Durand, Shiawausee County. Improvements will enhance pavement rideability and increase pavement smoothness | Pavement Improvement | 09/25/2009 | 09/28/2009 | 11/30/2009 | 52000 | 0.244
5343 | Michigan | ST CLAIR | PORT HURON | 10 | 0977015 | The Michigan Department of Transportation will realign and make improvements to numerous local streets that cross under the Blue Water Bridge in Port Huron. The project will improve local traffic move | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2011 | 845737.52 | 0.618
5344 | Michigan | ST CLAIR | PORT HURON | 10 | 0977029 | 0.3 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along Collard Drive in Marysville. | Pavement Improvement | 01/06/2010 | 06/15/2010 | 05/30/2011 | 409478.11 | 0.288
5345 | Michigan | ST CLAIR |  | 10 | 0977031 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Dryden Road in St. Clair County. | Pavement Improvement | 09/03/2009 | 10/21/2009 | 10/30/2009 | 213948 | 1.031
5346 | Michigan | ST CLAIR | PORT HURON | 10 | 0977035 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of Riverside Drive in Port Huron. | Pavement Improvement | 08/25/2009 | 09/03/2009 | 10/30/2009 | 279566.02 | 0.573
5347 | Michigan | ST CLAIR | PORT HURON | 10 | 0977040 | 10 miles of resurfacing to maintain the pavement condition and improve ride quality of M-25 in St. Clair by MDOT. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 04/11/2011 | 6151432.86 | 10.708
5348 | Michigan | ST CLAIR |  | 10 | 0977042 | Bridge replacement to improve safety and maintain mobility of I-94 over the Belle River in St. Clair County by MDOT. | Bridge Replacement | 12/02/2009 | 12/02/2009 | 10/08/2012 | 6367926.51 | 0
5349 | Michigan | ST CLAIR |  | 10 | 0977044 | 3.6 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty on I-94 in St. Clair County. | Pavement Improvement | 08/20/2009 | 08/20/2009 | 10/08/2012 | 19069337.86 | 4.479
5350 | Michigan | TUSCOLA |  | 5 | 0979010 | MDOT is upgrading 6.0 miles to create a paved pathway on M-15 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 06/02/2009 | 06/02/2009 | 03/31/2010 | 417499.15 | 6.047
5351 | Michigan | TUSCOLA |  | 5 | 0979014 | In the village of Mayville, Tuscola County there will be 0.20 miles of roadway reconstruction on Industrial Park Road at M-24 to improve the driving quality and make the road smoother. | Pavement Improvement | 09/28/2009 | 10/05/2009 | 06/01/2010 | 50000 | 0.12
5352 | Michigan | VAN BUREN |  | 6 | 0980009 | "The City of Hartford will resurface 0.5 miles of W. Main Street from the city limits to Center Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/20/2009 | 09/21/2009 | 07/27/2011 | 180000 | 0.501
5353 | Michigan | VAN BUREN |  | 6 | 0980013 | "The village of Decatur will resurface 0.4 miles of N. Phelps Street (CR 653) from the village limits to Cedar Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 08/28/2009 | 09/16/2009 | 05/28/2010 | 295294.75 | 0.417
5354 | Michigan | VAN BUREN |  | 6 | 0980020 | "The village of Paw Paw will resurface 0.9 miles of East Michigan Avenue from the E. village limits to Kalamazoo Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 10/02/2009 | 10/09/2009 | 11/15/2009 | 135000 | 0.933
5355 | Michigan | WASHTENAW |  | 7 | 0981027 | 5.50 miles of pavement resurfacing on I-94 from the Freer Road easterly to Parker Road, west of Ann Arbor in Washtenaw County. This project includes ramp reconstruction, drainage improvements and fre | Pavement Improvement | 05/14/2009 | 05/14/2009 | 12/31/2012 | 15786139.57 | 11
5356 | Michigan | WASHTENAW |  | 7 | 0981028 | 6.62 miles of pavement resurfacing on I-94 from the west Washtenaw County line easterly to Freer Road. This project includes ramp reconstruction, drainage improvements and freeway shoulder widening. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 12/31/2012 | 3450852.92 | 13.24
5357 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981031 | 0.35 miles of pavement resurfacing and drainage improvements on North Ann Arbor Street from US-12 to Bennett Street in the City of Saline, Washtenaw County. | Pavement Improvement | 08/04/2009 | 08/31/2009 | 10/02/2009 | 210000 | 0.35
5358 | Michigan | WASHTENAW | ANN ARBOR | 15 | 0981035 | Throughout Washtenaw County the cracks in the pavement will be sealed to extend the life of the pavement. | Pavement Improvement | 07/29/2009 | 09/01/2009 | 09/01/2010 | 27220 | 7.795
5359 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981036 | 6.56 miles of roadway will be resurfaced in Washtenaw county, north of the City of Ann Arbor at multiple locations. North Territorial Road from Webster Church to Whitmore Lake, North Territorial Road | Pavement Improvement | 07/29/2009 | 07/29/2009 | 09/01/2010 | 616691.99 | 6.146
5360 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 0981037 | 5.44 miles of pavement repair in the city of Ann Arbor area. This project will provide for improved rideability and increased pavement smoothness on Jackson Road from Honey Creek Drive to Wagner Road | Pavement Improvement | 07/29/2009 | 01/06/2010 | 08/01/2010 | 88259.15 | 5.435
5361 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 0981038 | 11 miles of pavement resurfacing at various locations thourghout Washtenaw County to improve pavement rideability and pavement smoothness. Locations include Ann Arbor Road from Zeeb Road to West Ann | Pavement Improvement | 07/29/2009 | 04/28/2010 | 09/01/2010 | 1007882.17 | 13.065
5362 | Michigan | WASHTENAW | ANN ARBOR | 15 | 0981039 | 2.36 miles of Loer Road from Textile Road to W Ellsworth Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, south of the City of Ann Arb | Pavement Improvement | 07/29/2009 | 09/01/2009 | 09/01/2010 | 43026 | 2.364
5363 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981040 | 2.43 miles of pavement resurfacing on Huron River Drive along the scenic Huron River between the Village of Dexter and the City of Ann Arbor in Washtenaw County. Improvements will provide for increas | Pavement Improvement | 07/29/2009 | 07/20/2009 | 09/01/2010 | 250000 | 2.426
5364 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981042 | 2.0 miles of Baker Road from I-94 to Dan Hoey Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, West of the City of Ann Arbor in Washte | Pavement Improvement | 08/04/2009 | 09/01/2009 | 09/01/2010 | 49700 | 2.055
5365 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 0981043 | 1.78 miles of Ann Arbor-Saline Road from Oak Valley Drive to Maple Road and Maple Road from Ann Arbor-Saline Road to Saline City limits will have a Chip and Seal treatment to preserve pavement life an | Pavement Improvement | 08/04/2009 | 09/01/2009 | 09/01/2010 | 82098 | 1.778
5366 | Michigan | WASHTENAW | ANN ARBOR | 7 | 0981044 | 2.0 miles of Dexter Ann Arbor Road from Dan Hoey Road to Zeeb Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, West of the City of Ann | Pavement Improvement | 08/04/2009 | 09/01/2009 | 09/01/2010 | 48887 | 2.112
5367 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 0981050 | 2.23 miles of Miller Road from Dexter Ann Arbor Road to Wagner Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, west of the City of An | Pavement Improvement | 08/13/2009 | 09/01/2009 | 09/01/2010 | 59628 | 2.229
5368 | Michigan | WASHTENAW | ANN ARBOR | 15 | 0981061 | This project will provide for traffic signal upgrades on Packard Road from the East Eisenhower Parkway to East Stadium Blvd. This work will improve traffic safety, ease congestion and increase traffi | Safety/Traffic Management | 09/21/2009 | 03/15/2010 | 06/15/2010 | 185242.62 | 1.309
5369 | Michigan | WAYNE | DETROIT,MI | 11 | 0982054 | MDOT will repair and resurface . 9 miles of US-24 in Redford Township in Wayne County to improve driving quality and increase service life | Pavement Improvement | 05/14/2009 | 05/14/2009 | 12/31/2011 | 1002797.53 | 0.921
5370 | Michigan | WAYNE | DETROIT,MI | 15 | 0982055 | MDOT will resurface .8 miles of US-24 in the City of Flat Rock to improve the driving quality and extend the service life of the road | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/01/2009 | 360996.73 | 0.816
5371 | Michigan | WAYNE | DETROIT,MI | 14 | 0982057 | MDOT will landscape and replace fence on . 6 miles of I-75 in the City of Hamtamck Wayne County which will beautify the drive and make it safer. | Transportation Enhancements | 05/14/2009 | 05/14/2009 | 09/19/2011 | 686902.79 | 1.553
5372 | Michigan | WAYNE | DETROIT,MI | 13,14 | 0982058 | MDOT will rehabilitate 7 bridges in the City of Detroit on I-96 to make the bridges last longer | Bridge Improvement | 05/14/2009 | 05/14/2009 | 12/31/2011 | 11733244.14 | 0
5373 | Michigan | WAYNE | DETROIT,MI | 13 | 0982059 | MDOT will repair the I-96 under Underwood Avenue bridge in the City of Detroit to make the bridge last longer | Bridge Improvement | 05/14/2009 | 05/14/2009 | 12/17/2010 | 1179301.38 | 0
5374 | Michigan | WAYNE | DETROIT,MI | 14 | 0982060 | MDOT will rehabilitate 3 bridges in the City of Detroit on I-96 to make the bridges last longer | Bridge Improvement | 05/19/2009 | 05/19/2009 | 12/31/2010 | 3918931.54 | 0
5375 | Michigan | WAYNE | DETROIT,MI | 11 | 0982061 | The City of Westland will reconstruct the Newburgh and Warren intersection in the City of Westland to improve the driving quality and safety | Pavement Improvement | 05/19/2009 | 05/19/2009 | 07/31/2010 | 681745.36 | 0.005
5376 | Michigan | WAYNE | DETROIT,MI | 14 | 0982064 | MDOT is removing 2 railroad bridges over I-96 in the City of Detroit because they are no longer used | Bridge Improvement | 05/21/2009 | 05/21/2009 | 12/31/2010 | 1013288.99 | 0
5377 | Michigan | WAYNE | DETROIT,MI | 11,15 | 0982066 | 1 mile of Warren Road in the City of Dearborn Heights will be resurfaced by Wayne County to improve the driving quality and increase the road service life | Pavement Improvement | 05/21/2009 | 05/21/2009 | 09/14/2010 | 937323.29 | 0.994
5378 | Michigan | WAYNE | DETROIT,MI | 15 | 0982067 | MDOT will construct a sound will at I-96 and US-24 to reduce road sounds to adjacent properties | Other | 05/29/2009 | 05/29/2009 | 09/20/2012 | 4339421.51 | 1.615
5379 | Michigan | WAYNE | DETROIT,MI | 13 | 0982076 | The City of Grosse Point will resurface .4 miles of St Clair Road to improve driving quality and increase road service life | Pavement Improvement | 07/31/2009 | 08/22/2009 | 10/30/2009 | 324883.76 | 0.388
5380 | Michigan | WAYNE | ANN ARBOR | 11 | 0982082 | MDOT will repair and resurface the ramps on I-94 at Belleville road in Van Buren Township Wayne County to improve the driving quality and increase service life | Pavement Improvement | 06/04/2009 | 06/04/2009 | 12/31/2010 | 637939.76 | 0.944
5381 | Michigan | WAYNE | STATEWIDE | 11 | 0982083 | MDOT will repair and resurface the ramps on I-94 at Haggerty Road in Van Buren Township Wayne County to improve the driving quality and increase service life | Pavement Improvement | 06/04/2009 | 06/04/2009 | 12/31/2010 | 589436.5 | 0.839
5382 | Michigan | WAYNE |  | 11 | 0982098 | MDOT will repair and resurface 6.3 miles of non motorized path along I-275 in Wayne County for cyclists, walkers and joggers to promote alternate modes of transportation | Transportation Enhancements | 04/01/2009 | 04/01/2009 | 03/12/2012 | 4559455.12 | 12.53
5383 | Michigan | WAYNE | DETROIT,MI | 13 | 0982100 | The City of Grosse Point Shores will resurface .4 miles of Vernier Road to improve driving quality and increase service life | Pavement Improvement | 07/07/2009 | 10/14/2009 | 08/31/2010 | 263330.54 | 0.364
5384 | Michigan | WAYNE | DETROIT,MI | 14 | 0982108 | MDOT will replace pumping equipment on I-94 in the City of Dearborn Wayne County to insure rainwater will not interfere with traffic | Pavement Improvement | 07/21/2009 | 07/21/2009 | 12/31/2010 | 1032329.78 | 0.324
5385 | Michigan | WAYNE | DETROIT,MI | 14 | 0982113 | MDOT will rehabilitate the M-8 under Joseph Campau bridge to make the bridge last longer | Bridge Improvement | 09/16/2009 | 09/16/2009 | 12/31/2011 | 1724905.14 | 0.226
5386 | Michigan | WAYNE | DETROIT,MI | 14 | 0982114 | MDOT will repair the M-8 under Charest Avenue walkover bridge to make the bridge last longer | Bridge Improvement | 05/11/2009 | 05/11/2009 | 12/31/2011 | 194264.47 | 0.048
5387 | Michigan | WAYNE | DETROIT,MI | 14 | 0982115 | MDOT will rehabilitate the M-8 under Goddard Avenue bridge to make the bridge last longer | Bridge Improvement | 07/24/2009 | 07/24/2009 | 12/31/2011 | 1714610.1 | 0.262
5388 | Michigan | WAYNE | DETROIT,MI | 14 | 0982116 | MDOT will resurface 1.4 miles of M-8 in the City of Detroit to improve driving quality and extend service life of the road | Pavement Improvement | 07/24/2009 | 07/24/2009 | 12/31/2011 | 12458747.68 | 2.722
5389 | Michigan | WAYNE | DETROIT,MI | 14 | 0982117 | MDOT will rehabilitate 5 bridges on M-8 to make the bridges last longer | Bridge Improvement | 09/16/2009 | 09/16/2009 | 12/31/2011 | 583657.03 | 0
5390 | Michigan | WAYNE | DETROIT,MI | 11 | 0982121 | Wayne County will resurface .5 Miles of Merriman Road in the Cities of Westland and Livonia to improve driving quality and increase service life | Pavement Improvement | 07/29/2009 | 12/18/2009 | 10/01/2010 | 795644.91 | 0.516
5391 | Michigan | WAYNE | DETROIT,MI | 11 | 0982122 | The City of Livonia will resurface .5 miles of Lyndon Road to improve driving quality and increase service life | Pavement Improvement | 07/29/2009 | 11/17/2009 | 08/30/2010 | 675000 | 0.502
5392 | Michigan | WAYNE | DETROIT,MI | 13 | 0982123 | Wayne County will resurface .6 miles of 7 Mile Road to improve driving quality and increase service life | Pavement Improvement | 07/30/2009 | 07/30/2009 | 10/01/2010 | 653456.8 | 0.625
5393 | Michigan | WAYNE | DETROIT,MI | 15 | 0982124 | MDOT will repair and resurface .4 miles of US-12 in the City of Dearborn to improve the driving quality and increase service life | Pavement Improvement | 05/11/2009 | 05/11/2009 | 12/31/2011 | 2449807.27 | 3.025
5394 | Michigan | WAYNE | DETROIT,MI | 13 | 0982130 | MDOT will install an active speed warning system on the I-94 Ebd ramp to I-96 in the City of Detroit which will improve safety | Safety/Traffic Management | 10/06/2009 | 06/01/2010 | 11/15/2012 | 476061.37 | 0.07
5395 | Michigan | WAYNE | DETROIT,MI | 13 | 0982131 | MDOT will install an active speed warning system on the I-94 Wbd ramp to I-96 in the City of Detroit which will improve safety | Safety/Traffic Management | 10/06/2009 | 06/01/2010 | 11/15/2012 | 395535.08 | 0.108
5396 | Michigan | WAYNE | DETROIT,MI | 13 | 0982136 | MDOT will repair 2 railroad bridges over M-85 in the City of Detroit to make the bridges last longer | Bridge Improvement | 05/11/2009 | 05/11/2009 | 12/17/2010 | 910284.81 | 0
5397 | Michigan | WAYNE | DETROIT,MI | 14 | 0982141 | MDOT will repair and resurface 6 miles of M-39 in the cities of Detroit and Dearborn to improve driving quality and increase service life | Pavement Improvement | 08/11/2009 | 08/11/2009 | 12/31/2011 | 3122660.9 | 11.939
5398 | Michigan | WAYNE | DETROIT,MI | 14 | 0982152 | The City of Detroit is resurfacing portions of Seven Mile, Conner, McNichols, East Vernor, Mt Elliot, Mack and Warren Roads to improve driving quality and increase service life | Pavement Improvement | 08/20/2009 | 08/20/2009 | 11/02/2010 | 4562400.24 | 0.36
5399 | Michigan | WAYNE | DETROIT,MI | 13,14 | 0982153 | The City of Detroit is resurfacing portions of E. Congress, E. Lafayette, E. Larned, Clark, Chicago and Puritan Roads to improve driving quality and increase service life | Pavement Improvement | 08/20/2009 | 04/15/2010 | 11/02/2010 | 2870051.21 | 6.576
5400 | Michigan | WAYNE | DETROIT,MI | 14 | 0982154 | The City of Detroit is resurfacing portions of Meyers, Burt, Southfield Service Drive, Lodge Service Drive and Livernois Roads to improve driving quality and increase service life | Pavement Improvement | 08/20/2009 | 03/03/2010 | 11/02/2010 | 3942896.29 | 7.267
5401 | Michigan | WAYNE | DETROIT,MI | 11,15 | 0982170 | Wayne County will resurface 1.5 Miles of Middlebelt Road in the City of Romulus to improve driving quality and increase service life | Pavement Improvement | 09/09/2009 | 09/09/2009 | 10/01/2010 | 1558682.52 | 1.501
5402 | Michigan | WAYNE | DETROIT,MI | 11 | 0982173 | Wayne County will will reconstruct and widen to 5 lanes 1.4 miles of Canton Center Road in Canton Township to improve safety and ease congestion | Pavement Widening | 09/16/2009 | 09/16/2009 | 10/01/2010 | 3867492 | 1
5403 | Michigan | WEXFORD |  | 2 | 0983019 | The MDOT is replacing the US-131 bridge over the Manistee River in the City of Manistee to improve safety and increase mobility. | Bridge Replacement | 06/04/2009 | 06/04/2009 | 07/02/2010 | 168088.04 | 0.11
5404 | Michigan | STATEWIDE |  | 3,4 | 0984075 | The MDOT is undertaking areawide pavement repairs on 14 miles of roadway in Howard City area to improve the pavement condition and extend pavement life. | Pavement Improvement | 04/28/2009 | 04/28/2009 | 11/14/2009 | 202569.95 | 19.42
5405 | Michigan | STATEWIDE |  | 2 | 0984076 | The MDOT is undertaking areawide pavement repairs on nearly 18 miles of roadway in the Grand Region area to improve the pavement condition and extend pavement life. | Pavement Improvement | 05/05/2009 | 05/05/2009 | 06/30/2010 | 289336.54 | 23.773
5406 | Michigan | STATEWIDE |  | 1 | 0984084 | The 8 weather towers, called an Environmental Sensor Station are designed to aid motorists and the Michigan Department of Transportation (MDOT), and are expected to be particularly helpful in the wint | Safety/Traffic Management | 05/05/2009 | 05/05/2009 | 10/30/2009 | 1050920.77 | 1.6
5407 | Michigan | STATEWIDE | DETROIT,MI | 13 | 0984088 | Throughout the Detroit Metropolitan Freeway System the automated traffic control system will receive upgrades to its equipment. This will lessen freeway congestion and improve safety. | Other | 06/04/2009 | 06/04/2009 | 12/31/2015 | 7000000 | 0
5408 | Michigan | GRAND TRAVERSE |  | 1,2,4 | 0984100 | MDOT will repair 27 miles of M-37, US-131, and US-31 at various locations in Grand Traverse Countyto extend the service life of the existing roadways. | Pavement Improvement | 04/17/2009 | 04/17/2009 |  | 166934.78 | 27.206
5409 | Michigan | STATEWIDE |  | 1 | 0984103 | At numerous Statewide locations along US-23 and M-55 the guardrail will be replaced with upgraded guardrail to improve safety | Safety/Traffic Management | 06/17/2009 | 06/17/2009 | 05/28/2010 | 339789.51 | 29.15
5410 | Michigan | STATEWIDE |  | 1 | 0984107 | The weather tower and message sign project will consist of 12 Environmental Sensor Stations and 10 Dynamic Message Signs in 4 Counties and will improve safety and mobility. | Safety/Traffic Management | 07/07/2009 | 07/07/2009 | 12/01/2010 | 1542972.2 | 7.711
5411 | Michigan | STATEWIDE |  | 1,2,4 | 0984108 | The MDOT is installing environmental sensors in the North Region at various locations to monitor environmental conditions in the Region. | Safety/Traffic Management | 07/07/2009 | 07/07/2009 | 12/01/2010 | 1425543.8 | 13.966
5412 | Michigan | STATEWIDE | DETROIT,MI | 10,11 | 0984133 | Establishing a protective security fence around five towers in Oakland, Macomb and St. Clair Counties by MDOT. | Safety/Traffic Management | 08/17/2009 | 08/17/2009 | 11/15/2009 | 45999.75 | 0.001
5413 | Michigan | ALGER |  | 1 | 1002010 | This pavement project near Wetmore on road FF 13 at M28 S will smooth the road and improve ride quality | Pavement Improvement | 02/09/2010 | 05/01/2010 | 09/15/2010 | 51386 | 2.626
5414 | Michigan | ALGER |  | 1 | 1002012 | This project will improve safety by replacing the guardrail on M-94 Chatham to Munising in Alger County | Pavement Improvement | 05/11/2009 | 05/11/2009 | 08/27/2010 | 402646.4 | 10.2
5415 | Michigan | ALLEGAN | HOLLAND | 2 | 1003005 | The Allegan County Road Commisssion will resurface one mile of 40th Street from Washington Avenue to Lincoln Avenue, in the city of Holland. This will improve the driving quality by making the road | Pavement Improvement | 03/11/2010 | 03/29/2010 | 09/15/2010 | 797585 | 1.987
5416 | Michigan | ALLEGAN | HOLLAND | 2 | 1003007 | The Allegan County Road Commisssion will resurface 2.8 miles of 136th Avenue from 58th Street to Blue Star Highway just north of the ciy of Saugatuck in Allegan county. | Pavement Improvement | 03/26/2010 | 05/03/2010 | 07/01/2010 | 476387.5 | 2.785
5417 | Michigan | ALLEGAN |  | 6 | 1003008 | This 1.4 mile long pavement project on in Plainwell on Main Street from South City Limits to Norfolk Southern Rail will improve the drive quality and make the road smoother | Pavement Improvement | 04/29/2010 | 05/14/2010 | 06/15/2010 | 205000 | 1.252
5418 | Michigan | ALPENA |  | 1 | 1004003 | The Alpena County Road Commission will resurface 1.5 miles of Misery Bay Rd from the Lafarge property to the east city limits of Alpena. This will improve the driving quality by making the road smoot | Pavement Improvement | 02/26/2010 | 03/02/2010 | 06/30/2010 | 290000 | 0.764
5419 | Michigan | ANTRIM |  | 1 | 1005006 | This 8 mile long pavement project on E Torch Lake/Alden Rd/Comfort South County Line to M8 8will improve the drive quality and make the road smoother | Pavement Improvement | 04/22/2010 | 05/19/2010 | 06/30/2010 | 366683 | 8.679
5420 | Michigan | ARENAC |  | 1 | 1006005 | Arenac County will repave 3 miles of Turner Rd from Herr Rd-Tonkey Rd Arenac County | Pavement Improvement | 05/05/2010 | 06/21/2010 | 07/23/2010 | 234154 | 3.012
5421 | Michigan | BARAGA |  | 1 | 1007003 | This 1.6 mile long pavement project on Skanee Road in Baraga County will improve the drive quality and make the road smoother. | Pavement Improvement | 04/02/2010 |  | 08/22/2010 | 330310 | 1.525
5422 | Michigan | BARAGA |  | 1 | 1007004 | MDOT will relocate 1.6 miles of US-41 in rural Baraga County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/24/2010 | 02/24/2010 | 10/22/2010 | 2518599.21 | 1.621
5423 | Michigan | BARRY |  | 3 | 1008007 | This tenth mile long pavement project in Hastings on South Jefferson Street from Green Street to Grand Street will improve the drive quality and make the road smoother | Pavement Improvement | 04/27/2010 | 07/06/2010 | 08/27/2010 | 107000 | 0.126
5424 | Michigan | BARRY |  | 3 | 1008009 | This pavement project near Middleville on Finkbeiner Road from Cherry Valley Road to M-37 will make the pavement smoother and improve ride quality. | Pavement Improvement | 06/29/2010 | 07/06/2010 | 07/01/2011 | 950833.04 | 1.25
5425 | Michigan | BAY | BAY CITY | 5 | 1009009 | The City of Essexville will resurface 0.4 mile of Borton Ave from Caroline St to Scheurmann St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/29/2010 | 06/14/2010 | 07/30/2010 | 221319 | 0.392
5426 | Michigan | BAY | BAY CITY | 1,5 | 1009013 | This 2 mile long pavement project on Wilder Road from I-75 to M-13 and M-13 to Patterson Road in the City of Bay City will improve the drive quality and make the road smoother | Pavement Improvement | 04/28/2010 | 06/01/2010 | 08/13/2010 | 450000 | 4.042
5427 | Michigan | BAY | BAY CITY | 5 | 1009015 | This 2 mile long pavement project in Bay City on Truman Parkway/Woodside Avenue from Saginaw River to Woodside/McEwan will improve the drive quality and make the road smoother | Pavement Improvement | 04/28/2010 | 06/01/2010 | 08/13/2010 | 707085 | 0.657
5428 | Michigan | BAY |  | 1,5 | 1009016 | This pavement project near Bay City on S 7 Mile Rd from Hotchkiss Rd to Salzburg Rd will smooth the road and improve ride quality. | Pavement Improvement | 02/17/2010 | 06/01/2010 | 09/03/2010 | 306858.4 | 1.009
5429 | Michigan | BAY |  | 1,4,5 | 1009017 | This pavement project near Bay City on Hotchkiss Rd from 7 Mile Rd to Carter Rd will smooth the road and improve ride quality | Pavement Improvement | 02/17/2010 | 06/01/2010 | 07/31/2010 | 65887 | 4.871
5430 | Michigan | BENZIE |  | 2 | 1010003 | About 2 miles of County Road 708 from M22 to Platte River near the City of Honor in Benzie County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 02/10/2010 | 07/14/2010 | 07/30/2010 | 80303.64 | 2.146
5431 | Michigan | BENZIE |  | 2 | 1010004 | Aboutt 5 miles of River Rd from M22 to Benzonia West Village Limit in Benzie County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 02/10/2010 | 07/14/2010 | 07/30/2010 | 160452.36 | 5.241
5432 | Michigan | BENZIE |  | 2 | 1010009 | Benzie County will resurface six miles of N Manistee County Line Rd from US31 to Kurick Road | Other | 02/10/2010 | 07/14/2010 | 07/30/2010 | 23634 | 6.214
5433 | Michigan | BERRIEN |  | 6 | 1011003 | "The village of Eau Claire will resurface 0.84 miles of E. Main Street throughout the limits of the village. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/05/2010 |  | 06/18/2010 | 92500 | 0.837
5434 | Michigan | BERRIEN | BENTON HARBOR | 6 | 1011005 | The Allegan County Road Commisssion will resurface one mile of 40th Street from Washington Avenue to Lincoln Avenue, in the city of Holland. This will improve the driving quality by making the road | Pavement Improvement | 02/26/2010 | 03/29/2010 | 10/01/2010 | 671000 | 0.229
5435 | Michigan | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 1011007 | A quarter mile of Lake St from Fifth Street to Eleventh Street in the city of Niles will be repaved to improve smoothness and ride quality. | Pavement Improvement | 03/04/2010 | 04/26/2010 |  | 64677.93 | 0.289
5436 | Michigan | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 1011008 | The Berrien County Road Commisssion will resurface 0.63 miles of E. Main Street from Maple Street to 17th Street in the city of Niles. This will improve the driving quality by making the road smoother | Pavement Improvement | 03/04/2010 | 04/26/2010 |  | 163404.89 | 0.629
5437 | Michigan | BERRIEN | BENTON HARBOR | 6 | 1011013 | This quarter mile long pavement project in St. Joseph on Broad St from Lake Blvd. to State St. will improve the drive quality and make the road smoother | Pavement Improvement | 04/01/2010 | 04/19/2010 | 07/27/2011 | 42626 | 0.27
5438 | Michigan | BERRIEN |  | 6 | 1011014 | This 4 mile long pavement project in Berrien County on W Shawnee Rd from Burgoyne Road to Cleveland Avenue will improve the drive quality and make the road smoother | Pavement Improvement | 02/03/2010 | 06/01/2010 | 08/01/2010 | 47665.8 | 3.961
5439 | Michigan | BERRIEN |  | 6 | 1011015 | The Berrien County Road Commisssion will resurface 0.19 miles of North Main Street from Mars Street to Hamilton Street in the Niles metropolitan area. This will improve the driving quality by making | Pavement Improvement | 06/14/2010 | 06/21/2010 | 08/20/2010 | 92500 | 0.191
5440 | Michigan | BRANCH |  | 7 | 1012004 | The Branch County Road Commisssion will resurface 0.28 miles of North Michigan Avenue from Smith Street to Seeley Street in the city of Coldwater. This will improve the driving quality by making the | Pavement Improvement | 04/09/2010 | 05/14/2010 |  | 146979 | 0.278
5441 | Michigan | BRANCH |  | 7 | 1012005 | A pavement improvement project in Branch County near the city of Colwater on Central road from Bloack Road to South Angola Road and on Warren Road from Lake Drive to Fremont road will smooth the road | Pavement Improvement | 02/17/2010 | 07/26/2010 | 08/13/2010 | 93000 | 5.471
5442 | Michigan | CALHOUN | BATTLE CREEK | 7 | 1013012 | The Calhoun County Road Commission will resurface 0.8 miles of Meachem Road from Upton to Capital in the Battle Creek urbanized area. This will improve the driving quality by making the road smoother | Pavement Improvement | 04/28/2010 | 05/06/2010 |  | 189830.75 | 0.781
5443 | Michigan | CALHOUN | BATTLE CREEK | 7 | 1013013 | This half mile pavement project on Riverside Dr Burnham St. Territorial Rd. will improve the drive quality and make the road smoother | Pavement Improvement | 04/28/2010 | 05/06/2010 |  | 92237.61 | 0.288
5444 | Michigan | CALHOUN |  | 7 | 1013014 | This half mile long pavement project on Watson Street from Eaton to Maple Street in Albion will make the road smoother and improve ride quality. | Pavement Improvement | 03/25/2010 | 07/12/2010 |  | 185000 | 0.503
5445 | Michigan | CALHOUN | BATTLE CREEK | 7 | 1013017 | The Calhoun County Road Commission will resurface 0.7 miles of 6 1/2 Mile Road from B Drive N to Christian Drive | Pavement Improvement | 05/28/2010 | 06/01/2010 |  | 176658.4 | 0.774
5446 | Michigan | CALHOUN |  | 7 | 1013020 | This mile long pavement project in Calhoun County on N Dr N from 15 Mile Rd to 16 Mile Rd will improve the drive quality and make the road smoother | Pavement Improvement | 05/28/2010 | 06/01/2010 |  | 109313.64 | 1.028
5447 | Michigan | CASS |  | 6 | 1014003 | The Cass County Road Commisssion will resurface 1.2 miles of Dixon Road from Indian Lake Road to M-152, in the northwest part of the county. This will improve the driving quality by making the road s | Pavement Improvement | 10/21/2009 | 07/19/2010 | 07/30/2010 | 24950 | 1.197
5448 | Michigan | CASS |  | 6 | 1014004 | City of Dowagiac will repave Middle Crossing Road from West Prairie Ronde to City Limits | Pavement Improvement | 02/08/2010 | 05/01/2010 | 06/30/2010 | 50000 | 0.27
5449 | Michigan | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 6 | 1014005 | The Cass County Road Commission will resurface 0.6 miles of Gumwood Road from the state line to Redfield Street | Pavement Improvement | 02/17/2010 | 07/06/2010 | 09/10/2010 | 241685.41 | 0.63
5450 | Michigan | CHARLEVOIX |  | 1 | 1015003 | The Charlevoix County Road Commission will resurface 2.5 miles of Peninsula Rd from Advance Rd to Reich Rd in the vicinity of East Jordane. This will improve the driving quality by making the road s | Pavement Improvement | 05/06/2010 | 05/26/2010 | 07/02/2010 | 340911 | 2.438
5451 | Michigan | CHEBOYGAN |  | 1 | 1016006 | Four tenths of a mile of West Central Ave will be resurfaced from Nicolet to Huron in the Village of Mackinaw City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/22/2010 | 04/26/2010 | 05/27/2010 | 286436.23 | 0.352
5452 | Michigan | CHEBOYGAN |  | 1 | 1016008 | The Village of Mackinaw City will build a paved pathway on the Mackinaw City Rail to Trail route for cyclists walkers and joggers to promote alternative modes of transportation. | Transportation Enhancements | 06/15/2010 | 06/30/2010 | 08/13/2010 | 805648.8 | 0.082
5453 | Michigan | CHEBOYGAN |  | 1 | 1016012 | This pavement project in Cheboygan on S Western Ave from city line to Lincoln Ave will improve the drive quality and make the road smoother | Pavement Improvement | 06/09/2010 |  | 07/16/2010 | 71319 | 1.016
5454 | Michigan | CHIPPEWA |  | 1 | 1017003 | This pavement project on Riverside Drive in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 01/05/2010 | 05/17/2010 | 07/02/2010 | 573808.58 | 4.986
5455 | Michigan | CHIPPEWA |  | 1 | 1017007 | This pavement project at Kincheloe AFB in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 03/26/2010 | 05/06/2010 | 07/30/2010 | 135000 | 0.572
5456 | Michigan | CHIPPEWA |  | 1 | 1017009 | This pavement project on Oak Street in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 04/01/2010 | 05/24/2010 | 07/15/2010 | 310000 | 0.969
5457 | Michigan | CHIPPEWA |  | 1 | 1017011 | This pavement and Rumble Strip project on M-129 in Chippewa County will improve safety and make the road smoother. | Pavement Improvement | 01/28/2010 | 01/28/2010 | 10/15/2010 | 3657022.92 | 7.251
5458 | Michigan | CHIPPEWA |  | 1 | 1017013 | This pavement project in Chippewa County on H40 (Main & Albert) from M63 Westerly-S of South Street will smooth the road and improve ride quality | Pavement Improvement | 04/22/2010 | 05/12/2010 | 10/29/2010 | 108457.42 | 0.578
5459 | Michigan | CHIPPEWA |  | 1 | 1017014 | This guardrail installation project on M-48 in Chippewa County will improve safety. | Other | 05/11/2009 | 05/11/2009 | 06/25/2010 | 164594.73 | 24
5460 | Michigan | CHIPPEWA |  | 1 | 1017015 | This shoulder paving project on M-28 in Chippewa County will improve safety. | Pavement Improvement | 04/22/2010 | 07/14/2010 | 09/03/2010 | 1429962.75 | 10.769
5461 | Michigan | CLARE |  | 4 | 1018007 | Just outside the City of Clare in Clare County there will be 2.0 miles of resurfacing on E. Beaverton Rd to improve driving quality by making the road smoother. | Pavement Improvement | 03/12/2010 | 04/26/2010 | 06/11/2010 | 449771 | 2.001
5462 | Michigan | CLARE |  | 4 | 1018011 | A bike trail will be built on the Pere Marquette Rail Trail east of Evart for walkers and cyclists. | Transportation Enhancements | 02/23/2010 | 02/23/2010 | 12/31/2010 | 753890.46 | 15.62
5463 | Michigan | CLINTON |  | 8 | 1019004 | This pavement project on N Lansing St BR 127 to Walker in St. Johns will improve the drive quality and make the road smoother | Pavement Improvement | 04/01/2010 |  | 07/02/2010 | 78215.65 | 0.117
5464 | Michigan | CLINTON |  | 8 | 1019005 | This pavement project on W Howe Rd Grange to Wacousta will improve the drive quality and make the road smoother | Pavement Improvement | 11/23/2009 | 07/12/2010 | 07/30/2010 | 67457 | 4.887
5465 | Michigan | CLINTON |  | 8 | 1019006 | In the City of St. Johns | Pavement Improvement | 06/10/2010 | 06/19/2010 | 08/10/2010 | 47000 | 0.436
5466 | Michigan | CRAWFORD |  | 1 | 1020006 | This pavement project near Grayling on W County Road from east of North Stephan Bridge Rd to west of KP Rd will smooth the road and improve ride quality. | Pavement Improvement | 01/01/2010 | 01/01/2010 | 06/25/2010 | 72977.5 | 0.978
5467 | Michigan | DELTA |  | 1 | 1021011 | This pavement prjoect from Ludington St to 8th Avenue in the City of Escanaba will improve the drive quality and make the road smoother. | Pavement Improvement | 06/11/2010 | 07/06/2010 | 09/24/2010 | 300000 | 0.733
5468 | Michigan | DELTA |  | 1 | 1021012 | This pavement improvement project in Delta County near the town of Gulliver on County Road 432 will rebuild a little over one mile of pavment and improve the ride quality. | Pavement Improvement | 06/30/2010 |  | 10/15/2010 | 199394.58 | 1.207
5469 | Michigan | DICKINSON |  | 1 | 1022006 | This pavement project on County Road 569 in Dickinson County will improve the drive quality and make the road smoother. | Pavement Improvement | 02/26/2010 | 05/12/2010 | 08/28/2010 | 277036.3 | 1.465
5470 | Michigan | DICKINSON |  | 1 | 1022009 | This pavement project on West Ludington Street in the City of Iron Mountain will improve the drive quality and make the road smoother. | Pavement Improvement | 05/25/2010 | 06/01/2010 | 09/20/2010 | 94000 | 0.185
5471 | Michigan | EATON |  | 7 | 1023004 | In the City of Eaton Rapids just under 1/2 mile of State Street will be reconstructed from West of Miller Drive to the City Limits. Work will include reconstructing the roadway and building a left tu | Pavement Improvement | 04/02/2010 | 06/14/2010 |  | 110000 | 0.389
5472 | Michigan | EATON |  | 7 | 1023005 | This pavement project on S Cochran Rd Butterfield to Five Point Highway will improve the drive quality and make the road smoother | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 71300 | 5.047
5473 | Michigan | EATON |  | 7 | 1023006 | This pavement project on E Five Point Hwy Freeman to Narrow Lake Road will improve the drive quality and make the road smoother | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 66400 | 4.552
5474 | Michigan | EATON |  | 7 | 1023007 | This pavement project on W Five Point Hwy Lacey Lake Road to Battle Creek Road will improve the drive quality and make the road smoother | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 68200 | 4.808
5475 | Michigan | EATON |  | 7 | 1023008 | This pavement project on W Vermontville Hwy Hager Road to Vertmontville will improve the drive quality and make the road smoother | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 34600 | 2.373
5476 | Michigan | EATON |  | 7 | 1023009 | This pavement project on N Cochran Rd M-50 to Pinch Street will improve the drive quality and make the road smoother | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 47180 | 3.293
5477 | Michigan | EATON |  | 7 | 1023010 | This pavement project on N Canal Rd Bentley to Vermontville Highway will improve the drive quality and make the road smoother | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 82600 | 5.526
5478 | Michigan | EATON |  | 7 | 1023011 | This pavement project on Mulliken Rd M-50 to Cochran will improve the drive quality and make the road smoother | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 76440 | 5.423
5479 | Michigan | EATON |  | 7 | 1023012 | This pavement project on N Cochran Rd Mt. Hope to M-43; M-43 to Eaton Highway will improve the drive quality and make the road smoother | Pavement Improvement | 11/23/2009 | 06/14/2010 | 07/31/2010 | 59000 | 4.03
5480 | Michigan | EATON |  | 7 | 1023013 | In the City of Potterville in Eaton County 1/4 mile of East Main Street will be reconstructed from Hartel Road (State Route M-100) to Dawn Court. Work will include sidewalk improvements and drainage | Pavement Improvement | 03/11/2010 |  | 08/27/2010 | 220000 | 0.218
5481 | Michigan | GENESEE |  | 5 | 1025003 | In Genesee County, MDOT will repair 8.11 miles on M-15 from the Oakland County line northerly to south of I-69 to extend the service life of the existing road. | Pavement Improvement | 03/31/2009 | 03/31/2009 | 01/21/2011 | 1276737.62 | 8.243
5482 | Michigan | GENESEE |  | 5 | 1025009 | The MDOT will make repairs to the bridge at M-11 over the Grand River in the City of Walker to make the bridge last longer. | Transportation Enhancements | 04/19/2010 | 04/29/2010 | 09/15/2011 | 935890.15 | 0.182
5483 | Michigan | GENESEE | FLINT | 5 | 1025020 | Four tenths of a mile of Elms Rd from River Rd to Flusing Rd in the City of Flushing will be resurfaced. This will improve the driving quality by making the road smoother. | Pavement Improvement | 03/31/2009 | 03/31/2009 | 09/17/2010 | 607702.56 | 0.524
5484 | Michigan | GENESEE | FLINT | 5 | 1025021 | One mile of Davison Rd from Genesee Rd to Belsay Rd in the City of Burton will be resurfaced. This will improve the driving quality by making the road smoother. | Pavement Improvement | 12/22/2009 | 12/22/2009 | 06/30/2010 | 725856.48 | 0.999
5485 | Michigan | GENESEE | FLINT | 5 | 1025024 | This pavement project in Flint on Perry Road From Terrace Drive to City Limits will improve the drive quality and make the road smoother | Pavement Improvement | 04/28/2010 | 05/06/2010 | 09/01/2010 | 140861 | 0.336
5486 | Michigan | GENESEE | FLINT | 5 | 1025026 | The City of Flushing is resurfacing 0.3 miles of Terrace Street from River Road to Main Street. This project will improve the pavement condition and ride quality. | Pavement Improvement | 06/29/2010 | 07/02/2010 | 10/10/2010 | 152280 | 0.242
5487 | Michigan | GOGEBIC |  | 1 | 1027004 | About 1/2 mile of Johnson Rd from Colby St to Bessemer City Limits, in Gogebic County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 04/14/2010 | 06/21/2010 | 08/20/2010 | 64948.7 | 0.315
5488 | Michigan | GOGEBIC |  | 1 | 1027006 | This paving project on Prison Camp Road in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 04/08/2010 | 06/28/2010 | 10/15/2010 | 247913.8 | 1.606
5489 | Michigan | GOGEBIC |  | 1 | 1027007 | This pavement project on North Lake Street in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 06/18/2010 |  | 10/15/2010 | 120000 | 0.25
5490 | Michigan | GRAND TRAVERSE |  | 4 | 1028008 | New pavement markings will be placed in Traverse City on various roadways to improve roadway delineation. | Safety/Traffic Management | 05/25/2010 |  | 09/30/2010 | 127870.92 | 1.09
5491 | Michigan | GRAND TRAVERSE |  | 4 | 1028011 | This project will improve safety by renewing the pavement striping throughout Grand Traverse County. | Safety/Traffic Management | 06/03/2010 | 06/07/2010 | 07/02/2010 | 36282.09 | 1.154
5492 | Michigan | GRATIOT |  | 4 | 1029006 | From the St. Louis north city limit northerly to McGregor Road in Gratiot County there will be 0.76 miles reconstruction on Riverside Drive to improve the driving quality of the roadway. | Pavement Improvement | 01/22/2010 | 04/06/2010 | 08/13/2010 | 299266.73 | 0.79
5493 | Michigan | HILLSDALE |  | 7 | 1030004 | 10.43 miles of South Meridian Road (US-127) from the Ohio State line north to M-34 will be resurfaced to improve pavement rideability and increase pavement smoothness. This project will include drain | Pavement Improvement | 10/29/2009 | 10/29/2009 | 11/15/2010 | 6229866.88 | 10.43
5494 | Michigan | HILLSDALE |  | 7 | 1030008 | This pavement project in Hillsdale on East Fayette Street from Hillsdale to Oake will improve the drive quality and make the road smoother | Pavement Improvement | 02/02/2010 | 04/05/2010 | 07/24/2010 | 170000 | 0.213
5495 | Michigan | HILLSDALE |  | 7 | 1030010 | This pavement project on Squawfield Road from US-127 to Waldron Road in rural Hillsdale County will improve the drive quality and make the road smoother | Pavement Improvement | 02/03/2010 | 06/01/2010 | 09/30/2010 | 41933.6 | 2.987
5496 | Michigan | HOUGHTON |  | 1 | 1031008 | This pavement project in Owosso on Pike River Rd from Chassell/Painesdale Rd- to Lower Worham Rd will improve the drive quality and make the road smoother | Pavement Improvement | 04/01/2010 | 05/12/2010 | 09/24/2010 | 442629 | 1.565
5497 | Michigan | HOUGHTON |  | 1 | 1031009 | This pavement project in Houghton on Campus Drive from Poplar Street to Elevation Street will improve the drive quality and make the road smoother | Pavement Improvement | 04/23/2010 | 04/28/2010 | 10/15/2010 | 90000 | 0.123
5498 | Michigan | HOUGHTON |  | 1 | 1031011 | This guardrail installation project on M-26 in Houghton County will improve safety. | Other | 02/23/2010 | 02/23/2010 |  | 59094.52 | 0.789
5499 | Michigan | HURON |  | 10 | 1032008 | The Huron County Road Commission will resurface 2 and a quarter miles of French Line Rd from the east Village limits of Ubly to Verona Rd. This will improve the driving quality by making the road smo | Pavement Improvement | 04/01/2010 |  | 09/15/2010 | 278144 | 2.237
5500 | Michigan | INGHAM |  | 8 | 1033005 | 0.20 miles of North Williamston Road from I-96 to the north in Ingham County near the city of Williamston will be resurfaced to improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 04/23/2010 | 05/10/2010 |  | 92000 | 0.2
5501 | Michigan | INGHAM | LANSING | 8 | 1033009 | This pavement project on W Holmes Rd Berwick to Plesant Grove will improve the drive quality and make the road smoother | Pavement Improvement | 04/08/2010 | 06/14/2010 | 08/27/2010 | 551424.39 | 0.841
5502 | Michigan | INGHAM | LANSING | 8 | 1033010 | 1.33 Miles of Edgewood Blvd will be reconstructed in the city of Lansing from South Washington Avenue to South Cedar Street Improvements will improve roadway rideability and make the roadway smoother | Pavement Improvement | 01/20/2010 | 06/07/2010 | 09/07/2010 | 731384.29 | 2.463
5503 | Michigan | INGHAM | LANSING | 7,8 | 1033011 | 1.7 miles of North Waverly Road from West Willow Street to North Grand River Avenue will be resurfaced in Lansing. The roadway will have improved rideablity and the improved smoothness. | Bridge Improvement | 05/19/2010 | 06/02/2010 | 09/03/2010 | 996268.14 | 1.487
5504 | Michigan | IONIA |  | 3 | 1034004 | The Ionia County Road Commission will resurface three quarters of a of Mill Street from Bridge Street to the Village of Saranac. This will improve the driving quality by making the road smoother. | Pavement Improvement | 03/24/2010 | 05/04/2010 | 06/12/2010 | 239737 | 0.754
5505 | Michigan | IONIA |  | 3 | 1034005 | At various loacation on Hall Street in Belding | Pavement Improvement | 04/14/2010 | 07/06/2010 | 07/30/2010 | 110000 | 0.359
5506 | Michigan | IONIA |  | 3 | 1034011 | 1.7 miles of North Waverly Road from West Willow Street to North Grand River Avenue will be resurfaced in Lansing. The roadway will have improved rideablity and the improved smoothness. | Pavement Improvement | 01/01/2010 | 01/01/2010 | 11/12/2010 | 239736 | 1.001
5507 | Michigan | IONIA |  | 3 | 1034014 | This two and a half mle long pavement project on M-21 from east of the Kent / Ionia County line to Pinckney Road will make the pavement smoother and improve ride quality | Pavement Improvement | 02/08/2010 | 02/08/2010 | 03/31/2012 | 1003691.7 | 2.759
5508 | Michigan | IOSCO |  | 1 | 1035003 | The Iosco County Road Commission will resurface three quarters of a mile of North Skeel Ave from F-41 to Arrow St in the Huron National Forest. This will improve the driving quality by making the roa | Pavement Improvement | 02/08/2010 | 06/03/2010 | 07/23/2010 | 135000 | 0.719
5509 | Michigan | IOSCO |  | 1 | 1035004 | The Iosco County Road Commission will resurface 2.5 miles of Rollway Rd from M-65 to Liberty Rd in the Huron National Forest west of Oscoda. This will improve the driving quality by making the road s | Pavement Improvement | 03/09/2010 | 05/18/2010 | 06/25/2010 | 353290 | 2.419
5510 | Michigan | IRON |  | 1 | 1036006 | A little over 2 miles of CR651 from W Sunset Lake Rd-Noren Rd near the city of Iron River in Iron County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 04/26/2010 | 06/01/2010 | 06/30/2010 | 213058.22 | 2.21
5511 | Michigan | IRON |  | 1 | 1036007 | This pavement project on Lay Ave. in the City of Iron River will improve the drive quality and make the road smoother. | Pavement Improvement | 03/23/2010 | 06/25/2010 | 08/13/2010 | 196603 | 0.675
5512 | Michigan | ISABELLA |  | 4 | 1037004 | The City of Mt. Pleasant is resurfacing 1.01 miles on South Mission Street to improve driving quality by making the road smoother. | Pavement Improvement | 03/10/2010 | 05/03/2010 | 05/28/2010 | 188041.91 | 1.01
5513 | Michigan | ISABELLA |  | 4 | 1037005 | The City of Rosbush is resurfacing 0.94 miles on E. Broomfield Road to improve driving quality by making the road smoother. | Pavement Improvement | 03/23/2010 | 06/08/2010 | 06/25/2010 | 50000 | 0.94
5514 | Michigan | ISABELLA |  | 4 | 1037006 | The City of Mt. Pleasant is resurfacing 0.219 miles on East Michigan Street to improve driving quality by making the road smoother. | Pavement Improvement | 06/11/2010 | 06/28/2010 | 09/01/2010 | 324668.61 | 0.219
5515 | Michigan | JACKSON |  | 7 | 1038005 | I-94 near the city of Jackson in Jackson County from East of Sargent Road to the Washtenaw County Line will be rebuilt to improve mobility and reduce congestion | Pavement Improvement | 10/26/2009 | 10/26/2009 | 05/02/2012 | 30000000 | 22.952
5516 | Michigan | JACKSON | JACKSON | 7 | 1038010 | This pavement project on W Argyle St from Wisner Street to West Avenue | Pavement Improvement | 05/18/2010 | 08/02/2010 |  | 297511.96 | 0.253
5517 | Michigan | JACKSON | JACKSON | 7 | 1038014 | This pavement project near the city of Jackson on Spring Arbor Rd., from Mc Cain Road to west of Robinson Road will improve the drive quality and make the road smoother | Pavement Improvement | 06/01/2010 | 06/21/2010 |  | 236975.07 | 1.211
5518 | Michigan | KALAMAZOO |  | 6 | 1039009 | A path for walkers and cyclists will be built on Kalamazoo River Valley Trail | Transportation Enhancements | 11/18/2009 | 04/05/2010 | 10/31/2012 | 1708230.65 | 6.105
5519 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 1039011 | To improve safety this project will realign the intersection of Texas Drive @ 8th Street | Pavement Improvement | 04/09/2010 | 04/19/2010 | 07/02/2010 | 270318.17 | 0.062
5520 | Michigan | KALAMAZOO |  | 6,7 | 1039012 | This pavement project on Mercury Dr From MN Avenue to East County Line will improve the drive quality and make the road smoother | Pavement Improvement | 01/27/2010 | 07/05/2010 | 08/06/2010 | 32384.65 | 2.185
5521 | Michigan | KALAMAZOO |  | 6 | 1039013 | This pavement project on C Avenue 24th Street and AB Avenue from D Avenue to AB Aven will improve the drive quality and make the road smoother | Pavement Improvement | 01/27/2010 | 07/05/2010 | 08/06/2010 | 91010 | 3.375
5522 | Michigan | KALAMAZOO | KALAMAZOO | 6 | 1039015 | This pavement project in Kalamazoo on W Michigan Ave Sprague to the west line of Section 21 will smooth the road and improve ride quality. | Pavement Improvement | 06/25/2010 |  |  | 129441 | 0.27
5523 | Michigan | KALKASKA |  | 4 | 1040205 | This pavement project in Kalkaska County on County Highway 612 from Darke Rd W 1/2 Mile will improve the drive quality and make the road smoother | Pavement Improvement | 05/17/2010 | 06/08/2010 | 06/11/2010 | 27944.53 | 0.499
5524 | Michigan | KENT | GRAND RAPIDS | 3 | 1041007 | About a mile of Lake Drive From Fuller Avenue to Calton Avenue in the City of Gran in Kent County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 10/26/2009 | 04/19/2010 | 07/30/2010 | 158730.36 | 0.19
5525 | Michigan | KENT |  | 3 | 1041017 | The MDOT will resurface a half mile of the John J. Oostema Boulevard from Patterson Avenue to Gateway Drive at the Gerald Ford International Airport in the City of Kentwood. This will improve the dri | Pavement Improvement | 03/26/2010 | 04/26/2010 | 06/30/2010 | 794954.79 | 1.178
5526 | Michigan | KENT | GRAND RAPIDS | 3 | 1041018 | The MDOT will replace the Diamond Avenue bridge over I-196 in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 12/01/2009 | 12/01/2009 | 08/01/2011 | 2251949.13 | 0
5527 | Michigan | KENT | GRAND RAPIDS | 3 | 1041020 | The MDOT will repair almost 2 miles of M-11 from Division Avenue to kalamazoo Avenue in the City of Grand Rapids to extend the service life of the existing road. | Pavement Improvement | 04/01/2009 | 04/01/2009 | 12/30/2010 | 2236772.13 | 1.849
5528 | Michigan | KENT | GRAND RAPIDS | 3 | 1041021 | The City of Grand Rapids is building sidewalks to improve pedestrian mobility along M-11 from Division Avenue to Kalamazoo Avenue | Pavement Improvement | 03/24/2010 | 03/24/2010 | 03/31/2012 | 1369375.31 | 1.924
5529 | Michigan | KENT | GRAND RAPIDS | 3 | 1041022 | The Kent County Road Commission will widen three quarters of a West River Drive from Jupitor Road to the Rogue River Bridge in Kent County. This will improve mobility and the driving quality. | Pavement Improvement | 04/16/2010 | 04/19/2010 | 08/15/2010 | 1628585.79 | 0.754
5530 | Michigan | KENT | GRAND RAPIDS | 3 | 1041024 | The City of Kentwood will resurface a 0.8 miles of East Paris Avenue from Sparks Drive to Burton Street in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 03/29/2010 | 05/03/2010 | 06/19/2010 | 556511 | 0.792
5531 | Michigan | KENT | GRAND RAPIDS | 3 | 1041027 | The City of Rockford will resurface a quarter mile Main Street from Division Street to Courtland Street in the City of Rockford. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/16/2010 | 05/14/2010 | 05/28/2010 | 127500 | 0.238
5532 | Michigan | KENT | GRAND RAPIDS | 3 | 1041028 | The City of Kentwood will resurface a 0.4 miles of Barden Drive from East Paris Avenue to M-37 in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 03/26/2010 | 05/03/2010 | 06/11/2010 | 238505 | 0.353
5533 | Michigan | KENT | GRAND RAPIDS | 3 | 1041033 | This pavement project in Grand Rapids on Scribner Avenue From US-131 off ramp to Webster Street will improve the drive quality and make the road smoother | Pavement Improvement | 04/23/2010 | 05/10/2010 | 07/01/2010 | 144067.25 | 0.438
5534 | Michigan | KENT | GRAND RAPIDS | 3 | 1041034 | This pavement project in Grand Rapids on Turner Avenue From Leonard Street to 6th Street. Grand Rapids will improve the drive quality and make the road smoother | Pavement Improvement | 04/23/2010 | 05/10/2010 | 07/01/2010 | 100006.5 | 0.551
5535 | Michigan | KENT |  | 3 | 1041036 | This pavement project in Kent County on Cannonsburg Road from From Giles Avenue to Meyers Lake Avenue will improve the drive quality and make the road smoother | Pavement Improvement | 04/29/2010 | 05/04/2010 | 07/30/2010 | 142761 | 2.86
5536 | Michigan | KENT |  | 3 | 1041037 | This pavement project on _will improve the drive quality and make the road smoother | Pavement Improvement | 04/29/2010 | 05/06/2010 | 06/18/2010 | 120000 | 0.903
5537 | Michigan | KENT | GRAND RAPIDS | 3 | 1041038 | Grand Rapids will repave Hall Street From US-131 SB ramps to Grandville Avenue GR | Pavement Improvement | 06/15/2010 | 06/17/2010 | 06/30/2010 | 150000 | 0.162
5538 | Michigan | KENT | GRAND RAPIDS | 3 | 1041039 | The MDOT will make repairs to the bridge at 44th Street over I-196 in the City Grandville area to make the bridge last longer. | Bridge Improvement | 05/11/2009 | 04/21/2009 | 12/31/2010 | 463317.5 | 0
5539 | Michigan | KENT | GRAND RAPIDS | 3 | 1041040 | The City of Walker will resurface a half mile of Veteran's Memorial Drive from Riverbend to Maynard Avenue in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 06/10/2010 | 06/28/2010 | 08/11/2010 | 920282.3 | 1.338
5540 | Michigan | KENT | GRAND RAPIDS | 2 | 1041053 | This pavement project in Jackson on W Argyle St from West to Wisner will smooth the road and improve ride quality | Pavement Improvement | 06/22/2010 | 07/06/2010 | 07/30/2010 | 213925.38 | 3.951
5541 | Michigan | LAPEER |  | 10 | 1044006 | From the southern Macomb County line northerly to the northern village limit of Almont and from the northern village limit northerly to just south of I-69 in Lapeer County there will be 6.20 miles of | Pavement Improvement | 10/15/2009 | 10/15/2009 | 09/18/2010 | 1284955.19 | 6.57
5542 | Michigan | LAPEER |  | 10 | 1044011 | The city of Imlay will reconstruct 0.94 miles on Imlay City road to improve the driving quality by making the road smoother. | Pavement Improvement | 06/15/2010 | 07/09/2010 | 10/15/2010 | 721039 | 1.371
5543 | Michigan | LENAWEE |  | 7 | 1046006 | This pavement project in Adrian on Sutton Road form Occidental to Green will make the road smoother and improve ride quality | Pavement Improvement | 02/10/2010 | 04/05/2010 | 09/03/2010 | 258333 | 1.144
5544 | Michigan | LENAWEE |  | 7 | 1046007 | 1/4 of a mile of North Ottawa Street is being resurfaced from M-50 to Evans Street in the City of Tecumseh | Pavement Improvement | 06/11/2010 | 07/08/2010 | 08/13/2010 | 80333 | 0.284
5545 | Michigan | LENAWEE |  | 7 | 1046008 | This pavement project in Adrian on McKenzie Street from Maumee Street to Maple Avenue will smooth the road and improve ride quality. | Pavement Improvement | 06/24/2010 | 07/12/2010 | 07/30/2010 | 215313.83 | 0.376
5546 | Michigan | LENAWEE |  | 7 | 1046009 | 1.0 miles of pavement resurfacing of North Evan Street from Burt Road to the city limits of Tecumseh | Pavement Improvement | 06/11/2010 | 07/08/2010 | 08/13/2010 | 157651.37 | 0.572
5547 | Michigan | LENAWEE |  | 7 | 1046010 | The community of Clinton will reconstruct 1 mile of Tecumseh/Clinton Road. This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/01/2010 | 07/12/2010 | 06/01/2011 | 599080.4 | 1.322
5548 | Michigan | LUCE |  | 1 | 1048006 | This pavement project on County Road 405 in Luce County will improve the drive quality and make the road smoother. | Pavement Improvement | 04/28/2010 | 06/08/2010 | 10/08/2010 | 275238 | 2.283
5549 | Michigan | LUCE |  | 1 | 1048007 | This shoulder paving project on M-28 in Luce County will improve safety. | Pavement Improvement | 02/23/2010 | 02/23/2010 | 09/03/2010 | 1062349.03 | 5.977
5550 | Michigan | MACKINAC |  | 1 | 1049003 | This pavement project on M-134 from east of the I-75 Overpass to west of 3 M will make the road smoother and improve ride quality | Pavement Widening | 10/15/2009 | 10/15/2009 | 09/02/2010 | 2466828.62 | 13.535
5551 | Michigan | MACKINAC |  | 1 | 1049012 | This pavement project in Mackinac County on Borgstrom Rd US2-H40 will improve the drive quality and make the road smoother | Pavement Improvement | 02/05/2010 | 05/15/2010 | 07/15/2010 | 400284 | 4.74
5552 | Michigan | MACOMB | DETROIT,MI | 12 | 1050006 | MDOT will rebuild concrete barrier and landscaping along I-696 from Gratiot Road to I-75 in Metro Detroit in Macomb County to improve safety | Pavement Improvement | 01/25/2010 | 04/28/2009 | 10/01/2013 | 10362276.81 | 17.407
5553 | Michigan | MACOMB | DETROIT,MI | 10,12 | 1050007 | Pavement patching to extend the service life of the existing road throughout Macomb County. | Pavement Improvement | 03/11/2010 | 04/06/2010 | 07/31/2010 | 2863042.19 | 15.494
5554 | Michigan | MACOMB | DETROIT,MI | 12 | 1050008 | Resurfacing to maintain the pavement condition and improve ride quality of Calahan Road in Roseville. | Pavement Improvement | 03/25/2010 | 04/05/2010 | 06/15/2010 | 380182.8 | 0.508
5555 | Michigan | MACOMB |  | 10 | 1050009 | This pavement project on Division Street M-19 to Grand Trunk Railroad will improve the drive quality and make the road smoother | Pavement Improvement | 06/03/2010 |  | 08/30/2010 | 95000 | 0.406
5556 | Michigan | MACOMB | DETROIT,MI | 10 | 1050010 | Complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along North Fulton in Macomb County. | Pavement Improvement | 04/14/2010 | 04/27/2010 | 09/16/2011 | 475298.65 | 0.427
5557 | Michigan | MACOMB | DETROIT,MI | 12 | 1050012 | Resurfacing to maintain the pavement condition and improve ride quality of South Main Street in Mt. Clemens. | Pavement Improvement | 04/29/2010 | 05/03/2010 | 06/01/2010 | 318321.95 | 0.348
5558 | Michigan | MACOMB | DETROIT,MI | 12 | 1050013 | Resurfacing to maintain the pavement condition and improve ride quality of Rathbone Street in Mt. Clemens. | Pavement Improvement | 04/29/2010 | 05/03/2010 | 06/01/2010 | 161280.32 | 0.264
5559 | Michigan | MACOMB | DETROIT,MI | 12 | 1050014 | Resurfacing to maintain the pavement condition and improve ride quality of Hayes Avenue in Eastpointe. | Pavement Improvement | 05/13/2010 | 05/12/2010 | 08/28/2010 | 790606.02 | 0.51
5560 | Michigan | MACOMB | DETROIT,MI | 12 | 1050015 | Resurfacing to maintain the pavement condition and improve ride quality of | Pavement Improvement | 06/03/2010 | 06/10/2010 | 05/30/2011 | 1250000 | 0.515
5561 | Michigan | MACOMB | DETROIT,MI | 12 | 1050016 | Macomb County will reconstruct Kelly SB from Toepfer to 8 Mile to improve driving quality by making the road smoother | Pavement Improvement | 05/24/2010 | 06/01/2010 | 09/18/2010 | 1128751.38 | 1.642
5562 | Michigan | MANISTEE |  | 2 | 1051009 | The City truck route in the City of Mainistee will be resurfaced for 1 mile from 10th St to 16th St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 04/14/2010 | 06/01/2010 | 07/02/2010 | 110000 | 0.9
5563 | Michigan | MANISTEE |  | 2 | 1051011 | The Manistee County Road Commission is replacing a bridge on 9 Mile Road east of the Village of Kaleva. This will improve safety and mobility. | Pavement Improvement | 02/24/2010 | 06/01/2010 | 10/01/2010 | 36296 | 0.08
5564 | Michigan | MARQUETTE |  | 1 | 1052005 | This pavement project on County Road 545 US41 South 0.5 will improve the drive quality and make the road smoother | Pavement Improvement | 04/14/2010 |  | 10/01/2010 | 90650.41 | 0.54
5565 | Michigan | MARQUETTE |  | 1 | 1052006 | This pavement project on Croix Street in the City of Negaunee will improve the drive quality and make the road smoother. | Pavement Improvement | 07/23/2010 |  | 08/28/2010 | 250000 | 0.486
5566 | Michigan | MASON |  | 2 | 1053003 | This pavement project on Qrtrlne/SgrGrv/Reek/Bnsn/Hwly County Line to .25 Mi S of Lak will improve the drive quality and make the road smoother | Pavement Improvement | 04/22/2010 | 07/21/2010 | 08/31/2010 | 339566.6 | 18.239
5567 | Michigan | MASON |  | 2 | 1053004 | This pavement project in Ludington on South Williams Street from Ludington Avenue to Filer Street will improve the drive quality and make the road smoother | Pavement Improvement | 04/29/2010 | 05/10/2010 | 06/25/2010 | 171252 | 0.144
5568 | Michigan | MECOSTA |  | 4 | 1054007 | The City of Big Rapids will resurface a half mile of Bronson Ave from Maple to Milton in the City of Big Rapids. This will improve the driving by making the road smoother. | Pavement Improvement | 04/08/2010 | 07/13/2010 | 08/20/2010 | 210400.9 | 1.358
5569 | Michigan | MENOMINEE |  | 1 | 1055006 | Almost 2 miles of County Road 352 from CR577 to Hallfrisch Road near the city of Stephenson in Menominee County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 02/22/2010 |  | 09/03/2010 | 268649.11 | 1.871
5570 | Michigan | MENOMINEE |  | 1 | 1055008 | This pavement project on River Road in the Village of Stephenson will improve the drive quality and make the road smoother. | Pavement Improvement | 03/09/2010 |  | 08/31/2010 | 95700 | 0.359
5571 | Michigan | MENOMINEE |  | 1 | 1055009 | Menominee County will repave County Road 581 from 0.17 Mi W of River Rd to CR577 | Pavement Improvement | 02/22/2010 |  | 09/03/2010 | 65700 | 1.274
5572 | Michigan | MENOMINEE |  | 1 | 1055012 | This pavement project in Menominee on 14th Avenue from 1st Street to 13th Street will smooth the road and improve ride quality | Pavement Improvement | 06/01/2010 |  | 08/15/2010 | 175000 | 0.456
5573 | Michigan | MIDLAND |  | 4 | 1056008 | This pavement project in Midland on North Saginaw Road from S.B.S. RR Xing to 3752 Feet North and Austin to J will improve the drive quality and make the road smoother | Pavement Improvement | 06/09/2010 | 06/14/2010 | 09/03/2010 | 470000 | 0.63
5574 | Michigan | MISSAUKEE |  | 4 | 1057008 | This pavement project in Missaukee County on N Lucas Rd from Manistee River to County Line will improve the drive quality and make the road smoother | Pavement Improvement | 04/30/2010 | 06/15/2010 | 06/25/2010 | 60072.5 | 1.884
5575 | Michigan | MONROE | TOLEDO (OH) | 15 | 1058010 | There will be a culvert rehabilitation of the culvert at the Springbrook Drain at Sterns Road in southern Monroe county south of the city of Luna Pier. This project will provide to effect county drai | Pavement Improvement | 01/27/2010 | 05/10/2010 | 07/16/2010 | 334074.86 | 0.037
5576 | Michigan | MONROE | MONROE | 15 | 1058012 | This pavement project in Monroe County on LaPlaisance Road from Sixth Street to Jones Avenue will improve the drive quality and make the road smoother | Pavement Improvement | 05/06/2010 |  | 07/31/2010 | 280000 | 0.348
5577 | Michigan | MONROE | TOLEDO (OH) | 15 | 1058013 | Monroe County will repave Erie Road from US-24 to M-125 | Pavement Improvement | 02/08/2010 | 02/10/2010 | 09/30/2010 | 9600 | 0.557
5578 | Michigan | MONROE | TOLEDO (OH) | 15 | 1058014 | This project near Temperance will smooth the pavement at the intersection of Jackman Road and Smith Road to improve the ride quality. | Pavement Improvement | 02/17/2010 | 03/05/2010 | 10/07/2010 | 102970.49 | 0.048
5579 | Michigan | MONROE | MONROE | 15 | 1058015 | Various pavements county wide will be resurfaced in Monroe County to smooth the roads and improve ride quality. | Pavement Improvement | 02/17/2010 | 06/21/2010 | 10/07/2010 | 39747.7 | 1.651
5580 | Michigan | MONROE | MONROE | 15 | 1058016 | This project will resurface the roadway at 2 locations; on Laplaissance Road from Dunbar Road to Jones Avenue in the city of Monroe | Pavement Improvement | 02/17/2010 | 04/30/2010 | 11/25/2010 | 243064.72 | 1.593
5581 | Michigan | MONROE | DETROIT,MI | 15 | 1058017 | 0.14 miles of pavement resurfacing on Fort Road from South Huron River Drive to the Wayne County Line in northern Monroe County. This project will improve pavement rideability and increase pavement s | Pavement Improvement | 02/17/2010 | 05/04/2010 | 11/25/2010 | 33152.71 | 0.137
5582 | Michigan | MONROE |  | 15 | 1058018 | Various pavements county wide will be resurfaced in Monroe County to smooth the roads and improve ride quality. | Pavement Improvement | 02/17/2010 | 03/05/2010 | 10/07/2010 | 161805.13 | 5.009
5583 | Michigan | MONROE |  | 15 | 1058019 | This project will provide for 1/2 mile of pavement resurfacing on North Dixie Highway from the Fermi Railroad crossing to Post Road north of the city of Monroe in Monroe County. This will provide for | Pavement Improvement | 02/17/2010 | 03/05/2010 | 09/30/2010 | 72376.84 | 0.503
5584 | Michigan | MONROE | TOLEDO (OH) | 15 | 1058020 | Various pavements county wide will be resurfaced in Monroe County to smooth the roads and improve ride quality. | Pavement Improvement | 02/17/2010 | 06/21/2010 | 10/07/2010 | 5384 | 6.135
5585 | Michigan | MONROE | MONROE | 15 | 1058021 | This project will provide for 3/4 of a mile of pavement resurfacing on Albain Road from the Railroad crossing to M-125 in the city of Monroe in Monroe County. This will provide for improved pavement | Pavement Improvement | 02/17/2010 | 05/04/2010 | 11/25/2010 | 81451.16 | 0.735
5586 | Michigan | MONROE |  | 15 | 1058023 | Chip and Seal treatment at 3 locations in Monroe County. Sterns Road from M-125 to Summit Raod | Pavement Improvement | 02/19/2010 | 02/23/2010 | 09/30/2010 | 81800 | 5.635
5587 | Michigan | MONROE |  | 15 | 1058024 | This project will provide for 1.94 miles of pavement resurfacing on Luna Pier Road from M-125 to I-75 west of the city of Luna Pier in southern Monroe County. This will provide for improved pavement | Pavement Improvement | 02/19/2010 | 03/05/2010 | 08/23/2010 | 166214.87 | 1.939
5588 | Michigan | MONROE | TOLEDO (OH) | 15 | 1058025 | MDOT is resurfacing the pavement and shoulders of 1.43 miles of M-125 from the Michigan/Ohio State Line to Sterns Road. This project will improve the pavement condition and ride quality. | Pavement Improvement | 02/23/2010 | 02/23/2010 | 09/02/2010 | 131664.27 | 1.43
5589 | Michigan | MONROE | TOLEDO (OH) | 15 | 1058026 | The Monroe County Road Commission will be resurfacing 0.6 miles of Lewis Avenue from the Ann Arbor Railroad Crossing to Pickard Avenue. This project will improve the pavement condition and ride quali | Pavement Improvement | 02/23/2010 | 03/05/2010 | 10/13/2010 | 151197.72 | 0.602
5590 | Michigan | MONROE | STATEWIDE | 15 | 1058031 | Resurface | Pavement Improvement | 04/07/2010 | 04/20/2010 | 11/25/2010 | 180241.21 | 2.04
5591 | Michigan | MONTCALM |  | 4 | 1059009 | This pavement project in Montcalm County on Newcosta/Mt Hope/Sidney Rds from Pakes-Cond;M66-Derby;M82-Kndvlle will improve the drive quality and make the road smoother | Pavement Improvement | 07/09/2010 | 07/21/2010 | 07/30/2010 | 25775 | 13.545
5592 | Michigan | MONTCALM |  | 4 | 1059010 | This pavement project in Montcalm County on County Road 510/Sidney Rd from Derby Rd to Sheridan Rd will improve the drive quality and make the road smoother | Pavement Improvement | 02/03/2010 | 07/01/2010 | 08/27/2010 | 55000 | 3.015
5593 | Michigan | MONTCALM |  | 4 | 1059011 | This pavement project in Montcalm County on Lake Montcalm Rd NW from Sheridan Road to Wyman Road will improve the drive quality and make the road smoother | Pavement Improvement | 02/03/2010 | 07/01/2010 | 08/27/2010 | 36686 | 2.05
5594 | Michigan | MONTCALM |  | 4 | 1059012 | This pavement project in Montcalm County on S Mount Hope Rd from Stanton Rd to Condensary Rd will improve the drive quality and make the road smoother | Pavement Improvement | 02/03/2010 | 07/01/2010 | 08/27/2010 | 70877 | 6.186
5595 | Michigan | MONTCALM |  | 4 | 1059013 | This pavement project in Greenvile on Hillcrest Street from north M-57 to Grove Street will smooth the road and improve ride quality. | Pavement Improvement | 05/20/2010 | 07/12/2010 | 07/31/2010 | 65120 | 0.309
5596 | Michigan | MONTCALM |  | 2,4 | 1059014 | This project in rural Montcalm County will resurface 3.3 miles of pavement on N. Lakeview Rd./Newcosta Rd. improving the ride quality. | Pavement Improvement | 02/23/2010 | 07/01/2010 | 08/27/2010 | 55732 | 3.388
5597 | Michigan | MONTMORENCY |  | 1 | 1060006 | Over 3 miles of County Road 624 from CR459 to Ess Lake Road near the city of Hillman in Montmorency County will be repaved to improve ride quality and make the road smoother | Other | 10/23/2009 | 11/01/2009 | 08/15/2010 | 11000 | 3.051
5598 | Michigan | MONTMORENCY |  | 1 | 1060008 | This pavement project in Montmorency County on County Road 624 from CR459 to Ess Lake Road will improve the drive quality and make the road smoother | Pavement Improvement | 02/03/2010 | 04/05/2010 | 08/15/2010 | 266568.37 | 3.051
5599 | Michigan | MONTMORENCY |  | 1 | 1060009 | This countywide Pavement Marking project in rural Montmorency County will improve traffic operations. | Safety/Traffic Management | 06/29/2010 |  | 09/15/2010 | 34356 | 1.289
5600 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 1061305 | The MDOT is installing cable guard rail on US-31 from Airline Rd north to Marquette Ave in the Cities of Norton Shores and Muskegon to improve safety. | Safety/Traffic Management | 10/15/2009 | 10/15/2009 | 09/13/2010 | 731165.9 | 10.075
5601 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 1061308 | The City of Norton Shores will resurface a half mile of Sherman Ave from Peck St to Riordan St. This will improve driving quality by making the road smoother. | Pavement Improvement | 03/11/2010 | 04/29/2010 | 06/11/2010 | 220017.15 | 0.442
5602 | Michigan | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 2 | 1061314 | The City of Whitehall will resurface a 0.8 miles of White Lake Dr from Whitehall Rd to Hyde Park Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 05/21/2010 | 05/25/2010 |  | 124318.75 | 0.794
5603 | Michigan | MUSKEGON |  | 2 | 1061316 | Eight miles of Scenic Drive in the City of North Muskegon will be resurfaced from Fenner Rd to South Shore Drive. This will improve driving quality by making the road smoother. | Pavement Improvement | 06/17/2010 | 06/28/2010 |  | 1276972.65 | 9.527
5604 | Michigan | NEWAYGO |  | 2 | 1062006 | A little over 3 miles of Alger Road from 128th Street to Moore Road near the city of Grant in Newaygo County will be repaved to improve ride quality and make the road smoother | Other | 10/23/2009 | 03/23/2010 | 07/30/2010 | 20253.11 | 2.013
5605 | Michigan | NEWAYGO |  | 2 | 1062007 | North Stone Rd will be resurfaced for one half mile from Main St to 44th St in the village of Fremont.. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/24/2010 | 05/17/2010 | 06/11/2010 | 95000 | 0.5
5606 | Michigan | NEWAYGO |  | 2 | 1062009 | Newaygo County will do a pavement project on Alger Road 128th from Street to Moore Road to improve the drive quality and make the road smoother | Pavement Improvement | 02/03/2010 | 03/23/2010 | 07/30/2010 | 625139.3 | 2.013
5607 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063003 | Complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along US-24 in Bloomfield Township by MDOT. | Pavement Improvement | 01/19/2010 | 01/19/2010 | 03/15/2011 | 8041044.35 | 1.93
5608 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063008 | This pavement project on Joslyn Ave Walton to North City Limits will improve the drive quality and make the road smoother | Pavement Improvement | 03/24/2010 | 07/07/2010 | 10/01/2010 | 263000 | 0.54
5609 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063009 | Resurfacing to maintain the pavement condition and improve ride quality of Wayne Street in Pontiac. | Pavement Improvement | 03/24/2010 | 05/26/2010 | 07/02/2010 | 187000 | 0.321
5610 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063010 | New pedestrian bridge to improve safety and pedestrian access over US-24 in Pontiac. | Transportation Enhancements | 07/15/2010 |  | 11/15/2010 | 2022628.85 | 0.125
5611 | Michigan | OAKLAND | DETROIT,MI | 12 | 1063011 | Resurfacing to maintain the pavement condition and improve ride quality of 12 Mile Road in Lathrup Village. | Pavement Improvement | 03/30/2010 | 05/10/2010 | 09/30/2010 | 1031000 | 0.987
5612 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063013 | Resurfacing to maintain the pavement condition and improve ride quality of Centerpoint Parkway in Pontiac. | Pavement Improvement | 04/20/2010 | 05/10/2010 | 08/25/2010 | 638489.58 | 1.282
5613 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063014 | Resurfacing to maintain the pavement condition and improve ride quality of Opdyke Road in Auburn Hills. | Pavement Improvement | 04/14/2010 | 04/17/2010 | 08/01/2010 | 1125833.4 | 1.059
5614 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063015 | Resurfacing to maintain the pavement condition and improve ride quality of Middlebelt Road in Farmington Hills. | Pavement Improvement | 04/01/2010 | 04/19/2010 | 08/30/2010 | 1033000 | 1.982
5615 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063016 | Resurfacing to maintain the pavement condition and improve ride quality of Middlebelt Road in Farmington Hills. | Pavement Improvement | 04/01/2010 | 04/19/2010 | 08/30/2010 | 673000 | 2.003
5616 | Michigan | OAKLAND | DETROIT,MI | 9,12 | 1063017 | This pavement project on Inkster Road from 9 Mile to 11 Mile in the City of Southfield will improve the drive quality and make the road smoother | Pavement Improvement | 05/11/2009 | 05/11/2009 | 10/15/2010 | 1964000 | 1
5617 | Michigan | OAKLAND | SOUTH LYON-HOWELL-BRIGHTON | 11 | 1063019 | This pavement project in South Lyonon Nine Mile Road from Dean Drive to Pontiac Trail will improve the drive quality and make the road smoother | Pavement Improvement | 05/26/2010 | 06/21/2010 | 09/30/2010 | 509000 | 0.473
5618 | Michigan | OAKLAND | DETROIT,MI | 8,9,11 | 1063020 | This pavement project in Oakland County Countywide at 3 locations in Oakland County will improve the drive quality and make the road smoother | Pavement Improvement | 05/06/2010 | 07/08/2010 | 08/25/2010 | 952666.3 | 6.233
5619 | Michigan | OAKLAND |  | 8 | 1063021 | This pavement project in Oakland County on Grange Hall Road from West Village Limits to North Holly Road will improve the drive quality and make the road smoother | Pavement Improvement | 05/06/2010 | 07/08/2010 | 08/25/2010 | 130000 | 0.622
5620 | Michigan | OAKLAND | DETROIT,MI | 12 | 1063022 | This pavement project in Ferndale on Fern Avenue From Chesterfield to Intermodal Ave will improve the drive quality and make the road smoother | Pavement Improvement | 06/15/2010 | 06/15/2010 | 09/13/2010 | 290699.33 | 0.187
5621 | Michigan | OAKLAND | DETROIT,MI | 8,9,12 | 1063023 | This pavement project in Ferndale on Chesterfield From Fair to Fern will improve the drive quality and make the road smoother | Pavement Improvement | 06/15/2010 | 06/15/2010 | 09/13/2010 | 173533.06 | 0.526
5622 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063024 | Resurfacing to maintain the pavement condition and improve ride quality of Cooley Lake Road in Waterford. | Pavement Improvement | 05/06/2010 | 05/07/2010 | 11/12/2010 | 1121451.71 | 0.472
5623 | Michigan | OAKLAND | DETROIT,MI | 8 | 1063025 | Resurfacing to maintain the pavement condition and improve ride quality of White Lake Road in Clarkston. | Pavement Improvement | 05/13/2010 | 05/19/2010 | 09/01/2010 | 986000 | 0.937
5624 | Michigan | OAKLAND | DETROIT,MI | 8 | 1063026 | Paving Ray Road east of M-24 to Oxford Road in Oakland County. | Pavement Improvement | 06/11/2010 | 06/21/2010 | 10/15/2010 | 1284335.47 | 0.704
5625 | Michigan | OAKLAND | DETROIT,MI | 12 | 1063027 | Resurfacing to maintain the pavement condition and improve ride quality of Hilton Road in Detroit. | Pavement Improvement | 05/20/2010 | 06/29/2010 | 09/01/2010 | 475000 | 0.518
5626 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063029 | This pavement project near Farmington on Orchard Lake Road from 12 Mile Road to 13 Mile Road will smooth the road and improve ride quality | Pavement Improvement | 05/12/2010 | 05/19/2010 | 08/20/2010 | 864000 | 0.372
5627 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063030 | This pavement project in Pontiac on Walton Road from Joslyn to East City Limits will smooth the road and improve ride quality | Pavement Improvement | 05/20/2010 | 07/06/2010 | 10/29/2010 | 716000 | 1.487
5628 | Michigan | OAKLAND | DETROIT,MI | 9,11 | 1063031 | This pavement project in Farmington Hills on Grand River Avenue from Haggerty to Ten Mile Road will smooth the road and improve ride quality | Pavement Improvement | 02/17/2010 | 06/24/2010 | 09/25/2010 | 1253938.76 | 0.26
5629 | Michigan | OAKLAND | DETROIT,MI | 9 | 1063032 | This pavement project on Main Street from 13 Mile Road to Chippewa in Royal Oak will smooth the road and improve ride quality | Pavement Improvement | 02/17/2010 | 08/02/2010 | 10/30/2010 | 391000 | 0.462
5630 | Michigan | OAKLAND | DETROIT,MI | 9,12 | 1063033 | This pavement project on Lincoln Street from Campbell to Stephenson in Royal Oak will smooth the road and improve ride quality | Pavement Improvement | 02/17/2010 | 08/02/2010 | 10/30/2010 | 506000 | 0.499
5631 | Michigan | OAKLAND | DETROIT,MI | 12 | 1063035 | The City of Hazel Park in Metro Detroit will be resurfacing 2.56 miles of the Chrysler Service Drive between 8 Mile Rd. and 9 Mile Rd. This project will improve pavement condition and ride quality. | Pavement Improvement | 02/23/2010 | 07/19/2010 | 11/14/2010 | 1168000 | 2.539
5632 | Michigan | OAKLAND | DETROIT,MI | 12 | 1063044 | Resurface, Rehab, or Restore | Pavement Improvement | 04/01/2010 | 07/19/2010 | 11/14/2010 | 1017000 | 2.117
5633 | Michigan | OGEMAW |  | 1 | 1065006 | The Ogemaw County Road Commission will resurface a half mile of Sage Lake Rd from Harrison Rd to the village limits of Prescott. This will improve the driving quality by making the road smoother. | Pavement Improvement | 03/24/2010 |  | 08/27/2010 | 26386 | 0.37
5634 | Michigan | OGEMAW |  | 1 | 1065007 | The Ogemaw County Road Commission will resurface 5.5 miles of West State Rd from Fairview Rd to M-33 east of West Branch. This will improve the driving quality by making the road smoother. | Pavement Improvement | 03/10/2010 |  | 08/27/2010 | 256558.07 | 5.49
5635 | Michigan | ONTONAGON |  | 1 | 1066007 | This pavement project on East Shore Rd 4.0 Mi S of M28 to 7.5 Mi S will improve the drive quality and make the road smoother | Pavement Improvement | 06/02/2010 |  | 10/15/2010 | 360202.38 | 3.559
5636 | Michigan | ONTONAGON |  | 1 | 1066008 | This guardrail installation project on M-26 in Ontonagon County will improve safety. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 09/17/2010 | 522334.45 | 31.324
5637 | Michigan | ONTONAGON |  | 1 | 1066009 | The culvert project on M-28 in Ontonagon and Dickinson Counties will improve drainage and safety | Pavement Improvement | 02/17/2010 | 02/17/2010 | 07/30/2010 | 157588.98 | 0
5638 | Michigan | OSCEOLA |  | 4 | 1067006 | A little over 4 miles of River/115th/4 Mile Rpad snear the city of Evart in Osceola County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 10/21/2009 | 05/17/2010 | 07/31/2010 | 229923.57 | 4.143
5639 | Michigan | OSCODA |  | 1 | 1068005 | The Oscoda County Road Commission will replace a drainage culvert on Cherry Creek Rd 200 ft west of West Camp Ten Rd to improve drainage and extend the life of the roadway. | Pavement Improvement | 02/09/2010 | 03/19/2010 | 07/30/2010 | 59583 | 0.384
5640 | Michigan | OSCODA |  | 1 | 1068006 | The Oscoda County Road Commission will replace a drainage culvert on East Kittle Rd 100 ft east of Caldwell Rd to improve drainage and extend the life of the roadway. | Pavement Improvement | 02/09/2010 | 04/08/2010 | 08/30/2010 | 25110 | 0.565
5641 | Michigan | OSCODA |  | 1 | 1068007 | The Oscoda County Road Commission will replace a drainage culvert on East Kittle Rd 800 ft east of M-33 to improve drainage and extend the life of the roadway. | Pavement Improvement | 02/09/2010 | 04/08/2010 | 08/30/2010 | 55413 | 0.786
5642 | Michigan | OSCODA |  | 1 | 1068008 | The Oscoda County Road Commission will replace a drainage culvert on Zimowske Rd 900 ft east of Mishler Rd to improve drainage and extend the life of the roadway. | Pavement Improvement | 02/17/2010 | 04/08/2010 | 07/30/2010 | 21445 | 1.043
5643 | Michigan | OTSEGO |  | 1 | 1069003 | 0.3 miles of Meecher Rd from Anna Dr to Buddy Ave will be resurfaced west of Gaylord . This will improve the driving quality by making the road smoother. | Pavement Improvement | 07/20/2009 | 07/20/2009 | 06/04/2010 | 150000 | 0.304
5644 | Michigan | OTTAWA | HOLLAND | 2 | 1070006 | Zeeland County will repave 104th Avenue from Paw Paw Drive to I-196 BL in Holland | Pavement Improvement | 03/23/2010 | 04/19/2010 | 07/16/2010 | 506085 | 0.284
5645 | Michigan | OTTAWA |  | 2 | 1070008 | The MDOT will resurface 3.5 miles of M-104 from 144th Ave east to I-96 near Spring Lake. This will improve the driving quality by making the road smoother. | Pavement Improvement | 05/11/2009 | 05/11/2009 | 03/31/2012 | 848086.93 | 3.468
5646 | Michigan | OTTAWA |  | 2 | 1070009 | This pavement project near Eastmanville on 68th Ave from Leonard Street to I-96 will smooth the road and improve ride quality | Pavement Improvement | 06/01/2010 | 06/15/2010 | 07/09/2010 | 163866 | 2.731
5647 | Michigan | OTTAWA | GRAND RAPIDS | 2 | 1070013 | The MDOT will resurface 2 miles of M-121 from 40th Ave to Rush Creek near Hudsonville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 02/17/2010 | 02/17/2010 | 03/31/2012 | 2663674.64 | 4.029
5648 | Michigan | PRESQUE ISLE |  | 1 | 1071003 | The Presque Isle County Road Commission will resurface 1.5 miles of East Heythaler Highway from US-23 to County Road 451 south of Rogers City. This will improve the driving quality by making the road | Pavement Improvement | 03/24/2010 | 05/10/2010 | 07/16/2010 | 352152 | 1.442
5649 | Michigan | ROSCOMMON |  | 4 | 1072006 | Over 2 miles of US Old 27 from Mary Road to Yeager Road near the city of Houghton Lake in Roscommon County will have its shoulder widened to improve safety and improve mobility | Pavement Improvement | 10/26/2009 | 10/26/2009 | 07/15/2010 | 119470.4 | 2.218
5650 | Michigan | ROSCOMMON |  | 4 | 1072014 | Rosscommon County will repave M 76 from Madision St-Artesia Beach Rd | Pavement Improvement | 02/08/2010 | 02/08/2010 | 11/12/2010 | 347246 | 1.884
5651 | Michigan | ROSCOMMON |  | 4 | 1072015 | The Roscommon County Road Commission is resurfacing 0.8 miles of Loxley Road in the community of Houghton Lake to improve the ride quality of the road. | Pavement Improvement | 06/17/2010 |  | 09/01/2010 | 44289.61 | 0.819
5652 | Michigan | SAGINAW |  | 5 | 1073006 | In the city of Saginaw, MDOT will resurface 8.78 miles on M-81 from Indiantown Road easterly to Wadsworth Avenue to improve the driving quality of the roadway. | Pavement Improvement | 10/15/2009 | 10/15/2009 | 02/01/2012 | 881962.16 | 8.78
5653 | Michigan | SAGINAW |  | 4 | 1073007 | This pavement project on Ditch Rd Briggs Rd to Sheridan Rd will improve the drive quality and make the road smoother | Pavement Improvement | 11/10/2009 | 06/01/2010 | 08/31/2010 | 65000 | 3.972
5654 | Michigan | SAGINAW |  | 4 | 1073008 | In Thomas Township there is 5.31 miles of resurfacing on Brant Fordney & Ring Roads to improve driving quality by making the road smoother. | Pavement Improvement | 11/10/2009 | 06/01/2010 | 08/31/2010 | 66000 | 4.287
5655 | Michigan | SAGINAW |  | 4 | 1073009 | In Thomas Township there is 4.18 miles of resurfacing on Fordney & Hemlock Roads to improve driving quality by making the road smoother. | Pavement Improvement | 11/10/2009 | 06/01/2010 | 08/31/2010 | 70000 | 4.188
5656 | Michigan | SAGINAW |  | 4 | 1073010 | The City of SaginawThomas Township & Saginaw Township is resurfacing 5.33 miles on various locations from River through Midland Road to improve driving quality by making the road smoother. | Pavement Improvement | 11/10/2009 | 06/01/2010 | 08/31/2010 | 80993.12 | 5.131
5657 | Michigan | SANILAC |  | 10 | 1074006 | This pavement project on West French Line Road over the Elk Creek Bridge in Sanilac County will improve the drive quality and make the road smoother | Bridge Replacement | 04/02/2010 | 05/19/2010 | 07/16/2010 | 357422 | 0.865
5658 | Michigan | SANILAC |  | 10 | 1074007 | This pavement project in Sandusky on Cambell Road from Industrial Road to Miller Road will improve the drive quality and make the road smoother | Pavement Improvement | 04/01/2010 | 06/22/2010 | 07/31/2010 | 294422.18 | 0.098
5659 | Michigan | SCHOOLCRAFT |  | 1 | 1075003 | This shoulder paving project on County Road 442 in Schoolcraft County will improve safety. | Pavement Improvement | 10/21/2009 | 06/14/2010 | 09/30/2010 | 94000 | 4.039
5660 | Michigan | SCHOOLCRAFT |  | 1 | 1075006 | Schoolcraft county will resurface County Road 442 from US-2 to M-149 to make the road smoother and improve the ride quality. | Pavement Improvement | 12/11/2009 | 07/01/2010 | 09/30/2010 | 11952 | 6.41
5661 | Michigan | SHIAWASSEE |  | 4 | 1076003 | Almost 3 miles of S Delaney Rd near the city of Owosso in Shiawassee County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 02/19/2010 | 04/26/2010 | 05/29/2010 | 508914 | 2.681
5662 | Michigan | SHIAWASSEE |  | 4 | 1076007 | This pavement project near Ann Arbor on Shiawassee Street from Walnut Street to 100' south of St Mary Street will improve the drive quality and make the road smoother | Pavement Improvement | 05/17/2010 | 06/14/2010 |  | 180000 | 0.12
5663 | Michigan | SHIAWASSEE |  | 8 | 1076008 | This pavement project near Ann Arbor on Shiawassee Street from Walnut Street to 100' south of St Mary Street will improve the drive quality and make the road smoother | Transportation Enhancements | 06/08/2010 | 06/09/2010 | 08/30/2010 | 50000 | 0.202
5664 | Michigan | SHIAWASSEE |  | 8 | 1076009 | 0.26 miles of pavement resurfacing on East Main Street from the Mercer Street to the East City limits of Durand | Pavement Improvement | 06/08/2010 | 06/14/2010 |  | 52000 | 0.258
5665 | Michigan | ST CLAIR | PORT HURON | 10 | 1077216 | Resurfacing to maintain the pavement condition and improve ride quality of Scott Avenue in Port Huron. | Pavement Improvement | 02/19/2010 | 05/03/2010 | 07/31/2010 | 152704.07 | 0.101
5666 | Michigan | ST CLAIR | PORT HURON | 10 | 1077223 | Resurfacing to maintain the pavement condition and improve ride quality of Fred W. Moore Highway in St. Clair. | Pavement Improvement | 03/30/2010 | 04/26/2010 | 07/02/2010 | 265898.57 | 0.277
5667 | Michigan | ST CLAIR | PORT HURON | 10 | 1077227 | This project will improve drainage by replacing a culvert at Ravenswood Road At Michigan Avenue to Huffman Drain | Pavement Improvement | 04/23/2010 | 05/10/2010 | 08/20/2010 | 264882.59 | 0.16
5668 | Michigan | ST CLAIR | PORT HURON | 10 | 1077229 | This pavement project in St. Clair on St. Clair Highway from Oak Street to Palmer Street will improve the drive quality and make the road smoother | Pavement Improvement | 05/03/2010 | 05/14/2010 | 07/31/2010 | 381288.15 | 0.311
5669 | Michigan | ST CLAIR | PORT HURON | 10 | 1077230 | Resurfacing to maintain the pavement condition and improve ride quality of Fred W. Moore Highway in St. Clair. | Pavement Improvement | 06/08/2010 |  | 10/10/2010 | 423922.72 | 0.051
5670 | Michigan | ST JOSEPH |  | 6 | 1078004 | The St. Joseph County Road Commisssion is installing pavement marking to improve safety on 223 miles of roads throughout the county. | Pavement Improvement | 04/20/2010 | 04/30/2010 | 11/01/2010 | 147998.07 | 8.07
5671 | Michigan | ST JOSEPH |  | 6 | 1078006 | The St. Joseph County Road Commisssion will resurface 3 miles of Bent Road from M-216 to Dutch Settlement Road in the northwest corner of the county. This will improve the driving quality by making t | Pavement Improvement | 12/22/2009 | 07/22/2010 | 07/31/2009 | 42260 | 3.048
5672 | Michigan | ST JOSEPH |  | 6 | 1078007 | The St. Joseph County Road Commisssion will resurface 7.8 miles of Featherstone Road from M-66 to Engle Road north of Sturgis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 12/22/2009 | 07/13/2010 | 07/31/2009 | 86617 | 7.79
5673 | Michigan | ST JOSEPH |  | 6 | 1078008 | The City of Sturgis will resurface 0.6 miles of North Centerville Road from West Lafayette Road to Haines Boulevard in the city. This will improve the driving quality by making the road smoother. | Other | 04/16/2010 | 04/27/2010 | 05/28/2010 | 125000 | 0.622
5674 | Michigan | ST JOSEPH |  | 6 | 1078009 | The St. Joseph County Road Commisssion will resurface 0.5 miles of Big Hill Road from M-12 to Lafayette Road in Sturgis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 01/27/2010 | 03/01/2010 | 08/31/2010 | 130000 | 0.532
5675 | Michigan | ST JOSEPH |  | 6 | 1078010 | This pavement project on Spring Street from West Michigan to Millard Street will make the road smoother and improve ride quality | Pavement Improvement | 06/01/2010 | 06/28/2010 | 10/01/2010 | 185000 | 0.181
5676 | Michigan | TUSCOLA |  | 5 | 1079006 | The Tuscola County Road Commission will replace the West Cass City Rd bridge over the Allen drain to improve safety and mobility. | Bridge Replacement | 02/01/2010 | 04/05/2010 | 08/28/2010 | 342711 | 0.489
5677 | Michigan | TUSCOLA |  | 5 | 1079007 | The Tuscola County Road Commission will resurface 2 miles of Irish Rd from Willard to Birch Run south of the Village of Millington. This will improve the driving quality by making the road smoother. | Pavement Improvement | 03/04/2010 |  | 08/31/2010 | 287689.34 | 2.027
5678 | Michigan | TUSCOLA |  | 5 | 1079009 | The community of Caro is resurfacing 0.94 miles of Hooper Street to improve the pavement condition and ride quality of the road. | Pavement Improvement | 05/03/2010 | 07/06/2010 | 09/30/2010 | 100000 | 0.943
5679 | Michigan | TUSCOLA |  | 5 | 1079010 | The community of Mayville is resurfacing 0.5 miles of Fulton Street to improve the pavement condition and ride quality of the road. | Pavement Improvement | 06/01/2010 | 06/14/2010 | 08/15/2010 | 90198 | 0.504
5680 | Michigan | VAN BUREN |  | 6 | 1080008 | The Van Buren County Road Commisssion is building a paved pathway for 0.33 miles along the Kal-Haven State Trail from 10th Street (Kalamazoo Street) to CR 655 in Bloomingdale for cyclists walkers and | Transportation Enhancements | 12/23/2009 | 05/01/2010 | 08/31/2010 | 900000 | 0.333
5681 | Michigan | VAN BUREN |  | 6 | 1080009 | MDOT will resurface 1.5 miles of M-40 from St. Joseph Avenue to Power Plant Road in Paw Paw. This will improve the driving quality by making the road smoother. | Pavement Improvement | 01/19/2010 | 01/19/2010 | 04/30/2011 | 2128586.32 | 1.46
5682 | Michigan | VAN BUREN |  | 6 | 1080011 | The Van Buren County Road Commisssion will resurface 0.3 miles of 73rd Street from Phoenix Street to the Tractor Supply Store in South Haven. This will improve the driving quality by making the road | Pavement Improvement | 07/20/2010 |  | 10/01/2010 | 125000 | 0.28
5683 | Michigan | VAN BUREN |  | 6 | 1080014 | This project Van Buren County will replace the culbert on CR653/29th St Over North Branch of Paw Paw River to improve drainage and safety. | Bridge Replacement | 04/23/2010 |  | 08/30/2010 | 164336.25 | 0.219
5684 | Michigan | WASHTENAW | ANN ARBOR | 15 | 1081002 | 2.28 miles of nonmotorized path expansion at various location throughout the city of Ann Arbor. This project will enhance nonmotorized and pedestrian mobilty and safety throughout 34 locations throug | Safety/Traffic Management | 12/09/2009 | 08/02/2010 | 09/17/2010 | 250000 | 2.278
5685 | Michigan | WASHTENAW | DETROIT,MI | 15 | 1081003 | The Historic Freighthouse in Ypsilant will receive a makeover. | Transportation Enhancements | 03/01/2010 | 03/19/2010 | 05/28/2010 | 270465.81 | 0
5686 | Michigan | WASHTENAW |  | 15 | 1081004 | This pavement project in Milan on Marvin Street from the County Street to Michigan Miller Street will improve the drive quality and make the road smoother | Pavement Improvement | 04/16/2010 | 06/30/2010 | 07/30/2010 | 125000 | 0.362
5687 | Michigan | WASHTENAW | ANN ARBOR | 7 | 1081005 | This pavement project in Ann Arbor on Wagner Road from Ann Arbor-Saline Road to Liberty Road will improve the drive quality and make the road smoother | Pavement Improvement | 01/08/2010 | 04/01/2010 | 12/31/2010 | 82600 | 2.412
5688 | Michigan | WASHTENAW | ANN ARBOR | 15 | 1081006 | This pavement project in Ypsilanti on Textile Road from Deer Creek Drive to Stony Creek Road will improve the drive quality and make the road smoother | Pavement Improvement | 01/08/2010 | 04/01/2010 | 12/31/2010 | 34100 | 1.468
5689 | Michigan | WASHTENAW | ANN ARBOR | 7 | 1081007 | This pavement project in Ann Arbor on Scio Church Road from Zeeb Road to Tessmer Road will improve the drive quality and make the road smoother | Pavement Improvement | 01/08/2010 | 04/01/2010 | 12/31/2010 | 20800 | 0.752
5690 | Michigan | WASHTENAW | ANN ARBOR | 7 | 1081008 | This pavement project in Ann Arbor on Zeeb Road from Pratt Road to Scio Road will improve the drive quality and make the road smoother | Pavement Improvement | 01/08/2010 | 04/01/2010 | 12/31/2010 | 40600 | 0.595
5691 | Michigan | WASHTENAW | ANN ARBOR | 15 | 1081009 | This pavement project will improve the drive quality and make the road smoother at four locations in the Ann Arbor area. | Pavement Improvement | 01/12/2010 | 04/01/2010 | 12/31/2010 | 409200 | 1.38
5692 | Michigan | WASHTENAW | ANN ARBOR | 7,15 | 1081010 | This pavement project on Ellsworth from Maple Road to State will make the road smoother and improve ride quality | Pavement Improvement | 01/12/2010 | 04/01/2010 | 12/31/2010 | 387700 | 2.04
5693 | Michigan | WASHTENAW | ANN ARBOR | 7 | 1081011 | Washtenaw County will repave Dexter Ann Arbor Road From Kensington to Meadow View in Dexter | Pavement Improvement | 04/01/2010 | 06/14/2010 | 07/26/2010 | 100000 | 0.241
5694 | Michigan | WASHTENAW | ANN ARBOR | 15 | 1081014 | This pavement project in Washtenaw County on Mansfield Street from Westmoorland Street to Congress Street will improve the drive quality and make the road smoother | Pavement Improvement | 02/03/2010 | 04/02/2010 | 08/20/2010 | 502469.15 | 0.321
5695 | Michigan | WASHTENAW | ANN ARBOR | 15 | 1081015 | This pavement project in Washtenaw County on College Place from West Cross to Forest will improve the drive quality and make the road smoother | Pavement Improvement | 02/03/2010 | 04/02/2010 | 08/27/2010 | 204000 | 0.105
5696 | Michigan | WASHTENAW | ANN ARBOR | 15 | 1081017 | Ann Arbor will repave Plymouth and Green Roads from Nixon to US-23 & Plymouth to Hubbard | Pavement Improvement | 02/08/2010 | 06/03/2010 | 11/15/2010 | 2232914.38 | 1.756
5697 | Michigan | WASHTENAW | DETROIT,MI | 15 | 1081027 | Historic Preservation | Transportation Enhancements | 08/03/2010 |  | 10/15/2010 | 229534.19 | 0
5698 | Michigan | WAYNE | DETROIT,MI | 13 | 1082009 | Detroit is building a mile of paved pathway for cyclists, walkers, and joggers to promote alternative modes of transportation | Transportation Enhancements | 10/26/2009 | 10/26/2009 | 11/15/2012 | 1946988.29 | 0.824
5699 | Michigan | WAYNE | DETROIT,MI | 13 | 1082012 | This project is for the design of an off-shore wharf to expand the capacity to ship and receive water-borne Detroit River freight in the Detroit area. | Other | 04/01/2009 | 01/31/2010 |  | 599205 | 0.129
5700 | Michigan | WAYNE | DETROIT,MI | 13 | 1082013 | This project is for the design of a terminal building expansion to store receive and process increased freight in the Detroit riverfront area. | Other | 04/01/2009 | 01/19/2010 |  | 210250 | 0.129
5701 | Michigan | WAYNE | DETROIT,MI | 15 | 1082014 | The City of Romulus will resurface 4.7 miles of Huron River Drive to improve driving quality and increase service life | Pavement Improvement | 11/18/2009 | 11/18/2009 | 09/15/2010 | 643000 | 3.67
5702 | Michigan | WAYNE | DETROIT,MI | 15 | 1082015 | The City of Dearborn will resurface .7 miles of the Southfield Service Drive SBd to improve driving quality and increase service life | Pavement Improvement | 11/25/2009 | 03/22/2010 | 10/31/2010 | 282787.5 | 0.464
5703 | Michigan | WAYNE | DETROIT,MI | 13 | 1082016 | The City of Grosse Point Farms will resurface .2 miles of Fisher Road to improve driving quality and increase service life | Pavement Improvement | 11/18/2009 | 02/18/2010 | 08/31/2010 | 99643.95 | 0.213
5704 | Michigan | WAYNE | DETROIT,MI | 13,14 | 1082017 | The City of Detroit is resurfacing portions of Dickerson Van Dyke Antoinette. Fourteenth Trumbull Schaeffer Wyoming Southfield Service West Vernor Fullerton Hayes Dequindre and East Forest Roads to im | Pavement Improvement | 11/18/2009 | 04/15/2010 | 11/02/2010 | 5103729 | 10.093
5705 | Michigan | WAYNE | DETROIT,MI | 15 | 1082018 | The City of Romulus will resurface .1 miles of Shook Road to improve driving quality and increase service life | Pavement Improvement | 11/18/2009 | 11/18/2009 | 09/15/2010 | 669683.12 | 0.897
5706 | Michigan | WAYNE | DETROIT,MI | 11 | 1082019 | The City of Wayne will resurface .6 miles of Newburgh Road to improve driving quality and increase service life | Pavement Improvement | 11/18/2009 | 11/18/2009 | 07/01/2010 | 512208.86 | 0.558
5707 | Michigan | WAYNE | DETROIT,MI | 15 | 1082020 | The City of Dearborn will resurface .2 miles of the Southfield Service Drive SBd to improve driving quality and increase service life | Pavement Improvement | 11/18/2009 | 03/22/2010 | 10/31/2010 | 148323.91 | 0.18
5708 | Michigan | WAYNE | DETROIT,MI | 14 | 1082021 | The City of Dearborn will resurface .5 miles of Miller Road to improve driving quality and increase service life | Pavement Improvement | 03/12/2010 | 03/22/2010 | 10/31/2010 | 402000 | 0.502
5709 | Michigan | WAYNE | DETROIT,MI | 13 | 1082022 | This project is for the construction of a terminal building expansion to store receive and process increased freight in the Detroit riverfront area. | Other | 04/01/2009 | 01/19/2010 |  | 1000000 | 0.129
5710 | Michigan | WAYNE | DETROIT,MI | 13 | 1082023 | This project is for the construction of an off-shore wharf to expand the capacity to ship and receive water-borne Detroit River freight in the Detroit metropolitan area. | Other | 04/01/2009 | 01/31/2010 |  | 5330000 | 0.129
5711 | Michigan | WAYNE | DETROIT,MI | 13 | 1082024 | The City of Grosse Point Farms will resurface .5 miles of Jefferson Avenue to improve driving quality and increase service life | Pavement Improvement | 11/18/2009 | 02/18/2010 | 08/31/2010 | 311942.24 | 0.456
5712 | Michigan | WAYNE | DETROIT,MI | 13 | 1082025 | The City of Wyandotte will resurface .2 miles of Oak Street in Wyandotte to improve the driving quality and increase the road service life | Pavement Improvement | 11/25/2009 | 11/25/2009 | 07/15/2010 | 206918.13 | 0.225
5713 | Michigan | WAYNE | DETROIT,MI | 13 | 1082026 | The City of Detroit will beautify .4 miles of its downtown on Monroe and Brush Streets by building a streetscape | Transportation Enhancements | 03/23/2010 | 04/05/2010 | 09/30/2012 | 1489002.77 | 0.401
5714 | Michigan | WAYNE | DETROIT,MI | 13 | 1082035 | The City of Detroit will rehabilitate the Larned Street over Dequindre Cut bridge to make the bridge last longer | Bridge Replacement | 01/06/2010 | 03/01/2010 | 05/02/2011 | 1200000 | 0.1
5715 | Michigan | WAYNE | DETROIT,MI | 14 | 1082036 | 2 Miles of Five Mile Road in the City of Detroit will be resurfaced to improve driving quality and increase service life | Pavement Improvement | 01/12/2010 | 06/11/2010 | 10/15/2010 | 1300000 | 1.997
5716 | Michigan | WAYNE | DETROIT,MI | 11 | 1082037 | Wayne County in Canton Township will resurface the Warren Road and Lilley Road intersection to improve the driving quality and increase the road service life | Pavement Improvement | 01/12/2010 | 05/24/2010 | 09/15/2010 | 881000 | 0.012
5717 | Michigan | WAYNE | DETROIT,MI | 15 | 1082038 | Wayne County will resurface 1.0 Miles of Van Born Road fromTelegraph Road to Monroe Road to improve driving quality and increase service life | Pavement Improvement | 01/12/2010 | 04/28/2010 | 09/15/2010 | 1272440.41 | 1.001
5718 | Michigan | WAYNE | DETROIT,MI | 15 | 1082040 | Wayne County will replace the Goddard Extension over Merriman Road bridge to improve safety and increase moblility | Bridge Replacement | 01/27/2010 | 01/27/2010 | 09/30/2010 | 1070230.04 | 0.02
5719 | Michigan | WAYNE | DETROIT,MI | 13 | 1082045 | MDOT will repave US-12 in Wayne County from 28th Street to Rosa Parks to improve the drive quality and make the road smoother | Pavement Improvement | 04/05/2010 | 04/26/2010 | 10/15/2010 | 4842113.93 | 1.779
5720 | Michigan | WAYNE | DETROIT,MI | 13 | 1082046 | MDOT will repave US-12 in Wayne County from Livernois to 28th Street to improve the drive quality and make the road smoother | Pavement Improvement | 02/05/2010 | 02/05/2010 | 12/31/2010 | 3109141.23 | 0.835
5721 | Michigan | WAYNE |  | 15 | 1082048 | This pavement project in Wayne County on Judd from at Haggerty will improve the drive quality and make the road smoother | Pavement Improvement | 02/08/2010 | 07/15/2010 | 08/31/2010 | 231808.67 | 0.518
5722 | Michigan | WAYNE | DETROIT,MI | 13 | 1082050 | This pavement project on Lake Shore Drive from Moross Road to Vernier Road will make the road smoother and improve ride quality | Pavement Improvement | 02/10/2010 | 07/15/2010 | 10/15/2010 | 2163906.49 | 4.163
5723 | Michigan | WAYNE | DETROIT,MI | 13 | 1082052 | This pavement project on Third Street from Vinewood to Northline will make the road smoother and improve ride quality | Pavement Improvement | 02/17/2010 | 04/05/2010 | 10/29/2010 | 255410.75 | 0.451
5724 | Michigan | WAYNE | DETROIT,MI | 11 | 1082053 | This pavement project on Wayne Road Ramps At Michigan Avenue will make the road smoother and improve ride quality | Pavement Improvement | 02/17/2010 | 05/11/2010 | 08/31/2010 | 173129.55 | 0.136
5725 | Michigan | WAYNE | DETROIT,MI | 11 | 1082054 | This pavement project on Edward N. Hines Drive from Ann Arbor Trail to Merriman Road will make the road smoother and improve ride quality | Pavement Improvement | 02/17/2010 | 07/15/2010 | 08/31/2010 | 954872.94 | 3.339
5726 | Michigan | WAYNE | DETROIT,MI | 11,15 | 1082055 | This pavement project on Middlebelt Road from Cherry Hill Road to Warren in Garden City will make the road smoother and improve ride quality | Pavement Improvement | 02/17/2010 | 07/15/2010 | 09/30/2010 | 2504684.12 | 0.968
5727 | Michigan | WAYNE | DETROIT,MI | 11 | 1082057 | This pavement project on Joy Road from Inkster to Beech Daly will make the road smoother and improve ride quality | Pavement Improvement | 02/17/2010 | 07/15/2010 | 08/31/2010 | 1030039.34 | 0.911
5728 | Michigan | WAYNE | DETROIT,MI | 13 | 1082058 | This project in Detroit will upgrade the traffic signal at 29 locations on Jefferson Avenue to improve traffic flow and enhance safety. | Safety/Traffic Management | 06/25/2010 |  | 12/15/2010 | 1384609.62 | 2.188
5729 | Michigan | WEXFORD |  | 2 | 1083006 | This pavement project in Wexford County on Various Roads at Various Locations will improve the drive quality and make the road smoother | Pavement Improvement | 05/05/2010 |  | 08/01/2010 | 365485.3 | 27.243
5730 | Michigan | WEXFORD |  | 2 | 1083007 | This pavement project on Boon Road from Mitchell Street to the west will make the road smoother and improve ride quality | Pavement Improvement | 06/15/2010 | 06/21/2010 | 07/01/2010 | 193929.41 | 0.933
5731 | Michigan | STATEWIDE |  | 2,3 | 1084044 | At various locations in metropolitan Detroit this project will install protective fences and security for power towers to improve safety. | Safety/Traffic Management | 05/11/2009 | 05/11/2009 | 03/15/2012 | 2606740 | 0
5732 | Minnesota | TODD, WADENA |  | 7, 8 | 09ES001 | Remove and replace pavement on State Highway 10 from Wadena to Staples. Add turn lanes, replace signs, pave shoulders, install rumble strips and lighting and improve pedestrian crossings. | Pavement Improvement | 03/23/2009 | 05/01/2009 | 07/15/2009 | 7312124 | 21.757
5733 | Minnesota | BIG STONE |  | 7 | 09ES002 | Placement of asphalt pavement on State Highway 75 form Graceville to Ortonville. | Pavement Improvement | 04/23/2009 | 05/04/2009 | 07/31/2009 | 5143074 | 19.036
5734 | Minnesota | MILLE LACS |  | 8 | 09ES003 | Remove and replace pavement on State Highway 169 from Princeton to Milaca. | Pavement Improvement | 03/11/2009 | 05/01/2009 | 09/25/2009 | 4163703 | 13.696
5735 | Minnesota | RICE |  | 2 | 09ES004 | Replace pavement, add new median guardrail and improve water drainage pipes on northbound and southbound lanes of I-35 through Faribault. | Pavement Improvement | 05/04/2009 | 05/11/2009 | 09/11/2009 | 4769068 | 4.875
5736 | Minnesota | STATEWIDE |  | 1,2,7 | 09ES006 | Construct guardrail improvements on State Highways throughout south central and western Minnesota to improve safety. | Safety/Traffic Management | 04/16/2009 | 05/04/2009 | 08/04/2009 | 471228.93 | 78.092
5737 | Minnesota | STATEWIDE |  | 1,2 | 09ES007 | Replace guardrail on State Highways throughout southeast Minnesota. | Safety/Traffic Management | 04/17/2009 | 05/11/2009 | 10/01/2009 | 1695398 | 217.325
5738 | Minnesota | MOWER, OLMSTED |  | 1 | 09ES008 | Replace pavement, upgrade guardrail and improve water drainage pipes on eastbound I-90 from Stewartville to 8.6 miles west. | Pavement Improvement | 04/17/2009 | 05/04/2009 | 07/05/2009 | 2108897 | 8.633
5739 | Minnesota | FREEBORN |  | 1 | 09ES009 | Replace pavement on I-90, upgrade guardrail and improve water drainage pipes from Albert Lea to Alden. | Pavement Improvement | 03/23/2009 | 05/01/2009 | 09/30/2009 | 17117366 | 10.045
5740 | Minnesota | WINONA |  | 1 | 09ES010 | Replace existing pavement, upgrade guardrail and improve water drainage pipes on westbound I-90 from east of State Highway 74 to west of State Highway 43. | Pavement Improvement | 06/10/2009 | 06/22/2009 | 08/28/2009 | 4511492 | 14.099
5741 | Minnesota | STEARNS, TODD |  | 6, 7 | 09ES011 | Install cable median barrier on I-94 from Sauk Centre to the Douglas/Todd County Line. | Safety/Traffic Management | 03/23/2009 | 05/01/2009 | 09/20/2009 | 1551326 | 11.955
5742 | Minnesota | STATEWIDE |  | 8 | 09ES012 | Install hazardous curve signs at various locations on State Highways 1, 38, 65, and 217 in Itasca, Koochiching and St Louis Counties in Northeast Minnesota. | Safety/Traffic Management | 04/23/2009 | 05/11/2009 | 06/21/2009 | 45740 | 48.909
5743 | Minnesota | WINONA |  | 1 | 09ES013 | Replace existing pavement, upgrade guardrail and improve water drainage pipes on eastbound and westbound I-90 from Nadine to Dakota. | Pavement Improvement | 04/27/2009 | 07/13/2009 | 10/23/2009 | 3016818 | 4.996
5744 | Minnesota | SIBLEY |  | 7 | 09ES014 | Remove and replace pavement on State Highway 93 from Liqueur to Highway 169. | Pavement Improvement | 04/15/2009 | 05/11/2009 | 08/07/2009 | 437312 | 0.83
5745 | Minnesota | KANDIYOHI |  | 7 | 09ES015 | Resurface Highway 23 from County Road 31 near New London to County Road 6 near Paynesville in Kandiyohi County. | Pavement Improvement | 03/23/2009 | 05/01/2009 | 10/12/2009 | 1202117 | 6.652
5746 | Minnesota | AITKIN |  | 8 | 09ES016 | Resurfacing and safety improvements on State Highway 65 from State Highway 210 in McGregor to south of Big Sandy River Bridge. | Pavement Improvement | 06/10/2009 | 06/17/2009 | 08/21/2009 | 5161594 | 11.395
5747 | Minnesota | LAKE |  | 8 | 09ES017 | Skid prevention in Silver Cliff and Lafayette Tunnels on Highway 61 north of Two Harbors. | Safety/Traffic Management | 04/24/2009 | 04/27/2009 | 05/26/2009 | 78722 | 3.72
5748 | Minnesota | CARLTON |  | 8 | 09ES018 | Install plantings to create a living snow fence to prevent blowing snow from crossing two bridges on I-35 South of Carlton. | Transportation Enhancements | 03/19/2009 | 06/01/2009 | 07/01/2009 | 77971 | 0
5749 | Minnesota | ST LOUIS |  | 8 | 09ES019 | Reinforced concrete pavement on State Highway 169 from South of County Road 5 to west of County Road 67 near Chisholm where underground mining had occurred. | Pavement Improvement | 06/04/2009 | 06/08/2009 | 06/25/2010 | 7925926 | 0.74
5750 | Minnesota | BELTRAMI, CASS, STATEWIDE |  | 7, 8 | 09ES020 | Replace traffic signal at State Highway 197 and Ridgeway Avenue in Bemidji and at State Highway 2 and Grant Utley Avenue in Cass Lake. | Safety/Traffic Management | 07/07/2009 | 07/15/2009 | 08/15/2009 | 317685 | 0
5751 | Minnesota | PENNINGTON, MARSHALL |  | 7 | 09ES021 | Resurface State Highway 1 from Warren to Thief River Falls. | Pavement Improvement | 03/11/2009 | 05/01/2009 | 10/01/2009 | 6632798 | 26.896
5752 | Minnesota | BELTRAMI |  | 7 | 09ES022 | Lowering roadway by removal of bridges over abandoned railroad tracks along with additional safety improvements on State Highway 2 in Bemidji. | Pavement Improvement | 07/23/2009 | 07/23/2009 | 09/30/2009 | 2515000 | 0.863
5753 | Minnesota | STEARNS, WRIGHT |  | 6 | 09ES023 | Repair pavement on I-94 from Clearwater to Monticello. | Pavement Improvement | 03/18/2009 | 05/01/2009 | 08/19/2009 | 6312466 | 47.868
5754 | Minnesota | STEARNS |  | 6,7 | 09ES024 | Remove and replace pavement and paint bridge at County Road 143 and I-94. Remove and replace pavement and paint bridge at County road 186 and I-94. | Bridge Improvement | 03/18/2009 | 05/01/2009 | 10/15/2009 | 1592142 | 48.949
5755 | Minnesota | OTTER TAIL, GRANT |  | 7 | 09ES025 | Concrete resurfacing and rest area preservation on I-94 north of Fergus Falls to Grant County line. | Pavement Improvement | 05/04/2009 | 05/11/2009 | 06/18/2010 | 8762711 | 20.797
5756 | Minnesota | MOWER |  | 1 | 09ES026 | Replace west bound exit ramp bridge on I-90 into Austin. | Bridge Replacement | 05/08/2009 | 07/17/2009 | 09/01/2010 | 5075891 | 19.229
5757 | Minnesota | NICOLLET |  | 1 | 09ES029 | Replace utilities, reconstruct pavement and install signal and pedestrian crossing on State Highway 169 in St. Peter. | Pavement Improvement | 06/01/2009 | 06/01/2009 | 07/25/2010 | 16422468 | 1.594
5758 | Minnesota | JACKSON |  | 1 | 09ES031 | Parking lot and sidewalk improvements at two rest areas on I-90 near Jackson. | Pavement Improvement | 09/11/2009 | 09/21/2009 | 09/27/2009 | 344287.42 | 0.556
5759 | Minnesota | CHIPPEWA |  | 7 | 09ES033 | Resurface Highway 7 from Montevideo to Clara City in Chippewa County. | Pavement Improvement | 03/18/2009 | 05/01/2009 | 08/28/2009 | 9897248 | 15.238
5760 | Minnesota | STATEWIDE |  | 1,7 | 09ES034 | Guardrail replacement at various locations in Southwest Minnesota | Safety/Traffic Management | 06/30/2009 | 06/30/2009 | 06/30/2010 | 921855 | 33.993
5761 | Minnesota | REDWOOD |  | 7 | 09ES035 | Resurface Highway 68 from Milroy to Wabash in Redwood County. | Pavement Improvement | 03/11/2009 | 08/01/2009 | 11/02/2009 | 2219889 | 15.322
5762 | Minnesota | CHISAGO, ISANTI |  | 8 | 09ES036 | Remove and replace pavement on State Highway 95 from east of Cambridge to the Isanti/Chisago County Line, including culvert replacement. | Pavement Improvement | 03/11/2009 | 05/01/2009 | 08/07/2009 | 2771586 | 9.669
5763 | Minnesota | ST LOUIS | DULUTH-SUPERIOR (WI) | 8 | 09ES039 | Resurface State Highway 194 from northwest of Anderson Road to northwest of Masada Ave in the Duluth Heights neighborhood of Duluth. | Pavement Improvement | 05/06/2009 | 05/26/2009 | 07/15/2009 | 1572086 | 1.857
5764 | Minnesota | ST LOUIS | DULUTH-SUPERIOR (WI) | 8 | 09ES040 | Roadway Resurfacing, curb & gutter removal and replacement, sidewalks, lighting and safety improvements on Highway 23 from East of 130th Street to North of County Road 3 in the Gary and Fond Du Lac ne | Pavement Improvement | 06/05/2009 | 06/15/2009 | 09/30/2009 | 3469216 | 3.881
5765 | Minnesota | ST LOUIS |  | 8 | 09ES041 | Pavement reconstruction and bridge rehabilitation on State Highway 53 from north of Highway 194 to north of Highway 33. | Pavement Improvement | 06/05/2009 | 06/11/2009 | 10/30/2009 | 12582156 | 13.632
5766 | Minnesota | STATEWIDE |  | 7,8 | 09ES042 | Rest area sign replacement at five locations on Highway 2. | Safety/Traffic Management | 06/01/2009 | 07/06/2009 | 08/28/2009 | 115134.4 | 0
5767 | Minnesota | ITASCA |  | 8 | 09ES043 | Resurfacing on Highway 2 west of Deer River from County Road 18 to west of Highway 6, and on Highway 6 north of Deer River. | Pavement Improvement | 04/16/2009 | 06/01/2009 | 10/30/2009 | 4031685 | 16.96
5768 | Minnesota | MILLE LACS |  | 8 | 09ES046 | Remove and replace pavement on Highway 169 from Rum River rest area to south of Omani. | Pavement Improvement | 04/08/2009 | 05/01/2009 | 07/24/2009 | 4788587 | 7.686
5769 | Minnesota | MILLE LACS |  | 8 | 09ES047 | Replace bridge on Highway 23 over the Rum River in Milaca. | Bridge Replacement | 04/20/2009 | 06/01/2009 | 11/13/2009 | 1692300 | 0.598
5770 | Minnesota | ISANTI |  | 8 | 09ES048 | Replace bridge on Highway 95 over the Rum River west of Cambridge. | Bridge Replacement | 04/20/2009 | 05/01/2009 | 11/13/2009 | 1410631 | 0.042
5771 | Minnesota | KANABEC |  | 8 | 09ES049 | Remove and replace bridge on State Highway 107 over the Snake River in Garston. | Bridge Replacement | 04/20/2009 | 06/01/2009 | 11/13/2009 | 1322178 | 0.034
5772 | Minnesota | STATEWIDE |  | 6,7,8 | 09ES050 | Improve road safety and operations by coordinating 85 traffic signals in Big Lake, Brainerd, Baxter, Elk River, Monticello, St. Cloud and St. Michael. | Safety/Traffic Management | 08/26/2009 | 08/26/2009 | 04/27/2011 | 413094 | 0
5773 | Minnesota | DOUGLAS |  | 7 | 09ES052 | Install a traffic signal at I-94 and State Highway 27 in Alexandria. | Safety/Traffic Management | 04/10/2009 | 07/01/2009 | 09/07/2009 | 227909 | 0
5774 | Minnesota | OTTER TAIL |  | 7 | 09ES053 | Install a traffic signal at State Highway 210 and Redwood Lane in Fergus Falls. | Safety/Traffic Management | 08/19/2009 | 09/12/2009 | 10/28/2009 | 380084 | 0
5775 | Minnesota | WILKIN |  | 7 | 09ES054 | Install railroad gates and signals at State Highway 9 west of Nashua. | Safety/Traffic Management | 06/10/2009 | 08/03/2009 | 06/15/2010 | 115403 | 0
5776 | Minnesota | STEVENS |  | 7 | 09ES055 | Install railroad gates, signals cantilevers at State Highway 28 southwest of Morris. | Safety/Traffic Management | 05/06/2009 | 08/03/2009 | 05/12/2010 | 263338 | 0.001
5777 | Minnesota | FARIBAULT, FREEBORN |  | 1 | 09ES059 | Remove and replace pavement on I-90 between Alden and State Highway 22. | Pavement Improvement | 06/10/2009 | 06/16/2009 | 09/30/2009 | 3923374 | 7.111
5778 | Minnesota | ROCK |  | 1 | 09ES060 | Build new state entrance sign at the South Dakota border on I-90 at the Beaver Creek rest area. | Transportation Enhancements | 04/28/2009 | 08/01/2009 | 10/01/2009 | 66806 | 0
5779 | Minnesota | MORRISON |  | 8 | 09ES061 | Plant living snow fence on Highway 371 in Crow Wing and Morrison Counties. | Transportation Enhancements | 04/08/2009 | 05/01/2009 | 07/01/2009 | 119698 | 1.34
5780 | Minnesota | ST LOUIS | DULUTH-SUPERIOR (WI) | 8 | 09ES063 | Preserve the historic Aerial lift bridge over the Duluth Shipping Canal on Park Point, replacing lead based paint, structural steel and concrete elements. | Transportation Enhancements | 04/08/2009 | 04/08/2009 | 03/20/2011 | 4900000 | 0.1
5781 | Minnesota | ST LOUIS | MINNEAPOLIS-ST. PAU, MN | 8 | 09ES064 | Resurfacing, curb and drainage repairs on the Rice Lake Road from Arrowhead Road to Masada Avenue in Duluth. | Pavement Improvement | 07/21/2009 | 08/06/2009 | 09/18/2009 | 1178846 | 2.33
5782 | Minnesota | AITKIN |  | 8 | 09ES066 | Replace bridge on County Road 14 northeast of Highway 65, north of McGregor in Aitkin County. | Bridge Replacement | 06/18/2009 | 06/22/2009 | 10/23/2009 | 1180574 | 0.1
5783 | Minnesota | HUBBARD |  | 8 | 09ES067 | Replacement of bridge on County Road 9 over the Schoolcraft River, about 10 miles southwest of Bemidji in Hubbard County. | Bridge Replacement | 07/01/2009 | 06/16/2009 | 10/16/2009 | 416683.9 | 0.1
5784 | Minnesota | KITTSON |  | 7 | 09ES068 | Replacement of bridge on County Road 1 over the North Branch of Two Rivers, north of Hillock in Kittson County. | Bridge Replacement | 06/16/2009 | 06/22/2009 | 11/01/2009 | 798863 | 0.1
5785 | Minnesota | BELTRAMI |  | 7 | 09ES069 | Rehabilitate surface, new curb and gutter, replace sewers and fix water lines on Irvine Ave from 3rd St. to State Highway 197 in Bemidji. | Pavement Improvement | 06/30/2009 | 07/06/2009 | 11/01/2009 | 1453986 | 1.4
5786 | Minnesota | MARSHALL |  | 7 | 09ES070 | West of Grille on County Road 7, replace bridge with a box culvert in Marshall County. | Bridge Replacement | 06/03/2009 | 08/05/2009 | 08/07/2009 | 65353 | 0.05
5787 | Minnesota | MARSHALL |  | 7 | 09ES071 | Replace timber bridge on County Road 15 over the Snake River with two culverts, West of Warren in Marshall County. | Bridge Replacement | 07/17/2009 | 08/03/2009 | 09/04/2009 | 537485 | 0.1
5788 | Minnesota | MORRISON |  | 8 | 09ES072 | Reconstruction of Lindbergh Drive from State Highway 27 to the North city limits in Little Falls. | Pavement Improvement | 08/21/2009 | 08/24/2009 | 11/15/2009 | 894237 | 0.997
5789 | Minnesota | ISANTI |  | 8 | 09ES073 | Replace bridge on County Road 6 over Stanch field Creek West of Grandee in Isanti County. | Bridge Replacement | 08/17/2009 | 08/26/2009 | 12/25/2009 | 369849 | 0.1
5790 | Minnesota | MORRISON |  | 8 | 09ES074 | Reconstruct County Road 203 beginning at Highway 10 and add additional asphalt surface on County Road 203 to County Road 2 in Morrison County, south of Motley. | Pavement Improvement | 05/27/2009 | 06/15/2009 | 10/10/2009 | 626164 | 3.98
5791 | Minnesota | BECKER |  | 7 | 09ES075 | Replace existing bridge with three culverts on County Highway 7, north of Lake Park in Becker County. | Bridge Replacement | 08/31/2009 | 08/19/2009 | 09/09/2009 | 304089 | 0.1
5792 | Minnesota | DOUGLAS |  | 7 | 09ES076 | Resurface County Road 7 from the north city limits of Brandon to the south city limits of Millersville in Douglas County. | Pavement Improvement | 05/29/2009 | 05/29/2009 | 07/31/2009 | 813899 | 6.73
5793 | Minnesota | SWIFT |  | 7 | 09ES077 | Replace bridge with two culverts on County Road 33 over Mud Creek, North East of Murdock in Swift County. | Bridge Replacement | 07/01/2009 | 07/13/2009 | 08/15/2009 | 244039.21 | 0.04
5794 | Minnesota | TRAVERSE |  | 7 | 09ES078 | Place asphalt pavement and gravel shoulders on County Road 6 from the South Dakota State line to Highway 75, north of Wheaton in Traverse County. | Pavement Improvement | 06/16/2009 | 06/18/2009 | 09/15/2009 | 1441828 | 1.39
5795 | Minnesota | STEELE |  | 1 | 09ES079 | Replace Cedar Avenue bridge over Maple Creek in Owatonna; also replace two railroad crossing signals. | Pavement Improvement | 07/15/2009 | 08/04/2009 | 07/16/2010 | 1365638 | 0.1
5796 | Minnesota | GOODHUE |  | 2 | 09ES080 | Reconstruct County Highway 1 in Red Wing, including bridge replacement, new pavement, drainage pipe replacement, and new storm sewer in Goodhue County. | Pavement Improvement | 06/09/2009 | 06/09/2009 | 11/30/2009 | 1784727 | 1.16
5797 | Minnesota | JACKSON |  | 1 | 09ES081 | Replace bridge on County Road 20 southwest of Kabana in Jackson County. | Bridge Replacement | 07/16/2009 | 07/27/2009 | 10/02/2009 | 326354.34 | 0.1
5798 | Minnesota | WASECA |  | 1 | 09ES082 | Replace bridge on County Road 3 over the Liqueur River south of Janesville in Waseca County. | Bridge Replacement | 07/21/2009 | 07/23/2009 | 11/15/2009 | 609994 | 0.1
5799 | Minnesota | WASECA |  | 1 | 09ES083 | Replace bridge with culvert to carry Loco Creek under County Road 3, northeast of Janesville in Waseca County. | Bridge Replacement | 07/21/2009 | 09/22/2009 | 10/30/2009 | 328828 | 0.11
5800 | Minnesota | NOBLES |  | 1 | 09ES084 | Resurface County Road 1 from Brewster to Kin brae in Nobles County. | Pavement Improvement | 06/04/2009 | 08/24/2009 | 09/21/2009 | 1521460.06 | 8.31
5801 | Minnesota | BLUE EARTH |  | 1 | 09ES085 | Construct a new bridge on a new roadway on County Road 12 over the DM&E RR in east Mankato in Blue Earth County | New Bridge Construction | 08/19/2009 | 08/24/2009 | 09/24/2010 | 3073031 | 0.57
5802 | Minnesota | CHIPPEWA |  | 7 | 09ES086 | Replace bridge on County Road 32, southeast of the City of Milan in Chippewa County. | Bridge Replacement | 06/08/2009 | 07/27/2009 | 10/23/2009 | 476489 | 0.1
5803 | Minnesota | LYON |  | 7 | 09ES087 | Replace bridge on County Road 3 over the south branch of the Yellow Medicine River, south of Minnesota in Lyon County. | Bridge Replacement | 06/19/2009 | 06/24/2009 | 11/15/2009 | 308307 | 0.05
5804 | Minnesota | MCLEOD |  | 7 | 09ES088 | Replace timber bridge on County Road 7 over High Island County Road south of Stewart in McLeod County. | Bridge Replacement | 06/01/2009 | 06/15/2009 | 08/24/2009 | 317742.12 | 0.1
5805 | Minnesota | LINCOLN |  | 7 | 09ES089 | Resurface County Road 6 from South County Line to Highway 14, 3 miles south of Tyler. Resurface County Road 9 from County Road 1 to County Road 2, West of Verdi. Resurface County Road 11 from County R | Pavement Improvement | 05/21/2009 | 05/19/2009 | 06/16/2009 | 792677.8 | 4.01
5806 | Minnesota | RENVILLE |  | 7 | 09ES090 | Replace bridge on County Road 9 over Chetamba Creek in Renville County. | Bridge Replacement | 06/24/2009 | 06/24/2009 | 09/30/2009 | 332117 | 0.1
5807 | Minnesota | YELLOW MEDICINE |  | 7 | 09ES091 | Replace bridge on County Road 3 over Lac Qui Parle River in Yellow Medicine County. | Bridge Replacement | 06/10/2009 | 08/10/2009 | 08/21/2009 | 209872 | 0.1
5808 | Minnesota | ITASCA |  | 8 | 09ES092 | Complete reconstruction, including utilities on 7th Avenue Southeast from 17th Street Southeast to 33rd Street Southeast in Grand Rapids. | Pavement Improvement | 06/03/2009 | 06/04/2009 | 07/15/2010 | 1498037 | 1.535
5809 | Minnesota | BELTRAMI |  | 8 | 09ES093 | Resurface County Road 23 from County Highway 29 to County Highway 32 in Beltrami County. | Pavement Improvement | 06/18/2009 | 06/22/2009 | 07/10/2009 | 776124.27 | 4.82
5810 | Minnesota | CLEARWATER |  | 7 | 09ES094 | Resurfacing County Road 5 from Clearbrook to the Red Lake Reservation line in Clearwater County. | Pavement Improvement | 06/19/2009 | 06/22/2009 | 07/09/2009 | 1240119.69 | 8.83
5811 | Minnesota | TODD |  | 7 | 09ES095 | Resurfacing on County Road 2 from Highway 28 to County Road 11 northeast of Sauk Center in Todd County. | Pavement Improvement | 06/18/2009 | 06/25/2009 | 09/11/2009 | 866884.64 | 10.6
5812 | Minnesota | SHERBURNE |  | 6 | 09ES096 | Replace bridge on County Road 5 over St. Francis River south of Sherburne County Road 3. | Bridge Replacement | 06/04/2009 | 06/04/2009 | 10/02/2009 | 469472 | 0.11
5813 | Minnesota | WRIGHT |  | 6 | 09ES097 | Reconstruction and widening including curb and gutter and recreational trail on Jamison Ave from County Road 119 to County Road 18 in St. Michael. | Pavement Improvement | 06/22/2009 | 06/23/2009 | 10/16/2009 | 2136106 | 1.451
5814 | Minnesota | OTTER TAIL |  | 7 | 09ES098 | Resurface and add shoulders to County Road 1 from Sophus Anderson Rd to County Road 10 east of Fergus Falls in Ottertail County. | Pavement Improvement | 07/07/2009 | 07/07/2009 | 09/30/2009 | 1206813.06 | 5.08
5815 | Minnesota | OTTER TAIL |  | 7 | 09ES099 | Replace bridge over Otter Tail River on Concord Street in Fergus Falls. | Bridge Replacement | 06/30/2009 | 07/06/2009 | 06/26/2010 | 776855 | 0.1
5816 | Minnesota | YELLOW MEDICINE |  | 7 | 09ES100 | Resurface County Road 8 from Highway 67 to County Road 5, north of Clarkfield in Yellow Medicine County. | Pavement Improvement | 06/03/2009 | 07/08/2009 | 09/18/2009 | 907551.7 | 3.99
5817 | Minnesota | KANDIYOHI, RENVILLE |  | 7 | 09ES101 | Resurface County Road 2, south of County Road 77 to Highway 7 in Renville and Kandiyohi Counties. | Pavement Improvement | 05/28/2009 | 06/30/2009 | 08/01/2010 | 2297109 | 1.92
5818 | Minnesota | ST LOUIS |  | 8 | 09ES103 | Resurfacing on St. Louis County Road 4 from Arrowhead Road to Martin Road in Duluth. | Pavement Improvement | 06/26/2009 | 07/29/2009 | 10/09/2009 | 1895908 | 3.42
5819 | Minnesota | STEARNS |  | 6 | 09ES104 | Reconstruction and widening of Pinecone road from County Road 120 to County Road 134 in St. Cloud, including roundabouts. | Pavement Improvement | 08/17/2009 | 08/20/2009 | 05/30/2010 | 1509238 | 0.6
5820 | Minnesota | STEARNS |  | 6 | 09ES105 | Extending 28th Ave from State Highway 23 to County Road 137 in the City of Waite Park. | Pavement Improvement | 09/28/2009 | 09/28/2009 | 07/16/2010 | 2433666 | 1.3
5821 | Minnesota | OLMSTED | ROCHESTER | 1 | 09ES106 | Replace 4th Street bridge over Bear Creek in Rochester. | Bridge Replacement | 08/26/2009 | 09/01/2009 | 10/15/2010 | 2810822 | 0.1
5822 | Minnesota | STATEWIDE |  | 8 | 09ES107 | Replace deteriorated landscaping at the state entry signs at the US/Canada border on Highway 61 near Grand Portage, and the Minnesota/Wisconsin border on I-535 and Highway 2 in Duluth. | Transportation Enhancements | 04/16/2009 | 06/01/2009 | 11/15/2011 | 132579 | 0
5823 | Minnesota | FREEBORN |  | 1 | 09ES122 | Replacing landscaping around Entering and Leaving Minnesota Signs on I-35 at the Iowa Border near Albert Lea. | Transportation Enhancements | 05/13/2009 | 08/01/2009 | 10/01/2009 | 60642 | 0
5824 | Minnesota | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 8 | 09ES124 | Plant living snow fence on I-35 at County Road 17 south of North Branch. | Transportation Enhancements | 04/24/2009 | 04/01/2009 | 11/01/2010 | 79895 | 0
5825 | Minnesota | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 8 | 09ES125 | Remove and replace pavement on I-35 north of North Branch; repair drainage and replace lighting and pavement at the Goose Creek Rest Area. | Pavement Improvement | 07/08/2009 | 07/09/2009 | 10/30/2009 | 9096643 | 7.113
5826 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 6 | 09ES126 | Reconstruct State Highway 5 from south of State Highway 36 to Manning Avenue. Drainage improvements were made through this section and west to I-694. | Pavement Improvement | 04/24/2009 | 08/04/2009 | 10/03/2009 | 2066476 | 7.414
5827 | Minnesota | DAKOTA, HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES127 | Replace lighting on Highway 100 from 50th in Edina to Excelsior Boulevard in St. Louis Park. Replace lighting on Highway 100 from I-494 to Vernon Avenue in Edina. Replace lighting on I-35W from Cliff | Safety/Traffic Management | 04/24/2009 | 06/01/2009 | 05/20/2010 | 2296429 | 5.137
5828 | Minnesota | DAKOTA, STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES128 | Remove and replace 2 traffic signals on State Highway 13 in Burnsville. | Safety/Traffic Management | 05/22/2009 | 08/01/2009 | 11/06/2009 | 493780 | 0.262
5829 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES130 | Rebuild the cable median barrier on I-94 from I-494 in Maple Grove to the Crow River. | Safety/Traffic Management | 04/24/2009 | 06/01/2009 | 09/07/2009 | 1239274 | 10.873
5830 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 6 | 09ES131 | Remove and replace pavement at the north junction of I-35E and I-35W, including extending a merge lane on I-35. | Pavement Improvement | 07/09/2009 | 08/03/2009 | 10/30/2009 | 6139952 | 25.67
5831 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES132 | Plant landscaping on I-494 from State Highway 5 to I-394. | Other | 05/28/2009 | 08/01/2009 | 10/30/2012 | 573664 | 7.522
5832 | Minnesota | POLK |  | 7 | 09ES133 | Replace the bridge over the Red River and approaches on County Road 9 in Polk County. | Bridge Replacement | 09/11/2009 | 09/02/2009 | 10/01/2010 | 6763057 | 0.01
5833 | Minnesota | CASS |  | 8 | 09ES134 | Resurface Sucker Bay Road in Cass County and install Rail Road crossing signal and gates at BNSF Rail Road. | Safety/Traffic Management | 01/15/2010 | 01/20/2010 | 09/30/2010 | 300000 | 0
5834 | Minnesota | CLAY | FARGO-MOORHEAD (ND) | 7 | 09ES135 | Restore landscaping at state entry sign in Moorhead. | Transportation Enhancements | 06/04/2009 | 08/01/2009 | 10/19/2009 | 65879 | 0.3
5835 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES136 | Construct State Highway 610 from County Road 81 to State Highway 169 in Maple Grove and Brooklyn Park. | Pavement Widening | 05/14/2009 | 08/01/2009 | 06/01/2012 | 28440763 | 3.226
5836 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,5,6 | 09ES137 | Remove and replace traffic signals and lighting on state highways and interstate throughout the Twin Cities region. | Safety/Traffic Management | 05/27/2009 | 07/01/2009 | 12/28/2009 | 1927016 | 25.444
5837 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES138 | Add a traffic lane to the ramp from westbound I-494 to westbound US 212. | Pavement Improvement | 07/23/2009 | 08/17/2009 | 09/23/2009 | 1275463 | 0.758
5838 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES139 | Separate existing westbound and eastbound I-494 interchange ramps as they merge onto I-35E southbound. | Safety/Traffic Management | 07/23/2009 | 08/07/2009 | 09/21/2009 | 836447 | 0.386
5839 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,5,6,8 | 09ES140 | Install Fiber Optic cable throughout the Twin Cities region on state highways and interstate. | Safety/Traffic Management | 05/27/2009 | 08/01/2009 | 10/31/2010 | 1246688 | 0
5840 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,5,6,8 | 09ES141 | Install pavement markings throughout the Twin Cities region on state highways and interstate. | Pavement Improvement | 05/27/2009 | 08/01/2009 | 11/15/2009 | 1140008 | 14.581
5841 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES143 | Remove and replace lighting on US 169 from I-494 to I-94. | Safety/Traffic Management | 05/27/2009 | 08/01/2009 | 06/19/2010 | 4525919 | 15.652
5842 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES145 | In Rosemount and Inver Grove Heights, resurface road and repair four bridges on Highway 52 from County Road 42 to Highway 55 in Dakota County. | Pavement Improvement | 10/06/2009 | 10/13/2009 | 06/04/2010 | 3944447 | 3.613
5843 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 6 | 09ES146 | Remove and replace pavement on State Highway 95 from Stillwater 16 to State Highway 97. | Pavement Improvement | 06/22/2009 | 09/08/2009 | 06/04/2010 | 5145778 | 15.32
5844 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,5,6,8 | 09ES147 | Installation of changeable message signs in the Minneapolis-St. Paul Metro area. | Safety/Traffic Management | 09/03/2009 | 09/09/2009 | 05/13/2010 | 1470917 | 0
5845 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4 | 09ES148 | Storm tunnel restoration on I-35E at Shepard Road in St. Paul. | Pavement Improvement | 10/21/2009 | 10/21/2009 | 05/31/2010 | 1682848 | 0.475
5846 | Minnesota | ANOKA, RAMSEY | MINNEAPOLIS-ST. PAU, MN | 6 | 09ES149 | Resurfacing of US 10 from State Highway 65 in Blaine to North of junction with I-35W in Shoreview. | Pavement Improvement | 03/04/2010 | 04/19/2010 | 09/03/2010 | 9173634 | 2.975
5847 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES155 | Landscaping along I-94 from I-494 in Maple Grove to Brooklyn Blvd in Brooklyn Park, Hennepin County. | Transportation Enhancements | 08/03/2009 | 08/03/2009 | 10/31/2012 | 210494 | 5.51
5848 | Minnesota | CARVER | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES156 | Landscape Highway 212 interchange at State Highway 101 and at Carver County Road 17 (Powers Blvd) in Chanhassen in Carver County. | Transportation Enhancements | 08/03/2009 | 08/03/2009 | 10/30/2012 | 236776 | 0
5849 | Minnesota | CARVER | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES157 | Landscape Highway 212 interchange at Carver County Road 10 (Engler Blvd) and Carver County Road 11 in Chaska, Carver County. | Transportation Enhancements | 08/03/2009 | 08/03/2009 | 10/30/2012 | 358078 | 0
5850 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES158 | Landscape Highway 212 at Hennepin County Road 4 and Dell Road in Eden Prairie. | Transportation Enhancements | 08/03/2009 | 08/03/2009 | 10/30/2012 | 201631 | 0
5851 | Minnesota | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 8 | 09ES159 | Reconstruct interchange of Highway 95 and I-35 in North Branch, Chisago County. | Pavement Improvement | 11/16/2009 | 11/19/2009 | 11/20/2010 | 3765286 | 1.045
5852 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES161 | In Rosemount and Inver Grove Heights of Dakota County, resurface, revise signals and improve accessibility on 6 miles of Highway 3 from County Road 42 to Highway 149 in northbound and southbound lanes | Pavement Improvement | 03/03/2010 | 05/10/2010 | 06/30/2010 | 2947591 | 6.341
5853 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES162 | Replace concrete, replace lighting, and add acceleration lane to I-94 from the Crow River in Rogers to I-494 in Maple Grove. | Pavement Improvement | 02/17/2010 | 05/03/2010 | 09/24/2010 | 2791108 | 4.245
5854 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES163 | Resurface shoulders on Highway 252 from I-694 to Highway 610 in Brooklyn Park, to accommodate buses. Project also replaced curb and gutter and updated pedestrian facilities. | Safety/Traffic Management | 10/14/2009 |  | 10/01/2010 | 2848375 | 4.456
5855 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES165 | Replace lighting on Highway 62 from State Highway 212 in Eden Prairie to Gleason Road in Edina. | Safety/Traffic Management | 10/19/2009 | 04/05/2010 | 05/28/2010 | 827898 | 1.212
5856 | Minnesota | STATEWIDE |  | 2,4,5,6,8 | 09ES166 | Guardrail upgrades at various locations around the east Minneapolis-St. Paul Metro area. | Safety/Traffic Management | 09/12/2009 | 05/01/2010 | 07/17/2010 | 288884 | 0
5857 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,5 | 09ES167 | Guardrail upgrades at various locations around the west Minneapolis-St. Paul Metro area. | Safety/Traffic Management | 08/24/2009 | 04/01/2010 | 07/03/2010 | 232723 | 0
5858 | Minnesota | SCOTT |  | 2 | 09ES168 | Preserve historic bridge in downtown Shakopee as non-motorized Minnesota River crossing in Scott County. | Transportation Enhancements | 10/26/2009 | 02/01/2010 | 09/17/2010 | 5557690 | 0
5859 | Minnesota | ANOKA | MINNEAPOLIS-ST. PAU, MN | 6 | 09ES169 | Reconstruct interchange at I-35 and County Road 14. | Pavement Improvement | 12/04/2009 | 01/26/2010 | 06/30/2011 | 6825000 | 1.041
5860 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 5 | 09ES171 | Construct interchange at Highway 7 & Wooddale Avenue including pedestrian walkway and trail in St. Louis Park. | New Bridge Construction | 09/25/2009 | 09/29/2009 | 11/01/2010 | 3465000 | 0.129
5861 | Minnesota | CLAY | FARGO-MOORHEAD (ND) | 7 | 09ES173 | Reconstruct 20th Street between 12th Avenue South and 24th Avenue South replacing pavement, curb and gutter and storm sewer. | Other | 08/26/2009 | 08/28/2009 | 11/13/2009 | 1098380 | 0.42
5862 | Minnesota | CLAY | FARGO-MOORHEAD (ND) | 7 | 09ES174 | Repair and repaint bridge over the Red River on Center Avenue in Moorhead. | Bridge Improvement | 09/21/2009 | 10/05/2009 | 07/01/2010 | 909806 | 0.1
5863 | Minnesota | ST LOUIS |  | 8 | 09ES175 | Construct asphalt pavement on the Mesabi Trail system from the Giants Ridge recreation area near Biwabik to State Highway 135. Including pedestrian bridge over Narrows between Sabin Lake and Wynne. | Transportation Enhancements | 12/22/2009 | 04/26/2010 | 09/15/2010 | 1407835 | 0
5864 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 09ES176 | Realign and widen County Road 10 from County Road 101 to West of Peony Lane in Maple Grove. | Pavement Widening | 09/02/2009 | 09/03/2009 | 11/15/2010 | 3064000 | 0.61
5865 | Minnesota | SCOTT | MINNEAPOLIS-ST. PAU, MN | 2 | 09ES179 | Constructing a paved surface on a new alignment for County Road 21 from County Road 42 in Prior Lake to County Road 16 in Shakopee in Scott County. | Pavement Improvement | 11/12/2009 | 11/16/2009 | 07/20/2012 | 7324000 | 0.66
5866 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4 | 10ES001 | Construct pedestrian and bike trail connections to Anderson Memorial Trail in Arden Hills. | Transportation Enhancements | 03/24/2010 | 03/29/2010 | 06/25/2010 | 288326 | 0
5867 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 5 | 10ES002 | Provide a wider pedestrian path from the Cedar Lake Bike Trail system to the new downtown Minneapolis ballpark. | Transportation Enhancements | 11/05/2009 | 11/06/2009 | 05/31/2010 | 695067 | 0
5868 | Minnesota | CARVER |  | 2 | 10ES005 | Construct a pedestrian and bike Dakota Rail Trail from East County Line to City of Mayer in Carver County. | Transportation Enhancements | 03/26/2010 | 04/06/2010 | 12/31/2010 | 550680 | 0
5869 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4,5 | 10ES006 | Construct Sam Morgan Trail, a pedestrian and bike trail, from I-35E to State Highway 5 in St. Paul. | Transportation Enhancements | 05/26/2010 | 06/01/2010 | 08/30/2010 | 448800 | 0
5870 | Minnesota | HENNEPIN |  | 5 | 10ES007 | Improve the Bryant Avenue Pedestrian Bridge over Minnehaha Creek in Minneapolis. | Transportation Enhancements | 05/05/2010 | 05/05/2010 | 09/02/2010 | 382000 | 0
5871 | Minnesota | RAMSEY, WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 4 | 10ES009 | Provide bridge for Gateway State Trail users over Highway 120 in the Cities of North St. Paul and Oakdale. | Transportation Enhancements | 03/11/2010 | 05/17/2010 | 08/27/2010 | 1257903 | 0
5872 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 10ES010 | Construct a pedestrian and bike trail along County Road 10 from Brooklyn Blvd to State Highway 100 in Brooklyn Center. | Transportation Enhancements | 03/17/2010 | 04/19/2010 | 10/15/2010 | 2000000 | 0
5873 | Minnesota | CARVER | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES011 | Construct turn lanes on County Road 30 at the Compost Site Access in Mayer. | Safety/Traffic Management | 05/07/2010 | 05/10/2010 | 07/31/2010 | 96000 | 0.2
5874 | Minnesota | CARVER | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES012 | Install a signal at intersection of State Highway 41 and 2nd Street and concrete median at 1st, 3rd, and 5th streets in Chaska. | Safety/Traffic Management | 02/25/2010 | 05/24/2010 | 09/03/2010 | 485272 | 0.215
5875 | Minnesota | WASHINGTON |  | 6 | 10ES015 | Construct bridge and retaining walls for County Road 83 on the overpass of I-35 in Washington County. | Pavement Improvement | 04/06/2010 | 04/12/2010 | 06/01/2011 | 5000000 | 0.2
5876 | Minnesota | ANOKA |  | 5 | 10ES016 | Reconstruct pedestrian bridge crossing State Highway 65 and approaches in the vicinity of 49th Avenue in Columbia Heights. | Bridge Replacement | 04/12/2010 | 04/12/2010 | 06/15/2011 | 1925678 | 0
5877 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 4 | 10ES017 | Construct intersection control at Mendota Heights Road at Vistation Drive and at Lake Drive in Mendota Heights. | Safety/Traffic Management | 02/16/2010 | 06/14/2010 | 07/01/2010 | 310000 | 0.69
5878 | Minnesota | ANOKA | MINNEAPOLIS-ST. PAU, MN | 5 | 10ES018 | Resurface and stripe for bike lanes on 61st Avenue from Main Street to Central Avenue in Fridley. | Pavement Improvement | 04/20/2010 | 05/03/2010 | 06/18/2010 | 262500 | 1.27
5879 | Minnesota | CARVER | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES019 | Resurface four sections of county roads in Carver County: County Road 10, County Road 15 and County Road 17. | Pavement Improvement | 09/10/2009 | 11/01/2009 | 11/01/2009 | 856368 | 0.33
5880 | Minnesota | CARVER | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES020 | Reconstruct State Highway 25 from White Street to State Street in Watertown. | Pavement Improvement | 03/23/2010 | 05/10/2010 | 07/31/2010 | 704000 | 0.23
5881 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 10ES021 | Construct overpass from I-94 westbound to Highway 101 northbound over South Diamond Lake Road in Rogers. | New Bridge Construction | 03/11/2010 | 04/06/2010 | 10/29/2010 | 3780000 | 0.348
5882 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 6 | 10ES023 | Minor road improvements including curb repair, utility repair, and resurfacing at various locations of Public Road 101 in Woodbury. | Pavement Improvement | 02/02/2010 | 05/20/2010 | 09/30/2010 | 1250250 | 2.66
5883 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES024 | Resurface 140th Street West from 134th Street to Guild Avenue and Garden View Drive from 140th Street to Walnut Street. This project will also include spot repair of deteriorated storm sewer, sanitar | Pavement Improvement | 06/11/2010 | 06/14/2010 | 09/16/2010 | 561000 | 1.201
5884 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 5 | 10ES025 | Rehabilitate bridge on 42nd Ave. North/37th Avenue northeast from Lyndale Avenue north to St. Anthony Parkway in Minneapolis. | Bridge Improvement | 03/08/2010 | 03/15/2010 | 08/31/2011 | 9539619 | 0.331
5885 | Minnesota | ANOKA | MINNEAPOLIS-ST. PAU, MN | 3 | 10ES026 | Upgrade 56 existing signal systems in Coon Rapids, including new lenses, pedestrian lights with count down timers and revised pedestrian signs. | Safety/Traffic Management | 10/07/2009 | 11/23/2009 | 03/01/2010 | 180000 | 0
5886 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES027 | Reconstruct County Road 73 from County Road 42 to Bonaire Path. | Pavement Improvement | 04/02/2010 | 04/07/2010 | 10/07/2010 | 2257896 | 1
5887 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 10ES028 | Campus Drive/26th Avenue from County Road 61 to Sycamore Lane in Plymouth: Resurface from County Road 61 to Teakwood Lane and reconstruct from Teakwood lane to Sycamore Lane. | Pavement Improvement | 02/23/2010 | 05/07/2010 | 06/10/2010 | 346560 | 0.395
5888 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 4 | 10ES029 | Resurface and stripe Hadley Avenue from Hudson Boulevard North to 11th Street North in Oakdale. | Pavement Improvement | 02/26/2010 | 04/26/2010 | 05/06/2010 | 273767 | 1.118
5889 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES030 | Resurface Holyoke/Highview Avenue from Heritage Drive to Dodd Boulevard in Lakeville. | Pavement Improvement | 10/06/2009 | 10/07/2009 | 08/01/2010 | 812122 | 1.252
5890 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 10ES031 | Street lighting replacement, reconstruction of sidewalk on Shoreline Boulevard and Commerce Boulevard from east city limits to west city limits in Mound. | Safety/Traffic Management | 05/25/2010 | 06/01/2010 | 10/15/2010 | 630000 | 2.04
5891 | Minnesota | ANOKA | MINNEAPOLIS-ST. PAU, MN | 5 | 10ES032 | Resurfacing of Terrance Road from County Road 8 to Sanburnol Drive and Able Street from County Road 8 to County Road 10. | Pavement Improvement | 04/15/2010 | 04/26/2010 | 10/08/2010 | 1468480 | 1.16
5892 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 4 | 10ES033 | Construct right lane and bypass lane on State Highway 244 at Old Wildwood Road in Mahtomedi. | Safety/Traffic Management | 02/16/2010 | 05/03/2010 | 07/30/2010 | 156000 | 0.051
5893 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 6 | 10ES034 | Resurfacing and storm sewer work on Washington Avenue from State Highway 36 to Orleans in Stillwater. | Pavement Improvement | 02/16/2010 | 05/19/2010 | 06/30/2010 | 274998 | 0.529
5894 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 5 | 10ES035 | Reconstruct the pavement, improve and construct additional storm sewer, replace failing water main, complete spot repair of sanitary sewer, replace portions of curb and gutter and widen portions of ex | Pavement Improvement | 10/28/2009 | 04/12/2010 | 07/10/2011 | 778723 | 0.49
5895 | Minnesota | SCOTT | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES036 | Construct a pedestrian bridge over Highway 169 and trail connection from Appolossa Ave to Vierling Drive on Fuller Street in Shakopee. | Transportation Enhancements | 01/22/2010 | 05/26/2010 | 07/01/2010 | 700000 | 0
5896 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 10ES037 | Construct two trail bridges over State Highway 7 and County Road 92 and connection of paved regional trail between bridges and the Carver County/Hennepin County Line. | Transportation Enhancements | 03/03/2010 | 03/03/2010 | 08/16/2010 | 2717408 | 0
5897 | Minnesota | DAKOTA |  | 2 | 10ES038 | Reconstruct Dakota County Road 96 from West of 11th Avenue to State Highway 3, with paved shoulders and right turn lanes at intersections. | Pavement Improvement | 10/19/2009 | 10/23/2009 | 08/01/2010 | 1677105 | 0.49
5898 | Minnesota | SCOTT | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES039 | Construction of South Frontage Road from County Road 5 to County Road 3 and South Street from US 169 to O'Brien Parkway in Belle Plaine. | Pavement Improvement | 03/11/2010 | 03/18/2010 | 07/11/2010 | 1555923 | 0.2
5899 | Minnesota | SCOTT | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES040 | Install new traffic control signal system at the intersection of County Road 42 and McKenna Road in Prior Lake. | Safety/Traffic Management | 12/14/2009 | 05/15/2010 | 07/01/2010 | 154486.51 | 0.02
5900 | Minnesota | ST LOUIS |  | 8 | 10ES041 | Roadway resurfacing and drainage improvements on US 2 west of Duluth. | Pavement Improvement | 09/29/2009 | 10/07/2009 | 07/15/2010 | 3677037 | 14.556
5901 | Minnesota | AITKIN |  | 8 | 10ES042 | Replace a deficient and deteriorated bridge located north of Aitkin on County Highway 1 in Aitkin County. | Bridge Replacement | 11/18/2009 | 04/05/2010 | 10/11/2010 | 869880 | 0.24
5902 | Minnesota | SIBLEY |  | 7 | 10ES043 | Upgrade railroad from Green Isle to Gaylord. | Safety/Traffic Management | 03/03/2010 | 05/11/2010 | 07/31/2010 | 2675000 | 0
5903 | Minnesota | PINE |  | 8 | 10ES044 | Replace failed piers on closed St Croix Valley railroad bridge over Snake river in Pine County. | Bridge Improvement | 10/05/2009 | 10/05/2009 | 01/31/2010 | 1030026 | 0
5904 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4,5 | 10ES045 | Reconstruct County Road D from Flandrau Street to White Bear Avenue in Ramsey County including, dedicated turn lanes, and traffic signals. | Pavement Improvement | 12/02/2009 | 04/19/2010 | 10/15/2010 | 2449882 | 0.45
5905 | Minnesota | MARSHALL |  | 7 | 10ES046 | Replace bridge on County Road 5 over the Tamarac River in Stephen in Marshall County. | Bridge Replacement | 12/29/2009 | 04/12/2010 | 11/20/2010 | 1115118 | 0.08
5906 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 5 | 10ES047 | Curb ramps, sidewalk, pedestrian crossings on State Highway 47 from I-35W to 27th Avenue Northeast in Minneapolis. | Transportation Enhancements | 02/08/2010 | 06/21/2010 | 08/01/2010 | 437563 | 2.811
5907 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4,5 | 10ES048 | Curb ramps, sidewalk, pedestrian crossings on State Highway 5 from Davern St. in St. Paul to McKnight Road in Maplewood and on US 61 from State Highway 5 to Wheelock Parkway in St. Paul. | Transportation Enhancements | 02/09/2010 | 04/14/2010 | 08/15/2010 | 1191786 | 9.836
5908 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,6,8 | 10ES049 | Minneapolis-St. Paul metrowide upgrades to comply with the Americans with Disabilities Act. | Safety/Traffic Management | 03/17/2010 | 05/03/2010 | 07/15/2010 | 795332 | 16.583
5909 | Minnesota | STATEWIDE |  | 4 | 10ES050 | Provide Commercial Drivers License training and certification for women and minorities. | Other | 09/22/2009 | 12/15/2009 | 04/30/2010 | 286812 | 0
5910 | Minnesota | SIBLEY |  | 7 | 10ES051 | Resurface Sibley County Road 2 from County Road 7 to Gibbon north. | Pavement Improvement | 06/09/2010 | 07/01/2010 | 08/20/2010 | 2764546 | 0.21
5911 | Minnesota | WADENA |  | 8 | 10ES052 | Replace bridge on County Road 2 over the Patridge River in Wadena County. | Bridge Replacement | 01/04/2010 | 06/07/2010 | 09/01/2010 | 352680 | 0.133
5912 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 3 | 10ES053 | Resurface and update existing guardrail and drainage systems on I-94 from the Crow River in Rogers to I-494 in Maple Grove. | Pavement Improvement | 02/08/2010 | 04/12/2010 | 10/29/2010 | 17970171 | 7.798
5913 | Minnesota | FILLMORE |  | 1 | 10ES054 | Resurfacing of Root River Trail from Fountain to Lanesboro. | Transportation Enhancements | 03/29/2010 |  | 07/30/2010 | 700000 | 0
5914 | Minnesota | BLUE EARTH |  | 1 | 10ES055 | Construct New Roadway On County Road 12 from County Highway 26 to County Highway 3 including County Highway 3 intersection in Mankato. | New Construction | 05/19/2010 | 05/20/2010 | 11/01/2010 | 2000000 | 6.654
5915 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4 | 10ES056 | Change lane configuration on northbound to westbound 35E/694 Ramp. | Safety/Traffic Management | 01/13/2010 | 06/01/2010 | 06/21/2010 | 133515 | 0
5916 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES057 | US 61 from Cannon St to 4th St in Hastings - replace pavement and install Americans with Disabilities Act pedestrian improvements. | Pavement Improvement | 02/18/2010 | 05/17/2010 | 07/23/2010 | 822185 | 2.027
5917 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4,5 | 10ES058 | Pedestrian & bike trail pavement replacement from Minnehaha Avenue to Century Avenue in Maplewood. | Transportation Enhancements | 04/30/2010 | 05/17/2010 | 09/16/2010 | 1291544 | 1.336
5918 | Minnesota | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 5 | 10ES059 | 5 separate Paving ramp meter bypass lanes at 5 separate locations on State Highway 100 from the south limits of Robbinsdale to France Avenue North. | Pavement Improvement | 01/20/2010 |  | 08/27/2010 | 541407 | 0.792
5919 | Minnesota | STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 2,3,4,5,6,8 | 10ES060 | Metrowide - Put in new LED lamps and refurbish control room video wall. | Safety/Traffic Management | 01/20/2010 | 02/03/2010 | 05/17/2010 | 669614 | 0
5920 | Minnesota | HENNEPIN |  | 5 | 10ES062 | Resurface both bridges, westbound off ramp over Light Rail Transit and City Street and over I35W in Minneapolis on I-94. | Bridge Improvement | 03/04/2010 | 06/21/2010 | 08/19/2010 | 1440502 | 0.169
5921 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4 | 10ES063 | Modify ramps and widen two bridges on I-694 at I-35W in New Brighton and Arden Hills. | Pavement Improvement | 11/20/2009 | 07/06/2010 | 10/11/2010 | 2713667 | 0.436
5922 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 6 | 10ES065 | Unbonded concrete overlay, guardrail, rehabilitate bridges, cable median barrier, drainage improvements on I-694 from I-94 to 50th Street. | Pavement Improvement | 03/17/2010 | 04/19/2010 | 10/01/2010 | 13395746 | 4.975
5923 | Minnesota | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES066 | Resurface Highway 61 from Highway 10 to St. Paul Park Road in Cottage Grove and St. Paul Park. | Pavement Improvement | 06/10/2010 | 06/14/2010 | 10/15/2010 | 17323825 | 8.373
5924 | Minnesota | ST LOUIS |  | 8 | 10ES069 | Permanent repairs to failing sheet piling at the Port of Duluth. | Other | 04/13/2010 | 05/25/2010 | 06/20/2011 | 1595090 | 0
5925 | Minnesota | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 4,5 | 10ES070 | Replace pavement, drainage, shoulder reconstruction on I-94 From State Highway 280 to Western Avenue in St. Paul. | Pavement Improvement | 04/28/2010 | 05/10/2010 | 08/20/2010 | 11331606 | 4.338
5926 | Minnesota | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 2 | 10ES071 | North of Cannon Falls on US 52 replace existing RR signals and add advance warning signs. | Safety/Traffic Management | 11/23/2009 | 11/23/2009 | 12/30/2009 | 285193 | 0.5
5927 | Minnesota | RICE |  | 2 | 10ES072 | Replace bridge over Falls Creek on County Road 23 north of State Highway 60. | Bridge Replacement | 04/21/2010 | 05/19/2010 | 08/27/2010 | 363816 | 0.09
5928 | Minnesota | LE SUEUR, RICE |  | 2 | 10ES074 | Pavement replacement on State Highway 60 from State Highway 13 to State Highway 21. | Pavement Improvement | 02/18/2010 |  | 10/29/2010 | 3697823 | 15.064
5929 | Minnesota | CROW WING |  | 8 | 10ES075 | On County Road 20 from North Ahrens Hill Rd to County Highway 49 in Crow Wing Co. Reconstruct to urban standards that include grading, surfacing, storm sewer & slope reinforcement. | Pavement Improvement | 04/07/2010 | 04/19/2010 | 09/03/2010 | 1913731 | 0.935
5930 | Minnesota | CHISAGO |  | 8 | 10ES076 | Overly State Highway 243 from State Highway 95 to the St. Croix River and also rehabilitate the St. Croix River Bridge and approaches. | Pavement Improvement | 03/30/2010 | 04/12/2010 | 07/31/2010 | 685352 | 1.066
5931 | Minnesota | CASS |  | 8 | 10ES077 | Resurface State Highway 84 from State Highway 371 to County Road 2, including upgrading pedestrian ramps in Pine River. | Transportation Enhancements | 03/25/2010 | 04/26/2010 | 05/27/2010 | 164556 | 0.346
5932 | Minnesota | AITKIN |  | 8 | 10ES078 | Replace sidewalks and pedestrian ramps to meet the Americans with Disabilities Act requirements. | Transportation Enhancements | 04/20/2010 | 05/03/2010 | 05/28/2010 | 210044 | 0.44
5933 | Minnesota | ST LOUIS | DULUTH-SUPERIOR (WI) | 8 | 10ES079 | Restoration of Lester River Bridge on State Highway 61 between 60th and 61st Avenues in East Duluth. | Transportation Enhancements | 06/10/2010 | 06/14/2010 | 10/01/2010 | 100000 | 0.132
5934 | Mississippi | ATTALA |  | 2 | 0004017 | "This project will resurface and extend the life of the pavement on two sites in Attala county. The first site 25.6 miles in length on Vaiden French Camp Road just south of French Camp and the other | Pavement Improvement | 07/20/2009 | 08/20/2009 | 01/06/2010 | 1183400 | 31
5935 | Mississippi | PANOLA |  | 1 | 0012024 | The city of Batesville will install traffic signals and make other improvements at various locations. MS Hwy 6 at Lakewood/Power Dr.; MS Hwy 6 at Keating/Woodland Rd.; and MS Hwy 6 at US Hwy 51. This | Safety/Traffic Management | 04/30/2010 |  |  | 255255 | 0.066
5936 | Mississippi | RANKIN | JACKSON | 3 | 0013040 | In Rankin county the city of Brandon resurface Crossgates Drive from Crossgates Blvd. east 1000 feet, resurface Marquette Road from Highway 80 to Region 8 Building, resurface North College Street from | Pavement Improvement | 05/01/2010 | 05/07/2010 |  | 585548 | 0.196
5937 | Mississippi | COPIAH |  | 2 | 0015029 | This project will resurface and extend the life of the pavement on Carter Hill Road from Old Port Gibson Road to Dentville Road and on Browns Wells Road from Sylvarena Road to 0.7 miles south of Highw | Pavement Improvement | 06/08/2009 | 06/08/2009 | 10/30/2009 | 456620 | 12.8
5938 | Mississippi | FORREST | HATTIESBURG | 4 | 0018026 | The county of Forrest will resurface Monroe Rd, 42 Bypass to Travis Rd, Elks Lake Road, Hwy 98 to Hwy 49, Glendale ve/Eatonville Rd to Monroe Rd to I-59. This project will make the road smoother and | Pavement Improvement | 03/01/2010 | 03/09/2010 | 05/05/2010 | 650906 | 15.008
5939 | Mississippi | NOXUBEE |  | 3 | 0023071 | This project will resurface and extend the life of the pavement on US 45 from the Kemper County Line to Brooksville in Noxubee county. | Pavement Improvement | 04/10/2009 | 06/01/2009 | 07/06/2010 | 12702800 | 22.188
5940 | Mississippi | HINDS | JACKSON | 2, 3 | 0025033 | The city of Clinton will replace 4 bridges: Kickapoo Road over Bogue Chitto Creek, Clinton-Tennin Road over Straight Fence Creek, McRaven Road over Smith creek, and Magnolia Road over Branch-Bogue Chi | Bridge Replacement | 03/01/2010 | 03/15/2010 | 09/29/2010 | 1722106 | 0
5941 | Mississippi | MONROE |  | 1 | 0025065 | This project will resurface and extend the life of the pavement for approximately 8 miles on US Highway 45 between New Wren and the Lee County Line, Monroe county. | Pavement Improvement | 07/09/2009 | 06/14/2009 | 03/30/2010 | 3656300 | 7.233
5942 | Mississippi | HINDS | JACKSON | 2, 3 | 0025068 | The county of Hinds will resurface Siwell Road from Raymond Road to McCluer Road, resurface Terry Road from Siwell Road to Gary Road, resurface West Northside Drive from I-20 to Norrell Road, resurfa | Pavement Improvement | 05/01/2010 | 05/21/2010 |  | 1487257 | 7.592
5943 | Mississippi | HOLMES |  | 2 | 0026007 | This project will replace a bridge on Old Highway 49 over Tchula Lake near the town of Tchula, Holmes county. | Bridge Replacement | 03/15/2010 | 03/16/2010 | 01/27/2011 | 816866 | 0.16
5944 | Mississippi | HINDS |  | 2,3 | 0027012 | The town of Bolton will resurface Bolton-Brownsville Road from I-20 South 1300 feet. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 04/28/2010 | 04/29/2010 |  | 128713 | 1.166
5945 | Mississippi | ALCORN |  | 1 | 0028014 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas on the Alcorn County Welcome Center, Alcorn county. | Transportation Enhancements | 10/08/2009 |  | 07/16/2010 | 186700 | 0
5946 | Mississippi | ITAWAMBA |  | 1 | 0029027 | This project will replace a bridge over Cummings Creek on Cummings Street north of Fulton, Itawamba county. | Bridge Replacement | 02/12/2010 | 02/16/2010 | 09/18/2010 | 666900 | 0.3
5947 | Mississippi | JACKSON | PASCAGOULA-MOSS POINT | 4 | 0031086 | This project will widen, add turn lanes and resurface US 90 from SR 57 to the West Pascagoula River Bridge in Jackson county. | Pavement Improvement | 08/06/2009 | 08/10/2009 | 08/31/2010 | 10799800 | 3.23
5948 | Mississippi | HARRISON |  | 4 | 0031144 | This project will construct walking trails, parking, landscaping, and lighting to connect with the multi use path on the Bay St. Louis Bridge, Harrison county. | Transportation Enhancements | 03/11/2010 | 03/11/2010 |  | 1351000 | 0.413
5949 | Mississippi | JACKSON |  | 4 | 0031145 | This project will construct walking trails, parking, landscaping, and lighting to connect with the multi use path for the Biloxi Bay Bridge, Jackson county. | Transportation Enhancements | 03/11/2010 | 03/11/2010 |  | 329500 | 0.299
5950 | Mississippi | HARRISON | BILOXI-GULFPORT | 4 | 0031147 | The city of Pass Christian will install street lighting along US 90 from Market Street to Davis Avenue. This project will improve traffic operations and safety. | Safety/Traffic Management | 06/07/2010 | 06/07/2010 | 12/04/2010 | 128541 | 0.315
5951 | Mississippi | MARSHALL |  | 1 | 0047320 | This project will reconstruct and add new pavement for 0.9 miles on the Chickasaw Trail Industrial Park Access Road approx. 6 miles north of Byhalia, Marshall county. | Pavement Improvement | 11/23/2009 | 11/23/2009 | 05/17/2010 | 242645 | 1
5952 | Mississippi | PANOLA |  | 1 | 0054032 | This project will replace the bridge over McLvor Canal on Mt. Level Road in Panola county. This project is located approx. 4 miles west of Sardis. | Bridge Replacement | 07/02/2009 | 07/02/2009 | 12/22/2009 | 745300 | 0.2
5953 | Mississippi | PANOLA |  | 1 | 0054034 | This project will replace the bridge over Bobo Creek on Benson Herron Road 1.5 miles southwest from the town of Courtland, Panola county. | Bridge Replacement | 07/02/2009 | 07/02/2009 | 11/21/2009 | 297600 | 0.19
5954 | Mississippi | RANKIN | JACKSON | 3 | 0061035 | The county of Rankin will resurface Spillway Road from Mill Creek Bridge to Eagle Point, Overlay Thomasville Road from Monterey Road east for 2.2 miles, Old Hwy 49 from Cleary Road north for 2.87 mile | Pavement Improvement | 03/16/2010 | 03/16/2010 |  | 1324847 | 8.904
5955 | Mississippi | SHARKEY |  | 2 | 0063010 | This project will resurface various roads in the town of Anguilla, Sharkey county. | Pavement Improvement | 05/04/2009 | 05/05/2009 | 08/31/2009 | 102200 | 5.6
5956 | Mississippi | ITAWAMBA |  | 1 | 0063036 | This project will upgrade US 78 to interstate standards from the east end of the Tenn-Tom Bridge to the Alabama State Line. This includes shoulder paving, guardrail upgrade, rumble strips and fencing. | Pavement Improvement | 04/09/2009 | 04/20/2009 | 08/28/2009 | 4629100 | 13.05
5957 | Mississippi | LEE |  | 1 | 0063037 | This project will upgrade approximately 5 miles of US Highway 78 in Tupelo to interstate standards McCullough Boulevard @ Belden to US 45. This includes shoulder paving, guardrail upgrade, rumble stri | Pavement Improvement | 06/11/2009 | 06/26/2009 | 09/16/2009 | 3227900 | 4.657
5958 | Mississippi | TALLAHATCHIE |  | 2 | 0068100 | This project will resurface and extend the life of the pavement on 14 different roads in the town of Webb, Tallahatchie county: Main Street Extension, 5th Street, Deere Avenue, Plow Street, John Stree | Pavement Improvement | 08/20/2009 | 08/20/2009 | 10/29/2009 | 47000 | 2.9
5959 | Mississippi | MADISON |  | 2,3 | 0070017 | The city of Canton will resurface North Old Canton Road from the City Limits to US 51; Walnut Street from Dinkins Street to Peace Street; and West North Street from Canal Street to MLK Drive. This pro | Pavement Improvement | 05/01/2010 | 05/05/2010 |  | 374194 | 1.591
5960 | Mississippi | ALCORN |  | 1 | 0071074 | This project will resurface and extend the life of the pavement for approximately 15 miles on US Highway 72 between the Tippah County Line and State Route 2, Alcorn county. | Pavement Improvement | 07/09/2009 | 08/07/2009 | 04/26/2010 | 6927600 | 14.778
5961 | Mississippi | COAHOMA |  | 2 | 0080026 | The city of Clarksdale will resurface Florence Avenue, Martin Luther King, Jr. Boulevard, New Africa Road, Oakridge Road, and Maple Street. This project will make the road smoother and extend the life | Pavement Improvement | 03/01/2010 | 03/02/2010 |  | 742361 | 4.492
5962 | Mississippi | COVINGTON |  | 3 | 0082093 | This project will resurface and extend the life of the pavement on approximately 18 miles of US Highway 49 northbound lanes from Seminary to the Simpson County Line in Covington county. | Pavement Improvement | 04/09/2009 | 04/20/2009 | 09/29/2009 | 4206800 | 16.782
5963 | Mississippi | SIMPSON |  | 3 | 0082094 | This project will resurface and extend the life of the pavement for approximately 6 miles of US Highway 49 beginning 15.9 miles north of the Covington county line then running north for 5.6 miles near | Pavement Improvement | 08/06/2009 | 08/13/2009 | 11/25/2009 | 2565500 | 5.611
5964 | Mississippi | SIMPSON |  | 3 | 0082095 | This project will resurface and extend the life of the pavement for approximately 16 miles on US Highway 49 beginning at the Covington county line and continuing north, Simpson county. Northbound lane | Pavement Improvement | 08/06/2009 | 09/04/2009 | 03/25/2010 | 3603900 | 15.892
5965 | Mississippi | YAZOO |  | 2 | 0084061 | This project will resurface and extend the life of the pavement on US Highway 49 between the Madison County Line and Bentonia in Yazoo county. | Pavement Improvement | 04/08/2009 | 05/12/2009 | 08/07/2009 | 2473900 | 5.005
5966 | Mississippi | LEFLORE |  | 2 | 0085028 | This project will resurface and extend the life of the pavement for approximately 11 miles on US 49 from US 82 to SR 8, Leflore County. | Pavement Improvement | 08/06/2009 | 08/06/2009 | 12/07/2009 | 4247400 | 15.65
5967 | Mississippi | JACKSON |  | 4 | 0101133 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-10 East rest area, Jackson county. | Transportation Enhancements | 03/11/2010 | 03/11/2010 |  | 1011100 | 0
5968 | Mississippi | PONTOTOC |  | 1 | 0102008 | The city of Pontotoc will resurface Industrial Drive/South Industrial Circle east of First National Bank on Hwy 15 to intersection of Bolton Street. This project will make the road smoother and extend | Pavement Improvement | 03/01/2010 | 03/08/2010 |  | 185763 | 0.951
5969 | Mississippi | LOWNDES |  | 1 | 0110023 | The city of Columbus will resurface Military Rd between 18th & 3rd; 7th between Bluecutt and 18th; Willowbrook between 5th & 7th; MS 12 between Lehmberg & US 82; Island between W Br. End & Dead End; W | Pavement Improvement | 03/01/2010 | 05/03/2010 | 08/31/2010 | 716183 | 4.396
5970 | Mississippi | LOWNDES |  | 1 | 0110024 | This project will stripe and resurface Military Road between Ridge Rd. and Hwy 82 and Bell Ave/ Airline Rd. between Hwy 69 and S. 25th St./Martin Luther King Jr. Drive in the city of Columbus, Lowndes | Pavement Improvement | 05/01/2010 | 05/03/2010 | 06/18/2010 | 422497 | 0
5971 | Mississippi | LOWNDES |  | 1 | 0113076 | This project will resurface and extend the life of the pavement for approximately 9 miles on US Highway 82 between near Military Road in Columbus and the Alabama State Line, Lowndes county. | Pavement Improvement | 07/09/2009 | 07/20/2009 | 10/13/2009 | 3473000 | 8.249
5972 | Mississippi | ALCORN |  | 1 | 0120015 | The city of Corinth will resurface and stripe Fulton Drive from Linden to Shiloh Rd; Fulton Drive from Hwy 72 south to city limits; and Alcorn Drive from Hwy 72 to Linden Street. This project will mak | Pavement Improvement | 03/01/2010 | 03/01/2010 | 04/26/2010 | 589662 | 1.635
5973 | Mississippi | PEARL RIVER |  | 4 | 0124040 | This project will replace four bridges over Hobolochito Creek on Burned Bridge-Pine Grove Road west of Picayune, Pearl River county. | Bridge Replacement | 08/24/2009 | 08/24/2009 | 04/06/2010 | 2199700 | 0.9
5974 | Mississippi | WALTHALL |  | 3 | 0142060 | This project will resurface and extend the life of the pavement on approximately 6 miles of U.S. Highway 98 between the Pike County Line and Tylertown in Walthall county. | Pavement Improvement | 04/09/2009 | 04/13/2009 | 08/12/2009 | 3174600 | 6.081
5975 | Mississippi | WALTHALL |  | 3 | 0142061 | This project will resurface and extend the life of the pavement on approximately 5 miles of US Highway 98 from the west end of the Tylertown bypass to the east end of the Tylertown bypass, Walthall co | Pavement Improvement | 06/11/2009 | 08/14/2009 | 09/02/2009 | 1809000 | 4.391
5976 | Mississippi | LAMAR |  | 4 | 0142063 | This project will resurface and improve the safety of US 98 from State Route 589 to Weathersby Road in Lamar county. | Pavement Improvement | 10/08/2009 | 11/03/2009 | 09/30/2010 | 7811200 | 5.878
5977 | Mississippi | ADAMS |  | 3 | 0151054 | This project will resurface and extend the life of the pavement on US 84 from US 61 Intersection to the Franklin county line, Adams county. | Pavement Improvement | 07/24/2009 | 07/30/2009 | 11/30/2009 | 4311200 | 10.053
5978 | Mississippi | ADAMS |  | 3 | 0151060 | This project will install aesthetic street and bridge lighting and traffic cameras on the bridge over the Mississippi River in Natchez in Adams county. | Transportation Enhancements | 07/09/2009 | 10/29/2009 | 04/30/2010 | 1702600 | 2.496
5979 | Mississippi | FRANKLIN |  | 3 | 0151063 | This project will resurface and extend the life of the pavement on approximately 8 miles of U.S. Hwy 84 west the Bude/Meadville By-Pass in Franklin county. | Pavement Improvement | 03/31/2009 | 04/28/2009 | 09/30/2009 | 4383300 | 8.715
5980 | Mississippi | BOLIVAR, SUNFLOWER |  | 2 | 0161029 | This project will construct 2 additional lanes on State Route 8 between Cleveland and Ruleville in Bolivar and Sunflower Counties. | Pavement Widening | 06/11/2009 | 06/19/2009 | 07/09/2010 | 8630000 | 7.872
5981 | Mississippi | BOLIVAR, SUNFLOWER |  | 2 | 0161033 | This project will resurface and extend the life of the pavement on State Route 8 from the Bolivar county Hospital to Ruleville, Bolivar and Sunflower county. | Pavement Improvement | 07/09/2009 | 08/06/2009 | 10/09/2009 | 2626200 | 8.654
5982 | Mississippi | AMITE, PIKE |  | 3 | 0168010 | This project will reconstruct the existing pavement, replace utilities, and improve safety on State Route 570 from .58 miles west of the Pike county line to the Pike county line and on State Route 570 | Pavement Improvement | 07/30/2009 | 08/26/2009 | 04/26/2011 | 6372500 | 3.553
5983 | Mississippi | LEFLORE |  | 2 | 0180017 | The city of Greenwood will resurface Claiborne Street from US 82 to Grand Boulevard, Poplar Street from Claiborne to Park, and Garrard Avenue from US 82 to Sycamore Street. This project will make the | Pavement Improvement | 03/01/2010 | 04/13/2010 |  | 659169 | 2.35
5984 | Mississippi | GRENADA |  | 1 | 0190005 | The city of Grenada will resurface Vance Road from Townes Ave to Browns Creek Bridge and Jackson Avenue from US 51 to Monroe St. This project will make the road smoother and extend the life of the pav | Pavement Improvement | 03/01/2010 | 04/05/2010 |  | 577722 | 3.433
5985 | Mississippi | FORREST | HATTIESBURG | 4 | 0193008 | The city of Petal will resurface Hillcrest Loop and Carterville Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/10/2010 | 04/30/2010 | 554497 | 4.084
5986 | Mississippi | SCOTT |  | 3 | 0202079 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the rest area on I-20 East and West Bound Rest Areas, Scott County. | Transportation Enhancements | 11/05/2009 | 10/26/2009 | 07/31/2010 | 1056100 | 0
5987 | Mississippi | FORREST, LAMAR |  | 4 | 0210017 | This project will install overhead message signs, traffic cameras, and other traffic monitoring devices on US 49, US 98 & I-59 in Hattiesburg, Forrest county. | Other | 11/05/2009 | 02/08/2010 | 06/30/2011 | 3878600 | 21.422
5988 | Mississippi | FORREST | HATTIESBURG | 4 | 0210021 | The city of Hattiesburg will construct a bikepath beginning Construction of a park along the Leaf River and construction of a multi-use trail. This project will improve bike access. | Transportation Enhancements | 07/05/2010 | 06/28/2010 | 12/06/2010 | 507742 | 0.08
5989 | Mississippi | FORREST | HATTIESBURG | 4 | 0210022 | This project will add a new bikeway from US 49 to the University of Southern Mississippi. Forrest County | Transportation Enhancements | 04/08/2010 | 05/17/2010 |  | 880400 | 0.047
5990 | Mississippi | DE SOTO | MEMPHIS (TN-AR) | 1 | 0211105 | The city of Horn Lake will construct a sidewalk along Goodman Rd. from Horn Lake Rd. to Hurt Rd. and pave Tulane Rd. from Nail Rd to Goodman Rd. This project will improve pedestrian access along Goodm | Pavement Improvement | 03/01/2010 | 03/01/2010 |  | 434689 | 2.55
5991 | Mississippi | DE SOTO | MEMPHIS (TN-AR) | 1 | 0211106 | The city of Horn Lake will install a traffic signal and make other improvements at Goodman Road and Windchase Drive. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 03/01/2010 | 03/01/2010 |  | 173445 | 0.01
5992 | Mississippi | JONES |  | 4 | 0221072 | This project will resurface and extend the life of the pavement approximately 2 miles in length on State Route 15 from 115th Street to Old Highway 15 in Laurel, Jones. | Pavement Improvement | 04/08/2009 | 04/09/2009 | 06/04/2009 | 1202383 | 2.287
5993 | Mississippi | HARRISON | BILOXI-GULFPORT | 4 | 0221073 | This project will resurface and extend the life of the pavement for approximately 6.2 miles on State Route 15 from the intersection of State Route 67 going north. Harrison county. | Pavement Improvement | 03/11/2010 | 03/11/2010 |  | 940000 | 6.143
5994 | Mississippi | CHICKASAW |  | 1 | 0223023 | This project will resurface and extend the life of the pavement for approximately 9 miles on State Route 15 between Houston and the Pontotoc county line, Chickasaw county. | Pavement Improvement | 07/09/2009 | 07/16/2009 | 09/25/2009 | 2571300 | 9.385
5995 | Mississippi | PERRY |  | 4 | 0224034 | This project will replace a bridge on State Route 29 over Black Creek in Perry county. | Bridge Improvement | 06/01/2009 | 06/01/2009 | 07/30/2010 | 4258100 | 0.092
5996 | Mississippi | MARSHALL |  | 1 | 0230008 | The city of Holly Springs will resurface College Street from Boundary to Memphis Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/01/2010 |  | 261488 | 0.672
5997 | Mississippi | ATTALA |  | 2 | 0232047 | This project will resurface and extend the life of the pavement on State Route 35 multilane section in Kosciusko from Natchez Trace Parkway to State Route 12, approximately 3 miles, Attala county. | Pavement Improvement | 09/10/2009 | 10/22/2009 | 02/26/2010 | 1342300 | 2.444
5998 | Mississippi | WAYNE |  | 4 | 0233013 | This project is a base repair, leveling, and overlay project along Clara-Buckatuna Road for 4.92 miles, Wayne county. This project will make the road smoother and will extend the life of the pavement | Pavement Improvement | 06/01/2010 |  |  | 192139 | 4.92
5999 | Mississippi | SUNFLOWER |  | 2 | 0240009 | The city of Indianola will resurface BB King, Westside Avenue, and Wiggins Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/04/2010 |  | 577010 | 2.744
6000 | Mississippi | HINDS | JACKSON | 2,3 | 0250034 | The city of Jackson will resurface Northside Drive from Medgar Evers Boulevard to Jackson City Limits and Maddox Road from MS 18 to John R. Lynch Street. This project will make the road smoother and e | Pavement Improvement | 05/06/2010 | 07/21/2010 | 10/08/2010 | 2763700 | 10.541
6001 | Mississippi | NEWTON, NESHOBA |  | 3 | 0261076 | This project will construct additional lanes on State Route 19 between the Lauderdale County Line and SR 492 in Newton and Neshoba county. | Pavement Widening | 04/06/2009 | 04/15/2009 | 02/01/2012 | 34406000 | 7.147
6002 | Mississippi | LINCOLN |  | 3 | 0275017 | This project will resurface, improve drainage, and extend the life of the pavement on approx. 7.2 miles of the Eddiceton-Caseyville Road in the Homochitto National Forrest located approx. ten miles we | Pavement Improvement | 11/09/2009 | 11/30/2009 | 02/24/2011 | 1668230 | 8
6003 | Mississippi | RANKIN | JACKSON | 3 | 0291004 | The city of Flowood will resurface 1.95 miles of Old Brandon Road from Hwy 80 to Pearl River Bridge and the addition of a left-turn lane along Treetops Blvd. at the existing intersection with Top Stre | Pavement Improvement | 05/01/2010 | 05/06/2010 | 06/23/2010 | 564430 | 1.992
6004 | Mississippi | PIKE |  | 3 | 0310013 | The city of McComb will resurface and perform sidewalk Improvements to Pearl River Avenue, South Magnolia Street and Summit Street. This project will make the road smoother and extend the life of the | Pavement Improvement | 03/01/2010 | 03/02/2010 |  | 760469 | 1.83
6005 | Mississippi | DE SOTO |  | 1 | 0311018 | This project will replace 4 bridges on MS Highway 305 from Cockrum to Lewisburg in Desoto county. | Bridge Replacement | 07/09/2009 | 07/09/2009 | 08/03/2011 | 7551300 | 1.43
6006 | Mississippi | HANCOCK | BILOXI-GULFPORT | 4 | 0321034 | The city of Bay St. Louis will install street lighting along Hwy 43 from Longfellow Road to I-10. This project will improve traffic operations and safety along this section of roadway. | Safety/Traffic Management | 03/01/2010 | 03/29/2010 |  | 725705 | 4.889
6007 | Mississippi | ADAMS |  | 3 | 0340034 | The city of Natchez will resurface Pearl Street, Commerce Street, Rankin Street, Washington Street, Canal Street, State Street and Melrose Avenue. This project will make the road smoother and extend t | Pavement Improvement | 03/01/2010 | 03/01/2010 |  | 618934 | 2.101
6008 | Mississippi | UNION |  | 1 | 0350012 | The city of New Albany will resurface and stripe Carter Ave. between Camp Ave. and Main St; on Bankhead Street between Camp Ave. and Glade Ave.; and replace a box culvert on Carter Avenue. This projec | Pavement Improvement | 03/01/2010 | 03/01/2010 |  | 200921 | 0.483
6009 | Mississippi | LAFAYETTE |  | 1 | 0360009 | The city of Oxford will resurface Jackson Avenue, Old Taylor Road (8601), Old Taylor Road (9426) and Belk Drive. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 04/05/2010 | 04/05/2010 |  | 421873 | 1.363
6010 | Mississippi | JEFFERSON DAVIS |  | 2 | 0371051 | This project will resurface and extend the life of the pavement on State Route 13 from north of the Marion County Line to US 84, Jefferson Davis county. | Pavement Improvement | 07/09/2009 | 07/06/2009 | 09/30/2009 | 1749000 | 9.334
6011 | Mississippi | NESHOBA |  | 3 | 0390009 | The city of Philadelphia will resurface Herman Alford Blvd. from Pecan Ave to 250 feet South of Saxon Airport Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 04/01/2010 | 04/01/2010 | 04/08/2010 | 299561 | 0.565
6012 | Mississippi | SIMPSON |  | 3 | 0392050 | This project will replace a bridge over the Middle Prong- Silver Creek on the Rockport-Shivers and Mount Zion Road 2.5 miles north of the Jefferson Davis/Simpson county line, Simpson County. | Bridge Replacement | 07/07/2009 | 08/07/2009 | 01/11/2010 | 525400 | 0.3
6013 | Mississippi | PEARL RIVER |  | 4 | 0400023 | The city of Picayune will resurface North Main Street between West Canal Street and E. 4th Street' Beech Street between Will Street and Palentine Rd., and Palestine Rd and Crosby St. between West Cana | Pavement Improvement | 03/01/2010 | 03/02/2010 |  | 378056 | 4.081
6014 | Mississippi | OKTIBBEHA |  | 3 | 0420017 | The city of Starkville will resurface: N. Montgomery St., University Drive, Jackson Street, Louisville Street, Yellow Jacket Drive and S. Montgomery Street. This project will make the road smoother an | Pavement Improvement | 03/01/2010 | 03/24/2010 |  | 627315 | 4.405
6015 | Mississippi | OKTIBBEHA |  | 3 | 0420018 | This project will stripe and resurface Whitfield St. between Greensboro St. and Ave. of Patriots; and Louisville St. between Lynn Lane and Industrial Park Road in the city of Starkville, Oktibbeha co | Pavement Improvement | 05/24/2010 | 06/02/2010 |  | 157713 | 0
6016 | Mississippi | BOLIVAR |  | 2 | 0432015 | This project will resurface and extend the life of the pavement on approximately 11 miles of State Route 1 north of Rosedale in Bolivar county. | Pavement Improvement | 05/19/2009 | 05/21/2009 | 07/24/2009 | 3026300 | 10.736
6017 | Mississippi | WARREN |  | 2 | 0440010 | The city of Vicksburg will resurface Wisconsin Avenue Overlay from Bazinsky Road to Interstate 20 and will resurface Clay Street from Cherry Street to Mission 66. This project will make the road smoot | Pavement Improvement | 03/01/2010 | 03/01/2010 |  | 714352 | 1.732
6018 | Mississippi | MONTGOMERY |  | 2 | 0470010 | The city of Winona will resurface Fairgrounds Street from Railroad Crossing to a point 1250 feet North of Railroad Crossing and Pecan Street from Fairgrounds St. to US Hwy 82 (begin State Maintenance) | Pavement Improvement | 03/01/2010 | 03/24/2010 |  | 183775 | 1.083
6019 | Mississippi | YAZOO |  | 2 | 0480036 | The city of Yazoo will resurface Grady Ave from Mike Espy Dr to 9th, Lamar Ave from W 2nd St to 15th St., MLK Dr from 1st to 9th St. This project will make the road smoother and extend the life of the | Pavement Improvement | 03/01/2010 | 03/04/2010 | 04/16/2010 | 470640 | 2.174
6020 | Mississippi | COPIAH |  | 2 | 0541050 | This project will resurface and extend the life of the pavement on approximately 10 miles of State Route 27 north of Georgetown in Copiah county. | Pavement Improvement | 04/09/2009 | 04/28/2009 | 07/15/2009 | 3421000 | 9.969
6021 | Mississippi | PIKE |  | 3 | 0551094 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 welcome center, Pike County | Transportation Enhancements | 03/11/2010 | 12/16/2009 |  | 396000 | 0
6022 | Mississippi | COPIAH |  | 2 | 0551095 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Rest Area in Copiah County - North Bound Lanes. | Transportation Enhancements | 12/03/2009 | 12/03/2009 | 08/31/2010 | 760900 | 0
6023 | Mississippi | HOLMES |  | 2 | 0552201 | This project will resurface and extend the life of the pavement on approximately 22.4 miles of I-55 between State Route 17 and the Carroll County Line, Holmes county. | Pavement Improvement | 05/06/2010 |  | 10/21/2011 | 10570800 | 22.871
6024 | Mississippi | HOLMES |  | 2 | 0552210 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the rest area on I-55 Northbound north of Durant, Holmes county. | Transportation Enhancements | 10/01/2009 | 10/22/2009 | 06/30/2010 | 467600 | 0
6025 | Mississippi | CARROLL |  | 2 | 0553083 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Rest Area near Vaiden, Carroll county. | Transportation Enhancements | 10/08/2009 | 10/12/2009 | 07/12/2010 | 166000 | 0
6026 | Mississippi | DE SOTO |  | 1 | 0554091 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Desoto County Rest Area, Desoto county. | Transportation Enhancements | 12/03/2009 | 12/18/2009 |  | 498300 | 0
6027 | Mississippi | STATEWIDE |  | 01, 02 | 0554093 | This project will add new landscaping to along ths side of the I-55 North and South Bound lanes throughout the Mississippi Deparment of Transportation's District 2. This includes the counties of ..... | Transportation Enhancements | 06/10/2010 |  | 06/30/2010 | 374700 | 248.347
6028 | Mississippi | RANKIN |  | 3 | 0561068 | This project will resurface and extend the life of the pavement on State Route 25 from State Route 471 to State Route 43 in Rankin county. | Pavement Improvement | 04/10/2009 | 06/27/2009 | 05/07/2010 | 8833500 | 10.195
6029 | Mississippi | COAHOMA |  | 2 | 0571004 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the Delma Furniss Hospitality Station, Coahoma county. | Transportation Enhancements | 10/08/2009 | 10/14/2009 | 09/14/2010 | 263800 | 0
6030 | Mississippi | PEARL RIVER |  | 4 | 0591105 | This is a design build project which will add shoulders to 12 bridges on I-59 from the Louisiana state line to Poplarville, Pearl River County. | Bridge Improvement | 08/10/2009 | 10/20/2009 | 09/01/2010 | 10000000 | 0.633
6031 | Mississippi | PEARL RIVER |  | 4 | 0591106 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-59 welcome center, Pearl River Co. | Transportation Enhancements | 03/11/2010 | 02/23/2010 |  | 439900 | 0
6032 | Mississippi | LAUDERDALE |  | 3 | 0593084 | This project will build a new interchange at I-20/59 and Hawkins Rd. & 23rd Ave in Meridian in Lauderdale county. This project will add new pavement, street lights, and bridge construction. | New Construction | 07/09/2009 | 07/09/2009 | 07/29/2011 | 15311899 | 0.064
6033 | Mississippi | LAUDERDALE, NEWTON |  | 3 | 0593090 | This project is a design build project which will extend the I-59/I-20 merge lanes in Lauderdale county. Also, this project will add shoulders to 6 bridges on I-20 in Newton county. | Bridge Improvement | 10/21/2009 | 01/25/2010 | 10/16/2010 | 9999999 | 6.335
6034 | Mississippi | WASHINGTON |  | 2 | 0622027 | This project will resurface and extend the life of the pavement for approximately 10 miles on State Route 438 from US 61 through Arcola to Highway 1, Washington county. | Pavement Improvement | 06/11/2009 | 06/17/2009 | 09/04/2009 | 2500800 | 9.673
6035 | Mississippi | WINSTON |  | 3 | 0679004 | This project will resurface and extend the life of the pavement on Ellison Ridge Road for approx 4 miles in length located 7 miles northeast of Noxapater, Winston county. | Pavement Improvement | 06/26/2009 | 07/09/2009 | 10/27/2009 | 409900 | 4.15
6036 | Mississippi | LOWNDES |  | 1 | 0681017 | State Route 69 from Plymouth Road to Highway 69 south and SR 182 from State Route 69 to the Alabama state line for 9.67 miles, Lowndes county. This project will resurface and extend the life of the p | Pavement Improvement | 05/10/2010 | 05/25/2010 |  | 3536800 | 0
6037 | Mississippi | PANOLA |  | 1 | 0703016 | This project will resurface and extend the life of the pavement for approximately 11 miles on eastbound lanes for State Route 6 east of Batesville, Panola county. | Pavement Improvement | 08/04/2009 | 08/06/2009 | 12/14/2009 | 3227500 | 11.916
6038 | Mississippi | LAUDERDALE |  | 3 | 0741010 | This project will resurface and extend the life of the pavement on State Route 39 From I-20 to 52nd Street in Meridian, Lauderdale county. | Pavement Improvement | 07/09/2009 | 08/03/2009 | 11/24/2009 | 3867400 | 3.864
6039 | Mississippi | MONROE, CLAY |  | 1 | 0791029 | This project will resurface and extend the life of the pavement on US 45 Alternative from West Point to one mile north of State Route 25, Monroe and Clay county. | Pavement Improvement | 07/09/2009 | 07/14/2009 | 11/09/2009 | 4199800 | 8.187
6040 | Mississippi | LOWNDES |  | 1 | 0791030 | This project will resurface and extend the life of the pavement on US 45 Alternative from 9 miles north of the Noxubee County Line to the Clay county line, Lowndes county. | Pavement Improvement | 07/09/2009 | 08/03/2009 | 10/19/2009 | 2735100 | 6.625
6041 | Mississippi | MONROE, CHICKASAW |  | 1 | 0792015 | This project will resurface and extend the life of the pavement on approximately 9 miles of US 45 Alternative between State Route 8 and the northern Monroe county line, Monroe and Chickasaw county. | Pavement Improvement | 07/09/2009 | 07/29/2009 | 11/23/2009 | 4174300 | 8.847
6042 | Mississippi | LAFAYETTE |  | 1 | 0793002 | This project will replace a bridge on State Route 331 over Yocona River near State Route 334 in Lafayette county. | Bridge Replacement | 07/09/2009 | 07/09/2009 | 04/08/2011 | 3960000 | 1.109
6043 | Mississippi | FORREST | HATTIESBURG | 4 | 0801015 | This project will resurface and extend the life of the pavement on US 49 from Edwards St. to 31st. Avenue in Hattiesburg, Forrest county. | Pavement Improvement | 07/09/2009 | 07/10/2009 | 04/30/2010 | 8636900 | 5.835
6044 | Mississippi | TISHOMINGO |  | 1 | 0948008 | This project will resurface and extend the life of the pavement on State Route 365 from the Prentiss/Tishomingo County Line to US 72 in Tishomingo county | Pavement Improvement | 07/09/2009 | 07/03/2009 | 09/02/2009 | 1548700 | 6.569
6045 | Mississippi | PERRY |  | 4 | 1152001 | This project will replace the existing bridge on State Route 198 over Dickey Creek near Beaumont in Perry county. | Bridge Replacement | 07/09/2009 | 07/13/2009 | 03/31/2010 | 1469900 | 0.038
6046 | Mississippi | OKTIBBEHA |  | 3 | 2714001 | This project will replace two bridges, first bridge over Glen Creek and second bridge over Tobacco Juice Creek, along Poorhouse Road 3 miles south of Starkville, Oktibbeha county. | Pavement Improvement | 12/21/2009 | 01/05/2010 | 09/21/2010 | 1309000 | 1.3
6047 | Mississippi | YALOBUSHA, CALHOUN |  | 1 | 2791008 | This project will replace 9 bridges on State Route 32 from Water Valley to State Route 330 in Yalobusha and Calhoun county. | Bridge Replacement | 08/06/2009 | 08/14/2009 | 09/26/2011 | 5923600 | 0.137
6048 | Mississippi | TATE |  | 1 | 2920001 | This project will construct two additional lanes on US 51 between Senatobia and Coldwater in Tate county. | New Construction | 10/08/2009 | 10/08/2009 | 02/01/2012 | 10497777 | 2.999
6049 | Mississippi | TATE |  | 1 | 5512002 | The city of Senatobia will resurface East Main Street from SR 4 to Park Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/18/2010 |  | 217140 | 0.489
6050 | Mississippi | WAYNE |  | 4 | 5583001 | The city of Waynesboro will resurface West Avenue from MS 184 to Turner Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/04/2010 |  | 176421 | 0.856
6051 | Mississippi | COPIAH |  | 2 | 5604001 | The city of Crystal Springs will resurface and add sidewalk ramps on Newton Street between Georgetown Street and Harmony Road. This project will make the road smoother and extend the life of the pave | Pavement Improvement | 03/01/2010 | 05/05/2010 |  | 210757 | 0.38
6052 | Mississippi | TIPPAH |  | 1 | 5659002 | The city of Ripley will resurface a section of Main Street from Highway 15 and extending northerly, approximately 0.75 miles to Highway 15. This project will make the road smoother and extend the life | Pavement Improvement | 03/01/2010 | 03/01/2010 |  | 171834 | 0.579
6053 | Mississippi | MARION |  | 4 | 6034005 | The city of Columbia will resurface and stripe Main Street beginning approx. 500 feet west of the intersection of Broad St. and High School Ave. and then west and north to Lafayette Street. This proje | Pavement Improvement | 03/01/2010 | 03/08/2010 |  | 236954 | 0.519
6054 | Mississippi | WASHINGTON |  | 2 | 6922001 | The city of Greenville will resurface Tennessee Gas Road from Main Street to Highway 1. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/01/2010 |  | 1083959 | 1.135
6055 | Mississippi | MADISON | JACKSON | 2,3 | 6980001 | The city of Flora will resurface First Street from US 49 to US 49. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 04/30/2010 | 05/18/2010 |  | 382315 | 2.663
6056 | Mississippi | MADISON | JACKSON | 2,3 | 6988001 | The city of Madison will resurface North Old Canton Road from Sowell Road to Canton City Limits. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 05/01/2010 | 05/05/2010 |  | 344501 | 1.87
6057 | Mississippi | HINDS | JACKSON | 2,3 | 7037001 | The town of Terry will resurface Cunningham Avenue from I-55 to Railroad Avenue. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 05/01/2010 | 05/12/2010 |  | 267604 | 0.677
6058 | Mississippi | MONROE |  | 1 | 7163001 | The city of Aberdeen will resurface Chestnut Street from Hwy 45/25 to Hwy 145. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 02/15/2010 | 02/15/2010 | 04/02/2010 | 166973 | 0.65
6059 | Mississippi | WASHINGTON |  | 2 | 7221002 | The city of Greenville will add left turn lanes at the intersection of Reed Road and Main Street. This project will improve traffic operations and safety. | Pavement Improvement | 03/15/2010 | 03/15/2010 |  | 523897 | 0.02
6060 | Mississippi | RANKIN | JACKSON | 3 | 7272006 | The city of Pearl at Old Brandon Road will install a traffic signal and make other improvements at the intersection at Bierdeman Road and at Patton Drive. This project will improve traffic operations | Safety/Traffic Management | 03/01/2010 | 06/01/2010 | 08/01/2010 | 181433 | 0.008
6061 | Mississippi | HINDS | JACKSON | 2 | 7314022 | This project will improve safety and traffic operations by installing a traffic signal installation at the intersection of US Hwy 80 and Shaw Road in Hinds county. | Safety/Traffic Management | 06/11/2009 | 09/08/2009 | 11/24/2009 | 134800 | 0.001
6062 | Mississippi | HINDS | JACKSON | 2 | 7314023 | This project will resurface and extend the life of the pavement on US 80 from Springridge Road to Terry Road, Hinds county. | Pavement Improvement | 07/09/2009 | 07/22/2009 | 11/24/2009 | 6478100 | 7.909
6063 | Mississippi | RANKIN | JACKSON | 3 | 7336004 | The city of Pearl will resurface Pirates Cove Road from Hwy 80 to Pearl High School Entrance. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/15/2010 | 03/15/2010 |  | 341053 | 1.06
6064 | Mississippi | MADISON | JACKSON | 2,3 | 7354001 | The city of Madison will resurface Highland Colony Parkway -South Bound - between Madison Avenue and Broadmoor Baptist Church. This project will make the road smoother and extend the life of the pavem | Pavement Improvement | 05/01/2010 | 05/05/2010 |  | 387782 | 1.006
6065 | Mississippi | MADISON | JACKSON | 2,3 | 7354002 | The city of Ridgeland will resurface Highland Colony Parkway from Steed Road north 3000 feet. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 04/30/2010 | 05/03/2010 | 06/27/2010 | 433024 | 0.559
6066 | Mississippi | PIKE |  | 3 | 7570004 | This project will reconstruct the existing pavement and replace utilities and improve safety on State Route 570 from West limits of McComb East .9 miles in Pike county. | Pavement Improvement | 07/30/2009 | 08/26/2009 | 04/26/2011 | 1889000 | 0.876
6067 | Mississippi | HARRISON | BILOXI-GULFPORT | 4 | 7829002 | The city of Biloxi will construct a right turn lane and intersection and signal upgrades on Division Street at Bohn Avenue and the I-110 on-ramp. This project will improve traffic operations and safet | Safety/Traffic Management | 06/21/2010 |  |  | 561323 | 0.013
6068 | Mississippi | DE SOTO | MEMPHIS (TN-AR) | 1 | 7861002 | The city of Southaven will improve safety and traffic operations by installing traffic signals at two intersections along Getwell Road. Getwell Road at Central Parkway and Getwell Road at Nail Road in | Safety/Traffic Management | 03/01/2010 | 03/01/2010 |  | 278733 | 0.022
6069 | Mississippi | DE SOTO | MEMPHIS (TN-AR) | 1 | 7862003 | The city of Olive Branch will widen Stateline Road from two to three lanes, between Alexander Road and Hacks Cross Road. This project will improve traffic operations and safety. | Pavement Widening | 03/01/2010 | 03/01/2010 |  | 715781 | 1.004
6070 | Mississippi | DE SOTO | MEMPHIS (TN-AR) | 1 | 7868005 | The city of Southaven will resurface Airways Boulevard from Hwy 302 to the Mississippi/Tennessee state line. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/01/2010 |  | 645419 | 2.232
6071 | Mississippi | DE SOTO |  | 1 | 7886001 | The city of Hernando will resurface Commerce Street from US 51 east to the Illinois Central Railroad Crossing. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/11/2010 | 03/11/2010 |  | 204131 | 1.233
6072 | Mississippi | DE SOTO | MEMPHIS (TN-AR) | 1 | 7904001 | The city of Olive Branch will install a traffic signal and make other improvements at the intersection of Pigeon Roost Road and Hwy 305. This project will improve traffic operations at this intersecti | Safety/Traffic Management | 03/01/2010 | 03/01/2010 |  | 215436 | 0.011
6073 | Mississippi | CLAY |  | 1 | 7950001 | The city of West Point will resurface Lone Oak Drive from approximately East Oak Ridge Drive to Lone Oak Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/03/2010 |  | 418724 | 0.749
6074 | Mississippi | BOLIVAR |  | 2 | 8032005 | The city of Cleveland will construct sidewalks along Court Street and North Street. This project will improve pedestrian access along these roads. | Safety/Traffic Management | 05/05/2010 | 05/05/2010 |  | 1001016 | 0.606
6075 | Mississippi | JONES |  | 4 | 8063001 | The city of Laurel will replace a bridge on 5th Avenue over Gardiner Creek. | Bridge Replacement | 03/01/2010 | 03/12/2010 | 05/14/2010 | 132829 | 0.013
6076 | Mississippi | JONES |  | 4 | 8077001 | The city of Laurel will install a traffic signal and make other improvements at the intersection of Beacon Street and Mason Street. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 03/01/2010 |  |  | 160376 | 0.017
6077 | Mississippi | JONES |  | 4 | 8093001 | The city of Laurel will resurface 16th Avenue from King Street to Ferrill Street and will resurface 16th Ave from Ellisville Boulevard to Lee Street. This project will make the road smoother and exten | Pavement Improvement | 03/03/2010 | 03/04/2010 |  | 146087 | 0.123
6078 | Mississippi | LAUDERDALE |  | 3 | 8134001 | The city of Meridian will replace a bridge over Sowashee Creek. This project will improve traffic safety. | Bridge Improvement | 03/15/2010 | 05/14/2010 |  | 1048479 | 0.014
6079 | Mississippi | LAUDERDALE |  | 3 | 8161001 | The city of Meridian will make safety upgrades, replace lighting, and other enhancements to the 26th Avenue viaduct. This project willextend the life of the structure and improve safety. | Pavement Improvement | 03/15/2009 | 03/22/2010 |  | 912796 | 0.149
6080 | Mississippi | LEE |  | 1 | 8193007 | The city of Tupelo will build a new bridge to extend Eason Boulevard over Town Creek and Kings Creek. | Bridge Improvement | 09/28/2009 | 10/19/2009 | 09/28/2010 | 1227688 | 0.145
6081 | Mississippi | FORREST | HATTIESBURG | 4 | 8762002 | The city of Hattiesburg will resurface W. Pine Street from Broadway Drive to Hwy 49S. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/01/2010 | 04/30/2010 | 553842 | 1.113
6082 | Mississippi | ATTALA |  | 2 | 8930001 | The city of Kosciusko will resurface Love Road from South Natchez Street to South Huntington Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/04/2010 |  | 228271 | 0.719
6083 | Mississippi | JACKSON | PASCAGOULA-MOSS POINT | 4 | 8943002 | The city of Pascagoula will replace a bridge and resurface the pavement on Old Mobile Highway between 14th Street and Chicot Street. This project will make the road smoother and extend the life of the | Pavement Improvement | 05/21/2010 | 06/21/2010 |  | 819874 | 0.794
6084 | Mississippi | MARSHALL |  | 1 | 9025100 | This project will add pavement to 2.1 miles of the North Holly Springs Industrial Bypass Road just north of Holly Springs. This project will make the road smoother and extend the life of the pavement. | New Construction | 09/28/2009 | 09/28/2009 | 06/16/2010 | 1637100 | 2.1
6085 | Mississippi | HARRISON | BILOXI-GULFPORT | 4 | 9044001 | The city of Biloxi will install street lighting along MS Hwy 67 from the Tchoutacabouffa River north to the City Limits. This project will improve traffic operations and safety. | Safety/Traffic Management | 03/01/2010 | 06/02/2010 |  | 249486 | 0.906
6086 | Mississippi | JACKSON | BILOXI-GULFPORT | 4 | 9064008 | The county of Jackson will add a right turn lane and make sidewalk improvements on Beachview Rd and Old Spanish Trail; and install traffic signals on Old Spanish Trail at Beachview Drive and at Hansha | Safety/Traffic Management | 03/01/2010 | 04/22/2010 |  | 522479 | 0.035
6087 | Mississippi | HARRISON | BILOXI-GULFPORT | 4 | 9082002 | The city of Long Beach will replace a bridge on Klondyke Road, which crosses Canal No. 1. This project will improve traffic safety. | Bridge Replacement | 05/28/2010 | 06/07/2010 |  | 599524 | 0.013
6088 | Mississippi | HARRISON | BILOXI-GULFPORT | 4 | 9082003 | The city of Long Beach will install traffic signals and make other intersection improvements at the intersection of Klondyke Road and 28th Street. This project will improve traffic operations and saf | Safety/Traffic Management | 06/02/2010 | 06/03/2010 | 01/30/2011 | 492824 | 0.013
6089 | Mississippi | HANCOCK | BILOXI-GULFPORT | 4 | 9137002 | The county of Hancock will resurface and make other repairs to Kiln-Waveland Cutoff Road from US 90 to Hwy 603. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 06/21/2010 |  | 10/19/2010 | 798064 | 1.431
6090 | Mississippi | HARRISON | BILOXI-GULFPORT | 4 | 9183001 | The city of D'Iberville will replace a bridge over the bayou on Gorenflo Road, south of Borries Street. This project will improve traffic safety. | Bridge Replacement | 05/24/2010 | 06/01/2010 |  | 430420 | 0.013
6091 | Mississippi | JACKSON | PASCAGOULA-MOSS POINT | 4 | 9192001 | The city of Gautier will install a traffic signal at the intersection of Ladnier Road and Old Spanish Trail. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 04/12/2010 | 04/12/2010 |  | 131030 | 0.009
6092 | Mississippi | HARRISON | BILOXI-GULFPORT | 4 | 9375005 | The city of Biloxi will resurface Beauvoir Road, from US 90 to Pass Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 05/03/2010 | 05/11/2010 |  | 274406 | 0.744
6093 | Mississippi | LINCOLN |  | 3 | 9518003 | The city of Brookhaven will resurface Brookway Boulevard beginning at the east end of State Maintenance just east of I-55 and then east to US Hwy 51. This project will make the road smoother and exten | Pavement Improvement | 03/01/2010 | 03/01/2010 |  | 342652 | 0.99
6094 | Mississippi | MONROE |  | 1 | 9569003 | The city of Amory will resurface Waterway Drive from Hwy 278 to 5th Ave. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 02/15/2010 | 02/15/2010 |  | 249621 | 0.832
6095 | Mississippi | PRENTISS |  | 1 | 9629002 | The city of Booneville will install a traffic signal and make other improvements at the intersection along N. 2nd Street at Hwy 4, College Street, Veterans (George E. Allen Drive) and Cunningham Boule | Safety/Traffic Management | 03/01/2010 | 03/01/2010 |  | 441425 | 0.11
6096 | Mississippi | WASHINGTON |  | 2 | 9670003 | The city of Leland will resurface North Broad Street from 8th Street to the City Limits. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/04/2010 | 04/09/2010 | 171417 | 0.566
6097 | Mississippi | WINSTON |  | 3 | 9674008 | The city of Louisville will resurface South Church Street from Hwy 15 to Armstrong Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 03/01/2010 | 03/10/2010 |  | 289276 | 1.553
6098 | Mississippi | RANKIN, HINDS, MADISON | JACKSON | 02, 03 | 9999510 | This project takes place in the following three counties: Hinds, Madison, and Rankin. This project will resurface and extend the lives of Louis Wilson Drive in Brandon from US Highway 80 to MS Hwy 18; | Pavement Improvement | 08/05/2010 |  |  | 876732 | 0
6099 | Missouri | CASS |  | 04 | 0021032 | This project consist of a thin lift asphalt overlay from Commercial Street to Route ZZ in Cass and Johnson counties | Pavement Improvement | 09/08/2009 | 07/29/2009 | 12/01/2009 | 504700 | 14.656
6100 | Missouri | LACLEDE |  | 04 | 0052029 | This project consists of constucting a five lane roadway on Route 5, Laclede County to improve safety and improve capacity. | Pavement Widening | 03/01/2010 | 03/01/2010 | 11/15/2010 | 2809319.52 | 2.25
6101 | Missouri | CAMDEN |  | 04 | 0053053 | This project consist of widening Route 5 to three lanes through Sunrise Beach in Camden county | Pavement Widening | 06/15/2009 | 06/15/2009 | 05/28/2010 | 984700 | 0.9
6102 | Missouri | PUTNAM |  | 06 | 0054025 | This project consist of resurfacing roadway from Iowa State line to Route 136 - Putnam county | Pavement Improvement | 02/08/2010 | 04/01/2010 | 11/01/2010 | 468300 | 8.435
6103 | Missouri | BENTON |  | 04 | 0072039 | This project consist of rehabilitation of bridges on Route 7 over Truman Lake (Osage Arm Bridge and Grand River Arm Bridge) in Benton county | Bridge Improvement | 06/15/2009 | 06/18/2009 | 10/15/2010 | 5026400 | 2
6104 | Missouri | CLAY |  | 6,5 | 0091014 | This project consists of rehabilitation of the Heart of America bridge over the Missouri River, including addition of a bicycle and pedistrian facility, on Route 9 in Clay county. | Pavement Improvement | 02/01/2010 | 06/07/2010 | 12/01/2010 | 455549.99 | 0.4
6105 | Missouri | PLATTE | KANSAS CITY (KS)-MO | 06 | 0091015 | This project consists of interchange improvements, building ramps and roundabout from SB Rte. 9 to Briarcliff in Clay county. | Pavement Improvement | 01/04/2010 | 01/25/2010 | 11/01/2010 | 2500000 | 0.941
6106 | Missouri | PLATTE | KANSAS CITY (KS)-MO | 06 | 0091016 | This project consists of a bridge replacement on Route 9 over the White Aloe Branch in Platte county south of Route FF. | Bridge Replacement | 01/04/2010 | 06/09/2010 | 10/01/2010 | 105000 | 0.113
6107 | Missouri | RAY |  | 4,6 | 0134027 | This project consist of resurfacing roadway from the Caldwell county Line to Route 10 at the City of Richmond - Ray county | Pavement Improvement | 03/08/2010 |  | 11/01/2010 | 1150600 | 18.597
6108 | Missouri | CALDWELL |  | 06 | 0134028 | This project consist of replacing bridge deck over Route 36 in Hamilton - Caldwell county | Bridge Replacement | 03/08/2010 | 06/02/2010 | 08/01/2010 | 592000 | 0.081
6109 | Missouri | MONROE |  | 09 | 0151011 | This project consist of pavement and shoulder improvements from Route 154 north junction to 1.1 miles north of Route 22 in Monroe and Audrain counties | Pavement Improvement | 05/18/2009 | 09/15/2009 | 12/01/2009 | 2227800 | 24.572
6110 | Missouri | AUDRAIN |  | 09 | 0151012 | This project consist of pavement improvements from 1.1 miles north of Route 22 to 0.2 miles north of Route 54 in Audrain county | Pavement Improvement | 07/06/2009 | 08/18/2009 | 12/01/2009 | 796130.05 | 5.038
6111 | Missouri | TEXAS |  | 08 | 0171009 | This project consist of a thin lift asphalt overlay from Route 106 in Summersville to Route 60 in Mt. View in Texas and Howell counties | Pavement Improvement | 06/08/2009 | 07/09/2009 | 12/01/2009 | 564176.21 | 13.251
6112 | Missouri | HOWELL |  | 08 | 0171010 | This project consist of a thin lift asphalt overlay from Route 60 in Mt. View to Route 160 in Howel county | Pavement Improvement | 06/08/2009 | 07/08/2009 | 12/01/2009 | 860642.49 | 19.349
6113 | Missouri | MILLER |  | 09 | 0172010 | This project consist of replacement of bridge over the Osage River one mile east of Tuscumbia in Miller county, project involves bridge J0719 | Bridge Replacement | 02/17/2009 | 02/23/2009 | 10/01/2010 | 8277485 | 0.591
6114 | Missouri | MILLER |  | 4,9 | 0172011 | This project consist of a thin lift asphalt overlay from Route 54 to Brush Creek in Cole and Miller counties | Pavement Improvement | 06/08/2009 | 06/12/2009 | 12/01/2009 | 831658.73 | 19.266
6115 | Missouri | SHANNON |  | 08 | 0191008 | This project consist of roadway resurfacing on Route 19 from Route 106 to .4 miles north of Route F in Eminence and on Route 106 from Route 19 to 1.3 miles west of Route 19 - Shannon county | Pavement Improvement | 02/08/2010 | 04/05/2010 | 12/01/2010 | 139443 | 2.23
6116 | Missouri | CRAWFORD |  | 09 | 0192017 | This project consist of resurfacing roadway from .6 miles north of Route 8 to Route 19 South in Steelville - Crawford county | Pavement Improvement | 03/08/2010 |  | 12/01/2010 | 109557 | 1.2
6117 | Missouri | MONTGOMERY |  | 09 | 0194012 | This project consists of asphalt resurfacing from near Route B (just north of Montgomery City) to 1.7 miles south of Route I-70. | Pavement Improvement | 01/04/2010 | 04/15/2010 | 12/01/2010 | 2140300 | 8.792
6118 | Missouri | WASHINGTON |  | 08 | 0211018 | This project consist of pavement improvements from 1.7 miles south of Route 8 in Potosi to Route N in Iron county | Pavement Improvement | 06/08/2009 | 06/24/2009 | 11/01/2009 | 2249090.65 | 21.247
6119 | Missouri | MARION |  | 09 | 0243033 | This project consists of bridge rehabilitation over the North fabius river .9 miles north of Route 6 near Taylor. | Bridge Improvement | 03/08/2010 | 04/05/2010 | 12/01/2010 | 1843000 | 0.2
6120 | Missouri | MARIES |  | 9,4 | 0281009 | This project consist of a thin lift asphalt overlay from Route 63 to Dixon in Maries and Pulaski counties | Pavement Improvement | 04/06/2009 | 06/09/2009 | 12/01/2009 | 815732.51 | 16.964
6121 | Missouri | PLATTE |  | 06 | 0291111 | This project consists of extensive pavement repair, hot in place recycle and asphalt resurfacing from Rte. 273 near Platte City for 18 miles (North and South) to Vivion Road, new rumble strip and pave | Pavement Improvement | 05/04/2009 | 05/18/2009 | 11/01/2009 | 11799300 | 34.857
6122 | Missouri | BUCHANAN |  | 06 | 0292155 | This project consist of resurfacing roadway from Route 169 (Belt Highway) to Route 371 (22nd Street) in St. Joseph - Buchanan county | Pavement Improvement | 03/18/2010 | 04/01/2010 | 11/01/2010 | 373642.1 | 1.773
6123 | Missouri | BUCHANAN |  | 06 | 0311005 | This project consist of a thin lift asphalt overlay from Route 36 to Route 169 in Buchanan county | Pavement Improvement | 07/06/2009 | 10/28/2009 | 10/01/2010 | 308549.72 | 6.222
6124 | Missouri | DENT |  | 08 | 0322017 | This project consist of resurfacing roadway from .2 mile west of Route 72 to 2.5 miles east of Route 72 in the City of Salem - Dent county | Pavement Improvement | 03/08/2010 | 03/23/2010 | 12/01/2010 | 488236.2 | 2.7
6125 | Missouri | ST FRANCOIS |  | 08 | 0323019 | This project consist of rehabilitation of the existing pavement on Route 32 (Karsh Blvd) from Route OO to Route 67 in the City of Farmington - St. Francois county | Pavement Improvement | 03/08/2010 | 04/26/2010 | 12/01/2010 | 1069447.24 | 2.823
6126 | Missouri | WAYNE |  | 08 | 0341035 | The project consists of adding shoulders, repaving, and several new alignments between Piedmont and Patterson. The alignment will change several curves and eliminate at least one 's' curve. A three | Pavement Widening | 11/17/2008 | 11/17/2008 | 12/01/2010 | 12735200 | 13.349
6127 | Missouri | BOLLINGER |  | 08 | 0341036 | This project consist of resurfacing roadway in Marble Hill - Bollinger county | Pavement Improvement | 03/08/2010 | 06/21/2010 | 09/01/2010 | 526500 | 2.589
6128 | Missouri | CLINTON |  | 06 | 0352082 | This project consists of asphalt resurfacing on I-35 north of Shoal Creek to north of Route 116 near Lathrop. | Pavement Improvement | 02/17/2009 | 02/17/2009 | 12/15/2009 | 14156500 | 7.057
6129 | Missouri | LINN |  | 06 | 0362077 | This project consist of a thin lift asphalt overlay from Route 36 to Route 11 in Linn county | Pavement Improvement | 06/08/2009 | 08/06/2009 | 12/01/2009 | 172000 | 1.772
6130 | Missouri | LAWRENCE |  | 07 | 0391022 | This project consist of a thin lift asphalt overlay from Route 60 to 1.5 miles north of Route 248 in Barry and Lawrence county | Pavement Improvement | 04/06/2009 | 04/14/2009 | 12/01/2009 | 475300.14 | 12.113
6131 | Missouri | CARROLL |  | 04,06 | 0411003 | This project consist of pavement and shoulder improvements from Route 24 to Route 240 in Saline and Carroll counties | Pavement Improvement | 03/30/2009 | 03/30/2009 | 12/01/2009 | 1575664.74 | 17.68
6132 | Missouri | SALINE |  | 04 | 0411004 | This project consist of a thin lift asphalt overlay from Route 240 to Route TT in Saline county | Pavement Improvement | 03/30/2009 | 03/30/2009 | 12/01/2009 | 511733.26 | 10.268
6133 | Missouri | PHELPS |  | 08 | 0442223 | This project consist of major pavement rehabilitation/reconstruction on westbound lanes from Business Loop 44 (Rolla) to Sugartree Road Interchange in Phelps county | Pavement Improvement | 07/06/2009 | 09/08/2009 | 12/01/2009 | 10378900.69 | 8.213
6134 | Missouri | PULASKI |  | 04 | 0442224 | This project consist of an asphalt mill and fill from SP 44 to Route H/I-44 in St. Robert/Waynesville in Pulaski county | Pavement Improvement | 07/06/2009 | 10/16/2009 | 12/01/2009 | 911377.3 | 5.62
6135 | Missouri | CRAWFORD |  | 09 | 0443100 | This project consist of pavement rehabilitation on westbound lanes from 0.6 miles west of Route H to the Phelps County line in Crawford county | Pavement Improvement | 06/08/2009 | 09/21/2009 | 12/01/2009 | 888525.09 | 12.507
6136 | Missouri | FRANKLIN |  | 09 | 0443101 | This project consist of rebuilding of pavement from Viaduct Street to Route 100 West in Franklin county | Pavement Widening | 08/10/2009 | 08/21/2009 | 10/01/2010 | 17377500 | 5.072
6137 | Missouri | PLATTE |  | 06 | 0451025 | This project consist of a thin lift asphalt overlay from Route 273 to Spur 45 south in Platte county | Pavement Improvement | 06/08/2009 | 10/05/2009 | 12/01/2009 | 507200 | 11.89
6138 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | 0501042 | This project will complete a diamond interchange at Route 50 and Bynum Road in Jackson county. | New Construction | 03/29/2010 | 03/29/2010 | 12/01/2010 | 4199200 | 0.1
6139 | Missouri | COLE |  | 04 | 0503078 | This project consist of pavement treatment on westbound lanes from Truman Blvd. To west of Truman Blvd. - Cole county | Pavement Improvement | 03/08/2010 | 04/13/2010 | 12/01/2010 | 328862.64 | 1.539
6140 | Missouri | PERRY |  | 08 | 0512016 | This project consist of pavement improvements from I-55 to Route 72 in Perry and Bollinger counties | Pavement Improvement | 06/08/2009 | 06/24/2009 | 11/01/2009 | 1722800 | 16.297
6141 | Missouri | HENRY |  | 04 | 0521007 | This project consist of a thin lift asphalt overlay from the St. Clair county line to Route 13 in Henry county | Pavement Improvement | 06/08/2009 | 07/29/2009 | 12/01/2009 | 509600 | 15.143
6142 | Missouri | BATES |  | 04 | 0521008 | This project consist of a thin lift asphalt overlay from Route BB to 1.6 miles east of Route W in Bates county | Pavement Improvement | 06/08/2009 | 07/29/2009 | 12/01/2009 | 194615.17 | 5.268
6143 | Missouri | ST CLAIR |  | 04 | 0521009 | This project consist of a thin lift asphalt overlay from 1.0 miles west of Route P to 1.8 miles east of Route A in St. Clair county | Pavement Improvement | 06/08/2009 | 07/29/2009 | 12/01/2009 | 192400 | 4.741
6144 | Missouri | COLE |  | 04 | 0543155 | This project consist of pavement improvements from the Missouri River Bridge to .25 miles west of Stadium Blvd. in Jefferson City. Project includes ramps at Route 50-54-63 interchange (tri- level) - C | Pavement Improvement | 03/08/2010 | 04/13/2010 | 12/01/2010 | 935730.6 | 3.3
6145 | Missouri | CALLOWAY |  | 09 | 0543156 | This project consist of resurfacing westbound lanes from Holts Summit to the Missouri River Bridge in Jefferson City - Callaway county | Pavement Improvement | 03/15/2010 |  | 12/01/2010 | 1219596.6 | 5.184
6146 | Missouri | NEW MADRID |  | 08 | 0551134 | This project consist of pavement rehabilitation of north and south bound lanes from Route 84 to Scott county in New Madrid county | Pavement Improvement | 02/17/2009 | 05/12/2009 | 10/31/2010 | 15743400 | 46.834
6147 | Missouri | PEMISCOT |  | 08 | 0551135 | This project consist of pavement rehabilitation on the northbound lanes from the Arkansas state line to I-155 in Pemiscot county | Pavement Improvement | 06/08/2009 | 06/24/2009 | 07/30/2010 | 16085700 | 15.282
6148 | Missouri | NEW MADRID |  | 08 | 0551136 | The construction of a new Welcome Center on I-55 at Marston | Transportation Enhancements | 01/23/2009 | 01/23/2009 | 11/15/2010 | 5768950 | 0.3
6149 | Missouri | JEFFERSON |  | 03 | 0552086 | This project consists of adding lands and widening or rplacing two bridges on Route 55 between north of Route M and north of Route Z in Jefferson county. | Pavement Widening | 03/08/2010 | 03/08/2010 | 12/01/2011 | 13539119.84 | 4.509
6150 | Missouri | ATCHISON |  | 06 | 0591025 | This project consist of a thin lift asphalt overlay from the Iowa state line to Route 136 in Atchison county | Pavement Improvement | 06/08/2009 | 06/29/2009 | 12/01/2009 | 713109.87 | 9.908
6151 | Missouri | BARRY |  | 07 | 0601030 | The jobs combine to provide new surface and alternating passing lane improvements for 22 plus miles of a 25 mile stretch of Route 60 in Barry, Lawrence, Christian, and Greene Counties. As designed, J | Pavement Improvement | 02/17/2009 | 07/08/2009 | 11/01/2009 | 222135.57 | 17.617
6152 | Missouri | BARRY |  | 07 | 0601031 | The jobs combine to provide new surface and alternating passing lane improvements for 22 plus miles of a 25 mile stretch of Route 60 in Barry, Lawrence, Christian, and Greene Counties. As designed, J | Pavement Improvement | 02/17/2009 | 07/08/2009 | 11/01/2009 | 7884701.29 | 15.894
6153 | Missouri | GREENE | SPRINGFIELD | 07 | 0602067 | This project consists of improvements at the James River Freeway and National Avenue interchange. | Pavement Widening | 09/23/2009 | 09/23/2009 | 12/01/2011 | 4569383 | 0.474
6154 | Missouri | CARTER |  | 08 | 0603095 | This project consist of ADA sidewalk improvements on Business 60 from Oliver Street to Alexander Street in Van Buren, 0.98 miles. | Transportation Enhancements | 01/04/2010 | 03/01/2010 | 05/14/2010 | 101771 | 0.098
6155 | Missouri | TEXAS |  | 08 | 0603096 | This project consist of resurfacing roadway from Route 181 to Route 60 in Cabool - Texas county | Pavement Improvement | 02/08/2010 |  | 12/01/2010 | 147400 | 2.666
6156 | Missouri | LEWIS |  | 09 | 0614137 | This project consist of a thin lift asphalt overlay from Route 961 to Route B in LaGrange - Lewis county | Pavement Improvement | 02/08/2010 |  | 11/01/2010 | 93900 | 1.776
6157 | Missouri | MISSISSIPPI |  | 08 | 0621022 | This project consist of a thin lift asphalt overlay from Route B in Bertrand to the City of Charleston in Mississippi county | Pavement Improvement | 06/08/2009 | 06/16/2009 | 12/01/2009 | 325653.65 | 5.856
6158 | Missouri | HOWELL |  | 08 | 0631029 | This project consist of an asphalt mill and fill from Route 63 North to Broadway in West Plains in Howell county | Pavement Improvement | 07/06/2009 | 10/28/2009 | 12/01/2009 | 526470.69 | 1.801
6159 | Missouri | ADAIR |  | 09 | 0634066 | This is the first in a series of two projects to construct an Alternate Route 63 around Kirksville Missouri. This project runs from the North edge of Kirksville to Route 6, just east of Kirksville. | New Construction | 08/03/2009 | 08/12/2009 | 08/01/2011 | 17491350.38 | 8.5
6160 | Missouri | GREENE |  | 07 | 0652063 | This project consist of widening route to six lanes from Business 65 (Chestnut Expressway) to Route D (Sunshine Street) in Greene County | Pavement Widening | 08/24/2009 | 08/24/2009 | 12/01/2011 | 8613400 | 2.027
6161 | Missouri | GREENE |  | 07 | 0652064 | This project consist of widening route to six lanes from Route D (Sunshine Street) to Route 60 (James River Freeway) in Greene County | Pavement Widening | 08/24/2009 | 08/24/2009 | 12/01/2011 | 2985865.5 | 3.466
6162 | Missouri | GREENE | SPRINGFIELD | 07 | 0652065 | This project consist of widening route to six lanes from Business 65 (Chestnut Expressway) to Route D (Sunshine Street) in Greene County | Pavement Widening | 08/24/2009 | 08/24/2009 | 12/01/2011 | 9701900 | 2.027
6163 | Missouri | DALLAS |  | 04 | 0652066 | This project consist of adding a center turn lane for 1.0 mile north of Route 32 in Dallas county | Pavement Widening | 01/04/2010 |  | 12/01/2010 | 1016100 | 1
6164 | Missouri | BENTON |  | 04 | 0653088 | This project consist of rehabilitation of bridge on Route 65 over the Osge River near Warsaw in Benton county | Bridge Improvement | 06/15/2009 | 06/18/2009 | 10/15/2010 | 1497700 | 0.144
6165 | Missouri | JASPER |  | 07 | 0661017 | This project consist of resurfacing disconnected section from Geneva Avenue to Duquesne Road in Joplin - Jasper county | Pavement Improvement | 03/08/2010 |  | 12/01/2010 | 236600 | 0.887
6166 | Missouri | BUTLER |  | 08 | 0671018 | This project consist of intersection improvements at Business Route 67, OR 67 and Industrial Park Bypass - Butler county | Pavement Improvement | 03/08/2010 |  | 11/01/2010 | 688600 | 0.2
6167 | Missouri | ST LOUIS |  | 01 | 0673109 | This project consists of ADA sidwalk improvements from I-270 to Old St. Charles Rd and on Route AC from Route 67 (Lindbergh) to I-270 in St. Louis county | Transportation Enhancements | 09/08/2009 | 09/28/2009 | 05/01/2010 | 1667700 | 7.5
6168 | Missouri | CLAY |  | 06 | 0691013 | This project consist of a thin lift asphalt overlay from the Clinton county line to Route 92 in Clay county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 260300 | 6.017
6169 | Missouri | JACKSON |  | 04,05,06 | 0701179 | This project consist of constructing a new half diamond interchange at Route 40 - I435, replacement of Blue Ridge cut off bridge over I-70, add lanes to I-70, and modification to some ramps in Jackson | New Construction | 10/07/2009 | 10/07/2009 | 03/01/2012 | 34936045 | 5.437
6170 | Missouri | JACKSON |  | 05 | 0701190 | This project consist of rehabilitating eastbound bridges from Troost to Route 40 in Jackson county | Bridge Improvement | 03/08/2010 | 03/08/2010 | 07/01/2011 | 6673400 | 26
6171 | Missouri | LAFAYETTE |  | 04 | 0702101 | This project consists of resurfacing of the roadway and shoulders on eastbound and westbound Interstate 70 from the Lafayette County line to Odessa. | Pavement Improvement | 05/04/2009 | 06/15/2009 | 12/01/2009 | 6861500 | 20.23
6172 | Missouri | COOPER |  | 6 | 0703217 | This project consist of pavement improvements on the westbound lanes from 0.3 miles east of Route B to the Saline county line in Cooper county | Pavement Improvement | 04/06/2009 | 06/12/2009 | 12/01/2009 | 7612000 | 17.1
6173 | Missouri | BOONE |  | 09 | 0703218 | This project consist of a thin lift asphalt overlay from Route 63 north connector to Route Z in Boone county | Pavement Improvement | 06/08/2009 | 08/10/2009 | 12/01/2009 | 283369.62 | 5.34
6174 | Missouri | BOONE |  | 09 | 0703220 | This project consist of a thin lift resurfacing from Route E west to the end of state maintenance in the City of Columbia - Boone county | Pavement Improvement | 03/08/2010 | 04/06/2010 | 12/01/2010 | 138359.3 | 2
6175 | Missouri | ST LOUIS CITY |  | 1,3 | 0705314 | This project consist of pavement improvements from I-44/I-55 to Washington Ave. in St. Louis City | Pavement Improvement | 07/20/2009 | 07/20/2009 | 12/01/2009 | 5092700 | 0.57
6176 | Missouri | BARTON |  | 4,7 | 0712061 | This project consists of constructing a new interchange at Route 71 and 126. Work includes grading, asphalt pavement and new bridge. | New Construction | 06/22/2009 | 06/22/2009 | 10/01/2010 | 4516400 | 3.805
6177 | Missouri | BARTON |  | 04 | 0712062 | This project consists of constructing a new interchange at Route 71 and DD/EE. Work includes grading, asphalt pavement and new bridge. | New Construction | 07/06/2009 | 07/13/2009 | 10/01/2010 | 3667300 | 3.059
6178 | Missouri | BARTON |  | 04 | 0712063 | This project consists of constructing a new interchange at Route 71 and V/C. Work includes grading, asphalt pavement and new bridge. | New Construction | 07/06/2009 | 07/13/2009 | 10/01/2010 | 3681800 | 6.2
6179 | Missouri | BATES |  | 04 | 0713045 | This project consists of the construction of an overpass with on and off ramps at the junction of Highway 71 and Highway 52 East. Two other bridges will be built as part of this project. One will re | New Construction | 07/06/2009 | 08/18/2009 | 10/01/2010 | 5096700 | 2.904
6180 | Missouri | MADISON |  | 08 | 0722020 | This project consist of resurfacing roadway through the City of Fredricktown - Madison county | Pavement Improvement | 03/08/2010 | 04/26/2010 | 12/01/2010 | 481500 | 1.995
6181 | Missouri | TANEY |  | 07 | 0761014 | This project consist of ADA sidewalk improvements from Roark Valley Road to Gretna (Branson) in Taney county | Transportation Enhancements | 07/27/2009 | 08/19/2009 | 12/01/2009 | 675976.35 | 2.864
6182 | Missouri | TANEY |  | 07 | 0761015 | This project consists of construction of a roundabout and new bridge over Lake Taneycomo. | New Bridge Construction | 06/23/2009 | 06/23/2009 | 07/01/2011 | 8943704.39 | 0.21
6183 | Missouri | BENTON |  | 04 | 0831001 | This project consist of rehabilitation of bridge on Route 83 over Truman Lake near Mockingbird Road in Benton county | Bridge Improvement | 06/15/2009 | 06/18/2009 | 10/15/2010 | 2399300 | 0.5
6184 | Missouri | NEWTON |  | 07 | 0861007 | This project consist of improvements on existing pavement and shoulders with the addition of rumble strips from Route P to 0.2 miles west of Route 71 in Newton county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 802960.38 | 9.952
6185 | Missouri | BARRY |  | 07 | 0861008 | This project consist of improvements on existing pavement and shoulders with the addition of rumble strips from Route F to 2.9 miles east of Route H in Barry county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 922994.44 | 11.596
6186 | Missouri | PULASKI |  | 04 | 1037004 | This project consist of roadway resurfacing on Route 133 from Route 7 to the railroad tracks and resurfacing Route 7 from Route 133 to Route A in Richland - Pulaski county | Pavement Improvement | 03/08/2010 |  | 12/01/2010 | 99000 | 1.303
6187 | Missouri | WEBSTER |  | 04 | 1045005 | This project consist of a thin lift asphalt overlay from Route 60 to south of railroad in Webster county | Pavement Improvement | 06/08/2009 | 09/09/2009 | 12/01/2009 | 32417.41 | 1.19
6188 | Missouri | RIPLEY |  | 08 | 1098007 | This project consist of resurfacing roadway from Route 160 to Route E in Doniphan - Ripley county | Pavement Improvement | 03/08/2010 | 04/21/2010 | 07/01/2010 | 355000 | 4.064
6189 | Missouri | CAPE GIRARDEAU |  | 08 | 1130006 | This project consist of rehabilitating pavement surface from I-55 to Kingshighway in Cape Girardeau county | Pavement Improvement | 07/06/2009 | 07/24/2009 | 08/14/2009 | 520520.09 | 1.703
6190 | Missouri | BUTLER |  | 08 | 1200003 | This project consist of a thin lift asphalt overlay from County Road 462 to Route 67 in Butler county | Pavement Improvement | 04/06/2009 | 06/09/2009 | 12/01/2009 | 362742.14 | 8.183
6191 | Missouri | RIPLEY |  | 08 | 1206005 | This project consist of a thin lift asphalt overlay from Route V west of Doniphan to Route 160 in Doniphan in Ripley county | Pavement Improvement | 04/06/2009 | 08/31/2009 | 12/01/2009 | 762576.55 | 14.548
6192 | Missouri | BUTLER |  | 08 | 1221003 | This project consist of a thin lift asphalt overlay from Route WW in Poplar Bluff to Route 158 in Butler county | Pavement Improvement | 04/06/2009 | 06/09/2009 | 12/01/2009 | 267090.49 | 5.628
6193 | Missouri | CAPE GIRARDEAU |  | 08 | 1271004 | This project consist of resurfacing roadway from the Jackson city limits to Route 61 - Cape Girardeau county | Pavement Improvement | 03/08/2010 |  | 09/01/2010 | 422100 | 2.277
6194 | Missouri | CAPE GIRARDEAU |  | 08 | 1277002 | This project consist of resurfacing and improving shoulders from Lasalle Ave to Lexington Ave. in Cape Girardeau county | Pavement Improvement | 11/09/2009 | 03/15/2010 | 12/01/2010 | 2357519.01 | 4.2
6195 | Missouri | PEMISCOT |  | 08 | 1286003 | This project consist of a thin lift asphalt overlay from Route 164 to the Arkansas state line in Pemiscot county | Pavement Improvement | 05/08/2009 | 05/08/2009 | 12/01/2009 | 364909.97 | 6.465
6196 | Missouri | PEMISCOT |  | 08 | 1321002 | This project consist of a thin lift asphalt overlay from Route U to Route 164 in Pemiscot county | Pavement Improvement | 05/08/2009 | 05/08/2009 | 12/01/2009 | 467598.93 | 6.091
6197 | Missouri | HOLT |  | 06 | 1324003 | This project consist of a thin lift asphalt overlay on Spur 113 in Holt County from Route 113 to Route A and on Route A in Nodaway County from Spur 113 to Route 71 | Pavement Improvement | 07/06/2009 | 08/24/2009 | 07/01/2010 | 680396.98 | 11.702
6198 | Missouri | ATCHISON |  | 06 | 1361059 | This project involves painting, redeck and bridge repairs of the Missouri River brige at Brownville, NE | Bridge Improvement | 08/31/2009 | 08/31/2009 | 12/01/2011 | 4868280 | 0.6
6199 | Missouri | PUTNAM |  | 06 | 1362025 | This project consist of a thin lift asphalt overlay from Route 63 to Route N in Schuyler and Putnam counties | Pavement Improvement | 04/06/2009 | 04/10/2009 | 12/01/2009 | 842800.72 | 8.334
6200 | Missouri | PUTNAM |  | 06 | 1362026 | This project consist of resurfacing roadway from Route 5 to Route N - Putnam county | Pavement Improvement | 02/08/2010 | 04/01/2010 | 11/01/2010 | 998300 | 17.839
6201 | Missouri | ST LOUIS |  | 03 | 1411029 | This project consist of right of way acquisition to relocate and construct Route 141 from Route 40 to Route 340 (Olive Blvd). In cooperation with St. Louis County, construct Route 141 from Route 340 | New Construction | 08/19/2009 | 08/19/2009 | 03/01/2012 | 57750900 | 2.7
6202 | Missouri | ST LOUIS |  | 01,02,03 | 1411034 | This project consist of grading for the utility relocation at Route 340 in St. Louis county | Pavement Improvement | 09/08/2009 | 09/08/2009 | 05/01/2010 | 741600 | 0.5
6203 | Missouri | JACKSON |  | 5 | 1501010 | This project consists of grading, drainage and new concrete pavement to construct a divided 4 lane highway on Route 9 from Horridge Road to Route 291 in Lee's Summit. | Pavement Widening | 09/08/2009 | 09/08/2009 | 11/01/2011 | 14101900 | 3.426
6204 | Missouri | STATEWIDE |  | 4,7 | 1600706 | This project consist of resurfacing in communities with populations less than 5,000 in Barton and Jasper | Pavement Improvement | 03/15/2010 | 05/03/2010 | 10/01/2010 | 270818.67 | 0
6205 | Missouri | BATES |  | 4 | 1600707 | This project consist of resurfacing in communities with populations less than 5,000 in Bates County. Project split from 7S0010B. | Pavement Improvement | 03/15/2010 |  | 10/01/2010 | 173083.46 | 0
6206 | Missouri | ST CLAIR |  | 4 | 1600708 | This project consist of resurfacing in communities with populations less than 5,000 in St. Clair county. | Pavement Improvement | 03/15/2010 | 06/10/2010 | 10/01/2010 | 213974.32 | 0
6207 | Missouri | BARRY |  | 7 | 1600709 | This project consist of resurfacing in communities with populations less than 5,000 in Barry County. | Pavement Improvement | 03/15/2010 | 05/11/2010 | 10/01/2010 | 123123.57 | 0
6208 | Missouri | PEMISCOT |  | 08 | 1641008 | This project consist of a thin lift asphalt overlay from Route D to Route DD in Pemiscot county | Pavement Improvement | 05/08/2009 | 05/08/2009 | 12/01/2009 | 99361.37 | 1.725
6209 | Missouri | CLAY |  | 06 | 1691086 | A $1.1 million contract awarded to St. Joseph Fuel Oil & Manufacturing Company for two miles of sidewalk improvements. Included are new upgrades to the existing sidewalk and adding curb ramps to accom | Transportation Enhancements | 08/10/2009 | 08/10/2009 | 12/01/2009 | 1133856.23 | 2.023
6210 | Missouri | ANDREW |  | 06 | 1692021 | This project consist of pavement and shoulder improvements from Route 31 to I-29 in Dekalb, Andrew, and Buchanan counties | Pavement Improvement | 07/06/2009 | 09/25/2009 | 12/01/2009 | 2694300 | 21.438
6211 | Missouri | SALINE |  | 04 | 2401019 | This project consist of a thin lift asphalt overlay from east of Route 65 to Route 41 in Saline county | Pavement Improvement | 03/30/2009 | 03/30/2009 | 12/01/2009 | 73420.03 | 0.391
6212 | Missouri | HOWARD |  | 06 | 2401020 | This project consist of pavement and shoulder improvements from Route 5 to Route 40 in Howard county | Pavement Improvement | 06/08/2009 | 09/28/2009 | 12/01/2009 | 1072711.37 | 12.8
6213 | Missouri | STONE |  | 7 | 2651001 | This project consist of a thin lift asphalt overlay from Route 76 to Route 165 in Stone and Taney counties | Pavement Improvement | 04/06/2009 | 04/14/2009 | 12/01/2009 | 282036.46 | 5.364
6214 | Missouri | GREENE |  | 07 | 2661012 | This project consist of a thin lift asphalt overlay from Route AB to Farm Road 107 in Greene county | Pavement Improvement | 06/08/2009 | 07/14/2009 | 12/01/2009 | 64386.58 | 1.324
6215 | Missouri | ST CHARLES |  | 02 | 3641032 | This project consist of extending Page Ave. from 0.3 miles west of Harvester to 0.6 miles east of Central School Road at Woodstream in St. Charles county | New Construction | 10/05/2009 | 10/22/2009 | 09/30/2011 | 20570800 | 0.3
6216 | Missouri | ST CHARLES |  | 02 | 3641033 | This project consist of extending Page Ave. from 0.6 miles east of Central School Road at Woodstream to 0.3 miles wet of Central School Road in St. Charles county | New Construction | 10/05/2009 | 10/22/2009 | 09/30/2011 | 23240000 | 0.9
6217 | Missouri | ST CHARLES | ST. LOUIS (IL) | 02 | 3641034 | This project consist of grading, paving, bridge and one-way outer roads from .3 miles west of Central School Road to Mid Rivers Mall Drive - St. Charles county | Pavement Improvement | 03/01/2010 | 03/10/2010 | 09/30/2011 | 6065000 | 1.3
6218 | Missouri | STATEWIDE |  | Statewide | 4500205 | This project consist of cold in Place Recycling on various routes in Nodaway, Caldwell, Harrison, DeKalb, Daviess,Worth, Andrew and Gentry counties | Pavement Improvement | 06/08/2009 | 06/23/2009 | 10/01/2009 | 3490059.09 | 0
6219 | Missouri | ST LOUIS CITY |  | 01 | 5500664 | "St.Louis City will be doing enhancements on Manchester Road from Taylor Ave. to Sarah Ave. This consist of sidewalk widening, removal and relocation of curbs to create four 11'-6"" lanes, pedestrian | Transportation Enhancements | 01/07/2010 | 01/07/2010 | 05/01/2011 | 1311873.89 | 0.7
6220 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | 5595611 | St.Louis City will be doing Phase 2 of the Salisbury Street enhancements from N. Florissant to 11th Street. This consist of reconstructing sidewalks and ramps, new pedestrian lighting, curb repair, la | Transportation Enhancements | 01/08/2010 | 01/08/2010 | 05/15/2011 | 870681 | 0.4
6221 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 03 | 5602602 | St. Louis City will be widening bridge over Union Pacific RR tracks, including iimprovements to intersections with southbound I-55 off ramp (Loughborough Ave over Union Pacific Railroad) | Bridge Replacement | 05/24/2010 |  | 11/01/2010 | 631032 | 0.11
6222 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | 5603602 | St. Louis City will be doing asphalt resurfacing and constructing retaining walls and culverts on the Tucker Street Bridge from O'Fallon St. to Washington Avenue | Pavement Widening | 01/08/2010 | 01/08/2010 | 12/01/2011 | 17387181 | 0.665
6223 | Missouri | FRANKLIN | ST. LOUIS (IL) | 09 | 6201602 | The City of Union has received additional funds for improvments on the Church Street project including sidewalks, paved approaches, curb and gutter, utility adjustments and retaining walls from Route | Transportation Enhancements | 05/04/2009 | 07/01/2009 | 10/30/2009 | 207932 | 1.2
6224 | Missouri | BOONE |  | 09 | 7401020 | This project consist of pavement improvements on westbound and eastbound lanes from Broadway to Route 63 in Boone county | Pavement Improvement | 07/13/2009 | 07/13/2009 | 10/05/2009 | 1916857.02 | 5.303
6225 | Missouri | BUCHANAN |  | 06 | 7591001 | This project consists of pavement repair and resurfacing the roadway and shoulders on Route 759 Buchanan county. | Pavement Improvement | 02/01/2010 | 04/26/2010 | 12/01/2010 | 2158382.86 | 2.118
6226 | Missouri | STONE |  | 07 | 9900832 | In Gelena, the city will be doing sidewalk improvements around the square along 4th Street, Maple Street, and Main Street | Transportation Enhancements | 10/15/2009 | 11/01/2009 | 09/01/2010 | 252235.93 | 0.15
6227 | Missouri | OZARK |  | 08 | 9900840 | In Gainsville, the city will be doing sidewalk rehabilitation and construction near the square and along various city streets | Transportation Enhancements | 01/29/2010 | 02/16/2010 | 09/01/2010 | 113780 | 0.35
6228 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | 9900860 | This project will provide scoping and final design to improve safety and capacity of Route CC from Main Street in the City of Nixa to Route NN/J in the City of Ozark. | Other | 09/21/2009 | 09/28/2009 | 09/01/2010 | 900000 | 3.7
6229 | Missouri | BUCHANAN | ST. JOSEPH (KS) | 06 | ES01001 | This project consist of constructing a new truck staging area along Stockyard Expressway and intersections improvements in the St. Joseph Regional Port area | Pavement Widening | 07/17/2009 | 08/27/2009 | 11/01/2010 | 1097188.28 | 0
6230 | Missouri | NODAWAY |  | 06 | ES01002 | The City of Maryville will be constructing Phase A-II, which is a walking/biking trail located within the city limits of Maryville. This trail will be 3760 ft. in length and 6' to 8' in wide with a co | Transportation Enhancements | 09/11/2009 | 09/11/2009 | 08/30/2010 | 284421.34 | 0.712
6231 | Missouri | BUCHANAN | ST. JOSEPH (KS) | 06 | ES01003 | "The Urban Trail System incorporates the construction of 10' wide, 6"" thick concrete pavement for use as a high-volume, shared-use trail. This specific phase constitutes the first component of a two | Transportation Enhancements | 04/05/2010 | 04/05/2010 | 08/30/2010 | 190994.62 | 0.316
6232 | Missouri | CHARITON |  | 06 | ES02002 | The City of Brunswick will be replacing existing sidewalks along Route 24 from Polk Street to Adams Street | Transportation Enhancements | 10/13/2009 | 10/14/2009 | 07/01/2010 | 412126.01 | 0.712
6233 | Missouri | WARREN |  | 09 | ES03002 | City will construct a new ADA (Americans with Disabilities Act) compliant sidewalk, which will provide connectivity of Marthasville?s ?Uptown? section to the ?Downtown? section. There will be replace | Transportation Enhancements | 09/23/2009 | 10/01/2009 | 07/31/2010 | 57549.52 | 0.15
6234 | Missouri | LEWIS |  | 09 | ES03003 | City will remove old, deteriorated existing sidewalks with safe new sidewalks, which will be constructed to American with Disabilities Act (ADA) Standards. The five-foot-wide sidewalk will connect th | Transportation Enhancements | 08/07/2009 | 08/07/2009 | 07/01/2010 | 68422.79 | 0.09
6235 | Missouri | PIKE |  | 09 | ES03004 | City will install historic/ornamental lighting in the downtown district. The new lighting will be in the vicinity of Lewis Street, Clark Street and 4th Street (State Route B) | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 07/01/2010 | 90000 | 0.4
6236 | Missouri | MONROE |  | 09 | ES03005 | The City of Paris will replace existing sidewalk with new sidewalk that will be constructed to American with Disabilities Act (ADA) Standards. There will also be the installation of historic lightin | Transportation Enhancements | 08/20/2009 | 08/20/2009 | 07/01/2010 | 76378.82 | 0.6
6237 | Missouri | MONTGOMERY |  | 09 | ES03007 | The City of Jonesburg proposes to remove 982 linear feet of existing sidewalk and construct 4? concrete sidewalk that will be constructed to American with Disabilities Act (ADA) Standards. The sidewa | Transportation Enhancements | 10/19/2009 | 10/19/2009 | 07/31/2010 | 60990.83 | 0.19
6238 | Missouri | CLAY | KANSAS CITY (KS)-MO | 06 | ES04001 | The City of Gladstone will be doing landscaping, decorative lighting, crosswalks and other scenic corridor improvements along North Oak Trafficway from NE 69th Street to NE 71st Street | Pavement Improvement | 09/18/2009 | 09/22/2009 | 10/24/2009 | 305097.35 | 1.51
6239 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 04,06 | ES04002 | The City of Blue Springs will be doing mill, asphalt overlay, and curb pavement markings at Adams Dairy Parkway from Duncan to Moreland School Road | Pavement Improvement | 10/21/2009 | 10/21/2009 | 11/16/2009 | 378061 | 0.4
6240 | Missouri | CLAY | KANSAS CITY (KS)-MO | 06 | ES04003 | The City of Liberty will be putting in additional curbs, lane width and improvements of medians of Kansas Street, Liberty Drive, and Mill Street | Pavement Improvement | 10/12/2009 | 10/13/2009 | 11/18/2009 | 378061 | 0.803
6241 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04004 | The City of Raytown will be doing removal and replacement of deteriorated curbs and sidewalk. There will also be construction of new curbs and sidewalks at varius location throughout Raytown | Pavement Improvement | 06/09/2010 | 06/10/2010 | 12/01/2010 | 377971.28 | 2.745
6242 | Missouri | PLATTE | KANSAS CITY (KS)-MO | 06 | ES04005 | This project consist of construction of left turn lanes at Route AA in the City of Riverside - Platte county | New Construction | 03/08/2010 | 03/24/2010 | 06/11/2010 | 334600 | 0.304
6243 | Missouri | CASS | KANSAS CITY (KS)-MO | 04 | ES04006 | In Pleasant Hill, the city will be doing milling and overlay work on Business Route 7, Country Club Drive, and Sugarland Drive | Pavement Improvement | 06/01/2010 |  | 12/01/2010 | 222284.68 | 1.5
6244 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 06 | ES04007 | Jackson County will be replacing failing deck and upgrading guardrail system on Blue Mills Bridge | Bridge Improvement | 02/15/2010 | 02/15/2010 | 12/01/2010 | 378061 | 0.049
6245 | Missouri | CASS | KANSAS CITY (KS)-MO | 04 | ES04008 | In Harrisonville, the city will be doing milling and overlay work on North Independence, South Street, North Commercial Street, and South Independence | Pavement Improvement | 03/01/2010 |  | 08/01/2010 | 259218.75 | 1.76
6246 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04009 | The City of Grandview will be reconstruction 2000 ft of the rural section of 2nd Street to connect with 1600 ft long 3rd Street being constructed on a new alignment | Pavement Widening | 06/15/2010 | 06/16/2010 | 06/11/2011 | 378061 | 0.34
6247 | Missouri | CASS | KANSAS CITY (KS)-MO | 05 | ES04012 | In Raymore, the city will be doing milling and overlay work on M-58 Highway | Pavement Improvement | 06/01/2010 |  | 08/30/2010 | 359621.95 | 0.01
6248 | Missouri | STATEWIDE | KANSAS CITY (KS)-MO | 04,05,06 | ES04016 | Signal retiming/synchronization, vehicle detection on creitical intersection, cameras added, Operation Green Light location expansion, new communication tower and upgrades to the wireless backbone. | Safety/Traffic Management | 08/26/2009 | 08/27/2009 | 12/31/2011 | 3592250.5 | 0
6249 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04017 | The City of Independence will be creating a Major North-South divided four lane street. The new roadway will have open ditches, sidewalk, and a shared bicycle/pedestrian path to reconnect city and so | New Construction | 03/15/2010 | 03/29/2010 | 12/01/2011 | 2584846.31 | 0.8
6250 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04019 | The City of Independence will be widening Jackson Drive from Holke Road to M-78 Highway from the existing 2 lanes to 4. There will also be installation of curb, gutter, sidewalk, and shared use path | Pavement Widening | 02/01/2010 | 02/03/2010 | 09/01/2010 | 1016096.05 | 0.604
6251 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04020 | Kansas City will be constructing traffic signals at five intersections: 31st Street at Southwest Trafficway, The Paseo, Benton Blvd, Cleveland Avenue, and Jackson Avenue | Safety/Traffic Management | 04/26/2010 | 04/26/2010 | 12/01/2010 | 749388.4 | 0
6252 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04022 | The City of Blue Springs will be construction traffic signals at two intersections: 39th Street and Broadway Blvd and 39th Street and Roanake Road | Safety/Traffic Management | 03/15/2010 | 03/15/2010 | 12/01/2010 | 400000 | 0
6253 | Missouri | STATEWIDE | KANSAS CITY (KS)-MO | 05,06 | ES04023 | A planning study to develop detailed transit implementation, phasing, and costing information to support expanded local, county, and retional service implementation. | Other | 08/12/2009 | 08/12/2009 | 12/31/2011 | 261250 | 0
6254 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04024 | "The City of Kansas City will be constructing a 10"" wide 1600 ft trail, which will connect to the existing trail " | Transportation Enhancements | 04/15/2010 | 04/15/2010 | 12/01/2010 | 313753.73 | 0.49
6255 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 06 | ES04027 | The City of Raytown will be reconstructing a 6.2 mile bicycle and pedestrian trail at Longview Lake | Transportation Enhancements | 02/15/2010 | 02/15/2010 | 12/01/2010 | 250000 | 6.2
6256 | Missouri | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04028 | The City of Lee's Summit will be construction 0.7 miles of multi-use 10' wide trail along Todd George Road to connect to existing multi-use trail on both north and south | Transportation Enhancements | 05/03/2010 | 05/14/2010 | 12/01/2010 | 154541.4 | 0.46
6257 | Missouri | PLATTE |  | 06 | ES04032 | The City of Weston will be constructing new 5' wide sidewalks on 5th Street | Transportation Enhancements | 09/17/2009 | 09/17/2009 | 12/01/2010 | 74516.34 | 0.09
6258 | Missouri | LAFAYETTE |  | 04 | ES04034 | The City of Higginsville will be constructing new 5' wide sidewalks on Fairground Park/Grandview Elementary Sidewalks | Transportation Enhancements | 08/19/2009 | 08/19/2009 | 12/01/2010 | 150754.33 | 0.57
6259 | Missouri | HENRY |  | 04 | ES04035 | This project consist of sidewalk improvements on Route 18 from east of 9th Street to west of Pawnee Street in the City of Clinton | Transportation Enhancements | 09/11/2009 | 09/21/2009 | 08/15/2010 | 139996.52 | 0.428
6260 | Missouri | CLAY |  | 04 | ES04036 | City of Kearney will be installing street lights, 5' sidewalks, fence handrail landscape along Main Street | Transportation Enhancements | 09/25/2009 | 09/25/2009 | 12/01/2010 | 116565.3 | 0.22
6261 | Missouri | BOONE | COLUMBIA | 09 | ES05003 | In Columbia, the city will be building a raiload bridge over Route 63 north of Route B in Boone county | Safety/Traffic Management | 07/30/2009 | 08/17/2009 | 10/01/2010 | 3350137.6 | 0.2
6262 | Missouri | BENTON |  | 04 | ES05004 | Construction of the Steamboat Landing Trail in the City of Warsaw. This project includes a pedestrian trail, landscaping, and lighting along the north side of the harbor connecting Drake Harbor to th | Transportation Enhancements | 03/10/2010 | 03/10/2010 | 10/01/2010 | 260476 | 0
6263 | Missouri | BOONE |  | 09 | ES05005 | The City of Hallsville will be constructing sidewalks along Ricketts Road, Sunrise Drive, Fairview Street, and Route OO | Transportation Enhancements | 06/28/2010 | 07/01/2010 | 10/01/2010 | 289331 | 0
6264 | Missouri | MARIES |  | 09 | ES05006 | The City of Belle will be replacing old broken sidewalk on Third St. from Tellman Ave. to Linn Ave. Also included are new sidewalks on Third St. from Johnson Ave. to Apple Ave and along Fourth St. be | Transportation Enhancements | 02/10/2010 | 03/01/2010 | 10/01/2010 | 66653 | 0
6265 | Missouri | CAMDEN |  | 04 | ES05007 | The City of Osage Beach will be constructing new sidewalks along the west side of Rte 54 from Redbud Road to Zebra Road and along the east side of Rte 54 from Zebra Road to Hatchery Road | Transportation Enhancements | 02/17/2010 | 02/18/2010 | 10/01/2010 | 281786 | 0.76
6266 | Missouri | BOONE |  | 09 | ES05008 | This project consist of MDNR bridge rehabilitation on Katy Trail over Moniteau Creek near Rocheport - Boone county | Transportation Enhancements | 03/15/2010 |  | 10/01/2010 | 487300 | 0
6267 | Missouri | COOPER |  | 06 | ES05009 | This project consist of MDNR culvert rehabilitation on Katy Trail over an unnamed creek, near Pleasant Green - Cooper county | Transportation Enhancements | 03/15/2010 |  | 10/01/2010 | 199700 | 0
6268 | Missouri | ST CHARLES |  | 2,9 | ES05010 | This project consist of MDNR bridge replacement on Katy Trail over Little Femme Osage Creek, near Defiance - St. Charles county | Transportation Enhancements | 03/15/2010 |  | 10/01/2010 | 249000 | 0
6269 | Missouri | ST CHARLES |  | 2,9 | ES05011 | This project consist of MDNR construction of approximately 2.5 miles of new Katy Trail from St. Charles to Machens - St. Charles County | Transportation Enhancements | 03/15/2010 |  | 10/01/2010 | 370000 | 0
6270 | Missouri | FRANKLIN | ST. LOUIS (IL) | 01 | ES06001 | Goodfellow-Skinker Asphalt Overlay and Pedestrian Improvements . Design Study - Engineering Design Study -pedestrian facilities,streetscaping elements, and reconfiguration of the MO T / Front Street i | Other | 07/10/2009 | 07/10/2009 | 03/01/2010 | 327404.08 | 0.2
6271 | Missouri | FRANKLIN | ST. LOUIS (IL) | 09 | ES06002 | Franklin County will be doing a pedestrian/bike path along the west side of Route T from Great Oaks Drive to Labadie Elementary School | Transportation Enhancements | 07/10/2009 | 07/10/2009 | 10/01/2010 | 280866.6 | 0.6
6272 | Missouri | FRANKLIN | ST. LOUIS (IL) | 09 | ES06006 | The City of Washington will be doing asphalt resurfacing on various streets: W. Eighth Street, W. Main Street, Grand Avenue, Pottery Road, Old Route 100, Route 47 to Stafford Street | Pavement Improvement | 08/07/2009 | 08/07/2009 | 10/01/2009 | 683713.6 | 3
6273 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06007 | The City of Crystal City will be doing aphalt resurfacing on Crystal City Heights Road from Missouri Ave. to Commercial Blvd | Pavement Improvement | 08/19/2009 | 08/19/2009 | 02/10/2010 | 369778.1 | 1.4
6274 | Missouri | FRANKLIN | ST. LOUIS (IL) | 09 | ES06008 | Washington Special Road Distrct will be doning asphalt resurfacing on Bieker Road from S. Pointe Road to the Washington City limits. | Pavement Improvement | 08/27/2009 | 08/27/2009 | 07/31/2010 | 192368 | 4
6275 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06009 | Jefferson County will be doing asphalt resurfacing on Antire Road from High Ridge Blvd. to the St. Louis County line | Pavement Improvement | 12/15/2009 |  | 08/27/2010 | 311351.1 | 3.96
6276 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06010 | Jefferson County will be installing guradrail on Old Lemay Ferry Road from Route M to Wedde Road | Safety/Traffic Management | 05/10/2010 | 05/11/2010 | 12/01/2010 | 125160 | 0.43
6277 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06011 | Jefferson County will be doing asphalt resurfacing on River Street Road from Route K to Route 61/67 | Pavement Improvement | 11/19/2009 | 11/23/2009 | 03/24/2010 | 67515.5 | 0.22
6278 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06012 | The City of De Soto will be doing asphalt resurfacing, concrete slab replacement, curb ramp replacement, curb and gutter, and street trees on Amvets Drive from S. Main Street to Route 21 | Pavement Improvement | 02/24/2010 | 03/03/2010 | 08/31/2010 | 855774.6 | 1.1
6279 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06013 | Jefferson County will be doing asphalt resurfacing on Flucom Road from Route 67 to De Soto city limits | Pavement Improvement | 03/30/2010 | 03/30/2010 | 06/25/2010 | 454077.66 | 4.38
6280 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06014 | Jefferson County will be doing asphalt resurfacing on Klondike (South) Road from Route E to McClain Street | Pavement Improvement | 01/20/2010 | 03/29/2010 | 10/01/2010 | 439039 | 1.8
6281 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06015 | Festust Special Road District will be doing asphalt resurfacing on Scenic Dr., County Road, Cherry Ln., Scenic - Herculaneum city limits to Festus city limit, Cherry - Route Z to County Rd., County Ro | Pavement Improvement | 09/10/2009 | 09/10/2009 | 10/01/2010 | 421918.77 | 3
6282 | Missouri | JEFFERSON | ST. LOUIS (IL) | 03 | ES06016 | Jefferson County will be reconstructing and adding a center turn lane on Little Brennan Road from Route 30 to Gravois Road | Pavement Widening | 05/10/2010 | 05/10/2010 | 04/01/2011 | 208356.66 | 0.1
6283 | Missouri | ST LOUIS | ST. LOUIS (IL) | 03 | ES06017 | St. Louis County will be construction and completing the Maryland Heights Expressway Connector (4 lane freeway) from Page Ave. (Rte. 364) to Olive Blvd. (Rte. 340) | New Bridge Construction | 04/19/2010 | 04/19/2010 | 07/01/2010 | 20000000 | 2.5
6284 | Missouri | ST CHARLES | ST. LOUIS (IL) | 09 | ES06018 | The City of Cottleville will be constructing a new traffice signal at Route N and Brittany Cove | Pavement Widening | 08/21/2009 | 08/21/2009 | 12/01/2010 | 164133.52 | 0.1
6285 | Missouri | ST CHARLES | ST. LOUIS (IL) | 09 | ES06019 | The City of O'Fallon will be doing asphalt Resurfacing on Main (Rte.M), Sonderen, East Pitman: Main St. (Rte. M) - I-70 to 3rd St., Sonderen - Wabash Ave. to I-70, East Pitman St. - Main St. to Sonde | Pavement Improvement | 09/01/2009 | 09/01/2009 | 05/28/2010 | 623575.63 | 1.32
6286 | Missouri | ST CHARLES | ST. LOUIS (IL) | 02 | ES06020 | The City of St. Charles will be doing Phase 2 on the Fifth Street Corridor, which consist of widen lanes from three to five from First Capiol to Tompkins Street | Pavement Widening | 03/10/2010 | 03/10/2010 | 08/01/2010 | 318002 | 0.12
6287 | Missouri | ST CHARLES | ST. LOUIS (IL) | 09 | ES06021 | St. Charles County will be installing a shared use lane on Route 94 from Defiance Road to Walnut Springs Road | Pavement Widening | 09/08/2009 | 09/08/2009 | 10/01/2010 | 430000 | 0.5
6288 | Missouri | ST LOUIS | ST. LOUIS (IL) | 02 | ES06023 | Great Streets Demonstration Project - Manchester Road - Rte. 141 to Rte. 109Engineering Planning and Design Study of entrances and exits and traffic flow. | Other | 09/08/2009 | 09/10/2009 | 03/01/2010 | 1100000 | 5
6289 | Missouri | ST LOUIS | ST. LOUIS (IL) | 01 | ES06024 | Engineering Design Study of Great Streets Demonstration Project - Natural Bridge Rd. - Lucas & Hunt Rd. to UMSL South Metrolink Station in Normandy | Other | 10/13/2009 | 10/19/2009 | 03/01/2010 | 998644.49 | 0.75
6290 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06025 | Great Streets Demostration Project on South Grand from Arsenel to McDonald in City of St. Louis to improve entrances and exits and traffic flow. | Other | 07/10/2009 | 07/10/2009 | 04/30/2010 | 890000 | 0.4
6291 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06026 | Grand Center/Grand Blvd. Streetscape- Lindell to Page Ave.Sidewalk improvements, new pedestrian signs, crosswalks and traffic calming | Transportation Enhancements | 08/12/2009 | 08/12/2009 | 05/01/2011 | 2000000 | 0.66
6292 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06027 | St. Louis City will be doing improvements to South Grand from Arsenal to McDonald by installing a pedestrian signal and update sidewalks | Pavement Widening | 01/15/2010 | 01/15/2010 | 06/01/2011 | 1503740.28 | 0.4
6293 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01,03 | ES06028 | St. Louis City will be doing streetscapes on Vandeventer Avenue, Kingshighway to Shaw; segment of Accomac. They will be adding pedestrian signal, solar powered lighting, and rain garden | Pavement Widening | 08/12/2009 | 08/12/2009 | 12/01/2010 | 763777.67 | 0.45
6294 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06029 | The Land Clearance for Development Authority for the City of St. Louis will be doing reconstruction, reconstruct and new construction of sidewalks, improved railroad crossings, signal improvements at | Pavement Widening | 07/29/2009 | 07/29/2009 | 02/01/2011 | 2603872.03 | 0.6
6295 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06030 | St. Louis City will be doing repairs to Compton Avenue over Union Pacific Railroad from Chouteau to Spruce and bridge repairs | Bridge Improvement | 01/08/2010 | 01/08/2010 | 08/01/2011 | 1255915.02 | 0.5
6296 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06031 | St. Louis City will be doing pedestrian lighting enhancements on Dr. Martin Luther King Road from Arlington West to city limits | Transportation Enhancements | 06/07/2010 |  |  | 949875.15 | 1.6
6297 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06032 | St. Louis City will be adding new pedestrian lighting on Manchester Road from Taylor Ave. to Sarah Ave. | Transportation Enhancements | 01/07/2010 | 01/07/2010 | 08/01/2010 | 981044.13 | 0.67
6298 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06033 | St. Louis City will be doing signal interconnect/Upgrade on Morgan Ford Road. This will consist of 11 signalized intersections from Arsenal Street to City limits. Interconneect traffic signals, signa | Safety/Traffic Management | 07/24/2009 | 07/24/2009 | 04/01/2011 | 1477016.57 | 3.74
6299 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06034 | The Land Clearance for Development Authority of the City of St. Louis will be doing mill/resurfacesurfacing and new curbs, bumpouts, sidewalks, ramps, lighting, and signals on North Sarah Street from | Pavement Improvement | 06/22/2009 | 06/22/2009 | 09/01/2010 | 1250000 | 0.26
6300 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06035 | St. Louis City will be doing overlay and pedestrian improvements on Good Fellow/Skinker. This will consist of asphalt mill and overlay, sidewalk improvements, new ADA compliant curb ramps, and stripin | Pavement Improvement | 08/12/2009 | 08/12/2009 | 07/01/2011 | 3371273 | 7.3
6301 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06036 | South Broadway Streetscape - Courtois to Upton St..Traffic calming measures, access management, new lighting, sidewalks | Pavement Widening | 08/12/2009 | 08/12/2009 | 03/01/2010 | 1025690.19 | 0.28
6302 | Missouri | ST CHARLES | ST. LOUIS (IL) | 02 | ES06038 | City of Lake St. Louis will be connecting the pedestrian and bike pathway from Northshire Lane to Prospect Village Drive | Transportation Enhancements | 02/18/2010 | 03/30/2010 | 06/01/2010 | 41590.2 | 0.21
6303 | Missouri | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06040 | This project invovles the stabilization of the existing port muncipal dock at the St. Louis City Regional Port | Other | 09/23/2009 | 09/23/2009 | 12/01/2011 | 400000 | 0
6304 | Missouri | JASPER | JOPLIN | 07 | ES07001 | In Joplin, the city will be constructing a pedestrian and bicycle trail connecting the Frisco Greenway Trail to the intersection of Florida Avenue and Newman Road | Transportation Enhancements | 02/11/2010 | 02/15/2010 | 09/01/2010 | 439500 | 1.5
6305 | Missouri | JASPER | JOPLIN | 07 | ES07002 | In Carl Junction, the city will be doing the design and construction of a pedestrian and bicycle trail from Briarbrook Drive to Copper Oaks Drive. The beginning of this project starts where the previ | Transportation Enhancements | 08/06/2009 | 08/06/2009 | 09/01/2010 | 173025.53 | 0.67
6306 | Missouri | JASPER | JOPLIN | 07 | ES07003 | In Webb City, the city will be purchasing materials for the establishment of the Route 66 themed Welcome Center in Webb City | Transportation Enhancements | 11/20/2009 | 11/20/2009 | 07/31/2010 | 25828 | 0
6307 | Missouri | GREENE | SPRINGFIELD | 07 | ES08001 | The City of Strafford will be constructing sidewalks along McCabe St. from Washington Avenue to just west of Cedar Drive in front of Strafford Schools. | Transportation Enhancements | 02/16/2010 | 03/01/2010 | 06/16/2010 | 65074 | 0
6308 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | ES08002 | In Ozark, the city will be doing surface improvements by paving the existing Frisco Highline Trail from Springfield to Willard | Transportation Enhancements | 12/11/2009 | 01/14/2010 | 01/01/2010 | 78087.65 | 0.2
6309 | Missouri | GREENE | SPRINGFIELD | 07 | ES08003 | This project includes the construction of sidewalks along Highway Z from the existing Frisco Highline trail to the Willard Recreation Center in the City of Willard. | Transportation Enhancements | 10/16/2009 | 10/19/2009 | 01/01/2010 | 79625 | 0.6
6310 | Missouri | GREENE | SPRINGFIELD | 07 | ES08004 | This project will pave an existing segment of the Frisco Highline Trail from Willard to 3 miles north of Springfield | Transportation Enhancements | 11/05/2009 | 11/06/2009 | 06/01/2010 | 186482 | 0
6311 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | ES08006 | This project will provide an analysis of existing and projected traffic in order to develop an efficient traffic plan on 3rd Street from Jackson St. to Church St. | Other | 09/08/2009 | 09/08/2009 | 09/01/2010 | 13188 | 0.2
6312 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | ES08007 | This project consists of a Transportation Planning Study to determine priority corridors and priority projects with some prelminary scoping of transportation projects within the boundaries of the City | Other | 09/23/2009 | 09/23/2009 | 09/01/2010 | 40000 | 0
6313 | Missouri | GREENE | SPRINGFIELD | 07 | ES08008 | In Battlefield, the city will be constructing sidewalks along Cloverdale from Elm North | Transportation Enhancements | 11/04/2009 | 11/30/2009 | 09/01/2010 | 55879 | 0
6314 | Missouri | CHRISTIAN | SPRINGFIELD | 07 | ES08009 | This project will provide final design to improve safety and capacity at the intersection of Highway 160 & Highway 14 in the City of Nixa. | Other | 08/11/2009 | 08/25/2009 | 01/01/2010 | 119913 | 5.7
6315 | Missouri | POLK |  | 07 | ES08010 | This project will pave a segment of the existing Frisco Highline Trail near Bolivar and pave the Wishart trailhead. | Transportation Enhancements | 11/05/2009 | 11/06/2009 | 06/01/2010 | 151753.7 | 1
6316 | Missouri | GREENE | SPRINGFIELD | 7 | ES08011 | Ozark Greenways will be paving the current aggregate Frisco Highline Trail from Farm Road 115 to the trailhead in Springfield. | Transportation Enhancements | 05/18/2010 | 06/21/2010 | 06/01/2010 | 136782.9 | 0
6317 | Missouri | PHELPS |  | 08 | ES09001 | The City of St. James will replace inadequate and unsafe sidewalk and extend sidewalk where none exists, along Highway 68 from the downtown south to the city limits and on east and west Scioto Streets | Transportation Enhancements | 12/12/2009 | 12/18/2009 | 01/12/2010 | 114166.3 | 0.75
6318 | Missouri | TEXAS |  | 08 | ES09002 | The City of Houston is constructing 1.1 miles of new five foot sidewalk along Airport Road, Lone Star Drive, and Westwood Drive on city owned property at the Houston Memorial Airport. The sidewalk is | Transportation Enhancements | 10/23/2009 | 11/12/2009 | 12/01/2009 | 142096.84 | 1.1
6319 | Missouri | CAPE GIRARDEAU |  | 08 | ES10001 | This project involves the construction of a high-water rail line that will allow port rail to operate during high-water events | Other | 11/16/2009 | 11/16/2009 | 07/01/2010 | 890960.02 | 0
6320 | Missouri | NEW MADRID |  | 08 | ES10002 | This project involves extending a rail spur to a site for a new tenant. This includes rail extension, switch, crossings, and siding. | Safety/Traffic Management | 09/30/2009 | 11/16/2009 | 07/01/2010 | 687888.2 | 0
6321 | Missouri | STE GENEVIEVE |  | 03 | ES10003 | This project involves construction of phase 1 on a new port, which involves excavation and site developments. | Other | 04/01/2009 | 04/01/2009 | 07/01/2010 | 931816.81 | 0
6322 | Missouri | ST FRANCOIS |  | 08 | ES10004 | The City of Farmington will be doing constructing on sidewalks on North Fleming Ave., St. Genevieve Ave., Forster Street, Franklin Street, and Walton Drive | Transportation Enhancements | 06/01/2010 |  | 08/29/2010 | 201416.77 | 1.74
6323 | Missouri | DUNKLIN |  | 08 | ES10005 | The City of Malden will be doing Phase II, which consists of renovation of downtown of sidewalks. This consist of Main St. from Douglas to Marion, main St from Madison to Decatur, and Laclede from Ma | Transportation Enhancements | 05/21/2010 | 05/26/2010 | 10/13/2010 | 93104.8 | 0.5
6324 | Missouri | NEW MADRID |  | 08 | ES10006 | The City of New Madrid will be doing sidewalk construction on Crisler Street, Mott Street, Capitol Street, Waters Street, Main Street | Transportation Enhancements | 04/29/2010 | 06/01/2010 | 09/28/2010 | 103117.11 | 0.6
6325 | Missouri | PERRY |  | 08 | ES10007 | The City of Perryville will be doing sidewalk construction on Schindler Road, State Street, Bredall Street, Waters Street, Rosati Court, Zeno Street, Bruce Street, Drury Lane | Transportation Enhancements | 05/06/2010 | 06/01/2010 | 09/02/2010 | 207040.45 | 1
6326 | Missouri | BUTLER |  | 08 | ES10008 | The City of Poplar Bluff will be doing sidewalk construction on Poplar Street, Fifth Street, and Vine Street. There will be curb and gutter improvements on Vine Street. Construction of trail connecti | Transportation Enhancements | 05/25/2010 | 06/10/2010 | 09/28/2010 | 154629 | 1
6327 | Missouri | STODDARD |  | 08 | ES10009 | The City of Puxico will be doing sidewalk improvements on South East L. Hawks Street, East Owen Ave., South Hickman Street, and West Richard Ave. | Transportation Enhancements | 04/19/2010 | 06/09/2010 | 08/26/2010 | 83885.95 | 0.28
6328 | Missouri | LEWIS |  | 09 | FB03006 | This project involves port capital improvements. These improvements include making the existing road and staging area concrete, installing public restrooms and storage depot, and improving existing d | Other | 01/05/2010 | 01/05/2010 | 06/01/2011 | 21000 | 0
6329 | Missouri | STE GENEVIEVE |  | 03 | FB08001 | This project is located at the Port of New Bourbon and consit of a ferry boat berthing, bank stabiization an construction of a mooring structure in Ste. Genevieve C | Other | 04/01/2009 | 04/18/2010 | 01/01/2011 | 68183.19 | 0
6330 | Missouri | MISSISSIPPI |  | 08 | FB10010 | This project invovles the installation of new enginees and coolers on an existing tug, and the purchase of a new barge. | Other | 02/08/2010 | 02/22/2010 | 06/01/2011 | 57170.54 | 0
6331 | Missouri | STATEWIDE |  | 01 | FY09005 | The project is part of an ongoing program that is designed to increase participation among minorities, women and disadvantaged individuals in the highway construction workforce and train and prepare i | Other | 01/13/2010 | 01/13/2010 | 10/31/2010 | 145000 | 0
6332 | Missouri | BOONE |  | 09 | FY09006 | The project is part of an ongoing program that provides minorities, women and disadvantaged individuals the educational experiences to enhance work maturity skills, GED attainment, tools, equipment an | Other | 01/13/2010 | 01/13/2010 | 10/31/2010 | 190433.54 | 0
6333 | Missouri | ATCHISON |  | 06 | S001011 | This project consist of a thin lift asphalt overlay from Route 136 to I-29 in Atchison county | Pavement Improvement | 06/08/2009 | 06/29/2009 | 10/01/2009 | 267860.32 | 3.75
6334 | Missouri | NODAWAY |  | 06 | S004007 | This project consist of a thin lift asphalt overlay from Route 148 to Route E in Nodaway county | Pavement Improvement | 07/06/2009 | 08/24/2009 | 07/01/2010 | 395140.08 | 8.133
6335 | Missouri | NODAWAY |  | 06 | S006009 | This project consist of resurfacing roadway from Maryville west city limits to east city limits - Nodaway county | Pavement Improvement | 03/08/2010 | 05/28/2010 | 12/01/2010 | 481300 | 2.299
6336 | Missouri | ATCHISON |  | 06 | S007006 | This project consist of a thin lift asphalt overlay from Route C to Route 136 in Atchison county | Pavement Improvement | 06/08/2009 | 06/29/2009 | 10/01/2009 | 593013.14 | 9.881
6337 | Missouri | ANDREW |  | 06 | S029004 | This project consist of a thin lift asphalt overlay from Route 48 to Route E in Andrew county | Pavement Improvement | 07/06/2009 | 08/24/2009 | 07/01/2010 | 420917.25 | 7.984
6338 | Missouri | BUCHANAN |  | 06 | S042005 | This project consist of a thin lift asphalt overlay to improve pavement condition from Route 6 to Route OO, near Clarksdale - Buchanan/Dekalb county | Pavement Improvement | 03/08/2010 | 04/01/2010 | 11/01/2010 | 409400 | 8.253
6339 | Missouri | BUCHANAN |  | 06 | S058005 | This project consist of a thin lift asphalt overlay from Route 371 to Route MM in Buchanan county | Pavement Improvement | 07/06/2009 | 09/25/2009 | 07/01/2010 | 213527.81 | 4.036
6340 | Missouri | CLINTON |  | 06 | S067011 | This project consist of a thin lift asphalt overlay from Route 69 to Route H in Clinton county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 599812.81 | 11.022
6341 | Missouri | BUCHANAN |  | 06 | S083013 | "This project consists of concrete pavement repair to the existing concrete roadway and a 3-3/4"" asphalt overlay over the existing concrete roadway along with a 3-3/4"" asphalt overlay of the existin | Pavement Improvement | 08/10/2009 | 09/10/2009 | 12/01/2009 | 1886410.39 | 2.4
6342 | Missouri | LIVINGSTON |  | 06 | S111009 | This project consist of a thin lift asphalt overlay from the Daviess County line to Route 65 in Livingston county | Pavement Improvement | 06/08/2009 | 08/06/2009 | 11/01/2009 | 1228044.9 | 12.13
6343 | Missouri | MACON |  | 09 | S116007 | This project consist of a thin lift asphalt overlay from Route 63 to Route 156 in LaPlata in Macon county | Pavement Improvement | 04/06/2009 | 04/10/2009 | 12/01/2009 | 74654.59 | 0.916
6344 | Missouri | MACON |  | 09 | S124007 | This project consist of a thin lift asphalt overlay in Macon County from Route 63 to the Knox county line | Pavement Improvement | 04/06/2009 | 04/10/2009 | 12/01/2009 | 541918.62 | 8.989
6345 | Missouri | RANDOLPH |  | 09 | S148003 | This project consist of resurfacing roadway from Business 63 to Route 63 - Randolph county | Pavement Improvement | 02/08/2010 | 05/04/2010 | 11/01/2010 | 141100 | 1.067
6346 | Missouri | RANDOLPH |  | 09 | S152001 | This project consist of resurfacing roadway from Business 63 to Route 63 - Randolph county | Pavement Improvement | 02/08/2010 | 05/04/2010 | 11/01/2010 | 129000 | 1.096
6347 | Missouri | LEWIS |  | 09 | S182010 | This project consist of a thin lift asphalt overlay from Route 67 in Ewing to Route 61 - Lewis county | Pavement Improvement | 02/08/2010 |  | 11/01/2010 | 560300 | 12.576
6348 | Missouri | SCHUYLER |  | 06 | S189007 | This project consist of a thin lift asphalt overlay from the Iowa state line to Route 63 in Schuyler county | Pavement Improvement | 04/06/2009 | 04/10/2009 | 12/01/2009 | 547629.5 | 8.502
6349 | Missouri | MARION |  | 09 | S192003 | This project consist of a thin lift asphalt overlay on Route W from Route 61 north junction to Route 61 south junction, and Route 61 outer road from Route W to 0.3 miles south of Route W in Marion cou | Pavement Improvement | 04/06/2009 | 05/12/2009 | 12/01/2009 | 179958.87 | 3.378
6350 | Missouri | RANDOLPH |  | 09 | S197005 | This project consist of resurfacing roadway from Macon county line to Route JJ - Randolph county | Pavement Improvement | 02/08/2010 | 05/04/2010 | 11/01/2010 | 885200 | 13.515
6351 | Missouri | RANDOLPH |  | 09 | S203003 | This project consist of resurfacing roadway from County Road 103 to Route 24 - Randolph county | Pavement Improvement | 02/08/2010 | 05/04/2010 | 11/01/2010 | 141559.17 | 2.225
6352 | Missouri | RANDOLPH |  | 09 | S205005 | This project consist of a thin lift asphalt overlay from Business Route 63 to Route B in Randolph county | Pavement Improvement | 06/08/2009 | 10/23/2009 | 12/01/2009 | 577200 | 9.56
6353 | Missouri | MONROE |  | 9 | S206007 | This project consist of a thin lift asphalt overlay from Route 24 to Route J in Ralls and Monroe counties | Pavement Improvement | 04/06/2009 | 05/12/2009 | 12/01/2009 | 228386.46 | 4.006
6354 | Missouri | BOONE |  | 09 | S209017 | This project consist of resurfacing roadway from Route TT to I-70 Drive SW in the City of Columbia - Boone county | Pavement Improvement | 03/08/2010 | 04/06/2010 | 12/01/2010 | 43936.59 | 1.113
6355 | Missouri | SHELBY |  | 09 | S233005 | This project consist of a thin lift asphalt overlay from Business Route 36 to Route 24 in Shelby and Monroe counties | Pavement Improvement | 06/08/2009 | 10/23/2009 | 12/01/2009 | 1112200 | 22.13
6356 | Missouri | MONROE |  | 09 | S249007 | This project consist of a thin lift asphalt overlay from Route 24 in Madison to the Audrain county line - Monroe county | Pavement Improvement | 02/08/2010 | 05/04/2010 | 11/01/2010 | 430000 | 9.725
6357 | Missouri | LINCOLN |  | 02 | S258009 | This project consist of a thin lift asphalt overlay from Route O to north junction to Route UU in Silex - Lincoln county | Pavement Improvement | 02/08/2010 | 05/24/2010 | 11/01/2010 | 478200 | 10.886
6358 | Missouri | LINCOLN |  | 02 | S264004 | This project consist of a thin lift asphalt overlay from Old Route 61 to Route W in Lincoln county | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/01/2009 | 305352.49 | 6.361
6359 | Missouri | LINCOLN |  | 02 | S270004 | This project consist of a thin lift asphalt overlay from Route Y to Route 47 in Lincoln county | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/01/2009 | 261982.39 | 5.259
6360 | Missouri | AUDRAIN |  | 09 | S273003 | This project consist of a thin lift asphalt overlay from Route V in Vandalia to Roue K east junction - Audrain county | Pavement Improvement | 02/08/2010 | 05/24/2010 | 11/01/2010 | 375800 | 10.886
6361 | Missouri | LEWIS |  | 09 | S283005 | This project consist of a thin lift asphalt overlay from Route E to Route 6 in LaBelle - Lewis county | Pavement Improvement | 02/08/2010 |  | 11/01/2010 | 377400 | 8.183
6362 | Missouri | PLATTE |  | 06 | S286005 | This project consist of pavement improvements on Route 273 from Route JJ to I-29 and Spur 92 from Route 273 to Route 92 in Platte county | Pavement Improvement | 06/08/2009 | 10/05/2009 | 12/01/2009 | 478800 | 4.907
6363 | Missouri | PLATTE |  | 06 | S290005 | This project consist of a bridge replacement over I-29 in Platte City. Project involves bridge A0200 | Bridge Replacement | 03/08/2010 | 04/01/2010 | 10/01/2010 | 1063246.12 | 0.01
6364 | Missouri | RALLS |  | 09 | S301018 | This project consist of a thin lift asphalt overlay from Route EE to Route 154 in Ralls county | Pavement Improvement | 04/06/2009 | 05/12/2009 | 12/01/2009 | 414988.04 | 7.713
6365 | Missouri | RALLS |  | 09 | S301019 | This project consist of a thin lift asphalt overlay from Route J to Route 19 in Ralls county | Pavement Improvement | 04/06/2009 | 05/12/2009 | 12/01/2009 | 248345.13 | 4.684
6366 | Missouri | CLAY |  | 06 | S304023 | A $1.2 million contract awarded to Musselman and Hall Contractors, LLC for nearly three miles of sidewalk improvements. Included are new upgrades to the existing sidewalk and adding curb ramps to acco | Transportation Enhancements | 08/10/2009 | 08/10/2009 | 02/01/2010 | 1220000 | 2.623
6367 | Missouri | STATEWIDE |  | 02 | S321005 | This project consist of a thin lift asphalt overlay from Route 47 to the Warren County line in Lincoln County, and from the Lincoln County line to I-70 north outer road in Warren county | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/01/2009 | 542103.37 | 11.537
6368 | Missouri | LINCOLN |  | 02 | S321006 | This project consist of a thin lift asphalt overlay from Route Z to Route E in Silex - Lincoln county | Pavement Improvement | 02/08/2010 | 05/24/2010 | 11/01/2010 | 198700 | 4.456
6369 | Missouri | PIKE |  | 09 | S328004 | This project consist of a thin lift asphalt overlay from Business 61 in Bowling Green to County Road 486 - Pike county | Pavement Improvement | 02/08/2010 | 05/24/2010 | 11/01/2010 | 130700 | 2.36
6370 | Missouri | BOONE |  | 09 | S340011 | This project consist of resurfacing roadway from North Fork Creek in the City of Columbia to Route J in Boone county | Pavement Improvement | 03/08/2010 | 04/06/2010 | 12/01/2010 | 474752.55 | 8.9
6371 | Missouri | BOONE |  | 09 | S342002 | This project consist of resurfacing roadway from Route K to the end of maintenance in the City of Columbia - Boone county | Pavement Improvement | 03/08/2010 | 04/06/2010 | 12/01/2010 | 92300 | 18.597
6372 | Missouri | RAY |  | 04 | S349005 | This project consist of a thin lift asphalt overlay from Route C to Route 10 in Ray county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 281304.36 | 5.763
6373 | Missouri | RAY |  | 04 | S351005 | This project consist of a thin lift asphalt overlay from Route U to Route 10 in Ray county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 182000 | 5.117
6374 | Missouri | BOONE |  | 09 | S375003 | This project consist of a thin lift asphalt overlay from Route 124 to I-70 | Pavement Improvement | 06/08/2009 | 08/10/2009 | 12/01/2009 | 856658.78 | 19.186
6375 | Missouri | CALLOWAY |  | 09 | S383010 | This project will widen Route OO in Callaway couty to three lanes to add capacity and improve safty in holts Summit. | Pavement Widening | 09/15/2009 | 09/15/2009 | 12/01/2010 | 486100 | 0.841
6376 | Missouri | LAFAYETTE |  | 04 | S388005 | This project consist of a thin lift asphalt overlay from Gillespie Drive to Route O in LaFayette county | Pavement Improvement | 04/06/2009 | 10/30/2009 | 12/01/2009 | 552746.39 | 12.287
6377 | Missouri | WARREN |  | 09 | S417004 | This project consist of improvements on intersection and outer road, which is located 0.2 miles south of I-70 in Warren county | Pavement Improvement | 02/08/2010 |  | 12/01/2010 | 514600 | 0.631
6378 | Missouri | WARREN |  | 09 | S429007 | This project consist of a thin lift asphalt overlay from Route T to Route 94 in Warren and St. Charles counties | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/01/2009 | 179695.27 | 3.5
6379 | Missouri | PETTIS |  | 04 | S434005 | This project consist of intersection improvements at Winchester Road in Sedalia in Pettis county | Pavement Improvement | 01/04/2010 | 04/01/2010 | 12/01/2010 | 354059.03 | 0.3
6380 | Missouri | PETTIS |  | 04 | S434006 | This project consist of resurfacing roadway from the railroad tracks to Route 65 in Sedalia in Pettis county | Pavement Improvement | 03/08/2010 | 04/13/2010 | 12/01/2010 | 331600 | 1.336
6381 | Missouri | PETTIS |  | 04 | S434007 | This project consist of resurfacing roadway from west of Route 65 to Quisenberry Road in the City of Sedalia - Pettis county | Pavement Improvement | 03/08/2010 | 04/14/2010 | 12/01/2010 | 86346.1 | 2
6382 | Missouri | PETTIS |  | 04 | S434008 | This project consist of resurfacing various roadways within the Missouri State fairgrounds in the City of Sedalia - Pettis county | Pavement Improvement | 03/08/2010 | 04/14/2010 | 12/01/2010 | 212019.54 | 0.003
6383 | Missouri | JOHNSON |  | 04 | S467005 | This project consist of pavement improvements from Route 50 to Route 2 in Johnson county | Pavement Improvement | 06/08/2009 | 08/18/2009 | 12/01/2009 | 1258926.82 | 16.143
6384 | Missouri | COLE |  | 04 | S490010 | This project consists of improvements at the intersection of Route 50 and Route 179 in Jefferson City. | Pavement Improvement | 03/01/2010 | 03/01/2010 | 07/01/2011 | 6806623.77 | 0.3
6385 | Missouri | MONITEAU |  | 04 | S498006 | This project consist of pavement improvements from Route AA to Route 52 in Cole, Moniteau, and Morgan counties | Pavement Improvement | 05/26/2009 | 06/10/2009 | 12/01/2009 | 2054900 | 21.1
6386 | Missouri | PETTIS |  | 04 | S539008 | This project consist of a thin lift resurfacing from the intersection of 28th street and Ingrm Avenue to Route V, south of Sedalia - Pettis county | Pavement Improvement | 03/08/2010 | 04/14/2010 | 12/01/2010 | 319800 | 8.01
6387 | Missouri | COOPER |  | 06 | S567005 | This project consist of a thin lift resurfacing from Route 135 to old Route 50 - Cooper county | Pavement Improvement | 03/08/2010 | 04/14/2010 | 12/01/2010 | 301200 | 7.838
6388 | Missouri | COOPER |  | 06 | S573009 | This project consist of pavement improvements from I-70 to Main Street (old Route B) in the City of Booneville - Cooper county | Pavement Improvement | 02/08/2010 | 03/22/2010 | 11/01/2010 | 1635914.61 | 3.406
6389 | Missouri | MONITEAU |  | 04 | S579017 | This project consist of a thin lift asphalt overlay from Route O to Route C in Moniteau county | Pavement Improvement | 06/08/2009 | 06/12/2009 | 12/01/2009 | 485200 | 10.5
6390 | Missouri | MILLER |  | 09 | S579018 | This project consist of resurfacing roadway from Salem Road to Route 54 in the City of Eldon - Miller county | Pavement Improvement | 03/08/2010 | 05/03/2010 | 12/01/2010 | 122219.51 | 2.331
6391 | Missouri | MILLER |  | 09 | S583009 | This project consist of resurfacing roadway from Salem Road to Route 52 in the City of Eldon - Miller county | Pavement Improvement | 03/03/2010 | 05/03/2010 | 12/01/2010 | 72259.2 | 1.301
6392 | Missouri | ST FRANCOIS |  | 08 | S638004 | This project consist of a thin lift asphalt overlay from the Washington County line to the City of Bonne Terre in St. Francois county | Pavement Improvement | 06/08/2009 | 09/03/2009 | 12/01/2009 | 181075 | 5.219
6393 | Missouri | ST FRANCOIS |  | 08 | S638005 | This project consist of a thin lift asphalt overlay from the City of Bonne Terre to Route 67 in St. Francois county | Pavement Improvement | 06/08/2009 | 09/03/2009 | 12/01/2009 | 104275.83 | 1.788
6394 | Missouri | IRON |  | 08 | S670010 | This project consistes of ADA sidewalk improvements on Route M from Shepherd Mountain Road to Burnett Street in Ironton, 0.275 miles. | Transportation Enhancements | 01/04/2010 | 03/29/2010 | 06/01/2010 | 122869.5 | 0.282
6395 | Missouri | VERNON |  | 04 | S706003 | This project consist of a thin lift asphalt overlay from Route 54 to 0.9 mile north of Highland in Vernon county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 111147.54 | 2.377
6396 | Missouri | VERNON |  | 04 | S708004 | This project consist of a thin lift asphalt overlay from Business 71 to County Road 507 in Vernon county | Pavement Improvement | 04/20/2009 | 04/18/2009 | 12/01/2009 | 110527.8 | 2.489
6397 | Missouri | VERNON |  | 04 | S710009 | This project consist of a thin lift asphalt overlay from Route 54 to Route F in Vernon county | Pavement Improvement | 04/18/2009 | 04/20/2009 | 12/01/2009 | 259900.93 | 5.913
6398 | Missouri | POLK |  | 4,7 | S736004 | This project consist of a thin lift asphalt overlay from Route 123 to Route 13 in Polk county | Pavement Improvement | 06/08/2009 | 07/14/2009 | 12/01/2009 | 333600 | 10.9
6399 | Missouri | WASHINGTON |  | 08 | S755002 | This project consist of resurfacing roadway from Route 8 to Route 21 in Potosi - Washington county | Pavement Improvement | 03/08/2010 | 04/26/2010 | 12/01/2010 | 89500 | 1.518
6400 | Missouri | JASPER |  | 07 | S770004 | This project consist of a thin lift asphalt overlay from Route J to Route 66 in Jasper county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 208244.24 | 4.446
6401 | Missouri | JASPER |  | 07 | S776011 | This project consist of widening Route FF to include a center two-way left turn lane form US 71 to Prigmor Avenue in Jasper/Newton counties | Pavement Improvement | 08/03/2009 | 09/30/2009 | 11/01/2010 | 1939830.56 | 1.169
6402 | Missouri | JASPER | JOPLIN | 07 | S776012 | This project consists of constructing new signalized intersection and turn lanes on route FF, one mile east of Route 71. Work includes grading, asphalt pavement and new signals. | Pavement Improvement | 05/29/2009 | 05/29/2009 | 11/01/2010 | 1376841.2 | 0.2
6403 | Missouri | STE GENEVIEVE |  | 03 | S805002 | This project consists of bridge replacement, asphalt overlay and shoulder widening on Route B in Ste Genevieve county. | Pavement Widening | 02/25/2010 | 02/25/2010 | 12/01/2010 | 2924762.15 | 13.756
6404 | Missouri | STE GENEVIEVE |  | 8,3 | S811005 | This project consist of a thin lift asphalt overlay from Route 51 to Route 61 in Ste. Genevieve and Perry counties | Pavement Improvement | 06/08/2009 | 09/03/2009 | 12/01/2009 | 329807.35 | 6.844
6405 | Missouri | JASPER |  | 07 | S853002 | This project consist of a thin lift asphalt overlay from Route Z to Route P in Jasper county | Pavement Improvement | 04/18/2009 | 04/18/2009 | 12/01/2009 | 169926.73 | 3.959
6406 | Missouri | WRIGHT |  | 08 | S926008 | This project consist of a thin lift asphalt overlay from Hartville to Route 95 - Wright county | Pavement Improvement | 02/08/2010 |  | 12/01/2010 | 568200 | 12.949
6407 | Missouri | GREENE |  | 07 | S938008 | This project consist of a thin lift asphalt overlay from Route AB to Route 160 in Greene county | Pavement Improvement | 06/08/2009 | 07/14/2009 | 12/01/2009 | 260617.29 | 5.417
6408 | Missouri | WEBSTER |  | 04 | S946008 | This project consist of a thin lift asphalt overlay from Route 60 to 1.0 mile west of Route FF in Webster county | Pavement Improvement | 06/08/2009 | 09/09/2009 | 12/01/2009 | 51870.58 | 1.78
6409 | Missouri | GREENE |  | 07 | S947011 | This project consist of a thin lift asphalt overlay from south of Route KK to north of Valley Water Mill Road in Greene county | Pavement Improvement | 06/08/2009 | 09/11/2009 | 12/01/2009 | 158145.83 | 3.857
6410 | Missouri | POLK |  | 7 | S947012 | This project consist of pavement and shoulder improvements from Route 32 to Route WW in Polk and Greene counties | Pavement Improvement | 06/08/2009 | 09/11/2009 | 12/01/2009 | 1273000 | 20.57
6411 | Missouri | GREENE |  | 07 | S953005 | This project consist of a thin lift asphalt overlay from Route 160 to Route 266 in Greene county | Pavement Improvement | 06/08/2009 | 07/14/2009 | 12/01/2009 | 297598.83 | 6.121
6412 | Missouri | WEBSTER |  | 04 | S967004 | This project consist of a thin lift asphalt overlay from Route AD to Business Route 60 in Webster county | Pavement Improvement | 06/08/2009 |  | 12/01/2009 | 163937.35 | 5.683
6413 | Montana | MCCONE, CARTER, PHILLIPS, DAWSON, PRAIRIE, WIBAUX, VALLEY |  | 00 | 0002874 | Glendive District multiple location culvert replacement, abandonment, and major maintenance project. | Bridge Improvement | 02/22/2010 | 04/09/2010 | 01/20/2011 | 2545862 | 0
6414 | Montana | FLATHEAD |  | 00 | 0015090 | Construct New Bypass segment - US 93 to Airport Road | New Construction | 12/21/2009 | 12/28/2009 | 12/20/2011 | 8148323 | 0
6415 | Montana | FLATHEAD |  | 00 | 0015091 | Construct New Bypass segment - Airport Road to Foys Lake Road | New Construction | 11/30/2009 | 02/03/2010 | 12/20/2011 | 5361624 | 0
6416 | Montana | FLATHEAD |  | 00 | 0015092 | Construct New Bypass segment - Foys Lake Road to US 2 | New Construction | 11/30/2009 | 02/03/2010 | 12/20/2011 | 7780165 | 0
6417 | Montana | GALLATIN |  | 00 | 0016073 | Wetland mitigation in the NW quadrant of the I-90 East Main Street Interchange in Bozeman. | Other | 07/06/2009 | 08/03/2009 | 12/01/2009 | 296700 | 0
6418 | Montana | LEWIS AND CLARK |  | 00 | 0025050 | Reconstruction of existing Wylie Drive in Lewis & Clark County. | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 12/20/2010 | 1186274 | 0
6419 | Montana | TETON |  | 00 | 0032033 | Replacement of the US 89 Big Muddy Creek Bridge, North of Bynum | Bridge Replacement | 07/20/2009 | 09/10/2009 | 12/20/2010 | 2728753 | 0.4
6420 | Montana | GLACIER |  | 00 | 0034013 | Overlay, Slope Flattening & Widening on US 89 within the Blackfeet Reservation | Pavement Improvement | 07/06/2009 | 07/13/2009 | 12/20/2010 | 9884850 | 8.93
6421 | Montana | PARK |  | 00 | 0034026 | Off site wetland mitigation reserve for Watershed #13 - Upper Yellowstone in Park County | Other | 07/20/2009 | 09/09/2009 | 12/01/2009 | 375399 | 0
6422 | Montana | LAKE |  | 00 | 0052152 | Construct a Bicycle/Pedestrian Overcrossing Bridge over US 93 in Pablo. | Transportation Enhancements | 04/26/2010 | 05/03/2010 | 01/01/2011 | 2725080 | 0
6423 | Montana | RAVALLI |  | 00 | 0071118 | Reconstruct and widen approximately 1.8 miles of US-93 near Stevensville | Pavement Widening | 08/12/2009 | 08/17/2009 | 12/20/2010 | 5493307 | 1.855
6424 | Montana | PARK |  | 00 | 0111051 | Seal and Cover existing roadway on Grand Avenue -between Florence and Continental in Butte | Pavement Improvement | 04/26/2010 | 04/26/2010 | 12/20/2010 | 2920736 | 4.7
6425 | Montana | MADISON |  | 00 | 0131045 | Replacement of an existing irrigation siphon with a culvert on US 287 south of Cameron | Pavement Improvement | 10/05/2009 | 10/21/2009 | 06/01/2010 | 348911 | 0
6426 | Montana | SILVER BOW |  | 00 | 0152081 | Replace I-15 Structures near Butte. | Pavement Improvement | 04/05/2010 | 04/12/2010 | 12/20/2012 | 7526406 | 1.311
6427 | Montana | LEWIS AND CLARK |  | 00 | 0154089 | I 15 Dearborn Rest Area Replacement | Safety/Traffic Management | 08/14/2009 | 01/08/2010 | 12/20/2010 | 4018300 | 0
6428 | Montana | CARTER |  | 00 | 0271009 | Bridge Replacement Project on MT 7 North of Ekalaka | Pavement Improvement | 08/03/2009 | 09/15/2009 | 12/20/2010 | 2301902 | 0
6429 | Montana | FALLON |  | 00 | 0272019 | Reconstruction of the existing roadway and structure work on MT 7 | Pavement Improvement | 09/21/2009 | 09/28/2009 | 12/20/2011 | 7255566 | 5.321
6430 | Montana | DANIELS |  | 00 | 0322016 | 14.2 mile chip seal on MT 13 in Daniels County north of Scoby | Pavement Improvement | 06/15/2009 | 06/29/2009 | 12/20/2009 | 450273.2 | 14.292
6431 | Montana | SHERIDAN |  | 00 | 0341009 | 15.3 mile overlay on MT 16 between Plentywood and the Port of Raymond in Sheridan County. | Pavement Improvement | 08/17/2009 | 06/01/2010 | 12/20/2010 | 3022926 | 15.3
6432 | Montana | LAKE, SANDERS, FLATHEAD |  | 00 | 0361011 | Reconstruct a 10 mile segment of MT-28, beginning at milepost 26.1 and ending approximately 10 miles west of Dayton. | Pavement Improvement | 03/01/2010 | 03/02/2010 | 12/20/2012 | 6465635 | 10
6433 | Montana | BIG HORN |  | 00 | 0371033 | Mill and fill 5.5 miles of US 212 in Big Horn County and within the Northern Cheyenne Reservation. | Pavement Improvement | 07/17/2009 | 07/21/2009 | 12/20/2010 | 2287646 | 5.58
6434 | Montana | ROSEBUD |  | 00 | 0391039 | 8.1 mile pavement preservation, minor widening & pavement marking/guardrail upgrade on MT 39 in Rosebud County, just north of the Northern Cheyenne Reservation. | Pavement Improvement | 06/08/2009 | 06/12/2009 | 12/20/2009 | 1360255.2 | 8.168
6435 | Montana | DAWSON |  | 00 | 0512004 | 9 mile overlay on MT 200 west of Richey, in Dawson County | Pavement Improvement | 06/22/2009 | 07/13/2009 | 12/20/2009 | 1989865.8 | 9.03
6436 | Montana | CASCADE | GREAT FALLS | 0 | 0602073 | Reconstruct 0.65 mile segment of 10th Avenue South - between 26th and 20th St in Great Falls | Pavement Widening | 03/15/2010 | 03/15/2010 | 12/20/2011 | 4194082 | 0.65
6437 | Montana | JEFFERSON |  | 00 | 0691027 | Widen and overlay the existing MT 69 roadway south of Elk Horn Road, south east of Boulder. | Pavement Improvement | 03/08/2010 | 04/05/2010 | 12/20/2011 | 6723186 | 9.5
6438 | Montana | GALLATIN |  | 00 | 0861040 | 14.6 mile chip seal on MT 86 northeast of Bozeman in Gallatin County. | Pavement Improvement | 07/06/2009 | 07/13/2009 | 12/20/2009 | 830804.85 | 14.63
6439 | Montana | GALLATIN |  | 00 | 0906087 | Reconstruction of the I-90 East Three Forks Interchange | Pavement Improvement | 10/05/2009 | 10/19/2009 | 12/20/2011 | 3676814 | 0.265
6440 | Montana | SWEET GRASS |  | 00 | 0907089 | 5 mile mill and resurface of I 90 in Sweet Grass County | Pavement Improvement | 08/17/2009 | 04/05/2010 | 12/20/2010 | 3205584 | 5.003
6441 | Montana | YELLOWSTONE | BILLINGS | 00 | 0908157 | Cold mill and overlay I -90 at the Pinehills Interchange and 3.2 miles to the west. | Pavement Improvement | 08/05/2009 | 08/08/2009 | 12/20/2009 | 1229277 | 3.285
6442 | Montana | YELLOWSTONE, BIG HORN |  | 00 | 0909098 | 13.3 mile full width overlay of I 90. Ramps will be cold milled and overlaid. The rest area parking lot will be crack sealed and s&c. | Pavement Improvement | 06/01/2009 | 08/13/2009 | 12/20/2010 | 8244422 | 13.3
6443 | Montana | YELLOWSTONE |  | 00 | 0941068 | Mill, overlay, and seal & cover a 12.1 mile segment of the I-94 roadway and bridge decks fromPompey's Pillar to Waco, east of Billings | Pavement Improvement | 07/06/2010 |  | 12/20/2011 | 4942304 | 12.122
6444 | Montana | CUSTER, ROSEBUD, DAWSON, WIBAUX |  | 00 | 0943059 | I 94 Bridge Deck Rehabilitation In Rosebud County | Bridge Improvement | 08/03/2009 | 08/10/2009 | 12/20/2010 | 5498221 | 0
6445 | Montana | WIBAUX |  | 00 | 0947028 | 6.2 mile mill and fill on I 94 east of Wibaux, in Wibaux County. | Pavement Improvement | 07/20/2009 | 07/21/2009 | 12/20/2009 | 1078036.68 | 6.298
6446 | Montana | CASCADE | GREAT FALLS | 00 | 1011004 | Reconstruction of the Smelter Ave. & 10th St. North Intersection | Pavement Improvement | 04/26/2010 | 04/26/2010 | 12/20/2010 | 2000158 | 0
6447 | Montana | YELLOWSTONE | BILLINGS | 00 | 1028004 | 1.4 mile overlay on Hardin Road in Billings | Pavement Improvement | 06/01/2009 | 06/26/2009 | 06/01/2010 | 556542 | 1.46
6448 | Montana | YELLOWSTONE | BILLINGS | 00 | 1031009 | Reconstruct an approximate 1.7 mile segment of Shilo Road from 2 lane to 4 lane - Billings | Pavement Widening | 06/01/2009 | 06/15/2009 | 12/20/2010 | 9301727 | 1.714
6449 | Montana | YELLOWSTONE | BILLINGS | 00 | 1031011 | Reconstruct the remaining 2.11 mile segment of Shiloh Road - Billings | Pavement Widening | 11/02/2009 | 11/13/2009 | 12/20/2011 | 5789636 | 2.117
6450 | Montana | SILVER BOW |  | 00 | 1806008 | 0.7 mile mill and fill on Front Street in Butte | Pavement Improvement | 06/22/2009 | 06/23/2009 | 12/20/2010 | 1380530 | 0.7
6451 | Montana | SILVER BOW |  | 00 | 1810004 | 4.7 mile mill and overlay of P-11 northeast of Livingston | Pavement Improvement | 05/17/2010 | 05/17/2010 | 12/20/2010 | 1293112 | 1.3
6452 | Montana | PHILLIPS |  | 00 | 2081006 | Reconstruction of 9.4 miles of Seconday 208 between Whitewater and US 191 | Pavement Improvement | 11/30/2009 | 03/29/2010 | 12/20/2012 | 5943362 | 9.424
6453 | Montana | GALLATIN |  | 00 | 2351011 | Reconstruct existing State Secondary 235 east of MT 85 | Pavement Improvement | 10/05/2009 | 10/29/2009 | 12/20/2010 | 4924155 | 2.55
6454 | Montana | LINCOLN |  | 00 | 2601005 | 3.5 mile chip seal on S 260 north of Libby | Pavement Improvement | 07/06/2009 | 07/07/2009 | 12/20/2009 | 167705.45 | 3.5
6455 | Montana | GRANITE |  | 00 | 2711010 | 2.3 mile chip seal on S 271 northeast of Drummond in Powell County | Pavement Improvement | 06/29/2009 | 06/29/2009 | 12/20/2009 | 98178.62 | 2.3
6456 | Montana | LEWIS AND CLARK |  | 00 | 2791013 | Installing post mounted flashers at the intersection of S-279 & S 231 north of Helena | Safety/Traffic Management | 08/03/2009 | 08/20/2009 | 11/01/2009 | 34010 | 0.8
6457 | Montana | LEWIS AND CLARK |  | 00 | 2801019 | Installing post mounted flashers on York Road northeast of Helena | Safety/Traffic Management | 08/03/2009 | 08/20/2009 | 11/01/2009 | 30098 | 0.2
6458 | Montana | MEAGHER |  | 00 | 2941008 | Reconstruction of the roadway and structure work on State Secondary 294 | Pavement Improvement | 01/04/2010 | 03/02/2010 | 12/20/2011 | 4001426 | 2.12
6459 | Montana | CARBON |  | 00 | 3081026 | 7.7 mile overlay on S-308 in Carbon County west of Belfry | Pavement Improvement | 07/06/2009 | 07/06/2009 | 12/20/2009 | 1343448 | 7.7
6460 | Montana | CARTER |  | 00 | 3231029 | Pave State Secondary 323 from RP 24.83 to 37.1 This is the section that is currently under contract with a total reconstruct to a all weather gravel surface. | Pavement Improvement | 07/06/2009 | 07/16/2009 | 12/20/2010 | 8652601 | 12.274
6461 | Montana | MISSOULA | MISSOULA | 00 | 3275813 | 2.6 mile seal and cover on a state highway west of Missoula. | Pavement Improvement | 07/06/2009 | 07/07/2009 | 12/20/2009 | 254647.34 | 2.6
6462 | Montana | STILLWATER |  | 00 | 4211004 | Reconstruction of the existing roadway and constructing bus turn arounds on State Secondary 421 7 km E. of Columbus | Pavement Improvement | 10/05/2009 | 10/23/2009 | 12/20/2010 | 3795714 | 2.732
6463 | Montana | FLATHEAD |  | 00 | 4241008 | 4.6 mile chip seal on S 424 west of Kalispell | Pavement Improvement | 06/29/2009 | 06/30/2009 | 12/20/2009 | 164937.05 | 4.61
6464 | Montana | LEWIS AND CLARK |  | 00 | 4301008 | Reconstruction of the existing roadway and structure work on Canyon Ferry Road | Pavement Improvement | 10/05/2009 | 10/09/2009 | 12/20/2011 | 7862308 | 4.2
6465 | Montana | FLATHEAD |  | 00 | 5031010 | 3.5 mile chip seal on S 503 southwest of Kalispell | Pavement Improvement | 06/29/2009 | 06/30/2009 | 12/20/2009 | 125547.93 | 3.5
6466 | Montana | MINERAL, MISSOULA |  | 00 | 5071008 | 2.4 mile mill and fill on S 507 east of Alberton, Missoula County | Pavement Improvement | 06/22/2009 | 07/22/2009 | 12/20/2009 | 418403.68 | 2.498
6467 | Montana | CASCADE | GREAT FALLS | 00 | 5205024 | 0.9 mile overlay on River Drive in Great Falls | Pavement Improvement | 07/20/2009 | 08/17/2009 | 12/20/2009 | 598282 | 0.94
6468 | Montana | CASCADE | GREAT FALLS | 00 | 5208002 | 0.7 mile overlay of Park Drive in Great Falls. | Pavement Improvement | 07/20/2009 | 08/10/2009 | 12/20/2009 | 323622.14 | 0.7
6469 | Montana | CASCADE | GREAT FALLS | 00 | 5209005 | 0.6 mile overlay of 6th Street in Great Falls. | Pavement Improvement | 07/20/2009 | 08/10/2009 | 12/20/2009 | 258322.6 | 0.61
6470 | Montana | CASCADE | GREAT FALLS | 00 | 5210018 | 0.18 mile mill and fill on 1st Avenue NW of River Drive in Great Falls | Pavement Improvement | 07/20/2009 | 08/17/2009 | 12/20/2009 | 355857 | 0.18
6471 | Montana | CASCADE | GREAT FALLS | 00 | 5299080 | Multiple Location sidewalk Improvment Project - Great Falls | Transportation Enhancements | 06/22/2009 | 07/06/2009 | 02/01/2010 | 1052700 | 0
6472 | Montana | CASCADE | GREAT FALLS | 00 | 5299081 | Phase 3 of a Multiple Location sidewalk Improvment Project - Great Falls | Transportation Enhancements | 09/14/2009 | 09/17/2009 | 07/01/2010 | 413691 | 0
6473 | Montana | CASCADE | GREAT FALLS | 00 | 5299086 | Construction of approx. 2300 ln ft of asphalt and concrete paths including fencing, drainage culverts, signing, striping and retaining wall in Great Falls. | Transportation Enhancements | 10/16/2009 | 10/16/2009 | 09/01/2010 | 355544 | 0
6474 | Montana | CASCADE | GREAT FALLS | 00 | 5299087 | Construction of approx. 1800 ln ft of asphalt bicycle/pedestrian pathway along the Missouri River in Great Falls. | Transportation Enhancements | 06/01/2010 | 06/02/2010 | 11/01/2010 | 644456 | 0
6475 | Montana | LEWIS AND CLARK |  | 00 | 5802012 | Widneing 1.09 mile segment of Custer Avenue in Helena | Pavement Improvement | 07/06/2009 | 08/03/2009 | 12/20/2009 | 675340 | 1.09
6476 | Montana | LEWIS AND CLARK |  | 00 | 5805013 | 0.3 mile mill and fill on Benton Ave in Helena | Pavement Improvement | 06/29/2009 | 06/29/2009 | 12/20/2009 | 242918 | 0.3
6477 | Montana | LEWIS AND CLARK |  | 00 | 5822002 | 0.83 mile overlay on Hauser Blvd in Helena | Pavement Improvement | 06/29/2009 | 06/29/2009 | 12/20/2009 | 403276.24 | 0.83
6478 | Montana | YELLOWSTONE |  | 00 | 6905002 | Reconstruct the existing 8th Ave Roadway in Laurel | Pavement Improvement | 11/16/2009 | 01/22/2010 | 12/20/2011 | 2798134 | 0.64
6479 | Montana | PARK |  | 00 | 7406007 | 0.7 mile mill and fill on Chinook and Gallatin Street in Livingston | Pavement Improvement | 06/15/2009 | 06/18/2009 | 12/20/2009 | 214020.37 | 0.71
6480 | Montana | MISSOULA | MISSOULA | 00 | 8105014 | 0.8 mile mill and fill on Russell Street in Missoula | Pavement Improvement | 06/01/2009 | 06/15/2009 | 12/20/2009 | 143343.5 | 0.8
6481 | Montana | MISSOULA | MISSOULA | 00 | 8107019 | 0.17 mile mill and fill on Orange Street in Missoula | Pavement Improvement | 06/01/2009 | 06/15/2009 | 12/20/2009 | 78367.49 | 0.173
6482 | Montana | MISSOULA | MISSOULA | 00 | 8109002 | On the Scott Street overpass in Missoula, Bridge deck repair and replacing the surface with a high strength epoxy concrete. | Bridge Improvement | 07/13/2009 | 07/22/2009 | 07/01/2010 | 1939051 | 0
6483 | Montana | MISSOULA | MISSOULA | 00 | 8113006 | 0.3 mile mill and fill on Higgins Street in Missoula | Pavement Improvement | 06/01/2009 | 06/15/2009 | 12/20/2009 | 115275.18 | 0.34
6484 | Montana | MISSOULA | MISSOULA | 00 | 8117006 | Higgins/Hill/Beckwith Intersection & Signal Improvement in Missoula | Pavement Improvement | 06/15/2009 | 06/17/2009 | 12/20/2009 | 693643.94 | 0
6485 | Montana | MISSOULA | MISSOULA | 00 | 8119001 | Design and construction of sidewalks, bike lanes, and period lighting. The proejct is in Missoula along both sides if Higgins Avenue between Broadway and Railroad Streets. | Transportation Enhancements | 04/26/2010 | 04/26/2010 | 12/01/2010 | 1250000 | 0
6486 | Montana | MISSOULA | MISSOULA | 00 | 8120005 | 2 mile mill and fill on South Avenue in Missoula | Pavement Improvement | 06/01/2009 | 06/15/2009 | 12/20/2009 | 624945.36 | 2
6487 | Montana | MISSOULA | MISSOULA | 00 | 8123001 | Design and construct a bicycle and pedstrian path in the Missoula Urbanized Area along the south side of Mullan Road between Flyn Lane and Cote Lane. | Transportation Enhancements | 04/12/2010 | 04/12/2010 | 10/01/2010 | 600000 | 0
6488 | Montana | MISSOULA | MISSOULA | 00 | 8199088 | Installation of accessible curb ramps on existing sidewalks at multiple locations within the City of Missoula. | Transportation Enhancements | 06/14/2010 | 06/24/2010 | 10/01/2010 | 350000 | 0
6489 | Montana | MISSOULA | MISSOULA | 00 | 8199089 | Design and construct sidewalks and bike paths in Missoula - on both sides of Greenough Drvie between Madison St and Wateworks Hill Trailhead. | Transportation Enhancements | 05/25/2010 | 06/15/2010 | 10/01/2010 | 193799.65 | 0
6490 | Montana | BLAINE |  | 00 | 9003032 | Replacement of an off system bridge & approaches in Blaine County. | Bridge Replacement | 06/22/2009 | 07/10/2009 | 12/20/2010 | 2402036 | 0
6491 | Montana | BLAINE |  | 00 | 9003039 | Bridge Replacement 7 KM west of Harlem | Bridge Replacement | 01/04/2010 | 02/04/2010 | 12/20/2011 | 2546147 | 0
6492 | Montana | DEER LODGE |  | 00 | 9012131 | Replace existing structure over the Clark Fork, 2 KM East of Warm Springs | Bridge Replacement | 11/02/2009 | 03/22/2010 | 12/20/2010 | 399726 | 0
6493 | Montana | FALLON |  | 00 | 9013015 | Off-system Bridge Replacement Project North West of Baker in Fallon County | Pavement Improvement | 08/03/2009 | 09/15/2009 | 12/20/2010 | 684245 | 0
6494 | Nebraska | BUFFALO |  | 3 | 0010060 | Restore a historic depot in the park in Pleasanton. Exterior work to include new foundation, windows, roof, gutters, and siding. Interior work to include new insulation, repair of floors, wall and tr | Transportation Enhancements | 04/22/2010 |  | 12/11/2010 | 243780 | 0
6495 | Nebraska | DAKOTA | SIOUX CITY (IA-SD) | 3 | 0022028 | This projects constructs an 8' concrete trail as a safe crossing from the Tri-State Trail under the Missouri River bridge on US-77 | Transportation Enhancements | 04/28/2010 |  | 08/07/2010 | 396223 | 0
6496 | Nebraska | DODGE |  | 1 | 0027052 | This project will replace existing street lights located on Main Street from 5th to 1st Streets with historic replica lighting in Fremont. | Transportation Enhancements | 01/15/2010 |  | 10/30/2010 | 132804 | 0
6497 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 0028091 | This project restores the brick pavement and replaces granite curbs in the historic Old Market District of downtown Omaha, bringing back the original historical flavor of this popular shopping and ent | Transportation Enhancements | 04/29/2010 |  | 11/27/2010 | 829359 | 0
6498 | Nebraska | KEARNEY |  | 3 | 0050035 | This project will construct an 8-foot-wide pedestrian and bicycle trail connecting the Axtell City Park and Axtell School at the edge of downtown, with the Natures Mosaic Recreation Area 3,000 feet no | Transportation Enhancements | 04/06/2010 |  | 10/30/2010 | 208516 | 0
6499 | Nebraska | ADAMS |  | 3 | 0064125 | 12.1 miles of asphalt resurfacing and bridge repair west of Hastings, including the spurs to Juniata and the Hastings Regional Center. | Pavement Improvement | 05/07/2009 | 05/14/2009 | 11/28/2009 | 3665228 | 9.86
6500 | Nebraska | PLATTE |  | 3 | 0071030 | This project will construct a 10-foot-wide concrete pedestrian and bicycle trail approximately one mile in length, connecting the existing Wilderness Park Trail and the Robert Bob White Trail on the o | Transportation Enhancements | 11/19/2009 |  | 06/19/2010 | 366930 | 0
6501 | Nebraska | WASHINGTON |  | 1 | 0089024 | Construct 10' wide concrete trail from the Blair Deerfield Lions Trail to the Dana College recreation fields, a distance of 0.9 mile | Transportation Enhancements | 03/04/2010 |  | 10/30/2010 | 435371 | 0
6502 | Nebraska | BUFFALO |  | 3 | 0102115 | This resurfacing project will bring this roadway to a state of good repair. It will address pavement deficiencies with an asphalt overlay. | Pavement Improvement | 09/22/2009 | 06/21/2010 | 10/30/2010 | 1321101 | 10
6503 | Nebraska | HALL |  | 3 | 0112116 | This project provides for installation of landscaping along Highway N-11 along the Loup River Scenic Byway. It includes landscape areas in the downtown corridor (2.5 blocks); and a 20-foot wide lands | Transportation Enhancements | 01/27/2010 | 04/01/2010 | 05/29/2010 | 149078 | 0
6504 | Nebraska | JEFFERSON |  | 3 | 0151113 | Replacement of 2 deficient bridges south of Fairbury on N-15. The structure at reference post 3.07 is over a stream. The second structure at R.P 4.53 is over Rose Creek. | Bridge Replacement | 05/04/2009 | 05/18/2009 | 04/30/2011 | 2966171 | 0
6505 | Nebraska | HOLT |  | 3 | 0204117 | The project consists of resurfacing the existing 24 foot roadway and 8 foot surfaced shoulders of US-20 just southeast of the city of O'Neill and continue southeast 5.14 miles. The project will mill 4 | Pavement Improvement | 11/25/2009 | 07/22/2010 | 10/30/2010 | 1459958 | 5.02
6506 | Nebraska | ANTELOPE |  | 3 | 0205111 | The project consists of resurfacing the existing 24 foot roadway and 8 foot surfaced shoulders of US-20 from Royal to Plainview and for a short length on S-2B. The project along US-20 will mill off f | Pavement Improvement | 12/11/2009 | 07/06/2010 | 10/30/2010 | 5274390 | 14.15
6507 | Nebraska | PHELPS |  | 3 | 0233105 | Asphalt resurfacing of the 6.96 miles of N-23 between Loomis and Holdrege. The existing 4' shoulders will be widened to 6' with 2' being surfaced. | Pavement Improvement | 07/17/2009 | 09/08/2009 | 08/05/2010 | 2594512 | 6.96
6508 | Nebraska | BUFFALO |  | 3 | 0304148 | This project is on US-30 from Avenue B to Avenue E and from Avenue I to Avenue L in the city of Kearney. The existing narrorw raised median will be widened to 15 feet to accommodate turn lanes. To acc | Pavement Improvement | 06/08/2009 | 07/13/2009 | 07/01/2010 | 2318659 | 0.22
6509 | Nebraska | WASHINGTON |  | 1 | 0307116 | This project consists of concrete repair and diamond grinding on US-30 from US-75 in Blair east 1.8 miles to the Missouri River Bridge | Pavement Improvement | 04/16/2010 | 07/06/2010 | 10/02/2010 | 460750 | 0
6510 | Nebraska | MADISON |  | 1 | 0325106 | "Improvements of this project east of Madison will include the vertical realignment of N-32 at the bridge over Union Creek at R.P. 36.73, which will be replaced along with raising the highway grade 9 | Bridge Replacement | 09/23/2009 | 03/01/2010 | 11/13/2010 | 3643201 | 0.74
6511 | Nebraska | HALL |  | 3 | 0344131 | "This project is located on US-34 and US-281 just south of and in the city of Grand Island. It extends from just north of the I-80 interchange to just south of Capital Avenue for a total lenth of 8.33 | Pavement Improvement | 06/03/2009 | 07/13/2009 | 07/01/2010 | 6504399 | 5.06
6512 | Nebraska | LANCASTER | LINCOLN | 1 | 0346139 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement, bridge and guardrail deficiencies with an asphalt overlay, bridge repair and new guardrail. | Pavement Improvement | 07/13/2009 | 07/27/2009 | 06/19/2010 | 2049649 | 2.49
6513 | Nebraska | LANCASTER | LINCOLN | 1 | 0346140 | Urban asphalt resurfacing on ""O"" Street from 15th St. to 25th St.; from 29th St. to 44th St. and from Wedgewood Dr. to 84th St. in Lincoln" | Pavement Improvement | 03/18/2010 | 05/03/2010 | 05/13/2011 | 1711546 | 0
6514 | Nebraska | DAKOTA |  | 1 | 0354118 | This bridge replacement project will bring this roadway to a state of good repair. It will replace two deficient bridges and rehabilitate another bridge. | Bridge Replacement | 06/03/2009 | 06/22/2009 | 10/01/2010 | 1944384 | 0
6515 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 0387106 | This project reconstructs the busy West Center Road between 156th St. and 148th St. in Omaha to a 4-lane divided roadway in Omaha, providing a safer and more efficient segment. | Pavement Widening | 04/26/2010 | 05/10/2010 | 10/31/2011 | 7470191 | 0
6516 | Nebraska | OTOE |  | 1 | 0502128 | This resurfacing and bridge project will bring this roadway to a state of good repair. It will improve safety by eliminating surface and bridge deficiencies through an asphalt overlay and bridge reha | Pavement Improvement | 03/25/2009 | 03/31/2009 | 07/31/2010 | 4907360 | 9.46
6517 | Nebraska | VALLEY |  | 3 | 0704107 | This project is located on N-70 near Arcadia. The existing 275' bridge with a 28' roadway will be widened and rehabilitated with a new south span and new superstructure. The rehabilitated bridge will | Bridge Improvement | 05/11/2009 | 05/18/2009 | 08/21/2010 | 1717017 | 0
6518 | Nebraska | KIMBALL |  | 3 | 0712109 | This resurfacing project will bring this roadway to a state of good repair by providing a new, wider driving surface. | Pavement Improvement | 06/03/2009 | 06/29/2009 | 11/21/2009 | 4633135 | 14.86
6519 | Nebraska | WASHINGTON |  | 1 | 0753115 | This urban project in Blair adds a 2' curb and gutter section with storm sewer and inlets. This will allow for the future construction of a 10' sidewalk / bike trail on the south side of US-75 from De | Pavement Improvement | 04/07/2010 | 06/28/2010 | 09/10/2010 | 458420 | 0.25
6520 | Nebraska | THURSTON |  | 1 | 0754108 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. It also includes new lighting to improve safety at the Macy | Bridge Replacement | 03/02/2010 | 03/15/2010 | 09/17/2010 | 1995848 | 0.91
6521 | Nebraska | DEUEL |  | 3 | 0802090 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies through an asphalt overlay. | Pavement Improvement | 05/04/2009 | 06/15/2009 | 07/24/2010 | 6943834 | 9.82
6522 | Nebraska | CHEYENNE |  | 3 | 0802093 | This rehabilitation and restoration project will bring this roadway to a state of good repair. It will extend the life and improve the surface condition of the existing pavement. | Pavement Improvement | 05/11/2009 | 06/15/2009 | 09/30/2009 | 1380504 | 24.85
6523 | Nebraska | DEUEL |  | 3 | 0803119 | The improvements on this project will consist of concrete pavement repairs to the existing dual 24' roadway, plus the 3' inside and 10' outside shoulders. The existing inside shoulders and roadway wil | Pavement Improvement | 12/02/2009 | 05/03/2010 | 10/30/2010 | 4074809 | 4.22
6524 | Nebraska | KEITH |  | 3 | 0803135 | This project rehabilitates Interstate 80 between the Brule and Ogallala interchanges by milling the surface and placing new asphaltic concrete. | Pavement Improvement | 12/17/2009 | 04/26/2010 | 10/09/2010 | 4149433 | 10.81
6525 | Nebraska | KEITH |  | 3 | 0803139 | This project rehabilitates Interstate 80 between the Ogallala and Roscoe interchanges by milling the surface and placing new asphaltic concrete. | Pavement Improvement | 01/20/2010 | 03/11/2010 | 08/28/2010 | 3465321 | 6.68
6526 | Nebraska | LINCOLN |  | 3 | 0804104 | This rehabilitation project will bring this roadway to a state of good repair, by preserving the structure (the interchange over I-80) and providing an improved driving surface. | Bridge Improvement | 03/23/2009 | 05/18/2009 | 09/16/2009 | 1315548 | 0
6527 | Nebraska | DAWSON |  | 3 | 0804129 | This rehabilitation project will bring this roadway to a state of good repair, by preserving the structure (the interchange over I-80) and providing an improved driving surface. | Bridge Improvement | 04/28/2009 | 06/08/2009 | 10/04/2009 | 1050940 | 0
6528 | Nebraska | LINCOLN |  | 3 | 0804133 | This restoration and rehabilitation project will bring this roadway to a state of good repair. It will extend the life and improve the surface condition of the existing pavement. | Pavement Improvement | 07/23/2009 | 09/08/2009 | 07/23/2010 | 1743733 | 5.87
6529 | Nebraska | DAWSON |  | 3 | 0805069 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 03/25/2009 | 06/15/2009 | 10/10/2009 | 6670500 | 10.49
6530 | Nebraska | HALL |  | 3 | 0806097 | This project will resurface 11.61 miles of I-80 between the Wood River and West Grand Island Interchanges. Improvements consist of joint repair, pavement repair, milling and resurfacing with asphalt a | Pavement Improvement | 06/08/2009 | 07/06/2009 | 06/26/2010 | 5255421 | 11.63
6531 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 0809889 | This reconstruction project will bring this roadway to a state of good repair and will improve the level of service (traffic flow). This expansion of I-80 on the Nebraska side is occurring in conjunct | Pavement Widening | 07/09/2009 | 08/10/2009 | 06/01/2012 | 16486652 | 2.23
6532 | Nebraska | YORK |  | 3 | 0812142 | The project begins 0.6 miles north of US-34 north of York and continues 7.2 miles north, including 0.6 miles at the S-93 junction. It consists of asphaltic concrete resurfacing of the roadway and shou | Pavement Improvement | 01/06/2010 |  | 10/30/2010 | 2712263 | 0
6533 | Nebraska | THOMAS |  | 3 | 0833106 | This bridge project will bring this roadway to a state of good repair and will improve mobility and safety, by eliminating existing at-grade rail and highway crossings (over the BNSF RR) in close prox | Bridge Replacement | 04/01/2009 | 05/04/2009 | 07/12/2010 | 6943648 | 1.66
6534 | Nebraska | CHERRY |  | 3 | 0834113 | The scope of this project consists of resurfacing US Highway 83 (US-83) for approximately 10 miles. The project will be milled and constructed using 4 inches of High RAP Base which contains a high Rec | Pavement Improvement | 11/25/2009 | 07/12/2010 | 10/02/2010 | 3442996 | 10.05
6535 | Nebraska | LOUP |  | 3 | 0913107 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 06/08/2009 | 08/24/2009 | 10/31/2009 | 2135795 | 8.47
6536 | Nebraska | PLATTE |  | 3 | 0915121 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 05/14/2009 | 06/01/2009 | 09/10/2009 | 3745305 | 11.95
6537 | Nebraska | COLFAX |  | 1 | 0916111 | This resurfacing project brought this roadway to a state of good repair. It addressed pavement deficiencies with an asphalt overlay, including milling off 2" of old asphalt surfacing and replacing wi | Pavement Improvement | 05/14/2009 | 06/22/2009 | 08/31/2009 | 2395806 | 16.71
6538 | Nebraska | BANNER |  | 3 | 1035006 | This project is on a county road 5.55 miles north and 10.5 miles west of Harrisburg, continuing north 4.0 miles to the county line. It consists of an asphalt resurfacing of the 22' roadway and rehabil | Pavement Improvement | 03/25/2010 |  | 10/16/2010 | 1098868 | 0
6539 | Nebraska | DIXON |  | 1 | 1164102 | This bridge replacement project will bring this roadway to a state of good repair. It is replacing a 52-year old structure. | Bridge Replacement | 05/04/2009 | 05/18/2009 | 10/31/2009 | 372654 | 0
6540 | Nebraska | THAYER |  | 3 | 1365111 | Milling and asphalt resurfacing of 4.2 miles of US-136 from 1.7 miles west of Gilead to the Thayer/Jefferson county line. | Pavement Improvement | 03/25/2009 | 06/03/2009 | 07/21/2009 | 1635326 | 5.02
6541 | Nebraska | GAGE |  | 1 | 1366116 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 04/29/2009 | 06/25/2009 | 10/31/2009 | 3304415 | 9.41
6542 | Nebraska | JEFFERSON |  | 3 | 1366118 | This project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 03/25/2009 | 06/19/2009 | 08/22/2009 | 2878863 | 8.1
6543 | Nebraska | NEMAHA |  | 1 | 1367122 | This bridge rehabilitation project will bring this roadway to a state of good repair. It will extend the life and improve the safety of the existing bridge by repairing and rehabilitating the structu | Bridge Improvement | 10/05/2009 | 08/31/2009 | 12/01/2011 | 3245529 | 0
6544 | Nebraska | FRONTIER |  | 3 | 1575003 | This project is on a county road 9.5 miles south and 9.0 miles east of Stockville, continuing north 3.1 miles. It consists of an asphalt resurfacing of the 22' roadway and rehabilitation of the 4' ear | Pavement Improvement | 01/25/2010 |  | 10/30/2010 | 932064 | 0
6545 | Nebraska | KEYA PAHA |  | 3 | 1710004 | This project is on a county road 4.7 miles north and 2.8 miles west of Springview, extending 3.0 miles east. It consists of an asphalt resurfacing of the 22.5' roadway and rehabilitation of the 4' ear | Pavement Improvement | 03/09/2010 |  | 10/02/2010 | 939271 | 0
6546 | Nebraska | THOMAS |  | 3 | 1755013 | This project is on a county road 3.5 miles north of Halsey, extending 4.2 miles north. It consists of an asphalt resurfacing of the 20' roadway and rehabilitation of the 4' earth shoulders. | Pavement Improvement | 05/04/2010 |  | 10/30/2010 | 1115827 | 0
6547 | Nebraska | HALL |  | 3 | 2235005 | This project consists of the paving of the northbound lanes of Locust Street from I-80 north 2.9 miles to Grand Island. | Pavement Improvement | 04/22/2010 | 05/13/2010 | 08/21/2010 | 3355633 | 0
6548 | Nebraska | HOLT |  | 3 | 2280005 | Replace a deficient bridge on a county road 14.2 miles east of O'Neill, crossing the middle branch of Verdigris Creek with a twin 9' x 8' x 88' concrete box culvert. | Pavement Improvement | 01/25/2010 | 03/29/2010 | 06/19/2010 | 252522 | 0
6549 | Nebraska | HOLT |  | 3 | 2814118 | The scope of this project consists of resurfacing the existing 24' asphalt roadway and 8' surfaced shoulders of US-281 near the city of O'Neill (approximately 7.5 miles in length). The project will m | Pavement Improvement | 11/25/2009 | 07/12/2010 | 10/09/2010 | 2276268 | 7.41
6550 | Nebraska | JEFFERSON |  | 3 | 3005008 | This project consists of a 3 inch asphaltic concrete overlay of an existing bituminous road. The project includes earth shoulder construction to match the pavement rise along both sides of the road. T | Pavement Improvement | 01/07/2010 |  | 10/30/2010 | 756007 | 0
6551 | Nebraska | GAGE |  | 1 | 3265004 | New 30' x 28' concrete slab bridge over Plum Creek 0.7 miles south of Barneston. | Bridge Replacement | 01/26/2010 | 03/22/2010 | 11/27/2010 | 837486 | 0
6552 | Nebraska | LANCASTER | LINCOLN | 1 | 3340007 | This project consists of replacing a deficient bridge box culvert. This bridge is a 4-barrel 10 foot by 26 foot concrete box culvert. It will be replaced with a 4-barrel 14 foot by 61 foot concrete | Bridge Replacement | 04/20/2010 | 06/21/2010 | 10/02/2010 | 310884 | 0
6553 | Nebraska | SAUNDERS |  | 1 | 3430006 | The project is the replacement of a deficient bridge with a triple 16' x 16' x 18' concrete box culvert. It is located on a county road (Highway Avenue) on the southern edge of Prague, crossing Cotton | Bridge Replacement | 02/03/2010 | 03/29/2010 | 11/27/2010 | 567100 | 0
6554 | Nebraska | SARPY | OMAHA (IA) | 1 | 3770003 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 03/09/2010 |  | 10/30/2010 | 560000 | 0
6555 | Nebraska | SARPY | OMAHA (IA) | 2 | 3787003 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with joint repair and an asphalt overlay. | Pavement Improvement | 03/09/2010 |  | 10/30/2010 | 610700 | 0
6556 | Nebraska | BOX BUTTE |  | 3 | 3854129 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 04/29/2009 | 08/10/2009 | 10/31/2009 | 3139546 | 7.91
6557 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 4809776 | This is a new 311' x 58' bridge on US-75 southbound over 30th St. and the exit ramps in Omaha. | Bridge Replacement | 08/19/2009 | 08/31/2009 | 06/11/2011 | 1680143 | 0
6558 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 4809777 | Rehabilitation of the I-480 183' x 72' steel girder bridge over 24th St. in Omaha | Bridge Improvement | 08/19/2009 | 08/31/2009 | 06/11/2011 | 1600854 | 0
6559 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 4809778 | This project is the reconstruction of the I-480 / US-75 southbound interchange in Omaha. Work consists of grading, mechanically stabilized earth walls, culverts, three bridge removals, guardrail, fenc | Pavement Improvement | 08/19/2009 | 08/31/2009 | 06/11/2011 | 13146340 | 0.88
6560 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 4809787 | This project is the widening and rehabilitiation of the southbound US-75 bridge over Burt St. and Cuming St. in Omaha. The new structure will be 532' long and 58' wide. | Bridge Improvement | 08/19/2009 | 08/31/2009 | 06/11/2011 | 3262610 | 0
6561 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 5003008 | This project improves safety and mobility by constructing a 4-lane divided roadway. | Pavement Widening | 03/16/2010 | 03/22/2010 | 10/08/2010 | 2592465 | 0
6562 | Nebraska | SARPY | OMAHA (IA) | 2 | 5006005 | This project is to replace the 50+ year old traffic signals, poles and mast arms at the intersection of Harvell Drive and Fort Crook Road in the City of Bellevue. The work included is to install new s | New Construction | 02/18/2010 |  | 10/30/2010 | 135800 | 0
6563 | Nebraska | SARPY | OMAHA (IA) | 2 | 5011013 | This project is to install traffic warning signals for the intersection of 108th Street and Chandler Road in La Vista. | New Construction | 03/01/2010 |  | 10/30/2010 | 30000 | 0
6564 | Nebraska | SARPY | OMAHA (IA) | 2 | 5012009 | The scope of the project consists of dowel bar retrofitting, diamond grinding, and texturing on Giles Road, beginning at 108th St and ending approximately 200 feet southeast of Southport Parkway in th | Pavement Improvement | 02/25/2010 |  | 10/30/2010 | 970700 | 0
6565 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 5052003 | This project improves safety and mobility by installing traffic signals. | Safety/Traffic Management | 03/25/2010 |  | 10/08/2010 | 252654 | 0
6566 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 5093001 | This project improves safety and mobility by installing traffic signals. | Safety/Traffic Management | 03/25/2010 |  | 11/19/2010 | 332605 | 0
6567 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 5095003 | This asphalt resurfacing project will bring urban streets at city-wide locations to a state of good repair. | Pavement Improvement | 03/01/2010 | 05/17/2010 | 10/29/2010 | 3000000 | 0
6568 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 5097002 | This project improves safety and mobility by installing traffic signals. | Safety/Traffic Management | 03/25/2010 | 06/14/2010 | 09/01/2010 | 276944 | 0
6569 | Nebraska | SARPY | OMAHA (IA) | 2 | 5106001 | This project improves safety and mobility for pedestrians by replacing sidewalks and adding ADA-approved ramps. | Pavement Improvement | 04/28/2010 | 06/01/2010 | 10/02/2010 | 837240 | 0
6570 | Nebraska | SARPY | OMAHA (IA) | 2 | 5106002 | This asphalt resurfacing project will bring this urban street to a state of good repair. | Pavement Improvement | 03/22/2010 |  | 10/30/2010 | 309154 | 0
6571 | Nebraska | SARPY | OMAHA (IA) | 2 | 5109007 | This project is to replace the 50+ year old traffic signals, poles and mast arms at the intersection of Harvell Drive and Galvin Road in the City of Bellevue. The work included is to install new signa | New Construction | 02/16/2010 |  | 10/30/2010 | 136531 | 0
6572 | Nebraska | SARPY | OMAHA (IA) | 2 | 5145001 | This asphalt resurfacing project will bring these urban roadways into a good state of repair. | Pavement Improvement | 03/24/2010 | 08/02/2010 | 09/18/2010 | 1190700 | 0
6573 | Nebraska | LANCASTER | LINCOLN | 1 | 5220003 | Asphalt resurfacing on A Street between 63rd St. and Imperial Drive and on Van Dorn St. from Normal Blvd. to 70th St. in Lincoln. | Pavement Improvement | 01/26/2010 | 04/12/2010 | 09/30/2010 | 662985 | 0
6574 | Nebraska | LANCASTER | LINCOLN | 1 | 5236002 | Asphalt resurfacing on P St. between 18th St. and 27th St., P St. between 17th St. and 27th St. and on Northwest 1st St. between Highland Blvd. and West Fletcher Ave. in Lincoln." | Pavement Improvement | 02/28/2010 | 04/27/2010 | 09/30/2011 | 926670 | 0
6575 | Nebraska | LANCASTER | LINCOLN | 1 | 5244007 | Asphalt resurfacing and ADA approved curb ramps on Holdrege Street from 33rd St. to 47th St. in Lincoln | Pavement Improvement | 02/28/2010 |  | 08/12/2011 | 916546 | 0
6576 | Nebraska | LANCASTER | LINCOLN | 1 | 5244008 | Asphalt resurfacing and ADA approved curb ramps on Holdrege Street from 70th St. to 79th St. in Lincoln | Pavement Improvement | 02/28/2010 |  | 08/12/2011 | 809396 | 0
6577 | Nebraska | LANCASTER | LINCOLN | 1 | 5247011 | Asphalt resurfacing on Holdrege St. from 19th St to 25th St; on Cornhusker Hwy from Russell Dr. to 70th St.; on 70th St. from Adams St. to Aylesworth St.; on Vine St. from 70th St. to Sierra Dr. and o | Pavement Improvement | 02/28/2010 | 05/17/2010 | 09/30/2011 | 1129378 | 0
6578 | Nebraska | LANCASTER | LINCOLN | 1 | 5247012 | 0.64 mile of asphalt resurfacing and curb ramp replacement on 70th St. from Aylesworth St. south to Vine St. in Lincoln | Pavement Improvement | 02/28/2010 |  | 08/12/2011 | 740069 | 0
6579 | Nebraska | LANCASTER | LINCOLN | 1 | 5250003 | Asphalt resurfacing on Adams St. from 57th St. to 62nd St. in Lincoln | Pavement Improvement | 02/02/2010 | 06/07/2010 | 07/23/2010 | 463377 | 0
6580 | Nebraska | LANCASTER | LINCOLN | 1 | 5254009 | This project consists of bridge rehabilitation for the Superior Street Bridge over Salt Creek just west of 40th Street in Lincoln. The existing steel girder structure is 293 feet long and 50 feet wid | Bridge Improvement | 01/27/2010 | 03/22/2010 | 08/15/2010 | 271922 | 0
6581 | Nebraska | LANCASTER | LINCOLN | 1 | 5280001 | This asphalt resurfacing project will bring the roadway into a good state of repair. It is located on Saltillo Rd., from Highway US-77 to South 70th St. in Lincoln, Nebraska. | Pavement Improvement | 06/15/2010 | 08/02/2010 | 10/30/2010 | 884155 | 0
6582 | Nebraska | DAKOTA | SIOUX CITY (IA-SD) | 1 | 5305008 | This project improves safety by providing new intersection lighting. | New Construction | 04/06/2010 |  | 11/27/2010 | 1012259 | 0
6583 | Nebraska | DAKOTA | SIOUX CITY (IA-SD) | 1 | 5305009 | This project improves safety and mobility by installing traffic signals at urban intersections. | Safety/Traffic Management | 03/04/2010 |  | 11/27/2010 | 177781 | 0
6584 | Nebraska | ADAMS |  | 3 | 5505003 | 0.81 mile of asphalt resurfacing, four intersections and curb ramps on Baltimore Avenue from 2nd St. to 12th st. in Hastings | Pavement Improvement | 02/28/2010 | 06/07/2010 | 08/28/2010 | 651357 | 0
6585 | Nebraska | ADAMS |  | 3 | 5512008 | 0.24 mile of asphalt resurfacing and curb ramp replacements on 7th Street, from Baltimore Ave. to Oswego Ave. in Hastings | Pavement Improvement | 02/18/2010 | 05/17/2010 | 10/30/2010 | 174333 | 0
6586 | Nebraska | ADAMS |  | 3 | 5514003 | 0.49 mile of asphalt resurfacing, three intersections and curb ramps on 9th Street from Burlington Ave. to Baltimore Ave. in Hastings. | Pavement Improvement | 02/18/2010 | 05/20/2010 | 10/30/2010 | 357453 | 0
6587 | Nebraska | ADAMS |  | 3 | 5527001 | 0.56 mile of asphalt resurfacing on Showboat Blvd. between 7th and 12th Streets in Hastings. | Pavement Improvement | 01/29/2010 | 04/12/2010 | 10/30/2010 | 265260 | 0
6588 | Nebraska | SCOTTS BLUFF |  | 3 | 5709003 | Urban reconstruction of 0.43 mile of Avenue B from South Beltline Highway to Overland Drive in Scottsbluff | Pavement Improvement | 04/27/2010 | 07/26/2010 | 11/27/2010 | 950808 | 0
6589 | Nebraska | SCOTTS BLUFF |  | 3 | 5724002 | Concrete reconstruction of 0.34 mile of D Street between Rundell Rd. and Lockwood Rd. in Gering | Pavement Improvement | 04/19/2010 |  | 10/30/2010 | 408564 | 0
6590 | Nebraska | BUFFALO |  | 3 | 5922003 | Urban reconstruction of 39th St. between Pony Express and Avenue M in Kearney | Pavement Improvement | 04/15/2010 | 06/01/2010 | 11/27/2010 | 2418216 | 0
6591 | Nebraska | PLATTE |  | 3 | 6074005 | Construct 2 lanes of concrete pavement for 1.6 miles on Lost Creek Parkway between US-81 and 48th Ave. in Columbus | New Construction | 04/26/2010 |  | 07/01/2010 | 2398778 | 0
6592 | Nebraska | REDWILLOW |  | 3 | 6156002 | Reconstruction of 0.72 mile of West J Street from West 10th St. to Norris Ave. in McCook. Project inlcudes storm sewers, sidewalks, ADA ramps and traffic signals. | Pavement Improvement | 07/22/2009 | 07/27/2009 | 04/16/2010 | 1071992 | 0
6593 | Nebraska | OTOE |  | 1 | 6204004 | Reconstruction of 0.24 mile of 11th Corso between 10th and 11th Streets in Nebraska City. | Pavement Improvement | 04/19/2010 | 05/03/2010 | 07/17/2010 | 575330 | 0
6594 | Nebraska | OTOE |  | 1 | 6210003 | Asphalt resurfacing and installation of decorative crosswalks for 0.49 mile of Central Ave. between 11th and 6th Streets in Nebraska City. | Pavement Improvement | 02/16/2010 | 07/14/2010 | 10/30/2010 | 603601 | 0
6595 | Nebraska | OTOE |  | 1 | 6218001 | Urban widening and reconstruction of 11th Street between 10th and 14th Corsos in Nebraska City | Pavement Improvement | 04/19/2010 | 05/03/2010 | 09/11/2010 | 1249502 | 0
6596 | Nebraska | YORK |  | 3 | 6305001 | 0.5 mile of urban reconstruction on Nebraska Ave. between 4th and 14th Streets in York. | Pavement Improvement | 04/22/2010 | 04/28/2010 | 12/03/2010 | 2198101 | 0
6597 | Nebraska | CASS |  | 1 | 6403002 | 0.16 mile of asphalt resurfacing on 15th St. between Ave. A and Ave. C in Plattsmouth. | Pavement Improvement | 03/18/2010 |  | 10/30/2010 | 131467 | 0
6598 | Nebraska | CASS |  | 1 | 6403003 | Urban reconstruction on 15th St. between 1st Ave. and Main St. in Plattsmouth | Pavement Improvement | 03/18/2010 |  | 11/20/2010 | 76963 | 0
6599 | Nebraska | PHELPS |  | 3 | 6602001 | Urban reconstruciton of 0.52 mile of 11th ave. between Sherman St. and Lincoln St. in Holdrege. | Pavement Improvement | 04/19/2010 | 07/12/2010 | 11/27/2010 | 1623819 | 0
6600 | Nebraska | SALINE |  | 3 | 6904001 | Urban reconstruction of 0.95 mile of East 13th St. between Hawthorn St. and the east city limits of Crete. | Pavement Improvement | 04/19/2010 |  | 11/27/2010 | 2213114 | 0
6601 | Nebraska | COLFAX |  | 1 | 6954001 | Asphalt resurfacing of 0.44 mile of 9th St. between B St. and G St. in Schuyler | Pavement Improvement | 02/25/2010 |  | 11/27/2010 | 432349 | 0
6602 | Nebraska | ADAMS |  | 3 | 7001014 | Replacement of a deficient bridge with a new 83' x 28' steel girder structure. The project is located 4 miles south and 0.8 mile west of Juniata, crossing the west branch of 32 mile Creek | Bridge Replacement | 01/27/2010 |  | 11/27/2010 | 481073 | 0
6603 | Nebraska | DODGE |  | 1 | 7027008 | The project entails a new 140' x 28' concrete slab bridge over Cuming Creek, 2.5 miles north and 0.8 mile east of Scribner. | Bridge Replacement | 02/17/2010 |  | 11/27/2010 | 673908 | 0
6604 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 7028044 | New bridge over Thomas Creek on a county road 2.1 miles east and 0.5 mile north of Bennington. | Bridge Replacement | 03/18/2010 |  | 11/27/2010 | 483142 | 0
6605 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 7028045 | New bridge over a stream on a county road 2.0 miles north and 0.1 mile east of Valley. | Bridge Replacement | 03/18/2010 |  | 11/27/2010 | 469421 | 0
6606 | Nebraska | FILLMORE |  | 3 | 7030033 | New bridge over a tributary of Turkey Creek on a county road 2.6 miles east of Geneva. | Bridge Replacement | 04/13/2010 | 05/17/2010 | 11/27/2010 | 396297 | 0
6607 | Nebraska | FRANKLIN |  | 3 | 7031012 | New twin 9' x 9' x 52' concrete box culvert on the Bostwick irrigation canal 1.5 miles east of Naponee | Bridge Replacement | 01/26/2010 |  | 11/20/2010 | 76982 | 0
6608 | Nebraska | JOHNSON |  | 1 | 7049021 | New 232' x 28' pre-stressed concrete girder bridge over the middle branch of the Big Nemaha River on a county road 2.0 miles west of Sterling. | Bridge Replacement | 01/21/2010 | 03/22/2010 | 11/27/2010 | 901857 | 0
6609 | Nebraska | NUCKOLLS |  | 3 | 7065021 | Triple 3.66m x 18.5m concrete box culvert on Oak Creek 1.0 mile south of Oak on a county road. | Bridge Replacement | 02/02/2010 |  | 11/27/2010 | 302190 | 0
6610 | Nebraska | PHELPS |  | 3 | 7069015 | Triple 10' x 8' concrete box culvert on the Central Nebraska Public Power Irrigation District canal on a county road 1 miles west of Funk | Bridge Replacement | 01/25/2010 |  | 11/27/2010 | 124014 | 0
6611 | Nebraska | DOUGLAS | OMAHA (IA) | 2 | 7941001 | The project consists of the removal of the upper 2 inches of the existing asphaltic concrete (asphalt) pavement to remove rutting on seven segments of 2 and 3-lane rural roadways, including turn lanes | Pavement Improvement | 02/12/2010 |  | 10/30/2010 | 1860020 | 0
6612 | Nebraska | CLAY |  | 3 | S18B104 | This project is on the Edgar Spur from N-14 to the city of Edgar, a length of 4.0 miles. The scope consists of resurfacing and widening the existing roadway to provide a 24' roadway with 1' surfaced s | Pavement Improvement | 04/07/2009 | 05/11/2009 | 09/05/2009 | 1947585 | 3.99
6613 | Nebraska | DOUGLAS, LANCASTER, STATEWIDE | STATEWIDE | 1,2,3 | STWD093 | This project assists counties, municipalilties and metropolitan planning organizations in completing requirements for environmental documentation on ARRA projects. Six consulting engineering firms ar | Other | 07/09/2009 | 07/09/2009 | 07/30/2013 | 997500 | 0
6614 | Nevada | CLARK | LAS VEGAS | 3 | 0003115 | The City of Boulder City will resurface approximately 1.3 miles of the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 03/01/2010 | 03/01/2010 | 06/20/2010 | 1000000 | 0
6615 | Nevada | CLARK | LAS VEGAS | 1 | 0003117 | The City of North Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 03/01/2010 | 03/01/2010 | 06/29/2010 | 2752865 | 0
6616 | Nevada | CLARK | LAS VEGAS | 3 | 0003118 | The City of Henderson will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 03/29/2010 | 03/30/2010 | 08/01/2010 | 840814 | 0
6617 | Nevada | CLARK | LAS VEGAS | 1,3 | 0003119 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 01/19/2010 | 01/25/2010 | 09/17/2010 | 1209550 | 0
6618 | Nevada | CLARK | LAS VEGAS | 1,3 | 0003120 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 01/19/2010 | 01/25/2010 | 09/17/2010 | 942171 | 0
6619 | Nevada | CLARK | LAS VEGAS | 3 | 0003121 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 01/19/2010 | 01/25/2010 | 09/17/2010 | 647543 | 0
6620 | Nevada | CLARK | LAS VEGAS | 1 | 0003122 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 01/19/2010 | 01/25/2010 | 09/17/2010 | 1150411 | 0
6621 | Nevada | CLARK | LAS VEGAS | 3 | 0003123 | The City of Henderson will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 04/19/2010 | 04/19/2010 | 12/13/2010 | 2582000 | 0
6622 | Nevada | CLARK | LAS VEGAS | 3 | 0003124 | The City of Henderson will reconstruct approximately 1.7 miles of the existing roadway. This will improve driving quality by widening the road, which will make the road safer and extend Volunteer Blvd | Pavement Improvement | 04/14/2010 | 05/03/2010 | 10/14/2010 | 1084976 | 0
6623 | Nevada | CLARK | LAS VEGAS | 2 | 0003126 | The City of Mesquite will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 11/30/2009 | 11/30/2009 | 01/28/2010 | 755622 | 0
6624 | Nevada | CLARK | LAS VEGAS | 1 | 0003127 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 03/15/2010 | 03/15/2010 | 01/24/2011 | 1390263 | 0
6625 | Nevada | CLARK | LAS VEGAS | 3 | 0003129 | Clark County will resurface the top four inches of approximately 1.8 miles of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smo | Pavement Improvement | 07/12/2010 |  | 09/12/2010 | 1903000 | 0
6626 | Nevada | CLARK | LAS VEGAS | 1,3 | 0003131 | Clark County will reconstruct 15 existing bus stops along Maryland Parkway between east Reno and Sahara. | Transportation Enhancements | 01/24/2010 | 01/24/2010 | 02/25/2010 | 329814 | 0
6627 | Nevada | CLARK | LAS VEGAS | 1 | 0003133 | Clark County will resurface the top four inches of approximately 3.2 miles of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smo | Pavement Improvement | 07/06/2010 |  | 10/06/2010 | 3574342 | 0
6628 | Nevada | CLARK | LAS VEGAS | 2 | 0003140 | The City of Mesquite will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 04/26/2010 | 05/18/2010 | 06/25/2010 | 244378 | 0
6629 | Nevada | CLARK | LAS VEGAS | 1 | 0003142 | The City of Las Vegas will resurface the three inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 05/17/2010 | 05/28/2010 | 09/20/2010 | 1609058 | 0
6630 | Nevada | CLARK | LAS VEGAS | 3 | 0003143 | The City of Henderson will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 05/17/2010 | 05/17/2010 | 07/21/2010 | 337230 | 0
6631 | Nevada | DOUGLAS |  | 2 | 0005018 | The Nevada Department of Transportation in coordination with Douglas County will resurface the existing asphalt with a two inches of new asphalt. This will improve driving quality by resurfacing the r | Pavement Improvement | 07/06/2010 |  | 08/30/2010 | 511571 | 0
6632 | Nevada | ELKO |  | 2 | 0007033 | The City of Elko will resurface the top inche of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of | Pavement Improvement | 05/05/2010 | 05/05/2010 | 08/30/2010 | 868135 | 0
6633 | Nevada | ESMERALDA |  | 2 | 0009005 | The Nevada Department of Transportation will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 06/29/2010 |  | 08/30/2010 | 582401 | 0
6634 | Nevada | EUREKA |  | 2 | 0011036 | Eureka County will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of 11th Street from | Pavement Improvement | 05/19/2010 |  | 08/30/2010 | 384358 | 0
6635 | Nevada | HUMBOLDT |  | 2 | 0013019 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade sur | Pavement Improvement | 06/29/2009 | 07/07/2009 | 01/04/2010 | 1588585 | 0
6636 | Nevada | LANDER |  | 2 | 0015015 | The Nevada Department of Transportation will resurface the existing asphalt with new asphalt, replace substandard street lights and repair damaged curb. This will improve driving quality by updating t | Pavement Improvement | 07/01/2010 |  | 08/30/2010 | 421666 | 0
6637 | Nevada | LINCOLN |  | 2 | 0017019 | The Nevada Department of Transportation will Place a chip seal on 6.2 miles of Rose Valley Rd,West of Ursine in Lincoln County, Nevada. to extend its service life. | Pavement Improvement | 06/29/2010 |  | 08/30/2010 | 426960 | 0
6638 | Nevada | LYON |  | 2 | 0019019 | The Nevada Department of Transportation will place Geotextile Fabric and a 2.5 inch overlay with fog seal on 1.9 miles of Six Mile Canyon Rd. to restore the pavement structure and extend its service l | Pavement Improvement | 07/06/2010 |  | 08/30/2010 | 641720 | 0
6639 | Nevada | LYON |  | 2 | 0019020 | The Nevada Department of Transportation in coordination with the City of Fernley will preserve and extend the pavement life of various city streets by placing a slurry seal over the existing roadway. | Pavement Improvement | 06/24/2010 |  | 08/30/2010 | 158085 | 0
6640 | Nevada | MINERAL |  | 2 | 0021045 | Nye County will preserve and extend the pavement life of a section of Gamebird Rd. by placing a 3.5 inch asphalt overlay on the existing roadway. | Safety/Traffic Management | 06/22/2010 |  | 08/30/2010 | 181233 | 0
6641 | Nevada | NYE |  | 2 | 0023011 | Nye County will preserve and extend the pavement life of a section of Gamebird Rd. by placing a 3.5 inch asphalt overlay on the existing roadway. | Pavement Improvement | 06/30/2010 |  | 08/30/2010 | 533738 | 0
6642 | Nevada | CARSON CITY | CARSON CITY | 2 | 0025016 | Carson City will preserve and extend the pavement life of several city streets by placing a thin asphalt/slurry overlay on the existing roadways | Pavement Improvement | 05/03/2010 | 05/12/2010 | 09/30/2010 | 798215 | 0
6643 | Nevada | PERSHING |  | 2 | 0027016 | The Nevada Department of Transportation will add sidewalks to increase the safety of pedestrians and make routes ADA compliant on 0.71 miles of roads in Lovelock, Nevada. | Transportation Enhancements | 06/29/2010 |  | 08/30/2010 | 122180 | 0
6644 | Nevada | STOREY |  | 2 | 0029013 | The Nevada Department of Transportation in coordination with Storey County will preserve and extend the pavement life of about 2.7 miles of Six Mile Canyon Rd. in various locations by placing a 2.5 in | Pavement Improvement | 07/06/2010 |  | 08/30/2010 | 538439 | 0
6645 | Nevada | CARSON CITY, LYON |  | 2 | 0032071 | The Nevada Commission for the Reconstruction of the V&T Railway will construct just over one mile of railroad track along of the historic Virginia and Truckee Railway roadbed on existing railroad grad | Transportation Enhancements | 07/16/2009 | 07/21/2009 | 11/04/2009 | 2033899 | 0
6646 | Nevada | WHITE PINE |  | 2 | 0033014 | The Nevada Department of Transportation will place a slurry seal on 3 miles of streets in Ely, Nevada to extend their service life. | Pavement Improvement | 05/24/2010 |  | 10/11/2010 | 191503 | 0
6647 | Nevada | WHITE PINE |  | 2 | 0033015 | The Nevada Department of Transportation will construct curb, gutter, sidewalk on the south side of the street on SR 221 Chestnut St. from 6th St. to 10th St to provide pedestrian enhancements in Carli | Pavement Improvement | 05/24/2010 |  | 10/11/2010 | 593083 | 0
6648 | Nevada | CLARK |  | 2 | 0151140 | NDOT will use asphalt overlay on I-15 From CA/NV Stateline to Milepost 17.00 (CL0.00 to CL17.00) as part of the pavement preservation program. | Pavement Improvement | 11/23/2009 |  | 09/06/2010 | 8379233 | 16
6649 | Nevada | CLARK | LAS VEGAS | 2 | 0152039 | NDOT will use asphalt overlay on I-15 from .369 MN of East Mesa Intg. To 1.033 MW of the Bunkerville Intg. from 1.033 MW of Bunkerville Intg. To 1.889 MS of West Mesquite Intg. as part of the pavemen | Pavement Improvement | 05/10/2010 |  | 09/10/2010 | 1525026 | 0
6650 | Nevada | ELKO |  | 2 | 0221004 | The Nevada Department of Transportation in coordination with the City of Carlin will construct curb, gutter, sidewalk on the south side of the street on SR 221 Chestnut St. from 6th St. to 10th St. | Transportation Enhancements | 06/30/2010 |  | 08/30/2010 | 248201 | 0
6651 | Nevada | ELKO |  | 2 | 0223002 | The Nevada Department of Transportation in coordination with the City of Wells will construct pedestrian improvements including curb, gutter, sidewalk on the east side of the street on SR 223 Humboldt | Transportation Enhancements | 07/01/2010 |  | 08/30/2010 | 175500 | 0
6652 | Nevada | HUMBOLDT |  | 2 | 0289001 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 06/29/2009 | 07/07/2009 | 01/04/2010 | 1011170 | 0
6653 | Nevada | STATEWIDE |  | 2 | 0318013 | The Nevada Department of Transportation will generally cold in place recycle 3 inches depth of existing asphalt pavement, a 3 inch plantmix asphalt overlay with open grade surface course, or 8 inch ro | Pavement Improvement | 07/13/2009 | 07/27/2009 | 02/22/2010 | 14016262 | 0
6654 | Nevada | CHURCHILL |  | 2 | 0801165 | The Nevada Department of Transportation will cold mill 1.5 inches depth of existing asphalt pavement and place a plantmix asphalt overlay with open grade surface course. This will improve driving qual | Pavement Improvement | 12/21/2009 | 01/31/2010 | 06/21/2010 | 10820369 | 0
6655 | Nevada | PERSHING |  | 2 | 0802052 | NDOT will preserve and extend the pavement life of about 14 miles of I-80 by milling 1 inch of existing pavement and replacing it with 3 inches of new asphalt and an open-graded wearing course. | Pavement Improvement | 06/08/2009 | 06/08/2009 | 12/07/2009 | 12349915 | 0
6656 | Nevada | LANDER |  | 2 | 0803059 | The Nevada Department of Transportation will construct 8 inch roadbed modification with 5.5 inches of plantmix asphalt with open grade surface course. This will improve driving quality by resurfacing | Pavement Improvement | 07/20/2009 | 08/17/2009 | 10/26/2009 | 2422580 | 0
6657 | Nevada | CLARK |  | 2 | 0932002 | NDOT will use asphalt overlay on US93 from 15.82 miles N of I15 at Garnet Interchange to the CL/LN County Line (CL67.83 to CL86.59) as part of the pavement preservation program. | Pavement Improvement | 09/14/2009 |  | 09/13/2010 | 6609682 | 19
6658 | Nevada | LINCOLN |  | 2 | 0932004 | The Nevada Department of Transportation will construct will pedestrian improvements including curb, gutter and sidewalk on US 93 from .50 MW of SR 317 to .05 MW of SR 317. | Transportation Enhancements | 11/20/2009 | 11/20/2009 | 08/30/2010 | 136017 | 0
6659 | Nevada | WHITE PINE |  | 2 | 0934016 | The Nevada Department of Transportation will resurface the top three inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road sm | Pavement Improvement | 05/24/2010 |  | 10/11/2010 | 9921759 | 0
6660 | Nevada | ELKO |  | 2 | 0935006 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 3 inch plantmix asphalt overlay with open grade surface course. This will imp | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/07/2009 | 10645650 | 0
6661 | Nevada | ELKO |  | 2 | 0935007 | The Nevada Department of Transportation will construct a approximately 66 feet wide by 162 feet long precast concrete arch overpass in a location with a history of many animal/vehicle collisions and a | New Bridge Construction | 08/10/2009 | 09/09/2009 | 11/28/2009 | 1075515 | 0
6662 | Nevada | ELKO |  | 2 | 093A004 | The Nevada Department of Transportation in coordination with the City of West Wendover will construct curb, gutter, sidewalk on the east side of the street on US 93A from W. Wendover Blvd to I 80 WB O | Transportation Enhancements | 06/30/2010 |  | 08/30/2010 | 183090 | 0
6663 | Nevada | CLARK |  | 3 | 0951041 | NDOT will build a Visitor's Center on US 95 to enhance the experience of the travelling public. | Transportation Enhancements | 07/15/2009 | 07/15/2009 | 01/18/2010 | 3389007 | 0
6664 | Nevada | CLARK | LAS VEGAS | 3 | 0952054 | NDOT will use asphalt overlay on US 95 from 0.737 MN of SR157, Charleston Park Road, to 7.716 MN of SR156, Lee Canyon Road, as part of the pavement preservation program. | Pavement Improvement | 05/10/2010 |  | 03/17/2011 | 29772969 | 0
6665 | Nevada | CLARK | LAS VEGAS | 1 | 0952055 | NDOT will perform landscaping on US95 from Martin Luther King Blvd. to Rainbow Blvd. | Transportation Enhancements | 09/21/2009 | 09/29/2009 | 07/05/2010 | 3477042 | 0
6666 | Nevada | NYE |  | 2 | 0952056 | NDOT will use asphalt overlay on US 95 from 1.63 mi S of Jackass Flat to 0.62 mi N of SR 160. MP NY6.98 - NY14.38 as part of the pavement preservation program. | Pavement Improvement | 09/14/2009 | 09/14/2009 | 11/23/2009 | 2441345 | 7
6667 | Nevada | MINERAL |  | 2 | 0954015 | The Nevada Department of Transportation in coordination with Mineral County expects to improve traffic management and pedestrian safety at the intersection of US 95 and SR 359 in Hawthorne by upgradin | Safety/Traffic Management | 06/22/2010 |  | 08/30/2010 | 46561 | 0
6668 | Nevada | HUMBOLDT |  | 2 | 0956007 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 06/29/2009 | 07/07/2009 | 01/04/2010 | 1191458 | 0
6669 | Nevada | HUMBOLDT |  | 2 | 0956008 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 06/29/2009 | 07/07/2009 | 01/04/2010 | 3256353 | 0
6670 | Nevada | DOUGLAS, CARSON CITY | CARSON CITY | 2 | 3951021 | The Nevada Department of Transportation in coordination with Douglas County will widen US 395 in the northbound direction for approximately 6000 feet from Sunridge Dr. east to Lupin Dr. This will all | Pavement Widening | 04/26/2010 | 04/26/2010 | 10/08/2010 | 3018798 | 0
6671 | Nevada | CARSON CITY | CARSON CITY | 2 | 3951022 | NEVADA DEPARTMENT OF TRANSPORTATION WILL PERFORM LANDSCAPING ON US395, CARSON CITY BYPASS, AT 5TH STREET GRADE SEPARATION AND FAIRVIEW INTERCHANGE. | Transportation Enhancements | 07/12/2010 |  | 09/10/2010 | 1314644 | 0
6672 | Nevada | WASHOE | RENO | 2 | 5801029 | The NDOT and the Regional Transportation Commission (RTC) of Washoe County will reconfigure the existing Neil Rd. Interchange to a split diamond configuration with Meadowood Mall Way and extend Meadow | New Construction | 05/17/2010 |  | 02/21/2012 | 18473423 | 0
6673 | New Hampshire | MERRIMACK |  | 02 | A000091 | The Winnipesaukee River Trail Phase 2B project extends an existing 3 mile bicycle and pedestrian trail facility by providing signs for a temporary connection from Park Street in Northfield to Morrison | Transportation Enhancements | 02/09/2010 | 05/17/2010 | 08/30/2010 | 429646.25 | 1
6674 | New Hampshire | HILLSBOROUGH |  | 02 | A000094 | In Hillsborough, on route US 202/NH 9, a historic stone arch bridge will be preserved and resurfaced to better accommodate pedestrians and bicycles | Transportation Enhancements | 10/20/2009 | 05/10/2010 | 06/14/2010 | 150045 | 0
6675 | New Hampshire | HILLSBOROUGH | NASHUA | 02 | A000095 | In Hudson, the town will be building almost a mile of new sidewalk and a nearly mile long bicycle lane on Route 102 between Evergreen Drive and Megan. | Transportation Enhancements | 07/17/2009 |  | 07/01/2010 | 357000 | 0
6676 | New Hampshire | ROCKINGHAM | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 02 | A000127 | On I-93 near Exit 3 in the Salem and Windham area, new northbound and southbound travel lanes will be constructed to improve safety and relieve congestion. | New Construction | 05/07/2009 | 06/17/2009 | 11/01/2011 | 27135145.95 | 2.2
6677 | New Hampshire | HILLSBOROUGH |  | 01 | A000258 | This project will widen the FE Everett Turnpike to provide improved access to and from the Manchester-Boston Regional Airport. | Pavement Widening | 04/16/2009 | 05/11/2009 | 06/01/2011 | 10365508.68 | 2.9
6678 | New Hampshire | HILLSBOROUGH |  | 02 | A000341 | In Bennington, this project will provide over a half-mile of sidewalk with crosswalks, and will clearly separate these facilities from vehicular traffic and parking to improve pedestrian access and sa | Transportation Enhancements | 07/22/2009 | 08/10/2009 | 05/01/2010 | 617600.1 | 0
6679 | New Hampshire | MERRIMACK |  | 02 | A000342 | This project in Boscawen will provide new sidewalks on Main Street through the route US3/4 intersection and along King Street. New crosswalks and pedestrian signals will enhance pedestrian safety at t | Transportation Enhancements | 08/21/2009 | 09/24/2009 | 05/01/2010 | 440231.5 | 0
6680 | New Hampshire | STRAFFORD |  | 01 | A000345 | On Durham's Main Street near the downtown area and the University of New Hampshire, this project will improve bicycle and pedestrian access and mobility by providing over a mile of new sidewalks, sepa | Transportation Enhancements | 11/13/2009 | 12/08/2009 | 09/30/2010 | 758258.55 | 0
6681 | New Hampshire | BELKNAP |  | 01 | A000349 | This project will provide around 1.5 miles of trail within an active rail corridor for bicyclists and pedestrians that will run from Main Street in Laconia to Elm Street in Lakeport. Improvements will | Transportation Enhancements | 08/31/2009 | 09/03/2009 | 12/01/2009 | 575980.5 | 0
6682 | New Hampshire | HILLSBOROUGH | MANCHESTER | 01 | A000390 | This project consists of earthwork west of the Merrimack River for Manchester Airport Access Road. | New Construction | 07/17/2009 | 08/05/2009 | 06/01/2011 | 5110519.37 | 0.62
6683 | New Hampshire | ROCKINGHAM |  | 02 | A000558 | The Windham Depot project will provide a restored historic train depot that will function as a combined visitor center, museum and way station at the head of a 4 mile bicycle and pedestrian trail from | Transportation Enhancements | 03/02/2010 | 03/15/2010 | 07/15/2010 | 181755 | 0
6684 | New Hampshire | HILLSBOROUGH |  | 02 | A000566 | This project in Litchfield will help improve pedestrian and bicycle access and mobility by building nearly 2 miles of pedestrian and bike trail along Albuquerque Avenue. | Transportation Enhancements | 09/10/2009 | 09/25/2009 | 05/15/2010 | 394477.25 | 0
6685 | New Hampshire | ROCKINGHAM |  | 01 | A000620 | In Epping and Exeter, this project will provide new pavement on a 9.5 mile section of State Route 101 between Exit 6 and the Squamscott River Bridge in Exeter. | Pavement Improvement | 04/02/2009 | 04/10/2009 | 08/01/2009 | 7073670.8 | 9.74
6686 | New Hampshire | STATEWIDE |  | 02 | A000837 | This project will provide a thin layer of new pavement on about 7 miles of I-89 roadway from Exit 12A to Exit 13 in the New London and Grantham area. | Pavement Improvement | 05/07/2009 | 06/04/2009 | 09/01/2009 | 1032533.01 | 6.086
6687 | New Hampshire | MERRIMACK |  | 02 | A000838 | This project will provide crack filling and will provide a thin layer of new pavement on 4.9 miles of I-393 from I-93 to it's ending point in the Concord area. | Pavement Improvement | 06/18/2009 | 06/24/2009 | 09/01/2009 | 817740 | 3.197
6688 | New Hampshire | MERRIMACK |  | 02 | A000839 | This project provides new pavement to 5.4 miles of I-93 from Exit 14 to Exit 17 from the Concord area to Canterbury. Guardrail posts will also be replaced to improve safety. | Pavement Improvement | 06/18/2009 | 06/24/2009 | 10/01/2010 | 5356186 | 6.17
6689 | New Hampshire | STATEWIDE |  | 02 | A000840 | This project in the Sanbornton area provides new pavement on a 4 mile section of I-93 from north of Exit 19 in Northfield to Exit 22 in Sanbornton. The project also includes some bridge rehabilitation | Pavement Improvement | 05/21/2009 | 06/29/2009 | 06/01/2010 | 2188626 | 6.27
6690 | New Hampshire | GRAFTON |  | 02 | A000841 | This project provides new pavement on 7 miles of I-93 from Plymouth to Thornton, just south of the Exit 27 interchange north to the railroad bridge. | Pavement Improvement | 05/21/2009 | 06/09/2009 | 10/01/2009 | 747127.22 | 7.83
6691 | New Hampshire | ROCKINGHAM | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 01 | A000842 | This Portsmouth area project provides new pavement and some bridge deck and guardrail improvements for safety on about 1 and a half miles of I-95 from the Portsmouth traffic circle to the bridge over | Pavement Improvement | 07/17/2009 | 07/30/2009 | 08/01/2010 | 3470149.15 | 12.966
6692 | New Hampshire | GRAFTON |  | 02 | A000843 | This project provides new pavement and bridge improvements on 5.4 miles of I-93 from Exit 30 to Exit 32 in the Woodstock and Lincoln areas. | Pavement Improvement | 07/17/2009 | 07/30/2009 | 10/01/2010 | 8082359.5 | 58.275
6693 | New Hampshire | STATEWIDE |  | 01,02 | A000845 | This project is located in the New Hampton and Ashland and will provide new pavement and bridge improvements on about 6 miles of I-93. | Pavement Improvement | 05/21/2009 | 06/04/2009 | 06/01/2010 | 3924108.25 | 6.083
6694 | New Hampshire | MERRIMACK |  | 02 | A000846 | This New London area project on 5 miles of I-89 provides new pavement from Exit 11 north to Exit 12A. | Pavement Improvement | 04/02/2009 | 04/21/2009 | 08/01/2010 | 5315917 | 6.31
6695 | New Hampshire | STATEWIDE |  | 02 | A000871 | This project provides new pavement on various roadways in the counties of Coos, Carroll, and Grafton. | Pavement Improvement | 04/02/2009 | 05/05/2009 | 09/01/2009 | 3297522.19 | 56.58
6696 | New Hampshire | STATEWIDE |  | 01,02 | A000872 | This project is located along multiple sections of roadway within the counties of Grafton, Sullivan, and Merrimack. The project involves the resurfacing of approx. 48 miles of various roadways.; all | Pavement Improvement | 04/02/2009 | 05/14/2009 | 09/02/2009 | 3161306.53 | 47.18
6697 | New Hampshire | STATEWIDE |  | 01,02 | A000873 | This project provides about 48 miles of new pavement along many sections of roadway in Carroll, Grafton, and Belknap counties. | Pavement Improvement | 04/16/2009 | 05/27/2009 | 09/03/2009 | 3118908.13 | 47.26
6698 | New Hampshire | STATEWIDE |  | 02 | A000874 | This project provides new pavement and safety improvements on about 41 miles of multiple sections of roadway in Cheshire and Hillsborough counties. | Pavement Improvement | 05/07/2009 | 05/20/2009 | 09/01/2009 | 2710153.4 | 40.63
6699 | New Hampshire | STATEWIDE |  | 01,02 | A000875 | This project provides about 28 miles of new pavement on various sections of roadway in Merrimack, Hillsborough and Rockingham counties. | Pavement Improvement | 05/07/2009 | 05/28/2009 | 09/01/2009 | 3009237.13 | 35.32
6700 | New Hampshire | STATEWIDE | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 01,02 | A000876 | This project provides new pavement and intersection safety improvements on various roadways in Rockingham and Strafford counties. | Pavement Improvement | 05/07/2009 | 06/11/2009 | 09/01/2009 | 2941966.74 | 43.38
6701 | New Hampshire | GRAFTON |  | 02 | A000947 | This project on I-89 provides a more efficient I-89/NH 12A interchange at Exit 20 in Lebanon. The project includes bridge and ramp improvements for the interchange, including the bridge over the K-Mar | Pavement Widening | 10/08/2009 | 10/13/2009 | 10/28/2011 | 16217629.33 | 0.9
6702 | New Hampshire | STATEWIDE |  | 02 | A001014 | This project consists of 18 miles of roadway resurfacing in Cheshire, Hillsborough, and Sullivan counties. | Pavement Improvement | 03/11/2010 | 04/08/2010 | 08/20/2010 | 973593 | 18.55
6703 | New Hampshire | STATEWIDE |  | 01,02 | A001015 | This project consists of 42 miles of roadway resurfacing in Hillsborough, Merrimack, and Rockingham counties. | Pavement Improvement | 03/11/2010 | 04/13/2010 | 08/20/2010 | 2118692 | 41.49
6704 | New Hampshire | ROCKINGHAM |  | 01 | A001016 | This project consists of 41 miles of raodway resurfacing in Strafford and Rockingham counties. | Pavement Improvement | 03/11/2010 | 06/11/2010 | 08/20/2010 | 1243349 | 41.28
6705 | New Hampshire | COOS |  | 01,02 | A001031 | This project consists of 72 miles of roadway resurfacing in Coos, Carroll, Grafton, Merrimack, and Sullivan counties. | Pavement Improvement | 04/14/2010 | 04/23/2010 | 09/10/2009 | 4336142.4 | 72.7
6706 | New Hampshire | ROCKINGHAM |  | 01 | A001049 | This project provides about 8 miles of roadway resurfacing, new guardrail and drainage improvements from Exeter to Hampton. | Pavement Improvement | 02/09/2010 | 03/09/2010 | 09/10/2010 | 1787471.07 | 8.836
6707 | New Jersey | CAPE MAY |  | 02 | 0007109 | The Route 52 Causeway Contract B project replaces the two bridges located closest to Somers Point and Ocean City at Ship Channel and Beach Thorofare, respectively, with high level (55' clearance) brid | Bridge Replacement | 07/10/2009 | 08/11/2009 | 01/25/2012 | 73141235 | 1.09
6708 | New Jersey | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 02 | 0012110 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 05/10/2010 |  | 02/17/2012 | 833907 | 2
6709 | New Jersey | ATLANTIC |  | 02 | 0016157 | This project will replace deteriorated pavement with new pavement along 4.5 miles of Route 30 in Hammonton and Mullica Townships in Atlantic County NJ. | Pavement Improvement | 07/08/2009 | 08/24/2009 | 12/01/2009 | 2348430 | 4.4
6710 | New Jersey | CAMDEN |  | 01 | 0016158 | This project will relieve flooding on Route 30 for 1.5 miles by upgrading pavement and replaceing the inlets, pipes and basins in Township of Pennsauken and City of Camden, Camden County. | Pavement Improvement | 08/24/2009 | 09/21/2009 | 09/14/2010 | 9978216 | 1.65
6711 | New Jersey | OCEAN |  | 03 | 0019110 | The project will extend the life of the bridge by including deck repair and curb repair on the entire deck (2.75 miles) of Rt.72 over the Manhawkin Bay in Townships of Stafford and Ship Bottom, Ocean | Bridge Improvement | 09/04/2009 | 09/16/2009 | 07/23/2010 | 4865767 | 2.15
6712 | New Jersey | MIDDLESEX |  | 06 | 0029163 | This project will design the work to replace the bridge deck of Route 18 over Route 1 in the city of New Brunswick, Middlesex County. | Other | 09/01/2009 | 09/01/2009 | 05/08/2012 | 1231172 | 0.5
6713 | New Jersey | HUNTERDON |  | 12 | 0031124 | This project will replace deteriorated pavement with new pavement and improve water drainage along 1 one mile of Route 29 in West Amwell Township & City of Lambertville in Hunterdon County. | Pavement Improvement | 08/19/2009 | 09/14/2009 | 10/04/2010 | 2722977 | 1.02
6714 | New Jersey | HUNTERDON |  | 12 | 0031125 | This project is the utility relocaitons associated with the Route 29 project in West Amwell Township & City of Lambertville in Hunterdon County. | Other | 08/19/2009 | 09/14/2009 | 10/04/2010 | 168405 | 1.02
6715 | New Jersey | HUDSON |  | 10 | 0033274 | This project will paint two Route 1&9(Truck) movable bridges over the Hackensack and Passaic Rivers in the cities of Newark, Jersey City and Kearny, Hudson and Essex County. | Pavement Improvement | 07/16/2009 | 11/02/2009 | 12/31/2011 | 30717257 | 1.06
6716 | New Jersey | MERCER |  | 12 | 0033277 | This project will replace deteriorated pavement with new pavement along 2 miles of Route 1 in both northbound and southbound directions located in the Townships of Lawrence and West Windsor, Mercer Co | Pavement Improvement | 07/30/2009 | 08/04/2009 | 10/30/2009 | 4315080 | 2.02
6717 | New Jersey | MIDDLESEX |  | 06 | 0034109 | This project will replace the bridge decks of Rt 440 NB over Ramp WI and Ramp WK over CR 514. Both bridges are within the interchange of RT 440, CR 514 and NJTA exit 10. in the township of Edison, Mi | Pavement Improvement | 09/01/2009 | 09/15/2009 | 06/01/2010 | 4863155 | 0.27
6718 | New Jersey | MIDDLESEX |  | 13 | 0034110 | This project will design the work to replace the bridge deck of Route 440 Ramp V over Boggs Street, West Side Avenue, State Street and NJ transit in the city of Perth Amboy, Middlesex County. | Other | 07/30/2009 | 10/09/2009 | 09/01/2010 | 1014247 | 0.23
6719 | New Jersey | UNION |  | 10 | 0040168 | This project will replace the Route 22 bridge over the Conrail railroad and Liberty Avenue and improve safety by eliminating the substandard roadway features in Hillside Township, Union County. | Bridge Replacement | 04/26/2010 | 05/26/2010 | 02/15/2013 | 25556508 | 0.46
6720 | New Jersey | BERGEN |  | 09 | 0056151 | This project will design the work for a bridge deck replacement for Route 4 over Flat Rock Road in Englewwod City Bergen County | Other | 08/31/2009 | 08/31/2009 | 09/30/2010 | 410961 | 0.2
6721 | New Jersey | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0158104 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 11/11/2009 | 11/19/2009 | 02/17/2012 | 486732 | 1.5
6722 | New Jersey | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0158105 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 04/05/2010 | 04/05/2010 | 02/17/2012 | 511284 | 1.09
6723 | New Jersey | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0160109 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 04/19/2010 | 04/19/2010 | 02/17/2012 | 424939 | 1.55
6724 | New Jersey | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 02 | 0161103 | Gloucester County will install a new traffic signal to reduce travel delays, provide pedestrian crossings, and allow emergency access for the Fire Department. The project will also provide a new pave | Other | 04/14/2010 | 04/17/2010 | 02/17/2012 | 389487 | 0.06
6725 | New Jersey | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0165101 | Morris County will improve two intersections along Ridgedale Ave to improve traffic flow, increase safety for pedestrians, and provide emergency access for the fire department. | Other | 06/14/2010 |  | 02/17/2012 | 360103 | 0.2
6726 | New Jersey | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 0169101 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 11/09/2009 | 11/09/2009 | 02/17/2012 | 477988 | 1.1
6727 | New Jersey | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 02 | 0177106 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 11/02/2009 | 11/23/2009 | 02/17/2012 | 2618616 | 7.2
6728 | New Jersey | ATLANTIC |  | 02 | 0181112 | This project will replace the Tuckahoe Road Bride over the NJ Tranist Cape May Branch in the City of Estell Manor, Atlantic County. | Bridge Replacement | 03/02/2010 | 03/08/2010 | 02/17/2012 | 4779469 | 0.2
6729 | New Jersey | WARREN | ALLENTOWN-BETHLEHEM-EASTON (PA) | 05 | 0378108 | Warren County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Other | 03/18/2010 | 04/01/2010 | 02/17/2012 | 682081 | 3.04
6730 | New Jersey | WARREN | NEW YORK-NORTHEASTERN NJ (NY) | 05 | 0378109 | Warren County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Other | 03/18/2010 |  | 02/17/2012 | 2262137 | 0
6731 | New Jersey | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 05 | 0386103 | Sussex County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Pavement Improvement | 05/11/2010 | 05/19/2010 | 02/17/2012 | 1035636 | 5.1
6732 | New Jersey | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 05 | 0393108 | Sussex County will be rehabilitating the roadway to provide structural improvements and a new driving surface. This will improve driving quality by rehabilitating the road, which will make the road | Pavement Improvement | 06/28/2010 |  | 02/17/2012 | 910140 | 3.54
6733 | New Jersey | ESSEX |  | 10 | 0785101 | This project will replace deteriorated pavement with new pavement and improve safety along nearly 2 miles of I-78 in the City of Newark, Essex County. | Pavement Improvement | 07/20/2009 | 08/31/2009 | 11/10/2010 | 15138024 | 1.43
6734 | New Jersey | HUNTERDON |  | 07 | 0785102 | This project will design the work to replace the bridge deck of I-78 ramp A, over I-78 in Township of Clinton Hunterdon County. | Other | 08/31/2009 | 08/31/2009 | 09/01/2010 | 457281 | 0.5
6735 | New Jersey | WARREN |  | 05 | 0785103 | This project will remove the existing concrete slabs and replace with new pavement for nearly 1 mile on I-78 in Greenwich Township, Warren County. | Pavement Improvement | 08/18/2009 | 09/14/2009 | 08/01/2010 | 4243137 | 0.54
6736 | New Jersey | PASSAIC |  | 08,09 | 0805087 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 6 miles on I-80 Eastbound from West of Madison Ave to Polifly Road | Pavement Improvement | 07/16/2009 | 08/19/2009 | 09/02/2011 | 17443515 | 6.5
6737 | New Jersey | ESSEX |  | 11 | 0805088 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 8 miles on I-80 westbound form East of South Beverwyck Road to West | Pavement Improvement | 06/02/2009 | 06/24/2009 | 03/12/2010 | 10952559 | 7.7
6738 | New Jersey | MORRIS |  | 11 | 0805090 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and repairing bridge supports for the I-80 EB and WB bridges over Berkshire Valley Road i | Bridge Improvement | 07/07/2009 | 07/29/2009 | 06/11/2010 | 10752697 | 0.59
6739 | New Jersey | PASSAIC |  | 08,11 | 0805091 | This project will paint 5 bridges on Route I-80 in the Counties of Bergen, Essex, Passaic, Warren and Essex. | Pavement Improvement | 09/14/2009 | 11/05/2009 | 12/05/2010 | 8206557 | 0.28
6740 | New Jersey | CUMBERLAND | ATLANTIC CITY | 02 | 1019113 | Cumberland County will repair the concrete joints and concrete sections along the curbs to allow for an asphalt overlay. This will improve driving quality by resurfacing the road, which will make the | Pavement Improvement | 03/17/2010 | 03/17/2010 | 02/17/2012 | 667026 | 0.48
6741 | New Jersey | MERCER |  | 04 | 1958056 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 5 miles on I-195 from the New Jersey Turnpike to just East of Imlay | Pavement Improvement | 04/09/2010 | 04/21/2010 | 11/12/2010 | 10580678 | 7.54
6742 | New Jersey | ESSEX |  | 09,10 | 2806103 | This project will paint 16 bridges on Route I-280 between mile points 12.7 to 14.5 in the Cities of Newark, Orange, East and West Orange, Essex County | Pavement Improvement | 07/28/2009 | 09/21/2009 | 08/15/2011 | 8965761 | 1.72
6743 | New Jersey | ESSEX |  | 08,10 | 2806105 | This project will paint 17 bridges on Route I-280 between mile points 7.5 to 11.1 in the Cities of Newark, Orange, East and West Orange, Essex County | Pavement Improvement | 07/27/2009 | 11/02/2009 | 08/15/2011 | 6833569 | 3.62
6744 | New Jersey | MIDDLESEX |  | 06 | 2873080 | This project will replace existing deteriorating bridge decks and pavement with new pavement, upgrade guardrails and improve water drainage on nearly 7 miles on I-287 NB and SB in Piscataway, Middlese | Pavement Improvement | 09/14/2009 | 09/17/2009 | 11/09/2011 | 35711860 | 7
6745 | New Jersey | MORRIS |  | 11 | 2873081 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck for the I-287 NB bridge over Route 46 in Parsippany-Troy Hills, Morris County. | Pavement Improvement | 07/10/2009 | 08/03/2009 | 09/30/2009 | 1782845 | 0
6746 | New Jersey | SALEM |  | 02 | 2952121 | This project will address the painting needs for 49 bridges on the Route I-295 corridor in Gloucester and Salem Counties. | Pavement Improvement | 08/31/2009 | 10/19/2009 | 09/01/2010 | 3084703 | 0
6747 | New Jersey | CAMDEN |  | 01,03 | 2952123 | This project will replace existing deteriorating bridge decks and pavement with new pavement, upgrade guardrails and improve water drainage on nearly 8 miles on I-295 NB and SB in West Deptford, Deptf | Pavement Improvement | 06/29/2009 | 06/29/2009 | 07/20/2012 | 77320125 | 7.9
6748 | New Jersey | CAMDEN |  | 01 | 2952124 | This project provides the funding for the ROW acquisition to allow for the construction of a new alignment that carries I-295 mainline through the interchange of Route 42 and I-76 in Bellmawr and Mt. | Other | 04/24/2009 | 04/24/2009 | 03/06/2012 | 4807500 | 3.62
6749 | New Jersey | GLOUCESTER | TRENTON (PA) | 02 | 4037107 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 06/07/2010 |  | 02/17/2012 | 536973 | 0.9
6750 | New Jersey | CAMDEN |  | 01 | 4145110 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 04/05/2010 |  | 02/17/2012 | 290540 | 0
6751 | New Jersey | CAMDEN |  | 01 | 4184101 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 05/17/2010 |  | 02/17/2012 | 485649 | 0
6752 | New Jersey | CAMDEN |  | 01 | 4187101 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 05/17/2010 |  | 02/17/2012 | 523841 | 0
6753 | New Jersey | BURLINGTON |  | 04 | 4395101 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and repairing bridge supports for the Main St. (CR 543) over Rt. 206 bridge in Townships | Pavement Improvement | 08/26/2009 | 10/28/2009 | 11/09/2010 | 1946479 | 0.02
6754 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | 7044101 | This project will resurface 4 miles of roadway and improve water drainage from mile point 0 to mile point 4 on Route 35 in Berkely Township, Seside Heights, Seaside Park and Toms River, Ocean County. | Other | 06/17/2009 | 08/31/2009 | 11/01/2010 | 1491129 | 4
6755 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | 7044102 | This project will resurface 5 miles of roadway and improve water drainage from mile point 4 to mile point 9 on Route 35 in Toms River, Lavallette and Mantoloking, Ocean County. | Other | 05/20/2009 | 05/20/2009 | 10/01/2010 | 1498266 | 5
6756 | New Jersey | MIDDLESEX |  | 06 | 7269101 | This project will extend the life of the bridge and improve safety replacing the existing deteriorated deck and in the Township of Woodbridge, Middlesex County. | Bridge Improvement | 08/28/2009 | 08/27/2009 | 09/01/2010 | 2966116 | 0.3
6757 | New Jersey | UNION |  | 10 | 7510101 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 04/23/2010 |  | 02/17/2012 | 1015894 | 0
6758 | New Jersey | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09,13 | 7675115 | This project will design the work for a new bridge over the Hackensack River in Jersey City and Kearny, Hudson County. | Other | 04/14/2009 | 08/27/2009 | 12/23/2010 | 3471845 | 0.3
6759 | New Jersey | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09,13 | 7675116 | This project will design the work for the approaches and a new bridge and over the Hackensack River in Jersey City and Kearny, Hudson County. | Other | 08/04/2009 | 08/04/2009 | 03/23/2011 | 9716313 | 0.6
6760 | New Jersey | MORRIS |  | 11 | 7741139 | This project will design the work to replace the bridge deck of County route 665 (Salem Street) over Route 10 over Randolph, Morris County. | Other | 08/31/2009 | 08/31/2009 | 06/01/2011 | 617616 | 0.11
6761 | New Jersey | MORRIS |  | 11 | 7789102 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and is located in the Township of Montville, Morris County. in addition this project will | Bridge Improvement | 07/14/2009 | 07/31/2009 | 04/26/2010 | 1341542 | 0.01
6762 | New Jersey | BERGEN |  | 09 | 7802160 | This project will replace two bridges at the intersection of Route 46 over Main Street , improve safety and drainage in the Borough of Lodi, Bergen County. | Pavement Improvement | 05/28/2009 | 06/15/2009 | 09/01/2012 | 30817985 | 0.42
6763 | New Jersey | BERGEN |  | 09 | 7802163 | This project is the utility relocaitons associated with the Route 46 over Main Street in the Borough of Lodi, Bergen County. | Other | 05/28/2009 | 06/18/2009 | 09/01/2012 | 2644220 | 0.42
6764 | New Jersey | HUDSON |  | 13 | 7811116 | This project will replace deteriorated pavement with new pavement along 1.5 miles of Route 440 in both northbound and southbound directions from JFK Blvd. to 22nd street. The project is located in the | Pavement Improvement | 07/28/2009 | 08/11/2009 | 11/19/2009 | 3660338 | 1.4
6765 | New Jersey | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 09 | 8112137 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck of the Roff Avenue Bridge over Route 46 in Palisades Park, Bergen County. | Bridge Improvement | 08/17/2009 | 11/02/2009 | 11/05/2010 | 2052177 | 0
6766 | New Jersey | PASSAIC |  | 08 | 8112138 | This project will improve safety and extend the life of the Grove Street (CR 623) bridge over Route 46 in Clifton Passaic County, by replacing the existing deteriorated deck, and repairing bridge supp | Pavement Improvement | 08/26/2009 | 10/14/2009 | 10/20/2010 | 3737371 | 0.1
6767 | New Jersey | BERGEN |  | 09 | 8112139 | This project is the utility relocaitons associated with the Roff Avenue bridge over Route 46 in Palisades Park, Bergen County. | Other | 08/17/2009 | 11/04/2009 | 11/05/2010 | 261101 | 0.02
6768 | New Jersey | BERGEN |  | 05 | 8669101 | This project will extend the life of the bridge and improve safety and drainage by replacing the existing deteriorated deck and repairing bridge supports in Township of Mahwah, Bergen County NJ. | Bridge Improvement | 06/18/2009 | 06/18/2009 | 08/14/2009 | 718013 | 0.03
6769 | New Jersey | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | A00S961 | This project will improve the park appearance, promote and enhance pedestrian activities, and beautify the landscape. | Other | 05/18/2010 | 05/18/2010 | 02/17/2012 | 128999 | 0
6770 | New Jersey | STATEWIDE |  | 03,04,05,06,07,08,09,10,11,12 | B00S688 | The Statewide project will provide safety enhancement at hazardous highway-rail grade crossings to improve rail road crossing safety, improve visibility of traffic stripes and pavement markings, and i | Safety/Traffic Management | 01/11/2010 | 02/26/2010 | 12/28/2011 | 1197121 | 0
6771 | New Jersey | HUDSON |  | 13 | B00S719 | This project will improve the walkway appearance, promote and enhance pedestrian activities, and beautify the landscape. | Transportation Enhancements | 01/28/2010 | 01/28/2010 | 02/17/2012 | 1902500 | 0
6772 | New Jersey | STATEWIDE |  | 04,12 | B00S785 | This project (Contract #10) will provide guiderail down the middle of the roadway on 5.14 miles of Route 18 and 4.64 miles of Route I-95 in the Counties of Mercer, Middlesex, Monmouth. | Safety/Traffic Management | 08/17/2009 | 09/30/2009 | 07/01/2010 | 3337794 | 8.22
6773 | New Jersey | STATEWIDE |  | 11 | B00S786 | This project (Contract #11) will provide guiderail down the middle of the roadway on 5.14 miles of Route 18 and 4.64 miles of Route I-95 in the Counties of Mercer, Middlesex, Monmouth. | Other | 08/24/2009 | 09/14/2009 | 11/01/2010 | 1204790 | 6.6
6774 | New Jersey | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S793 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 05/20/2010 | 05/20/2010 | 02/17/2012 | 1214294 | 7.79
6775 | New Jersey | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S796 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 05/31/2010 |  | 02/17/2012 | 432644 | 1.76
6776 | New Jersey | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S797 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 05/17/2010 | 05/19/2010 | 02/17/2012 | 557865 | 2.03
6777 | New Jersey | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S798 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 05/21/2010 | 05/21/2010 | 02/17/2012 | 721277 | 3.59
6778 | New Jersey | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S799 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 06/28/2010 |  | 02/17/2012 | 559538 | 5.05
6779 | New Jersey | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S800 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 06/21/2010 |  | 02/17/2012 | 542920 | 1.37
6780 | New Jersey | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S801 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 06/07/2010 |  | 02/17/2012 | 1214185 | 4.64
6781 | New Jersey | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S803 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 05/19/2010 | 05/24/2010 | 02/17/2012 | 2595789 | 10.3
6782 | New Jersey | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 05 | B00S805 | Sussex County will improve safety over the Sparta Glen Brook by replacing the bridge. | Bridge Replacement | 06/08/2010 |  | 02/17/2012 | 901238 | 0.09
6783 | New Jersey | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S814 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 04/12/2010 | 04/12/2010 | 02/17/2012 | 359392 | 1.3
6784 | New Jersey | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S815 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 04/12/2010 | 04/12/2010 | 02/17/2012 | 466694 | 1.73
6785 | New Jersey | SOMERSET | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S816 | Somerset County will resurface the existing asphalt roadway with new asphalt on multiple County roads. This will improve driving quality by resurfacing the road, which will make the road smoother and | Transportation Enhancements | 10/19/2009 | 10/21/2009 | 02/17/2012 | 4171290 | 15.3
6786 | New Jersey | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 02 | B00S826 | Gloucester County will upgrade over 100 traffic signals to include new pedestrian signals. These signals will include count down timer displays. Count down timer displays provide additional informat | Other | 05/10/2010 | 06/01/2010 | 02/17/2012 | 852320 | 0
6787 | New Jersey | CUMBERLAND | ATLANTIC CITY | 02 | B00S829 | Cumberland County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at | Pavement Improvement | 10/06/2009 | 10/06/2009 | 02/17/2012 | 2350000 | 10
6788 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | B00S830 | Ocean County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother and | Pavement Improvement | 03/18/2010 |  | 02/17/2012 | 2673607 | 9.5
6789 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | B00S831 | Ocean County will upgrade the existing end treatments of the guide rails on 82 bridges to extruder end sections. This will bring each bridge with guide rail to current standards and enhances the safet | Safety/Traffic Management | 01/19/2010 |  | 02/17/2012 | 926963 | 1
6790 | New Jersey | MIDDLESEX | NEW YORK-NORTHEASTERN NJ (NY) | 06 | B00S832 | Middlesex County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother | Pavement Improvement | 06/14/2010 |  | 02/17/2012 | 7283014 | 0
6791 | New Jersey | ESSEX | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S834 | Essex County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at multi | Pavement Improvement | 04/01/2010 | 04/14/2010 | 02/17/2012 | 10739136 | 17.5
6792 | New Jersey | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S835 | Morris County will upgrade the intersection to improve traffic flow and increase safety for pedestrians. | Other | 06/04/2010 |  | 02/17/2012 | 231778 | 0.1
6793 | New Jersey | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S836 | Morris County will improve two intersections along Littleton Road to improve traffic flow and increase safety for pedestrians. | Other | 06/14/2010 |  | 02/17/2012 | 220126 | 0.05
6794 | New Jersey | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S858 | Bergen County will extend the life of the bridge and improve safety over the Hackensack River by rehabilitating the bridge, reconstructing the approach spans, and upgrading the electrical equipment. | Bridge Improvement | 06/23/2010 |  | 02/17/2012 | 17788000 | 0
6795 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | B00S864 | Ocean County will replace the Beach Boulevard Bridge along the existing alignment. | Bridge Replacement | 02/01/2010 |  | 02/17/2012 | 5491883 | 0.25
6796 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | B00S865 | Ocean County will be preserving its bridge's structural integrity and extend its useful life by re-painting the crossing. | Bridge Improvement | 03/08/2010 |  | 02/17/2012 | 575500 | 0.1
6797 | New Jersey | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S890 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at mult | Pavement Improvement | 06/02/2010 |  | 02/17/2012 | 208659 | 0
6798 | New Jersey | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S895 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Pavement Improvement | 05/03/2010 | 05/10/2010 | 02/17/2012 | 1293000 | 0
6799 | New Jersey | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S946 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 05/18/2010 | 06/14/2010 | 02/17/2012 | 283691 | 0.38
6800 | New Jersey | CUMBERLAND | ATLANTIC CITY | 02 | B00S953 | This project will restore the Bivalve Shipping Sheds. | Transportation Enhancements | 05/24/2010 | 05/25/2010 | 02/17/2012 | 1250000 | 0
6801 | New Jersey | SOMERSET | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S959 | This project will improve, promote, and enhance pedestrian/bicycle activities. | Transportation Enhancements | 06/08/2010 |  | 02/17/2012 | 2591113 | 0.54
6802 | New Jersey | HUNTERDON |  | 07 | B00S969 | This project will facilitate additional trail corridor through the acquisition of right of way to promote and enhance pedestrian activities. | Transportation Enhancements | 02/18/2010 |  | 02/17/2012 | 636000 | 0
6803 | New Jersey | PASSAIC |  | 08 | B00S984 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 05/19/2010 |  | 02/17/2012 | 396670 | 0.66
6804 | New Jersey | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 04 | PLHD001 | Ocean County will improve the intersection to improve traffic flow and increase safety. | Pavement Improvement | 10/07/2009 |  | 02/17/2012 | 197429 | 0.4
6805 | New Mexico | EDDY |  | 02 | 0062004 | Project consists of construction of two new lanes on US62/180 (northbuond lanes) between White City and Carlsbad to allow for a four lane highway. Project consists of new roadway, shoulders, striping, | Pavement Widening | 04/08/2009 | 04/08/2009 | 10/07/2010 | 14855940.31 | 10
6806 | New Mexico | DONA ANA | LAS CRUCES | 02 | 0102111 | The I-10 six lane project will provide a total of (3) lanes for both east and west bound traffic, the additional lanes will be constructed within NMDOT ROW, this project is 18.3 miles in length, sta | Pavement Widening | 11/30/2009 | 12/23/2009 | 07/13/2011 | 10000000 | 20.4
6807 | New Mexico | GRANT |  | 02 | 0356005 | The project will include rebuilding and aligning of the curb and gutter, sidewalks, lighting and improvements so that people with disabilities will be able to use the sidewalks. It will, also, includ | Pavement Improvement | 02/02/2010 | 03/08/2010 | 06/16/2010 | 350000 | 0
6808 | New Mexico | BERNALILLO | ALBUQUERQUE | 01 | 0403104 | The City of Albuquerque proposes to construct a trail which would connect existing facilities to enhance the multi-modal transportation network | Transportation Enhancements | 10/26/2009 | 10/26/2009 | 07/26/2010 | 4118517.76 | 0
6809 | New Mexico | BERNALILLO |  | 01 | 0403168 | Reconstruction of I-40 and West Central consists of construction of a new overpass over I-25, new on and off ramps, new construction of Paseo Del Volcan and Central Avenue, and re-alignment of Central | Pavement Widening | 04/28/2009 | 04/28/2009 | 10/24/2010 | 14800000 | 1
6810 | New Mexico | SANTA FE |  | 03 | 0511097 | This project will reconstruction the four lanes of US 84/285 from Arroyo Seco to La Puebla and adds a two-way frontage road on both sides of the highway. | Pavement Widening | 05/27/2009 | 05/27/2009 | 10/10/2010 | 13040682.99 | 2.9
6811 | New Mexico | SANTA FE |  | 03 | 0511098 | This project will reconstruct the four lanes of US 84/285 highway and adds medians from Dandy Burger South to the Dreamcatcher Theater. It will also add a new traffic signal at the Upper San Pedro in | Pavement Improvement | 04/08/2009 | 04/08/2009 | 06/15/2010 | 9023269.25 | 1.5
6812 | New Mexico | COLFAX |  | 03 | 0649036 | This project will construct 2 new lanes on US64/87 from Des Moines to Capulin, converting this portion of US64/87 to a 4-lane facility. This is Phase Vi of a seven Phase project to widen US64/87 to 4 | New Construction | 08/12/2009 | 08/12/2009 | 01/26/2011 | 25662731.53 | 16
6813 | New Mexico | OTERO |  | 03 | 0821026 | Structural evaluation, preservation of sound timbers and replacement of decayed/missing timbers. | Transportation Enhancements | 08/26/2009 | 08/26/2009 | 09/29/2009 | 249747 | 0
6814 | New Mexico | LEA |  | 02 | 1271015 | Project consists of total reconstruction of a 14.4 mile segment of NM128 between Carlsbad and Jal on an offset new alignment. Project will consist of new roadway, shoulders, striping, permanent signin | Pavement Improvement | 04/13/2009 | 04/13/2009 | 05/19/2010 | 8252068.4 | 14.11
6815 | New Mexico | LINCOLN |  | 02 | 3801206 | Bridge Replacement of the Priest Gulch Bridge on US380 at Milepost 96.3 in the Lincoln Historic District In Lincoln County approximately 60 miles west of Roswell | Pavement Improvement | 03/16/2010 | 04/05/2010 | 10/08/2010 | 1145245.88 | 0
6816 | New Mexico | SANDOVAL | ALBUQUERQUE | 01 | 4007003 | This project will complete Stage II of the Paseo Del Volcan corridor within the city of Rio Rancho. The project will consist of a new 2-lane facility including lighting, bridges, and various drainage | Pavement Widening | 08/06/2009 | 08/10/2009 | 02/11/2011 | 14000000 | 0
6817 | New Mexico | SAN JUAN |  | 03 | 4911011 | This project will provide two new traveling lanes to make the US 491 roadway a four lane facility. This is one segment of 9 segments to four lane US 491 from MP 15.7 to MP 84.7. | New Construction | 06/30/2009 | 06/30/2009 | 05/04/2010 | 21624989 | 8
6818 | New Mexico | MCKINLEY |  | 03 | 4911031 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. Project will also provide intersection improvements for better t | Pavement Improvement | 04/10/2009 | 04/10/2009 | 03/04/2010 | 10576186.05 | 13.9
6819 | New Mexico | SANDOVAL | ALBUQUERQUE | 03 | 5119001 | Reconstruct 2 lanes & add/improve sidewalks. Add center double left turn lanes & add deceleration lane for new school bus access. | Pavement Improvement | 01/11/2010 | 01/25/2010 | 07/24/2010 | 1875051.11 | 0
6820 | New Mexico | RIO ARRIBA |  | 03 | 5348002 | To construct road improvements to Industrial Park Road for its entire length of 1.1 miles in Espanola that includes added lanes, drainage improvements, pedestrian facilities, utilities, curb and gutte | Pavement Improvement | 10/07/2009 | 10/07/2009 | 06/16/2010 | 1250000 | 0
6821 | New Mexico | GRANT |  | 02 | 7517010 | This project will consist of improving (paving) the roadway on Diaz Avenue from Cul de Sac North to E. Street. In addition, it will include inspection and oversight. | Pavement Improvement | 02/16/2010 | 03/01/2010 | 08/29/2010 | 390000 | 0
6822 | New Mexico | BERNALILLO | ALBUQUERQUE | 03 | ES03184 | "The City of Albuquerque proposes to expand its Advanced Transportation Management System with the installation of the communication infrastructure for the following corridors: 1) Alameda Blvd. from | Safety/Traffic Management | 12/09/2009 | 01/11/2010 | 07/10/2010 | 2651176 | 0
6823 | New Mexico | ROOSEVELT |  | 03 | ES04049 | Enhancements such as; Bushes, Trees Sidewalks & ADA Ramps | Transportation Enhancements | 04/05/2010 | 04/06/2010 | 07/06/2010 | 242101 | 0
6824 | New Mexico | LUNA |  | 02 | ES11140 | Installation of a left turning lane | Pavement Widening | 02/15/2010 | 04/05/2010 | 08/02/2010 | 143503.76 | 0
6825 | New Mexico | SIERRA |  | 02 | ES11150 | Landscaping, pedestrian facilities, & base course. | Transportation Enhancements | 02/15/2010 | 02/15/2010 | 04/08/2010 | 93906 | 0
6826 | New Mexico | DONA ANA |  | 02 | ES11160 | Installation of landscaping materials and erosion control measures | Transportation Enhancements | 02/17/2010 | 03/10/2010 | 05/19/2010 | 178881.23 | 0
6827 | New Mexico | DONA ANA |  | 02 | ES11170 | Construct eight bus shelters | Transportation Enhancements | 02/09/2010 | 03/01/2010 | 04/14/2010 | 71000 | 0
6828 | New Mexico | DONA ANA |  | 02 | ES11180 | Project will consist of milling & removing 2.5" of old asphalt on driving & passing lanes and replace with 2.5" Hot Mix Asphalt, Open Graded Friction Course and fog seal shoulders. | Pavement Improvement | 03/09/2010 | 03/18/2010 | 06/11/2010 | 3462816.28 | 0
6829 | New Mexico | HIDALGO |  | 02 | ES11200 | This project will include making roadway improvements to NM 494 from mile post 0 to mile post 1.7. Existing old pavement will be removed and replaced with new pavement. Sidewalks, curb and gutter, d | Pavement Improvement | 02/04/2010 | 02/16/2010 | 04/27/2010 | 400000 | 0
6830 | New Mexico | DONA ANA |  | 02 | ES11210 | This project will include roadway improvements by adding more pavement on top of the existing pavement on Calle del Norte from NM 28 to Tres Sendas. In addition, it will include inspection and oversi | Pavement Improvement | 02/23/2010 | 03/15/2010 | 04/30/2010 | 500000 | 0
6831 | New Mexico | LUNA |  | 02 | ES11220 | Reconstruction to include pedestrian facilities | Pavement Improvement | 12/22/2009 | 01/03/2010 | 11/08/2010 | 850000 | 0
6832 | New Mexico | DONA ANA |  | 02 | ES11230 | Sidewalks, curb & gutter, drainage structures, storm drains, bike lanes & pedestrian facilities. | Pavement Improvement | 02/10/2010 | 03/15/2010 | 11/30/2010 | 2000000 | 0
6833 | New Mexico | GRANT |  | 02 | ES11240 | This project will include grinding down existing old pavement and replacing with new pavement on 12th Street from Gold Street to Mississippi Street. In addition, it will include inspection and oversi | Pavement Improvement | 02/02/2010 | 02/03/2010 | 05/03/2010 | 591668.46 | 0
6834 | New Mexico | SOCORRO |  | 02 | ES11250 | This project will include inspection and oversight of pavement rehabilitation and maintenance, grinding down existing asphalt and replacing with new material on California Street from mile post 0 to m | Pavement Improvement | 04/01/2010 | 04/01/2010 | 11/26/2010 | 704080 | 0
6835 | New Mexico | SIERRA |  | 02 | ES11260 | This project will include new pavement on the I-25 Business Loop (Old US 85) from Ashbaugh at mile post 0 to Morgan at mile post 3.9. Construction will include management and pedestrian facilities. | Pavement Improvement | 02/22/2010 | 03/01/2010 | 07/28/2010 | 604305 | 0
6836 | New Mexico | DONA ANA | EL PASO, TX-NM | 02 | ES11270 | Project will improve the roadway surface on NM 213 which is a heavily traveled route between El Paso, Chaparral, White Sands Missile Range, and Jct. NM 404 to Interstate 10 and Anthony, NM | Pavement Improvement | 02/25/2010 | 03/10/2010 | 04/21/2010 | 940288.3 | 0
6837 | New Mexico | HIDALGO |  | 02 | ES11400 | This seven mile maintenance project includes removing 2 inches of the existing pavement and replacing it with new pavement. The purpose of this project is to improve the quality of the roadway surface | Pavement Improvement | 04/06/2010 | 06/01/2010 | 08/03/2010 | 1851727.18 | 0
6838 | New Mexico | LEA |  | 02 | ES21070 | This project will include downtown beautification consisting of new pavement, lighting, crosswalks, sidewalks, curb and gutter and landscaping on NM 176 from mile post 34.9 to milepost 35.4 and on NM | Transportation Enhancements | 02/05/2010 | 02/08/2010 | 06/27/2010 | 249747 | 0
6839 | New Mexico | OTERO |  | 03 | ES21190 | This project will include the removal of an old bridge and construction of a new bridge to replace the old bridge on 9th Street and Washington Street. | Pavement Improvement | 01/13/2010 | 01/19/2010 | 03/10/2010 | 150000 | 0
6840 | New Mexico | CHAVES |  | 02 | ES21200 | This project will include grinding down old pavement and replacing with new pavement along an existing paved road. The project is located on West Brasher Road from the entrance of the City’s municipal | Pavement Improvement | 02/19/2010 | 03/15/2010 | 06/04/2010 | 831489 | 0
6841 | New Mexico | LEA |  | 02 | ES21210 | This project includes new pavement on Ninth Street from Avenue D to Polk Avenue. | Pavement Improvement | 01/18/2010 | 01/19/2010 | 08/19/2010 | 592084.58 | 0
6842 | New Mexico | LEA |  | 02 | ES21220 | Mill, check sub-base, relay and add 4 inches of asphalt. | Pavement Improvement | 03/16/2010 | 03/29/2010 | 06/27/2010 | 831489 | 0
6843 | New Mexico | LEA |  | 02 | ES21230 | 10 feet wide concrete multi-use trail with landscape, pedestrian lighting and americans with disabilites act intersection improvements | Transportation Enhancements | 02/08/2010 | 02/15/2010 | 03/26/2010 | 249747 | 0
6844 | New Mexico | LINCOLN |  | 02 | ES21240 | This project will consist of new pavement on Paradise Canyon from Suddeth Drive to Country Club Drive. | Pavement Improvement | 04/28/2010 | 05/03/2010 | 06/02/2010 | 352651 | 0
6845 | New Mexico | CHAVES |  | 02 | ES21250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 03/22/2010 | 03/29/2010 | 05/28/2010 | 830000 | 0
6846 | New Mexico | EDDY |  | 02 | ES21260 | This project will include new pavement on Greene Street from Canal to Moore Drive. | Pavement Improvement | 02/18/2010 | 03/03/2010 | 07/21/2010 | 831489 | 0
6847 | New Mexico | OTERO |  | 03 | ES21270 | This project will include the construction of accessible sidewalks and ramps, and driveways for people with disabilities on 1st Street from White Sands to Florida and 10th Street from Cuba to College. | Transportation Enhancements | 02/02/2010 | 05/09/2010 | 02/08/2010 | 246401.34 | 0
6848 | New Mexico | CURRY |  | 02 | ES21280 | Bridge replacement on Hull Street spanning over Burlington Northern Santa Fe Railroad | Bridge Replacement | 11/24/2009 | 01/04/2010 | 10/31/2010 | 831489 | 0.3
6849 | New Mexico | CURRY |  | 02 | ES21300 | Project consists of landscaping at the intersection of US60/70/84 intersection at the New Mexico/Texas State Line in the Town of Texico in Curry County. Project will include trees, shrubs, flowers, Am | Transportation Enhancements | 04/20/2010 | 05/05/2010 | 07/30/2010 | 303258.15 | 1
6850 | New Mexico | CURRY |  | 02 | ES21310 | Project will rehabilitate a section of NM 209 between Broadview and Grady in Curry County. Project consists of milling full width the existing roadway and a Hot mix asphalt overlay. | Pavement Improvement | 04/28/2010 | 05/20/2010 | 08/12/2010 | 1267659.56 | 6
6851 | New Mexico | LEA |  | 02 | ES21320 | Pavement reconstruction including milling excavation, subgrade base course, asphalt treated base, hot-mix asphalt and minor concrete. | Pavement Improvement | 01/15/2010 | 01/25/2010 | 07/24/2010 | 831489 | 1
6852 | New Mexico | ROOSEVELT |  | 03 | ES21330 | Project consists of rehabilitating a four-mile section of NM 88 east of the City of Portales in Roosevelt County. The typical section will be process, placed and compacted and then overlayed with a 2. | Pavement Improvement | 04/01/2010 | 04/23/2010 | 09/10/2010 | 1589128.83 | 5.4
6853 | New Mexico | DONA ANA |  | 02 | ES21350 | This project will consist of improving the road pavement and drainage on East Berino Road from NM 478 to Stern Drive. It will, also, include curb and gutter, sidewalks, storm drainage installation an | Pavement Improvement | 04/26/2010 | 05/10/2010 | 02/03/2011 | 2168207 | 0
6854 | New Mexico | CURRY |  | 03 | ES21360 | Project will consist of full lane width milling and removal of the existing pavement and replacing full width Hot Mix Asphalt overlay south of Portales in Roosevelt County. | Pavement Improvement | 02/05/2010 | 02/25/2010 | 06/18/2010 | 4088475.9 | 0
6855 | New Mexico | CURRY |  | 03 | ES21420 | The project will include grinding the existing pavement, putting it back in place and compacting it. Then the existing roadway will receive a new asphalt pavement overlay. | Pavement Improvement | 03/15/2010 | 04/04/2010 | 06/25/2010 | 2490462.56 | 0
6856 | New Mexico | VALENCIA |  | 02 | ES31110 | The Village of Bosque Farms proposes to enhance 21 side street accesses onto Bosque Loop Road by providing road improvements by re-aligning, resurfacing with Hot mix Asphalt , and constructing a secti | Pavement Improvement | 04/28/2010 | 05/03/2010 | 06/18/2010 | 63000 | 0
6857 | New Mexico | VALENCIA |  | 02 | ES31120 | This project is a joint effort between the City of Belen and The Mid Region Council of Governments. The project will provide Pedestrian Access to the Rail Runner Station by constructing an Americans | Transportation Enhancements | 06/16/2010 | 06/21/2010 | 01/14/2011 | 2410012.2 | 14
6858 | New Mexico | VALENCIA |  | 02 | ES31160 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 03/30/2010 | 04/14/2010 | 07/02/2010 | 5024079.96 | 0
6859 | New Mexico | COLFAX |  | 03 | ES41190 | The project will upgrade signing, striping, curb and gutter, sidewalk, drainage structures, and pavement that will enhance safety and improve existing pavement. | Pavement Improvement | 06/02/2010 | 06/21/2010 | 09/21/2010 | 762000 | 0
6860 | New Mexico | SAN MIGUEL |  | 03 | ES41210 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 04/26/2010 | 04/26/2010 | 08/13/2010 | 1944135.31 | 0
6861 | New Mexico | COLFAX |  | 03 | ES41220 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 07/07/2010 | 07/22/2010 | 09/22/2010 | 763077.01 | 0
6862 | New Mexico | QUAY |  | 02 | ES41240 | The project will upgrade signing, striping, curb and gutter, sidewalk, drainage structures, and pavement that will enhance safety and improve existing pavement. | Pavement Improvement | 03/08/2010 | 03/08/2010 | 08/23/2010 | 1785000 | 0
6863 | New Mexico | UNION |  | 03 | ES41250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 02/04/2010 | 02/25/2010 | 05/21/2010 | 3625670.49 | 0
6864 | New Mexico | GUADALUPE |  | 03 | ES41360 | This project will crack seal 28.5 miles of Interstate 40 in Quay County, 30.7 miles of US 54 in Quay County, and 5.6 miles of US 84 in Guadalupe County | Pavement Improvement | 03/15/2010 | 04/05/2010 | 06/25/2010 | 1217669.1 | 0
6865 | New Mexico | LOS ALAMOS |  | 03 | ES51140 | Rehabilitate & reconstruct highly deteriorated roadway to include; pavement, curb, gutter, sidewalks, storm drain systems & roadway lighting. | Pavement Widening | 11/02/2009 | 11/02/2009 | 03/01/2010 | 1962217 | 0
6866 | New Mexico | SAN JUAN |  | 02 | ES51260 | The New Mexico Department of Transportation will resurface the top three inches of existing asphalt in the southbound driving lanes of US 491 with 3” of new Hot Mix Asphalt. This will improve driving | Pavement Improvement | 02/04/2010 | 02/25/2010 | 10/01/2010 | 3815204.58 | 0
6867 | New Mexico | TORRANCE |  | 01 | ES51270 | Repair cracks in pavement and repave roadway | Pavement Improvement | 03/02/2010 | 03/25/2010 | 10/01/2010 | 1476353.15 | 0
6868 | New Mexico | SANDOVAL |  | 03 | ES61160 | This project will replace the existing old bridge with a new prefabricated bridge. | Bridge Improvement | 03/11/2010 | 03/11/2010 | 05/31/2010 | 169132.72 | 0
6869 | New Mexico | SANDOVAL |  | 03 | ES61170 | This project will replace the existing old bridge with a new prefabricated bridge. | Bridge Improvement | 03/11/2010 | 03/11/2010 | 05/31/2010 | 194636.65 | 0
6870 | New Mexico | MCKINLEY |  | 03 | ES61190 | This project will replace the existing old bridge with a new concrete bridge. | Pavement Widening | 03/19/2010 | 03/29/2010 | 11/29/2010 | 1642344.68 | 0
6871 | New Mexico | CIBOLA |  | 02 | ES61200 | This project will replace the existing old bridge with a new concrete bridge. | Bridge Replacement | 12/28/2009 | 01/04/2010 | 05/04/2010 | 800000 | 0
6872 | New Mexico | MCKINLEY |  | 03 | ES61250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 01/13/2010 | 02/03/2010 | 04/04/2010 | 3967200.35 | 0
6873 | New Mexico | MCKINLEY |  | 03 | ES61260 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 03/16/2010 | 04/05/2010 | 06/25/2010 | 1811053.07 | 0
6874 | New Mexico | MCKINLEY |  | 03 | ES61330 | This project will replace the existing old bridge with a new concrete bridge. | Bridge Replacement | 04/06/2010 | 04/23/2010 | 09/10/2010 | 2066181.83 | 0
6875 | New Mexico | SANDOVAL |  | 01 | ESA3320 | The purpose of the project will consist of the installation of lighting between the Southern Boulevard intersection and US 550 within the City of Rio Rancho and the town of Bernalillo. The lighting w | Transportation Enhancements | 03/15/2010 | 03/25/2010 | 06/18/2010 | 854875.09 | 0
6876 | New Mexico | BERNALILLO |  | 01 | ESA3330 | The project will consist of the repaving of the Multi use trail from Central to Montgomery. The project will also consist of various improvements from Central to Tramway Terrace which include the upgr | Transportation Enhancements | 04/20/2010 | 05/05/2010 | 08/19/2010 | 763884.35 | 0
6877 | New Mexico | SAN JUAN |  | 03 | ESF1050 | The City of Aztec is developing an East Arterial to alleviate heavy truck traffic through it's Main Street (US 550). The arterial will intersect at the south end of town and will traverse east and the | Pavement Improvement | 04/05/2010 | 04/05/2010 | 10/02/2010 | 1700000 | 0
6878 | New Mexico | SAN JUAN |  | 03 | ESF1070 | This project is a widening and intersection improvements for Wildflower Parkway from Browning Parkway to Yarrow Street in Farmington that includes bike paths, new sidewalks and turning lanes. | Transportation Enhancements | 03/25/2010 | 04/12/2010 | 09/09/2010 | 1000000 | 0
6879 | New Mexico | SAN JUAN |  | 03 | ESF1080 | For reconstruction of West Maple Street in Bloomfield to include removal of existing pavement, adding curb and gutter, lighting, sidewalk, new asphalt, and removal and replacement of utilities from US | Pavement Improvement | 04/28/2010 | 05/10/2010 | 10/16/2010 | 900000 | 0
6880 | New Mexico | SANTA FE |  | 01 | ESS1010 | This project will provide landscaping of all medians on Rodeo Road from Galisteo Street to Camino Carlos Rey. | Transportation Enhancements | 09/22/2009 | 09/22/2009 | 11/30/2009 | 132313.01 | 0
6881 | New Mexico | SANTA FE |  | 01 | ESS1020 | This project will pave a small portion of the Santa Fe Rail Trail in Santa Fe County from Interstate Highway 25 southerly to Rabbit Road. | Transportation Enhancements | 04/07/2010 | 04/07/2010 | 08/13/2010 | 85529.59 | 0
6882 | New Mexico | SANTA FE |  | 02 | ESS1030 | This project will involve cold milling the existing pavement on Airport Road from Cerrillos Road to Calle Debra, inlaying a new pavement, sidewalk and Americans with Disabilities Act ramp improvements | Pavement Improvement | 05/21/2010 | 06/01/2010 | 10/30/2010 | 2000000 | 0
6883 | New Mexico | SAN JUAN |  | 02 | F100030 | A complete bridge replacement for Bridge #8116 located on San Juan County Road 2900 at mile marker 6.20 situated between the City of Aztec and the community of Cedar Hill. | Bridge Replacement | 04/05/2010 | 04/05/2010 | 08/05/2010 | 1000000 | 0
6884 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 1 | 0016263 | Completely renovating 3.5 miles of New York Route 112 in Brookhaven, Suffolk County to improve the safety for the approximately 20,000 motorists, pedestrians and bicyclists who use the roadway daily. | Pavement Improvement | 08/06/2009 | 08/06/2009 | 12/14/2011 | 37751010 | 3
6885 | New York | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 3 | 0757523 | A project to construct the ferry terminal bulkhead and make site improvements at the Glen Cove Ferry Terminal in the City of Glen Cove, Town of North Hempstead, Nassau County. | Other | 04/26/2010 | 04/26/2010 | 10/01/2010 | 10743372 | 0
6886 | New York | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 4 | 0758463 | Provide new bike lanes and improved pedestrian facilities, including new sidewalks and crosswalks, on Prospect Avenue between Brush Hollow Road and Cantiague Rock Road in New Cassel, in the Town of No | Safety/Traffic Management | 10/13/2009 | 10/13/2009 | 07/30/2010 | 5000000 | 0
6887 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2 | 0758583 | Reconstruct Walt Whitman Road in the Town of Huntington | Pavement Improvement | 10/06/2009 | 10/06/2009 | 04/29/2011 | 5436138 | 0
6888 | New York | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 2, 3, 4, 5 | 0759373 | A project to clean, paint, and thereby preserve the integrity of four bridges accessing Hempstead Lake Park in the Village of Rockville Centre, Nassau County. | Bridge Improvement | 03/31/2010 | 03/31/2010 | 07/01/2010 | 2956079 | 0
6889 | New York | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 3 | 0759383 | A project to provide safety, pavement and drainage improvements on Cedar Swamp Road in Glen Cove, Town of North Hempstead, Nassau County. | Pavement Improvement | 04/05/2010 | 04/05/2010 | 07/01/2010 | 3606831 | 0
6890 | New York | NASSAU |  | 2, 3, 4, 5 | 0759393 | Resurface select local roads in Nassau County. The existing deteriorated pavement surface will be removed and replaced with new asphalt and pavement markings. | Pavement Improvement | 08/14/2009 | 08/14/2009 | 05/31/2010 | 3536500 | 0
6891 | New York | NASSAU |  | 2, 3, 4, 5 | 0759403 | Resurface select local roads in Nassau County. The existing deteriorated pavement surface will be removed and replaced with new asphalt and pavement markings. | Pavement Improvement | 08/14/2009 | 08/14/2009 | 05/31/2010 | 3943500 | 0
6892 | New York | NASSAU |  | 2, 3, 4, 5 | 0759413 | A project to construct a seven-mile shared-use bike path in Mitchell Park, Nassau County. The new, shared-use path will provide a non-motorized transportation facility that connects multiple recreat | Transportation Enhancements | 03/01/2010 | 03/01/2010 | 07/01/2010 | 2254972 | 0
6893 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2 | 0759423 | Recondition, preserve asphalt pavement and improve drainage on Commack Road, County Road 4, between Nicolls Road and Polo Street in the towns of Babylon and Huntington, Suffolk County. | Pavement Improvement | 09/07/2009 | 09/07/2009 | 08/13/2010 | 3497737 | 0
6894 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2 | 0759433 | Rehabilitate the roadway pavement and make needed drainage improvements on County Route 67 between the Long Island Expressway (LIE/I495) and County Route 17 in the Town of Islip, Suffolk County. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 05/01/2010 | 3723129 | 3.65
6895 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 1, 2 | 0759443 | A project to remove the top layer of worn, distressed pavement on Long Island Expressway service roads between Exit 59 and 63 in the towns of Islip and Brookhaven, Suffolk County, and replace it w | Pavement Improvement | 11/30/2009 | 11/30/2009 | 06/01/2010 | 6813857 | 6.8
6896 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2 | 0759453 | A project to remove the top layer of worn, distressed pavement on Long Island Expressway service roads between Exit 54 and 59 in the towns of Islip and Brookhaven, Suffolk County, and replace it w | Pavement Improvement | 09/22/2009 | 09/22/2009 | 06/01/2010 | 7860803 | 7.5
6897 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 2, 3, 4, 5 | 0808183 | Improve roadway storm water run off, clean and repair or replace drainage basins to locations on NY25A, Nassau County, NY RT102, Nassau County, NY RT25A, Suffolk County, & Robert Moses Causeway, Suffo | Other | 08/12/2009 | 08/12/2009 | 05/24/2010 | 743417 | 0.51
6898 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 1, 2, 5 | 0808193 | Resurface approximately nine miles of State roadways in Nassau and Suffolk counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement marki | Pavement Improvement | 06/26/2009 | 06/26/2009 | 06/30/2010 | 7768550 | 7.71
6899 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 2, 3, 4 | 0808393 | Much-needed concrete pavement repairs to sections of distressed, aging roadway systems throughout Nassau and Suffolk counties to improve pavement smoothness, reduce accidents and maintain pavement int | Pavement Improvement | 06/24/2009 | 06/24/2009 | 11/17/2009 | 1894701 | 23.59
6900 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2, 3 | 0808503 | Clean the steel of 10 bridges in Babylon, Brookhaven and Islip in Suffolk County to eliminate corrosion and rust and to paint the structures. These preventative-maintenance repairs will maintain the b | Bridge Improvement | 06/15/2009 | 06/15/2009 | 12/31/2010 | 5558704 | 0
6901 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 1, 2, 3, 4 | 0808543 | Designing pavement repairs of State highways in Nassau and Suffolk counties, in the towns of Babylon, Islip, Hempstead, Riverhead, Brookhaven and North Hempstead. | Pavement Improvement | 03/05/2010 | 03/05/2010 | 12/16/2011 | 19796636 | 15.11
6902 | New York | STATEWIDE |  | 1, 2, 3, 4, 5 | 0808553 | Upgrade approximately 900 traffic signals in Nassau and Suffolk counties by replacing existing incandescent lights with more energy efficient Light Emitting Diode (LED) bulbs to reduce energy use and | Safety/Traffic Management | 08/20/2009 | 08/20/2009 | 04/25/2011 | 4795970 | 0
6903 | New York | STATEWIDE |  | 1, 2, 3, 4, 5 | 0808563 | Upgrade the outdated, 22-year-old original technology that operates 53 out of 190 motorist information signs operated by NYSDOT INFORM's transportation management center. The project will increase the | Safety/Traffic Management | 10/07/2009 | 10/07/2009 | 03/31/2011 | 2911845 | 0
6904 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 2, 3 | 0808621 | Designing pavement repairs of State highways in Nassau and Suffolk counties, targeting sections of the NY 231 and the Sagtikos Parkway. | Other | 03/18/2010 | 03/18/2010 | 01/21/2011 | 30297 | 19.5
6905 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 1 | 0808643 | Preserve the Stony Brook Mill Pond as a fragile aquatic resource and better protect motorists from roadway flooding conditions on NY Route 25A (North Country Road) in Stony Brook, Town of Brookhaven, | Other | 10/01/2009 | 10/01/2009 | 04/09/2010 | 728494 | 1.6
6906 | New York | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 1 | 0935613 | Calverton Enterprise Park Rail Spur in the Town of Riverhead. Rehabilitate Freight rail access to Calverton Industrial Park from the LIRR Main line. The rail spur is 2.3 miles from the LIRR main line | Other | 01/27/2010 | 01/27/2010 | 02/17/2012 | 4246856 | 0
6907 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1753373 | Relocate the Maxwell Road intersection with Albany Shaker Road in the town of Colonie, Albany County 800 feet to the east, away from the existing intersection. The existing intersection will remain, b | Pavement Widening | 09/23/2009 | 09/23/2009 | 11/30/2010 | 5333409 | 0
6908 | New York | STATEWIDE |  | 21 | 1754523 | A project to provide pedestrian and bicycle access to the Troy-Menands Bridge. | Transportation Enhancements | 04/09/2010 | 04/09/2010 | 12/31/2011 | 1107000 | 0.01
6909 | New York | ESSEX |  | 23 | 1755123 | Replace the bridge carrying Haselton Road over West Branch Ausable River, Town of Wilmington. | Bridge Replacement | 11/16/2009 | 11/16/2009 | 12/01/2010 | 1580480 | 0
6910 | New York | WASHINGTON |  | 20 | 1755153 | Replace the bridge carrying Clinton Street, Saunders Street and Division Street over the Delaware and Hudson Railroad in the Village of Whitehall in Washington County. This rail line serves the area a | Bridge Replacement | 09/01/2009 | 09/01/2009 | 12/31/2010 | 5167794 | 0
6911 | New York | WARREN |  | 20 | 1755213 | Replace the County Route 3/Warrensburg Road Bridge over Stony Creek in the Town of Stony Creek, Warren County. | Bridge Replacement | 06/05/2009 | 06/05/2009 | 04/30/2010 | 1458010 | 0.01
6912 | New York | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1755933 | A project to construct Spring Run Trail, a multi-use path, from Congress Park to I-87 in the City of Saratoga Springs. | Transportation Enhancements | 03/05/2010 | 03/05/2010 | 06/30/2010 | 2070003 | 0
6913 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756353 | Replace the bridge over the Fifth Branch of the Mohawk River in the City of Cohoes, Albany County. A new five-span steel bridge will be constructed on existing bridge alignment, including reconstructi | Bridge Replacement | 07/28/2009 | 07/28/2009 | 07/31/2010 | 7833000 | 0.09
6914 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756593 | Reconstruction of 19th Street in the City of Watervliet in Albany County. 19th Street carries New York State Touring Route 2 through the City between the Congress Street Bridge and the City Line and s | Pavement Improvement | 07/29/2009 | 07/29/2009 | 11/30/2010 | 6639194 | 1.17
6915 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756613 | Reconstruct Delaware Avenue for the 1.6 miles between Madison Avenue and the bridge over the New York State Thruway linking Albany and Delmar, Albany County. The project will include curb, drainage an | Pavement Improvement | 04/09/2009 | 04/09/2009 | 10/31/2010 | 15160612 | 1.63
6916 | New York | RENSSELAER | ALBANY-SCHENECTADY-TROY | 21 | 1756623 | Reconstruction of NY Route 2 from 5th Avenue to 11th Street in the City of Troy | Pavement Widening | 09/28/2009 | 09/28/2009 | 12/31/2010 | 6796680 | 0
6917 | New York | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1757073 | A bridge replacement project of County Road 43 (Geyser Road) over the D and H Railroad. | Bridge Improvement | 02/12/2010 | 02/12/2010 | 10/31/2010 | 1743000 | 0
6918 | New York | RENSSELAER |  | 20 | 1757083 | Replace the bridge carrying Caretaker Road over the Walloomsac River in the town of Hoosick, Rensselaer County. This bridge, built in 1900, accesses a historic site, the Bennington Battlefield. Withou | Bridge Replacement | 08/11/2009 | 08/11/2009 | 12/31/2009 | 1215112 | 0
6919 | New York | GREENE |  | 20 | 1757123 | Replacement of the bridge carrying New Baltimore Road over Hannacrois Creek in the Town of New Baltimore in Greene County. The existing box-beam bridge, built in 1972 and owned by Greene County, conti | Bridge Replacement | 07/29/2009 | 07/29/2009 | 12/31/2009 | 1262477 | 0.01
6920 | New York | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1757143 | Reconstruct a portion of Church Street -- State Touring Route 9N -- in the city of Saratoga Springs, Saratoga County. The project will improve Church Street between West Avenue and North Van Rensselae | Pavement Improvement | 09/11/2009 | 09/11/2009 | 07/30/2010 | 2830782 | 0
6921 | New York | WARREN |  | 20 | 1757173 | Replace the Grist Mill Road Bridge over Stony Creek in the Town of Stony Creek, Warren County. | Bridge Replacement | 06/05/2009 | 06/05/2009 | 04/30/2010 | 1017426 | 0.01
6922 | New York | ESSEX |  | 20 | 1758333 | Rehabilitation of Essex County Route 84, Blue Ridge Road, between the Adirondack Northway and State Route 28N in the towns of Newcomb, Minerva and North Hudson in Essex County. This county road, measu | Pavement Improvement | 08/04/2009 | 08/04/2009 | 08/01/2009 | 3372180 | 17.36
6923 | New York | WARREN |  | 20 | 1758613 | The second phase of the reconstruction of Bay Street in the City of Glens Falls in Warren County. This deteriorating city street is a major north-south route linking the City and the Town of Queensbur | Pavement Improvement | 08/05/2009 | 08/05/2009 | 06/30/2010 | 2889596 | 1.03
6924 | New York | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1758623 | A project to complete the Zim Smith Trail in the towns of Ballston and Malta in Saratoga County. The project will construct 2 miles of pedestrian trail and connect two existing trails between Oak St | Transportation Enhancements | 11/24/2009 | 11/24/2009 | 06/30/2010 | 669237 | 0
6925 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1758673 | Washington Avenue Pavement Resurfacing, Washington Avenue, Fuller Road to I-90, Jermain Street to North Main Avenue, Ontario Streen to Lark Street. | Pavement Improvement | 09/25/2009 | 09/25/2009 | 11/30/2009 | 2315336 | 0
6926 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1758683 | Resurfacing and American's With Disabilities Act Compliance on County Road 52, Elm Avenue, Delmar Bypass and Feura Bush Road in the Town Of Bethlehem. | Pavement Improvement | 11/05/2009 | 11/05/2009 | 11/30/2009 | 202842 | 0
6927 | New York | RENSSELAER | ALBANY-SCHENECTADY-TROY | 21 | 1758693 | Pavement Resurfacing of County Route 145, Oakwood Avenue. | Pavement Improvement | 09/25/2009 | 09/25/2009 | 11/30/2009 | 847655 | 1.32
6928 | New York | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758703 | River Road / Providence Avenue Resurfacing, River Road/Rosendale Road to General Electric Circle, General Electric Circle to Route 146, Route 146 to Schenectady City Line, Town of Niskayuna. | Pavement Improvement | 01/14/2010 | 01/14/2010 | 11/30/2009 | 1205917 | 0
6929 | New York | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758713 | Resurfacing of Rosendale Road/River Road in the Town of Niskayuna. | Pavement Improvement | 01/15/2010 | 01/15/2010 | 11/30/2009 | 313788 | 0
6930 | New York | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758723 | Pavement resurfacing of Van Vanken Avenue, Nott Street to Maxon Road in the City of Schenectady. | Pavement Improvement | 10/05/2009 | 10/05/2009 | 11/30/2009 | 1241513 | 0
6931 | New York | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1758733 | Resurface Saratoga County Route 108, Dunning Street, between State Route 9 and State Route 9P in the town of Malta, Saratoga County. The project will remove and replace deteriorating pavement and cons | Pavement Improvement | 10/07/2009 | 10/07/2009 | 11/30/2009 | 312472 | 0
6932 | New York | GREENE |  | 20 | 1758743 | Resurface Greene County Route 28, Schoharie Turnpike, between U.S. Route 9W in the town of Athens and Second Street in the village of Athens. The project will remove and replace deteriorating pavement | Pavement Improvement | 10/02/2009 | 10/02/2009 | 10/31/2009 | 400082 | 0
6933 | New York | WARREN |  | 20 | 1758753 | Road Resurfacing and Americans With Disabilities Act Compliance on County Route 34, Glenwood Avenue, Glen Street to Bay Road in the Town of Queensbury. | Pavement Improvement | 01/19/2010 | 01/19/2010 | 04/30/2010 | 186000 | 0
6934 | New York | WARREN |  | 20 | 1758763 | Resurfacing And Americans With Disabilities Act Compliance on County Route 28, Corinth Road, Indiana Avenue to Vandusen Drive in the Town of Queensbury. | Pavement Improvement | 01/19/2010 | 01/19/2010 | 04/30/2010 | 227000 | 0
6935 | New York | WASHINGTON | GLENS FALLS | 20 | 1758773 | Resurfacing project along county Route 42 (Basin Road), State Rt 196 to State R7 197. Resurfacing and Americans with disabilities Act. Town of Kingsbury and Fort Edward. | Pavement Improvement | 05/19/2010 | 05/19/2010 | 06/30/2010 | 545274 | 0
6936 | New York | WASHINGTON | GLENS FALLS | 20 | 1758783 | Sumpter and Allen Streets Resurfacing. Village of Hudson Falls. | Pavement Improvement | 05/19/2010 | 05/19/2010 | 06/30/2010 | 123000 | 0
6937 | New York | STATEWIDE |  | 21 | 1807993 | Pavement improvements on Route 5 in Albany, Schenectady and the towns of Colonie, Albany County, and Niskayuna, Schenectady County. Work also will include the installation at 159 intersections of ramp | Pavement Improvement | 09/15/2009 | 09/15/2009 | 09/15/2010 | 7618489 | 6.84
6938 | New York | STATEWIDE |  | 20, 21 | 1808173 | Resurface Albany, Rensselaer, Saratoga and Schenectady counties. Locations include: State Route 9 in Halfmoon, Clifton Park and Malta between State Route 146 and Crescent Avenue; State Route 20 in Gui | Pavement Improvement | 08/27/2009 | 08/27/2009 | 11/15/2009 | 9065733 | 24.07
6939 | New York | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1935773 | Wharf and dock repairs at the Port of Albany in the City of Albany. | Other | 12/14/2009 | 12/14/2009 | 06/30/2010 | 5021041 | 0
6940 | New York | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1941253 | Rehabilitation of the Existing Schenectady Trail | Transportation Enhancements | 11/18/2009 | 11/18/2009 | 10/29/2010 | 1380000 | 0
6941 | New York | HERKIMER |  | 24 | 2012043 | Rehabilitate the bridge carrying Route 169 over the CSX railroad and the Erie Canal in the City of Little Falls, Herkimer County. The project will include repairing deteriorated concrete and repaving | Bridge Improvement | 05/27/2009 | 05/27/2009 | 06/30/2010 | 1262528 | 0
6942 | New York | STATEWIDE |  | 21, 23, 24 | 2804843 | Paint and wash bridges carrying state highways in Oneida, Madison, Herkimer, Hamilton, Fulton and Montgomery counties. These preventative maintenance treatments will inhibit deterioration and extend t | Bridge Improvement | 04/29/2009 | 04/29/2009 | 11/30/2009 | 2119629 | 0
6943 | New York | STATEWIDE |  | 21, 23, 24 | 2804853 | Paint and wash bridges carrying state highways in Oneida, Madison, Herkimer, Hamilton, Fulton and Montgomery counties. These preventative maintenance treatments will inhibit deterioration and extend t | Bridge Improvement | 05/14/2009 | 05/14/2009 | 11/30/2009 | 314229 | 0
6944 | New York | ONEIDA | UTICA-ROME | 24 | 2804893 | Resurface Routes 5A and 69 in the City of Rome, Town of Whitestown and villages of Oriskany, Yorktown and Whitesboro in Oneida County. The project will include repaving, traffic signal replacement and | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/18/2009 | 2657494 | 14.76
6945 | New York | ONEIDA | UTICA-ROME | 24 | 2805083 | Replace the bridge joints on five structures along Interstate 790 in the City of Utica, Oneida County. This preventative maintenance project will maintain the bridges structural reliability. | Bridge Improvement | 05/19/2009 | 05/19/2009 | 11/30/2009 | 520969 | 0
6946 | New York | STATEWIDE |  | 21, 23, 24 | 2ST0043 | Paint 14 bridges, one in Fulton County, four in Herkimer County, two in Montgomery County and seven in Oneida County. The structural steel elements of each bridge will be commercially sandblasted to e | Bridge Improvement | 08/21/2009 | 08/21/2009 | 05/14/2010 | 2657480 | 0
6947 | New York | STATEWIDE |  | 21, 23, 24 | 2ST0123 | Repair or replace deficient sidewalks in 20 municipalities in Fulton, Hamilton, Herkimer, Madison, Montgomery and Oneida counties. New, concrete sidewalks will be installed and ramps will be upda | Safety/Traffic Management | 02/10/2010 | 02/10/2010 | 09/30/2010 | 2643708 | 13.99
6948 | New York | HAMILTON |  | 23 | 2ST0343 | Replace the bridge carrying Big Brook Road over Lake Abanake in the town of Indian Lake, Hamilton County. The existing structure will be replaced with a higher bridge to accommodate boat traffic in th | Bridge Replacement | 09/17/2009 | 09/17/2009 | 09/30/2010 | 694413 | 0
6949 | New York | STATEWIDE |  | 21, 23, 24 | 2ST0413 | A project to provide various safety improvements in the cities of Amsterdam, Johnstown, Gloversville, Little Falls, Oneida, Sherrill, Rome and Utica, in Montgomery, Fulton, Herkimer, Madison and Oneid | Safety/Traffic Management | 02/15/2010 | 02/15/2010 | 09/30/2010 | 550000 | 2.43
6950 | New York | STATEWIDE |  | 21, 23 | 2ST1003 | Resurface approximately three miles of Route 5S from the Herkimer County Line to Sanders Road in the town of Minden, Montgomery County and resurface approximately 5.5 miles of Route 29 from Vail Mills | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 767545 | 8.9
6951 | New York | HERKIMER | UTICA-ROME | 24 | 2ST1013 | Resurface highways in Herkimer County, including approximately 1.5 miles of Route 5S from Main Street in Frankfort to Route 51 in Ilion; approximately three miles of Route 28 from Route 8 to Comstock | Pavement Improvement | 10/05/2009 | 10/05/2009 | 07/30/2010 | 1426649 | 4.35
6952 | New York | ONEIDA | UTICA-ROME | 23, 24 | 2ST1023 | Rehabilitate several state highways in Oneida County, including resurfacing approximately 16 miles of various highways and approximately five miles of shoulders along I-790 in Oneida County. In the ur | Pavement Improvement | 10/06/2009 | 10/06/2009 | 11/30/2009 | 4428330 | 35.58
6953 | New York | STATEWIDE |  | 21, 24 | 2ST2003 | Rehabilitate pavement at 14 sites in the cities of Amsterdam, Montgomery County; Johnstown and Gloversville, Fulton County; and Little Falls, Herkimer County. Work will consist primarily of milling an | Pavement Improvement | 10/06/2009 | 10/06/2009 | 08/31/2010 | 3368195 | 0
6954 | New York | MONTGOMERY |  | 21 | 2V09513 | Resurface Route 67 through the towns of Amsterdam and Mohawk in Montgomery County. This preventive maintenance project will seal the asphalt surface to prevent water from entering cracks in the paveme | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/30/2010 | 131753 | 3.07
6955 | New York | STATEWIDE |  | 23, 24 | 2V09613 | Resurface approximately 15 miles of Routes 8, 12 and 20 through the towns of Trenton, Steuben, Forestport and Cazenovia in Oneida County and the Town of Brookfield, Madison County. This preventive mai | Pavement Improvement | 08/04/2009 | 08/04/2009 | 06/30/2010 | 963062 | 11.51
6956 | New York | STATEWIDE |  | 23, 24 | 2V09713 | Resurface approximately nine miles of Route 12B in the towns of Marshall and Kirkland, Oneida County, and the towns of Madison and Augusta, Madison County. This preventive maintenance project will sea | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/30/2010 | 553669 | 9
6957 | New York | CAYUGA |  | 24 | 3155243 | Replace two bridges on State Route 90 in Cayuga County. One bridge is over Little Salmon Creek in the Town of Genoa and the other is over Paines Creek in the Town of Ledyard. This project will remove | Bridge Replacement | 10/13/2009 | 10/13/2009 | 05/25/2010 | 3261673 | 0.01
6958 | New York | ONONDAGA |  | 25 | 3501423 | Replacement of the bridge carrying Bartell Road over Interstate 81 in the Town of Cicero, Onondaga County. The new bridge will increase safety and capacity. | Bridge Replacement | 05/21/2009 | 05/21/2009 | 01/28/2010 | 6671356 | 0.1
6959 | New York | ONONDAGA | SYRACUSE | 25 | 3601923 | Resurface almost five miles of Interstate 690 eastbound and westbound from the Teall Avenue interchange to the Interstate 481 interchange. This essential maintenance in the City of Syracuse, Onondaga | Pavement Improvement | 05/25/2009 | 05/25/2009 | 12/05/2009 | 8826956 | 11.32
6960 | New York | ONONDAGA | SYRACUSE | 25 | 3602033 | Resurface Route 20 in Madison County and Onondaga County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 06/01/2010 | 06/01/2010 | 07/28/2009 | 1213799 | 8.6
6961 | New York | OSWEGO |  | 23 | 3602043 | Paving Route 11 in the Town of Hastings, Onondaga County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/28/2009 | 303719 | 2.5
6962 | New York | TOMPKINS | ITHACA | 24 | 3602063 | Resurface Route 79 from the Tioga County line to Besner Hill in the Town of Caroline, Tompkins County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fr | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/28/2009 | 1230448 | 7
6963 | New York | TOMPKINS | ITHACA | 22, 24 | 3602073 | Resurface Route 79 through the towns of Ithaca and Enfield, Tompkins County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 06/01/2010 | 06/01/2010 | 07/28/2009 | 1080000 | 8.46
6964 | New York | OSWEGO |  | 23 | 3602106 | Paving Route 34, Cayuga County | Pavement Improvement | 06/01/2010 | 06/01/2010 | 07/28/2009 | 529000 | 3.6
6965 | New York | OSWEGO |  | 23 | 3602113 | Paving Route 104A, Cayuga County Line To Oswego County | Pavement Improvement | 06/08/2010 | 06/08/2010 | 07/28/2009 | 455000 | 2.78
6966 | New York | SENECA |  | 24 | 3602313 | Paving Route 96 to Village of Waterloo, Seneca County | Pavement Improvement | 06/15/2010 | 06/15/2010 | 07/28/2009 | 901863 | 6.24
6967 | New York | CAYUGA |  | 24 | 3602353 | Paving Route 34, County Route 43B at Venice Center to Skillet/Mosher Road. Towns of Scipio and Venice, Cayuga County | Pavement Improvement | 05/15/2010 | 05/15/2010 | 07/28/2009 | 960000 | 5.97
6968 | New York | CAYUGA |  | 24 | 3602393 | Paving Route 38, Hamlet of Cascade to Wyckoff Road, Towns of Venice & Scipio, Cayuga County | Pavement Improvement | 07/15/2010 | 07/15/2010 | 07/28/2009 | 1142203 | 6.95
6969 | New York | CORTLAND |  | 24 | 3602403 | Paving Route 11/41, City of Cortland to Village of McGraw, Town of Cortlandville, Cortland County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/28/2009 | 844908 | 5.66
6970 | New York | SENECA |  | 24 | 3602493 | Paving Route 414, Fayette South Town Line to Village of Seneca Falls, Towns of Fayette and Seneca Falls, Seneca County | Pavement Improvement | 07/01/2010 | 07/01/2010 | 07/28/2009 | 910000 | 5.79
6971 | New York | ONONDAGA |  | 25 | 3752893 | Rehabilitate the Dorwin Avenue bridge over Onondaga Creek in the City of Syracuse, Onondaga County. The bridge deck and superstructure will be removed and replaced with a new multi-girder steel supers | Bridge Improvement | 08/03/2009 | 08/03/2009 | 07/01/2010 | 1396000 | 0.02
6972 | New York | ONONDAGA | SYRACUSE | 25 | 3752983 | Reconstruct Taft Road from South Bay Road to Northern Boulevard in the town of Clay and Cicero, Onondaga County. The project will rehabilitate and widen Taft Road from South Bay Road to Church Street | Pavement Improvement | 07/06/2009 | 07/06/2009 | 12/01/2010 | 8444943 | 3.1
6973 | New York | TOMPKINS | ITHACA | 24 | 3753733 | Reconstruct County Route 121, Warren Road, from Route 13 to North Asbury Road in the Village and Town of Lansing, Tompkins County. The safety-improvement project will include new asphalt and fresh pav | Pavement Improvement | 07/09/2009 | 07/09/2009 | 09/07/2010 | 5313433 | 2.97
6974 | New York | SENECA |  | 24 | 3754223 | A project sponsored by Seneca County to replace the Brewer Road bridge over Black Brook. This project will remove this bridge from the deficient bridge inventory. | Bridge Replacement | 07/28/2009 | 07/28/2009 | 06/01/2010 | 405000 | 0
6975 | New York | SENECA |  | 24 | 3754273 | County Route 43, Dawson Corners over Boardman Creek in Seneca County. | Bridge Replacement | 02/01/2010 | 02/01/2010 | 09/16/2010 | 861000 | 0
6976 | New York | CAYUGA |  | 24 | 3754923 | A project sponsored by the Town of Mentz, Cayuga County, to replace the Haiti Road Bridge over the Seneca River. This project will remove this bridge from the deficient bridge inventory. | Bridge Replacement | 03/11/2010 | 03/11/2010 | 12/17/2010 | 1399535 | 0
6977 | New York | TOMPKINS | ITHACA | 22 | 3755043 | Replace and Upgrade the traffic signal at the College Ave/Dryden Rd Intersection, City Of Ithaca. | Safety/Traffic Management | 02/24/2010 | 02/24/2010 | 05/18/2010 | 220000 | 0
6978 | New York | STATEWIDE |  | 23, 24, 25 | 3804963 | Clean and paint nine different state bridges in Cayuga, Oswego, and Onondaga counties. This project will protect the structural integrity of the steel and improve the aesthetic appearance of each brid | Bridge Improvement | 07/23/2009 | 07/23/2009 | 11/27/2009 | 1939980 | 0.01
6979 | New York | CORTLAND |  | 24 | 3M07283 | Paving Route 222, Cortlandville, Cortland/Tompkins County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/28/2009 | 541984 | 3.5
6980 | New York | OSWEGO |  | 23 | 3M07293 | Paving Route 11, Town of Parish- Oswego County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/28/2009 | 381442 | 0
6981 | New York | CAYUGA |  | 25 | 3M07303 | Paving Route 104, Towns of Sterling & Victory, Cayuga County | Pavement Improvement | 06/15/2010 | 06/15/2010 | 07/28/2009 | 1250000 | 4
6982 | New York | OSWEGO |  | 23 | 3M07323 | Paving Route 104, Town and Village of Hannibal, Oswego County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/28/2009 | 468560 | 0
6983 | New York | OSWEGO |  | 23 | 3M07333 | Paving Route 104, Village of Hannibal, Oswego County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/28/2009 | 864098 | 3.1
6984 | New York | STATEWIDE |  | 23, 24, 25 | 3M09043 | Rehabilitate multiple state-owned bridges in Cayuga, Cortland, Onondaga, Oswego and Seneca counties. This project will improve the overall condition and safety of multiple state-owned bridges. | Bridge Improvement | 11/03/2009 | 11/03/2009 | 02/26/2010 | 2140952 | 0
6985 | New York | LIVINGSTON |  | 26 | 4005503 | Resurfacing of Route 5 from the Village of Lima to Ontario County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 206212 | 2.17
6986 | New York | LIVINGSTON |  | 26 | 4005573 | Resurfacing of Route 5 from the Village of Avon to the Village of Lima | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 531400 | 5.53
6987 | New York | MONROE | ROCHESTER | 29 | 4015343 | Resurface a portion of State Route 15 from Route 252 to I-390 in the towns of Brighton and Henrietta, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new | Pavement Improvement | 07/24/2009 | 07/24/2009 | 11/30/2009 | 2077780 | 1.8
6988 | New York | WYOMING |  | 26 | 4019563 | Resurfacing of Route 19 from Route 78 to Route 19a - Town of Gainseville | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 275426 | 2.03
6989 | New York | ONTARIO |  | 29 | 4021223 | Resurfacing of Route 21 from Route 332 to Route 96 - City of Canandaigua | Pavement Improvement | 05/01/2010 | 05/01/2010 | 06/30/2010 | 861000 | 7.2
6990 | New York | ONTARIO |  | 29 | 4021243 | Resurfacing of Route 21 from Griesha Hill Road to Bopple Hill Road | Pavement Improvement | 05/01/2010 | 05/01/2010 | 06/30/2010 | 615000 | 10.92
6991 | New York | MONROE | ROCHESTER | 28 | 4031393 | Replace the Route 31F bridge over Irondequoit Creek in the Town of Perinton. (BIN 1022120) | Bridge Replacement | 12/17/2009 | 12/17/2009 | 12/30/2010 | 1218000 | 0
6992 | New York | ORLEANS |  | 26 | 4031763 | Resurfacing of Route 31 from Niagara County to Salt Works Road | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 269285 | 2.4
6993 | New York | MONROE | ROCHESTER | 28, 29 | 4031793 | Resurface a portion of State Route 31F from Route 250 in the village of Fairport to the Wayne County line in the town of Perinton, Monroe County. The top layer of worn, deteriorated pavement will be r | Pavement Improvement | 09/10/2009 | 09/10/2009 | 10/29/2009 | 1196861 | 3.78
6994 | New York | WAYNE |  | 25, 29 | 4031823 | RESURFACING OF VARIOUS FA ROUTES REGIONWIDE RT 31 | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 658620 | 7.56
6995 | New York | LIVINGSTON |  | 26 | 4036173 | Construction of a Genesee Valley Greenway Trail bridge over the Genesee River at Route 36 in the towns of Mt. Morris and Leicester, Livingston County. This new pedestrian bridge will make continuous a | Bridge Improvement | 08/12/2009 | 08/12/2009 | 12/31/2010 | 1884379 | 0
6996 | New York | LIVINGSTON |  | 26 | 4036183 | Resurface a portion of State Route 36 from the Steuben County line to Route 63 and from Route 63 to Route 436 in town of Dansville, Livingston County. The top layer of worn, deteriorated pavement will | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/19/2009 | 664113 | 2.32
6997 | New York | LIVINGSTON |  | 26 | 4036213 | Resurfacing of Route 36 from Route 20 to Route 5 | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 592182 | 7.38
6998 | New York | WYOMING |  | 26 | 4039493 | Install edge drain on State Route 39 from Route 98 to Eagle Road in towns of Arcade and Eagle, Wyoming County. Edge drain will improve the proper draining of storm-water runoff and aid in prevention o | Pavement Improvement | 05/26/2009 | 05/26/2009 | 07/10/2009 | 676473 | 6.19
6999 | New York | WYOMING |  | 26 | 4039523 | Resurfacing of Route 39, Wyoming County | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 550525 | 5.65
7000 | New York | MONROE | ROCHESTER | 29 | 4064103 | Resurfacing of Route 64 from Route 5 & 20 in Ontario/Monroe County | Pavement Improvement | 05/01/2010 | 05/01/2010 | 08/30/2010 | 679000 | 14.45
7001 | New York | ONTARIO |  | 29 | 4064113 | Resurfacing of Route 64 from Dugway Road To Route 5&20 | Pavement Improvement | 07/16/2009 | 07/16/2009 | 10/30/2009 | 671961 | 7.01
7002 | New York | GENESEE |  | 26 | 4077063 | Resurface a portion of State Route 77 from Route 20 to Route 5 and on Route 5 from Route 33 to the Corfu village line in the towns of Darien and Pembroke and the village of Corfu, Genesee County. The | Pavement Improvement | 05/26/2009 | 05/26/2009 | 12/14/2009 | 3205000 | 16.04
7003 | New York | WAYNE |  | 25, 26 | 4088183 | Resurfacing of Route 88 from Village of Newark to Route 104 | Pavement Improvement | 08/04/2009 | 08/04/2009 | 10/30/2009 | 393185 | 12.25
7004 | New York | MONROE | ROCHESTER | 29 | 4096513 | Resurface a portion of State Route 96 from Kreag Road in the town of Perinton, Monroe County, to Route 64 in the town of Pittsford, Monroe County. The top layer of worn, deteriorated pavement will be | Pavement Improvement | 08/03/2009 | 08/03/2009 | 11/19/2009 | 1002454 | 2.61
7005 | New York | ONTARIO |  | 29 | 4096523 | Resurface a portion of State Route 96 from Rt. 88 to Lester Road in the village of Phelps, Ontario County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt an | Pavement Improvement | 07/23/2009 | 07/23/2009 | 09/03/2009 | 374949 | 1.8
7006 | New York | GENESEE | ROCHESTER | 26 | 4098393 | Repave Rt. 98 between Rt. 5 (Main St.) and Noonan Drive in the City of Batavia, Genesee County. | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/18/2009 | 529281 | 1.18
7007 | New York | MONROE | ROCHESTER | 26 | 4104423 | Resurface a portion of State Route 104 from Route 259 to Route 261 in the towns of Greece and Parma, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new a | Pavement Improvement | 07/14/2009 | 07/14/2009 | 10/12/2009 | 1320000 | 2.01
7008 | New York | WYOMING |  | 26 | 4246083 | Resurfacing of Route 246 from Route 39 to the North Village Line | Pavement Improvement | 08/05/2009 | 08/05/2009 | 10/30/2009 | 136309 | 1.01
7009 | New York | LIVINGSTON |  | 26 | 4256063 | Paving on Route 256 from Sliker Hill Road to Route 20A | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 1074321 | 9.83
7010 | New York | MONROE | ROCHESTER | 26 | 4259063 | Resurface a portion of State Route 259 from Colby Street to Big Ridge Road in town of Ogden and village of Spencerport, Monroe County. The top layer of worn, deteriorated pavement will be removed and | Pavement Improvement | 06/25/2009 | 06/25/2009 | 10/29/2009 | 1406970 | 1.67
7011 | New York | MONROE | ROCHESTER | 26 | 4261063 | Resurfacing of Route 261 from Route 104 to Route 18 | Pavement Improvement | 07/16/2009 | 07/16/2009 | 10/30/2009 | 249623 | 2.62
7012 | New York | GENESEE |  | 26 | 4262063 | Resurfacing of Route 262 from Route 98 to Route 237 | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 502595 | 6.51
7013 | New York | ONTARIO | ROCHESTER | 29 | 4332053 | Repave Rt. 332 from Rt. 5 & 20 to Chapel Street in the City of Canandaigua, Ontario County. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 10/31/2009 | 1825407 | 3.42
7014 | New York | WYOMING |  | 26 | 4354063 | Resurfacing of Route 354 from Erie County Line to Route 98 | Pavement Improvement | 07/16/2009 | 07/16/2009 | 10/30/2009 | 1111548 | 11.21
7015 | New York | ONTARIO |  | 29 | 4364023 | Resurfacing of Route 364 from Gateway Road to Route 5/20 | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 365998 | 5.29
7016 | New York | MONROE | ROCHESTER | 29 | 4390553 | Resurface a portion of Interstate 390 from the New York State Thruway to the interchange of Interstate 590 in the town of Henrietta, Monroe County. The top layer of worn, deteriorated pavement will be | Pavement Improvement | 08/25/2009 | 08/25/2009 | 08/30/2010 | 2200248 | 5.07
7017 | New York | ONTARIO |  | 29 | 4488043 | Resurfacing of Route 488 from Route 21 To Route 96, Ontario County. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 10/30/2009 | 265423 | 9.13
7018 | New York | MONROE | ROCHESTER | 26, 29 | 4531063 | Resurface a portion of State Route 531 from Route 36 in the town of Ogden, Monroe County, to I-490 in the town of Gates, Monroe County. The top layer of worn, deteriorated pavement will be removed and | Pavement Improvement | 07/07/2009 | 07/07/2009 | 11/20/2010 | 2125400 | 7.56
7019 | New York | STATEWIDE | ROCHESTER | 25, 26, 28, 29 | 4805653 | Apply a preventative maintenance treatment to seal cracks in the pavement along various state highways in Genesee and Monroe counties. This type of work keeps the highway system in a state of good rep | Pavement Improvement | 07/16/2009 | 07/16/2009 | 03/10/2010 | 263924 | 0
7020 | New York | STATEWIDE | ROCHESTER | 25, 26, 28, 29 | 4805693 | Wash bridges and seal bridge decks at selected locations in Wayne, Ontario, Monroe, Livingston, Orleans, Genesee and Wyoming counties. This type of work keeps the system in a state of good repair. | Bridge Improvement | 07/27/2009 | 07/27/2009 | 08/26/2009 | 433412 | 0
7021 | New York | STATEWIDE | ROCHESTER | 25 | 4805733 | Regionwide Resurfacing Of Rural/Low Volume Highways | Pavement Improvement | 05/01/2010 | 05/01/2010 | 10/30/2009 | 569000 | 0
7022 | New York | MONROE | ROCHESTER | 26, 28 | 4947213 | Resurfacing of Route 947A -Lake Ontario State Parkway | Pavement Improvement | 05/01/2010 | 05/01/2010 | 08/30/2010 | 864000 | 6.79
7023 | New York | GENESEE |  | 26 | 4LS0003 | A Genesee County project to resurface a portion of Batavia-Stafford Town Line Road from Route 33 to Assemblyman R. Steven Hawley Drive, and a portion of Assemblyman R. Steven Hawley Drive from Bank St | Pavement Improvement | 08/01/2009 | 08/01/2009 | 12/30/2009 | 325000 | 0
7024 | New York | LIVINGSTON |  | 26 | 4LS0023 | A Livingston County project to resurface a portion of Sliker Hill Road from Route 256 to Route 15 in the town of Conesus, and a portion of Perry Road from Route 36 to Route 20A in the town of Leiceste | Pavement Improvement | 08/05/2009 | 08/05/2009 | 12/31/2009 | 1601700 | 0
7025 | New York | LIVINGSTON |  | 26 | 4LS0043 | A village of Dansville project to resurface a portion of Maple Avenue from Route 63 to Route 36 in the village of Dansville, Livingston County. The top layer of worn, deteriorated pavement will be rem | Pavement Improvement | 09/10/2009 | 09/10/2009 | 12/30/2009 | 370500 | 0
7026 | New York | LIVINGSTON |  | 26 | 4LS0073 | A village of Geneseo project to resurface a portion of Lima Road from North Street to Geneseo village line in the village of Geneseo, Livingston County. The top layer of worn, deteriorated pavement wi | Pavement Improvement | 09/09/2009 | 09/09/2009 | 12/30/2009 | 285000 | 0
7027 | New York | MONROE | ROCHESTER | 28 | 4LS0083 | Upgrade bridges on Driving Park, East Main Street, Main Street, Court Street, Elmwood Avenue, Lake Avenue, Andrews Street and Ford Street in the City of Rochester, Monroe County, with appropriate prev | Bridge Improvement | 07/20/2009 | 07/20/2009 | 01/06/2010 | 1442500 | 0
7028 | New York | MONROE | ROCHESTER | 28, 29 | 4LS0153 | A city of Rochester project to resurface a portion of Thurston Road from Brooks Avenue to Chili Avenue in the city of Rochester, Monroe County. A thin layer of asphalt will be placed on top of the exi | Pavement Improvement | 11/24/2009 | 11/24/2009 | 06/30/2010 | 1916000 | 0
7029 | New York | MONROE | ROCHESTER | 28 | 4LS0163 | A City of Rochester project to reconstruct a portion of East Henrietta Road from Mount Hope Avenue to the Erie Canal in the city of Rochester, Monroe County. The existing pavement will be complete | Pavement Improvement | 04/08/2010 | 04/08/2010 | 08/30/2010 | 1820000 | 0
7030 | New York | MONROE |  | 28 | 4LS0223 | A city of Rochester project to resurface Byron Street from South Avenue to S. Clinton Avenue in the city of Rochester, Monroe County. The top layer of worn, deteriorated pavement will be removed and r | Pavement Improvement | 04/13/2010 | 04/13/2010 | 01/06/2010 | 2549000 | 0
7031 | New York | MONROE | ROCHESTER | 28 | 4LS0263 | A city of Rochester project to replace sections of hazardous sidewalks in multiple locations within the city limits, Monroe County. Replacing sidewalks that are in disrepair will improve the service l | Transportation Enhancements | 02/03/2010 | 02/03/2010 | 08/30/2010 | 978000 | 0
7032 | New York | MONROE | ROCHESTER | 28 | 4LS0273 | Streetscape Enhancements on North Clinton Avenue | Other | 09/30/2009 | 09/30/2009 | 06/30/2010 | 1716000 | 0
7033 | New York | MONROE | ROCHESTER | 26, 28, 29 | 4LS0323 | A Monroe County project to resurface Chili Center Coldwater Road from Route 33A to Westside Drive in the town of Chili, Elmgrove Road from Route 33 to Route 531 in the town of Gates, North Greece Road | Pavement Improvement | 08/25/2009 | 08/25/2009 | 06/30/2010 | 3555000 | 0
7034 | New York | MONROE |  | 25, 26 | 4LS0343 | Resurface various roads owned by Monroe County including: Dewey Avenue, Long Pond Road, English Road, East Ridge Road, North Goodman Street, Thomas Avenue, Culver Road, Panorama Trail, and Old Ridge R | Pavement Improvement | 07/29/2009 | 07/29/2009 | 12/30/2009 | 6104500 | 0
7035 | New York | MONROE | ROCHESTER | 28 | 4LS0363 | Preventative maintenance projects on Monroe County bridges. The Flynn Road bridge in the town of Greece and the Brick School House bridge in the town of Hamlin will be deck sealed; the Redman Road and | Bridge Improvement | 09/23/2009 | 09/23/2009 | 12/31/2009 | 323308 | 0
7036 | New York | MONROE | ROCHESTER | 25 | 4LS0633 | A Monroe County project to replace signs in various municipalities around the County. | Other | 02/10/2010 | 02/10/2010 | 06/30/2010 | 300000 | 0
7037 | New York | ONTARIO |  | 29 | 4LS0653 | A city of Canandaigua project to resurface a portion of Lakeshore Drive from Muar Street to S. Main Street in the city of Canandaigua, Ontario County. The top layer of worn, deteriorated pavement will | Pavement Improvement | 09/03/2009 | 09/03/2009 | 12/30/2009 | 159726 | 0
7038 | New York | ONTARIO | ROCHESTER | 29 | 4LS0663 | A city of Canandaigua project to replace the West Avenue Bridge over Sucker Brook in the city of Canandaigua, Ontario County. | Bridge Replacement | 09/03/2009 | 09/03/2009 | 08/30/2010 | 556600 | 0
7039 | New York | ONTARIO |  | 29 | 4LS0673 | An Ontario County project to resurface County Road 41 from State Route 332 to County Road 8 in the town of Farmington, Bankert Road from State Route 96 to County Road 13 in the town of Phelps and Coun | Pavement Improvement | 08/20/2009 | 08/20/2009 | 12/30/2009 | 2790000 | 0
7040 | New York | ORLEANS |  | 25 | 4LS0703 | An Orleans County project to replace signs in various municipalities around the county. | Other | 07/28/2009 | 07/28/2009 | 12/30/2009 | 200000 | 0
7041 | New York | WAYNE |  | 25 | 4LS0713 | A town of Arcadia to locally administer a project to make element-specific repairs to the Van Buren Street Bridge over CSX Railroad in the town of Arcadia, Wayne County. The deck will be sealed and wo | Bridge Improvement | 08/25/2009 | 08/25/2009 | 06/30/2010 | 345000 | 0
7042 | New York | WAYNE |  | 25 | 4LS0723 | Resurface a portion of Lake Bluff Road from Route 104 to Ridge Road in the town of Sodus, Wayne County and a portion of Newark Marion Road from Lyon Road to the gravel pit in the town of Palmyra, Wayn | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/30/2009 | 177000 | 0
7043 | New York | WAYNE |  | 25 | 4LS0743 | A Wayne County project to resurface a portion of Ridge Road from East Williamson hamlet to Van Slyke Road in the town of Sodus, Wayne County. The top layer of worn, deteriorated pavement will be remov | Pavement Improvement | 02/02/2010 | 02/02/2010 | 08/30/2010 | 418000 | 0
7044 | New York | WAYNE |  | 25 | 4LS0753 | A Wayne County project to replace the bridge deck on the Christian Holler Road bridge over Salmon Creek in the town of Sodus, Wayne County. | Bridge Improvement | 12/01/2009 | 12/01/2009 | 06/30/2010 | 225000 | 0
7045 | New York | WAYNE |  | 25 | 4LS0763 | Resurface a portion of Atlantic Avenue from Downs Road to Route 350 in the town of Walworth, Wayne County. The top layer of worn, deteriorated pavement will be removed and replaced with new surface an | Pavement Improvement | 08/04/2009 | 08/04/2009 | 12/30/2009 | 87153 | 0.65
7046 | New York | WAYNE |  | 25 | 4LS0773 | A town of Williamson project to replace the sidewalks on Ridge Road in the hamlet of Williamson, Wayne County. Replacing sidewalks that are in disrepair will improve the service life and provide a bet | Transportation Enhancements | 01/04/2010 | 01/04/2010 | 06/30/2010 | 90000 | 0
7047 | New York | WAYNE |  | 25 | 4LS0783 | A village of Palmyra project to reconstruct a portion of Route 21 (Canandaigua Street) from southern village line to Route 31 in the village of Palmyra, Wayne County. The existing pavement will be | Pavement Improvement | 02/01/2010 | 02/01/2010 | 08/30/2010 | 1846689 | 0
7048 | New York | WYOMING |  | 26 | 4LS0793 | Resurface a portion of Bixby Hill Road from Route 39 to the Cattaraugus county line in the town of Arcade, Wyoming County. The top layer of worn, deteriorated pavement will be removed and replaced wit | Pavement Improvement | 06/25/2009 | 06/25/2009 | 12/30/2009 | 697382 | 1
7049 | New York | MONROE | ROCHESTER | 28 | 4LS0893 | A city of Rochester to locally administer a preventative maintenance project to paint and deck seal the Lake Avenue Bridge over CSX Railroad in the city of Rochester, Monroe County. Painting and s | Bridge Improvement | 10/08/2009 | 10/08/2009 | 06/30/2010 | 80000 | 0
7050 | New York | LIVINGSTON |  | 26 | 4LS0923 | Highway Preventative Maintenance, County Road 10, Geneseo Village Line to Maple Beach Road (County Road 44) in the Towns of Geneseo and Groveland, Livingston County. | Pavement Improvement | 06/08/2010 | 06/08/2010 | 08/30/2010 | 2142000 | 0
7051 | New York | MONROE | ROCHESTER | 25, 28, 29 | 4LSA303 | Resurface various roads owned by Monroe County including: Brighton-Henrietta Town Line Road, South Winton Road, Calkins Road, Creek Street, Whalen Road, Five Mile Line Road, Whitney Road, Philips Road | Pavement Improvement | 07/31/2009 | 07/31/2009 | 06/30/2010 | 5630000 | 0
7052 | New York | MONROE | ROCHESTER | 25, 26, 28, 29 | 4T47103 | Install detectable warning fields at more than 800 locations across the seven-county region. The installation of plastic tiles containing raised bumps will help alert pedestrians with visual impairmen | Other | 08/11/2009 | 08/11/2009 | 08/30/2010 | 305913 | 0
7053 | New York | CATTARAUGUS |  | 29 | 5006743 | Rehabilitate approximately 6.5 miles of Interstate 86 eastbound in the towns of Randolph and Cold Springs and the village of Randolph, all in Cattaraugus County. The project is addressing deterioratin | Other | 07/31/2009 | 07/31/2009 | 01/29/2010 | 1018824 | 6.31
7054 | New York | CHAUTAUQUA |  | 27 | 5006753 | Rehabilitate approximately 12 miles of Interstate 86 in the Towns of Sherman, North Harmony, and Ellery, in Chautauqua County. Eleven miles eastbound and 1 mile westbound will be improved. | Pavement Improvement | 09/09/2009 | 09/09/2009 | 01/31/2011 | 2800000 | 11.63
7055 | New York | CATTARAUGUS |  | 29 | 5017283 | Replace two culverts on NY Route 242 in the towns of Ellicottville and Little Valley, Cattaraugus County. This project will eliminate culvert deficiencies and ensure good structural condition. | Other | 06/23/2009 | 06/23/2009 | 10/31/2009 | 1269919 | 0
7056 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5019233 | Repave two sections of NY Route 265 (Military Road) in Erie County. Section 1 is .4 miles in length and extends from Fletcher Street to Tonawanda Creek in the city of Tonawanda, Erie County. Section 2 | Pavement Improvement | 08/21/2009 | 08/21/2009 | 01/29/2010 | 1248149 | 1.94
7057 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5050963 | A bridge replacement project in the city of Niagara Falls of I-190 over the LaSalle arterial ramps. The project also includes repaving and guiderail improvements on I-190. | Pavement Improvement | 02/26/2010 | 02/26/2010 | 09/26/2012 | 4072362 | 0.77
7058 | New York | CHAUTAUQUA |  | 27 | 5058393 | Conduct a bridge replacement and highway resurfacing and reconstruction project in the city of Jamestown, Chautauqua County. The objective of the project is to replace the Washington Street Bridge ove | Bridge Replacement | 10/06/2009 | 10/06/2009 | 12/30/2010 | 4011173 | 0.5
7059 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5086283 | A project to reconstruct into a modern roundabout the intersection of State Route 324 (Grand Island Boulevard) and Stahley Road in the Town of Grand Island, Erie County. The project will address safe | Pavement Improvement | 03/03/2010 | 03/03/2010 | 03/23/2011 | 2186800 | 0
7060 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5101793 | Repair culverts on US Route 219 and NY Route 400 in the towns of Boston and Concord, Erie County. This preventative maintenance work will eliminate corrosion and restore drainage elements to a state o | Other | 05/22/2009 | 05/22/2009 | 12/29/2009 | 826961 | 4.7
7061 | New York | CHAUTAUQUA |  | 27 | 5111903 | Replace the bridge for NY Route 20 over Bell Creek in the Town of Westfield, Chautauqua County. The existing bridge will be replaced with 3-side precast concrete bridge. | Bridge Replacement | 01/04/2010 | 01/04/2010 | 10/15/2010 | 1042868 | 0
7062 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5470243 | Rehabilitate the stone facade of a notable bridge carrying NY Route 198, the Scajaquada Expressway, over NY Route 384 in the City of Buffalo, Erie County. The bridge is located in the historic site of | Bridge Replacement | 08/03/2009 | 08/03/2009 | 08/30/2010 | 2383814 | 0
7063 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5512463 | Route 33 Retaining Wall Railing and Corridor Enhancements | Other | 10/23/2009 | 10/23/2009 | 12/15/2010 | 3990004 | 2.75
7064 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5580393 | Replace two highway ramp bridges at the Interstate I-190/ I-290 interchange in the Town of Tonawanda, Erie County. New bridges will be installed on new alignments to the north of the existing bridges, | Bridge Replacement | 11/06/2009 | 11/06/2009 | 12/30/2011 | 1830426 | 0
7065 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26 | 5755473 | Reconstruct Maple Road for 1.6 miles from Route 62 to Flint Road -- the entrance to State University of New York at Buffalo -- in the Town of Amherst, Erie County. The project will also reconstruct a | Pavement Improvement | 08/20/2009 | 08/20/2009 | 07/24/2011 | 7000000 | 0.43
7066 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5755993 | Construct four new local roads in support of the Inner Harbor Redevelopment Plan, City of Buffalo, Erie County. The four roads are Lloyd, Hanover, Perry, and Prime Slip. | New Construction | 09/22/2009 | 09/22/2009 | 12/18/2011 | 1900000 | 0
7067 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5756293 | A pavement resurfacing project including sidewalk and snow storage improvement on Porter Avenue in the city of Buffalo. | Pavement Improvement | 05/03/2010 | 05/03/2010 | 12/15/2010 | 850000 | 0
7068 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5757173 | A roadway reconstruction project on portions of 10th Street and Cedar Avenue in the city of Niagara Falls. | Pavement Improvement | 04/12/2010 | 04/12/2010 | 10/15/2011 | 1330000 | 0
7069 | New York | STATEWIDE |  | 26 | 5757213 | Replace the Cedar Street Bridge over Tonawanda Creek in the town of Newstead, Erie County, and the town of Royalton, Niagara County. The bridge is in poor condition and will be reconstructed so that i | Bridge Replacement | 08/11/2009 | 08/11/2009 | 06/15/2011 | 2055000 | 0
7070 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5757223 | A bridge replacement project of Drum Seaman Road over Johnson Creek in the town of Hartland. | Bridge Replacement | 02/16/2010 | 02/16/2010 | 12/15/2010 | 790000 | 0
7071 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5757823 | Repave portions of three local streets in the city of Buffalo, Erie County, to address deteriorating pavement conditions. The streets are: Grant Street, Amherst Street, and Hertel Avenue. | Pavement Improvement | 02/11/2010 | 02/11/2010 | 12/15/2010 | 460000 | 0
7072 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5758893 | Repave a 2.2 mile section of South Park Avenue, from Bailey Avenue to the Buffalo city line, in the city of Buffalo, Erie County. Sidewalks and lighting will also be improved along this corridor. | Transportation Enhancements | 04/12/2010 | 04/12/2010 | 12/15/2010 | 1125000 | 0
7073 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27, 28 | 5759143 | A project to conduct sidewalk and curb replacement along nine local streets in the City of Buffalo, Erie County. The streets are: Abbott Street from Cazenovia Street to Red Jacket Street; Austin Stre | Transportation Enhancements | 05/07/2010 | 05/07/2010 | 12/15/2010 | 405000 | 0
7074 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27, 28 | 5759153 | A project to repave nine local streets in the city of Buffalo, Erie County, to address deteriorating pavement conditions. The streets are: Abbott Street from Cazenovia Street to Red Jacket Street; Aus | Pavement Improvement | 02/11/2010 | 02/11/2010 | 12/15/2010 | 1250000 | 0
7075 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759213 | Repave 1.6 miles of Main Street (NY Route 104) from Ontario Street to Pierce Street in the city of Niagara Falls, Niagara County ( Main Street, Walnut Avenue to Ontario Avenue; 11th Street, Lockport S | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/15/2009 | 950694 | 0
7076 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759223 | Repave 0.4 miles of Packard Road from Niagara Falls Bou levard to the CSX Bridge in the City of Niagara Falls, Niagara County. The project will address deteriorating pavement conditions. | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/15/2009 | 952000 | 0
7077 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759233 | Repave 1.6 miles of Pine Avenue US Route 62 to Main Street (NY Route 104) in the city of Niagara Falls, Niagara County. The project will address deteriorating pavement conditions. | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/15/2009 | 1441000 | 0
7078 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759243 | Repave a two-mile section of Townline Road from Beach Ridge Road to the Bridge Over Bull Creek in the towns of Pendleton and Wheatfield in Niagara County to address deteriorating pavement conditions. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 07/15/2010 | 2064253 | 1.7
7079 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759253 | Conduct guide rail end replacements at approximately 50 locations throughout Niagara County to meet current federal standards. | Other | 08/10/2009 | 08/10/2009 | 08/15/2010 | 141160 | 0
7080 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759263 | Repave a 3.1 mile section of Hartland Road, from Townline Road to Lake Road (NY Route 18), in the town of Somerset, Niagara County. The roadway will be paved to address deteriorating pavement conditio | Pavement Improvement | 08/10/2009 | 08/10/2009 | 08/15/2010 | 401627 | 2.95
7081 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759273 | Repave a one-mile section of Nash Road from Cherry Hill Road to Steig Road in the town of Wheatfield, Niagara County. The paving address deteriorating pavement conditions. | Pavement Improvement | 08/10/2009 | 08/10/2009 | 08/15/2011 | 558000 | 0.93
7082 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759283 | Improve storm water management along Tonawanda Creek Road in the Town of Pendleton, Niagara County. | Other | 08/10/2009 | 08/10/2009 | 08/15/2011 | 82733 | 1.81
7083 | New York | CHAUTAUQUA |  | 27 | 5759293 | Repave 4.1 miles of NY Route 430 from County Route 128/44 to County Route 13 in the Town of Ellery, Chautauqua County. The project will address deteriorating pavement conditions. | Pavement Improvement | 10/20/2009 | 10/20/2009 | 12/15/2009 | 877000 | 0
7084 | New York | CHAUTAUQUA |  | 27 | 5759303 | Repave 5.6 miles of Hunt Road (County Route 82/32) from County Route 43 to the Jamestown city line in the towns of Busti, Ellicott, and North Harmony, in Chautauqua County. The project will address de | Pavement Improvement | 10/06/2009 | 10/06/2009 | 01/06/2010 | 1099696 | 0
7085 | New York | CATTARAUGUS |  | 29 | 5759313 | Repave 1.7 miles of State Route 417 (West State Street) from the Olean city line to State Route 16 in the City of Olean, Cattaraugus County. The project will address deteriorating pavement conditions. | Pavement Improvement | 10/20/2009 | 10/20/2009 | 06/30/2010 | 896000 | 1.7
7086 | New York | CHAUTAUQUA |  | 27 | 5759323 | Repave 0.2 miles of Doughty Street from the NY Route 60 to Lincoln Avenue in the City of Dunkirk, Chautauqua County. The project will address deteriorating pavement conditions. | Pavement Improvement | 10/19/2009 | 10/19/2009 | 06/30/2010 | 433635 | 0
7087 | New York | CATTARAUGUS |  | 29 | 5759343 | Repave 1.2 miles of County Route 4 (Broadway Road) in the Town of Persia. Repave 2.84 miles of CR 83 (Old Buffalo Road)and 0.9 miles of CR19 (Five Mile Road) in Town of Allegany,Cattaraugus County. Th | Pavement Improvement | 09/03/2009 | 09/03/2009 | 11/01/2009 | 1081500 | 0
7088 | New York | CATTARAUGUS |  | 29 | 5759363 | Repave 2.1 miles of NY Route 417 (Wildwood Avenue) from Linwood Avenue to the east City line in the City of Salamanca, Cattaraugus County. The project will address deteriorating pavement conditions. | Pavement Improvement | 09/10/2009 | 09/10/2009 | 12/15/2009 | 1210000 | 0
7089 | New York | CHAUTAUQUA |  | 27 | 5759413 | Enhancement project that will construct a two-classroom building for traffic and personal safety instruction at the Chautauqua Children's Safety Education Village in the town of North Harmony, Chautau | Transportation Enhancements | 09/15/2009 | 09/15/2009 | 08/15/2011 | 1760000 | 0
7090 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5759433 | UNION SHIP CANAL PROMEMADE - IMPROVE WESTERN END OF UNION SHIP CANAL. CONSTRUCT BOARDWALK AND PROMENADE WITH BENCHES, ARCHITECTUAL LIGHTING, FISH CLEANING TABLES AND RAISED LETTERING INFORMATIONAL DIS | Transportation Enhancements | 04/06/2010 | 04/06/2010 | 12/15/2010 | 2000000 | 0
7091 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26, 28 | 5759523 | A project to upgrade and repair bridge joints on six bridges in the towns of Lockport, Newfane, Niagara, Pendleton, Wilson, and Wheatfield. | Bridge Improvement | 05/01/2010 | 05/01/2010 | 01/15/2011 | 185000 | 0
7092 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5805903 | Replace nine traffic signals and 41 pedestrian signals at various locations in Erie County. | Other | 08/21/2009 | 08/21/2009 | 12/31/2010 | 891570 | 0
7093 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5806113 | Replace selected signs on state highways throughout the City of Buffalo, towns of Amherst and Cheektowaga and Village of Williamsville, Erie County. | Other | 07/03/2009 | 07/03/2009 | 08/23/2010 | 397000 | 0
7094 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 28 | 5807623 | Repair and replace bridge joints along Interstate 290 in the towns of Tonawanda and Amherst, Erie County. Joints require periodic repair to prevent water from penetrating onto other bridge elements, | Bridge Improvement | 10/23/2009 | 10/23/2009 | 11/15/2010 | 200000 | 0
7095 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27, 28 | 5807653 | Paint eight bridges in various locations in the city of Buffalo and town of Tonawanda, Erie County. The bridge painting is preventive maintenance. | Bridge Improvement | 08/13/2009 | 08/13/2009 | 06/03/2011 | 537000 | 0
7096 | New York | STATEWIDE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5807683 | A project to paint and seal eight bridges in Erie and Niagara counties. Painting bridges and sealing their supportive members and decks is preventive maintenance done to keep water from penetra | Bridge Improvement | 01/18/2010 | 01/18/2010 | 03/02/2011 | 1000000 | 0
7097 | New York | STATEWIDE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5808233 | Install approximately 285 detectable warnings at various locations in the city of Buffalo and the town of Cheektowaga in Erie County, and the city of Niagara Falls and the town of Wheatfield in Niagar | Transportation Enhancements | 08/21/2009 | 08/21/2009 | 01/11/2010 | 263066 | 0
7098 | New York | CATTARAUGUS |  | 29 | 5810433 | Resurface approximately three miles of pavement on US Route 219 and NY Route 417 in the City of Salamanca, Cattaraugus County, and Allegany Reservation of the Seneca Nation of Indians. The top layer o | Pavement Improvement | 07/02/2009 | 07/02/2009 | 09/30/2009 | 978714 | 6.24
7099 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5810463 | Mill and repave highway access ramps with a single course overlay. Ramp locations, all in Erie County, include: N.Y. Route 78 in the towns of Clarence and Amherst, N.Y. Route 263 in the town of Amhers | Other | 07/23/2009 | 07/23/2009 | 10/19/2009 | 474226 | 1.46
7100 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27 | 5810473 | Resurface approximately 1.5 miles of pavement on NY Route 78 in the Village of Depew and towns of Lancaster and Cheektowaga, Erie County. The top layer of worn, deteriorated pavement will be removed a | Pavement Improvement | 05/28/2009 | 05/28/2009 | 10/22/2009 | 726874 | 1.44
7101 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5810513 | Repave Route 957A, Robert Moses Parkway, from Interstate 190 to JB Daly Boulevard in the City of Niagara Falls, Niagara County. The top layer of worn, deteriorated pavement will be removed and replace | Pavement Improvement | 07/23/2009 | 07/23/2009 | 12/10/2009 | 1172173 | 3.23
7102 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5810563 | Clean and repair closed drainage systems along State Routes 198, 78, 277, 5 and 425 in the towns of Tonawanda, Amherst and Clarence and the city of Buffalo, Erie County. Collapsed drainage structures | Other | 08/06/2009 | 08/06/2009 | 12/29/2009 | 261041 | 5.04
7103 | New York | STATEWIDE |  | 26, 27, 28, 29 | 5810613 | Replace two overhead sign structures on State Route 400 in the towns of West Seneca and Elma and also install a 511 system signage region-wide. 511 is the state's latest traveler-advisory system. With | Other | 08/12/2009 | 08/12/2009 | 06/15/2010 | 528419 | 0
7104 | New York | ERIE |  | 27, 28 | 5810623 | Replace joints on various bridges along the NY Route 33 corridor in the city of Buffalo and town of Cheektowaga, Erie County. | Bridge Improvement | 07/03/2009 | 07/03/2009 | 01/06/2010 | 501454 | 0
7105 | New York | STATEWIDE |  | 26, 27, 28 | 5810723 | Install signs for bike route 517 in Erie, Niagara, and Chautauqua counties. The project also includes sidewalk construction at the intersection of State Route 263 and State Route 270 in the Town of Am | Transportation Enhancements | 10/27/2009 | 10/27/2009 | 06/30/2010 | 318340 | 0
7106 | New York | CATTARAUGUS |  | 29 | 5V09133 | Repave portions of State Route 394 totaling 6.2 miles in the towns of Cold Spring, Conewango, Napoli and Randolph and the village of East Randolph, in Cattaraugus County. The new pavement will address | Pavement Improvement | 10/08/2009 | 10/08/2009 | 06/15/2010 | 574789 | 6.16
7107 | New York | CATTARAUGUS |  | 29 | 5V09153 | Repave a five-mile portion of U.S. Route 62, from the Chautauqua County line to Youngs Road in the towns of Conewango and Leon, Cattaraugus County. | Pavement Improvement | 05/15/2010 | 05/15/2010 | 06/18/2010 | 342468 | 3.1
7108 | New York | CATTARAUGUS |  | 29 | 5V09163 | Conduct pavement crack sealing on approximately 100 miles of roads throughout Cattaraugus County. Asphalt pavement will be cleaned and sealant will be applied. | Pavement Improvement | 09/01/2009 | 09/01/2009 | 12/15/2009 | 220061 | 0
7109 | New York | STATEWIDE |  | 27, 29 | 5V09213 | Repave approximately 21 miles of Interstate 86 in the towns of Ellery, Ellicott and Poland, the village of Falconer and the city of Jamestown in Chautauqua County, and the town and village of Randolph | Pavement Improvement | 05/15/2010 | 05/15/2010 | 06/18/2010 | 1520000 | 21.34
7110 | New York | CATTARAUGUS |  | 27 | 5V09223 | Repave a 2.5 mile bypass from Interstate 86 to NY Route 430 in the town of Ellery and village of Bemus Point, Chautauqua County. A single course overlay will be applied to address deteriorating paveme | Pavement Improvement | 05/15/2010 | 05/15/2010 | 06/18/2010 | 348446 | 1.62
7111 | New York | CHAUTAUQUA |  | 27 | 5V09253 | Conduct pavement crack sealing on approximately 100 miles of roads throughout Chautauqua County. Asphalt pavement will be cleaned and sealant will be applied. | Pavement Improvement | 08/31/2009 | 08/31/2009 | 12/15/2009 | 260285 | 0
7112 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 26, 27, 28 | 5V09323 | Seal pavement cracks on federal aid-eligible routes in northern Erie County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pave | Pavement Improvement | 05/01/2010 | 05/01/2010 | 10/15/2010 | 128297 | 0
7113 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09413 | Repave a 0.8 mile portion of US Route 20, from Cazenovia Creek to Seneca Street (NY Route 16) in the towns of West Seneca and Elma, Erie County. | Pavement Improvement | 06/01/2010 | 06/01/2010 | 10/15/2010 | 229321 | 1.54
7114 | New York | ERIE |  | 27 | 5V09423 | Repave a one-mile portion of U.S. Route 20A (Quaker Street) in the village of Orchard Park, Erie County. The project will address deteriorating pavement conditions. The top layer of worn, deteriorated | Pavement Improvement | 09/21/2009 | 09/21/2009 | 09/15/2009 | 109955 | 1.02
7115 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09433 | Repave a 5.8-mile-long section of N.Y. Route 39 in Erie County, from N.Y. Route 75 in the town of Collins to Trevett Road in the town of Concord. The project will address deteriorating pavement condit | Pavement Improvement | 06/01/2010 | 06/01/2010 | 06/15/2010 | 447857 | 5.77
7116 | New York | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09463 | Seal pavement cracks on federal aid-eligible routes in southern Erie County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pave | Pavement Improvement | 06/01/2010 | 06/01/2010 | 06/15/2010 | 252000 | 0
7117 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09513 | Repave a 3.7-mile-long portion of N.Y. Route 425 in the town of Cambria, Niagara County. The paving will extend from Upper Mountain Road to N.Y. Route 104. It will address deteriorating pavement condi | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/15/2010 | 456000 | 3.74
7118 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09523 | Repave a 10.4-mile-long portion of N.Y. Route 77 in the towns of Lockport and Royalton, Niagara County. The project will extend from N.Y. Route 31 to the Genesee County line. It will address deteriora | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/15/2010 | 1109897 | 10.44
7119 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26, 28 | 5V09533 | Repave a 5.8-mile-long portion of NY Route 429 in Niagara County. The project will extend from Lockport Road in the town of Wheatfield to N.Y. Route 104 in the towns of Cambria and Lockport, where the | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/15/2010 | 964862 | 5.81
7120 | New York | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26, 28 | 5V09543 | Seal pavement cracks on federal aid-eligible routes in Niagara County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pavements | Pavement Improvement | 08/10/2009 | 08/10/2009 | 06/15/2010 | 135253 | 0
7121 | New York | STEUBEN |  | 29 | 6008513 | Build embankment and pavement on a five-mile section of relocated US Route 15 in the Town of Lindley, Steuben County. This project is the first phase of a staged project to build a four lane highway w | Other | 09/14/2009 | 09/14/2009 | 08/31/2012 | 5000000 | 0
7122 | New York | YATES |  | 29 | 6011163 | A highway resurfacing project on Rt 54A from Branchport to Penn Yan in the town of Jerusalem and the village of Penn Yan in Yates County. | Pavement Improvement | 03/23/2010 | 03/23/2010 | 12/15/2010 | 5514097 | 5.94
7123 | New York | SCHUYLER |  | 29 | 6017213 | Replace the bridge carrying State Route 224 over Catharine Creek in the village of Montour Falls, Schuyler County. | Bridge Improvement | 01/13/2010 | 01/13/2010 | 12/15/2010 | 1652135 | 0
7124 | New York | ALLEGANY |  | 29 | 6021143 | Replace the bridge carrying State Route 244 over the north branch of Phillips Creek in the town of Amity, Allegany County. | Bridge Replacement | 01/14/2010 | 01/14/2010 | 12/15/2010 | 1446329 | 0
7125 | New York | STEUBEN |  | 29 | 6037173 | Replace the bridge on Route 415 over Wolf Run Creek in the town of Campbell, Steuben County. | Bridge Replacement | 05/20/2009 | 05/20/2009 | 12/30/2009 | 1616042 | 0
7126 | New York | ALLEGANY |  | 29 | 6056233 | Replace the bridge carrying State Route 417 over Dyke Creek in the town of Andover, Allegany County. | Bridge Replacement | 01/12/2010 | 01/12/2010 | 12/11/2010 | 1414283 | 0
7127 | New York | STEUBEN |  | 29 | 6066843 | Replace the I-86 bridge over Route 415 in the town of Painted Post, Steuben County. | Bridge Replacement | 05/15/2009 | 05/15/2009 | 11/30/2010 | 4973974 | 0
7128 | New York | CHEMUNG | ELMIRA | 29 | 6753763 | A project to replace the county Route 43 bridge over Sing Sing Creek in the town of Big Flats, Chemung County. | Bridge Replacement | 01/04/2010 | 01/04/2010 | 12/30/2010 | 1160000 | 0
7129 | New York | CHEMUNG | ELMIRA | 29 | 6754133 | A project to reconstruct Washington Avenue, from Davis Street to Walnut Street, in the city of Elmira, Chemung County. | Pavement Improvement | 12/07/2009 | 12/07/2009 | 10/30/2010 | 741000 | 0
7130 | New York | ALLEGANY |  | 29 | 6754293 | Resurface seven miles of County Route 12 from the Village of Alfred to State Route 417 in the towns of Andover, Ward, and Alfred, Allegany County. Existing pavement will be overlaid to provide a smoot | Pavement Improvement | 08/20/2009 | 08/20/2009 | 11/30/2009 | 797924 | 0
7131 | New York | SCHUYLER |  | 29 | 6754303 | Resurface 2.5 miles of County Route 16 from Meads Hill Road to Townsend Road in the Town of Dix, Schuyler County. The existing pavement will be resurfaced to provide a smooth surface and prolong the l | Pavement Improvement | 10/01/2009 | 10/01/2009 | 11/30/2009 | 241776 | 0
7132 | New York | YATES |  | 29 | 6754313 | Resurface 1.8 miles of County Route 32 from County Route 29 to County Route 33 in the Town of Jerusalem, Yates County. Existing pavement will be overlaid to provide a smooth surface and prolong the li | Pavement Improvement | 05/13/2010 | 05/13/2010 | 11/30/2009 | 183647 | 0
7133 | New York | STEUBEN |  | 29 | 6754323 | Resurface 1.9 miles of County Route 14 from County Route 15 south in the Town of Bath, Steuben County. The existing pavement will be recycled and resurfaced with new asphalt. | Pavement Improvement | 08/03/2009 | 08/03/2009 | 11/30/2009 | 230148 | 0
7134 | New York | STEUBEN |  | 29 | 6754333 | Resurface 3.3 miles of County Route 14 from County Route 69 north in the towns of Bath and Howard, Steuben County. The existing pavement will be recycled and resurfaced with new asphalt. | Pavement Improvement | 08/03/2009 | 08/03/2009 | 11/30/2009 | 438573 | 0
7135 | New York | STEUBEN |  | 29 | 6754343 | Resurface four-tenths of a mile of East Avenue from Main Street to Addison Street in the Village of Arkport, Steuben County. The existing deteriorated pavement surface will be removed and replaced wit | Pavement Improvement | 09/18/2009 | 09/18/2009 | 11/30/2009 | 80104 | 0
7136 | New York | STEUBEN |  | 29 | 6754353 | Resurface 1.2 miles of streets in the City of Hornell, Steuben County. The project will overlay the existing pavement on portions of Thatcher, North Church, Erie, Center, and Adsit Streets to provide | Pavement Improvement | 09/08/2009 | 09/08/2009 | 11/30/2009 | 152437 | 0
7137 | New York | STEUBEN | ELMIRA | 29 | 6754443 | Resurface two-tenths of a mile of West Third Street in the City of Corning, Steuben County. The existing deteriorated pavement surface, from Walnut Street to State Street, will be removed and replaced | Pavement Improvement | 10/05/2009 | 10/05/2009 | 11/30/2009 | 21677 | 0
7138 | New York | STEUBEN | ELMIRA | 29 | 6754453 | Resurface one-tenth of a mile of East Third Street from Cedar Street to Pine Street in the City of Corning, Steuben County. The existing deteriorated pavement surface will be removed and replaced with | Pavement Improvement | 08/11/2009 | 08/11/2009 | 11/30/2009 | 18000 | 0
7139 | New York | STEUBEN | ELMIRA | 29 | 6754463 | Resurface four-tenths of a mile of West William Street from Pulteney Street to Bissell Avenue in the City of Corning, Steuben County. The existing deteriorated pavement surface will be removed and rep | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/30/2009 | 79584 | 0
7140 | New York | STEUBEN |  | 29 | 6803963 | Rehabilitate culverts in various locations in the towns of Urbana and Pulteney, Steuben County. | Pavement Improvement | 04/20/2009 | 04/20/2009 | 05/30/2010 | 915925 | 0
7141 | New York | STATEWIDE |  | 29 | 6804183 | Wash bridges and seal bridge decks at various locations in Allegany and Steuben counties. | Bridge Improvement | 05/14/2009 | 05/14/2009 | 09/30/2009 | 591035 | 0
7142 | New York | STATEWIDE |  | 29 | 6804223 | A project to remove hazardous trees along select state rights-of-way in Allegany, Schuyler, Steuben, and Yates counties. | Other | 02/01/2010 | 02/01/2010 | 05/30/2010 | 229199 | 0
7143 | New York | STATEWIDE |  | 29 | 6804233 | Sidewalk Reconstruction for ADA compliance, Montour Falls, Addison, Southport. | Transportation Enhancements | 10/27/2009 | 10/27/2009 | 06/30/2010 | 186044 | 1.37
7144 | New York | YATES |  | 29 | 6804263 | A project resurface 30 miles of state Routes 14, 14A, 245, 409 in Schuyler and Yates counties. | Pavement Improvement | 03/04/2010 | 03/04/2010 | 12/15/2010 | 1965777 | 5.71
7145 | New York | STATEWIDE |  | 29 | 6804273 | Rock Slope Remediation of 10 sites in Allegany & Steuben Counties. | Other | 03/17/2010 | 03/17/2010 | 06/30/2010 | 366505 | 0.1
7146 | New York | STATEWIDE |  | 29 | 6804283 | Paint bridges on I-86 and I-390 at various locations in Allegany and Steuben counties. | Bridge Improvement | 08/25/2009 | 08/25/2009 | 10/31/2010 | 1085544 | 0
7147 | New York | STATEWIDE |  | 29 | 6804293 | Rehabilitate bridges in various locations in Allegany and Steuben counties. | Bridge Improvement | 07/07/2009 | 07/07/2009 | 10/31/2009 | 444923 | 0
7148 | New York | ALLEGANY |  | 29 | 6804333 | Repair 21 culverts on Interstate 86 in the towns of Cuba and Friendship, Allegany County. The project includes drainage structure replacement and culvert relining. | Other | 08/13/2009 | 08/13/2009 | 06/30/2010 | 916349 | 0
7149 | New York | ST LAWRENCE |  | 23 | 7752473 | Replace the County Route 39 Bridge over the Grasse River in the Town of Louisville, St. Lawrence County. This project involves replacing the historic stone arch bridge with a steel structure adjacent | Bridge Replacement | 08/03/2009 | 08/03/2009 | 11/01/2011 | 3653885 | 0
7150 | New York | LEWIS |  | 23 | 7752543 | A project to replace the Sweeney Road bridge over the East Branch of Fish Creek in the Town of West Turin, Lewis County. The new bridge will be built next to the existing structure and will have wide | Bridge Replacement | 12/23/2009 | 12/23/2009 | 07/07/2010 | 795857 | 0
7151 | New York | JEFFERSON |  | 23 | 7752583 | A project to replace the Lisk Bridge carrying County Route 69 over Sandy Creek in the Town of Adams, Jefferson County. The new structure will be built adjacent to the existing bridge. Improvements w | Bridge Replacement | 11/26/2009 | 11/26/2009 | 09/20/2010 | 2389999.53 | 0
7152 | New York | FRANKLIN |  | 23 | 7752913 | Replace the Willow Street Bridge over the Salmon River in the Village of Malone, Franklin County. This project involves replacing the existing steel structure with a concrete structure at the same loc | Bridge Replacement | 08/04/2009 | 08/04/2009 | 11/03/2010 | 1361000 | 0
7153 | New York | LEWIS |  | 23 | 7752973 | Pave County Route 29, West Road, in the Town of Martinsburg, Lewis County. This project involves the rehabilitation of nearly three miles of roadway from Cemetery Road to State Route 26. | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/07/2009 | 990038 | 0
7154 | New York | CLINTON |  | 23 | 7753023 | Replace the Narrows Road Bridge over the Chateaugay Narrows in the Town of Ellenburg, Clinton County. The new bridge will have increased vertical clearance, allowing for easier movement of recreationa | Bridge Replacement | 04/01/2010 | 04/01/2010 | 08/10/2010 | 1444000 | 0
7155 | New York | CLINTON |  | 23 | 7753033 | Replace the Silver Lake Road Bridge over the Saranac River in the Town of Black Brook, Clinton County. The existing steel bridge will be replaced with a concrete structure at the same location. | Bridge Replacement | 09/23/2009 | 09/23/2009 | 08/10/2010 | 1529682 | 0
7156 | New York | CLINTON |  | 23 | 7753083 | A bridge replacement project of Slosson Road over Little Chazy River in Clinton County. | Bridge Replacement | 05/03/2010 | 05/03/2010 | 03/10/2011 | 952000 | 0
7157 | New York | CLINTON |  | 23 | 7753103 | Resurface approximately one mile of Oak Street, a Plattsburgh city street, and one mile of North Catherine Street (State Route 22), also in Plattsburgh. The streets, which run parallel to each other, | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/02/2009 | 218836 | 3.33
7158 | New York | JEFFERSON |  | 23 | 7753113 | Resurface Arsenal Street and Washington Street in the City of Watertown | Pavement Improvement | 08/10/2009 | 08/10/2009 | 11/02/2009 | 353116 | 1.79
7159 | New York | STATEWIDE |  | 23 | 7804393 | Replace five intersection signal systems in Clinton, Franklin and Jefferson counties. These signal improvements will maximize travel efficiency at the intersections as well as provide an added measure | Safety/Traffic Management | 07/03/2009 | 07/03/2009 | 12/31/2009 | 624067 | 0
7160 | New York | STATEWIDE |  | 23 | 7804453 | Restore the protective paint on eight bridges in Jefferson and St. Lawrence counties. Structures to be addressed in the contract include Interstate bridges on I-81 in Jefferson County, as well as a pa | Bridge Improvement | 07/14/2009 | 07/14/2009 | 12/18/2009 | 2897462 | 0
7161 | New York | STATEWIDE |  | 23 | 7804553 | Provide much-needed maintenance to approximately 500 miles of highway in Lewis, Jefferson, St. Lawrence, Franklin and Clinton counties. This work involves cleaning and sealing cracks in the pavement t | Pavement Improvement | 07/03/2009 | 07/03/2009 | 06/30/2010 | 1060415 | 0
7162 | New York | STATEWIDE |  | 23 | 7804573 | Rehabilitate four large culverts in Jefferson and St. Lawrence counties. The culverts are located on State Routes 72, 184 and 342 and will be receiving new linings as well as inlet and outlet cleaning | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/22/2009 | 2631840 | 0
7163 | New York | STATEWIDE |  | 23 | 7804733 | Clean and repaint nine state highway bridges in order to extend their useful service life. The project includes bridges carrying State Routes 22, 37, 37 C, 420 and 458 and U.S. Route 11 in Franklin, C | Bridge Improvement | 04/06/2010 | 04/06/2010 | 03/17/2010 | 3433155 | 0
7164 | New York | STATEWIDE |  | 23 | 7804763 | Repair bridges in Lewis, Jefferson, St. Lawrence, Franklin and Clinton counties. This work will help curb deterioration and improve overall bridge conditions. | Bridge Improvement | 05/03/2010 | 05/03/2010 | 07/02/2010 | 2200000 | 0
7165 | New York | ST LAWRENCE |  | 23 | 7805033 | Provide needed maintenance work to two bridges in St. Lawrence County. One structure is on State Route 11B and crosses the East Branch of the St. Regis River while the second is on State Route 420 and | Bridge Improvement | 06/03/2009 | 06/03/2009 | 01/20/2010 | 1298112 | 0
7166 | New York | STATEWIDE |  | 23 | 7805053 | Replacing deteriorated guide rail in the Adirondack Park in Clinton Franklin and St. Lawrence counties. | Safety/Traffic Management | 07/03/2009 | 07/03/2009 | 11/20/2009 | 1139464 | 0
7167 | New York | STATEWIDE |  | 23 | 7805213 | Reconstruct 1.5 miles of sidewalks and approximately 100 sidewalk ramps to bring them into compliance with federal Americans with Disabilities Act guidelines. Construction will focus on sidewalks and | Other | 07/31/2009 | 07/31/2009 | 07/30/2010 | 735230 | 0
7168 | New York | JEFFERSON |  | 23 | 7BRD083 | Construct two new traffic lanes and enhance shoulders on Interstate 81 on Wellesley Island in the Town of Orleans, Jefferson County. The improvements will help expedite border crossing movements and e | Pavement Widening | 08/20/2009 | 08/20/2009 | 12/31/2009 | 1488325 | 0.18
7169 | New York | CLINTON |  | 23 | 7V09113 | Resurface 1.3 Miles of Route 374, Village of Dannemora | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 174420 | 1.3
7170 | New York | CLINTON |  | 23 | 7V09123 | Resurface 1.4 Miles of Route 9, Village of Champlain | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 156083 | 1.4
7171 | New York | CLINTON |  | 23 | 7V09133 | Resurface 0.4 Miles Of Route 2U, US Route 11 - Vermont State Line | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 68800 | 0.4
7172 | New York | FRANKLIN |  | 23 | 7V09243 | Resurface 4.8 Miles Of Route 374, Chateaugay - Brainardsville | Pavement Improvement | 05/01/2010 | 05/01/2010 | 10/16/2009 | 945807 | 4.8
7173 | New York | FRANKLIN |  | 23 | 7V09293 | Resurface 2.0 Miles of Route 3, Saint Lawrence County -Tupper Lake | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 249237 | 2
7174 | New York | FRANKLIN |  | 23 | 7V09294 | Resurface 9.2 Miles Of Route 11, Malone - Chateaugay | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 1127902 | 9.2
7175 | New York | FRANKLIN |  | 23 | 7V09295 | Resurface 0.8 Miles Of Route 30, Malone, Elm Street & Constable Street | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 140000 | 0.5
7176 | New York | ST LAWRENCE |  | 23 | 7V09594 | Resurface 3.9 Miles Of Route 68, Pierrepont - Colton | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 331343 | 3.9
7177 | New York | ST LAWRENCE |  | 23 | 7V09595 | Resurface 1.1 Miles Of Route 184, Heuvelton Village (Union St) | Pavement Improvement | 08/10/2009 | 08/10/2009 | 10/30/2009 | 130454 | 1.07
7178 | New York | COLUMBIA |  | 20 | 8001443 | Rehabilitate the Route 9G bridge over the Roeliff Jansen Kill in the Town of Germantown, Columbia County. | Bridge Improvement | 10/06/2009 | 10/06/2009 | 08/31/2010 | 6741732 | 0.1
7179 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8010683 | A project to install a stormwater treatment system along Route 9, adjacent the Wappingers Lake in the Village of Wappingers Falls, Dutchess County. The new system will help to reduce pollutants enter | Other | 11/26/2009 | 11/26/2009 | 01/31/2011 | 438002 | 0.29
7180 | New York | WESTCHESTER | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 19 | 8029053 | A pavement overlay project of Route 123 in the city of Rye in Westchester County. | Pavement Improvement | 02/12/2010 | 02/12/2010 | 01/31/2011 | 379700 | 1.49
7181 | New York | ORANGE | NEWBURGH | 22 | 8062123 | Provide much-needed general maintenance of four bridges carrying Interstate 84 in the Town of Newburgh, Orange County. The work will extend the service life of the structures. | Bridge Improvement | 09/07/2009 | 09/07/2009 | 06/30/2010 | 742023 | 0
7182 | New York | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 19 | 8093573 | Replace the Palisades Interstate Parkway bridge over Route 202 in the towns of Haverstraw and Ramapo, Rockland County. | Bridge Replacement | 06/11/2009 | 06/11/2009 | 01/31/2011 | 15395348 | 1.52
7183 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 17, 18, 19 | 8099413 | Install an automated traffic management system on the Cross County Parkway in Westchester County. The new system will include acoustic vehicle detectors that will communicate with the regional Transpo | Safety/Traffic Management | 05/29/2009 | 05/29/2009 | 12/31/2010 | 5363251 | 122.46
7184 | New York | ULSTER |  | 22 | 8177323 | Construct new bluestone sidewalks along Route 209 in the Hamlet of Stone Ridge located in the Town of Marbletown, Ulster County. The project will restore the historic sidewalk, repave a nearly one mil | Pavement Improvement | 07/09/2009 | 07/09/2009 | 05/31/2010 | 2570867 | 0.96
7185 | New York | ORANGE | POUGHKEEPSIE-NEWBURGH | 19, 22 | 8239163 | A project to reconstruct almost two miles of Robinson Avenue (Route 9W) in the City of Newburgh, Orange County. | Pavement Improvement | 02/08/2010 | 02/08/2010 | 01/31/2011 | 8580000 | 1.87
7186 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8327363 | A project to improve sidewalks and crosswalks at the intersection of Main Street (Route 9D) and Spring Street in the Village of Wappingers Falls, Dutchess County. The project will improve pedestrian | Safety/Traffic Management | 05/13/2010 | 05/13/2010 | 01/31/2011 | 158035 | 0.09
7187 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 20 | 8753783 | Replace the Leedsville Road (County Road 2) bridge over the Webutuck Tributary in the Town of Amenia, Dutchess County. | Bridge Replacement | 12/28/2009 | 12/28/2009 | 11/30/2010 | 593000 | 0
7188 | New York | ULSTER |  | 22 | 8755143 | New Paltz Road/Conrail Bridge Repleacement in the Town of Lloyd. | Bridge Replacement | 02/24/2010 | 02/24/2010 | 01/31/2011 | 2224115 | 0
7189 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 20 | 8755813 | Replace the Crum Elbow Road, County Road 41, bridge over the Fallkill Creek in the Town of Hyde Park, Dutchess County. | Bridge Replacement | 04/15/2010 | 04/15/2010 | 08/31/2010 | 1110520 | 0
7190 | New York | ULSTER |  | 22 | 8756193 | Replace the Main Street bridge over the Rondout Creek in the Town of Wawarsing, Ulster County. | Bridge Replacement | 09/14/2009 | 09/14/2009 | 08/31/2010 | 4614656 | 0
7191 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8756673 | Replace the Popham Road Bridge over the Metro-North Railroad tracks in the Village of Scarsdale, Westchester County. | Bridge Replacement | 08/25/2009 | 08/25/2009 | 06/30/2010 | 13376683 | 0.01
7192 | New York | COLUMBIA |  | 20 | 8757184 | A project to replace the Hall Hill Road bridge over the Roeliff Jansen Kill in the Town of Ancram, Columbia County. | Bridge Replacement | 03/24/2010 | 03/24/2010 | 01/31/2011 | 1355000 | 0
7193 | New York | DUTCHESS |  | 19 | 8757253 | Rehabilitate the Lime Kiln Road bridge over the Ten Mile River in the Town of Dover, Dutchess County. The project will include cleaning and painting bridge members, waterproofing the bridge deck, repa | Bridge Improvement | 09/24/2009 | 09/24/2009 | 06/30/2010 | 1610100 | 0.02
7194 | New York | COLUMBIA |  | 20 | 8757613 | A project to replace the Empire Road bridge over the Roeliff Jansen Kill in the Town of Copake, Columbia County. | Bridge Replacement | 03/24/2010 | 03/24/2010 | 01/31/2011 | 1107000 | 0
7195 | New York | WESTCHESTER | POUGHKEEPSIE-NEWBURGH | 18 | 8757723 | Replace the Odell Avenue Bridge over abandoned railroad tracks in the City of Yonkers, Westchester County. | Bridge Replacement | 04/01/2009 | 04/01/2009 | 03/30/2010 | 1744219 | 0.02
7196 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 17 | 8757733 | Replace the South First Avenue Bridge over the Metro-North Railroad tracks in the City of Mount Vernon, Westchester County. | Bridge Replacement | 09/08/2009 | 09/08/2009 | 06/30/2010 | 7616157 | 0
7197 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 22 | 8757873 | A project to replace the Hoffman Street bridge over Metro-North Railroad in the City of Poughkeepsie, Dutchess County. | Bridge Replacement | 06/30/2010 | 06/30/2010 | 01/31/2011 | 10289683 | 0
7198 | New York | ORANGE |  | 22 | 8757933 | Replace the Petticoate Lane bridge over the Shawagunkill in the Town of Crawford, Orange County. (BIN 3344340) | Bridge Replacement | 04/15/2010 | 04/15/2010 | 12/31/2010 | 1396000 | 0
7199 | New York | ULSTER |  | 22 | 8758023 | Rehabilitate the Beckley Drive bridge over the Fantine Kill in the Town of Wawarsing, Ulster County. | Bridge Replacement | 11/10/2009 | 11/10/2009 | 10/31/2010 | 1159000 | 0
7200 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19, 20 | 8759123 | Provide new pavement markings along select highways throughout Dutchess County. The new pavement markings will improve roadway safety by increasing their reflectivity and better delineating the travel | Other | 09/25/2009 | 09/25/2009 | 08/31/2010 | 770140 | 0
7201 | New York | ULSTER |  | 22 | 8759143 | A project for a new/improved bicycle facility on the Hudson Valley Rail Trail from Haviland Road to Commercial Avenue in the town of Lloyd. | Transportation Enhancements | 03/30/2010 | 03/30/2010 | 01/31/2011 | 2750000 | 0
7202 | New York | ULSTER |  | 19 | 8759163 | Construction of a Park and Ride lot in the Village of Kiryas Joel. | Transportation Enhancements | 12/29/2009 | 12/29/2009 | 12/31/2010 | 1524194 | 0
7203 | New York | ORANGE | POUGHKEEPSIE-NEWBURGH | 19 | 8759473 | A project to improve East Shore Road in the Town of Warwick, Orange County. Pavement, drainage and retaining wall improvements will be made as part of the project. | Pavement Widening | 03/11/2010 | 03/11/2010 | 01/31/2011 | 879000 | 0
7204 | New York | ORANGE | NEWBURGH | 19 | 8759493 | Phase 6 of a project to provide new sidewalks and rehabilitate existing sidewalks in the Village of Kiryas Joel, Orange County . The project will improve pedestrian access and safety. | Other | 04/12/2010 | 04/12/2010 | 01/31/2011 | 501000 | 0
7205 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8759793 | A project to perform pavement rehabilitation along County Roads 27, 93, 114, 35 and 77 in the towns of East Fishkill, Fishkill, Wappingers Falls and Poughkeepsie, Dutchess County. | Pavement Improvement | 02/02/2010 | 02/02/2010 | 11/30/2010 | 3978186 | 0
7206 | New York | ULSTER |  | 22 | 8760193 | Construct a pedestrian walkway along the Rondout Creek waterfront from Ravine Street to Route 9W in the City of Kingston, Ulster County. The project will build approximately .25 miles of walkway and 4 | Transportation Enhancements | 09/16/2009 | 09/16/2009 | 01/31/2011 | 200000 | 0
7207 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760533 | Improve intersection lighting along the Bronx River Parkway in Westchester County. The intersections include Virginia Road, Parkway Holmes Road, Fisher Lane, Old Tarrytown Road, and Strathmore Road. | Other | 08/17/2009 | 08/17/2009 | 06/30/2010 | 334018 | 0
7208 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18, 19 | 8760543 | Upgrade 60 traffic signals at select locations in Westchester County. | Other | 08/17/2009 | 08/17/2009 | 06/30/2010 | 302642 | 0
7209 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18, 19 | 8760553 | Install an automated traffic management system on the Bronx River Parkway in Westchester County. The new system will include in-pavement vehicle detectors capable of monitoring traffic volume and spee | Other | 08/17/2009 | 08/17/2009 | 12/31/2009 | 619827 | 0
7210 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18, 19 | 8760563 | Replace guide rail at select locations in Westchester County. | Other | 08/17/2009 | 08/17/2009 | 01/31/2010 | 867000 | 0
7211 | New York | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 17, 18, 19 | 8760573 | A project to paint 10 local bridges at select locations throughout Rockland County. | Bridge Improvement | 03/18/2010 | 03/18/2010 | 12/31/2010 | 1100000 | 0
7212 | New York | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 17, 19 | 8760583 | Replace roadside guiderail at select locations on local roadways throughout Rockland County. | Other | 09/23/2009 | 09/23/2009 | 08/31/2010 | 661845 | 0
7213 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760593 | Upgrade and modernize existing traffic and pedestrian signal equipment in the City of Yonkers, Westchester County. | Safety/Traffic Management | 09/23/2009 | 09/23/2009 | 05/05/2010 | 1000000 | 0
7214 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760623 | A project to rehabilitate Creek Road pavement from the Poughkeepsie city line to Cottage Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 04/07/2010 | 04/07/2010 | 01/31/2011 | 1564986 | 0
7215 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760653 | Rehabilitate the pavement along Buckingham Avenue from East Cedar Street to Fulton Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 09/16/2009 | 09/16/2009 | 12/31/2009 | 238421 | 0
7216 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760663 | Rehabilitate the pavement along Fairview Avenue from the Poughkeepsie city line to Fulton Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 04/07/2010 | 04/07/2010 | 01/31/2011 | 679014 | 0
7217 | New York | ORANGE | NEWBURGH | 19, 22 | 8760683 | Orange County Paving | Pavement Improvement | 02/23/2010 | 02/23/2010 | 12/31/2010 | 2641829 | 0
7218 | New York | ORANGE | NEWBURGH | 19 | 8760803 | A project to repave Peenpack Trail in the Town of Deerpark, Orange County. | Transportation Enhancements | 12/21/2009 | 12/21/2009 | 10/31/2010 | 310140 | 0
7219 | New York | ORANGE | NEWBURGH | 19, 22 | 8760813 | Paint 20 bridges at select locations throughout Orange County. This preventative-maintenance project will enhance the bridges structural integrity. | Bridge Improvement | 01/19/2010 | 01/19/2010 | 11/30/2010 | 655283 | 0
7220 | New York | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760833 | Resurface select local roadways throughout the Town of Clarkstown, Rockland County. | Pavement Improvement | 10/07/2009 | 10/07/2009 | 09/30/2010 | 618689 | 0
7221 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760843 | A sidewalk/pedestrian improvement project throughout the city of Rye in Westchester County. Includes work on sidewalks, pedestrian signals, and curb cuts. | Safety/Traffic Management | 03/22/2010 | 03/22/2010 | 01/31/2011 | 695000 | 0
7222 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760853 | A pavement rehabilitation project on Sheafe Road, from South Road to Channingville Road, in the town of Poughkeepsie. | Pavement Improvement | 04/07/2010 | 04/07/2010 | 01/31/2011 | 1007000 | 0
7223 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 17, 18, 19 | 8810893 | Provide much-needed general maintenance of 18 bridges along Interstate 684 in Westchester County, helping to extend the service life of the structures. | Bridge Improvement | 06/30/2009 | 06/30/2009 | 04/30/2010 | 14958837 | 0
7224 | New York | STATEWIDE | STATEWIDE | 19, 20 | 8810903 | Repave approximately 18 miles of state roadway in Columbia, Dutchess and Putnam counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement | Pavement Improvement | 06/18/2009 | 06/18/2009 | 05/31/2010 | 5073732 | 11.12
7225 | New York | STATEWIDE |  | 19, 22 | 8810993 | Repave approximately 22 miles of state roadway in Orange and Ulster counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings to | Pavement Improvement | 06/15/2009 | 06/15/2009 | 05/31/2010 | 4398529 | 10.06
7226 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 17, 18, 19 | 8811003 | Repave approximately 34 miles of state roadway in Westchester and Rockland counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement marki | Pavement Improvement | 06/10/2009 | 06/10/2009 | 05/12/2010 | 5652954 | 14.37
7227 | New York | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 19 | 8811123 | Pavement Resurfacing on the Taconic State Parkway Southbound | Pavement Improvement | 09/18/2009 | 09/18/2009 | 07/31/2010 | 4571430 | 3.3
7228 | New York | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19, 20, 22 | 8811283 | A preventative maintenance project in Dutchess County on Rt 44/55 AND RT 9G. | Pavement Improvement | 02/25/2010 | 02/25/2010 | 01/31/2011 | 5480000 | 7.17
7229 | New York | ULSTER |  | 22 | 8811293 | Repave approximately four miles of Route 28 between Route 212 and Route 214 in the Town of Shandaken, Ulster County. The top layer of worn, deteriorated pavement will be removed and replaced with new | Pavement Improvement | 07/23/2009 | 07/23/2009 | 06/30/2010 | 1642659 | 3.43
7230 | New York | ORANGE | NEWBURGH | 22 | 8811303 | Rebuild existing sidewalks and curb ramps along South Street from Dubois Street to Liberty Street in the City of Newburgh, Orange County. The project will improve pedestrian access and safety. | Safety/Traffic Management | 11/11/2009 | 11/11/2009 | 09/30/2010 | 317000 | 0.24
7231 | New York | ULSTER |  | 22 | 8811363 | A pavement resurfacing project on Rt 28 from Route 375 to Route 28A and Route 214 to Delaware County line in towns of Hurley, Olive, and Shandaken. | Pavement Improvement | 03/10/2010 | 03/10/2010 | 01/31/2011 | 8250000 | 22.9
7232 | New York | DELAWARE |  | 20 | 9014463 | This project will use a Mill and Fill treatment to resurface this section of Route 206 in the Town of Walton. | Pavement Improvement | 05/24/2010 | 05/24/2010 | 02/11/2010 | 1000000 | 4.33
7233 | New York | DELAWARE |  | 20 | 9028103 | This project will resurface sections of Rtes. 23 and 30 in the Village of Grand Gorge | Pavement Improvement | 05/24/2010 | 05/24/2010 | 02/11/2010 | 160000 | 0.71
7234 | New York | TIOGA | BINGHAMTON | 22 | 9038193 | Resurface State Route 434 from the Court Street Bridge to the eastern intersection with Marshland Road in the Village and Town of Owego, Tioga County. This project will improve 11 miles of pavement, r | Pavement Improvement | 09/30/2009 | 09/30/2009 | 08/26/2010 | 5315655 | 11.08
7235 | New York | TIOGA | BINGHAMTON | 22 | 9067323 | Resurface State Route 17 between Pumpelly Creek in the Village of Owego and the Broome County line in the Town of Owego, Tioga County.The top layer of 42 miles of worn, deteriorated pavement will be r | Pavement Improvement | 08/31/2009 | 08/31/2009 | 07/09/2010 | 8355750 | 10.59
7236 | New York | TIOGA |  | 22 | 9067333 | Resurface State Route 17 between the Chemung County Line and Sackett's Creel in the Village of Waverly and towns of Barton and Nichols, Tioga County. This project will improve 40 miles of pavement, re | Pavement Improvement | 09/04/2009 | 09/04/2009 | 08/20/2010 | 6089717 | 10
7237 | New York | BROOME |  | 22 | 9067343 | Resurface 18 miles of State Route 17 in the Town of Windsor in Broome County. | Pavement Improvement | 09/09/2009 | 09/09/2009 | 06/15/2010 | 1921921 | 4.46
7238 | New York | SCHOHARIE |  | 21 | 9125083 | This project will resurface this section of Rtes. 30A and 20 to restore the riding surface in the Town of Esperance. | Pavement Improvement | 06/10/2010 | 06/10/2010 | 02/11/2010 | 223000 | 1.83
7239 | New York | SCHOHARIE |  | 21 | 9358093 | Rehabilitate approaches to seven bridges carrying Interstate 88 in Schoharie County. Guide rail will also be improved at these locations. | Bridge Improvement | 07/28/2009 | 07/28/2009 | 11/30/2009 | 2205315 | 0
7240 | New York | CHENANGO |  | 24 | 9752543 | Replace the bridge carrying County Route 34 over Johnson Creek in the Town of Norwich, Chenango County. | Bridge Replacement | 09/14/2009 | 09/14/2009 | 06/09/2010 | 921802 | 0
7241 | New York | BROOME | BINGHAMTON | 22 | 9753413 | Paint the bridge carrying County Route 48 over the Susquehanna River in the Town of Vestal and Village of Endicott, Broome County. | Bridge Improvement | 04/13/2010 | 04/13/2010 | 12/15/2010 | 2535000 | 0
7242 | New York | BROOME | BINGHAMTON | 22 | 9753423 | Rehabilitee the bridge carrying Arch Street over the Norfolk-Southern Railroad in the Village of Johnson City, Broome County. | Bridge Improvement | 09/30/2009 | 09/30/2009 | 02/17/2010 | 72811 | 0
7243 | New York | BROOME | BINGHAMTON | 22 | 9753433 | A project to culvert replacement project on Barlow Road over Acre Creek in the Town of Kirkwood, Broome County. | Other | 05/01/2010 | 05/01/2010 | 12/31/2009 | 350000 | 0
7244 | New York | TIOGA | BINGHAMTON | 22 | 9753443 | Replace the bridge carrying South side Drive over Pumpelly Creek in the town and village of Owego, Tioga County. | Bridge Replacement | 04/15/2010 | 04/15/2010 | 11/30/2009 | 1500000 | 0
7245 | New York | BROOME |  | 22 | 9753453 | A project to replace the bridge carrying Mason Road over Tracey Creek in the Town of Vestal, Broome County. | Bridge Replacement | 02/11/2010 | 02/11/2010 | 12/31/2010 | 560000 | 0
7246 | New York | BROOME |  | 22 | 9753463 | Resurface County Route 44, Vestal Road, from Jensen Road to Orchid Street in the Town of Vestal, Broome County. | Pavement Improvement | 03/05/2010 | 03/05/2010 | 10/27/2009 | 346000 | 0
7247 | New York | BROOME | BINGHAMTON | 22 | 9753473 | Resurface Main Street from Front Street to the western city line in the City of Binghamton, Broome County. | Pavement Improvement | 09/30/2009 | 09/30/2009 | 02/05/2010 | 734602 | 1.67
7248 | New York | BROOME | BINGHAMTON | 22 | 9753483 | A project to resurface Vestal Avenue from the Vestal-Endicott Bridge to East Main Street in the Village of Endicott, Broome County. | Pavement Improvement | 01/26/2010 | 01/26/2010 | 11/30/2009 | 65000 | 0
7249 | New York | DELAWARE |  | 20 | 9753493 | Resurface approximately one mile of County Route 7 from the Sullivan County line to Beaver Kill Road in the Town of Colchester, Delaware County. | Pavement Improvement | 09/10/2009 | 09/10/2009 | 10/30/2009 | 330050 | 0.95
7250 | New York | DELAWARE |  | 20 | 9753503 | Resurface County Route 21 from Leland Hull Road to Oak Hill Road in the Town of Franklin, Delaware County. | Pavement Improvement | 05/15/2010 | 05/15/2010 | 06/30/2010 | 547808 | 0
7251 | New York | CHENANGO |  | 24 | 9753513 | Install new signage on County Routes 5, 10A, 25, 32, 32A, 32B, 33, 34, 35, 36 and 44 in Chenango County. | Safety/Traffic Management | 07/27/2009 | 07/27/2009 | 06/01/2010 | 127758 | 0
7252 | New York | OTSEGO |  | 24 | 9753523 | Highway Resurfacing on County Route 31, Springfield Hill Road to Route 20, Town of Springfield. | Pavement Improvement | 06/01/2010 | 06/01/2010 | 10/30/2009 | 331252 | 0
7253 | New York | OTSEGO |  | 20 | 9753533 | Highway Resurfacing on County Route 33, Village of Cooperstown to Route 166, Town of Middlefield. | Pavement Improvement | 09/16/2009 | 09/16/2009 | 12/16/2009 | 751843 | 0
7254 | New York | SULLIVAN |  | 22 | 9753543 | Paint 22 local bridges in Sullivan County. | Bridge Improvement | 09/17/2009 | 09/17/2009 | 11/30/2010 | 2251241 | 0
7255 | New York | OTSEGO |  | 24 | 9753553 | A project to rehabilitate the bridge carrying Spring Street in the Town of Butternuts, Otsego County. | Bridge Improvement | 06/30/2010 | 06/30/2010 | 12/16/2010 | 380000 | 0
7256 | New York | SCHOHARIE |  | 21 | 9753563 | Repave nearly 10 miles of County Route 1, Mineral Springs Road, in the Town of Richmondville and the Town and Village of Cobleskill, Schoharie County. | Pavement Improvement | 09/23/2009 | 09/23/2009 | 02/23/2010 | 1112996 | 0
7257 | New York | SULLIVAN |  | 22 | 9753573 | Replace approximately 132 signs on various county roads in Sullivan County. | Other | 10/20/2009 | 10/20/2009 | 01/07/2010 | 91995 | 0
7258 | New York | SULLIVAN |  | 22 | 9753583 | Upgrade five traffic signals in the towns of Fallsburg, Highland, Rockland and Tusten in Sullivan County. | Safety/Traffic Management | 10/12/2009 | 10/12/2009 | 12/23/2009 | 119458 | 0
7259 | New York | SCHOHARIE |  | 21 | 9753593 | Culvert replacement project on County Route 8 in the Town of Cobleskill, Schoharie County. | Pavement Improvement | 09/23/2009 | 09/23/2009 | 03/18/2010 | 246000 | 0
7260 | New York | OTSEGO |  | 24 | 9753643 | A project to resurface East Street from Irving Place to Graduate Avenue in the City of Oneonta, Otsego County. | Pavement Improvement | 01/22/2010 | 01/22/2010 | 05/03/2010 | 200000 | 0
7261 | New York | OTSEGO |  | 24 | 9753653 | A project to resurface Grand Street from Division Street to Main Street and Division Street from James Georgeson Avenue to Grand Street in the City of Oneonta, Otsego County. | Pavement Improvement | 01/22/2010 | 01/22/2010 | 04/30/2010 | 106000 | 0
7262 | New York | DELAWARE |  | 20 | 9753663 | Rehabilitation of CR 21 in the Town of Franklin | Pavement Improvement | 03/11/2010 | 03/11/2010 | 09/23/2010 | 571000 | 0
7263 | New York | CHENANGO |  | 24 | 9753673 | Rehabilitation of CR 44 within the Towns of N. Norwich and Plymouth | Pavement Improvement | 05/15/2010 | 05/15/2010 | 05/19/2010 | 266198 | 0
7264 | New York | OTSEGO |  | 20, 21, 24 | 9805603 | Rehabilitate twelve culverts along Interstate 88 in the Towns of Otego, Oneonta, Milford and Maryland, Otsego County. | Pavement Improvement | 08/04/2009 | 08/04/2009 | 12/29/2009 | 3063739 | 81.93
7265 | New York | STATEWIDE | BINGHAMTON | 22, 24 | 9805633 | Paint 25 bridges on State Route 17 in Broome and Tioga counties in the towns of Vestal, Candor, Nichols, Barton and the Village of Waverly. The work will be entirely funded by ARRA. Bridge painting he | Bridge Improvement | 07/27/2009 | 07/27/2009 | 08/02/2010 | 7270361 | 0
7266 | New York | STATEWIDE |  | 20, 21, 22, 24 | 9805643 | Replace signage on state highways in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. Signs that are no longer in compliance with federal and state standards will be updated | Safety/Traffic Management | 08/12/2009 | 08/12/2009 | 09/02/2010 | 856624 | 0
7267 | New York | BROOME | BINGHAMTON | 22 | 9805653 | Bring sidewalks and curbs at select locations in the Town of Union and the villages of Johnson City and Endicott, Broome County, into compliance with Americans with Disabilities Act guidelines. | Safety/Traffic Management | 07/21/2009 | 07/21/2009 | 12/03/2009 | 502821 | 0
7268 | New York | STATEWIDE |  | 22, 24 | 9805663 | Perform bridge maintenance at various locations in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. The projects will be entirely funded by ARRA. This work includes repairs | Bridge Improvement | 08/26/2009 | 08/26/2009 | 04/30/2010 | 1000000 | 0
7269 | New York | STATEWIDE |  | 20, 21, 22, 24 | 9805673 | Perform bridge maintenance at various locations in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. The projects will be entirely funded by ARRA. This work includes repairs | Other | 08/26/2009 | 08/26/2009 | 04/30/2010 | 1084624 | 0
7270 | New York | DELAWARE |  | 20, 22 | 9805713 | Remove hazardous trees in south Delaware County. Removal of these trees will increase safety for the traveling public. | Safety/Traffic Management | 07/23/2009 | 07/23/2009 | 08/07/2009 | 634587 | 0
7271 | New York | STATEWIDE |  | 20, 22, 24 | 9805813 | A project to remove and replace curb ramps and sidewalks that are not in compliance with the Americans With Disabilities Act. | Safety/Traffic Management | 02/12/2010 | 02/12/2010 | 11/30/2010 | 571752 | 0
7272 | New York | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X731303 | A project to improve access on the Staten Island Expressway (I-278) between the Verrazano Narrows Bridge toll plaza and Renwick Avenue in Richmond County. Improvements will include the construction o | Bridge Replacement | 06/24/2010 | 06/24/2010 | 05/22/2012 | 39710000 | 1.15
7273 | New York | STATEWIDE |  | 12, 8 | X751064 | Rehabilitate the Brooklyn Bridge in Kings and New York counties. The project will repair and widen the ramps leading to the bridge in Brooklyn and Manhattan and the entire bridge will be repainted. Th | Bridge Improvement | 12/15/2009 | 12/15/2009 | 09/20/2013 | 30000000 | 0
7274 | New York | QUEENS | NEW YORK-NORTHEASTERN NJ (NJ) | 12 | X770613 | Rehabilitation of the Greenpoint Avenue Bridge over Newton Creek In Kings County. The project will replace deteriorated bridge deck material with a light weight grid deck. Replacement of cracked memb | Bridge Improvement | 12/24/2009 | 12/24/2009 | 01/05/2011 | 2500000 | 0
7275 | New York | BRONX | NEW YORK-NORTHEASTERN NJ (NJ) | 16 | X770623 | Painting and maintenance to extend the useful life of Bruckner Expressway Bridges in the Bronx County. | Bridge Improvement | 03/17/2010 | 03/17/2010 | 01/05/2011 | 3500000 | 0
7276 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 11, 13, 14, 15, 16, 8, 9 | X770633 | Rehabilitation of 12 concrete and steel bridges in Bronx, Kings, New York , Queens and Richmond counties. The work will include deck overlay, sidewalk improvements, joint sealing, painting, washing, u | Bridge Improvement | 01/29/2010 | 01/29/2010 | 01/05/2011 | 2500000 | 0
7277 | New York | NEW YORK | NEW YORK-NORTHEASTERN NJ (NJ) | 15 | X770643 | A project to mechanically and electrically rehabilitate the Wards Island pedestrian bridge. | Bridge Improvement | 03/25/2010 | 03/25/2010 | 06/15/2012 | 1500000 | 0
7278 | New York | STATEWIDE |  | 10, 12, 13, 15, 5, 6, 7, 9 | X805933 | Replace sign panels on highway s in Bronx, Kings, New York, Queens and Richmond counties. Approximately 150 overhead and 11 ground-mounted sign panels that are exhibiting deterioration, have lost refl | Safety/Traffic Management | 10/20/2009 | 10/20/2009 | 03/31/2011 | 1937815 | 0
7279 | New York | STATEWIDE |  | 15, 16, 17, 5, 7, 9 | X806253 | Repair and resurface approximately 45 miles of pavement on highways in Bronx, New York and Queens counties. In Bronx County, work will be done on the Major Deegan Expressway southbound lanes from the | Pavement Improvement | 09/09/2009 | 09/09/2009 | 09/02/2011 | 21630220 | 10.85
7280 | New York | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X806383 | Park & Ride Lot Expansion at Huguenot Ave, Richmond County | Transportation Enhancements | 10/01/2009 | 10/01/2009 | 05/14/2010 | 1942472 | 0
7281 | New York | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X806393 | Park & Ride Lot Expansion (Adding 159 Spaces) at Eltingville Transit Center- Richmond County | Other | 09/07/2009 | 09/07/2009 | 05/12/2010 | 2475075 | 0
7282 | New York | STATEWIDE |  | 10, 12, 13, 14, 15, 16, 17, 5, 6, 7, 8, 9 | X806463 | Repairs to Various State Highway Bridges- Richmond, Kings, Queens, New York and Bronx Counties | Bridge Improvement | 10/20/2009 | 10/20/2009 | 03/12/2012 | 8101708 | 0
7283 | New York | QUEENS | NEW YORK-NORTHEASTERN NJ (NJ) | 5, 9 | X806483 | Landscape enhancement on the right-of-way on the Long Island Expressway (Oceania Street to Cloverdale Boulevard) to include controlling noxious weeds, remove invasive species and establish native spec | Transportation Enhancements | 02/12/2010 | 02/12/2010 | 06/10/2013 | 1295450 | 0
7284 | New York | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) | 13, 5, 6, 9 | X806533 | THIS PROJECT WILL REPLACE SIGN PANELS, OVERHEAD AND GROUND MOUNTED, IN POOR CONDITION ON STATE HIGHWAYS WITH PANELS CONFORMING TO THE MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES. | Safety/Traffic Management | 12/23/2009 | 12/23/2009 | 04/29/2011 | 1714204 | 18.01
7285 | New York | BRONX |  | 15, 16 | XM09063 | Painting of South Bound Bruckner Expressway viaduct and ramps between RFK bridges and Sheridan Expressway to arrest the deterioration of the structure and extend its service life. | Bridge Improvement | 04/14/2010 | 04/14/2010 | 10/28/2011 | 20000000 | 0
7286 | North Carolina | FRANKLIN |  | 2 | 0001122 | This project will repave US 1 in Franklin County from Wake County line to NC 56 to improve road condition. Includes TIP project U-5125. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 10/30/2009 | 2159490 | 17.04
7287 | North Carolina | LEE |  | 2 | 0001123 | This project will repave US 1 in Lee County from US 1 Business to Farrell Road to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/20/2009 | 2116025 | 10.22
7288 | North Carolina | MOORE |  | 6 | 0001124 | This project will add paved shoulders on US 1 in Moore County from Morganton Road to Aiden Road to enhance safety. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/20/2009 | 1371666 | 16.37
7289 | North Carolina | VANCE |  | 2 | 0001133 | This project will repave the following roadways in Vance County to improve road condition: US 1 in Kittrell, US 1/158 Business from Henderson to the Warren County line, NC 39 from Rock Springs Road to | Pavement Improvement | 12/21/2009 | 06/02/2010 | 10/15/2010 | 2000000 | 24.05
7290 | North Carolina | BUNCOMBE |  | 11 | 000S531 | Preliminary engineering to rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for m | Other | 04/29/2009 | 04/29/2009 |  | 325250 | 0
7291 | North Carolina | JOHNSTON |  | 2 | 000S533 | Construct the Neuse River Greenway in Smithfield which includes a ten foot paved greenway from Wake County Line to Sam's Branch parallel to the Neuse River in Johnston County. This section of greenwa | Transportation Enhancements | 01/19/2010 | 06/16/2010 | 11/01/2011 | 1519294 | 3
7292 | North Carolina | CHOWAN |  | 1 | 000S534 | This project will clean and paint the structural steel on Bridge #26 over US 17 Bypass on SR 1234, Bridge #28 over US17 Bypass on SR 1319, Bridge #27 over NC 32 on US17 Bypass and Bridge #30 over the | Bridge Improvement | 06/15/2009 | 06/15/2009 | 11/04/2011 | 555850 | 0
7293 | North Carolina | CHOWAN |  | 1 | 000S536 | This project will relocate the lighthouse to a new foundation system, complete required hazardous material abatement, perform structural repairs, historic restoration and stabilization of the lighthou | Transportation Enhancements | 06/15/2009 | 08/17/2009 | 10/02/2010 | 841215 | 0
7294 | North Carolina | DAVIDSON |  | 13 | 000S538 | This project will repave the following roadways in Davidson County to improve road condition: NC 62 from NC 109 to the Randolph County line, NC 109 from Denton Road to north of Ben Lee Road, NC 150 f | Pavement Improvement | 05/22/2009 | 05/22/2009 | 11/01/2009 | 1784410 | 13.56
7295 | North Carolina | DAVIE |  | 5,6,12 | 000S540 | This project will repave the following roadways in Davidson and Davie Counties to improve road condition: US 64 from Lake Louise Golf Course to east of the Yadkin River, US 64-601 from US 158 to US 6 | Pavement Improvement | 06/12/2009 | 06/12/2009 | 11/30/2009 | 3384782 | 18.436
7296 | North Carolina | ROWAN |  | 6,12 | 000S541 | This project will repave various roadways in Rowan County, including the following, to improve road condition: Section of US 52, Section of NC 150, Section of NC 152, Section of NC 801, Sections of 8 | Pavement Improvement | 05/22/2009 | 05/22/2009 | 11/30/2009 | 4465640 | 38.693
7297 | North Carolina | STOKES |  | 5 | 000S542 | This project will repave various roadways in Stokes County, including the following, to improve road condition: US 52 from King City limits to Surry County line, Section of NC 65, Section of NC 66, S | Pavement Improvement | 06/12/2009 | 06/12/2009 | 11/30/2009 | 3226120 | 31.79
7298 | North Carolina | DURHAM | DURHAM | 4 | 000S564 | This project will provide for upgrades for traffic signals including the replacement of incandescent bulbs with LED inserts in signal heads, upgrade of undersized signal heads with LED signal heads an | Safety/Traffic Management | 10/19/2009 | 02/12/2010 | 09/30/2010 | 625600 | 0
7299 | North Carolina | FORSYTH |  | 5 | 000S568 | This project will repave Northwest Boulevard and construct sidewalk in Winston-Salem / Forsyth County to improve road condition and provide pedestrian accommodation. | Pavement Improvement | 08/11/2009 | 09/09/2009 | 05/10/2010 | 383584 | 0
7300 | North Carolina | HARNETT |  | 2 | 000S574 | The project (ER-5100F) will preliminary engineer Roadside Environmental Rehabilitation/Renovation projects in Highway Division 6 (Fayetteville). | Other | 11/01/2009 |  |  | 4720 | 0
7301 | North Carolina | STATEWIDE |  | 5, 12 | 000S577 | These funds will provide the preliminary engineering for the project that will renovate the landscape enhancement for the I-85 Rest Area in Davidson County and the I-40/US-52 landscape initiative in F | Other | 08/05/2009 | 08/05/2009 |  | 4311 | 0
7302 | North Carolina | STATEWIDE |  | 11 | 000S582 | The project will install landscape enhancement planting in Columbus at the US 74 and I-26 Interchange in Polk County and at the intersection of US 64 and Jones Cove Road in Haywood County. | Transportation Enhancements | 08/20/2009 | 01/12/2010 | 03/05/2010 | 94684 | 0.11
7303 | North Carolina | ORANGE | DURHAM | 4 | 000S588 | This project provides for the construction of a 10 foot multi-use asphalt trail including bridge over Jones Creek for the Twin Creeks Park Greenway in Orrange County. This is a locally administered p | Transportation Enhancements | 09/22/2009 | 03/01/2010 | 08/26/2010 | 429457 | 0
7304 | North Carolina | BUNCOMBE |  | 11 | 000S593 | Rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for motorists. | Bridge Improvement | 08/12/2009 | 04/20/2010 | 08/15/2010 | 4109972 | 0
7305 | North Carolina | BUNCOMBE |  | 11 | 000S594 | Rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for motorists. | Bridge Improvement | 11/16/2009 | 06/28/2010 | 09/30/2011 | 7031435 | 0
7306 | North Carolina | HENDERSON | ASHEVILLE | 11 | 000S597 | This project provides for the purchase of a transit bus fueled by compressed natural gas (CNG), and the construction of a CNG fueling station in Henderson County. | Other | 08/31/2009 |  | 09/20/2010 | 641347 | 0
7307 | North Carolina | HENDERSON |  | 11 | 000S605 | The project will install flowering tree seedlings for reforestation at the following locations: I-26 at US 25 in Henderson County, I-26 at US 74 in Polk County, US 64 from US 74 to NC 141 in Cherokee | Transportation Enhancements | 09/09/2009 | 12/11/2009 | 02/26/2010 | 187531 | 11.37
7308 | North Carolina | FORSYTH |  | 05 | 000S610 | The project (U-5195) will upgrade dynamic message signs at various locations in Forsyth county. | Safety/Traffic Management | 12/17/2009 | 03/02/2010 | 10/01/2010 | 500000 | 0
7309 | North Carolina | HERTFORD |  | 1 | 0011015 | This project will resurface NC 11 Business in Hertford County from NC 11 to the Aulander East City Limits to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 280500 | 2.1
7310 | North Carolina | HERTFORD |  | 1 | 0011017 | This project will resurface NC 11in Hertford County from SR 1130 (Modlin Hatchery Road) southward for 2.6 miles to the Bridge over Ahoskie Creek to improve road condition. | Pavement Improvement | 01/04/2010 |  | 06/30/2011 | 466553 | 2.6
7311 | North Carolina | MARTIN |  | 1 | 0011018 | This project will clean and paint the structural steel on Bridge #39 over the Roanoke River on NC 11 in Martin County to extend the life of the structure. | Bridge Improvement | 11/24/2009 |  | 12/15/2010 | 405583 | 0
7312 | North Carolina | HYDE |  | 3 | 0012036 | This project will resurface NC 12 from the Northern Ferry Dock to Ocracoke Village in Hyde County to improve road condition. Widen paved shoulders to accommodate bicycles will be added on a 3.26 mile | Pavement Improvement | 06/15/2009 | 06/15/2009 | 08/20/2010 | 2560811 | 12.98
7313 | North Carolina | HYDE |  | 3 | 0012037 | This project will construct a multi-use asphalt trail adjacent to NC 12 from Ocracoke Village to the National Park Service Campground in Hyde County to enhance pedestrian and bicycle access and safety | Transportation Enhancements | 06/15/2009 | 06/15/2009 | 08/20/2010 | 627400 | 3.1
7314 | North Carolina | DARE |  | 3 | 0012039 | This project will resurface NC 12 from National Park Service Boundary South of Salvo to 8 miles south of the National Park Service Boundary in Dare County to improve road condition. | Pavement Improvement | 01/12/2010 |  | 06/11/2011 | 1000000 | 8
7315 | North Carolina | HERTFORD |  | 1 | 0013028 | This project will strengthen and resurface US 13 in Hertford County from SR 1130 (Modlin Hatchery Road) to NC 461 to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 10/30/2009 | 487952 | 4.2
7316 | North Carolina | HERTFORD |  | 1 | 0013029 | Replace deficient bridges #12 and #25 carrying US 13 over Ahoskie Creek and Ahoskie Creek Overflow in Hertford County. | Bridge Replacement | 04/21/2009 | 04/21/2009 | 10/28/2011 | 3060409 | 0.23
7317 | North Carolina | BERTIE |  | 1 | 0013031 | This project will resurface US 13-US 17 from the Roanoke River to Saint Francis Road in Bertie County to improve road condition. | Pavement Improvement | 11/10/2009 | 04/05/2010 | 06/15/2010 | 1236936 | 4.92
7318 | North Carolina | BERTIE |  | 1 | 0013032 | This project will level existing pavement and resurface US 13/US 17 in Bertie County from SR 1106( St. Francis Road) to SR 1102 (Pleasant Oak Road) to improve road condition. | Pavement Improvement | 11/10/2009 | 04/05/2010 | 06/15/2010 | 1018267 | 3.44
7319 | North Carolina | GRANVILLE, ORANGE |  | 13 | 0015020 | This project will repave US 15 in Granville County from Tar River Road south of Oxford to Industry Drive in Oxford to improve road condition. | Pavement Improvement | 11/16/2009 |  | 10/15/2010 | 3127240 | 8.63
7320 | North Carolina | ORANGE |  | 4 | 0015026 | Thie project provides for the construciton of the Morgan Creek Greenway, Phase I, to improve pedestrian access from US 15/501 (Culbeth Road) to Smith Level Road in Orange County. This project is loc | Transportation Enhancements | 10/14/2009 | 03/01/2010 | 03/01/2011 | 300000 | 0
7321 | North Carolina | CHATHAM | DURHAM | 4 | 0015027 | Preliminary engineering for pedestrian enhancements to traffic signals and sidewalks on East and/or the west side of US 15-501 in the Cole Park area north to the Orange County line using the existing | Transportation Enhancements | 06/23/2009 | 07/09/2009 | 06/15/2010 | 157013 | 2.338
7322 | North Carolina | CHATHAM | DURHAM | 8 | 0015028 | This project will renovate the existing landscape enhancement US 421 & US 64 in Chatham County. | Transportation Enhancements | 06/23/2009 | 07/09/2009 | 06/15/2010 | 30913 | 2.338
7323 | North Carolina | ORANGE | DURHAM | 4 | 0015029 | This projet provides for the construction of sidewalk ro increase pedestrain safety and mobility on US 15/501/NC 54 from SR 1902 (Manning Drive) to Old Mason Farm Road in Orange County. This is a loc | Transportation Enhancements | 09/21/2009 | 01/13/2010 | 06/24/2010 | 142613 | 0.28
7324 | North Carolina | DURHAM |  | 04 | 0015030 | The project (R-5164C) will resurface US 15/501 Business south from NC 98 to US 15/501 Business; US 15/501 Business north from US 15/501 to NC 98, US 15/501 Business from US 15/501 to SR 1361 (Vickers | Pavement Improvement | 12/17/2009 | 05/19/2010 |  | 960790 | 2.9
7325 | North Carolina | ORANGE |  | 4 | 0015031 | The project (ER-5100GE) will provide plantings on US 15/501 at Erwin Road/Europa Drive intersection in Orange county. | Transportation Enhancements | 11/10/2009 |  | 04/30/2012 | 65000 | 0
7326 | North Carolina | MECKLENBURG |  | 9 | 0016045 | This project inlcudes landscaping on NC 16 within construction project limits from South of SR 2948 (Marvin School Road) in Uniton County to South of I-185 in Mecklenburg County to enhance aesthetics | Transportation Enhancements | 04/10/2009 |  |  | 162864 | 3.35
7327 | North Carolina | UNION | CHARLOTTE | 9 | 0016046 | This project includes turning lane radius improvements, traffic signal upgrades and a railroad crossing upgrade in Waxhaw on NC 16 at the NC 75 intersection to improve intersection operations and safe | Pavement Improvement | 05/13/2009 | 05/13/2009 | 09/17/2010 | 734744 | 0
7328 | North Carolina | WILKES |  | 5 | 0016047 | This project will rehabilitate pavement and improve guardrail on NC 16 N from SR 1559 (Old NC 16) to the Ashe County line in Wilkes County to improve road condition and safety. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/31/2009 | 1602356 | 9.35
7329 | North Carolina | ASHE |  | 5 | 0016048 | This project will rehabilitate pavement and improve guardrail on NC 16 from NC 88 to the Virginia line in Ashe County to improve road condition and safety. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 12/31/2009 | 2311563 | 13.125
7330 | North Carolina | MARTIN |  | 1 | 0017089 | This project will mill asphalt from existing pavement and resurface US 17 Business in Williamston from NC 125 to 0.7 miles east to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 190643 | 0.66
7331 | North Carolina | PERQUIMANS |  | 1 | 0017090 | This project will resurface US 17 in Perquimans County from SR 1101 (Bear Swamp Road) to SR 1302 (Union Hall Road) to improve road condition. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 07/10/2010 | 2373375 | 15.4
7332 | North Carolina | NEW HANOVER, BRUNSWICK |  | 7 | 0017097 | Construct US 17 Bypass (Future I-140) from NC 87 to US 74-76 in Brunswick County. Route will be a four lane divided freeway to alleviate congestion on surrounding roadways. | New Bridge Construction | 10/13/2009 | 03/29/2010 | 10/15/2013 | 14725487 | 6.1
7333 | North Carolina | PASQUOTANK |  | 1 | 0017098 | This project will resurface four sections of the US 17 Bypass of Elizabeth City to eliminate ponding of water on roadway and improve safety conditions.. | Pavement Improvement | 11/24/2009 |  | 10/01/2010 | 231511 | 2.3
7334 | North Carolina | PASQUOTANK |  | 1 | 0017100 | The project (ER-5100AC) will provide reforestation on US 17 (Elizabeth City Bypass) in Pasquotank county. | Transportation Enhancements | 10/28/2009 |  |  | 76000 | 7.4
7335 | North Carolina | ROBESON |  | 7 | 0017101 | The project will renovate and improve existing landscape enhancement in Maxton at the NC 71 and I-74 Interchange in Robeson County | Transportation Enhancements | 09/24/2009 | 03/03/2010 | 04/30/2010 | 68609 | 0
7336 | North Carolina | PASQUOTANK |  | 1 | 0017104 | ER-5100AE - This project will provide Czip Planting at the US 17 Bypass/US 17 Interchange in Pasquotank County, North Carolina. | Transportation Enhancements | 02/09/2010 |  |  | 145500 | 0
7337 | North Carolina | PERQUIMANS |  | 1 | 0017105 | The project (ER-5100AF) will repair critical eroding slopes on US 17 in Perquimans county. | Transportation Enhancements | 11/24/2009 |  |  | 101500 | 30.376
7338 | North Carolina | MARTIN |  | 1 | 0017106 | B-4576 - Replace Bridge #6 On US 17 Southbound Over Ready Branch in Martin County, North Carolina. | Bridge Replacement | 02/18/2010 |  | 04/15/2011 | 975000 | 0
7339 | North Carolina | ALLEGHANY |  | 5 | 0018014 | This project will add a left turn lane on NC 18 from SR 1173 (Tayson Rd) to SR 1138 (Osborne Rd) and realign Osborne Rd to improve safety and mobility. | Pavement Improvement | 03/15/2010 | 04/07/2010 | 08/15/2010 | 408783 | 0.54
7340 | North Carolina | MONTGOMERY |  | 8 | 0024036 | Widen NC 24-27 in Biscoe / Montgomery County, between US 220A and Future I-73/74, to enhance safety and mobility. | Pavement Widening | 03/02/2009 | 03/02/2009 | 08/01/2011 | 4541752 | 0.909
7341 | North Carolina | MOORE |  | 6 | 0024037 | This project will widen NC 24-27 in Moore County and add turn lanes, from Montgomery County line to NC 705, to enhance safety and mobility. | Pavement Widening | 03/26/2009 | 03/26/2009 | 06/25/2010 | 3313779 | 9.4
7342 | North Carolina | STANLY |  | 8 | 0024038 | This project will inlcude landscaping in Albemarle within the construction project limits from East of Big Bear Creek to SR 1963 (St. Martin Road) to enhance aesthics when ,otorists enter the Albemarl | Transportation Enhancements | 06/08/2009 |  |  | 140280 | 5.8
7343 | North Carolina | STANLY |  | 8 | 0024042 | This project includes resurfacing NC 740 from SR 1730 (Vickers Store Rd) to Island in Stanly County. Milling and resurfacing NC 24/27 from NC 740 to Bird St in Stanly County. Pavement rehabilitation | Pavement Improvement | 11/17/2009 |  | 07/30/2010 | 1919233 | 7.28
7344 | North Carolina | BUNCOMBE |  | 11 | 0025025 | Preliminary engineering for the installation of trees, shrubs, and flowering plants as well as hardscape items and native grasses in Asheville on future I-26, Exit 23, interchange in Woodfin and I-2 | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 06/30/2011 | 214051 | 0
7345 | North Carolina | ROCKINGHAM |  | 13 | 0029044 | This project will repair and rehabilitate concrete pavement and shoulders on US 29 in Rockingham County from Guilford County line to Troublesome Creek to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 10/16/2009 | 1712661 | 3.89
7346 | North Carolina | ROCKINGHAM |  | 13 | 0029045 | Repair bridge expansion joints on 8 structures: Bridge 23 on US 29 Business, Bridge 116 on SR 2600, Bridge 134 on NC 700, Bridge 168 on NC 14/87, Bridge 169 on NC 770, Bridge 124 on SR 2177, Bridge 1 | Bridge Improvement | 07/28/2009 | 12/29/2009 | 05/29/2010 | 123202 | 0.045
7347 | North Carolina | GUILFORD |  | 12, 13 | 0029046 | The project will install landscape enhancement plantings in Greensboro on US 29 from SR 4240 (Lee Street) to 16th Street in Guilford County. Includes TIP project ER-5100GC. | Transportation Enhancements | 10/22/2009 | 01/26/2010 | 04/30/2012 | 181542 | 3.1
7348 | North Carolina | GUILFORD |  | 12,13 | 0029047 | Upgrade Electrical Wiring System And Replace Metal Breakaway Poles On US 29 From I-40/I-85 Business To Phillips Avenue In Guilford County, North Carolina | Safety/Traffic Management | 01/22/2010 |  | 12/31/2010 | 488216 | 3.1
7349 | North Carolina | GUILFORD | GREENSBORO | 13 | 0029048 | The project (U-5202) will upgrade fiberglass poles with metal breakaway poles and install high mast lighting at interchanges on US 29 from Phillips Avenue to north of SR 2835 (McKnight Mill Road) in G | Pavement Improvement | 12/21/2009 |  | 07/31/2011 | 605874 | 1.5
7350 | North Carolina | NORTHAMPTON |  | 1 | 0035005 | This project will resurface NC 35 in Northampton County from US 158 to SR 1545 (Buck Boone Road) to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 11/13/2009 | 285500 | 2.2
7351 | North Carolina | PERQUIMANS |  | 1 | 0037002 | The project will replace Culvert #6 with a new aluminum culvert for Burnt Mill Creek on NC 37 at the Perquimans/Chowan County Line in Perquimans County. | Bridge Replacement | 08/17/2009 | 08/17/2009 | 07/31/2010 | 313120 | 0
7352 | North Carolina | JOHNSTON |  | 2 | 0042020 | This project provides improvements to increase safety and mobility on NC 42 at the intersection with SR 1010 (Cleveland Road) in Johnston County. | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/15/2009 | 760513 | 0
7353 | North Carolina | PITT |  | 3 | 0043012 | This project adds sidewalks along the southwest side of NC43 in Greenville from US 264A to Red Banks Road in Pitt County to improve pedestrian safety. | Transportation Enhancements | 08/18/2009 | 09/11/2009 | 06/29/2010 | 60090 | 0.5
7354 | North Carolina | CRAVEN |  | 1 | 0043013 | This project will resurface and do minimal widening on NC 43 from US 17 South to Bosch Boulevard in Craven County to improve road condition. | Pavement Improvement | 09/21/2009 |  | 11/15/2010 | 2722008 | 8.6
7355 | North Carolina | WASHINGTON |  | 1 | 0045004 | This project will replace deficient Bridge #1 over a canal on NC 45/99 0.6 miles north of the Hyde County line in Washington County. | Bridge Improvement | 08/05/2009 | 08/05/2009 | 06/28/2010 | 306410 | 0
7356 | North Carolina | BERTIE |  | 1 | 0045006 | This project will perform concrete and steel repairs to the bridge supports, replace five leaking construction joints and finger joints at the ends of the bridge span and clean & paint structural ste | Bridge Replacement | 12/21/2009 |  | 06/30/2011 | 1805645 | 0
7357 | North Carolina | NORTHAMPTON |  | 1 | 0048006 | This project will resurface NC 48 in Northampton County from SR 1200 (James Jones Road) to the Gaston East City Limits to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 11/13/2009 | 250000 | 2.66
7358 | North Carolina | PERSON |  | 13 | 0049027 | This project will repave the following roadways in Person County to improve road condition: NC 49 from south of Salem Church Road to Hassell Horton Road, NC 49 from Roxboro southern city limits to US | Pavement Improvement | 11/09/2009 |  | 11/01/2010 | 1557725 | 8.63
7359 | North Carolina | STATEWIDE | RALEIGH | 4, 13 | 0050011 | This project will perform a comprehensive Corridor Study on NC 50 From I-540 in Wake County to the City of Creedmoor in Granville County to identify alternatives for easing congestion and managing are | Other | 09/24/2009 | 01/21/2010 | 12/31/2010 | 200000 | 0
7360 | North Carolina | MECKLENBURG |  | 9 | 0051028 | This project will widen NC 51 from the South Carolina state line to SR 3645 (Downs Circle) in Mecklenburg County to improve safety and mobility. | Pavement Widening | 03/02/2009 | 03/02/2009 | 11/24/2010 | 5560529 | 1.063
7361 | North Carolina | MECKLENBURG |  | 9 | 0051030 | U-5199 - This project will lengthen the left turn lanes on NC 51 at NC 51 at Fullwood Lane and Monroe Road in Matthews, Mecklenbug county, North Carolina. | Pavement Improvement | 01/21/2010 |  |  | 225000 | 0
7362 | North Carolina | SURRY |  | 5 | 0052033 | This project will rehabilitate pavement on US 52 from Stokes County line to SR 1815 (Cooke School Rd) in Surry County to improve road condition. | Pavement Improvement | 08/05/2009 | 10/13/2009 | 06/15/2010 | 3247234 | 31.96
7363 | North Carolina | STOKES |  | 05 | 0052036 | The project (R-5174A) will overlay existing pavement with an ultrathin bonded wearing course on US from the King city limits to the Surry county line in Stokes county. | Pavement Improvement | 12/17/2009 | 04/01/2010 | 08/15/2010 | 100000 | 9.61
7364 | North Carolina | STANLY |  | 08 | 0052037 | The project (ER-5100JE) will landscape US 52 and NC 24/27/73 interchange in Albemarle, Stanley county. | Transportation Enhancements | 12/15/2009 |  |  | 35000 | 0
7365 | North Carolina | HARNETT | RALEIGH | 2 | 0055041 | This project will resurface NC 55 from NC 210 to SR 1415 (Rawls Church Raod) to imporve road condition in Harnett County. | Pavement Improvement | 09/09/2009 | 01/27/2010 | 07/16/2010 | 321689 | 0.48
7366 | North Carolina | DURHAM |  | 4 | 0055042 | This project will add turn lanes on NC 55 in Durham at the Riddle Road intersection to enhance safety and improve mobility. | Pavement Improvement | 08/03/2009 | 08/03/2009 | 10/30/2009 | 275900 | 0
7367 | North Carolina | ORANGE |  | 4 | 0057004 | This project will repave NC 57 and add two foot paved shoulders in Orange County from NC 86 to SR 1544 (Pearson Road) to improve road condition. | Pavement Improvement | 08/04/2009 | 04/05/2010 | 07/30/2010 | 1214026 | 6.34
7368 | North Carolina | CARTERET |  | 3 | 0058011 | Construct the Emerald Isle Bike Path in Emerald Isle which includes a 10 feet multiuse path along NC58 from Black Skimmer Drive (MP 19) to the Regional Beach Access (MP 15) and future site of the new | Transportation Enhancements | 07/16/2009 | 01/04/2010 | 06/30/2010 | 478171 | 2
7369 | North Carolina | ALAMANCE |  | 6 | 0062008 | Repair bridge expansion joints four (4) structures: Bridge 12 on NC 62, Bridge 109 on SR 2309, Bridge 115 on SR 1154 and Bridge 75 on SR 1158 in Alamance County to extend the life of the structures. | Bridge Improvement | 08/05/2009 | 08/05/2009 | 05/29/2010 | 123202 | 0
7370 | North Carolina | MARTIN |  | 1 | 0064117 | This project will mill asphalt from existing pavement and resurface US 64 in Martin County from the Jamesville East City Limit to west of Sweetwater Creek to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 10/01/2009 | 3018256 | 19.42
7371 | North Carolina | MARTIN |  | 1 | 0064118 | This project will resurface US 64 from Edgecombe County Line to US 64 Alternate in Williamston in Martin County to improve road condition. | Pavement Improvement | 05/06/2009 | 05/06/2009 | 11/15/2010 | 6440404 | 36.8
7372 | North Carolina | TYRRELL |  | 3 | 0064119 | This project will resurface US 64 in Tyrrell County from the Bridge over the Alligator River westward for 3 miles to improve road condition. | Pavement Improvement | 04/15/2009 | 08/24/2009 | 11/13/2009 | 313643 | 3
7373 | North Carolina | WAKE |  | 2, 13 | 0064120 | This project will repave US 64 and US 264 in Wake and Franklin Counties from US 64 / US 264 interchange to Nash County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/01/2009 | 7074430 | 30.92
7374 | North Carolina | ALEXANDER |  | 5 | 0064121 | This project will resurface US 64 from NC 90 in Iredell County to NC 90 in Alexander County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 10/16/2009 | 2510843 | 18.12
7375 | North Carolina | NASH |  | 2, 3 | 0064122 | This project will resurface US 64 from the Franklin County Line to Winstead Avenue in Nash County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/15/2009 | 3822437 | 46.36
7376 | North Carolina | EDGECOMBE, NASH |  | 2, 3 | 0064123 | This project will resurface US 64 from Winstead Avenue in Nash County to the Tar River Bridge in Edgecombe County to improve road condition. | Pavement Improvement | 04/10/2009 | 04/10/2009 | 11/15/2009 | 7800702 | 38.42
7377 | North Carolina | DARE |  | 3 | 0064125 | This project will clean and paint the structural steel of Bridge #9 (Old Manns Harbor Bridge) carrying US 64 over Croatan Sound in Dare County to extend the life of the structure. | Bridge Replacement | 06/15/2009 | 06/15/2009 | 11/04/2011 | 3529350 | 0
7378 | North Carolina | DARE |  | 3 | 0064126 | This project will construct a stormwater wetland at the corner of US64/264 Business and Greenville Street in Manteo, NC in Dare County. This saltwater wetland will be used to treat stormwater runoff | Other | 09/24/2009 | 09/24/2009 | 05/11/2010 | 236913 | 0
7379 | North Carolina | EDGECOMBE |  | 1 | 0064130 | This is the preliminary engineering for the project that will focus efforts to improve enhancement of the landscape at the interchanges US 64 / US 258 and US 64 / McNair Road in Halifax County. | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 12/15/2010 | 96055 | 0
7380 | North Carolina | NASH |  | 1,2,3 | 0064131 | This is the preliminary engineering for the project that will improve the landscape at the interchanges US 64 / Buck Leonard Boulevard and I-95 / NC 481 in Nash and Halifax Counties. | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 12/15/2010 | 107694 | 0
7381 | North Carolina | MARTIN |  | 1 | 0064132 | This project will mill asphalt pavement from US 64 Alt. in Williamston and resurface with new asphalt pavement from SR 1446 (Sycamore St.) to SR 1445 (Main Street) to improve road condition. | Pavement Improvement | 09/24/2009 |  | 11/30/2010 | 734049 | 2.6
7382 | North Carolina | TYRRELL |  | 3 | 0064135 | This project will provide concrete repairs to the bridge supports and clean & paint the structural steel on Bridge #7 over the Alligator River on US 64 at the Tyrrell/Dare County Line to extend the li | Bridge Improvement | 12/16/2009 | 04/01/2010 | 06/30/2011 | 1260513 | 0
7383 | North Carolina | MACON |  | 11 | 0064137 | The project (R-5203) will construct left turn lanes on US 64 at the intersections of SR 1516 (Sanders Road), SF 1517 (Bethel Church Road) and SR 1533 (Walnet Creek Road) in Macon county. | Pavement Improvement | 11/19/2009 | 12/02/2009 | 07/30/2010 | 673839 | 0.611
7384 | North Carolina | TYRRELL, WASHINGTON |  | 1 | 0064138 | The project (ER-511AD) will provide reforestation using Atlantic White Cedar on US 64 in Washington and Tyrell counties. | Transportation Enhancements | 09/24/2009 | 01/25/2010 | 04/01/2010 | 145000 | 0
7385 | North Carolina | ROCKINGHAM |  | 13 | 0065007 | Replace deficient bridge Number 54 carrying NC 65 over Rock House Creek in Rockingham County. | Bridge Replacement | 11/09/2009 | 02/08/2010 | 11/01/2010 | 1283747 | 0
7386 | North Carolina | GUILFORD |  | 6 | 0068012 | This project will repave, widen and add trun lanes on NC 68 in Guilford County from SR 2011 (Edgefield Road) south of Oak Ridge to NC 65 north of Stokesdale to improve road condition. | Pavement Widening | 07/21/2009 | 04/12/2010 | 07/31/2010 | 1572439 | 4.38
7387 | North Carolina | GUILFORD |  | 12 | 0068013 | This project provides for improvements at the intersection of NC 68 (Westchester Avenue) and Burton Street of adding turn lanes, revising the signals and improving draininge to increase safety and mob | Pavement Improvement | 09/23/2009 |  | 11/06/2010 | 318603 | 0
7388 | North Carolina | GUILFORD |  | 6, 12 | 0068014 | This project provides for improvements at the intersection of NC 68 (Westchester Avenue) and Clinard Farms Road of adding turn lanes and improving draininge to increase safety and mobility in Guilford | Pavement Improvement | 09/23/2009 |  | 11/06/2010 | 77433 | 0
7389 | North Carolina | CLAY |  | 11 | 0069006 | The project (R-5204) will construct a center turn lane and improve access management on NC 69 from north of US 64 to south of SR 1118 in Clay county. | Pavement Improvement | 01/12/2010 | 03/22/2010 | 06/30/2011 | 1512370 | 1.004
7390 | North Carolina | JOHNSTON |  | 2 | 0070121 | This project will provide improvements to increase safety and mobility on US 70 Business at the SR 1553 (Shotwell Road) intersection in Johnston County. | Pavement Improvement | 11/09/2009 | 03/01/2010 | 04/15/2010 | 77203 | 0
7391 | North Carolina | ORANGE |  | 4 | 0070127 | Repair bridge expansion joints on one (1) structure: Bridge 6 on US 70 in Orange County to extend the life of the structure. | Bridge Improvement | 07/28/2009 | 01/25/2010 | 05/29/2010 | 26753 | 0
7392 | North Carolina | ALAMANCE |  | 6,13 | 0070129 | This project will repave US 70 (Church Street) in Burlington / Alamance County, from SR 1716 (Graham-Hopedale Road) to NC 62 to improve road condition. Includes TIP project R-5175B. | Pavement Improvement | 08/17/2009 | 03/17/2010 | 09/17/2010 | 1897335 | 11.17
7393 | North Carolina | JOHNSTON |  | 02 | 0070134 | The project (ER-5100DE) will provide roadside landscape enhancement and establishment on US 70 (Clayton Bypass) in Johnston county. | Transportation Enhancements | 12/28/2009 |  |  | 318423 | 0
7394 | North Carolina | STANLY |  | 8 | 0073019 | Replace deficient bridge carrying NC 73 over Long Creek in Stanly County. | Bridge Replacement | 03/02/2009 | 03/02/2009 | 12/31/2010 | 3020655 | 0
7395 | North Carolina | CABARRUS |  | 8 | 0073020 | "This project includes construction to repair drainage and pavement issues in Mount Pleasant on NC 73 from east of the City Limits to SR 1411 (Cold Springs Road) as follows: Project 1: Removes the ex | Pavement Improvement | 06/02/2009 | 06/02/2009 | 12/31/2010 | 531623 | 11.004
7396 | North Carolina | MECKLENBURG | CHARLOTTE | 9 | 0073021 | Widen NC 73 from US 21 to NC 115 in Mecklenburg County to improve safety and mobility. | Pavement Widening | 09/21/2009 | 09/21/2009 | 11/15/2012 | 21684048 | 1.19
7397 | North Carolina | RICHMOND |  | 6 | 0073022 | B-4614 - This project will replace bridge 41 on NC 73 over Naked Creek in Richmond county, North Carolina. | Bridge Replacement | 02/09/2010 | 06/02/2010 | 09/17/2010 | 1000000 | 0
7398 | North Carolina | CLEVELAND |  | 10 | 0074104 | This project will resurface US 74 from SR 1170 (Lucas Rd) to West Lee in Cleveland County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/02/2009 | 1515551 | 3.066
7399 | North Carolina | SWAIN |  | 11 | 0074105 | This project will rehabilitate pavement on US 74 from SR 1159 (Spring St) to the Jackson County line in Swain County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 12/15/2009 | 6108843 | 9.74
7400 | North Carolina | ANSON |  | 8 | 0074108 | This project will include pavement rehabilitation, paved shoulders, and guardrail on US 74 westbound from beginning of divided highway west of SR 1259 to Union County line in Anson County, improving r | Pavement Improvement | 09/09/2009 | 05/07/2010 | 07/02/2010 | 3215394 | 10.8
7401 | North Carolina | ANSON |  | 8 | 0074109 | The project (U-5196) will mill and surface US 74 from NC 109 to west of North Park Road in Anson county. | Pavement Improvement | 01/07/2010 |  | 11/15/2010 | 313772 | 1.48
7402 | North Carolina | LEE |  | 2 | 0078004 | This project will widen NC 78 in Sanford / Lee County, from Tramway to beyond St. Andrews Road, to enhance safety and mobility. | Pavement Widening | 03/26/2009 | 03/26/2009 | 04/30/2010 | 1939063 | 2.45
7403 | North Carolina | CASWELL |  | 13 | 0086008 | This project will repave NC 86 in Caswell County from NC 119 to US 158, including shoulders, to improve road condition. | Pavement Improvement | 08/04/2009 | 07/19/2010 | 08/06/2010 | 1379720 | 7.813
7404 | North Carolina | ORANGE | DURHAM | 4 | 0086010 | R-5178B - This project will mill, resurface and replace curb and gutter on NC 86 from SR 1010 (Franklin Street) to Cameron Avenue in Chapel Hill, Orange county, North Carolina. | Pavement Improvement | 08/04/2009 |  | 08/13/2010 | 181152 | 0.2
7405 | North Carolina | ALAMANCE |  | 6 | 0087022 | This project provides for the replacement of existing signal poles & mast arms at the NC 87 (Webb Avenue) and Elmira Street intersection to improve road conditions in Alamance County. | Other | 08/05/2009 | 08/05/2009 | 02/16/2010 | 2484 | 0.62
7406 | North Carolina | BLADEN |  | 07 | 0087024 | The project (ER-5100FF) will provide Czip planting on NC 87 north from SR 1356 (Pearl Lloyd Road) to SR 1308 (Old NC 20) in Bladen county. | Transportation Enhancements | 01/04/2010 | 05/17/2010 | 06/30/2010 | 45000 | 0.47
7407 | North Carolina | ALLEGHANY |  | 5 | 0093003 | This project will rehabilitate pavement on NC 93 from US 221 to SR 1337 (Mt. Carmel Rd) in Alleghany County to improve road condition. This project includes TIP R-5157. | Pavement Improvement | 06/22/2009 | 07/01/2009 | 07/01/2010 | 1208490 | 10
7408 | North Carolina | DURHAM |  | 4 | 0098025 | This project will repave NC 98 in Durham County from Junction Road to Sherron Road to improve road condition. | Pavement Widening | 05/13/2009 | 05/13/2009 | 05/14/2010 | 1284838 | 0
7409 | North Carolina | FRANKLIN |  | 2 | 0098026 | This project will repave the following roadways in Franklin County to improve road condition: NC 98 from US 401 to Bunn and US 1A from US 1 to NC 56 in Franklinton. | Pavement Improvement | 11/09/2009 |  | 11/01/2010 | 2471341 | 9.83
7410 | North Carolina | CUMBERLAND | FAYETTEVILLE | 2 | 0100017 | This project will perform grading and construct the bridges on the future I-295 Fayetteville Outer Loop in Cumberland County from Bragg Boulevard to Murchison Road for a four lane divided highway. Pa | Pavement Widening | 04/21/2009 | 04/21/2009 | 07/01/2012 | 54501720 | 1.39
7411 | North Carolina | JACKSON |  | 11 | 0107011 | The project (R-5202) will widen pavement and shoulders, improve drainage and construct a left turn late on NC 107 at SR 1145 in Jackson county. | Pavement Improvement | 01/06/2010 |  | 11/01/2010 | 2470302 | 0.784
7412 | North Carolina | WILKES |  | 5 | 0115005 | R-5159 - This project will widenen and rehabilitate pavement on NC 115 from US 421 to the Iredell county line in Wilkes county, North Carolina. | Pavement Improvement | 02/05/2010 | 05/04/2010 | 11/15/2010 | 3749661 | 8.1
7413 | North Carolina | ALAMANCE |  | 6, 13 | 0119003 | This project will repave NC 119 with two foot shoulders in Alamance County from the Mebane north city limits to the Caswell County line to improve road condition. | Pavement Improvement | 11/16/2009 | 03/18/2010 | 05/17/2010 | 1811017 | 9.998
7414 | North Carolina | GRAHAM |  | 11 | 0129002 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 10 over East Buffaloe Creek on US 129 in Graham County to extend the life of the structure. | Bridge Improvement | 10/15/2009 | 10/15/2009 | 02/01/2010 | 1137716 | 0
7415 | North Carolina | CHEROKEE |  | 11 | 0141005 | This project will rehabilitate pavement on NC 141 from US 64 to US 74 in Cherokee County to improve road condition. | Pavement Improvement | 07/08/2009 | 07/08/2009 | 11/15/2010 | 2468528 | 16.22
7416 | North Carolina | CAMDEN |  | 3 | 0158040 | This project will widen US 158-NC 34 from East of the Pasquotank River in Elizabeth City to North of Havenwood Road in Camden County from two lanes to multi-lanes to improve traffic operations and im | Pavement Widening | 03/02/2009 | 03/02/2009 | 08/01/2011 | 7057343 | 3.855
7417 | North Carolina | DARE |  | 3 | 0158042 | This project will perform renovations to the existing buildings at the Kitty Hawk Rest Area on US 158 including replacement of wall tile and plumbing fixtures, addition of an ADA compliant family rest | Pavement Improvement | 05/26/2009 | 05/26/2009 | 05/16/2010 | 209000 | 0
7418 | North Carolina | NORTHAMPTON |  | 1 | 0158043 | This project will resurface US 158 from Halifax County Line to multi-lane section west of Hertford County Line in Northampton County to improve road condition. | Pavement Improvement | 08/05/2009 | 08/05/2009 | 11/15/2011 | 7710316 | 28.19
7419 | North Carolina | HERTFORD |  | 1 | 0158048 | The project (ER-5100AA) will renovate existing plantings and add additional plant material on US 158 Business from SR 1300 (Wise Store Road) to 0.2 miles east of SR 1335 (Lance Road) and along US 258 | Transportation Enhancements | 10/28/2009 |  | 05/31/2011 | 108967 | 1.899
7420 | North Carolina | NORTHAMPTON |  | 1 | 0158049 | ER-5100AB - This project will provide for the installation of enhancement plantings at three ""Welcome to Garysburg"" signs on US 158, US 301 and NC 46 in Northampton county, North Carolina." | Transportation Enhancements | 02/09/2010 |  | 05/31/2011 | 31969 | 0
7421 | North Carolina | HENDERSON |  | 11 | 0176006 | This project will rehabilitate pavement on US 176 from NC 225 to US 25 in Henderson County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 12/15/2009 | 2496038 | 4.98
7422 | North Carolina | RICHMOND |  | 8 | 0177003 | The project will install landscape enhancement plantings at the NC 177 and SR1900 Battlet Dairy Road interchange in Richmond County. | Transportation Enhancements | 09/21/2009 | 11/30/2009 | 02/26/2009 | 23492 | 0
7423 | North Carolina | AVERY |  | 5 | 0194010 | This project will rehabilitate pavement and widen NC 194 from US 221 to US 19 E in Avery County to improve road condition and safety. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 06/01/2010 | 1030620 | 4.2
7424 | North Carolina | BEAUFORT |  | 3 | 0207002 | The project (ER-5100BD) will provide picnic tables with shelters, bike rack with concrete pad and concrete trash cans at the Bayview Beach Ferry Terminal in Beaufort county. | Transportation Enhancements | 10/23/2009 |  | 03/15/2010 | 25000 | 0
7425 | North Carolina | TRANSYLVANIA |  | 11 | 0215004 | This project will install and revise guardrail on NC 215 from US 64 to the Haywood County line in Transylvania County to improve safety. | Safety/Traffic Management | 05/13/2009 | 05/13/2009 | 08/01/2010 | 2257227 | 16.82
7426 | North Carolina | UNION |  | 8, 9 | 0218008 | This project will rehabilitate pavement on NC 218 from east of I-485 to west of US 601 in Mecklenburg and Union Counties to improve road condition. | Pavement Improvement | 06/16/2009 | 07/08/2009 | 09/30/2011 | 1736308 | 6.96
7427 | North Carolina | UNION |  | 8,9 | 0218009 | This project will rehabilitate pavement on NC 218 from east of US 601 to west of NC 205 in Union County to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 10/30/2009 | 3330424 | 10.93
7428 | North Carolina | UNION |  | 8 | 0218010 | This project will rehabilitate pavement on NC 218 from east of NC 205 to US 74 in Anson and Union Counties to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 11/20/2009 | 3300000 | 13.65
7429 | North Carolina | UNION | CHARLOTTE | 8,9 | 0218011 | Widening for turn lanes on NC 218 @ NC 205, Also widening for turn lanes on US 601 @ NC 218. | Pavement Widening | 05/07/2009 | 05/07/2009 | 09/30/2009 | 567418 | 0
7430 | North Carolina | UNION |  | 8,9,12 | 0218012 | This project will construct three filtration basins and a stormwater wetland for the purpose of treating stormwater runoff, from the intersection of US 601 and NC 218 in Union County, before dischargi | Other | 09/15/2009 | 09/15/2009 | 02/15/2010 | 138349 | 0
7431 | North Carolina | ROCKINGHAM |  | 13 | 0220041 | This project will repave US 220 in Rockingham County from NC 135 to the Virginia State line to improve road condition. Includes TIP project R-5180 | Pavement Improvement | 09/08/2009 |  | 09/24/2010 | 2870657 | 18.64
7432 | North Carolina | RANDOLPH |  | 2 | 0220044 | Landscape Planting Renovation on US 220 At US 64 And SR 1713 (Albemarle Road) Interchanges In Randolph County, North Carolina | Transportation Enhancements | 10/29/2009 | 02/09/2010 | 03/31/2010 | 138170 | 0
7433 | North Carolina | LENOIR |  | 3 | 0224013 | Perform grading and construct the bridges on C. Felix Harvey Parkway in Lenoir County from US 70 to US 258 for a four lane divided highway. Paving contract will be done as a separate project in the f | New Construction | 05/08/2009 | 05/08/2009 | 08/01/2012 | 42926208 | 0
7434 | North Carolina | CRAVEN |  | 1,3 | 0229010 | The project (ER-5100BA) will implement plantings at the intersections of US 70 and Pembroke Avenue, Glenburnie Avenue, NC 41 AND US 17; intersection of NC 43 Bypass and NC55, Broad Street median; and | Transportation Enhancements | 09/21/2009 | 02/22/2010 | 12/31/2010 | 302130 | 0
7435 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 0240002 | Rehabilitate pavement on I-240 from US 70 to I-40 in Buncombe County to improve road condition. | Pavement Improvement | 01/13/2010 | 03/29/2010 | 09/15/2011 | 1000000 | 5.93
7436 | North Carolina | BUNCOMBE |  | 11 | 0240003 | This project will construct three filtration basin systems for treating stormwater runoff, from I-240, near mile marker 6, just west of Chuns Cove Road, in Asheville, NC before discharging to Ross Cre | Other | 11/05/2009 | 04/16/2010 | 07/02/2010 | 235122 | 0
7437 | North Carolina | NORTHAMPTON |  | 1 | 0258015 | This project will mill asphalt from existing pavement and resurface US 258 from Roanoke River to NC 305 in Northampton County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/01/2009 | 1034928 | 7.45
7438 | North Carolina | GREENE |  | 1 | 0258017 | This project will resurface and do minimal widening on US 258 from Contentnea Creek to NC 123 in Greene County to improve road condition. | Pavement Improvement | 09/21/2009 |  | 11/15/2010 | 1269268 | 4
7439 | North Carolina | PAMLICO |  | 3 | 0259002 | The project (ER-5100BC) will provide picnic tables with shelters, bike rack with concrete pad and concrete trash cans at the Minnessott Beach Ferry Terminal in Pamlico county. | Transportation Enhancements | 10/23/2009 | 02/23/2010 | 03/15/2010 | 25000 | 0
7440 | North Carolina | BUNCOMBE |  | 11 | 0261083 | Mill areas where potholes, cracking and/or delamination of the asphalt surface has occurred and resurface to promote the life of the roadway surface on I-26 from mile post 31 to mile post 37 in Buncom | Pavement Improvement | 04/15/2009 | 04/15/2009 | 09/30/2010 | 7208169 | 5.36
7441 | North Carolina | POLK |  | 11 | 0261085 | This project provides for preconstruction activities to rehabilitate the pavement on I-26 from milepost 61 to milepost 71 in Polk County to improve road condition. | Pavement Improvement | 07/08/2009 | 07/08/2009 | 09/30/2010 | 7011743 | 27.57
7442 | North Carolina | DARE |  | 3 | 0264039 | This project will resurface US 264 in Dare County from SR 1100 (Stumpy Point Road) to the Navy Range to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 350034 | 2.87
7443 | North Carolina | PITT |  | 1 | 0264042 | This project adds an additional turn lane on US 264 in Greenville at the intersection of Stantonsburg Road and Arlington Blvd in Pitt County to ease congestion and improve safety. This is a locally a | Pavement Widening | 08/18/2009 | 09/08/2009 | 07/14/2010 | 91227 | 0
7444 | North Carolina | WILSON |  | 3 | 0264043 | This project will resurface US 264 from NC 58 to the Greene County Line in Wilson County to improve road condition. | Pavement Improvement | 09/09/2009 |  | 11/01/2010 | 4016081 | 16.4
7445 | North Carolina | NASH, WILSON |  | 2, 3 | 0264045 | This project will resurface US 264 from the Wake County Line to US 264 Alternate in Nash and Wilson Counties to improve road condition. | Pavement Improvement | 11/10/2009 | 04/17/2010 | 10/01/2010 | 4207992 | 25.8
7446 | North Carolina | PITT |  | 1 | 0264046 | The project (ER-5100BB) will provide tree planting on US 264 and US 258 in Farmville, Pitt county. | Transportation Enhancements | 11/02/2009 | 03/15/2010 | 12/15/2010 | 122000 | 0
7447 | North Carolina | GASTON |  | 9 | 0274007 | This project will widen NC 274 from SR 1484 (Maine Ave) to NC 275 in Gaston County to improve safety and mobility. | Pavement Widening | 03/02/2009 | 03/02/2009 | 07/01/2011 | 5450259 | 1.261
7448 | North Carolina | TRANSYLVANIA |  | 11 | 0276008 | This project will rehabilitate pavement and install paved shoulders on US 276 from Pisgah Forest to Brevard in Transylvania County to improve road condition and safety. | Pavement Improvement | 04/10/2009 | 04/10/2009 | 05/15/2010 | 2055586 | 6.768
7449 | North Carolina | BERTIE |  | 1 | 0305001 | This project will mill asphalt from existing pavement, overlay with an asphalt surface treatment (mat & seal) and resurface the pavement of NC 305 NC 305 from US 13 to NC 11 in Bertie County to improv | Pavement Improvement | 05/06/2009 | 05/06/2009 | 07/01/2010 | 1749315 | 12.45
7450 | North Carolina | BERTIE |  | 1 | 0308004 | This project will resurface NC 308 in Windsor from King Street to Sterlingworth Street to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 81100 | 0.27
7451 | North Carolina | BERTIE |  | 1 | 0308005 | This project will resurface NC 308 in Bertie County from the Kelford East City Limits to the Kelford West City Limits to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 147000 | 1
7452 | North Carolina | BERTIE |  | 1 | 0308006 | This project will resurface NC 308 in Bertie County from SR 1119 (Jack Branch Road) to SR 1247 (Mount Olive Road) to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/13/2009 | 165000 | 1.72
7453 | North Carolina | GUILFORD |  | 6, 12 | 0311026 | This project includes the preparation of an environmental document for the replacement of the interchange at US 311 & NC 68 in High Point in Guilford County. This is a locally administered project by | Other | 08/21/2009 | 08/21/2009 |  | 475000 | 0
7454 | North Carolina | GUILFORD |  | 6 | 0311027 | This project will modify two existing hazardous spill basins and construct a linear filtration basin to collect the runoff from the bridge over the Oak Hollow Reservoir located on US-311/SR-1979 in Gu | Other | 12/21/2009 |  | 10/30/2010 | 68568 | 0
7455 | North Carolina | CALDWELL |  | 5 | 0321020 | This project will rehabilitate pavement on US 321 from SR 1178 (Hibriten Dr SE) to city limits of Lenoir in Caldwell County to improve road condition. | Pavement Improvement | 06/01/2009 | 08/31/2009 | 10/30/2009 | 478748 | 2.32
7456 | North Carolina | CATAWBA |  | 10 | 0321021 | The project (ER-5100LB) will provide reforestation of trees on US 321 northbound and southbound from the lincoln county line to the NC 127 interchange in Catawba county. | Transportation Enhancements | 10/28/2009 | 02/10/2010 | 04/29/2011 | 65000 | 23.722
7457 | North Carolina | NEW HANOVER |  | 7 | 0332034 | This project will construct a 0.6 mile long asphalt multi-use path in Wilmington along South 17th Street between the Cameron Art Museum and Halyburton Park and an 0.2 mile long asphalt multi-use path | Transportation Enhancements | 08/03/2009 | 02/01/2010 | 07/01/2010 | 300180 | 0
7458 | North Carolina | NEW HANOVER |  | 7 | 0332035 | This project will construct a 2.6 mile long asphalt multi-use path in Wilmington between Randall Parkway and Converse Road, parallel to Rosemont Avenue, Caswell Street, Park Avenue and Independence Bo | Transportation Enhancements | 05/28/2009 | 03/01/2010 | 09/01/2010 | 1650000 | 0
7459 | North Carolina | HAYWOOD |  | 11 | 0401200 | This project will improve drainage and?complete minor landscape improvements to the I-40 west bound rest area building in Haywood County at MM 10. | Transportation Enhancements | 07/27/2009 | 01/26/2010 | 03/05/2010 | 25445 | 0.35
7460 | North Carolina | BUNCOMBE |  | 11 | 0401204 | Rehabilitate pavement on I-40 from SR 2838 (Exit 55) to mile post 67 in Buncombe County to improve road condition. | Pavement Improvement | 11/17/2009 | 02/01/2010 | 10/30/2010 | 8340778 | 11.72
7461 | North Carolina | WAKE | RALEIGH | 13 | 0401206 | Widen US 401 in Wake County between Neuse River and Louisburg Road near Rolesville, to enhance safety and mobility. | Pavement Widening | 11/09/2009 | 02/19/2010 | 12/31/2011 | 9917986 | 3.695
7462 | North Carolina | HAYWOOD |  | 11 | 0401210 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 124 over SR 1338 ON I-40 in Haywood County to extend the life of the structure. | Bridge Improvement | 10/15/2009 | 10/15/2009 | 01/31/2010 | 738971 | 0
7463 | North Carolina | HAYWOOD |  | 11 | 0401211 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 205 over SR 1364 ON I-40 in Haywood County to extend the life of the structure. | Bridge Improvement | 11/19/2009 | 11/20/2009 | 01/31/2010 | 699271 | 0
7464 | North Carolina | HAYWOOD |  | 11 | 0401212 | The project (I-5140) will replace six dynamic message signs on Interstate 40 at milepost 33.4 (east and westbound), milepost 28.7 (east and westbound), milepost 21 (westbound), and milepost 0.7 (eastb | Safety/Traffic Management | 11/02/2009 | 02/22/2010 | 08/27/2010 | 672744 | 0
7465 | North Carolina | BURKE |  | 10 | 0402142 | This project will resurface the roadway with an asphalt microsurface (a thinner yet extremely durable treatment) to extend the life of the road and provide improved rideability on I-40 from mile post | Pavement Improvement | 04/16/2009 | 04/17/2009 | 06/30/2010 | 9633578 | 23.83
7466 | North Carolina | CATAWBA |  | 10 | 0402146 | This project will renovate the existing pair of?rest area?buildings located on I-40, west of Claremont into vending,?security offices?and storage, construct a new pair of restroom buildings with dual | Pavement Improvement | 01/13/2010 | 03/30/2010 | 04/01/2011 | 1408843 | 0
7467 | North Carolina | BURKE |  | 10 | 0402149 | ER-5100MB - This project will provide sod seeding and tree plantings on I-40 from milepost 95 to milepost 119 in Burke county, North Carolina. | Transportation Enhancements | 01/21/2010 |  | 05/03/2011 | 176000 | 2.01
7468 | North Carolina | FORSYTH |  | 12 | 0403122 | Resurface I-40 from Clemmonsville Road to US 311 in Winston-Salem / Forsyth County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 09/15/2009 | 1786444 | 3.5
7469 | North Carolina | GUILFORD |  | 6 | 0403123 | Resurface I-40/85 from Rock Creek Dairy Road in Guilford County to University Drive in Alamance County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 10/30/2009 | 4416766 | 8.294
7470 | North Carolina | FORSYTH |  | 5 | 0403124 | Resurface I-40 from Harper Road to Jonestown Road in Forsyth County to improve road condition. | Pavement Improvement | 06/15/2009 | 06/15/2009 | 06/15/2010 | 3279043 | 9.2
7471 | North Carolina | GUILFORD |  | 6,13 | 0403125 | Replace damaged/missing reflectors in pavement lane markers on I-40/85 in Guilford County, between I-40 and I-85 junction east of Greensboro to beyond Mount Hope Church Road, to improve nighttime visi | Pavement Improvement | 08/05/2009 | 08/05/2009 | 05/01/2010 | 10950 | 2
7472 | North Carolina | ALAMANCE |  | 6 | 0403126 | The project will install landscape enhancement in Burlington at the interchange of I-40/85 and SR 1226 (University Drive) in Alamance County. | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 12/15/2011 | 190000 | 0
7473 | North Carolina | FORSYTH |  | 12 | 0403127 | The project will renovate multiple landscape beds in Winston Salem along I-40 and install flowering trees along US-52 in Forsyth County. | Transportation Enhancements | 12/04/2009 | 12/10/2009 | 03/31/2011 | 507010 | 22.06
7474 | North Carolina | ALAMANCE |  | 06 | 0403128 | The project (ER-5100GG) will provide landscape rehabilitation on Interstate 40/Interstate 85 at the NC 87 interchange in Alamance county. | Transportation Enhancements | 12/21/2009 | 03/01/2010 | 05/28/2012 | 67999 | 0
7475 | North Carolina | SAMPSON, DUPLIN |  | 2, 7 | 0405052 | Resurface I-40 from east of Newton Grove in Sampson County to east of Warsaw in Duplin County to improve road condition. | Pavement Improvement | 03/26/2009 | 03/26/2009 | 11/15/2010 | 13541125 | 41.76
7476 | North Carolina | JOHNSTON |  | 2 | 0405053 | This projects provides for the resurfacing of I-40 from west of Morgan Road to the Sampson County Line in Johnston County to improve road condition. | Pavement Improvement | 04/10/2009 | 04/10/2009 | 11/15/2010 | 2516114 | 22
7477 | North Carolina | DUPLIN |  | 07 | 0405054 | The project (I-5001A) will repave Interstate 40 from milepost 369.4 in Duplin county to milepost 389.5 in Pender county to improve road condition. | Pavement Improvement | 12/16/2009 | 02/08/2010 | 05/31/2011 | 1000000 | 40.18
7478 | North Carolina | NEW HANOVER, SAMPSON, DUPLIN, PENDER |  | 7 | 0405055 | The project (ER-5100CA) will provide wildflower seeding and mulching on Interstate 40 in New Hanover, Pender, Duplin and Sampson counties. | Transportation Enhancements | 10/09/2009 | 02/08/2010 | 04/02/2010 | 160788 | 0
7479 | North Carolina | WAYNE |  | 1 | 0414004 | This project will install a computerized central signal system in the City of Goldsboro to synchronize the traffic signals to improve traffic flow. | Safety/Traffic Management | 08/05/2009 | 08/05/2009 | 02/01/2012 | 3622986 | 0
7480 | North Carolina | WATAUGA |  | 5 | 0421047 | This project will widen US 421 (King Street) from NC 194 to US 321 in Watauga County to improve safety and mobility. | Other | 05/06/2009 | 05/06/2009 | 12/31/2011 | 15412414 | 1.098
7481 | North Carolina | LEE |  | 2 | 0421050 | Construct section of Sanford Bypass between NC 42 and NC 87 south of Sanford, to reduce congestion and improve mobility. | New Construction | 11/09/2009 | 02/22/2010 | 11/15/2012 | 27757178 | 0
7482 | North Carolina | GUILFORD | GREENSBORO | 6 | 0421053 | This project will repave US 421 in Guilford County from the Randolph County line to north of SR 3485 (Harmont Drive) to improve road condition. | Pavement Improvement | 10/13/2009 | 03/08/2010 | 09/03/2010 | 3621330 | 19.92
7483 | North Carolina | CHATHAM |  | 6 | 0421055 | The project (ER-5100HC) will provide landscape renovation planting and plant bed restoration on US 421 at US 64 and US 421 at SR 1362 (Piney Grove Church Road) in Chatham county. | Transportation Enhancements | 10/23/2009 | 01/30/2010 | 03/31/2010 | 113018 | 0
7484 | North Carolina | FORSYTH |  | 05 | 0421057 | The project (U-5144B) wil mill, rehabilitate pavement and resurface two lanes northbound and two lanes southbound of US 421 from pavement joint at the ramps at Lesisville to the Yadkin county line in | Pavement Improvement | 12/17/2009 | 05/09/2010 | 09/30/2010 | 500000 | 8.186
7485 | North Carolina | WILKES |  | 05 | 0421058 | The project (ER-5100KA) will provide reforestation and manual clearing on US 421 From SR 1765 (Unifi Industrial Road) in Yadkin County to the Boome Town limits in Wataugh County in Wilkes County. | Transportation Enhancements | 10/22/2009 | 01/27/2010 | 04/23/2010 | 93044 | 33.76
7486 | North Carolina | WILKES |  | 5 | 0421060 | ER-5100KB - This project will renovate and enhance landscape plantings on US 421 at the interchanges with NC 268, NC 16/18 South and SR 1001 (Brushy Mountain Road) in Wilkesboro in Wilkes county, Nort | Transportation Enhancements | 04/05/2010 |  | 12/17/2011 | 106799 | 0
7487 | North Carolina | WAKE |  | 13 | 0440006 | Remove sections of concrete pavement and replace with asphalt to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 06/30/2010 | 3963204 | 5
7488 | North Carolina | WAKE |  | 13 | 0440007 | Resurface I-440 Beltline in Raleigh from Wade Avenue to Wake Forest Road to improve road condition | Pavement Improvement | 03/26/2009 | 03/26/2009 | 12/31/2009 | 3709164 | 10
7489 | North Carolina | WAKE | RALEIGH | 13 | 0440008 | This project consists of cleaning and painting bridges in Raleigh along I-440 including bridge numbers, 249 (Glen Eden), 252 (Ridge Road), 139 (US 401), 287 (US 1), and 288 (US 410 SBL) to extend lif | Bridge Improvement | 08/24/2009 | 04/14/2010 | 10/30/2010 | 956775 | 0
7490 | North Carolina | WAKE |  | 13 | 0440009 | This project provides for the installation of a Wireless Camera System on the Northern Section of I-440 in Raleigh to improve response to traffic congestion in Wake County. | Safety/Traffic Management | 04/30/2009 | 04/30/2009 | 03/18/2010 | 382762 | 3.68
7491 | North Carolina | MECKLENBURG |  | 8,9,12 | 0485016 | This project will construct a filtration basin/wetland at NC 51/I-485 to treat stormwater runoff from NC 51 in Mecklenburg County helping to prevent pollutants from entering into a tributary of Clear | Other | 10/15/2009 | 10/15/2009 | 04/30/2010 | 148065 | 0
7492 | North Carolina | MECKLENBURG |  | 8,9,12 | 0485025 | ER-5100JD - This project will reforestate at various locations on I-485 from US 74 East to I-85 North in Mecklenburg county, North Carolina. | Transportation Enhancements | 01/21/2010 |  |  | 40000 | 26.54
7493 | North Carolina | DURHAM |  | 4 | 0501014 | This project will repave Duke Street in Durham from Horton Road to Hudson Street to improve road condition. | Pavement Widening | 05/13/2009 | 05/13/2009 | 05/14/2010 | 770485 | 0
7494 | North Carolina | WAKE | RALEIGH | 4 | 0501015 | This project will install a traffic signal in Apex at the Intersection of SR 1010 (Center Street) and SR 1011 (North Salem Street) to improve safety. This is a locally administered project by the Tow | Safety/Traffic Management | 09/17/2009 | 04/14/2010 | 07/28/2010 | 92191 | 0
7495 | North Carolina | WAKE | RALEIGH | 4 | 0503007 | This project will construct a portion of the Black Creek Greenway pedestrian and bicycle facilities from the Credit Union near the intersection of Chapel Hill Road and Northwest Maynard Road to the Sh | Transportation Enhancements | 09/21/2009 | 03/01/2010 | 10/26/2010 | 1299000 | 0
7496 | North Carolina | DURHAM |  | 4 | 0505034 | This project will provide for traffic signal upgrades in Durham including pedestrian installed equipment at various locations for the city maintained signals to improve operating efficiency and safety | Safety/Traffic Management | 09/22/2009 | 01/15/2010 | 09/12/2010 | 125729 | 0
7497 | North Carolina | DURHAM |  | 4 | 0505036 | The project provides for the installation of a new traffic signal in Durham at Northpoint Drive at Home Depot Entrance and Dehaven?s Entrance to improve safety in Durham County. TIP U-5150 is include | Safety/Traffic Management | 09/23/2009 | 01/15/2010 | 09/12/2010 | 346539 | 0
7498 | North Carolina | DURHAM |  | 4 | 0505037 | This project provides for the installation of a new signal on Renaissance Parkway at the ATT Crossing and at the Mall Site Drive to improve access and safety in Durham County. This project includes T | Safety/Traffic Management | 09/23/2009 | 01/15/2010 | 09/12/2010 | 232071 | 0
7499 | North Carolina | DURHAM | DURHAM | 4 | 0505039 | This project will remove the free flow traffic turn lane in Durham at the intersection of SR 1670 (Greer Street) and Miami Boulevard to improve safety a the intersection in Durham County. This is a | Pavement Improvement | 09/18/2009 |  |  | 80000 | 0
7500 | North Carolina | DURHAM | DURHAM | 4 | 0505040 | The project will provide for replacement of trees in Durham along Duke and Gregson streets to improve neighborhood appearance in Durham County. This is a locally administered project by the City of D | Transportation Enhancements | 09/21/2009 | 01/10/2010 | 04/10/2010 | 108572 | 0
7501 | North Carolina | DURHAM | DURHAM | 4 | 0505042 | This project will construct neighborhood accesses to the Third Fork Creek Greenway to improve community access in Durham County. This is a locally administered project by the City of Durham. | Transportation Enhancements | 09/22/2009 | 01/18/2010 | 10/15/2010 | 827000 | 0
7502 | North Carolina | DURHAM | DURHAM | 4 | 0505043 | This project will resurface asphalt on the North-South Greenway Trail in Durham from Lavender Street to Murray Avenue to improve pavement life and ride quality in Durham County. U-4726HI includes TIP | Transportation Enhancements | 09/18/2009 |  |  | 342183 | 0
7503 | North Carolina | WAKE |  | 13 | 0520028 | This project will construct the Neuse River Greenway pedestrian and bicycle facilities from Falls Lake Dam to the South Soccer Complex on SR 2006 (Perry Creek Road) in Wake County. This project is lo | Transportation Enhancements | 08/28/2009 | 01/19/2010 | 03/19/2011 | 3250000 | 0
7504 | North Carolina | WAKE | RALEIGH | 4 | 0527006 | This project provides for the construction of the Dunn Creek Greenway to improve pedestrain access and safety from Smith Creek Soccer Center to the NC 98 Bypass in Wake County. This is a locally adm | Transportation Enhancements | 09/16/2009 | 01/22/2010 | 08/20/2010 | 450000 | 0
7505 | North Carolina | WAKE | RALEIGH | 6 | 0529001 | This project provides for the construction of crosswalks at Athird and Main Streets to improve pedestrain safety and mobility in Wake County. This is a locally administered project by the Town of Wen | Transportation Enhancements | 09/10/2009 | 02/01/2010 | 03/13/2010 | 33810 | 0
7506 | North Carolina | WAKE | RALEIGH | 4 | 0529002 | This project provides for the construction of 4500 feet of sidewalk in Wendell along Third Street and Buffaloe Road to improve pedestrian access to the park in Wake County. This is a locally adminis | Transportation Enhancements | 08/14/2009 | 02/15/2010 | 08/11/2010 | 375749 | 0.3
7507 | North Carolina | WAKE | RALEIGH | 4 | 0532003 | This project constructs sidewalk in Zebulon on West Judd Street from North Wakfield Street to North Church Street in Wake County. This is a locally administered project by the Town of Zebulon. | Transportation Enhancements | 09/08/2009 | 02/08/2010 | 04/08/2010 | 71923 | 0
7508 | North Carolina | DURHAM |  | 4 | 0540015 | Widen ramp from I-540 west to I-40 west in Durham and Wake Counties, and add merge lane on I-40 westbound between I-540 and Page Road in Durham County, to reduce congestion. | Pavement Improvement | 12/17/2009 | 04/01/2010 | 12/31/2010 | 3835029 | 7.767
7509 | North Carolina | WAKE |  | 4 | 0540016 | Resurface I-540 in Wake County from north of I-40 to US 70 to improve road condition | Pavement Improvement | 04/15/2009 | 04/15/2009 | 05/27/2010 | 2569522 | 3.8
7510 | North Carolina | WAKE | RALEIGH | 13 | 0540018 | The project will provide for landscape enhancement in Knightdale at the interchange of I-540 and US 64 in Wake County. This is a locally administered project by the Town of Knightdale. | Transportation Enhancements | 09/16/2009 | 03/24/2010 | 07/16/2010 | 130697 | 0
7511 | North Carolina | HERTFORD |  | 1 | 0561020 | This project will widen and resurface NC 561 from NC 11 to Northampton County in Hertford County to improve road condition. | Pavement Widening | 07/20/2009 |  | 06/30/2011 | 1919494 | 10.21
7512 | North Carolina | ROCKINGHAM |  | 13 | 0700008 | This project will repave NC 700 in Rockingham County from the Dan River to SR 1902 (Dibrell Road) to improve road condition. | Pavement Improvement | 03/01/2010 | 04/15/2010 | 05/29/2010 | 870044 | 8.671
7513 | North Carolina | ALAMANCE |  | 6 | 0701018 | This project provides for the replacement of existing signal poles & mast arms at the SR 1300 (University Drive) and Rural Retreat Road intersection to improve road conditions in Alamance County. Inc | Safety/Traffic Management | 08/05/2009 | 08/05/2009 | 06/30/2011 | 413272 | 0
7514 | North Carolina | BLADEN |  | 7 | 0701020 | This project will construct bicycle lanes on US 701 between Elizabethtown and White Lake for approximately 6 miles by widening the existing paved shoulder to four feet on both sides in Bladen County. | Transportation Enhancements | 08/07/2009 | 08/07/2009 | 06/01/2010 | 975000 | 5.3
7515 | North Carolina | ALAMANCE |  | 13 | 0701022 | This project provides for the construction of sidewalks, including curb and gutter to improve pedestrian mobility and safety on Piedmont Street from SR 1785 (Sellars Mill Road) to the Cummings High S | Transportation Enhancements | 09/23/2009 | 03/27/2010 | 04/16/2010 | 25138 | 0
7516 | North Carolina | ALAMANCE |  | 6 | 0701023 | This project provides for the construction of sidewalk and the installation of pedestrian signals to improve pedestrian safety and mobility on US 70 (Church Street)/SR 1158 (Huffman Mill Rd) from SR | Transportation Enhancements | 12/21/2009 | 04/05/2010 | 06/30/2010 | 52463 | 0
7517 | North Carolina | ALAMANCE |  | 6 | 0701024 | This project provides for the construction of an ADA-compliant crosswalk and sidewalk to improve pedestrian mobility and safety on SR 1158 (Huffman Mill Road) and Forestdale Drive in Alamance County. | Transportation Enhancements | 12/21/2009 | 04/05/2010 | 06/30/2010 | 53208 | 0
7518 | North Carolina | ORANGE | DURHAM | 4 | 0702015 | This project provides for the construction of Bus Stop Shelters to improve pedestrain mobility and safety at various locations in Carboro in Orange County. This is a locally administered project by t | Transportation Enhancements | 08/27/2009 | 08/27/2009 | 06/23/2010 | 76296 | 0
7519 | North Carolina | ORANGE | DURHAM | 4 | 0702016 | This project proivdes for the construction of sidewalk on one side of Ashe Street from West Main Street to Shelton Street in Carrboro in Orange County. This is a locally administered project by the T | Other | 09/09/2009 | 03/18/2010 | 06/28/2010 | 139938 | 0
7520 | North Carolina | ORANGE | DURHAM | 4 | 0702017 | This project provides for the construction of sidewalk on one side of Bim Street from SR 1005 (Jones Ferry Rd) to Fidelity Street in Carrboro in Orange County. This is a locally administered project | Transportation Enhancements | 09/11/2009 | 03/18/2010 | 06/28/2010 | 144238 | 0
7521 | North Carolina | ORANGE | DURHAM | 4 | 0703014 | This project will upgrade the citywide traffic signal system at 124 intersections and install fiber optic communications cable in Chapel Hill / Orange County to reduce congestion and emissions and imp | Safety/Traffic Management | 08/05/2009 | 08/05/2009 | 08/01/2012 | 5686446 | 0
7522 | North Carolina | ORANGE | DURHAM | 4 | 0703015 | This project provides for the construction of ADA Ramps to improve pedestrian mobility and safety at seven (7) selected locations in Chapel Hill in Orange County. This is a locally administered proj | Transportation Enhancements | 09/21/2009 | 01/13/2010 | 06/24/2010 | 50000 | 0
7523 | North Carolina | ORANGE | DURHAM | 4 | 0703016 | This project proides for the construction of raised crosswalks and traffic calming devices at eight (8) selected locations in Chapel Hill in Orange County. This is a locally administered project by t | Safety/Traffic Management | 09/21/2009 | 01/13/2010 | 06/24/2010 | 65189 | 0
7524 | North Carolina | ORANGE | DURHAM | 4 | 0703017 | This project provides for the construction of pedestrian safety improvements, pedestrain refuge islands, at one (1) location on NC 86 (Martin Luther King, Jr. Drive) and four (4) locations on east Fra | Transportation Enhancements | 07/29/2009 | 08/05/2009 | 06/24/2010 | 403952 | 0
7525 | North Carolina | GUILFORD |  | 6 | 0705004 | This project provides for the construction of sidewalk to improve pedestrian mobility on the West side of Oak Street from East Trollinger Street to Truitt Drive in Guildford County. This is a loca | Transportation Enhancements | 12/08/2009 | 03/08/2010 | 06/07/2010 | 65025 | 0.2
7526 | North Carolina | GUILFORD |  | 6 | 0708022 | This project provides for the construction of Phases IV and V of the Bicentenial Greenway, multi-use path and sidewalk, to improve pedestrin safety and mobility, from Ballinger Road to Market Street i | Transportation Enhancements | 08/28/2009 | 03/31/2010 | 05/28/2011 | 548112 | 0
7527 | North Carolina | GUILFORD | GREENSBORO | 6, 13 | 0708023 | This project provides for the construction of intersection improvements and sidewalk and widening Lake Jeanette Road from Lawndale Drive to SR 2348 (Bass Chapel Road/Elm Street) to improve safety and | Pavement Widening | 09/18/2009 | 02/08/2010 | 05/23/2011 | 2867263 | 0
7528 | North Carolina | GUILFORD | GREENSBORO | 12 | 0708024 | This project provides for the construction of pedestrain improvements by replacing the median turn lane on South Elm-Sugene Street from JJ Drive to Vandalia Road to improve safety and mobility in Gree | Pavement Improvement | 09/01/2009 | 01/25/2010 | 09/15/2010 | 1628417 | 0
7529 | North Carolina | GUILFORD | GREENSBORO | 6, 12 | 0708025 | This project will repave Holden Road from SR 4121 (High Point Road) to Pinecroft Road, Cone Boulevard form Elm Street to Summitt Avenue, Friendly Avenue from Radience Drive to Elam Avenue and Smith St | Pavement Improvement | 08/04/2009 | 03/23/2010 | 09/03/2010 | 1501890 | 0
7530 | North Carolina | GUILFORD |  | 12 | 0710021 | The project (EB-5118GH) will construct Sidewalks on the north side of SR 1486 (Lexington Avenue) from the High Point Greenway to SR 1471 (Montlieu Avenue) and on the south side from the High Point Gre | Transportation Enhancements | 12/21/2009 | 03/15/2010 | 06/15/2010 | 107136 | 0.2
7531 | North Carolina | ORANGE |  | 4 | 0711011 | This project provides for the construction of sidewalks to improve pedestrian safety and mobility on Nash Street, Faucette Mill Street, Revere Road, Hayes Street, Union Street, Eno Street and Allison | Transportation Enhancements | 09/22/2009 | 03/01/2010 | 12/21/2010 | 319459 | 0
7532 | North Carolina | GUILFORD |  | 6 | 0729002 | This project provides for the acquisition of right-of-way to construct trailhead parking area to access the Lake Brandt Greenway on US 220 North of Strawberry Road in Guildofrd County. This is a loc | Transportation Enhancements | 08/18/2009 | 05/27/2010 | 12/31/2010 | 274538 | 0
7533 | North Carolina | CHATHAM | DURHAM | 4 | 0751023 | This project will construct left turn lanes and a traffic signal on NC-751 at the intersection of O'Kelly Church Road in Chatham County to ease congestion. | Safety/Traffic Management | 08/18/2009 | 03/16/2010 | 09/12/2010 | 523000 | 0
7534 | North Carolina | ROCKINGHAM |  | 13 | 0770003 | This project will construct curb & gutter and sidewalk to improve pedestrian mobility on the north side of NC 770 from Westridge Apartments to SR 1405 (South Glenn Street) in Rockingham County. Thi | Transportation Enhancements | 11/09/2009 | 03/05/2010 | 05/15/2010 | 252462 | 1.5
7535 | North Carolina | SURRY |  | 5 | 0771192 | Rehabilitate pavement on I-77 from US 21 (Exit 79) to milepost 84 in Surry and Yadkin Counties to improve road condition. | Pavement Improvement | 04/21/2009 | 04/21/2009 | 12/31/2009 | 3502719 | 10.2
7536 | North Carolina | MECKLENBURG |  | 12 | 0771194 | The project (I-5128) will paint bridges at selected locations on Interstate 77 from Nations Ford Road to Catawba Avenue in Mecklenburg county. | Other | 05/13/2009 |  |  | 20000 | 0
7537 | North Carolina | YADKIN |  | 5 | 0771195 | Rehabilitate pavement on I-77 from Iredell County line to south of SR 1125 (Asbury Church Rd) in Yadkin County to improve road condition. | Pavement Improvement | 09/08/2009 | 05/07/2010 | 07/01/2010 | 1057392 | 6.24
7538 | North Carolina | SURRY |  | 5 | 0771196 | Rehabilitate pavement on I-77 from mile post 88.4 to mile post 90 in Surry County to improve road condition. | Pavement Improvement | 08/06/2009 | 08/06/2009 | 11/20/2009 | 336992 | 3.2
7539 | North Carolina | SURRY |  | 5 | 0771197 | Paint bridges carrying I-77 over NC 89 and I-74 eastbound lane in Surry County to extend the life of the structures. | Bridge Improvement | 05/01/2009 |  | 10/23/2010 | 638037 | 0
7540 | North Carolina | MECKLENBURG | CHARLOTTE | 8,9,12 | 0771198 | This project will construct a linear wetland at the I-77 Welcome Center in Mecklenburg County, NC. The purpose of this project is to treat stormwater runoff from the Welcome Center parking lot helpin | Other | 12/07/2009 |  | 03/01/2010 | 87218 | 0
7541 | North Carolina | IREDELL |  | 10 | 0771199 | This project will construct a stormwater wetland, at the I-77SB Rest Area in Iredell County, to treat stormwater runoff from the Rest Area and a portion of the roadway before discharging into Lake Nor | Other | 10/30/2009 | 02/08/2010 | 04/30/2010 | 132000 | 0
7542 | North Carolina | IREDELL |  | 10 | 0771200 | The project will install landscape enhancement plantings at the I-77 and Langtree Road interchange in Iredell County. | Transportation Enhancements | 08/05/2009 | 08/05/2009 | 12/15/2009 | 148121 | 0
7543 | North Carolina | MECKLENBURG |  | 12 | 0771201 | This project provides for the cleaning and painting of bridges 136, 120 and 85 on I-77 from Nations Ford Road to Catawba Avenue in Mecklenburg County to extend the life of the structures. | Bridge Improvement | 09/09/2009 | 06/23/2010 | 09/30/2010 | 1050000 | 0
7544 | North Carolina | LEE |  | 2 | 0837005 | This project will construct the Endor Iron Furnace Greenway in Sanford which is a 10 feet wide paved asphalt multi-use greenway trail from Kiwanis Family Park on Carbonton Road to Boone Drive (approxi | Transportation Enhancements | 08/14/2009 | 01/12/2010 | 10/12/2010 | 554171 | 0
7545 | North Carolina | GASTON |  | 9 | 0851114 | Interchange Planings On I-85 At Exit 26 In Belmont In Gaston County, North Carolina | Transportation Enhancements | 01/21/2010 | 03/15/2010 | 04/29/2011 | 112000 | 0
7546 | North Carolina | CABARRUS |  | 8 | 0852067 | This project will rehabilitate existing pavement on I-85 from US 29/601 to NC 73 in Cabarrus County to improve road condition. | Pavement Improvement | 03/27/2009 | 03/27/2009 | 10/30/2009 | 2647031 | 6.68
7547 | North Carolina | GASTON |  | 9 | 0852068 | Mill and resurface I-85 from mile post 21.8 to mile post 23.5 in Gaston County to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 11/02/2009 | 926217 | 3.6
7548 | North Carolina | MECKLENBURG |  | 8,9,12 | 0852069 | This project will construct a wetland and provide credit for excess stabilization on the Northbound side of I-85 near the bridge crossing over Mallard Creek in Mecklenburg County. The purpose is to t | Other | 10/19/2009 | 04/06/2010 | 04/30/2009 | 29114 | 0
7549 | North Carolina | CABARRUS |  | 8,12 | 0852070 | This project will renovate the existing pair of?rest area buildings located on I-85, west of Concord at Mile Post 59 into vending,?security offices?and storage, construct a new pair of restroom buildi | Pavement Improvement | 08/05/2009 | 12/01/2009 | 10/15/2010 | 1719300 | 0
7550 | North Carolina | GUILFORD |  | 6 | 0853195 | This project provides for resurfacing I-85 in Guilford County from US 29-70/Business 85 to Groometown Road to improve road condition. | Pavement Improvement | 04/15/2009 | 04/15/2009 | 08/13/2010 | 2684769 | 2.8
7551 | North Carolina | DAVIDSON |  | 6 | 0853200 | This project will renovate the existing pair of?rest area located on I-85, south of Thomasville at Mile Post 100 into vending,?security offices?and storage, construct a new pair of restroom buildings | Pavement Improvement | 08/05/2009 | 08/05/2009 | 08/15/2010 | 1944158 | 0
7552 | North Carolina | GUILFORD | GREENSBORO | 6,12,13 | 0853201 | Install pavement marking reflectors and replace damaged/missing reflectors on I-85 in Guilford County, between Groomtown Road (milepost 131) and I-40 / I-85 junction east (milepost 120) of Greensboro, | Pavement Improvement | 08/05/2009 | 09/24/2009 | 05/01/2010 | 644332 | 22
7553 | North Carolina | GUILFORD |  | 6 | 0853202 | Install pavement marking reflectors and replace damaged/missing reflectors on I-85 in Guilford County, between NC 62 near Archdale and Business 85 in Greensboro, to improve nighttime visibility. | Pavement Improvement | 08/05/2009 | 09/24/2009 | 05/01/2010 | 244621 | 6
7554 | North Carolina | GUILFORD |  | 6, 12, 13 | 0853204 | The project will provide reforestation along I-73 and I-85 at Various Locations in Guilford County, south of Greensboro | Transportation Enhancements | 11/17/2009 |  | 04/30/2012 | 100000 | 0
7555 | North Carolina | DAVIDSON |  | 6 | 0853205 | The project will renovate landscaping south of Thomasville at the I-85 Rest Area Vietnam Memorial in Davidson County. | Transportation Enhancements | 12/02/2009 | 12/07/2009 | 03/31/2011 | 60000 | 0
7556 | North Carolina | GUILFORD |  | 06 | 0853206 | The proejct (ER-5100GF) wil provide corridor plantings on Interstate 85 from Groometown Road (milepost 120) to I-85/I-85 Business (milepost 118) in Guilford county. | Transportation Enhancements | 12/21/2009 | 03/09/2010 | 05/28/2012 | 200000 | 2
7557 | North Carolina | ORANGE |  | 4 | 0854113 | Resurface I-85 in Orange County from I-40 / I-85 interchange to SR 1006 (Orange Grove Road) to improve road condition. | Pavement Improvement | 09/08/2009 | 04/11/2010 | 07/16/2010 | 1881209 | 1.466
7558 | North Carolina | DURHAM |  | 04 | 0854114 | The project (R-5164A) will mill asphalt from existing pavement and resurface on Interstate 85 from the Orange county line to SR 1401 (Cole Mill Road); NC 147 from I-85 to the end of asphalt roadway ne | Pavement Improvement | 12/17/2009 |  | 12/16/2010 | 5575120 | 19.432
7559 | North Carolina | FORSYTH |  | 5 | 0909004 | This project constructs 481 square yards of sidewalk in Kernersville along the west side of Oakhurst Drive from Cherry St north past Lambeth Farm Lane to enhance pedestrian safety in Forsyth County. | Transportation Enhancements | 07/14/2009 | 05/20/2010 | 06/30/2010 | 54140 | 0
7560 | North Carolina | FORSYTH |  | 12 | 0918068 | This projects constructs new sidewalk & installs one bus shelter and required retaining walls in Winston-Salem on east side of New Walkertown Road from Waterworks Road to Spaulding Drive to enhance pe | Transportation Enhancements | 08/14/2009 | 03/01/2010 | 03/30/2010 | 109916 | 0
7561 | North Carolina | FORSYTH |  | 12 | 0918069 | This project constructs new sidewalk and installs two bus shelters in Winston-Salem on east side of Peters Creek Parkway from Brewer Road to the existing sidewalk and from existing sidewalk to the bus | Transportation Enhancements | 08/14/2009 | 09/24/2009 | 03/30/2010 | 95786 | 0
7562 | North Carolina | FORSYTH |  | 12 | 0918070 | This project provides intersection improvements in Winston-Salem along Shattalon Drive intersections from Murray Road to Bright Oak Avenue to improve safety in Forsyth County. This is a locally admin | Safety/Traffic Management | 06/23/2009 | 09/24/2009 | 09/08/2010 | 292000 | 0.4
7563 | North Carolina | FORSYTH |  | 5 | 0923003 | This project will construct 725 feet of sidewalk in Walkertown on East Friendly Road from SR 2004 (Main Street) to Willoughby Drive with high visibility improvements to the Friendly Road/Walkertown El | Transportation Enhancements | 06/05/2009 | 01/06/2010 | 03/05/2010 | 33026 | 0
7564 | North Carolina | FORSYTH |  | 5 | 0923004 | This project will construct 617 feet of 5 feet wide concrete sidewalk in Walkertown on the east shoulder of Morris Street between Old Hollow Road (NC 66) and New Walkertown Road (US 311) to enhance pe | Transportation Enhancements | 07/14/2009 | 02/08/2010 | 04/16/2010 | 31356 | 0
7565 | North Carolina | FORSYTH |  | 5 | 0926003 | This project constructs 5,750 feet of sidewalk and required storm drainage in the Village of Clemmons on Middlebrook Drive between Idols Road and Greenbrook Drive to enhance pedestrian safety in Forsy | Transportation Enhancements | 07/02/2009 | 01/25/2010 | 05/12/2010 | 203228 | 1.1
7566 | North Carolina | FORSYTH |  | 5 | 0927003 | This project constructs a roundabout in Lewisville at the Lewisville-Concord Church Road/US 421/Williams Road intersection to improve safety in Forsyth County. This is a locally administered project | Pavement Improvement | 01/21/2010 | 05/19/2010 | 11/30/2010 | 322765 | 0.02
7567 | North Carolina | CUMBERLAND |  | 7 | 0951080 | This the preliminary engineering for the project that will renovate and improve existing landscape enhancements at the interchange of I-95 and NC 87 in Cumberland County. | Other | 07/13/2009 | 07/13/2009 |  | 187 | 0.35
7568 | North Carolina | ROBESON |  | 7 | 0951081 | The project will renovate and improve existing landscape enhancement along I-95 between Mile Post 4 through 30 in Robeson County | Transportation Enhancements | 09/24/2009 | 12/29/2009 | 03/26/2010 | 102084 | 0
7569 | North Carolina | CUMBERLAND |  | 07 | 0951082 | The project (ER-5100FD) will renovate plantings on Interstate 95 and NC 87 at exit 46 in Cumberland county. | Transportation Enhancements | 10/23/2009 | 03/22/2010 | 05/28/2010 | 210170 | 0.35
7570 | North Carolina | ROBESON |  | 07 | 0951083 | The project (ER-5100FE) will provide reforestation on Interstate 95 from mile marker 3 to mile marker 5 in Robeson county. | Transportation Enhancements | 10/28/2009 | 03/22/2010 | 04/02/2010 | 11875 | 2
7571 | North Carolina | JOHNSTON |  | 2 | 0952114 | Resurface I-95 from North of US 70 to North of Main Street in Johnston County to improve road condition. | Pavement Improvement | 09/11/2009 | 03/31/2010 | 08/01/2010 | 2217715 | 14.6
7572 | North Carolina | CUMBERLAND |  | 7 | 0952115 | This project will provide landscape enhancement at the I-95 Rest Area near Mile Post 48 in Cumberland County. | Transportation Enhancements | 09/24/2009 |  |  | 152459 | 0
7573 | North Carolina | WILSON |  | 3 | 0953104 | This is the preliminary engineering for the project that will focus on landscape enhancement at the interchanges US 264/US 264 Alt & I-95 / US 264 in Wilson County. | Transportation Enhancements | 07/09/2009 | 07/09/2009 | 12/15/2010 | 160265 | 0.07
7574 | North Carolina | STATEWIDE |  | 2, 3 | 0953105 | This project provides for pavement rehabilitation and resurfacing I-95 from south of the Nash County line (Milepost 123) in Wilson County to south of NC 58 (Milepost 128) in Nash County to improve ro | Pavement Improvement | 09/09/2009 | 05/26/2010 | 08/15/2010 | 1599947 | 9
7575 | North Carolina | FORSYTH |  | 5 | 0999007 | This project constructs sidewalk in Rural Hall on NC 66 between Paso Street and Wall Street and constructs sidewalk and curb and gutter along Park Street between NC 66 and Church Street to improve ped | Transportation Enhancements | 06/12/2009 | 03/01/2010 | 05/19/2010 | 166075 | 0.2
7576 | North Carolina | STANLY |  | 08 | 1001052 | The project (E-4129B) will construct the Snyder Greenway from Salisbury Avenue to Depot Street in Albemarle, Stanley county. | Transportation Enhancements | 11/02/2009 | 03/08/2010 | 07/07/2010 | 281777 | 0
7577 | North Carolina | MECKLENBURG | CHARLOTTE | 9, 12 | 1003085 | This project will design the upgrade and expansion of Charlotte's Intelligent Transportation System (ITS) Communications backbone which will provide for on-the-fly remote operation of Traffic Signaliz | Safety/Traffic Management | 05/21/2009 | 05/21/2009 | 12/22/2011 | 1314169 | 0
7578 | North Carolina | MECKLENBURG |  | 12 | 1003086 | This project includes the construction of two miles of the Toby Creek Greenway in Charlotte from Mallard Creek Greenway near US 29 to University Blvd (NC 49) to improve pedestrian access in Mecklenbur | Transportation Enhancements | 09/22/2009 | 09/22/2009 | 01/27/2011 | 1169772 | 0
7579 | North Carolina | MECKLENBURG | CHARLOTTE | 9 | 1003089 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the South Charlotte area including surveillance system along Providence Road, Ballentyne Commons Parkway and NC 51 | Safety/Traffic Management | 09/09/2009 | 09/09/2009 | 10/15/2010 | 629362 | 0
7580 | North Carolina | MECKLENBURG |  | 9 | 1003090 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the Northwest Charlotte area including surveillance system along Beatties Ford Road, Sunset Road, Statesville Road | Safety/Traffic Management | 05/19/2009 | 10/15/2009 | 12/15/2010 | 1037565 | 0
7581 | North Carolina | MECKLENBURG |  | 8,9 | 1003091 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the University area (Northwest Charlotte) including surveillance system along W. T. Harris, The Plaza, North Tryon | Safety/Traffic Management | 10/15/2009 | 10/15/2009 | 12/15/2010 | 1018904 | 0
7582 | North Carolina | MECKLENBURG |  | 9, 12 | 1003093 | The project (EB-5118JC) will construct pedestrian signals and crosswalk markings at various locations in Charlotte, Mecklenburg County. | Transportation Enhancements | 10/14/2009 | 10/20/2009 | 11/19/2010 | 800000 | 0
7583 | North Carolina | MECKLENBURG |  | 09 | 1003094 | The project (EB-5118JD) will install a sidewalk along Shasta Lane from Randolph Road to Sardis Road in Charlotte, Mecklenburg county. | Transportation Enhancements | 10/20/2009 | 10/20/2009 | 08/15/2010 | 363826 | 0
7584 | North Carolina | DURHAM |  | 4 | 1004039 | This project will repave Old Oxford Road in Durham County from Roxboro Street to Granville County line to improve road condition. | Pavement Widening | 05/13/2009 | 05/13/2009 | 05/14/2010 | 1670081 | 16.62
7585 | North Carolina | MECKLENBURG |  | 12 | 1006034 | The project (EB-5118JB) will construct the West Branch Rocky River Greenway from River Ford Drive eastward along West Branch Rocky River for 1.1 miles in Davidson, Mecklenburg county. | Transportation Enhancements | 10/20/2009 | 10/20/2009 | 04/07/2011 | 487767 | 0
7586 | North Carolina | UNION | CHARLOTTE | 8, 9 | 1008020 | This project will construct left turn lanes in Indian trail on Unionville Indian Trail Road at the intersection with Faith Church Road in Union County to improve safety. | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/11/2009 | 299675 | 0
7587 | North Carolina | MECKLENBURG | CHARLOTTE | 9 | 1013002 | This project includes milling existing asphalt, patching existing asphalt, repaving existing roadway, thermoplastic long life pavement markings in Matthews from North Trade Street/Matthews-Mint Hill R | Pavement Improvement | 08/18/2009 | 08/19/2009 | 06/01/2010 | 653571 | 1.11
7588 | North Carolina | MECKLENBURG |  | 09 | 1031007 | The project (EB-5118JA) will construct sidewalks on Wilgrove-Mint Hill Road from NC 51 to Jim Harper Lane in Mint Hill, Mecklenburg county. | Transportation Enhancements | 10/09/2009 | 03/05/2010 | 05/31/2010 | 142998 | 0.8
7589 | North Carolina | IREDELL |  | 5 | 1100024 | Widen Brawley School Rd from Centre Church Rd to I-77 in Iredell County to improve safety and mobility. | Pavement Widening | 09/15/2009 | 11/30/2009 | 07/01/2013 | 22964090 | 1.203
7590 | North Carolina | GATES |  | 1 | 1100025 | This project will replace deficient Bridge #32 over Trotman Creek on SR 1100 (Carters Road) in Gates County. | Bridge Replacement | 12/28/2009 |  | 08/11/2011 | 881091 | 0
7591 | North Carolina | ORANGE |  | 4 | 1107016 | This project will widen Old Fayetteville Road to accommodate pedestrain, bicycle and transit traffic in Carrboro / Orange County from NC 54 to Stroud Lane to provide bike lanes, sidewalks and bus turn | Transportation Enhancements | 06/22/2009 | 06/22/2009 | 09/15/2010 | 800000 | 0.45
7592 | North Carolina | PITT |  | 3 | 1133006 | This project adds sidewalks along the south side of SR 1133 (Main Street) in Winterville from Graham Street to Railroad Street in Pitt County to improve pedestrian safety. | Transportation Enhancements | 07/24/2009 | 09/11/2009 |  | 75000 | 0.4
7593 | North Carolina | PITT |  | 3 | 1133007 | This project adds sidewalks along the south side of SR 1133 (Main Street) in Winterville from Mill Street to Winterville Parkway in Pitt County to improve pedestrian safety. | Transportation Enhancements | 07/24/2009 | 09/11/2009 |  | 55000 | 0.2
7594 | North Carolina | SURRY |  | 5 | 1138016 | Paint bridges carrying SR 1138 (CC Camp Rd), SR 1131, SR 1122 (Dobbins Mill Rd), SR 1001, and SR 1345 over I-77 in Surry County to extend the life of the structures. | Bridge Improvement | 05/01/2009 |  | 10/23/2010 | 996933 | 0
7595 | North Carolina | PITT |  | 3 | 1149007 | This project adds sidewalks along SR 1149 (Lee Street/Old NC 11) in Ayden from West Barwick Street to Allen Drive in Pitt County to improve pedestrian safety. | Transportation Enhancements | 07/14/2009 | 09/11/2009 | 08/18/2010 | 75500 | 0.3
7596 | North Carolina | PITT |  | 3 | 1149008 | This project adds sidewalks along the west side of SR 1149 (Lee Street/Old NC 11) in Ayden from the northernmost intersection of Countryaure Drive to First Street in Pitt County to improve pedestrian | Transportation Enhancements | 09/11/2009 | 09/11/2009 | 08/18/2010 | 142405 | 1.1
7597 | North Carolina | MADISON |  | 11 | 1151008 | B-3488 - This project will replace bridge #142 on SR 1151 over Big Pine Creek in Madison county, North Carolina. | Bridge Replacement | 02/01/2010 |  |  | 625000 | 0
7598 | North Carolina | BERTIE |  | 1 | 1221013 | This project will replace deficient Bridge #36 over Connaritsa Swamp on SR 1221 (Charles Taylor Road) in Bertie County. | Bridge Replacement | 08/21/2009 |  |  | 660967 | 0.013
7599 | North Carolina | CURRITUCK |  | 3 | 1222012 | Replace deficient bridge carrying Tullis Creek Road over Shingle Landing Creek in Currituck County. | Bridge Replacement | 03/02/2009 | 03/02/2009 | 12/01/2009 | 650000 | 0
7600 | North Carolina | BERTIE |  | 1 | 1260002 | This project will replace deficient Bridge #16 over the Cashie River on SR 1260 (Republican Road) in Bertie County. | Bridge Replacement | 08/21/2009 |  | 10/25/2010 | 803637 | 0
7601 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302043 | This project will provide safe, efficient mobility for bicyclist while making much needed repairs to Coxe Avenue in the Asheville in Buncombe County. Includes TIP project U-5177. | Transportation Enhancements | 08/24/2009 | 04/15/2010 | 09/17/2010 | 246340 | 0
7602 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302044 | This is an enhancement project to provide trees, shrubs and other landscape items in the downtown central business district and a Gateway locations on Lexington and Clingman Avenues, College Street me | Transportation Enhancements | 08/28/2009 | 03/01/2010 | 05/04/2010 | 94717 | 0
7603 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302046 | This project will provide and promote safe pedestrian facilities including the upgrade of traffic signals to for pedestrian use along Fairview Road at heavily traveled intersections in Asheville in Bu | Transportation Enhancements | 08/18/2009 | 04/01/2010 | 05/04/2010 | 67481 | 0
7604 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302047 | This City of Asheville plans to build sidewalks to fill in gaps along city streets and NCDOT facilities to provide safe, effective pedestrian mobility to communities and businesses within Asheville in | Transportation Enhancements | 09/09/2009 | 05/11/2010 | 09/17/2010 | 502458 | 0
7605 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1302048 | This project includes repaving Kimberly Avenue from Edwin Place to Gracelyn Road and is focused at providing safe, efficient mobility for bicyclist while making much needed repairs in Asheville in Bun | Pavement Improvement | 12/03/2009 |  | 10/15/2010 | 598994 | 0
7606 | North Carolina | BUNCOMBE |  | 11 | 1302050 | This project consist of installing a pedestrian crosswalk with signals to allow safe travel between two schools located on either side of Overlook Road (SR 3503) in Buncombe County. | Transportation Enhancements | 10/19/2009 |  | 03/19/2010 | 7548 | 0
7607 | North Carolina | BUNCOMBE |  | 11 | 1302051 | This project consist of installing sidewalk and wheelchair ramps at SR 3503 (Overlook Road) at Pinchot Drive in Buncombe County. This project is in conjunction with E-5105A. | Transportation Enhancements | 10/19/2009 | 12/14/2009 | 03/26/2010 | 17223 | 0
7608 | North Carolina | MITCHELL |  | 11 | 1303007 | The project (EL-5107) will construct concrete sidewalks on SR 1260 (South Mitchell Avenue) from Bowman Middle School to NC 226 and along NC 226 from SR 1260 to SR 1211 (Cane Creek Road) in Bakersville | Transportation Enhancements | 12/29/2009 | 05/11/2010 | 08/06/2010 | 100551 | 0
7609 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1305006 | This project will extend existing sidewalk along the US 70 in Black Mountain from Blue Ridge Road to Grovestone Road to promote walkability from surrounding neighborhoods to businesses along this rou | Transportation Enhancements | 08/11/2009 | 03/22/2010 | 07/31/2010 | 233328 | 1.27
7610 | North Carolina | BUNCOMBE | ASHEVILLE | 11 | 1305007 | Preliminary engineering for the Flat Creek Greenway from Cotton Avenue for Charlotte Street as a part of a larger plan to promote multimodal forms of transportation in the Town of Black Mountain and s | Transportation Enhancements | 08/11/2009 | 08/19/2009 | 06/30/2011 | 196503 | 0
7611 | North Carolina | ALAMANCE |  | 6 | 1306020 | This project will widen SR 1306 (Mebane Street) in Burlington / Alamance County from Huffman Mill Road to Chapel Hill Road to four naes with a divided media to enhance safety and improve mobility. | Pavement Widening | 03/02/2009 | 03/02/2009 | 08/15/2011 | 13386283 | 2.563
7612 | North Carolina | YANCEY |  | 11 | 1307004 | This project includes construction of 850 feet of sidewalk in Burnsville to include curb and gutter and drainage items to connect with existing sidewalks and provide safe pedestrian travel along Mitch | Transportation Enhancements | 10/28/2009 | 03/15/2010 | 05/21/2010 | 189719 | 0
7613 | North Carolina | NASH |  | 2 | 1316012 | Replace deficient bridge Number 82 carrying SR 1316/SR 1612 over Cypress Creek in Nash County. | Bridge Replacement | 08/05/2009 | 08/05/2009 | 09/26/2010 | 722314 | 0
7614 | North Carolina | MCDOWELL |  | 11 | 1316013 | The project (EL-5106) will construct concrete sidewalks on SR1001 (Sugar Hill Road) from SR 1168 (Reid Street) to Wilhemenia Street in Maron, McDowell county. | Transportation Enhancements | 12/29/2009 |  | 08/06/2010 | 27953 | 0.1
7615 | North Carolina | GATES |  | 1 | 1320009 | B-4521 - This project will replace bridge #26 on SR 1320 over Duke Swamp in Gates county, North Carolina. | Bridge Replacement | 02/18/2010 |  |  | 675000 | 0
7616 | North Carolina | DURHAM |  | 4 | 1321005 | This project will repave Hillandale Road / Fulton Street in Durham from I-85 to Erwin Road to improve road condition. | Pavement Widening | 05/18/2009 | 05/18/2009 | 05/14/2010 | 299865 | 0
7617 | North Carolina | PITT |  | 1 | 1323004 | This project adds sidewalks along the east side of SR 1323 (Arlington Boulevard) in Greenville from SR 1467 (Stantonsburg Road) to US 13 in Pitt County to improve pedestrian safety. | Transportation Enhancements | 08/18/2009 | 09/11/2009 | 06/23/2010 | 108897 | 0
7618 | North Carolina | BRUNSWICK |  | 7 | 1357005 | This project will realign the intersection of Smith Avenue and NC 130 in Brunswick County to eliminate the offset condition to improve safety and congestion. | Pavement Widening | 03/02/2009 | 03/02/2009 | 12/31/2010 | 6702506 | 1.225
7619 | North Carolina | CHEROKEE |  | 11 | 1393004 | Replace deficient bridge carrying SR 1393 (Rocky Creek-Wakefield Roads) over Junaluska Creek in Cherokee County. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 11/15/2009 | 480727 | 0
7620 | North Carolina | SURRY |  | 5 | 1396002 | Paint bridges carrying SR 1396 (Pine Ridge Rd), SR 1602, and SR 1649 (Clyde Hayes Rd) over I-77 in Surry County to extend the life of the structures. | Bridge Improvement | 05/01/2009 |  | 10/23/2010 | 385910 | 0
7621 | North Carolina | HENDERSON | ASHEVILLE | 11 | 1413010 | This project will construct a new road around the Oakdale Cemetery in Hendersonville and will provide access from US 64 to Hendersonville Elementary and Middle schools without disturbing the cemetery | Other | 10/26/2009 | 11/05/2009 | 07/01/2010 | 363000 | 0.2
7622 | North Carolina | HENDERSON | ASHEVILLE | 11 | 1429003 | This project will construct the Cane Creek Greenway in Fletcher which includes a 10 feet multi-use greenway trail along the banks of Cane Creek to enhance pedestrian access in Henderson County. This | Transportation Enhancements | 09/23/2009 | 01/13/2010 | 06/30/2010 | 222517 | 0
7623 | North Carolina | HENDERSON | ASHEVILLE | 11 | 1429004 | This project will construct a sidewalk in Fletcher along St. Johns Road from US 25 to Fanning Bridge Road to enhance pedestrian access within the Town of Fletcher in Henderson County. This is a local | Transportation Enhancements | 09/23/2009 | 01/13/2010 | 06/30/2010 | 390830 | 0.66
7624 | North Carolina | HENDERSON | ASHEVILLE | 11 | 1429005 | U-5184 - This project will construct the Cane Creek Greenway in Fletcher, Henderson county, North Carolina | Other | 02/11/2010 |  |  | 51286 | 0
7625 | North Carolina | HENDERSON | ASHEVILLE | 11 | 1430006 | This project will construct a brick paver sidewalk in the Village of Flat Rock along US 225 and Little River Road to enhance pedestrian access within the central historic area of the Village in Haywoo | Transportation Enhancements | 09/23/2009 |  |  | 55000 | 0
7626 | North Carolina | HALIFAX |  | 1 | 1434004 | Replace deficient bridge Number 24 carrying SR 1434 over Quankey Creek in Halifax County. | Bridge Replacement | 03/15/2010 | 03/01/2010 | 07/01/2010 | 538152 | 0
7627 | North Carolina | WAKE | RALEIGH | 04 | 1435008 | The project (R-5169B) will mill, strengthen, and resurface SR 1435 (Old Raleigh Road) from Mason Street to SR 1521 (Lake Pine Drive) and SR 1521 (Lake Pine Drive) from SR 1435 (Old Raleigh Road) to US | Pavement Improvement | 12/15/2009 | 05/03/2010 |  | 626973 | 2.5
7628 | North Carolina | GUILFORD |  | 6,12 | 1486002 | This project will repave SR 1486/1768 (Lexington Avenue) from Montlieu Avenue to US 311 Business in High Point in Guilford County to improve ride quality and extend pavement life. | Pavement Improvement | 09/14/2009 |  | 11/15/2009 | 689533 | 2.24
7629 | North Carolina | HAYWOOD | ASHEVILLE | 11 | 1499003 | Preliminary engineering for the construction of sidewalks along Moody Farm Road terminating at Soco Road (US 19) enhancing pedestrian access within the Town of Maggie Valley in Haywood County. This i | Transportation Enhancements | 08/19/2009 | 08/19/2009 | 11/29/2010 | 915738 | 1.88
7630 | North Carolina | HAYWOOD | ASHEVILLE | 11 | 1499004 | Maggie Valley: Two Pedestrian Bridges At Jonathan Creek Along Moody Farm Road (SR 1307) In Haywood County, North Carolina | Transportation Enhancements | 09/23/2009 | 04/01/2010 | 11/09/2010 | 687970 | 0
7631 | North Carolina | LENOIR |  | 3 | 1515009 | B-4570 - This project will replace bridge #79 on SR 1544 over Gum Swamp Creek in Lenior county, North Carolina. | Bridge Replacement | 02/11/2010 | 05/10/2010 | 09/24/2010 | 669494 | 0
7632 | North Carolina | GUILFORD |  | 6, 12 | 1538007 | This project will provide for the realignment, resurfacing, sidewalks and drainiage improvements on SR 1538 (Deep River Road) at Sunset Hollow Drive to NC 68 (Eastchester Drive) at Lake Forest Drive o | Pavement Improvement | 09/23/2009 |  | 11/06/2010 | 1508572 | 0.5
7633 | North Carolina | STANLY |  | 8 | 1542009 | This project will relocate a portion of SR 1542 (Ridge St) and extend SR 1542 on new location from existing Ridge Street west of SR 1545 (Mountain View Church Rd) to SR 1549 (Airport Rd) in Stanly Cou | New Construction | 03/02/2009 | 03/02/2009 | 12/31/2010 | 4109737 | 0
7634 | North Carolina | LENOIR |  | 3 | 1544005 | B-4604 - This project will replace bridge #13 on SR 1753 over Indian Wells Swamp in Pitt county, North Carolina. | Bridge Replacement | 06/01/2010 | 06/17/2010 | 12/14/2010 | 547746 | 0
7635 | North Carolina | RANDOLPH |  | 6 | 1547008 | This project will make improvements to increase mobility and safety at the intersection of SR 1547 (Finch Farm Road) at the intersection of SR 1533 (Mountain Road) and SR 3106 (Kennedy Road) in Trini | Other | 09/17/2009 | 09/17/2009 |  | 135000 | 0
7636 | North Carolina | FORSYTH, STOKES | WINSTON-SALEM | 5 | 1611007 | Widen Doral Drive / Main Street in Forsyth and Stokes Counties, between Tobaccoville and King, to enhance safety and mobility. | Pavement Widening | 04/27/2009 | 04/27/2009 | 08/15/2011 | 14684035 | 1.02
7637 | North Carolina | ANSON |  | 8 | 1627009 | Replace deficient bridge carrying SR 1627 (Pinkston-River Rd.) over Winston-Salem Southbound Railroad in Anson County. Includes TIP project B-4410 (replace bridge #307). | Bridge Replacement | 06/22/2009 | 06/22/2009 | 09/01/2011 | 2526117 | 0
7638 | North Carolina | DURHAM |  | 4 | 1666002 | This project provides for the installation of sidewalk in Durham on SR 1666 (Dearborn Drive) from SR 1004 (Old Oxford Highway) to Ruth Street to improve pedestrian access and safety in Durham County. | Transportation Enhancements | 09/16/2009 |  |  | 579977 | 6.13
7639 | North Carolina | SCOTLAND |  | 8 | 1674005 | This project will widen Lauchwood Drive in Laurinburg / Scotland County from US 15-401 Business to US 501 to improve traffic flow. | Pavement Widening | 03/02/2009 | 03/02/2009 | 07/15/2010 | 2724877 | 1.2
7640 | North Carolina | PITT |  | 3 | 1708008 | This project provides for the construction of SR 1708 (Fire tower Road) from SR 1709 (Corey Road) to NC 43 to improve safety and mobility in Pitt County. This is a locally administered project by the | Pavement Improvement | 10/19/2009 | 03/15/2010 | 08/31/2010 | 800000 | 1.04
7641 | North Carolina | WAKE |  | 13 | 1728004 | This project will repave the following roadways in Wake County to improve road condition: Wade Avenue from Faircloth Street to Capital Boulevard (Raleigh), Old Raleigh Road from Gregson Drive to Maso | Pavement Improvement | 08/05/2009 | 08/05/2009 | 06/11/2010 | 1497307 | 2.5
7642 | North Carolina | PITT |  | 3 | 1753003 | B-4568 - This project will replace bridge #67 on SR 1515 over Falling Creek in Lenior county, North Carolina. | Bridge Replacement | 02/18/2010 |  | 12/14/2010 | 666600 | 0
7643 | North Carolina | GASTON |  | 9,10 | 1800006 | B-4519 - This project will replace Bridge #155 on SR 1800 over Little Long Creek in Gaston county, North Carolina. | Bridge Replacement | 02/19/2010 | 04/19/2010 | 08/20/2010 | 700000 | 0
7644 | North Carolina | GUILFORD |  | 06 | 1853001 | The project (R-4436GED) will implement environmental restoration and pollution abatement at the NCDOT west maintenance yard on Sandy Camp Road in Guilford county. | Other | 12/29/2009 |  | 10/30/2010 | 146719 | 0
7645 | North Carolina | HAYWOOD |  | 11 | 1890003 | B-2988 - This project will replace bridge #13 on SR 1890 over East Fork of Pigeon River in Haywood county, North Carolina. | Bridge Replacement | 02/19/2010 |  | 10/14/2010 | 905724 | 0
7646 | North Carolina | RUTHERFORD |  | 10,11 | 1913003 | B-4633 - This project will replace bridge #32 on SR 1913 over Webbs Creek in Rutherford county, North Carolina. | Bridge Replacement | 02/19/2010 |  |  | 800000 | 0
7647 | North Carolina | JOHNSTON |  | 2 | 1923009 | This project will extend Booker Dairy Road from US 70 Business to Buffalo Road in Johnston County. Route will be a two lane roadway with a new bridge over the Neuse River. | New Construction | 04/09/2009 | 04/09/2009 | 12/31/2011 | 11673744 | 0
7648 | North Carolina | NASH |  | 2 | 1945005 | Replace deficient bridge Number 69 carrying SR 1945 over Toisnot Swamp in Nash County. | Bridge Replacement | 09/11/2009 | 09/11/2009 | 05/24/2010 | 782000 | 0
7649 | North Carolina | RANDOLPH |  | 06 | 1952001 | The project (U-5194) will improve the intersections of SR 1952 (High Point Street) at SR 1950 (Academy Street) and SR 1989 (Tiger's Den Road) and the Walmart entrance in Randolph county. | Other | 11/09/2009 | 04/26/2010 | 05/01/2011 | 1180122 | 0.4
7650 | North Carolina | STANLY |  | 8 | 1968003 | Replace deficient bridge carrying SR 1968 (St. Martin Rd.) over Long Creek in Stanly County. | Bridge Replacement | 01/12/2010 | 04/05/2010 | 11/15/2010 | 1048491 | 0
7651 | North Carolina | GUILFORD |  | 6 | 1970001 | Repair bridge expansion joints on 12 structures: Bridge 12 on SR 1970, Bridge 274 on US 220, Bridge 136 on SR 2254, Bridge 220 on SR 1547, Bridge 757 on US 311 Business, Bridge 287 on US 70 (Wendover | Bridge Improvement | 08/05/2009 | 08/05/2009 | 05/29/2010 | 199652 | 0
7652 | North Carolina | DURHAM |  | 4 | 1978003 | This project will repave US 158 Bypass in Granville County from US 15 to US 158 Business to improve road condition. | Pavement Widening | 05/13/2009 | 05/13/2009 | 05/14/2010 | 128414 | 0
7653 | North Carolina | RUTHERFORD |  | 10, 11 | 2169001 | The project will realign Brick Store Road (SR 2194) to intersect across from Pine Ridge Rd (SR 2159) and with Oakland Rd (SR 2193) at the existing signal in Forrest City in Rutherford County. The pur | Pavement Improvement | 10/19/2009 | 02/23/2010 | 10/22/2010 | 633052 | 0
7654 | North Carolina | MECKLENBURG | CHARLOTTE | 9, 12 | 2693002 | This project includes the construction of a roundabout in Davidson at the intersection of SR-2420 (East Rocky River Road) and SR 2693 (Davidson-Concord Road) to improve safety In Mecklenburg County. | Safety/Traffic Management | 05/13/2009 | 05/13/2009 | 10/23/2009 | 516055 | 0
7655 | North Carolina | GUILFORD |  | 06 | 2825001 | The project (R-4436GD) will implement environmental restoration and pollution abatement at the NCDOT east maintenance yard on Camp Burton Road in Guilford county. | Other | 09/24/2009 |  | 10/30/2010 | 135511 | 0
7656 | North Carolina | MECKLENBURG |  | 9 | 4497001 | U-5198 - This project will mill and resurface SR 4497 (Independence Point Parkway) from NC 51 to Matthews-Mint Hill Road in Matthews, Mecklenburg county, North Carolina. | Pavement Improvement | 01/21/2010 |  |  | 245000 | 0.45
7657 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 0008027 | This Bismarck project is an enhancement project to contstruct a shared use path at United Tribes Technical College. | Transportation Enhancements | 03/01/2010 | 05/17/2010 | 07/31/2010 | 170925 | 0
7658 | North Dakota | CASS |  | 00 | 0009030 | This Cass County project is a Structure Replacement project on a Off-System Bridge at Maple River, 6 miles East & 6 miles south of Alice. | Bridge Replacement | 06/01/2009 | 08/20/2009 | 10/03/2009 | 487890.38 | 0.047
7659 | North Dakota | TOWNER |  | 00 | 0048010 | This Towner County project is a Structure Replacement project on Off-System Bridge Off-System - 2 Miles South & 1 Mile West of Cando. | Bridge Replacement | 08/10/2009 | 09/28/2009 | 10/31/2009 | 287305.08 | 0.047
7660 | North Dakota | BARNES |  | 00 | 0221069 | This Barnes County project is a Microsurfacing on CMC 221 - From10 Miles South of Valley City, N to preserve the pavement structure. | Pavement Improvement | 06/23/2009 | 09/03/2009 | 09/15/2009 | 533000 | 9.607
7661 | North Dakota | BOTTINEAU |  | 00 | 0520055 | This Bottineau County project is a Microsurfacing on CMC 0520 - From the Souris River, E to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 06/23/2009 | 09/01/2009 | 233058.04 | 4.56
7662 | North Dakota | BOTTINEAU |  | 00 | 0547058 | This Bottineau project is an enhancement project to complete surfacing of a shared use path at Lake Metigoshe from Sam Mill corner north. | Transportation Enhancements | 03/09/2010 |  | 10/15/2010 | 350509.03 | 0
7663 | North Dakota | CASS |  | 00 | 0918055 | This Cass County project is a Thin Lift Overlay on CMC 0918 - From 8 Miles West of ND 18, E to preserve the pavement structure. | Pavement Improvement | 06/01/2009 | 06/11/2009 | 08/28/2009 | 995719 | 8.039
7664 | North Dakota | CAVALIER |  | 00 | 1017061 | This Cavalier County project is a Chip Seal Coat on CMC 1017 - From ND 5, N to Wales to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 08/03/2009 | 09/01/2009 | 243461.81 | 8.966
7665 | North Dakota | BURLEIGH |  | 00 | 1083071 | This NDDOT project is a structure replacement project on US 83, to replace the Sterling Railroad separation. | Bridge Replacement | 02/09/2010 | 04/14/2010 | 11/05/2011 | 1784825.87 | 0.1
7666 | North Dakota | BURLEIGH |  | 00 | 1083078 | This NDDOT project is a surcharge project prior to a structure replacment project on US 83 for the Sterline Railroad separation. | Pavement Improvement | 02/09/2010 | 04/14/2010 | 08/07/2010 | 425389.69 | 0.1
7667 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1083086 | This Bismarck project is a Mill & Asphalt Overlay, Curb & Gutter, Marking and Video Detection on Bismarck - 7th Street from Bismarck Expressway to Boulevard Avenue to rehabilitate the pavement structu | Pavement Improvement | 07/14/2009 | 08/10/2009 | 10/15/2009 | 658920 | 1.47
7668 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1083087 | This Bismarck project is a Mill & Asphalt Overlay, Curb & Gutter, Marking and Video Detection on Bismarck - 9th Street from Bismarck Expressway to Boulevard Avenue to rehabilitate the pavement structu | Pavement Improvement | 07/14/2009 | 08/24/2009 | 10/15/2009 | 403664 | 1.47
7669 | North Dakota | BURLEIGH |  | 00 | 1083088 | This NDDOT project is a thin overlay on US 83 from Bismarck north to south of Wilton to preserve the pavement structure. | Pavement Improvement | 04/19/2010 |  | 10/15/2010 | 6627764.86 | 19.866
7670 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1083093 | This NDDOT project is a thin overlay on US 83 from Bismarck north to 57th Ave to preserve the pavement structure. | Pavement Improvement | 04/19/2010 |  | 10/15/2010 | 482384.82 | 1.492
7671 | North Dakota | KIDDER |  | 00 | 1094121 | This NDDOT project is a Mill & Hot Bituminous Pavement on I 94 - From County Line E TO Dawson to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 | 04/20/2010 | 09/19/2010 | 4355847 | 15.574
7672 | North Dakota | KIDDER |  | 00 | 1094122 | This NDDOT project is a Mill & Hot Bituminous Pavement on I 94 - From County Line TO E Dawson Interchange to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 | 04/20/2010 | 09/19/2010 | 5214656.59 | 15.684
7673 | North Dakota | DICKEY |  | 01 | 1112062 | This Dickey County project is a shoulder widening and aggregate project on CMC 1112 - 9 miles west of ND 1, east to widen the pavement structure. | Pavement Improvement | 05/07/2010 |  | 09/25/2010 | 731000 | 4.104
7674 | North Dakota | DIVIDE |  | 00 | 1249059 | This Divide County project is a Chip Seal Coat on CMC 1249 - From 9 & 18 Miles South of Noonan, N to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 07/22/2009 | 09/01/2009 | 159553 | 6.127
7675 | North Dakota | EMMONS |  | 00 | 1515051 | This Emmons County project is a Hot Bituminous Pavement on CMC 1515 - 0.5 miles south of ND 32, N to rehabilitate the pavement structure. | Pavement Improvement | 07/27/2009 | 09/09/2009 | 10/01/2009 | 161532.12 | 0.5
7676 | North Dakota | FOSTER |  | 00 | 1613054 | This Foster County project is a microsurface on CMC 1613 from ND 9 north to preserve the pavement structure. | Pavement Improvement | 02/22/2010 |  | 09/15/2010 | 484716 | 16.969
7677 | North Dakota | GRANT |  | 00 | 1919054 | This Grant County project is a grading project on CMC 1919 from 26 miles south of Heil, north, to reconstruct the pavement structure. | Pavement Improvement | 03/04/2010 |  | 10/15/2010 | 488291.63 | 2
7678 | North Dakota | BURLEIGH |  | 00 | 1981086 | This Bismarck project is a Hot Bituminous Pavement and Curb & Gutter on Bismarck - North 19th Street from 75' N of E Century Ave to Oregon Dr to rehabilitate the pavement structure. | Pavement Improvement | 08/17/2009 | 09/02/2009 | 08/01/2010 | 755631.64 | 0.28
7679 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1981088 | This Bismarck project is a Concrete Pavement Repair and Mill & Overlay on Bismarck - West Main Avenue from Washington Street to Memorial Highway to rehabilitate the pavement structure. | Pavement Improvement | 06/23/2009 | 07/16/2009 | 08/01/2010 | 1367500 | 0.88
7680 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1981089 | This Bismarck project is a Mill & Asphalt Overlay on Bismarck - South Washington Street from Bismarck Expressway to 175' south of Billings Drive to rehabilitate the pavement structure. | Pavement Improvement | 08/17/2009 | 09/28/2009 | 08/01/2010 | 594755 | 1
7681 | North Dakota | BURLEIGH | BISMARCK-MANDAN | 00 | 1981091 | This Bismarck Project is an enhancement project to construct a bike/ped facility along South Washington Street. | Transportation Enhancements | 03/23/2010 |  | 10/29/2010 | 314257.56 | 0
7682 | North Dakota | MORTON | BISMARCK-MANDAN | 00 | 1988026 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - Division St NE from Collins Ave to 8th Ave NE to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 08/03/2009 | 09/18/2009 | 300000 | 0.511
7683 | North Dakota | MORTON | BISMARCK-MANDAN | 00 | 1988028 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 14th St NE from Collins Ave to 3rd Avenue NE to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 08/26/2009 | 09/18/2009 | 150000 | 0.246
7684 | North Dakota | MORTON | BISMARCK-MANDAN | 00 | 1988029 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 3rd Ave NE from 5th St NE to 14th St NE to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 08/17/2009 | 09/18/2009 | 250000 | 0.39
7685 | North Dakota | MORTON |  | 00 | 1988030 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 27th St NW from 12th Ave NW to 8th Ave NW to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 10/08/2009 | 06/30/2010 | 150000 | 0.231
7686 | North Dakota | MORTON | BISMARCK-MANDAN | 00 | 1988031 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - Old Red Trail from Sunset Drive to Collins Avenue to rehabilitate the pavement structure. | Pavement Improvement | 07/09/2009 | 10/08/2009 | 06/30/2010 | 400000 | 0.795
7687 | North Dakota | MORTON | BISMARCK-MANDAN | 00 | 1988032 | This Mandan Project is an enhancement project to construct a bike/ped facility from Main St/Mandan Ave south to 3rd St Trolley Station. | Transportation Enhancements | 04/19/2010 |  | 10/15/2010 | 385438.36 | 0
7688 | North Dakota | BARNES |  | 00 | 2001053 | This NDDOT project is a Thin Lift Overlay on ND 1 - From W Jct I-94 N To Jct ND 26-DAZEY to preserve the pavement structure. | Pavement Improvement | 10/06/2009 | 05/03/2010 | 10/02/2010 | 4332048.58 | 19.329
7689 | North Dakota | LOGAN, MCINTOSH, LA MOURE |  | 00 | 2013028 | This NDDOT project is a Thin Lift Overlay on ND 13 - From JCT 30 East To E JCT 56 to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 09/17/2009 | 10/17/2009 | 2098744.99 | 19.763
7690 | North Dakota | KIDDER |  | 00 | 2094081 | This NDDOT project is a Hot Bituminous Pavement on I 94 - From E Dawson Interchange To Crystal Springs to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 | 05/17/2010 | 10/02/2010 | 2778734.27 | 11.863
7691 | North Dakota | BARNES |  | 00 | 2094082 | This NDDOT project is a Hot Bituminous Pavement on I 94 - From W Eckelson E To E ND 1-OAKES to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 | 05/17/2010 | 10/02/2010 | 2887483.15 | 13.168
7692 | North Dakota | HETTINGER |  | 00 | 2117056 | This Hettinger County project is a Hot Bituminous Pavement on CMC 2117 - 0.8 Miles N of ND 21, N to rehabilitate the pavement structure. | Pavement Improvement | 01/07/2010 | 05/20/2010 | 10/01/2010 | 484084 | 5
7693 | North Dakota | KIDDER |  | 00 | 2215054 | This Kidder County project is a Hot Bituminous Pavement on CMC 2215 - From 5 Miles South of ND 36, N to rehabilitate the pavement structure. | Pavement Improvement | 06/24/2009 | 09/23/2009 | 10/02/2009 | 687270.6 | 5.17
7694 | North Dakota | LA MOURE |  | 00 | 2281034 | This NDDOT project is a Microsurfacing and Chip Seal on US 281 - From Edgeley To 1.345 MI N JCT 46 to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/24/2009 | 09/19/2009 | 709552.95 | 20.274
7695 | North Dakota | STUTSMAN |  | 00 | 2281036 | This Jamestown project is a Concrete Pavement Repair, Dowel Bar Retrofit, and Grinding on Jamestown - US 281 from 17th St SW to 4th Ave SW to rehabilitate the pavement structure. | Pavement Improvement | 01/06/2010 | 05/17/2010 | 10/15/2010 | 525664.88 | 0.46
7696 | North Dakota | MCHENRY |  | 00 | 2511055 | This McHenry County project is a Microsurfacing on CMC 2511 - From 7 Miles North of Granville, N to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 06/16/2009 | 09/01/2009 | 249923.3 | 5.006
7697 | North Dakota | MCKENZIE |  | 00 | 2755053 | This McKenzie County project is a Hot Bituminous Pavement on CMC 2755 - From 4.5 Miles North of Keene, N to rehabilitate the pavement structure. | Pavement Improvement | 05/29/2009 | 08/19/2009 | 09/01/2009 | 264525 | 6.275
7698 | North Dakota | MCLEAN |  | 00 | 2800009 | This McLean County project is a Microsurfacing on CMC 2828, 2836, & 2879 - County Wide to preserve the pavement structure. | Pavement Improvement | 06/29/2009 | 07/09/2009 | 09/19/2009 | 317756.65 | 12.176
7699 | North Dakota | STUTSMAN |  | 00 | 2987031 | This Jamestown project is a Mill and Overlay, Signing, Striping, and Mailbox Post Replacement on Jamestown - 3rd Street E from BNSF Railroad to 87th Avenue SE to rehabilitate the pavement structure. | Pavement Improvement | 07/17/2009 | 08/18/2009 | 09/05/2009 | 679198.39 | 2.88
7700 | North Dakota | BARNES |  | 00 | 2990024 | This Valley City project is a Mill & Asphalt Overlay on Valley City - Wintershow Road from 4th Avenue SW to 5th Avenue SE to rehabilitate the pavement structure. | Pavement Improvement | 03/17/2010 |  | 08/28/2010 | 266451.82 | 0.538
7701 | North Dakota | BARNES |  | 00 | 2990025 | This Valley City project is a Chip Seal Coat on Valley City - 7th Street SE from 5th Avenue SE to 12th Avenue SE to preserve the pavement structure. | Pavement Improvement | 03/17/2010 |  | 08/28/2010 | 35787 | 0.473
7702 | North Dakota | BARNES |  | 00 | 2990026 | This Valley City project is a Mill & Asphalt Overlay on Valley City - 2nd Street NW from 9th Avenue NW to Central Avenue to rehabilitate the pavement structure. | Pavement Improvement | 03/17/2010 |  | 08/28/2010 | 231536.14 | 0.545
7703 | North Dakota | BARNES |  | 00 | 2990027 | This Valley City project is a Mill & Asphalt Overlay on Valley City - 2nd Street NE from 3rd Ave NE to 6th Ave NE to rehabilitate the pavement structure. | Pavement Improvement | 03/17/2010 |  | 08/28/2010 | 104636.72 | 0.191
7704 | North Dakota | MORTON |  | 00 | 3000009 | This Morton County project is a Chip Seal Coat on CMC 3003 & 3006 - County Wide to preserve the pavement structure. | Pavement Improvement | 08/03/2009 | 08/28/2009 | 09/01/2009 | 358562 | 14.485
7705 | North Dakota | RAMSEY |  | 00 | 3002099 | This NDDOT project is a Concrete Pavement Repair, Dowel Bar Retrofit and Grinding on US 2 - From Mauvais Coulee To Channel A to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 | 06/01/2010 | 09/15/2010 | 4519241.25 | 14.704
7706 | North Dakota | PIERCE |  | 00 | 3002106 | This NDDOT project is a Thin Lift Overlay on US 2 - From Rugby E To Near Leeds to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/02/2010 | 3783505.47 | 23.993
7707 | North Dakota | PIERCE |  | 00 | 3003023 | This NDDOT project is a Hot Bituminous Pavement on ND 3 - From Rugby N TO JCT 66-Fonda to rehabilitate the pavement structure. | Pavement Improvement | 05/26/2009 | 06/24/2009 | 10/10/2009 | 4583614.25 | 22.957
7708 | North Dakota | BENSON |  | 00 | 3019042 | This NDDOT project is a thin overlay on ND 19 from Esmond east to junction ND 30 to preserve the pavement structure. | Pavement Improvement | 01/20/2010 |  | 10/09/2010 | 1808461.36 | 12.564
7709 | North Dakota | BENSON |  | 00 | 3019046 | This NDDOT project is a thin overlay on ND 19 from Benson County line to Esmond to preserve the pavement structure. | Pavement Improvement | 01/20/2010 |  | 10/09/2010 | 575697.6 | 4.082
7710 | North Dakota | RAMSEY |  | 00 | 3019047 | This Devils Lake project is a Mill & Asphalt Overlay on Devils Lake - ND 19 from US 2 to ND 20 (Asphalt Portion only) to rehabilitate the pavement structure. | Pavement Improvement | 05/26/2009 | 08/22/2009 | 10/01/2009 | 75000 | 0.182
7711 | North Dakota | PIERCE |  | 00 | 3019050 | This NDDOT project is a thin overlay on ND 19 from junction ND 3 to the county line to preserve the pavement structure. | Pavement Improvement | 01/20/2010 |  | 10/09/2010 | 861427.36 | 4.698
7712 | North Dakota | WARD |  | 00 | 3020081 | This Devils Lake project is a Mill & Asphalt Overlay on Devils Lake - ND 20 from US 2 to (RP 104.408) Urban Limits (exception 3rd St NW to 6th St NE) to rehabilitate the pavement structure. | Pavement Improvement | 05/26/2009 | 08/05/2009 | 10/01/2009 | 647824 | 1.504
7713 | North Dakota | RAMSEY |  | 00 | 3020086 | This Devils Lake project is an enhancement project to install entrance welcome signage at the city of Devils Lake at ND 20 north and south of town. | Transportation Enhancements | 03/02/2010 | 05/10/2010 | 06/25/2010 | 160297 | 0
7714 | North Dakota | MOUNTRAIL |  | 00 | 3100009 | This Mountrail County project is a Chip Seal Coat on CMC 3114, 3133, 3136, & 3143 - County Wide to preserve the pavement structure. | Pavement Improvement | 07/21/2009 | 08/21/2009 | 09/04/2009 | 264592 | 11.835
7715 | North Dakota | NELSON |  | 00 | 3204064 | This Nelson County project is a Chip Seal Coat on CMC 3204 - From ND 1, E to preserve the pavement structure. | Pavement Improvement | 05/22/2009 | 08/05/2009 | 08/15/2009 | 283946.62 | 9.993
7716 | North Dakota | PEMBINA |  | 00 | 3428053 | This Pembina County project is a Structure Replacement project on CMC 3428 - 6 Miles West of Pittsburg. | Bridge Replacement | 07/13/2009 | 07/28/2009 | 10/31/2009 | 299600.91 | 0.1
7717 | North Dakota | PIERCE |  | 00 | 3521058 | This Pierce County project is a Chip Seal Coat on CMC 3521 - City of Rugby to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 07/23/2009 | 09/01/2009 | 100003.62 | 2.807
7718 | North Dakota | PIERCE |  | 00 | 3521059 | This Pierce County project is a Chip Seal Coat on CMC 3521 - City of Rugby CMC 3521 Spur to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 07/24/2009 | 09/01/2009 | 33650.85 | 1.116
7719 | North Dakota | RAMSEY |  | 00 | 3627061 | This Ramsey County project is a grading, widening, and HBP project on CMC 3627 - From the Benson County Line, N, to reconstruct the pavement structure. | Pavement Improvement | 02/22/2010 | 05/31/2010 | 09/25/2010 | 253804 | 3.244
7720 | North Dakota | RANSOM |  | 00 | 3705055 | This Ransom County project is a Chip Seal Coat on CMC 3705 - 8 miles south of ND 46, N to preserve the pavement structure. | Pavement Improvement | 06/16/2009 | 08/25/2009 | 09/01/2009 | 185632 | 8.022
7721 | North Dakota | RICHLAND |  | 00 | 3913054 | This Richland County project is a Hot Bituminous Pavement on CMC 3913 - 4 miles north of Barney, N to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 | 09/14/2009 | 10/02/2009 | 407833 | 4
7722 | North Dakota | WARD |  | 00 | 4002084 | This NDDOT project is a Thin Lift Overlay on US 2 - From 3 Miles W Jct 52 E TO 1 Mile W Jct 83 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 | 05/03/2010 | 10/02/2010 | 2381095.48 | 14.192
7723 | North Dakota | WARD |  | 00 | 4002092 | This NDDOT project is a Thin Lift Overlay on US 2 - From 3 Miles West of Jct 52 East TO 1 Mile West Jct 83 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 | 05/03/2010 | 10/02/2010 | 2311718.04 | 13.934
7724 | North Dakota | ROLETTE |  | 00 | 4006060 | This Rolette County project is a Hot Bituminous Pavement on CMC 4006 - From 5.7 Miles West of St. John, E to rehabilitate the pavement structure. | Pavement Improvement | 05/26/2009 | 07/24/2009 | 10/09/2009 | 796362 | 5.667
7725 | North Dakota | ROLETTE |  | 00 | 4006062 | This Rolette County project is an enhancement project to complete surfacing of a shared use path near St. John from the Horse Arena to town | Transportation Enhancements | 03/02/2010 |  | 10/15/2010 | 105301.9 | 0
7726 | North Dakota | MOUNTRAIL |  | 00 | 4023009 | This NDDOT project is a Thin Lift Overlay on ND 23 - From JCT 8 East To Makoti to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/17/2009 | 10/10/2009 | 2348797.22 | 23.896
7727 | North Dakota | WARD |  | 00 | 4023010 | This NDDOT project is a Thin Lift Overlay on ND 23 - From Makoti E To JCT US 83 to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/17/2009 | 10/10/2009 | 2542353.46 | 24.869
7728 | North Dakota | MCLEAN, MOUNTRAIL |  | 00 | 4037012 | This NDDOT project is a Thin Lift Overlay on ND 37 - From JCT 23-Parshall-S TO 1 MI W ND 1804 to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/10/2009 | 10/10/2009 | 1880576.02 | 15.693
7729 | North Dakota | MCLEAN |  | 00 | 4037013 | This NDDOT project is a Thin Lift Overlay on ND 37 - From 1 MI W JCT 1804 E & S TO Emmet Corner to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/10/2009 | 10/10/2009 | 2916300.13 | 28.112
7730 | North Dakota | MCLEAN |  | 00 | 4083053 | This NDDOT project is a Grading, Base and Asphalt Pavement project on US 83 - From Near JCT 37 N TO 0.6 MI N Max Southbound to reconstruction the existing pavement. | Pavement Improvement | 04/21/2009 | 05/20/2009 | 10/17/2009 | 9346770.49 | 13.358
7731 | North Dakota | SARGENT |  | 00 | 4124052 | This Sargeant County project is a Hot Bituminous Pavement project on CMC 4124 - From 3.5 Miles East of ND 32, E, to rehabilitate the pavement. | Pavement Improvement | 03/02/2010 |  | 09/18/2010 | 211998 | 1.993
7732 | North Dakota | SARGENT |  | 00 | 4125059 | This Sargeant County project is a Hot Bituminous Pavement project on CMC 4125 - From 1 Mile North of County Line, N, to rehabilitate the pavement. | Pavement Improvement | 03/02/2010 |  | 09/18/2010 | 317996 | 3.019
7733 | North Dakota | STARK |  | 00 | 4510060 | This Stark County project is a Thin Lift Overlay on CMC 4510 - From South Heart, East to preserve the pavement structure. | Pavement Improvement | 07/07/2009 | 08/12/2009 | 10/16/2009 | 680000 | 4.871
7734 | North Dakota | GRIGGS |  | 00 | 4612051 | This Steele County project is a Chip Seal Coat on CMC 4612 - Griggs co ln, east to ND 32 to preserve the pavement structure. | Pavement Improvement | 07/07/2009 | 07/20/2009 | 09/01/2009 | 136481 | 8
7735 | North Dakota | STUTSMAN |  | 00 | 4718058 | This Stutsman County project is a Chip Seal Coat on CMC 4718 - From Buchanan, E to preserve the pavement structure. | Pavement Improvement | 06/16/2009 | 07/14/2009 | 09/01/2009 | 143265.59 | 7.141
7736 | North Dakota | STUTSMAN |  | 00 | 4718059 | This Stutsman County project is a Chip Seal Coat on CMC 4718 - From ND 20, E to preserve the pavement structure. | Pavement Improvement | 06/16/2009 | 07/14/2009 | 09/01/2009 | 160737.27 | 8.01
7737 | North Dakota | WARD |  | 00 | 4989070 | This Minot project is a Mill & Asphalt Overlay on Minot - 31st Ave SW from Broadway to 16th St SW to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 | 08/03/2009 | 07/01/2010 | 379301.71 | 1.009
7738 | North Dakota | WARD |  | 00 | 4989071 | This Minot project is a Mill & Asphalt Overlay on Minot - 4th Ave NW from Broadway to Bypass to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 | 08/03/2009 | 07/01/2010 | 878864.52 | 1.822
7739 | North Dakota | WARD |  | 00 | 4989072 | This Minot project is a Chip Seal Coat on Minot - 11th Ave S from Hiawatha to 16th St SW to preserve the pavement structure. | Pavement Improvement | 07/17/2009 | 08/03/2009 | 09/01/2009 | 90661.88 | 1.391
7740 | North Dakota | WARD |  | 00 | 4989073 | This Minot project is a Chip Seal Coat on Minot - 31st Ave SE from Broadway to 13th St SE to preserve the pavement structure. | Pavement Improvement | 07/17/2009 | 08/03/2009 | 09/01/2009 | 49839.39 | 0.987
7741 | North Dakota | WARD |  | 00 | 4989075 | This Minot project is a Mill & Asphalt Overlay on Minot - 3rd St NE from Hillcrest to Airport to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 | 08/04/2009 | 07/01/2010 | 136353.18 | 0.502
7742 | North Dakota | WARD |  | 00 | 4989076 | This Minot project is a Chip Seal Coat on Minot - 3rd St NE from Hillcrest to 5th Ave NE to preserve the pavement structure. | Pavement Improvement | 07/17/2009 | 08/03/2009 | 09/01/2009 | 43499.82 | 0.417
7743 | North Dakota | WARD |  | 00 | 4989077 | This Minot project is a Asphalt Overlay on Minot - 11th Ave SE from 31st St SE to 42nd St SE to rehabilitate the pavement structure. | Pavement Improvement | 12/30/2009 | 06/04/2010 | 10/15/2010 | 160242.09 | 0.739
7744 | North Dakota | WARD |  | 00 | 4989078 | This Minot project is a Asphalt Overlay on Minot - 31st St SE from Burdick Expressway to 11th Ave SE to rehabilitate the pavement structure. | Pavement Improvement | 12/30/2009 | 06/04/2010 | 10/15/2010 | 32489.52 | 0.254
7745 | North Dakota | WARD |  | 00 | 4989079 | This Minot project is a Mill & Asphalt Overlay on Minot - Railway Ave from 5th St NE to 13th St NE to rehabilitate the pavement structure. | Pavement Improvement | 12/30/2009 |  | 10/15/2010 | 227356.26 | 0.53
7746 | North Dakota | WARD |  | 00 | 4989080 | This Minot project is a Chip Seal Coat on Minot - 27th St from Burdick to Railway Ave to preserve the pavement structure. | Pavement Improvement | 07/17/2009 | 08/03/2009 | 09/01/2009 | 42761.53 | 0.657
7747 | North Dakota | WARD |  | 00 | 4989081 | This Minot project is a Chip Seal Coat on Minot - 21st Ave NW from US 83 Bypass to 20th St NW to preserve the pavement structure. | Pavement Improvement | 07/17/2009 | 08/03/2009 | 09/01/2009 | 42122.69 | 0.625
7748 | North Dakota | WARD |  | 00 | 4989082 | This Minot project is an interior reconstruction of the Amtrak Depot in Minot - 401 1st Avenue SW. | Transportation Enhancements | 03/01/2010 |  | 10/01/2010 | 477000 | 0
7749 | North Dakota | WARD |  | 00 | 4989084 | This Minot project is a mill and bituminous pavement overlay project on 16th St SW from 20th Ave SW to 4th Ave SW, to rehabilitate the pavement. | Pavement Improvement | 03/16/2010 |  | 10/16/2010 | 608011.23 | 1.36
7750 | North Dakota | WALSH |  | 00 | 5000009 | This Walsh County project is a Chip Seal Coat on CMC 5018 & 5047 - County Wide to preserve the pavement structure. | Pavement Improvement | 06/02/2009 | 07/28/2009 | 09/01/2009 | 316589.27 | 12.494
7751 | North Dakota | STARK |  | 00 | 5008033 | This NDDOT project is a Thin Lift Overlay on ND 8 - From 1.4 Miles N County Line N Through Richardton to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 10/09/2010 | 2612119.85 | 16.821
7752 | North Dakota | STARK |  | 00 | 5022085 | This Dickinson project is a Slurry Seal on Dickinson - ND 22 from 8th Street SW to Heart River Bridge to rehabilitate the pavement structure. | Pavement Improvement | 09/08/2009 | 09/08/2009 | 09/19/2009 | 119278.57 | 0.682
7753 | North Dakota | BILLINGS |  | 00 | 5085055 | This NDDOT project is a thin overlay on US 85 from Belfield north to near Gorham junction to preserve the pavement structure. | Pavement Improvement | 01/20/2010 |  | 10/16/2010 | 2990642.18 | 14.61
7754 | North Dakota | STARK |  | 00 | 5094045 | This NDDOT project is a PCC Pavement Recycle project on I 94 - From Youngmans Butte to near Eagles Nest to reconstruction the existing pavement. | Pavement Improvement | 03/24/2009 | 05/01/2009 | 10/17/2009 | 19503471.09 | 9.193
7755 | North Dakota | STARK |  | 00 | 5094055 | This NDDOT project is a I-94 landscaping enhancement near Dickinson - I-94 from Exit 59 to Exit 64. | Transportation Enhancements | 11/10/2009 | 04/22/2010 | 10/29/2010 | 272395.64 | 5.011
7756 | North Dakota | BILLINGS |  | 00 | 5094067 | This NDDOT project is a Slurry Seal on I 94 - From Fryburg To Belfield to preserve the pavement structure. | Pavement Improvement | 04/07/2009 | 08/17/2009 | 09/01/2009 | 580075.65 | 7.175
7757 | North Dakota | WARD |  | 00 | 5153056 | This Ward County project is a Chip Seal Coat on CMC 5153 - From 4 Miles East of Surrey, N & from 17 Miles South & 1 Mile west of Sawyer, N to preserve the pavement structure. | Pavement Improvement | 06/29/2009 | 07/07/2009 | 09/01/2009 | 626623 | 26.021
7758 | North Dakota | WILLIAMS |  | 00 | 5351053 | This Williams County project is a Hot Bituminous Pavement on CMC 5351 - FROM From 4 Miles South of US 2, N to rehabilitate the pavement structure. | Pavement Improvement | 06/02/2009 | 06/25/2009 | 10/01/2009 | 439452.04 | 3.968
7759 | North Dakota | STARK |  | 00 | 5983038 | This Dickinson project is a Slurry Seal on Dickinson - ND 22 Frontage Roads from 8th Street SW to Heart River Bridge to rehabilitate the pavement structure. | Pavement Improvement | 09/08/2009 | 09/08/2009 | 09/19/2009 | 76312.33 | 0.5
7760 | North Dakota | STARK |  | 00 | 5983039 | This Dickinson project is a Slurry Seal on Dickinson - 4th Avenue E from Villard to Museum Drive to rehabilitate the pavement structure. | Pavement Improvement | 09/08/2009 | 09/08/2009 | 09/19/2009 | 119986.8 | 1.1
7761 | North Dakota | STARK |  | 00 | 5983040 | This Dickinson project is a Mill & Asphalt Overlay on Dickinson - 21st Street W from 10th Avenue W to 10th Ave E to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/21/2009 | 10/16/2009 | 721357.13 | 1.447
7762 | North Dakota | NELSON |  | 00 | 6002078 | This NDDOT project is a Thin Lift Overlay on US 2 - From Michigan Bypass E To County Line? to preserve the pavement structure. | Pavement Improvement | 10/06/2009 | 04/29/2010 | 10/02/2010 | 1705937.92 | 10.189
7763 | North Dakota | PEMBINA |  | 00 | 6066016 | This NDDOT project is a Thin Lift Overlay on ND 66 - From S Jct 81-St. Thomas E TO I-29 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 | 05/27/2010 | 10/02/2010 | 1729395.06 | 11.975
7764 | North Dakota | CAVALIER |  | 00 | 6066017 | This NDDOT project is a Thin Lift Overlay on ND 66 - From District Boundary E TO N Jct 32 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 | 05/27/2010 | 10/02/2010 | 798701.9 | 8.033
7765 | North Dakota | PEMBINA |  | 00 | 6066018 | This NDDOT project is a Mill & Asphalt Overlay on ND 66 - From S JCT 32-Gardar E To Crystal to rehabilitate the pavement structure. | Pavement Improvement | 10/06/2009 | 05/27/2010 | 10/02/2010 | 1325483.57 | 8.127
7766 | North Dakota | PEMBINA |  | 00 | 6066019 | This NDDOT project is a Thin Lift Overlay on ND 66 - From Crystal E To N Jct 81 St. Thomas to preserve the pavement structure. | Pavement Improvement | 10/06/2009 | 05/27/2010 | 10/02/2010 | 1461386.28 | 10.943
7767 | North Dakota | WALSH |  | 00 | 6985042 | This Grafton project is a Mill & Asphalt Overlay on Grafton - 5th Street from McHugh Avenue to Burgamott Avenue to rehabilitate the pavement structure. | Pavement Improvement | 06/12/2009 | 06/16/2009 | 10/02/2009 | 314166.29 | 0.6
7768 | North Dakota | WALSH |  | 00 | 6985043 | This Grafton project is a Chip Seal Coat on Grafton Urban Roads - 10 Sites to preserve the pavement structure. | Pavement Improvement | 07/02/2009 | 07/08/2009 | 09/01/2009 | 209850 | 4
7769 | North Dakota | WALSH |  | 00 | 6985044 | This Grafton Project is an enhancement project to construct a bike/ped facility along ND 17 from School Road west and along Colette Ave from ND 17 south to School Road . | Transportation Enhancements | 03/17/2010 |  | 10/08/2010 | 358652.67 | 0
7770 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986087 | This Grand Forks project is a Signals and Pavement Marking on Grand Forks - Intersection of 47th Ave S and Washington Street to preserve the pavement structure. | Pavement Improvement | 06/17/2009 | 07/22/2009 | 11/01/2009 | 372275.65 | 0.06
7771 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986088 | This Grand Forks project is a Sign Replacement project on various Streets. | Other | 11/03/2009 | 04/13/2010 | 07/01/2010 | 257142.56 | 9.118
7772 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986089 | This Grand Forks project is a concrete panel replacement and mill and bituminous pavement overlay project on Cherry Street from 25th Ave S to 47th Ave S, to rehabilitate the pavement. | Pavement Improvement | 02/16/2010 |  | 09/29/2010 | 870539.8 | 1.464
7773 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986090 | This Grand Forks project is a Chip Seal Coat on Grand Forks - University Avenue from 3rd Street N to State Street to preserve the pavement structure. | Pavement Improvement | 07/15/2009 | 08/03/2009 | 09/01/2009 | 257324.19 | 2.42
7774 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986091 | This Grand Forks project is a Chip Seal Coat on Grand Forks - Mill Road from Gateway Drive N to Urban limit to preserve the pavement structure. | Pavement Improvement | 07/15/2009 | 08/03/2009 | 09/01/2009 | 57000 | 1.56
7775 | North Dakota | GRAND FORKS |  | 00 | 6986092 | This Grand Forks project is a Chip Seal Coat on Grand Forks - 20th Street N from Gateway Drive to University Avenue to preserve the pavement structure. | Pavement Improvement | 07/15/2009 | 08/03/2009 | 09/01/2009 | 37551.33 | 0.73
7776 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986093 | This Grand Forks project is a Chip Seal Coat on Grand Forks - 20th Street S from 24th Avenue S to 32nd Avenue to preserve the pavement structure. | Pavement Improvement | 07/15/2009 | 08/03/2009 | 09/01/2009 | 25319.27 | 0.48
7777 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986096 | This Grand Forks project is a Concrete Pavement Repair and Mill & Overlay on Grand Forks - 8th Avenue N from 3rd Street N to Columbia Road to rehabilitate the pavement structure. | Pavement Improvement | 07/15/2009 | 08/06/2009 | 10/01/2009 | 365000 | 1.06
7778 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986097 | This Grand Forks project is a concrete panel replacement and mill and bituminous pavement overlay project on 13th Avenue S from Cherry Street to Columbia Road, to rehabilitate the pavement. | Pavement Improvement | 02/16/2010 |  | 11/19/2010 | 415669.38 | 0.928
7779 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986099 | This Grand Forks project is a Concrete Pavement Repair on Grand Forks - 17th Avenue S from Washington Street to 42nd Ave S to rehabilitate the pavement structure. | Pavement Improvement | 07/15/2009 | 07/27/2009 | 10/01/2009 | 679879.12 | 1.96
7780 | North Dakota | GRAND FORKS | GRAND FORKS (MN) | 00 | 6986100 | This Grand Forks Project is an enhancement project to construct a bike/ped facility along south 42nd street from 11th Ave S to 17th Ave S. | Transportation Enhancements | 02/16/2010 | 05/20/2010 | 09/29/2010 | 95709 | 0
7781 | North Dakota | MCKENZIE |  | 00 | 7023027 | This NDDOT project is a Hot Bituminous Pavement on ND 23 - From Watford City East TO JCT 73 to rehabilitate the pavement structure. | Pavement Improvement | 05/05/2009 | 06/29/2009 | 10/10/2009 | 4255041.2 | 16.408
7782 | North Dakota | MCKENZIE |  | 00 | 7023029 | This NDDOT project is a Thin Lift Overlay on ND 23 - From JCT 73 N&E TO Reservation Boundary to preserve the pavement structure. | Pavement Improvement | 05/05/2009 | 06/29/2009 | 10/10/2009 | 2492984.65 | 19.291
7783 | North Dakota | WILLIAMS |  | 00 | 7804034 | This NDDOT project is a Thin Lift Overlay on ND 1804 - From Beaver Creek W TO E BN Overpass to preserve the pavement structure. | Pavement Improvement | 03/24/2009 | 06/19/2009 | 10/10/2009 | 3462202.62 | 29.029
7784 | North Dakota | WILLIAMS |  | 00 | 7993030 | This Williston project is a Mill & Asphalt Overlay, Curb Ramps, and Driveways on Williston - 22nd St from 2nd Avenue West to University Ave to rehabilitate the pavement structure. | Pavement Improvement | 06/26/2009 | 07/07/2009 | 10/02/2009 | 240000 | 0.487
7785 | North Dakota | WILLIAMS |  | 00 | 7993031 | This Williston project is a Mill & Asphalt Overlay, Curb Ramps, Sidewalks, and Driveways on Williston - 22nd St E from University Ave to 12th Ave E (E Dakota Parkway) to rehabilitate the pavement stru | Pavement Improvement | 06/26/2009 | 07/07/2009 | 10/02/2009 | 108686 | 0.33
7786 | North Dakota | WILLIAMS |  | 00 | 7993032 | This Williston project is a Mill & Asphalt Overlay, Sidewalk, Driveway, Valley Gutters, Curb Ramps on Williston - 26th St W from 6th Ave W to 16th Ave W to rehabilitate the pavement structure. | Pavement Improvement | 06/26/2009 | 07/07/2009 | 10/02/2009 | 260000 | 0.675
7787 | North Dakota | WILLIAMS |  | 00 | 7993033 | This Williston project is a Mill & Asphalt Overlay, Sidewalk, Driveway, Valley Gutters, Curb Ramps on Williston - West 2nd Avenue W Frontage Road from 6th Ave W to 42nd Street to rehabilitate the pav | Pavement Improvement | 06/26/2009 | 07/08/2009 | 10/02/2009 | 157203.52 | 0.7
7788 | North Dakota | WILLIAMS |  | 00 | 7993035 | This Williston project is a Railroad Park enhancement and landscaping project at Railroad Park - 1 South Main Street. | Transportation Enhancements | 12/23/2009 | 05/17/2010 | 11/12/2010 | 210000 | 0
7789 | North Dakota | WILLIAMS |  | 00 | 7993038 | This Williston project is a Pavement Reconstruction project on Williston - Main St from Amtrak Depot to Front St to reconstruction the existing pavement. | Pavement Improvement | 12/23/2009 | 05/17/2010 | 11/12/2010 | 250000 | 0.039
7790 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8010034 | This Fargo project is a Mill & Asphalt Overlay on Fargo - Main Avenue from 2nd Street N to 25th Street to rehabilitate the pavement structure. | Pavement Improvement | 07/29/2009 | 08/19/2009 | 10/01/2009 | 495000 | 1.54
7791 | North Dakota | SARGENT |  | 00 | 8011022 | This NDDOT project is a Thin Lift Overlay on ND 11 - From N Jct 32 To S JCT 32-Forman to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 09/19/2010 | 98553.13 | 1.314
7792 | North Dakota | RICHLAND |  | 00 | 8011023 | This NDDOT project is a thin overlay on ND 11 from Lidgerwood east to Hankinson to preserve the pavement structure. | Pavement Improvement | 01/20/2010 |  | 10/09/2010 | 1657497.6 | 12.693
7793 | North Dakota | RICHLAND |  | 00 | 8029099 | This NDDOT project is a Concrete Pavement Repair on I 29 - From ND 13 N TO Christine Interchange to rehabilitate the pavement structure. | Pavement Improvement | 03/24/2009 | 06/10/2009 | 09/26/2009 | 1315100.15 | 21.572
7794 | North Dakota | RICHLAND |  | 00 | 8029104 | This NDDOT project is a Concrete Pavement Repair on I 29 - From ND 13 N TO Christine Interchange to rehabilitate the pavement structure. | Pavement Improvement | 03/24/2009 | 06/16/2009 | 09/26/2009 | 1611906.87 | 21.57
7795 | North Dakota | SARGENT |  | 00 | 8032028 | This NDDOT project is a Thin Lift Overlay on ND 32 - From SD Line to S. Jct. ND 11 to preserve the pavement structure. | Pavement Improvement | 10/06/2009 |  | 09/19/2010 | 1205336.44 | 10.196
7796 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8984108 | This Fargo project is a concrete pavement reconstruction project on 45th St from 26th Ave S to 52nd Ave S to include grading, storm drains, sanitary sewer, lighting, and signals to reconstruct the exi | Pavement Improvement | 03/22/2010 | 03/31/2010 | 10/15/2010 | 4212312.06 | 2.47
7797 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8984113 | This Fargo project is a Structure Replacement project on Fargo - 38th St Bridge over Drain 27. | Bridge Replacement | 12/14/2009 | 02/02/2010 | 09/03/2010 | 751743.94 | 0.091
7798 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8984114 | This Fargo project is a Structure Widening project on Fargo - 45th St at Drain 27. | Bridge Improvement | 12/14/2009 | 02/15/2010 | 09/03/2010 | 317000 | 0.022
7799 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8984116 | This Fargo project is a Mill & Asphalt Overlay on Fargo - 25th Street from 32nd Avenue S to Rose Coulee to rehabilitate the pavement structure. | Pavement Improvement | 07/29/2009 | 07/29/2009 | 08/22/2009 | 362500 | 1.487
7800 | North Dakota | CASS | BISMARCK-MANDAN | 00 | 8984118 | This Fargo project is a Asphalt Overlay and Concrete Pavement Repair on Fargo - Old HWY 81 from Dakota Dr to Co. Rd 20 to rehabilitate the pavement structure. | Pavement Improvement | 07/29/2009 | 09/21/2009 | 10/01/2009 | 380000 | 1.94
7801 | North Dakota | CASS | BISMARCK-MANDAN | 00 | 8984119 | This Fargo project is a City wide pavement marking project to restore pavement markings. | Pavement Improvement | 07/20/2009 | 07/27/2009 | 10/15/2009 | 400000 | 10.075
7802 | North Dakota | RICHLAND |  | 00 | 8991021 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 6th Street S from Dakota Ave. to 11th Ave. S. to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/12/2009 | 10/02/2009 | 102000 | 0.658
7803 | North Dakota | RICHLAND |  | 00 | 8991022 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 4th Avenue S from 6th St. S to 11th St. S to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/12/2009 | 10/02/2009 | 41000 | 0.34
7804 | North Dakota | RICHLAND |  | 00 | 8991023 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 2nd Avenue N from 2nd St. N to 11th St. N to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/12/2009 | 10/02/2009 | 56000 | 0.698
7805 | North Dakota | RICHLAND |  | 00 | 8991024 | This Wahpeton project is a Pavement Patching and Seal Coat on Wahpeton - 7th Street N from 8th Ave N to 16th Ave N to preserve the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 48236.61 | 0.747
7806 | North Dakota | RICHLAND |  | 00 | 8991025 | This Wahpeton project is a Chip Seal Coat on Wahpeton - 4th Street N from 2nd Ave N to ND 210 to preserve the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 121146.63 | 1.69
7807 | North Dakota | RICHLAND |  | 00 | 8991026 | This Wahpeton project is a Mill & Asphalt Overlay on Wahpeton - 11th Street N from 16th Ave N to ND 210 to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 148473.92 | 0.487
7808 | North Dakota | RICHLAND |  | 00 | 8991027 | This Wahpeton project is a Pavement Patching and Mill & Asphalt Overlay on Wahpeton - 7th Street N from 2nd Ave N to 8th Ave N to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 119400 | 0.435
7809 | North Dakota | RICHLAND |  | 00 | 8991028 | This Wahpeton project is a Pavement Patching and Mill & Asphalt Overlay on Wahpeton - 11th Street N from Dakota to B Ave to rehabilitate the pavement structure. | Pavement Improvement | 07/20/2009 | 08/03/2009 | 10/02/2009 | 106984 | 0.794
7810 | North Dakota | CASS |  | 00 | 8992031 | This West Fargo project is a Mill & Asphalt Overlay on West Fargo, 6 locations to rehabilitate the pavement structure. | Pavement Improvement | 07/06/2009 | 07/15/2009 | 08/15/2009 | 1226294 | 5.24
7811 | North Dakota | CASS | FARGO-MOORHEAD (MN) | 00 | 8992033 | This West Fargo Project is an enhancement project to construct a bike/ped facility from Sheyenne River to 9th St West. | Transportation Enhancements | 03/29/2010 |  | 08/15/2010 | 247238.2 | 0
7812 | North Dakota | STATEWIDE |  | 00 | 9999248 | This NDDOT project is a project to update the history of the NDDOT. | Transportation Enhancements | 04/06/2010 | 04/20/2010 | 05/30/2011 | 267747 | 0
7813 | North Dakota | CAVALIER |  | 00 | A010032 | This Langdon project is an enhancement project to install entrance welcome signage at the city of Langdon. | Transportation Enhancements | 03/01/2010 |  | 08/01/2010 | 146029 | 0
7814 | North Dakota | TRAILL |  | 00 | T0UR035 | This NDDOT project is an enhancement project to rehabilitate the Viking Bridge northwest of Portland. | Transportation Enhancements | 01/20/2010 | 03/09/2010 | 10/01/2010 | 529912.15 | 0
7815 | North Dakota | GRAND FORKS |  | 00 | T0UR036 | This North Dakota Parks and Recreation project is an enhancement project to contruct a new pedestrian briridge at Turtle River State Park. | Transportation Enhancements | 03/03/2010 |  | 10/29/2010 | 329769 | 0
7816 | North Dakota | BURLEIGH |  | 00 | T0UR037 | This SHSND project is a enhancement project to Camp Hancock Locomotive at Camp Hancock in Bismarck - Main Avenue near 2nd Street. | Transportation Enhancements | 03/30/2010 |  | 07/15/2010 | 206421.39 | 0
7817 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | 0H03001 | This project is for preliminary engineering for a multi use bike and hike trail along the north bank of the Ohio River | Transportation Enhancements | 12/08/2009 | 03/15/2010 | 07/15/2011 | 1657588.75 | 6.69
7818 | Ohio | LUCAS |  | 9 | E031995 | This is a preservation project on I-75 from North Cove bridge to Cecilia. It will prevent future pavement decay on this priority route. The resurfacing project will prolong the life of I-75 between Be | Pavement Improvement | 08/25/2009 | 09/08/2009 | 11/20/2009 | 1133582.59 | 2.7
7819 | Ohio | CRAWFORD |  | 5 | E032086 | This project will resurface approximately 11.50 miles of SR 4 from the north corporation limit of the city of Bucyrus to the Seneca County line. It includes bridge work at seven locations. | Pavement Improvement | 08/20/2009 | 09/16/2009 | 07/30/2010 | 3250840 | 11.33
7820 | Ohio | SUMMIT | AKRON | 13 | E032369 | This project is to reconstruct the 15th street bridge over ABC railroad in Barberton | Bridge Replacement | 09/11/2009 | 09/11/2009 | 07/31/2011 | 268000 | 0
7821 | Ohio | LAKE | CLEVELAND, OH | 14 | E033177 | In the City of Willowick this project is to upgrade and interconnet the traffic signal system at approximately 15 locations along Lakshore Blvd, Vine St and E 305th Street to improve safety. | Safety/Traffic Management | 04/05/2010 | 05/20/2010 | 09/30/2011 | 1190290 | 0.01
7822 | Ohio | JACKSON |  | 18 | E035110 | This is a four-lane minor rehabilitation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Jackson County. The project includes re | Pavement Improvement | 08/18/2009 | 08/28/2009 | 10/31/2010 | 9260615.02 | 9.69
7823 | Ohio | CLERMONT |  | 1, 2, 3, 7, 8 | E035574 | Painting of Clinton U.S. 68 bridge over Cowan Creek; Clinton U.S. 68 over Anderson Ford; Wilmington Road bridge over I-71 in Warren; Stubbs Mills Road bridge over I-71 in Warren. | Bridge Improvement | 08/12/2009 | 08/21/2009 | 08/31/2010 | 1334490 | 0
7824 | Ohio | PREBLE |  | 8 | E035896 | Repave portions of SR 732; also resurface Eaton-Oxford Rd., CR 29, in from the Morning Sun Outpost | Pavement Improvement | 10/02/2009 | 04/22/2010 | 06/30/2010 | 2332670 | 13.54
7825 | Ohio | LICKING |  | 12, 18 | E036406 | This project includes the resurfacing of State Route 16 from mile marker 19.72 near the 21st Street bridge east to mile marker 23.66 near the Dayton Road Intersection. The project also includes the re | Pavement Improvement | 09/03/2009 | 09/08/2009 | 10/30/2010 | 6230065.56 | 6.3
7826 | Ohio | JACKSON |  | 18 | E036464 | This is a preservation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Jackson County. The project will resurface 11.45 miles (2 | Pavement Improvement | 08/19/2009 | 09/21/2009 | 10/31/2009 | 1580350 | 11.45
7827 | Ohio | CUYAHOGA | CLEVELAND, OH | 10 | E036720 | This project is to rahabilitate the West 77th Street bridge over Norfolk Southern Railroad and GCRTA located between Franklin Ave and Madison Ave in Cleveland | Bridge Replacement | 11/02/2009 | 01/06/2010 | 06/30/2011 | 1509000 | 0
7828 | Ohio | MIAMI | DAYTON | 3,8 | E040008 | Improving travel and providing better connectivity is what this project will do. 5 miles of roadway will be resurfaced from the Montgomery/Miami county line to Tipp City in Miami County. | Pavement Improvement | 06/25/2009 | 07/08/2009 | 09/30/2009 | 1800000 | 4.84
7829 | Ohio | ATHENS |  | 6, 18 | E040367 | The project is a five-mile, two-lane resurfacing project which includes two miles of SR 682 in Athens County and six miles of SR 356 in Vinton County. | Pavement Improvement | 07/01/2009 | 08/21/2009 | 08/31/2010 | 803850 | 12.52
7830 | Ohio | TUSCARAWAS |  | 18 | E040567 | Replace existing bridge constructed in 1906 over the Tuscarawas River between Front Street and Broadway in the city of Dover with a new multi-span, multi-beam bridge with sidewalks and pedestrian rail | Bridge Improvement | 08/05/2009 | 09/18/2009 | 06/30/2011 | 810944 | 0.06
7831 | Ohio | HANCOCK |  | 4 | E040571 | Pave deteriorated sections along Interstate 75 in Hancock County, starting at State Route 613 north to the Wood County line. | Pavement Improvement | 06/12/2009 | 07/06/2009 | 08/30/2009 | 1128068.62 | 2.81
7832 | Ohio | HARDIN |  | 4 | E040577 | Repave route SR37 from the Hancock County line to the Wyandot County line through the village of Forest and SR53 from the North Corporation limit of Kenton to SR37 in Hardin County due to pavement det | Pavement Improvement | 07/08/2009 | 08/27/2009 | 10/01/2009 | 291000 | 12.87
7833 | Ohio | LORAIN |  | 9 | E040597 | This project in southern Lorain County replaces 2 structures west of the Village of Wellington. The first is a 133' structure over the West Branch of the Black River, 0.57-mile west of Quarry Road and | Bridge Replacement | 12/01/2009 | 02/22/2010 | 09/01/2011 | 1000000 | 0.08
7834 | Ohio | MEDINA |  | 16 | E040717 | The project includes the complete reconstruction of 6.5 miles of Interstate 76 east of its interchange with Interstate 71 in Medina County. The project ends at the western side of the State Route 57 i | Pavement Improvement | 04/14/2010 | 04/15/2010 | 09/30/2011 | 14883240.88 | 7
7835 | Ohio | LORAIN | CLEVELAND, OH | 13 | E040910 | This project will widen the lanes of CR61 by 1' each side and add 4' paved shoulder. | Pavement Improvement | 06/16/2010 | 06/16/2010 | 11/05/2010 | 1875065 | 2.65
7836 | Ohio | MONTGOMERY |  | 3 | E050142 | This project is to create a 4 lane divided roadway at Austin Pike to Washinton Church Road in Montgomery County. This project will also construct a recreation trail on the north side of the roadway. | Pavement Widening | 04/06/2010 | 04/26/2010 | 06/30/2011 | 2000000 | 1.03
7837 | Ohio | LOGAN |  | 4 | E050427 | This project will replace beams, deck, substructure and widen the structure over Great Miami River. | Bridge Improvement | 04/14/2010 | 04/20/2010 | 11/30/2010 | 1341353.99 | 0
7838 | Ohio | MUSKINGUM |  | 18 | E050443 | To improve this major distribution link in East Central Ohio, this project will resurface approximately 3 miles of State Route 16 in Muskingum County and almost 10 miles of State Route 16 in Coshocton | Pavement Improvement | 06/26/2009 | 07/06/2009 | 11/20/2009 | 2998548.2 | 13
7839 | Ohio | MERCER |  | 4 | E050631 | This project will correct deficiencies in the bridge as part of an Ohio Department of Transportation (ODOT) initiative to ?Fix it First.? Preserving this bridge on SR 118 in Mercer County by removing | Bridge Improvement | 07/21/2009 | 08/27/2009 | 09/30/2009 | 205790 | 0
7840 | Ohio | HOCKING |  | 18 | E050633 | This project is a nine mile, two-lane resurfacing project using an asphalt overlay on SR-180 in Hocking county | Pavement Improvement | 09/03/2009 | 05/10/2010 | 07/15/2010 | 961651.6 | 9.16
7841 | Ohio | PICKAWAY |  | 7 | E051164 | This project rehabilitates nine bridges on US 23 throughout Pickaway County. Original construction of these bridges was in the 1950s. Rehabilitation includes resurfacing or replacement of the bridge d | Pavement Improvement | 07/24/2009 | 07/24/2009 | 09/30/2010 | 9816695.96 | 0.58
7842 | Ohio | STARK | CANTON | 16 | E051227 | Construct bicycle/pedestrian bridge at Deer Creek Dam spill way in Stark County | Transportation Enhancements | 08/12/2009 | 09/14/2009 | 07/29/2010 | 611485 | 0
7843 | Ohio | FRANKLIN |  | 15 | E051293 | Bridge maintenance projects on the Broad Street bridge over I-71 including backwall repair, new barrier wall, vandal fence and curb ramps. | Bridge Improvement | 09/02/2009 | 10/26/2009 | 05/31/2010 | 714080 | 0.01
7844 | Ohio | MONTGOMERY | DAYTON | 3 | E051296 | Kettering Boulevard from the Moraine North Corp Line to the Moraine South Corp Line-Reconfigure right turn drop lanes, replace existing bridge, install sidewalk, resurface the existing roadway. | Pavement Improvement | 05/13/2010 | 04/22/2010 | 11/22/2010 | 375000 | 1.87
7845 | Ohio | MONTGOMERY | DAYTON | 3 | E051298 | Reconstruction 5 lanes of MOT CR 99 from Stonequarry Road to Cresthill Drive in Vandalialanes. | Pavement Improvement | 07/21/2009 | 09/16/2009 | 07/20/2010 | 126392 | 0.45
7846 | Ohio | FRANKLIN | COLUMBUS | 12 | E060146 | In Gahanna at the IR270/SR317 (Hamilton Road) Interchange complete interchange ramp modifications by adding two lanes to the east bound exit ramd and one lane to the west bound exit ramp. Also will ex | Pavement Improvement | 04/29/2010 | 05/03/2010 | 10/31/2010 | 1985651.56 | 1.07
7847 | Ohio | SENECA |  | 5 | E060167 | Bridge replacement on State Route 67, near State Route 100, in Seneca County. This project will provide a new bridge structure. | Bridge Replacement | 06/26/2009 | 08/25/2009 | 09/30/2010 | 1575119.1 | 0.09
7848 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | E060194 | Construct a bikepath from Sutton Avenue to Four Mile Road along north side of Kellogg Avenue including a spur into Kellogg Park on the south side of Kellogg Ave. near Four Mile Road; utilizing the cro | Transportation Enhancements | 05/12/2010 | 05/03/2010 | 08/30/2010 | 463000 | 1.45
7849 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 17 | E060228 | Construction of new bridge over Mahoning River to replace current RR bridge | New Bridge Construction | 03/26/2010 | 03/26/2010 | 10/01/2010 | 703610.06 | 0
7850 | Ohio | SUMMIT |  | 13 | E060255 | This project is to construct a pedestrian trail along Ohio and Erie Canal Towpath, in downtown Akron. | Transportation Enhancements | 05/27/2010 | 06/07/2010 | 09/01/2011 | 2500000 | 0
7851 | Ohio | TUSCARAWAS |  | 18 | E060275 | This project is to construct a new interchange off I-77 at CR 80 in Dover to help relieve congestion at the existing I-77 interchanges in Dover and Strasburg. This interchange will provide improved ac | New Construction | 08/27/2009 | 09/16/2009 | 06/30/2011 | 2162071.79 | 1.74
7852 | Ohio | HURON |  | 5 | E060304 | Replacement of the North Street Bridge in the Village of Plymouth. The existing bridge is in very poor condition, has an ODOT bridge appraisal rating of 2P and a load limit of 20 tons. The project inc | Bridge Replacement | 07/09/2009 | 09/08/2009 | 10/30/2009 | 210000 | 0.02
7853 | Ohio | HANCOCK |  | 4 | E060317 | Add turn lanes on the north and west approaches of the intersection at SR 568 and Township Road 236 | Safety/Traffic Management | 08/20/2009 | 08/31/2009 | 10/31/2010 | 475500 | 0.22
7854 | Ohio | CRAWFORD |  | 5 | E060342 | This project involves the full reconstruction of State Route 4/State Route 98 (Sandusky Avenue) through Downtown Bucyrus. The 0.51 mile long project begins at Charles Avenue and concludes at the Sandu | Pavement Improvement | 08/03/2009 | 08/03/2009 | 10/27/2010 | 4691295.62 | 0.55
7855 | Ohio | HURON |  | 5 | E060344 | This is the third in a series of projects to reconstruct, widen and improve safety along the U.S. Route 224 corridor through the City of Willard. The project will replace 1400 linear feet of two lane | Pavement Improvement | 05/24/2010 | 06/05/2010 | 10/31/2010 | 1200000 | 0.45
7856 | Ohio | BELMONT |  | 6, 18 | E060378 | Resurface almost six miles of SR 147, from Belmont to SR 9 near Centerville, and over six miles of SR 149 from SR 9 at Warnock to Belmont. | Pavement Improvement | 08/10/2009 | 08/31/2009 | 05/31/2010 | 935980 | 11.98
7857 | Ohio | LAKE | CLEVELAND, OH | 14 | E060405 | This project is for reconstruction of Fairgrounds Road from SR-84 to Woodland Road in Concord and Painesville Twps. | Pavement Improvement | 03/26/2010 | 03/29/2010 | 10/29/2010 | 2730074 | 1.14
7858 | Ohio | LUCAS | TOLEDO (MI) | 9 | E060436 | This project is for the reconstruction of Secor Road in Toledo from Monroe St to Laskey Rd. It will also modify the configuration of the intersection of Secor Rd and Sylvania Ave to improve traffic | Pavement Improvement | 02/04/2010 | 03/17/2010 | 11/12/2010 | 2880000 | 1.09
7859 | Ohio | BROWN |  | 2 | E060440 | This project is to maintain and preserve the pavement by making the necessary repairs and overlaying the existing pavement with asphalt concrete on SR-32 from Clermont/Brown Co. Line to .017 miles eas | Pavement Improvement | 02/09/2010 | 03/17/2010 | 10/31/2010 | 4093535.94 | 5.8
7860 | Ohio | PERRY |  | 7 | E060540 | Modernizing a main connector for residents and businesses to the major cities of Zanesville in Muskingum County and Lancaster in Fairfield County, this project will resurface 14 miles of highly-travel | Pavement Improvement | 06/25/2009 | 08/20/2009 | 09/30/2009 | 1535913.92 | 7.5
7861 | Ohio | LICKING |  | 18 | E060550 | As part of the Ohio Department of Transportation?s ?Fix it First? initiative, this project will help correct deficiencies in the bridges at two locations on U.S. 40 in Licking and Muskingum counties. | Bridge Improvement | 09/03/2009 | 09/08/2009 | 09/15/2010 | 356130 | 0.04
7862 | Ohio | PUTNAM |  | 5 | E060605 | Repave routes SR189 and SR190 through the village of Ft. Jennings from the west corporation limits to US224 and SR694 from SR115 to the west corporation limit of the village of Glandorf in Putnam Coun | Pavement Improvement | 06/25/2009 | 09/25/2009 | 10/31/2009 | 958437.3 | 9.62
7863 | Ohio | SUMMIT |  | 13 | E060754 | This project is the resurfacing of I-77 from Ghent Road to the Richfield Village corporation line. Project also includes minor repairs (sealing and patching) to six bridges, including two over Ira Roa | Pavement Improvement | 04/14/2010 | 04/23/2010 | 11/30/2010 | 2926115.03 | 4.17
7864 | Ohio | AUGLAIZE |  | 4 | E060946 | This project is to resurface the existing roadway with asphalt concrete on SR-362 in Auglaize county from the Shelby/Auglaize county line to the Village of Minster and in Shelby county from Lake Loram | Pavement Improvement | 06/11/2009 | 07/21/2009 | 08/31/2009 | 476000 | 3.37
7865 | Ohio | CUYAHOGA | CLEVELAND, OH | 11 | E060950 | This project is to rehabilitate the Aetna Road Bridge over the CSX tracks in the City of Cleveland | Bridge Improvement | 03/29/2010 |  | 06/30/2011 | 1048230 | 1.12
7866 | Ohio | SHELBY |  | 4 | E060967 | This project is to resurface the existing roadway with asphalt concrete on SR47 from 0.59 mile East of SR66 to Kuther Road in Shelby county | Pavement Improvement | 09/02/2009 | 09/15/2009 | 10/31/2009 | 1239028.25 | 8.17
7867 | Ohio | HIGHLAND |  | 3 | E070048 | This is a preservation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Highland County. The project will resurface U.S. Route 62 | Pavement Improvement | 06/25/2009 | 09/09/2009 | 10/31/2009 | 488841.23 | 12.02
7868 | Ohio | LAWRENCE |  | 6 | E070064 | This project will replace a deficient structure situated over Dick Creek, at the 5.78-mile marker on state Route 217, just west of the route?s junction with state Route 378. This project is necessary | Bridge Replacement | 08/04/2009 | 08/17/2009 | 12/04/2009 | 349960 | 0
7869 | Ohio | SCIOTO |  | 2 | E070067 | This project will replace a deficient structure situated over Gas Hollow and located at the 1.28-mile marker on U.S. Route 52 (just east of Township Road 97 and the Adams-Scioto County line) and inclu | Bridge Replacement | 06/15/2009 | 07/13/2009 | 12/31/2009 | 726871.92 | 0
7870 | Ohio | GEAUGA |  | 14 | E070129 | Resurfacing of State Route 700 from U.S. 422 to State Route 168 in Troy and Burton Townships. | Pavement Improvement | 09/02/2009 | 04/15/2010 | 08/31/2010 | 987570 | 5.04
7871 | Ohio | MUSKINGUM |  | 18 | E070130 | This project includes the resurfacing of approximately 7 miles of State Route 60 from the Morgan County line to the south corporation limit of Duncan Falls in Muskingum County. | Pavement Improvement | 08/24/2009 | 09/08/2009 | 10/19/2009 | 1449185.43 | 8.15
7872 | Ohio | PICKAWAY |  | 7, 15 | E070267 | The Rickenbacker area, 10 miles southeast of Columbus, includes Rickenbacker International Airport, the Rickenbacker Intermodal Terminal and an industrial area. Building a new road that includes bette | New Construction | 05/17/2010 | 05/24/2010 | 12/30/2011 | 8824871.33 | 0.01
7873 | Ohio | CLERMONT |  | 2 | E070273 | Resurface portions of SR 232 in Clermont County to include just over 10 miles of roadway. | Pavement Improvement | 08/18/2009 | 10/06/2009 | 07/30/2010 | 567090 | 10.19
7874 | Ohio | BELMONT |  | 6, 18 | E070284 | Resurface over 14 miles of SR 148 from SR 145 to SR 7 at Powhatan Point in Belmont County; resurface over four miles of SR 164 in Carroll County from SR 9 at Kilgore to SR 43 at Amsterdam; and resurfa | Pavement Improvement | 08/31/2009 | 04/19/2010 | 07/31/2010 | 2850600 | 19.02
7875 | Ohio | BELMONT |  | 6 | E070294 | Replace SR 148 bridge deck just west of the junction with SR 7 near Steinersville. | Bridge Improvement | 08/27/2009 | 03/31/2010 | 08/31/2010 | 210583.55 | 0.01
7876 | Ohio | BELMONT |  | 6, 18 | E070304 | Resurface just over five miles of SR 149 from the village of Flushing in Belmont County to the village of New Athens in Harrison County, as well as resurfacing just under a mile of SR 9 in New Athens. | Pavement Improvement | 07/01/2009 | 08/13/2009 | 04/15/2010 | 809655.81 | 6.15
7877 | Ohio | LUCAS | TOLEDO (MI) | 9 | E070362 | This project will upgrade of the existing traffic control at the intersection of Coy Rd and Starr Ave, in the City of Oregon, from all-way stop to a fully actuated traffic signal. | Other | 02/17/2010 | 06/08/2010 | 10/15/2010 | 194201 | 0.04
7878 | Ohio | ASHLAND |  | 16 | E070379 | This project will rehabilitate a deficient 160-foot bridge over Claremont Avenue, 0.25-mile south of Baney Road. | Bridge Improvement | 07/17/2009 | 07/28/2009 | 09/15/2010 | 1216227.98 | 0.02
7879 | Ohio | CLERMONT |  | 2 | E070407 | This project is to replace the bridge that carries SR 276 over Kain Run in Clermont county. | Pavement Improvement | 06/15/2009 | 08/03/2009 | 10/30/2009 | 326082.73 | 0
7880 | Ohio | CLINTON |  | 3 | E070412 | In Clinton county replace Culvert on SR 124 and SR 350 | Pavement Improvement | 08/20/2009 | 08/28/2009 | 09/01/2010 | 226720 | 0.1
7881 | Ohio | BUTLER |  | 8 | E070422 | This project will resurface portions of US 27 for approximately 15 miles. | Pavement Improvement | 09/10/2009 | 09/11/2009 | 06/30/2010 | 2281937.33 | 14.94
7882 | Ohio | LUCAS |  | 9 | E070513 | This project will alleviate safety concerns by widening State Route 2 in Lucas County at the Howard Road intersection, with exclusive left and right turn lanes. Work will also provide wider medians an | Safety/Traffic Management | 05/20/2010 | 06/03/2010 | 10/22/2010 | 2227275.21 | 1.1
7883 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 6 | E070634 | Rehab existing single span steel beam bridge, originally built in 1952. Reconstruction of bridge/approach railing with decorative stone face wall. Installation of bridge lighting. Drainage improvement | Transportation Enhancements | 09/17/2009 | 08/10/2009 | 12/31/2010 | 400000 | 0.46
7884 | Ohio | GEAUGA | CLEVELAND, OH | 14 | E070642 | Resurface Washington Street from the County line to Chillicothe Rd. (SR-306) in the Village of South Russell and Bainbridge Twp | Pavement Improvement | 08/19/2009 | 08/10/2009 | 12/01/2009 | 363187.4 | 2.18
7885 | Ohio | GEAUGA | CLEVELAND, OH | 14 | E070646 | This project is to resurface Wilson Mills Road from County Line Rd. to Chillicothe Road (SR-306) in Chester Twp in Geauga county | Pavement Improvement | 08/19/2009 | 08/17/2009 | 03/01/2010 | 499885.18 | 2.75
7886 | Ohio | CHAMPAIGN |  | 4 | E070751 | This project is to resurface the existing roadway with asphalt concrete on SR-55 in Champaign county from the junction of SR-560 to the Urbana west county line. | Pavement Improvement | 06/25/2009 | 08/31/2009 | 09/30/2009 | 424299.72 | 3.43
7887 | Ohio | MEDINA | CLEVELAND, OH | 16 | E070779 | In Medina county on CR 97 (Greenwich Road) - from SR 3 to SR 57 resurface existing pavement and add paved shoulders to provide a new pavement surface and preserve the pavement structure | Pavement Improvement | 05/25/2010 | 05/25/2010 | 10/09/2010 | 2240921.33 | 5.55
7888 | Ohio | MEDINA | CLEVELAND, OH | 16 | E070780 | In Medina county on Marks Road (CR 22) - from Fenn Road (CR 70) to Hamilton Road (CR 76) resurface existing pavement and add paved shoulders to provide a new pavement surface and preserve the pavemen | Pavement Improvement | 08/07/2009 | 09/21/2009 | 10/16/2009 | 606369.06 | 1.84
7889 | Ohio | DARKE |  | 8 | E070781 | The project will resurface 4.5 miles of SR 571 near the Darke/Miami County Line, specifically between the City Greenville and the Village of West Milton. This route is heavily traveled by truck traffi | Pavement Improvement | 06/16/2009 | 08/17/2009 | 09/30/2009 | 510000 | 4.15
7890 | Ohio | MEDINA | CLEVELAND, OH | 16 | E070785 | This project is to resurface CR 19 (Lake Road) - from CR 50 (Chippewa Road) to SR 162 (Wedgewood Road) which will include adding paved shoulders to provide a new pavement surface and preserve the pave | Pavement Improvement | 08/07/2009 | 09/21/2009 | 10/16/2009 | 366647.49 | 1.54
7891 | Ohio | LOGAN |  | 4 | E070856 | The project will replace the bridge on SR 274 over the Great Miami River, which is two miles west of SR 235. The original structure was built in 1954 and is being replaced because of its age as well a | Bridge Replacement | 06/26/2009 | 07/20/2009 | 10/30/2009 | 856200 | 0
7892 | Ohio | CHAMPAIGN |  | 4 | E070928 | This project will resurface the existing roadway on State Route 29 between State Route 560 and State Route 296 as well as the roadway on State Route 187 between the Madison / Champaign County Line and | Pavement Improvement | 03/19/2010 | 05/03/2010 | 08/31/2010 | 598631.51 | 8.39
7893 | Ohio | DARKE |  | 8 | E070933 | This project is to resurface SR503 from the Preble/Darke county line to SR121 | Pavement Improvement | 08/04/2009 | 09/15/2009 | 10/31/2009 | 1055290 | 9.29
7894 | Ohio | GUERNSEY |  | 6, 18 | E070951 | Interstate 77 is a major North-South economic corridor for eastern Ohio. This project will upgrade and rehabilitate approximately 2.5 miles of I-77 through Guernsey County. | Pavement Improvement | 06/26/2009 | 07/01/2009 | 10/15/2009 | 1604000 | 2.51
7895 | Ohio | FAIRFIELD |  | 7 | E070952 | In Fairfield county resurface SR 204 from SR 256 to SR 158 and SR 204A from IR 70 to SR 204 | Pavement Improvement | 03/17/2010 | 05/04/2010 | 10/15/2010 | 1719897.05 | 11.65
7896 | Ohio | PERRY |  | 7 | E070959 | This project calls for the replacement of a deficient bridge deck located over Penn Central railroad on SR 93. This project is necessary for the safety of the traveling public, as well as to preserve | Bridge Improvement | 06/25/2009 | 07/06/2009 | 06/30/2010 | 1188410 | 0.02
7897 | Ohio | MAHONING |  | 17 | E071098 | Resurfacing SR 7 from Midlothian Blvd. to Indianola Ave; nearly one-half mile of U.S. 62 from Williamson Ave. to Hadnett Drive, and three-quarter miles of SR 625 from Midlothian Blvd. to U.S. 62. | Pavement Improvement | 08/04/2009 | 08/14/2009 | 10/15/2009 | 879598.91 | 1.98
7898 | Ohio | STARK | CANTON | 16 | E071109 | This is a safety project to reconstruct and rehabilitate sections of SR153 in Louisville including new curbs, gutters, sidewaly pavement widening west of California and Signals at California | Other | 06/16/2009 | 06/16/2009 | 09/30/2012 | 330000 | 1.09
7899 | Ohio | SUMMIT |  | 14 | E071111 | The project is for the slope repair and reconstruction on I-271 at two locations between the Ohio Turnpike and Brandywine Road. | Pavement Improvement | 06/24/2009 | 07/20/2009 | 12/01/2009 | 754120.55 | 0.02
7900 | Ohio | BUTLER | CINCINNATI (KY) | 8 | E080046 | This project is to construct Superstreet intersection at Hamilton Mason Road and SR 4B with associated widening on SR 4B, including tapers. | Pavement Improvement | 05/10/2010 | 05/10/2010 | 10/28/2011 | 577562.84 | 0.62
7901 | Ohio | MAHONING |  | 6 | E080099 | Bridge deck replacement and painting of the SR 11 twin bridges over Indian Run between U.S. 224 and Western Reserve Road. | Bridge Improvement | 08/04/2009 | 08/14/2009 | 10/15/2010 | 1897104.09 | 0
7902 | Ohio | MEDINA |  | 16 | E080129 | The project will replace a deficient 68-foot, three-span bridge on State Route 301, over Rudd Creek, north of the Village of Spencer. | Bridge Replacement | 06/09/2009 | 03/31/2010 | 10/29/2010 | 391432.6 | 0.04
7903 | Ohio | LORAIN |  | 13 | E080130 | This project involves the replacement of a deficient 38-foot bridge structure over the Carpenter Ditch, 0.17 mile north of Jason Road. | Bridge Replacement | 06/11/2009 | 06/18/2009 | 10/29/2010 | 427996.38 | 0.01
7904 | Ohio | STARK |  | 16 | E080160 | This project will resurface US Route 62 from SR 44 to State Street. Project also includes minor bridge work (patching and sealing) to six structures, two over Beech Creek, one over the Nimishillen Cre | Pavement Improvement | 05/20/2010 | 05/26/2010 | 10/15/2010 | 3416393.19 | 5.37
7905 | Ohio | LORAIN | CLEVELAND, OH | 9 | E080278 | In Loraine county, resurface CR 57 (Russia Road) from SR 58 to CR 231 (Oberlin Elyria Road) | Pavement Improvement | 10/08/2009 | 01/07/2010 | 10/29/2010 | 1584000 | 4.91
7906 | Ohio | MONTGOMERY | DAYTON | 3 | E080481 | This project is to rebuild Fifteen Signalized Intersections Throughout The City, Including Poles, Vehicle Signals, Pedestrian Signals And Cable. | Safety/Traffic Management | 06/17/2010 | 06/17/2010 | 12/01/2011 | 379921 | 0.12
7907 | Ohio | NOBLE |  | 6 | E080504 | This is a two-Lane resurfacing project using an asphalt overlay treatment on SR145 in Washington and Noble counties. Work includes raised pavement markers, pavement marking and berm conditioning. | Pavement Improvement | 03/03/2010 |  | 11/10/2010 | 3161690 | 24.77
7908 | Ohio | MIAMI | DAYTON | 8 | E080519 | Great Miami River Bikeway from Old Springfield Road north to Kyle Park in Tipp City-Construct a missing link on the River Corridor Bikeway. | Transportation Enhancements | 06/15/2010 | 06/15/2010 | 04/30/2011 | 263276 | 0
7909 | Ohio | STARK |  | 16 | E080527 | Resurfacing of ten miles of U.S. Route 30 East Canton and Minerva. Extensive pavement repairs and guardrail replacement are included. There is also some minor work being done to the bridges in this se | Pavement Improvement | 04/14/2010 | 04/21/2010 | 10/31/2010 | 2857379 | 10.41
7910 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E080541 | Realignment of four sets of railroad tracks to the south of the present location along US 50 in Cincinnati, Ohio. Track realignment is necessary to permit maintenance of traffic for the future roadwa | Pavement Improvement | 12/01/2009 | 01/05/2010 | 06/30/2011 | 1075000 | 0.1
7911 | Ohio | SHELBY |  | 4 | E080582 | This project is to replace a heavily deteriorated 9'x5' concrete culvert. The project is located 0.87 miles east of the Darke/Shelby county line. This section of SR 47 runs between the Village of Vers | Pavement Improvement | 06/05/2009 | 07/21/2009 | 08/31/2009 | 133217.78 | 0.01
7912 | Ohio | COLUMBIANA |  | 6 | E080586 | Resurface nearly five miles of SR 45, from McCracken Rd. south of Salem to U.S. 62 in Salem, and resurface just over 12 miles of SR 558 from SR 45 at Teegarden to SR 517 at East Fairfield, and from SR | Pavement Improvement | 09/02/2009 | 04/07/2010 | 07/31/2010 | 1099055 | 17.11
7913 | Ohio | CARROLL |  | 18 | E080587 | This project includes the resurfacing of approximately five miles of SR 39 in Carroll County and almost eight miles of SR 39 and SR 44 in Columbiana County. | Pavement Improvement | 07/01/2009 | 07/20/2009 | 04/15/2010 | 1486660 | 13.07
7914 | Ohio | CARROLL |  | 18 | E080588 | Almost three miles of SR 183 will be resurfaced, including just over a mile in Carroll County, from the Tuscarawas County line to the Stark County line at Magnolia, and about a mile and a half in Tusc | Pavement Improvement | 08/04/2009 | 09/12/2009 | 06/30/2010 | 361029.35 | 2.85
7915 | Ohio | LORAIN |  | 9, 13 | E080613 | The project includes the reconstruction and resurfacing of 1.2 miles of East River Street in the City of Elyria. This includes the replacement of concrete curb & gutter, upgrading existing sidewalk, r | Pavement Improvement | 03/15/2010 | 03/26/2010 | 10/29/2010 | 1457759 | 1.16
7916 | Ohio | COLUMBIANA |  | 6 | E080657 | Replace existing box beam bridge on SR 154, located approximately one mile east of SR 7 at Rogers, with a steel beam superstructure. | Bridge Improvement | 08/25/2009 | 02/22/2010 | 08/30/2010 | 559650 | 0.5
7917 | Ohio | LORAIN | CLEVELAND, OH | 13 | E080683 | This project is to upgrade State Route 611 to three lanes in Loraine County to provide adquate capacity. | Pavement Improvement | 03/26/2010 | 03/16/2010 | 11/19/2010 | 4540176 | 2.81
7918 | Ohio | WAYNE |  | 16 | E080696 | This project will rehabilitate a 282' bridge on State Route 539 over Interstate 71 in northwestern Wayne County. The project is between Ruff Road and Palmer Road. The SR-539/I-71 interchange is south | Bridge Replacement | 09/09/2009 | 04/16/2010 | 10/15/2010 | 1325730.17 | 0.01
7919 | Ohio | ERIE |  | 9 | E080699 | This project will replace twin 10-foot arch bridges on SR-61 over Old Woman?s Creek, 0.15-mile east of the south juncture with State Route 113. | Pavement Improvement | 06/12/2009 | 07/24/2009 | 10/15/2009 | 314234.94 | 0.02
7920 | Ohio | HARRISON |  | 18 | E080712 | Fifteen miles of asphalt resurfacing and base repairs on SR 9 as well as six miles of asphalt resurfacing and chip sealing on SR 799 in Harrison County. | Pavement Improvement | 07/17/2009 | 07/20/2009 | 08/31/2010 | 2706796 | 21.07
7921 | Ohio | GREENE |  | 3, 7 | E080736 | This project is to resurface U.S. 35 from the Montgomery/Greene county line to the US 35/I-675 interchange | Bridge Improvement | 08/28/2009 | 09/29/2009 | 07/31/2010 | 6000790 | 1.09
7922 | Ohio | DARKE |  | 8 | E080747 | The project will reconstruct and lower USR 36 just west of Arcanum-Bears Mill Road to improve visibility and intersection safety. Due to the high accident rate at this intersection, the road grade wil | Safety/Traffic Management | 06/12/2009 | 07/07/2009 | 07/21/2009 | 105981.5 | 0.09
7923 | Ohio | CUYAHOGA |  | 14 | E080755 | The project is a minor rehabilitation of Interstate 271, from Wilson Mills Road to Interstate 90 in Cuyahoga County and Lake County. The work includes replacement of overhead signs. | Pavement Improvement | 07/20/2009 | 07/20/2009 | 10/15/2010 | 9355450 | 4.31
7924 | Ohio | LUCAS |  | 9 | E080757 | This safety related resurfacing project on SR 2 will provide motorists with safer access to Interstate 475 from the Spring Meadows shopping corridor. The safety project includes updated pavement marki | Safety/Traffic Management | 08/12/2009 | 09/09/2009 | 12/15/2009 | 137437.18 | 0.43
7925 | Ohio | ASHTABULA |  | 14 | E080763 | Resurfacing 7.88 miles of U.S. 20 from SR 11 to the Norfolk and Southern Railroad. | Pavement Improvement | 06/26/2009 | 07/14/2009 | 10/31/2009 | 2680540 | 7.88
7926 | Ohio | MEIGS |  | 6 | E080790 | The project focuses on pavement surfacing of a 7-mile portion of SR 7 through Meigs County. The two-lane micro-surfacing will improve pavement deficiencies and pavement conditions, thereby enhancing t | Pavement Improvement | 06/25/2009 | 07/02/2009 | 08/31/2009 | 1289972.42 | 7.29
7927 | Ohio | WASHINGTON |  | 6 | E080793 | Six miles of SR 60 in Washington County is being resurfaced. The work includes resurfacing on both lanes of the project. | Pavement Improvement | 08/20/2009 | 09/03/2009 | 10/31/2009 | 1202410 | 6.09
7928 | Ohio | WYANDOT |  | 5 | E080796 | Grind and pave deteriorated pavement on US23 from County Road 62 to the CSX railroad in Wyandot county | Pavement Improvement | 06/25/2009 | 07/06/2009 | 10/10/2009 | 500000 | 3.48
7929 | Ohio | MONROE |  | 6 | E080827 | An eight-mile stretch of SR 379 in Monroe County will be resurfaced. The project includes resurfacing work on both lanes of the roadway. | Pavement Improvement | 08/12/2009 | 10/07/2009 | 06/30/2010 | 232940 | 8.07
7930 | Ohio | STARK | CANTON | 16 | E080895 | Resurfacing I-77 from the US 30 interchange to the SR 800/Cleveland Avenue interchange. Resurfacing of various ramps at both the US 30 and the SR 800/Cleveland Ave. interchanges. The project also incl | Pavement Improvement | 06/15/2009 | 06/15/2009 | 07/01/2010 | 2939729 | 1.05
7931 | Ohio | WOOD |  | 5 | E081010 | This project is a 2-Lane resurfacing project with pavement repairs on SR-582 from the Village of Luckey west corp line to US-23 | Pavement Improvement | 03/09/2010 | 04/16/2010 | 08/06/2010 | 984254.55 | 4.34
7932 | Ohio | SANDUSKY |  | 5 | E081011 | This project is on SR-600 from Wood County Line to US-20 and SR-300 in Gibsonburg. A 2-Lane resurfacing project with pavement repairs of SR-600 from Wood County Line to US-20 in Sandusky County and SR | Pavement Improvement | 04/06/2010 | 06/01/2010 | 08/30/2010 | 3298923.4 | 10.82
7933 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E081028 | Minor rehabilitation/resurfacing with two deck overlays from Gypsy Ln in Niles to Girard city limits. | Pavement Improvement | 06/08/2010 |  | 10/31/2010 | 250000 | 2.95
7934 | Ohio | CHAMPAIGN |  | 4 | E081032 | In Champaign county, replace 23 foot bridge over Jumping Run with minimal approach work. | Bridge Replacement | 09/02/2009 | 09/28/2009 | 10/31/2009 | 314212 | 0
7935 | Ohio | BUTLER | CINCINNATI (KY) | 8 | E081064 | State Route 4 was built in the late 1960s as a 2 lane highway, but tremendous business growth in the area has led to congestion and has limited future economic potential. This latest phase of the bypa | Pavement Widening | 05/07/2010 | 05/10/2010 | 04/13/2012 | 6291933 | 1.6
7936 | Ohio | HAMILTON |  | 1 | E081077 | Improve the pavement condition of Interstate 75 from south of SR 126 to south of the Lockland corporation. Project includes several minor bridge rehabilitations. | Pavement Improvement | 08/04/2009 | 08/11/2009 | 08/01/2010 | 6100000 | 2.49
7937 | Ohio | BELMONT |  | 6, 18 | E081127 | Chip seal will be used as a preventive maintenance treatment to extend the pavement life on almost seven miles of SR 379 in Belmont County, between the Monroe and Noble county lines. Additionally, it | Pavement Improvement | 08/18/2009 |  | 08/30/2010 | 123100 | 9.4
7938 | Ohio | CARROLL |  | 6, 18 | E081129 | Chip seal will be used as a preventive maintenance treatment to extend the pavement life on about 18 miles of two-lane roadways in Carroll and Columbiana counties. Six miles of SR 9 in Carroll County | Pavement Improvement | 07/08/2009 | 08/10/2009 | 05/31/2010 | 674860 | 17.6
7939 | Ohio | SUMMIT | AKRON | 17 | E081175 | In Summit county on Waterloo Road, From US224 to Portage Line Road this project is to improve the road by making pavement repairs and resurfacing the full width of the roadway , applying pavement mark | Pavement Improvement | 05/10/2010 | 05/10/2010 | 05/31/2011 | 663695 | 1.67
7940 | Ohio | CLINTON |  | 3, 7 | E090047 | Resurface State Route 380 from Greene County to Highland County | Pavement Improvement | 09/17/2009 | 04/05/2010 | 07/01/2010 | 1895250 | 9.71
7941 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090071 | This project is to resurface Michigan St. (SR-25D) from Lafayette St. to Madison Ave in Toledo | Pavement Improvement | 02/02/2010 | 03/22/2010 | 11/19/2010 | 1024570.45 | 0.44
7942 | Ohio | STARK |  | 16, 18 | E090118 | Resurfacing of SR 800 from the Tuscarawas County line to south of Faircrest Street in Canton and Pike Townships and in the Village of East Sparta. | Pavement Improvement | 07/01/2009 | 07/20/2009 | 12/01/2009 | 1256052.25 | 7.03
7943 | Ohio | CLINTON |  | 3 | E090187 | Resurface State Route 72 from Highland County to Greene County to improve pavement condition. | Pavement Improvement | 06/15/2009 | 07/08/2009 | 10/30/2009 | 2955680.41 | 14
7944 | Ohio | MONROE |  | 6 | E090192 | The project is a seven-mile, two-lane resurfacing project of SR 7 in Monroe County, including four miles of SR 7 in Washington County. | Pavement Improvement | 09/02/2009 | 09/30/2009 | 07/15/2010 | 2439830 | 12.46
7945 | Ohio | MORGAN |  | 18 | E090196 | Ten miles of SR 376 in Morgan County are being resurfaced. The project includes resurfacing work on both lanes of the highway. | Pavement Improvement | 07/23/2009 | 08/12/2009 | 06/30/2010 | 1313282.43 | 9.73
7946 | Ohio | MEIGS |  | 6 | E090248 | This project begins 0.05 mi. N of 6th Street and SR 124 intersection. It includes upgrades to Starmill Park in Racine. Work includes parking lot resurfacing, walking track lighting, park entrance upg | Transportation Enhancements | 05/17/2010 | 06/09/2010 | 10/15/2010 | 800000 | 0
7947 | Ohio | MERCER |  | 5 | E090250 | This project includes pavement planing, shoulder stabilization, and resurfacing the existing roadway on SR29 and SR707 with Asphalt Concrete. | Pavement Improvement | 02/24/2010 | 04/21/2010 | 07/15/2010 | 1610789.56 | 17.32
7948 | Ohio | ALLEN |  | 4 | E090292 | Repair and replace sections of deteriorated safety median wall barrier on both Interstate 75 in Allen County and U.S. Route 68 in Hancock County. Excessive deterioration of the existing concrete walls | Safety/Traffic Management | 07/01/2009 | 07/27/2009 | 10/01/2009 | 875273.76 | 4.65
7949 | Ohio | GEAUGA | CLEVELAND, OH | 14 | E090309 | This project is resurface Wilson Mills Road from Chillicothe Road (SR-306) to Heath Rd. in Chester Township | Pavement Improvement | 08/19/2009 | 08/17/2009 | 12/01/2009 | 405387.99 | 2.2
7950 | Ohio | CLINTON |  | 3 | E090320 | The project will repair two of Wilmington?s most traveled streets, Main and Locust street as well as install curbs and gutter. In addition to the semi-truck traffic that travels these two streets, the | Pavement Improvement | 03/11/2010 | 03/25/2010 | 10/15/2010 | 3222400 | 3.42
7951 | Ohio | STARK |  | 16 | E090325 | This project is to resurface U.S. Route 62 from Sugar Creek to Navarre. | Pavement Improvement | 06/16/2009 | 07/20/2009 | 05/11/2010 | 1946899.26 | 5.26
7952 | Ohio | AUGLAIZE |  | 4 | E090342 | This project involves pavement planing and resurfacing the existing roadway of SR 67 with Asphalt Concrete. | Pavement Improvement | 02/18/2010 | 04/19/2010 | 08/31/2010 | 1429551.87 | 10.69
7953 | Ohio | MONTGOMERY |  | 8,3 | E090343 | This project will resurface the existing roadway with asphalt concrete on US-40 from the Preble / Montgomery county line to the west corporation limit of Clayton. | Pavement Improvement | 03/16/2010 | 06/08/2010 | 09/30/2010 | 900000 | 6.22
7954 | Ohio | LUCAS |  | 9 | E090357 | This project will provide various ?finishing touches? on the Veterans? Glass City Skyway. The project will provide funding for the installation of permanent inspection platforms. Work will also includ | Bridge Improvement | 04/05/2010 | 04/26/2010 | 10/29/2010 | 1549690 | 2
7955 | Ohio | MAHONING |  | 17 | E090373 | Resurfacing four miles of I-680 from SR 11 to Steel Street. Project also includes minor bridge work. | Pavement Improvement | 07/27/2009 | 07/27/2009 | 09/30/2010 | 4506180 | 4.06
7956 | Ohio | GREENE |  | 7 | E090375 | This project will resurface I-675 from SR 235 to the Clark County line and resurface SR 444 at I-675 interchange | Bridge Improvement | 09/17/2009 | 09/21/2009 | 09/01/2010 | 5003060 | 3.24
7957 | Ohio | VAN WERT |  | 5 | E090387 | Repave route SR49 in Van Wert and Paulding County from US30 to the south corporation limit of Payne due to pavement deterioration | Pavement Improvement | 06/12/2009 | 09/08/2009 | 11/04/2009 | 675236.63 | 8.26
7958 | Ohio | CLARK |  | 7 | E090400 | Improving the roadways and making sure the access points are ADA compliant is what this project will do for the city of Springfield. Five roadways in all will be resurfaced and new new ADA curb ramps | Pavement Improvement | 04/13/2010 | 04/01/2010 | 08/06/2010 | 952040.15 | 3.18
7959 | Ohio | CLARK |  | 7 | E090401 | This is Clark County?s longest bridge and is in need of repair. The project will rehabilitate the structure and paint the Dayton Road bridge over the Norfolk Southern railroad near the Greene County L | Bridge Improvement | 03/10/2010 | 03/10/2010 | 08/20/2010 | 384877 | 0
7960 | Ohio | MEDINA |  | 16 | E090427 | This project will replace a deficient 12-foot structure over small creek in Medina County on SR 421, .25 miles west of SR 85. | Pavement Improvement | 08/24/2009 |  | 10/15/2010 | 668947.93 | 0.04
7961 | Ohio | SUMMIT |  | 13 | E090439 | This project is to rehabilitate the State Street bridge in downtown Akron. | Other | 09/17/2009 | 09/17/2009 | 07/31/2014 | 500000 | 0.01
7962 | Ohio | ADAMS |  | 2 | E090442 | This is a four-lane preventive maintenance (preservation) project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Adams County. The proj | Pavement Improvement | 09/02/2009 | 04/20/2010 | 08/31/2010 | 3631913.33 | 13.7
7963 | Ohio | GREENE | DAYTON | 7 | E090485 | Resurface South Maple Avenue from Doris Drive to Dayton Yellow Springs Road-Asphalt. | Pavement Improvement | 09/10/2009 | 09/25/2009 | 10/31/2009 | 272935.36 | 1.2
7964 | Ohio | TRUMBULL |  | 17 | E090491 | This is a safety project to install pedestrian lighting along Mahoning Ave between High Street and Summit Street. | Safety/Traffic Management | 03/03/2010 | 03/15/2010 | 08/31/2010 | 214646.65 | 0.52
7965 | Ohio | WARREN |  | 3 | E090503 | Resurface Clearcreek-Franklin Road from approximately 160 feet south of Whispering Pines to Pennyroyal Road. | Pavement Improvement | 01/07/2010 | 04/23/2010 | 08/01/2010 | 185900 | 0.76
7966 | Ohio | GREENE |  | 7 | E090504 | Resurface Dayton-Yellow Springs Road from Kauffman Avenue to Ironwood Drive to improve pavement condition | Pavement Improvement | 10/23/2009 | 10/07/2009 | 05/28/2010 | 227824 | 0.64
7967 | Ohio | CLINTON |  | 3 | E090505 | This paving project would improve U.S. 68 through the city of Wilmington, another of the city?s most heavily used streets by car and truck traffic. The project would replace the curb, gutter and pavem | Pavement Improvement | 04/21/2010 | 05/11/2010 | 10/15/2010 | 880119 | 0.96
7968 | Ohio | HAMILTON |  | 1, 2 | E090506 | This project constructs Phase 2 of the Banks Intermodal Facility and the surrounding street network. The Banks Intermodal Facility, in conjunciton with the Riverfront Transit Center, will serve as Ci | New Construction | 06/10/2010 | 06/10/2010 | 09/30/2011 | 8000000 | 0.33
7969 | Ohio | HAMILTON | CINCINNATI (KY) | 1, 2 | E090507 | Project will design and construct Freedom Way between Rosa Parks and Race Street, Mehring Way between Main Street and Elm Street, and relocate and construct components of a new utility distribution li | New Construction | 03/29/2010 | 03/15/2010 | 08/12/2011 | 6500000 | 0.32
7970 | Ohio | MORGAN |  | 18 | E090508 | The majority of bridges in Morgan County accommodate mostly truck, car and school bus traffic. All but one bridge in Morgan County spans a river or waterway. Some of the bridges are as old as 1914 and | Bridge Improvement | 07/01/2009 | 07/27/2009 | 09/21/2009 | 94366.38 | 0
7971 | Ohio | MORGAN |  | 18 | E090509 | Safety studies have indicated that guardrail is needed along 11,000 feet of roadway that parallels the Muskingum River. Slopes in these areas are very steep and guardrail would protect vehicles from g | Safety/Traffic Management | 09/18/2009 | 10/19/2009 | 11/15/2009 | 128620 | 10.95
7972 | Ohio | WASHINGTON |  | 6 | E090511 | Resurfacing over seven miles of Marietta city streets, reconstructing 100 ADA curb ramps along city streets, and limited drainage improvements. Includes various sections on Acme, Colegate, Front, Gilm | Pavement Improvement | 08/20/2009 | 09/03/2009 | 07/31/2011 | 1174593.52 | 9
7973 | Ohio | GALLIA |  | 6 | E090512 | The project will focus on the resurfacing of 5.25 miles of Gallia County roads, thereby reducing maintenance needs and providing structural strength for all local travelers. The roads are as follows: | Pavement Improvement | 07/06/2009 | 09/03/2009 | 06/30/2010 | 352552.41 | 5.01
7974 | Ohio | VINTON |  | 18 | E090513 | This project will focus on resurfacing over ten miles of Vinton County roads, reducing maintenance needs and providing structural strength for all local travelers. | Pavement Improvement | 06/24/2009 | 04/22/2010 | 06/30/2010 | 426720 | 4.44
7975 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 17 | E090515 | Resurfacing from Walnut St to the Crab Creek Bridge. | Pavement Improvement | 03/26/2010 | 04/14/2010 | 09/30/2010 | 441152.99 | 0.42
7976 | Ohio | ALLEN |  | 4 | E090516 | This railroad grade separation underpass project in the city of Lima?s south side is located on Vine St. between Main St. and Central Ave. The project is being constructed in conjunction with IGCC (Li | New Bridge Construction | 05/18/2009 | 05/10/2010 | 03/03/2012 | 12665306.94 | 0
7977 | Ohio | MONTGOMERY |  | 3, 8 | E090517 | The KROC Center is a $66 million community center under construction in the Keowee/Webster Street area of Dayton. The $66 million is also being invested to renovate a very large historic home once cov | Pavement Improvement | 10/06/2009 | 09/08/2009 | 11/30/2009 | 349497.57 | 0.83
7978 | Ohio | MONTGOMERY |  | 3 | E090518 | As the largest city in Montgomery County, Dayton has more than 150,000 residents. This project will improve the safety of five major thoroughfares that are deteriorating and will continue to unless im | Pavement Improvement | 10/22/2009 | 10/09/2009 | 04/30/2010 | 1414900.9 | 5.61
7979 | Ohio | MONTGOMERY |  | 3 | E090519 | This project will restore and preserve a major thoroughfare for residents and businesses using the heavily traveled James H. McGee Boulevard. Construction work will resurface the boulevard and make re | Pavement Improvement | 04/26/2010 | 03/29/2010 | 08/27/2010 | 1129110.32 | 0.31
7980 | Ohio | MONTGOMERY | DAYTON | 3 | E090520 | In the Central Business District in Dayton-Add gateway features, resurface, curb and sidewalk repair, add tree lawn on several main corridors. | Pavement Improvement | 06/09/2010 | 05/17/2010 | 11/01/2010 | 3242487.6 | 2.19
7981 | Ohio | STARK | CANTON | 16 | E090523 | New Box Beam Superstructure replacement over the Tuscarawas River | Bridge Replacement | 03/03/2010 | 03/01/2010 | 08/31/2010 | 747654.5 | 0.01
7982 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E090524 | This is to resurface Tod Ave. from south corp. limits to West Market St in Warren | Pavement Improvement | 05/17/2010 | 06/04/2010 | 08/02/2010 | 418387.46 | 1
7983 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E090525 | This project is to resurface Hallock Young Road from SR 45 east to Austintown Warren Rd in Trumbull county. | Pavement Improvement | 03/22/2010 | 03/22/2010 | 07/30/2010 | 611100 | 0.66
7984 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 6 | E090526 | Resurfacing from Presidential Drive to Mathews Rd in Mahoning County | Pavement Improvement | 11/12/2009 | 09/14/2009 | 09/30/2010 | 986008.52 | 1.45
7985 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 17 | E090527 | Resurfacing from SR 616 west to city corp. limits. Also includes Handicap ramps installed with associated sidewalk and curbing, catch basin inlet adjustments. | Pavement Improvement | 03/08/2010 | 03/08/2010 | 09/30/2010 | 316926 | 0.89
7986 | Ohio | MUSKINGUM |  | 18 | E090528 | The EastPointe Industrial Park on State Route 93 in Muskingum County is a 1200 acre business park home to several major distribution centers. This project will construct a left turn lane to accommodat | Pavement Widening | 04/01/2010 | 04/01/2010 | 09/30/2010 | 1032471 | 0.7
7987 | Ohio | MUSKINGUM |  | 18 | E090529 | Zanesville is the county seat for Muskingum County, and this project will improve four major thoroughfares in Zanesville. The streets are Dryden, Pershing, Dresden and Ridge. The project will also imp | Pavement Improvement | 03/08/2010 | 05/24/2010 | 08/31/2010 | 865660.85 | 3.84
7988 | Ohio | LICKING |  | 18 | E090530 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. Bayer and the City of Newark requested Federal Stimulus funds for the replacement of a crossing surface on a | Safety/Traffic Management | 09/01/2009 | 09/25/2009 | 07/31/2010 | 100000 | 0.1
7989 | Ohio | MORROW |  | 4 | E090531 | The project will replace the traffic signal at US Route 42 and State Route 529 in Cardington in Morrow County. The traffic signal is old and outdated. | Safety/Traffic Management | 01/04/2010 | 03/22/2010 | 06/04/2010 | 85000 | 0.02
7990 | Ohio | MARION |  | 4 | E090532 | Marion County is in a unique position in that its industrial base is on the west side of the county, yet the major route for moving commerce is located on the east side of Marion. The Northwest Indust | New Construction | 01/04/2010 | 12/14/2009 | 12/31/2010 | 5100000 | 0
7991 | Ohio | MADISON |  | 15 | E090533 | Xenia Road is also County Road 12 in the southern part of Madison County between the Clark County line and State Route 56 near London. This project will replace the bridge that is currently deficient. | Bridge Replacement | 03/30/2010 | 03/30/2010 | 09/01/2010 | 393680 | 0.1
7992 | Ohio | FRANKLIN |  | 15 | E090534 | This project is to rehabilitate Camp Chase Railroad's railroad bridge over West Broad Street (US40) in Franklin Co. This work will encompass concrete patching, replacement, painting, vegetation contr | Other | 03/31/2010 |  | 10/01/2010 | 300000 | 0
7993 | Ohio | FRANKLIN |  | 15 | E090535 | As part of the City of Columbus Capital Improvement plan, the project will convert several one-way downtown streets to accommodate both directions of traffic in an effort to be more user friendlier fo | Pavement Widening | 04/19/2010 | 04/20/2010 | 10/07/2011 | 5500000 | 0.77
7994 | Ohio | FRANKLIN |  | 15 | E090536 | Parsons Avenue and Livingston Avenue surround the campus of Nationwide Children?s Hospital in Columbus. This project widens Livingston Avenue between Ohio Avenue and Ninth Street and Parsons Avenue be | Pavement Widening | 06/01/2010 | 06/01/2010 | 09/30/2011 | 15804875.51 | 1.08
7995 | Ohio | DELAWARE | COLUMBUS | 12 | E090537 | The project connects a recently constructed commercial shopping area with the US 36 corridor and provides the surrounding properties with improvements and necessary access for additional development o | New Construction | 04/21/2010 | 05/07/2010 | 12/31/2010 | 3465177 | 0.35
7996 | Ohio | BELMONT |  | 18 | E090540 | Install pavement markings on Mall Road and Banfield Road to increase safety. These are two of Belmont County highest volume of traffic roadways, and the pavement markings are very hard to maintain, be | Pavement Improvement | 06/11/2010 | 06/11/2010 | 08/12/2010 | 31059.62 | 1.3
7997 | Ohio | BELMONT |  | 6 | E090541 | Install a traffic control device at the intersection of State Route 7 and State Route 148 in the village of Powhatan Point. There are currently stop signs at this intersection because the traffic sign | Safety/Traffic Management | 06/11/2009 | 06/11/2009 | 11/15/2010 | 122000 | 0.02
7998 | Ohio | CARROLL |  | 18 | E090542 | The project will install new energy efficient traffic signals with integrated traffic demand devices in an effort to reduce traffic idling and fuel waste. With the installation of five new traffic sig | Safety/Traffic Management | 06/05/2009 | 06/05/2009 | 11/30/2010 | 565794.25 | 0.1
7999 | Ohio | HOLMES |  | 18 | E090543 | Repair and resurface over a mile of State Route 39 from Grant St. to Port Washington Rd. in the village of Millersburg as well as two miles of State Route 83 from Jackson St. to the western village co | Pavement Improvement | 01/07/2010 | 04/01/2010 | 07/31/2010 | 242240 | 13.07
8000 | Ohio | JEFFERSON |  | 6 | E090544 | SR 43 (Washington St) was built with concrete pavement in 1973 and is currently in very poor condition. The roadway is a four-lane, east-west arterial through the city, carrying approximately 15-18,00 | Pavement Improvement | 08/07/2009 | 08/07/2009 | 09/30/2011 | 7348941.44 | 1.09
8001 | Ohio | TUSCARAWAS |  | 18 | E090545 | Renovation of three existing bridges on the county system, including steel beam repair and painting, deck repair, repair of waterproofing, and repair of wearing surface. The three bridges are located | Bridge Replacement | 03/17/2010 | 03/17/2010 | 11/01/2010 | 1178514.5 | 0
8002 | Ohio | ADAMS |  | 2 | E090547 | This project calls for resurfacing County Road 70 (Lloyd Road) and County Road 18 (Blue Creek Road), for a total of 0.90 miles of a Rural Major Collector Route and 4.38 miles of a Rural Minor Collecto | Pavement Improvement | 03/19/2010 | 06/02/2010 | 06/30/2010 | 124230 | 0.95
8003 | Ohio | ROSS |  | 18 | E090548 | The project will rehabilitate and correct deficiencies of the U.S Rail in the city of Jackson. This rail service is crucial for business in rural, Appalachian Ohio serving two of the poorest counties, | Safety/Traffic Management | 12/02/2009 |  | 12/31/2010 | 1813951.21 | 0
8004 | Ohio | SCIOTO |  | 6 | E090549 | It is proposed to resurface approximately 10 miles of roadway along county roads 28, 53, 1, 163 and 15. The project also includes milling where necessary, signs and pavement marking installation. This | Pavement Improvement | 04/21/2010 | 04/21/2010 | 08/18/2010 | 1200000 | 8.67
8005 | Ohio | HENRY |  | 5 | E090553 | The replacement and widening of the existing bridge along Oakwood Avenue in Napoleon will restore legal load limits to the structure, allowing for larger vehicles and trucks to use this potential haul | Bridge Replacement | 08/19/2009 | 08/31/2009 | 05/15/2010 | 400000 | 0.01
8006 | Ohio | FULTON |  | 5 | E090554 | Resurfacing of State Route 66, S. Defiance Street, within the Village of Archbold from West Barre Road (CR C) north to the Norfolk-Southern Railway. This section of roadway was reconstructed by ODOT i | Pavement Improvement | 03/17/2010 | 05/24/2010 | 10/19/2010 | 240000 | 0.42
8007 | Ohio | LUCAS |  | 9 | E090556 | Otter Creek Road is an important trucking route. This $3 million project reconstructs the concrete pavement and adds a new asphalt overlay to Otter Creek Road between Corduroy Road and Bay Shore Road, | Pavement Improvement | 02/17/2010 | 04/12/2010 | 10/15/2010 | 2998709.1 | 2.16
8008 | Ohio | OTTAWA |  | 9 | E090557 | This outdated bridge was built in 1954. By upgrading and rehabilitating this bridge, carrying Billman Road over Cedar Creek in Allen Township, this bridge will safely carry traffic in Allen Township f | Bridge Replacement | 06/02/2010 | 06/02/2010 | 10/31/2010 | 292365 | 0.01
8009 | Ohio | WILLIAMS |  | 5 | E090558 | Construction of this overhead bridge crane and conveyor system will render the Port Authority's Intermodal Facility fully operational. This bridge crane will be able to transload cargo from a barge on | Other | 04/14/2010 | 05/17/2010 | 10/15/2010 | 432970.42 | 0
8010 | Ohio | LUCAS |  | 9 | E090559 | Norfolk Southern is committed to revise the layout of Airline Yard to increase the capacity from 30,000 lifts per year to 60,000 lifts per year, while minimizing any disruption of the adjacent rail li | Other | 07/01/2010 |  | 03/01/2012 | 7150000 | 0
8011 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090560 | This is a project to upgarde signalization at 13 intersections in Lucas County and to perform necessary related work. | Safety/Traffic Management | 09/14/2009 | 03/17/2010 | 08/20/2010 | 420000 | 0.01
8012 | Ohio | WOOD | TOLEDO (MI) | 5 | E090562 | This is a project to improve lighting from intersection of Bacon St & SR-65 to 2600 feet northeast, in the City of Rossford. | Safety/Traffic Management | 05/10/2010 |  | 08/31/2010 | 219270 | 0.49
8013 | Ohio | HURON |  | 5 | E090563 | This project will replace the Gibbs Road Bridge in Norwalk Township, east of the City of Norwalk. There is minimal road work involved; however the existing bridge is in poor condition. The ODOT bridge | Bridge Replacement | 12/17/2009 | 03/12/2010 | 10/29/2010 | 208590.24 | 0.05
8014 | Ohio | HURON |  | 5 | E090564 | The project will replace the deteriorated Ogan Rd Bridge, west of the Village of Wakeman. The existing 1-span steel beam bridge has a clear span of 28' and a width of 20'; has a bridge rating of 3P7 a | Bridge Replacement | 07/09/2009 | 07/20/2009 | 10/30/2009 | 220000 | 0.13
8015 | Ohio | LORAIN |  | 13 | E090565 | The project proposes to mill and resurface 0.422 miles of South Broadway Ave., between Cooper Foster Parkway (State Route 611) and the State Route 2 interchange, in the City of Lorain. Other work incl | Pavement Improvement | 04/29/2010 | 05/07/2010 | 10/29/2010 | 530931.78 | 0.78
8016 | Ohio | LORAIN |  | 13 | E090566 | Repair, Reconstruct and Resurface about 1.4 miles of Gateway Blvd., from Lake Ave. to Infirmary Rd. The roadway varies from 2 to 3 lanes (24 to 36 feet wide). This is a major arterial through the city | Pavement Improvement | 03/15/2010 | 05/07/2010 | 10/29/2010 | 584998 | 1.22
8017 | Ohio | LORAIN |  | 13 | E090567 | The project involves the continued re-development of Lorain?s waterfront on a portion of a U.S. Army Corps of Engineers 58-acre dredge disposal site. The project is part of a plan to diversify Lorain? | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 10/29/2010 | 3261892.16 | 0
8018 | Ohio | RICHLAND |  | 4 | E090568 | This project will renovate approximately 4700 centerline feet of existing streetscape in downtown Mansfield, including widening a section of State Route 430 and improving traffic congestion near State | Transportation Enhancements | 04/08/2010 | 03/26/2010 | 10/29/2010 | 960808.05 | 1.06
8019 | Ohio | RICHLAND |  | 4 | E090569 | Project consists of construction of approx. 3000' of new 29' curb & gutter street for an industrial park. Approx. 500' of existing street will be rebuilt on new vertical alignment to provide a safer i | New Construction | 02/11/2010 | 04/12/2010 | 10/29/2010 | 1284248.88 | 1.08
8020 | Ohio | MUSKINGUM |  | 18 | E090570 | This project involves overhauling and rehabilitating the overpasses carrying Zane Grey Road (County Road 199) and Moose Eye Road (County Road 436) over Interstate 70. To ensure continued safety for tr | Bridge Improvement | 08/19/2009 | 08/31/2009 | 07/31/2010 | 1655920 | 0.08
8021 | Ohio | MONTGOMERY | DAYTON | 3 | E090574 | Union Boulevard from I-70 to National Road-Smooth sealing of the roadway. | Pavement Improvement | 08/12/2009 | 09/17/2009 | 09/19/2009 | 200000 | 1.5
8022 | Ohio | MIAMI | DAYTON | 8 | E090575 | This project is to pave Evanston Road from CR 25A easterly to the CSX RR tracks in Tipp City. | Pavement Improvement | 09/03/2009 | 08/29/2009 | 09/08/2009 | 205140.12 | 1.59
8023 | Ohio | MIAMI | DAYTON | 8 | E090576 | Plane and resurface West Stanfield Road from South Stanfield Road to 300' west of Industry Court. | Pavement Improvement | 10/07/2009 | 10/16/2009 | 11/30/2009 | 76473.59 | 0.25
8024 | Ohio | MIAMI | DAYTON | 8 | E090577 | Plane and resurface South Stanfield Road from State Route 41 to West Stanfield Road. | Pavement Improvement | 10/07/2009 | 10/16/2009 | 11/30/2009 | 102667.4 | 0.38
8025 | Ohio | MONTGOMERY | DAYTON | 3 | E090578 | Wilmington Pike from Smithville Road to the Kettering North Corp Line -Mill the existing roadway, repair concrete pavement base, resurface and install new pavement markings, including raised pavement | Pavement Improvement | 10/15/2009 | 11/03/2009 | 09/10/2010 | 504277.85 | 1
8026 | Ohio | MONTGOMERY | DAYTON | 8 | E090579 | Various locations in Huber Heights-Rehab pavement at the following locations: Taylorsville Road from State Route 202 to Gentry Lane and from Wildcat Road to Timbercrest Drive; Powell Road from the wes | Pavement Improvement | 11/23/2009 | 11/23/2009 | 06/15/2010 | 491788 | 0.53
8027 | Ohio | MONTGOMERY | DAYTON | 3 | E090580 | Maue Road from Heincke Road to Byers Road-Pavement milling, adjustment of valve boxes and manholes, crack sealing and asphalt overlay, and new pavement markings. | Pavement Improvement | 05/12/2010 | 05/12/2010 | 07/30/2010 | 389400 | 1.19
8028 | Ohio | MONTGOMERY | DAYTON | 3 | E090581 | Olive Road from Salem Avenue to Main Street-Repair existing curbs as needed, pavement planing, full depth repairs, pavement overlay, new curbs and pavement markings. | Pavement Improvement | 06/08/2010 | 06/11/2010 | 09/15/2010 | 792000 | 1.99
8029 | Ohio | MONTGOMERY | DAYTON | 3 | E090582 | Stonequarry Road from the Vandaila West Corp Line to the East Line of the Ashbury Farms Subdivision-Mill and resurface the roadway, water valves and manholes will be adjusted to grade, construct ADA c | Pavement Improvement | 04/14/2010 | 05/17/2010 | 06/30/2010 | 272778 | 1.15
8030 | Ohio | MONTGOMERY | DAYTON | 3 | E090583 | Wolf Creek Street from McMaken Lane to Market Street-Mill and overlay roadway, including restriping and improving curb ramps. | Pavement Improvement | 10/01/2009 | 04/28/2010 | 06/15/2010 | 200000 | 1.43
8031 | Ohio | MONTGOMERY | DAYTON | 3, 8 | E090584 | Spinning Road from Airway Road to Linden Avenue-Slurry seal of the existing pavement with some full depth base repairs, utility manhole and valve adjustments and thermoplastic striping. | Pavement Improvement | 01/08/2010 | 03/24/2010 | 07/15/2010 | 327590 | 2.03
8032 | Ohio | MONTGOMERY | DAYTON | 3 | E090585 | Paragon Road from Congress Park to Normandy Road and Paragon Road from Alex-Bell Road to Grants Trail-Street resurfacing. | Pavement Improvement | 10/27/2009 | 05/07/2010 | 07/01/2010 | 205282 | 0.72
8033 | Ohio | MONTGOMERY | DAYTON | 3 | E090587 | Various locations in the City of Clayton-Install up to 179 handicap accessible ramps in two areas in the city. | Transportation Enhancements | 03/16/2010 | 04/05/2010 | 05/31/2010 | 293485 | 0
8034 | Ohio | MONTGOMERY | DAYTON | 3 | E090588 | West Central Avenue from Miami Avenue to Walnut Street and Miami Avenue from Central Avenue to Hydraulic Road-Pavement planing and repaving to eliminate rutting and support heavy loads. Sections of cu | Pavement Improvement | 03/05/2010 | 03/25/2010 | 06/30/2010 | 307120 | 0.15
8035 | Ohio | MONTGOMERY | DAYTON | 3 | E090589 | Patterson Boulevard/Riverside Drive Bridge over the Great Miami River-Replace backwalls, rehab main superstructure steel immediately adjacent to the backwalls and replace minor bracing members adjacen | Bridge Improvement | 03/17/2010 | 05/03/2010 | 08/23/2010 | 460800 | 0.03
8036 | Ohio | MONTGOMERY | DAYTON | 3 | E090590 | Little York Road Bridge over the Great Miami River-Replace the prestressed box beams due to beam delaminations and strand failure. | Bridge Replacement | 05/27/2010 | 05/27/2010 | 11/29/2010 | 1343393.7 | 0.5
8037 | Ohio | MONTGOMERY | DAYTON | 3 | E090591 | Shoup Mill Road Bridge over the Stillwater River-Remove paint from the structural steel and reapply. Repair damaged guardrail. | Bridge Improvement | 04/26/2010 | 04/26/2010 | 11/30/2010 | 573436.65 | 0
8038 | Ohio | MONTGOMERY | DAYTON | 3 | E090592 | Bigger Road from State Route 725 to the Centerville North Corp Line-Mill and resurface the existing roadway, maintenance to the curb, sidewalk and shared use path. Upgrade ramps to meet ADA compliance | Pavement Improvement | 10/22/2009 | 10/12/2009 | 06/30/2010 | 638526 | 1.04
8039 | Ohio | MIAMI | DAYTON | 8 | E090593 | Washington Road from a point 1,200' north of State Route 41, north to Drake Road-Shoulder stabilization and asphalt overlay. | Pavement Improvement | 03/10/2010 | 03/10/2010 | 05/21/2010 | 884112 | 1
8040 | Ohio | MIAMI | DAYTON | 8 | E090594 | Plane and resurface North Elm Street from State Route 41 to the Troy City Limits. | Pavement Improvement | 10/07/2009 | 10/05/2009 | 11/30/2009 | 148373.42 | 0.38
8041 | Ohio | MONTGOMERY | DAYTON | 3 | E090595 | Various locations in Oakwood-Replace current curb ramps with ADA compliant ramps and associated work. | Safety/Traffic Management | 01/07/2010 | 04/05/2010 | 05/31/2010 | 184209 | 2.84
8042 | Ohio | SUMMIT |  | 13 | E090598 | This project is for the rehabilitation of Main Street between I-277 and Firestone Blvd. This I-277 Corridor project involves reconstruction of four lanes of pavement on South Main Street in South Akro | Pavement Improvement | 05/26/2010 | 05/26/2010 | 06/30/2011 | 4775323.77 | 0.62
8043 | Ohio | CUYAHOGA | CLEVELAND, OH | 11 | E090599 | This project is to repair the bridge surface and sidewalks on the Center Street Lift Bridge over the Cuyahoga River channel in the City of Cleveland. | Bridge Improvement | 05/21/2010 | 05/27/2010 | 06/30/2011 | 2845462.91 | 0.1
8044 | Ohio | CUYAHOGA | CLEVELAND, OH | 11 | E090600 | This project consists of the reconstruction of E. 12th Street between from Superior Avenue to Chester Avenue in the City of Cleveland. Work includes removal of existing sidewalk, pavement planning and | Transportation Enhancements | 06/08/2010 | 04/20/2010 | 11/30/2010 | 413619.14 | 0.49
8045 | Ohio | CUYAHOGA | CLEVELAND, OH | 11 | E090601 | In Cleveland, this project is to rehabilitate the Willow Street bridge over the Cuyahoga River channel | Bridge Improvement | 04/23/2010 | 04/23/2010 | 09/30/2011 | 3392348.88 | 0.03
8046 | Ohio | LICKING | COLUMBUS | 12 | E090604 | This project is in downtown Pataskala, Sidewalks, install ADA ramps and replace sidewalks. | Safety/Traffic Management | 04/14/2010 | 04/26/2010 | 09/30/2010 | 191345 | 0.89
8047 | Ohio | FRANKLIN | COLUMBUS | 7, 12, 15 | E090605 | In Franklin County, resurfacing and pavement reconstruction of various roadways. Locations include Alkire Road from MAD County to Big Darby Creek; Brice Road from Chatterton Road to Refugee Road; Cas | Pavement Improvement | 10/06/2009 | 09/11/2009 | 06/15/2010 | 2226274.06 | 12.87
8048 | Ohio | FRANKLIN | COLUMBUS | 2 | E090606 | This project is along Alum Creek near Sunbury Rd from Mock Rd to Innis Rd at Innis Park. MORPC stimulus project funded 100% up to $3.0 M2.2 mile Muliti-use path, including three bridges and two neigh | Transportation Enhancements | 01/26/2010 | 02/08/2010 | 11/15/2010 | 3000000 | 0
8049 | Ohio | FRANKLIN | COLUMBUS | 12 | E090607 | This project is in Reynoldsburg. Trail from Civic Park trailhead to Blackoak Drive. Civic Park multi-purpose trail.Blacklick Creek Greenway mulit-use path from Civic Park trailhead to Blackoak Drive. | Transportation Enhancements | 04/29/2010 | 04/29/2010 | 09/30/2010 | 317219.2 | 0
8050 | Ohio | FRANKLIN | COLUMBUS | 15 | E090609 | Approximately 9000' of new sidewalks on school bus routes. Glenn Avenue: Tremont to Northwest; Waltham Road: Hampshire Road to Cambridge Blvd; Tremont Road: Pemberton Drive to Private Road; Mountview | Transportation Enhancements | 01/04/2010 | 03/30/2010 | 07/01/2010 | 466000 | 0
8051 | Ohio | FRANKLIN | COLUMBUS | 12 | E090610 | This project is in New Albany. Intersection of SR-605 and Walton Parkway. Install a new traffic signalization systsem including posts and mast arms. Repair pavement deficiencies, overlay 1.5" asphalt | Safety/Traffic Management | 01/26/2010 | 04/01/2010 | 11/01/2010 | 398402.5 | 0.05
8052 | Ohio | FRANKLIN | COLUMBUS | 15 | E090611 | This project is in Hilliard. Intersection of CR-3/Avery Rd and Northwest Parkway. Intersection upgrade including sidewalks, multi-use path, and street lighting - Avery Rd and Norwest Pkwy. | Pavement Improvement | 03/26/2010 | 04/05/2010 | 12/15/2010 | 1000000 | 0.02
8053 | Ohio | FRANKLIN | COLUMBUS | 12 | E090612 | This project is in Plain Twp. CR546/Dublin Granville Rd over Sugar Run. Just W of Harlem Road. Replace superstructure - concrete slab deck and rehab work to abutments and pier. | Bridge Improvement | 04/13/2010 | 04/13/2010 | 10/29/2010 | 390380.3 | 0.01
8054 | Ohio | DELAWARE | COLUMBUS | 12 | E090613 | Replace deck and superstructure members.Modify or replace bridge abutments.Possible piers work, minor roadway approach work, guardrail replacement. Vilage of Galena. South Old 3C Highway over Hoover R | Bridge Improvement | 01/21/2010 | 01/21/2010 | 09/30/2010 | 708753 | 0.04
8055 | Ohio | FRANKLIN | COLUMBUS | 7 | E090614 | This project is in Whitehall. From Broad St to Mayflower Blvd. Yearling Road Reconstruction Phase 3Signalization, street lighting, storm sewer, ADA sidewalk, and traffic signal improvements. | Pavement Improvement | 04/21/2010 | 05/03/2010 | 10/15/2010 | 2288044.16 | 0.45
8056 | Ohio | FRANKLIN | COLUMBUS | 12 | E090615 | This project is in Blendon Twp. CR-18/Central College Rd over Big Walnut Creek. 0.27 mi E of Sunbury Rd. MORPC funded stimulus project for $960,000.Replace existing superstructure - prestressed box b | Bridge Improvement | 03/17/2010 | 04/19/2010 | 07/16/2010 | 960000 | 0.08
8057 | Ohio | FRANKLIN | COLUMBUS | 12 | E090616 | This project is in Bexley. Urban core ADA Accessibility.Sidewalks, curb ramps, sidewalk improvements, and traffic signal improvements for better ADA accessibility. | Transportation Enhancements | 03/15/2010 | 04/19/2010 | 11/01/2010 | 800779.9 | 2.43
8058 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090633 | This is a project to rehabilitate George Hardy Dr., From Tiffin Ave to Saint Lawrence Dr in the Port of Toledo; and to perform necessary related work | Pavement Widening | 03/29/2010 | 03/29/2010 | 08/30/2010 | 954229.25 | 0
8059 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090634 | This is a project to mill and fill Illinois Ave (US-20A) in the City of Maumee from Ford St to west of Conant St (US-20) and to perform necessary related work. | Pavement Improvement | 02/11/2010 | 05/31/2010 | 07/16/2010 | 461994 | 0.86
8060 | Ohio | WOOD | TOLEDO (MI) | 5 | E090635 | This project is to resurface S. Main St (SR-25) in the City of Bowling Green from Clay St to Dill Ave; The project includes some curb and curb ramp replacements. The sidewalk on the east side | Pavement Improvement | 03/17/2010 | 06/03/2010 | 08/31/2010 | 527630.88 | 0.45
8061 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090636 | This project is to to resurface Hill Ave, in the City of Toledo, from Westwood Ave to Detroit Ave. | Pavement Improvement | 11/09/2009 | 03/29/2010 | 11/19/2010 | 1175000 | 0.83
8062 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090637 | This project is to resurface South Ave, in the City of Toledo, from Airport Hwy (SR-2) to Detroit Ave (US-24) | Pavement Improvement | 11/17/2009 | 05/10/2010 | 10/16/2010 | 242522 | 0.21
8063 | Ohio | WOOD | TOLEDO (MI) | 5 | E090638 | This project is to improve the intersection of Curtice Rd and Bradner Rd in the City of Northwood | Safety/Traffic Management | 04/27/2010 | 06/11/2010 | 08/27/2010 | 61506 | 0.01
8064 | Ohio | SUMMIT |  | 13 | E090639 | The project includes rehabilitating the existing Frank Boulevard including a reconstructed intersection with White Pond Drive | Pavement Improvement | 06/03/2010 | 04/19/2010 | 05/09/2011 | 2156644.31 | 0.44
8065 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | E090650 | This project is on Galbraith from Deer Park West Corp line to Blue Ash Road to resurface and restore pavement, curbs, improve drainage, and replace traffic loops | Pavement Improvement | 12/10/2009 | 03/29/2010 | 09/30/2010 | 648840 | 0.54
8066 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E090653 | This project involves Troy Ave and Morse Road. Resurfacing, curb replacement, base repairs, inlet reconstruction and storm sewer to restore roadway intergrity and ride quality and improve drainage. | Pavement Improvement | 01/07/2010 | 03/15/2010 | 08/01/2010 | 226120 | 0.35
8067 | Ohio | ASHTABULA |  | 14 | E090656 | There are four interrelated and interdependent highway infrastructure projects within this important regional transportation center. The project along SR 45 begins at the intersection of I-90 and SR 4 | Safety/Traffic Management | 06/15/2010 | 06/15/2010 | 05/02/2011 | 622073 | 0.13
8068 | Ohio | ASHTABULA |  | 14 | E090658 | Reconstruction and paving of North Eagle Street in the city of Geneva. | Pavement Improvement | 07/09/2009 | 07/09/2009 | 09/30/2010 | 450000 | 0.5
8069 | Ohio | ASHTABULA |  | 14 | E090659 | This project is for the resurfacing and improvements to Middle Road. The area is heavily traveled and located in a major manufacturing area. | Pavement Improvement | 05/05/2010 | 06/09/2010 | 09/30/2010 | 769764 | 4.68
8070 | Ohio | MAHONING |  | 17 | E090660 | The Norfolk Southern Line relocation entails the relocation of rail line in conjunction with the $900,000,000 steel mill expansion. The project will free up 100 acres for future growth and development | Safety/Traffic Management | 11/02/2009 | 11/06/2009 | 05/30/2010 | 3927397.32 | 0
8071 | Ohio | STARK |  | 16 | E090661 | The Fulton Road/Park Dr. NW Intersection Improvement includes the widening and addition of turn lanes to Park Drive north and south of Fulton Rd. NW; full width road pavement reconstruction with concr | Safety/Traffic Management | 04/01/2010 | 05/03/2010 | 03/30/2011 | 368994.98 | 0.01
8072 | Ohio | STARK |  | 16 | E090662 | The Sherrick Road stabilization project includes the injection of High Density Polyurethane (HDPE) Foam columns to stabilize the sanitary sewer trench; install ADA compliant curb ramps; and the profil | Pavement Improvement | 02/17/2010 | 05/03/2010 | 12/01/2010 | 1242574.19 | 0.72
8073 | Ohio | STARK |  | 16 | E090663 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project will involve three (3) crossings in Hartville and the surrounding area. One of the crossings wa | Safety/Traffic Management | 11/12/2009 | 11/12/2009 | 05/11/2011 | 540000 | 0.01
8074 | Ohio | STARK |  | 16 | E090664 | This project is Wheeling Lake Erie Rail Line track rehabilitation in Stark, Portage, Jefferson, Wayne, Lorain, Tuscarawas, and Cuyahoga counties | Other | 09/08/2009 | 09/15/2009 | 12/15/2010 | 1200000 | 0
8075 | Ohio | SUMMIT |  | 13 | E090665 | The city of Akron is proposing to hydro-demo and resurface approximately 24,500 squar yards of the Y-Bridge deck from Perkins to the northern limits of the bridges along with other minor associated br | Bridge Improvement | 11/25/2009 | 03/29/2010 | 03/29/2011 | 6767748.63 | 0
8076 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E090668 | Resurfacing Olive St from Ohio Ave to northern corp. limits in the Village of McDonald | Pavement Improvement | 10/29/2009 | 01/04/2010 | 06/30/2010 | 211671 | 0.5
8077 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 17 | E090669 | Resurfacing 12th street from Robinson Rd to Coitsville Rd in the city of Campbell. | Pavement Improvement | 11/25/2009 | 12/23/2009 | 09/01/2010 | 399660 | 1.22
8078 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E090677 | This project involves Dining Lane to Catalina Apartments west driveway. Resurface, curb replacement, base repairs and inlet reconstruction to restore roadway integrity and ride quality and improve dr | Pavement Improvement | 01/08/2010 | 03/29/2010 | 08/01/2010 | 275110 | 1.1
8079 | Ohio | FRANKLIN | COLUMBUS | 15 | E090679 | This project consists of 2 parts. Part one will replace a 700 foot bridge over the Scioto River with minimal appraoch work. This new bridge will connect to Rich Street and to reconstruct Washington Bl | Pavement Improvement | 02/19/2010 | 03/03/2010 | 08/31/2011 | 2061717 | 0.21
8080 | Ohio | PORTAGE | AKRON | 17 | E090680 | This project is to replace or rehabilitate the bridge over the Cuyahoga River and CSX. It will also improve the Crain Ave intersection | Bridge Replacement | 07/31/2009 | 09/18/2009 | 12/01/2012 | 3000000 | 0.09
8081 | Ohio | ROSS |  | 7, 18 | E090681 | State Route 104 is currently a two-lane highway between U.S. Route 35 and the new state Route 207 extension to U.S. Route 23, and it serves as the northwest bypass of Chillicothe. The project consists | Pavement Improvement | 07/01/2009 | 07/02/2009 | 09/30/2010 | 6530215.42 | 3.76
8082 | Ohio | HOCKING |  | 18 | E090683 | This is part 2 of 3 for the Nelsonville By-Pass Project. The portion of this project is for preliminary engineering and right of way activities. | New Construction | 09/29/2009 | 10/07/2009 | 03/03/2012 | 45547525.57 | 4.56
8083 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090684 | In Lucas county, widening of Wheeling Street from Navarre (SR2) to Pickle Road. This includes widening the bridge over I-280 in the City of Oregon | Pavement Widening | 05/05/2010 | 06/21/2010 | 11/18/2011 | 1522607.9 | 0.51
8084 | Ohio | DEFIANCE |  | 5 | E090685 | This project is to widen and add concrete islands to SR-66 corridor through Defiance. This activity will reduce the high rate of accidents caused by unsafe turning along the city?s busiest business c | Pavement Widening | 02/02/2010 | 02/24/2010 | 10/31/2010 | 3258910 | 1.44
8085 | Ohio | CUYAHOGA | CLEVELAND, OH | 10 | E090686 | Construct a grade separation at Columbia Road (SR-252) and the CSX Railroad Company tracks in the City of Olmsted Falls, from north of Sprague Road to the Ohio Turnpike (IR-80). | New Bridge Construction | 03/27/2009 | 07/21/2009 | 06/30/2011 | 7693000 | 0.35
8086 | Ohio | LICKING |  | 12 | E090687 | This project provides for the realignment and reconstruction of Waterworks Road and Deo Drive at State Route 13 and relocation and improvement the existing Railroad crossing. | Safety/Traffic Management | 03/31/2010 | 04/08/2010 | 10/31/2010 | 1800000 | 0.5
8087 | Ohio | HOCKING |  | 18 | E090688 | The US 33 Corridor is a designated National Highway System route that extends from Michigan to Virginia and includes the Nelsonville Bypass. This construction project will focus on the west end of a n | New Construction | 09/14/2009 | 09/21/2009 | 03/03/2012 | 93863443.8 | 3.04
8088 | Ohio | UNION | COLUMBUS | 15 | E090691 | This project takes place at the Intersection of SR-161, CR1(Industrial Parkway) and CR24 (Post Rd). MORPC stimulus project for $1,000,000.Realignment of 2050' of Industrial Parkway on north side of S | New Construction | 11/02/2009 | 11/15/2009 | 11/30/2010 | 1000000 | 0.82
8089 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 6 | E090692 | Resurfacing from Main St to Beloit Village limit with ADA compliant intersections. | Pavement Improvement | 08/04/2009 | 08/27/2009 | 10/30/2009 | 161158.41 | 0.75
8090 | Ohio | LICKING |  | 18 | E090703 | The project begins at SR79 at the intersection of South High Street and terminates at the North end in a cul-de-sac created when the new SR79 was created. A two lane roadway (formerly SR79) passes thr | Pavement Improvement | 02/16/2010 | 05/17/2010 | 08/31/2010 | 354376.7 | 1.72
8091 | Ohio | LAKE |  | 14 | E090708 | This section of four lane roadway, which is on the federal aid system, was rated in the ?poor? category during a 2006 pavement condition rating performed by our local Metropolitan Planning Organizatio | Pavement Improvement | 06/02/2010 | 06/02/2010 | 10/29/2010 | 2528188.52 | 3.03
8092 | Ohio | PREBLE |  | 8 | E090709 | Replace small culvert; existing culvert is an 84? by 40? cast-in-place concrete culvert in Preble county | Pavement Improvement | 06/19/2009 | 07/31/2009 | 08/07/2009 | 129940.63 | 0.01
8093 | Ohio | BUTLER | CINCINNATI (KY) | 8 | E090710 | In Butler county, resurface sections of Tylersville and River Roads and replace striping. | Pavement Improvement | 08/05/2009 | 09/08/2009 | 06/30/2010 | 2289190.2 | 6
8094 | Ohio | CLERMONT | CINCINNATI (KY) | 2 | E090711 | This project is to resuface county roads in Clermont county and add curb and ADA curb ramps on Buckwheat Road | Pavement Improvement | 10/20/2009 | 08/26/2009 | 05/28/2010 | 2464300 | 32.48
8095 | Ohio | GREENE | DAYTON | 7 | E090712 | Construct second phase of Access Road from Union Road to State Route 380, south and west of US 35 and Route 68 interchange. | New Construction | 11/06/2009 | 12/14/2009 | 08/18/2010 | 1350905.49 | 0
8096 | Ohio | GREENE | DAYTON | 7 | E090713 | Overlay of pavement, striping and berm repair of Valley Road from Upper Bellbrook Road to US 35 | Pavement Improvement | 09/02/2009 | 09/11/2009 | 04/16/2010 | 182714.87 | 1.79
8097 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E090714 | This project is to resurface a portion of Blue Rock Road in Hamilton county. This will include base repair and replacing guardrail. | Pavement Improvement | 03/17/2010 | 04/19/2010 | 08/16/2010 | 500000 | 1.35
8098 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | E090715 | This project is to microsurface Cornell Road from the bridge over I-71 to the bridge over I-275. This will include new pavement marking and curb ramps. | Pavement Improvement | 09/29/2009 | 09/18/2009 | 11/15/2009 | 95520.86 | 0.68
8099 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | E090716 | Resurface a portion of the Reed Hartman Hwy. Also, perform pavement repair, curb & gutter repair, replace signal loops with video detection, replacing pavement striping, place new RPMs, and where ap | Pavement Improvement | 08/12/2009 | 08/10/2009 | 10/31/2009 | 675121.57 | 1.2
8100 | Ohio | WARREN | CINCINNATI (KY) | 2, 3 | E090717 | Resurfacing of Kings Island Drive from the theater entrance to Western Row Road. | Pavement Improvement | 11/25/2009 | 11/16/2009 | 09/30/2010 | 307880 | 1.2
8101 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E090718 | This project is for resurfacing, curb replacement, base repairs and inlet reconstruction on Harrison Ave from Section Road to Lovell Avenue to restore roadway integrity | Pavement Improvement | 11/06/2009 | 10/09/2009 | 05/01/2010 | 635000 | 1
8102 | Ohio | BUTLER | CINCINNATI (KY) | 8 | E090719 | This project is in the city of Middleton on Sutphin between Grand Avenue to Central Avenue to resurface, spot curb and gutter repair, and ensurecurb ramps to be ADA compliant. | Pavement Improvement | 04/07/2010 | 06/07/2010 | 08/10/2010 | 716542.94 | 0.92
8103 | Ohio | BUTLER | CINCINNATI (KY) | 8 | E090720 | This project is in Middleton on University Blvd from Reinartz Blvd. to Briel to resurface, spot curb and gutter repair, and ADA compliant curb ramps | Pavement Improvement | 04/07/2010 | 04/19/2010 | 09/02/2010 | 1920838.04 | 0.38
8104 | Ohio | WARREN | DAYTON | 3 | E090721 | Various locations on State Route 73 and State Route 741 in Springboro-Replace existing traffic signal lamps with LED lamps. Install three battery backups and interconnect three traffic signals between | Safety/Traffic Management | 01/07/2010 | 04/01/2010 | 10/01/2010 | 186080 | 0.01
8105 | Ohio | WARREN | DAYTON | 3 | E090722 | Franklin-Trenton Road from the Franklin West Corp Line to Park Ave.-Resurface roadway including restriping and making curb ramps ADA compliant. | Pavement Improvement | 12/09/2009 | 04/13/2010 | 06/23/2010 | 218260 | 1.8
8106 | Ohio | GREENE | DAYTON | 7 | E090723 | From the intersection of Miami Avenue and South Detroit Street to 150' east of the intersection of Hill Street and South Detroit Street-Realign and widen sidewalks, replacing and aligning curb ramps, | Transportation Enhancements | 04/22/2010 | 03/26/2010 | 12/01/2010 | 30172.73 | 0
8107 | Ohio | WARREN | CINCINNATI (KY) | 2 | E090724 | In Warren county, on Columbia road and various county roads resurface, stripe, and add berm and curb ramp. | Pavement Improvement | 12/09/2009 | 04/02/2010 | 06/30/2010 | 2057181 | 1
8108 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | E090726 | In the village of Terrace Park on US 50 from Milford/Terrace Park Corp Line to Elm St. catch basin repair, curb replacement, install curb ramps as required, sidewalk replacement where necessary, impr | Safety/Traffic Management | 03/16/2010 | 03/18/2010 | 09/30/2010 | 761880 | 1.4
8109 | Ohio | GREENE | DAYTON | 7 | E090727 | East Main Street from Whiteman Street to Collier Street-Streetscape improvements that include curbs, replacing sidewalks, driveway apron improvements, aesthetic enhancements in the form of tree remova | Transportation Enhancements | 04/23/2010 | 04/19/2010 | 12/01/2010 | 209348 | 0.1
8110 | Ohio | GREENE | DAYTON | 7 | E090728 | Colonel Glenn Highway from the west corp. of Beavercreek to National Road-Mill and resurface the roadway. Includes base repairs, pavement markings, restoration of traffic signal loops, curb ramp upgra | Pavement Improvement | 02/02/2010 | 04/06/2010 | 08/31/2010 | 395989 | 0.49
8111 | Ohio | GREENE | DAYTON | 7 | E090729 | Creekside Trail from the Beavercreek WCL to the Beavercreek East Corp Line -Resurface the bikepath, install top soil berms, upgrade curb remps at crossing, replace/repair expansion joints on path brid | Transportation Enhancements | 01/27/2010 | 01/27/2010 | 08/13/2010 | 220000 | 0
8112 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E090730 | On Northland Blvd in Springdale, repair the concrete base, extend the west bound turn lane, widen the east boun turn land, curb replacement, catch basin repair, resurfacing, and a pedestrian walkway. | Pavement Improvement | 04/29/2010 | 04/26/2010 | 08/15/2010 | 876221.37 | 0.82
8113 | Ohio | HAMILTON | CINCINNATI (KY) | 2 | E090731 | This project is on Mosteller Rd from Sharon Road to 400 ft south of Kemper to resurface, replace curbs, base repairs, and inlet construction | Pavement Improvement | 04/29/2010 | 04/19/2010 | 07/30/2010 | 761565.9 | 1.02
8114 | Ohio | HAMILTON | CINCINNATI (KY) | 1, 2 | E090732 | In Cincinnati replacement and expansion of the existing computerized traffic control system interconnect cabling. The current cable is telephone grade twisted pair wire and the project will replace th | Other | 04/22/2010 | 04/22/2010 | 09/10/2010 | 1126694.94 | 0
8115 | Ohio | BUTLER | CINCINNATI (KY) | 8 | E090734 | This project is to complete the construction of missing segments of the multi us path within the Oxford Community Park | Pavement Improvement | 04/27/2010 | 05/14/2010 | 08/06/2010 | 201850 | 0
8116 | Ohio | FRANKLIN | COLUMBUS | 7, 12, 15 | E090747 | This project is in Columbus and includes various routes in the City of Columbus. Regional resurfacing program in City of Columbus. | Pavement Improvement | 08/24/2009 | 09/08/2009 | 06/15/2010 | 2938282.91 | 6.2
8117 | Ohio | DELAWARE | COLUMBUS | 12 | E090748 | In Delaware County, resurfacing and pavement reconstruction of various county roads and city streets. Locations include London Road in the City of Delaware from US42 north 0.10 miles; Liberty Street | Pavement Improvement | 10/08/2009 | 09/28/2009 | 10/01/2010 | 1795005 | 14.07
8118 | Ohio | CUYAHOGA |  | 10, 11 | E090751 | Widening of the ramp from I-490 eastbound to I-77 northbound and re-facing of the outside parapets on the I-77 bridge over U.S. 422 (Orange Avenue) and East 30th Street. The work includes replacement | Bridge Improvement | 05/18/2009 | 06/02/2009 | 05/15/2010 | 2613279.82 | 0.84
8119 | Ohio | WOOD |  | 5, 9 | E090752 | This project consists of replacing the current bridge deck surface on the Disalle bridge crossing the Maumee River. Additional bridge work will be performed at Miami Street overpass and railroad bridg | Bridge Improvement | 06/15/2009 | 06/15/2009 | 10/15/2010 | 5585106.13 | 0.82
8120 | Ohio | HARRISON |  | 18 | E090753 | Three bridges on U.S. 22 (eastbound U.S. 22, westbound U.S. 22, and the westbound on-ramp to U.S. 22) over an abandoned railroad just west of SR 9 in Cadiz Township will be removed and replaced with e | Bridge Replacement | 05/26/2009 | 06/30/2009 | 05/15/2010 | 910619.13 | 0.03
8121 | Ohio | FRANKLIN |  | 15 | E090754 | Resurface two miles of US 40 between Hague Avenue and Central Avenue in Columbus including the ramp from I-70 eastbound to Broad Street and the ramp from Broad Street to I-70 westbound. | Pavement Improvement | 06/01/2010 |  | 08/31/2010 | 654980 | 1.96
8122 | Ohio | TUSCARAWAS |  | 18 | E090755 | Resurfacing nearly four miles of U.S. 250 from SR 800 at Dennison to the Harrison County line, and just over a mile of SR 800 from Thornwood Park in Dennison to U.S. 250. | Pavement Improvement | 07/17/2009 | 09/11/2009 | 04/15/2010 | 1093310 | 4.99
8123 | Ohio | LOGAN |  | 4 | E090756 | This project is to resurface Main Street in Bellefontaine from Lake Street (SLM 7.32) to Water Street (SLM 7.94) with asphalt concrete. | Pavement Improvement | 06/25/2009 | 09/16/2009 | 09/30/2009 | 227525 | 0.62
8124 | Ohio | CUYAHOGA |  | 10 | E090757 | The project calls for a complete ramp replacement at the Interstate 480/West 130th Street interchange in the city of Cleveland. The work will include a complete replacement of aging pavements. | Pavement Improvement | 08/27/2009 | 09/25/2009 | 06/25/2010 | 816050 | 0
8125 | Ohio | ASHLAND |  | 16 | E090767 | This project will replace the bridge over Jerome Fork on SR89 in Ashland County. | Bridge Replacement | 06/26/2009 | 08/17/2009 | 08/15/2010 | 393060 | 0.04
8126 | Ohio | PORTAGE | AKRON | 17 | E090769 | This project is to resurface Chestnut street from Ravenna South Corp to State Route 14. | Pavement Improvement | 04/19/2010 | 04/26/2010 | 10/29/2010 | 616000 | 2.57
8127 | Ohio | PORTAGE | AKRON | 14 | E090770 | This project is for the consturction of curbs and gutters with some storm sewer on SR 305 from State Route 700 to East Corp limit. | Pavement Improvement | 02/24/2010 | 05/13/2010 | 07/31/2010 | 143600 | 0.48
8128 | Ohio | SUMMIT | AKRON | 13 | E090771 | In the City of Norton, Summit County, rehabilitation of 2.59 miles of Greenwich Road beginning at the Medina County line and ending at Cleveland-Massillon Road. Included in the rehabilitation are mill | Pavement Improvement | 03/29/2010 | 03/29/2010 | 09/30/2010 | 484340 | 3.3
8129 | Ohio | SUMMIT | AKRON | 17 | E090772 | This project invloves reconstruction, Including traffic signal upgrade on Summit CR 512 from Triplett Boulevard to East Market Street. | Pavement Improvement | 04/19/2010 | 04/05/2010 | 11/15/2010 | 2224006 | 1.16
8130 | Ohio | SUMMIT | AKRON | 17 | E090773 | This project invloves Mogadore Road at Cleveland Avenue, with removal of retaining wall, and increasing turning radius. | Safety/Traffic Management | 03/24/2010 | 04/30/2010 | 06/30/2010 | 54729.72 | 0.01
8131 | Ohio | SUMMIT | AKRON | 14 | E090779 | This project invloves resurfacing of Liberty Road from Cannon Road to Cuyahoga County line. | Pavement Improvement | 11/06/2009 | 10/05/2009 | 08/31/2010 | 444263.97 | 2.54
8132 | Ohio | SUMMIT | AKRON | 13, 14 | E090780 | This project involves Reconstruction and Adding turn lanes on Summit CR 145 from Wyoga Lake Road to Allen Road. | Pavement Widening | 06/05/2009 | 03/01/2010 | 12/31/2010 | 2560000 | 1.17
8133 | Ohio | SUMMIT | AKRON | 13 | E090781 | This project involves Wheatley Road at Brecksville Road. Construct turn lanes. Install new traffic signal. Upgrade existing signal. | Safety/Traffic Management | 06/23/2010 |  | 10/30/2010 | 239800 | 0.03
8134 | Ohio | ASHLAND |  | 16 | E090785 | This project will replace a deficient 3-span steel beam bridge over the Muddy Fork on State Route 302, 0.19 mile west of Township Road 63, in Perry Township. This is east of the community known as Red | Bridge Replacement | 06/25/2009 | 08/31/2009 | 07/15/2010 | 439070 | 0.03
8135 | Ohio | WAYNE |  | 16 | E090786 | This project will rehabilitate a deficient bridge on SR 301 in Wayne county over Interstate 71. | Bridge Improvement | 07/17/2009 | 04/26/2010 | 10/15/2010 | 1519660 | 0.01
8136 | Ohio | BUTLER | CINCINNATI (KY) | 8 | E090787 | This project is in the city of Monroe to install new signal at Britton and improve signal at intersection of Cincinnati Dayton Road and SR 63 by adding backplates, led heads, and dilemma zone detectio | Safety/Traffic Management | 06/04/2010 | 06/04/2010 | 11/05/2010 | 543960 | 0.29
8137 | Ohio | CUYAHOGA | CLEVELAND, OH | 10, 11, 13, 14 | E090788 | To provide access to work for low income individuals not able otherwise to hold a job. Some of these services are provided directly by GCRTA and some are contracted to other area transportation provi | Other | 09/23/2009 | 09/23/2009 | 09/23/2011 | 1863358 | 0
8138 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090789 | This project is to resurface Telegraph Rd (US-24) from Alexis Rd (SR-184) to just south of the Michigan State Line in the City of Toledo. | Pavement Improvement | 11/09/2009 | 05/05/2010 | 10/19/2010 | 315000 | 0.53
8139 | Ohio | LUCAS | TOLEDO (MI) | 9 | E090790 | This project is to resurface Detroit Ave (US-24) in the City of Toledo from I-75 near Monroe St to Central Ave (SR-120). | Pavement Improvement | 11/09/2009 | 05/07/2010 | 10/19/2010 | 570000 | 0.86
8140 | Ohio | CUYAHOGA |  | 10, 11, 13, 14 | E090792 | Track rehabilitation work to reduce derailment expenses and help railroad provide reliable service to two rail-dependent businesses that employ a total of 50 people. | Other | 05/27/2010 |  |  | 66988 | 0
8141 | Ohio | KNOX |  | 18 | E090793 | Knox and Muskingum Counties are considered smaller to medium sized counties with populations that have grown in the last decade. The average driver in these counties spends between 16 and 26 minutes i | Bridge Improvement | 08/28/2009 | 09/04/2009 | 11/09/2009 | 1100000 | 0.46
8142 | Ohio | LAWRENCE |  | 6 | E090794 | The project will construct access roads to allow for better access handling between Ohio River barges, rail and highway freight and spur the development of the South Point Inter-modal Transfer Facilit | Other | 04/01/2010 | 04/15/2010 | 11/30/2010 | 1170500 | 0
8143 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E090795 | In Hamilton county on Galbraith Rd from Daly Road to Winton, remove and replace pavement with ajacent curbs and sidewalk. Also replace the signal Galbraith and Mockingbird. | Pavement Improvement | 04/23/2010 | 04/23/2010 | 11/19/2010 | 2655491.58 | 0.59
8144 | Ohio | MONTGOMERY | DAYTON | 3 | E090797 | The project consists of infrastructure repairs along Woodman Drive from north of US 35 and Linden Avenue to the community of Beavercreek. The improvement work in both areas include milling and asphalt | Pavement Improvement | 03/31/2010 | 05/10/2010 | 08/31/2010 | 2024540 | 2.16
8145 | Ohio | PIKE |  | 7 | E090798 | The project will improve the cloverleaf interchange at U.S. Route 23 and the exit for the Portsmouth Gaseous Diffusion Plant (A-Plant), south of Piketon, by creating access to the west side and into t | Pavement Improvement | 05/03/2010 | 05/19/2010 | 10/31/2010 | 1454412.91 | 0.01
8146 | Ohio | WAYNE |  | 5 | E090800 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project involves five grade crossings on the W&LE rail line between Smithville and Orrville. All five c | Safety/Traffic Management | 09/16/2009 | 10/20/2009 | 06/17/2010 | 850000 | 0
8147 | Ohio | CLARK |  | 4, 7 | E090801 | This project expands the existing investment by the State of Ohio and the West Central Ohio Port Authority (WESTCO) by improving bridge and track conditions on the rail lines. | Other | 11/04/2009 | 11/12/2009 | 12/31/2011 | 1000000 | 0
8148 | Ohio | COLUMBIANA |  | 6 | E090802 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project will install state-of-the-art warning devices and a new high-type grade crossing surface at the | Safety/Traffic Management | 02/18/2010 | 06/04/2010 |  | 250000 | 0
8149 | Ohio | PORTAGE | AKRON | 14 | E090807 | In the City of Aurora (Portage Co.), widening and resurfacing of 2.15 miles of SR 43 (North Aurora Road) including new storm sewer, curb and gutter, water mains, traffic signals, signing and pavement | Pavement Improvement | 07/17/2009 | 08/31/2009 | 12/31/2010 | 1000000 | 2.01
8150 | Ohio | CUYAHOGA, SUMMIT |  | 10, 11, 13, 14 | E090808 | This is a two-part project to install a new intelligent transportation system. Part 1 (Cuyahoga, Lorain, Medina, Summit, Portage & Lake Counties) includes the putting in place of approximately 83 traf | Safety/Traffic Management | 08/21/2009 | 10/21/2009 | 09/30/2011 | 21258860 | 0
8151 | Ohio | LAKE | CLEVELAND, OH | 14 | E090811 | Traffic signal and widening improvements along SR-91 in Willougby Hills. | Safety/Traffic Management | 04/05/2010 | 05/18/2010 | 11/30/2010 | 862360 | 2.38
8152 | Ohio | CUYAHOGA |  | 10 | E090812 | This project is located in the City of Cleveland on Lorain Avenue between the City of Cleveland west corporation limit and Groveland Avenue. This project is a streetscape improvement that includes new | Transportation Enhancements | 06/08/2010 | 06/08/2010 | 11/30/2010 | 1553291.81 | 0.53
8153 | Ohio | GEAUGA | CLEVELAND, OH | 14 | E090813 | In Geauga county this project will resurface Auburn Road from Kinsman Rd. to Fairmount Rd. in Newbury Twp | Pavement Improvement | 12/01/2009 | 05/24/2010 | 07/31/2010 | 283806.79 | 1.77
8154 | Ohio | STARK | CANTON | 16 | E090846 | In Stark County, CR-98, from SR-241(Wales Ave.) to Brunerdale Ave. Widen existing road to four lanes with curb and gutters. Increase to 5 lanes at all major intersections. Includes Storm Sewer and tra | Pavement Widening | 06/15/2009 | 09/21/2009 | 07/31/2011 | 4800000 | 2.54
8155 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 2 | E090848 | Resurfacing of Fairground Blvd from SR 46 east to city limits. Resurfacing of Herbert Rd from the east city limits to the west city limits. | Pavement Improvement | 03/24/2010 | 05/03/2010 | 08/31/2010 | 312791.65 | 1.15
8156 | Ohio | STATEWIDE |  | 10, 12, 15 | E090851 | This project provides long term rail improvements to the State of Ohio-owned Panhandle Rail line including the repair and rehabilitation of bridges, rail and a tunnel. | Other | 04/13/2010 |  | 10/31/2010 | 7699941 | 0
8157 | Ohio | STATEWIDE |  | 7, 8, 15 | E090852 | The project consists of five rail line impediments between Rickenbacker and Sharonville and on-site improvements at the Rickenbacker Terminal that when complete will allow for the movement of double-s | Other | 06/11/2010 |  | 03/01/2012 | 4100000 | 0
8158 | Ohio | STATEWIDE |  | 4, 8 | E090854 | Railroad tie replacement and other related track work to rehabilitate RJ Corman-owned lines in Western Ohio. Overall, the RJC Western Ohio lines generated 4,274 (2005), 4,541 (2006), and 3,648 (2007) | Other | 11/18/2009 | 11/30/2009 | 06/30/2010 | 1300000 | 0
8159 | Ohio | LICKING | COLUMBUS | 12, 18 | E090856 | The resurfacing of Taylor Rd (TR36) from SR16 north to Havens Corners Rd and the resurfacing of Palmer Road (TR169) from Mink Road west to the Reynoldsburg Corporation. | Pavement Improvement | 03/02/2010 | 06/07/2010 | 08/31/2010 | 421785 | 4.81
8160 | Ohio | FAIRFIELD | COLUMBUS | 7 | E090857 | The resurfacing of sections or various federal aid routes within Fairfield County - Twsp Rd 223 (Wagram Rd) from Taylor Rd north to the county line. County Rd 13 (Baisl-Western Rd) from CR18 east to C | Pavement Improvement | 05/03/2010 | 05/03/2010 | 11/30/2010 | 514815 | 5.62
8161 | Ohio | TRUMBULL |  | 17 | E090859 | The Mahoning Avenue Resurfacing and Lighting Project includes resurfacing the asphalt pavement. The alignment will follow existing and include curb ramp construction in accordance with ADA standards. | Pavement Improvement | 05/17/2010 | 05/17/2010 | 12/31/2010 | 573679.14 | 1.72
8162 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E090869 | Planing and resurfacing of 1.78 miles of High Street from Mahoning Ave to Chestnut; incidental curb and walk replacement. | Pavement Improvement | 05/17/2010 | 05/17/2010 | 10/25/2010 | 401830.79 | 0.59
8163 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E090870 | Roadway resurfacing and repair on Trumbull Ave from the City of Girard to SR 193. Roadway resurfacing and repair on West Liberty St from Four Mile Run Rd to Salt Springs Rd. Roadway resurfacing and | Pavement Improvement | 05/05/2010 | 05/06/2010 | 08/30/2010 | 489080 | 2.43
8164 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E090871 | Resurfacing Austintown Warren Road from Burnett East Rd to the City of Warren south corp. limits in Trumbell county. | Pavement Improvement | 05/10/2010 | 06/05/2010 | 07/31/2010 | 258550 | 1.17
8165 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E090872 | Roadway resurfacing and repair on Carson Salt Springs Rd from railroad to Austintown Warren Rd. Roadway resurfacing and repair on Austintown Warren Rd from Village of Lordstown to Carson Salt Springs | Pavement Improvement | 04/14/2010 | 05/19/2010 | 08/31/2010 | 494050 | 2.73
8166 | Ohio | HAMILTON | CINCINNATI (KY) | 1, 2 | E090875 | This project is in Amberely Village to surface, replace damaged curb, repair pavement distressed areas, repair damaged inlets, install ADA compliant ramps where needed, upgrade existing traffic signal | Pavement Improvement | 04/19/2010 | 04/19/2010 | 10/30/2010 | 1039370 | 1.49
8167 | Ohio | MONTGOMERY |  | 3 | E090876 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project involves upgrading circuitry and warning devices on six (6) crossings in Montgomery and Warren | Safety/Traffic Management | 02/01/2010 | 03/01/2010 |  | 1000000 | 0
8168 | Ohio | FRANKLIN | COLUMBUS | 7, 12, 15 | E090879 | In Franklin County, resurfacing and pavement reconstruction of various roadways. Locations include Alum Creek Drive from Big Walnut Creek to Rathmell Road; Cambridge Blvd from Riverside Drive to Arli | Pavement Improvement | 04/13/2010 | 04/21/2010 | 07/30/2010 | 1879848.59 | 11.67
8169 | Ohio | PORTAGE |  | 17 | E090927 | This project replaces the Brady Lake Road bridge over the CSX Railroad and Breakneck Creek in Franklin Township, Portage County. | Bridge Replacement | 09/16/2009 | 01/04/2010 | 12/31/2010 | 1124000 | 0.01
8170 | Ohio | LAWRENCE |  | 6 | E090992 | The project will construct access roads to allow for better access handling between Ohio River barges, rail and highway freight and spur the development of the South Point Inter-modal Transfer Facilit | Other | 05/26/2010 | 05/26/2010 | 11/30/2010 | 2429500 | 0
8171 | Ohio | FAYETTE |  | 7 | E091007 | In Fayette County, pavement repairs and resurfacing of SR 734 beginning at Greene county line and ending at SR 38. Included in this distance is State Street (also known as SR 41 & SR 734) through the | Pavement Improvement | 02/11/2010 |  | 09/30/2010 | 1021283.42 | 13.59
8172 | Ohio | STARK | CANTON | 16 | E091023 | This project will resurface County Route 66 from 12th Street to 50th Street. | Pavement Improvement | 05/10/2010 | 05/10/2010 | 12/30/2010 | 102345.5 | 3.44
8173 | Ohio | LORAIN | CLEVELAND, OH | 9, 13 | E091030 | To fund a transportation brokerage in Lorain County to receive and redirect requests for work trips to eligible transportation providers | Other | 01/04/2010 | 01/04/2010 | 01/04/2012 | 140000 | 0
8174 | Ohio | SUMMIT |  | 13 | E091052 | This project is in Summit county South Main St. Intersection, Widen North and South approaches. Convert Southbound right turn lane into a through/right lane. Upgrade of signal control. | Other | 06/09/2010 | 06/09/2010 | 09/30/2012 | 200000 | 0.02
8175 | Ohio | HAMILTON | CINCINNATI (KY) | 1 | E091103 | This project takes place at Vine Street from Mitchell Avenue to Elmwood Place South Corp Line. It consists of resurfacing with asphaltic concrete and restriping. | Pavement Improvement | 04/16/2010 | 04/15/2010 | 10/01/2010 | 949740 | 2.11
8176 | Ohio | MONTGOMERY | DAYTON | 3 | E091106 | From the southern terminus of Hempstead Station Drive, north along Hempstead Station Drive to Stroop Road then east along Stroop to the southwest corner of the Stroop/Wilmington Pike intersection-Cons | Transportation Enhancements | 11/23/2009 | 11/09/2009 | 06/30/2010 | 179792 | 0
8177 | Ohio | SUMMIT | AKRON | 13, 17 | E091125 | In the city of Green, widen and resuface of Arlington road. Also adding turn lanes, signal coordinate and drainage improvments. This project also includes the realignment of Jarvis Road | Safety/Traffic Management | 03/08/2010 | 04/05/2010 | 10/01/2011 | 2000000 | 1.38
8178 | Ohio | ASHTABULA |  | 14 | E091126 | This project is a bridge replacement taking place over Penn Central Rail Road. | Bridge Replacement | 06/02/2010 | 06/02/2010 | 10/29/2010 | 350000 | 0
8179 | Ohio | LUCAS |  | 9 | E091159 | This project is In the Port of Toledo from Sinclair Ave to John Carey Dr. It is for the reconstruction of a portion of St. Lawrence Drive, and the realignment of a portion of St. Lawrence Drive which | New Construction | 03/29/2010 | 03/29/2010 | 10/22/2010 | 1985975.58 | 0
8180 | Ohio | MONTGOMERY |  | 3 | E091204 | National Road in Vandalia from I-75 to just east of Brown School Road-Remove and replace trees, add decorative tree grates, decorative lights, replace sidewalk, pavers, drive aprons an upgrade bus sto | Transportation Enhancements | 05/20/2010 | 05/25/2010 | 10/29/2010 | 1014170 | 0.33
8181 | Ohio | CUYAHOGA |  | 11 | E091217 | This project is in Cleveland from Prospect Avenue to Euclic Avenue. It involves East 14th Street Streetscape: Sidewalks, paving, trees, plants and benches. | Transportation Enhancements | 06/11/2010 | 04/20/2010 | 11/30/2010 | 1923151.12 | 0.28
8182 | Ohio | MONTGOMERY |  | 3 | E091251 | In Montgomery county, widen Byers Road from 2 to 5 lanes and Relocate To The West To Form A Four-Leg Intersection With The Northern Most Section of Wood Rd. | Pavement Widening | 02/27/2009 | 05/26/2010 | 05/30/2011 | 4000000 | 2
8183 | Ohio | CUYAHOGA | CLEVELAND, OH | 14 | E091267 | The project consists of reconstructing approximately 2.44 miles of Bainbridge Road within the City of Solon. The work includes a new flexible pavement, integral bike lanes, and a new curb. | Pavement Improvement | 01/21/2010 | 04/05/2010 | 06/30/2012 | 12606660.97 | 2.46
8184 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E091291 | This project will resurface and rehab Girard-I80/SR11 to Girard south corp. limit. It will include planing the entire roadway, repairing and widening sub-standard lane widths, pavement marking applic | Pavement Improvement | 01/14/2010 | 03/30/2010 | 12/31/2010 | 800000 | 1.32
8185 | Ohio | MAHONING | YOUNGSTOWN-WARREN | 6 | E091335 | This project is to resurface Mahoning Ave from SR45 east to Lipkey Road. | Pavement Improvement | 06/08/2010 | 05/10/2010 | 09/30/2010 | 519835.53 | 1.77
8186 | Ohio | TRUMBULL | YOUNGSTOWN-WARREN | 17 | E091336 | This project is to resurface Tibbets Wick from US422 east to SR 11. | Pavement Improvement | 06/11/2010 |  | 09/30/2010 | 384815.45 | 1.35
8187 | Ohio | DELAWARE |  | 12 | E100027 | This project is the construction of a grade separation with the CSX Railroad. | New Construction | 05/03/2010 | 05/03/2010 | 10/31/2011 | 7677529.5 | 0.34
8188 | Ohio | CLARK |  | 7 | E100102 | This project includes streetscape and resurfacing Fountain Street from the bridge over Buck Creek to McCreight Ave. | Transportation Enhancements | 05/25/2010 | 05/17/2010 | 09/11/2010 | 847106 | 0.62
8189 | Ohio | FULTON |  | 5 | E100110 | This project is a Tier 1 Railroad Grade Separation project for Hallett Ave/Norfolk Southern in the Village of Swanton with offset alignment. | Safety/Traffic Management | 05/18/2010 |  | 09/30/2012 | 7900000 | 0
8190 | Ohio | HAMILTON |  | 1 | E100123 | This project is Phase 2 of the Hamilton Interstate 75 corridor improvement project. The scope of this project includes replacing the Monmouth Street overpass, and converting the roadway to a through s | Bridge Replacement | 02/25/2010 | 03/11/2010 | 08/31/2011 | 7192394.16 | 0
8191 | Ohio | SUMMIT | AKRON | 17 | E100141 | This project is to construction a 6 leg roundabout including sight distance to the Northeast Avenue approach in Tallmage. This is the intersection of Howe Road/Northeast Avenue/Munroe Road | Pavement Improvement | 06/03/2009 | 04/12/2010 | 03/02/2011 | 268800 | 0.1
8192 | Ohio | UNION |  | 15 | E100220 | The project will replace the 1913 bridge with a modern covered bridge bringing tourism to the country which will be highlighted at the County?s Annual Covered Bridge Festival. | Bridge Replacement | 04/10/2009 | 04/10/2009 | 12/30/2010 | 377000 | 0.01
8193 | Ohio | MONTGOMERY | DAYTON | 3 | E100295 | This project is intended to preserve roadway in the City of Kettering. It will include replacing pavement and installation of tree lawns with trees and new sidewalks. It will also include updating | Pavement Improvement | 04/13/2010 | 05/03/2010 | 07/01/2011 | 1345519.34 | 0.1
8194 | Oklahoma | MUSKOGEE |  | 2 | STIM001 | Resurface 6.50 miles of concrete pavement on east and westbound I-40 from MP 281.67 to MP 288.22 and replace the east and westbound Dirty Creek bridges. | Pavement Improvement | 06/01/2009 | 06/01/2009 | 01/21/2011 | 26884000 | 6.55
8195 | Oklahoma | LE FLORE |  | 2 | STIM008 | Roadway construction of the remaining 2 lanes of a 4 lane facility from SH-9A extending east to SH-112 to add capacity for an existing two lane facility and replace structurally obsolete and/or defien | Bridge Replacement | 09/14/2009 | 12/01/2009 | 09/13/2010 | 5968238 | 1.8
8196 | Oklahoma | ATOKA |  | 2 | STIM009 | Roadway and Bridge construction of a new 2 lane facility offset to an existing 2 lane facility from 0.33 miles West of the Atoka and Pushmataha County Line extending East into Atoka County 1.82 miles. | Pavement Widening | 04/27/2009 | 04/27/2009 | 11/22/2009 | 3818000 | 1.82
8197 | Oklahoma | GARVIN |  | 4 | STIM010 | This project will extend the life of the pavement and significantly improves ride quality on 6.57 miles of I-35 by stabalizing the existing pavement. Project begins at SH-29 and extends to SH-19. | Pavement Improvement | 04/27/2009 | 04/27/2009 | 11/27/2010 | 24830000 | 6.57
8198 | Oklahoma | SEMINOLE |  | 5 | STIM011 | Full depth concrete pavement reconstruction for 2.47 miles on I-40 in Seminole County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 07/13/2009 | 07/07/2009 | 01/28/2010 | 2730000 | 2.47
8199 | Oklahoma | MCCLAIN |  | 4 | STIM013 | Asphalt pavement resurfacing and bridge repair on I-44 in McClain County. This project was resurfaced within existing right of ways and no lanes were added. | Pavement Improvement | 04/27/2009 | 04/27/2009 | 09/23/2009 | 6760000 | 7.5
8200 | Oklahoma | CANADIAN |  | 3 | STIM015 | "This project overlays the existing concrete pavement with a concrete overlay. Also, 2 additional lanes are being added injunction with reconstructing the existing bridges The project starts at Mile M | Pavement Improvement | 06/01/2009 | 06/01/2009 | 08/09/2011 | 30000000 | 4
8201 | Oklahoma | KAY |  | 3 | STIM019 | This project reconstructs the pavement surfacing upgrades the bridges and installs cable barrier in the median. The project starts at Mile Marker 224.4 and extends to Mile Marker 229.3 on I-35. | Pavement Improvement | 06/01/2009 | 06/01/2009 | 03/02/2011 | 21586000 | 4.9
8202 | Oklahoma | BECKHAM |  | 3 | STIM024 | "This project replaces deteriorated bridge decks and improves deteriorated pavement for eight miles of I-40 near Sayre, OK. " | Pavement Improvement | 04/27/2009 | 05/01/2009 | 01/21/2010 | 13379000 | 8
8203 | Oklahoma | TEXAS |  | 3 | STIM028 | This project seals cracks and overlays the existing asphalt pavement. The project starts at Guymon and extends east 7.0 miles on US- 412 | Pavement Improvement | 04/27/2009 | 04/27/2009 | 09/23/2009 | 6297000 | 7.3
8204 | Oklahoma | CIMARRON |  | 3 | STIM031 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at 7.5 miles east of Jct. with US-287 on US-64 and extends 14.5 miles east. | Pavement Improvement | 06/09/2009 | 07/28/2009 |  | 6410000 | 8
8205 | Oklahoma | TEXAS |  | 3 | STIM033 | This project crack seals and overlays the existing asphalt pavement. The project starts at the Texas/Cimarron County Line and extends east 4.5 miles on US-64 north of Guymon. | Pavement Improvement | 04/27/2009 | 04/27/2009 | 09/03/2009 | 3567000 | 4.5
8206 | Oklahoma | ELLIS |  | 3 | STIM034 | This project installs a new bridge on US -283 over 25 mile creek 0.5 miles north of the Jct with State Highway 15 | Pavement Improvement | 04/27/2009 | 04/27/2009 | 11/22/2009 | 3472000 | 0.75
8207 | Oklahoma | COMANCHE |  | 4 | STIM037 | "This project replaces the deficient bridge over Beaver Creek for the west bound lanes of State Highway 7 west of Lawton, OK. " | Bridge Replacement | 04/27/2009 | 05/06/2009 | 12/02/2009 | 2241000 | 0.381
8208 | Oklahoma | CARTER |  | 4 | STIM038 | "This project replaces a deficient bridge over Red Oak Creek on US 70 west of Ardmore, OK. " | Bridge Replacement | 04/27/2009 | 04/27/2009 | 12/22/2009 | 1272000 | 0.25
8209 | Oklahoma | STEPHENS |  | 4 | STIM039 | "This project constructs a new interchange at US 81 and Bois D'Arc Avenue in Duncan, OK to provide four lanes of Bois D'Arc Avenue at this location. " | Pavement Widening | 06/01/2009 | 06/01/2009 | 02/25/2010 | 4954000 | 0.44
8210 | Oklahoma | CARTER |  | 4 | STIM040 | "This project widens about 3 miles of US 70 from two lanes to four lanes east of the Jefferson County line west of Ardmore, OK. " | Pavement Improvement | 04/27/2009 | 04/27/2009 | 12/22/2009 | 5344000 | 3.08
8211 | Oklahoma | TULSA | TULSA | 1 | STIM047 | "This project is located on the north bound lanes of Interstate 244 beginning at the U.S. Highway 75 interchange extending north to the U.S. Highway 64 interchange (also referred to as the west leg of | Bridge Improvement | 06/08/2009 | 06/08/2009 | 01/08/2011 | 11850000 | 1.176
8212 | Oklahoma | TULSA | TULSA | 1 | STIM048 | "This project is located on the south bound lanes of Interstate 244 beginning at the U.S. Highway 75 interchange extending north to the U.S. Highway 64 interchange (also referred to as the west leg of | Bridge Improvement | 06/08/2009 | 06/08/2009 | 01/08/2011 | 19716000 | 1.124
8213 | Oklahoma | TULSA | TULSA | 1 | STIM049 | "This project is located on the east bound lanes of Interstate 244 beginning at the U.S. Highway 64 interchange extending east to the U.S. Highway 75 interchange (also referred to as the north leg of | Bridge Improvement | 06/08/2009 | 06/08/2009 | 01/08/2011 | 15100000 | 1.754
8214 | Oklahoma | TULSA | TULSA | 1 | STIM050 | "This project is located on the west bound lanes of Interstate 244 beginning at the U.S. Highway 64 interchange extending east to the U.S. Highway 75 interchange (also referred to as the north leg of | Bridge Improvement | 06/08/2009 | 06/08/2009 | 01/08/2011 | 18100000 | 1.751
8215 | Oklahoma | TULSA |  | 1 | STIM061 | "This project will replace the pavement approaching the State Highway 151 bridges over State Highway 51 and SL/SF railroad, replace the both deteriorated bridges and install new safety barriers. The | Bridge Replacement | 06/01/2009 | 05/27/2009 | 03/27/2010 | 6059000 | 0.25
8216 | Oklahoma | NOWATA |  | 2 | STIM062 | "This project will resurface 6.0 mile of U.S. Highway 169 beginning at the Kansas State Line by replacing 2 to 4 inches of existing asphalt with 4 inches of new asphalt which results in a smoother rid | Pavement Widening | 07/06/2009 | 07/23/2009 | 09/03/2009 | 3535000 | 6
8217 | Oklahoma | WOODS |  | 3 | STIM063 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 4.5 miles north of the Woods/Major County Line on US-281 and entends south 3.7 miles | Pavement Improvement | 07/06/2009 | 04/29/2009 | 08/24/2009 | 706900 | 3.7
8218 | Oklahoma | TEXAS |  | 3 | STIM064 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 5.3 miles southwest of the Junction with State Highway 94 on State Highway 54 and entends northeast 5. | Pavement Improvement | 07/22/2009 | 10/01/2009 |  | 1090729 | 5
8219 | Oklahoma | TEXAS |  | 3 | STIM065 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 9.8 miles northeast of the Texas State line on US 54 miles entends 1.6 miles to the Goodwell City limi | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/03/2009 | 807900 | 1.6
8220 | Oklahoma | TEXAS |  | 3 | STIM066 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 11.4 miles northeast of the Texas State line on US 54 miles entends 7.0 miles. | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/03/2009 | 1424500 | 7
8221 | Oklahoma | WOODS |  | 3 | STIM067 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 4.6 miles east of the Jct US-281 on State Highway 45 and entends east 3.5 miles. | Pavement Improvement | 07/06/2009 | 04/29/2009 | 08/24/2009 | 598700 | 3.5
8222 | Oklahoma | CUSTER |  | 3 | STIM069 | "This project resurfaces about 6 miles of US 183 north of Clinton, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 06/24/2009 | 08/28/2009 |  | 1197383 | 5.96
8223 | Oklahoma | CUSTER |  | 3 | STIM070 | "This project resurfaces about 5 miles of US 183 north of Clinton, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 06/24/2009 | 08/28/2009 |  | 938475 | 4.66
8224 | Oklahoma | JACKSON |  | 4 | STIM071 | "This project resurfaces about 8 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 06/01/2009 | 06/01/2009 | 09/08/2009 | 997900 | 7.7
8225 | Oklahoma | TILLMAN |  | 3 | STIM086 | "This project resurfaces about 4 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 06/01/2009 | 06/01/2009 | 09/08/2009 | 795600 | 3.92
8226 | Oklahoma | TILLMAN |  | 3 | STIM087 | "This project resurfaces about 7 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 06/01/2009 | 06/01/2009 | 09/08/2009 | 1463000 | 7.13
8227 | Oklahoma | ROGERS |  | 2 | STIM088 | This project extends the service life of the pavement by removing 2 inches of asphalt and placing 2 inches of new asphalt on U.S. Highway 412 beginning at the McClelan Kerr Navigation Channel extendin | Pavement Improvement | 07/06/2009 | 07/30/2009 | 10/03/2009 | 1378900 | 5.02
8228 | Oklahoma | OKFUSKEE |  | 2 | STIM093 | This project resurfaces about 8 miles of I-40 east of the Seminole County line to improve the smoothness of the road and to extend it's life. This project was reconstructed within existing right of wa | Pavement Improvement | 06/09/2009 | 08/31/2009 |  | 3380000 | 8
8229 | Oklahoma | POTTAWATOMIE |  | 5 | STIM095 | Asphalt pavement resurfacing for 7.72 miles on I-40 in Seminole County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 07/06/2009 | 05/18/2009 | 08/19/2009 | 1296700 | 7.72
8230 | Oklahoma | SEMINOLE |  | 5 | STIM096 | Resurface I-40 from the Pottawatomie county line going east about 6.5 miles. | Pavement Improvement | 07/06/2009 | 05/18/2009 | 08/19/2009 | 1086200 | 6.46
8231 | Oklahoma | MURRAY |  | 4 | STIM120 | This project resurfaces about 7 miles of I-35 north of the Carter County line to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 04/27/2009 | 05/26/2009 | 07/20/2009 | 4927000 | 6.56
8232 | Oklahoma | CARTER |  | 4 | STIM121 | "This project resurfaces about 8 miles of US 70 east of Ardmore, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 06/09/2009 | 11/09/2009 |  | 2915633 | 8
8233 | Oklahoma | ATOKA |  | 2 | STIM150 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 1.44 miles to 3.80 miles North of State Highway to repair deteriorating pavement section. | Pavement Improvement | 04/20/2009 | 04/21/2009 | 10/16/2009 | 640070 | 3.8
8234 | Oklahoma | BRYAN |  | 2 | STIM152 | Asphalt pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.21 miles to 5.26 miles North of Oklahoma-Texas State Line for Southbound and Northbound Lanes to repair det | Pavement Improvement | 07/06/2009 | 07/22/2009 | 09/18/2009 | 3992600 | 5.26
8235 | Oklahoma | CANADIAN |  | 3 | STIM153 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at Mile Marker 108 and entends to Mile Marker 115 on I-40 west of Oklahoma city | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/18/2009 | 1716300 | 7
8236 | Oklahoma | CANADIAN |  | 3 | STIM154 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at Mile Marker 115 and entends to Mile Marker 118 on I-40 west of Oklahoma city | Pavement Improvement | 07/06/2009 | 07/06/2009 | 09/18/2009 | 922650 | 4.2
8237 | Oklahoma | GARVIN |  | 4 | STIM156 | Asphalt pavement resurfacing for 8.01 miles on State Highway 76 in Garvin County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 07/06/2009 | 05/29/2009 | 08/09/2009 | 1128800 | 8.01
8238 | Oklahoma | HASKELL |  | 2 | STIM157 | "13.85 miles of 9.5"" thick of concrete patching and concrete surface smoothing at varies locations in Haskell county. These project were reconstructed within existing right of ways and no lanes were | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 242250 | 1.07
8239 | Oklahoma | MUSKOGEE |  | 2 | STIM158 | Concrete pavement reconstrcution of the driving lanes and shoulder along SH-2 beginning 14 miles north of Haskell County line and going north approximately 2 miles. | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 473800 | 1.75
8240 | Oklahoma | OKMULGEE |  | 2 | STIM159 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-75 beginning at I-40 and going north approximately 2.5 miles. | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 857500 | 2.44
8241 | Oklahoma | WAGONER |  | 1 | STIM163 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-69 beginning 0.5 miles north of SH-51 and going north approximately 8 miles. | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 1716800 | 7.84
8242 | Oklahoma | WAGONER |  | 1 | STIM164 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-69 beginning 1/4 miles south of SH-51 and going north approximately 1 mile. | Pavement Improvement | 04/27/2009 | 05/04/2009 | 11/22/2009 | 393800 | 0.75
8243 | Oklahoma | LE FLORE |  | 2 | STIM169 | "Roadway and Bridge Construction of driving lanes and shoulder on an offset alignment of along US Highway 59 from State Highway West to 5.26 miles North of Junction to increase the capacity and update | Pavement Widening | 09/08/2009 | 07/06/2009 | 11/01/2010 | 12000000 | 5
8244 | Oklahoma | HUGHES |  | 2 | STIM172 | Asphalt pavement resurfacing for 1.96 miles on U.S. Highway 270B in Hughes County. Part of this project include full depth concrete patching. This project was reconstructed within existing right of wa | Pavement Improvement | 07/06/2009 | 06/16/2009 | 08/04/2009 | 387000 | 1.96
8245 | Oklahoma | LINCOLN |  | 3 | STIM173 | "This project resurfaces about 8 miles of SH-105 in Lincoln County, OK between US-177 and SH-18 to improve the smoothness of the road and to extend it's life. This project was reconstructed within ex | Pavement Improvement | 07/06/2009 | 07/02/2009 | 08/04/2009 | 985000 | 7.97
8246 | Oklahoma | LINCOLN |  | 3 | STIM174 | Asphalt pavement resurfacing for 5.05 miles on State. Highway 18 in Lincoln County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 07/06/2009 | 07/13/2009 | 08/04/2009 | 487000 | 5.05
8247 | Oklahoma | MAYES |  | 2 | STIM175 | "This project will provide a smother ride and extend the service life of the pavement by rehabilitating the existing concrete pavement. Improvements include patching deteriorated sections, adding sup | Pavement Improvement | 06/01/2009 | 07/28/2009 | 09/28/2009 | 1871300 | 4.5
8248 | Oklahoma | NOBLE |  | 3 | STIM176 | Resurface both directions of I-35 starting about 1 mile north of the Payne county line and going north 6 miles. | Pavement Improvement | 07/06/2009 | 07/17/2009 | 08/19/2009 | 1255000 | 6
8249 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM177 | This project will extend the life of the pavement and significantly improves ride quality on 3.5 miles of I-235 in Oklahoma City by stabalizing the existing pavement. | Pavement Improvement | 04/27/2009 | 05/18/2009 | 07/25/2009 | 2532000 | 3.47
8250 | Oklahoma | PITTSBURG |  | 2 | STIM178 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.00 miles to 3.0 miles North of County Line for Southbound and Northbound Lanes to repair deteriorating pav | Pavement Improvement | 04/20/2009 | 04/21/2009 | 10/16/2009 | 1571640 | 3
8251 | Oklahoma | PITTSBURG |  | 2 | STIM179 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.30 miles to 4.65 miles North of Atoka County Line for Southbound Lanes and from 3.08 miles to 6.0 miles No | Pavement Improvement | 04/20/2009 | 04/21/2009 | 10/16/2009 | 2121700 | 4.65
8252 | Oklahoma | ROGERS |  | 2 | STIM180 | This project extends the service life of the pavement by removing 2 inches of asphalt and placing 3 inches of new asphalt on State Highway 266 beginning at State Highway 167 extending east approximate | Pavement Improvement | 07/06/2009 | 07/30/2009 | 10/03/2009 | 1008200 | 6
8253 | Oklahoma | SEMINOLE |  | 5 | STIM181 | Asphalt pavement resurfacing for 4.76 miles on State Highway 56 in Seminole County. Part of this project include full depth concrete patching. This project was reconstructed within existing right of w | Pavement Improvement | 07/06/2009 | 06/30/2009 | 09/03/2009 | 935000 | 4.76
8254 | Oklahoma | TILLMAN |  | 4 | STIM182 | "This project resurfaces about 4 miles of US 183 south of Frederick, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 07/06/2009 | 07/09/2009 | 08/04/2009 | 713900 | 4.05
8255 | Oklahoma | MAYES |  | 2 | STIM183 | This project will replace a deteriorated county bridge on EW-58 over Chouteau Creek located approximately 0.3 mile south and 2.3 miles east of Chouteau. | Bridge Replacement | 09/08/2009 | 09/29/2009 | 03/06/2010 | 980000 | 0.06
8256 | Oklahoma | MAYES |  | 2 | STIM184 | This project replaces a deteriorated bridge over Brushy Creek located approximately 2.2 miles south and 2.5 miles west of the U.S. Highway 412/69 junction. | Bridge Replacement | 09/08/2009 | 10/05/2009 | 01/05/2010 | 290000 | 0.02
8257 | Oklahoma | TULSA |  | 1 | STIM185 | This project replaces a deteriorated county bridge over Delaware Creek overflow on Cincinnati Avenue located 0.5 mile south of 86th Street North in Tulsa. | Bridge Replacement | 08/03/2009 | 08/03/2009 | 01/29/2010 | 900000 | 0.4
8258 | Oklahoma | WASHINGTON |  | 1 | STIM186 | This project will replace a low water crossing on N-401 over Unnamed Creek located 0.6 miles south and 4.2 miles east of the U.S. Highway 75/ Kansas Border junction. | Bridge Replacement | 08/03/2009 | 07/24/2009 | 03/30/2010 | 636000 | 0.02
8259 | Oklahoma | WASHINGTON |  | 1 | STIM187 | This project will replace a low water crossing with a new bridge on N-400 over Brush Creek located approximately 0.8 mile south and 2.0 miles east of the U.S. Highway / State Highway 10 junction. | New Bridge Construction | 08/03/2009 | 07/24/2009 | 03/30/2010 | 480000 | 0.2
8260 | Oklahoma | ADAIR |  | 2 | STIM188 | Construct a new bridge on Peavine Road about 4 miles north of junction US-59/SH-51. Additional right of way was acquired to construct this project. | New Bridge Construction | 09/08/2009 | 09/08/2009 | 01/25/2010 | 584000 | 0.25
8261 | Oklahoma | CHEROKEE |  | 2 | STIM189 | Replace the bridge over the Telmay Hollow creek in Cherokee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 08/03/2009 | 07/27/2009 | 10/31/2009 | 288000 | 0.23
8262 | Oklahoma | MCINTOSH |  | 2 | STIM190 | Replace the bridge over the Flat Rock creek creek in McIntosh county. Additional right of way was acquired to construct this project. | Bridge Replacement | 09/08/2009 | 08/10/2009 | 12/06/2009 | 335000 | 0.25
8263 | Oklahoma | MUSKOGEE |  | 2 | STIM191 | Replace the bridge over Cloud creek north and east of Boyton in Muskogee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 11/30/2009 | 11/30/2009 | 04/28/2010 | 438449 | 0.365
8264 | Oklahoma | OKMULGEE |  | 2 | STIM192 | Replace the bridge over the unnamed creek creek that is about 4 miles east and 2 miles north of US-75 in Okmulgee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 09/08/2009 | 07/13/2009 | 01/05/2010 | 320000 | 0.2
8265 | Oklahoma | SEQUOYAH |  | 2 | STIM193 | Construct a new bridge over the Prairie Creek just south and west of Akins in Sequoyah county. Additional right of way was acquired to construct this project. | New Bridge Construction | 12/07/2009 | 09/08/2009 | 04/05/2010 | 300000 | 0.25
8266 | Oklahoma | WAGONER |  | 1 | STIM194 | Replace the bridge 1 mile north and 4 miles west of the junction of US-69 and SH-51 in Wagoner county. Additional right of way was acquired to construct this project. | Bridge Replacement | 08/03/2009 | 07/22/2009 | 10/31/2009 | 220000 | 0.125
8267 | Oklahoma | BRYAN |  | 2 | STIM195 | County Bridge Constrcution of the driving lanes and shoulders over Island Bayou and Island Bayou Tributaries located 2.60 miles North of State Highway 78 on NS 380 Section Line Road to replace a struc | Bridge Replacement | 08/03/2009 | 08/17/2009 | 11/30/2009 | 558000 | 0.4
8268 | Oklahoma | BRYAN |  | 2 | STIM196 | County Bridge Constrcution of the driving lanes and shoulders over Red Ranch Creek located 1.00 miles North and 1.50 miles East of the Town of Smith-Lee to replace a strucutrally defecient or obsolete | Bridge Replacement | 08/03/2009 | 08/17/2009 | 11/30/2009 | 381000 | 0.3
8269 | Oklahoma | LATIMER |  | 2 | STIM197 | County Bridge Constrcution of the driving lanes and shoulders over Peachland Creek located 0.70 miles North and 2.00 miles West of the Town of Bengal to replace a strucutrally defecient or obsolete lo | Bridge Replacement | 08/03/2009 | 08/14/2009 | 11/30/2009 | 535000 | 0.2
8270 | Oklahoma | LE FLORE |  | 2 | STIM198 | County Bridge Constrcution of the driving lanes and shoulders over Fourche Maline Creek located 1.50 miles North and 2.30 miles East of the Town of LeFLore to replace a strucutrally defecient or obso | Bridge Replacement | 10/05/2009 | 06/10/2009 | 03/03/2010 | 1000376.12 | 0.5
8271 | Oklahoma | PITTSBURG |  | 2 | STIM199 | County Bridge Constrcution of the driving lanes and shoulders over Unnamed Creek located 2.00 miles North and 3.70 miles West of the Town of Quinton to replace a strucutrally defecient or obsolete loc | Bridge Replacement | 10/05/2009 | 06/25/2009 | 02/01/2010 | 329623.88 | 0.3
8272 | Oklahoma | COAL |  | 2 | STIM200 | Replace the bridge over Coal Creek thats about 2 miles east and 2 miles south of Lehigh | Bridge Replacement | 08/03/2009 | 08/03/2009 | 01/29/2010 | 295400 | 0.2
8273 | Oklahoma | COAL |  | 2 | STIM201 | Replace the bridge over the tributary to Keel Creek that is about 8 miles north and 7 miles east of Coalgate. | Bridge Replacement | 08/03/2009 | 08/03/2009 | 01/29/2010 | 162000 | 0.2
8274 | Oklahoma | HUGHES |  | 2 | STIM202 | Replace the bridge over the Big creek that is about 4 miles east of Allen in Hughes county. Additional right of way was acquired to construct this project. | Bridge Replacement | 09/08/2009 | 08/17/2009 | 01/05/2010 | 429292 | 0.3
8275 | Oklahoma | LINCOLN |  | 3 | STIM203 | Replace the bridge over the Spring creek about a mile west of US-177 junction SH-66 in Lincoln county. Additional right of way was acquired to construct this project. | Bridge Replacement | 08/03/2009 | 08/03/2009 | 11/30/2009 | 259200 | 0.3
8276 | Oklahoma | OKFUSKEE |  | 2 | STIM204 | Replace the bridge over the Harrican creek that is about 3 miles south of Micawber in Okfuskee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 08/03/2009 | 06/05/2009 | 11/30/2009 | 401400 | 0.24
8277 | Oklahoma | PONTOTOC |  | 4 | STIM205 | Replace the bridge over the Grayson Creek that is about 2 miles south and 7 miles east of SH-59a junction SH-3w. | Bridge Replacement | 09/08/2009 | 09/01/2009 | 04/05/2010 | 387159 | 0.02
8278 | Oklahoma | PONTOTOC |  | 4 | STIM206 | Replace the bridge over the Mill creek that is about 0.5 miles north and 2 miles east of Fittstown. Additional right of way was acquired to construct this project. | Bridge Replacement | 09/08/2009 | 09/01/2009 | 04/05/2010 | 275105 | 0.02
8279 | Oklahoma | POTTAWATOMIE |  | 5 | STIM207 | "Replace the bridge over the Popshego creek that is about 3 miles east of St. Louis, Oklahoma. Additional right of way was acquired to construct this project." | Bridge Replacement | 09/08/2009 | 09/09/2009 | 01/05/2010 | 491743 | 0.02
8280 | Oklahoma | GARVIN |  | 4 | STIM208 | Replace the bridge over the unnamed creek that is about 3.5 miles north of SH-7. | Bridge Replacement | 08/03/2009 | 07/01/2009 | 11/30/2009 | 544000 | 0.3
8281 | Oklahoma | LOGAN |  | 3 | STIM209 | Replace the bridge on EW-81 over Blue Creek about 4 miles west of Meridian. | Bridge Replacement | 08/03/2009 | 07/01/2009 | 11/30/2009 | 400000 | 0.21
8282 | Oklahoma | MURRAY |  | 4 | STIM210 | Replace the bridge over Guy Sandy Creek that is about 8 miles north and a mile west of Sulphur in Murray County. | Bridge Replacement | 10/05/2009 | 10/05/2009 | 02/01/2010 | 600000 | 0.25
8283 | Oklahoma | PAYNE |  | 3 | STIM211 | Replace the bridge over Clear Creek that is about 2 miles east and 7 miles south of the junction of I-35 and SH-51 | Bridge Replacement | 08/03/2009 | 07/21/2009 | 10/31/2009 | 400000 | 0.25
8284 | Oklahoma | CANADIAN |  | 3 | STIM212 | This project installs a new bridge and approaches on a county bridge 3.9 miles west and 1 mile south of Piedmont | Bridge Replacement | 08/03/2009 | 06/12/2009 | 12/30/2009 | 462972 | 0.2
8285 | Oklahoma | CANADIAN |  | 3 | STIM213 | This project installs a new box culvert and approaches on a county road 2 miles north and 3.6 mile east of Geary | Bridge Replacement | 08/03/2009 | 06/12/2009 | 12/30/2009 | 166877 | 0.2
8286 | Oklahoma | COTTON |  | 4 | STIM214 | "This project replaces the deficient county bridge over East Cache Creek near Walters, OK. " | Bridge Replacement | 08/03/2009 | 07/20/2009 | 11/30/2009 | 239425 | 0.25
8287 | Oklahoma | JEFFERSON |  | 4 | STIM215 | "This project replaces the deficient county bridge over Mud Creek near Ringling, OK. " | Bridge Replacement | 08/03/2009 | 05/29/2009 | 12/30/2009 | 477024 | 0.25
8288 | Oklahoma | LOVE |  | 2 | STIM216 | This project replaces a low water crossing with a new bridge over Simon Creek northeast of the intersection of State Highways 76 and 32. | New Bridge Construction | 08/03/2009 | 08/11/2009 | 12/30/2009 | 519881 | 0.12
8289 | Oklahoma | STEPHENS |  | 4 | STIM217 | "This project replaces the deficient county bridge over Deer Creek southeast of Comanche, OK. " | Bridge Replacement | 10/05/2009 | 09/08/2009 | 05/02/2010 | 382956 | 0.01
8290 | Oklahoma | STEPHENS |  | 4 | STIM218 | "This project replaces the deficient county bridge over Stage Stand Creek southwest of Duncan, OK. " | Bridge Replacement | 10/05/2009 | 09/08/2009 | 05/02/2010 | 452164 | 0.01
8291 | Oklahoma | BECKHAM |  | 3 | STIM219 | "This project replaces a deficient county bridge over Buffalo Creek located about 7.5 miles north of Erick, OK. " | Bridge Replacement | 08/03/2009 | 08/03/2009 | 11/30/2009 | 709380.4 | 0.01
8292 | Oklahoma | CUSTER |  | 3 | STIM220 | "This project replaces the deficient county bridge over Barnitz Creek northwest of Clinton, OK. " | Bridge Replacement | 08/03/2009 | 08/03/2009 | 10/31/2009 | 465500 | 0.2
8293 | Oklahoma | DEWEY |  | 3 | STIM221 | "This project replaces the deficient county bridge over the South Canadian River northwest of Oakwood, OK. " | Bridge Replacement | 10/05/2009 | 09/16/2009 | 04/02/2010 | 1726572 | 0.379
8294 | Oklahoma | GREER |  | 3 | STIM222 | "This project replaces the deficient county bridge over Unnamed Creek southwest of Willow, OK. " | Bridge Replacement | 10/05/2009 | 08/12/2009 | 01/02/2010 | 348518.43 | 0.01
8295 | Oklahoma | TILLMAN |  | 4 | STIM223 | "This project replaces the deficient county bridge over Deep Red Creek southeast of Loveland, OK. " | Bridge Replacement | 08/03/2009 | 07/28/2009 | 11/30/2009 | 442728.6 | 0.2
8296 | Oklahoma | ALFALFA |  | 3 | STIM224 | This project resurfaces the existing asphalt pavement with and asphalt overlay on county road ( NS-271) 1.0 miles west Goltry and extends north 2.1 miles | Pavement Improvement | 08/03/2009 | 07/06/2009 | 10/01/2009 | 468364 | 2.2
8297 | Oklahoma | BEAVER |  | 3 | STIM225 | This project installs a new bridge and approaches on a county road ( NS-146) 7.0 miles east and 3.5 miles south of Elmwood | Bridge Replacement | 08/03/2009 | 07/28/2009 | 03/30/2010 | 496040 | 0.2
8298 | Oklahoma | CIMARRON |  | 3 | STIM226 | This project rehabitates the existing bridge over the Beaver River on a county road ( NS-13) 1.2 miles north of Felt | Bridge Improvement | 08/03/2009 | 08/03/2009 | 10/31/2009 | 267370 | 0.01
8299 | Oklahoma | GARFIELD |  | 3 | STIM227 | This project installs a new bridge and approaches on a county road ( NS-188) 0.6 miles north and 6.6 miles east of Waukomis | Bridge Replacement | 08/03/2009 | 07/06/2009 | 12/30/2009 | 539870 | 0.25
8300 | Oklahoma | GRANT |  | 3 | STIM228 | This project installs a new bridge and approaches on a county bridge over Sand Creek 1.0 miles north and 1.5 miles east of the junction with State Highway 11 and State Highway 132. | Bridge Replacement | 08/03/2009 | 09/01/2009 | 12/30/2009 | 516378 | 0.25
8301 | Oklahoma | GRANT |  | 3 | STIM229 | This project resurfaces the existing asphalt pavement with and asphalt overlay on a county road 5.3 miles south of Pond Creek and extends north 5.3 miles | Pavement Improvement | 08/03/2009 | 08/06/2009 | 11/30/2009 | 50000 | 5.3
8302 | Oklahoma | KINGFISHER |  | 3 | STIM230 | This project installs a new bridge and reconstruct the roadway approaches on a county bridge 4.5 miles west State Highway74F in Cashion | Bridge Replacement | 08/03/2009 | 09/08/2009 | 12/30/2009 | 571545 | 0.2
8303 | Oklahoma | NOBLE |  | 3 | STIM231 | This project installs a new bridge and approaches on county road over Red Rock Creek 4.5 miles west of the Junction with US 77 and State Highway 15 | Bridge Replacement | 08/03/2009 | 07/09/2009 | 12/30/2009 | 765687 | 0.2
8304 | Oklahoma | BEAVER |  | 3 | STIM232 | This project installs a new bridge and approaches on county road over Bull Creek 3.0 miles west and 3.4 miles north of the junction with State Highway 3 and US 83 at Byran Corner | Bridge Replacement | 08/03/2009 | 07/28/2009 | 03/30/2010 | 439600 | 0.1
8305 | Oklahoma | PITTSBURG |  | 2 | STIM233 | Embankment Stablization and Asphalt Paving reconstrcution of the driving lanes and shoulder along local road and bridge approach causeway over Lake Eufaulat o repair embankment sloughing and pavement | Pavement Widening | 02/01/2010 | 10/26/2009 | 08/29/2010 | 450000 | 0.1
8306 | Oklahoma | CANADIAN | OKLAHOMA CITY | 3 | STIM235 | This project installs a new bridge and approaches on county road over a unnamed creek 15.0 miles east and 7.0 miles south of Okarche | Bridge Replacement | 12/07/2009 | 11/18/2009 | 03/06/2010 | 225000 | 0.25
8307 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM236 | Installation of traffic signals and signal interconnection on 24th West Avenue beginning at State Highway 9 extending North to Tecumseh Road in Norman. | Safety/Traffic Management | 08/03/2009 | 08/03/2009 | 10/01/2009 | 598663 | 0.01
8308 | Oklahoma | NOBLE |  | 3 | STIM237 | This project resurfaces and widens the existing asphalt pavement with an concrete overlay The project starts at Mile Marker 198 and entends to Mile Marker 203 on I-35 north of Perry | Pavement Widening | 09/08/2009 | 08/10/2009 | 12/21/2010 | 8474000 | 5
8309 | Oklahoma | CANADIAN |  | 3 | STIM238 | This project resurfaces the existing asphalt pavement with a Ultrathin MicroSurfacing preventive maintenance treatment The project starts at at the Kingfisher County Line on State Highway 3 east of Ok | Pavement Improvement | 06/05/2009 | 08/31/2009 |  | 2500000 | 15.54
8310 | Oklahoma | GARFIELD |  | 3 | STIM239 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the Major County Line on US 60 and extends east 5.0 miles toward Enid | Pavement Improvement | 06/05/2009 | 08/10/2009 |  | 2201741 | 5
8311 | Oklahoma | WASHITA |  | 3 | STIM240 | "This project widens 2.5 miles of US 183 from two lanes to four lanes just south of Cordell, OK. " | Pavement Widening | 08/03/2009 | 08/03/2009 | 01/19/2010 | 3781000 | 2.5
8312 | Oklahoma | BLAINE |  | 3 | STIM241 | "This project resurfaces about 8 miles of US 270 west of Watonga, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 05/29/2009 | 08/19/2009 |  | 2778000 | 7.9
8313 | Oklahoma | TULSA | TULSA | 1 | STIM263 | Reconstruct, widen, and replace traffic signals at the intersection of E 131ST STREET & MEMORIAL | Safety/Traffic Management | 08/02/2010 |  | 04/28/2011 | 908199 | 0.3
8314 | Oklahoma | TULSA | TULSA | 1 | STIM264 | Resurface Elm Place from New Orleans St. to Florence St. | Pavement Improvement | 02/01/2010 | 02/01/2010 | 06/30/2010 | 812315 | 1
8315 | Oklahoma | TULSA | TULSA | 1 | STIM265 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt at the intersection of Elm Place and Houston Street in Broken Arrow. The | Pavement Improvement | 02/01/2010 | 02/01/2010 | 06/30/2010 | 222405 | 0.25
8316 | Oklahoma | TULSA | TULSA | 1 | STIM266 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Kenosha Street from Main Street to Sixth Street in Broken Arrow. This | Pavement Improvement | 02/01/2010 | 11/16/2009 | 05/31/2010 | 242578 | 0.5
8317 | Oklahoma | TULSA | TULSA | 1 | STIM267 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Kenosha Street from Hickory Court to Aspen Avenue in Broken Arrow. The | Pavement Improvement | 02/01/2010 | 11/16/2009 | 05/31/2010 | 295984 | 0.5
8318 | Oklahoma | TULSA | TULSA | 1 | STIM268 | Resurface intersection of 9th Street and Houston Street | Pavement Improvement | 02/01/2010 | 02/01/2010 | 06/30/2010 | 198538 | 0.25
8319 | Oklahoma | TULSA | TULSA | 1 | STIM269 | Installation of traffic signals at the intersection of Albany Street and Stone Ridge Drive in Broken Arrow. | Safety/Traffic Management | 01/04/2010 | 03/15/2010 | 04/03/2010 | 106331 | 0.125
8320 | Oklahoma | TULSA | TULSA | 1 | STIM270 | Installation of traffic signals at the intersection of New Orleans and 9th Street in Broken Arrow. | Safety/Traffic Management | 01/04/2010 | 03/15/2010 | 04/03/2010 | 88505 | 0.125
8321 | Oklahoma | TULSA | TULSA | 1 | STIM271 | Installation of traffic signals at the intersection of Elm Place and Stonewood Drive in Broken Arrow. | Safety/Traffic Management | 01/04/2010 | 03/15/2010 | 04/03/2010 | 105921 | 0.01
8322 | Oklahoma | ROGERS | TULSA | 1 | STIM272 | Installation of traffic signals at the intersection of Cherokee and South School Access in Catoosa. | Safety/Traffic Management | 02/01/2010 | 04/21/2010 | 05/31/2010 | 149975 | 0.125
8323 | Oklahoma | WAGONER | TULSA | 1 | STIM273 | Installation of traffic signals at the intesection of 141st Street and State Highway 51 in Coweta. | Safety/Traffic Management | 02/01/2010 | 06/11/2010 | 05/01/2010 | 9653 | 0.125
8324 | Oklahoma | WAGONER | TULSA | 1 | STIM274 | Resurface 151st St. from Division to SH-72 | Pavement Improvement | 02/01/2010 | 06/11/2010 | 05/01/2010 | 34507 | 0.25
8325 | Oklahoma | CREEK | TULSA | 1 | STIM275 | "GRADE, DRAIN & SURFACE WEST 81ST STREET SOUTH FROM SH-66 WEST TO FRANKHOMA ROAD" | Pavement Widening | 08/02/2010 |  | 01/28/2011 | 671260.9 | 1
8326 | Oklahoma | TULSA | TULSA | 1 | STIM276 | RESURFACE 5TH STREET OVERLAY | Pavement Improvement | 04/19/2010 | 05/25/2010 | 06/02/2010 | 120650 | 0.5
8327 | Oklahoma | TULSA | TULSA | 3 | STIM278 | This project will resurface the pavement of Airport Access Road from Euchee Creek Boulevard to West Shellcreek Road in Sand Springs by placing 2 to 2-3/4 inches of new asphalt which results in a smoot | Pavement Improvement | 10/05/2009 | 10/05/2009 | 11/18/2009 | 472877 | 3
8328 | Oklahoma | CREEK | TULSA | 3 | STIM279 | This project will remove and replace the 6 inch concrete pavement on East Line Street from Mission Street to Moccasin Place in Sapulpa. | Pavement Improvement | 11/02/2009 | 11/03/2009 | 03/01/2010 | 450828 | 0.5
8329 | Oklahoma | TULSA | TULSA | 1 | STIM281 | This project includes pavement and driveway repairs and will resurface the pavement to Mohawk Boulevard from Cincinnati Avenue to Hartford Avenue in Tulsa by placing 2 inches of new asphalt. The proj | Pavement Improvement | 10/05/2009 | 10/05/2009 | 02/01/2010 | 687730 | 0.5
8330 | Oklahoma | TULSA | TULSA | 1 | STIM282 | Pavement reconstruction and drainage improvements on Yale Avenue from Admiral Place to Pine Street in Tulsa. | Pavement Improvement | 01/04/2010 | 02/08/2010 | 08/01/2010 | 1195167 | 1
8331 | Oklahoma | TULSA | TULSA | 1 | STIM283 | "This project includes full depth concrete repairs and complete concrete pavement replacement on Southwest Boulevard from 23rd Street South to the Arkansas River Bridge in Tulsa. This project also re | Pavement Improvement | 11/30/2009 | 11/30/2009 | 09/25/2010 | 1940282 | 0.75
8332 | Oklahoma | TULSA | TULSA | 1 | STIM284 | This project will extend the service life of the pavement by removing 2-3/4 inches of asphalt and placing 3 inches of new asphalt on Sheridan Road from 111th Street South to Admiral Boulevard in Tulsa | Pavement Improvement | 01/04/2010 | 02/02/2010 | 03/29/2011 | 1371058 | 1
8333 | Oklahoma | TULSA | TULSA | 1 | STIM285 | "This project improves safety by adding paved shoulders and will extend the service life of the pavement by removing 3"" of existing asphalt and placing 3"" of new asphalt pavement. The project is lo | Pavement Improvement | 03/15/2010 | 04/14/2010 | 12/24/2010 | 718372 | 0.35
8334 | Oklahoma | TULSA | TULSA | 1 | STIM286 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Sheridan Road from 11th Street South to 21st Street South in Tulsa. Th | Pavement Improvement | 01/04/2010 | 02/02/2010 | 03/29/2011 | 1434857 | 1
8335 | Oklahoma | TULSA | TULSA | 1 | STIM287 | This project will extend the service life of the pavement and makes driveway repairs to East 31st Street South from just west of South 132nd East Avenue to just east of South 140th East Avenue in Tuls | Pavement Improvement | 10/05/2009 | 10/05/2009 | 04/02/2010 | 516454 | 1
8336 | Oklahoma | TULSA | TULSA | 1 | STIM288 | "This project will extend the service life of the pavement by removing 3-1/2"" of existing asphalt and placing 3"" of new asphalt pavement. The project also includes bridge deck repairs, upgrades an | Pavement Improvement | 01/11/2010 | 01/11/2010 | 11/06/2010 | 1374172 | 1
8337 | Oklahoma | TULSA | TULSA | 1 | STIM289 | "This project removes and replaces the existing pavement on East 41st Street from Interstate 44 to Sheridan Road and South Yale Avenue from 31st Street South to 36st Street South in Tulsa. The projec | Pavement Improvement | 01/11/2010 | 01/11/2010 | 09/07/2010 | 1841843 | 0.75
8338 | Oklahoma | OSAGE |  | 3 | STIM290 | This project will extend the service life of the pavement by placing 3 inches of new asphalt pavement on U.S. Highway 60 beginning 0.75 mile east of the Osage/Kay County Line extending east 4.44 miles | Pavement Improvement | 07/06/2009 | 07/01/2009 | 07/28/2009 | 1240000 | 4.44
8339 | Oklahoma | OSAGE |  | 3 | STIM291 | This project will extend the service life of the pavement by removing 1 inch of asphalt pavement and placing 2 inches of new asphalt pavement on State Highway 99 beginning 0 .86 mile north of the Stat | Pavement Improvement | 07/06/2009 | 06/24/2009 | 08/05/2009 | 670000 | 4.17
8340 | Oklahoma | PAWNEE |  | 3 | STIM293 | "This project will extend the service life of the pavement by patching the existing concrete pavement, installing supports at the joints, and grinding the surface to provide a smooth ride on U.S. High | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/14/2009 | 2108340 | 7.65
8341 | Oklahoma | PAWNEE |  | 3 | STIM294 | "This project will extend the service life of the pavement by patching the existing concrete pavement, installing supports at the joints, and grinding the surface to provide a smooth ride on U.S. High | Pavement Improvement | 08/17/2009 | 08/17/2009 | 12/14/2009 | 1141660 | 6.7
8342 | Oklahoma | MUSKOGEE |  | 2 | STIM295 | Asphalt pavement resurfacing for 2.77 miles on I-40 in Muskogee County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 06/05/2009 | 08/24/2009 |  | 2360000 | 4.39
8343 | Oklahoma | COMANCHE | LAWTON | 4 | STIM296 | "This project repairs 5 bridges, reconstructs deteriorated pavement, and improves safety features for about 2.5 miles of I-44 in Lawton, OK. " | Pavement Improvement | 08/24/2009 | 08/24/2009 | 08/18/2010 | 14217384 | 1.52
8344 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM297 | Resurface Rockwell Ave from NW 16th to NW 23rd and resurface NW 36th from Rockwell to Hammond | Pavement Improvement | 02/18/2010 | 03/23/2010 |  | 414237 | 1
8345 | Oklahoma | MCCLAIN | OKLAHOMA CITY | 4 | STIM298 | RESURFACE BLANCHARD ARRA: FROM SH-76 TO COUNTY LINE ROAD | Pavement Improvement | 04/26/2010 | 04/27/2010 | 05/25/2010 | 211712 | 0.9
8346 | Oklahoma | CIMARRON |  | 3 | STIM299 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the Junction with US 287 and extends east 7.5 miles on US 412 | Pavement Improvement | 06/09/2009 | 07/28/2009 |  | 2150000 | 7.5
8347 | Oklahoma | LOGAN | OKLAHOMA CITY | 3 | STIM300 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the on County Line road in the Cashion Area and extends from Seward Road to Forest Hill Road | Pavement Improvement | 09/28/2009 | 09/28/2009 | 12/11/2009 | 176426 | 1
8348 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM301 | RESURFACE NE 23RD FROM HENNEY RD TO CHOCTAW RD | Pavement Improvement | 07/26/2010 | 07/26/2010 | 09/08/2010 | 323286 | 0.01
8349 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM302 | Resurface Etowah road from 108th Ave to 180th Ave SE. | Pavement Improvement | 08/12/2009 | 08/31/2009 |  | 587297 | 6
8350 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 4 | STIM303 | "This project will resurface 1.75 miles of road in Del City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 02/01/2010 | 11/23/2009 | 03/02/2010 | 262802 | 1.75
8351 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM304 | "RESURFACE EDMOND ARRA: MULTIPLE LOCATIONS ON KELLY AVE, DANFORTH, EDMOND RD & 15TH STREET" | Pavement Improvement | 05/04/2010 | 05/24/2010 |  | 1779176 | 4.7
8352 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM305 | This project will resurface 1 mile of road in the vicinity of Forrest Park in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 | 03/17/2010 | 05/09/2010 | 147302 | 1
8353 | Oklahoma | LOGAN | OKLAHOMA CITY | 3 | STIM306 | Resurface Coltrane rodade from Seward road to Lakeshore Drive. | Pavement Improvement | 04/01/2010 |  | 04/30/2010 | 271669 | 1.5
8354 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM307 | Resurface Reno Avenue from Harrah Road to Pottawatomie Road | Pavement Improvement | 04/05/2010 | 03/15/2010 | 05/19/2010 | 197078 | 1.5
8355 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM308 | This project will resurface 1.5 miles of Main Street in Jones to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 | 03/17/2010 | 05/09/2010 | 131157 | 1.5
8356 | Oklahoma | LOGAN | OKLAHOMA CITY | 3 | STIM309 | Resurface Pensylvania avenue from Oklahoma Couty line north into logan county | Pavement Improvement | 09/28/2009 | 09/28/2009 | 12/11/2009 | 443708 | 1.7
8357 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 4 | STIM400 | Resurface multiple locations in Midwest City on SE 29th and NE 10th. | Pavement Improvement | 07/12/2010 | 07/20/2010 | 11/28/2010 | 239175 | 2
8358 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM401 | Resurface Janeway and Santa Fe from NW 12th to NW 27th | Pavement Improvement | 08/12/2009 | 08/31/2009 |  | 612303 | 2
8359 | Oklahoma | CANADIAN | OKLAHOMA CITY | 4 | STIM403 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts is on N Sara Rd in Mustang and extends from State Highwy 152 to SW 59th Street and South Mustage Fronta | Pavement Improvement | 08/19/2009 | 10/16/2009 |  | 279620 | 2
8360 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM404 | TRAFFIC SIGNALS NE 23RD AT NICHOLS (TRAFFIC SIGNALS) | Transportation Enhancements | 07/26/2010 | 07/26/2010 | 08/25/2010 | 71467 | 0.01
8361 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM405 | This project will resurface 1 mile of road in the vicinity of Nicoma Park in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 | 03/17/2010 | 05/09/2010 | 61197 | 1
8362 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM406 | Resurface Etowah road from 48th Ave SE to US-77 | Pavement Improvement | 04/05/2010 | 03/22/2010 | 05/04/2010 | 191548 | 2.5
8363 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM407 | "Asphalt pavement resurfacing of portions of Eufaula Street, Flood Avenue, Jenkins Avenue, Lindsey Street, Porter Avenue, and University Boulevard in Cleveland County. This project was reconstructed w | Pavement Improvement | 08/12/2009 | 08/31/2009 |  | 1272437 | 3.74
8364 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM408 | "This project will resurface 5 miles of Memorial Road through north east Oklahoma City and Edmond to improve ride quality and extend the life of the pavement. In addition, new curb ramps will be insta | Pavement Improvement | 08/13/2009 | 08/24/2009 |  | 1355644 | 5
8365 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM409 | "This project will resurface 8 miles of road in north west Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 10/05/2009 | 10/05/2009 | 12/18/2009 | 3189188 | 8
8366 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM410 | "This project will resurface 1.7 miles of road in north west Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 08/19/2009 | 08/31/2009 |  | 652692 | 1.7
8367 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM411 | "This project will resurface 3 miles of May Avenue in south Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 08/19/2009 | 08/31/2009 |  | 966992 | 3
8368 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM412 | "This project will resurface 3.5 miles of Shields Boulevard in south Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 07/27/2009 | 07/20/2009 | 11/23/2009 | 1514850 | 3.5
8369 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM413 | Resurface multiple locations on Penn and May in the areas of SW 89th and SW 119th. | Pavement Improvement | 07/27/2009 | 07/20/2009 | 11/23/2009 | 1416273 | 5
8370 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM414 | "This project will resurface 6 miles of road in Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 09/28/2009 | 09/15/2009 | 11/26/2009 | 2202725 | 6
8371 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM415 | This project will resurface 6.3 miles of Midwest Boulevard in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 | 03/17/2010 | 05/09/2010 | 2250617 | 6.3
8372 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM416 | This project will resurface 3 miles of road north of Luther to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 | 03/17/2010 | 05/09/2010 | 522272 | 3
8373 | Oklahoma | CANADIAN | OKLAHOMA CITY | 3 | STIM417 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts is on Piedmont Rd in Mustang and extends from Arrowhead Road to Apache Street. | Pavement Improvement | 07/27/2009 | 08/03/2009 | 08/26/2009 | 188523 | 1
8374 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 4 | STIM418 | This project will resurface 1 mile of road south of Spencer to improve ride quality and extend the life of the pavement. | Pavement Improvement | 10/12/2009 | 03/17/2010 | 05/09/2010 | 118461 | 1
8375 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM419 | "This project will resurface 1 mile of Penn Avenue in the city of Village to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 08/19/2009 | 08/31/2009 |  | 278129 | 1
8376 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM420 | "This project will resurface 0.5 mile of road in the city of Warr Acres to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramp " | Pavement Improvement | 02/01/2010 | 02/01/2010 | 03/02/2010 | 117535 | 0.5
8377 | Oklahoma | CANADIAN | OKLAHOMA CITY | 3 | STIM421 | Resurface Cornwell from NW10th to Vandement. | Pavement Improvement | 05/03/2010 | 05/03/2010 | 08/30/2010 | 676877 | 1
8378 | Oklahoma | TULSA | TULSA | 1 | STIM422 | This project will extend the service life of the pavement by removing 2 inches of asphalt and placing 2 inches of new asphalt on East 2nd Street from Main Street to Adams Street in Sand Springs. | Pavement Improvement | 10/05/2009 | 10/05/2009 | 11/18/2009 | 185046 | 0.5
8379 | Oklahoma | MCCLAIN | OKLAHOMA CITY | 4 | STIM423 | Redeck and rehabilitation of US-62 bridge and approaches over H.E. Bailey Turnpike (I-44) in McClain County. This project was reconstructed within existing right of ways and no lanes were added. | Bridge Improvement | 03/01/2010 | 03/01/2010 | 04/29/2010 | 225000 | 0.01
8380 | Oklahoma | MCCLAIN | OKLAHOMA CITY | 4 | STIM424 | Installation of traffic signals on U.S. Highway 77 at the intesections of State Highway 74 and State Highway 39. | Safety/Traffic Management | 02/08/2010 | 02/08/2010 | 05/08/2010 | 170026 | 0.01
8381 | Oklahoma | GRADY | OKLAHOMA CITY | 4 | STIM425 | INTERSECTION MOD. & TRAF. SIGNALS TUTTLE ARRA: INTERSECTION OF SH-37 & CIMARRON ROAD | Transportation Enhancements | 05/03/2010 | 04/28/2010 | 07/16/2010 | 225000 | 0.01
8382 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 4 | STIM427 | Resurface SE 15th from Douglas Blvd to Post Road. | Pavement Improvement | 05/03/2010 | 05/04/2010 | 06/01/2010 | 351192 | 1
8383 | Oklahoma | CIMARRON |  | 3 | STIM428 | This project reconstructs the existing pavement with a new asphalt pavement. The project starts 7.0 miles south of the juncton with US 64 on US 287 and extends 0.8 miles | Pavement Improvement | 08/17/2009 | 08/26/2009 | 02/12/2010 | 2084606 | 0.83
8384 | Oklahoma | LOGAN |  | 3 | STIM429 | This project installs a new bridge and approaches on a county bridge over Wof Creek 2.0 miles north and 2.2 miles east of the junction with State Highway 74 and State Highway 74C. | Bridge Replacement | 10/28/2009 | 11/30/2009 | 04/03/2010 | 172636 | 0.25
8385 | Oklahoma | MURRAY |  | 4 | STIM430 | "This project replaces the deficient county bridge over Eight Mile Creek near Hennepin, OK. " | Bridge Replacement | 12/07/2009 | 11/30/2009 | 04/05/2010 | 247000 | 0.25
8386 | Oklahoma | ALFALFA |  | 3 | STIM431 | This project installs a new bridge and approaches on a county bridge over West Clay Creek on county road( NS 262) 1.0 miles east and 2.7 miles north of SH-8 junction with US-64 | Bridge Replacement | 01/05/2010 | 01/05/2010 | 05/04/2010 | 519465 | 0.2
8387 | Oklahoma | OSAGE |  | 3 | STIM432 | This project replaces a deteriorated bridge on EW-33 over Cander Creek located 0.2 mile south and 1.3 miles east of Wolco. | Bridge Replacement | 03/22/2010 | 03/08/2010 | 10/17/2010 | 430812 | 0.4
8388 | Oklahoma | LATIMER |  | 2 | STIM433 | County Bridge Constrcution of the driving lanes and shoulders over Bear Creek located 0.50 miles North and 0.50 miles East of the Town of Lodi to replace a strucutrally defecient or obsolete local gov | Bridge Replacement | 04/05/2010 | 04/05/2010 | 08/02/2010 | 125149 | 0.5
8389 | Oklahoma | CHEROKEE |  | 2 | STIM434 | PEDESTRIAN IMPROVEMENTS HULBERT ARRA: SH-51 RIDER LN TO HALF BLOCK EAST OF THE POST OFFICE | Transportation Enhancements | 08/02/2010 |  | 10/30/2010 | 366699 | 0.1
8390 | Oklahoma | MUSKOGEE |  | 2 | STIM435 | PEDESTRIAN IMPROVEMENTS COUNCIL HILL ARRA: SH-72 FROM 4TH ST TO 8TH ST (WEST SIDE ONLY) | Transportation Enhancements | 04/05/2010 | 03/23/2010 | 07/02/2010 | 143395 | 0.1
8391 | Oklahoma | MUSKOGEE |  | 2 | STIM436 | PEDESTRIAN IMPROVEMENTS PORUM ARRA SH-2 FROM HALF BLOCK NORTH OF OSAGE SOUTH TO CHEROKEE AVE | Transportation Enhancements | 08/02/2010 |  | 10/30/2010 | 348474 | 0.1
8392 | Oklahoma | SEQUOYAH |  | 2 | STIM437 | PEDESTRIAN IMPROVEMENTS VIAN ARRA US-64 FROM BLACKSTONE TO KENNEDY; SH-82 FROM MAIN TO SEQUOYAH | Transportation Enhancements | 04/05/2010 | 04/05/2010 | 06/03/2010 | 441911 | 0.1
8393 | Oklahoma | MUSKOGEE |  | 2 | STIM438 | PEDESTRIAN IMPROVEMENTS BOYNTON ARRA SH-72 FROM LUCILLE AVE NORTH TO NORTH OF KENEFICK AVE | Transportation Enhancements | 04/05/2010 | 03/23/2010 | 07/02/2010 | 89298 | 0.1
8394 | Oklahoma | HASKELL |  | 2 | STIM439 | PEDESTRIAN IMPROVEMENTS KINTA ARRA SH-31 FROM HOYT TO MAIN; SH-2 FROM 4TH ST TO NORTH OF 2ND ST | Transportation Enhancements | 04/05/2010 | 04/05/2010 | 06/03/2010 | 161325 | 0.1
8395 | Oklahoma | LE FLORE |  | 2 | STIM441 | PEDESTRIAN IMPROVEMENTS TALIHINA ARRA US-271 FROM 1ST ST TO DUKE ST 1/2 BLOCK NORTH ON SH-1 | Transportation Enhancements | 04/05/2010 | 03/11/2010 | 06/03/2010 | 128467 | 0.1
8396 | Oklahoma | MCCURTAIN |  | 2 | STIM442 | PEDESTRIAN IMPROVEMENTS BROKEN BOW ARRA US-70 FROM PARK DR TO CHATA RD; US-259 FROM US-70 NORTH 0.4 MI (WEST SIDE ONLY) | Transportation Enhancements | 04/05/2010 | 03/25/2010 | 06/03/2010 | 239644 | 0.1
8397 | Oklahoma | MARSHALL |  | 4 | STIM445 | PEDESTRIAN IMPROVEMENTS KINGSTON ARRA US-70 FROM MAYTUBBY ST TO HANEY ST; US-70B FROM US-70 TO 1ST ST | Transportation Enhancements | 04/05/2010 | 04/01/2010 | 08/02/2010 | 457323 | 0.1
8398 | Oklahoma | LINCOLN |  | 3 | STIM446 | PEDESTRIAN IMPROVEMENTS AGRA ARRA SH-18 HAYES ST TO WASHINGTON ST | Transportation Enhancements | 04/05/2010 | 04/09/2010 | 06/03/2010 | 144663 | 0.1
8399 | Oklahoma | LINCOLN |  | 3 | STIM447 | PEDESTRIAN IMPROVEMENTS TRYON ARRA SH-105 FROM OKLAHOMA ST TO 1ST ST | Transportation Enhancements | 05/03/2010 | 05/11/2010 | 07/31/2010 | 237215 | 0.1
8400 | Oklahoma | SEMINOLE |  | 5 | STIM448 | PEDESTRIAN IMPROVEMENTS SASAKWA ARRA SH-56 FROM PINE ST TO CHESTNUT ST | Transportation Enhancements | 05/03/2010 | 05/05/2010 | 08/30/2010 | 148764 | 0.1
8401 | Oklahoma | GARVIN |  | 4 | STIM449 | PEDESTRIAN IMPROVEMENTS MAYSVILLE ARRA SH-19/SH-74 EAST TO PINE ALLEY | Transportation Enhancements | 07/12/2010 |  | 09/10/2010 | 95958 | 0.1
8402 | Oklahoma | KAY |  | 3 | STIM452 | PEDESTRIAN IMPROVEMENTS TONKAWA ARRA US-77/US-60B FROM GRAND AVE TO PARK AVE & MAIN ST TO PUBLIC ST | Transportation Enhancements | 05/03/2010 | 04/19/2010 | 07/01/2010 | 307386 | 0.1
8403 | Oklahoma | KINGFISHER |  | 3 | STIM453 | PEDESTRIAN IMPROVEMENTS OKARCHE ARRA US-81 FROM IOWA ST NORTH TO MISSOURI (EAST SIDE ONLY) & MEMORIAL (WEST SIDE) | Transportation Enhancements | 04/05/2010 | 04/26/2010 | 06/03/2010 | 304492 | 0.1
8404 | Oklahoma | KINGFISHER |  | 3 | STIM454 | PEDESTRIAN IMPROVEMENTS HENNESSEY ARRA US-81 FROM IOWA ST SOUTH TO 6TH ST | Transportation Enhancements | 07/05/2010 |  | 10/02/2010 | 778345 | 0.1
8405 | Oklahoma | LOGAN |  | 3 | STIM455 | PEDESTRIAN IMPROVEMENTS CRESCENT ARRA SH-74 FROM NORTH LOCUST ST SOUTH TO WEST ADAMS ST | Transportation Enhancements | 07/19/2010 |  | 10/16/2010 | 355410 | 0.1
8406 | Oklahoma | LOGAN |  | 3 | STIM456 | PEDESTRIAN IMPROVEMENTS LANGSTON ARRA SH-OB FROM WASHINGTON ST EAST TO MARTIN LUTHER KING ST | Transportation Enhancements | 05/03/2010 |  | 07/31/2010 | 1357120 | 0.01
8407 | Oklahoma | KINGFISHER |  | 3 | STIM457 | PEDESTRIAN IMPROVEMENTS KINGFISHER ARRA US-81 NORTH OF SH-33 RECONSTRUCTION OF THREE INTERSECTIONS | Transportation Enhancements | 04/05/2010 | 04/13/2010 | 06/03/2010 | 504012 | 0.87
8408 | Oklahoma | HARMON |  | 3 | STIM458 | PEDESTRIAN IMPROVEMENTS HOLLIS ARRA US-62 FROM MAIN ST EAST TO 1ST ST | Transportation Enhancements | 07/19/2010 |  | 10/16/2010 | 452793 | 0.1
8409 | Oklahoma | BECKHAM |  | 3 | STIM459 | PEDESTRIAN IMPROVEMENTS SAYRE ARRA SH-152/US-283 EAST TO COURTHOUSE SQUARE; US-283 FROM MAIN ST NORTH TO US-66 | Transportation Enhancements | 03/01/2010 | 04/26/2010 | 04/29/2010 | 441823 | 0.1
8410 | Oklahoma | DEWEY |  | 3 | STIM460 | PEDESTRIAN IMPROVEMENTS VICI ARRA SH-51 FROM SPECK ST EAST TO BROWN ST **CERT** | Transportation Enhancements | 04/05/2010 | 03/09/2010 | 06/03/2010 | 299649 | 0.1
8411 | Oklahoma | BLAINE |  | 3 | STIM461 | PEDESTRIAN IMPROVEMENTS CANTON ARRA SH-51 FROM GRANT ST TO LINCOLN ST; SH-58 FROM MAIN ST TO PARK ST | Transportation Enhancements | 07/05/2010 | 06/07/2010 | 10/02/2010 | 595704 | 0.1
8412 | Oklahoma | GREER |  | 3 | STIM462 | PEDESTRIAN IMPROVEMENTS MANGUM ARRA SH-34 FROM EAST JACKSON ST TO EAST SOUTH ST | Transportation Enhancements | 08/02/2010 |  | 10/30/2010 | 478252 | 0.1
8413 | Oklahoma | KIOWA |  | 3 | STIM463 | PEDESTRIAN IMPROVEMENTS HOBART ARRA US-183 | Transportation Enhancements | 07/05/2010 | 07/06/2010 | 10/02/2010 | 491751 | 1
8414 | Oklahoma | TEXAS |  | 3 | STIM464 | PEDESTRIAN IMPROVEMENTS HARDESTY ARRA US-412 FROM 2ND ST WEST TO 6TH ST | Transportation Enhancements | 03/01/2010 | 03/01/2010 | 04/29/2010 | 202303 | 0.1
8415 | Oklahoma | ELLIS |  | 3 | STIM465 | PEDESTRIAN IMPROVEMENTS SHATTUCK ARRA US-283 FROM GRAND AVE SOUTH TO 10TH ST | Transportation Enhancements | 05/03/2010 | 05/03/2010 | 07/01/2010 | 574649 | 0.1
8416 | Oklahoma | ELLIS |  | 3 | STIM466 | PEDESTRIAN IMPROVEMENTS GAGE ARRA SH-46 FROM NORTH ST SOUTH TO SH-46/SH-15 JCT | Transportation Enhancements | 07/12/2010 |  | 09/10/2010 | 112804 | 0.1
8417 | Oklahoma | ALFALFA |  | 3 | STIM467 | PEDESTRIAN IMPROVEMENTS GOLTRY ARRA SH-45 FROM 7TH ST SOUTH TO 1/4 MI SOUTH OF MAIN ST | Transportation Enhancements | 07/19/2010 |  | 10/16/2010 | 467028 | 0.1
8418 | Oklahoma | BEAVER |  | 3 | STIM468 | PEDESTRIAN IMPROVEMENTS FORGAN ARRA US-270 FROM TEXAS ST TO MISSISSIPPI AVE | Transportation Enhancements | 04/19/2010 | 04/06/2010 | 06/17/2010 | 631284 | 0.1
8419 | Oklahoma | JEFFERSON |  | 4 | STIM469 | PEDESTRIAN IMPROVEMENTS WAURIKA ARRA SH-5 FROM ANDERSON AVE SOUTH TO US-70 | Transportation Enhancements | 03/01/2010 | 03/01/2010 | 04/29/2010 | 236578 | 0.1
8420 | Oklahoma | GRADY |  | 4 | STIM470 | PEDESTRIAN IMPROVEMENTS POCASSET ARRA US-81 FROM 1ST ST SOUTH TO 5TH ST | Transportation Enhancements | 04/05/2010 | 03/01/2010 | 06/03/2010 | 127638 | 0.1
8421 | Oklahoma | COTTON |  | 4 | STIM471 | PEDESTRIAN IMPROVEMENTS TEMPLE ARRA SH-65 FROM OREGON ST SOUTH TO OKLAHOMA ST | Transportation Enhancements | 07/12/2010 |  | 10/09/2010 | 440815 | 0.1
8422 | Oklahoma | GRADY |  | 4 | STIM472 | PEDESTRIAN IMPROVEMENTS RUSH SPRINGS ARRA SH-17/SH-81B JCT TO SH-81 | Transportation Enhancements | 04/05/2010 | 03/01/2010 | 07/03/2010 | 152435 | 0.1
8423 | Oklahoma | JEFFERSON |  | 4 | STIM473 | PEDESTRIAN IMPROVEMENTS HASTINGS ARRA SH-5 FROM COMMERCIAL AVE TO 4TH ST | Transportation Enhancements | 05/03/2010 | 05/03/2010 | 07/01/2010 | 215191 | 0.1
8424 | Oklahoma | CADDO |  | 3 | STIM474 | "PEDESTRIAN IMPROVEMENTS CEMENT ARRA US-277(SH-19) FROM ""F"" AVE WEST TO ONE BLK WEST OF MAIN ST " | Transportation Enhancements | 05/03/2010 | 06/01/2010 | 07/01/2010 | 53608 | 0.1
8425 | Oklahoma | CARTER |  | 4 | STIM475 | PEDESTRIAN IMPROVEMENTS GENE AUTRY ARRA SH-53A FROM GRANT AVE TO MILL ST (WEST SIDE ONLY) | Transportation Enhancements | 04/05/2010 | 03/29/2010 |  | 95369 | 0.1
8426 | Oklahoma | CREEK |  | 1 | STIM476 | PEDESTRIAN IMPROVEMENTS MOUNDS ARRA US-75A FROM 9TH ST TO 14TH ST | Transportation Enhancements | 07/05/2010 | 07/05/2010 | 10/02/2010 | 238017 | 0.2
8427 | Oklahoma | NOWATA |  | 2 | STIM477 | PEDESTRIAN IMPROVEMENTS NOWATA ARRA US-60 FROM DELAWARE OAK ST | Transportation Enhancements | 05/03/2010 | 04/26/2010 | 07/01/2010 | 189298 | 0.1
8428 | Oklahoma | OSAGE |  | 3 | STIM478 | PEDESTRIAN IMPROVEMENTS FAIRFAX ARRA SH-18 FROM WALNUT ST TO MULBERRY ST | Transportation Enhancements | 07/05/2010 | 06/21/2010 | 09/03/2010 | 200199 | 0.1
8429 | Oklahoma | OTTAWA |  | 2 | STIM479 | PEDESTRIAN IMPROVEMENTS QUAPAW ARRA US-69A FROM 1ST ST SOUTH TO 4TH ST | Transportation Enhancements | 07/05/2010 |  | 10/02/2010 | 382625 | 0.1
8430 | Oklahoma | MAYES |  | 2 | STIM480 | PEDESTRIAN IMPROVEMENTS LOCUST GROVE ARRA US-412A FROM BROADWAY EAST TO CHEROKEE ST | Transportation Enhancements | 07/05/2010 |  | 10/02/2010 | 223695 | 0.1
8431 | Oklahoma | HASKELL |  | 2 | STIM481 | Replace the bridge over San Bois Creek about 1 mile south and 2 miles west of Kinta. | Bridge Replacement | 03/01/2010 | 03/16/2010 | 06/28/2010 | 229857.57 | 0.22
8432 | Oklahoma | TULSA | TULSA | 1 | STIM482 | Intersection modifications and installation of traffic signals at 21st Street and Sheridan Road in Tulsa. | Pavement Improvement | 01/04/2010 | 02/02/2010 | 03/29/2011 | 686902 | 0.01
8433 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM483 | RESURFACE BRYANT AVE BEG @ SH-37 & EXT NORTH TO N.E. 27TH ST & S.E. 34TH ST FR BRYANT AVE. TO SOONER RD. | Pavement Improvement | 03/24/2010 | 06/23/2010 |  | 851806 | 4
8434 | Oklahoma | WAGONER |  | 1 | STIM484 | PEDESTRIAN IMPROVEMENTS PORTER ARRA SH-51B FROM HALE ST SOUTH 6 BLK TO BELAIRE ST | Transportation Enhancements | 04/05/2010 | 03/18/2010 | 06/18/2010 | 367227 | 0.5
8435 | Oklahoma | PITTSBURG |  | 2 | STIM485 | PEDESTRIAN IMPROVEMENTS KIOWA ARRA US-69 START & END AT THE CURB & GUTTER BOTH SIDES OF ROAD 8/10 MI LONG | Transportation Enhancements | 04/05/2010 | 04/13/2010 | 08/02/2010 | 511485 | 0.8
8436 | Oklahoma | OTTAWA |  | 2 | STIM489 | PEDESTRIAN IMPROVEMENTS MIAMI ARRA US-69 FROM C ST SW TO A ST SW 4 BLK; SH-10 FROM A ST SW EAST 1.5 BLK | Transportation Enhancements | 04/05/2010 | 05/05/2010 | 06/03/2010 | 460384 | 0.1
8437 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM490 | RESURFACE S.E. 44TH STREET BEG @ BRYANT AVE. & EXTEND EAST TO SOONER ROAD IN DEL CITY & OKLAHOMA CITY | Pavement Improvement | 04/19/2010 | 04/19/2010 | 05/18/2010 | 600229 | 2
8438 | Oklahoma | CANADIAN | OKLAHOMA CITY | 4 | STIM491 | RESURFACE MORGAN ROAD BEG @ S.W. 89TH STREET & EXTEND NORTH TO S.W. 59TH STREET IN MUSTANG. | Pavement Improvement | 05/17/2010 | 05/17/2010 | 06/15/2010 | 210466 | 2
8439 | Oklahoma | LOGAN | OKLAHOMA CITY | 3 | STIM492 | RESURFACE KELLY AVE BEG @ WATERLOO ROAD & EXTEND NORTH TO CO RD(EW-88) | Pavement Improvement | 04/26/2010 | 04/26/2010 | 05/25/2010 | 111305 | 1
8440 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM493 | RESURFACE MAIN STREET BEG @ STATE STREET & EXTEND EAST 0.5 MILE | Pavement Improvement | 05/17/2010 | 05/10/2010 | 07/15/2010 | 87399 | 0.5
8441 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM494 | RESURFACE JONES ARRA: N.E. 36TH STREET BEG @ COLTRANE & EXT TO BARTREL RD | Pavement Improvement | 05/17/2010 | 05/10/2010 | 07/15/2010 | 71068 | 1
8442 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM495 | RESURFACE LUTHER ARRA: LUTHER ROAD BEG @ EDMOND ROAD & EXT NORTH TO DANFORTH RD | Pavement Improvement | 05/17/2010 | 05/10/2010 | 07/15/2010 | 188000 | 1.1
8443 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM497 | "RESURFACE SPENCER ARRA: SPNCR RD FR NE 36TH EXT N TO NE 50TH; SDWLKS & ADA RMPS FR NE 23RD TO NE 36TH ON SPNCR RD**CERT**(DEL FR 02-10, ADD TO 03-10;PLAN REV)" | Pavement Improvement | 07/05/2010 | 07/16/2010 | 08/18/2010 | 98418 | 1
8444 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM499 | RESURFACE WARR ACRES ARRA: MACARTHUR AVE BEG @ NW 63RD ST & EXT NORTH TO N.W. EXPRESSWAY | Pavement Improvement | 04/19/2010 | 05/21/2010 | 05/18/2010 | 166957 | 0.8
8445 | Oklahoma | LOGAN | OKLAHOMA CITY | 3 | STIM500 | RESURFACE GUTHRIE ARRA: WALNUT AVE FROM NOBLE TO MANSUR | Pavement Improvement | 08/02/2010 |  | 08/22/2010 | 46150 | 0.2
8446 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM501 | RESURFACE OKC ARRA: ANDERSON RD BEG @ S.E. 149TH ST. & EXT NORTH TO S.E. 89TH ST. | Pavement Improvement | 05/17/2010 |  | 06/30/2010 | 1304447 | 4
8447 | Oklahoma | OKLAHOMA | OKLAHOMA CITY | 5 | STIM502 | RESURFACE OKC ARRA: MERIDIAN AVE BEG AT S.W. 54TH ST. & EXT NORTH TO S.W. 29TH ST. | Pavement Improvement | 06/07/2010 | 06/07/2010 | 07/06/2010 | 503821 | 1.6
8448 | Oklahoma | GRANT |  | 3 | STIM503 | "GRADE,DRAINING,BRIDGE & SURFACE CO. BR. OVER POND CR., 3 MI. N. AND 4.9 MI. E. OF THE SH-11/SH-11A JCT (FORMERLY BRO-127D(100)CO) " | Bridge Replacement | 05/03/2010 | 04/12/2010 | 08/30/2010 | 95480 | 0.1
8449 | Oklahoma | CLEVELAND | OKLAHOMA CITY | 4 | STIM504 | "GRADE,DRAINING,BRIDGE & SURFACE ROBINSON STREET AT THE BURLINGTON NORTHERN SANTE FE RAILROAD CROSSING, IN NORMAN " | Pavement Improvement | 08/02/2010 |  | 11/09/2011 | 1888512 | 0.2
8450 | Oklahoma | TULSA | TULSA | 1 | STIM505 | RESURFACE BROKEN ARROW ARRA: HOUSTON ST(81ST STREET SOUTH) BEG @ ASPEN AVE(145TH E. AVE) & EXT TO ELM PLACE(161ST E. AVE) | Pavement Improvement | 07/05/2010 |  | 08/18/2010 | 444076 | 1
8451 | Oklahoma | TULSA | TULSA | 1 | STIM506 | PAVEMENT REHABILITATION JENKS ARRA: MAIN STREET - RAILROAD EAST TO 4TH STREET | Pavement Improvement | 08/02/2010 |  | 10/30/2010 | 161815 | 0.3
8452 | Oklahoma | CREEK | TULSA | 1 | STIM508 | PAVEMENT REHABILITATION SAPULPA ARRA: 71ST ST SOUTH FROM RIVA RIDGE ROAD EAST TO 41ST STREET | Pavement Improvement | 08/02/2010 |  | 10/01/2010 | 220668 | 0.5
8453 | Oklahoma | TULSA | TULSA | 1 | STIM512 | RESURFACE BROKEN ARROW ARRA: FLORENCE ST(111TH ST S) BEG @ OLIVE AVE(129TH E. AVE) & EXT TO ASPEN AVE(145TH E. AVE) | Pavement Improvement | 07/05/2010 |  | 10/02/2010 | 311801 | 1
8454 | Oklahoma | TULSA | TULSA | 1 | STIM513 | RESURFACE BROKEN ARROW ARRA: 23RD ST(COUNTY LINE) BEG @ JASPER ST(131ST ST S) & EXT TO YAZOO ST(141ST ST S) | Pavement Improvement | 07/05/2010 |  | 10/02/2010 | 286225 | 1
8455 | Oklahoma | MURRAY |  | 4 | STIM516 | PEDESTRIAN IMPROVEMENTS SULPHUR ARRA SH-7 FROM 9TH ST EAST 0.521 MI TO FIRST ST | Transportation Enhancements | 07/12/2010 | 07/12/2010 | 09/10/2010 | 298566 | 0.521
8456 | Oklahoma | MAJOR |  | 3 | STIM519 | Bridge replacement and redo approaches of US-281 over Griever Creek approx. 5.0 miles north of junction of US-281 and US-60E | Bridge Replacement | 08/02/2010 | 06/25/2010 | 05/03/2011 | 2295065 | 1
8457 | Oklahoma | OKLAHOMA |  | 5 | STIM526 | Railroad Rehabilation - Stabilize the river banks & THE railroad bed along the OKC to Shawnee spur (multiple locations) | Other | 07/21/2010 | 08/02/2010 |  | 4000000 | 0.01
8458 | Oklahoma | BECKHAM |  | 3 | STIM527 | Resurface I-40 eastward from mile marker 22 to approximatly mile marker 25. | Pavement Improvement | 06/07/2010 | 06/10/2010 | 10/04/2010 | 3036915 | 2.36
8459 | Oklahoma | GARFIELD |  | 3 | STIM528 | Reconstruct US-81 beginning at the Kingfisher C/L & extending north approximately 7.2 miles resurfacing both the north and south lanes | Pavement Widening | 08/02/2010 |  | 01/28/2011 | 1010225 | 7.2
8460 | Oregon | LANE |  | 4 | 0000183 | Enhance safety to pedestrians and bicyclists by repaving the EWEB Bike Path between Pioneer Parkway and 31st street in Eugene. | Other | 05/11/2009 | 05/11/2009 |  | 1766.48 | 0
8461 | Oregon | LINN |  | 4 | 0100030 | Pave Salem Ave between Sherman St and the UP railroad crossing in Albany to improve safety and extend pavement life. | Pavement Improvement | 07/14/2009 | 07/22/2009 | 03/31/2010 | 1040874.6 | 0
8462 | Oregon | LINN |  | 4 | 0100031 | Pave Salem Ave between Sherman St and the UP railroad crossing in Albany to improve safety and extend pavement life. | Other | 04/28/2009 | 04/28/2009 |  | 3129.4 | 0
8463 | Oregon | JACKSON |  |  | 0305019 | Improves safety on Hersey St between Oak St and Ann St in Ashland by reconstructing sidewalks. | Transportation Enhancements | 07/14/2009 | 08/05/2009 | 11/21/2009 | 194597.81 | 0
8464 | Oregon | JACKSON | MEDFORD | 2 | 0305020 | Pave several city streets in Ashland to improve safety and extend pavement life. | Other | 04/15/2009 | 04/15/2009 |  | 20095.52 | 0
8465 | Oregon | JACKSON |  |  | 0305021 | Improves safety on Hersey St between Oak St and Ann St in Ashland by reconstructing sidewalks. | Other | 04/15/2009 | 04/15/2009 |  | 3986.69 | 0
8466 | Oregon | JACKSON | MEDFORD | 2 | 0305022 | Pave several city streets in Ashland to improve safety and extend pavement life. | Pavement Improvement | 08/11/2009 | 09/22/2009 | 10/31/2009 | 396607.29 | 0
8467 | Oregon | CLATSOP |  | 1 | 0315006 | Pave several city streets in Astoria to improve safety and extend pavement life. | Pavement Improvement | 03/03/2010 |  | 08/31/2010 | 195779 | 0
8468 | Oregon | CLATSOP |  | 1 | 0315007 | Pave several city streets in Astoria to improve safety and extend pavement life. | Other | 07/23/2009 | 07/23/2009 |  | 20000 | 0
8469 | Oregon | MARION |  | 5 | 0330007 | Improve pedestrian and bicycle safety by adding sidewalks, curb cuts and drainage on OR 99E between Main St and 4th Street in Aurora. | Transportation Enhancements | 07/24/2009 | 01/13/2010 | 04/30/2010 | 159569.44 | 0.09
8470 | Oregon | MARION |  | 5 | 0330008 | Improve pedestrian and bicycle safety by adding sidewalks, curb cuts and drainage on OR 99E between Main St and 4th Street in Aurora. | Other | 06/25/2009 | 06/25/2009 |  | 344.11 | 0.09
8471 | Oregon | BAKER |  | 2 | 0365020 | Construct a pedestrian/bicycle shared use path on the Leo Adler Memorial Parkway between Madison St and Court St in Baker City. | Transportation Enhancements | 11/23/2009 | 05/11/2010 |  | 217064 | 0
8472 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535022 | Pave Hall Blvd between Hart Rd and Ridgecrest Dr in Beaverton to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 46671.81 | 0
8473 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535023 | Improve pedestrian safety and access by constructing sidewalks and ADA ramps on Laurelwood Ave and 87th Ave in Beaverton. | Other | 07/08/2009 | 07/08/2009 |  | 212580.97 | 0
8474 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535024 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Other | 08/05/2009 | 08/05/2009 |  | 117929.99 | 0
8475 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535026 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Safety/Traffic Management | 08/28/2009 | 08/28/2009 | 09/01/2010 | 280000 | 0
8476 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535027 | Pave Hall Blvd between Hart Rd and Ridgecrest Dr in Beaverton to improve safety and extend pavement life. | Pavement Improvement | 12/18/2009 | 02/23/2010 | 05/15/2010 | 568757.05 | 0
8477 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535028 | Improve pedestrian safety and access by constructing sidewalks and ADA ramps on Laurelwood Ave and 87th Ave in Beaverton. | Transportation Enhancements | 02/19/2010 | 03/16/2010 | 07/15/2010 | 505197.96 | 0
8478 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 0535029 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Safety/Traffic Management | 03/05/2010 |  |  | 300500.81 | 0
8479 | Oregon | DESCHUTES |  | 2 | 0580035 | Pave several city streets in Bend to improve safety and extend pavement life. | Pavement Improvement | 09/18/2009 | 04/30/2010 | 06/01/2010 | 1181404.7 | 0
8480 | Oregon | DESCHUTES | BEND | 2 | 0580036 | Pave several city streets in Bend to improve safety and extend pavement life. | Other | 05/04/2009 | 05/04/2009 |  | 50014.3 | 0
8481 | Oregon | CLACKAMAS |  | 5 | 1075005 | Improve vehicle and pedestrian safety and extend pavement life by paving and adding curbs and sidewalk on North Knights Bridge Rd between Knights Bridge and N Grant St in Canby. | Other | 06/22/2009 | 06/22/2009 |  | 40000 | 0
8482 | Oregon | CLACKAMAS |  | 5 | 1075006 | Improve vehicle and pedestrian safety and extend pavement life by paving and adding curbs and sidewalk on North Knights Bridge Rd between Knights Bridge and N Grant St in Canby. | Pavement Improvement | 04/21/2010 |  |  | 284632 | 0
8483 | Oregon | HARNEY |  | 2 | 1240011 | Pave Pine St between 1st St and 6th St in Central Point to improve safety and extend pavement life. | Safety/Traffic Management | 02/04/2010 |  |  | 367787 | 0
8484 | Oregon | JACKSON | MEDFORD | 2 | 1240012 | Pave Pine St between 1st St and 6th St in Central Point to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 24877.49 | 0
8485 | Oregon | WASCO |  | 2 | 1342003 | Improves safety and access on US 30 at the Brewery Grade intersection in The Dalles by reconstructing intersection to a round-about. | Pavement Improvement | 07/09/2009 | 08/25/2009 | 05/23/2010 | 2524023.94 | 0.41
8486 | Oregon | LANE | EUGENE | 4 | 1440000 | Improve safety and drainage by repaving East Locust St and North Diamond St in Coburg. | Other | 06/04/2009 | 06/04/2009 |  | 10000 | 0
8487 | Oregon | COOS |  | 4 | 1525004 | Pave North 10th St between Central Ave and Cedar Ave in Coos County to improve safety and extend pavement life. | Pavement Improvement | 10/09/2009 | 11/30/2009 | 05/31/2010 | 349118.56 | 0
8488 | Oregon | WASHINGTON |  | 1 | 1555007 | Improve pavement, add curbs, sidewalks and signals to enhance safety and reduce wear and tear on OR Hwy 8 in Cornelius. | Other | 04/09/2009 | 04/09/2009 |  | 40000 | 0
8489 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 1555008 | Improve pavement, add curbs, sidewalks and signals to enhance safety and reduce wear and tear on OR Hwy 8 in Cornelius. | Pavement Improvement | 05/22/2008 | 06/09/2008 | 12/31/2009 | 495659 | 0
8490 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 1555011 | Improve safety and extend the life of the pavement by sealing craks and repaving several streets in Cornelius. | Other | 08/21/2009 | 08/21/2009 |  | 21474.9 | 0
8491 | Oregon | BENTON | CORVALLIS | 4 | 1580031 | Pave several city streets in Corvallis to improve safety and extend pavement life. | Pavement Improvement | 08/28/2009 | 09/08/2009 | 10/14/2009 | 738125 | 0
8492 | Oregon | BENTON |  | 4 | 1580032 | Enhance safety to pedestrians and bicyclists by repaving the Corvallis-Phillomath multi-use bicycle and pedestrian path in Benton County. | Pavement Improvement | 07/09/2009 | 07/29/2009 | 09/09/2009 | 352040.18 | 0
8493 | Oregon | BENTON | CORVALLIS | 4 | 1580034 | Pave Western Ave between 7th and 17th St and 5th St between Western and 9th Ave in Corvallis to improve safety and extend pavement life. | Pavement Improvement | 01/14/2010 | 05/18/2010 | 06/30/2010 | 508366 | 0
8494 | Oregon | LANE |  | 4 | 1595004 | Improve safety on South 8th St and Woodson Bridge approaches in Cottage Grove by adding curb, gutter, sidewalks and paved shoulders. | Other | 08/13/2009 | 08/13/2009 |  | 5188.99 | 0
8495 | Oregon | LANE |  | 4 | 1595005 | Improve safety on South 8th St and Woodson Bridge approaches in Cottage Grove by adding curb, gutter, sidewalks and paved shoulders. | Pavement Improvement | 03/08/2010 | 04/07/2010 | 06/15/2010 | 191111.69 | 0
8496 | Oregon | POLK |  | 5 | 1770002 | Pave several city streets in Dallas to improve safety and extend pavement life. | Pavement Improvement | 08/06/2009 | 08/24/2009 | 05/11/2010 | 328109.74 | 0
8497 | Oregon | POLK |  | 5 | 1770003 | Pave several city streets in Dallas to improve safety and extend pavement life. | Other | 06/04/2009 | 06/04/2009 |  | 697.26 | 0
8498 | Oregon | LANE |  | 4 | 2385052 | Enhances bridge and trail elements to improve usage of the Delta Ponds multi-use path between Goodpasture Island and Robin Hood Ln in Eugene. | Other | 05/17/2007 | 05/17/2007 |  | 60027.44 | 0
8499 | Oregon | LANE |  | 4 | 2385059 | Improves access to the Eugene train depot by adding sidewalk and lighting to the pedestrian access. | Transportation Enhancements | 07/13/2009 | 08/03/2009 | 05/31/2010 | 177900 | 0
8500 | Oregon | LANE | EUGENE | 4 | 2385060 | Enhances bridge and trail elements to improve usage of the Delta Ponds multi-use path between Goodpasture Island and Robin Hood Ln in Eugene. | Transportation Enhancements | 08/10/2009 | 08/24/2009 | 10/01/2010 | 1229085.82 | 0
8501 | Oregon | LANE | EUGENE | 4 | 2385061 | Complete pavement preservation project on Garfeield St between W 6th Ave and W 11th Ave in Eugene to improve safety and extend the life of the pavement. | Other | 05/21/2009 | 05/21/2009 |  | 45000 | 0
8502 | Oregon | LANE | EUGENE | 4 | 2385063 | Complete pavement preservation project on Crescent Ave between Gamefarm Rd and Shadowview in Eugene to improve safety and extend the life of the pavement. | Other | 06/19/2009 | 06/19/2009 |  | 6000 | 0
8503 | Oregon | LANE | EUGENE | 4 | 2385064 | Complete pavement preservation project on High St between 3rd Ave and 17th Ave in Eugene to improve safety and extend the life of the pavement. | Other | 06/19/2009 | 06/19/2009 |  | 55000 | 0
8504 | Oregon | LANE |  | 4 | 2605001 | Pave several city streets in Florence to improve safety and extend pavement life. | Other | 04/29/2009 | 04/29/2009 |  | 15000 | 0
8505 | Oregon | LANE |  | 4 | 2605002 | Pave several city streets in Florence to improve safety and extend pavement life. | Pavement Improvement | 01/06/2010 | 05/07/2010 |  | 186437 | 0
8506 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 2620003 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Other | 04/04/2006 | 04/04/2006 |  | 86399.5 | 0
8507 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 2620004 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Transportation Enhancements | 04/04/2008 | 04/28/2008 | 01/11/2010 | 1490000 | 0
8508 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 2620005 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Other | 08/29/2007 | 08/29/2007 |  | 9222.45 | 0
8509 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 2900008 | Pave several city streets in Gladstone to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 66989.51 | 0
8510 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 2900009 | Pave several city streets in Gladstone to improve safety and extend pavement life. | Pavement Improvement | 03/04/2010 | 05/06/2010 |  | 727357 | 0
8511 | Oregon | JOSEPHINE |  | 4 | 3055403 | Pave several city streets in Grants Pass to improve safety and extend pavement life. | Other | 06/05/2009 | 06/05/2009 |  | 60000 | 0
8512 | Oregon | JOSEPHINE |  | 4 | 3055404 | Pave several city streets in Grants Pass to improve safety and extend pavement life. | Pavement Improvement | 02/01/2010 | 05/03/2010 |  | 630580 | 0
8513 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | 3125034 | Improve safety and access to vehicles, bicycles and pedestrians on 242nd and Hogan Rd between Glisan St and Stark St by widening the seciton of road and adding four travel lanes, center turn lane, bic | Other | 06/11/2009 | 06/11/2009 |  | 34032.76 | 0
8514 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | 3125035 | Improve safety and access to vehicles, bicycles and pedestrians on 242nd and Hogan Rd between Glisan St and Stark St by widening the seciton of road and adding four travel lanes, center turn lane, bic | Pavement Improvement | 11/24/2009 | 02/01/2010 | 10/09/2010 | 1711867.04 | 0
8515 | Oregon | CLACKAMAS | PORTLAND (WA) | 3 | 3205001 | Extend the life of the pavement on city streets in Happy Valley by sealing and resurfacing several minor arterial streets. | Other | 05/15/2009 | 05/15/2009 |  | 80051.09 | 0
8516 | Oregon | CLACKAMAS | PORTLAND (WA) | 3 | 3205002 | Extend the life of the pavement on city streets in Happy Valley by sealing and resurfacing several minor arterial streets. | Pavement Improvement | 03/05/2010 |  |  | 599441.81 | 0
8517 | Oregon | UMATILLA |  | 2 | 3370003 | Pave Feedville Rd and Kelli blvd between OR 395 and Cook Industrial site in Umatilla County to improve safety and extend pavement life. | Pavement Improvement | 12/22/2009 |  |  | 326219.17 | 0
8518 | Oregon | UMATILLA |  | 2 | 3370004 | Pave Feedville Rd and Kelli blvd between OR 395 and Cook Industrial site in Umatilla County to improve safety and extend pavement life. | Other | 07/29/2009 | 07/29/2009 |  | 14067.89 | 0
8519 | Oregon | MORROW |  | 2 | 3650003 | Enhance pedestrian and bicycle safety by constructing sidewalks, bike lanes, and a planter strip with street trees along 1st St and Main Ave in Irrigon. | Transportation Enhancements | 07/09/2009 | 07/23/2009 | 06/15/2010 | 1527961.59 | 0
8520 | Oregon | MORROW |  | 2 | 3650004 | Enhance pedestrian and bicycle safety by constructing sidewalks, bike lanes, and a planter strip with street trees along 1st St and Main Ave in Irrigon. | Other | 05/13/2009 | 05/13/2009 |  | 94570.28 | 0
8521 | Oregon | JACKSON | MEDFORD | 2 | 3700009 | Improve bicycle and pedestrian safety and mobility by adding bike lanes and sidewalks to C St in Jacksonville. | Other | 05/14/2009 | 05/14/2009 |  | 58000 | 0
8522 | Oregon | JACKSON |  | 2 | 3700010 | Improve bicycle and pedestrian safety and mobility by adding bike lanes and sidewalks to C St in Jacksonville. | Transportation Enhancements | 02/19/2010 | 03/08/2010 | 06/30/2010 | 180500 | 0
8523 | Oregon | MARION | SALEM | 5 | 3850008 | Pave Dearborn Ave and Chemawa Rd in Keizer to improve safety and extend pavement life. | Pavement Improvement | 04/06/2010 |  |  | 87050 | 0
8524 | Oregon | MARION | SALEM | 5 | 3850009 | Pave Dearborn Ave and Chemawa Rd in Keizer to improve safety and extend pavement life. | Other | 03/22/2010 | 03/22/2010 |  | 5000 | 0
8525 | Oregon | KLAMATH |  | 2 | 3970018 | Improve safety of pedestrian connections to the bus and train station in Klamath Falls by restoring fencing, adding lighting and crossing enhancements. Improves mobility by repaving Spring St. | Transportation Enhancements | 06/10/2009 | 07/13/2009 | 10/15/2009 | 136097.56 | 0
8526 | Oregon | UNION |  | 2 | 4035014 | Pave Spruce St between Monroe Ave and Z avenue in LaGrande to improve safety and extend pavement life. | Pavement Improvement | 02/11/2010 |  |  | 265320.49 | 0
8527 | Oregon | UNION |  | 2 | 4035015 | Pave Spruce St between Monroe Ave and Z avenue in LaGrande to improve safety and extend pavement life. | Other | 07/20/2009 | 07/20/2009 |  | 11574.51 | 0
8528 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 4055009 | Pave Royce and McNary St in Lake Oswego to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 83490.87 | 0
8529 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 4055010 | Pave Royce and McNary St in Lake Oswego to improve safety and extend pavement life. | Pavement Improvement | 03/08/2010 | 05/06/2010 |  | 466812.72 | 0
8530 | Oregon | LINN |  | 4 | 4165007 | Pave 2nd St and Airport Rd in Lebanon to improve safety and extend pavement life. | Pavement Improvement | 02/23/2010 | 04/23/2010 | 07/31/2010 | 281947.08 | 0
8531 | Oregon | LINN |  | 4 | 4165008 | Pave 2nd St and Airport Rd in Lebanon to improve safety and extend pavement life. | Other | 07/01/2009 | 07/01/2009 |  | 43112.92 | 0
8532 | Oregon | YAMHILL |  | 1 | 4500006 | Pave several city streets in McMinnville to improve safety and extend pavement life. | Pavement Improvement | 07/16/2009 | 08/13/2009 | 10/20/2009 | 874200.11 | 0
8533 | Oregon | YAMHILL |  | 1 | 4500007 | Pave several city streets in McMinnville to improve safety and extend pavement life. | Other | 06/18/2009 | 06/18/2009 |  | 7924.48 | 0
8534 | Oregon | CLACKAMAS | PORTLAND (WA) | 3 | 4865010 | Improve pedestrian safety and access by reconstructing sidewalks, streetscape, and curb extensions on Jackson St between Main St and 21st Ave in Clackamas. | Other | 08/05/2009 | 08/05/2009 |  | 159573.74 | 0
8535 | Oregon | CLATSOP | PORTLAND (WA) | 3 | 4865013 | Improve pedestrian safety and access by reconstructing sidewalks, streetscape, and curb extensions on Jackson St between Main St and 21st Ave in Clackamas. | Transportation Enhancements | 04/15/2010 |  |  | 680336.63 | 0
8536 | Oregon | POLK |  | 5 | 4955001 | Pave Stadium Dr and Jackson St in Monmouth to improve safety and extend pavement life. | Pavement Improvement | 01/11/2010 | 05/11/2010 |  | 161839.54 | 0
8537 | Oregon | POLK |  | 5 | 4955002 | Pave Stadium Dr and Jackson St in Monmouth to improve safety and extend pavement life. | Other | 08/10/2009 | 08/10/2009 |  | 2170.49 | 0
8538 | Oregon | GRANT |  | 2 | 5025101 | Install additional lights on Main Street in Mt. Vernon to improve pedestrian safety. | Transportation Enhancements | 02/24/2009 | 03/30/2009 | 08/14/2009 | 100000 | 0.5
8539 | Oregon | YAMHILL |  | 1 | 5210002 | Pave several city streets in Newberg to improve safety and extend pavement life. | Other | 10/30/2009 | 10/30/2009 |  | 34745.71 | 0
8540 | Oregon | YAMHILL |  | 1 | 5210003 | Pave several city streets in Newberg to improve safety and extend pavement life. | Pavement Improvement | 03/18/2010 |  |  | 394754 | 0
8541 | Oregon | LINCOLN |  | 5 | 5245004 | Improve safety and access with repairs to sidewalks, curb and gutter, paving, and lighting on Bay Blvd in Newport. | Pavement Improvement | 08/17/2009 | 09/08/2009 | 06/30/2010 | 583000 | 0
8542 | Oregon | LINCOLN |  | 5 | 5245005 | Improve safety and access with repairs to sidewalks, curb and gutter, paving, and lighting on Bay Blvd in Newport. | Other | 04/15/2009 | 04/15/2009 |  | 11671.95 | 0
8543 | Oregon | JACKSON | MEDFORD | 2 | 5245006 | Improve safety and extend pavement life on several city streets in Talent and Phoenix by paving, addind additional signage and signals. | Pavement Improvement | 08/11/2009 | 10/12/2009 | 03/31/2010 | 387054.89 | 0
8544 | Oregon | LINCOLN |  | 5 | 5245007 | Pave several city streets in Newport to improve safety and extend pavement life. | Other | 05/21/2009 | 05/21/2009 |  | 2315.29 | 0
8545 | Oregon | LINCOLN |  | 5 | 5245008 | Pave several city streets in Newport to improve safety and extend pavement life. | Pavement Improvement | 08/07/2009 | 09/01/2009 | 10/20/2009 | 216483 | 0
8546 | Oregon | COOS |  | 4 | 5300006 | Pave Sherman Ave between Newmark St and City Limits in North Bend to improve safety and extend pavement life. | Pavement Improvement | 03/01/2010 |  |  | 205963 | 0
8547 | Oregon | MALHEUR |  | 2 | 5490003 | Enhance safety by widening and repaving roadway, and installing sidewalks and curbs on N Oregon St between Idaho Ave and NW 1st St in Ontario. | Pavement Improvement | 07/06/2009 | 07/24/2009 | 12/18/2009 | 1991199.17 | 0
8548 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 5520019 | Improve vehicle and pedestrian safety, mobility and traffic flow on Warner Milne Rd between Beaversreek and Mollala in Oregon City buy realigning the intersection, updating signal timing and adding si | Safety/Traffic Management | 08/18/2009 | 09/21/2009 | 07/15/2010 | 885000 | 0
8549 | Oregon | CLACKAMAS |  | 5 | 5520020 | Enhance safety on historic McLoughlin Promenade multi-use path between 7th St and S 1st St in Oregon City by restoring historing walls, including wall caps and joints, handrails, stairs and tunnel. | Transportation Enhancements | 07/09/2009 | 08/20/2009 | 09/01/2010 | 1065721 | 0
8550 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 5520023 | Improve vehicle and pedestrian safety, mobility and traffic flow on Warner Milne Rd between Beaversreek and Mollala in Oregon City buy realigning the intersection, updating signal timing and adding si | Other | 04/27/2009 | 04/27/2009 |  | 14151.71 | 0
8551 | Oregon | UMATILLA |  | 2 | 5715013 | Pave Tutuilla Rd between US 395 (Southgate) and SW Athens Way in Umatilla County to improve safety and extend pavement life. | Pavement Improvement | 01/07/2010 |  |  | 336300 | 0
8552 | Oregon | UMATILLA |  | 2 | 5715014 | Pave Tutuilla Rd between US 395 (Southgate) and SW Athens Way in Umatilla County to improve safety and extend pavement life. | Other | 07/29/2009 | 07/29/2009 |  | 19959.51 | 0
8553 | Oregon | MULTNOMAH | PORTLAND (WA) | 1 | 5900175 | Improve safety and mobility for motorists, pedestrians and bicyclists and extend pavement life by reconstructing roadway, sidewalks and bikelanes on NW 23rd Ave between Lovejoy and Burnside. | Safety/Traffic Management | 01/04/2010 | 01/04/2010 |  | 432000 | 0
8554 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | 5900197 | Complete pavement preservation project on several streets in SE Portland to improve safety and extend the life of the pavement. | Pavement Improvement | 03/22/2010 | 03/25/2010 | 04/30/2011 | 2596002.47 | 0
8555 | Oregon | MULTNOMAH | PORTLAND (WA) | V | 5900201 | Improve bicycle safety and mobility by adding striping, signage and wayfinding to the Portland bicycle boulevard project. | Other | 07/21/2009 | 07/21/2009 |  | 100000 | 0
8556 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | 5900202 | Improve interesection safety and access by adding a right turn lane from 82nd Ave to westbound Columbia Blvd in Portland. | Other | 07/20/2009 | 07/20/2009 | 04/09/2011 | 200000 | 0
8557 | Oregon | MULTNOMAH | PORTLAND (WA) | V | 5900203 | Pave Springwater Trail between UPRR Bridge and the East City border in Portland to improve safety and extend the life of the pavement. | Other | 07/21/2009 | 07/21/2009 |  | 151000 | 0
8558 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | 5900204 | Complete pavement preservation project on several streets in SE Portland to improve safety and extend the life of the pavement. | Other | 08/05/2009 | 08/05/2009 |  | 15000 | 0
8559 | Oregon | MULTNOMAH | PORTLAND (WA) | V | 5900205 | Pave Springwater Trail between UPRR Bridge and the East City border in Portland to improve safety and extend the life of the pavement. | Pavement Improvement | 03/18/2010 | 05/06/2010 | 11/30/2010 | 1191463.06 | 0
8560 | Oregon | MULTNOMAH | PORTLAND (WA) | V | 5900207 | Improve safety and accessibility in southwest and east Portland with curb cuts and sidewalks on variuos streets. | Other | 08/05/2009 | 08/05/2009 |  | 300000 | 0
8561 | Oregon | MULTNOMAH | PORTLAND (WA) | V | 5900215 | Improve bicycle safety and mobility by adding striping, signage and wayfinding to the Portland bicycle boulevard project. | Transportation Enhancements | 03/09/2010 | 03/31/2010 | 03/31/2011 | 802179.44 | 0
8562 | Oregon | CROOK |  | 2 | 5985008 | Improve mobility and safety by adding 2nd Street egress to OR 126 (3rd St) in Prineville. | Other | 03/24/2009 | 03/24/2009 |  | 4126.71 | 0
8563 | Oregon | CROOK |  | 2 | 5985009 | Improve mobility and safety by adding 2nd Street egress to OR 126 (3rd St) in Prineville. | New Construction | 07/13/2009 | 08/24/2009 | 04/30/2010 | 284798.58 | 0
8564 | Oregon | CROOK |  | 2 | 5985010 | Pave several city streets in Prineville to improve safety and extend pavement life. | Pavement Improvement | 08/05/2009 | 09/02/2009 | 11/10/2009 | 217987 | 0
8565 | Oregon | CROOK |  | 2 | 5985011 | Pave several city streets in Prineville to improve safety and extend pavement life. | Other | 03/24/2009 | 03/24/2009 |  | 3312.4 | 0
8566 | Oregon | DESCHUTES |  | 2 | 6120009 | Improve safety by reconstructing 5th St between SW Glacier and Jackpine in Redmond. Project includes paving, stormwater system, curb repair and sidewalks. | Other | 02/23/2009 | 02/23/2009 |  | 3468 | 1.02
8567 | Oregon | DESCHUTES |  | 2 | 6120010 | Improve safety by reconstructing 5th St between SW Glacier and Jackpine in Redmond. Project includes paving, stormwater system, curb repair and sidewalks. | Pavement Improvement | 07/07/2009 | 08/03/2009 | 06/30/2010 | 3636425.62 | 1.02
8568 | Oregon | DOUGLAS |  | 4 | 6365002 | Pave Garden Valley Blvd between Stewart Pkwy and West City Line in Roseburg to improve safety and extend pavement life. | Pavement Improvement | 02/22/2010 |  |  | 658791 | 0
8569 | Oregon | COLUMBIA |  | 1 | 6460002 | Improve vehcile and pedestrian safety and extend pavement life on Columbia Blvd between US 30 and 1st St in St. Helens by paving and adding sidewalks, curb and gutter. | Pavement Improvement | 02/17/2010 |  |  | 203837 | 0
8570 | Oregon | COLUMBIA |  | 1 | 6460003 | Improve vehcile and pedestrian safety and extend pavement life on Columbia Blvd between US 30 and 1st St in St. Helens by paving and adding sidewalks, curb and gutter. | Other | 08/14/2009 | 08/14/2009 |  | 60000 | 0
8571 | Oregon | POLK |  | 5 | 6490071 | Preserve investment in Union Street Rail Road bridge shared use path in Salem by removing lead based paint and re-painting upper portion of the bridge. | Other | 05/11/2009 | 05/11/2009 |  | 20213.81 | 0
8572 | Oregon | MARION | SALEM | 5 | 6490072 | Pave sections of Hyacinth St, Chemawa Rd, Cordon Rd, Hawthorne Ave and Kuebler Blvd in Salem to improve safety and extend pavement life. | Other | 08/13/2009 | 08/13/2009 |  | 50000 | 0
8573 | Oregon | MARION | SALEM | 5 | 6490073 | Pave sections of Hyacinth St, Chemawa Rd, Cordon Rd, Hawthorne Ave and Kuebler Blvd in Salem to improve safety and extend pavement life. | Pavement Improvement | 03/08/2010 | 03/25/2010 | 09/30/2010 | 3736461.44 | 0
8574 | Oregon | MARION |  | 5 | 6490075 | Preserve investment in Union Street Rail Road bridge shared use path in Salem by removing lead based paint and re-painting upper portion of the bridge. | Transportation Enhancements | 10/16/2009 | 11/09/2009 | 05/31/2010 | 2066707.9 | 0
8575 | Oregon | POLK | SALEM | 5 | 6490077 | Improve bicycle and pedestrian safety and mobility by improving the bike / ped path in Wallace Marine Park from the Union St Bridge to Glen Creek Rd. | Other | 11/24/2009 | 11/24/2009 |  | 50000 | 0
8576 | Oregon | COLUMBIA |  | 1 | 6550002 | Improve safety along road by removing and replacing curb, gutter, sidewalk and street trees along US 30 between Old Portland Rd and Crown Zellerbach Rd in Scappoose. | Transportation Enhancements | 07/15/2009 | 08/05/2009 | 10/30/2009 | 251831.27 | 1.03
8577 | Oregon | COLUMBIA |  | 1 | 6550003 | Improve safety along road by removing and replacing curb, gutter, sidewalk and street trees along US 30 between Old Portland Rd and Crown Zellerbach Rd in Scappoose. | Other | 04/22/2009 | 04/22/2009 |  | 59079.34 | 1.03
8578 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | 6710003 | Pave Sherwood Blvd between 3rd St and Langer Dr in Sherwood to improve safety and extend pavement life. | Other | 08/26/2009 | 08/26/2009 |  | 23666.88 | 0
8579 | Oregon | LANE | EUGENE | 4 | 6900026 | Complete pavement preseravation project on 23rd St between Yolanda and Hayden Bridge Rd in Springfield to improve safety and extend the life of the pavement. | Other | 07/01/2009 | 07/01/2009 |  | 10000 | 0
8580 | Oregon | LANE | EUGENE | 4 | 6960020 | Complete pavement preservation project on Pioneer Parkway between Hayden Bridge and Q St in Springfield to improve safety and extend pavement life. | Other | 07/01/2009 | 07/01/2009 |  | 68314.84 | 0
8581 | Oregon | LANE | EUGENE | 4 | 6960021 | Complete pavement preservation project on Pioneer Parkway between Hayden Bridge and Q St in Springfield to improve safety and extend pavement life. | Pavement Improvement | 03/26/2010 | 04/20/2010 | 10/29/2010 | 2032000 | 0
8582 | Oregon | LANE | EUGENE | 4 | 6960029 | Improve safety and traffic flow on several city streets in Springfield retiming traffic signals. | Safety/Traffic Management | 01/12/2010 | 05/18/2010 |  | 199556.52 | 0
8583 | Oregon | LANE | EUGENE | 4 | 6960030 | Improve safety on several city streets in Springfield by replacing low pressure sodium lights with high pressure sodium and metal halide lights. | Other | 08/10/2009 | 08/10/2009 |  | 15000 | 0
8584 | Oregon | LANE | EUGENE | 4 | 6960031 | Improve safety and traffic flow on several city streets in Springfield retiming traffic signals. | Other | 08/13/2009 | 08/13/2009 |  | 10000 | 0
8585 | Oregon | JACKSON | MEDFORD | 2 | 7250009 | Improve safety and extend pavement life on several city streets in Talent and Phoenix by paving, addind additional signage and signals. | Other | 04/16/2009 | 04/16/2009 |  | 43161.49 | 0
8586 | Oregon | WASHINGTON | PORTLAND (WA) | V | 7365007 | Pave Bonita, Durham and 72nd Ave in Tigard to improve safety and extend pavement life. | Other | 08/21/2009 | 08/21/2009 |  | 46057.84 | 0
8587 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 8015000 | Pave Salamo Rd between Barrington Dr and Rosemont in West Linn to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 84710.75 | 0
8588 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 8015001 | Pave Salamo Rd between Barrington Dr and Rosemont in West Linn to improve safety and extend pavement life. | Pavement Improvement | 04/01/2010 |  |  | 814262.54 | 0
8589 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 8015002 | Improve pedestrian and bicycle safety and mobility by construcing the West Linn Trainl bike / ped path. | Other | 11/24/2009 | 11/24/2009 | 10/27/2011 | 250000 | 0
8590 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 8280005 | Improve vehicle, bicycle and pedestrian safety on Barber St between Boberg Rd and Boones Ferry Rd in Wilsonville by widening to allow for bike lanes and sidewalks on both sides and a center turn lane. | Other | 08/26/2009 | 08/26/2009 |  | 24499.83 | 0
8591 | Oregon | CLACKAMAS | PORTLAND (WA) | 5 | 8280006 | Improve vehicle, bicycle and pedestrian safety on Barber St between Boberg Rd and Boones Ferry Rd in Wilsonville by widening to allow for bike lanes and sidewalks on both sides and a center turn lane. | Transportation Enhancements | 04/19/2010 | 06/03/2010 |  | 623424.35 | 0
8592 | Oregon | HARNEY |  | 2 | C001011 | Pave Wingville Ln from mile point 0 to milp point 4.76 in Baker County to improve safety and extend pavement life. | Pavement Improvement | 03/01/2010 |  |  | 417238.82 | 0
8593 | Oregon | BAKER |  | 2 | C001012 | Pave Wingville Ln from mile point 0 to milp point 4.76 in Baker County to improve safety and extend pavement life. | Other | 07/21/2009 | 07/21/2009 |  | 13271.77 | 0
8594 | Oregon | BENTON |  | 4 | C003035 | Pave Alpine Rd in Benton County to improve safety and extend pavement life. | Pavement Improvement | 07/20/2009 | 07/20/2009 | 07/24/2009 | 317997.56 | 0
8595 | Oregon | BENTON |  | 5 | C003036 | Improve safety to pedestrians and bicyclists by repaving the Campus Way multi-use bicycle and pedestrian path between 35th St and 53rd St in Corvallis. | Pavement Improvement | 07/02/2009 | 07/06/2009 | 07/29/2009 | 90000 | 0
8596 | Oregon | BENTON |  | 5 | C003037 | Pave Springhill Dr between Buena Vista Rd and Independence Hwy to improve safety and extend pavement life. | Pavement Improvement | 03/10/2010 |  | 07/30/2010 | 171902.44 | 0
8597 | Oregon | CLATSOP |  | 1 | C007023 | Pave Lewis & clark Rd between Tucker Creek Rd and Lyngstad Heights Rd in Clatsop County to improve safety and extend pavement life. | Other | 06/11/2009 | 06/11/2009 |  | 17125.84 | 0
8598 | Oregon | CLATSOP |  | 1 | C007024 | Pave Lewis & clark Rd between Tucker Creek Rd and Lyngstad Heights Rd in Clatsop County to improve safety and extend pavement life. | Pavement Improvement | 12/09/2009 | 04/19/2010 | 06/15/2010 | 481530 | 0
8599 | Oregon | CLATSOP |  | 1 | C007025 | Improve pedestrian and bicycle safety and access by constructing shared-use paths, rest/view sites, and gazebo shelters on the Port of Astoria Pedestrian Access Paths. | Transportation Enhancements | 02/16/2010 | 04/05/2010 | 08/06/2010 | 432686.09 | 0
8600 | Oregon | COLUMBIA |  | 1 | C009055 | Pave Apiary Rd between mile point 14 and mile point 19 in Columbia County to improve safety and extend pavement life. | Other | 06/09/2009 | 06/09/2009 |  | 50947.86 | 0
8601 | Oregon | COLUMBIA |  | 1 | C009056 | Pave Apiary Rd between mile point 14 and mile point 19 in Columbia County to improve safety and extend pavement life. | Safety/Traffic Management | 10/09/2009 | 05/10/2010 |  | 719692.52 | 0
8602 | Oregon | COOS |  | 4 | C011057 | Pave and add additional signage to Central Blvd between OR 42 and 10th St in Coos County to improve safety and extend pavement life. | Pavement Improvement | 02/26/2010 |  |  | 401970 | 0
8603 | Oregon | COOS |  | 4 | C011058 | Pave and add additional signage to Central Blvd between OR 42 and 10th St in Coos County to improve safety and extend pavement life. | Other | 06/12/2009 | 06/12/2009 |  | 60000 | 0
8604 | Oregon | COOS |  | 4 | C011059 | Repair the Anson Rogers Bridge on South Coos River Rd in Coos County to improve safety and extend the life of the bridge. | Other | 06/10/2009 | 06/10/2009 |  | 50000 | 0
8605 | Oregon | COOS |  | 4 | C011060 | Pave Sherman Ave between Newmark St and City Limits in North Bend to improve safety and extend pavement life. | Other | 08/14/2009 | 08/14/2009 |  | 1748.6 | 0
8606 | Oregon | COOS |  | 4 | C011061 | Repair the Anson Rogers Bridge on South Coos River Rd in Coos County to improve safety and extend the life of the bridge. | Bridge Improvement | 02/03/2010 | 03/23/2010 | 08/31/2010 | 365000 | 0
8607 | Oregon | CROOK |  | 2 | C013015 | Pave Lone Pine Rd and Smith Rock Way in Crook County to improve safety and extend pavement life. | Pavement Improvement | 01/12/2010 | 04/09/2010 | 04/30/2010 | 404763 | 0
8608 | Oregon | CROOK |  | 2 | C013016 | Pave Lone Pine Rd and Smith Rock Way in Crook County to improve safety and extend pavement life. | Other | 05/05/2009 | 05/05/2009 |  | 23351.47 | 0
8609 | Oregon | DESCHUTES |  | 2 | C017013 | Pave Huntington Rd and Riverview Rd between South Century Drive and Burgess Rd in Deschutes County to improve safety and extend pavement life. | Pavement Improvement | 08/27/2009 | 09/30/2009 | 10/19/2009 | 1074637.3 | 0
8610 | Oregon | DESCHUTES |  | 2 | C017014 | Pave Huntington Rd and Riverview Rd between South Century Drive and Burgess Rd in Deschutes County to improve safety and extend pavement life. | Other | 05/03/2009 | 05/03/2009 |  | 19841.7 | 0
8611 | Oregon | DOUGLAS |  | 4 | C019036 | Pave Dillard Hwy between mile point .71 and mile point 5.85 in Douglas County to improve safety and extend pavement life. | Other | 06/14/2009 | 06/14/2009 |  | 28087.55 | 0
8612 | Oregon | DOUGLAS |  | 4 | C019037 | Pave Dillard Hwy between mile point .71 and mile point 5.85 in Douglas County to improve safety and extend pavement life. | Pavement Improvement | 10/09/2009 | 03/12/2010 |  | 1516177.45 | 0
8613 | Oregon | GRANT |  | 2 | C023007 | Pave County Rd 51 (Adams Rd) between MP 0 and MP 3.24 to improve safety and extend pavement life. | Pavement Improvement | 03/18/2010 | 05/14/2010 |  | 336793.25 | 0
8614 | Oregon | HARNEY |  | 2 | C025019 | Place chip seal on Silver Creek Rd and Green House Ln in Harney County to improve safety and extend pavement life. | Pavement Improvement | 09/16/2009 | 09/23/2009 |  | 427396.72 | 0
8615 | Oregon | HARNEY |  | 2 | C025021 | Place chip seal on Silver Creek Rd and Green House Ln in Harney County to improve safety and extend pavement life. | Other | 07/21/2009 | 07/21/2009 |  | 5750.58 | 0
8616 | Oregon | HOOD RIVER |  | 2 | C027013 | Pave Belmont Dr and Cooper Spur Rd in Hood River County to improve safety and extend pavement life. | Other | 05/15/2009 | 05/15/2009 |  | 100000 | 0
8617 | Oregon | HOOD RIVER |  | 2 | C027014 | Pave Belmont Dr and Cooper Spur Rd in Hood River County to improve safety and extend pavement life. | Pavement Improvement | 03/09/2010 |  |  | 326419 | 0
8618 | Oregon | JACKSON |  | 2 | C029058 | Pave several county roads in Jackson County to improve safety and extend pavement life. | Other | 04/29/2009 | 04/29/2009 |  | 84998.86 | 0
8619 | Oregon | JACKSON |  | 2 | C029059 | Improve pedestrian and bicycle safety and access by constructing a shared use path on Barnett Rd in Jackson County. | Transportation Enhancements | 10/07/2009 | 11/16/2009 | 07/31/2010 | 1027699 | 0
8620 | Oregon | JACKSON |  | 2 | C029061 | Pave several county roads in Jackson County to improve safety and extend pavement life. | Pavement Improvement | 09/10/2009 | 10/06/2009 | 11/19/2009 | 1390795 | 0
8621 | Oregon | JEFFERSON |  | 2 | C031004 | Pave Lone Pine Rd from mile point 0 to mile point 3.7 in Jefferson County to improve safety and extend pavement life. | Pavement Improvement | 09/03/2009 | 10/01/2009 | 11/20/2009 | 448488.35 | 0
8622 | Oregon | JEFFERSON |  | 2 | C031005 | Pave Lone Pine Rd from mile point 0 to mile point 3.7 in Jefferson County to improve safety and extend pavement life. | Other | 05/05/2009 | 05/05/2009 |  | 15527.2 | 0
8623 | Oregon | JOSEPHINE |  | 4 | C033031 | Pave Old Hwy 99 from mile point 0 to mile point .67 in Josephine County to improve safety and extend pavement life. | Other | 06/04/2009 | 06/04/2009 |  | 1386.94 | 0
8624 | Oregon | JOSEPHINE |  | 4 | C033032 | Pave Old Hwy 99 from mile point 0 to mile point .67 in Josephine County to improve safety and extend pavement life. | Pavement Improvement | 08/17/2009 | 09/28/2009 | 10/30/2009 | 203390.44 | 0
8625 | Oregon | KLAMATH |  | 2 | C035024 | Improve safety on Washburn Way between Crosby and Joe Wright Rd in Klamath Falls by paving and adding additional signage. | Other | 05/01/2009 | 05/01/2009 |  | 55810.71 | 0
8626 | Oregon | KLAMATH |  | 2 | C035025 | Improve safety on Washburn Way between Crosby and Joe Wright Rd in Klamath Falls by paving and adding additional signage. | Pavement Improvement | 08/10/2009 | 09/09/2009 | 10/23/2009 | 1032597.72 | 0
8627 | Oregon | LANE | EUGENE | 4 | C039027 | Enhance safety to pedestrians and bicyclists by repaving the EWEB Bike Path between Pioneer Parkway and 31st street in Eugene. | Pavement Improvement | 07/15/2009 | 07/20/2009 | 09/30/2009 | 314268.1 | 0
8628 | Oregon | LANE |  | 4 | C039028 | Pave Clear Lake Rd and Marcola Rd in Lane County to improve safety and extend pavement life. | Other | 05/07/2009 | 05/07/2009 |  | 75420.85 | 0
8629 | Oregon | LANE |  | 4 | C039029 | Pave Clear Lake Rd and Marcola Rd in Lane County to improve safety and extend pavement life. | Pavement Improvement | 12/17/2009 |  |  | 1596640.02 | 0
8630 | Oregon | LANE | EUGENE | 4 | C039030 | Complete pavement preservation project on River Rd, 23rd St and Coburg Rd in Eugene to improve safety and extend the life of the pavement. | Other | 06/04/2009 | 06/04/2009 |  | 40000 | 0
8631 | Oregon | LANE | EUGENE | 4 | C039031 | Complete pavement preservation project on River Rd, 23rd St and Coburg Rd in Eugene to improve safety and extend the life of the pavement. | Pavement Improvement | 12/17/2009 |  |  | 1013064.98 | 0
8632 | Oregon | LANE | EUGENE | 4 | C039032 | Complete pavement preservation project on W 1st Ave between Seneca Rd and Bertelsen Rd in Eugene to improve safety and extend the life of the pavement. | Other | 06/11/2009 | 06/11/2009 |  | 26000 | 0
8633 | Oregon | LINCOLN |  | 5 | C041009 | Pave Northbank Rd and Schooner Creek Rd in Lincoln County to improve safety and extend pavement life. | Other | 05/05/2009 | 05/05/2009 |  | 44063.54 | 0
8634 | Oregon | LINCOLN |  | 5 | C041010 | Pave Northbank Rd and Schooner Creek Rd in Lincoln County to improve safety and extend pavement life. | Pavement Improvement | 08/24/2009 | 09/11/2009 | 10/21/2009 | 822455 | 0
8635 | Oregon | LINN |  | 4 | C043021 | Pave Stayton-Scio Rd and Oakville Rd in Linn County to improve safety and extend pavement life. | Other | 05/07/2009 | 05/07/2009 |  | 42692.83 | 0
8636 | Oregon | LINN |  | 4 | C043022 | Pave Stayton-Scio Rd and Oakville Rd in Linn County to improve safety and extend pavement life. | Pavement Improvement | 09/17/2009 | 09/21/2009 | 11/24/2009 | 1237130 | 0
8637 | Oregon | MALHEUR |  | 2 | C045025 | Pave Foothill Dr, Halliday St and Railroad Ave in Malheur County to improve safety and extend pavement life. | Pavement Improvement | 02/05/2010 |  |  | 765592 | 0
8638 | Oregon | MALHEUR |  | 2 | C045026 | Pave Foothill Dr, Halliday St and Railroad Ave in Malheur County to improve safety and extend pavement life. | Other | 01/14/2009 | 01/14/2009 |  | 12689.19 | 0
8639 | Oregon | MARION | SALEM | 5 | C047041 | Pave several county roads in Marion County and Young St in Woodburn to improve safety and extend pavement life. | Pavement Improvement | 08/28/2009 |  |  | 1636132.72 | 0
8640 | Oregon | MARION | SALEM | 5 | C047042 | Pave sections of Auburn Rd, Hazelgreen Rd, State St, Turner Rd, Center St, Ward Dr and Brown Rd in Marion County (Salem and Keizer) to improve safety and extend pavement life. | Other | 06/05/2009 | 06/05/2009 | 07/23/2009 | 2253.58 | 0
8641 | Oregon | MARION | SALEM | 5 | C047043 | Pave sections of Auburn Rd, Hazelgreen Rd, State St, Turner Rd, Center St, Ward Dr and Brown Rd in Marion County (Salem and Keizer) to improve safety and extend pavement life. | Pavement Improvement | 08/28/2009 | 10/26/2009 | 06/30/2010 | 1513140.52 | 0
8642 | Oregon | MARION |  | 5 | C047044 | Pave several county roads in Marion County and Young St in Woodburn to improve safety and extend pavement life. | Other | 06/19/2009 | 06/19/2009 | 07/23/2009 | 10000 | 0
8643 | Oregon | MARION | SALEM | 5 | C047047 | Upgrade signals at Lancaster Dr and Durbin to improve safety and traffic flow. | Other | 07/27/2009 | 07/27/2009 |  | 47458.89 | 0
8644 | Oregon | MARION | SALEM | 5 | C047048 | Upgrade signals at Lancaster Dr and Durbin to improve safety and traffic flow. | Safety/Traffic Management | 03/23/2010 |  |  | 318009.56 | 0
8645 | Oregon | MARION |  | 5 | C047049 | Improve access by replacing Buena Vista Ferry Boat and make improvements to ferry terminal. | Other | 12/22/2009 | 12/22/2009 |  | 534000 | 0
8646 | Oregon | MARION | SALEM | 5 | C047051 | Pave Cordon Rd, Garfield St, Harrison St and Cleaveland in Salem to improve safety and extend pavement life. | Pavement Improvement | 03/31/2010 |  |  | 350518.28 | 0
8647 | Oregon | MARION |  | 5 | C047052 | Pave Cordon Rd, Garfield St, Harrison St and Cleaveland in Salem to improve safety and extend pavement life. | Other | 01/13/2010 | 01/13/2010 |  | 5000 | 0
8648 | Oregon | MORROW |  | 2 | C049013 | Pave Upper Rhea Creek Rd from mile point 2.2 to mile point 4.5 in Morrow County to improve safety and extend pavement life. | Pavement Improvement | 10/07/2009 | 10/22/2009 | 11/30/2009 | 509211 | 0
8649 | Oregon | MULTNOMAH |  | 3 | C051070 | Improve safety and mobility at the intersection of 282nd Ave and Stone Rd in Multnomah County by widening 282nd Ave to provide left turn lanes and widening and aligning Stone Rd. | Pavement Improvement | 05/05/2008 | 05/22/2008 | 06/30/2009 | 184655 | 0
8650 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | C051080 | Improve safety on NW Cornelius Pass Rd in Portland by installing signs and signals and repairing guardrail. | Safety/Traffic Management | 10/07/2009 | 12/22/2009 | 03/31/2010 | 205161.11 | 0
8651 | Oregon | MULTNOMAH | PORTLAND (WA) | 1 | C051081 | Improve pedestrian safety and access by constructing sidwalks on Halsey St and Stark St in Multnomah County. | Other | 06/05/2009 | 06/05/2009 |  | 40000.07 | 0
8652 | Oregon | MULTNOMAH |  | 3 | C051082 | Improve safety on NW Cornelius Pass Rd in Portland by installing signs and signals and repairing guardrail. | Other | 06/11/2009 | 06/11/2009 |  | 11934.38 | 0
8653 | Oregon | MULTNOMAH | PORTLAND (WA) | 1 | C051083 | Pave city streets and perform sealing and crack repair to concrete pavement in Tigard, Sherwood and Cornelius to improve safety and extend pavement life. | Pavement Improvement | 03/12/2010 | 04/05/2010 | 06/15/2010 | 1312205.06 | 0
8654 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | C051085 | Pave various streets in Multnomah County tp improve safety and extend pavement life. | Pavement Improvement | 04/13/2010 |  |  | 1210980.78 | 0
8655 | Oregon | POLK |  | 5 | C053033 | Pave Falls City Rd from mile point 0 to mile point 3.8 in Polk County to improve safety and extend pavement life. | Pavement Improvement | 09/17/2009 | 10/07/2009 | 10/29/2009 | 403929 | 0
8656 | Oregon | POLK |  | 5 | C053034 | Pave Falls City Rd from mile point 0 to mile point 3.8 in Polk County to improve safety and extend pavement life. | Other | 06/09/2009 | 06/09/2009 |  | 29670.72 | 0
8657 | Oregon | TILLAMOOK |  | 5 | C057034 | Repave Long Prairie Rd and the Johnson Bridge Rd approaches in Tillamook county to improve safety and extend pavement life. | Pavement Improvement | 08/07/2009 | 09/16/2009 | 12/31/2009 | 626548 | 0
8658 | Oregon | UMATILLA |  | 2 | C059038 | Pave Despain Gulch Rd between Pendleton-Cold Springs Hwy and mile point 6 in Umatilla County to improve safety and extend pavement life. | Pavement Improvement | 11/24/2009 | 05/03/2010 | 07/31/2010 | 979867.34 | 0
8659 | Oregon | UMATILLA |  | 2 | C059039 | Pave Despain Gulch Rd between Pendleton-Cold Springs Hwy and mile point 6 in Umatilla County to improve safety and extend pavement life. | Other | 07/29/2009 | 07/29/2009 |  | 12820.55 | 0
8660 | Oregon | WALLOWA |  | 2 | C063018 | Pave Upper Diamond Ln between OR 82 and Lower Diamond Ln in Wallowa County to improve safety and extend pavement life. | Pavement Improvement | 02/26/2010 |  |  | 359219 | 0
8661 | Oregon | WALLOWA |  | 2 | C063019 | Pave Upper Diamond Ln between OR 82 and Lower Diamond Ln in Wallowa County to improve safety and extend pavement life. | Other | 09/09/2009 | 09/09/2009 |  | 8388.26 | 0
8662 | Oregon | WASCO |  | 2 | C065018 | Pave severla county roads in Wasco County to improve safety and extend pavement life. | Pavement Improvement | 11/02/2009 |  |  | 424744.05 | 0
8663 | Oregon | WASCO |  | 2 | C065019 | Pave severla county roads in Wasco County to improve safety and extend pavement life. | Other | 04/23/2009 | 04/23/2009 |  | 11349.99 | 0
8664 | Oregon | WASHINGTON |  | 1 | C067063 | Pave several county roads in Washington County to improve safety and extend pavement life. | Other | 05/06/2009 | 05/06/2009 |  | 97000 | 0
8665 | Oregon | WASHINGTON |  | 1 | C067064 | Improve safety by installing upgraded bridge guardrail on several bridges in Washington County. | Other | 05/06/2009 | 05/06/2009 |  | 50000 | 0
8666 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067065 | Improve school zone safety by installing new solar powered school zone flasher units at several school zones in Washington County. | Other | 05/06/2009 | 05/06/2009 |  | 37013.19 | 0
8667 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067066 | Improve safety and traffic flow on several streets in Washington County by installing new signal hardware to include flasshing yellow arrows and replacing illuminated signs. | Other | 06/11/2009 | 06/11/2009 |  | 43733.73 | 0
8668 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067067 | Pave several city streets in Washington County to improve safety and extend pavement life. | Other | 05/07/2009 | 05/07/2009 |  | 167696.22 | 0
8669 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067068 | Improve mobility and traffic flow at several intersections in Washington County by evaluating signal timing and making changes to the signal timing as necessary. | Safety/Traffic Management | 05/28/2009 | 05/28/2009 | 09/01/2010 | 600000 | 0
8670 | Oregon | WASHINGTON |  | 1 | C067069 | Pave several county roads in Washington County to improve safety and extend pavement life. | Pavement Improvement | 02/18/2010 | 03/18/2010 | 05/31/2010 | 864192.15 | 0
8671 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067070 | Pave several city streets in Washington County to improve safety and extend pavement life. | Pavement Improvement | 02/18/2010 | 03/18/2010 | 06/15/2010 | 1498098.91 | 0
8672 | Oregon | WASHINGTON |  | 1 | C067071 | Improve pedestrian and bicycle safety and mobility by constructing Banks-Vernonia Train between South Trailhead and Banks Rd. Improve trailhead parking and provide landscaping. | Transportation Enhancements | 03/23/2010 | 05/17/2010 |  | 248126.56 | 0
8673 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067072 | Improve school zone safety by installing new solar powered school zone flasher units at several school zones in Washington County. | Safety/Traffic Management | 10/07/2009 | 12/15/2009 | 01/04/2010 | 225000 | 0
8674 | Oregon | STATEWIDE | PORTLAND (WA) | 1 | C067073 | Improve safety and traffic flow on several streets in Washington County by installing new signal hardware to include flasshing yellow arrows and replacing illuminated signs. | Safety/Traffic Management | 12/09/2009 | 02/15/2010 | 06/30/2010 | 470809.12 | 0
8675 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067076 | Improve safety by installing emergency vehicle signal pre-emption devices at approximately 86 intersections in Washington County. | Other | 08/28/2009 | 08/28/2009 |  | 21826 | 0
8676 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067078 | Improve safety and traffic flow by installing traffic video detection equipment at 20 intersections in Washington County and Tigard. | Safety/Traffic Management | 04/13/2010 |  |  | 599360.24 | 0
8677 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067080 | Improve safety and traffic flow by installing traffic video detection equipment at 20 intersections in Washington County and Tigard. | Other | 09/01/2009 | 09/01/2009 |  | 17796.28 | 0
8678 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067081 | Improve pedestrian safety by installing pedestrian countdown timers at approximately 150 intersections in Washington County. | Other | 08/28/2009 | 08/28/2009 |  | 48199 | 0
8679 | Oregon | WASHINGTON | PORTLAND (WA) | 1 | C067082 | Improve pedestrian safety by adding pedestrian countdown timers and improve emergency response by adding emergency signal pre-emption to several intersections in Washington County. | Safety/Traffic Management | 02/09/2010 |  | 12/31/2010 | 597129.9 | 0
8680 | Oregon | WASHINGTON |  | 1 | C067083 | Improve safety by installing upgraded bridge guardrail on several bridges in Washington County. | Safety/Traffic Management | 03/25/2010 | 05/28/2010 |  | 200000 | 0
8681 | Oregon | WASHINGTON |  | 1 | C067084 | Improve pedestrian and bicycle safety and mobility by constructing Banks-Vernonia Train between South Trailhead and Banks Rd. Improve trailhead parking and provide landscaping. | Transportation Enhancements | 12/01/2009 | 12/01/2009 |  | 120965.76 | 0
8682 | Oregon | WHEELER |  | 2 | C069001 | Pave Upper Rowe Creek Rd in Wheeler County to improve safety and extend pavement life. | Pavement Improvement | 03/18/2010 | 05/26/2010 |  | 199543 | 0
8683 | Oregon | WHEELER |  | 2 | C069002 | Pave Upper Rowe Creek Rd in Wheeler County to improve safety and extend pavement life. | Other | 10/14/2009 | 10/14/2009 |  | 16729.23 | 0
8684 | Oregon | YAMHILL |  | 1 | C071014 | Pave Baker Creek Rd between Michelbrook Ln and Power House Hill Rd in Yamhill County to improve safety and extend pavement life. | Pavement Improvement | 07/14/2009 | 08/10/2009 | 09/03/2009 | 731685.88 | 0
8685 | Oregon | YAMHILL |  | 1 | C071015 | Pave various roads in Yamhill County to improve safety and extend pavement life. | Pavement Improvement | 03/02/2010 | 05/17/2010 |  | 200180 | 0
8686 | Oregon | YAMHILL |  | 1 | C071016 | Pave various roads in Yamhill County to improve safety and extend pavement life. | Other | 01/06/2010 | 01/06/2010 |  | 291.87 | 0
8687 | Oregon | JOSEPHINE |  | 4 | S000312 | Preserves road by extending current project replacing poor pavement on OR 99 and OR 238 in Josephine County. | Other | 10/31/2006 | 10/31/2006 |  | 18193.32 | 4.47
8688 | Oregon | JOSEPHINE |  | 4 | S000393 | Preserves road by extending current project replacing poor pavement on OR 99 and OR 238 in Josephine County. | Pavement Improvement | 02/25/2009 | 03/03/2009 | 10/30/2009 | 3025555.32 | 4.47
8689 | Oregon | UMATILLA |  | 2 | S000431 | Improves safety of a dangerous rail crossing on US 30 between Pendleton and Athena through reconstruction and paving. | Pavement Improvement | 05/19/2009 | 06/24/2009 | 08/15/2010 | 899516.23 | 16.34
8690 | Oregon | LINCOLN |  | 5 | S000457 | Improve safety on US 20 between Pioneer Mountain Loop Rd and Yaquina River in Lincoln County by removing narrow, winding roads. | Other | 07/09/2009 | 07/09/2009 | 12/17/2009 | 317976.23 | 6.51
8691 | Oregon | STATEWIDE |  | 4 | S000481 | Enhance safety by replacing damaged or substandard guardrail on OR 219, OR 34, OR 58, OR 126, and US 101. | Safety/Traffic Management | 07/02/2009 | 02/08/2010 | 04/30/2010 | 1075678.38 | 0
8692 | Oregon | BAKER |  | 2 | S000485 | Improve safety for motorists and pedestrians by paving and adding curb and gutter to Birch Street in Baker City. | Pavement Improvement | 05/22/2009 | 06/08/2009 | 10/28/2009 | 648626.83 | 0
8693 | Oregon | BAKER |  | 2 | S000489 | Improve safety by replacing the aging Dewey Ave Union Pacific rail-road crossing on OR 7in Baker City. | Pavement Improvement | 05/22/2009 | 06/08/2009 | 11/30/2009 | 1485113.71 | 0.01
8694 | Oregon | STATEWIDE |  | V | S000493 | Improve mobility and safety at 277 intersections in the Portland Metropolitan reagion by installing 2070 signal controllers and updating signal control software at the intersections. | Other | 04/09/2009 | 04/09/2009 |  | 397300 | 0
8695 | Oregon | STATEWIDE |  | V | S000497 | Improve mobility and safety at 277 intersections in the Portland Metropolitan reagion by installing 2070 signal controllers and updating signal control software at the intersections. | Other | 07/07/2009 | 01/11/2010 | 07/02/2010 | 2771491.58 | 0
8696 | Oregon | STATEWIDE |  | 4 | S000499 | Improves safety by replacing or retrofitting restrooms at rest areas in Western Oregon. | Other | 05/05/2009 | 05/05/2009 | 08/11/2009 | 4398.52 | 0
8697 | Oregon | STATEWIDE |  | 4 | S000501 | Improves safety by replacing or retrofitting restrooms at rest areas in Western Oregon. | Pavement Improvement | 08/01/2009 | 08/01/2009 |  | 830000 | 0
8698 | Oregon | LINN |  | V | S000502 | Enhance freight operations by repairing 7 miles of track in along the Albany & Eastern Rail Road rail line. | Other | 05/05/2009 | 05/05/2009 |  | 30000 | 0
8699 | Oregon | CROOK |  | V | S000503 | Enhance freight operations by repairing unsafe track in Prineville. | Other | 05/06/2009 | 05/06/2009 |  | 20000 | 0
8700 | Oregon | LINN |  | V | S000504 | Improve safety at 7 rail road crossings and replace track on the Portland & Western Rail Road in Portland. | Other | 05/06/2009 | 05/06/2009 |  | 50000 | 0
8701 | Oregon | LANE |  | V | S000505 | Enhance freight operations by repairing unsafe track on the Coos Bay Rail Line in Coos Bay. | Other | 05/03/2009 | 05/03/2009 |  | 20000 | 0
8702 | Oregon | MORROW |  | V | S000506 | Enhance shipping by adding additional rail capacity at the Port of Morrow in Morrow County. | Other | 05/07/2009 | 05/07/2009 | 06/04/2009 | 30000 | 0
8703 | Oregon | MULTNOMAH | PORTLAND (WA) | V | S000507 | Enhance mobility with improved switching on the North Portland Junction crossovers in Portland. | Other | 05/18/2009 | 05/18/2009 |  | 50000 | 0
8704 | Oregon | BAKER |  | 2 | S000513 | Improve safety for motorists and pedestrians by paving and adding curb and gutter to Birch Street in Baker City. | Other | 04/30/2009 | 04/30/2009 |  | 24337.15 | 0
8705 | Oregon | LINN |  | V | S000516 | Improve safety at 7 rail road crossings and replace track on the Portland & Western Rail Road in Portland. | Safety/Traffic Management | 06/18/2009 | 06/18/2009 | 06/30/2010 | 1427700 | 0
8706 | Oregon | STATEWIDE |  | 2 | S000522 | Improves safety by replacing or retrofitting restrooms at 6 rest areas in Eastern Oregon. Repave one rest area. | Other | 06/19/2009 | 06/19/2009 |  | 9726.72 | 0
8707 | Oregon | CURRY |  | 4 | S000542 | Pave various roads in Curry County and the City of Brookings to improve safety and extend pavement life. | Pavement Improvement | 02/24/2010 | 05/03/2010 |  | 610279 | 0
8708 | Oregon | STATEWIDE |  | V | S000544 | Improve Oregon Workforce Development Program by providing on-the-job training and supportive services program to transportation related careers. | Other | 10/21/2009 | 10/21/2009 |  | 880000 | 0
8709 | Oregon | DOUGLAS |  | 4 | S001233 | Improves pedestrian access and safety by extending fairground multi-use path in Roseburg. | Transportation Enhancements | 05/05/2008 | 06/03/2008 | 10/05/2009 | 433118.2 | 0
8710 | Oregon | DOUGLAS |  | 4 | S001329 | Improves safety on I5 between Booth Rand and Glendale in Douglas county by replacing poor pavement. | Pavement Improvement | 05/13/2009 | 06/04/2009 | 12/02/2010 | 7074682 | 29.49
8711 | Oregon | JACKSON |  | 2 | S001332 | Improve safety by replacing pavement worn down by chains, severe weather on 11 miles of I-5 in Ashland. | Pavement Improvement | 05/01/2009 | 05/11/2009 | 10/29/2009 | 2154263.69 | 11
8712 | Oregon | STATEWIDE |  | 4 | S001333 | Improve safety by replacing worn striping on I-5 between mile point 18 and 168. | Safety/Traffic Management | 04/23/2009 | 06/03/2009 | 09/24/2009 | 1921586.41 | 150
8713 | Oregon | MARION |  | 5 | S001338 | Reduce truck crash probability on I-5 in Marion County by replacing substandard barriers. | Safety/Traffic Management | 06/23/2009 | 10/15/2009 | 05/27/2010 | 4518000.82 | 12.63
8714 | Oregon | WASHINGTON |  | 1 | S001339 | Pavement overlay of I-5 between Tualitin River Bridge and Willsonville Rd to improve traffic flow for vehicles merging on and off the freeway; added cable barrier to reduce risk of fatal crashes. | Pavement Improvement | 05/21/2009 | 06/08/2009 | 10/31/2010 | 3675781.89 | 6.37
8715 | Oregon | CLACKAMAS |  | 5 | S001357 | Improve awareness on the Oregon Solar Highway System by installing an interpretative display at the I-5 Baldock rest area. | Other | 10/27/2009 | 10/27/2009 | 12/31/2010 | 50000 | 0
8716 | Oregon | LINN |  | 4 | S001358 | Improve awareness on the Oregon Solar Highway System by installing an interpretative display at the I-5 Baldock rest area. | Pavement Improvement | 04/29/2010 |  |  | 7275661.3 | 13.14
8717 | Oregon | JACKSON |  | 2 | S001361 | Install welcome sign on I-5 northbound in Jackson County. | Other | 11/09/2009 | 11/09/2009 |  | 27449.98 | 0
8718 | Oregon | JACKSON |  | 2 | S001363 | Install welcome sign on I-5 northbound in Jackson County. | Other | 03/22/2010 |  |  | 339446.31 | 0
8719 | Oregon | STATEWIDE |  | V | S002079 | Repair and reconstruct access control fencing along I-84 between Sandy River and The Dalles to reduce weather/animal-related crashes. | Pavement Improvement | 06/02/2009 | 07/19/2009 | 08/31/2010 | 299999.61 | 44.2
8720 | Oregon | UMATILLA |  | 2 | S002109 | Builds rockfall screen along busy section of I-84 over Cabbage Hill to improve safety. | Safety/Traffic Management | 05/26/2009 | 08/24/2009 | 09/16/2009 | 206652.17 | 8.11
8721 | Oregon | MULTNOMAH | PORTLAND (WA) | 3 | S002110 | Enhances mobility by adding a right turn lane to I-84 exit at 257th in Troutdale. | Pavement Widening | 06/26/2009 | 08/10/2009 | 03/31/2010 | 602567.5 | 0.89
8722 | Oregon | GILLIAM |  | 2 | S002112 | Improve safety and extend pavement life on I-84 between Rufus and Swanson Canyon by repairing and chip sealing existing pavement. | Pavement Improvement | 04/21/2010 |  |  | 191959.3 | 0
8723 | Oregon | DESCHUTES |  | 2 | S004120 | Enhance safety on US 97 between Lava Butte and S Century Driver by adding lanes and access routes in Deschutes County. Improves safety by restoring fencing and crossing enhancements at the US 97 Lava | Pavement Improvement | 06/11/2009 | 06/22/2009 | 11/30/2011 | 11736733.38 | 10.73
8724 | Oregon | WASCO |  | 2 | S004125 | Enhances bicycle and pedestrian safety by building sidewalks, curbs, and multi-use paths on US 197 between Burnham Ave and 3rd St in Maupin. | Transportation Enhancements | 01/27/2009 | 02/11/2009 | 09/18/2009 | 800000 | 0.32
8725 | Oregon | WASCO |  | 2 | S004132 | Improve safety in extreme weather area by extending current pavement project on US 197 between The Dalles and Eight Mile Creek. | Pavement Improvement | 06/16/2009 | 07/31/2009 | 03/31/2010 | 3150982 | 5.68
8726 | Oregon | KLAMATH |  | 2 | S004133 | Improve safety and mobility by adding a 2 mile passing lane to US 97 at mile point 230 in Klamath County. | Pavement Improvement | 06/04/2009 | 06/22/2009 | 08/31/2010 | 5450893.73 | 5
8727 | Oregon | DESCHUTES |  | 2 | S004136 | Improves mobility and safety by installing an adaptive traffic signal control system at 19 intersections in Redmond. | Other | 03/13/2009 | 03/13/2009 |  | 80412.1 | 0
8728 | Oregon | DESCHUTES |  | 2 | S004137 | Improves mobility and safety by installing an adaptive traffic signal control system at 19 intersections in Redmond. | Safety/Traffic Management | 07/13/2009 | 08/17/2009 | 05/31/2010 | 1327816.22 | 0
8729 | Oregon | HARNEY |  | 2 | S007051 | Complete pavement preservation project on US 20 between Bulger Creek and Riley Junction in Hines. | Pavement Improvement | 05/20/2009 | 06/11/2009 | 07/31/2010 | 7046699.91 | 23.2
8730 | Oregon | TILLAMOOK |  | 5 | S009317 | Repave US 101 between 12th St and Farmer Creek Rd in Tillamook to improve safety and reduce maintainance costs by preventing water permeation. | Pavement Improvement | 04/29/2009 | 03/30/2010 | 08/31/2010 | 6175378.86 | 16.72
8731 | Oregon | DOUGLAS |  | 4 | S009323 | Improves safety along US 101 and OR 38 between Reedsport and Winchester Bay by repaving poor highway and upgrading sidewalks. | Pavement Improvement | 03/23/2009 | 04/20/2009 | 02/25/2010 | 781361.49 | 4.16
8732 | Oregon | CURRY |  | 4 | S009337 | Paves poor section of US 101 between Bethel Cr and Crystal Cr in Coos County to improve safety. | Pavement Improvement | 05/13/2009 | 08/10/2009 | 11/12/2009 | 1967967.45 | 10.8
8733 | Oregon | DOUGLAS |  | 4 | S009338 | Improve safety on OR 38 and US 101 between Lane County and Gardner in douglas County by replacing poor pavement. | Pavement Improvement | 05/20/2009 | 05/23/2009 | 04/01/2010 | 5428845.55 | 11.1
8734 | Oregon | UNION |  | 2 | S010037 | Improve pedestrian safety and stormwater drainage by sidewalks, curb, gutter and stormwater drainage system on OR82 in Imbler. | Pavement Improvement | 04/14/2010 |  |  | 485000 | 0
8735 | Oregon | JACKSON |  | 2 | S022031 | Improves safety and extends pavement life on OR 62 and OR 140 between Medford and White city by replacing worn out pavement. | Pavement Improvement | 06/08/2009 | 07/07/2009 | 08/15/2010 | 9511292.59 | 6.47
8736 | Oregon | CLACKAMAS |  | 3 | S026066 | Improve safety and extend pavement life with paving on US 26 between the Salmon River Bridge and E Lolo Pass Road. | Safety/Traffic Management | 06/23/2008 | 07/21/2008 | 08/23/2009 | 200000 | 5.23
8737 | Oregon | POLK |  | 5 | S030017 | Enhances safety by paving roadway and repairing guardrail on OR 22 between OR 18 and OR 99W in Polk County. | Pavement Improvement | 06/03/2009 | 06/04/2009 | 10/31/2009 | 5341543.22 | 16.4
8738 | Oregon | POLK |  | 5 | S030018 | Repaves bridge deck on OR 22 over Willamette River and paves older sections of OR 22 to increase safety in Polk County. | Pavement Improvement | 05/29/2009 | 08/20/2009 | 06/30/2010 | 7199497.33 | 5.38
8739 | Oregon | LINCOLN |  | 5 | S033021 | Improve safety on US 20 between Pioneer Mountain and Eddyville in Lincoln County by improving alignment, widening shoulders and adding channelization at appropriate locaitons. | Pavement Widening | 07/05/2005 | 07/05/2005 | 12/22/2011 | 4800526.6 | 11.54
8740 | Oregon | BENTON |  | 4 | S033031 | Install median landscaping on new section of US 20 / OR 34 between Newton Creek and Jade Place in Philomath. | Other | 06/05/2009 | 06/05/2009 |  | 41939.64 | 1.44
8741 | Oregon | LINCOLN |  | 5 | S033032 | Improve safety on US 20 between Pioneer Mountain Loop Rd and Yaquina River in Lincoln County by removing narrow, winding roads. | Other | 02/08/2010 | 02/23/2010 | 07/30/2011 | 2075000 | 6.51
8742 | Oregon | LINCOLN |  | 5 | S033033 | Improve safety on US 20 between Pioneer Mountain Loop Rd and Yaquina River in Lincoln County by removing narrow, winding roads. | Other | 06/16/2009 | 06/16/2009 | 06/30/2010 | 287000 | 6.51
8743 | Oregon | BENTON | CORVALLIS | 4 | S033034 | Install median landscaping on new section of US 20 / OR 34 between Newton Creek and Jade Place in Philomath. | Transportation Enhancements | 12/11/2009 | 02/09/2010 | 03/31/2011 | 226817.44 | 1.44
8744 | Oregon | DOUGLAS |  | 4 | S045037 | Improve safety by paving OR 38 between Rock Cr and I-5 and OR 138 between Elkton and mile point 8 in Douglas County. | Pavement Improvement | 06/01/2009 | 06/12/2009 | 08/25/2009 | 4301032.58 | 17.47
8745 | Oregon | WASHINGTON |  | 1 | S047074 | Replaces pavement on the Sunset Highway (US 26) between North Plains and Cornell Road to fix severe rutting and reduce hydroplaning and installs cable barrier to improve safety. | Pavement Improvement | 03/16/2009 | 04/17/2009 | 03/30/2010 | 1171732.52 | 8.61
8746 | Oregon | MORROW |  | 2 | S052018 | Improves roadway and pedestrian safety on OR 74 between Willow Creek Bridge and Morrow County fairgrounds in Heppner by repairing the bridge, adding bicycle and pedestrian facilities and repaving the | Safety/Traffic Management | 02/27/2009 | 03/11/2009 | 11/30/2009 | 1018000 | 1.02
8747 | Oregon | MULTNOMAH |  | 1 | S061009 | Replace existing concrete roadway on I-405 between the Freewont and Marquam bridges to reduces wear and tear on the roadway. Adds new lights and signs to improve safety on the same section of road. | Pavement Improvement | 05/18/2009 | 06/02/2009 | 08/31/2010 | 3696873.14 | 3.08
8748 | Oregon | JACKSON |  | 4 | S063030 | Repair the 70-year-old culvert at the Bear Gulch Slide Drainage Tunnel in Jackson County to preserve road. | Other | 07/21/2009 | 08/13/2009 | 11/24/2009 | 550425.38 | 0
8749 | Oregon | MULTNOMAH |  | 3 | S081014 | Pave detour streets to improve safety and reduce wear and tear while work is performed to replace the Martin Luther King Viaduct in Portland. | Pavement Improvement | 01/12/2007 | 02/27/2007 | 02/16/2011 | 1250000 | 0
8750 | Oregon | POLK |  | 5 | S091037 | Improve bicycle safety and mobility by preserving bike paths on OR 99W between Rickreall and Monmouth. | Other | 11/23/2009 | 11/23/2009 |  | 52000 | 0
8751 | Oregon | POLK |  | 5 | S091039 | Improve bicycle safety and mobility by preserving bike paths on OR 99W between Rickreall and Monmouth. | Transportation Enhancements | 05/12/2010 |  |  | 650552.56 | 0
8752 | Oregon | MULTNOMAH | PORTLAND (WA) | 1 | S092017 | Updates signage along US 30 in Portland to improve visibility and safety as part of the Yeon Street preservation project. | Other | 12/09/2008 | 12/09/2008 |  | 2295.08 | 1.95
8753 | Oregon | MULTNOMAH |  | 1 | S092028 | Updates signage along US 30 in Portland to improve visibility and safety as part of the Yeon Street preservation project. | Pavement Improvement | 12/09/2008 | 02/03/2009 | 09/30/2009 | 160000 | 1.95
8754 | Oregon | COLUMBIA |  | 1 | S092029 | Enhance mobility and safety on US 30 in Scappoose with a new RR crossing, improved signalization and street widening. | Pavement Improvement | 07/23/2009 | 12/07/2009 | 09/02/2010 | 1215789.35 | 0.01
8755 | Oregon | COLUMBIA |  | 1 | S092030 | Enhance mobility and safety on US 30 in Scappoose with a new RR crossing, improved signalization and street widening. | Safety/Traffic Management | 06/23/2009 | 06/23/2009 | 06/23/2009 | 2000000 | 0.01
8756 | Oregon | COLUMBIA |  | 1 | S092031 | Enhance mobility and safety on US 30 in Scappoose with a new RR crossing, improved signalization and street widening. | Other | 06/23/2009 | 06/23/2009 |  | 274500 | 0.01
8757 | Oregon | DOUGLAS |  | 4 | S138002 | Pavement preservation project to extend the life of existing pavement on OR 138 between mile point 4 and 18 and US 199 between mile point 20 and 41 in Douglas and Josephine Counties. | Pavement Improvement | 04/17/2009 | 06/29/2009 | 09/30/2010 | 4261225.59 | 25
8758 | Oregon | CLACKAMAS |  | 5 | S160040 | Preserves roadway with new pavement and adds signing, signal loops and lighting on OR 213 between I-205 and Redland Rd in Clackamas County. | Pavement Improvement | 07/21/2008 | 08/20/2008 | 11/05/2009 | 2500000 | 3.93
8759 | Oregon | MARION |  | 5 | S162040 | Enhance safety by installing cable and concrete barriers on OR 22 between Lancaster Dr and Golf Club Rd in Marion County. | Safety/Traffic Management | 07/08/2009 | 07/22/2009 | 10/30/2009 | 2025788.59 | 9.62
8760 | Oregon | LANE |  | 4 | S229010 | Complete pavement preservation project on OR 36 between OR 200 and OR 99W. | Pavement Improvement | 06/16/2009 | 07/30/2009 | 10/15/2009 | 1018931.86 | 4.18
8761 | Oregon | MALHEUR |  | 2 | S455016 | Complete pavement preservation projecton OR 201 between Weiser interchange and the Snake River (Payette Bridge). | Pavement Improvement | 06/04/2009 | 07/14/2009 | 04/15/2010 | 6959443.39 | 8.05
8762 | Pennsylvania | CRAWFORD |  | 3 | Z011211 | This is a Safety and drainage improvement project involving pavement resurfacing, markings, guiderail upgrade on State Route 77 covering seven municipalities in Crawford County. | Pavement Improvement | 05/18/2009 | 06/22/2009 | 12/11/2009 | 2641449.82 | 11.378
8763 | Pennsylvania | CRAWFORD |  | 3 | Z011212 | This project located in the City of Meadville, Crawford County, updates and retrofits Curb Ramps and pedestrian signals for Pedestrian Safety and in compliance with ADA requirements. | Transportation Enhancements | 04/27/2009 | 05/18/2009 | 01/27/2010 | 830943.03 | 4.09
8764 | Pennsylvania | CRAWFORD |  | 3 | Z011213 | This project replaces the bridges and reconstructs the roadway approaches on State Routes 1020 and 3025 in Venango and Crawford Counties of District 1. | Bridge Improvement | 06/25/2009 | 07/30/2009 | 08/18/2010 | 825000 | 0.017
8765 | Pennsylvania | CRAWFORD |  | 3 | Z011214 | This is a Safety and roadway preservation project of about 5 miles of Interstate 79 in Crawford and Mercer Counties. The project involves concrete patching, milling and resurfacing of the roadway as w | Pavement Improvement | 08/03/2009 | 08/27/2009 | 09/22/2010 | 4252282 | 10.38
8766 | Pennsylvania | CRAWFORD |  | 3 | Z011216 | This project in Crawford County is East Branch Trail Ph 1. It is multi-use trail North of the Borough of Spartansburg to the Borough of Centerville in Spartansburg & Centerville Boroughs, Sparta & R | Transportation Enhancements | 01/27/2010 | 03/29/2010 | 07/30/2010 | 1087307 | 0
8767 | Pennsylvania | CRAWFORD |  | 3 | Z011217 | In Blooming Valley borough of Crawford County, this project will improve safety and drainage as well as extend the life of about 2 miles of Blooming Valley road by milling and resurfacing of the deter | Pavement Improvement | 10/07/2009 | 04/02/2010 | 09/16/2010 | 963711 | 1.636
8768 | Pennsylvania | ERIE |  | 3 | Z012356 | This is a Safety project to install durable Railroad Crossing markings on various state routes in District 1, and this covers the Counties of Crawford, Erie, Forest, Mercer, Venango and Warren. | Safety/Traffic Management | 04/27/2009 | 05/04/2009 | 12/25/2009 | 377037.44 | 0
8769 | Pennsylvania | ERIE |  | 3 | Z012357 | This project will extend the life of the bridges over Elk Creek and improve roadway approaches on State Route 98 in Fairview Township of Erie County. | Bridge Improvement | 05/04/2009 | 05/04/2009 | 10/15/2009 | 620221.97 | 0.043
8770 | Pennsylvania | ERIE |  | 3 | Z012358 | This milling and resurfacing project will extend the life of the existing roadway, State Route 20 in Springfield, Millcreek and Girard Townships of Erie County; and upgrade Curb ramps to comply with A | Pavement Improvement | 06/29/2009 | 06/29/2009 | 01/17/2010 | 3892213.33 | 20.049
8771 | Pennsylvania | ERIE |  | 3 | Z012359 | The project extends the life of the pavement on State Route 8 in Venango and Millcreek Townships of the City of Erie, Erie County. It involves pavement resurfacing and markings, guiderail improvements | Pavement Improvement | 06/16/2009 | 06/23/2009 | 11/05/2009 | 1240090.49 | 4.623
8772 | Pennsylvania | ERIE | ERIE | 3 | Z012360 | This project replaces the bridges over Six Mile Creek and Seven Mile Creek on State Route 955 in Harborcreek Township of Erie County. The project will also include drainage and guiderail upgrades as w | Bridge Replacement | 07/06/2009 | 07/06/2009 | 02/14/2011 | 1976099 | 0.52
8773 | Pennsylvania | ERIE |  | 3 | Z012361 | This project in the City of Erie, Erie County, improves Pedestrian Safety through the construction of sidewalks, installation of curb ramps, lightings, and signals improvements on City Street and Para | Transportation Enhancements | 08/25/2009 | 08/25/2009 | 07/27/2010 | 727031 | 0
8774 | Pennsylvania | ERIE | ERIE | 3 | Z012363 | This project, located in the City of Erie, Erie County, will update and retrofit Curb Ramps and pedestrian signals for Pedestrian Safety and in compliance with ADA requirements. | Transportation Enhancements | 06/01/2009 | 06/01/2009 | 08/04/2010 | 1570000 | 33.017
8775 | Pennsylvania | ERIE |  | 3 | Z012364 | This project will preserve the pavement and prevent skidding on 10 miles of Interstate 79 covering Franklin, McKean and Summit Townships in Erie County. It will involve the use of friction-resistant p | Pavement Improvement | 07/22/2009 | 08/17/2009 | 08/21/2010 | 5549437 | 21.111
8776 | Pennsylvania | ERIE | ERIE | 3 | Z012371 | This Erie County project extends the life of the pavement and improves Safety and drainage on 1.5 miles of State Route 290 (the Bayfront Connector); and this involves pavement resurfacing, guiderail a | Pavement Improvement | 10/14/2009 | 05/17/2010 | 09/15/2010 | 497559 | 0.768
8777 | Pennsylvania | ERIE | ERIE | 3 | Z012372 | This project will preserve the pavement and improve drainage on PA 5 (Lake road) in Harborcreek and Lawrence Townships of Erie County. It involves pavement resurfacing and other miscellaneous work. | Pavement Improvement | 10/08/2009 | 04/12/2010 | 08/15/2010 | 798000 | 3.051
8778 | Pennsylvania | ERIE | ERIE | 3 | Z012373 | This project in the City of Erie, Erie County, improves Pedestrian Safety through the construction of sidewalks, installation of curb ramps, lightings, and landscaping on State Street between Bayfront | Transportation Enhancements | 10/23/2009 | 10/23/2009 | 10/29/2010 | 900000 | 0
8779 | Pennsylvania | ERIE |  | 3 | Z012386 | This project on SR 2010 over Pine Run is in Erie County. It will improve safety by replacing the existing deteriorating bridge carrying Concord Road (SR 2010) over Pine Run in Union Township. | Bridge Replacement | 01/27/2010 |  | 02/17/2011 | 806632 | 0.365
8780 | Pennsylvania | FOREST |  | 5 | Z013119 | This project will restore State route 66 in Jenks Township of Forest County; and it involves pavement resurfacing and guiderail safety upgrades. | Pavement Improvement | 06/08/2009 | 07/13/2009 | 11/12/2009 | 917920.42 | 4.292
8781 | Pennsylvania | MERCER | YOUNGSTOWN | 3 | Z014231 | This project will extend the life of the pavement and improve pedestrian Safety on State Routes 18, 2005 and 4019 in Greenville Borough, Pine Hempfield, Sugar Grove and Salem Townships of Mercer Coun | Pavement Improvement | 06/24/2009 | 06/29/2009 | 09/06/2010 | 1551346 | 4.116
8782 | Pennsylvania | MERCER |  | 3 | Z014232 | This project will restore and preserve various State Routes including 62, 19, 58, 1028 located in various Townships and Boroughs in Mercer County; it involves milling and overlays as well as guiderail | Pavement Improvement | 06/29/2009 | 06/29/2009 | 12/03/2009 | 2144664.79 | 13.347
8783 | Pennsylvania | MERCER | YOUNGSTOWN | 3, 4 | Z014233 | This project on State Route 3011 (Keel Ridge Road) in Shenango Township and City of Hermitage of Mercer County, will preserve the pavement and improve Safety; it involves pavement repairs and overlays | Pavement Improvement | 06/24/2009 | 07/06/2009 | 04/15/2010 | 821484.28 | 6.547
8784 | Pennsylvania | MERCER | YOUNGSTOWN | 3, 4 | Z014235 | This project will extend the life of pavement on 17 miles of Interstate 80 in Shenango, Lackawannock and East Lackawannock Townships of Mercer County; it involves pavement patching and overlay, guide | Pavement Improvement | 08/10/2009 | 08/10/2009 | 08/24/2010 | 1780000 | 31.068
8785 | Pennsylvania | MERCER |  | 3 | Z014240 | This project will restore the deteriorating portion of US Route 62 in CoolSpring and Jackson Townships and Jackson Center Borough of Mercer County; it involves pavement and bridge repairs, overlay, | Pavement Improvement | 07/20/2009 | 08/17/2009 | 08/10/2010 | 1830329 | 5.141
8786 | Pennsylvania | MERCER |  | 1 | Z014243 | This project in Mercer County will improve safety for the public by replacing the deteriorating bridge carrying Baker Hill Road (SR 4024) over Lenango Creek in Delaware Township. | Bridge Replacement | 01/19/2010 | 03/01/2010 | 11/28/2010 | 789834 | 0
8787 | Pennsylvania | MERCER | YOUNGSTOWN | 3 | Z014247 | This project on State Route 3020 (Lamar Road) in the City of Hermitage of Mercer County, will improve safety and mobility through roadway widening, guiderail and drainage upgrades. | Pavement Widening | 12/04/2009 | 04/19/2010 | 09/29/2010 | 637922 | 0.549
8788 | Pennsylvania | MERCER |  | 3, 5 | Z014248 | This project will extend the life of the pavement and improve drainage on approximately 1.15 miles of State Route 322 (28th Division Highway) in French Creek Township of Mercer County; it involves pav | Pavement Improvement | 09/21/2009 | 04/19/2010 | 08/04/2010 | 347000 | 1.147
8789 | Pennsylvania | VENANGO |  | 5 | Z015189 | This project will extend the life of the pavement on US Route 62 in the City of Franklin, French Creek and Sandy Creek Townships of Venango County; it also involves improvements to drainage and guide | Pavement Improvement | 05/11/2009 | 07/25/2009 | 11/10/2009 | 1330276.28 | 6.74
8790 | Pennsylvania | VENANGO |  | 5 | Z015190 | This project will replace two bridges over Prathers Run and Little Sugar Creek on State Route 428 in Oakland Township of Venango County; it also includes improvements to the approach roadways and drai | Bridge Replacement | 06/24/2009 | 07/06/2009 | 02/25/2011 | 1634720 | 0.021
8791 | Pennsylvania | VENANGO |  | 5 | Z015193 | This project will stabilize and preserve pavement on State Route 8 Bypass in the City of Oil City of Venango County; it involves construction of a retaining wall; it also involves guiderail and draina | Other | 08/11/2009 | 10/12/2009 | 09/01/2010 | 2705312 | 0.782
8792 | Pennsylvania | WARREN |  | 5 | Z016177 | This project will preserve about 2.5 miles of pavement on State Route 3005 covering various Townships in Warren County; it involves pavement repairs and overlay as well as improvements to guiderail an | Pavement Improvement | 05/04/2009 | 06/11/2009 | 10/13/2009 | 599631.19 | 2.451
8793 | Pennsylvania | WARREN |  | 5 | Z016178 | This project will replace the bridge over Six Mile Creek on State Route 6 (Grand Army Highway) in Mead Township of Warren County. | Pavement Improvement | 08/25/2009 | 08/25/2009 | 08/04/2011 | 1592996 | 0.008
8794 | Pennsylvania | WARREN |  | 5 | Z016185 | This project is on US-6 in Warren County will repair the mechanically stabilized earth retaing wall on the Warren Bypass (US 6) left side in Mead Township. | Pavement Improvement | 01/27/2010 | 04/06/2010 | 09/12/2010 | 466006 | 0.306
8795 | Pennsylvania | CENTRE |  | 5 | Z021241 | This project will improve safety and mobility on State Route 26, in Pleasant Gap of Center County. This is an alternate emergency Route to terstate 80. The work involves widening, resurfacing, guider | Pavement Improvement | 04/08/2009 | 06/17/2009 | 11/19/2009 | 3365202.47 | 6.372
8796 | Pennsylvania | CENTRE |  | 5 | Z021253 | This project will replace the existing bridge over Marsh Creek on State Route 1001 in Curtin Township of Center County; it also involves drainage and guiderail upgrades. | Bridge Replacement | 04/27/2009 | 05/18/2009 | 02/04/2010 | 1051267.99 | 0.778
8797 | Pennsylvania | CENTRE | STATE COLLEGE | 5 | Z021254 | This project will extend the life of bridges on State Route 322 including bridges in College and Harris Townships of Center County. The bridges will be painted for protection from rusts and other dete | Bridge Improvement | 06/01/2009 | 07/06/2009 | 01/18/2010 | 869587.08 | 0.585
8798 | Pennsylvania | CENTRE |  | 5 | Z021255 | This project will replace the bridge over the Tributary to Penns Creek on State Route 2014 in Gregg Township of Center County; it also involves guiderail and drainage upgrades. | Bridge Replacement | 05/18/2009 | 06/15/2009 | 11/24/2009 | 466403.41 | 0.496
8799 | Pennsylvania | CENTRE |  | 5, 9 | Z021259 | This project extends the life of 5.59 miles of pavement on State Route 3040 (Old SR 220) covering Taylor and Worth Townships in Center County; it also involves roadway resurfacing, guiderail and drain | Pavement Improvement | 09/08/2009 | 04/05/2010 | 11/07/2010 | 1992296.63 | 5.611
8800 | Pennsylvania | CLEARFIELD |  | 5 | Z022246 | This project will improve the existing roadway, on State Route 219 in Brady, Union and Bloom Townships of Clearfield County, for longevity and Safety; it involves resurfacing, bridge deck repairs, min | Pavement Improvement | 04/20/2009 | 04/20/2009 | 03/08/2010 | 2797706.16 | 3.077
8801 | Pennsylvania | CLEARFIELD |  | 5 | Z022249 | This project is for roadway preservation and Safety on State Route 970 in Bradford and Goshen Townships of Clearfield County; it involves pavement widening and resurfacing, guiderail and drainage upgr | Pavement Improvement | 06/23/2009 | 06/23/2009 | 12/18/2009 | 3615370 | 5.122
8802 | Pennsylvania | CLEARFIELD |  | 5 | Z022252 | This project will preserve six bridges at various locations in various municipalities grouped together as GROUP-2-09-R04 in Cameron, Clearfield, McKean and Potter Counties; it involves bridge deck rep | Bridge Improvement | 07/27/2009 | 08/03/2009 | 08/08/2011 | 4087029 | 2.649
8803 | Pennsylvania | CLEARFIELD |  | 5, 9 | Z022253 | This project will preserve seven bridges at various locations in various municipalities grouped together as GROUP-2-09-R05 in Clearfield and Potter Counties; it involves bridge deck repairs, steel pai | Bridge Improvement | 07/31/2009 | 09/01/2009 | 12/09/2010 | 2414522 | 1.423
8804 | Pennsylvania | CLINTON |  | 5 | Z023177 | The project will construct a new asphalt riding surface on Lock Haven Bypass from Salona to Avis in Pine Creek, Wayne, Castenea, Bald Eagle and Lamar Townships | Pavement Improvement | 06/15/2009 | 06/22/2009 | 08/15/2010 | 7425000 | 28.174
8805 | Pennsylvania | CLINTON |  | 5, 10 | Z023178 | This project is for the preservation of 24 miles of roadway and associated bridges on Interstate 80 in Greene, Lamar and Porter Townships of Clinton and Union Counties; it involves concrete and bridge | Pavement Improvement | 09/10/2009 | 09/28/2009 | 11/20/2010 | 14604501 | 95.906
8806 | Pennsylvania | CAMERON |  | 5 | Z024116 | This project will improve safety to the traveling public by replacing the deteriorating bridge on SR 0555 (Low Grade Road), over Hicks Run, north of Run road in Gibson Township in Cameron County. | Bridge Replacement | 01/27/2010 | 02/03/2010 | 12/05/2010 | 1245703 | 0.17
8807 | Pennsylvania | MCKEAN |  | 5 | Z025185 | This project will extend pavement life and improve Safety on US Route 219 in Bradford Township of Mckean County; it involves roadway repairs and resurfacing, drainage and guiderail upgrades. | Pavement Improvement | 07/23/2009 | 09/11/2009 | 10/03/2010 | 3114663 | 3.503
8808 | Pennsylvania | MCKEAN |  | 5 | Z025187 | This project will replace the bridge over Janders Run on State 44 in Ceres Township of McKean County; it also involves guiderail and drainage upgrades. | Bridge Replacement | 11/06/2009 | 03/22/2010 | 07/09/2010 | 785993 | 0.005
8809 | Pennsylvania | POTTER |  | 5 | Z026154 | This project will restore the deteriorating portion of US Route 6 in Coudersport Borough and Eulalia Township in Potter County; it involves pavement, sidewalk and bridge repairs, overlay, guiderail | Pavement Improvement | 04/13/2009 | 04/14/2009 | 01/25/2010 | 2361612.76 | 1.688
8810 | Pennsylvania | POTTER |  | 5 | Z026161 | This project will increase the life of the pavement and make the road smoother by restoring the deteriorating asphalt pavement on SR 0006 (Second Street), east of SR 0144 (Main Street) in Coudersport | Pavement Improvement | 01/25/2010 | 03/29/2010 | 10/30/2010 | 2154460 | 2.049
8811 | Pennsylvania | MIFFLIN |  | 5 | Z027151 | This project will preserve 1.5 miles of pavement on State Route 1005 (Electric Avenue) in Derry Township and Burnham Borough of Mifflin County; it involves milling and resurfacing of roadway, guiderai | Pavement Improvement | 11/30/2009 | 03/29/2010 | 09/25/2010 | 1299512 | 1.274
8812 | Pennsylvania | ELK |  | 5 | Z028158 | This project will extend the life of 5 miles of pavement on State Route 219 in Johnsonburg Borough, Ridgeway and Jones Townships in Elk County; it involves pavement repairs and resurfacing as well as | Bridge Replacement | 09/14/2009 | 10/08/2009 | 09/17/2010 | 975000 | 5.166
8813 | Pennsylvania | JUNIATA |  | 9 | Z029135 | This project will extend the life of bridge over Juniata River on State Route 75 in the Borough of Port Royal and Walker Township in Juniata County; it involves deck and steel repairs, bridge paintin | Bridge Improvement | 06/22/2009 | 06/22/2009 | 08/27/2010 | 5010000 | 0.246
8814 | Pennsylvania | COLUMBIA |  | 5, 9, 10, 11 | Z031209 | The project will replace deteriorated, outdated, and substandard major guide signs and install additional major guide signs on various highways in Lycoming County to improve visibility and legibility | Safety/Traffic Management | 06/10/2009 | 07/23/2009 | 06/02/2010 | 186974.86 | 538.206
8815 | Pennsylvania | COLUMBIA |  | 11 | Z031211 | This project in Columbia County will increase the life of the bridge and make it safet for the public by rehabilitating the deteriorating State Route 42 bridge over Roaring Creek in Catawissa and Locu | Bridge Improvement | 07/10/2009 | 07/10/2009 | 12/24/2010 | 738343 | 0.189
8816 | Pennsylvania | COLUMBIA |  | 11 | Z031212 | This project in Columbia County will increase the life of the bridge and increase safety for the pulic by rehabilitating the deteriorating State Route 2001 bridge over a tributary of Roaring Creek in | Bridge Improvement | 07/10/2009 | 07/10/2009 | 12/24/2010 | 355250 | 0.076
8817 | Pennsylvania | COLUMBIA |  | 11 | Z031213 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck of the State Route 42 bridge over State Route 11 at Bloomsburg in Montour Township in Col | Bridge Improvement | 09/04/2009 | 04/12/2010 | 10/03/2010 | 1434490 | 0.074
8818 | Pennsylvania | LYCOMING |  | 5, 10 | Z032285 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 05/18/2009 | 08/03/2009 | 09/16/2010 | 911000 | 0.791
8819 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5, 10 | Z032286 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 15 from Beauty's Run to Trout Run in Lewis, Old Lycoming, and Lycoming | Pavement Improvement | 05/18/2009 | 07/27/2009 | 08/12/2010 | 2155314.94 | 7.488
8820 | Pennsylvania | LYCOMING |  | 10 | Z032287 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 220 from Lycoming County Line to Muncy Valley in Davidson Township, Sul | Pavement Improvement | 06/01/2009 | 06/29/2009 | 12/13/2009 | 662706.97 | 1.696
8821 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5 | Z032288 | This project will overlay the existing deteriorating pavement with new asphalt pavement on State Route 2014 from Montour Street to Fairfield Road in Montoursville Borough in Lycoming County. | Pavement Improvement | 06/01/2009 | 06/29/2009 | 12/09/2009 | 527915.57 | 1.89
8822 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5 | Z032290 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the US Route 220 bridge over Pine Run in Woodward Township | Pavement Improvement | 07/06/2009 | 03/29/2010 | 10/02/2010 | 634024 | 0.076
8823 | Pennsylvania | LYCOMING |  | 10 | Z032291 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the State Route 2085 bridge over Muncy Creek in Penn Towns | Bridge Improvement | 09/02/2009 | 04/05/2010 | 09/22/2010 | 687000 | 0.095
8824 | Pennsylvania | LYCOMING |  | 10 | Z032292 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the State Route 2048 bridge over Little Muncy Creek in Mun | Bridge Improvement | 08/21/2009 | 04/05/2010 | 11/07/2010 | 800000 | 0.024
8825 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5 | Z032298 | This project will make the pavement smoother and last longer by removing the upper layers of the deteriorating asphalt pavement and replace it with new asphalt pavement on SR 3028 from Thomas to Main | Pavement Improvement | 10/05/2009 | 04/08/2010 | 10/06/2010 | 489136 | 2.177
8826 | Pennsylvania | LYCOMING | WILLIAMSPORT | 5 | Z032300 | This project will make the road smoother by removing several inches of deteriorating pavement and replacing it with asphalt on SR 3028 from Thomas to Main Street in Jersey Shore Borough and Porter Tow | Pavement Improvement | 10/05/2009 | 04/08/2010 | 10/06/2010 | 235000 | 1.099
8827 | Pennsylvania | LYCOMING |  | 10 | Z032308 | This project in Lycoming County is to improve safety and riding smoothness by adding a traction enhancing layer (microsurface) to the asphalt roadway on PA 14 from Red Burn Road in McIntyre Township | Pavement Improvement | 02/01/2010 | 04/14/2010 | 08/08/2010 | 785842 | 14.081
8828 | Pennsylvania | MONTOUR |  | 10, 11 | Z033128 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on Interstate 80 Eastbound from West of Grey Hill Road to Old US Route 15 in White | Pavement Improvement | 05/28/2009 | 06/25/2009 | 10/21/2009 | 158143.87 | 4.609
8829 | Pennsylvania | MONTOUR |  | 10 | Z033129 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 54 from State Route 44 to State Route 254 in Anthony, Derry, Limesto | Pavement Improvement | 06/22/2009 | 08/17/2009 | 02/23/2010 | 1574940.35 | 4.665
8830 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034190 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 54 from State Route 2024 to Natalie in Coal, Mt. Carmel and Ralpho T | Pavement Improvement | 06/19/2009 | 06/25/2009 | 02/16/2010 | 1707618 | 4.399
8831 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034191 | This project in Northumberland County will make the pavement last longer and ride smoother by resurfacing the deteriorating asphalt roadway on State Route 54 from State Route 2024 to Natalie in Coal, | Pavement Improvement | 06/19/2009 | 06/25/2009 | 02/16/2010 | 888912.92 | 2.102
8832 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034192 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 05/13/2009 | 06/01/2009 | 10/20/2009 | 513648.14 | 1.067
8833 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034193 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck on the State Route 4009 bridge over Shamokin Creek in Upper Augusta Township in Northumbe | Bridge Improvement | 06/02/2009 | 06/15/2009 | 01/25/2010 | 1025868.01 | 0.158
8834 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034194 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the Interstate 180 bridge over State Route 44 in Delaware | Bridge Improvement | 08/07/2009 | 04/05/2010 | 12/12/2010 | 3191614 | 0.124
8835 | Pennsylvania | NORTHUMBERLAND |  | 10 | Z034197 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on Snydertown Road from Zimmermans Hollow Road to PA 487 in Northumberland County. | Pavement Improvement | 10/26/2009 | 10/26/2009 | 09/26/2010 | 2070789 | 8.287
8836 | Pennsylvania | SNYDER |  | 10 | Z035131 | This project in Snyder County will make the ride smoother and make the pavement last longer by resurfacing the deteriorating asphalt pavement on State Route 235 from Snyder/Union County Line to Breinn | Pavement Improvement | 06/05/2009 | 06/08/2009 | 02/11/2010 | 957900 | 4.158
8837 | Pennsylvania | SNYDER |  | 10 | Z035132 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the State Route 35 bridge over Tributary to Middle Creek i | Bridge Improvement | 07/10/2009 | 07/10/2009 | 12/24/2010 | 1280807 | 0.076
8838 | Pennsylvania | SNYDER |  | 10 | Z035133 | This project will remove the existing deteriorating bridge and replace it with a new bridge on State Route 3009 over Middle Creek in Franklin Township in Snyder County. | Bridge Replacement | 08/19/2009 | 09/14/2009 | 12/19/2010 | 1908357 | 0.104
8839 | Pennsylvania | SULLIVAN |  | 10 | Z036129 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 220 from Ringdale to Dushore in Cherry and Laporte Townships in Sulliva | Pavement Improvement | 06/01/2009 | 09/01/2009 | 01/28/2010 | 1170207.35 | 4.689
8840 | Pennsylvania | SULLIVAN |  | 10 | Z036130 | This project in Sullivan County will make the road last longer and the ride smoother by resurfacing the deteriorating asphalt roadway on US Route 220 from Lycoming County Line to Muncy Valley in David | Pavement Improvement | 06/01/2009 | 06/29/2009 | 12/13/2009 | 708624.3 | 2.579
8841 | Pennsylvania | SULLIVAN |  | 5, 10 | Z036131 | This project will upgrade the old metal guardrail to meet new design standards at various locations in Lycoming County | Safety/Traffic Management | 06/22/2009 | 06/22/2009 | 02/17/2010 | 536214.33 | 36.631
8842 | Pennsylvania | TIOGA |  | 5 | Z037222 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 04/02/2009 | 05/27/2009 | 09/10/2009 | 344345.56 | 0.288
8843 | Pennsylvania | TIOGA |  | 5 | Z037223 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 287 from Wilson Creek to Shumway Hill Road in Delmar Township, Tioga | Pavement Improvement | 05/15/2009 | 05/25/2009 | 09/20/2009 | 1629006.53 | 4.65
8844 | Pennsylvania | TIOGA |  | 5 | Z037224 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 15 from State Route 287 to Tioga River in Lawrence, Tioga Townships and | Pavement Improvement | 05/15/2009 | 05/18/2009 | 01/05/2010 | 1948999.89 | 4.839
8845 | Pennsylvania | TIOGA |  | 5 | Z037225 | This project will remove the existing deteriorating bridge and replace it with a new bridge on State Route 414 bridge over Zimmerman's Creek in Liberty Township, Tioga County. | Bridge Replacement | 06/29/2009 | 06/29/2009 | 08/13/2010 | 1062834 | 0.082
8846 | Pennsylvania | TIOGA |  | 5 | Z037226 | This project in Tioga County will make the bridge last longer by repairing deteriorating portions of State Route 2005 bridge over Blockhouse Creek in Liberty Township. This bridge is part of State Pr | Bridge Improvement | 06/29/2009 | 06/29/2009 | 08/13/2010 | 24960 | 0.009
8847 | Pennsylvania | TIOGA |  | 5 | Z037233 | This project in Tioga County will make the pavement last longer and ride smoother by removing the upper layers of the deteriorating asphalt pavenemt and replace with new asphalt on US 15 southbound fr | Pavement Improvement | 01/29/2010 | 05/03/2010 | 09/05/2015 | 1976116 | 7.797
8848 | Pennsylvania | UNION |  | 10 | Z038150 | This project in Union County will make the roadway last longer and ride smoother by resurfacing the deteriorating pavement on the eastbound Interstate 80 lanes from West of Grey Hill Road to Old US Ro | Pavement Improvement | 05/28/2009 | 06/25/2009 | 10/21/2009 | 114468.93 | 2.601
8849 | Pennsylvania | UNION |  | 10 | Z038151 | This project will make the roadway last longer and ride smoother by resurfacing the deteriorating pavement on Interstate 80 Westbound from old US Route 15 to White Deer Pike in White Deer in Union Co | Pavement Improvement | 05/28/2009 | 06/25/2009 | 10/21/2009 | 114619.5 | 3.431
8850 | Pennsylvania | UNION |  | 10 | Z038152 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 235 from Snyder/Union County Line to Breinnger Run in Adams Township | Pavement Improvement | 06/05/2009 | 06/08/2009 | 02/11/2010 | 985980.26 | 5.299
8851 | Pennsylvania | UNION |  | 10 | Z038153 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 08/27/2009 | 03/29/2010 | 10/03/2010 | 1363000 | 0.05
8852 | Pennsylvania | BRADFORD |  | 5, 10 | Z039194 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 06/25/2009 | 03/29/2010 | 10/03/2010 | 1714714 | 0.258
8853 | Pennsylvania | BRADFORD |  | 10 | Z039195 | This project will preserve the concrete deck by removing the top layer of concrete and replacing or patching it with a latex-modified concrete and add an epoxy overlay on the State Route 187 bridge ov | Bridge Improvement | 07/21/2009 | 08/03/2009 | 09/27/2010 | 1087483 | 0.189
8854 | Pennsylvania | BRADFORD |  | 10 | Z039196 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the US Route 6 bridge over Sugar Creek in Sylvania Borough | Bridge Improvement | 07/29/2009 | 04/05/2010 | 12/05/2010 | 955000 | 0.196
8855 | Pennsylvania | BRADFORD |  | 10 | Z039197 | This project in Bradford County will make the bridge safer and last longer by rehabilitating the deteriorating portions of State Route 187 bridge over Bullard Creek in Rome Borough and Township. This | Bridge Improvement | 07/29/2009 | 04/05/2010 | 12/05/2010 | 663000 | 0.076
8856 | Pennsylvania | BRADFORD |  | 10 | Z039198 | This project in Bradford County will make the bridge safer and last longer by rehabilitating the deteriorating portions of the bridge on State Route 1055 over Parks Creek in Rome Township. This is pro | Bridge Improvement | 07/29/2009 | 04/05/2010 | 12/05/2010 | 430450 | 0.076
8857 | Pennsylvania | BRADFORD |  | 10 | Z039202 | This project will preserve the deteriorating steel beams by painting the bridges on PA 187 over Susquehanna River in Asylum and Wysox Townships, in Bradford County. | Bridge Improvement | 10/02/2009 |  | 10/31/2010 | 919000 | 0.189
8858 | Pennsylvania | LACKAWANNA | SCRANTON--WILKES-BARRE | 11 | Z042405 | This project in Lackawanna County will resurface a heavily travelled local road to improve ride quality and extend the life of the pavement. | Pavement Improvement | 09/23/2009 | 09/24/2009 | 06/26/2010 | 1083949 | 1.795
8859 | Pennsylvania | LUZERNE | SCRANTON--WILKES-BARRE | 11 | Z043387 | This project in Luzerne County is construction of a new Cleveland Street Bridge over Mill Creek in Plains Township to replace one that had been closed to traffic. | Bridge Replacement | 06/04/2009 | 06/04/2009 | 09/12/2010 | 1521835 | 0
8860 | Pennsylvania | LUZERNE | SCRANTON--WILKES-BARRE | 11 | Z043407 | This project in Luzerne County will extend the life of the State Route 29 Bridges over the Susquehanna River and over State Route 2002 by repairing deteriorated steel, replacing the deteriorated decks | Bridge Improvement | 08/03/2009 | 08/10/2009 | 11/10/2011 | 19236548 | 0.563
8861 | Pennsylvania | LUZERNE |  | 10, 11 | Z043408 | This project in Luzerne County will extend the life of the State Route 4001 bridge over Branch of Hunlock Creek and State Route 4016 bridge over Marsh Creek by repairing deteriorated steel, replacing | Bridge Improvement | 06/03/2009 | 07/13/2009 | 10/23/2010 | 979000 | 1.001
8862 | Pennsylvania | LUZERNE |  | 11 | Z043411 | This 11.5 mile-long project in Luzerne County will mill and resurface a heavily travelled Interstate Highway to improve ride quality and extend the life of the pavement on both the northbound and sou | Pavement Improvement | 07/09/2009 | 07/09/2009 | 12/24/2009 | 2797620.44 | 10.694
8863 | Pennsylvania | LUZERNE |  | 11 | Z043412 | This 28 mile-long project will mill and resurface a heavily travelled Interstate Highway to improve ride quality and extend the life of the pavement on both the northbound and southbound lanes includi | Pavement Improvement | 06/30/2009 | 07/22/2009 | 02/05/2010 | 6843231.53 | 43.866
8864 | Pennsylvania | LUZERNE |  | 11 | Z043415 | This project in Luzerne and Lackawanna Counties will resurface a number heavily travelled highways (SR 924, 11, 3033, 3027, 347, 315) to improve ride quality and extend the life of the pavement. Inclu | Pavement Improvement | 07/17/2009 | 08/03/2009 | 07/04/2010 | 6000000 | 16.095
8865 | Pennsylvania | PIKE |  | 10 | Z044172 | This 5 mile long project in Pike and Wayne Counties will improve safety for bicyclists utilizing US Route 6 by widening the shoulders, placing new bituminous pavement, painting new pavement markings a | Transportation Enhancements | 06/01/2009 | 06/01/2009 | 05/21/2010 | 1532505.27 | 13.502
8866 | Pennsylvania | PIKE |  | 10 | Z044180 | This 2.8 mile-long project in Blooming Grove Township, Pike County, will resurface a heavily travelled highway to improve ride quality and extend the life of the pavement. Included in this project ar | Pavement Improvement | 07/08/2009 | 07/08/2009 | 12/08/2009 | 571506.74 | 3.338
8867 | Pennsylvania | PIKE |  | 10 | Z044181 | This 28 mile-long project will mill and resurface a heavily travelled Interstate 84 highway in Pike County to improve ride quality and extend the life of the pavement on the eastbound lanes includin | Pavement Improvement | 08/17/2009 | 07/22/2009 | 06/20/2010 | 7535000 | 57.18
8868 | Pennsylvania | PIKE |  | 10 | Z044184 | This project in Pike County will extend the life of the US Route 6 bridge over the Delaware River by repairing deteriorated steel, replacing the deteriorated deck with a new concrete deck, and repairi | Bridge Improvement | 10/21/2009 | 10/21/2009 | 11/25/2010 | 2802280 | 0.125
8869 | Pennsylvania | PIKE |  | 10 | Z044185 | This 5 mile-long project in Pike County will resurface a heavily travelled highway to improve ride quality and extend the life of the pavement. Included in this project are edge repairs, resurfacing | Pavement Improvement | 09/08/2009 | 09/08/2009 | 03/03/2010 | 998349.03 | 4.959
8870 | Pennsylvania | PIKE |  | 10 | Z044191 | This project is to make it safet for the public by replacing the deteriorating bridge carrying Twin Lakes Road (SR 1005) over Shohola Creek in Shohola Township in Pike County. | Bridge Replacement | 01/04/2010 | 01/04/2010 | 10/14/2010 | 897035 | 0.028
8871 | Pennsylvania | PIKE |  | 10 | Z044192 | This project is to replace the deteriorating bridge carrying Twin Lakes Road (SR 1005) over Shohola Creek in Shohola Township in Pike County. | Bridge Replacement | 01/04/2010 | 01/04/2010 | 10/14/2010 | 913403 | 0.028
8872 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045231 | This 0.5 mile long project in Susquehanna County will repair a section of roadway embankment on State Route 267 in Coconut Township damaged by numerous storms between 2006 and 2009. Repairs will inclu | Pavement Improvement | 05/27/2009 | 06/11/2009 | 12/30/2009 | 509463.37 | 0.294
8873 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045244 | This project in Susquehanna County will extend the life of the bridge on State Route 2040 over the Lackawanna River by installing new prestressed concrete beams, a new concrete deck, and replacing the | Bridge Improvement | 08/06/2009 | 08/24/2009 | 12/12/2010 | 1243000 | 0.038
8874 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045245 | This 16 mile long project will resurface two heavily travelled highways, SR 11 and SR 2023 in Susquehanna County, to improve ride quality and extend the life of the pavement. Included in this project | Pavement Improvement | 06/22/2009 | 07/13/2009 | 12/30/2009 | 660057.02 | 6.398
8875 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045246 | This project is to make the roadway last longer and ride smoother by resurfacing the deteriorating asphalt roadways on various State Routes in Susquehanna County. This project is part of State Project | Pavement Improvement | 06/22/2009 | 07/13/2009 | 12/30/2009 | 1689748.8 | 9.485
8876 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045249 | This 4 mile long project in Susquehanna County will resurface a local highway, SR 4002 (Laurel Lake Road) to improve ride quality and extend the life of the pavement. Included in this project are edg | Pavement Improvement | 09/14/2009 | 10/08/2009 | 02/07/2010 | 649211.27 | 4.231
8877 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045251 | This project is to make the traveling public safer by replacing the deteriorating bridge carrying Graham Road (SR 3033) over Wyalusing Creek in Rush Township in Susquehanna County. | Bridge Replacement | 01/08/2010 | 03/29/2010 | 12/01/2010 | 900000 | 0.016
8878 | Pennsylvania | SUSQUEHANNA |  | 10 | Z045252 | This project is make the traveling public safer by replacing the deteriorating bridge carrying Graham Road (SR 3033) over Wyalusing Creek in Rush Township in Susquehanna County. | Bridge Replacement | 01/08/2010 | 03/29/2010 | 12/01/2010 | 150000 | 0.016
8879 | Pennsylvania | WAYNE |  | 10 | Z046215 | This project will extend the lives of the SR 3037 Bridge over Middle Creek in Cherry Ridge Township, Wayne County, and the SR 2005 Bridge over Roaring Brook in Moscow, Lackawanna County. On 3037, the | Bridge Improvement | 04/20/2009 | 04/20/2009 | 11/29/2009 | 798819.14 | 0.495
8880 | Pennsylvania | WAYNE |  | 10 | Z046217 | This project in Wayne County will extend the life of the State Route 3006 Ledgedale Road bridge over Ariel Creek by replacing the deteriorated superstructure with a new concrete superstructure. | Bridge Improvement | 06/22/2009 | 06/22/2009 | 06/16/2010 | 578000 | 0.409
8881 | Pennsylvania | WAYNE |  | 10 | Z046218 | This State Route 4031 bridge over Johnson Creek, painting project in Wayne County will include containment and disposal of hazardous material and painting the steel beams to extend the life of the bri | Bridge Improvement | 06/08/2009 | 07/13/2009 | 12/17/2009 | 94086.54 | 0.428
8882 | Pennsylvania | WYOMING |  | 10 | Z047189 | This project will extend the lives of the SR 29 Bridge in Laceyville Borough and the SR 3001 Bridge in Eaton Township, Wyoming County. On SR 29, the project will repair the deteriorated deck, constru | Bridge Improvement | 07/07/2009 | 07/07/2009 | 12/05/2010 | 3450000 | 1.569
8883 | Pennsylvania | BERKS | READING | 6 | Z051239 | This project will make the road smoother by removing several inches of deteriorating pavement, patching the concrete, and replacing it with new pavement surface on SR 3222 from PA 724 (Philadelphia Av | Pavement Improvement | 10/22/2009 | 10/22/2009 | 11/30/2010 | 2180274.25 | 3.776
8884 | Pennsylvania | BERKS | READING | 6, 17 | Z051240 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 2005 - 5th Street in the City of Reading, Berks County. | Pavement Improvement | 06/03/2009 | 10/13/2009 | 11/30/2010 | 3442714.22 | 3.789
8885 | Pennsylvania | BERKS | READING | 6, 16, 17 | Z051241 | The project will paint the steel beams on 11 bridges in various locations in Berks County | Bridge Improvement | 05/14/2009 | 05/14/2009 | 11/30/2010 | 4958346.78 | 2.991
8886 | Pennsylvania | BERKS | READING | 6 | Z051242 | The project will install metal guardrail in median of State Route 100 to improve safety and reduce median crossover crashes in Berks County. | Safety/Traffic Management | 09/22/2009 | 10/13/2009 | 03/22/2010 | 308242.92 | 1.645
8887 | Pennsylvania | BERKS | READING | 16, 17 | Z051243 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and adding linestriping on US Route 222 in Spring, Muhlenberg, Ontelaunee and Mai | Pavement Improvement | 07/07/2009 | 07/08/2009 | 12/30/2010 | 11244850 | 28.311
8888 | Pennsylvania | BERKS |  | 17 | Z051246 | The project will install cameras and changeable message signs to improve traveler information availability on Interstate 78 from the Lebanon County Line to State Route 61 in Berks County. | Safety/Traffic Management | 06/29/2009 | 06/29/2009 | 07/24/2010 | 1943027 | 0.8
8889 | Pennsylvania | BERKS | READING | 17 | Z051247 | This project is to replace the substandard precast parapets (concrete railing) on bridges on Interstate 78 in Lenhartsville, Greenwich Township in Berks County. This project is part of State Project N | Safety/Traffic Management | 10/13/2009 | 05/03/2010 | 12/01/2011 | 1020000 | 0.362
8890 | Pennsylvania | BERKS | READING | 6, 17 | Z051265 | This project will make pedestrian safer by installing curb ramps that meet Americans with Disablities Act requirements in various locations in Berks County. | Transportation Enhancements | 02/18/2010 | 02/18/2010 | 07/30/2011 | 1848395.46 | 96.503
8891 | Pennsylvania | CARBON |  | 11 | Z052135 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 209 from McCall Bridge through Lehighton in Carbon County | Pavement Improvement | 06/30/2009 | 09/23/9 | 08/23/2010 | 1810887.7 | 4.249
8892 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053191 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 329 in North Whitehall and Whitehall Townships in Lehigh County | Pavement Improvement | 06/04/2009 | 10/26/2009 | 01/30/2010 | 1754025.14 | 1.51
8893 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053193 | This project will increase the life of several bridges by painting the steel beams on 11 bridges in various locations in Lehigh County | Bridge Improvement | 05/21/2009 | 05/21/2009 | 11/30/2010 | 1548670.24 | 0.18
8894 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053194 | The project will repair bridge parapets on various state routes in Weisenberg, South Whitehall, Whitehall, Washington Townships and City of Bethlehem, in Lehigh and Northampton Counties | Safety/Traffic Management | 10/13/2009 | 05/03/2010 | 12/01/2011 | 4010648 | 1.997
8895 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053202 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and add curb ramps on Fairmont Avenue from MacArthur Road to Fullerton Avenue in Wh | Pavement Improvement | 01/19/2010 | 01/19/2010 | 11/30/2010 | 855513.88 | 0
8896 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053203 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and add curb ramps on Hanover Avenue from the Lehigh River Bridge to Irving Street | Pavement Improvement | 01/19/2010 | 01/19/2010 | 11/30/2010 | 2591766.44 | 0
8897 | Pennsylvania | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053205 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and add curb ramps on Broad Street from Terrace Avenue to Eaton Avenue and on Penns | Pavement Improvement | 05/03/2010 | 05/03/2010 | 11/30/2010 | 1952000 | 0
8898 | Pennsylvania | MONROE |  | 11, 17 | Z054183 | The project will replace the deteriorated decks of 10 bridges in various locations in Monroe and Schuylkill Counties | Bridge Improvement | 06/04/2009 | 06/15/2009 | 11/30/2010 | 2177420.16 | 0.254
8899 | Pennsylvania | MONROE |  | 11 | Z054184 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 33 and State Route 8017 in Hamilton Township, Monroe County. | Pavement Improvement | 07/16/2009 | 08/17/2009 | 09/01/2010 | 7997775 | 6.324
8900 | Pennsylvania | MONROE |  | 11, 17 | Z054185 | This project will upgrade existing traffic barrier on bridges to improve safety on Interstate 80 in Pocono Township, Monroe County. This project will also upgrade existing traffic barrier on bridge | Safety/Traffic Management | 09/25/2009 | 04/11/2010 | 11/11/2011 | 1969052 | 1.804
8901 | Pennsylvania | MONROE |  | 11 | Z054186 | This project is to replace non-standard precast parapets (concrete railings) on bridges on Interstate 80 in Pocono Township in Monroe County. This project is part of State Project Number 66660, 66662, | Safety/Traffic Management | 09/25/2009 | 04/11/2010 | 11/11/2011 | 4650801 | 1.13
8902 | Pennsylvania | MONROE |  | 11 | Z054187 | This project is to replace non-standard precast parapets (concrete railings) on various bridges in Stroud, Smithfield Townships, Stroudsburg and East Stroudsburg Boroughs in Monroe County. This proje | Safety/Traffic Management | 09/25/2009 | 04/11/2010 | 11/11/2011 | 3482484 | 0.93
8903 | Pennsylvania | MONROE |  | 11 | Z054189 | The project will construct curb ramps for improving pedestrian access and safety at various locations in Coolbaugh, Middle Smithfield, Pocono, Polk, Smithfield and Stroud Townships, the Boroughs of Ea | Transportation Enhancements | 01/21/2010 | 01/21/2010 | 11/29/2010 | 458695 | 23.907
8904 | Pennsylvania | MONROE |  | 11 | Z054192 | This project will repair the concrete pavement, repair and seal the joints, and resurface the pavement from the Luzerne County line to PA 54 Interchange including new pavement on the four ramps at the | Pavement Improvement | 02/19/2010 | 02/19/2010 | 01/29/2012 | 14785154 | 10.178
8905 | Pennsylvania | MONROE |  | 12 | Z054195 | This project in Monroe County will make the roadway last longer and ride smoother by improving the asphalt roadway on PA 33, including the Sciota and Snydersville ramps, from Bossardsville Road includ | Pavement Improvement | 02/25/2010 | 02/25/2010 | 12/31/2010 | 6123419.51 | 11.058
8906 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055193 | The project will replace the deteriorated decks of 7 bridges in various locations in Northampton County | Bridge Improvement | 05/14/2009 | 05/14/2009 | 01/11/2010 | 1751795.77 | 0.198
8907 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055194 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and linestriping on State Route 33 from Belfast to Wind Gap in Northampton County | Pavement Improvement | 06/30/2009 | 09/08/2009 | 12/30/2010 | 9967135 | 13.53
8908 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055195 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 412 from Interstate 78 through Hellertown in Northampton County | Pavement Improvement | 05/27/2009 | 07/20/2009 | 02/21/2010 | 1408327.7 | 1.991
8909 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055197 | This project will construct curb ramps to improve pedestrian access and safety at various locations in Northampton County. | Transportation Enhancements | 01/22/2010 | 01/21/2010 | 01/30/2011 | 1041110.74 | 40.962
8910 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055198 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on Interstate 78 from State Route 412 to Easton in Northampton County | Bridge Replacement | 09/15/2009 | 05/09/10 | 01/30/2011 | 9552180 | 31.883
8911 | Pennsylvania | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055203 | This project will make the street system safer by relocating and realigning the existing 2nd Street ramp from 3rd Street to PA 378 in the City of Bethlehem in Northampton County. | Pavement Improvement | 02/17/2010 | 04/12/2010 | 01/08/2012 | 6106044 | 0.194
8912 | Pennsylvania | NORTHAMPTON |  | 15 | Z055204 | This project in Northampton County will make the bridge last longer by replacing deterioriating portions of the Eighth Street Bridge over PA 33 in Plainfield Township. | Bridge Improvement | 03/03/2010 | 04/12/2010 | 08/12/2010 | 382931.78 | 0
8913 | Pennsylvania | SCHUYLKILL |  | 17 | Z056178 | This project in Schukill County is to replace the non-standard precast bridge parapets (concrete railings) on several bridges. This project is part of State Project Numbers 66660, 66661, and 66662. | Safety/Traffic Management | 09/25/2009 | 04/11/2010 | 11/11/2011 | 631520 | 0.224
8914 | Pennsylvania | SCHUYLKILL |  | 17 | Z056179 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 924 from State Route 61 to 4 lane section north of Frackville in Sch | Pavement Improvement | 07/09/2009 | 07/13/2009 | 08/19/2010 | 832809 | 0.963
8915 | Pennsylvania | SCHUYLKILL |  | 17 | Z056180 | The project will construct curb ramps at various locations in Schuylkill County to improve pedestrian access and safety. | Safety/Traffic Management | 01/04/2010 | 01/04/2010 | 01/29/2011 | 398047 | 49.616
8916 | Pennsylvania | SCHUYLKILL |  | 17 | Z056182 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on PA 54 from the Bridge over the Reading and Blue Mountain Railroad, near Coles S | Pavement Improvement | 01/20/2010 | 01/19/2010 | 12/15/2010 | 3665205.9 | 5.131
8917 | Pennsylvania | SCHUYLKILL |  | 11, 17 | Z056187 | This project will improve the smoothness of the roadway surface by repairing and sealing the concrete, milling, overlay and shoulder rehabilitation and upgrading I-81 from Luzerne County Line to the P | Pavement Improvement | 02/19/2010 | 02/19/2010 | 12/30/2011 | 24425748 | 17.138
8918 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 8 | Z061100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Bucks County | Transportation Enhancements | 06/19/2009 | 07/20/2009 | 04/01/2010 | 1053026.4 | 3.835
8919 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 2, 8, 13 | Z061101 | This project will add cameras, message boards and instrumentation to detect incidents and provide Travel Times to help the traveling public on Interstate 95 in various locations of Bucks and Philadelp | Safety/Traffic Management | 06/30/2009 | 08/31/2009 | 10/09/2013 | 22853719 | 46.963
8920 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 8, 13 | Z061102 | This project will add cameras, message boards and instrumentation to detect incidents and provide Travel Times to help the traveling public in various locations of Philadelphia and Bucks Counties. | Safety/Traffic Management | 09/14/2009 | 09/14/2009 | 11/27/2013 | 19879059 | 41.837
8921 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 8 | Z061103 | This project will mill and overlay the existing pavement, install a landscaped median, provide new traffic signals, pavement markings and signing on Stoopville Road in Newton Township, Bucks County. | Pavement Improvement | 09/23/2009 | 11/09/2009 | 09/01/2010 | 1125034 | 4.112
8922 | Pennsylvania | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 8, 13, 15 | Z061104 | This project will provide a paved pedestrian and bike trail from the New Hope borough municipal parking lot to the New Hope-Ivyland historic train station in Bucks County. | Transportation Enhancements | 12/10/2009 | 01/27/2010 | 08/20/2010 | 275621 | 0
8923 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7, 16 | Z062100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Chester County | Transportation Enhancements | 04/30/2009 | 06/29/2009 | 09/28/2010 | 4978590 | 101.163
8924 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6 | Z062101 | This project will mill and overlay 5 miles of existing pavement, install an updated median barrier, shoulder rumble strips, pavement markings, and updated signing and guiderail on the US Route 30 Exto | Pavement Improvement | 08/24/2009 | 08/24/2009 | 02/21/2010 | 5212807 | 10.249
8925 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 16 | Z062102 | This project will convert 2 miles of abandoned railway into a paved pedestrian and bike trail from State Route 29 to Church Farm School Road in Tredyffrin, East Whiteland and West Whiteland Townships, | Transportation Enhancements | 09/20/2009 | 09/23/9 | 09/19/2010 | 4135414 | 0
8926 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 16 | Z062103 | This project in Chester County is to remove the abandonded abutments from the old State Street bridge over AMTRAK in Parkesburg Borough. | Pavement Improvement | 01/27/2010 | 02/01/2010 | 08/01/2010 | 707000 | 0
8927 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 7 | Z062104 | This project in Chester County will make the roadway last longer and ride smoother by removing the deteriorating upper layers of asphalt and replace it with new asphalt on US 202 from Stanton Avenue t | Pavement Improvement | 05/21/2010 | 05/25/2010 | 09/30/2011 | 15408924 | 7.614
8928 | Pennsylvania | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7 | Z062105 | This project will provide new sidewalks along sections of Old Lancaster Rd., Conestoga Rd., Howelville Rd., and Irish Rd. It will also install traffic calming measures and provide storm water manageme | Transportation Enhancements | 01/06/2010 | 03/01/2010 | 06/24/2010 | 2181452 | 0
8929 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 7 | Z063100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Delaware County. | Transportation Enhancements | 05/08/2009 | 06/15/2009 | 06/27/2010 | 5396777 | 27.008
8930 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 6, 7 | Z063101 | This project on I-95 and I-476, in Philadelphia, Delaware, and Montgomery Counties, will install cameras, message boards, and instrumentation to detect incidents and provide Travel Times to minimize d | Safety/Traffic Management | 07/13/2009 | 07/20/2009 | 10/09/2013 | 15009061 | 72.188
8931 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 7 | Z063102 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings on Bridgewater and Brookhaven Roads in Brookhaven Borough, Delaware County. | Transportation Enhancements | 07/06/2009 | 10/21/2009 | 03/07/2010 | 198434.35 | 0.769
8932 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 7 | Z063103 | This project will provide new traffic signal equipment at the intersection of Darby-Paoli and Whitehorse Roads in Newtown Township, Delaware County. | Safety/Traffic Management | 08/31/2009 | 08/31/2009 | 02/15/2010 | 130067.16 | 0.361
8933 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 7 | Z063104 | This project will replace incandescent traffic signal heads with more efficient Light Emitting Diode traffic signal heads at 7 intersections and pedestrian signals at 4 locations in Darby, Brookhaven | Safety/Traffic Management | 08/31/2009 | 08/31/2009 | 01/16/2010 | 206907 | 2.551
8934 | Pennsylvania | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 7 | Z063105 | This project will provide a smoother road by milling and repaving Valley Rd. from Middletown Road to Brick House Farm Road in Edgemont Township, Delaware County. | Pavement Improvement | 09/25/2009 | 10/01/2009 | 01/25/2010 | 188733.24 | 0
8935 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7 | Z064100 | This project will repair existing pavement and resurface and provide pavement markings and drainage and guiderail improvements on US Route 422 from State Route 29 to Township Line in Limerick and Upp | Pavement Improvement | 05/22/2009 | 05/22/2009 | 07/27/2010 | 14939569 | 10.05
8936 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7, 15 | Z064101 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Montgomery County to improve pedestrian access and safety. | Transportation Enhancements | 05/19/2009 | 07/20/2009 | 04/11/2010 | 1557211.9 | 7.197
8937 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 13 | Z064102 | This project will provide landscaping enhancements along Bethlehem Pike in Springfield and Whitemarsh Townships, Montgomery County, to improve the aesthetics for drivers and pedestrians. | Transportation Enhancements | 07/17/2009 | 07/17/2009 | 08/26/2010 | 273000 | 0.095
8938 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 6, 7 | Z064103 | This project will reconstruct the pavement and shoulders along I-476 from I-76 to the PA Turnpike, in Plymouth Township and West Conshohocken Borough, Montgomery County. This project also include bri | Pavement Improvement | 08/31/2009 | 09/14/2009 | 11/22/2012 | 3525084 | 9.831
8939 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 7 | Z064104 | This project will construct new ramps to and from I-76 at Henderson Rd. in Upper Merion Township, Montgomery County. | Pavement Improvement | 10/15/2009 | 11/06/2009 | 07/19/2012 | 11638178 | 3.718
8940 | Pennsylvania | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 13 | Z064105 | This project will include traffic signal improvements and pedestrian signals, and construct concrete curb ramp for pedestrian access and safety in 11 municipalities in Montgomery County.. | Safety/Traffic Management | 12/31/2009 | 12/31/2009 | 07/28/2011 | 4673888 | 0.51
8941 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 2, 13 | Z065100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings on various state highways in the City of Philadelphia, Philadelphia County. | Transportation Enhancements | 06/25/2009 | 08/17/2009 | 11/29/2009 | 1605428 | 18.345
8942 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 2, 6, 8, 13 | Z065101 | This project provides for milling and paving of over 20 miles of Philadelphia City streets and installing concrete curb ramps. | Transportation Enhancements | 10/14/2009 | 10/14/2009 | 12/12/2010 | 6198539 | 0
8943 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1 | Z065102 | This project will make the bidge last longer by repairing and painting structural steel, and redecking the bridge surface on the Girard Point Bridge on I-95 in Philadelphia. | Bridge Improvement | 10/02/2009 | 10/02/2009 | 10/24/2012 | 77377214 | 1.958
8944 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 2, 6, 8, 13 | Z065103 | This project provides for milling and paving various Philadelphia City streets and providing concrete curb ramps. | Transportation Enhancements | 01/29/2010 | 02/04/2010 | 10/19/2010 | 4317115 | 0
8945 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 2 | Z065104 | This project is to replace four deteriorating Gustine Lake Bridges in the City of Philadelphia, Philadelphia County. | New Construction | 02/18/2010 | 03/01/2010 | 10/30/2011 | 13672965 | 0.205
8946 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 1, 2, 6, 7, 8, 13 | Z065105 | This project will improve safety by constructing concrete and brick curb ramps, replacing traffic signal poles, and resurfacing various city of Philadelphia streets in the southeast quadrant of the ce | Pavement Improvement | 03/25/2010 | 03/25/2010 | 11/10/2010 | 3674000 | 0
8947 | Pennsylvania | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 2 | Z065106 | This project is to install safety improvements and rehabilitate both bridge structures that carry US 1 (Roosevelt Expressway) over the Schuylkill River in the City of Philadelphia, Philadelphia County | Bridge Improvement | 02/19/2010 | 02/19/2010 | 03/04/2011 | 6375859 | 0.748
8948 | Pennsylvania | ADAMS |  | 19 | Z081001 | This project will improve rideability and safety by resurfacing and updating guiderail on 6 miles of US 15 north of Gettysburg in Adams County. | Pavement Improvement | 06/22/2009 | 06/25/2009 | 11/18/2011 | 6785000 | 9.378
8949 | Pennsylvania | CUMBERLAND |  | 9 | Z082001 | This project will improve safety by replacing an existing deteriorated bridge on SR 34 north of Carlisle in Cumberland County. | Bridge Replacement | 04/29/2009 | 06/11/2009 | 02/18/2010 | 1887212.4 | 0.032
8950 | Pennsylvania | CUMBERLAND |  | 19 | Z082002 | This Cumberland County project will improve rideability and safety by resurfacing about 8 miles of I-81 SB from Exit 57 to Exit 65, Restoring concrete pavement at Milepost 50.5 Northbound near Carlisl | Pavement Improvement | 07/27/2009 | 07/30/2009 | 03/03/2010 | 5000077 | 18.534
8951 | Pennsylvania | CUMBERLAND | HARRISBURG | 19 | Z082003 | This project will extend the life of the bridge and improve safety of the SR 15 bridge over SR 114 south of the Pennsylvania Turnpike and of the Wesley Road/Rossmoyne Road bridge over US 15 north of t | Bridge Improvement | 07/08/2009 | 07/13/2009 | 07/16/2010 | 3177102 | 0.076
8952 | Pennsylvania | CUMBERLAND | HARRISBURG | 9, 19 | Z082004 | This project will improve rideability and safety by resurfacing about 2 miles of SR 641 from US 11 to PA 465 in North Middletown Township on the west side of Carlisle, in Cumberland County. This pr | Pavement Improvement | 09/23/2009 | 09/28/2009 | 08/22/2010 | 2064050 | 4.658
8953 | Pennsylvania | FRANKLIN |  | 9 | Z083001 | This project will improve rideability and safety by resurfacing 6 miles of US 30 from Norlo Road to the Adams County Line in Guilford and Greene Townships east of Chambersburg in Franklin County. | Pavement Improvement | 05/18/2009 | 05/20/2009 | 01/21/2010 | 2970387.06 | 6.843
8954 | Pennsylvania | YORK | YORK | 19 | Z083002 | This project will improve rideability and safety by resurfacing, updating guiderail and restoring 3 structures (surfacing and substructure repairs) on about 5 miles of US 30 from the Hellam Interchang | Pavement Improvement | 06/08/2009 | 06/11/2009 | 01/12/2010 | 3419337.33 | 9.954
8955 | Pennsylvania | FRANKLIN |  | 9 | Z083003 | This Franklin County project will improve rideability and safety by resurfacing and updating guiderail on US 30 from State Route 3012 (Jack Road) to Hilltop Drive in St Thomas and Hamilton Townships w | Pavement Improvement | 07/02/2009 | 07/06/2009 | 03/11/2010 | 3051618.47 | 5.717
8956 | Pennsylvania | FRANKLIN |  | 9 | Z083004 | This Franklin County project will extend the life of the PA 433 bridge over Rowe Run in Southampton Township and improve safety by replacing the superstructure (beams and deck) and improving approache | Bridge Improvement | 09/14/2009 | 09/17/2009 | 07/06/2010 | 434000 | 0.108
8957 | Pennsylvania | FRANKLIN |  | 9 | Z083005 | This bridge painting project will preserve the steel beams on the US 11 bridge (Molly Pitcher Highway) over I-81 Exit 3 in Antrim Township in Franklin County. | Bridge Improvement | 09/14/2009 | 04/12/2010 | 09/06/2010 | 404550 | 0.052
8958 | Pennsylvania | FRANKLIN |  | 9 | Z083006 | This Franklin County project will make the bridge last longer by rehabilitating the deteriorating portions of the bridge carrying Mont Alto Road (SR 2031) over the Conococheague Creek tributary in Gui | Bridge Improvement | 02/08/2010 | 02/08/2010 | 10/02/2010 | 437150 | 0.006
8959 | Pennsylvania | YORK | YORK | 17, 19 | z084001 | This work will provide 3 closed circuit TV cameras in the York County Area on I-83 (Exits 21, 24, Milepost 30) and 1 Highway Advisory Radio (HAR) & 4 Signs at I-83 (Exit 22) to allow the District to m | Safety/Traffic Management | 05/29/2009 |  | 08/17/2009 | 662988 | 0
8960 | Pennsylvania | YORK | YORK | 19 | Z084002 | This project will improve rideability and safety by resurfacing and updating guiderail on about 2.5 miles of US 30 from Interstate 83 to State Route 24 in Manchester and Springettsbury Townships on th | Pavement Improvement | 08/17/2009 | 08/20/2009 | 06/26/2011 | 7700000 | 7.499
8961 | Pennsylvania | YORK | YORK | 19 | Z084003 | This York County project will improve rideability and safety by resurfacing the roadway and upgrading guiderail on about 7.5 miles of US 15 from Golf Course Road to Cumberland County Line in Carroll T | Pavement Improvement | 09/23/2009 | 03/01/2010 | 11/18/2010 | 2881500 | 5.035
8962 | Pennsylvania | YORK |  | 19 | Z084004 | This York County project will make the bridge last longer by restoring the deteriorating portions of the Indian Rock Dam Road (SR 3044) bridge over West Branch of Codorus Creek in North Codorus and We | Bridge Improvement | 02/15/2010 | 02/15/2010 | 08/30/2010 | 674489 | 0.128
8963 | Pennsylvania | YORK |  | 19 | Z084005 | This project will make the roadway last longer and ride smoother by resurfacing PA 116 with a new asphalt riding surface from Jacobs Mill Road (SR 3045) to PA 516 in Heidelberg and North Codorus Town | Pavement Improvement | 02/25/2010 | 02/25/2010 | 10/30/2010 | 1787166 | 4.319
8964 | Pennsylvania | DAUPHIN |  | 17 | Z085001 | This project will improve rideability and safety by resurfacing and updating guiderail on 1.5 miles of PA 147 from Fisher Street to Dawn Road north of Halifax, in Dauphin County. This Dauphin Count | Pavement Improvement | 04/30/2009 | 05/18/2009 | 12/30/2009 | 2029182.6 | 5.344
8965 | Pennsylvania | DAUPHIN |  | 17 | Z085002 | This project will upgrade the crashworthiness of precast concrete parapets on bridges in Dauphin County at US 22 Eastbound, Westbound, Ramps and Retaining Walls over the Susquehanna River at Clarks Fe | Safety/Traffic Management | 06/23/2009 | 06/23/2009 | 09/24/2010 | 5107600 | 1.372
8966 | Pennsylvania | DAUPHIN | HARRISBURG | 6, 10, 17, 19 | z085003 | This Dauphin County project will provide 5 closed circuit TV cameras in the Harrisburg Metropolitan Area on I-81 (Exits 45, 47, Milepost 74, Milepost 79) and US 22/322 (PA39 Exit) to allow the Distric | Safety/Traffic Management | 05/29/2009 |  | 06/28/2009 | 689500 | 0
8967 | Pennsylvania | DAUPHIN | HARRISBURG | 17 | Z085004 | This Dauphin County project will improve rideability and safety by resurfacing 2 miles of I-83 south of Union Deposit Road interchange to Bridge over Valley Road in Lower Paxton Township from Exit 48 | Pavement Improvement | 07/27/2009 | 08/31/2009 | 08/22/2010 | 3055000 | 8.802
8968 | Pennsylvania | DAUPHIN | HARRISBURG | 17 | Z085006 | This project will relieve congestion and improve safety of about 1.5 miles of PA 39 with pavement widening and reconstruction, installing traffic signals and other misc. work at the PA 39/I-81 Interch | Pavement Widening | 07/17/2009 | 07/20/2009 | 12/31/2011 | 10700000 | 2.045
8969 | Pennsylvania | DAUPHIN | HARRISBURG | 17 | Z085007 | This Dauphin County project will improve rideability and safety by resurfacing, drainage improvements, ADA ramps and other misc. improvements on about 2 miles of SR 230 (Cameron Street) and about 6 mi | Pavement Improvement | 09/28/2009 | 04/20/2010 | 09/29/2010 | 2258960 | 3.651
8970 | Pennsylvania | LANCASTER | LANCASTER | 16 | Z087001 | This Lancaster County project will improve safety and remove weight restrictions on the PA 324 bridge over Pequea Creek in Pequea and Martic Townships by replacing the superstructure (beams and deck) | Bridge Improvement | 04/20/2009 | 04/20/2009 | 09/01/2010 | 1616041 | 0.037
8971 | Pennsylvania | LANCASTER |  | 9, 16, 19 | Z087002 | This project will upgrade the crashworthiness of precast concrete parapets on bridges in Adams County on SR 1005 over Mud Creek, 3 miles southeast of York Springs; in Cumberland County on I-83 over SR | Safety/Traffic Management | 06/23/2009 | 06/23/2009 | 07/08/2010 | 2063628 | 2.947
8972 | Pennsylvania | LANCASTER | LANCASTER | 6, 16, 17, 19 | z087003 | This Lancaster County project will provide 2 closed circuit TV Cameras in the Lancaster County Area on US 30 (PA 501 and PA 283 Exits under Part IV of Contract 354R23, Phase 4 (Expansion of the Harris | Safety/Traffic Management | 05/29/2009 |  | 08/17/2009 | 318350 | 0
8973 | Pennsylvania | LANCASTER | LANCASTER | 16 | Z087004 | This Lancaster County project will improve rideability and safety by resurfacing and updating guiderail on about 7.5 miles of State Route 222 from north of Bushong Road to US Route 322 in Ephrata, Man | Pavement Improvement | 06/22/2009 | 06/24/2009 | 02/06/2011 | 12821485 | 12.297
8974 | Pennsylvania | LANCASTER |  | 16 | Z087005 | This Lancaster County project will improve rideability and safety by resurfacing and updating guiderail on about 5 miles of State Route 222 from Quarryville to Brennenman Road in Providence and Stras | Pavement Improvement | 08/14/2009 | 08/17/2009 | 09/12/2010 | 3390677 | 5.218
8975 | Pennsylvania | LANCASTER | LANCASTER | 16 | Z087006 | This Lancaster County project will improve rideability and safety by resurfacing and updating guiderail on US 30 from PA 896 to PA 897 in East Lampeter, Leacock, Paradise, and Salisbury Townships east | Pavement Improvement | 09/28/2009 | 09/30/2009 | 11/14/2010 | 4366500 | 9.8
8976 | Pennsylvania | LANCASTER |  | 16 | Z087007 | This Lancaster County project will make the roadway last longer and ride smoother by resurfacing the deteriorating asphalt pavement with a new riding surface on PA 272 from US 222 to north of Dennis D | Pavement Improvement | 02/20/2010 | 03/01/2010 | 11/11/2010 | 4082123 | 9.551
8977 | Pennsylvania | LEBANON |  | 17 | Z088001 | This Lebanon County project will improve rideability and safety by resurfacing, upgrading guiderail, placing concrete median barrier and constructing left turn lanes on about 3 miles of US 22 from Lin | Pavement Improvement | 08/14/2009 | 08/17/2009 | 09/15/2010 | 6179250 | 5.89
8978 | Pennsylvania | PERRY |  | 9, 17 | Z089001 | This Perry County project will improve rideability and safety by resurfacing and updating guiderail on about 3 miles of State Route 74 east of Loysville. | Pavement Improvement | 04/30/2009 | 06/15/2009 | 12/24/2009 | 1104310.59 | 3.134
8979 | Pennsylvania | PERRY |  | 9 | Z089002 | This project will make the bridge last longer by restoring the deteriorating portions of the bridge carrying Waggoners Gap Road (PA 74) over Sherman's Creek in Spring Township in Perry County. | Bridge Improvement | 02/17/2010 | 03/17/2010 | 11/09/2011 | 3093159 | 0.341
8980 | Pennsylvania | BEDFORD |  | 9 | Z091001 | This project will overlay the existing deteriorating pavement with new asphalt pavement of State Route 30 from Stony Lane (T-720) to the Snake Spring Twp Line in Bedford Township and Bedford Borough i | Pavement Improvement | 04/29/2009 | 04/29/2009 | 01/22/2011 | 6536325 | 9.321
8981 | Pennsylvania | BEDFORD |  | 9, 12 | Z091002 | The project will paint the steel beams of 20 bridges in Bedford, Blair, Cambria, Fulton, Huntingdon and Somerset Counties | Bridge Improvement | 05/04/2009 | 05/18/2009 | 02/10/2010 | 4616127.54 | 2.495
8982 | Pennsylvania | BEDFORD |  | 9 | Z091003 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated decks on various structures in Bedford County | Bridge Improvement | 05/01/2009 | 07/14/2009 | 02/01/2010 | 251406.63 | 0.103
8983 | Pennsylvania | BEDFORD |  | 9 | Z091004 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams of 2 bridges on State Route 915 over Sandy Run in Broadtop To | Bridge Improvement | 07/22/2009 | 08/17/2009 | 12/10/2010 | 1509774 | 0.134
8984 | Pennsylvania | BEDFORD |  | 9 | Z091005 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on SR 1010 (Woy Bridge Road) over Raystown Branch of the Jun | Bridge Improvement | 09/11/2009 | 04/16/2010 | 11/24/2010 | 1932884 | 0.134
8985 | Pennsylvania | BLAIR | ALTOONA | 9 | Z092001 | The Blair County project will construct new pavement surface, guardrail, and curb ramps on State Route 1001 from Convention Center Blvd north to 3rd Street and on State Route 36 from Pine St (T-612) t | Pavement Improvement | 05/20/2009 | 05/26/2009 | 02/01/2010 | 4043473.6 | 11.386
8986 | Pennsylvania | BLAIR | ALTOONA | 9 | Z092002 | The project will construct a new pavement surface and curb ramps on Penn Street (State Route 36) from Chimney Rocks Road to Pine Street in Hollidaysburg Borough, Blair County. | Pavement Improvement | 06/23/2009 | 06/23/9 | 11/13/2010 | 3132375 | 1.842
8987 | Pennsylvania | BLAIR | ALTOONA | 9 | Z092003 | The project will replace deteriorated bridge deck surfaces on various bridges in Snyder, Antis Townships and Tyrone Borough, Blair County. | Bridge Improvement | 07/21/2009 | 08/03/2009 | 09/09/2011 | 1511446 | 0.293
8988 | Pennsylvania | CAMBRIA | JOHNSTOWN | 9 | Z093001 | Replacement of deteriorated bridge decks on 3 bridges on State Route 1021 over Wyerough Run, State Route 1026 over Slate Lake Run, State Route 4024 over Chest Creek in White and Chest Township, Cambri | Bridge Improvement | 06/16/2009 | 08/03/2009 | 02/13/2011 | 1562093 | 0.062
8989 | Pennsylvania | CAMBRIA | JOHNSTOWN | 12 | Z093002 | The project will construct a new pavement surface on US Route 219 from Galleria Drive to Palestine Road and resurface the bridge deck on the Palestine Road Bridge in Adams and Richland Townships in | Pavement Improvement | 07/16/2009 | 08/03/2009 | 03/06/2011 | 5481851 | 9.457
8990 | Pennsylvania | CAMBRIA |  | 9, 12 | Z093003 | The project will replace deteriorated bridge decks for 2 bridges on Manor Drive (State Route 1001) over R. J. Corman Railroad near the intersection of Munster Rd (State Route 1003) and over R. J. Corm | Bridge Improvement | 07/20/2009 | 08/03/2009 | 12/12/2010 | 909753 | 0.038
8991 | Pennsylvania | CAMBRIA |  | 9, 12 | Z093004 | This project in Cambria County will make the bridges last longer by repairing deteriorating portions of 10 bridges on US 219, PA 36, PA 56, PA 271 and SR 3031. | Bridge Improvement | 03/01/2010 | 03/08/2010 | 11/06/2011 | 1772380 | 0.574
8992 | Pennsylvania | CAMBRIA | JOHNSTOWN | 12 | Z093005 | This Cambria County project will make the bridge last longer by rehabilitaing deteriorating portions of Eisenhower Boulevard (SR 3006) bridge over Stonycreek River near the intersection of Ferndale A | Bridge Improvement | 02/02/2010 | 05/03/2010 | 12/04/2010 | 1635298 | 0.044
8993 | Pennsylvania | FULTON |  | 9 | Z094001 | This Fulton County project will replace bridge decks of 3 bridges on State Route 1003 over Cove Creek, State Route 3006 over Little Tonoloway, and State Route 4004 over Wooden Bridge Creek in Ayr an | Bridge Improvement | 04/13/2009 | 04/20/2009 | 11/30/2009 | 506138.69 | 0.03
8994 | Pennsylvania | FULTON |  | 9 | Z094002 | The Fulton County project will construct a new pavement surface on US Route 30 from Bedford County line to the Truck Pull-off in Brush Creek Township. | Pavement Improvement | 04/17/2009 | 05/05/2009 | 12/27/2009 | 591442.83 | 2.624
8995 | Pennsylvania | HUNTINGDON |  | 9 | Z095001 | The project will replace the bridge on State Route 1010 in Huntingdon Borough over Standing Stone Creek in Huntingdon County. | Bridge Replacement | 05/06/2009 | 06/12/2009 | 02/04/2010 | 1354916.74 | 0.024
8996 | Pennsylvania | HUNTINGDON |  | 9 | Z095002 | The project will construct a new pavement surface on US Route 22 from Old Twenty-two Road (T-613) to Walnut Terrace Road (T-561) in Smithfield and Porter Townships, Huntingdon County. | Pavement Improvement | 05/20/2009 | 05/26/2009 | 01/22/2010 | 1374826 | 1.904
8997 | Pennsylvania | HUNTINGDON |  | 9 | Z095003 | The project will replace the deteriorated bridge deck surface on US 522 over Pump Station Road (T-396), Aughwick Creek and East Broad Top Railroad in Shirley Township | Bridge Improvement | 09/24/2009 | 09/24/2009 | 01/12/2011 | 1724415 | 0.216
8998 | Pennsylvania | SOMERSET |  | 12, 18 | Z097001 | The project will construct a new pavement surface on US Route 30 from Westmoreland County Line to State Route 985 in Jenner Township and Jennerstown Borough | Pavement Improvement | 04/15/2009 | 05/13/2009 | 10/15/2009 | 1222568.55 | 3.816
8999 | Pennsylvania | SOMERSET |  | 9 | Z097002 | The project will replace 3 bridges and 2 deteriorated bridge decks on State Route 2019 and State Route 2021 over Shaffers Run in Fairhope Township | Bridge Replacement | 06/01/2009 | 06/22/2009 | 12/17/2011 | 2422643 | 0.105
9000 | Pennsylvania | SOMERSET |  | 12 | Z097003 | The project will remove a bridge and place it with earth fill and asphalt pavement at Wilber Coal Company Coal Mine Railroad bridge in Quemahoning Township | Bridge Replacement | 07/20/2009 | 08/11/2009 | 11/13/2010 | 467600 | 0.076
9001 | Pennsylvania | ARMSTRONG |  | 3 | Z101207 | This project will extend the life of one bridge by placing an epoxy overlay on the deck. The bridge is on Iron Bridge Road, in Armstrong County, South Buffalo Township just west of the South Scenic Dr | Bridge Improvement | 04/27/2009 | 06/08/2009 | 11/18/2009 | 313290.78 | 0.066
9002 | Pennsylvania | ARMSTRONG |  | 3 | Z101208 | This project will patch the existing concrete roadway on State Route 422 in Armstrong County West Franklin township and Worthington Borough. The project is from approximately 0.26 miles west of the SR | Pavement Improvement | 04/27/2009 | 04/27/2009 | 01/20/2010 | 5331218.42 | 13.338
9003 | Pennsylvania | ARMSTRONG | PITTSBURGH , PA | 3 | Z101209 | This project will patch the existing concrete on State Route 28 and overlay it with asphalt from the overpass at Iron Bridge Road to the overpass at State Route 128, in Armstrong County South Buffalo | Pavement Improvement | 05/27/2009 | 05/27/2009 | 01/26/2010 | 5581694.05 | 9.376
9004 | Pennsylvania | ARMSTRONG |  | 3 | Z101219 | This project will extend the life of two bridges and improve safety by replacing the existing deteriorated decks on two State Route 422 bridges that pass over State Route 28 in Armstrong County's East | Bridge Improvement | 07/17/2009 | 08/17/2009 | 09/30/2010 | 4732838 | 2.417
9005 | Pennsylvania | ARMSTRONG |  | 12 | z101220 | This is a Transportation Enhancement project that consists of a tar and chip widening of approximately 1/2 mile of the existing trail, construction of about two miles of new trail, and construction of | Transportation Enhancements | 08/11/2009 | 08/11/2009 | 01/25/2010 | 667947.7 | 0
9006 | Pennsylvania | BUTLER |  | 3 | Z102224 | This project will extend the service life of one bridge by patching the deck/joints and overlaying the deck with a latex modified concrete surface. The bridge is on State Route 528 in Butler County ap | Bridge Improvement | 04/27/2009 | 04/27/2009 | 10/04/2009 | 415810.45 | 0.058
9007 | Pennsylvania | BUTLER |  | 3 | Z102225 | This project will extend the life of four bridges in Butler County with preservation activities, including, shear key replacement, concrete beam repair and placement of concrete composite deck on Stat | Bridge Improvement | 04/27/2009 | 05/04/2009 | 12/16/2009 | 729884.37 | 0.348
9008 | Pennsylvania | BUTLER |  | 4 | Z102226 | This project will replace the existing bridge with a new two-lane six span multi-girder steel bridge on State Route 3027 in Butler County, Jackson Township. | Bridge Replacement | 06/08/2009 | 06/08/2009 | 09/08/2010 | 5507500 | 0.287
9009 | Pennsylvania | BUTLER |  | 3 | Z102229 | This project will extend the life of the roadway by replacing the surface course on State Route 422 in Butler County from the SR 422/T439 Whipporwill Road intersection to approximately 500 feet east o | Pavement Improvement | 07/13/2009 | 07/27/2009 | 01/17/2010 | 1410518.13 | 3.915
9010 | Pennsylvania | BUTLER |  | 3 | Z102233 | This project will replace the bridge deck on I-79 in Worth Township in Butler County and replace the bridge decks on two structures over Interstate 79, with one being State Route 4007 and the other Pa | Bridge Improvement | 08/03/2009 | 08/31/2008 | 10/30/2010 | 3170989 | 0.085
9011 | Pennsylvania | CLARION |  | 5 | Z103194 | This project will extend the service life of two bridges by replacing the decks. These are the bridges that carry State Route 68 over interstate 80 in Clarion County. The project will replace the d | Bridge Improvement | 05/18/2009 | 07/20/2009 | 08/11/2010 | 5929371 | 0.87
9012 | Pennsylvania | CLARION |  | 5 | Z103196 | Bridge preservation activities, including, shear key replacement, concrete beam repair, placement of concrete composite deck and other miscellaneous construction for State routes 66(#1), 66(#2), 2007( | Bridge Improvement | 05/04/2009 | 05/04/2009 | 10/20/2009 | 750174.62 | 0.176
9013 | Pennsylvania | CLARION |  | 5 | Z103200 | This project will replace an existing two lane single span structure with a two lane single span prestressed spread box beam bridge with minimal approach work on state route 28 in Clarion County Redba | Bridge Replacement | 07/21/2009 | 10/19/2009 | 11/14/2010 | 1943009 | 0.27
9014 | Pennsylvania | CLARION |  | 5 | Z103201 | This project will increase Americans with Disabilities Act facilities by building ADA compliant curb ramps on State Route 322 in Clarion Borough, Clarion County from approximately the First Avenue int | Transportation Enhancements | 12/01/2009 | 03/26/2010 | 08/29/2010 | 402000 | 0.842
9015 | Pennsylvania | INDIANA |  | 9 | Z104234 | This project will extend the service life of the roadway by patching the existing concrete pavement and overlaying it with asphalt. The project is on State Route 119 in Indiana County from the SR 56/S | Pavement Improvement | 06/08/2009 | 07/01/2009 | 06/21/2010 | 1149940.41 | 2.272
9016 | Pennsylvania | INDIANA |  | 12 | Z104235 | This project will extend the service life of two bridges by replacing their decks and repairing the piers. The bridges are on eastbound and westbound State Route 422 at the Chestnut Ridge Road overpas | Bridge Improvement | 07/20/2009 | 08/04/2009 | 07/30/2010 | 3343338 | 0.378
9017 | Pennsylvania | INDIANA |  | 9 | Z104236 | This project will extend the service life of the existing concrete pavement by performing slab stabilization, full depth slab patching, dowel bar retrofits, crack and joint sealing and microsurfacing. | Pavement Improvement | 09/18/2009 | 09/24/2009 | 07/30/2010 | 4445241 | 7.014
9018 | Pennsylvania | INDIANA |  | 12 | Z104241 | This project is to replace the deteriorating bridge carrying PA 403 (Clymer Bridge) over Dixon Run and Two Lick Creek in Clymer Borough in Indiana County. | Bridge Replacement | 01/04/2010 | 01/27/2010 | 12/18/2011 | 5435892 | 0.379
9019 | Pennsylvania | INDIANA |  | 9 | Z104242 | This project will make the bridge last longer by rehabilitating the deteriorating portions of the Heshbon Bridgebridge carrying Yellow Creek Park Road (PA 259) over Blacklick Creek in West Wheatfield | Bridge Improvement | 01/28/2010 | 04/01/2010 | 06/30/2011 | 1526197 | 0.03
9020 | Pennsylvania | JEFFERSON |  | 5 | Z105182 | This project will extend the service life of one bridge by performing preventative maintenance activities such as shear key replacement, concrete beam repair and the placement of concrete composite de | Bridge Improvement | 05/18/2009 | 06/24/2009 | 01/04/2010 | 627262.1 | 0.045
9021 | Pennsylvania | JEFFERSON |  | 5 | Z105183 | This project will replace the superstructure (bridge beams and deck) on a one Span Steel Multi-Girder Structure. The structure is on State Route 2023 (Knoxdale Road) in Jefferson County approximately | Bridge Improvement | 05/18/2009 | 06/01/2009 | 02/02/2010 | 1048484.85 | 0.095
9022 | Pennsylvania | JEFFERSON |  | 5 | Z105185 | This project will extend the service life of State Route 36 in Punxsutawney Borough by performing activities such as leveling, Superpave overlay, transverse joint repair, guiderail and ADA ramp upgrad | Pavement Improvement | 06/22/2009 | 06/22/2009 | 02/03/2010 | 1752109.89 | 5.633
9023 | Pennsylvania | JEFFERSON |  | 5 | Z105187 | This project will construct ADA compliant curb ramps along State Route 28 in Brockway Borough from approximately the SR 28/Second Avenue intersection to approximately the SR 28/SR 219 intersection. | Transportation Enhancements | 10/13/2009 | 04/13/2010 | 10/30/2010 | 469000 | 1.159
9024 | Pennsylvania | JEFFERSON |  | 5 | Z105188 | This project will extend the service life of the existing roadway by milling the surface course and replacing it with a bituminous overlay. This project is on State Route 436 in Punxsutawney Borough | Pavement Improvement | 09/22/2009 | 04/05/2010 | 08/22/2010 | 717335 | 1.792
9025 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 18 | Z111300 | The project involves reconstructing the ramp pavement, eliminating 2 ramps, and installing new signals and signs in Robinson and North Fayette Townships. It will also construct new asphalt pavement al | Pavement Improvement | 06/01/2009 | 06/08/2009 | 12/19/2010 | 9620000 | 1.65
9026 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 14 | Z111606 | This project involves relocating a railroad, moving a pier, building a few retaining walls to prepare for the next project phase which will widen Route 28 from Troy Hill to Milvale in the City of Pitt | Other | 11/02/2009 | 11/02/2009 | 06/09/2012 | 23150000 | 4.112
9027 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 14 | Z111624 | The project will fix or repair various tunnel components that are worn out or deteriorated of the tunnel carrying State Route 3069 from the Liberty Bridge over the Monongahela River to State Route 51 | Pavement Improvement | 09/21/2009 | 10/01/2009 | 09/30/2010 | 12526662 | 2.252
9028 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 14, 18 | Z111625 | The project will replace the bridge deck surfaces on the Ft. Duquesne Bridge in City of Pittsburgh | Bridge Improvement | 07/07/2009 | 07/07/2009 | 11/28/2010 | 26190521 | 2.265
9029 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 4 | Z111640 | The project will construct a new pavement surface along the entire route. | Pavement Improvement | 09/10/2009 | 09/10/2009 | 01/21/2011 | 845658 | 5.728
9030 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 4 | Z111659 | This project will make the bridge last longer by rehabilitating the deteriorating portions of the bridge carrying California Avenue (SR 7301) over Jacks Run in the City of Pittsburgh in Allegheny Coun | Bridge Improvement | 02/12/2010 | 02/12/2010 | 08/17/2011 | 9347210.05 | 0
9031 | Pennsylvania | ALLEGHENY | PITTSBURGH , PA | 14 | Z111660 | This project in Allegheny County will make pedestrians safer by replacing deteriorating sidewalks and curbing, installing four handicap ramps to access the sidewalks, installing four street lights wit | Transportation Enhancements | 05/18/2010 | 06/03/2010 | 05/31/2010 | 328450 | 0
9032 | Pennsylvania | BEAVER | PITTSBURGH , PA | 4 | Z112213 | The project will repair steel members, paint the bridge, and replace expansion joints on the Rochester Bridge over Beaver River in Rochester and Bridgewater Boroughs | Bridge Improvement | 05/18/2009 | 05/18/2009 | 01/30/2011 | 12160227 | 0.329
9033 | Pennsylvania | LAWRENCE |  | 4 | Z114210 | The project will upgrade the interchange by adding a lane on SR60 southbound, installing new signs and sign structures, and modifying ramps at various interchanges to meet standards in preparing for t | Pavement Improvement | 11/16/2009 | 01/20/2010 | 10/14/2010 | 10450000 | 15.802
9034 | Pennsylvania | LAWRENCE |  | 4 | Z114220 | The project will construct a new asphalt riding surface on US Route 422 (Ben Franklin Highway) from Pine Glen Road to Zoccoli Road in Mahoning and Pulaski Townships | Pavement Improvement | 06/22/2009 | 06/23/2009 | 01/28/2010 | 2574486.13 | 4.392
9035 | Pennsylvania | LAWRENCE |  | 4 | Z114221 | The project will replace the deck and provide other miscellaneous repairs of the State Route 2004 (Grove Street) bridge over Neshannock Creek in City of New Castle. | Bridge Improvement | 06/30/2009 | 08/10/2009 | 10/07/2010 | 3291447 | 0.149
9036 | Pennsylvania | LAWRENCE | PITTSBURGH , PA | 4 | Z114225 | This Lawrence County project will make the area more esthetic and pedestrians safer by constructing concrete curbs, sidewalks, pedestrian lighting, landscaping, and adding street furniture. It is loca | Transportation Enhancements | 02/12/2010 | 04/08/2010 | 11/28/2010 | 542940 | 0
9037 | Pennsylvania | LAWRENCE |  | 4 | Z114227 | This project will make the roadway last longer and the ride smoother by patching and overlaying the deteriorating pavement on US 422 from Cascade Street (SR 2004) to Ben Franklin Highway (Butler Count | Pavement Improvement | 01/28/2010 | 04/05/2010 | 11/15/2010 | 8480988 | 10.266
9038 | Pennsylvania | FAYETTE | UNIONTOWN-CONNELLSVILLE | 9, 12, 18 | Z121001 | This project includes the replacement of bridge strip seals, bridge beam repair and minor concrete bridge deck repair for 31 bridges throughout Fayette, Greene, Washington and Westmoreland Counties. T | Bridge Improvement | 05/07/2009 | 07/08/2009 | 09/15/2010 | 1285216 | 1.462
9039 | Pennsylvania | FAYETTE |  | 9 | Z121002 | This project is the full replacement of a structurally deficient two span bridge carrying State Route 3006 over York Run. The roadway rehabilitation will consist of bridge approach slabs, drainage enh | Bridge Replacement | 07/20/2009 | 07/21/2009 | 10/12/2011 | 1531676 | 0.17
9040 | Pennsylvania | FAYETTE |  | 12 | Z121003 | This project is the full replacement of two structurally deficient bridges carrying State Route 1054 over Trout Run. The roadway rehabilitation will consist of bridge approach slabs, drainage enhancem | Bridge Replacement | 07/20/2009 | 07/21/2009 | 10/30/2011 | 1364102 | 0.01
9041 | Pennsylvania | FAYETTE | UNIONTOWN-CONNELLSVILLE | 12 | Z121004 | This project includes the full bridge replacement of SR 1039 over Dickerson Run in Dunbar Township, Fayette County. | Bridge Replacement | 07/09/2009 | 08/17/2009 | 11/13/2011 | 844081 | 0.004
9042 | Pennsylvania | FAYETTE | UNIONTOWN-CONNELLSVILLE | 12 | Z121005 | This project consists of concrete pavement overlay to 2.19 miles of SR 0119 from Penn State Fayette to Pechin Road in North Union and Dunbar Townships. This project includes existing pavement milling, | Pavement Improvement | 08/06/2009 | 01/01/2010 | 10/30/2010 | 4635933 | 6.214
9043 | Pennsylvania | FAYETTE | UNIONTOWN-CONNELLSVILLE | 12 | Z121006 | This Fayette County project will make the roadway last longer and ride smoother by overlaying the deteriorating pavement on US 119 from Penn State Fayette to the Connellsville Street exit in North Uni | Pavement Improvement | 02/25/2010 | 03/08/2010 | 08/22/2010 | 2525922 | 8.011
9044 | Pennsylvania | FAYETTE |  | 12 | Z121008 | This Fayette County project will make the roadway last longer and the ride smoother by overlaying the deteiorating pavement on PA 51 from Waltersburg Bridge to Smock Road (SR 4016) in Franklin and Men | Pavement Improvement | 02/26/2010 | 03/22/2010 | 09/02/2010 | 1140000 | 8.902
9045 | Pennsylvania | GREENE |  | 12 | Z122001 | This project is the full replacement of a structurally deficient bridge carrying State Route 0018 over Browns Creek in Franklin Township, Greene County. The roadway rehabilitation will consist of brid | Bridge Replacement | 10/02/2009 | 10/02/2009 | 12/14/2011 | 2110953 | 0.018
9046 | Pennsylvania | GREENE |  | 12 | Z122002 | This project is the full replacement of a structurally deficient bridge carrying State Route 0018 over a Branch of Browns Run in Morris Township, Greene County. The roadway rehabilitation will consist | Bridge Replacement | 08/07/2009 | 08/17/2009 | 12/10/2011 | 1114156 | 0.006
9047 | Pennsylvania | GREENE |  | 12 | Z122003 | This project is the full replacement of a structurally deficient bridge carrying State Route 0018 over Garner's Run in Washington Township, Greene County. The roadway rehabilitation will consist of br | Bridge Replacement | 08/07/2009 | 08/17/2009 | 09/03/2011 | 851172 | 0.004
9048 | Pennsylvania | GREENE |  | 12 | Z122004 | This is a safety improvement project that will upgrade curb ramps to current standards in the Borough of Waynesburg and Franklin Township, Greene County. | Transportation Enhancements | 07/31/2009 | 09/15/2008 | 11/28/2010 | 1517593 | 3.9
9049 | Pennsylvania | WASHINGTON |  | 18 | Z124001 | This project is the full replacement of the Pattersons Mill Bridge over the North Fork of Cross Creek on SR 4029 in Cross Creek Township, Washington County. | Bridge Replacement | 07/24/2009 | 08/05/2009 | 11/25/2011 | 1021520 | 0.15
9050 | Pennsylvania | WASHINGTON |  | 18 | Z124002 | This project consists of pavement preservation and other miscellaneous construction for State Route 0019, in Washington County, North Strabane Township from approximately Conklin Rd. (T-639) to approx | Pavement Improvement | 07/28/2009 | 08/17/2009 | 01/20/2010 | 765630.22 | 3.126
9051 | Pennsylvania | WASHINGTON | PITTSBURGH , PA | 12, 18 | Z124003 | This project includes repairing the deteriorating concrete roadway by concrete patches on Interstate 79 from Canonsburg to the Allegheny County Line in Washington County | Pavement Improvement | 10/21/2009 | 10/21/2009 | 10/01/2011 | 15594320 | 14.218
9052 | Pennsylvania | WASHINGTON | UNIONTOWN-CONNELLSVILLE | 12 | Z124006 | This project is to repair the deteriorating portions of the bridge carrying Bridge Boulevard on SR 2067 over the Monogalhlela River in West Brownsville Bourough in Fayette and Washington counties . Br | Bridge Improvement | 04/07/2010 | 04/26/2010 | 09/24/2010 | 1630560 | 0.199
9053 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 12, 18 | Z125001 | This project will consist of existing pavement milling, pavement resurfacing, installing concrete barrier in the median, adding left turn lanes at the following intersections: SR 30/ Monastery Dr (T-7 | Pavement Improvement | 05/07/2009 | 05/20/2009 | 03/15/2010 | 2210688.44 | 4.005
9054 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 18 | Z125002 | This project consists of existing pavement milling, bituminous pavement overlay, minor drainage improvements, new guide rail, bridge approach slabs, traffic signal improvements for State Route 0030, i | Pavement Improvement | 07/30/2009 | 08/23/9 | 09/20/2010 | 2743610 | 5.434
9055 | Pennsylvania | WESTMORELAND | MONESSEN | 12 | Z125003 | This project consists of steel repairs, bridge beam painting, and concrete pier repairs for State Route over Interstate 70, in Westmoreland County, Rostraver Township. These upgrades will extend the l | Bridge Improvement | 07/01/2009 | 08/22/2009 | 01/19/2010 | 799043.66 | 0.029
9056 | Pennsylvania | WESTMORELAND |  | 12 | Z125004 | This project is the full bridge replacement of SR 1006 (Moon's Bridge) over a Tubmill Run in Fairfield Township, Westmoreland County. | Bridge Replacement | 07/02/2009 | 07/20/2009 | 11/13/2011 | 719905 | 0.008
9057 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 18 | Z125005 | This project will consist of a truss bridge rehabilitation and concrete bridge deck rehabilitation for State Route 993 (Larimer Bridge) over Brush Creek, in Westmoreland County, North Huntingdon Towns | Bridge Improvement | 08/04/2009 | 03/22/10 | 11/08/2010 | 2372698 | 0.028
9058 | Pennsylvania | WESTMORELAND |  | 12 | Z125006 | This project consists of the full replacement of the existing one span concrete bridge of State Route 201 over Pollock Run in Rostraver Township, Westmoreland County. The structurally deficient bridge | Bridge Replacement | 07/17/2009 | 07/27/2009 | 09/15/2010 | 738269 | 0.005
9059 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 18 | Z125007 | This project consists of painting the ends of the bridge beams at expansion joints, repairing bridge pier columns and caps at various locations, jacking and resetting of expansion bearings at piers 3 | Bridge Improvement | 07/13/2009 | 07/20/2009 | 08/16/2010 | 1132170 | 0.175
9060 | Pennsylvania | WESTMORELAND | MONESSEN | 12 | Z125008 | This project includes bridge abutment upgrades, spot painting, pier protection, and new bridge lighting for State Route 981 (Smithton Lo-Level Bridge), in Westmoreland County, Smithton Borough, Rostra | Bridge Improvement | 07/13/2009 | 07/20/2009 | 07/28/2010 | 665349 | 0.136
9061 | Pennsylvania | WESTMORELAND | MONESSEN | 12 | Z125009 | This project includes the enhancing several traffic signalized intersections. The work includes upgrading vehicular and pedestrian signal heads, replacing existing detection sensors, amplifiers, contr | Safety/Traffic Management | 07/29/2009 | 08/24/2009 | 07/06/2010 | 193460.02 | 1.133
9062 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 12 | Z125010 | This project will make the bridge last longer by replacing the deteriorating portons of the bridge carrying PA 136 over the Youghiogheny River in West Newton Borough in Westmoreland County. | Bridge Improvement | 02/18/2010 | 04/27/10 | 09/16/2010 | 1385535 | 0.133
9063 | Pennsylvania | WESTMORELAND | PITTSBURGH , PA | 12, 18 | Z125011 | This Westmoreland County project will make the roadway last longer and the ride smoother by overlaying the deteriorating pavement on US 30 from US 119 to Georges Station Road in Hempfield and Unity T | Pavement Improvement | 02/22/2010 | 02/22/2010 | 12/23/2011 | 5430982 | 9.987
9064 | Rhode Island | WASHINGTON |  | 2 | 0001104 | This project includes excavating planting beds, placing loam and installing new planting material in select locations in the U.S. Route 1 median between Mooresfield Road and the Oliver Stedman Governm | Pavement Improvement | 03/03/2009 | 06/15/2009 | 11/30/2010 | 156981.9 | 6.837
9065 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 2 | 0010011 | This project involves replacement of all signage on Route 10 from Park Avenue/Route 12 in Cranston to I-95 in Providence (5 miles). | Safety/Traffic Management | 05/20/2009 | 10/19/2009 | 09/22/2010 | 4403205.41 | 9.953
9066 | Rhode Island | WASHINGTON |  | 2 | 0043002 | This project will rehabilitate both Wyoming Bridges in Hopkinton, which carry Bridge Street over the Wood River, which are presently closed to traffic due to structural deterioration. | Bridge Replacement | 06/03/2009 |  | 09/23/2011 | 2908062.11 | 0.033
9067 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1 | 0146020 | This project will resurface Route 146 in Lincoln, from the Route 116 interchange to area of Sherman Avenue and Old Louisquisset Pike/Route 246 interchange, and will include guardrail replacement, join | Pavement Improvement | 09/22/2009 | 04/27/2009 | 07/01/2011 | 9893503.23 | 1.15
9068 | Rhode Island | WASHINGTON |  | 2 | 0481001 | This project will rehabilitate three bridges at the Dillons Corner Rotary in Narragansett. Work to consist of superstructure replacement of Dillions Corner Bridge (two structures), which carries Route | Bridge Improvement | 06/30/2009 | 09/28/2009 | 05/21/2011 | 8344543.05 | 0.099
9069 | Rhode Island | WASHINGTON |  | 1,2 | 0800003 | This project will fund continued long-term maintenance on the Jamestown-Verrazzano Bridge, which carries Route 138 over the West Passage of Narragansett Bay. | Bridge Improvement | 05/26/2009 | 09/14/2009 | 09/24/2010 | 1180959.5 | 1.4
9070 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1 | 0882002 | This project will rehabilitate Industrial Drive Bridge, which carries Industrial Drive over the Moshassuck River in Providence, including sidewalk repairs and resurfacing with new pavement. | Bridge Improvement | 06/09/2009 | 03/08/2010 | 05/15/2011 | 2459263.23 | 0.031
9071 | Rhode Island | WASHINGTON |  | 2 | 0953108 | This project is the first phase of a 25-mile resurfacing project of I-95 from Connecticut line to Exit 8 in Warwick. Stimulus funds will pay for first 7.6 miles from the State line to Exit 3 (Route 13 | Pavement Improvement | 04/15/2009 | 07/13/2009 | 12/09/2009 | 9061550 | 15.059
9072 | Rhode Island | KENT |  | 2 | 2955108 | This project will removal and replace light poles and electrical systems for overhead lighting on I-295 at Exits 1, 2, 4 and 5 in Warwick, Cranston and Johnston. Contract also includes additional traf | Safety/Traffic Management | 03/16/2009 | 07/12/2009 | 11/04/2010 | 3865243.39 | 11.9
9073 | Rhode Island | STATEWIDE |  | 1 | 4444072 | This project involves the application of striping on State roadways in Burrillville, Central Falls, Cumberland, Glocester, Lincoln, North Providence, North Smithfield, Pawtucket, Smithfield and Woonso | Safety/Traffic Management | 03/03/2009 | 05/10/2009 | 11/30/2010 | 1811221.25 | 0
9074 | Rhode Island | STATEWIDE |  | 1,2 | 4444073 | This project involves the application of striping on State roadways in Barrington, Bristol, East Providence, Little Compton, Middletown, Newport, Portsmouth, Providence, Tiverton and Warren. | Safety/Traffic Management | 03/03/2009 | 05/17/2009 | 11/30/2010 | 1695755.5 | 0
9075 | Rhode Island | PROVIDENCE |  | 2 | 8888180 | This enhancement project will improve the Manton Avenue streetscape in Providence, from Delaine Street to Sisson Street, and will include new sidewalks, crosswalks, street trees and street lighting (0 | Safety/Traffic Management | 03/17/2009 | 08/01/2009 | 07/15/2010 | 175547.74 | 0.8
9076 | Rhode Island | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1,2 | 8888181 | This statewide maintenance contract which involves signal repair and minor resurfacing as needed at roughly 60 different intersections throughout the state | Safety/Traffic Management | 06/02/2009 | 09/21/2009 | 05/18/2010 | 1245448.96 | 1
9077 | Rhode Island | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1 | 8888182 | This project will make various traffic signal improvements including the installation of new signals, signal modifications, and island modifications in Barrington, Burrillville, Foster, Johnston, Nort | Safety/Traffic Management | 06/03/2009 | 10/19/2009 | 08/18/2010 | 948050.79 | 1
9078 | Rhode Island | STATEWIDE |  | 2 | 8888183 | This project will make various traffic signal improvements including the installation of new signals, signal modifications, and island modifications in Coventry, East Greenwich, Exeter, North Kingstow | Safety/Traffic Management | 09/09/2009 | 03/22/2010 | 10/31/2010 | 696968.88 | 1
9079 | Rhode Island | STATEWIDE |  | 1,2 | 9999071 | The project involves the replacement and repair of rusted, damaged and/or substandard guardrail throughout the state to improve traffic safety. | Safety/Traffic Management | 03/09/2009 | 05/10/2009 | 03/31/2011 | 848648.82 | 1
9080 | Rhode Island | PROVIDENCE |  | 2 | A951001 | This project will replace the Chestnut Hill Road Bridge which carries Chestnut Hill Road over the spillway that flows from the Sayles and Smith Reservoir to the Chepachet River in Glocester. The proje | Bridge Improvement | 02/08/2010 |  |  | 1467015.08 | 1
9081 | Rhode Island | NEWPORT |  | 1 | AWDA016 | This project will install new sidewalks and curbing on Bristol Ferry Road in Portsmouth, from West Main Road/Route 114 to Boyd's Lane, and will Include intersection improvements and new traffic signal | Pavement Improvement | 03/04/2009 | 05/18/2009 | 11/12/2009 | 1919374.39 | 1.225
9082 | Rhode Island | KENT |  | 2 | AWDA019 | This project includes installation of new sidewalks and curbing in West Warwick on Legion Way, from Main Street to Providence Street, and on Providence Street, from Legion Way to East Main Street/Rout | Pavement Improvement | 03/16/2009 | 07/06/2009 | 09/16/2009 | 881335.99 | 0.72
9083 | Rhode Island | BRISTOL |  | 1 | AWDA020 | This project includes installation of new sidewalks in Warren, including new curbs and curb ramps, on Child Street from Cutler Street to the Massachusetts State line. (2.2 miles). | Pavement Improvement | 04/07/2009 | 10/26/2009 | 08/20/2010 | 2397793.22 | 1.803
9084 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 2 | AWDA021 | This project will repair a number of sidewalks in downtown Providence along Washington Street, from Empire Street to Eddy Street, and on Westminster Street, from Empire Street to 100 feet east of Math | Transportation Enhancements | 07/13/2009 |  |  | 1328267.94 | 0.43
9085 | Rhode Island | BRISTOL |  | 1 | AWDA023 | This project will install new sidewalks and curbing in Warren along North Main Street from Park Street to Wood Street and on Child Street from Cutler Street to the East Bay Bike Path (0.2 miles). | Pavement Improvement | 04/09/2010 | 04/09/2010 | 08/20/2010 | 761032.72 | 0.215
9086 | Rhode Island | STATEWIDE |  | 1,2 | DRNG015 | This project involves drainage improvements in the following communities: Hopkinton (Mechanic Street), Johnston (Winsor Avenue at Hawkins Pond), North Smithfield (Greenville Road), and West Greenwich | Pavement Improvement | 03/03/2009 | 06/09/2009 | 09/15/2009 | 862575.69 | 1
9087 | Rhode Island | STATEWIDE |  | 2 | DRNG016 | This project will improve the drainage at the intersection of Ten Rod Road/Route 165 and Black Plain Rd in Exeter. | Pavement Improvement | 03/04/2009 | 06/22/2009 | 09/15/2009 | 417661.62 | 1
9088 | Rhode Island | STATEWIDE |  | 1,2 | DRNG018 | This project involves various drainage improvements in the following communities: Cranston (Pippin Orchard Road), Lincoln (River Road/Route 126), and Narragansett (Bridgetown Road). | Pavement Improvement | 05/20/2009 | 09/02/2009 | 10/30/2009 | 510324.14 | 1
9089 | Rhode Island | STATEWIDE |  | 1,2 | DRNG020 | This project involves various drainage improvements in the following communities: Providence (North Main St.); Tiverton (East Rd. & Crandall Rd.); West Greenwich (Escoheag Hill Road). These improveme | Pavement Improvement | 02/17/2010 |  | 10/30/2010 | 253958.12 | 0.59
9090 | Rhode Island | WASHINGTON |  | 2 | KSRR001 | This project will repair and replace certain portions if the lead coated copper roof of the Kingston Train Station located in the village of West Kingston. The public train sstation is of historical s | Transportation Enhancements | 02/22/2010 |  |  | 231380 | 0
9091 | Rhode Island | STATEWIDE |  | 1,2 | MAIN022 | This project involves the power washing of 65 of Rhode Island's 772 bridges to remove road salts, dirt and bird droppings. Includes bridges located in the following towns: Cumberland, East Providence, | Bridge Improvement | 03/03/2009 |  |  | 693970.05 | 1
9092 | Rhode Island | STATEWIDE |  | 1,2 | MAIN023 | This project will power wash bridges to remove road salts, dirt and bird droppings. Includes bridges located in the following towns: Burrillville, Charlestown, Cranston, East Greenwich, Exeter, Hopkin | Bridge Improvement | 03/03/2009 | 06/29/2009 | 11/30/2009 | 461518 | 1
9093 | Rhode Island | PROVIDENCE |  | 1 | R012009 | This project will result in the construction of a 400-foot rocky seawall along the shoreline of the Seekonk River in East Providence and will include salt marsh mitigation, installation of a stone dus | Other | 03/04/2009 | 06/15/2009 | 11/10/2009 | 425169.72 | 1
9094 | Rhode Island | PROVIDENCE |  | 2 | RESF136 | This project will resurface Putnam Pike/Route 44 in Glocester, from Tourtellot Hill Road to the RIDOT Maintenance Facility, and will include drainage improvements and guardrail replacement (2 miles). | Pavement Improvement | 03/06/2009 | 06/29/2009 | 08/26/2009 | 1725592.89 | 1.202
9095 | Rhode Island | PROVIDENCE |  | 1 | RESF137 | This project will resurface Putnam Pike/Route 44 in Smithfield, from Austin Avenue to West Greenville Road, and will include replacement of sidewalks and curbing, drainage improvements, and a new sign | Pavement Improvement | 04/07/2009 | 08/03/2009 | 05/07/2010 | 2072739.3 | 0.998
9096 | Rhode Island | NEWPORT |  | 1 | RESF138 | This project will resurface Main Road/Route 138 in Tiverton, from John Street to the Massachusetts State Line, and will include curbing, sidewalks, and drainage and guardrail improvements (2.3 miles). | Pavement Improvement | 03/03/2009 | 03/23/2009 | 09/21/2009 | 3358236.02 | 2.375
9097 | Rhode Island | PROVIDENCE |  | 1 | RESF139 | This project will resurface Old Louisquisset Pike/Route 246 in Lincoln, from Breakneck Hill Road/Route 123 to Route 116/Route 146 interchange (2.3 miles). | Pavement Improvement | 03/03/2009 | 05/18/2009 | 09/18/2009 | 1632539.58 | 2.318
9098 | Rhode Island | NEWPORT |  | 1 | RESF144 | This project will resurface West Main Road in Middletown, from Coddington Highway to John Kesson Lane, and will include curbing and sidewalk replacement, new signage and pavement markings, replacement | Pavement Improvement | 03/06/2009 | 05/26/2009 | 10/06/2010 | 5882718.35 | 2.22
9099 | Rhode Island | STATEWIDE |  | 1,2 | RESF147 | This project involves the application of a rubberized asphalt chip seal on top of existing pavement to extend pavement service life. Roads will be sealed in Burrillville, Charlestown, Coventry, East G | Pavement Improvement | 03/03/2009 | 06/03/2009 | 09/03/2009 | 2504018.26 | 21.8
9100 | Rhode Island | STATEWIDE |  | 1,2 | RESF148 | This project involves the cleaning and sealing of cracks and open joints in existing pavement with a hot applied rubberized asphalt sealant to extend the pavement service life of roads in the southern | Pavement Improvement | 03/31/2009 | 07/13/2009 | 09/30/2009 | 313141.21 | 1
9101 | Rhode Island | STATEWIDE |  | 1,2 | RESF149 | This project involves cleaning and sealing cracks and open joints in existing pavement with a hot applied rubberized asphalt sealant to extend the pavement service life of the roads in the northern an | Pavement Improvement | 03/31/2009 | 08/03/2009 | 09/30/2009 | 226057.8 | 1
9102 | Rhode Island | WASHINGTON |  | 2 | RESF151 | This project will resurface Kingstown Road/Route 138 in Richmond, from Beaver River Road to 660 feet west of Route 112 (2 miles). | Pavement Improvement | 05/04/2009 | 07/22/2009 | 11/06/2009 | 2802073.89 | 2.221
9103 | Rhode Island | WASHINGTON |  | 2 | RESF153 | This project will resurface Ocean Road in Narragansett, from Narragansett Town Beach to Point Judith (3.7 miles), and Shore Road in Westerly, from Post Road to Ocean View Highway (4.5 miles). | Pavement Improvement | 03/09/2009 | 05/18/2009 | 10/15/2009 | 3003428.08 | 8.73
9104 | Rhode Island | PROVIDENCE | STATEWIDE | 2 | RESF157 | Resurfacing of Route 102 from Route 101 in Scituate to Old Plainfield in Foster (7.4), including drainage, guardrail improvements and safety improvements involving highway signs and pavement markings. | Pavement Improvement | 02/22/2010 |  | 10/15/2010 | 1432355.54 | 7.54
9105 | Rhode Island | PROVIDENCE |  | 2 | RESF159 | This project will add chip seal overlay along Hartford Pike/Route 101, from the Connecticut State line to Route 94 in Foster, and from Anan Wade Road to Route 102 in Scituate (4 miles). | Pavement Improvement | 05/14/2009 | 09/28/2009 | 10/30/2009 | 1640832.43 | 4.2
9106 | Rhode Island | PROVIDENCE |  | 1 | RESF160 | This project will resurface Nate Whipple Highway/Route 120 in Cumberland, from Diamond Hill Road/Route 114 to Mendon Road/Route 122, and will include new curbing, sidewalk, guardrail, minor drainage w | Pavement Improvement | 03/06/2009 | 06/01/2009 | 11/30/2009 | 2791050 | 2.628
9107 | Rhode Island | PROVIDENCE |  | 1 | RESF166 | This project will resurface Nate Whipple Highway/Route 120, in Cumberland, from Diamond Hill Road/Route 114 to the Massachusetts State line, and will include new curbing, sidewalk, guardrail, minor dr | Pavement Improvement | 06/09/2009 | 09/07/2009 | 08/20/2010 | 1870898.88 | 1.7
9108 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1 | RESF170 | This project will resurface Diamond Hill Road/Route 114 in Woonsocket, from Social Street to Bound Road, and will include curbing, sidewalks, guardrail, minor drainage improvements, and signal work (2 | Pavement Improvement | 08/03/2009 | 10/26/2009 | 10/22/2010 | 4455588.1 | 2.16
9109 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 2 | RESF174 | This project involves reconstruction of Hartford Avenue/Route 6A in Johnston, from the I-295 interchange to Atwood Avenue/Route 5, and will include curbing, sidewalks, widening a portion to provide a | Pavement Improvement | 05/20/2009 | 09/28/2009 | 10/29/2010 | 4291253.67 | 2.542
9110 | Rhode Island | PROVIDENCE |  | 1 | RESF175 | This project will resurface High Street/Diamond Hill Road/Route 114 in Woonsocket, from the Cumberland Public Library to Blackstone Street, and will include curbing, sidewalk, guardrail, minor drainag | Pavement Improvement | 09/09/2009 | 04/17/2010 | 09/03/2010 | 1461894.6 | 1.021
9111 | Rhode Island | BRISTOL |  | 1 | RESF176 | Main St. (Rte. 114), installation of new curbing, sidewalks, minor drainage improvements and street tree preservation and replacement from Cherry St. to 160 feet south of Beach St. (0.3 miles). | Pavement Improvement | 02/12/2010 |  | 09/30/2010 | 684294 | 0.4
9112 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 2 | RESF178 | This project involves the resurfacing of three streets in Providence, from West Exchange Street to Point Street, encompassing Dean Street, Cahir Street and Stewart Street. It will include upgraded sig | Pavement Improvement | 05/20/2009 | 09/28/2009 | 12/14/2010 | 4636641.58 | 0.739
9113 | Rhode Island | WASHINGTON |  | 2 | RESF179 | This project will resurface Oak Street/Westerly Bradford Road/Route 91 in Westerly, from Route 3 to Westerly Maintenance Facility, and will include new sidewalks, minor drainage improvements, water li | Pavement Improvement | 06/17/2009 | 09/28/2009 | 10/21/2009 | 3779852.1 | 1.304
9114 | Rhode Island | PROVIDENCE |  | 2 | RESF181 | This project involves the reclamation and resurfacing of Route 14/Route 102/Plainfield Pike/Victory Highway from Briggs Rd. to Old Plainfield Pike in the Town of Foster. (1.2 miles). | Pavement Improvement | 02/03/2010 |  | 09/24/2010 | 710227.21 | 1.3
9115 | Rhode Island | PROVIDENCE |  | 2 | RESF182 | This project involves the reclamation and resurfacing of Moosup Valley Road from 0.9 miles west of Route 14/Plainfield Pike to Cucumber Hill Road in the Town of Foster.(1.4 miles). | Pavement Improvement | 02/03/2010 |  | 09/24/2010 | 849968.6 | 1.4
9116 | Rhode Island | WASHINGTON |  | 2 | RESF183 | This project will resurface Route 91/Westerly Bradford Road/Bradford Road, including curbing, sidewalks, guardrail, minor drainage improvements, signage and pavement markings, from Westerly Maintenanc | Pavement Improvement | 01/28/2010 | 05/24/2010 | 11/23/2010 | 2854508.85 | 4.45
9117 | Rhode Island | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 1 | RESF185 | Resurfacing of Route 99/Woonsocket Industrial Highway, including curbing, minor drainage work, signage structures and minor bridge work from Route 146 to Route 122/Mendon Rd. (2.7 miles). | Pavement Improvement | 02/12/2010 |  | 04/21/2011 | 3876686.39 | 3.84
9118 | Rhode Island | NEWPORT |  | 1 | RESF188 | Resurfacing of Colebrook Road in the town of Little Compton including the replacement of drainage systems, from Long Highway to Route 179 (1.7 miles) | Pavement Improvement | 02/08/2010 |  |  | 1895364.27 | 1.982
9119 | Rhode Island | PROVIDENCE |  | 2 | SDRP007 | This project involves the construction of a storm water treatment pond at the interchange of Route 6 on the Providence/Johnston line at the Killingly Street/Route 128 exit. | Other | 03/03/2009 | 04/13/2009 | 10/16/2009 | 917943.77 | 1
9120 | Rhode Island | PROVIDENCE |  | 1,2 | SDRP008 | This project will review approximately 60 out of 130 storm water drainage systems, ponds, catch basins, etc. that were previously upgraded to meet Federal Best Management Practices, in accordance with | Other | 06/04/2009 |  | 11/19/2010 | 197832.4 | 1
9121 | Rhode Island | STATEWIDE |  | 1,2 | SIGN015 | This project will replace signage along I-95 at Exits 6, 7 and 8 (West Greenwich, East Greenwich, West Warwick, and Warwick), Exit 12B (Warwick), Exists 16-18 (Cranston and Providence), and Exit 29 (P | Safety/Traffic Management | 03/09/2009 | 07/16/2009 | 07/07/2010 | 3001224.46 | 15.003
9122 | Rhode Island | PROVIDENCE |  | 2 | SIGN016 | This project will replace all road signage on Route 37 from Post Road/Route 1 in Warwick to Natick Avenue in Cranston (3.2 miles). | Safety/Traffic Management | 03/09/2009 | 07/20/2009 | 08/26/2010 | 3221335.62 | 6.424
9123 | Rhode Island | STATEWIDE |  | 1,2 | SSRV002 | OJT Training Supportive Services- ARRA OJT/SS PRogram 2009. The purpose of this award is to establish partnerships to facilitate the referral of qualified individuals to increase the participation o | Other | 07/16/2009 |  |  | 350000 | 0
9124 | Rhode Island | PROVIDENCE |  | 2 | TEA2060 | This enhancement project will improve the Manton Avenue streetscape in Providence, from Delaine Street to Sisson Street, and will include new sidewalks, crosswalks, street trees and street lighting (0 | Transportation Enhancements | 03/17/2009 | 08/01/2009 | 12/01/2010 | 500000 | 0.77
9125 | Rhode Island | PROVIDENCE |  | 2 | TEAC090 | This project will improve the Westminster Street streetscape in Providence, from Service Road No. 7 to Olneyville Square/Manton Avenue/Plainfield Street, and will include sidewalks, crosswalks, bicycl | Transportation Enhancements | 06/11/2009 |  |  | 3300000 | 1.223
9126 | Rhode Island | STATEWIDE |  | 1,2 | TRMS009 | This project involves the installation of radar-based vehicle detectors, at the same location as existing traffic cameras, to collect data on traffic volume and speeds. The new detectors provide alert | Safety/Traffic Management | 03/09/2009 | 06/07/2009 | 06/11/2010 | 584059.2 | 0
9127 | Rhode Island | STATEWIDE |  | 1,2 | TRMS010 | This project involves the installation of radar-based vehicle detectors in several locations to collect data on traffic volume, speed, and vehicle classification used for annual reporting requirements | Safety/Traffic Management | 03/03/2009 | 05/31/2009 | 06/16/2010 | 913832.26 | 0
9128 | South Carolina | AIKEN |  | 3 | SP09001 | Resurfacing various road in Aiken County. | Pavement Improvement | 01/25/2010 | 03/29/2010 | 10/31/2010 | 3009977.47 | 0
9129 | South Carolina | KERSHAW |  | 5 | SP09002 | Resurfacing various roads in Kershaw County. | Pavement Improvement | 02/04/2010 | 03/13/2010 | 07/31/2010 | 2480329.86 | 0
9130 | South Carolina | AIKEN | AUGUSTA (GA) | 3 | SP09003 | Resurfacing various roads in and around North August, in Aiken County SC. | Pavement Improvement | 04/23/2010 | 07/06/2010 | 08/31/2010 | 1604941.63 | 0
9131 | South Carolina | RICHLAND |  | 6 | SP09005 | Resurfacing various roads in Richland County. | Pavement Improvement | 07/31/2009 | 07/29/2009 | 11/30/2009 | 2343090.99 | 2.42
9132 | South Carolina | ANDERSON |  | 3 | SP09014 | Resurfacing various roads in Anderson County. | Pavement Improvement | 07/31/2009 | 07/31/2009 | 04/30/2010 | 3389929.67 | 0
9133 | South Carolina | MARION, FLORENCE |  | 6 | SP09028 | Resurfacing various roads in Florence and Marion Counties. | Pavement Improvement | 06/26/2009 | 08/03/2009 | 06/30/2010 | 4479716.13 | 0
9134 | South Carolina | GEORGETOWN, WILLIAMSBURG, HORRY |  | 1 | SP09029 | Resurfacing various roads in Georgetown and Horry Counties. | Pavement Improvement | 08/17/2009 | 08/31/2009 | 05/31/2010 | 8228104.08 | 3.36
9135 | South Carolina | JASPER, BEAUFORT |  | 2 | SP09034 | Resurfacing various roads in Beaufort and Jasper Counties. | Pavement Improvement | 03/29/2010 | 04/21/2010 | 08/31/2010 | 2311520.51 | 3.01
9136 | South Carolina | BERKELEY |  | 6 | SP09035 | Resurfacing various roads in Berkeley County. | Pavement Improvement | 07/15/2009 | 08/10/2009 | 11/30/2009 | 1914024.75 | 2.5
9137 | South Carolina | BERKELEY, CHARLESTON |  | 1,6 | SP09036 | Resurfacing various roads in Charleston County. | Pavement Improvement | 11/13/2009 | 01/13/2010 | 11/30/2010 | 2867171.49 | 0
9138 | South Carolina | STATEWIDE |  | 6 | SP09044 | Resurfacing various roads in Orangeburg County. | Pavement Improvement | 02/02/2010 | 04/19/2010 | 08/31/2010 | 4883991.06 | 0
9139 | South Carolina | KERSHAW |  | 5 | SP09048 | Resurfacing various roads in Kershaw County. | Pavement Improvement | 07/17/2009 | 07/14/2009 | 11/30/2009 | 1366589.44 | 0.56
9140 | South Carolina | SUMTER, LEE |  | 5, 6 | SP09049 | Resurfacing various roads in Lee County. | Pavement Improvement | 08/05/2009 | 08/05/2009 | 05/31/2010 | 2501220.77 | 0
9141 | South Carolina | LEXINGTON |  | 2 | SP09050 | Resurfacing various roads in Lexington County. | Pavement Improvement | 08/24/2009 | 08/26/2009 | 04/30/2010 | 3273380.28 | 0
9142 | South Carolina | GREENWOOD, LAURENS, ABBEVILLE |  | 3 | SP09053 | Resurfacing various roads in Abbeville, Greenwood, and Laurens Counties. | Pavement Improvement | 06/09/2009 | 09/10/2009 | 05/31/2010 | 6117334.59 | 0
9143 | South Carolina | EDGEFIELD, NEWBERRY, SALUDA, MCCORMICK |  | 3 | SP09054 | Resurfacing various roads in Edgefield, McCormick, Newberry, and Saluda Counties. | Pavement Improvement | 06/22/2009 | 06/22/2009 | 05/31/2010 | 5562117.73 | 9.92
9144 | South Carolina | GREENVILLE |  | 4 | SP09061 | Resurfacing various roads in Greenville County. | Pavement Improvement | 07/24/2009 | 07/27/2009 | 04/30/2010 | 5497874.66 | 0
9145 | South Carolina | OCONEE |  | 3 | SP09062 | Resurfacing various roads in Oconee County. | Pavement Improvement | 06/19/2009 | 06/12/2009 | 11/30/2009 | 2102074.79 | 0
9146 | South Carolina | PICKENS |  | 3 | SP09063 | Resurfacing various roads in Pickens County. | Pavement Improvement | 07/10/2009 | 07/16/2009 | 04/30/2010 | 2487281.1 | 0
9147 | South Carolina | SPARTANBURG |  | 4 | SP09064 | Resurfacing various roads in Spartanburg County. | Pavement Improvement | 11/19/2009 | 02/07/2010 | 11/30/2010 | 5071592.61 | 0
9148 | South Carolina | CHEROKEE, UNION |  | 5 | SP09065 | Resurfacing various roads in Cherokee and Union Counties. | Pavement Improvement | 06/19/2009 | 07/20/2009 | 05/31/2010 | 2302842.63 | 5.47
9149 | South Carolina | CHESTER |  | 5 | SP09066 | Resurfacing various roads in Chester County. | Pavement Improvement | 06/19/2009 | 07/06/2009 | 04/30/2010 | 1300877.82 | 0
9150 | South Carolina | CHESTERFIELD |  | 5 | SP09067 | Resurfacing various roads in Chesterfield County. | Pavement Improvement | 07/10/2009 | 07/06/2009 | 11/30/2009 | 1375591.1 | 0
9151 | South Carolina | FAIRFIELD |  | 5 | SP09068 | Resurfacing various roads in Fairfield County. | Pavement Improvement | 07/01/2009 | 07/01/2009 | 11/30/2009 | 1629550.78 | 0
9152 | South Carolina | LANCASTER |  | 5 | SP09069 | Resurfacing various roads in Lancaster County. | Pavement Improvement | 07/24/2009 | 07/27/2009 | 11/30/2009 | 1813681.97 | 0
9153 | South Carolina | YORK |  | 5 | SP09071 | Resurfacing various roads in York County. | Pavement Improvement | 07/24/2009 | 06/24/2009 | 11/30/2009 | 1905153.79 | 0
9154 | South Carolina | DILLON, DARLINGTON, MARLBORO |  | 5 | SP09072 | Resurfacing various roads in Darlington, Dillion, and Marlboro Counties. | Pavement Improvement | 07/17/2009 | 09/03/2009 | 05/31/2010 | 3662322.67 | 0
9155 | South Carolina | BEAUFORT |  | 2 | SP09080 | Resurfacing various roads in Beaufort County. | Pavement Improvement | 07/31/2009 | 08/14/2009 | 10/31/2009 | 2293705.65 | 0
9156 | South Carolina | CHARLESTON |  | 1, 6 | SP09082 | Resurfacing various roads in Charleston County. | Pavement Improvement | 07/10/2009 | 08/12/2009 | 11/30/2009 | 2704835.67 | 0
9157 | South Carolina | COLLETON |  | 6 | SP09083 | Resurface various roads in Colleton County. | Pavement Improvement | 07/24/2009 | 10/15/2009 | 11/30/2009 | 1928204.41 | 0
9158 | South Carolina | DORCHESTER |  | 1, 6 | SP09084 | Resurfacing various roads in Dorchester County. | Pavement Improvement | 07/24/2009 | 09/03/2009 | 11/30/2009 | 1729762.43 | 0
9159 | South Carolina | JASPER |  | 2 | SP09085 | Resurfacing various roads in Jasper County. | Pavement Improvement | 07/31/2009 | 08/18/2009 | 11/30/2009 | 1729264.13 | 2.42
9160 | South Carolina | BAMBERG, HAMPTON, ALLENDALE, BARNWELL |  | 2 | SP09086 | Resurfacing various roads in Allendale, Bamberg, Barnwell, and Hampton Counties. | Pavement Improvement | 06/09/2009 | 07/15/2009 | 05/31/2010 | 4556504.78 | 0
9161 | South Carolina | CLARENDON, ORANGEBURG, CALHOUN |  | 6, 2 | SP09089 | Resurfacing various roads in Calhoun, Clarendon, and Orangeburg Counties. | Pavement Improvement | 06/19/2009 | 06/29/2009 | 05/31/2010 | 4957777.28 | 0
9162 | South Carolina | AIKEN |  | 3 | SP09093 | Resurfacing various roads in Aiken County. | Pavement Improvement | 01/21/2010 | 04/13/2010 | 09/30/2010 | 3086735.13 | 0
9163 | South Carolina | RICHLAND |  | 6 | SP09095 | Resurfacing various roads in Richland County. | Pavement Improvement | 09/26/2009 | 01/20/2010 | 08/31/2010 | 2024617.01 | 0
9164 | South Carolina | LEXINGTON |  | 2 | SP09096 | Resurface various roads in Lexington County. | Pavement Improvement | 01/25/2010 | 04/26/2010 | 09/30/2010 | 2962858.16 | 0
9165 | South Carolina | SUMTER, LEE |  | 5 | SP09098 | Resurfacing various roads in Lee County. | Pavement Improvement | 04/01/2010 | 04/27/2010 | 08/31/2010 | 4173799.54 | 0
9166 | South Carolina | SPARTANBURG |  | 4 | SP09110 | Resurfacing various roads in Spartanburg County. | Pavement Improvement | 01/20/2010 | 02/04/2010 | 04/30/2011 | 9150459.55 | 0
9167 | South Carolina | CHEROKEE |  | 5 | SP09111 | Resurfacing various roads in Cherokee County. | Pavement Improvement | 11/23/2009 | 03/18/2010 | 06/30/2010 | 2176549.67 | 0
9168 | South Carolina | CHESTER |  | 5 | SP09112 | Resurfacing various roads in Cherster County. | Pavement Improvement | 11/12/2009 | 05/04/2010 | 08/17/2010 | 1671891.71 | 5.59
9169 | South Carolina | CHESTERFIELD |  | 5 | SP09113 | Resurfacing various roads in Chesterfield County. | Pavement Improvement | 12/01/2009 | 05/11/2010 | 08/31/2010 | 3187544.2 | 10.88
9170 | South Carolina | FAIRFIELD |  | 5 | SP09114 | Resurfacing various roads in Greenville County. | Pavement Improvement | 11/12/2009 | 06/15/2010 | 09/30/2010 | 1622393.52 | 0
9171 | South Carolina | LANCASTER |  | 5 | SP09115 | Resurfacing various roads in Lancaster County. | Pavement Improvement | 02/02/2010 | 05/06/2010 | 07/31/2010 | 2385184.77 | 0
9172 | South Carolina | DILLON, DARLINGTON, MARLBORO |  | 5 | SP09118 | Resurfacing various roads in Dillon, Darlington, and Marlboro Counties. | Pavement Improvement | 01/06/2010 | 01/28/2010 | 05/31/2011 | 5253043.62 | 8.82
9173 | South Carolina | GEORGETOWN, MARION, HORRY |  | 1 | SP09121 | Resurfacing various roads in Georgetown, Horry, Marion, and Williamsburg Counties | Pavement Improvement | 04/28/2010 | 04/28/2010 | 11/30/2010 | 8096694.85 | 1.12
9174 | South Carolina | WILLIAMSBURG, FLORENCE |  | 6 | SP09125 | Resurfacing various roads in Florence County. | Pavement Improvement | 11/05/2009 | 12/28/2009 | 06/30/2011 | 7678448.91 | 8.68
9175 | South Carolina | STATEWIDE |  | 2 | SP09132 | Resurfacing various roads in Allendale and Hampton Counties. | Pavement Improvement | 02/03/2010 | 05/05/2010 | 08/31/2010 | 3540566.35 | 11.85
9176 | South Carolina | BARNWELL |  | 2 | SP09134 | Resurfacing various roads in Barnwell County. | Pavement Improvement | 02/03/2010 | 03/24/2010 | 06/30/2010 | 1274979.82 | 3.76
9177 | South Carolina | CALHOUN |  | 2 | SP09135 | Resurfacing various roads in Calhoun County. | Pavement Improvement | 02/02/2010 | 03/08/2010 | 07/31/2010 | 1286276.33 | 2.66
9178 | South Carolina | RICHLAND |  | 6 | SP09143 | Resurfacing various roads in Richland County. | Pavement Improvement | 06/19/2009 | 07/17/2009 | 11/30/2009 | 2138817.41 | 0
9179 | South Carolina | GREENWOOD, LAURENS, ABBEVILLE |  | 3 | SP09145 | Resurfacing various roads in Abbeville County. | Pavement Improvement | 04/23/2010 | 06/14/2010 | 11/30/2010 | 3415707.88 | 4.71
9180 | South Carolina | EDGEFIELD, NEWBERRY, SALUDA, MCCORMICK |  | 3 | SP09146 | Resurfacing various roads in Edgefield, McCormick, Newberry, and Saluda Counties. | Pavement Improvement | 04/23/2010 |  | 09/30/2010 | 4656222.02 | 12.56
9181 | South Carolina | ANDERSON |  | 3 | SP09152 | Resurfacing various roads in Anderson County. | Pavement Improvement | 02/18/2010 | 06/02/2010 | 08/31/2010 | 1962809.24 | 0
9182 | South Carolina | GREENVILLE |  | 4 | SP09153 | Resurfacing various roads in Greenville County. | Pavement Improvement | 02/16/2010 | 02/26/2010 | 08/30/2010 | 2200000 | 0
9183 | South Carolina | OCONEE, PICKENS |  | 3 | SP09154 | Resurfacing various roads in Oconee and Pickens Counties. | Pavement Improvement | 10/26/2009 | 10/28/2009 | 09/30/2010 | 2229416.86 | 0
9184 | South Carolina | UNION |  | 4 | SP09162 | Resurfacing various roads in Union County. | Pavement Improvement | 11/12/2009 | 01/27/2010 | 07/31/2010 | 933446 | 3.61
9185 | South Carolina | YORK |  | 5 | SP09163 | Resurfacing various roads in York County. | Pavement Improvement | 11/27/2009 | 04/22/2010 | 11/30/2010 | 1702975.78 | 3.96
9186 | South Carolina | COLLETON, DORCHESTER |  | 6 | SP09175 | Resurfacing various roads in Colleton County. | Pavement Improvement | 09/28/2009 | 09/28/2009 | 08/31/2010 | 2607442.23 | 0
9187 | South Carolina | STATEWIDE |  | 1, 6 | SPBR001 | Replacement of eight bridges on US 378 over the Little Pee Dee River and Maple Swamp areas of Marion and Horry Counties. | Bridge Replacement | 07/10/2009 | 07/08/2009 | 10/31/2011 | 21000000 | 7.2
9188 | South Carolina | LAURENS |  | 3 | SPBR002 | Replacement of bridge over Durbin Creek on Allen Bridge Road in Laurens County 14.8 miles west of Laurens. | Bridge Replacement | 11/11/2009 | 11/18/2009 | 11/30/2010 | 1331973.78 | 0.1
9189 | South Carolina | EDGEFIELD |  | 3 | SPBR003 | Replacement of bridge over Turkey Creek on Weaver Road in Edgefield County 3.1 miles west of Johnston SC, and replacement of bridge over Bartly Branch on Bland Baptist Road 2.5 miles north west of Joh | Bridge Replacement | 09/23/2009 | 10/26/2009 | 07/31/2010 | 1891689.08 | 0.2
9190 | South Carolina | CHARLESTON | CHARLESTON | 1 | SPBR005 | Replacement of bridge over Tidal Creek on Brickyard Road in Charleston County. | Bridge Replacement | 07/24/2009 | 07/27/2009 | 04/30/2010 | 656042.29 | 0
9191 | South Carolina | COLLETON |  | 6 | SPBR006 | Replacement of bridge over Caphen Swamp on Combahee Road near Walterboro, SC in Colleton County. | Bridge Replacement | 11/30/2009 | 10/09/2009 | 03/10/2010 | 1022246.13 | 0.499
9192 | South Carolina | JASPER |  | 2 | SPBR007 | Replace bridge to Knowles Island in Jasper County. | Bridge Replacement | 10/12/2009 | 10/12/2009 | 06/30/2010 | 1619971.75 | 0.04
9193 | South Carolina | YORK | STATEWIDE | 5 | SPBR008 | Replacement of bridge over Catawba River on Cherry Road 4.1 miles north of Rock Hill, SC in York County. | Bridge Replacement | 03/11/2010 | 04/05/2010 | 11/30/2009 | 11836210 | 1.23
9194 | South Carolina | BAMBERG, ORANGEBURG |  | 6 | SPBR009 | Replacement of bridge and bridge approaches over the South Edisto River on Us 78 (Edwards Street) 4.0 miles west of Branchville near the Bamberg and Orangeburg County lines. | Bridge Replacement | 04/28/2010 | 05/18/2010 | 08/31/2012 | 12913741.56 | 1.31
9195 | South Carolina | KERSHAW, LEE |  | 5 | SPEH001 | Sidewalk repairs, replacement, and construction in various locations in Kershaw and Lee Counties. | Transportation Enhancements | 10/12/2009 | 11/04/2009 | 06/30/2010 | 316356.3 | 0
9196 | South Carolina | LAURENS |  | 3 | SPEH002 | Repair, replace, construct sidewalks in various locations in Laurens County SC | Transportation Enhancements | 04/23/2010 |  | 08/31/2010 | 218583.9 | 0
9197 | South Carolina | LEXINGTON |  | 2 | SPEH003 | Sidewalk repairs, replacement, and construction in various locations in Lexington County. | Transportation Enhancements | 11/16/2009 | 11/16/2009 | 07/31/2010 | 318476.49 | 0
9198 | South Carolina | YORK |  | 5 | SPEH004 | Sidewalk repairs, replacement, and construction in various locations in York County | Transportation Enhancements | 01/23/2010 | 03/19/2010 | 07/31/2010 | 586125.43 | 0
9199 | South Carolina | BERKELEY, DORCHESTER |  | 1,6 | SPEH005 | Construct, repair, replace ADA ramps in Berkeley and Dorchester Counties | Transportation Enhancements | 06/25/2010 |  | 11/30/2010 | 126387 | 0
9200 | South Carolina | COLLETON, JASPER, BEAUFORT |  | 1,6 | SPEH006 | Construct, repair, replace ADA ramps in various locations in Baufort, Colleton, and Jasper Counties SC | Transportation Enhancements | 06/25/2010 |  | 12/15/2010 | 171369 | 0
9201 | South Carolina | RICHLAND, LEXINGTON |  | 2,6 | SPEH007 | Sidewalk repairs, replacement, and construction in various locations in Richland County | Transportation Enhancements | 01/18/2010 | 01/20/2010 | 12/31/2010 | 688243.5 | 0
9202 | South Carolina | CHARLESTON |  | 1,6 | SPEH008 | Construct, repair, replace ADA ramps in various locations in Charleston County, SC | Transportation Enhancements | 06/25/2010 |  | 11/30/2010 | 275994 | 0
9203 | South Carolina | LEXINGTON |  | 2 | SPEH010 | Construct, repair, and replace side walks at various locations in Lexington County | Transportation Enhancements | 05/24/2010 |  | 09/30/2010 | 294901.94 | 0
9204 | South Carolina | SUMTER |  | 6,5 | SPEH011 | Sidewalk repairs, replacement, and construction in various locations in Sumter County | Transportation Enhancements | 05/07/2010 | 05/12/2010 | 07/31/2010 | 269904.96 | 0
9205 | South Carolina | ABBEVILLE |  | 3,5 | SPEH013 | Sidewalk repairs, replacement, and construction in various locations in Abbeville, Laurens, and Newberry Counties | Transportation Enhancements | 05/05/2010 | 05/05/2010 | 06/30/2010 | 108591.34 | 0
9206 | South Carolina | GREENWOOD, EDGEFIELD |  | 3 | SPEH014 | Sidewalk repairs, replacement, and construction in various locations in Edgefield, Greenwood, and McCormick Counties | Transportation Enhancements | 12/23/2009 | 01/18/2010 | 06/30/2010 | 660122.48 | 0
9207 | South Carolina | AIKEN |  | 3 | SPEH015 | Replace, repair, construct sidewalks in Aiken County | Transportation Enhancements | 05/18/2010 | 06/29/2010 | 07/31/2010 | 133156.87 | 0
9208 | South Carolina | LAURENS |  | 3 | SPEH016 | Repair, replace, construct sidewalks at various locations in Laurens County, SC | Transportation Enhancements | 03/29/2010 | 06/09/2010 | 09/30/2010 | 163899.99 | 0
9209 | South Carolina | GREENWOOD |  | 3 | SPEH018 | Construct, repair, and replace sidewalks at various locations in Greenwood County | Transportation Enhancements | 05/14/2010 |  | 09/30/2010 | 206397.99 | 0
9210 | South Carolina | GREENVILLE |  | 4 | SPEH020 | Sidewalk repairs, replacement, and construction in various locations in Greenville County | Transportation Enhancements | 12/01/2009 | 01/04/2010 | 07/31/2010 | 673205.15 | 0
9211 | South Carolina | GREENVILLE |  | 4 | SPEH022 | Sidewalk repairs, replacement, and construction in various locations in Greenville County | Transportation Enhancements | 06/03/2010 |  | 09/30/2010 | 263408.4 | 0
9212 | South Carolina | OCONEE, PICKENS |  | 3 | SPEH024 | Sidewalk repairs, replacement, and construction in various locations in Oconee and Pickens Counties | Transportation Enhancements | 02/02/2010 | 02/10/2010 | 06/30/2010 | 536991.48 | 0
9213 | South Carolina | SPARTANBURG |  | 4 | SPEH026 | Sidewalk repairs, replacement, and construction in various locations in Spartenburg County | Transportation Enhancements | 03/23/2010 | 03/24/2010 | 06/30/2010 | 459818.37 | 0
9214 | South Carolina | CHEROKEE, UNION |  | 5 | SPEH028 | Sidewalk repairs, replacement, and construction in various locations in Cherokee and Union Counties | Transportation Enhancements | 03/31/2010 | 05/12/2010 | 10/31/2011 | 317751.93 | 0
9215 | South Carolina | CHESTER, FAIRFIELD |  | 5 | SPEH029 | Sidewalk repairs, replacement, and construction in various locations in Chester County | Transportation Enhancements | 12/10/2009 | 01/04/2010 | 08/31/2010 | 413370 | 0
9216 | South Carolina | CHESTERFIELD, LANCASTER |  | 5 | SPEH030 | Sidewalk repairs, replacement, and construction in various locations in Chesterfield County | Transportation Enhancements | 11/19/2009 | 02/17/2010 | 10/10/2010 | 597586.98 | 0
9217 | South Carolina | DILLON, DARLINGTON, MARLBORO |  | 5 | SPEH037 | Sidewalk repairs, replacement, and construction in various locations in Darlingtion, Dillon, and Marlboro Counties | Transportation Enhancements | 09/28/2009 | 09/28/2009 | 04/30/2010 | 360744.3 | 0
9218 | South Carolina | WILLIAMSBURG, MARION, FLORENCE |  | 6 | SPEH039 | Sidewalk repairs, replacement, and construction in various locations in Florence, Marion, and Williamsburg Counties | Transportation Enhancements | 03/25/2010 | 03/28/2010 | 10/31/2010 | 312230.15 | 0
9219 | South Carolina | GEORGETOWN, HORRY |  | 1 | SPEH040 | Sidewalk repairs, replacement, and construction in various locations in Georgetown and Horry Counties | Transportation Enhancements | 03/01/2010 | 03/08/2010 | 07/31/2010 | 358968.45 | 0
9220 | South Carolina | DILLON, DARLINGTON, MARLBORO, FLORENCE |  | 5,6 | SPEH045 | Sidewalk repairs, replacement, and construction in various locations in Darlington, Dillon, Florence, and Marlboro Counties. | Transportation Enhancements | 12/27/2009 | 12/29/2009 | 06/30/2010 | 265725.97 | 0
9221 | South Carolina | GEORGETOWN, MARION, WILLIAMSBURG, HORRY |  | 1,6 | SPEH050 | Sidewalk repairs, replacement, and construction in various locations in Georgetown, Horry, Marion, and Williamsburg Counties. | Transportation Enhancements | 12/27/2009 | 02/12/2010 | 06/30/2010 | 139104 | 0
9222 | South Carolina | BERKELEY |  | 1,6 | SPEH054 | Sidewalk repairs, replacement, and construction in various locations in Berkeley and Dorchester Counties. | Transportation Enhancements | 04/26/2010 | 05/05/2010 | 08/31/2010 | 408843.94 | 0
9223 | South Carolina | DORCHESTER |  | 1,6 | SPEH059 | Repair, replace, construct sidewalks in various locations in Dorchester County SC | Transportation Enhancements | 03/22/2010 |  | 10/31/2010 | 169871.04 | 0
9224 | South Carolina | AIKEN |  | 3 | SPEH061 | Sidewalk repairs, replacement, and construction in various locations in Aiken County | Transportation Enhancements | 03/04/2010 | 05/12/2010 | 06/30/2010 | 566556.74 | 0
9225 | South Carolina | BAMBERG, HAMPTON, ALLENDALE, BARNWELL |  | 2,6 | SPEH065 | Sidewalk repairs, replacement, and construction in various locations in Allendale, Bamberg, Barnwell, Hampton Counties | Transportation Enhancements | 12/07/2009 | 01/18/2010 | 07/31/2010 | 358502.1 | 0
9226 | South Carolina | CLARENDON, ORANGEBURG, CALHOUN |  | 6,2 | SPEH068 | Sidewalk repairs, replacement, and construction in various locations in Calhoun, Clarendon, and Orangeburg Counties | Transportation Enhancements | 02/02/2010 | 02/23/2010 | 06/30/2010 | 471919.61 | 0
9227 | South Carolina | GREENVILLE |  | 4 | SPEH074 | ARRA Sidewalk repari, replacement, construction in various locations in Greenville County SC. | Transportation Enhancements | 06/01/2010 | 07/15/2010 | 10/31/2010 | 223521.34 | 0
9228 | South Carolina | ANDERSON |  | 3 | SPEH075 | Repair, replace, construct sidewalks at various locations in Anderson County SC | Transportation Enhancements | 04/16/2010 | 04/21/2010 | 08/31/2010 | 224212.32 | 0
9229 | South Carolina | ANDERSON |  | 3 | SPEH077 | Repair, replace, construct sidewalks at various locations in Anderson County SC | Transportation Enhancements | 04/16/2010 | 04/21/2010 | 06/30/2010 | 166206.6 | 0
9230 | South Carolina | NEWBERRY |  | 5 | SPEH078 | Repiar, replace, construct sidewalks at various locations in Newberry County SC | Transportation Enhancements | 05/24/2010 | 05/24/2010 | 09/30/2010 | 211746.67 | 0
9231 | South Carolina | STATEWIDE |  | 2, 6 | SPIM001 | Resurface and rehabilitate the east bound lane of I-20 in Lexington and Richland Counties from approximately US-378 to approximately US-321. | Pavement Improvement | 09/14/2009 | 09/14/2009 | 10/31/2010 | 10540556.3 | 10
9232 | South Carolina | AIKEN |  | 3 | SPIM002 | Resurface and rehabilitate the east bound lane of I-20 in Aiken County from approximately US-1 to approximately US-178. | Pavement Improvement | 08/24/2009 | 08/24/2009 | 09/30/2010 | 11868849.35 | 16
9233 | South Carolina | RICHLAND | COLUMBIA | 6 | SPIM003 | Resurface and rehabilitate the south bound lane of I-77 in Richland County from approximately S-151 to approximately US-1 | Pavement Improvement | 09/08/2009 | 09/08/2009 | 06/30/2010 | 2745808.23 | 5
9234 | South Carolina | CLARENDON |  | 6 | SPIM004 | Resurface and rehabilitate the south bound lane of I-95 in Clarendon County from approximately mile marker 99 to approximately mile marker 100. | Pavement Improvement | 08/10/2009 | 08/23/2009 | 07/31/2010 | 4542026.62 | 6
9235 | South Carolina | CHARLESTON | CHARLESTON | 1 | SPIM005 | Resurface and rehabilitate the east bound and west bound lane of I-26 in Charleston County from approximately mile marker 212 near I-526 to approximately mile marker 218 at Heriot Steet. | Pavement Improvement | 08/26/2009 | 09/30/2009 | 04/30/2011 | 14668347.24 | 18
9236 | South Carolina | GREENVILLE | GREENVILLE | 4 | SPIM007 | Resurface and rehabilitate I-85 in Greenville County from south of US-276 exit 48 to US-25 exit 44 | Pavement Improvement | 03/08/2010 | 03/22/2010 | 07/31/2011 | 5800000 | 5
9237 | South Carolina | JASPER |  | 2 | SPIM008 | Resurface and rehabilitate a portion of I-95 in Jasper County from approximately mile marker 18.3 to approximately mile marker 23.9 | Pavement Improvement | 09/18/2009 | 09/18/2009 | 06/30/2010 | 4882506.75 | 4.89
9238 | South Carolina | FLORENCE |  | 6 | SPIM010 | Resurface and rehabilitate the north bound lane of I-95 in Florence County from approximately mile marker 156 to approximately mile marker 161. | Pavement Improvement | 10/15/2009 | 10/15/2009 | 08/31/2010 | 1951212.7 | 5
9239 | South Carolina | SPARTANBURG |  | 4 | SPIM011 | Resurface and rehabilitate the east bound lane of I-26 in Spartanburg County from approximately mile marker 5 to approximately mile marker 11.1. | Pavement Improvement | 02/26/2010 | 03/29/2010 | 11/30/2010 | 6423499.26 | 5
9240 | South Carolina | GREENVILLE | GREENVILLE | 3 | SPIM012 | Resurface and rehabilitate Northbound I-185, from I-85 to Road S-260 near Greenville | Pavement Improvement | 02/08/2010 | 02/11/2010 | 10/31/2010 | 2394585.57 | 0
9241 | South Carolina | ANDERSON | ANDERSON | 3 | SPMC001 | Construction of a five lane roadway on new location in Anderson County known as the East - West Connector from US76-US178 (Clemson Boulevard) to SC Route 81 (Greenville Street). | New Construction | 10/20/2009 | 10/20/2009 | 10/31/2011 | 7363520.32 | 0
9242 | South Carolina | PICKENS | GREENVILLE | 3 | SPMC002 | Intersection improvement project at Calhoun Memorial Highway and Prince Perry in Easley, SC and includes replacing the bridge over the CSX railroad . | Pavement Improvement | 12/14/2009 | 12/21/2009 | 09/30/2010 | 5382417.52 | 0.85
9243 | South Carolina | UNION |  | 4 | SPMC003 | Intersection improvement of Wildcat Road in Union County. | Pavement Improvement | 05/11/2010 | 06/16/2010 | 10/31/2010 | 1020000 | 0.06
9244 | South Carolina | NEWBERRY |  | 5 | SPMC004 | Intersection improvement in Newberry County at SC Route 391 and Stoney Hill Road and Mt. Pillgram Road. | Pavement Improvement | 02/09/2010 | 03/10/2010 | 05/31/2010 | 160000 | 0.1
9245 | South Carolina | PICKENS |  | 3 | SPMC005 | Intersection improvement of SC 133 and Clemson Blvd. in the City of Clemson. Also includes the replacement of the railroad bridge at the interseciton. | Pavement Improvement | 07/12/2010 |  | 04/30/2012 | 6140000 | 0.4
9246 | South Carolina | BEAUFORT |  | 2 | SPMC006 | Widening from two lanes to five lanes Simmonsville Road in Bluffton, SC from US78 to Bluffton Parkway. Adding a lane eastbount and westbound to the existing 2 lanes along with a center turing lane | Pavement Widening | 06/28/2009 | 08/31/2009 | 12/15/2010 | 7000000 | 0.75
9247 | South Carolina | LAURENS |  | 3 | SPMC007 | Construction of road way "New Frontage Road" in Clinton SC from SC Highway 72 near exit 54 to SC Route 56 near exit 52. | New Construction | 02/26/2010 | 03/01/2010 | 05/31/2011 | 2159481.01 | 1.26
9248 | South Carolina | DORCHESTER |  | 6 | SPMC008 | Project to widen a section of US 178 to three lanes in the Town of Dorchester in Dorchester County, SC and to resurface a portion of US 178 in the Town of Dorchester. This project is a part of the Lo | Pavement Improvement | 10/29/2009 | 04/12/2010 | 06/30/2011 | 1000000 | 11.47
9249 | South Carolina | HORRY |  | 1 | SPMC009 | Intersection improvement project at US 17 Mineola Avenue in Horry County. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 06/30/2010 | 407673.91 | 0.28
9250 | South Carolina | GEORGETOWN |  | 1 | SPMC010 | Improvement of intersection of Fraiser Street and Front Street in Georgetown, SC. The project improvement includes signal upgrades, additonal pedestrian signals, and crosswalk and sidewalk improvement | Pavement Improvement | 01/04/2010 | 01/27/2010 | 06/30/2010 | 203431.49 | 0
9251 | South Carolina | SALUDA |  | 3 | SPMC011 | Intersection improvement at SC 39 (Chappells Highway) and SC 702 in Saluda County. Improvement includes realigning SC 702 to tie into SC 39 at a 90 degree angle. | Pavement Improvement | 09/23/2009 | 02/11/2010 | 07/31/2010 | 700989.68 | 0.28
9252 | South Carolina | GEORGETOWN | MYRTLE BEACH | 1 | SPMC012 | Intersection improvement of Sandy Island Road and US 17 in Georgetown County to improve safety. | Pavement Improvement | 03/15/2010 | 04/13/2010 | 08/31/2010 | 516155.17 | 0.15
9253 | South Carolina | GREENVILLE | GREENVILLE | 4 | SPMC013 | Widening of Fairforest Way from Mauldin Road to Laurens Road in Greenville County. This project includes reconstruction of the four lane facility to create a landscaped median, turn lanes at major in | Pavement Widening | 07/23/2010 |  | 08/31/2011 | 3118000 | 2.15
9254 | South Carolina | SUMTER | SUMTER | 5 | SPMC014 | Street sidewalk lighting and moving of overhead utilities underground on Alice Drive from Westmark Blvd to Camden Highway. | Other | 09/01/2009 | 09/01/2009 | 04/30/2011 | 1500000 | 1.2
9255 | South Carolina | SPARTANBURG | SPARTANBURG | 4 | SPMC015 | Widening of SC 9 in Boiling Springs SC from Fagans Creek Road to north of River Oak Phase I in Spartanburg County. The project consist of adding lanes in both directions as an undivided highway. | Pavement Widening | 07/15/2010 | 07/24/2010 | 08/31/2012 | 6000000 | 1.77
9256 | South Carolina | ANDERSON | GREENVILLE | 3 | SPMC016 | Resurfacing and 2 foot shoulder paving of Sc Route 153 from the Southern Connector end and widening SC Route 153 from 2 lanes to 3 lanes near I-85 | Pavement Widening | 04/14/2010 | 04/14/2010 | 08/31/2010 | 583189.69 | 0.435
9257 | South Carolina | YORK | ROCK HILL | 5 | SPMC018 | Widening of SC 5 Bypass from the interection of SC 5 Business and SC 161 on the east side of York , SC westward to SC 5 (Black Highway). This project is a part of the 1997 Pennies for Progress Progra | Pavement Widening | 12/27/2009 | 01/19/2010 | 08/31/2012 | 5750000 | 4.24
9258 | South Carolina | HORRY | MYRTLE BEACH | 1 | SPMC019 | New Construction from SC 544 to SC 707 to include clearing of new location and relocation of utilities. | Other | 01/04/2010 | 01/04/2010 | 06/27/2011 | 8838395.05 | 0
9259 | South Carolina | SPARTANBURG | SPARTANBURG | 4 | SPMC020 | Signalization projects at the intersection of US 29 and W.O. Ezell Blvd, US 221 and Church Street, and US 176 and Pine Street in Spartanburg County. | Safety/Traffic Management | 06/25/2010 |  | 03/31/2012 | 2924400.74 | 0
9260 | South Carolina | GEORGETOWN | MYRTLE BEACH | 1 | SPMC023 | Intersection improvement of US701 and Old Pee Dee Road in Georgetown for safety reasons. | Pavement Improvement | 03/15/2010 | 05/03/2010 | 07/31/2010 | 275387.35 | 0.14
9261 | South Carolina | HORRY | MYRTLE BEACH | 1 | SPMC024 | Widening of US 17 southbound from four lanes to six lanes from 2nd Avenue to Sea Mountain Highway | Pavement Widening | 04/20/2010 | 04/30/2010 | 11/30/2011 | 4098782.62 | 1.84
9262 | South Carolina | AIKEN | AUGUSTA (GA) | 3 | SPMC025 | Install smart signal system and imprve drainage along Whiskey Road in Aiken County from Corporate Parkway to Brookhaven Drive | Pavement Improvement | 06/30/2010 |  | 10/05/2010 | 966429.24 | 0
9263 | South Carolina | RICHLAND | COLUMBIA | 6 | SPMC026 | North Main Streetscape in the City of Columbia from Fuller Avenue to Fairfield Road. | Pavement Improvement | 04/28/2010 | 05/01/2010 | 04/30/2012 | 6000000 | 0.49
9264 | South Carolina | BERKELEY |  | 1 | SPMC027 | Widening of US 17 Alternate in Moncks Corner, SC by adding additional 2 lanes with center turning lane infrom Cypress Garden Road to near Moncks Corner. | Pavement Widening | 11/16/2009 | 11/16/2009 | 06/30/2012 | 1000000 | 7.3
9265 | South Carolina | LEXINGTON | COLUMBIA | 2 | SPMC028 | Widen from SC 6 to S-103 Platt Springs Road from 2 lanes to 5 lane curb and gutter. | Pavement Widening | 05/10/2010 | 05/13/2010 | 05/31/2013 | 13997320 | 4.92
9266 | South Carolina | GEORGETOWN |  | 1 | SPMC029 | Intersection improvement at US17 and Waverly Road. Adding a left turn lane on Waverly, Georgetown County SC | Pavement Improvement | 03/11/2010 | 03/03/2010 | 07/31/2010 | 230375.49 | 0.11
9267 | South Carolina | AIKEN | AUGUSTA (GA) | 3 | SPMC030 | Resurface US 1 from Richland Avenue to Valley Road in Aiken County | Pavement Improvement | 07/09/2010 |  | 08/31/2010 | 519000 | 0
9268 | South Carolina | GEORGETOWN | MYRTLE BEACH | 1,6 | SPMC031 | Improve drainage on street around High Market Street, Front Street, and US 17 in Georgetown SC. | Other | 06/14/2010 |  | 05/31/2012 | 3084133 | 0
9269 | South Carolina | BEAUFORT |  | 2 | SPMC032 | Resurfacing and rehabilitating three sections of the William Hilton Parkway from Shelter Cove to Sea Pines Circle on Hilton Head Island, Beaufort county. | Pavement Improvement | 04/23/2010 | 04/29/2010 | 03/31/2011 | 2211000 | 0
9270 | South Carolina | STATEWIDE |  | 5 | SPSA004 | Pavement marking project on Interstate 20 in Kershaw and Lee Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime | Safety/Traffic Management | 07/24/2009 | 07/14/2009 | 10/31/2009 | 641424 | 32.9
9271 | South Carolina | STATEWIDE |  | 3, 4 | SPSA005 | Pavement marking project on Interstate 26 in Laurens and Spartanburg Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve | Safety/Traffic Management | 08/03/2009 | 08/20/2009 | 10/31/2009 | 341188.9 | 17.4
9272 | South Carolina | STATEWIDE |  | 5 | SPSA006 | Pavement marking project on Interstate 77 in Chester and Fairfield Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve da | Safety/Traffic Management | 07/17/2009 | 08/19/2009 | 10/31/2009 | 236844.93 | 14.1
9273 | South Carolina | FLORENCE |  | 6 | SPSA007 | Pavement marking project on Interstate 95 in Florence County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night | Safety/Traffic Management | 06/26/2009 | 06/19/2009 | 10/31/2009 | 224003.65 | 12
9274 | South Carolina | AIKEN |  | 3 | SPSA008 | Pavement marking project on Interstate 20 in Aiken County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night ti | Safety/Traffic Management | 08/03/2009 | 08/22/2009 | 11/20/2009 | 297499.95 | 0
9275 | South Carolina | RICHLAND |  | 2 | SPSA009 | Pavement marking project on Interstate 20 in Richland County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night | Safety/Traffic Management | 09/01/2009 | 11/02/2009 | 11/20/2009 | 244560.15 | 7
9276 | South Carolina | STATEWIDE |  | 2, 5 | SPSA010 | Pavement marking project on Interstate 77 in Fairfield and Richland Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve d | Safety/Traffic Management | 07/16/2009 | 04/15/2010 | 11/20/2009 | 559817.7 | 23.4
9277 | South Carolina | COLLETON |  | 6 | SPSA011 | Pavement marking project on Interstate 95 in Colleton County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night | Safety/Traffic Management | 07/31/2009 | 10/23/2009 | 11/20/2009 | 170717.5 | 6.8
9278 | South Carolina | SPARTANBURG |  | 4 | SPSA012 | Pavement marking project on Interstate 26 in Spartanburg County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and ni | Safety/Traffic Management | 07/24/2009 | 10/06/2009 | 06/30/2010 | 332034.9 | 21.2
9279 | South Carolina | STATEWIDE |  | 5 | SPSA013 | Pavement marking project on Interstate 20 in Darlington and Lee Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve dayti | Safety/Traffic Management | 08/10/2009 | 08/04/2009 | 06/30/2010 | 385296.58 | 18.3
9280 | South Carolina | CHARLESTON |  | 1 | SPSA014 | Pavement marking project on Interstate 526 in Charleston County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and ni | Safety/Traffic Management | 07/30/2009 | 10/28/2009 | 06/30/2010 | 213296.54 | 7
9281 | South Carolina | STATEWIDE |  | 5, 6 | SPSA015 | Pavement marking project on Interstate 95 in Darlingtonand Florence Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve d | Safety/Traffic Management | 02/17/2010 | 06/13/2010 | 06/30/2010 | 166767.25 | 10
9282 | South Carolina | LEXINGTON |  | 2 | SPSA016 | Install fiber optic lines along various interstates and Fish Hatchery Road to connect to the Emergency Management Division office for the purpose of monitoring traffic camers in emergency situations. | Safety/Traffic Management | 07/01/2009 | 10/26/2009 | 02/26/2010 | 652005.96 | 0
9283 | South Carolina | LEXINGTON | COLUMBIA | 2 | SPSA017 | Realign and add turn lanes on Fish Hatchery Road in Lexington County. This project is to improve safety along Fish Hactchery Road | Safety/Traffic Management | 10/19/2009 | 01/27/2010 | 09/30/2010 | 691835.19 | 0.3
9284 | South Carolina | DARLINGTON |  | 5 | SPSA018 | Addition of turn lanes at the intersection of US 15 and S-10 in Darlington County. | Safety/Traffic Management | 07/24/2009 | 08/03/2009 | 11/30/2009 | 1364511.43 | 1.5
9285 | South Carolina | ANDERSON |  | 3 | SPSA019 | Improvement of interestion of Lane Avenue and S-283 (road) in Anderson County to realign, add turn lanes, and signals. | Pavement Improvement | 08/13/2009 | 08/13/2009 | 04/05/2010 | 411913.15 | 0.1
9286 | South Carolina | CHEROKEE |  | 5 | SPSA020 | Safety Improvement to flatten curve on SC105 in Cherokee County | Safety/Traffic Management | 09/21/2009 | 09/21/2009 | 08/31/2010 | 945740.33 | 0.65
9287 | South Carolina | RICHLAND |  | 2 | SPSA021 | Install gardrail at various locations along Wilson Road in Richland County. | Safety/Traffic Management | 08/10/2009 | 08/27/2009 | 01/07/2010 | 198366.78 | 0.199
9288 | South Carolina | STATEWIDE |  | 3, 4 | SPSA022 | Upgrade signal by installing LED signal heads at various interestions through out District 2 - Abbeville, Anderson, Edgefield, Greenwood, Laurens, McCormick, Newberry, and Saluda Counties. | Safety/Traffic Management | 08/19/2009 | 08/24/2009 | 08/31/2010 | 1555356.39 | 0
9289 | South Carolina | STATEWIDE |  |  | SPSA023 | Upgrade signal by installing LED signal heads at various interestions through out District 3 - Greenivlle, Oconee, Pickens, Spartanburg Counties. | Safety/Traffic Management | 08/04/2009 | 10/06/2009 | 06/30/2010 | 1024357 | 0
9290 | South Carolina | STATEWIDE |  | 5, 6 | SPSA024 | Upgrade signal by installing LED signal heads at various interestions through out District 5 - Darlington, Dillon, Florence, Georgetown, Horry, Marion, Marlboro, and Williamsburg Counties. | Safety/Traffic Management | 09/30/2009 | 10/26/2009 | 09/30/2010 | 424602.54 | 0
9291 | South Carolina | CHARLESTON, STATEWIDE |  | 1 | SPSA025 | Installation of fiber optic cable along I-526 from Clements Ferry Road to Johnny Dodds Boulevard. | Safety/Traffic Management | 08/05/2009 | 10/06/2009 | 04/30/2010 | 618961.12 | 9
9292 | South Carolina | UNION |  | 4 | SPSA026 | Intersection improvement at Jonesville Lockhart Highway and Bob Little Road in Union County. | Pavement Improvement | 05/11/2010 | 06/14/2010 | 08/31/2010 | 730351.45 | 0.4
9293 | South Carolina | ANDERSON |  | 3 | SPSA027 | Intersection improvement at Airline Road and Corning Avenue on the Abbeville Highway in Anderson County. The project involves reconstruction of the intersection for safety reasons. | Pavement Improvement | 05/27/2010 | 05/27/2010 | 11/30/2010 | 1090734.12 | 0.4
9294 | South Carolina | SPARTANBURG |  | 4 | SPSA029 | Intersection improvement at Lyman Road and New Cut Road in Spartanburg County. Improvement includes flattening out the curve and adding turn lanes. | Pavement Improvement | 05/10/2010 | 05/14/2010 | 11/30/2010 | 1141288.06 | 0.4
9295 | South Carolina | MARION |  | 6 | SPSA030 | Intersection improvement at US76 Wahee Road and SC 576. Improvement includes adding turn lanes and signals. | Pavement Improvement | 12/27/2009 | 01/18/2010 | 08/31/2010 | 881027.28 | 0.39
9296 | South Carolina | GEORGETOWN |  | 1 | SPSA031 | Two foot shoulder widening and improvement of various intersections on Penny Royal Road from US17 to US17A in Georgetown County. | Safety/Traffic Management | 03/18/2010 | 03/24/2010 | 12/15/2010 | 3784333.34 | 0
9297 | South Carolina | STATEWIDE |  | 1 | SPTC001 | To provide on-the-job training for women, minorities, and other disadvantages individuals for employment in the transportation industry. The training will be comprised of pre-emploment training, comm | Other | 12/29/2009 | 12/29/2009 | 12/31/2010 | 227546 | 0
9298 | South Dakota | MARSHALL, BROWN |  | 00 | 0010078 | This resurfacing project will extend the roadway life of SD Highway 10 from the east junction with SD Highway 37 to west of Britton. The project will also improve safety as the result of a smoother d | Pavement Improvement | 02/11/2010 |  | 10/15/2010 | 3580095.18 | 15.96
9299 | South Dakota | UNION |  | 00 | 0011047 | This resurfacing project will extend the roadway life for SD Highway 11 from 0.5 miles south of Alcester, north to the junction with SD Highway 46. Safety will also be improved as a result of a smoot | Pavement Improvement | 12/02/2009 | 06/01/2010 | 10/15/2010 | 1181557.77 | 5
9300 | South Dakota | DEUEL, HAMLIN |  | 00 | 0012154 | Ths project will mill and asphalt repave SD Highway 29 from the Hamlin/Deuel County Line to SD Highway 15. SD Highway 15 from SD 28 north the south city limits of Clear Lake, South Dakota. Safety wi | Pavement Improvement | 12/18/2009 | 05/21/2010 | 10/15/2010 | 3140064.83 | 20.03
9301 | South Dakota | HAND |  | 00 | 0014165 | This pavement grinding project will extend the life of US Highway 14 from Miller to east of Wessington. The project will also improve safety as the result of a smoother driving surface. | Pavement Improvement | 03/27/2009 | 06/01/2009 | 10/02/2009 | 1680152.75 | 18.7
9302 | South Dakota | PENNINGTON | RAPID CITY | 00 | 0016068 | This resurfacing project will extend the roadway life of US Highway 16 from Spring Creek Road to Cathedral Drive in Rapid City. | Pavement Improvement | 06/17/2009 | 09/14/2009 | 07/28/2010 | 4325570.46 | 5.7
9303 | South Dakota | SPINK |  | 00 | 0020092 | This resurfacing project will extend the roadway life for SD Highway 20 from SD Highway 45 to Brentford. | Pavement Improvement | 04/03/2009 | 05/11/2009 | 07/31/2010 | 6213585.95 | 34.8
9304 | South Dakota | PERKINS |  | 00 | 0020093 | This resurfacing project will extend the roadway life of SD Highway 20 from Prairie City to 2.6 miles west of Bison. | Pavement Improvement | 03/30/2009 | 10/03/2009 | 10/31/2009 | 4110659.94 | 14
9305 | South Dakota | CHARLES MIX |  | 00 | 0021094 | This project will mill and asphalt repave SD Highway 50 from the east junction with SD Highway 44 to US Highway 18 and SD Highway 1804 from south of the junction with SD Highway 50 to the junction wit | Pavement Improvement | 12/28/2009 | 06/03/2010 | 10/29/2010 | 4445171.34 | 23.7
9306 | South Dakota | DOUGLAS, CHARLES MIX, HUTCHINSON |  | 00 | 0021147 | This project will mill and asphalt repave US Highway 18 from the east junction with SD Highway 50 to the east junction with US Highway 281. It will also mill and asphalt repave US Highway 281 fromt t | Pavement Improvement | 12/16/2009 | 05/03/2010 | 10/29/2010 | 5908945.64 | 30.174
9307 | South Dakota | HAAKON |  | 00 | 0034132 | This resurfacing project will extend the roadway life of SD Highway 34 from east of the Cheyenne River to near the east junction with SD Highway 73. The project will also improve safety as a result o | Pavement Improvement | 03/30/2009 | 08/19/2009 | 10/16/2009 | 2612293.95 | 14.9
9308 | South Dakota | MOODY |  | 00 | 0034135 | This project will reconstruct SD Highway 34 from 1 mile west of SD Highway 13 to the Mineesota State Line. | Pavement Improvement | 12/17/2009 | 04/05/2010 | 05/27/2011 | 4753746 | 7.7
9309 | South Dakota | CUSTER |  | 00 | 0036010 | This resurfacing project will extend the roadway life for SD Highway 36 from the junction of US Highway 16A, easat 0.9 miles. | Pavement Improvement | 05/19/2009 | 04/26/2010 | 12/03/2010 | 178505.19 | 0.9
9310 | South Dakota | PENNINGTON, JACKSON |  | 00 | 0041144 | Mill & Asphalt Concrete Resurfacing | Pavement Improvement | 11/18/2009 | 06/24/2010 | 10/15/2010 | 2121331.59 | 12.525
9311 | South Dakota | FALL RIVER |  | 00 | 0043009 | This resurfacing project with ADA upgrades will extend the roadway life on US Highway 18B from the west junction with US 18 to the east junction of US Highway 18 in Hot Springs, US 18P from US 18 to S | Pavement Improvement | 01/20/2010 | 04/07/2010 | 12/03/2010 | 2036220.1 | 7.249
9312 | South Dakota | TURNER |  | 00 | 0044140 | This resurfacing project will extend the roadway life for SD Highway 44 from US Highway 81 to Marion Road. The safety of the route will also be improved by have a smoother driving surface. | Pavement Improvement | 12/17/2009 | 05/13/2010 | 10/15/2010 | 1706113.71 | 8
9313 | South Dakota | MELLETTE, TRIPP |  | 00 | 0044142 | This resurfacing project will extend the roadway life of SD Highway 44 from Wood to the US 183 Junction. | Pavement Improvement | 12/15/2009 | 05/04/2010 | 10/15/2010 | 4010027.74 | 24.994
9314 | South Dakota | YANKTON |  | 00 | 0046044 | This resurfacing project will extend the roadway life of SD Highway 46 from US Highway 281 to Irene. The project will also improve safety by providing a smoother driving surface. | Pavement Improvement | 12/18/2009 | 04/19/2010 | 10/15/2010 | 2707121.92 | 12.004
9315 | South Dakota | LYMAN |  | 00 | 0053004 | This resurfacing project will extend the roadway life of SD Highway 53 from the end of the pavement north of the White River to south of I-90 near Vivian. The project will also improve safety as the | Pavement Improvement | 03/27/2009 | 05/25/2009 | 10/30/2009 | 1278344.84 | 8
9316 | South Dakota | DEWEY |  | 00 | 0063037 | This resurfacing project will extend the roadway life of SD Highway 63 from north of the Moreau River to the west junciton with SD Highway 20. The project will also improve safety as a result of a sm | Pavement Improvement | 01/06/2010 | 05/18/2010 | 10/29/2010 | 2275867.47 | 13.198
9317 | South Dakota | ZIEBACH, DEWEY |  | 00 | 0063040 | This resurfacing project will extend the roadway life for SD Highway 63 from north of the Cheyenne River to the west Junction with US Highway 212. The project will also improve safety as reflected by | Pavement Improvement | 02/25/2010 | 05/03/2010 | 10/29/2010 | 5391709.41 | 22.38
9318 | South Dakota | HARDING |  | 00 | 0079066 | This resurfacing project will extend the roadway life of SD Highway 79 from the Slim Buttes area to west of the junction with SD Highway 20. The road will also improve safety as the result of a smoot | Pavement Improvement | 03/31/2009 | 04/15/2010 | 07/31/2010 | 3404848.86 | 14
9319 | South Dakota | LAKE, KINGSBURY |  | 00 | 0081035 | This project will resurface US Highway 81 from Madison north to the Kingsbury County Line, extending the life of the highway. Safety will also be improved by a smoother driving surface. | Pavement Improvement | 12/24/2009 |  | 10/15/2010 | 3236740.49 | 15.2
9320 | South Dakota | YANKTON |  | 00 | 0081063 | This project will convert the Meridian Bridge at Yankton from a highway bridge to a pedestrian bridge. | Transportation Enhancements | 12/23/2009 | 04/04/2010 | 04/30/2011 | 5236555.64 | 0
9321 | South Dakota | BUTTE |  | 00 | 0085051 | This project will reconstruct US Highway 85 in Belle Fourche from Hay Creek to the Belle Fourche River. | Pavement Widening | 10/22/2009 | 02/11/2010 | 12/03/2010 | 6203681.6 | 1.111
9322 | South Dakota | HARDING |  | 00 | 0085066 | Mill & AC Overlay, Pipe Repair & Guardrail | Pavement Improvement | 02/25/2010 | 04/20/2010 | 10/01/2010 | 4074426.93 | 20.3
9323 | South Dakota | ROBERTS |  | 00 | 0127006 | This resurfacing project will extend the roadway life of SD Highway 127 from I-29 west of the town of Victor, east and north to the North Dakota State Line. Safety will also be improved with the smoo | Pavement Improvement | 12/28/2009 |  | 10/15/2010 | 2939603.46 | 16.546
9324 | South Dakota | CUSTER |  | 00 | 016A002 | This resurfacing project will extend the roadway life of US Highway 16A from the west entrance of Custer State Park, easat to the junction with SD Highway 36. The project will also improve safety as | Pavement Improvement | 05/19/2009 | 04/26/2010 | 12/03/2010 | 2637284.48 | 13.7
9325 | South Dakota | CLARK |  | 00 | 0212113 | This pavement restoration project will extend the life of the section of US Highway 212 from the Spink/Clark County Line to East of Clark, and the section of US Highway 212 that goes through the town | Pavement Improvement | 03/27/2009 | 04/05/2010 | 09/03/2010 | 1613862.66 | 9
9326 | South Dakota | MCPHERSON |  | 00 | 0247005 | This resurfacing project will extend the roadway life of SD Highway 247 from Roscoe to north of SD Highway 10. The project will also improve safety as a result of a smoother driving surface. | Pavement Improvement | 10/08/2009 |  | 10/15/2010 | 2839699.59 | 22.535
9327 | South Dakota | UNION |  | 00 | 0291075 | This project will remove and replace the existing surface of the northbound lanes of I-29 from Elk Point to the SD Highway 50 exit. | Pavement Improvement | 10/26/2009 | 03/30/2010 | 11/24/2010 | 10604818.62 | 9.586
9328 | South Dakota | UNION |  | 00 | 0291101 | This project will remove and replace the concrete surface on the northbound lanes of I-29 from south of the Volin Exit to south of the Beresford exit. | Pavement Improvement | 04/02/2009 | 04/17/2009 | 08/20/2010 | 8495586.51 | 9.4
9329 | South Dakota | CODINGTON |  | 00 | 0297030 | This project will remove and replace the current concrete pavement on the southbound lanes of I-90 from SD Highway 20 north, 14.7 miles, to US Highway 212. The improvements will improve safety with a | Pavement Improvement | 03/27/2009 | 04/15/2009 | 10/30/2009 | 14595074.99 | 14.7
9330 | South Dakota | JACKSON |  | 00 | 0903078 | This resurfacing project will extend the pavement life of a section of both the east and west bound sections of I-90 from Murdo to the Jackson/Jones County Line. Safety will also be improved by shoul | Pavement Improvement | 04/01/2009 | 05/11/2009 | 07/16/2010 | 12963056.58 | 32.2
9331 | South Dakota | AURORA |  | 00 | 0907052 | This project will remove and replace the concrete surface on the westbound lanes of I-90 from White Lake to Mount Vernon. | Pavement Improvement | 03/30/2009 | 05/05/2009 | 10/29/2010 | 22752460.65 | 21.8
9332 | South Dakota | AURORA, DAVISON |  | 00 | 0907074 | This project will remove and replace the concrete surface on the eastbound lane of I-90 from 1 mile east of Plankinton to Mount Vernon. Safety will also be improved as a result of a smoother driving | Pavement Improvement | 12/16/2009 | 04/22/2010 | 10/29/2010 | 9585443.04 | 10.757
9333 | South Dakota | UNION |  | 00 | 0ENH185 | This project will design and construct a bike path throughout the City of Beresford. | Transportation Enhancements | 01/04/2010 |  | 10/29/2010 | 139336.46 | 0
9334 | South Dakota | LINCOLN |  | 00 | 0ENH187 | This project will restore a historic train depot into a museum. | Transportation Enhancements | 01/14/2010 | 03/24/2010 | 07/01/2010 | 119400 | 0
9335 | South Dakota | DEWEY |  | 00 | 0ENH189 | This project will design and construct a multi-use path along Main Street, Prairie Road, and Willow Street in Eagle Butte. | Transportation Enhancements | 01/11/2010 | 05/05/2010 | 10/29/2010 | 446012.14 | 0
9336 | South Dakota | GREGORY |  | 00 | 0ENH190 | This project will design and construct a bike path along 5th Street in Gregory. | Transportation Enhancements | 01/11/2010 | 02/08/2010 | 10/29/2010 | 489622.08 | 0
9337 | South Dakota | HUGHES |  | 00 | 0ENH191 | This project will design and contruct the Hilger's Gulch Bicycle and Pedestrian Trail along 4th Street in Pierre. | Transportation Enhancements | 01/06/2010 | 04/21/2010 | 09/24/2010 | 429560.47 | 0
9338 | South Dakota | SPINK |  | 00 | 0ENH193 | This project will design and contruct a bike path along 10th Avenue in Redfield. | Transportation Enhancements | 01/14/2010 |  | 10/29/2010 | 363865.63 | 0
9339 | South Dakota | MINNEHAHA | SIOUX FALLS | 00 | 0ENH194 | This project will rehabilitate a historic bridge along the Souix Falls Trail System. | Transportation Enhancements | 03/01/2010 | 03/08/2010 | 08/13/2010 | 608762.31 | 0
9340 | South Dakota | ROBERTS |  | 00 | 0ENH195 | This project will design and construct a bike path within the City of Sisseton | Transportation Enhancements | 01/05/2010 | 04/12/2010 | 10/29/2010 | 353944.71 | 0
9341 | South Dakota | CODINGTON |  | 00 | 0ENH196 | This project will design and construct a bike path along SD Highway 20 between Watertown and Lake Kampeska. | Transportation Enhancements | 12/18/2009 | 06/14/2010 | 08/01/2010 | 350704.73 | 0
9342 | South Dakota | BROWN |  | 00 | 0ENH198 | This project will restore the Railroad Depot in Aberdeen, SD. | Transportation Enhancements | 04/16/2010 | 06/28/2010 | 10/31/2010 | 383025.39 | 0
9343 | South Dakota | BEADLE |  | 00 | 0ENH199 | This project will provide for the preliminary engineering and construction of a pedestrian/bicycle trail in Wolsey, South Dakota | Transportation Enhancements | 01/05/2010 |  | 10/29/2010 | 229397.11 | 0
9344 | South Dakota | LAWRENCE |  | 00 | 0ENH201 | This project will design and construct a bike path at Black Hills State University in Spearfish | Transportation Enhancements | 01/05/2010 | 05/17/2010 | 08/31/2010 | 179033.78 | 0
9345 | South Dakota | LAKE |  | 00 | 0ENH202 | This project will rehabilitate a historic train depot in Madison. | Transportation Enhancements | 01/11/2010 | 04/05/2010 | 09/01/2010 | 141394.15 | 0
9346 | South Dakota | CHARLES MIX |  | 00 | 1804008 | This resurfacing project will extend the roadway life of SD Highway 1804 from SD Highway 44 south 8 miles. The project will also improve safety as the result of a smoother driving surface. | Pavement Improvement | 03/30/2009 | 04/25/2009 | 05/01/2010 | 1656681.66 | 8
9347 | South Dakota | BUTTE |  | 00 | 3034001 | This resurfacing project will extend the roadway life of SD Highway 34 from the Wyoming State Line to Belle Fourche. Safety will also be improved as the result of a smoother driving surface. | Pavement Improvement | 03/30/2009 | 06/22/2009 | 07/31/2010 | 1704882.03 | 9.8
9348 | South Dakota | CUSTER |  | 00 | 3040008 | This project will reconstruct SD Highway 40 in Hermosa, from SD Highway 79 to the trailer park east of the railroad tracks. Along with a new road surface, the project will include storm sewers, curb | Pavement Improvement | 07/21/2009 | 11/30/2009 | 08/14/2010 | 1675923.24 | 0.9
9349 | South Dakota | STANLEY |  | 00 | 3806027 | Drainage Improvement and Mill and Asphalt Concrete Resurfacing | Pavement Improvement | 02/09/2010 | 06/08/2010 | 10/15/2010 | 2190952.88 | 5.117
9350 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07,08,09 | 0001236 | This project located on SR-1 FROM ISABELLE STREET TO WHITE STATION ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ext | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1132123 | 2.7
9351 | Tennessee | WARREN |  | 04 | 0001237 | This project includes the necessary grading, drainage work, and bridge construction in preparation for a future paving project. | New Construction | 04/07/2009 | 04/07/2009 | 09/30/2011 | 8951029 | 5.2
9352 | Tennessee | VAN BUREN |  | 04 | 0001240 | This project located on SR-1 FROM WARREN COUNTY LINE TO WHITE COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 05/13/2009 | 05/13/2009 | 10/31/2009 | 321330 | 2.85
9353 | Tennessee | WARREN |  | 04 | 0001242 | This project located on SR-1 FROM VICTOR J. YOUNG ROAD TO VAN BUREN COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 05/13/2009 | 05/13/2009 | 10/31/2009 | 149908 | 1.15
9354 | Tennessee | WHITE |  | 04 | 0001243 | This project located on SR-1 FROM VAN BUREN COUNTY LINE TO COLE ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 05/13/2009 | 05/13/2009 | 10/31/2009 | 216950 | 1.89
9355 | Tennessee | HAYWOOD |  | 08 | 0001244 | This project located on SR-1 FROM TIPTON COUNTY LINE TO OVERFLOW BRIDGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ext | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/15/2009 | 883296 | 5.58
9356 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0001245 | This project is for the rehabilitation/upgrading of sidewalks on Harding Pike/West End Avenue from White Bridge Road to I-440 in Nashville | Transportation Enhancements | 11/06/2009 | 11/06/2009 | 01/31/2011 | 381766 | 1.68
9357 | Tennessee | LOUDON | KNOXVILLE | 02 | 0002092 | This project located on SR-2 FROM WEST OF SR-73 TO WEST OF SR-1 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 909796 | 5
9358 | Tennessee | RUTHERFORD | MURFREESBORO | 06 | 0002093 | This project located on SR-2 FROM NORTH OF RUTHERFORD BOULEVARD TO EPPS MILL ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will als | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 904837.41 | 6.8
9359 | Tennessee | BRADLEY | CLEVELAND | 03 | 0002094 | This project located on SR-2 FROM CLEVELAND CITY LIMITS TO SR-40 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 630246.93 | 2.6
9360 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0002095 | This project located on SR-2 FROM LILAC AVENUE TO NORFOLK SOUTHERN R/R OVERPASS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 746618.93 | 3
9361 | Tennessee | COFFEE |  | 04 | 0002096 | This project located on SR-2 FROM RUTHERFORD COL TO OLD HWY 41 (LT) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 840636 | 6.1
9362 | Tennessee | MCMINN |  | 02 | 0002097 | This project located on SR-2 FROM NORTH OF NIOTA TO MONROE COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 04/07/2009 | 04/07/2009 | 12/15/2009 | 365223.18 | 2.5
9363 | Tennessee | COFFEE |  | 04 | 0002098 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-2 with a new BRIDGE OVER DUCK RIVER IN MANCHESTER to serve the community for the next s | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2010 | 5572946 | 0.3
9364 | Tennessee | LAUDERDALE |  | 08 | 0003110 | This project located on SR-3 FROM TIPTON COUNTY LINE TO STATE HIGHWAY GARAGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also hel | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1456692 | 5
9365 | Tennessee | LAWRENCE |  | 04 | 0006070 | This project located on SR-6 FROM BUSBY ROAD TO LEOMA will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of th | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1851309.86 | 5
9366 | Tennessee | LAWRENCE |  | 04 | 0006072 | This project located on SR-6 FROM LAWRENCEBURG TO ALEXANDER SPRINGS ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ex | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 1876716.43 | 6.8
9367 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 0006075 | This project is for the construction of a median and addition of roadway lighting on SR-6 (West Main Street) from the Davidson County line to New Shackle Island Road in Hendersonville. | Pavement Improvement | 04/06/2009 | 04/06/2009 | 09/30/2015 | 1000000 | 4.26
9368 | Tennessee | GILES |  | 04 | 0007020 | This project located on SR-7 FROM POLLY ROAD TO SR-15 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of th | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 846252.27 | 4.6
9369 | Tennessee | MAURY |  | 04 | 0007021 | This project located on SR-7 FROM GILES COUNTY LINE TO SOUTH OF SR-50 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exten | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1329965.15 | 11.6
9370 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0008041 | This project is for improvements to the intersection of SR-8 (Ringgold Road) at Camp Jordan Parkway and including traffic signals | Safety/Traffic Management | 05/14/2009 | 05/14/2009 | 01/15/2010 | 134390 | 0
9371 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0008042 | This project is for the installation of traffic signals on SR-8 (Ridgeway Avenue) at the Intersection at Palisades Drive/Mississippi Avenue in Signal Mountain | Safety/Traffic Management | 02/16/2010 |  | 09/30/2015 | 81427 | 0
9372 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0008043 | This project is for the construction of bicycle lanes on SR-8/Ringgold Road in East Ridge | Transportation Enhancements | 02/10/2010 | 07/19/2010 | 09/30/2015 | 143284 | 0
9373 | Tennessee | COCKE |  | 01 | 0009059 | This project located on SR-9 FROM SR-35 TO WHITE OAK AVENUE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/15/2009 | 1797004.68 | 4.2
9374 | Tennessee | CAMPBELL |  | 04 | 0009060 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-9 with a new BRIDGE OVER CSX RAILROAD IN LAFOLLETTE to serve the community for the next | Bridge Replacement | 05/15/2009 | 05/15/2009 | 06/30/2011 | 5176486 | 0.36
9375 | Tennessee | TROUSDALE |  | 06 | 0010037 | This project located on SR-10 FROM SR-141 TO SOUTH OF SR-25 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 356299.75 | 2.86
9376 | Tennessee | MARSHALL |  | 06 | 0011051 | This project located on SR-11 FROM CHAPEL HILL CITY LIMITS TO WILLIAMSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 994550 | 6.1
9377 | Tennessee | RUTHERFORD |  | 06 | 0011052 | This project located on SR-11 FROM WILLIAMSON COUNTY LINE TO WILLIAMSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will a | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 323707.74 | 2.6
9378 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 0011053 | This project located on SR-11 FROM DAVIDSON COUNTY LINE TO SOUTH OF KASPER WAY will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 189938.94 | 0.6
9379 | Tennessee | WILLIAMSON |  | 04,07 | 0011054 | This project located on SR-11 FROM MARSHALL COUNTY LINE TO RUTHERFORD COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will als | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 103563.09 | 0.7
9380 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0012038 | This project located on SR-12 FROM I-65 TO SR-112 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the ro | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1101616.6 | 3
9381 | Tennessee | MONTGOMERY | CLARKSVILLE (KY) | 07 | 0012039 | This project located on SR-12 FROM SR-374 TO KENTUCKY STATE LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/14/2009 | 05/14/2009 | 12/15/2009 | 1545491 | 4.06
9382 | Tennessee | HUMPHREYS |  | 08 | 0013033 | This project located on SR-13 FROM NORTH OF TUMBLING CREEK ROAD TO SOUTH OF PUMPKIN CREEK will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and | Pavement Improvement | 05/13/2009 | 05/13/2009 | 11/15/2009 | 953545.52 | 6.91
9383 | Tennessee | TIPTON |  | 08 | 0014048 | This project will widen SR-14 from 2 lanes to 4 lanes FROM NORTH OF SR-206 TO 1.2 MILES EAST OF SR-384 | Pavement Widening | 04/06/2009 | 04/06/2009 | 12/15/2011 | 15487112 | 3.9
9384 | Tennessee | MCNAIRY |  | 07 | 0015141 | This project will widen SR-15 from 2 lanes to 4 lanes FROM NEAR SR-225 TO SANDY FLAT ROAD | Pavement Widening | 04/06/2009 | 04/06/2009 | 11/15/2011 | 24392926 | 3.4
9385 | Tennessee | FRANKLIN |  | 04 | 0015157 | This project located on SR-15 FROM NORTH OF SR-56 TO GRUNDY COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ext | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 572340.61 | 3.5
9386 | Tennessee | MCNAIRY |  | 07 | 0015158 | This project located on SR-15 FROM SR-5 (US-45 LEFT) TO SR-5 (US-45 RIGHT) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/10/2009 | 1066974 | 2.5
9387 | Tennessee | MADISON |  | 08 | 0018025 | This project located on SR-18 FROM MERIDIAN CREEK TO BRIDGE OVER ABANDONED R/R will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 887797.68 | 4.9
9388 | Tennessee | MADISON |  | 08 | 0020045 | This project located on SR-20 FROM POPLAR CORNER ROAD TO BRIDGE OVER OLD SR-20 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1443123.03 | 4.4
9389 | Tennessee | CARROLL |  | 08 | 0022057 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-22 with a new BRIDGES OVER OVERFLOW BEAVER CREEK, & OVERFLOW IN HUNTINGDON to serve the | Bridge Replacement | 04/06/2009 | 04/06/2009 | 09/30/2010 | 3329318 | 0
9390 | Tennessee | WILSON |  | 05,06 | 0026029 | This project located on SR-26 FROM NEAR MADDOX-SIMPSON PARKWAY TO EAST OF TAYLOR ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 695892.63 | 7.7
9391 | Tennessee | WHITE |  | 04 | 0026030 | This project located on SR-26 FROM EAST OF SR-136 TO WEST OF SR-111 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 645472.61 | 4.5
9392 | Tennessee | WILSON | NASHVILLE-DAVIDSON | 05 | 0026034 | This project on SR-26 will include the purchase of property for the future construction of an intersection at Maddox-Simpson Parkway in Lebanon. | Other | 09/08/2009 | 09/08/2009 | 09/30/2015 | 1000000 | 0
9393 | Tennessee | CUMBERLAND |  | 04 | 0028039 | This project located on SR-28 FROM NORTH OF WINNINGHAM ROAD TO SR-68 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 551565.06 | 5
9394 | Tennessee | SCOTT |  | 04 | 0029069 | This project located on SR-29 FROM WOLF RIVER ROAD TO SOUTH OF GLASSHOUSE ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 443943.46 | 6.9
9395 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0029070 | This project located on SR-29 FROM OVERHEAD OVER DAYTON PIKE TO OLD DAYTON PIKE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1966738 | 5.4
9396 | Tennessee | RHEA |  | 03 | 0029071 | This project located on SR-29 FROM SOUTH OF VANN'S CREEK ROAD/HOYAL ROAD TO SOUTH OF MACEDONIA ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automob | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/31/2009 | 553449 | 4.74
9397 | Tennessee | BLEDSOE |  | 04 | 0030047 | This project located on SR-30 FROM WEST OF CRANWELL ROAD RT TO SR-28 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/30/2009 | 765167 | 4.8
9398 | Tennessee | UNION |  | 03 | 0033075 | This project located on SR-33 FROM KNOX COUNTY LINE TO EAST OF MAIN STREET RIGHT will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/15/2009 | 672684 | 7.57
9399 | Tennessee | POLK |  | 03 | 0033076 | This project will widen SR-33 from 2 lanes to 4 lanes FROM BENTON NORTH CITY LIMITS TO SR-30 EAST | Pavement Widening | 04/07/2009 | 04/07/2009 | 12/31/2011 | 26667858 | 5.3
9400 | Tennessee | CLAIBORNE |  | 03 | 0033077 | This project located on SR-33 FROM SOUTH OF MOLLY HOLLOW ROAD TO SOUTH OF OLD SR-33 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will a | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/15/2009 | 564508 | 2.22
9401 | Tennessee | HAMBLEN | MORRISTOWN | 01 | 0034069 | This project is for traffic signal upgrades on SR-34 at the intersection of SR-34 and SR-160 in Morristown | Safety/Traffic Management | 07/17/2009 | 07/17/2009 | 09/30/2015 | 221362 | 0
9402 | Tennessee | KNOX | KNOXVILLE | 02 | 0034070 | This project located on SR-34 from SR-9 (US-25W) to the Jefferson County line will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also he | Pavement Improvement | 03/15/2010 | 03/15/2010 | 09/15/2010 | 663553 | 3.37
9403 | Tennessee | CARTER | JOHNSON CITY | 01 | 0037014 | This project located on SR-37 FROM NORTH OF CROOK STREET TO BRIDGE OVER WATAUGA RIVER will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 2625811 | 5.3
9404 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 0041019 | This project located on SR-41 FROM DICKERSON PIKE TO SR-257 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/31/2009 | 823041.34 | 5.3
9405 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 0044006 | This project located on SR-44 FROM SR-34 TO VIRGINIA STATE LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/01/2009 | 04/01/2009 | 10/31/2009 | 416929 | 2.5
9406 | Tennessee | DICKSON |  | 08 | 0046012 | This project located on SR-46 FROM ROBIN HOOD ROAD TO SR-1 BYPASS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend th | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1625263.4 | 4.4
9407 | Tennessee | WILLIAMSON |  | 04 | 0046013 | This project located on SR-46 FROM PEWITT ROAD TO NEAR SR-100 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 419327.73 | 5.21
9408 | Tennessee | HOUSTON |  | 08 | 0049020 | This project located on SR-49 FROM SR-147 TO SR-13 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 05/12/2009 | 05/12/2009 | 11/15/2009 | 743934 | 4.94
9409 | Tennessee | MORGAN |  | 04 | 0052055 | This project located on SR-52 FROM END OF BRIDGE OVER CLEAR FORK RIVER TO SCOTT COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, an | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 725453.2 | 3.9
9410 | Tennessee | SCOTT |  | 04 | 0052056 | This project located on SR-52 FROM MORGAN COUNTY LINE TO SR-29 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 758926.27 | 5.1
9411 | Tennessee | CLAY |  | 06 | 0052057 | This project located on SR-52 FROM EAST END OF CUMBERLAND RIVER BRIDGE TO SR-53 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 318728 | 1.1
9412 | Tennessee | FENTRESS |  | 04 | 0052058 | This project located on SR-52 FROM EAST OF BRIDGE OVER SR-28 TO SR-296 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/15/2009 | 806441.39 | 4
9413 | Tennessee | MACON |  | 06 | 0052059 | This project located on SR-52 FROM LAFAYETTE CITY LIMITS TO NEAR BUTLER ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also hel | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 1018931.84 | 5.35
9414 | Tennessee | MACON |  | 06 | 0056057 | This project located on SR-56 FROM JACKSON COUNTY LINE TO SR-262 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 11/15/2009 | 91780.49 | 2.7
9415 | Tennessee | GRUNDY |  | 04 | 0056058 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-56 with a new BRIDGE OVER FIRESCALD CREEK IN ALTAMONT to serve the community for the ne | Bridge Replacement | 05/12/2009 | 05/12/2009 | 08/10/2010 | 1691111 | 0
9416 | Tennessee | FAYETTE |  | 07 | 0057045 | This project located on SR-57 FROM COWAN LOOP ROAD TO SR-18 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 352747.44 | 5.04
9417 | Tennessee | HAMILTON |  | 03 | 0058032 | This project located on SR-58 FROM NORTH OF RUNYAN ROAD TO SOUTH OF SR-60 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 481373 | 4.73
9418 | Tennessee | TIPTON |  | 08 | 0059023 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-59 with a new BRIDGE OVER LITTLE BEAVER CREEK INCLUDING A DRAINAGE DITCH to serve the c | Bridge Replacement | 04/06/2009 | 04/06/2009 | 01/15/2010 | 1431494 | 0
9419 | Tennessee | MEIGS |  | 03 | 0060017 | This project located on SR-60 FROM NEAR MCINTRUFF ROAD IN MEIGS COUNTY TO NEAR FIVE POINTS ROAD IN RHEA COUNTY will provide a smoother riding surface for motorists, thus decreasing wear and tear on th | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 641331.92 | 1.46
9420 | Tennessee | ANDERSON |  | 03 | 0061022 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-61 with a new BRIDGE OVER POPLAR CREEK to serve the community for the next several deca | Bridge Replacement | 05/12/2009 | 05/12/2009 | 06/30/2010 | 1736988 | 0
9421 | Tennessee | SEVIER |  | 01 | 0066039 | This project will widen SR-66 from 4 lanes to 6 lanes FROM NORTH OF NICHOLS STREET IN SEVIERVILLE TO SR-338 (BOYDS CREEK HIGHWAY) | Pavement Widening | 05/15/2009 | 05/15/2009 | 12/31/2011 | 40690695 | 4.22
9422 | Tennessee | HAMBLEN | MORRISTOWN | 01 | 0066042 | This resurfacing project located on SR-66 WEST 1ST NORTH STREET, FROM MARS AVENUE TO NORTH CUMBERLAND STREET IN MORRISTOWN will provide a smoother riding surface for motorists, thus decreasing wear an | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 356575 | 0.98
9423 | Tennessee | BENTON |  | 08 | 0069068 | This project located on SR-69 FROM SOUTH OF SR-1 TO SOUTH OF SR-391 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 513194 | 1.5
9424 | Tennessee | HENRY |  | 08 | 0069069 | This project located on SR-69A FROM SCARBOROUGH RD TO SR-69 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1033658.43 | 6.4
9425 | Tennessee | HARDIN |  | 07 | 0069070 | This project located on SR-69 FROM HOLLAND CREEK ROAD TO SR-226 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 1363878 | 7.37
9426 | Tennessee | GREENE |  | 01 | 0070015 | This project located on SR-70 FROM RAMP TO I-81 TO HAWKINS COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/15/2009 | 881696 | 5.4
9427 | Tennessee | BRADLEY | CLEVELAND | 03 | 0074006 | This project located on SR-74 from SR-74 Southbound (Broad Street) to SR-2 (US-11) in Cleveland will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles | Pavement Improvement | 04/30/2010 | 05/15/2010 | 09/15/2010 | 151849 | 2.78
9428 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 0075009 | This project located on SR-75 FROM SOUTH OF SHADDEN ROAD TO NORTH OF I-26 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 04/01/2009 | 04/01/2009 | 12/15/2009 | 542054 | 1.5
9429 | Tennessee | GIBSON |  | 08 | 0076051 | This project will widen SR-76 from 2 lanes to 4 or 5 lanes FROM SR-43 IN MILAN TO NEAR THE CARROLL COUNTY LINE | Pavement Widening | 06/17/2009 | 06/17/2009 | 12/15/2011 | 20600000 | 4.4
9430 | Tennessee | HAYWOOD |  | 08 | 0076058 | This project located on SR-76 FROM FAYETTE COUNTY LINE TO SR-179 RT will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 1242698.91 | 5.6
9431 | Tennessee | STEWART |  | 08 | 0076059 | This project will widen SR-76 from 2 lanes to 4 lanes FROM SR-120 TO EAST OF MONTGOMERY COUNTY LINE | Pavement Widening | 05/15/2009 | 05/15/2009 | 11/01/2011 | 21460607 | 5.8
9432 | Tennessee | LAKE |  | 08 | 0078015 | This project located on SR-78 FROM SR-21 TO VAN WORKS ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 440794.26 | 4.95
9433 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 0081017 | This project located on SR-81 FROM SOUTH OF RIDGECREST ROAD TO NORTH OF ANDERSON ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/01/2009 | 04/01/2009 | 12/15/2009 | 626585 | 2.5
9434 | Tennessee | OBION |  | 08 | 0089016 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-89 with a new BRIDGE OVER GRASSY CREEK to serve the community for the next several deca | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 1111679 | 0
9435 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 0091033 | This project located on SR-91 FROM LEGION STREET TO SR-34(WB) AND FROM SR-34 TO LEGION STREET (EB) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobi | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 827195 | 1.36
9436 | Tennessee | ANDERSON |  | 03 | 0095007 | This project located on SR-95 FROM MELTON LAKE ROAD TO SR-61 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the lif | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 469175 | 1.17
9437 | Tennessee | CANNON |  | 06 | 0096024 | This project located on SR-96 FROM RUTHERFORD COUNTY LINE TO WILSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 775069.8 | 5
9438 | Tennessee | DECATUR |  | 07 | 0100045 | This project located on SR-100 FROM SR-69 TO BRIDGE AT RUSHING CREEK will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 561165 | 2.4
9439 | Tennessee | HARDEMAN |  | 07 | 0100046 | This project located on SR-100 FROM OLD SR-18 TO CHESTER COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 631960 | 3.9
9440 | Tennessee | ANDERSON |  | 03 | 0100047 | This project will improve safety and reliability of the transportation system by replacing an older bridge on BINKLEY ACRES ROAD with a new BRIDGE OVER BRUSHY FORK CREEK to serve the community for th | Bridge Replacement | 04/07/2009 | 04/07/2009 | 06/15/2010 | 468838 | 0
9441 | Tennessee | ANDERSON |  | 03 | 0100048 | This project will improve safety and reliability of the transportation system by replacing an older bridge on YARNELL ROAD with a new BRIDGE OVER LITTLE DISMAL CREEK NEAR CLINTON to serve the communi | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/30/2010 | 209099 | 0.1
9442 | Tennessee | ANDERSON |  | 03 | 0100049 | This project will improve safety and reliability of the transportation system by replacing an older bridge on HALF MOON ROAD with a new BRIDGE OVER STONEY FLAT CREE to serve the community for the next | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/31/2010 | 212832 | 0.1
9443 | Tennessee | CUMBERLAND |  | 04 | 0101015 | This project will widen SR-101 from 2 lanes to 5 lanes including bike lanes and sidwalks FROM SR-282 TO SR-392 | Pavement Widening | 06/30/2009 | 06/30/2009 | 11/01/2011 | 18025020 | 2.8
9444 | Tennessee | RUTHERFORD |  | 06 | 0102011 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-102 with a new BRIDGES OVER BRANCH AND ROCKY FORK CREEK to serve the community for the | Bridge Replacement | 04/06/2009 | 04/06/2009 | 08/10/2010 | 1476763 | 0
9445 | Tennessee | RUTHERFORD | MURFREESBORO | 06 | 0102013 | This project located on SR-102 FROM I-24 to SR-266 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 02/01/2010 | 02/01/2010 | 08/31/2010 | 363000 | 5.4
9446 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0106025 | This project located on SR-106 FROM HARDING PLACE TO I-440 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/15/2009 | 05/15/2009 | 10/31/2009 | 1845224.73 | 2.68
9447 | Tennessee | WASHINGTON |  | 01 | 0107014 | This project located on SR-107 FROM GREENE COUNTY LINE TO SR-81 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 2291975.55 | 11.34
9448 | Tennessee | SUMNER |  | 06 | 0109024 | This paving project will complete SR-109 from the Gallatin bypass to south of Hollis Chapel Road | New Construction | 05/15/2009 | 05/15/2009 | 11/30/2010 | 11372855 | 5.2
9449 | Tennessee | ANDERSON |  | 03 | 0116010 | This project located on SR-116 FROM NORTH OF BRADEN FLATS LANE TO SR-330 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ex | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 468134.73 | 3.4
9450 | Tennessee | WARREN |  | 04 | 0127012 | This project located on SR-127 FROM OLD SHELLSFORD ROAD TO SR-30 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 494087.42 | 3
9451 | Tennessee | COFFEE |  | 04 | 0127013 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-127 with a new BRIDGE OVER I-24 to serve the community for the next several decades. | Bridge Replacement | 04/06/2009 | 04/06/2009 | 09/30/2010 | 3890007 | 0
9452 | Tennessee | KNOX | KNOXVILLE | 02 | 0131020 | This project located on SR-131 FROM SR-33 TO SR-331 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the | Pavement Improvement | 04/07/2009 | 04/07/2009 | 11/15/2009 | 825168 | 4.9
9453 | Tennessee | KNOX | KNOXVILLE | 02 | 0131022 | This project located on SR-131 FROM SR-9 TO WEST OF GILL ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 459525 | 2.25
9454 | Tennessee | KNOX | KNOXVILLE | 02 | 0131025 | This project will widen SR-131 / LOVELL ROAD from 2 lanes to 5 lanes FROM WEST OF PELLISSIPPI PARKWAY TO SCHAEFFER ROAD | Pavement Widening | 11/13/2009 | 02/28/2010 | 06/30/2011 | 2739022 | 0.11
9455 | Tennessee | PUTNAM |  | 06 | 0135012 | This project located on SR-135 FROM NORTH OF DIXIE AVENUE TO JACKSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 861128.88 | 4.9
9456 | Tennessee | CARTER |  | 01 | 0143006 | This project located on SR-143 FROM NORTH CAROLINA STATE LINE TO SR-37 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 2235383 | 12.6
9457 | Tennessee | CANNON |  | 06 | 0146004 | This project located on SR-146 FROM SR-1 TO DEKALB COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 398036.62 | 9.7
9458 | Tennessee | DE KALB |  | 06 | 0146005 | This project located on SR-146 FROM CANNON COUNTY LINE TO NORTH OF BRIDGE OVER PINE CREEK will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 233612.75 | 5.5
9459 | Tennessee | BENTON |  | 08 | 0147002 | This project located on SR-147 FROM SR-69A TO PINE GROVE ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 04/06/2009 | 04/06/2009 | 11/30/2009 | 808586 | 5.4
9460 | Tennessee | MARION |  | 04 | 0156006 | This project located on SR-156 FROM MARION-FRANKLIN FOREST TO ORME MOUNTAIN ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 401587.84 | 6.4
9461 | Tennessee | JOHNSON |  | 01 | 0167004 | This project located on SR-167 FROM LITTLE DRY RUN ROAD TO SR-34 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 1496706 | 7.59
9462 | Tennessee | WILSON | NASHVILLE-DAVIDSON | 05 | 0171024 | This project will widen SR-171 (MOUNT JULIET ROAD) from 3 lanes to 5 lanes FROM DIVISION STREET TO SR-24 (US-70, LEBANON ROAD) | Pavement Widening | 06/17/2009 | 06/17/2009 | 11/15/2011 | 10297296 | 2.2
9463 | Tennessee | CARTER |  | 01 | 0173007 | This project located on SR-173 FROM UNICOI COUNTY LINE TO SR-37 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 353518 | 4.28
9464 | Tennessee | WEAKLEY |  | 08 | 0190009 | This project located on SR-190 FROM CARROLL COUNTY LINE TO SR-124 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend th | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 584620.41 | 4.55
9465 | Tennessee | FAYETTE |  | 07 | 0194011 | This project located on SR-194 FROM SR-15 TO SR-59 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 588120.99 | 8.43
9466 | Tennessee | DECATUR |  | 07 | 0202015 | This project located on SR-202 FROM SR-114 TO SR-69 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 707782.58 | 5.2
9467 | Tennessee | HENRY |  | 08 | 0218006 | Construction of a new bypass on the northwest side of Paris from SR-54 west of Paris to SR-69 northwest of Paris | New Construction | 04/06/2009 | 04/06/2009 | 11/30/2010 | 8673704 | 3.08
9468 | Tennessee | MADISON | JACKSON | 08 | 0223009 | This project located on SR-223 FROM SOUTH OF LOWER BROWNSVILLE RD TO BRIDGE OVER I-40 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 383371.48 | 0.6
9469 | Tennessee | CHESTER |  | 07 | 0225003 | This project located on SR-225 FROM OLD FRIENDSHIP ROAD TO MONTEZUMA ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 612968 | 5.3
9470 | Tennessee | MONTGOMERY |  | 07 | 0238003 | This project located on SR-238 FROM SR-76 TO KENTUCKY STATE LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/14/2009 | 05/14/2009 | 12/15/2009 | 569017.07 | 8.25
9471 | Tennessee | MARION |  | 04 | 0242127 | This project located on I-24 FROM SR-27/150 TO TENNESSEE RIVER BRIDGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exten | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 2416979 | 8.23
9472 | Tennessee | COFFEE |  | 04 | 0242129 | This project located on I-24 FROM RAMP FROM SR-55 (McMINNVILLE HWY) TO RAMP FROM AEDC will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 5222948 | 6.1
9473 | Tennessee | COFFEE |  | 04 | 0242130 | This project located on I-24 FROM NOAH FORK CREEK TO RAMP FROM SR-2 EB will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 3404807.34 | 5.32
9474 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0243083 | This project is for the construction of a new Welcome Center near Tiftonia on I-24 | Transportation Enhancements | 12/15/2009 | 12/15/2009 | 11/30/2010 | 2114760 | 0
9475 | Tennessee | CHEATHAM |  | 05,07 | 0251012 | This project located on SR-251 FROM SR-249 TO DAVIDSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend t | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 543073.15 | 4
9476 | Tennessee | ROBERTSON |  | 06 | 0257004 | This project located on SR-257 FROM SR-49 TO NEAR NEW CUT ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 680158.79 | 5.8
9477 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 0258007 | This project is for the development of design plans for the future widening of New Shackle Island Road from Iris Drive north to SR-386 in Hendersonville | Other | 08/12/2009 | 08/12/2009 | 09/30/2015 | 375000 | 0.86
9478 | Tennessee | MACON |  | 06 | 0262009 | This project located on SR-262 FROM SR-56 TO JACKSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/15/2009 | 05/15/2009 | 11/15/2009 | 93569.27 | 2.81
9479 | Tennessee | LINCOLN |  | 04 | 0275006 | This project located on SR-275 FROM NEAR 4-WAY STOP TO SR-15 EAST will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend th | Pavement Improvement | 05/15/2009 | 05/15/2009 | 11/15/2009 | 263249.27 | 7
9480 | Tennessee | SEQUATCHIE |  | 04 | 0283010 | This project located on SR-283 FROM MARION COUNTY LINE TO SR-8 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 548051.67 | 5.5
9481 | Tennessee | OVERTON |  | 06 | 0294002 | This project located on SR-294 FROM SR-111 TO OAKLEY-ALLONS ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 508318 | 6.2
9482 | Tennessee | CAMPBELL |  | 04 | 0297002 | This project located on SR-297 FROM WEST OF LICK FORK LANE LEFT TO EAST OF LITTLE ELK CREEK ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobile | Pavement Improvement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 921605.3 | 6.1
9483 | Tennessee | BENTON |  | 08 | 0300028 | This streetscape beautification project in Camden includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 07/30/2009 | 07/30/2009 | 08/31/2010 | 556476 | 0
9484 | Tennessee | BRADLEY |  | 03 | 0308006 | This project located on SR-308 FROM I-75 TO SR-2 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the roa | Pavement Improvement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 884548 | 3.3
9485 | Tennessee | POLK |  | 03 | 0314004 | This project located on SR-314 FROM SR-40 TO SR-33 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 1096860.25 | 6.08
9486 | Tennessee | FENTRESS |  | 04 | 0325007 | This project located on SR-325 FROM FENTRESS-PICKETT COUNTY LINE TO SR-28 IN PICKETT COUNTY will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, an | Pavement Improvement | 05/12/2009 | 05/12/2009 | 11/15/2009 | 241483.77 | 2.53
9487 | Tennessee | PICKETT |  | 04 | 0325008 | This project located on SR-325 FROM WEST OF HILL ROAD TO FENTRESS COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also he | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 380694.76 | 4.53
9488 | Tennessee | HAMBLEN | MORRISTOWN | 01 | 0343007 | This project located on SR-343 FROM SR-32 TO SR-34 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 06/18/2009 | 06/18/2009 | 12/01/2009 | 669203.29 | 3.89
9489 | Tennessee | HAWKINS |  | 01 | 0344006 | This project located on SR-344 FROM SR-113 TO HOLSTON RIVER BRIDGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend t | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 462078 | 3.8
9490 | Tennessee | HENRY |  | 08 | 0356001 | This project located on SR-356 FROM SR-69/54 TO SR-76 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of th | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 414186.21 | 1
9491 | Tennessee | CARTER |  | 01 | 0361003 | This project located on SR-361 FROM SR-359 TO SR-37 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 1620171 | 8.9
9492 | Tennessee | MARSHALL |  | 06 | 0373007 | This project will widen SR-373 from 2 lanes to 5 lanes FROM I-65 TO EAST OF SR-417 IN LEWISBURG | Pavement Widening | 04/07/2009 | 04/07/2009 | 12/15/2011 | 19252288 | 4
9493 | Tennessee | MONTGOMERY | CLARKSVILLE (KY) | 07 | 0374016 | This project is for the lighting of the interchange at SR-374 and SR-13 in Clarksville | Safety/Traffic Management | 02/18/2010 |  | 09/30/2015 | 342292 | 0
9494 | Tennessee | BENTON |  | 08 | 0391015 | This project located on SR-391 FROM SR-1 TO SR-1 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the roa | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 1350280.04 | 5.3
9495 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 0400023 | This project located on SR-400 FROM NORTH BROADWAY STREET TO WEST MAIN STREET (SB) AND FROM WEST MAIN STREET TO NORTH BROADWAY STREET (NB) will provide a smoother riding surface for motorists, thus de | Pavement Improvement | 05/13/2009 | 05/13/2009 | 12/15/2009 | 1062141 | 1.63
9496 | Tennessee | MADISON | JACKSON | 08 | 0401317 | This project located on I-40 FROM WEST OF EXIT 74 TO EAST OF EXIT 83 (Excludes LM 13.59 to LM 15.57) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automo | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 2951286.29 | 9.5
9497 | Tennessee | HENDERSON |  | 07 | 0402087 | This project located on I-40 FROM MADISON COUNTY LINE TO SR-104 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 2248548 | 6.1
9498 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403140 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-155 with a new BRIDGE OVER I-40 AT ROBERTSON ROAD to serve the community for the next s | Bridge Replacement | 04/09/2009 | 04/09/2009 | 09/15/2011 | 3570807 | 0
9499 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403141 | This project located on I-40 FROM CHARLOTTE PIKE TO OVERHEAD BRIDGE AT WESTBORO DRIVE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 04/07/2009 | 04/07/2009 | 09/30/2009 | 1402438.6 | 2.2
9500 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403142 | This project will complete the second phase of the interchange improvements at Briley Parkway/Robertson Road on Interstate 40 | Safety/Traffic Management | 04/09/2009 | 04/09/2009 | 09/15/2011 | 28200000 | 0.4
9501 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403143 | This project located on I-40 FROM SR-1 TO CHARLOTTE PIKE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 1808289.41 | 4.64
9502 | Tennessee | SMITH |  | 06 | 0405135 | This project located on I-40 FROM SR-53 TO PUTNAM COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 2074075.66 | 8.6
9503 | Tennessee | PUTNAM |  | 06 | 0406143 | This project located on I-40 FROM SMITH COUNTY LINE TO EAST OF SR-56 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 1832527.46 | 6.6
9504 | Tennessee | WEAKLEY |  | 08 | 0431011 | This project located on SR-431 FROM CENTRAL STREET TO SR-22 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 1416450.93 | 2.19
9505 | Tennessee | BEDFORD |  | 06 | 0437002 | Construction of a new bypass on the northeast side of Shelbyville from SR-10 north of Shelbyville to SR-16 east of Shelbyville | New Construction | 04/07/2009 | 04/07/2009 | 08/31/2011 | 15740454 | 6.3
9506 | Tennessee | BLEDSOE |  | 04 | 0443002 | This project located on SR-443 FROM 90 DEGREE TURN TO RHEA COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 05/12/2009 | 05/12/2009 | 11/30/2009 | 79377 | 1.38
9507 | Tennessee | RHEA |  | 03 | 0443003 | This project located on SR-443 FROM BLEDSOE COUNTY LINE TO SR-30 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 05/12/2009 | 05/12/2009 | 12/15/2009 | 431702 | 6.87
9508 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 0473002 | This project is for the optimization of traffic signal timing on SR-473/Martin Luther King Jr. Boulevard in Bristol | Safety/Traffic Management | 12/28/2009 | 12/28/2009 | 08/10/2010 | 86608 | 0
9509 | Tennessee | BLOUNT |  | 02 | 0500039 | This project will improve safety and reliability of the transportation system by replacing an older bridge on THOMPSON BRIDGE ROAD with a new BRIDGE OVER NINE MILE CREEK to serve the community for th | Bridge Replacement | 04/07/2009 | 04/07/2009 | 11/30/2010 | 1386644 | 0.001
9510 | Tennessee | BLOUNT |  | 02 | 0500040 | This project will improve safety and reliability of the transportation system by replacing an older bridge on REGAN MILL ROAD with a new BRIDGE OVER NINE MILE CREEK to serve the community for the ne | Bridge Replacement | 04/07/2009 | 04/07/2009 | 08/31/2011 | 357833 | 0.2
9511 | Tennessee | BLOUNT | KNOXVILLE | 02 | 0500041 | This project will improve safety and reliability of the transportation system by replacing an older bridge on GARLAND ROAD with a new BRIDGE OVER NINE MILE CREEK to serve the community for the next s | Bridge Replacement | 02/11/2010 | 02/11/2010 | 10/31/2010 | 571813 | 0
9512 | Tennessee | GILES |  | 04 | 0651069 | This project is for the construction of a new Welcome Center near Ardmore on I-65 | Transportation Enhancements | 01/11/2010 | 01/11/2010 | 02/28/2011 | 1419811 | 0
9513 | Tennessee | ROBERTSON |  | 06 | 0653116 | This project is for the construction of a new Welcome Center near Mitchellville on I-65 | Transportation Enhancements | 12/15/2009 | 02/01/2010 | 11/30/2010 | 2374533 | 0
9514 | Tennessee | BRADLEY | CLEVELAND | 03 | 0751118 | This project located on I-75 FROM EAST OF SR-60 TO SOUTH OF MCMINN COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 3730469.92 | 5.6
9515 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 0751126 | This project includes installation of landscaping at the Welcome Center near the Georgia state line on I-75 in Chattanooga | Transportation Enhancements | 05/14/2009 | 05/14/2009 | 05/15/2010 | 130000 | 0
9516 | Tennessee | LOUDON |  | 02 | 0752037 | This project located on I-75 FROM TENNESSEE RIVER BRIDGE TO SR-73 INTERCHANGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also he | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 5402750 | 6.9
9517 | Tennessee | KNOX | KNOXVILLE | 02 | 0753147 | This project located on I-75 FROM I-640 TO SOUTH OF CALLAHAN DRIVE AND ON I-275, FROM CONCRETE PAVEMENT TO I-640 will provide a smoother riding surface for motorists, thus decreasing wear and tear on | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/31/2009 | 2856699 | 3.4
9518 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 0811107 | This project includes installation of landscaping at the Welcome Center near the Virginia state line on I-81 in Bristol | Transportation Enhancements | 05/14/2009 | 05/14/2009 | 05/15/2010 | 130000 | 0
9519 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 0811108 | This project located on I-81 FROM SOUTH OF SR-357 TO NORTH OF SR-394 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 5191759 | 7.2
9520 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 0811112 | This project is for the widening of Houston Levee Road from Bailey Station Road to Winchester Road in Collierville from 4 lanes to 6 lanes. | Pavement Improvement | 02/16/2010 | 07/06/2010 | 09/30/2015 | 1608189 | 1.2
9521 | Tennessee | CARROLL |  | 08 | 0900031 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Westport Road with a new Bridges over the Big Sandy River and Overflow to serve the commu | Bridge Replacement | 03/03/2009 | 03/03/2009 | 06/01/2010 | 1802813 | 0.3
9522 | Tennessee | CARTER |  | 01 | 1000025 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Steel Bridge Road (Wilbur Dam Rd) with a new Bridge over the Watauga River to serve the co | Bridge Replacement | 03/03/2009 | 03/03/2009 | 09/01/2010 | 1702780 | 0.1
9523 | Tennessee | RUTHERFORD | MURFREESBORO | 06 | 1048006 | This resurfacing project located on THOMPSON LANE FROM SR-66 TO SR-1 (US-41/70S) IN MURFREESBORO will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobile | Pavement Improvement | 08/20/2009 | 08/20/2009 | 09/30/2015 | 629537 | 4.24
9524 | Tennessee | CHEATHAM |  | 05,07 | 1100027 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SPRING CREEK ROAD with a new BRIDGE OVER SPRING CREEK to serve the community for the next | Bridge Replacement | 04/07/2009 | 04/07/2009 | 06/14/2010 | 512092 | 0.1
9525 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 1406002 | This project is for the installation of traffic signals on Dayton Boulevard at the Intersections at Martin Road, Newberry Street, Leawood Avenue and Browntown Road in Red Bank | Safety/Traffic Management | 02/16/2010 |  | 09/30/2015 | 257093 | 0
9526 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 1406003 | This project is for the construction of sidewalks on Dayton Boulevard From Greenleaf Street to Browntown Road in Red Bank | Transportation Enhancements | 02/16/2010 |  | 09/30/2015 | 186180 | 2.15
9527 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 1406004 | This project located on Dayton Boulevard From the City limits to SR-153 in Chattanooga will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and wi | Pavement Improvement | 02/09/2010 |  | 09/30/2015 | 421115 | 2.86
9528 | Tennessee | COCKE |  | 01 | 1500050 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Splashaway Road with a new Bridge over Sinking Creek to serve the community for the next s | Bridge Replacement | 03/03/2009 | 03/03/2009 | 10/01/2009 | 185976 | 0
9529 | Tennessee | COFFEE |  | 04 | 1600016 | This project will improve safety and reliability of the transportation system by replacing an older bridge on MCKELLAR DRIVE with a new BRIDGE OVER LITTLE DUCK RIVER IN MANCHESTER to serve the communi | Bridge Replacement | 05/14/2009 | 05/14/2009 | 08/10/2010 | 537458 | 0
9530 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 1900029 | This project will improve safety and reliability of the transportation system by replacing an older bridge on CHESTNUT STREET with a new BRIDGE OVER CSX RAILROAD IN NASHVILLE to serve the community fo | Bridge Replacement | 06/30/2009 | 06/30/2009 | 07/31/2010 | 1799796 | 0
9531 | Tennessee | ROBERTSON | NASHVILLE-DAVIDSON | 06 | 1953001 | This resurfacing project located on CALISTA ROAD FROM OZZY FULKS ROAD TO SR-41 (US-31W) IN WHITE HOUSE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their auto | Pavement Improvement | 08/13/2009 | 08/13/2009 | 09/30/2015 | 514812 | 4.86
9532 | Tennessee | DECATUR |  | 07 | 2000013 | This project is for the construction of new sidewalks along SR-641 in Decatur County | Transportation Enhancements | 11/12/2009 | 11/12/2009 | 04/30/2011 | 251365 | 0
9533 | Tennessee | DECATUR |  | 07 | 2000014 | This streetscape beautification project in Parsons includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 08/21/2009 | 08/21/2009 | 08/14/2010 | 1040896 | 0
9534 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 2041001 | This project is for the construction of a new bridge on Big Station Camp Creek Boulevard from 0.2 miles north of SR-6 to 0.2 miles south of SR-6 including realigning the roadway to the new bridge in | Pavement Widening | 11/13/2009 | 11/13/2009 | 12/31/2010 | 1000000 | 0.2
9535 | Tennessee | FAYETTE |  | 07 | 2400032 | This project will improve safety and reliability of the transportation system by replacing an older bridge on FEATHERS CHAPEL ROAD with a new BRIDGE OVER TREADVILLE CREEK to serve the community for th | Bridge Replacement | 05/13/2009 | 05/13/2009 | 01/15/2010 | 345937 | 0.1
9536 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 2401289 | This project located on I-240 FROM MADISON AVENUE TO I-55 AND ON I-55, FROM NONCONNAH CREEK TO I-240 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automo | Pavement Improvement | 05/15/2009 | 05/15/2009 | 12/15/2009 | 4163630 | 5.65
9537 | Tennessee | FENTRESS |  | 04 | 2500024 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Delk Creek Road with a new Bridge over Delk Creek to serve the community for the next seve | Bridge Replacement | 03/03/2009 | 03/03/2009 | 11/01/2009 | 468403 | 0.1
9538 | Tennessee | GIBSON |  | 08 | 2700051 | This project will improve safety and reliability of the transportation system by replacing an older bridge on McMurry Road with a new Bridges over Branch, Davis Creek and Reagan Creek to serve the co | Bridge Replacement | 03/03/2009 | 03/03/2009 | 06/01/2010 | 1016860 | 0.3
9539 | Tennessee | GILES |  | 04 | 2800032 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Earl Townsend Road with a new Bridge over the West Fork of Shoal Creek to serve the commun | Bridge Replacement | 03/03/2009 | 03/03/2009 | 12/15/2009 | 273702 | 0.1
9540 | Tennessee | GILES |  | 04 | 2800033 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ELLA WEST ROAD with a new BRIDGE OVER EAST FORK OF LYNN CREEK to serve the community for | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/15/2009 | 189552.55 | 0
9541 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 2813009 | This project is for repairing the tunnel under the airport runway at Winchester Road in Memphis | Safety/Traffic Management | 02/11/2010 |  | 09/30/2015 | 161375 | 0
9542 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 2814003 | This project located on PERKINS ROAD EXT. FROM SR-57 (POPLAR AVENUE) TO LAURELWOOD DRIVE IN MEMPHIS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automob | Pavement Improvement | 02/10/2010 |  | 09/30/2015 | 267969 | 0.47
9543 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 2861002 | This project located on SOUTHERN AVENUE FROM SR-4 (LAMAR AVENUE) TO COLONIAL ROAD IN MEMPHIS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, a | Pavement Improvement | 02/10/2010 |  | 09/30/2015 | 1488860 | 5.62
9544 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3300046 | This project located on STANDIFER GAP ROAD FROM BILL REED ROAD TO BANKS ROAD and WOODLAND DRIVE FROM PATTENTOWN ROAD SOUTH TO BILL REED ROAD will provide a smoother riding surface for motorists, thus | Pavement Improvement | 12/07/2009 |  | 09/30/2015 | 281360 | 2.42
9545 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3300047 | This project located on MOSES ROAD FROM BOY SCOUT ROAD TO GANN ROAD/WEST CRABTREE ROAD FROM MIDDLE VALLEY ROAD TO BOWMAN ROAD/LOVELL ROAD FROM DAISY DALLAS ROAD TO THE SODDY DAISY CITY LIMITS will pro | Pavement Improvement | 12/07/2009 |  | 09/30/2015 | 432070 | 3.14
9546 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3300048 | This project located on FAIRVIEW ROAD FROM THE CHATTANOOGA CITY LIMITS TO GOLD POINT CIRCLE ROAD and GOLD POINT CIRCLE ROAD FROM HIXSON PIKE TO FAIRVIEW ROADwill provide a smoother riding surface for | Pavement Improvement | 12/07/2009 |  | 09/30/2015 | 251315 | 2.02
9547 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3300049 | This project located on CHAMPION ROAD FROM THE CHATTANOOGA CITY LIMITS TO HARRISON PIKE and HARRISON-OOLTEWAH ROAD FROM SR-58 TO THE ENTERPRISE SOUTH INDUSTRIAL PARK will provide a smoother riding sur | Pavement Improvement | 12/07/2009 | 06/01/2010 | 08/31/2010 | 267937 | 2.02
9548 | Tennessee | HARDEMAN |  | 07 | 3500036 | This project will improve safety and reliability of the transportation system by replacing an older bridge on VAN BUREN ROAD with a new BRIDGE OVER HAMER CREEK to serve the community for the next sev | Bridge Replacement | 04/06/2009 | 04/06/2009 | 10/31/2009 | 513939 | 0.1
9549 | Tennessee | HARDEMAN |  | 07 | 3500037 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Teague Road with a new Bridge over Clover Creek to serve the community for the next severa | Bridge Replacement | 03/03/2009 | 03/03/2009 | 06/01/2010 | 728855.92 | 0.1
9550 | Tennessee | HARDEMAN |  | 07 | 3500038 | This project will improve safety and reliability of the transportation system by replacing an older bridge on PARK SWAIN ROAD with a new BRIDGE OVER INDIAN CREEK to serve the community for the next s | Bridge Replacement | 04/06/2009 | 04/06/2009 | 09/30/2010 | 1019302 | 0.3
9551 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3589004 | This project located on Barton Avenue From Frazier Avenue to Hixson Pike in Chattanooga will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and w | Pavement Improvement | 02/12/2010 |  | 09/30/2015 | 216037 | 0.78
9552 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 3603003 | This project located on Hickory Valley Road From Shallowford Road to SR-317 (Bonny Oaks Drive) in Chattanooga will provide a smoother riding surface for motorists, thus decreasing wear and tear on th | Pavement Improvement | 02/09/2010 |  | 09/30/2015 | 250000 | 1.85
9553 | Tennessee | HAWKINS |  | 01 | 3700028 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Okolona Road with a new Bridge over Alexander Creek to serve the community for the next se | Bridge Replacement | 03/03/2009 | 03/03/2009 | 06/01/2010 | 549433 | 0.1
9554 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 3942003 | This project located on Walton Ferry Road From West Main Street to Curtis Cross Roads in Hendersonville will provide a smoother riding surface for motorists, thus decreasing wear and tear on their au | Pavement Improvement | 08/12/2009 | 08/12/2009 | 09/30/2015 | 620941 | 5.82
9555 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 3943003 | This project is for the development of design plans for a future bicycle and pedestrian facility project located on INDIAN LAKE BOULEVARD INTERSECTION AT SR-386 IN HENDERSONVILLE | Other | 08/12/2009 | 08/12/2009 | 09/30/2015 | 675830 | 0
9556 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 4032007 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Sam Cooper Boulevard with a new Bridge over Illinois Central and Union Pacific Railroads | Pavement Improvement | 02/16/2010 |  | 09/30/2015 | 245807 | 0
9557 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 4147001 | This project located on North Mack Smith Road From SR-8 (Ringgold Road) in East Ridge to the Georgia State Line will provide a smoother riding surface for motorists, thus decreasing wear and tear on | Pavement Improvement | 02/10/2010 | 07/15/2010 | 09/30/2015 | 62765 | 0.27
9558 | Tennessee | HUMPHREYS |  | 08 | 4300024 | This project is for the construction of a Welcome Center at and enhancement of the Interpretive Trail System at the Johnsonville State Historic Park | Transportation Enhancements | 12/28/2009 | 12/28/2009 | 09/30/2015 | 1456250 | 0
9559 | Tennessee | JACKSON |  | 06 | 4400052 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Overton Cemetary Road with a new bridge over Roaring River to serve the community for the | Bridge Replacement | 03/15/2010 | 03/15/2010 | 06/30/2011 | 430000 | 0.01
9560 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 4404077 | This project will rehabilitate the concrete pavement on I-440 from I-40 to I-24 in Nashville | Pavement Improvement | 05/15/2009 | 05/15/2009 | 05/31/2010 | 4768267 | 7.6
9561 | Tennessee | JEFFERSON | MORRISTOWN | 01 | 4500025 | This project located on Agricultural Park Boulevard From US-25E to the Railroad Bridge in White Pine will provide a smoother riding surface for motorists, thus decreasing wear and tear on their autom | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 80121 | 0.58
9562 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 4967003 | This project is for the construction of a bridge carrying Nashville and Eastern Railroad over Central Pike in Nashville | Pavement Widening | 09/25/2009 | 09/25/2009 | 09/30/2015 | 1000000 | 0
9563 | Tennessee | LAWRENCE |  | 04 | 5000014 | This project will improve safety and reliability of the transportation system by replacing an older bridge on LONG BRANCH ROAD with a new BRIDGE OVER LONG BRANCH to serve the community for the next s | New Bridge Construction | 04/06/2009 | 04/06/2009 | 05/15/2010 | 423673 | 0
9564 | Tennessee | LAWRENCE |  | 04 | 5000015 | This project will improve safety and reliability of the transportation system by replacing an older bridge on PINEY ROAD with a new BRIDGE OVER PINEY BRANCH to serve the community for the next sever | Bridge Replacement | 04/06/2009 | 04/06/2009 | 01/01/2010 | 412870 | 0
9565 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 5012001 | This project located on KNIGHT-ARNOLD ROAD FROM CHERRY STREET TO MT. MORIAH ROAD IN MEMPHIS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, an | Pavement Improvement | 02/11/2010 |  | 09/30/2015 | 2117133 | 4.59
9566 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 5365001 | This project is for preparing and implementing a resurfacing project located on SOUTH WATER AVENUE FROM MAPLE STREET TO BUSH AVENUE IN GALLATIN to provide a smoother riding surface for motorists, thus | Pavement Improvement | 08/12/2009 | 08/12/2009 | 09/30/2015 | 1329100 | 1.1
9567 | Tennessee | MCNAIRY |  | 07 | 5500050 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SULPHUR SPRINGS ROAD with a new BRIDGE OVER MOSSES CREEK to serve the community for the n | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/15/2010 | 534583 | 0.1
9568 | Tennessee | FAYETTE | MEMPHIS (AR-MS) | 07 | 5572001 | This project located on Fisherville Lake Road from Raleigh-LaGrange Road to SR-192 and Monterey Drive from the Shelby County line to Fisherville Lake Road will provide a smoother riding surface for mo | Pavement Improvement | 03/15/2010 | 03/15/2010 | 09/15/2010 | 352566 | 2.34
9569 | Tennessee | MACON |  | 06 | 5600045 | This project will improve safety and reliability of the transportation system by replacing an older bridge on CARR BRANCH ROAD with a new BRIDGE OVER CARR CREEK to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 05/31/2010 | 326442 | 0
9570 | Tennessee | MACON |  | 06 | 5600046 | This project will improve safety and reliability of the transportation system by replacing an older bridge on West Wixtown Road with a new Bridge over the West Fork of Long Creek to serve the communit | Bridge Replacement | 03/03/2009 | 03/03/2009 | 12/01/2009 | 309392 | 0
9571 | Tennessee | MADISON |  | 08 | 5700066 | This project will improve safety and reliability of the transportation system by replacing an older bridge on JOHN ANDERSON ROAD with a new BRIDGES OVER BRANCHS to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2009 | 315464 | 0.1
9572 | Tennessee | MEIGS |  | 03 | 6100021 | This project will improve safety and reliability of the transportation system by replacing an older bridge on LAMONTVILLE ROAD with a new BRIDGE OVER PRICE CREEK to serve the community for the next s | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/15/2010 | 532463 | 0
9573 | Tennessee | MONROE |  | 02 | 6200022 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Belcher Gap Road with a new Bridge over Notchy Creek to serve the community for the next s | Bridge Replacement | 03/03/2009 | 03/03/2009 | 11/30/2009 | 341498 | 0.1
9574 | Tennessee | MONROE |  | 02 | 6200023 | This project will improve safety and reliability of the transportation system by replacing an older bridge on GRIFFITH BRANCH ROAD with a new BRIDGE OVER NOTCHY CREEK to serve the community for the n | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2009 | 760048 | 0
9575 | Tennessee | PERRY |  | 07 | 6800022 | This streetscape beautification project in Linden includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 09/25/2009 | 03/01/2010 | 12/31/2010 | 1602008 | 0
9576 | Tennessee | SEVIER |  | 01 | 7800053 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ROARING FORK EXT. ROAD with a new BRIDGE OVER ROARING FORK CREEK IN GATLINBURG to serve t | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/15/2010 | 206916 | 0
9577 | Tennessee | SEVIER |  | 01 | 7800054 | This project will improve safety and reliability of the transportation system by replacing an older bridge on OLD NEWPORT HIGHWAY with a new BRIDGE OVER EAST FORK LITTLE PIGEON RIVER to serve the com | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/15/2010 | 568065 | 0
9578 | Tennessee | SEVIER |  | 01 | 7800055 | This project will improve safety and reliability of the transportation system by replacing an older bridge on LECONTE STREET with a new BRIDGE OVER WEST PRONG LITTLE PIGEON RIVER IN GATLINBURG to ser | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/31/2010 | 1338750 | 0
9579 | Tennessee | SEVIER |  | 01 | 7800056 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ROCKY FLATS ROAD with a new BRIDGE OVER DUNN CREEK to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/15/2010 | 611328 | 0
9580 | Tennessee | STEWART |  | 08 | 8100009 | This project is for the construction of a new visitors' center in Stewart County on Highway 79 | Transportation Enhancements | 05/14/2009 | 05/14/2009 | 08/25/2010 | 1045000 | 0
9581 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 8300072 | This project is for the development of design plans for the future construction of a greenway facility on Lower Station Camp Creek Road in Gallatin. | Other | 02/17/2010 | 02/25/2010 | 07/01/2011 | 194724 | 0
9582 | Tennessee | TIPTON |  | 08 | 8400067 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ROBERT JOHNSON ROAD with a new BRIDGE OVER DRAINAGE CANAL to serve the community for the | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2009 | 289775 | 0
9583 | Tennessee | TIPTON |  | 08 | 8400068 | This project will improve safety and reliability of the transportation system by replacing an older bridge on BUCKSNORT ROAD with a new BRIDGE OVER MATHIS CREEK to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 05/15/2010 | 754386 | 0
9584 | Tennessee | TIPTON |  | 08 | 8400069 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ANTIOCH HIGHWAY with a new BRIDGE OVER FLAT CREEK to serve the community for the next sev | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/15/2010 | 716762 | 0
9585 | Tennessee | TIPTON |  | 08 | 8400070 | This project will improve safety and reliability of the transportation system by replacing an older bridge on PORTERSVILLE ROAD with a new BRIDGE OVER HEBRON BRANCH to serve the community for the next | Bridge Replacement | 05/15/2009 | 05/15/2009 | 01/15/2010 | 489562 | 0.1
9586 | Tennessee | TROUSDALE |  | 06 | 8500018 | This streetscape beautification project in Hartsville includes elevator upgrades in the Hartsville Courthouse, rehabilitating/upgrading sidewalks, installing/upgrading lighting, pedestrian amenities a | Transportation Enhancements | 05/13/2009 | 05/21/2009 | 04/15/2010 | 367083 | 0
9587 | Tennessee | WASHINGTON |  | 01 | 9000045 | This project will improve safety and reliability of the transportation system by replacing an older bridge on BOB DAVIS ROAD with a new BRIDGE OVER CSX RAILROAD to serve the community for the next se | Bridge Replacement | 04/06/2009 | 04/06/2009 | 05/31/2010 | 953845 | 0
9588 | Tennessee | BLOUNT | KNOXVILLE | 02 | 9101010 | This project is for traffic signal system upgrades at various locations in Alcoa/Maryville | Safety/Traffic Management | 02/19/2010 | 07/19/2010 | 07/14/2011 | 1211503 | 0
9589 | Tennessee | BLOUNT | KNOXVILLE | 02 | 9101011 | This project is for the construction of a new pedestrian bridge over State Route 115 in Alcoa for the Culton Creek Greenway | Transportation Enhancements | 09/25/2009 | 09/25/2009 | 10/30/2010 | 1600000 | 0
9590 | Tennessee | BLOUNT | KNOXVILLE | 02 | 9101012 | This resurfacing project located on CALDERWOOD STREET FROM JOULE STREET TO THE CITY LIMITS OF ALCOA/SINGLETON STATION ROAD FROM SR-115 (ALOCA HWY) TO THE CITY LIMITS OF ALCOA will provide a smoother | Pavement Improvement | 08/07/2009 | 08/07/2009 | 09/30/2015 | 456698 | 4.1
9591 | Tennessee | SULLIVAN | BRISTOL TN- VA | 01 | 9102007 | This project located on OLD JONESBORO ROAD FROM THE CITY LIMITS TO GALWAY ROAD/EXIDE DRIVE FROM SR-34 (US-11E) TO EDISON CIRCLE/ASH STREET FROM MARTIN LUTHER KING JR. BOULEVARD TO SR-34 (US-421)/BROAD | Pavement Improvement | 01/07/2010 | 01/07/2010 | 09/30/2015 | 810904 | 5.1
9592 | Tennessee | CARTER | JOHNSON CITY | 01 | 9103013 | This project will widen LYNN AVENUE from 2 lanes to 5 lanes including bike lanes and sidwalks FROM SR-67 (BROAD STREET) TO EAST ELK AVENUE IN ELIZABETHTON | Pavement Improvement | 07/01/2009 | 07/10/2009 | 11/01/2010 | 1212573 | 0.17
9593 | Tennessee | GREENE |  | 01 | 9104011 | This project will improve safety and reliability of the transportation system by replacing an older bridge on HANNAH STREET (OLD TUSCULUM ROAD) with a new BRIDGE OVER HOLLEY CREEK IN GREENEVILLE to s | Bridge Replacement | 04/06/2009 | 04/06/2009 | 12/31/2009 | 326823.3 | 0
9594 | Tennessee | JEFFERSON | MORRISTOWN | 03 | 9106011 | This project located on North Russell Avenue From SR-92 to Old Andrew Johnson Highway in Jefferson City/North Chucky Pike From Clearbrook Drive to Old Andrew Johnson Highway in Jefferson City/North S | Pavement Improvement | 08/07/2009 | 08/07/2009 | 09/30/2015 | 400162 | 2.94
9595 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 9107009 | This project is for the construction of a bicycle and pedestrian path in Johnson City including landscaping and pedestrian amenities | Transportation Enhancements | 09/03/2009 | 09/03/2009 | 07/15/2010 | 400000 | 0
9596 | Tennessee | WASHINGTON | JOHNSON CITY | 01 | 9107025 | This project located on BAXTER STREET FROM SR-400 (EAST WATAUGA AVENUE) TO MOUNTCASTLE DRIVE/EAST FAIRVIEW AVENUE FROM EAST OAKLAND AVENUE TO SR-400 (EAST UNAKA AVENUE)/PEOPLES STREET/BROWNS MILL ROAD | Pavement Improvement | 01/08/2010 | 07/19/2010 | 09/30/2015 | 823368 | 2.91
9597 | Tennessee | SULLIVAN | KINGSPORT (VA) | 01 | 9108031 | This project located on NORTH EASTMAN ROAD FROM LINCOLN STREET TO EAST STONE DRIVE/CLINCHFIELD STREET FROM WEST CENTER STREET TO WEST STONE DRIVE/EAST CENTER STREET FROM FORT HENRY DRIVE TO MEMORIAL B | Pavement Improvement | 09/22/2009 | 09/22/2009 | 09/30/2015 | 1392309 | 3.75
9598 | Tennessee | SULLIVAN | KINGSPORT (VA) | 01 | 9108032 | This project located on OREBANK ROAD FROM MEMORIAL BOULEVARD TO LAMBERTH STREET/BLOOMINGDALE PIKE FROM WEST STONE DRIVE TO GRAVELY ROAD IN KINGSPORT will provide a smoother riding surface for motorist | Pavement Improvement | 09/22/2009 | 09/22/2009 | 05/30/2010 | 581878 | 3.65
9599 | Tennessee | KNOX | KNOXVILLE | 02 | 9109130 | This project will widen CAMPBELL STATION ROAD from 4 lanes to 5 lanes FROM PARKSIDE DRIVE TO JAMESTOWN BOULEVARD IN FARRAGUT | Pavement Widening | 05/15/2009 | 05/15/2009 | 12/31/2010 | 2355370 | 0.94
9600 | Tennessee | KNOX | KNOXVILLE | 02 | 9109132 | This project is for the construction of the Papermill Bluff bicycle/pedestrian pathway from Papermill Road to Weisgarber Road that includes landscaping. | Transportation Enhancements | 07/17/2009 | 07/17/2009 | 09/30/2015 | 642000 | 0
9601 | Tennessee | LOUDON | KNOXVILLE | 02 | 9111003 | This resurfacing project located on ADESA BOULEVARD ADESA BOULEVARD, FROM OLD HWY 95 TO SR-73 (US-321) IN LENOIR CITY/BROWDER HOLLOW ROAD/ JOHNSTON DRIVE FROM SR-2 (US-11) TO NEAR JOHNSON CIRCLE IN LE | Pavement Improvement | 09/22/2009 | 09/22/2009 | 09/30/2015 | 388574 | 4.24
9602 | Tennessee | LOUDON | KNOXVILLE | 03 | 9111005 | This streetscape project is for landscaping and scenic beautification on Creekwood Park Boulevard from SR-73 (US-321) to SR-1 (US-70) in Lenoir City | Transportation Enhancements | 02/08/2010 | 07/19/2010 | 09/30/2015 | 553290 | 1.39
9603 | Tennessee | HAMBLEN | MORRISTOWN | 01 | 9113014 | This resurfacing project located on EAST 2ND NORTH STREET FROM ANDERSON STREET TO NORTH CUMBERLAND STREET IN MORRISTOWN will provide a smoother riding surface for motorists, thus decreasing wear and t | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 273132 | 0.8
9604 | Tennessee | ANDERSON |  | 03 | 9117011 | This project will improve safety and reliability of the transportation system by replacing an older bridge on YARNELL ROAD with a new BRIDGE OVER LITTLE DISMAL CREEK IN CLINTON to serve the community | Bridge Replacement | 04/06/2009 | 04/06/2009 | 07/31/2010 | 286734 | 0.1
9605 | Tennessee | MCMINN |  | 02 | 9201011 | This streetscape beautification project in Athens includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 09/01/2009 | 09/01/2009 | 12/10/2010 | 1133078 | 0
9606 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9202095 | This project is for the construction of a new trail and bikeway along South Chickamauga Creek in Chattanooga | Transportation Enhancements | 09/02/2009 | 02/01/2010 | 12/01/2010 | 500000 | 0
9607 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9202098 | This project is for the replacement of traffic signals at various locations in Chattanooga. | Safety/Traffic Management | 02/09/2010 |  | 09/30/2015 | 900000 | 0
9608 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9202101 | This project located on Airport Road From Shepherd Road to Shallowford Road in Chattanooga & Shepherd Road From SR-153 to Airport Road in Chattanooga will provide a smoother riding surface for motori | Pavement Improvement | 02/16/2010 |  | 09/30/2015 | 778159 | 2.51
9609 | Tennessee | BRADLEY | CLEVELAND | 03 | 9203013 | This resurfacing project located on FREEWILL ROAD FROM CUMBERLAND HILLS CIRCLE TO NORTH OF COTTONWOOD BEND IN CLEVELAND will provide a smoother riding surface for motorists, thus decreasing wear and t | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 510359 | 4.76
9610 | Tennessee | BRADLEY | CLEVELAND | 03 | 9203014 | This resurfacing project located on RAIDER DRIVE FROM KEITH STREET TO PEERLESS ROAD IN CLEVELAND will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobile | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 468017 | 0.96
9611 | Tennessee | BRADLEY | CLEVELAND | 03 | 9203015 | This project is for the construction of a new comfort station that will include restrooms and drinking fountain for the Mouse Creek Greenway | Transportation Enhancements | 11/24/2009 |  | 09/30/2015 | 40000 | 0
9612 | Tennessee | BRADLEY | CLEVELAND | 03 | 9203016 | This project is for the construction of pedestrian amenities on various streets in Cleveland | Transportation Enhancements | 02/08/2010 |  | 09/30/2015 | 181408 | 0
9613 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9212001 | This project is for the installation of traffic signals on at the School Zones in Collegedale | Safety/Traffic Management | 02/16/2010 |  | 09/30/2015 | 8918 | 0
9614 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9212002 | This project is for the replacement of traffic signals at various locations in Collegedale. | Safety/Traffic Management | 03/04/2010 |  | 09/30/2015 | 761 | 0
9615 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9212003 | This project is for the installation of sidewalk lighting at various locations in Collegedale. | Safety/Traffic Management | 02/10/2010 | 07/28/2010 | 09/30/2015 | 128918 | 0
9616 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9212004 | This project located on multiple projects (Tallant Road From SR-317 (Apison Pike) to McDonald Road in Collegedale/Prospect Church Road From University Drive to Borzoi Lane in Collegedale/Standifer Ga | Pavement Improvement | 02/16/2010 |  | 09/30/2015 | 700454 | 6
9617 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9212005 | This project is for the construction of sidewalks and a greenway on Swinyar Drive and University Drive in Collegedale | Transportation Enhancements | 02/16/2010 | 07/28/2010 | 09/30/2015 | 152987 | 0
9618 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9213001 | This project is for the installation of traffic signals on at the School Zones in East Ridge | Safety/Traffic Management | 02/10/2010 |  | 09/30/2015 | 35627 | 0
9619 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9213003 | This project is for the construction of sidewalks on Camp Jordan Parkway From Camp Jordan Road to near SR-8 (Ringgold Road) in East Ridge | Transportation Enhancements | 02/09/2010 |  | 09/30/2015 | 159033 | 1.39
9620 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9214001 | This project located on Dayton Boulevard Dayton Boulevard from Signal Mountain Boulevard to Memorial Drive in Red Bank & Lupton Drive From Dayton Boulevard to the City Limits in Red Bank will provide | Pavement Improvement | 02/12/2010 |  | 09/30/2015 | 405882 | 4.27
9621 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9214002 | This project is for the construction of a greenway and lighting and streetscape improvements at various locations in Red Bank | Transportation Enhancements | 02/16/2010 |  | 09/30/2015 | 691314 | 0
9622 | Tennessee | HAMILTON | CHATTANOOGA (GA) | 03 | 9215001 | This project located on North Palisades Drive From Wilder Drive to the City Limits in Signal Mountain & Various Sections on James Boulevard will provide a smoother riding surface for motorists, thus | Pavement Improvement | 02/16/2010 |  | 09/30/2015 | 353683 | 1.78
9623 | Tennessee | WHITE |  | 04 | 9300039 | This project will improve safety and reliability of the transportation system by replacing an older bridge on FANCHER MILL ROAD with a new BRIDGE OVER TAYLOR CREEK to serve the community for the next | Bridge Replacement | 05/15/2009 | 05/15/2009 | 10/10/2010 | 891195 | 0.2
9624 | Tennessee | MONTGOMERY | CLARKSVILLE (KY) | 07 | 9301023 | This project located on LAFAYETTE ROAD FROM SR-374 TO THE FT. CAMPBELL BOUNDARY/ CUNNINGHAM LANE FROM LAFAYETTE ROAD TO SR-12 (US-41A)/ CROSSLAND AVENUE FROM S. RIVERSIDE DRIVE TO MADISON STREET/NEEDM | Pavement Improvement | 02/18/2010 |  | 09/30/2015 | 1902700 | 9.72
9625 | Tennessee | MAURY |  | 04 | 9302016 | This project will improve safety and reliability of the transportation system by replacing an older bridge on INDUSTRIAL PARK ROAD with a new BRIDGE OVER THE DUCK RIVER IN COLUMBIA to serve the commun | Bridge Replacement | 05/15/2009 | 05/15/2009 | 10/15/2010 | 2693882 | 0
9626 | Tennessee | DICKSON |  | 08 | 9303010 | This project includes the construction and installation of transportation exhibits in the Halbrook Hotel Railroad Museum in Dickson | Transportation Enhancements | 11/13/2009 | 01/01/2010 | 09/30/2014 | 171432 | 0
9627 | Tennessee | WILLIAMSON | NASHVILLE-DAVIDSON | 07 | 9305024 | This project is for the development of design plans for a future installation of video technology in Franklin to expand the existing traffic monitoring system and to assist incident management and qui | Safety/Traffic Management | 01/07/2010 | 01/07/2010 | 09/30/2015 | 1203242 | 0
9628 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 9306012 | This project is for the construction of a bicycle and pedestrian path, the Town Creek Greenway, in Gallatin including landscaping, pedestrian amenities, lighting, upgrading/rehabilitating sidewalks an | Transportation Enhancements | 01/05/2010 | 01/07/2010 | 09/30/2010 | 951809 | 0
9629 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 9306014 | This streetscape beautification project in Gallatin includes landscaping, pedestrian amenities, lighting, upgrading/rehabilitating sidewalks and utility relocation | Transportation Enhancements | 06/23/2010 |  | 09/15/2015 | 480000 | 0
9630 | Tennessee | RUTHERFORD | MURFREESBORO | 06 | 9311020 | This project is for the installation of video technology to expand the existing traffic monitoring system and to assist incident management and quick clearance response | Safety/Traffic Management | 02/18/2010 |  | 09/15/2015 | 1000000 | 0
9631 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 99 | 9312090 | This project located on TROUSDALE DRIVE FROM HARDING PLACE TO HOGAN ROAD/ABBOTT MARTIN ROAD FROM HILLSBORO PIKE TO THE CITY LIMITS/BOWLING AVENUE FROM WEST END AVENUE TO WOODLAWN AVENUE /HICKORY HOLLO | Pavement Improvement | 12/14/2009 | 07/19/2010 | 09/30/2015 | 1678321 | 7.46
9632 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312091 | This project located on JEFFERSON STREET FROM RAILROAD BRIDGE TO DR. DB TODD, JR./ELLISTON PLACE FROM WEST END AVENUE TO CHURCH STREET BOULEVARD/CHURCH STREET FROM 21ST AVENUE NORTH TO 16TH AVENUE NOR | Pavement Improvement | 12/14/2009 | 07/19/2010 | 09/30/2015 | 1521321 | 6.46
9633 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312092 | This project located on CENTRAL PIKE FROM DODSON CHAPEL ROAD TO OLD HICKORY BOULEVARD/SOUTH GRAYCROFT AVENUE FROM OLD HICKORY BOULEVARD TO DUE WEST AVENUE/ELM HILL PIKE FROM ATRIUM WAY TO DONELSON PIK | Pavement Improvement | 12/14/2009 | 07/08/2010 | 09/30/2015 | 1728821 | 7.57
9634 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312093 | This project will provide for the signal timing upgrades at various locations in Nashville | Safety/Traffic Management | 11/04/2009 | 11/04/2009 | 12/31/2010 | 762687 | 0
9635 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312094 | This project is for the optimization of traffic signal timing at various intersections in Nashville | Safety/Traffic Management | 09/11/2009 | 09/11/2009 | 10/31/2011 | 998984 | 0
9636 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312095 | This project is for the construction of a new bicycle and pedestrian path from the levee at Metro Center to Clifton Avenue in Nashville | Transportation Enhancements | 09/01/2009 |  | 09/30/2015 | 1000000 | 0
9637 | Tennessee | WILSON | NASHVILLE-DAVIDSON | 05 | 9312096 | This project is for the construction of a new greenway on West Division Street From the Music City Star Station to 4th Street in Mount Juliet. | Transportation Enhancements | 09/23/2009 | 09/23/2009 | 09/15/2015 | 450000 | 0
9638 | Tennessee | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312097 | This project is for intersection improvements including traffic light and crosswalk signal upgrades at various intersections on Harding Place (SR-255), Bell Road (SR-254), Nolensville Pike (SR-11), an | Safety/Traffic Management | 11/13/2009 | 07/14/2010 | 09/30/2015 | 791707 | 0
9639 | Tennessee | RUTHERFORD | MURFREESBORO | 06 | 9317007 | This project will widen WALDRON ROAD/PARTHENON BOULEVARD from 3 lanes to 5 lanes FROM NORTH OF INDUSTRIAL DRIVE/ENTERPRISE BOULEVARD TO SR-1 | Pavement Widening | 09/17/2009 | 09/17/2009 | 11/30/2011 | 1000000 | 2.19
9640 | Tennessee | SUMNER | NASHVILLE-DAVIDSON | 06 | 9319001 | This project located on South Russell Street From Main Street to Lynnwood Drive in Portland will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, a | Pavement Improvement | 02/10/2010 | 07/19/2010 | 09/30/2015 | 400880 | 0.69
9641 | Tennessee | ROBERTSON | NASHVILLE-DAVIDSON | 06 | 9320001 | This project is for upgrades to traffic signals along SR-75 and SR-41(US-31W) in White House. | Safety/Traffic Management | 02/10/2010 |  | 09/30/2015 | 367127 | 0
9642 | Tennessee | MADISON | JACKSON | 08 | 9406007 | This project is for the construction of curbs and addition of sidewalks on SR-198 (East Chester Street) from US-70 to Holland Avenue in Jackson | Pavement Widening | 02/04/2010 | 06/03/2010 | 12/15/2010 | 1500058 | 0.58
9643 | Tennessee | MADISON | JACKSON | 08 | 9406008 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SECOND STREET with a new BRIDGE OVER ANDERSON BRANCH IN JACKSON to serve the community f | Bridge Replacement | 04/06/2009 | 04/06/2009 | 05/20/2010 | 375956 | 0
9644 | Tennessee | WEAKLEY |  | 08 | 9408008 | This streetscape beautification project in Martin includes elevator upgrades in the Hartsville Courthouse, rehabilitating/upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and l | Transportation Enhancements | 09/14/2009 | 09/14/2009 | 07/14/2010 | 1374018 | 0
9645 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 9409135 | This resurfacing project located on HACKS CROSS ROAD FROM STATE LINE ROAD TO THE MEMPHIS CITY LIMITS/HOUSTON LEVEE ROAD FROM THE WOLD RIVER BRIDGE TO WOLF RIVER PARKWAY/WALNUT GROVE ROAD FROM ROCKY PO | Pavement Improvement | 07/17/2009 |  | 09/30/2015 | 2550995 | 28.94
9646 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9409137 | This project is for the development of design plans for a future bicycle and pedestrian facility project located on AIRLINE ROAD FROM THE C.S.X. RAILROAD TO I-40 IN ARLINGTON and to provide a smoother | Pavement Improvement | 02/19/2010 | 05/18/2010 | 08/31/2010 | 396807 | 4.34
9647 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9409140 | This project is for the construction of a bicycle/pedestrian pathway on Canada Road that includes landscaping. | Transportation Enhancements | 05/27/2009 | 06/09/2009 | 09/30/2015 | 1043432 | 2.5
9648 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 9409147 | This project located on several locations in Memphis (Millbranch Road from I-240 to Riverbrook Drive; Ball Road from Norris Road to Ketchum Road; Ross Road from Shelby Drive to Winchester Road; Warin | Pavement Improvement | 02/19/2009 |  | 09/30/2015 | 5280895 | 10.45
9649 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 9409148 | This resurfacing project located on CHELSEA AVENUE FROM NORTH WATKINS STREET TO FAIRFAX STREET IN MEMPHIS/SEMMES STREET FROM WILDROSE STREET TO WAVERLY AVENUE IN MEMPHIS will provide a smoother ridin | Pavement Improvement | 02/19/2009 |  | 09/30/2015 | 2220919 | 5.4
9650 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 9409149 | This resurfacing project located on MADISON AVENUE FROM NORTH CLEVELAND STREET TO EAST PARKWAY IN MEMPHIS/S. PARKWAY EAST FROM SOUTH LAUDERDALE STREET TO SR-3 (ELVIS PRESLEY BOULEVARD) IN MEMPHIS/S. F | Pavement Improvement | 02/19/2009 |  | 09/30/2015 | 2580513 | 5.91
9651 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 09 | 9409150 | This project is for the construction of hand rails on two bridges, Horn Lake Bridge over Johnston Railroad Yard and Rivergate Bridge over Nonconnah Creek, in Memphis | Safety/Traffic Management | 02/19/2009 |  | 09/30/2015 | 158525 | 0
9652 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 08 | 9411006 | This resurfacing project located on FROM PAUL BARRET PARKWAY TO THE CITY LIMITS OF MILLINGTON/CHURCH STREET FROM NAVY ROAD TO PAUL BARRET PARKWAY IN MILLINGTON/EASLEY ROAD FROM HWY 51 TO NAVY ROAD IN | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 1271225 | 6.08
9653 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 08 | 9411007 | This project consists of repairs to the bridge over Big Creek on Raleigh-Millington Road in Millington | Other | 07/17/2009 | 07/17/2009 | 09/30/2015 | 7240 | 0
9654 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 08 | 9411008 | This resurfacing project located on BIG CREEK CHURCH ROAD FROM HWY 51 TO RALIEGH-MILLINGTON ROAD IN MILLINGTON will provide a smoother riding surface for motorists, thus decreasing wear and tear on th | Other | 07/17/2009 | 07/17/2009 | 07/30/2010 | 18760 | 2.44
9655 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 08 | 9411009 | This streescape project is for landscaping and scenic beautification on Navy Road from US-51 to east of Veterans Parkway in Millington | Transportation Enhancements | 07/17/2009 | 07/17/2009 | 09/30/2015 | 769729 | 2.5
9656 | Tennessee | LAUDERDALE |  | 08 | 9418009 | This streetscape beautification project in Ripley includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 05/14/2009 | 11/01/2009 | 08/20/2010 | 1101917 | 0
9657 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9419003 | This resurfacing project located on ST. ELMO ROAD FROM MEMPHIS-ARLINGTON ROAD TO KIRBY WHITTEN ROAD IN BARTLETT/ELMORE PARK ROAD FROM ELMORE PARK TO YALE ROAD IN BARTLETT/SYCAMORE VIEW ROAD FROM STAGE | Other | 07/17/2009 | 07/17/2009 | 09/30/2015 | 61000 | 9.58
9658 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9419004 | This resurfacing project located on BARTLETT BOULEVARD FROM THE SOUTH CITY LIMITS TO MEMPHIS-ARLINGTON ROAD IN BARTLETT/ALTRURIA ROAD FROM SUMMER AVENUE TO YALE ROAD IN BARTLETT will provide a smooth | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 1619000 | 8.42
9659 | Tennessee | SHELBY | MEMPHIS (AR-MS) | 07 | 9420002 | This project is for the preparation and actual replacement of existing roadway pavement including sidewalks on Farmington Boulevard from Allenby Road to Wolf River Boulevard in Germantown. | Pavement Improvement | 07/17/2009 | 07/17/2009 | 09/30/2015 | 1732650 | 2.06
9660 | Tennessee | STATEWIDE |  | 05 | 9900013 | The On-the-Job Training/Supportive Services program will train ready, willing and able individuals for entry or re-entry into the workforce. | Other | 02/01/2010 | 02/01/2010 | 01/31/2011 | 800000 | 0
9661 | Texas | COLLIN |  | 03 | 0094179 | SPN:0918-24-040-RICHARDSON TRAIL Fr. ALMA ROAD To. 0.24 MILES SOUTH OF RENNER ROAD; CONST 10' WIDE CONC WALKWAY | Transportation Enhancements | 03/08/2010 | 03/08/2010 |  | 578650 | 2.2
9662 | Texas | DENTON |  | 24 | 0095067 | SPN:0918-46-065-REPLACE BRIDGE AND APPROACHES (NEW STEEL TRUSS) : ON GREGORY ROAD AT DUCK CREEK | Bridge Replacement | 07/02/2009 | 08/26/2009 | 05/01/2010 | 398815.28 | 0.07
9663 | Texas | HARRIS | HOUSTON | 18 | 0097224 | SPN:0912-71-545-WEST WHITE OAK BAYOU TRAIL EXTENSION : S. PINEMONT ANTOINE DR. | Transportation Enhancements | 06/24/2010 |  |  | 1622074 | 2.235
9664 | Texas | HARRIS | HOUSTON | 10 | 0099026 | SPN:0912-71-586-CONSTRUCT 2 LANE ASPHALT ROAD WITH TURN LANES : ON GOSLING RD FROM KUYKENDAHL | New Construction | 09/28/2009 | 10/28/2009 | 05/01/2011 | 1621404.85 | 0.503
9665 | Texas | HARRIS | HOUSTON | 29 | 0099550 | SPN:0912-71-637-WIDEN TO 4 LANE DIVIDED : ON LITTLE YORK E FROM AIRLINE HARDY TOLL ROAD | Pavement Widening | 05/24/2010 | 06/09/2010 |  | 5491472.07 | 0.917
9666 | Texas | WILLIAMSON | AUSTIN | 31 | 08TX001 | SPN:1378-02-034-WIDEN TO 4-LANE DIVIDED ROADWAY : 183A CR 185 | Pavement Improvement | 02/08/2010 | 03/08/2010 |  | 5049675.69 | 0.79
9667 | Texas | CHAMBERS |  | 14 | 2000065 | SPN:0508-03-075-CONSTRUCT TOURIST AND VISITOR CENTER, PARKING LOT AND LANDSCAPING : 2 MI WEST OF FM 1724 | Transportation Enhancements | 10/16/2009 | 02/15/2010 |  | 11017416.59 | 0.001
9668 | Texas | BEXAR | SAN ANTONIO | 21 | 2000148 | SPN:0915-12-329-GRAD, STR, BASE, SURF RECONSTRUCT & EXPAND 3 TO 4 LANES | Pavement Widening | 03/15/2010 |  |  | 500000 | 0.11
9669 | Texas | NAVARRO |  | 06 | 2000293 | SPN:0166-01-041-RECONSTRUCTION OF SAFETY REST AREA : 2 MILES S OF RICHLAND | Transportation Enhancements | 09/28/2009 | 10/08/2009 | 06/01/2009 | 11770092.74 | 1.231
9670 | Texas | DALLAS |  | 30 | 2000555 | SPN:0918-45-533-SCENIC BEAUTIFICATION PROJECT | Transportation Enhancements | 02/11/2010 | 03/01/2010 |  | 423839 | 0.001
9671 | Texas | HARRIS | HOUSTON | 18 | 2000597 | SPN:0912-71-705-LANDSCAPE AND SCENIC BEAUTIFICATION OF HISTORIC TRANSPORTATION HUB : AT ALLEN`S LANDING IN HOUSTON | Transportation Enhancements | 12/04/2009 | 12/10/2009 | 12/04/2009 | 902024.64 | 0.13
9672 | Texas | LUBBOCK | LUBBOCK | 19 | 2001597 | SPN:0783-02-065-WIDEN FREEWAY TO 6 MAIN LANES FOR THE CONSTRUCTION OF WIDENING EXISTING FREEWAY FACILITY : 0.2 MI NORTH OF 34TH STREET 200` WEST OF FM 2528 (FRANKFORD) | Pavement Widening | 04/05/2010 | 04/05/2010 |  | 6546325 | 0.001
9673 | Texas | TRAVIS |  | 10 | 2002109 | SPN:0914-04-191-CONSTRUCT TRAIL | Transportation Enhancements | 05/24/2010 |  |  | 1826571.29 | 0.001
9674 | Texas | WILLIAMSON |  | 31 | 2002110 | SPN:0914-05-122-CONSTRUCT TRAIL | Transportation Enhancements | 06/23/2009 | 10/05/2009 | 08/01/2014 | 331580.8 | 0.001
9675 | Texas | DALLAS | DALLAS-FORT WORTH | 03 | 2002126 | SPN:0918-45-640-CONSTRUCT PEDESTRIAN BRIDGE OVER IH635 (LBJ) TO DART STATION (LBJ/SKILLMAN PEDESTRIAN BRIDGE) : DART LINE FROM AUDELIA RD NORTHEAST 626 FT BRIDGE TO SKILLMAN DART STAT | Transportation Enhancements | 04/13/2010 |  |  | 1038717.18 | 0.001
9676 | Texas | DALLAS | DALLAS-FORT WORTH | 30 | 2002129 | SPN:0918-45-643-CONSTRUCT 2 MILES OF BICYCLE WEB ROUTE (TENISON TRAIL PHASE ONE-EAST DALLAS VELOWAY) : WINSTED DR WITHIN OLD SP&SF RR ROW, | Transportation Enhancements | 08/19/2009 | 09/10/2009 | 12/01/2010 | 1786702.8 | 2.372
9677 | Texas | JOHNSON |  | 17 | 2002141 | SPN:0902-50-077-BURLESON PEDESTRIAN AND BICYCLE TRAIL CONNECTING SCHOOLS, SUBDIVISION, ETC. TO THE EASTERN HALF OF OLD TOWN : OLD TOWN BURLESON SCHOOLS, SUBDIVISIONS & OTHER FACIL | Transportation Enhancements | 04/19/2010 | 04/19/2010 |  | 1059769.58 | 2.419
9678 | Texas | HARRIS | HOUSTON | 09 | 2002154 | SPN:0912-71-802-LANDSCAPE-OST/ALMEDA CORRIDORS REDEVELOPMENT AUTHORITY IN HOUSTON : ON OST FROM SH 288 TO GRIGGS ROAD GRIGGS FROM OST TO CALHOUN | Transportation Enhancements | 04/22/2010 | 06/02/2010 |  | 438941.6 | 1.76
9679 | Texas | SHERMAN |  | 13 | 2002207 | SPN:0904-40-010-TRANS ENHANCEMENT : STRATFORD STREETSCAPE | Transportation Enhancements | 09/01/2009 | 10/19/2009 | 09/01/2009 | 1558107.81 | 0.001
9680 | Texas | KNOX |  | 13 | 2002209 | SPN:0925-17-006-TRANSPORTATION ENHANCEMENT | Transportation Enhancements | 04/25/2010 |  |  | 76705.92 | 0.1
9681 | Texas | HALL |  | 13 | 2002754 | SPN:0925-09-021-REPLACE EXISTING BRIDGE FACILITY : CR P @ DRAW | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 248320.15 | 0.066
9682 | Texas | BEXAR | SAN ANTONIO | 20 | 2004424 | SPN:0915-12-418-EXPAND STREET TO 4 LANE | New Construction | 04/14/2010 |  |  | 11192666.69 | 1.4
9683 | Texas | BELL |  | 31 | 2005351 | SPN:0015-06-077-ADD NORTHBOUND FRONTAGE ROAD TO REDUCE CONGESTION AND ENHANCE SAFETY : AT LAMPASAS RIVER (NB FR) . | New Bridge Construction | 06/10/2010 |  |  | 181853.65 | 0.94
9684 | Texas | FORT BEND | HOUSTON | 14 | 2005833 | SPN:0912-34-117-REPLACE BRIDGE AND APPROACHES : MULLINS REYNOLDS AT BESSIES CREEK | Bridge Replacement | 10/16/2009 | 09/09/2009 |  | 493945.57 | 0.057
9685 | Texas | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2005982 | SPN:0921-02-133-WIDEN TO 4 LANES : ON SUGAR ROAD FROM SIOUX ROAD OWASSA ROAD | Pavement Widening | 05/17/2010 | 06/07/2010 |  | 3528788.67 | 2
9686 | Texas | SMITH |  | 01 | 2005996 | SPN:3487-01-004-CONSTRUCT 2 LNS CONTROLLED ACCESS TOLL ROAD ON NEW LOCATION (ULTIMATE 4-LANE FACILITY) (TOLL) : .11 M N OF SH 31(2 M E OF FM 2661)S | New Construction | 07/21/2009 | 08/06/2009 | 08/01/2013 | 29872772.08 | 6.569
9687 | Texas | TOM GREEN |  | 11 | 2006045 | SPN:0907-24-028-REFURBISH HISTORIC CS BRIDGE TO PEDESTRIAN/BIKE PATH BRIDGE : ON AVENUE K AT SOUTH CONCHO RIVER . | Transportation Enhancements | 06/04/2010 | 06/22/2010 |  | 1399601.86 | 0.355
9688 | Texas | GALVESTON | GALVESTON | 22 | 2006063 | SPN:0912-73-114-REPLACE BRIDGE : MCKAY ROAD AT DRAINAGE DITCH | Bridge Replacement | 05/28/2009 | 06/29/2009 | 11/01/2009 | 313362.02 | 0.065
9689 | Texas | STARR |  | 28 | 2006304 | SPN:0921-26-015-REHABILITATION OF PAVEMENT, CURB & GUTTER, STORM SEWER, AND RESTRIPE TO ONE WAY PAIR : US 83 N ON AVASOLO ST. | Pavement Improvement | 08/10/2009 | 10/20/2009 | 02/01/2011 | 1371513.37 | 0.678
9690 | Texas | RANDALL |  | 13 | 2006439 | SPN:0904-11-022-WIDEN TO A 4 LANE ARTERIAL : ON GEORGIA STREET, FROM SW 58TH AVE | Pavement Widening | 11/02/2009 | 01/25/2010 |  | 1940000 | 0.681
9691 | Texas | COLLIN | DALLAS-FORT WORTH | 03 | 2006470 | SPN:0091-05-055-INTERSECTION IMPROVEMENTS | Pavement Improvement | 09/16/2009 | 09/28/2009 | 02/01/2010 | 1034202.48 | 0.001
9692 | Texas | HARTLEY |  | 13 | 2007003 | SPN:0041-01-038-REHAB EXISTING ROADWAY (NBL) : DALHART SOUTH CITY LIMITS | Pavement Improvement | 06/29/2009 | 07/20/2009 | 01/01/2010 | 3815533.36 | 13.647
9693 | Texas | BURLESON |  | 10 | 2007109 | SPN:0186-03-057-OVERLAY CONSISTING OF A ONE COURSE SURFACE TREATMENT, AN HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : BRUSHY CREEK | Pavement Improvement | 06/29/2009 | 09/01/2009 | 03/01/2010 | 1921016.47 | 6.001
9694 | Texas | DALLAS | DALLAS-FORT WORTH | 30 | 2007383 | SPN:0196-07-027-CONSTRUCTION OF DECK AND PLAZA OVER FREEWAY WOODALL RODGERS DECK PLAZA : WEST OF SAINT PAUL | Transportation Enhancements | 09/22/2009 | 10/19/2009 | 06/01/2009 | 16700000 | 0.25
9695 | Texas | VAL VERDE |  | 23 | 2007565 | SPN:0922-11-027-FOR THE CONSTRUCTION OF A HIKE & BIKE TRAIL FACILITY PHASE II : BRIDGE ST | Transportation Enhancements | 10/06/2009 | 11/02/2009 |  | 64558.22 | 0.225
9696 | Texas | COMAL |  | 21 | 2007704 | SPN:0857-01-025-WIDEN NARROW ROADWAY TO ADD SHOULDERS AND PASSING LANES : FM 484 | Pavement Improvement | 07/10/2009 | 08/06/2009 | 01/01/2010 | 668050.28 | 0.863
9697 | Texas | ELLIS | DALLAS-FORT WORTH | 06 | 2007710 | SPN:0918-22-119-REPLACE BRIDGE AND APPROACHES : NORTH WARD ST AT HOUSTON CREEK | Bridge Replacement | 09/22/2009 | 10/22/2009 | 05/01/2010 | 229500 | 0.071
9698 | Texas | HARRIS |  | 10 | 2007822 | SPN:3050-03-012-CONSTRUCT RAILROAD-HIGHWAY GRADE SEPARATION : 0.307 MILES NORTH OF UPRR | New Bridge Construction | 10/14/2009 | 10/19/2009 |  | 6871970.66 | 0.777
9699 | Texas | HARRIS | HOUSTON | 29 | 2007854 | SPN:3256-03-072-TURN RADIUS IMPROVEMENTS AT VARIOUS LOCATIONS : AT VISTA,SPENCER,PASADENA BLVD_& | Pavement Improvement | 11/02/2009 | 12/14/2009 |  | 2349189.33 | 0.36
9700 | Texas | HIDALGO | MCALLEN-PHARR-EDINBURG | 15, 28 | 2008119 | SPN:0921-02-139-RECONSTRUCTION AND WIDENING OF MILE 2 NORTH ROAD : ON MI 2 N FROM SH 107 (CONWAY AVE.) TAYLOR ROAD | Pavement Widening | 01/04/2010 | 02/09/2010 |  | 4940668.63 | 3
9701 | Texas | HALL |  | 13 | 2008245 | SPN:0925-09-025-REPLACEMENT OF EXISTING BRIDGE FACILITY : CR C TRIBUTARY DRY SALT CREEK | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 279174.3 | 0.18
9702 | Texas | HALL |  | 13 | 2008246 | SPN:0925-09-028-REPLACE EXIST BRIDGE FACILITY : CR I @ DRAW CREEK | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 218989 | 0.063
9703 | Texas | TAYLOR |  | 19 | 2008341 | SPN:0908-33-079-REPLACE BRIDGE AND APPROACHES : ON CR 344 | Bridge Replacement | 06/22/2009 | 07/10/2009 | 01/01/2011 | 78347.06 | 0.051
9704 | Texas | TAYLOR |  | 19 | 2008348 | SPN:0908-33-075-REPLACE BRIDGE & APPROACHES : ON CR 173 (PSN 1) | Bridge Replacement | 06/22/2009 | 07/10/2009 | 01/01/2011 | 128146.2 | 0.042
9705 | Texas | TAYLOR |  | 19 | 2008350 | SPN:0908-33-077-REPLACE BRIDGE & APPROACHES : ON CR 345 (PSN 1) | Bridge Replacement | 06/22/2009 | 07/10/2009 | 01/01/2011 | 99350.34 | 0.044
9706 | Texas | TAYLOR |  | 19 | 2008351 | SPN:0908-33-078-REPLACE BRIDGE AND APPROACHES : ON CR 344 | Bridge Replacement | 06/22/2009 | 07/10/2009 | 01/01/2011 | 185772.3 | 0.068
9707 | Texas | CHILDRESS |  | 13 | 2008530 | SPN:0925-08-017-REPLACEMENT OF EXISTING BRIDGE FACILITY : CR 25 @ DRAW | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 134256 | 0.085
9708 | Texas | HALL |  | 13 | 2008532 | SPN:0925-09-027-REPLACE EXIST BRIDGE FACILITY : CR CC @ KENT CREEK | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 173523.7 | 0.227
9709 | Texas | ELLIS |  | 06 | 2008536 | SPN:0918-22-112-REPLACE BRIDGE AND APPROACHES : FRANKS ROAD AT RICHLAND CREEK | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 525000 | 0.074
9710 | Texas | ELLIS |  | 06 | 2008537 | SPN:0918-22-114-REPLACE BRIDGE AND APPROACHES : PLUTO RD. AT MILL CREEK | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 181000 | 0.65
9711 | Texas | ELLIS |  | 06 | 2008538 | SPN:0918-22-116-REPLACE BRIDGE : MORGAN RD AT HOG CREEK TRIB | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 208990.25 | 0.001
9712 | Texas | ELLIS |  | 06 | 2008539 | SPN:0918-22-117-REPLACE BRIDGE AND APPROACHES : SCHIELD ROAD AT ELM BRANCH | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 262000 | 0.001
9713 | Texas | ELLIS |  | 06 | 2008540 | SPN:0918-22-118-REPLACE BRIDGE AND APPROACHES : PECAN TREE ROAD AT BIG ONION CREEK | Bridge Replacement | 08/26/2009 | 09/11/2009 | 05/01/2010 | 214992.25 | 0.001
9714 | Texas | JEFFERSON | PORT ARTHUR | 02 | 2008658 | SPN:0306-03-118-RAISE ROADWAY ELEVATION : 0.96 MI W OF RAINBOW BRIDGE | Pavement Improvement | 11/02/2009 |  |  | 408556.79 | 0.321
9715 | Texas | HALL |  | 13 | 2008721 | SPN:0925-09-026-REPLACEMENT OF EXISTING BRIDGE FACILITY : CR 7 @TURKEY CREEK | Bridge Replacement | 06/22/2009 | 07/08/2009 | 07/01/2010 | 169359.15 | 0.065
9716 | Texas | MILLS |  | 11 | 2009012 | SPN:0054-09-030-SCARIFY AND RESHAPE BASE, NEW BASE, STRUCTURES, & SURFACING : US 183, EAST ; SPN:0055-01-025-SCARIFY AND RESHAPE BASE, NEW BASE, STRUCTURES, AND SURFACING : LOOP 15, EAST | Pavement Widening | 07/10/2009 | 08/07/2009 | 10/01/2011 | 4605444.97 | 9.848
9717 | Texas | TAYLOR |  | 19 | 2009054 | SPN:0733-03-032-REPLACE BRIDGE & APPROACHES : ON FM 126 (PSN 13) | Bridge Replacement | 07/06/2009 | 08/17/2009 | 03/01/2010 | 622795.2 | 0.112
9718 | Texas | TAYLOR | ABILENE | 19 | 2009056 | SPN:0181-01-056-MODIFY CROSS SECTION & ADD SIGNAL : JUDGE ELY BLVD IN ABILENE LP 322 | Pavement Improvement | 02/01/2010 | 02/17/2010 |  | 1583739.95 | 1.15
9719 | Texas | RUNNELS |  | 11 | 2009096 | SPN:0907-13-008-CONSTRUCT RAIL BRIDGE : SOUTH ORIENT RAILROAD AT COLORADO RIVER IN BALLINGER | New Construction | 03/12/2010 | 03/30/2010 |  | 2734944.78 | 1
9720 | Texas | LUBBOCK |  | 19 | 2009104 | SPN:0783-02-064-WIDEN FREEWAY TO 6 MAIN LANES AND NEW OVERPASS : 200`EAST OF FM 2528 (FRANKFORD AVE) | Pavement Widening | 07/21/2009 | 08/06/2009 | 01/01/2011 | 16518640.06 | 2.281
9721 | Texas | FREESTONE |  | 06 | 2009153 | SPN:0456-03-015-RESTORATION OF EXISTING ROAD CONSISTING OF GRADING, STRUCTURES, BASE, SURFACE AND PAVEMENT MARKINGS AND MARKERS : SH 75 ; SPN:0612-03-012-RESTORE EXISTING ROAD CONSISTING OF GRADING, F | Pavement Improvement | 06/12/2009 | 06/26/2009 | 07/01/2010 | 2957146.49 | 17.333
9722 | Texas | ZAVALA |  | 23 | 2009237 | SPN:0037-03-071-FOR THE CONSTRUCTION OF SEALCOAT TYPE WORK : 2.33 MI S. OF FM 1025 0.32 MI N OF FM 1433; SPN:0037-05-041-FOR THE CONSTRUCTION OF SEALCOAT TYPE WORK : ZAVALA/DIMMIT CO.LINE SH 85; SPN | Pavement Improvement | 11/18/2009 | 04/15/2010 |  | 2400948.66 | 49.048
9723 | Texas | FORT BEND | HOUSTON | 22 | 2009377 | SPN:0192-01-085-RECONFIGURE AND UPGRADE TRAFFIC SIGNAL SYSTEM AT INTERSECTION (RCTSS) : AT GLENN LAKES BLVD ; SPN:1257-01-044-RECONFIGURE AND UPGRADE TRAFFIC SIGNAL SYSTEM AT INTERSECTION (RCTSS) : AT | Safety/Traffic Management | 02/19/2010 | 03/15/2010 |  | 1319211.99 | 0
9724 | Texas | OCHILTREE |  | 13 | 2009455 | SPN:0030-02-041-REHAB EXISTING RDWY : PERRYTON | Pavement Improvement | 06/12/2009 | 06/17/2009 | 09/01/2009 | 1362796.41 | 7.761
9725 | Texas | ARMSTRONG |  | 13 | 2009456 | SPN:0042-03-038-REHAB EXISTING ROADWAY : CARSON COUNTY LINE | Pavement Improvement | 06/12/2009 | 07/13/2009 | 02/01/2010 | 8895225.05 | 8.646
9726 | Texas | RANDALL |  | 13 | 2009457 | SPN:0168-09-154-OVERLAY : POTTER COUNTY LINE | Pavement Improvement | 06/04/2009 | 06/09/2009 | 11/01/2010 | 1325113.17 | 2.608
9727 | Texas | HARDEMAN |  | 13 | 2009459 | SPN:0043-02-067-MILL & HOTMIX OVERLAY : CHILDRESS C/L, SE | Pavement Improvement | 06/22/2009 | 08/04/2009 | 10/01/2009 | 1256628.27 | 9.924
9728 | Texas | HALL, CHILDRESS |  | 13 | 2009460 | SPN:0704-01-018-REHABILITATION OF EXISTING ROADWAY : HALL C/L ; SPN:0704-03-012-REHABILITATION OF EXISTING ROADWAY : 1.818 MI N OF COTTLE C/L, NE | Pavement Improvement | 06/09/2009 | 06/25/2009 | 07/01/2010 | 3563720.58 | 6.97
9729 | Texas | BREWSTER |  | 23 | 2009461 | SPN:0020-11-046-MILL AND INLAY : MOSLEY LANE | Pavement Improvement | 06/23/2009 | 08/03/2009 | 10/01/2009 | 1956262.54 | 7.921
9730 | Texas | EL PASO |  | 16 | 2009462 | SPN:2326-01-020-OVERLAY, MILL AND INLAY : FM 3255 | Pavement Improvement | 05/07/2009 | 06/03/2009 | 09/01/2009 | 592762.81 | 2.938
9731 | Texas | EL PASO |  | 23 | 2009463 | SPN:1281-01-016-OVERLAY : INT OF FM 76 AND FM 1110 | Pavement Improvement | 05/19/2009 | 06/04/2009 | 09/01/2009 | 299899.9 | 1.2
9732 | Texas | EL PASO |  | 16 | 2009464 | SPN:2552-04-039-MILL AND INLAY AND BRIDGE DECK REPAIR : US 54/LP 375 | Pavement Improvement | 05/06/2009 | 05/30/2009 | 10/01/2009 | 1325044.9 | 1.74
9733 | Texas | CASTRO |  | 19 | 2009465 | SPN:1291-01-012-REHABILITATION OF EXISTING ROAD : SH 86 ; SPN:1291-08-005-REHABILITATION OF EXISTING ROAD : FM 2397 ; SPN:3133-02-002-REHABILITATION OF EXISTING ROAD RAISE LAKEFILLS : DEAF SMITH COU | Pavement Improvement | 06/02/2009 | 08/20/2009 | 03/01/2011 | 7681000 | 15.607
9734 | Texas | HALE, FLOYD |  | 19 | 2009466 | SPN:2125-01-011-OVERLAY : FM 400 ; SPN:2125-02-007-OVERLAY : HALE COUNTY LINE | Pavement Improvement | 06/05/2009 | 07/24/2009 | 03/01/2010 | 2416888.83 | 10.23
9735 | Texas | SWISHER, HALE, LUBBOCK |  | 19 | 2009467 | SPN:0905-06-077-IH 27 PAVEMENT REPAIR FY 2009 BACKLOG PROJECT; PLACEHOLDER CSJ : IH 27, CITY OF LUBBOCK ; SPN:0905-12-037-IH 27 PAVEMENT REPAIR FY 2009 BACKLOG PROJECT; PLACEHOLDER CSJ : IH 27, LUBB | Pavement Improvement | 05/19/2009 | 06/15/2009 | 07/01/2010 | 6219330.21 | 90.304
9736 | Texas | MARTIN |  | 11 | 2009468 | SPN:0494-02-023-PAVEMENT STRUCTURE RESTORATION : 7 MI SOUTH OF DAWSON CO.LINE | Pavement Improvement | 06/05/2009 | 09/16/2009 | 11/01/2009 | 1435027.95 | 7
9737 | Texas | PECOS |  | 23 | 2009469 | SPN:0866-06-018-PAVEMENT STRUCTURE RESTORATION : SPUR 194 | Pavement Improvement | 06/16/2009 | 08/27/2009 | 11/01/2009 | 1498725.45 | 17.914
9738 | Texas | ANDREWS |  | 11 | 2009470 | SPN:0548-01-036-ROADWAY REHABILITATION : US 385 ; SPN:0548-05-041-ROADWAY REHABILITATION : 1.0 MILE WEST OF US 385 | Pavement Improvement | 06/29/2009 | 07/14/2009 | 03/01/2010 | 4077150.57 | 1.535
9739 | Texas | IRION |  | 11 | 2009471 | SPN:0077-04-028-RESTORATION OF EXISTING ROADWAY : 10.219 MI. S. OF THE TOM GREEN C/L ; SPN:0077-05-027-RESTORATION OF EXISTING ROADWAY : 6.30 MILE SOUTH TOM GREEN CNTY LINE | Pavement Improvement | 06/22/2009 | 07/13/2009 | 10/01/2009 | 2253797.36 | 6.758
9740 | Texas | MENARD, EDWARDS |  | 23 | 2009472 | SPN:0235-02-043-CONSTRUCT BRIDGE AND APPROACHES : AT LITTLE HACKBERRY CREEK ; SPN:1296-01-016-CONSTRUCT BRIDGE AND APPROACHES : AT SAN SABA RIVER | Pavement Improvement | 06/18/2009 | 07/27/2009 | 09/01/2011 | 2489936.82 | 1.541
9741 | Texas | TRAVIS |  | 21 | 2009473 | SPN:1378-01-033-SEAL & THIN OVERLAY : LAGO VISTA CITY LIMITS | Pavement Improvement | 06/22/2009 | 07/08/2009 | 11/01/2009 | 3300717.11 | 7.962
9742 | Texas | TRAVIS |  | 10, 21 | 2009474 | SPN:3136-01-165-MILL, SEAL, & OVERLAY FRONTAGE ROADS : DUVAL ST | Pavement Improvement | 06/04/2009 | 08/25/2009 | 11/01/2009 | 2330028.81 | 9.857
9743 | Texas | WILLIAMSON |  | 31 | 2009475 | SPN:0204-01-060-FULL DEPTH REPAIR & OVERLAY : IH 35 NBFR | Pavement Improvement | 06/08/2009 | 06/24/2009 | 09/01/2009 | 1345917.68 | 1.704
9744 | Texas | HAYS |  | 25 | 2009478 | SPN:2293-01-021-SEAL & THIN OVERLAY : CENTERPOINT RD | Pavement Improvement | 06/12/2009 | 07/06/2009 | 08/01/2009 | 236568.43 | 2.197
9745 | Texas | LLANO |  | 11 | 2009479 | SPN:0700-04-037-MILL, SEAL & OVERLAY : SH 16 | Pavement Improvement | 06/09/2009 | 07/15/2009 | 08/01/2009 | 290581.6 | 1.815
9746 | Texas | KAUFMAN |  | 05 | 2009480 | SPN:0751-04-001-UPGRADE EXISTING COUNTY ROAD : FM 1392, 1.0 MI SW OF SH 205, SE | Pavement Improvement | 07/14/2009 | 01/04/2010 | 06/01/2011 | 2705889.55 | 2.249
9747 | Texas | BEXAR | SAN ANTONIO | 21, 23 | 2009484 | SPN:0253-04-140-SIGNALS OPERATIONAL IMPROVEMENTS AND RECONFIGURE INTERSECTIONS | Pavement Improvement | 03/15/2010 |  |  | 5256791.85 | 3.409
9748 | Texas | TARRANT | STATEWIDE | 12 | 2009485 | SPN:0504-02-022-CONSTRUCT NEW INTERCHANGE WITH IH 20/SH 183 FOR SH 121 TOLLROAD : SOUTH OF ARBORLAWN DRIVE SOUTH OF OVERTON RIDGE BLVD | New Construction | 02/01/2010 | 03/15/2010 |  | 116646468.88 | 0.1
9749 | Texas | NUECES | CORPUS CHRISTI | 27 | 2009486 | SPN:0916-35-156-RESURFACE & RECONSTRUCT ROADWAY | Pavement Improvement | 01/18/2009 |  |  | 6130478.97 | 9.537
9750 | Texas | HAYS |  | 25 | 2009487 | SPN:0366-01-065-OVERLAY : EBONY STREET | Pavement Improvement | 06/29/2009 | 07/15/2009 | 07/01/2009 | 292810.93 | 1.172
9751 | Texas | BLANCO |  | 21 | 2009488 | SPN:0253-01-047-MILL, SEAL & THIN OVERLAY : S OF US 290 | Pavement Improvement | 06/16/2009 | 08/24/2009 | 08/01/2009 | 610452.84 | 2.377
9752 | Texas | TRAVIS | AUSTIN | 10, 25 | 2009489 | SPN:0114-02-090-CONSTRUCT 4 DIRECT CONNECTORS | New Bridge Construction | 04/27/2010 | 04/27/2010 |  | 59477545.77 | 0.5
9753 | Texas | JIM WELLS |  | 15 | 2009490 | SPN:0255-01-068-OVERLAY ROADWAY : FM 1352 | Pavement Improvement | 06/09/2009 | 07/20/2009 |  | 650000 | 2.154
9754 | Texas | KLEBERG, JIM WELLS |  | 15 | 2009491 | SPN:0383-03-022-REHAB. EXISTING ROADWAY : KLEBERG CO. LINE ; SPN:0383-04-054-REHAB. EXISTING ROADWAY : JIM WELLS CO. LINE | Pavement Improvement | 06/29/2009 | 08/20/2009 |  | 3060294.94 | 12.62
9755 | Texas | SAN PATRICIO |  | 15 | 2009492 | SPN:0371-07-006-MILL, SEAL AND OVERLAY : US 181 ; SPN:0372-03-006-MILL, SEAL AND OVERLAY : US 181 | Pavement Improvement | 06/22/2009 | 07/29/2009 |  | 796264.02 | 3.778
9756 | Texas | SAN PATRICIO |  | 15 | 2009493 | SPN:0507-01-017-REHAB AND WIDEN ROADWAY : IH 37 | Pavement Improvement | 06/16/2009 | 06/23/2009 | 10/01/2009 | 1222413.27 | 5.737
9757 | Texas | REFUGIO |  | 15 | 2009494 | SPN:0371-02-066-MILL AND OVERLAY__(NORTH BOUND LANES ONLY) : 6 MI N. OF REFUGIO ; SPN:0371-03-109-MILL AND OVERLAY_(NORTH BOUND LANES ONLY) : N. OF REFUGIO N. CITY LIMITS | Pavement Improvement | 06/29/2009 | 08/03/2009 |  | 1997509.74 | 8.515
9758 | Texas | SAN PATRICIO |  | 15 | 2009495 | SPN:0371-05-016-REHAB AND WIDEN ROADWAY : COUNTY ROAD 82D | Pavement Improvement | 06/16/2009 | 07/02/2009 |  | 760634.69 | 3.267
9759 | Texas | BEE |  | 15 | 2009496 | SPN:0100-07-045-UNDERSEAL AND OVERLAY : KARNES COUNTY LINE ; SPN:0100-08-086-UNDERSEAL AND OVERLAY : O.76 MI. S. OF FM 1465 | Pavement Improvement | 06/16/2009 | 08/12/2009 |  | 2643872.33 | 10.983
9760 | Texas | DUVAL |  | 25 | 2009497 | SPN:0086-10-043-REHABILITATION OF AN EXISTING ROADWAY : SOUTH END OF SAN DIEGO CREEK BRIDGE | Pavement Improvement | 06/16/2009 | 07/02/2009 | 09/01/2009 | 729799.75 | 0.792
9761 | Texas | VAL VERDE |  | 23 | 2009498 | SPN:0022-08-022-REHABILITATION OF AN EXISTING ROADWAY : 4.44 MI SOUTH OF SH 163 | Pavement Improvement | 06/08/2009 | 10/27/2009 | 11/01/2009 | 1863200.78 | 4.023
9762 | Texas | MAVERICK |  | 23 | 2009499 | SPN:0299-03-047-REHABILITATION OF AN EXISTING ROADWAY : 2.899 MI NORTH OF FM 1664 | Pavement Improvement | 06/22/2009 | 07/13/2009 | 12/01/2009 | 2829391.92 | 5.928
9763 | Texas | MAVERICK |  | 23 | 2009500 | SPN:2636-01-007-RESTORATION OF AN EXISTING HIGHWAY : DIMMIT COUNTY LINE | Pavement Improvement | 06/04/2009 | 07/06/2009 | 03/01/2010 | 2325707.47 | 12.303
9764 | Texas | HIDALGO |  | 15, 28 | 2009502 | SPN:0342-01-078-FULL DEPTH REPAIR BOTH LANES : FM 2128 | Pavement Improvement | 06/22/2009 | 07/13/2009 | 12/01/2009 | 2143338.79 | 3.7
9765 | Texas | STARR |  | 28 | 2009504 | SPN:0039-01-073-OVERLAY : FM 1430 ; SPN:0039-02-061-OVERLAY : FM 2221 ; SPN:0342-01-079-OVERLAY : FM 2128 ; SPN:0433-02-048-OVERLAY : KING ST ; SPN:0433-04-021-OVERLAY : BUSINESS 77 ; SPN:0517-07 | Pavement Improvement | 06/22/2009 | 07/15/2009 | 12/01/2009 | 6758353.23 | 34.57
9766 | Texas | ORANGE |  | 08 | 2009507 | SPN:0028-11-195-RECONSTRUCT EXISTING 4-LANE FREEWAY FACILITY (PHASE 1 OF FUTURE EXPANSION TO 6 LANES) : SH 62, EAST UP RR; SPN:0028-14-105-RECONSTRUCT EXISTING 4-LANE FREEWAY FACILITY (PHASE 1 OF FUTU | Pavement Improvement | 04/22/2010 | 05/17/2010 |  | 32000000 | 2.433
9767 | Texas | KERR |  | 21 | 2009508 | SPN:0193-01-035-REPLACE BRIDGE AND APPROACHES : AT LYNX HAVEN CROSSING | New Bridge Construction | 06/09/2009 | 07/08/2009 | 03/01/2010 | 1048332.35 | 0.154
9768 | Texas | KERR |  | 21 | 2009509 | SPN:0829-04-029-REPLACE BRIDGE AND APPROACHES : AT MAYHUGH CROSSING | New Bridge Construction | 06/09/2009 | 08/14/2009 | 01/01/2010 | 518704.16 | 0.085
9769 | Texas | KERR |  | 21 | 2009510 | SPN:0855-05-009-REMOVE & REPLACE GUADALUPE RVR BRIDGE & RECONST APPROACHES : 0.1 MILE W. OF GUADALUPE RIVER | Pavement Improvement | 06/09/2009 | 07/27/2009 | 11/01/2009 | 827437.76 | 0.169
9770 | Texas | UVALDE |  | 23 | 2009511 | SPN:0369-03-027-REHAB EXISTING ROADWAY & ADD SHOULDERS : 0.2 MI SOUTH OF US 90 IN SABINAL | Pavement Improvement | 07/06/2009 | 07/29/2009 | 08/01/2010 | 3703743.51 | 11.42
9771 | Texas | MEDINA |  | 23 | 2009512 | SPN:0848-01-030-WIDEN NARROW ROADWAY & ADD SHOULDERS : FM 1250 | Pavement Improvement | 06/18/2009 | 07/20/2009 | 05/01/2010 | 1844944.89 | 4.716
9772 | Texas | TARRANT | DALLAS-FORT WORTH | 24 | 2009513 | SPN:0353-03-059-RECONSTRUCT FREEWAY, FRONTAGE ROADS AND RAMPS; SPN:0353-03-079-CONSTRUCT SEPARATE FREEWAY (MANAGED FACILITY); SPN:0364-01-113-RECONST FREEWAY 4 TO 6 LANES | Pavement Widening | 10/26/2009 | 10/26/2009 | 03/01/2014 | 250000000 | 10.452
9773 | Texas | HARRIS | HOUSTON | 18 | 2009514 | SPN:0271-07-301-RECONSTRUCT ROADWAY : IH 45 NORTH ; SPN:0508-01-329-RECONSTRUCT ROADWAY : WHITE OAK BAYOU BRIDGE | Pavement Improvement | 10/16/2009 | 11/01/2009 |  | 18038764.02 | 2.346
9774 | Texas | MEDINA |  | 23 | 2009515 | SPN:0017-05-073-CONSTRUCT NB EXIT RAMP AT CR 770 : 0.2 MI S OF CR 770 ; SPN:0017-05-074-RELOCATE EXISTING NB ENTRANCE RAMP : ON NBFR FROM SH 173, N ; SPN:0017-05-088-CONSTRUCTION NEW SB FRONTAGE ROA | Pavement Widening | 06/09/2009 | 09/01/2009 | 05/01/2010 | 2259919.03 | 2.022
9775 | Texas | COMAL |  | 21 | 2009516 | SPN:3106-01-012-WIDEN NARROW ROADWAY TO ADD SHOULDERS AND PASSING LANES : US 281 | Pavement Improvement | 06/08/2009 | 06/29/2009 | 11/01/2011 | 5146936.2 | 5.255
9776 | Texas | FRIO |  | 28 | 2009517 | SPN:0748-04-036-INSTALL CURB INLETS & STORM SEWER SYSTEM : TREVINO ST. | Pavement Improvement | 06/16/2009 | 07/20/2009 | 01/01/2010 | 656092.55 | 0.568
9777 | Texas | HARRIS |  | 18, 29 | 2009519 | SPN:0271-14-223-RECONSTRUCT ROADWAY : EAST OF ELLA | Pavement Improvement | 09/01/2009 | 09/16/2009 | 02/01/2012 | 28655986.56 | 2.91
9778 | Texas | GRAYSON | SHERMAN-DENISON | 04 | 2009520 | SPN:0666-01-022-WIDEN EXISTING HIGHWAY TO INCLUDE TURN LANES, TURN BAYS AND RAISED MEDIANS : 1,520` WEST OF US 75 C/L | Pavement Improvement | 08/26/2009 | 09/21/2009 | 11/01/2010 | 3000000 | 0.758
9779 | Texas | WHARTON |  | 14 | 2009521 | SPN:0027-04-039-SEAL COAT, ACP & SET : 3.3 MI E OF LISSIE | Pavement Improvement | 06/16/2009 | 07/20/2009 | 11/01/2009 | 3184624.51 | 7.157
9780 | Texas | AUSTIN |  | 10 | 2009522 | SPN:1258-01-021-GRADING, BASE, SURFACING : SH 36 | Pavement Improvement | 06/02/2009 | 06/22/2009 | 12/01/2009 | 2540876.78 | 3.755
9781 | Texas | COLORADO, DE WITT, VICTORIA |  | 14 | 2009523 | SPN:0088-06-003-ASPHALTIC CONCRETE PAVEMENT : GUADALUPE RIVER BRIDGE IN VICTORIA ; SPN:0270-01-047-ASPHALTIC CONCRETE PAVEMENT : SH 119 ; SPN:0270-02-038-ASPHALTIC CONCRETE PAVEMENT : FM 2980 ; SPN | Pavement Improvement | 06/16/2009 | 07/15/2009 | 09/01/2009 | 2844587.62 | 7.31
9782 | Texas | MATAGORDA |  | 14 | 2009524 | SPN:0847-01-013-REHABILITATE ROADWAY : FM 457 | Pavement Improvement | 06/23/2009 | 07/14/2009 | 11/01/2009 | 1856668.17 | 3.153
9783 | Texas | FAYETTE |  | 25 | 2009525 | SPN:0211-06-053-PAVEMENT REPAIR AND ACP SURFACING : ROITSCH STREET ; SPN:0268-01-052-PAVEMENT REPAIR AND ACP SURFACING : BS 71-E | Pavement Improvement | 06/22/2009 | 07/20/2009 | 08/01/2009 | 789505.41 | 1.672
9784 | Texas | HARDIN |  | 08 | 2009526 | SPN:0811-01-010-RESTORE EXISTING ROADWAY : US 69, EAST | Pavement Improvement | 06/12/2009 | 06/22/2009 | 09/01/2009 | 619326.17 | 3.807
9785 | Texas | JASPER |  | 08 | 2009527 | SPN:0784-03-014-PROVIDE ADDITIONAL PAVED SURFACE WIDTH : FM 105, SOUTH | Pavement Improvement | 06/22/2009 | 07/24/2009 | 11/01/2009 | 2569366.36 | 7.479
9786 | Texas | TYLER |  | 08 | 2009528 | SPN:0200-07-049-OVERLAY EXISTING ROADWAY : US 190 IN WOODVILLE, SOUTH ; SPN:0213-06-039-OVERLAY EXISTING ROADWAY : 3.9 MI W OF US 69 | Pavement Improvement | 06/02/2009 | 07/16/2009 | 09/01/2009 | 2393603.28 | 5.141
9787 | Texas | JEFFERSON |  | 02 | 2009529 | SPN:0508-04-154-OVERLAY EXISTING ROADWAY AND BASE REPAIRS : CHAMBERS COUNTY LINE | Pavement Improvement | 06/16/2009 | 07/22/2009 | 12/01/2009 | 4097310.61 | 18.993
9788 | Texas | CHAMBERS |  | 02 | 2009530 | SPN:0508-03-090-SPOT LEVEL UP & OVERLAY : 0.278 MI W OF FM 1406, EAST ; SPN:0739-01-044-SPOT LEVEL UP & OVERLAY : SH 73, EAST ; SPN:0762-02-044-OVERLAY EXISTING ROADWAY : US 90, SOUTH | Pavement Improvement | 06/02/2009 | 06/29/2009 | 09/01/2009 | 782288.36 | 3.718
9789 | Texas | BELL |  | 31 | 2009531 | SPN:0015-06-071-RECONSTRUCT AND WIDEN FROM FOUR TO SIX LANES TO REDUCE CONGESTION AND ENHANCE SAFETY : AMITY ROAD US 190; SPN:0015-06-078-INSTALL OVERHEAD DYNAMIC MESSAGE SIGNS TO MAKE FREEWAY OPERATI | Pavement Widening | 06/10/2010 |  |  | 102371100.59 | 6.969
9790 | Texas | HARDIN |  | 08 | 2009532 | SPN:0784-01-043-OVERLAY EXISTING ROADWAY : FM 92 IN SILSBEE, EAST | Pavement Improvement | 06/02/2009 | 06/22/2009 | 09/01/2009 | 352932.9 | 1.688
9791 | Texas | NEWTON |  | 08 | 2009533 | SPN:0304-08-012-UPGRADE BRIDGE RAIL : AT LITTLE COW CREEK ; SPN:0304-09-004-UPGRADE BRIDGE RAIL : AT TWO MILE BRANCH ; SPN:0627-02-017-UPGRADE BRIDGE RAIL : AT LITTLE COW CREEK, DRAW & WHITMAN ; SP | Safety/Traffic Management | 05/19/2009 | 07/07/2009 | 12/01/2010 | 1043652 | 2.402
9792 | Texas | ORANGE |  | 08 | 2009534 | SPN:0784-05-034-MILL & OVERLAY EXISTING ROADWAY, SEAL COAT : SH 12, EAST | Pavement Improvement | 06/03/2009 | 07/06/2009 | 09/01/2009 | 519724.35 | 1.657
9793 | Texas | BRAZOS |  | 17 | 2009535 | SPN:0116-04-096-OVERLAY CONSISTING OF A SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : FM 2818 ; SPN:0117-01-043-REHABILITATE EXISTING ROAD CONSISTING OF SPOT REPAIRS, SURFACE TREA | Pavement Improvement | 06/02/2009 | 07/17/2009 | 02/01/2010 | 672160.99 | 1.587
9794 | Texas | BRAZOS |  | 17 | 2009536 | SPN:0506-01-093-OVERLAY CONSISTING OF SPOT REPAIRS, SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : FM 2818 ; SPN:0506-01-094-OVERLAY CONSISTING OF A ONE COURSE SURFACE TREATMENT, H | Pavement Improvement | 05/19/2009 | 06/12/2009 | 01/01/2010 | 878657.3 | 2.462
9795 | Texas | BRAZOS |  | 17 | 2009537 | SPN:1316-01-053-OVERLAY CONSISTING OF A SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : 0.1 MILE EAST OF FM 158 | Pavement Improvement | 05/19/2009 | 06/03/2009 | 12/01/2009 | 298091.9 | 1
9796 | Texas | LEON |  | 06 | 2009538 | SPN:0675-03-068-OVERLAY CONSISTING OF CONCRETE PAVEMENT REPAIR, A ONE COURSE SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS : KEECHI CREEK | Pavement Improvement | 06/04/2009 | 08/17/2009 | 03/01/2010 | 6623247.22 | 7.269
9797 | Texas | HOWARD |  | 19 | 2009539 | SPN:0005-05-101-FLEXIBLE PAVEMENT REPAIR & ACP OVERLAY : MARTIN COUNTY LINE | Pavement Improvement | 05/28/2009 | 06/29/2009 | 12/01/2009 | 4997459.67 | 10.284
9798 | Texas | MORRIS |  | 04 | 2009540 | SPN:0222-03-056-WIDEN TO ADD SHOULDERS AND RESURFACE 4-LANE DIVIDED RURAL HIGHWAY : 0.7 MI. E. OF US 259 | Pavement Improvement | 05/28/2009 | 07/01/2009 | 10/01/2009 | 991156.2 | 2.021
9799 | Texas | BRAZORIA |  | 14 | 2009541 | SPN:0178-03-138-ONE-COURSE SURFACE TREATMENT, ASPHALT CONCRETE PAVEMENT OVERLAY, LOOP DETECTORS AND PAVEMENT MARKERINGS : SOUTH OF SH 35 BYPASS | Pavement Improvement | 06/08/2009 | 07/06/2009 | 11/01/2009 | 3047898.69 | 16.01
9800 | Texas | HARRIS |  | 22, 29 | 2009542 | SPN:0502-01-203-FULL DEPTH CONCRETE REPAIR AND REPAIR OF SPALLING IN CONCRETE PAVEMENT : SHELL OVERPASS | Pavement Improvement | 06/29/2009 | 07/30/2009 | 11/01/2009 | 882735.48 | 4.397
9801 | Texas | FORT BEND |  | 22 | 2009543 | SPN:3223-01-009-BASE REPAIR AND OVERLAY : US 90A | Pavement Improvement | 06/05/2009 | 06/23/2009 | 11/01/2009 | 188597.81 | 1.021
9802 | Texas | MONTGOMERY |  | 08 | 2009544 | SPN:0912-37-200-FAULT LINE BASE REPAIRS : VARIOUS LOCATIONS ON IH 45, LP 336 | Pavement Improvement | 06/02/2009 | 06/18/2009 | 11/01/2009 | 426244.36 | 0.001
9803 | Texas | FORT BEND |  | 22 | 2009545 | SPN:0188-01-036-REPLACE ASPHALT WITH CONCRETE : US 90A | Pavement Improvement | 06/05/2009 | 07/30/2009 | 11/01/2009 | 1269484.81 | 0.369
9804 | Texas | GALVESTON |  | 14 | 2009546 | "SPN:0389-11-057-BASE REPAIRS, MILLING & 1.5"" ASPHALT OVERLAY : FM 1765 " | Pavement Improvement | 06/05/2009 | 07/13/2009 | 11/01/2009 | 646223.04 | 1.77
9805 | Texas | BRAZORIA |  | 14 | 2009547 | SPN:1004-02-014-ASPHALT OVERLAY AND PAVEMENT MARKINGS : FM1301 ; SPN:1413-01-016-ASPHALT OVERLAY AND PAVEMENT MARKINGS : SH 35 | Pavement Improvement | 06/02/2009 | 07/21/2009 | 11/01/2009 | 1360458.79 | 11.799
9806 | Texas | FORT BEND |  | 14, 22 | 2009548 | SPN:0027-06-055-BASE REPAIR AND OVERLAY : WHARTON COUNTY LINE | Pavement Improvement | 06/04/2009 | 07/23/2009 | 11/01/2009 | 1118221.98 | 9.741
9807 | Texas | MONTGOMERY |  | 08 | 2009549 | SPN:0177-14-026-WIDEN SUBGRADE, OCST AND ACP OVERLAY : US 59 | Pavement Improvement | 06/02/2009 | 06/18/2009 | 07/01/2010 | 4317263.89 | 8.022
9808 | Texas | FORT BEND |  | 14 | 2009550 | SPN:1258-02-031-BASE REPAIR AND OVERLAY : FM 1489 | Pavement Improvement | 05/27/2009 | 06/17/2009 | 11/01/2009 | 820473.22 | 4.704
9809 | Texas | WALLER |  | 10 | 2009551 | SPN:0523-02-030-ADD SHOULDERS AND ACP OVERLAY : BU US 290 | Pavement Improvement | 06/02/2009 | 11/16/2009 | 12/01/2009 | 961664.41 | 0.971
9810 | Texas | HARRIS |  | 10 | 2009552 | SPN:3050-03-016-GRADING, LIME TREATED SUBGRADE, CEMENT TREATED BASE, ASPHALTIC OVERLAY AND PAVMENT MARKINGS : 0.140 MI N. OF HUFSMITH KUYKENDAHL | Pavement Improvement | 06/12/2009 | 06/28/2009 | 11/01/2009 | 366817.39 | 0.369
9811 | Texas | HARRIS |  | 07 | 2009553 | SPN:0050-08-088-CRACK & SPALL REPAIR, FULL DEPTH CONCRETE REPAIR (IN SECTIONS) : SH 6 | Pavement Improvement | 06/04/2009 | 06/24/2009 | 11/01/2009 | 118220 | 3.845
9812 | Texas | HARRIS |  | 07, 09 | 2009554 | "SPN:1258-04-058-2"" PLANING, 2"" ACP OVERLAY, PAVEMENT MARKINGS : DAIRY ASHFORD " | Pavement Improvement | 06/05/2009 | 08/17/2009 | 11/01/2009 | 4459705.68 | 8.923
9813 | Texas | WALLER |  | 10 | 2009555 | SPN:0527-02-015-SUBGRADE WIDENING, SEAL COAT, ACP O/L AND PAVEMENT MARKINGS : FM 359 | Pavement Improvement | 06/08/2009 | 09/01/2009 | 11/01/2009 | 2035566.78 | 7.292
9814 | Texas | GALVESTON |  | 14 | 2009556 | SPN:0367-02-073-RAISE, REHABILITATE AND OVERLAY (TO 5 YR. STORM ELEVATION) : INTERSECTION AT SH 124 ; SPN:0367-03-035-REHABILITATE AND OVERLAY (TO 5 YR. STORM ELEVATION) : CRYSTAL BEACH ; SPN:0367-0 | Pavement Improvement | 06/02/2009 | 06/18/2009 | 12/01/2009 | 6167954.73 | 21.338
9815 | Texas | HARRIS |  | 02 | 2009557 | SPN:0028-02-087-MILL, SEAL COAT, BASE REPAIR AND ACP OVERLAY : W OF KRENEK | Pavement Improvement | 06/08/2009 | 07/06/2009 | 11/01/2009 | 1241291.35 | 2.072
9816 | Texas | FORT BEND |  | 22 | 2009558 | SPN:0111-03-054-BASE REPAIR AND OVERLAY : SH 6 | Pavement Improvement | 06/05/2009 | 07/08/2009 | 11/01/2009 | 653888.42 | 4.807
9817 | Texas | WALLER |  | 10 | 2009559 | "SPN:0523-02-041-SEAL COAT AND 1.5"" OVERLAY, PAVEMENT MARKINGS : 0.5 MI N. OF CLAPP RD " | Pavement Improvement | 06/04/2009 | 06/22/2009 | 11/01/2009 | 614106.5 | 3.492
9818 | Texas | NACOGDOCHES |  | 01 | 2009560 | SPN:0138-06-039-RESURFACE WITH POROUS FRICTION COURSE : RUSK COUNTY LINE | Pavement Improvement | 06/02/2009 | 07/21/2009 | 09/01/2009 | 3217445.02 | 6.327
9819 | Texas | BURLESON |  | 17 | 2009561 | SPN:0648-03-046-WIDEN TO 4 LANE DIVIDED HIGHWAY : FM 50 | Pavement Widening | 06/16/2009 | 06/27/2009 | 01/01/2011 | 7505830.38 | 2.752
9820 | Texas | SHELBY |  | 01 | 2009562 | SPN:0743-02-022-RECONSTRUCT AND WIDEN EXISTING PAVEMENT : NACOGDOCHES CO LINE | Pavement Improvement | 06/18/2009 | 07/27/2009 | 06/01/2010 | 1199983.65 | 5.457
9821 | Texas | SHELBY |  | 01 | 2009563 | SPN:0175-02-080-REHAB EXISTING PAVEMENT : TENAHA CITY LIMITS | Pavement Improvement | 06/12/2009 | 08/25/2009 | 08/01/2010 | 4664748.68 | 9.375
9822 | Texas | HOUSTON |  | 05 | 2009564 | SPN:0937-03-015-RECONSTRUCT AND WIDEN EXISTING PAVEMENT : SH 21 | Pavement Improvement | 06/17/2009 | 06/26/2009 | 08/01/2010 | 2691341.91 | 11.173
9823 | Texas | MORRIS, TITUS |  | 04 | 2009565 | SPN:0222-01-046-OVERLAY 4-LANE RURAL HIGHWAY WITH ASPHALTIC CONCRETE : 1.6 MI WEST OF FM 2348 ; SPN:0222-02-051-OVERLAY 4-LANE RURAL HIGHWAY WITH ASPHALTIC CONCRETE : TITUS COUNTY LINE | Pavement Improvement | 07/09/2009 | 07/22/2009 | 11/01/2009 | 4699268.05 | 7.4
9824 | Texas | PANOLA |  | 01 | 2009566 | SPN:0247-02-043-WIDEN TO ADD SHOULDERS AND RESURFACE 4-LANE RURAL HIGHWAY : 0.1 MI. S. OF MILL CREEK | Pavement Improvement | 06/12/2009 | 06/30/2009 | 10/01/2009 | 2384758.4 | 3.187
9825 | Texas | CASS |  | 01, 04 | 2009568 | SPN:0569-01-048-WIDEN TO ADD SHOULDERS AND RESURFACE 2-LANE RURAL HIGHWAY : SOUTH OF FM 2328 | Pavement Improvement | 06/05/2009 | 07/24/2009 | 06/01/2010 | 886614.14 | 3.024
9826 | Texas | CASS |  | 04 | 2009569 | SPN:0277-03-024-WIDEN TO ADD SHOULDERS AND RESURFACE 2-LANE RURAL HIGHWAY : SH 8 IN DOUGLASSVILLE ; SPN:0277-03-025-WIDEN TO ADD SHOULDERS AND RESURFACE 2-LANE RURAL HIGHWAY : FM 96 | Pavement Improvement | 05/22/2009 | 06/15/2009 | 07/01/2010 | 2023245.06 | 11.305
9827 | Texas | BROWN |  | 11 | 2009570 | SPN:0054-06-090-MILL AND OVERLAY : 0.5 MI. W OF FM 3254 | Pavement Improvement | 06/05/2009 | 08/05/2009 | 10/01/2009 | 1562249.76 | 3.055
9828 | Texas | NAVARRO |  | 24 | 2009571 | SPN:0997-01-038-OV-ASPHALTIC CONCRETE PAVEMENT, OVERLAY, RESTORE PAVEMENT STRUCTURE AND UPGRADE DRAINAGE : FM 744 ; SPN:1289-01-028-OV-ASPHALTIC CONCRETE PAVEMENT, OVERLAY, RESTORE PAVEMENT STRUCTURE | Pavement Improvement | 06/22/2009 | 07/08/2009 | 12/01/2010 | 7287236.14 | 14.329
9829 | Texas | LEON |  | 06 | 2009572 | SPN:0426-03-037-RESTORE EXISTING ROAD CONSISTING OF GRADING, FLEXIBLE BASE, SURFACE AND PAVEMENT MARKINGS AND MARKERS : 2.5 MILES NORTH OF SH 7 | Pavement Improvement | 07/06/2009 | 08/17/2009 | 04/01/2010 | 369716.71 | 2.534
9830 | Texas | HOPKINS |  | 04 | 2009575 | SPN:0083-02-046-REHAB WITH SHOULDERS : 0.47 MI EAST OF FM 2653 S | Pavement Improvement | 08/21/2009 | 08/31/2009 | 06/01/2011 | 4160215 | 3.447
9831 | Texas | GRAYSON |  | 04 | 2009576 | SPN:0510-01-022-REHABILITATE EXISTING ROADWAY : SH 289 | Pavement Improvement | 05/28/2009 | 06/30/2009 | 06/01/2010 | 1876832.4 | 5.895
9832 | Texas | LAMAR |  | 04 | 2009577 | SPN:0680-01-012-REHAB EXIST ROAD : 3.38 MILES N OF FM 1497 | Pavement Improvement | 05/28/2009 | 05/28/2009 | 05/01/2010 | 896178.3 | 3.38
9833 | Texas | GRAYSON |  | 04 | 2009578 | SPN:0729-01-034-REHABILITATE EXISTING ROADWAY : US 377 | Pavement Improvement | 06/02/2009 | 06/16/2009 | 11/01/2010 | 3701118.28 | 11.354
9834 | Texas | LAMAR |  | 04 | 2009579 | SPN:1320-01-021-REHAB EXIST ROAD : FM 1497 NORTH | Pavement Improvement | 06/02/2009 | 06/04/2009 | 09/01/2011 | 2447477.14 | 10.32
9835 | Texas | GREGG |  | 01 | 2009580 | SPN:0096-06-071-PLANE & RESURFACE ROADWAY : SP 63/SH 31 IN LONGVIEW, E | Pavement Improvement | 06/05/2009 | 06/22/2009 | 11/01/2009 | 1712304.61 | 2.874
9836 | Texas | ANDERSON |  | 05 | 2009581 | SPN:0123-01-034-ADD SHOULDERS & RESURFACE ROADWAY : 3 MI E OF FM 3266, E OF P`STINE, E | Pavement Improvement | 06/02/2009 | 06/26/2009 | 11/01/2010 | 4110707.46 | 5.602
9837 | Texas | WOOD |  | 05 | 2009582 | SPN:0190-03-076-PLANE & RESURFACE ROADWAY : FM 564(N) IN MINEOLA, S ; SPN:0190-03-077-PLANE & RESURFACE ROADWAY : US 69/SH 37 SPLIT IN MINEOLA, S | Pavement Improvement | 05/22/2009 | 06/17/2009 | 11/01/2009 | 1637663.52 | 2.377
9838 | Texas | SMITH |  | 01 | 2009583 | SPN:0190-05-058-RESURFACE ROADWAY : 0.134 MI N OF IH 20 IN LINDALE, S | Pavement Improvement | 06/02/2009 | 07/20/2009 | 11/01/2009 | 2236906.91 | 7.045
9839 | Texas | GREGG |  | 01 | 2009584 | SPN:0393-01-088-PLANE & RESURFACE ROADWAY : IH 20 N FRONTAGE RD, N | Pavement Improvement | 05/19/2009 | 06/16/2009 | 10/01/2009 | 2066492.08 | 3.62
9840 | Texas | VAN ZANDT |  | 05 | 2009586 | SPN:0522-02-028-CONCRETE SURFACE REPAIR OF BRIDGE STRUCTURES : AT CANEY CRK, CANEY CREEK RELIEF | Pavement Improvement | 06/16/2009 | 07/06/2009 | 10/01/2009 | 61344 | 0.133
9841 | Texas | BELL |  | 31 | 2009588 | SPN:0015-05-043-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : FM 93 (6TH AVE) IN BELTON, SOUTH ; SPN:0398-04-067-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : 13TH ST IN BELTON, SOUTH | Pavement Improvement | 06/04/2009 | 06/22/2009 | 09/01/2009 | 1287407.66 | 1.607
9842 | Texas | CORYELL |  | 31 | 2009589 | SPN:0055-03-023-REHABILITATE ROADWAY, ADD PASSING LANES AND SHOULDERS : FM 932 | Pavement Improvement | 06/18/2009 | 06/24/2009 | 06/01/2011 | 8735023.01 | 10.235
9843 | Texas | CORYELL |  | 31 | 2009590 | SPN:0231-02-050-CONSTRUCT OVERPASS FOR FT HOOD ACCESS : @ RAILHEAD RD | New Bridge Construction | 08/10/2009 | 08/24/2009 | 04/01/2010 | 2368151.52 | 2.642
9844 | Texas | BELL |  | 31 | 2009591 | SPN:3534-02-002-ADD TURN LANES, TRAFFIC SIGNAL AND LIGHTING FOR IMPROVED ACCESS TO WEST FT HOOD : @ MOHAWK DRIVE IN KILLEEN | Pavement Improvement | 06/09/2009 | 06/23/2009 | 04/01/2010 | 1220438.55 | 0.8
9845 | Texas | WILBARGER |  | 13 | 2009592 | SPN:0043-07-104-SEAL COAT AND HMAC OVERLAY : NEAR US 70 IN OKLAUNION | Pavement Improvement | 06/09/2009 | 08/19/2009 | 12/01/2009 | 2590420.9 | 7.273
9846 | Texas | ARCHER |  | 19 | 2009593 | SPN:0137-05-028-EXTEND CULVERTS AND ADD SHOULDERS : FM 368 | Pavement Improvement | 06/09/2009 | 08/12/2009 | 10/01/2010 | 3147193.46 | 9.364
9847 | Texas | COOKE |  | 26 | 2009594 | SPN:0194-02-088-HEAVY HOT MIX OVERLAY : NEAR RED RIVER | Pavement Improvement | 06/05/2009 | 08/12/2009 | 11/01/2009 | 2396645.99 | 5.765
9848 | Texas | COOKE |  | 13, 26 | 2009595 | SPN:1855-01-021-ADD SHOULDERS : FM 372 | Pavement Improvement | 06/22/2009 | 07/14/2009 | 12/01/2010 | 2108363.87 | 8.579
9849 | Texas | RUSK |  | 01 | 2009596 | SPN:0138-02-034-PLANE & RESURFACE ROADWAY : US/BU 259 SPLIT, S OF KILGORE, S | Pavement Improvement | 05/22/2009 | 06/10/2009 | 11/01/2009 | 2886918.15 | 5.1
9850 | Texas | TRAVIS |  | 21, 25 | 2009597 | SPN:3136-01-162-MILL, SEAL & THIN OVERLAY : COLORADO RIVER | Pavement Improvement | 06/12/2009 | 07/28/2009 | 10/01/2009 | 1696542.45 | 2.818
9851 | Texas | TRAVIS |  | 25 | 2009598 | SPN:3136-01-166-MILL, SEAL, AND OVERLAY : GAINES CREEK | Pavement Improvement | 06/16/2009 | 07/06/2009 | 10/01/2009 | 943846.86 | 2
9852 | Texas | DENTON |  | 24 | 2009599 | SPN:0918-46-217-REPLACE BRIDGE AND APPROACHES : ON FREEMAN RD | Pavement Improvement | 07/02/2009 | 08/26/2009 | 05/01/2010 | 203297 | 0.001
9853 | Texas | DALLAS | DALLAS-FORT WORTH | 24, 30 | 2009600 | SPN:1047-02-044-INTERSECTION APPROACH WIDENING, SIGNAL UPGRADES AND TURN LANES AT STRAUS ROAD : AT STRAUS RD ; SPN:1047-03-062-INTERSECTION APPROACH WIDENING, SIGNAL UPGRADES AND TURN LANES AT STRAUS | Pavement Improvement | 05/28/2009 | 06/22/2009 | 10/01/2009 | 1388408.1 | 0.167
9854 | Texas | KAUFMAN |  | 24 | 2009601 | SPN:1091-01-016-REPLACE BRIDGE AND APPROACHES : BUFFALO CREEK ; SPN:1091-01-018-REPLACE BRIDGE AND APPROACHES : BUFFALO CREEK RELIEF | Pavement Improvement | 09/28/2009 | 02/16/2010 | 11/01/2010 | 2856520.65 | 0.323
9855 | Texas | KAUFMAN |  | 24 | 2009602 | SPN:1397-01-021-REPLACE BRIDGE AND APPROACHES : AT BIG COTTONWOOD CREEK ; SPN:1397-01-022-REPLACE BRIDGE AND APPROACHES : AT LITTLE COTTONWOOD CREEK | Pavement Improvement | 06/29/2009 | 09/11/2009 | 06/01/2010 | 1708659.34 | 0.402
9856 | Texas | PARKER |  | 12 | 2009603 | SPN:0008-03-096-2 INCH OVERLAY : SPUR 312 | Pavement Improvement | 06/05/2009 | 08/03/2009 | 11/01/2009 | 3460812.46 | 7.517
9857 | Texas | TARRANT |  | 12 | 2009604 | "SPN:0008-14-110-PAVEMENT AND BRIDGE JOINT REPAIR WITH 2"" HMAC OVERLAY : MARINE CREEK PARKWAY " | Pavement Improvement | 05/22/2009 | 06/15/2009 | 12/01/2009 | 3967559.84 | 4.983
9858 | Texas | WISE |  | 12 | 2009605 | SPN:0013-08-117-PLANE AND TEXTURIZE CRCP NORTHBOUND LANES : 1355` S OF CR 4840 ; SPN:0013-08-118-PLANE AND TEXTURIZE CRCP NORTHBOUND : NBL 1300` S OF CR 4421 ; SPN:0013-08-120-MILL ASPHALT, CONCRETE | Pavement Improvement | 06/12/2009 | 07/06/2009 | 11/01/2009 | 1846266.94 | 9.526
9859 | Texas | ERATH, HOOD, JOHNSON |  | 17 | 2009606 | "SPN:0080-03-050-MILL 2"" AND HMAC OVERLAY : BRAZOS RIVER BRIDGE ; SPN:0080-05-027-MILL 2"" AND HMAC OVERLAY : PARKER COUNTY LINE ; SPN:0250-07-014-MILL AND HMAC OVERLAY : BU 377J ; SPN:0365-02-028 | Pavement Improvement | 06/09/2009 | 07/27/2009 | 10/01/2009 | 1658039.41 | 7.483
9860 | Texas | JOHNSON |  | 17 | 2009607 | SPN:0259-04-036-PAVEMENT REPAIR AND OVERLAY : APPROX. 120 FT WEST OF FM 2331 ; SPN:0422-03-070-PAVEMENT REPAIR AND HOTMIX OVERLAY : PR 21 | Pavement Improvement | 05/22/2009 | 06/15/2009 | 10/01/2009 | 503662.32 | 2.314
9861 | Texas | WISE |  | 12 | 2009608 | SPN:0352-01-054-MILL AND HMAC OVERLAY : 0.33 MILE SOUTH OF US 380 INTERSECT | Pavement Improvement | 06/16/2009 | 08/17/2009 | 10/01/2009 | 553102.84 | 1.208
9862 | Texas | TARRANT |  | 26 | 2009609 | "SPN:0363-01-133-PAVEMENT REPAIR, 2"" MILLING, AND 2"" HMAC OVERLAY WITH PAVEMENT MARKINGS : NEAR FM 1938 " | Pavement Improvement | 06/02/2009 | 07/01/2009 | 11/01/2009 | 513264.2 | 3.22
9863 | Texas | PARKER |  | 12 | 2009610 | SPN:0365-01-042-MILL 1.5 INCH, FABRIC, HMAC OVERLAY AND TRAFFIC SIGNAL LOOPS : US 180 | Pavement Improvement | 06/04/2009 | 06/15/2009 | 09/01/2009 | 591312.34 | 1.2
9864 | Texas | JOHNSON |  | 17 | 2009611 | SPN:0019-01-135-HMAC OVERLAY : WILLINGHAM STREET ; SPN:0019-02-030-HMAC OVERLAY : AT&SF RAILROAD ; SPN:0519-01-026-HMAC OVERLAY : NORTH OF RIO VISTA | Pavement Improvement | 06/09/2009 | 07/28/2009 | 11/01/2009 | 1833526.78 | 8.631
9865 | Texas | TARRANT |  | 06 | 2009613 | SPN:0747-03-076-REPAIR FAILURES AND OVERLAY WITH 2 INCHES : COPELAND ROAD | Pavement Improvement | 06/05/2009 | 07/01/2009 | 09/01/2009 | 420119.98 | 1.393
9866 | Texas | TARRANT |  | 12, 24, 26 | 2009614 | SPN:0902-48-745-VARIOUS LOCATIONS FOR EXPANSION JOINT REPAIRS IN NORTH TARRANT COUNTY : VARIOUS LOCATIONS | Pavement Improvement | 06/05/2009 | 06/28/2009 | 02/01/2010 | 1065751 | 0.1
9867 | Texas | PARKER |  | 12 | 2009615 | SPN:3516-01-014-REHAB EXISTING ROADWAY WITH PAVEMENT REPAIRS AND OVERLAY : FM 1886 | Pavement Improvement | 10/30/2009 | 03/29/2010 |  | 587643.05 | 3.143
9868 | Texas | CHAMBERS |  | 14 | 2009622 | SPN:0242-03-068-OVERLAY EXISTING ROADWAY & SEAL COAT : LIBERTY CO/L, SOUTH | Pavement Improvement | 05/28/2009 | 06/23/2009 | 09/01/2009 | 715086.04 | 4.39
9869 | Texas | ELLIS |  | 24 | 2009623 | SPN:1048-02-031-REPLACE BRIDGE AND APPROACHES : AT TRIBUTARY OF BEAR CREEK . | Bridge Replacement | 05/03/2010 | 05/03/2010 |  | 320650 | 0.09
9870 | Texas | GUADALUPE |  | 28 | 2009624 | SPN:0535-01-065-RESTORE EXISTING ROADWAY WITH CRCP : 0.44 MI W OF SH 46 | Pavement Improvement | 09/18/2009 | 10/04/2009 | 09/01/2011 | 1784603.23 | 0.55
9871 | Texas | MATAGORDA |  | 14 | 2009625 | SPN:0179-04-089-ASPHALTIC CONCRETE PAVEMENT : SOUTH OF FM 457 | Pavement Improvement | 06/04/2009 | 07/10/2009 | 08/01/2009 | 567067.43 | 1.895
9872 | Texas | WHARTON |  | 14 | 2009626 | SPN:2819-02-009-PAVEMENT REPAIR AND ACP SURFACING : 0.14 MI. SOUTHWEST OF SH 71 | Pavement Improvement | 06/12/2009 | 07/06/2009 | 09/01/2009 | 745789.63 | 2.402
9873 | Texas | ELLIS |  | 06 | 2009627 | SPN:0092-10-007-REHABILITATE EXISTING ROADWAY : DALLAS COUNTY LINE | Pavement Improvement | 08/07/2009 | 08/28/2009 | 10/01/2010 | 1284123.14 | 2.285
9874 | Texas | MASON |  | 11 | 2009632 | SPN:0149-04-015-SEAL COAT : US 87 ; SPN:0396-02-024-SEAL COAT : MENARD C/L | Pavement Improvement | 07/02/2009 | 06/22/2009 | 09/01/2009 | 1045214.63 | 27.578
9875 | Texas | WISE |  | 12 | 2009633 | SPN:0013-08-114-3 INCH OVERLAY AND CONCRETE TEXTURE SOUTHBOUND LANES : SBL FROM 475` S OF US 380 | Pavement Improvement | 06/16/2009 | 08/24/2009 | 10/01/2009 | 1309578.7 | 12.75
9876 | Texas | BURNET |  | 11 | 2009634 | SPN:2206-01-013-OVERLAY : 11.7 MI N OF SH 29 | Pavement Improvement | 06/22/2009 | 06/29/2009 | 10/01/2009 | 1444444 | 9.444
9877 | Texas | CALDWELL |  | 25 | 2009635 | SPN:0286-02-028-PAVEMENT REPAIR,MILL,SEAL & OVERLAY : 0.35 MILES WEST OF HAYS C/L | Pavement Improvement | 07/06/2009 | 08/10/2009 | 10/01/2009 | 3794304.93 | 11.695
9878 | Texas | WISE |  | 12 | 2009636 | SPN:0013-08-116-MILL ASPHALT, CONCRETE REPAIRS, OVERLAY 2 INCHES : 2750` N OF PIONEER ROAD | Pavement Improvement | 06/16/2009 | 08/24/2009 | 10/01/2009 | 732136.28 | 3.289
9879 | Texas | WILSON |  | 28 | 2009637 | SPN:0215-11-020-WIDEN EXISTING ROADWAY TO ADD SHOULDERS : UNION AT CR 448 GONZALES COUNTY LINE | Pavement Improvement | 04/22/2010 | 04/22/2010 |  | 1576833.88 | 4.955
9880 | Texas | ATASCOSA |  | 28 | 2009638 | SPN:0517-01-040-WIDEN EXISTING ROADWAY TO PROVIDE PASSING LANES : 0.3 S OF FM 1332 | Pavement Improvement | 10/13/2009 | 10/26/2009 |  | 1849585.53 | 17.779
9881 | Texas | HENDERSON |  | 05 | 2009639 | SPN:0163-04-053-PLANE & RESURFACE ROADWAY : 1.2 MI E OF SH 198 IN MALAKOFF, E | Pavement Improvement | 06/02/2009 | 06/25/2009 | 10/01/2009 | 2119884.1 | 4.944
9882 | Texas | LEE |  | 10 | 2009640 | SPN:3114-01-010-LEVEL-UP & SEAL COAT : US 290 | Pavement Improvement | 06/22/2009 | 07/27/2009 | 09/01/2009 | 519810.19 | 13.155
9883 | Texas | LIVE OAK |  | 15 | 2009646 | SPN:0542-06-041-CONSTRUCT FOUR LANE BOULEVARD : US 281 ; SPN:0542-07-008-CONSTRUCT 4 LANE BOULEVARD : BU 59 INTERSECTION ; SPN:0542-07-012-CONSTRUCT RAILROAD GRADE SEPARATION STRUCTURE AND APPROACHE | Pavement Widening | 10/21/2009 | 01/04/2010 |  | 17155044.24 | 3.953
9884 | Texas | JIM WELLS |  | 15 | 2009647 | SPN:0255-01-074-CONSTRUCT DIAMOND INTERCHANGE : 0.95 MI. N. OF FM 2508 | Pavement Widening | 09/14/2009 | 11/16/2009 | 12/01/2011 | 13000000 | 1.84
9885 | Texas | WICHITA |  | 13 | 2009648 | "SPN:0156-14-027-""ULTRA THIN BONDED HOT MIX WEARING COURSE (UTBHMWC)"" : LP 11 " | Pavement Improvement | 08/04/2009 | 08/26/2009 | 10/01/2009 | 788364.75 | 1.706
9886 | Texas | HAYS |  | 25 | 2009650 | SPN:0016-02-104-REPLACE BRIDGE AND APPROACHES & WIDEN FRONTAGE ROADS : 2250 FT N OF MAIN ST | Pavement Improvement | 10/09/2009 | 11/02/2009 |  | 7000000 | 0.777
9887 | Texas | WEBB |  | 28 | 2009651 | SPN:0086-16-002-FOR THE CONSTRUCTION OF A NEW LOCATION 4 LANE DIVIDED ROADWAY : 4.8 MILES SOUTH OF SH 359 ; SPN:0086-16-003-FOR THE CONSTRUCTION OF A NEW LOCATION 4 LANE DIVIDED ROADWAY : 1.0 MILES SO | New Construction | 10/16/2009 | 11/16/2009 |  | 21758949 | 4.701
9888 | Texas | WEBB |  | 28 | 2009652 | SPN:0086-16-001-FOR THE CONSTRUCTION OF A NEW LOCATION 2 LANE ROADWAY : MANGANA-HEIN ROAD | New Construction | 10/16/2009 | 11/16/2009 |  | 9660310.81 | 2.267
9889 | Texas | BEXAR | SAN ANTONIO | 21 | 2009653 | SPN:0253-04-139-US 281 Fr. AT LP 1604 To. . ; EXPAND INTERCHANGE WITH SOUTHERN DIRECT CONN'S (PHASE 1) | Pavement Improvement | 05/24/2010 |  |  | 80000000 | 1.61
9890 | Texas | BEXAR | SAN ANTONIO | 21 | 2009655 | SPN:2452-03-103-EXPAND FROM 2 LANES TO 4 LANE DIVIDED : FM 78 GRAYTOWN ROAD | Pavement Widening | 04/11/2010 | 04/12/2010 |  | 6631042.98 | 0.001
9891 | Texas | BRAZOS |  | 17 | 2009657 | SPN:0050-02-082-CONSTRUCT NEW INTERCHANGE CONSISTING OF GRADING, STRUCTURES, BASE AND SURFACE - FUNDING CSJ FOR 0050-02-094 : AT BARRON ROAD | Pavement Improvement | 06/29/2009 | 07/17/2009 | 03/01/2011 | 7907149.79 | 1.676
9892 | Texas | HARRIS |  | 02, 18, 29 | 2009658 | SPN:3256-02-074-CONSTRUCT 4 DIRECT CONNECTORS : AT US 59 NORTH | New Bridge Construction | 10/06/2009 | 10/15/2009 |  | 29595089.52 | 1.624
9893 | Texas | CAMERON | MCALLEN-PHARR-EDINBURG | 27 | 2009662 | SPN:0684-01-066-CONSTRUCT TOLLED MAINLANES AND FRONTAGE ACCESS : 0.70 MI N OF FM 3248 OLD PORT ISABEL RD; SPN:3622-01-001-CONSTRUCT TOLLED MAINLANES AND FRONTAGE ACCESS : OLD PORT ISABEL RD, ON NEW | New Construction | 05/13/2010 |  |  | 34161741.4 | 3.926
9894 | Texas | BROOKS |  | 15 | 2009663 | SPN:0255-03-026-CONSTRUCT 4 LANE EXPRESSWAY_WITH TOLLED MAIN LANES : BUS 281 NORTH SIDE ; SPN:0255-04-072-CONSTRUCT 4 LANE EXPRESSWAY_WITH TOLLED MAIN LANES : 0.9 MILES SOUTH OF FM 3066 | Pavement Widening | 07/14/2009 | 08/18/2009 | 08/01/2012 | 40039527.42 | 5.581
9895 | Texas | BROOKS |  | 15 | 2009664 | SPN:0255-14-001-CONSTRUCT 4 LANE EXPRESSWAY WITH TOLLED MAIN LANES : BUS 281 NORTH SIDE | Pavement Widening | 07/14/2009 | 08/18/2009 | 08/01/2012 | 25860723.89 | 2.062
9896 | Texas | RUNNELS, TOM GREEN, COLEMAN |  | 11 | 2009665 | SPN:7107-09-001-REHABILITATION OF SOUTH ORIENT RR; SPN:7107-10-001-REHABILITATION OF SOUTH ORIENT RR; SPN:7123-11-001-REHABILITATION OF SOUTH ORIENT RR | Other | 09/01/2009 | 09/15/2009 | 12/01/2010 | 5078194.05 | 0.003
9897 | Texas | SMITH |  | 01 | 2009679 | SPN:3487-01-013-INSTALL ELECTRONIC TOLL GANTRIES AND EQUIPMENT FOR NEW 2-LN TOLL ROAD (ULTIMATE 4-LANE FACILITY) : SH 31,2.0 MI E OF FM 2661,S & SE ; SPN:3487-02-010-INSTALL ELECTRONIC TOLL GANTRIES A | Other | 07/21/2009 | 08/06/2009 | 08/01/2013 | 3876000 | 9.019
9898 | Texas | CAMERON |  | 27 | 2009682 | SPN:1425-04-020-WIDEN TO 4 LANE DIVIDED : 1.06 MILES S. OF US 77/83 | Pavement Widening | 08/10/2009 | 03/08/2010 | 06/01/2010 | 1887239.52 | 0.8
9899 | Texas | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2009689 | "SPN:0921-02-132-WIDEN TO 4 LANES : ON ""I"" ROAD FROM US 281 SOUTH " | Pavement Widening | 09/17/2009 | 10/13/2009 | 03/01/2011 | 4071711.18 | 1.761
9900 | Texas | BOWIE | TEXARKANA (TX-AR) | 04 | 2009691 | SPN:2879-02-010-INSTALL NEW TRAFFIC SIGNALS : AT ROBIN LANE IN TEXARKANA . | Safety/Traffic Management | 01/25/2010 | 06/09/2010 |  | 31344.75 | 0.001
9901 | Texas | BOWIE | TEXARKANA (TX-AR) | 04 | 2009692 | SPN:2879-02-011-INSTALL NEW TRAFFIC SIGNALS : AT COOKS LANE IN TEXARKANA . | Safety/Traffic Management | 01/25/2010 | 06/09/2010 |  | 31642.95 | 0.001
9902 | Texas | BOWIE | TEXARKANA (TX-AR) | 04 | 2009693 | SPN:2879-02-012-UPGRADE EXISTING TRAFFIC SIGNALS : AT COWHORN CREEK ROAD IN TEXARKANA . | Safety/Traffic Management | 01/25/2010 | 06/09/2010 |  | 59415.1 | 0.001
9903 | Texas | BOWIE | TEXARKANA (TX-AR) | 04 | 2009694 | SPN:0046-06-073-UPGRADE EXISTING TRAFFIC SIGNALS : AT 14TH STREET IN TEXARKANA . | Safety/Traffic Management | 01/25/2010 | 06/09/2010 |  | 84165.2 | 0.001
9904 | Texas | BOWIE | TEXARKANA (TX-AR) | 04 | 2009695 | SPN:0046-08-014-UPGRADE EXISTING TRAFFIC SIGNALS : AT COLLEGE DRIVE IN TEXARKANA . | Safety/Traffic Management | 01/25/2010 | 06/09/2010 |  | 85770 | 0.001
9905 | Texas | SHELBY |  | 01 | 2009696 | SPN:0064-01-064-RESURFACE WITH HOT MIX ASPHALT : JACKSON STREET ; SPN:0109-11-003-RESURFACE WITH HOT MIX ASPHALT : US 287 (N) ; SPN:0118-09-008-RESURFACE WITH HOT MIX ASPHALT : SH 21 ; SPN:0176-06- | Pavement Improvement | 07/28/2009 | 10/06/2009 | 09/04/2009 | 1612585.31 | 6.619
9906 | Texas | BRAZORIA | HOUSTON | 14 | 2009697 | SPN:2523-02-030-WIDEN TO 4 LANE DIVIDED SUBURBAN SECTION : SH 288 ; SPN:2523-02-058-CONSTRUCT RAILROAD-HIGHWAY GRADE SEPARATION : AT CR 288 AND UPRR | Pavement Widening | 09/01/2009 | 10/15/2009 | 10/01/2010 | 18452982.51 | 3.092
9907 | Texas | HARRIS | HOUSTON | 09 | 2009699 | SPN:0598-01-089-FRONTAGE ROAD INTERSECTION IMPROVEMENTS (TSM) : AT BW 8 | Pavement Improvement | 10/06/2009 | 10/27/2009 |  | 635655.19 | 0.603
9908 | Texas | WALLER | HOUSTON | 10 | 2009700 | SPN:0523-01-015-WIDEN TO 4-LANE DIVIDED URBAN SECTION : BU 290 | Pavement Widening | 09/09/2009 | 10/19/2009 | 10/01/2010 | 2485857.89 | 0.551
9909 | Texas | FORT BEND | HOUSTON | 22 | 2009701 | SPN:0543-02-047-RECONSTRUCT 2 LANES TO 4 LANES : W OF FARMER ROAD US 90A | Pavement Widening | 04/01/2010 | 04/19/2010 |  | 11849354.25 | 2.37
9910 | Texas | FORT BEND | HOUSTON | 22 | 2009703 | SPN:1415-02-040-WIDEN 2 LANES TO 4 LANES DIVIDED : SHILOH LAKES DR SH 99 | Pavement Widening | 04/14/2010 | 06/14/2010 |  | 13235602 | 2.63
9911 | Texas | GALVESTON | HOUSTON | 14 | 2009704 | SPN:1607-01-029-CONSTRUCT GRADE SEPARATION : AT WILLOW STREET EXTENSION | Pavement Improvement | 01/04/2010 | 01/25/2010 |  | 10399818.18 | 1.061
9912 | Texas | HARRIS | HOUSTON | 02 | 2009705 | SPN:0912-00-396-GULF COAST FREIGHT RAIL DISTRICT (GCFRD) COMMUTER RAIL STUDY | Other | 03/02/2010 | 03/08/2010 |  | 2000000 | 0.001
9913 | Texas | HARRIS | HOUSTON | 02 | 2009706 | SPN:0912-00-397-REAL-TIME HWY PERFORMANCE MONITORING : VARIOUS LOCATIONS DISTRICTWIDE . | Safety/Traffic Management | 05/13/2010 |  |  | 4073749 | 0.001
9914 | Texas | TAYLOR |  | 19 | 2009708 | SPN:0908-33-086-RECONSTRUCT EXIST ROADWAY | Pavement Improvement | 04/15/2010 |  |  | 583112.33 | 1.008
9915 | Texas | TAYLOR |  | 19 | 2009709 | SPN:0908-33-087-REHAB SURFACE | Pavement Improvement | 04/15/2010 |  |  | 394585.85 | 1.913
9916 | Texas | TAYLOR |  | 19 | 2009710 | SPN:0908-33-088-REHAB SURFACE | Pavement Improvement | 04/15/2010 |  |  | 878041.94 | 3.18
9917 | Texas | STARR |  | 28 | 2009711 | SPN:1103-04-025-REHABILITATION OF PAVEMENT, ADD CURB & GUTTER, STORM SEWER AND RESTRIPE TO ONE WAY PAIR : US 83 NORTH | Pavement Improvement | 08/10/2009 | 10/20/2009 | 02/01/2011 | 2521180.59 | 0.921
9918 | Texas | CAMERON |  | 27 | 2009712 | SPN:1425-03-053-OVERLAY : US 77 | Pavement Improvement | 08/19/2009 | 09/21/2009 | 09/01/2009 | 1671691.1 | 3.463
9919 | Texas | POTTER |  | 13 | 2009713 | SPN:0904-02-033-OVERLAY : ON HASTINGS AVE, FROM RIVER ROAD | Pavement Improvement | 10/22/2009 |  |  | 231677.92 | 1
9920 | Texas | RANDALL | AMARILLO | 13 | 2009714 | SPN:2635-03-014-UPGRADE TO URBAN SECTION : SW 83RD AVENUE SW 45TH AVENUE | Pavement Widening | 04/22/2010 |  |  | 2083226.09 | 1.988
9921 | Texas | RANDALL |  | 13 | 2009715 | SPN:0904-11-046-OVERLAY : ON S GEORGIA ST, FR .3 MI N OF FARM | Pavement Improvement | 11/02/2009 | 01/25/2010 |  | 155676.82 | 1
9922 | Texas | RANDALL | AMARILLO | 13 | 2009716 | SPN:0904-11-045-2-LANE REHABILITATION : ON HILLSIDE RD, FR LP 335 WEST NANCY ELLEN DRIVE | Pavement Improvement | 04/22/2010 |  |  | 451413.53 | 0.435
9923 | Texas | MIDLAND |  | 11 | 2009717 | SPN:0887-01-032-ROADWAY REHABILITATION : CR 1150 FM 1379 | Pavement Improvement | 01/06/2010 | 01/25/2010 |  | 5697710.48 | 7.099
9924 | Texas | ECTOR |  | 11 | 2009719 | SPN:3571-01-005-ROADWAY REHABILITATION : SH 191 MIDLAND COUNTY LINE | Pavement Improvement | 12/07/2009 | 02/09/2010 |  | 659899.92 | 0.432
9925 | Texas | MIDLAND |  | 11 | 2009720 | SPN:3571-02-005-ROADWAY REHABILITATION : ECTOR COUNTY LINE BI 20-E | Pavement Improvement | 12/07/2009 | 02/09/2010 |  | 810232.45 | 1.685
9926 | Texas | WICHITA |  | 13 | 2009721 | SPN:0903-03-093-HIKE AND BIKE TRAIL- PHASE 3 : HAMILTON PARK SCOTT STREET | Transportation Enhancements | 02/01/2010 | 02/16/2010 |  | 2582604.07 | 2.9
9927 | Texas | TOM GREEN |  | 11 | 2009724 | SPN:0077-09-005-ASPHALT CONCRETE PAVEMENT OVERLAY : RED ARROYO US 87 | Pavement Improvement | 12/07/2009 | 03/02/2010 |  | 2367545.34 | 3.42
9928 | Texas | TOM GREEN |  | 11 | 2009725 | SPN:0555-05-021-ASPHALT CONCRETE PAVEMENT OVERLAY : US 67 IN SAN ANGELO BU 67-H | Pavement Improvement | 05/05/2010 | 05/05/2010 |  | 357000 | 0.691
9929 | Texas | TOM GREEN | SAN ANGELO | 11 | 2009745 | SPN:0158-02-081-ASPHALT CONCRETE PAVEMENT OVERLAY : 1.18 MILES NORTH OF SMITH BLVD SMITH BLVD | Pavement Improvement | 05/03/2010 | 05/03/2010 |  | 316396.66 | 1.18
9930 | Texas | TOM GREEN | SAN ANGELO | 11 | 2009746 | SPN:0907-24-033-REHABILITATE EXISTING ROADWAY | Pavement Improvement | 04/12/2010 |  |  | 1103076 | 1
9931 | Texas | GREGG | LONGVIEW | 01 | 2009748 | SPN:1385-02-021-INSTALL TRAFFIC SIGNAL IN TWO LOCATIONS : AT FM 2275 AND AT CHERYL ST IN LONGVIEW | Safety/Traffic Management | 04/26/2010 | 04/26/2010 |  | 185678.15 | 0.2
9932 | Texas | VICTORIA | VICTORIA | 14 | 2009755 | SPN:0143-10-042-ASPHALTIC CONCRETE PAVEMENT : US 77 RED RIVER ST. IN VICTORIA | Pavement Improvement | 01/07/2010 | 02/01/2010 |  | 1338000 | 3.408
9933 | Texas | VICTORIA | VICTORIA | 14 | 2009762 | SPN:0143-10-043-CONSTRUCT TURN LANES : 0.36 MI. WEST OF TROPICAL DR. US 77 IN VICTORIA | Pavement Improvement | 01/07/2010 | 02/01/2010 |  | 531000 | 0.671
9934 | Texas | VICTORIA | VICTORIA | 14 | 2009763 | SPN:0144-01-067-ASPHALTIC CONCRETE PAVEMENT : RED RIVER ST. IN VICTORIA BU 59-T | Pavement Improvement | 01/07/2010 | 02/01/2010 |  | 137719.52 | 0.492
9935 | Texas | VICTORIA | VICTORIA | 14 | 2009764 | SPN:2350-01-046-CONSTRUCT TURN LANES : 0.24 MI. WEST OF MOCKINGBIRD LN 0.24 MI. EAST OF MOCKINGBIRD LN | Pavement Improvement | 01/07/2010 | 02/01/2010 |  | 350837.02 | 0.486
9936 | Texas | HIDALGO |  | 15, 28 | 2009785 | SPN:0039-17-167-CONSTRUCT OVERPASS : 0.30 MILES WEST OF FM 396 0.30 MILES EAST OF FM 396 | Pavement Improvement | 05/17/2010 |  |  | 10000000 | 0.6
9937 | Texas | FORT BEND | HOUSTON | 09, 22 | 2009792 | SPN:0912-34-126-WIDEN TO 4 LANES CURB & GUTTER : STAFFORD/STAFFORDSHIRE,HARRIS C/L 5TH STREET | Pavement Widening | 05/11/2010 | 06/07/2010 |  | 4500000 | 2.211
9938 | Texas | ELLIS |  | 06 | 2009801 | SPN:0092-08-015-REHABILITATE EXISTING ROADWAY : SOUTH OF SH 34 IN ENNIS | Pavement Improvement | 08/26/2009 | 09/15/2009 | 08/01/2010 | 1950526.15 | 2.26
9939 | Texas | CALLAHAN |  | 19 | 2009804 | SPN:0181-03-024-PLANNING, UNDERSEAL, ASPHALT CONCRETE PAVEMENT OVERLAY, AND METAL BEAM GUARD FENCE : US 283 ; SPN:0452-02-034-PLANNING, UNDERSEAL, ASPHALT CONCRETE PAVEMENT OVERLAY, AND METAL BEAM GUA | Pavement Improvement | 08/06/2009 | 08/10/2009 | 02/01/2010 | 4960299.07 | 18.082
9940 | Texas | SAN PATRICIO |  | 15 | 2009805 | SPN:0372-01-093-OVERLAY ROADWAY : ODEM N. CITY LIMITS | Pavement Improvement | 09/09/2009 | 09/25/2009 | 02/01/2009 | 2015197.58 | 4.182
9941 | Texas | JOHNSON | DALLAS-FORT WORTH | 17 | 2009834 | SPN:0422-05-001-WIDEN ROADWAY TO FOUR LANE DIVIDED WITH DIAMOND INTERCHANGE AT PROPOSED SH 121/NOLAN RIVER ROAD : 0.6 MI EAST OF FM 4 SH 174 | Pavement Widening | 01/25/2010 | 03/04/2010 |  | 7728131 | 2.329
9942 | Texas | JOHNSON | DALLAS-FORT WORTH | 17 | 2009835 | SPN:0259-06-005-CONSTRUCT RAMPS AT INTERCHANGE WITH SH 174 EB/WB AND ADD MEDIAN BARRIER : SH 174 0.9 MI EAST OF SH 174 | Pavement Improvement | 01/25/2010 | 03/04/2010 |  | 2271868.44 | 0.909
9943 | Texas | FORT BEND | HOUSTON | 22 | 2009837 | SPN:0192-01-086-RECONFIGURE AND UPGRADE TRAFFIC SIGNAL SYSTEM AT INTERSECTION (RCTSS) : FM 1092/UNIVERSITY BLVD | Safety/Traffic Management | 02/19/2010 | 03/15/2010 |  | 1038548.56 | 0
9944 | Texas | WILLIAMSON |  | 31 | 2009866 | SPN:2211-02-021-RECONST TO 4-LANE DIVIDED RDWY : CHANDLER RD | Pavement Widening | 10/30/2009 | 12/01/2009 |  | 9229357.32 | 2.356
9945 | Texas | DALLAS |  | 03, 05 | 2009874 | SPN:0009-02-058-ACP OVERLAY,CONCRETE FULL DEPTH REPAIR AND PAVEMENT MARKINGS : IH 635 | Pavement Improvement | 09/09/2009 | 10/19/2009 | 01/01/2010 | 1568590.18 | 3.256
9946 | Texas | TARRANT |  | 06 | 2009912 | "SPN:0172-02-067-REPAIR FAILURES, MILL, 2"" HMAC OVERLAY, PAVEMENT MARKINGS & SIGNALS : OAK STREET IN MANSFIELD ; SPN:0747-04-062-MILL EXISTING 2"" AND OVERLAY : 1000 FT SOUTH OF DEBBIE LANE ; SPN:23 | Pavement Improvement | 05/04/2010 | 05/04/2010 |  | 1267997.97 | 3.296
9947 | Texas | BOWIE | TEXARKANA (TX-AR) | 04 | 2009921 | SPN:0218-01-070-CONSTRUCT RAILROAD GRADE SEPARATION STRUCTURE AND APPROACHES : AT UNION PACIFIC RR OVERPASS | Pavement Improvement | 11/02/2009 | 11/19/2009 |  | 1713000 | 0.506
9948 | Texas | NUECES |  | 27 | 2009928 | SPN:2263-02-086-CONSTRUCT 2ND NEW 28 CAR FERRY BOAT PLANS BY NAVAL ARCHITECT : AT THE PORT ARANSAS FERRY LANDING | Other | 08/31/2009 | 01/25/2010 | 05/01/2011 | 6506000 | 0.001
9949 | Texas | STEPHENS |  | 19 | 2010003 | SPN:0257-01-038-FLEX BASE AND SEAL COAT : FM 576W, SOUTH | Pavement Improvement | 10/14/2009 | 11/19/2009 |  | 1648067 | 4.264
9950 | Texas | HAYS |  | 25 | 2010004 | SPN:0016-02-130-SEAL COAT, MILL&INLAY, OVERLAY W\PFC : 2000 FT N OF FM 2001 | Pavement Improvement | 10/09/2009 | 11/02/2009 |  | 431995.37 | 0.379
9951 | Texas | COKE |  | 11 | 2010005 | SPN:0264-04-046-CONCRETE PAVEMENT AT INTERSECTION : 0.353 MI NORTH OF SH 158 (MAIN ST) | Pavement Improvement | 10/21/2009 | 11/09/2009 |  | 387885.5 | 0.001
9952 | Texas | JOHNSON |  | 17 | 2010006 | SPN:2464-01-013-RECONSTRUCT ROADWAY : FM 4 END OF ROADWAY | Pavement Improvement | 11/30/2009 | 03/31/2010 |  | 1249457.36 | 6.266
9953 | Texas | CASS |  | 01 | 2010007 | SPN:0919-00-064-INSTALLATION AND UPGRADE OF TRAFFIC CONTROL DEVICES : VARIOUS LOCATIONS IN ATL DISTRICT | Safety/Traffic Management | 10/16/2009 | 02/23/2010 |  | 399251.94 | 0.001
9954 | Texas | MARION |  | 01 | 2010008 | SPN:0632-01-028-RESTORE SECTION AND RESURFACE 2 LANE HIGHWAY : FM 2208 | Pavement Improvement | 11/02/2009 |  |  | 267595.18 | 3.047
9955 | Texas | BOWIE | TEXARKANA (TX-AR) | 04 | 2010009 | SPN:0945-01-036-UPGRADE EXISTING TRAFFIC SIGNALS : AT 40TH/KENNEDY LANE IN TEXARKANA | Safety/Traffic Management | 10/16/2009 | 02/22/2010 |  | 134750.78 | 0.066
9956 | Texas | UPSHUR |  | 01 | 2010012 | SPN:0392-02-080-REPAIR PAVEMENT ON EXISTING 4 LANE HIGHWAY : 0.2 MI S OF FM 557 | Pavement Improvement | 10/16/2009 |  |  | 715360 | 3.23
9957 | Texas | LIBERTY |  | 08 | 2010024 | SPN:1146-01-027-RESTORE EXISTING ROADWAY : SH 146, EAST | Pavement Improvement | 10/14/2009 | 10/12/2009 |  | 994796.57 | 6
9958 | Texas | MILAM |  | 31 | 2010027 | SPN:0204-08-053-OVERLAY CONSISTING OF MILLING, HMA OVERLAY, SURFACE TREATMENT AND PAVEMENT MARKINGS AND MARKERS : 0.4 MILE WEST OF FM 2095 | Pavement Improvement | 10/30/2009 | 06/01/2010 |  | 766187.19 | 5.56
9959 | Texas | GRIMES |  | 17 | 2010029 | SPN:0212-04-032-OVERLAY CONSISTING OF HMA LEVEL-UP, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : FM 244 | Pavement Improvement | 10/14/2009 | 11/02/2009 |  | 1849901.76 | 8.067
9960 | Texas | FREESTONE |  | 06 | 2010030 | SPN:0426-02-018-RESTORE EXISTING ROAD CONSISTING OF GRADING, FLEXIBLE BASE, SURFACE AND PAVEMENT MARKINGS AND MARKERS : FM 1848 ; SPN:2144-01-013-RESTORE EXISTING ROAD CONSISTING OF GRADING, FLEXIBLE | Pavement Improvement | 11/06/2009 | 01/05/2010 |  | 1317884.18 | 10.464
9961 | Texas | DICKENS |  | 13 | 2010031 | SPN:0651-04-016-SEALCOAT ECONOMIC STIMULUS : FM 2565, SE | Pavement Improvement | 10/15/2009 | 10/27/2009 |  | 90114 | 7.715
9962 | Texas | JIM WELLS |  | 15 | 2010032 | SPN:0086-11-041-REHAB. EXISTING ROADWAY : VENTURA ST., IN SAN DIEGO, EAST | Pavement Improvement | 11/12/2009 | 01/20/2010 |  | 3776701.94 | 8.71
9963 | Texas | ARANSAS, SAN PATRICIO |  | 14 | 2010033 | SPN:0180-05-058-MILL,SEAL AND OVERLAY : STAPP ST. ; SPN:0180-06-088-MILL,SEAL AND OVERLAY : ARANSAS/SAN PAT CO. LINE | Pavement Improvement | 10/26/2009 | 11/11/2009 |  | 782350.63 | 1.942
9964 | Texas | SAN PATRICIO |  | 15 | 2010034 | SPN:0371-04-056-OVERLAY AND SEAL EXISTING LANES : ARANSAS RIVER BRIDGE | Pavement Improvement | 11/06/2009 | 12/09/2009 |  | 2224860.59 | 5.502
9965 | Texas | COLLIN |  | 04 | 2010037 | SPN:0387-05-019-RECONSTRUCT RURAL 2 LANE HIGHWAY TO 2 LANE URBAN WITH SHOULDERS AND TWLTL : US 380 | Pavement Improvement | 10/26/2009 |  |  | 4887963.33 | 1.054
9966 | Texas | PRESIDIO, BREWSTER |  | 23 | 2010040 | SPN:0020-09-017-OVERLAY : 1.286 MI E BREWSTER/PRESIDIO CO LIN ; SPN:0020-10-017-OVERLAY : APPROX 7 MI. W. OF MOSLEY LANE | Pavement Improvement | 09/30/2009 | 10/02/2009 |  | 981994.38 | 2.819
9967 | Texas | EL PASO |  | 16 | 2010041 | SPN:0924-00-067-UPGRADING OVERHEAD AND LARGE GROUND MOUNTED SIGNS : VARIOUS LOCATIONS DISTRICTWIDE | Safety/Traffic Management | 10/16/2009 | 02/28/2010 |  | 635030.08 | 1
9968 | Texas | PALO PINTO |  | 13 | 2010043 | "SPN:0007-08-026-CEMENT TREAT EXISTING BASE ON NB LANE AND SHOULDER, SEAL COAT AND 2"" HMAC OVERLAY ENTIRE ROADWAY : PALO PINTO CREEK " | Pavement Improvement | 11/02/2009 |  |  | 1473364.87 | 11.262
9969 | Texas | WISE |  | 12 | 2010044 | SPN:0013-08-115-2 INCH OVERLAY NORTHBOUND LANES : NBL 475` S OF US 380 | Pavement Improvement | 11/02/2009 |  |  | 837946.86 | 4.092
9970 | Texas | JOHNSON |  | 17 | 2010045 | SPN:0019-01-136-HOTMIX OVERLAY : NORTH OF POINDEXTER ST; IN CLEBURNE | Pavement Improvement | 11/16/2009 | 02/09/2010 |  | 2086653.12 | 2.829
9971 | Texas | JOHNSON |  | 17 | 2010046 | SPN:0019-02-031-SEAL COAT : CLEBURNE CITY LIMITS | Pavement Improvement | 11/12/2009 | 04/07/2010 |  | 1009579.3 | 3.588
9972 | Texas | HOOD |  | 17 | 2010047 | SPN:0080-08-024-MILL AND HMAC OVERLAY : US 377 | Pavement Improvement | 11/06/2009 | 12/14/2009 |  | 352322.3 | 2.01
9973 | Texas | ERATH, SOMERVELL |  | 31 | 2010048 | SPN:0258-01-026-SEAL COATS : FM 847 IN DUBLIN ; SPN:0258-02-050-SEAL COAT : 5.9 MI EAST OF FM 847 ; SPN:0259-02-045-SEAL COATS : ERATH COUNTY LINE | Pavement Improvement | 11/16/2009 |  |  | 1138715.02 | 18.31
9974 | Texas | GALVESTON |  | 14 | 2010051 | SPN:0051-09-023-RAISE ROADWAY AND BASE REPAIRS (PHASE 1) : SAN LUIS PASS TOLL BRIDGE | Pavement Improvement | 11/02/2009 | 11/18/2009 |  | 3227313 | 18.273
9975 | Texas | HARRIS | HOUSTON | 02, 18 | 2010053 | SPN:0110-05-116-PAVEMENT MARKINGS : NORTH OF BW 8 ; SPN:0110-06-130-PAVEMENT MARKINGS : SOUTH OF BW 8 | Safety/Traffic Management | 11/02/2009 | 01/12/2010 |  | 324477.4 | 8.818
9976 | Texas | WALLER |  | 10 | 2010055 | SPN:0543-01-059-SEAL COAT, OVERLAY AND PAVEMENT MARKINGS : BU 290 | Pavement Improvement | 10/21/2009 | 11/16/2009 |  | 1657626 | 10.859
9977 | Texas | FORT BEND | HOUSTON | 22 | 2010056 | SPN:0543-03-059-REPLACE BRIDGE AND APPROACHES : AT SMITHERS LAKE | Bridge Replacement | 10/16/2009 | 09/09/2009 |  | 1288241.82 | 0.124
9978 | Texas | HARRIS | HOUSTON | 02, 29, 22, 09, 07, 18 | 2010057 | SPN:0912-00-335-UPGRADE/RECONSTRUCT TRAFFIC SIGNALS : VARIOUS LOCATIONS DISTRICTWIDE | Safety/Traffic Management | 11/16/2009 |  | 10/30/2009 | 898349.73 | 0.001
9979 | Texas | HARRIS | HOUSTON | 02, 29, 22, 07, 18, 14, 09, 08, 10 | 2010058 | SPN:0912-00-383-UPGRADE/RECONSTRUCT TRAFFIC SIGNALS : VARIOUS LOCATIONS DISTRICTWIDE | Safety/Traffic Management | 10/30/2009 |  |  | 946870.85 | 0.001
9980 | Texas | FORT BEND |  | 14, 22 | 2010059 | SPN:0912-34-148-LANDSCAPE DEVELOPMENT : VARIOUS LOCATIONS ON US 59 | Transportation Enhancements | 11/16/2009 | 12/18/2009 |  | 186209.34 | 0.001
9981 | Texas | HARRIS |  | 22, 29, 02, 18, 09, 07, 10 | 2010061 | SPN:0912-72-181-BRIDGE MAINTENANCE-REPAIRING STEEL MEMBERS, SEALING ACCESS DOORS, CLEANING AND PAINTING CAPS AND OTHER MISC WORK : VARIOUS LOCATIONS | Other | 10/26/2009 | 11/18/2009 |  | 1348545 | 0.001
9982 | Texas | GALVESTON |  | 14, 22 | 2010063 | SPN:0912-73-131-COUNTYWIDE FULL DEPTH CONCRETE REPAIR : VARIOUS LOCATIONS | Pavement Improvement | 01/04/2010 |  |  | 442388.58 | 25.446
9983 | Texas | WALLER |  | 10 | 2010064 | SPN:1418-01-010-SEAL COAT, OVERLAY AND PAVEMENT MARKINGS : IH 10 EB FRONTAGE ROAD | Pavement Improvement | 10/21/2009 | 11/06/2009 |  | 777940 | 4.842
9984 | Texas | MONTGOMERY |  | 08 | 2010065 | SPN:1986-01-059-DRAINAGE IMPROVEMENTS : 0.212 MI NW OF MILLS ROAD | Other | 11/06/2009 | 02/03/2010 | 11/06/2009 | 367819.89 | 0.338
9985 | Texas | HARRIS |  | 07 | 2010066 | SPN:3256-01-094-RESHAPE AND STABILIZE EROSION : AT WHITE OAK BAYOU | Other | 11/04/2009 | 12/01/2009 |  | 106335.6 | 0.034
9986 | Texas | LA SALLE |  | 28 | 2010067 | SPN:0017-08-070-RECONSTRUCTION OF NORTH BOUND MAINLANES, RAMPS : LA SALLE/FRIO COUNTY LINE | Pavement Improvement | 11/18/2009 | 12/14/2009 |  | 1574216.7 | 8.468
9987 | Texas | CROSBY, FLOYD |  | 13 | 2010074 | SPN:0453-04-021-SEAL COAT ECONOMIC STIMULUS : US 62 ; SPN:0806-01-011-SEAL COAT ECONOMIC STIMULUS : US 62 EAST ; SPN:1143-01-009-SEAL COAT ECONOMIC STIMULUS : US 62 ; SPN:2497-02-005-SEAL COAT ECONOMI | Pavement Improvement | 10/15/2009 | 10/27/2009 |  | 816603.44 | 38.637
9988 | Texas | SAN AUGUSTINE, SABINE, SAN JACINTO |  | 08 | 2010075 | SPN:0177-02-085-MICROSURFACING : 0.61 MI S OF RR OVERPASS ; SPN:0177-02-086-MICROSURFACING : TRINITY RIVER BRIDGE ; SPN:0336-07-060-MICROSURFACING : FM 1751 ; SPN:0336-08-024-MICROSURFACING : SAN | Pavement Improvement | 11/02/2009 | 11/18/2009 |  | 1275635.47 | 23.09
9989 | Texas | WINKLER |  | 11 | 2010077 | SPN:0463-06-024-ROADWAY REHABILITATION : 1.3 MILES EAST OF SH 18 IN KERMIT | Pavement Improvement | 10/21/2009 | 11/17/2009 |  | 1773715.49 | 16.312
9990 | Texas | GRAYSON |  | 04 | 2010078 | SPN:0045-19-045-OVERLAY EXISTING 2 LANE ROADWAY : BETHANY ROAD | Pavement Improvement | 05/04/2010 | 05/04/2010 |  | 2943236.01 | 5.362
9991 | Texas | HIDALGO |  | 15 | 2010080 | SPN:0342-01-080-OVERLAY : 0.163 MI E OF FM 493 ; SPN:1586-01-055-OVERLAY : SH 107 | Pavement Improvement | 11/02/2009 | 02/26/2010 |  | 1603329.13 | 10.155
9992 | Texas | CAMERON |  | 27 | 2010081 | SPN:0872-04-025-UPGRADE DRAINAGE CULVERT AND RAISE ROAD : 2.96 MI N OF US 83 | Other | 10/15/2009 | 10/16/2009 |  | 864254.25 | 0.92
9993 | Texas | HIDALGO | MCALLEN-PHARR-EDINBURG | 15, 28 | 2010083 | SPN:1939-01-049-REHAB SB OUTSIDE LANE & OVERLAY FULL ROADWAY WIDTH : 1250` N. OF TRENTON RD | Pavement Improvement | 11/06/2009 | 12/07/2009 |  | 540908 | 2.377
9994 | Texas | BEXAR | SAN ANTONIO | 20, 23 | 2010087 | SPN:0291-10-097-LANDSCAPE PLANTING, IRRIGATION SYSTEM, & SPECIALIZED PAVING : AT LP 1604 | Transportation Enhancements | 11/02/2009 | 11/18/2009 |  | 191565.56 | 0.5
9995 | Texas | UVALDE |  | 23 | 2010088 | SPN:0369-03-028-REHAB EXISTING ROADWAY & ADD SHOULDERS : 0.8 MI. S OF SABINAL RIVER | Pavement Improvement | 10/15/2009 | 11/02/2009 |  | 1285287.46 | 5.566
9996 | Texas | BEXAR | SAN ANTONIO | 20 | 2010089 | SPN:0521-04-261-LANDSCAPE DEVELOPMENT : AT IH 10 | Transportation Enhancements | 11/02/2009 | 11/18/2009 |  | 865906.52 | 0.001
9997 | Texas | ATASCOSA |  | 28 | 2010090 | SPN:0613-02-055-LANDSCAPE PLANTING & IRRIGATION SYSTEM : AT SH 173, N OF JOURDANTON | Transportation Enhancements | 10/21/2009 | 12/02/2009 |  | 85788 | 0.7
9998 | Texas | FRIO |  | 28 | 2010091 | SPN:0748-01-028-REHAB AND WIDEN NARROW ROADWAY : 2.2 MI E OF PEARSALL | Pavement Improvement | 10/15/2009 | 10/19/2009 | 10/19/2009 | 3097967.34 | 10.7
9999 | Texas | GUADALUPE |  | 28 | 2010092 | SPN:0915-46-036-LANDSCAPE PLANTING AND IRRIGATION : VARIOUS LOCATIONS IN SEGUIN | Transportation Enhancements | 10/16/2009 | 11/01/2009 |  | 491794.72 | 0.001
10000 | Texas | SMITH | TYLER | 01 | 2010094 | SPN:0191-03-021-PLANE & RESURFACE ROADWAY : LP 323 IN TYLER, S | Pavement Improvement | 10/21/2009 | 05/05/2010 |  | 736484.3 | 1.593
10001 | Texas | ANDERSON |  | 05 | 2010095 | SPN:0205-07-071-PLANE & RESURFACE ROADWAY : 0.4 MI SE OF FM 2394 IN P`STINE, NE ; SPN:0206-01-046-PLANE & RESURFACE ROADWAY : 0.5 MI W OF SH 155 (JACKSON ST), NE | Pavement Improvement | 10/22/2009 |  |  | 1582436.6 | 3.391
10002 | Texas | MCLENNAN, LIMESTONE |  | 17 | 2010097 | SPN:0056-01-032-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : SH 31 ; SPN:0056-02-030-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : MCLENNAN CO LINE ; SPN:0056-03-057-REPAIR AND RESURFACE WITH ASPHALT | Pavement Improvement | 11/06/2009 | 12/03/2009 |  | 2332820 | 32.206
10003 | Texas | WILBARGER |  | 13 | 2010098 | SPN:0124-03-059-PLANING AND NOVACHIP OVERLAY : US 287 | Pavement Improvement | 10/26/2009 | 06/17/2010 |  | 605866.52 | 1.619
10004 | Texas | WHARTON |  | 14 | 2010099 | SPN:0089-07-140-PAVEMENT REPAIR & ACP SURFACING : CANEY CREEK ; SPN:0089-08-090-PAVEMENT REPAIR & ACP SURFACING : NORTH OF SH 60 | Pavement Improvement | 11/12/2009 | 12/30/2009 |  | 4409900.24 | 7.03
10005 | Texas | CALHOUN |  | 14 | 2010100 | SPN:0180-01-074-ASPHALTIC CONCRETE PAVEMENT : MILDRED DR IN PORT LAVACA | Pavement Improvement | 11/24/2009 | 01/25/2010 |  | 1813198.22 | 11.04
10006 | Texas | RANDALL |  | 13 | 2010103 | SPN:0168-09-153-CURB RAMPS AND CONCRETE MEDIAN : AT WESTERN, GEORGIA & REBECCA STRS | Pavement Improvement | 10/30/2009 | 02/15/2010 |  | 80828 | 0.414
10007 | Texas | LEE |  | 10 | 2010123 | SPN:1073-02-023-REPLACE BRIDGE AND APPROACHES : 1.390 MILES NE OF FM 619 2.204 MILES NE OF FM 619; SPN:1073-02-024-REPLACE BRIDGE AND APPROACHES : AT PIN OAK BR, 7.2 MI W OF FM 112 STR 1073-2-5 | Pavement Improvement | 01/07/2010 | 01/27/2010 |  | 2075715.18 | 1.628
10008 | Texas | NAVARRO |  | 06 | 2010137 | SPN:0162-04-051-REPLACE BRIDGE : WB AT CEDAR CREEK ; SPN:0997-01-033-REPLACE BRIDGE AND APPROACHES : AT TREADWELL BRANCH | Bridge Replacement | 12/07/2009 | 03/01/2010 |  | 855639.4 | 0.087
10009 | Texas | GREGG | LONGVIEW | 01 | 2010187 | SPN:0096-04-063-REPAIR AND RESURFACE ROADWAY : 1.3 MI W OF SL 281 (FISHER RD), E FM 1845 IN LONGVIEW; SPN:0096-06-072-REPAIR AND RESURFACE ROADWAY : FM 1845, IN LONGVIEW, E W OF SS 63 | Pavement Improvement | 05/04/2010 | 05/04/2010 |  | 1987737.8 | 4.04
10010 | Texas | GREGG | LONGVIEW | 01 | 2010188 | SPN:0392-03-042-RESURFACE ROADWAY : N OF SL 281, IN LONGVIEW, N 0.1 MI N OF FM 1844 | Pavement Improvement | 04/26/2010 | 04/26/2010 |  | 1294548.95 | 2.93
10011 | Texas | LA SALLE, VAL VERDE |  | 28 | 2010199 | SPN:0017-17-006-FOR THE CONSTRUCTION OF MICROSEAL TYPE OF WORK : IH 35/BI-35C NORTH INTERSECTION 1.867 MI SOUTH; SPN:0022-10-056-FOR THE CONSTRUCTION OF MICROSEAL TYPE OF WORK : STRICKLEN DRIVE 17TH | Pavement Improvement | 11/16/2009 |  |  | 573297.57 | 4.557
10012 | Texas | TRAVIS |  | 10 | 2010205 | SPN:0151-06-133-MILL SEAL AND THIN OVERLAY (FRTG RD) : SL 1 BURNET RD | Pavement Improvement | 05/05/2010 | 05/05/2010 |  | 498163.23 | 0.721
10013 | Texas | WILLIAMSON |  | 31 | 2010206 | SPN:0337-01-033-SPOT FULL DEPTH REPAIR : RAILROAD ST AUSTIN AVE; SPN:0337-02-039-SPOT FULL DEPTH REPAIR : AUSTIN AVE HUTTO RD. | Pavement Improvement | 04/05/2010 | 04/05/2010 |  | 501272.5 | 1.25
10014 | Texas | HAYS |  | 25 | 2010207 | SPN:0366-01-067-OVERLAY OVERLAY : IH 35 NBFR EBONY STREET | Pavement Improvement | 01/06/2010 | 03/11/2010 |  | 178235.61 | 0.375
10015 | Texas | CALDWELL |  | 25 | 2010208 | SPN:0384-01-020-MILL, SEAL, PAV. REPAIR & OVERLAY : BORCHERT LOOP IN LOCKHART US 183 | Pavement Improvement | 05/04/2010 | 05/04/2010 |  | 921349 | 1.838
10016 | Texas | HAYS |  | 25 | 2010211 | SPN:0987-03-009-SEAL COAT AND OVERLAY : SH 123 GUADALUPE COUNTY LINE | Pavement Improvement | 01/07/2010 | 03/09/2010 |  | 457264.3 | 2.935
10017 | Texas | LLANO |  | 11 | 2010212 | SPN:3101-01-006-REHAB RDWY : RM 1431 LLANO R | Pavement Improvement | 01/07/2010 | 03/16/2010 |  | 862584.83 | 0.985
10018 | Texas | HARRIS | HOUSTON | 07, 18 | 2010232 | SPN:0271-07-242-WIDEN AND RECONSTRUCT TO 2 3-LANE FRONTAGE ROADS WITH BRIDGES AT WHITE OAK BAYOU : WASHINGTON AVE. TAYLOR ST.; SPN:0271-07-278-REHABILITATE BRIDGE & APPROACHES : IH 10 WB FR AT WHITE | Pavement Widening | 04/26/2010 | 04/26/2010 |  | 46415172.1 | 3.423
10019 | Texas | COLEMAN |  | 11 | 2010243 | SPN:7123-11-003-GRADE CROSSING AND RAILROAD REHABILITATION : RRMP 0.00 RUNNELS COUNTY LINE RRMP 21.5 | Pavement Improvement | 04/09/2010 | 04/09/2010 |  | 646035.93 | 0.001
10020 | Texas | DUVAL |  | 25 | 2010249 | SPN:0237-05-032-REHABILITATION OF AN EXISTING ROADWAY : SH 16 0.510 MILE EAST; SPN:0542-03-030-REHABILITATION OF EXISTING ROADWAY : 0.316 MILE WEST OF SH 16 SH 16 | Pavement Improvement | 03/09/2010 | 03/29/2010 |  | 1109647.67 | 0.826
10021 | Texas | RUNNELS, TOM GREEN |  | 11 | 2010256 | SPN:7107-09-004-GRADE CROSSING AND RAILROAD REHABILITATION : RUNNELS COUNTY LINE RRMP 56.8 DOT CROSSING 18 771 H RRMP 721.52; SPN:7107-10-003-GRADE CROSSING AND RAILROAD REHABILITATION : COLEMAN COU | Pavement Improvement | 04/09/2010 | 04/09/2010 |  | 3669232.96 | 0.002
10022 | Texas | ATASCOSA |  | 28 | 2010286 | SPN:0073-10-045-MILL, BASE REPAIR, SEAL COAT, OVERLAY, SIGNS & PAVEMENT MARKINGS : US 281 BEXAR COUNTY LINE | Pavement Improvement | 02/08/2010 | 02/24/2010 |  | 3684661.2 | 14.741
10023 | Texas | COLORADO, FAYETTE |  | 25 | 2010289 | SPN:0535-07-046-ASPHALTIC CONCRETE PAVEMENT : US 77 COLORADO C/L WESTBOUND LANES; SPN:0535-08-082-ASPHALTIC CONCRETE PAVEMENT : FAYETTE C/L HATTERMAN LANE WESTBOUND LANES | Pavement Improvement | 02/16/2010 | 05/17/2010 |  | 3455979 | 15.333
10024 | Texas | JASPER |  | 08 | 2010301 | SPN:0064-08-050-RUBBLIZE AND OVERLAY EXISTING ROADWAY : 0.7 MI N OF RE 255, SOUTH 2.7 MI N OF US 190 | Pavement Improvement | 02/16/2010 | 04/14/2010 |  | 5671802.25 | 8.44
10025 | Texas | FORT BEND | HOUSTON | 09, 22 | 2010303 | SPN:0912-34-150-ITS: UPGRADE ALL TRAFFIC SIGNALS TO PROVIDE REGIONALIZED TRAFFIC FLOW : VARIOUS LOCATIONS IN MISSOURI CITY . | Safety/Traffic Management | 04/30/2010 |  |  | 2780094.72 | 0.1
10026 | Texas | TRAVIS | AUSTIN | 21 | 2010304 | SPN:0700-03-014-INSTALL 14` CONTINUOUS LEFT TURN LANE AND 10` SHOULDERS : 0.27 MI EAST OF RO DRIVE 1.4 MI WEST OF BEE CREEK | Pavement Improvement | 04/08/2010 | 06/07/2010 |  | 2550668.74 | 0.3
10027 | Texas | TRAVIS | AUSTIN | 21 | 2010305 | SPN:0700-03-015-INSTALL 14` CONTINUOUS LEFT TURN LANE AND 10` SHOULDERS : 0.2 MI WEST OF BEE CREEK RD 0.13 MILES WEST OF BEE CREEK RD | Pavement Improvement | 04/08/2010 | 06/07/2010 |  | 202557.12 | 0.001
10028 | Texas | HARRISON | LONGVIEW | 01 | 2010313 | SPN:2642-02-022-REHABILITATE PAVEMENT ON EXISTING 4 LANE HIGHWAY : GREGG COUNTY LINE US 80 | Pavement Improvement | 04/27/2010 | 04/27/2010 |  | 4656179.97 | 2.48
10029 | Texas | HAYS | AUSTIN | 25 | 2010314 | SPN:0016-02-120-CONST OVERPASS & RECONST FRT RDS : AT CR 132 (CEMENT PLANT RD) . | Pavement Improvement | 05/13/2010 | 06/08/2010 |  | 5462987.88 | 0.529
10030 | Texas | BASTROP |  | 25 | 2010317 | SPN:0115-04-041-WIDEN, REHAB, ADD TURN LANE & OVERLAY : SH 71 0.2 MILES NORTH OF FM 535 | Pavement Improvement | 04/13/2010 |  |  | 4792710.08 | 2.016
10031 | Texas | TRAVIS | AUSTIN | 10, 21 | 2010320 | SPN:3136-01-167-MILL, SEAL & THIN OVERLAY : RM 2222 LADYBIRD LAKE | Pavement Improvement | 03/18/2010 | 06/22/2010 |  | 3400000 | 4.81
10032 | Texas | DALLAM |  | 13 | 2010394 | SPN:0040-03-052-RECONSTRUCT, ADD 2 LANES : 8.19 MILES SE OF FM 1879 .53 MILES NE OF FM 1727 | Pavement Widening | 03/29/2010 | 03/29/2010 |  | 7838956.43 | 7.449
10033 | Texas | NUECES | CORPUS CHRISTI | 27 | 2010395 | SPN:0074-06-202-CONSTRUCT FRONTAGE ROAD AND MODIFY ENTRANCE AND EXIT RAMPS : .25 MI EAST OF CARBON PLANT RD. MCKINZIE RD. | Pavement Improvement | 02/01/2010 |  |  | 7841712.11 | 1.307
10034 | Texas | GRAYSON |  | 04 | 2010398 | SPN:0045-19-041-WIDEN FROM 2-LANE TO 4-LANE, DIVIDED MEDIAN : BETHANY ROAD US 69 | Pavement Widening | 04/30/2010 |  |  | 3467569.48 | 4.718
10035 | Texas | TARRANT |  | 06 | 2010399 | SPN:1330-02-034-WIDEN FROM 2 LANE TO 4 LANE WITH SHOULDERS AND CURB & GUTTER : NEWT PATTERSON BU 287P | Pavement Widening | 05/05/2010 |  |  | 6895052.12 | 1.503
10036 | Texas | HIDALGO |  | 15, 28 | 2010400 | SPN:3097-02-013-CONSTRUCT OVERPASS AND FRONTAGE ROADS : 1.6 MI SOUTH OF US 83 0.10 MI SOUTH OF US 83 | Pavement Improvement | 05/17/2010 |  |  | 11000000 | 1.5
10037 | Texas | POTTER | AMARILLO | 13 | 2010401 | SPN:0904-02-035-CONSTRUCT RR OVERPASS : ON GRAND ST AND SE 3RD AVE AT BNSF RR | Pavement Improvement | 05/26/2010 |  |  | 5073269.94 | 0.442
10038 | Texas | JEFFERSON |  | 02 | 2010402 | SPN:0932-01-076-ADD 2 LANES & LEFT TURN LANE : SP 93, EAST US 69 IN PORT ARTHUR | Pavement Widening | 06/22/2010 |  |  | 6775901.16 | 2.4
10039 | Texas | HARRIS | HOUSTON | 10 | 2010403 | SPN:0271-06-110-CONSTRUCT 2 DIRECT CONNECTORS ___**FUNDING CSJ 0271-06-119** : AT SH 99 . | New Bridge Construction | 06/15/2010 |  |  | 24308770.03 | 0.001
10040 | Texas | HARRIS | HOUSTON | 29 | 2010404 | SPN:0389-13-052-CONSTRUCT DIRECT CONNECTOR (RAMP E DC SB TO WB) : SH 146 (SB) SPUR 330 (WB) | New Bridge Construction | 03/18/2010 |  |  | 4118844.5 | 0.391
10041 | Texas | TRAVIS | AUSTIN | 21, 25 | 2010421 | SPN:0700-03-107-ADD TRAFFIC SIGNAL, LEFT TURN LN, RIGHT TURN LN & SHOULDERS : 0.62 MI E OF BEE CREEK RD 1.49 MI E OF BEE CREEK RD | Pavement Improvement | 01/13/2010 | 02/15/2010 |  | 1466792.03 | 0.87
10042 | Texas | EL PASO | EL PASO | 16 | 2010460 | SPN:7224-01-001-RL BNSF Fr. US/MX BORDER To. APPROX 1.5 MILES NORTH; REHABILITATE EXISTING TRACK AND CONSTUCT 550 FEET OF CONNECTING TRACK | Other | 03/04/2010 | 03/04/2010 |  | 1200000 | 1
10043 | Texas | KIMBLE |  | 11 | 2010484 | SPN:2469-01-007-CONSTRUCT EXTENSION TO EXISTING ROADWAY : CURRENT SOUTH TERMINUS OF FM 2169 US 377 IN JUNCTION | Pavement Widening | 05/03/2010 | 05/21/2010 |  | 2561075.41 | 0.661
10044 | Texas | ANDERSON |  | 05 | 2010531 | SPN:0109-01-055-REPAIR PAVEMENT & RESURFACE ROADWAY : 0.1 MI N OF FM 2419, S OF P`STINE,S SH 294 (W) IN ELKHART | Pavement Improvement | 03/11/2010 |  |  | 1541000 | 5.72
10045 | Texas | SMITH |  | 01 | 2010533 | SPN:0191-03-078-RESURFACE ROADWAY W/ NOVA CHIP & IMPRV LP 323 INTERSECTION : US 69 (S BROADWAY),SW LP 323 IN TYLER | Pavement Improvement | 03/09/2010 | 04/05/2010 |  | 700000 | 2.257
10046 | Texas | VAN ZANDT |  | 05 | 2010535 | SPN:0495-02-060-REPAIR & RESURFACE ROADWAY (EBL & WBL) VARIOUS LOCATIONS : 3.4 MI W OF FM 47 (KAUFMAN C/L), E 1.5 MI E OF SH 64 (EBL & WBL) | Pavement Improvement | 05/03/2010 | 05/03/2010 |  | 2253289.96 | 11.24
10047 | Texas | YOUNG |  | 19 | 2010538 | SPN:0134-02-053-MILL SURFACE AND FILL WITH HMAC : US 380 4TH STREET IN GRAHAM; SPN:0362-01-044-MILL SURFACE AND FILL WITH HMAC : 4TH STREET SOUTH SALEM LOOP | Pavement Improvement | 03/18/2010 | 05/10/2010 |  | 2124482.97 | 8.637
10048 | Texas | WHARTON |  | 14 | 2010539 | SPN:0089-15-017-PAVEMENT REPAIR AND ACP SURFACING : US 59 IN EL CAMPO US 59 | Pavement Improvement | 04/05/2010 | 04/05/2010 |  | 1324375 | 5.595
10049 | Texas | MCLENNAN |  | 17 | 2010545 | SPN:0015-21-010-WIDEN FROM TWO TO FOUR LANES WITH CONTINUOUS LEFT TURN LANE : TEXAS CENTRAL PKWY IN WACO FM 2063 (SUN VALLEY BLVD) IN HEWITT | Pavement Widening | 05/07/2010 | 06/01/2010 |  | 3293000 | 2.222
10050 | Texas | MCLENNAN |  | 17 | 2010546 | SPN:2506-01-027-WIDEN ROADWAY TO FOUR LANES WITH CONTINUOUS LEFT TURN LANE TO IMPROVE SAFETY AND REDUCE CONGESTION : 0.9 MI N OF FM 2113 WARREN ST | Pavement Widening | 06/04/2010 |  |  | 2895412.76 | 0.796
10051 | Texas | MONTGOMERY |  | 08 | 2010547 | SPN:0675-08-061-WIDEN TO 8 MAIN LANES AND RECONSTRUCT 2-LANE FRONTAGE ROADS : N OF LP 336 S OF FM 3083; SPN:0675-08-099-WIDEN TO 8 MAIN LANES AND RECONSTRUCT 2-LANE FRONTAGE ROADS : S OF FM 3083 N O | Pavement Widening | 04/15/2010 |  |  | 51235353.1 | 2.747
10052 | Texas | CHAMBERS |  | 14 | 2010550 | SPN:0508-03-092-CONSTRUCT RAMPS FOR NEW TOURIST AND VISITOR CENTER AND MAKE FRONTAGE ROAD ACCOMODATIONS : 2 MI W OF FM 1724 . | Transportation Enhancements | 04/27/2010 | 06/03/2010 |  | 1966157.9 | 1.401
10053 | Texas | MONTGOMERY |  | 08 | 2010552 | SPN:0675-08-092-ROW ACQUISITION, UTILITY ADJUSTMENTS AND RELOCATION ASSISTANCE : LP 336 NORTH FM 830 | Other | 04/15/2010 |  |  | 1000000 | 4.015
10054 | Texas | AUSTIN |  | 10 | 2010556 | SPN:0187-02-055-ADD 2-LANE FOR 4-LANE DIVIDED FACILITY (FUNDING CSJ - 0187-02-062) : FM 949 0.2 MI. NORTH OF FM 2429 | New Bridge Construction | 04/15/2010 | 06/11/2010 |  | 7348419.15 | 4.929
10055 | Texas | AUSTIN |  | 10 | 2010557 | SPN:0187-03-051-ADD 2-LANES FOR 4-LANE DIVIDED FACILITY : 0.2 MI SOUTH OF FM 2187 FM 949 | Pavement Widening | 04/15/2010 | 06/11/2010 |  | 15070823.13 | 5.885
10056 | Texas | JOHNSON | DALLAS-FORT WORTH | 17 | 2010558 | SPN:0422-05-004-WIDEN ROADWAY FROM 2 LANE TO 4 LANE FACILITY : BU 67M 0.6 MILES EAST OF FM 4 | Pavement Widening | 05/13/2010 | 05/21/2010 |  | 17260420.68 | 4.168
10057 | Texas | TAYLOR |  | 19 | 2010559 | SPN:0006-05-108-UPGRADE SAFETY LIGHTING : 0.9 MILES WEST OF FM 707 0.5 MILES EAST OF FM 707 | Safety/Traffic Management | 05/26/2010 |  |  | 162819.65 | 1.406
10058 | Texas | BOWIE |  | 04 | 2010569 | SPN:0046-06-074-RESURFACE EXISTING HIGHWAY : COWHORN CREEK 0.2 MI W OF US 59; SPN:2878-01-013-RESURFACE EXISTING HIGHWAY : 0.1 MI SOUTH OF FM 989 0.1 MI WEST OF FM 1297; SPN:2879-01-009-RESURFACE EX | Pavement Improvement | 03/26/2010 | 05/13/2010 |  | 625744.76 | 3.247
10059 | Texas | HAYS | AUSTIN | 25 | 2010570 | SPN:0285-03-048-ADD CENTER TURN LANE : PIONEER TRAIL BAPTIST ACADEMY | Pavement Improvement | 05/04/2010 | 05/04/2010 |  | 998761.29 | 1.042
10060 | Texas | TRAVIS | AUSTIN | 25 | 2010578 | SPN:0113-09-068-IMPROVEMENTS TO SIDEWALKS : AT BRODIE LANE . | Transportation Enhancements | 03/26/2010 | 04/20/2010 |  | 131080 | 0.1
10061 | Texas | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2010580 | SPN:0039-04-080-RECONSTRUCT EXISTING 3 LANE TO 4 LANE DIVIDED URBAN : FM 1015 IN WESLACO 0.7 MI E SP 31 IN MERCEDES | Pavement Widening | 05/11/2010 |  |  | 4144356.19 | 1.727
10062 | Texas | TAYLOR |  | 19 | 2010590 | SPN:0006-06-096-UPGRADE SAFETY LIGHTING : GRAPE STREET BU 83-D | Safety/Traffic Management | 05/26/2010 |  |  | 193328 | 0.523
10063 | Texas | JONES, TAYLOR |  | 13 | 2010591 | SPN:0033-05-085-UPGRADE SAFETY LIGHTING : 0.26 MI NORTH OF TAYLOR COUNTY LINE TAYLOR COUNTY LINE; SPN:0033-08-037-UPGRADE SAFETY LIGHTING : JONES COUNTY LINE 0.082 MILES SOUTH OF SUMMIT STREET | Safety/Traffic Management | 05/26/2010 |  |  | 184225 | 1.057
10064 | Texas | TAYLOR |  | 19 | 2010592 | SPN:0033-06-103-PAVEMENT MARKERS AND MARKINGS : NEAR US 277 (S 14TH ST) US 277 (S 14TH ST) | Safety/Traffic Management | 06/15/2010 |  |  | 76423.88 | 1.006
10065 | Texas | TAYLOR |  | 19 | 2010593 | SPN:0034-01-104-PAVEMENT MARKERS AND MARKINGS : US 277 (S 14TH ST) SOUTH OF FM 89 (BUFFALO GAP RD) | Safety/Traffic Management | 06/15/2010 |  |  | 201515.4 | 3.2
10066 | Texas | CALLAHAN |  | 19 | 2010602 | SPN:0007-02-047-RESURFACING AND PAVEMENT MARKINGS : EAST OF MEXIA CREEK EASTLAND COUNTY LINE | Pavement Improvement | 04/08/2010 |  |  | 2294673.03 | 8.914
10067 | Texas | CASS |  | 04 | 2010605 | SPN:0919-14-020-REMOVE BARRIERS TO COMPLY WITH ADA : VARIOUS LOCATIONS IN CASS COUNTY AND THE CITY OF LINDEN | Transportation Enhancements | 04/27/2010 |  |  | 416406.88 | 0.001
10068 | Texas | MONTGOMERY |  | 19 | 2010629 | SPN:0675-08-084-WIDEN TO 6 MAIN LANES : NORTH OF CALVARY SOUTH OF FM 830; SPN:0675-08-091-CONSTRUCT 1 NB ENTRANCE RAMP AND 1 SB EXIT RAMP : AT LONGSTREET ROAD IN WILLIS .; SPN:0675-08-101-BRIDGE REP | Pavement Widening | 05/07/2010 |  |  | 53027895 | 5.098
10069 | Texas | VICTORIA |  | 14 | 2010652 | SPN:0143-10-045-ACP SURFACING : 0.2 MI. NORTH OF TROPICAL DRIVE 2.0 MI. NORTH IN VICTORIA | Pavement Improvement | 04/13/2010 | 06/11/2010 |  | 540933.46 | 2
10070 | Texas | TRAVIS | AUSTIN | 25 | 2010669 | SPN:0113-09-067-INSTALL SIDEWALKS & PED SIGNALS : WEST OF BRODIE LN STEARNS LN | Transportation Enhancements | 03/26/2010 | 04/20/2010 |  | 39391.25 | 0.1
10071 | Texas | HARRIS | HOUSTON | 07 | 2010673 | SPN:0912-70-029-ASPHALT OVERLAY : GRANT ROAD, LAKEWOOD FOREST DRIVE OLD KLUGE ROAD | Pavement Improvement | 05/18/2010 | 06/07/2010 |  | 330160.58 | 0.001
10072 | Texas | BELL |  | 31 | 2010688 | SPN:0015-06-082-RIGHT OF WAY ACQUISITION, UTILITY ADJUSTMENTS AND RELOCATION ASSISTANCE : AMITY ROAD US 190 | Other | 06/10/2010 |  |  | 2000000 | 5.637
10073 | Texas | TRAVIS | AUSTIN | 21 | 2010690 | SPN:2718-01-009-RECONST TO 4-LANE DIVIDED : RM 620 WEST 0.75 MI PROPOSED ANDERSON MILL RD | Pavement Widening | 05/28/2010 |  |  | 3637513.4 | 0.753
10074 | Texas | HARRIS | HOUSTON | 29 | 2010693 | SPN:8004-12-006-CONSTRUCT DETENTION POND : ON LITTLE YORK, ALDINE-WESTFIELD OVER HALLS BAYOU, NW CORNER | Other | 05/24/2010 | 06/09/2010 |  | 1825628.71 | 0.001
10075 | Texas | GREGG |  | 01 | 2010698 | SPN:0392-08-021-RESURFACE ROADWAY USING NOVA CHIP METHOD : 1.2 MI N OF US 80 IN LONGVIEW NORTH OF US 80 IN LONGVIEW | Pavement Improvement | 04/13/2010 | 05/24/2010 |  | 209734.1 | 1.084
10076 | Texas | WICHITA |  | 13 | 2010699 | SPN:0043-09-118-UPGRADE HIGHWAY ILLUMINATION : 0.25 MILES EAST OF MAURINE STREET US 287 | Safety/Traffic Management | 06/01/2010 |  |  | 409757.5 | 0.623
10077 | Texas | WICHITA | WICHITA FALLS | 13 | 2010700 | SPN:0043-09-119-UPGRADE HIGHWAY ILLUMINATION : IH 44 0.25 MILES NORTH OF LP 11 | Safety/Traffic Management | 06/01/2010 |  |  | 126752.22 | 1.4
10078 | Texas | WICHITA |  | 13 | 2010701 | SPN:0156-07-106-UPGRADE HIGHWAY ILLUMINATION : US 287 0.25 MILES WEST OF FM 890 | Safety/Traffic Management | 06/01/2010 |  |  | 131103.52 | 0.941
10079 | Texas | WICHITA |  | 13 | 2010702 | SPN:0685-01-026-UPGRADE HIGHWAY ILLUMINATION : US 287 SH 240 | Safety/Traffic Management | 06/01/2010 |  |  | 218908.71 | 1.706
10080 | Texas | MIDLAND |  | 11 | 2010705 | SPN:0887-01-033-ROADWAY REHABILITATION : CR 1150 CR 1140 | Pavement Improvement | 06/10/2010 |  |  | 1026131.67 | 1.02
10081 | Texas | DALLAM |  | 13 | 2010707 | SPN:0040-03-056-REHABILITATION (SBL) : 8.19 MILES SE OF FM 1879 0.99 MILES NE OF FM 1727 | Pavement Improvement | 05/17/2010 |  |  | 1194872.29 | 6.988
10082 | Texas | WICHITA | WICHITA FALLS | 13 | 2010708 | SPN:0156-04-103-CONSTRUCTION OF RAILROAD AT GRADE CROSSING ON FRONTAGE ROAD : ON FRONTAGE RD, 0.5 MI E OF BARNETT 0.4 MI W OF FAIRWAY BLVD (WB) | Safety/Traffic Management | 06/15/2010 |  |  | 265000 | 0.065
10083 | Texas | LIBERTY | HOUSTON | 02 | 2010709 | SPN:0920-02-082-OVERLAY EXISTING ROADWAY : SAN JACINTO, WASHINGTON BOOTHE IN CLEVELAND; SPN:0920-02-083-OVERLAY EXISTING ROADWAY : TRAVIS, HANSON BOOTHE IN CLEVELAND | Pavement Improvement | 05/05/2010 | 05/05/2010 |  | 129560.62 | 0.002
10084 | Texas | MIDLAND |  | 11 | 2010724 | SPN:1718-07-035-NEW LOCATION NON-FREEWAY : FM 1788 CR 60 | New Construction | 05/24/2010 | 06/14/2010 |  | 1788000 | 1.496
10085 | Utah | DUCHESNE |  | 3 | 0040051 | This project widens US 40 to three lanes from West Roosevelt to Ioka Junction | Pavement Widening | 01/21/2005 | 01/21/2005 |  | 3221599.66 | 2
10086 | Utah | SALT LAKE | SALT LAKE CITY | 3 | 0068049 | This project will reconstruct the intersection of 6200 South and Redwood Road to add capacity and improve traffic operations | Other | 03/16/2009 | 03/16/2009 | 07/31/2011 | 11090229.9 | 0.1
10087 | Utah | DAVIS | OGDEN | 1 | 0108024 | This project reconstructs and widens Syracuse Road (SR 108) from 1000 West to 2000 West in Syracuse | Pavement Widening | 07/12/2007 | 07/12/2007 | 04/30/2010 | 19999849.11 | 1
10088 | Utah | SALT LAKE | SALT LAKE CITY | 2 | 0209013 | This project improves intersection operations at 9000 South and 450 West by adding turn lanes and other improvments | Pavement Improvement | 10/06/2006 | 10/06/2006 |  | 705446.19 | 0
10089 | Utah | SAN JUAN |  | 3 | 0491005 | This project reconstructs the pavement on SR-491 from milepost 0 to Milepost 1.5 in Monticello, Utah | Pavement Improvement | 12/13/2007 | 12/13/2007 |  | 3800000 | 1.5
10090 | Utah | SUMMIT |  | 3 | 0846088 | This project rehabilitates the pavement on I-84 form the Morgan County Line to Henefer by removing some of the existing pavement and adding a structural overlay. | Pavement Improvement | 12/12/2005 | 12/12/2005 |  | 600000 | 3
10091 | Utah | SALT LAKE | SALT LAKE CITY | 2 | 2172004 | This project adds safety improvements and reconstructs 3900 South from Highland Drive to 2300 East | Pavement Improvement | 10/31/2003 | 10/31/2003 | 07/13/2010 | 4646265.54 | 4
10092 | Utah | UTAH | PROVO-OREM | 3 | 2896002 | This project reconstructs 50 South in American fork from 700 East to 1100 East | New Construction | 04/26/2005 | 04/26/2005 | 02/26/2010 | 2299000 | 4
10093 | Utah | CACHE |  | 1 | F002726 | This project constructs a new three lane roadway from 800 South to 300 South along new and existing alignments in Logan | New Construction | 02/08/2008 | 02/08/2008 | 09/30/2010 | 2860580 | 5
10094 | Utah | WEBER |  | 1 | F003664 | This project reconstructs the pavement and adds pedestrian ramps on Wall Avenue (SR-204) From 23rd Street to US-89 in Ogden | Pavement Improvement | 03/09/2009 | 03/09/2009 | 10/30/2009 | 5482736.55 | 1
10095 | Utah | SUMMIT |  | 1 | F004135 | This project rehabilitated the pavement on I-80 from Echo Junction to Emory by removal some of the existing asphalt and adding a structural overlay. | Pavement Improvement | 03/16/2009 | 03/16/2009 |  | 14014488 | 12
10096 | Utah | WEBER |  | 1 | F004474 | This project constructs a new Bike and Pedestrian Trail in Hooper, Utah | Transportation Enhancements | 12/14/2007 | 12/14/2007 | 11/30/2009 | 311098.3 | 0
10097 | Utah | TOOELE |  | 1 | F004592 | Install menian and shoulder barrier | Safety/Traffic Management | 04/15/2010 | 04/15/2010 |  | 48604.2 | 0
10098 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F004615 | This project adds auxillary lanes on I-15 from 10000 South to 7200 South. These lanes will improve traffic operations and capacity. | Pavement Widening | 02/10/2009 | 03/03/2009 | 12/02/2009 | 12100070.7 | 2
10099 | Utah | WASATCH |  | 2 | F004648 | This project will add passing lanes on US-189 from Heber to Provo Canyon. | Pavement Widening | 07/01/2009 | 07/01/2009 |  | 7693255.66 | 3
10100 | Utah | UTAH | PROVO-OREM | 3 | F004654 | This project reahbilitates the pavement on US-189 from University Parkway to Provo Canyon and improves and widens intersections. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 3030975.01 | 0.5
10101 | Utah | UTAH | PROVO-OREM | 3 | F004680 | This project adds an asphalt overlay on SR-92 from SR-74 to SR-146. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1486379.83 | 1.8
10102 | Utah | SALT LAKE |  | 3 | F004864 | This project rehabilitates the concrete pavement on I-215 from 4700 South to SR-201, repairing potholes and grinding to improve rideability. | Pavement Improvement | 03/17/2009 | 03/17/2009 | 03/31/2010 | 3854043.46 | 3
10103 | Utah | SALT LAKE |  | 3 | F004890 | This project rehabilitates the asphalt pavement on SR-111 (8400 West) from 3500 South to SR-201 in Salt Lake county by removing some of the existing asphalt and adding a structural overlay | Pavement Improvement | 03/10/2009 | 03/10/2009 | 10/01/2009 | 931153.47 | 1.9
10104 | Utah | UTAH | PROVO-OREM | 3 | F005122 | This project replaces 3 bridge decks on I-15 in the Payson, Utah area. | Bridge Improvement | 03/03/2009 | 03/03/2009 |  | 5850000 | 1
10105 | Utah | CARBON |  | 3 | F005269 | This project reconstructs the pavement on Carbonville Road near Price, Utah | Pavement Improvement | 10/13/2008 | 10/13/2008 | 06/30/2010 | 2101040.31 | 0
10106 | Utah | SUMMIT |  | 3 | F005667 | This project reconstructs Coalville Main Street and SR-280 in Coalville, Utah | Pavement Improvement | 11/24/2008 | 12/15/2008 | 03/31/2010 | 1211276.5 | 0
10107 | Utah | SUMMIT |  | 3 | F005671 | This project replaces two bridges on I-80 over Echo Frontage Road near Echo Junction. | Bridge Replacement | 12/23/2008 | 12/23/2008 |  | 3475000 | 1
10108 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F005693 | This project provides intersection improvements along 6200 South from 3000 East to I-215. | Pavement Widening | 03/10/2009 | 03/10/2009 | 03/31/2010 | 1567196.3 | 0
10109 | Utah | WEBER | OGDEN | 1 | F005706 | This project applied a chip seal to various locations on US-89 to improve skid resistance and extend pavement life. It also retrofitted existing and installed new pedestrian ramps. | Pavement Improvement | 06/12/2008 | 06/12/2008 |  | 1027511.25 | 0
10110 | Utah | CACHE |  | 1 | F005788 | This project applied a chip seal on SR-101 from SR-23 to SR-165 to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 | 05/08/2009 | 1958745.61 | 5.9
10111 | Utah | UTAH |  | 3 | F005828 | This project applied a thin bonded overlay to the pavement on I-15 from the Benjamin interchange to Spanish Fork. This improves skid resistance and extends pavement life. | Pavement Improvement | 01/14/2009 | 01/14/2009 |  | 1522351.89 | 3.95
10112 | Utah | SALT LAKE |  | 1 | F005952 | This project rehabilitates the asphalt pavement on SR-269 and SR-270 at various locations. | Pavement Improvement | 03/09/2009 | 03/09/2009 |  | 1745728.08 | 0
10113 | Utah | SALT LAKE |  | 2 | F005957 | This project rehabilitates the concrete pavement on I-215 from Milepost 5.709 to Milepost 7.585, repairing potholes and grinding to improve rideability. | Pavement Improvement | 01/13/2009 | 01/13/2009 |  | 978427.59 | 1.876
10114 | Utah | UTAH |  | 3 | F005965 | This project is bridge scour repair in various locations of Region 3. | Bridge Improvement | 11/04/2009 | 11/04/2009 |  | 236101.14 | 0
10115 | Utah | WASHINGTON |  | 2,3 | F005966 | This project is bridge scour repair for 7 bridges in Region 4. | Other | 11/04/2009 | 11/04/2009 |  | 80000 | 0
10116 | Utah | SAN JUAN |  | 3 | F005983 | This project applied a chip seal on US-191 from Milepost 73 to Milepost 86 to improve skid resistance and extend pavement life. | Pavement Improvement | 01/06/2009 | 01/06/2009 |  | 720852.47 | 13
10117 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F005993 | This project entails the deployment of varriable message signs throughout the Salt Lake Valley | Safety/Traffic Management | 11/04/2009 | 11/04/2009 |  | 432597.67 | 0
10118 | Utah | SANPETE |  | 3 | F005994 | This project applied a chip seal on US-89 from Milepost 227.6 to 267.2 and on SR-132 to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 937474.02 | 0
10119 | Utah | SEVIER |  | 3 | F005996 | This project applied a lane leveling asphalt overlay on SR-118 from Milepost 6.9 to 10.0. | Pavement Improvement | 03/19/2009 | 03/19/2009 |  | 822400 | 3.1
10120 | Utah | UTAH | PROVO-OREM | 3 | F006024 | This project applied a polymer overaly on six bridges, extending the life of the bridge decks. | Bridge Improvement | 04/01/2009 | 04/01/2009 |  | 227937.34 | 0
10121 | Utah | TOOELE |  | 1 | F006065 | This project applied a 1 1/2 inch overlay on SR-36 from the Junction of SR 73 to Three O'Clock drive in Tooele, Utah to improve ride, skid resistance and extend the life of the pavement. | Pavement Improvement | 06/04/2009 | 06/04/2009 |  | 1542398.49 | 9.89
10122 | Utah | MILLARD |  | 3 | F006071 | This project applied a asphalt wearing surface on I-15 from Milepost 158.5 to 169 to improve skid resistance and extend the pavement life. | Pavement Improvement | 03/09/2009 | 03/09/2009 | 03/31/2010 | 4956974.61 | 10.5
10123 | Utah | SEVIER |  | 3 | F006072 | This project rehabilitated the concrete pavement on I-70 from Mile post 6.8 to 17.7. This rehabilitation included slab replacment and joint sealing. | Pavement Improvement | 03/10/2009 | 03/10/2009 |  | 1194720 | 10.9
10124 | Utah | WASHINGTON |  | 2 | F006073 | This project applied an asphalt wearing surface on SR-9 form Mile post 0 to 4.9 to improve skid resistance and extend pavement life. | Pavement Improvement | 03/03/2009 | 03/03/2009 |  | 2127812.14 | 4.9
10125 | Utah | WASHINGTON |  | 2 | F006074 | This project constructs a new bridge over the Santa Clara River in St. George, Utah. | Bridge Replacement | 03/03/2009 | 03/03/2009 | 04/30/2010 | 3570000 | 0
10126 | Utah | STATEWIDE |  | 1 | F006076 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 1(Northern Utah). | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 179178.82 | 0
10127 | Utah | STATEWIDE |  | 2 | F006077 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 1 (Northern Utah). | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 153499.04 | 0
10128 | Utah | STATEWIDE |  | 1 | F006080 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 2 (Salt Lake Area). | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 356431 | 0
10129 | Utah | STATEWIDE |  | 3 | F006082 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 3 (Central Utah). | Transportation Enhancements | 04/01/2009 | 04/01/2009 | 12/31/2009 | 419351.19 | 0
10130 | Utah | STATEWIDE |  | 1 | F006084 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Cedar City District of Region 4. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 124042.28 | 0
10131 | Utah | STATEWIDE |  | 2 | F006085 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Price District of Region 4. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 133996.05 | 0
10132 | Utah | STATEWIDE |  | 3 | F006086 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Richfield District of Region 4. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 132311.86 | 0
10133 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006088 | This project constructed safe sidewalks and installed pedestrian ramps in various locatons on SR-171. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 173702 | 0
10134 | Utah | WEBER |  | 1 | F006089 | This project constructed safe sidewalks and installed pedestrian ramps on US-89; 400 South to 4400 South in Ogden, Utah. | Transportation Enhancements | 03/03/2009 | 03/03/2009 |  | 131840 | 0
10135 | Utah | DAVIS |  | 1 | F006090 | This project constructed safe sidewalks and installed pedestrian ramps on SR-107; 4000 West to 4050 West in West Point, Utah. | Transportation Enhancements | 03/03/2009 | 03/03/2009 |  | 53176.42 | 0.05
10136 | Utah | DAVIS |  | 1 | F006091 | This project constructed safe sidewalks and installed pedestrian ramps on SR-37; 3500 West to 3550 West, in Clinton, Utah. | Transportation Enhancements | 03/12/2009 | 03/12/2009 |  | 145000 | 0
10137 | Utah | SALT LAKE |  | 2 | F006092 | This project constructed safe sidewalks and installed pedestrian ramps on SR-266; Redwood Road to 550 West in Taylorsville, Utah. | Transportation Enhancements | 03/12/2009 | 03/12/2009 |  | 321287 | 0
10138 | Utah | DUCHESNE |  | 2 | F006093 | This project constructed safe sidewalks and installed pedestrian ramps on SR-87; 800 NOrth to 1400 North in Duchesne, Utah. | Transportation Enhancements | 03/03/2009 | 03/03/2009 |  | 181550.79 | 0
10139 | Utah | STATEWIDE |  | 2 | F006095 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Cedar City District of Region 4. | Transportation Enhancements | 03/17/2009 | 03/17/2009 |  | 46710.32 | 0
10140 | Utah | STATEWIDE |  | 3 | F006096 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Price District of Region 4. | Other | 03/03/2009 | 03/03/2009 |  | 92331.19 | 0
10141 | Utah | STATEWIDE |  | 1 | F006097 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Richfield District of Region 4. | Transportation Enhancements | 03/03/2009 | 03/03/2009 |  | 95182.01 | 0
10142 | Utah | SALT LAKE |  | 2 | F006099 | This project constructed safe sidewalks and installed pedestrian ramps in variouslocations on SR-48. | Transportation Enhancements | 03/12/2009 | 03/12/2009 |  | 94466 | 0
10143 | Utah | WEBER | LOGAN | 1 | F006109 | This project provided fiber optic connections on US-89 from I-84 to Harrison Blvd to improve traffic signal operations. | Safety/Traffic Management | 04/01/2009 | 04/01/2009 |  | 187881.76 | 0
10144 | Utah | SALT LAKE |  | 2 | F006110 | This project provided traffic signal interconnection on SR-190 & SR-210; Wasatch Boulevard from I-215 to Cottonwood Canyon to improve traffic operations. | Safety/Traffic Management | 04/01/2009 | 04/01/2009 | 06/22/2010 | 929197.12 | 1
10145 | Utah | SUMMIT |  | 1 | F006118 | This project constructs wildlife fence along I-80 in Parley's Canyon to enhance safety for both drivers and wildlife. | Other | 03/10/2009 | 03/10/2009 |  | 420000 | 1
10146 | Utah | GARFIELD |  | 2 | F006119 | This project extends the bike path along SR-12 in Garfield County | Transportation Enhancements | 03/31/2009 | 03/31/2009 | 01/25/2010 | 460424.35 | 1
10147 | Utah | TOOELE |  | 1 | F006120 | This project constructed a new roadway along 1000 North from SR-112 to 600 West in Tooele, Utah. | New Construction | 03/12/2009 | 03/12/2009 | 12/31/2010 | 3500000 | 0
10148 | Utah | DAVIS | OGDEN | 1 | F006121 | This project will reconstruct 500 South into a five-lane roadway with two lanes in each direction and a center turning lane. Additional improvements include 12-foot shoulders to accommodate on street | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 6257007.62 | 1
10149 | Utah | UTAH |  | 3 | F006123 | This project on US-89 widens the shoulders to accomodate bicycles and pedestrians. | Transportation Enhancements | 03/16/2009 | 03/16/2009 |  | 215027.6 | 0.5
10150 | Utah | UTAH | PROVO-OREM | 3 | F006146 | This project Expands and installs computer hardware and software to update the emergency data intregration in Region 3. Enancing the commuter link system and providing better traffic operations. | Safety/Traffic Management | 03/12/2009 | 03/12/2009 |  | 525999 | 0
10151 | Utah | DAVIS | OGDEN | 1 | F006147 | This project provides signal detection upgrades in Weber and Davis Counties | Other | 03/12/2009 | 03/12/2009 |  | 524999.57 | 0
10152 | Utah | WEBER | OGDEN | 1 | F006148 | This project installs conduit to on I-15 from Layton to Riverdale Road to enhance the commuter link program, improving traffic operations. | Safety/Traffic Management | 03/12/2009 | 03/12/2009 |  | 575289.7 | 7.459
10153 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006149 | This project expands the Advanced Traffic Management System (ATMS) through improvements to the signal interconnection in the Salt Lake County Area. | Safety/Traffic Management | 03/03/2009 | 03/03/2009 | 09/30/2010 | 999091.81 | 0
10154 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006150 | This project expands the Variable Message Signs in the downtown Salt Lake Area, enhancing traffic operations. | Safety/Traffic Management | 03/03/2009 | 03/03/2009 |  | 346997.7 | 0
10155 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006151 | This project provdes upgrades to the traffic operations systems (signals Variable Message Signs etc.) along Bangerter Highway from 90th South to SR-201. | Safety/Traffic Management | 03/12/2009 | 03/12/2009 |  | 195308.46 | 9.623
10156 | Utah | EMERY |  | 2 | F006152 | This project reconstructs the Goblin Valley (Temple Mountain Road in Emery County, Utah | Pavement Widening | 03/12/2009 | 03/12/2009 |  | 1719953.6 | 0
10157 | Utah | UTAH |  | 2 | F006161 | This project constructed safe sidewalks and installed pedestrian rampson SR-198 at various locations in Payson and Santaquin, Utah. | Transportation Enhancements | 04/01/2009 | 04/01/2009 |  | 183663.63 | 0
10158 | Utah | SALT LAKE | SALT LAKE CITY | 2 | F006188 | This project made intersection imporvements at 9000 South and 700 East in Sandy, Utah. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1047652.54 | 0
10159 | Utah | UINTAH |  | 1 | F006191 | This project made improvements to the signalized intersection on US-40 at 1000 South and 500 East in Vernal, Utah | Other | 04/01/2009 | 04/01/2009 | 12/31/2009 | 220000 | 1
10160 | Utah | UTAH | PROVO-OREM | 2 | F006241 | This project made repairs to the SR-189 bridge at 600 South University AVenue. | Bridge Improvement | 04/01/2009 | 04/01/2009 |  | 2500000 | 1
10161 | Utah | DUCHESNE |  | 2 | F006242 | This project repainted the structural steel on the US-40 Bridge over Starvation Reservoir. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1161940.24 | 1
10162 | Utah | DAVIS |  | 1 | F006243 | This project entails applying a chip seal to the existing SR-109 roadway surface between Fairfield Road (MP 1.07) and US-89 (MP 2.962) in Layton City, UT. After applying the chip seal, traffic contro | Pavement Improvement | 04/01/2009 | 04/01/2009 | 05/20/2009 | 483177.99 | 24
10163 | Utah | DAVIS |  | 1 | F006244 | This project applied microsurfacing to SR-273 From US-89 To 200 South in Kaysville to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 | 05/20/2009 | 606262.9 | 1.4
10164 | Utah | SALT LAKE |  | 2 | F006245 | This project applied an asphalt seal coat to SR-190 from 3000 East to the sR-210 in Salt Lake County to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 485074.58 | 1.55
10165 | Utah | SALT LAKE |  | 2 | F006246 | This project applied a 1 1/2 inch overaly on SR-173 from 3200 West to 1900 West in Salt Lake County | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 667642.96 | 1.28
10166 | Utah | SALT LAKE |  | 2 | F006247 | This project applied a 1 1/2 inch overaly on SR-173 from 5600 West to 4800 West in Salt Lake County | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 463990.38 | 0.98
10167 | Utah | CARBON |  | 3 | F006248 | This project provided surface treatements on SR-10 and SR-55 in Carbon County to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 2365525.05 | 0
10168 | Utah | DAVIS |  | 1 | F006250 | This project made safety improvements to I-215 from Redwood Road to I-15. | Safety/Traffic Management | 04/01/2009 | 04/01/2009 | 06/01/2009 | 134451.59 | 1.9
10169 | Utah | SANPETE |  | 3 | F006253 | This project applied a slurry seal to US-89; Ephraim, Manti, Panguitch Main Streets and Snow College roads to improve skid resistance and exxtend pavement life | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 486159.52 | 1.2
10170 | Utah | IRON |  | 1 | F006254 | This project applied a wearing course on SR-130 in Iron County from milepost 0 to 5 to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1052197.26 | 5
10171 | Utah | SALT LAKE |  | 2 | F006307 | This project applied a polymer overlay on US-89; State Street from 90th South to 106th South and on SR-71; 700 East. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 397774.24 | 0
10172 | Utah | SALT LAKE |  | 2 | F006308 | This project installed median cable barrier on SR-154 north of SR-201 in Salt Lake County. | Safety/Traffic Management | 04/01/2009 | 04/01/2009 |  | 400000 | 1
10173 | Utah | SALT LAKE |  | 2 | F006309 | This project rehabilitated the asphalt pavement on SR-186; Foothill Boulevard from Sunnyside AVenue to 1300 East in Salt Lake City. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1809432.01 | 1
10174 | Utah | UTAH |  | 3 | F006315 | This project applied a wearing surface on SR-114 from SR-89 in Provo to SR-89 In Pleasant grove to improve skid resistance and extend pavement life. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1758829.39 | 0
10175 | Utah | WEBER |  | 1 | F006316 | This project Removes existing asphalt to a depth of approximately 7 inches, and replaces with 7 inches on SR-204 from SR-26 to 32nd street . Once all paving is complete, the manholes will be raised. | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 1135110.35 | 0.924
10176 | Utah | IRON |  | 1 | F006338 | This project rehabilitates the asphalt pavement on SR-143 in Iron County from Milepost 2 to 2.4 and on SR-274 from Milepost 0.57 to 1.3 by removing some of the existing asphalt and adding a structural | Pavement Improvement | 04/01/2009 | 04/01/2009 |  | 216297 | 0
10177 | Utah | WEBER |  | 1 | F006359 | This is a structures bridge rehabilitation project that includes pothole patching, membrane & overlay for I-15 near clearfield, bridges F-63, F-66, F-80. | Pavement Widening | 09/24/2009 | 09/24/2009 |  | 1347445.52 | 4
10178 | Utah | WASHINGTON |  | 1 | F006383 | This is a chip seal project for SR-228; Leed's Main Street; MP 0 TO 1.821. | Pavement Improvement | 09/24/2009 | 09/24/2009 |  | 137360 | 1.821
10179 | Utah | SANPETE |  | 3 | F006412 | This project is prevenative maintenance chip seal on US-89; FAIRVIEW TO COUNTY LINE, MP 284 TO 297 | Pavement Improvement | 09/24/2009 | 09/24/2009 |  | 689640.11 | 12.909
10180 | Utah | UTAH |  | 3 | F006426 | This project is a pavement preservation chip seal for SR-164; MP 0 TO 2.67 & SR-147; MP 15 TO 17. | Pavement Improvement | 09/24/2009 | 09/24/2009 |  | 449226.91 | 0
10181 | Utah | UTAH |  | 3 | F006429 | This project is a pavement preservation chip seal for US-89; Boys Ranch to Birdseye. | Pavement Improvement | 09/24/2009 | 09/24/2009 |  | 255838.07 | 5.2
10182 | Utah | RICH |  | 1 | F006477 | This project is for the scope and design of the US-89; Swan Creek Box Culvert | Safety/Traffic Management | 03/09/2010 |  |  | 343274.32 | 0
10183 | Utah | UTAH |  | 3 | F006481 | This project is a safe sidewalk installation on SR-198 & SR-115 PAYSON; in Various Locations. | Transportation Enhancements | 09/24/2009 | 09/24/2009 |  | 322423 | 0
10184 | Utah | UTAH |  | 3 | F006661 | Install sidewalks and pedestrian features at the Manila Elementry in Pleasant Grove. | Transportation Enhancements | 04/14/2010 |  |  | 85684 | 0
10185 | Utah | DAVIS | OGDEN | 1 | F006667 | This project is part of the Region 1 Commuterlink Program and will connect the Layton City signal system in Weber County with the Traffic Operations Center in Salt Lake County. | Safety/Traffic Management | 11/04/2009 | 11/04/2009 |  | 326305 | 0
10186 | Utah | WEBER | OGDEN | 1 | F006668 | This project is part of the Region 1 Commuterlink Program and will connect 8 signals on US-89 in Weber County to the Traffic Operations Center in Salt Lake County. | Other | 01/01/2010 | 01/01/2010 |  | 55938 | 0
10187 | Utah | UTAH | PROVO-OREM | 3 | F006688 | This project rehabilitates the pavement on US-89 from 100 North to 800 North in Utah County, Region 3. | Pavement Improvement | 01/01/2010 | 01/01/2010 |  | 1552925.79 | 0
10188 | Utah | SEVIER |  | 3 | F006689 | This project is a chip seal on SR-118 from MP 6.893 to 10.042 in Region 4, Sevier County. | Pavement Improvement | 01/01/2010 | 01/01/2010 |  | 174000 | 3.149
10189 | Utah | SANPETE |  | 3 | F006690 | This project is a chip seal on SR-132 from Fountain Green to Moroni in Region 4, Sanpete County. | Pavement Improvement | 01/01/2010 | 01/01/2010 |  | 615000 | 10
10190 | Utah | UTAH |  | 3 | I156172 | This project applies a micro surface seal to the pavement on I-15 from SR-75 to the Provo River, improving and extending the pavement life. | Pavement Improvement | 01/18/2008 | 01/18/2008 |  | 3418222.91 | 5
10191 | Utah | UTAH |  | 3 | I156173 | This project rehabilitates the pavement on I-15 from 800 South, Payson to the Juab County Line by removal of some of the existing asphalt pavement and adding a structural overlay. | Pavement Improvement | 01/18/2008 | 01/18/2008 |  | 1883718.01 | 9.3
10192 | Utah | SALT LAKE |  | 2 | I803148 | This project replaces the I-80 bridges over 2300 East | Bridge Replacement | 02/23/2009 | 02/23/2009 |  | 5774416 | 1
10193 | Utah | SALT LAKE | SALT LAKE CITY | 2 | I803149 | This project widens the ramps from I-80 East bound to I-215 from a single off ramp to a dual off ramp, improving operations and capacity. | Pavement Widening | 02/05/2009 | 02/05/2009 | 12/04/2009 | 1454387.97 | 0.099
10194 | Utah | SANPETE |  | 3 | LC39009 | This project reconstructs the Pigeon Hollow Road from Pigeon Hollow to Spring City | Pavement Improvement | 12/12/2005 | 12/12/2005 |  | 2098832.3 | 0
10195 | Utah | UTAH | PROVO-OREM | 3 | LC49089 | This project constructs a new trail along the historic Utah South Rail line via the UPRR North Lehi line | Pavement Improvement | 05/27/2005 | 05/27/2005 | 04/10/2010 | 2399999.69 | 0
10196 | Utah | WASATCH |  | 3 | LC51008 | This project reconstructs Center Street in Heber City from Main Street to 1400 East | Pavement Improvement | 04/24/2007 | 04/24/2007 | 06/01/2010 | 1290303.2 | 1
10197 | Utah | WASHINGTON |  | 1 | LC53022 | This project reconstructs the roadway from 600 North to SR-9 in Hurricane | Pavement Improvement | 11/24/2003 | 11/24/2003 |  | 1290303.2 | 0
10198 | Utah | WASHINGTON |  | 1 | LC53034 | This project reconstructs and widens Washington Fields Road, including the Virgin River Bridge from Indian Springs Drive to Telegraph Road in Washington. | Pavement Widening | 04/24/2008 | 04/24/2008 |  | 1035000 | 0
10199 | Utah | WASHINGTON |  | 1 | LC53042 | This project realigns Hilton Drive and Black Ridge Drive to improve traffic operations | Pavement Improvement | 08/28/2007 | 08/28/2007 | 08/02/2010 | 2089374.4 | 0
10200 | Vermont | WINDHAM |  | 00 | 0114005 | This project is for the repair of a bridge on Town Highway 1, approximately 1 mile west of the junction with State Route 100, in Wardsboro. | Bridge Improvement | 03/11/2010 | 03/11/2010 | 10/01/2010 | 509634.18 | 0.02
10201 | Vermont | WINDSOR |  | 00 | 0136001 | Repaving the roadway | Pavement Widening | 04/02/2009 | 04/02/2009 | 10/16/2009 | 2262660.57 | 4.4
10202 | Vermont | RUTLAND |  | 00 | 0193495 | Reconstruction of the existing roadway to provide wider shoulders. | Pavement Widening | 11/04/2009 | 11/04/2009 | 06/29/2012 | 11456392.57 | 4.347
10203 | Vermont | CHITTENDEN | BURLINGTON | 00 | 0209006 | This project replaces deteriorated truss members and aging concrete deck, along with providing a wider and friendlier pedestrian walkway, for this historic steel truss bridge in the town of Richmond. | Bridge Improvement | 02/06/2009 | 02/06/2009 | 07/06/2009 | 1978999.21 | 0.06
10204 | Vermont | FRANKLIN |  | 00 | 0283009 | This project will construct a new concrete bridge deck and clean and paint the structural steel on bridge # 30 on Sate Route 118 in the Town of East Berkshire. This bridge crosses the Missisuoi River | Bridge Improvement | 02/12/2010 | 02/12/2010 | 08/26/2011 | 1918019.36 | 0.056
10205 | Vermont | WASHINGTON |  | 00 | 0283036 | This project improves motorist safety by replacing a functionally obsolete 3-span bridge with a long-lasting single-span weathering steel girder bridge utilizing a high performance concrete deck, a ne | Bridge Replacement | 04/06/2009 | 04/06/2009 | 06/18/2010 | 2301276.64 | 0.027
10206 | Vermont | CALEDONIA |  | 00 | 0302018 | This project replaces an antiquated and deficient bridge on State Route 15 with a fully modern structure. | Bridge Improvement | 06/15/2009 | 06/15/2009 | 11/30/2009 | 969891.15 | 0.018
10207 | Vermont | WASHINGTON |  | 00 | 0372009 | Replace exisitng Bridge #69 ON VT14 in East Montpelier. | Pavement Improvement | 10/16/2009 | 10/16/2009 | 10/01/2010 | 1420790.97 | 0.038
10208 | Vermont | WINDSOR |  | 00 | 0891054 | Repaving the roadway | Pavement Improvement | 04/10/2009 | 04/10/2009 | 11/13/2009 | 7948259.08 | 7.9
10209 | Vermont | WINDSOR |  | 00 | 0891055 | Repairing the existing pipes by putting new pipes inside the existing pipes. | Pavement Improvement | 04/07/2009 | 04/07/2009 | 10/30/2009 | 1301016.35 | 25.8
10210 | Vermont | WINDSOR, ORANGE |  | 00 | 0912072 | This is a safety project for the removal of ledge from the edge of the roadway on Interstate I-91 at various locations between milepoint 69 and 110 in both the northbound and southbound lanes | Pavement Improvement | 09/16/2009 | 09/16/2009 | 11/19/2010 | 3024403.49 | 37.9
10211 | Vermont | RUTLAND |  | 00 | 1443039 | Replace Deck Bridge #15 ON TH3 in Clarendon. | Bridge Improvement | 09/14/2009 | 09/14/2009 | 08/20/2010 | 411132.22 | 0
10212 | Vermont | RUTLAND |  | 00 | 1443045 | Replace existing Bridge #19 ON TH23 (SHORT STRUCTURE) in Chittenden. | Pavement Improvement | 10/28/2009 | 10/28/2009 | 10/29/2010 | 425255.55 | 0.07
10213 | Vermont | RUTLAND |  | 00 | 1443046 | Replace Bridge #20 ON TH23 (SHORT STRUCTURE) in Chittenden. | Pavement Improvement | 10/28/2009 | 10/28/2009 | 10/29/2010 | 385076.63 | 0.07
10214 | Vermont | ORLEANS |  | 00 | 1449028 | This project will replace a severely deteriorated Town Highway bridge for the Town of Brownington | Bridge Replacement | 03/20/2009 | 03/20/2009 | 11/06/2009 | 1087051.02 | 0
10215 | Vermont | WINDSOR |  | 00 | 2206001 | This is a paving project for 5 miles of US route 5 between Hartford and Norwich. This project also includes paving the Wilder State highway and safety improvements at the I-91 off ramp with the Wilder | Pavement Improvement | 06/22/2009 | 06/22/2009 | 10/16/2009 | 2080427.52 | 4.3
10216 | Vermont | ORANGE |  | 00 | 2213001 | This project resurfaces 11.2 miles of pavement on Vermont Route 25 between Bradford and Orange | Pavement Improvement | 07/22/2009 | 07/22/2009 | 10/30/2009 | 4601359.13 | 11.33
10217 | Vermont | FRANKLIN |  | 00 | 2217001 | This is a paving project for 11 miles of Vermont Route 104 between the Towns of Fairfax and Saint Albans starting at milepoint 6.8 in the town of Fairfax. | Pavement Improvement | 09/03/2009 | 09/03/2009 | 06/11/2010 | 3305425.65 | 11.653
10218 | Vermont | ORANGE |  | 00 | 2331001 | Resurface VT113 Chelsea-Vershire. | Pavement Improvement | 04/19/2010 | 04/19/2010 | 08/25/2010 | 6274795.24 | 7
10219 | Vermont | WINDHAM |  | 00 | 2401001 | Resurface 11.458 miles of roadway on VT 30 | Pavement Improvement | 06/01/2010 | 06/01/2010 | 10/15/2010 | 4358051.28 | 11.425
10220 | Vermont | WINDSOR |  | 00 | 2602001 | This project is for paving .8 miles of US Route 5 and the Norwich State Highway and . 5 miles of Vermont Route 10A | Pavement Improvement | 06/22/2009 | 06/22/2009 | 10/16/2009 | 2273988.98 | 1.6
10221 | Vermont | WASHINGTON |  | 00 | 2604001 | This is a paving project for 3 miles of US 2 in Montpelier from Bailey Ave to Granite Street | Pavement Improvement | 06/08/2009 | 06/08/2009 | 08/26/2009 | 2179801.92 | 2.8
10222 | Vermont | ORLEANS |  | 00 | 2613001 | Repaving the roadway | Pavement Improvement | 04/19/2010 | 04/19/2010 | 08/19/2010 | 4187711.98 | 5.622
10223 | Vermont | RUTLAND |  | 00 | 2614001 | This project will resurface approximately 5.1 miles along route 4A in the Towns of Fair Haven and Castelton to provide a much smoother and safer ride. In addition key drainage improvements will be ma | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/16/2009 | 2625839.72 | 5.1
10224 | Vermont | RUTLAND |  | 00 | 2615001 | This project will resurface approximately 1.6 miles of deteriorated pavement which will provide for a smoother and safer ride along Route 4A in the Town of Fair Haven. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/16/2009 | 1075645.17 | 1.6
10225 | Vermont | CHITTENDEN | BURLINGTON | 00 | 2616001 | This project is for paving 2.9 miles of Vermont Route 15 in Colchester and Essex starting at the Winooski/Colchester town Line. | Pavement Improvement | 04/03/2009 | 04/03/2009 | 10/02/2009 | 2683849.59 | 2.9
10226 | Vermont | CHITTENDEN | BURLINGTON | 00 | 2617001 | This project is for paving .25 miles of Vermont Route 15 from the US Route 7/ Vermont Route 15 intersection to the Winooski/Colchester line. This project aslo includes concrete repair on US Route 7 in | Pavement Improvement | 06/14/2009 | 06/14/2009 | 10/14/2009 | 2644395.38 | 0.8
10227 | Vermont | WASHINGTON |  | 00 | 2618001 | This project is for paving of .9 miles US Route 302 in Montpelier starting from the US Route 2/US Route 302 intersection. | Pavement Improvement | 06/08/2009 | 06/08/2009 | 08/26/2009 | 731254.74 | 0.9
10228 | Vermont | ADDISON |  | 00 | 2627001 | This project is for repaving 3 miles of Vermont Route 125 starting at mile point 1.0 in the Town of Middlebury and ending at MP 4.0 in the Town of Middlebury | Pavement Improvement | 05/10/2010 | 05/10/2010 | 10/05/2010 | 1830299.76 | 3.094
10229 | Vermont | WINDHAM, WINDSOR |  | 00 | 2628001 | Repaving the roadway | Pavement Improvement | 04/24/2009 | 04/24/2009 | 10/16/2009 | 4095863.87 | 9.4
10230 | Vermont | WINDSOR |  | 00 | 2701001 | This is a paving project for 1.5 miles of Vermont Route 14 starting at the US Route 5 intersection.This project also include paving .25miles of US 4 in Hartford. | Pavement Improvement | 06/08/2009 | 06/08/2009 | 10/16/2009 | 1455720.33 | 1.7
10231 | Vermont | FRANKLIN |  | 00 | 2714001 | This project is for the paving of 9.5 miles of Vermont Route 105 between the towns of Sheldon and Enosburgh. | Pavement Improvement | 04/26/2010 | 04/26/2010 | 07/26/2010 | 2528939.31 | 9.479
10232 | Vermont | ESSEX |  | 00 | 2724001 | REpaving the roadway | Pavement Improvement | 08/24/2009 | 08/24/2009 | 09/26/2010 | 6209476.04 | 7.781
10233 | Vermont | ESSEX |  | 00 | 2725001 | Repaving the roadway | Pavement Improvement | 08/24/2009 | 08/24/2009 | 09/24/2010 | 5895533.52 | 7.96
10234 | Vermont | CHITTENDEN | BURLINGTON | 00 | 2726001 | This project is for paving US Route 7 from the South Burlington/Burlington city line and extending north .2 miles to include the intersection of Interstate 189 | Pavement Improvement | 06/14/2009 | 06/14/2009 | 10/14/2009 | 857779.42 | 0.2
10235 | Vermont | CHITTENDEN | BURLINGTON | 00 | 2727001 | This project is for paving US Route 7 from the Intersate 189 intersection and extending north for .25 miles to Hadley Road | Pavement Improvement | 06/14/2009 | 06/14/2009 | 10/14/2009 | 655443.12 | 0.2
10236 | Vermont | ADDISON |  | 00 | 2803001 | This project is for repaving 6.5 miles of Vermont Route 125 starting at mile point 0.00 in the Town of Ripton and ending at MP 0.750 in the Town of Hancock | Pavement Improvement | 05/10/2010 | 05/10/2010 | 10/05/2010 | 4193272.08 | 6.536
10237 | Vermont | WASHINGTON |  | 00 | 6000015 | This project improves motorist safety by rehabilitating existing bridge abutments and replacing the bridge superstructure with a modern steel beam bridge in Barre City. | Bridge Improvement | 04/15/2009 | 04/15/2009 | 11/27/2009 | 1266315.22 | 0.02
10238 | Vermont | WASHINGTON |  | 00 | 6400031 | This project will rehabilitate the historic Taylor St. bridge (Bridge #5, Truss Bridge) over the Winooski River in Montpelier. | Transportation Enhancements | 12/16/2009 | 12/16/2009 | 11/12/2010 | 1746920.78 | 0.067
10239 | Vermont | CHITTENDEN | BURLINGTON | 00 | AREH001 | In Shelburne install side walk on Mt. Philo Rd. beginning at Wild Granger Rd and ending at Falls Rd. | Transportation Enhancements | 01/11/2010 | 01/11/2010 | 07/01/2010 | 113760 | 0
10240 | Vermont | CHITTENDEN | BURLINGTON | 00 | AREH002 | In South Burlington repave portions of the bikes paths through out town. | Transportation Enhancements | 05/01/2010 | 05/01/2010 | 07/01/2010 | 163948 | 0
10241 | Vermont | BENNINGTON, RUTLAND |  | 00 | AREH004 | On the Delaware and Hudson rail trail replace the decks of ten bridges in the towns of Poultney, Pawlet, and Rupert. | Transportation Enhancements | 02/04/2010 | 02/04/2010 | 08/06/2010 | 189000 | 0
10242 | Vermont | FRANKLIN |  | 00 | AREH005 | In Franklin on Square Rd. also know as Town Highway 16 install sidewalk. | Transportation Enhancements | 01/14/2010 | 01/14/2010 | 07/30/2010 | 12000 | 0
10243 | Vermont | GRAND ISLE |  | 00 | AREH006 | In North Hero resurface pedestrian path in Knights Point State Park. | Transportation Enhancements | 02/18/2010 | 02/18/2010 | 05/28/2010 | 17000 | 0
10244 | Vermont | WASHINGTON |  | 00 | AREH007 | In Montpelier on Vine St. replace existing pedestrian bridge. | Transportation Enhancements | 04/19/2010 | 04/19/2010 | 06/18/2010 | 166200 | 0
10245 | Vermont | CHITTENDEN | BURLINGTON | 00 | AREH008 | In Essex on Rt. 15 install sidewalk, curbing, and pedestrian signs. | Transportation Enhancements | 01/08/2010 | 01/08/2010 | 09/17/2010 | 208503 | 0.197
10246 | Vermont | RUTLAND |  | 00 | ARPV001 | Repave 1.6 miles of Maple St and 2.4 miles of Wipple Hollow Rd in West Rutland. | Pavement Improvement | 05/01/2010 | 05/01/2010 | 10/01/2010 | 480164 | 2.417
10247 | Vermont | GRAND ISLE |  | 00 | ARPV002 | This is repaving 2.4 miles of (TH 3) West Shore Road and 1.5 miles of (TH 2 0 Alburgh Springs Road | Pavement Improvement | 05/10/2010 | 05/10/2010 | 10/01/2010 | 416750 | 3.16
10248 | Vermont | ORLEANS |  | 00 | ARPV003 | This project will resurface 5.5 miles of Town Highway 1 in Barton. | Pavement Improvement | 01/05/2010 | 01/05/2010 | 09/10/2010 | 588250 | 5.53
10249 | Vermont | WASHINGTON |  | 00 | ARPV004 | Paving roadway | Pavement Improvement | 05/11/2010 | 05/11/2010 | 07/10/2010 | 248405.14 | 2.086
10250 | Vermont | CALEDONIA |  | 00 | ARPV005 | This project is for the resurfacing of Center Road in Hardwick. | Pavement Improvement | 06/07/2010 | 06/07/2010 | 08/07/2010 | 411178.1 | 4.58
10251 | Vermont | ADDISON |  | 00 | ARPV006 | Paving roadway | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/15/2010 | 297113 | 4.674
10252 | Vermont | CHITTENDEN | BURLINGTON | 00 | ARPV007 | This is a repaving project for Lake Road in the Town of Milton Vermont | Pavement Improvement | 01/13/2010 | 01/13/2010 | 06/25/2010 | 287883.14 | 2.538
10253 | Vermont | ORLEANS |  | 00 | ARPV008 | Paving roadway | Pavement Improvement | 02/09/2010 | 02/09/2010 | 10/01/2010 | 367163 | 2.51
10254 | Vermont | ORANGE |  | 00 | ARPV009 | This is repaving 4.6 miles of roadway on VT Route 132 in the Town of Strafford | Pavement Improvement | 01/05/2010 | 01/05/2010 | 08/13/2010 | 703027.26 | 4.63
10255 | Vermont | ORANGE |  | 00 | ARPV010 | Paving roadway | Pavement Improvement | 01/11/2010 | 01/11/2010 | 08/27/2010 | 482755.37 | 5.006
10256 | Vermont | RUTLAND |  | 00 | ARTB002 | This project will rehabilitate the bridge carrying VT 144 (Town Highway 2) over a stream | Bridge Improvement | 06/11/2010 | 06/11/2010 | 09/17/2010 | 373947.84 | 0
10257 | Vermont | LAMOILLE |  | 00 | ARTB003 | The Town of Belvidere will replace the deck on this Town highway covered bridge. This will improve the ride quality and extend the life of the bridge This project is on the Mill (Lumber) covered br | Bridge Improvement | 07/09/2010 | 07/09/2010 | 09/17/2010 | 56029.72 | 0
10258 | Vermont | WINDSOR |  | 00 | ARTB004 | Bridge rehabilitation | Pavement Improvement | 06/14/2010 | 04/20/2010 | 09/17/2010 | 185465 | 0
10259 | Vermont | FRANKLIN |  | 00 | ARTB005 | The Town of Enosburg will remove the top 2" of pavement on this Town highway bridge and place a waterproff membrane and then resurface with new pavement. This will improve the ride quality and extend | Bridge Improvement | 05/10/2010 | 05/10/2010 | 09/17/2010 | 222923.5 | 0
10260 | Vermont | ORANGE |  | 00 | ARTB007 | This project will rehabilitate the bridge that carries Scotch Hollow Road over Peach Brook. | Pavement Improvement | 06/16/2010 | 06/16/2010 | 09/30/2010 | 164850 | 0
10261 | Vermont | RUTLAND |  | 00 | ARTB008 | This project rehabilitates the bridge that carries Pinnacle Ridge Road over a small tributary of East Creek. | Bridge Improvement | 03/31/2010 | 03/31/2010 | 08/13/2010 | 348355 | 0
10262 | Vermont | CALEDONIA |  | 00 | ARTB009 | This project is for the rehabilitation of a bridge on US Route 2 (Portland St.) in St. Johnsbury, over the Passumpsic River and the Washington County Railroad. | Bridge Improvement | 06/10/2010 | 06/10/2010 | 12/01/2010 | 776349 | 0
10263 | Vermont | STATEWIDE |  | 00 | NWRT001 | Rehab two pedestrian trail surfaces. One in Newport, one running from St. Albans-Richford. | Transportation Enhancements | 02/18/2010 | 02/18/2010 | 07/02/2010 | 855395.29 | 0
10264 | Vermont | STATEWIDE |  | 00 | RAMP001 | Statewide design and reconstruct existing sidewalk ramps to make them ADA compliant. | Transportation Enhancements | 03/11/2010 | 03/11/2010 | 08/27/2010 | 457336.62 | 0
10265 | Vermont | CALEDONIA |  | 00 | SURF014 | REPAVING THE ROADWAY WITH A THIN BITUMINOUS SURFACE TREATMENT. | Pavement Improvement | 07/27/2009 | 07/27/2009 | 10/15/2010 | 2287445.31 | 9.42
10266 | Vermont | WASHINGTON, ORANGE |  | 00 | SURF015 | This project resurfaces 9.4 miles of pavement on US Route 302 between Barre and Orange. | Pavement Improvement | 06/14/2010 | 06/14/2010 | 08/17/2010 | 1522387.78 | 9.38
10267 | Vermont | CALEDONIA |  | 00 | SURF016 | This project resurfaces 2.2 miles of pavement on US Route 302 between Groton and Ryegate. | Pavement Improvement | 06/14/2010 | 06/14/2010 | 08/17/2010 | 444550.87 | 2.221
10268 | Virginia | BOTETOURT | ROANOKE | 06 | FS09001 | This project includes a slab removal on the right travel lane on both the NBL and SBL of I-81. On the SBL it will begin at the South end of Rte 640 overpass (exit 156) moving South for 4.3 miles. On | Pavement Improvement | 07/08/2009 | 08/03/2009 |  | 19457862 | 9.64
10269 | Virginia | HENRICO | RICHMOND | 07 | FS09002 | Conversion of CRCP pavement to composite; extensive pavement rehab. Project underway. Completion date June 2010. | Pavement Improvement | 07/16/2009 | 07/16/2009 |  | 6465729 | 3.28
10270 | Virginia | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09003 | "This project will repair the existing deterioriated concrete pavement and then place 3.5"" inches of asphalt over the existing concrete pavement on I-64 in the City of Chesapeake." | Pavement Improvement | 07/08/2009 | 08/10/2009 |  | 15627101 | 15.6
10271 | Virginia | WYTHE |  | 09 | FS09004 | Milling, paving and guardrail upgrade in Wythe County Northbound I-77 from mile posts 24.19 to 25.69 and 26.59 to 29.22; and on Southbound I-77 from mile posts 40.69 to 46.31. | Pavement Improvement | 07/01/2009 |  |  | 6257313 | 0
10272 | Virginia | WASHINGTON | BRISTOL (VA-TN) | 09 | FS09005 | Milling, paving and guardrail upgrade on Southbound I-81 from mile post 19.63 to 25.36 in Washington County. | Pavement Improvement | 08/04/2009 | 08/04/2009 |  | 2905650 | 5.73
10273 | Virginia | PRINCE EDWARD |  | 05 | FS09006 | This project includes milling the existing 24 foot wide pavement and existing paved shoulder (approx. 2 inches on each side) of Rte. 460 EBL from 1.35 miles East of Rte. 735 to the Nottoway County Lin | Pavement Improvement | 08/10/2009 | 08/10/2009 |  | 3166600 | 2.88
10274 | Virginia | STATEWIDE |  | 04 | FS09007 | Basic bituminous overlay on Routes 360 and 460 in Richmond district. Complete. | Pavement Improvement | 06/22/2009 | 06/22/2009 |  | 2123382 | 23.08
10275 | Virginia | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09008 | VDOT will patch and seal cracks in the exitsting asphalt on I-464 in the City of Chesapeake then place 1.5 inches of new asphalt over the existing asphalt surface. This project also will upgrade the | Pavement Improvement | 07/08/2009 | 07/22/2009 |  | 5428192 | 5.95
10276 | Virginia | STAFFORD | FREDERICKSBURG | 01 | FS09009 | I-95, basic bituminous overlay. Work in Spotsylvania County is complete and work in Stafford to be done next year. | Pavement Improvement | 07/15/2009 | 08/06/2009 |  | 10221032 | 16.7
10277 | Virginia | RICHMOND |  | 01 | FS09010 | Basic bituminous overlay, Route 3 and Route 360 in Lancaster and Richmond counties. Complete. | Pavement Improvement | 07/01/2009 | 07/29/2009 |  | 2933654 | 16.2
10278 | Virginia | FAUQUIER |  | 10 | FS09011 | This resurfacing project inludes mill and overlay of 17.21 miles in length on various routes in Warrenton Residency | Pavement Improvement | 06/09/2009 | 09/11/2009 |  | 3823687 | 17.27
10279 | Virginia | CULPEPER |  | 07 | FS09012 | This resurfacing project includes mill and overlay of 18.41 miles on various routes in Culpeper Residency of VDOT | Pavement Improvement | 06/16/2009 | 07/06/2009 |  | 2849924 | 18.41
10280 | Virginia | ALBEMARLE | CHARLOTTESVILLE | 07 | FS09013 | This resurfacing project is in Albemarle County of Culpeper District includes mill and overlay of 20.3 miles on various routes | Pavement Improvement | 07/08/2009 | 08/02/2009 |  | 3557080 | 20.39
10281 | Virginia | WARREN |  | 07 | FS09014 | Asphalt overlay, rumble strips and guardrail upgrade on Westbound I-66 from mile post 6.6 to 10.7 in Warren County. | Pavement Improvement | 06/09/2009 | 08/04/2009 |  | 1411053 | 4.1
10282 | Virginia | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09015 | Mill existing asphalt 2 inches and overlay with 2 inches of asphalt | Pavement Improvement | 07/06/2009 | 07/09/2009 |  | 3426970 | 9
10283 | Virginia | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | 10 | FS09016 | Milling existing asphalt 2 inches and overlay with 2 inches of asphalt | Pavement Improvement | 08/16/2009 | 08/16/2009 |  | 4442320 | 17.5
10284 | Virginia | STATEWIDE |  | 09 | FS09017 | ***There is a statewide 2009 Design-Build contract to rehab 119 structually deficient bridges to make non-deficient. These are not full replacements. This is only for bridges that carry routes with | Pavement Improvement | 11/12/2009 | 11/19/2009 | 09/25/2011 | 4101890 | 0
10285 | Virginia | STATEWIDE |  | 09 | FS09018 | See above.*** This project is for the rehab of bridges in the Bristol District. | Pavement Improvement | 11/12/2009 | 11/19/2009 | 09/25/2011 | 6498250 | 0
10286 | Virginia | STATEWIDE |  | 05, 06 | FS09019 | See above.*** This project is for the rehab of culverts in the Lynchburg District. | Pavement Improvement | 11/11/2009 | 11/11/2009 | 09/25/2011 | 3961744 | 0
10287 | Virginia | STATEWIDE |  | 05 | FS09020 | See above.*** This project is for the replacement of superstructures in the Lynchburg District. | Pavement Improvement | 11/11/2009 | 11/18/2009 | 09/25/2011 | 12230600 | 0
10288 | Virginia | STATEWIDE | ROANOKE | 05 | FS09021 | See above.*** This project is for the replacement of culverts in the Salem District. | Pavement Improvement | 11/04/2009 | 11/09/2009 |  | 788100 | 0
10289 | Virginia | STATEWIDE |  | 05, 06 | FS09022 | See above.*** This project is for the replacement of culverts in the Stauton District. | Pavement Improvement | 11/04/2009 | 11/09/2009 |  | 482400 | 0
10290 | Virginia | STATEWIDE | FREDERICKSBURG | 01 | FS09023 | See above.*** This project is part of the bridge rehab for the Fredericksburg District. | Pavement Improvement | 11/04/2009 | 11/09/2009 |  | 3274583 | 0
10291 | Virginia | STATEWIDE |  | 01, 04, 07 | FS09024 | See above.*** This project is part of the bridge rehab for the Richmond District. | Pavement Improvement | 11/04/2009 | 11/09/2009 |  | 5955104 | 0
10292 | Virginia | FRANKLIN | ROANOKE | 05 | FS09027 | See above.*** This project is part of the bridge rehab for the Salem District. | Pavement Improvement | 11/11/2009 |  | 09/25/2011 | 930200 | 0
10293 | Virginia | SPOTSYLVANIA | FREDERICKSBURG | 1 | FS09029 | Design Build project to widen Route 3. Project recently awarded and design is proceeding; construction to begin in Spring. | Pavement Widening | 11/10/2009 | 11/10/2009 | 07/10/2012 | 25214915 | 1.21
10294 | Virginia | STATEWIDE | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01, 03 | FS09030 | This project will widen a 3.15 mile section of Route 105 in the City of Newport News and York County from 2 existing lanes to a 4 lane divided principle arterial.? | Pavement Widening | 10/20/2009 | 11/02/2009 |  | 19795937 | 6.8
10295 | Virginia | SMYTH |  | 09 | FS09031 | Milling, paving and guardrail upgrade on Northbound and Southbound I-81 from mile posts 34.25 to 35.35 (on NBL) and 35.35 to 34.32 (on SBL) in Smyth County. | Pavement Improvement | 07/23/2009 | 09/16/2009 | 06/01/2010 | 1795745 | 2.13
10296 | Virginia | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09032 | This project will repair cracks and patch the exisitng deteriorated pavement and then place a thin layer of asphalt of the existing pavement. | Pavement Improvement | 07/08/2009 | 07/24/2009 |  | 7677483 | 12.83
10297 | Virginia | BOTETOURT |  | 06 | FS09039 | This project will resurface and upgrade the guarrails on a portion of Rte. 220 and Rte. 58. | Pavement Improvement | 08/25/2009 | 02/16/2010 |  | 2919572 | 14.38
10298 | Virginia | MADISON |  | 07 | FS09040 | This project will provide smooth surface by milling and overlaying a portion of Route 230, 231 and 29 in Culpeper. | Pavement Improvement | 07/08/2009 | 07/15/2009 |  | 2253695 | 15.6
10299 | Virginia | STATEWIDE |  | 05 | FS09041 | Districtwide pavement overlay in Lynchburg District. | Pavement Improvement | 10/01/2009 | 10/20/2009 |  | 335869 | 2.97
10300 | Virginia | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | 01 | FS09044 | Construction of walkways at Marine Corps Heritage Center | Transportation Enhancements | 05/25/2010 | 06/03/2010 |  | 500000 | 0
10301 | Virginia | SPOTSYLVANIA | STATEWIDE | 01, 07 | FS09053 | This project is for Route 208 - Spotsylvania Courthouse Bypass - Phase II | Pavement Widening | 05/12/2010 | 05/27/2010 | 11/15/2012 | 11534887 | 4.416
10302 | Virginia | ALBEMARLE | CHARLOTTESVILLE | 05 | FS09056 | Widen the westbound exit approach lane of Interstate 64 starting at the westbound exit lane for 5th Street and widening to the intersection with Route 631, all in Albemarle County. | Safety/Traffic Management | 06/14/2010 | 06/14/2010 |  | 850271 | 0
10303 | Virginia | STAFFORD | FREDERICKSBURG | 01 | FS09058 | This project is for ARRA Route 630 - Bridge Over CSX Railroad (Structure #6040) | New Construction | 04/28/2010 | 05/12/2010 | 09/15/2011 | 4767194 | 0
10304 | Virginia | DANVILLE CITY | DANVILLE | 05 | FS09065 | This work is for improving the Grade, Drainage, Asphalt Pavement and the Robertson Bridge from the Intersection of Memorial Drive to 0.322 mi N. of the Intersection with Memorial Drive in the City of | New Bridge Construction | 06/01/2010 | 06/02/2010 |  | 16892680 | 0.32
10305 | Virginia | ROCKINGHAM | HARRISONBURG | 06 | FS09067 | Widening of Port Republic Road (Route 253) to 4 lanes from about a quarter mile (1150 feet) south of Route 704 (Boyers Road) to approximately 100 feet north of Harrisonburg East City Limits in Rocking | Pavement Widening | 03/16/2010 | 03/16/2010 |  | 13142797 | 0
10306 | Virginia | HAMPTON CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01, 02, 03 | FS09069 | This 3.4 mile long maintenance project will remove and replace approximately 2 inches of asphalt from Colliseum Drive to King Street and from Big Bethel Road to the Western City Limits | Other | 09/11/2009 | 09/22/2009 |  | 10000 | 0
10307 | Virginia | HAMPTON CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01, 02, 03 | FS09073 | Purchasing right of way and moving utilities in preparation of widening of Commander Shepard Boulevard from the intersection of Saunders and Big Bethel Roads to approximately 100 feet (0.019miles) we | Other | 12/30/2009 | 01/04/2010 |  | 3587296 | 0
10308 | Virginia | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02, 03 | FS09081 | Rail, roadway and infrastructure improvements at the Norfolk International Marine Terminal to improve train loading and unloading capabilities resulting in time savings, costs to shippers and reducing | Other | 02/22/2010 | 03/08/2010 |  | 11305958 | 3.92
10309 | Virginia | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09084 | This maintenance project on 12 bridges in the City of Chesapeake will seal cracks in the bridge decks and other preventative maintenance activities as warranted. Only Engineering funding is obligated | Other | 09/25/2009 | 10/05/2009 |  | 4500 | 0
10310 | Virginia | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09086 | This maintenance project will perform preventative maintenance and help preserve the condition of various roadways in the City of Chesapeake. Only Engineering funding is obligated at this time. | Other | 09/25/2009 | 10/05/2009 |  | 4500 | 0
10311 | Virginia | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01, 03 | FS09091 | This maintenance project will remove and replace 2 inches of asphalt on 6.5 miles of various routes in the City of Newport News including: Jefferson Ave. from Hemlock Rd. to 0.32 Mi. S. J. Clyde Morri | Other | 09/25/2009 | 10/05/2009 |  | 9846 | 0
10312 | Virginia | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02, 03 | FS09096 | This project will include repairing cracked and deterioriated beams and piers as well as other maintenance activities on the Norview Avenue Bridge in the City of Norfolk. Only Engineering funding is | Other | 09/24/2009 | 10/01/2009 |  | 5000 | 0
10313 | Virginia | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02, 03 | FS09098 | This maintenance project in the City of Norfolk will repave varoius routes within the City limits as determined by the City. Only Engineering funding is obligated at this time. | Other | 09/25/2009 | 10/05/2009 |  | 5014 | 0
10314 | Virginia | SUFFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09106 | This project will repave various sections of primary and secondary Routs as determined by the City of Suffolk. Only Engineering funding is obligated at this time. | Other | 09/25/2009 | 10/05/2009 |  | 3000 | 0
10315 | Virginia | WILLIAMSBURG CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09109 | This project will repave varoius routes within the City of Williamsburg. Only Engineering funding is obligated at this time. | Other | 09/25/2009 | 10/05/2009 |  | 10000 | 0
10316 | Virginia | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | 11 | FS09113 | ARRA Rt. 3000 Prince William Parkway (update to six-lanes) | Pavement Widening | 05/12/2010 | 05/12/2010 |  | 6771669 | 0
10317 | Virginia | RICHMOND CITY | RICHMOND | 04 | FS09138 | ARRA - COLONIAL HEIGHTS RESURFACING - CN ONLY | Pavement Improvement | 05/11/2010 | 05/16/2010 |  | 686070 | 0
10318 | Virginia | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 03, 04 | FS09168 | ARRA - Route 17 Turn Lane Improvement | Other | 12/16/2009 | 12/18/2009 |  | 5000 | 0
10319 | Virginia | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09170 | ARRA - Isle of Wight 58 Pavement Overlay | Other | 12/16/2009 | 12/22/2009 |  | 1000 | 0
10320 | Virginia | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09175 | ARRA - Isle of Wight 460 UPS Battery Back-up Systems | Other | 12/16/2009 | 12/22/2009 |  | 1500 | 0
10321 | Washington | SNOHOMISH |  | 2 | 0002300 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 05/28/2009 | 06/01/2009 | 10/12/2009 | 1833769.79 | 5.23
10322 | Washington | PEND OREILLE |  | 5 | 0002301 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 06/24/2009 | 07/20/2009 | 10/07/2009 | 5529554.68 | 12.68
10323 | Washington | LINCOLN |  | 5 | 0002302 | Construct a new sidewalk and pedestrian crossing that will provide safer passage for pedestrians to cross from Wilbur Street. | Safety/Traffic Management | 07/15/2009 | 08/03/2009 | 12/31/2009 | 160000 | 0.36
10324 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 0002821 | Improve the capacity and safety of the intersection by constructing additional traffic lanes and turn lanes. | Pavement Widening | 02/01/2010 |  |  | 2292401 | 0
10325 | Washington | THURSTON, GRAYS HARBOR |  | 06, 03 | 0008012 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 11/18/2009 |  | 07/15/2010 | 1500000 | 20.63
10326 | Washington | COLUMBIA |  | 05 | 0012194 | Add landscaping and irrigation system to the West entrance into the City of Dayton along US 12. | Transportation Enhancements | 09/14/2009 |  |  | 144169.27 | 0.166
10327 | Washington | KLICKITAT |  | 4 | 0014062 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 06/10/2009 | 07/27/2009 | 08/22/2009 | 412012.96 | 5.36
10328 | Washington | CLARK |  | 03 | 0014063 | Construct a pedestrian tunnel underneath State Route 14 to improve pedestrian access and safety. | Transportation Enhancements | 07/06/2009 |  |  | 506783 | 0.02
10329 | Washington | JEFFERSON |  | 06 | 0020163 | Construct roundabouts, center median, sidewalks, drainage, bike lanes, and turn lanes. | Pavement Widening | 09/15/2009 |  |  | 1959623 | 0.795
10330 | Washington | SNOHOMISH |  | 02 | 0045005 | Construction of a pedestrian and bike trail on the south side of 188th Street between 59th Avenue and 67th Avenue in Arlington. | Transportation Enhancements | 09/08/2009 |  |  | 122000 | 0.57
10331 | Washington | COWLITZ |  | 3 | 0051270 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 03/17/2010 | 07/01/2009 |  | 2394000 | 17.33
10332 | Washington | COWLITZ |  | 3 | 0051277 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 06/02/2009 | 06/24/2009 | 11/05/2009 | 6741921 | 7.01
10333 | Washington | CLARK |  | 3 | 0051278 | Constructs a new interchange that includes a wider bridge across I-5 and reconstruct the I-5 on and off ramps. | Bridge Replacement | 08/25/2009 | 09/09/2009 | 11/15/2011 | 8200000 | 1.21
10334 | Washington | CLARK, COWLITZ | PORTLAND-VANCOUVER, OR-WA | 3 | 0051281 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 08/17/2009 | 08/17/2009 | 03/12/2010 | 1475480 | 14.76
10335 | Washington | LEWIS, COWLITZ |  | 3 | 0051283 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 02/02/2010 |  |  | 5136067 | 0
10336 | Washington | LEWIS |  | 3 | 0052202 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 05/28/2009 | 06/19/2009 | 06/30/2010 | 2754590.95 | 13.29
10337 | Washington | PIERCE | SEATTLE-TACOMA, WA | 9 | 0053948 | This project will construct HOV lanes to relieve congestion and reduce the risk of collisions. | Bridge Replacement | 07/23/2009 | 08/06/2009 | 11/11/2011 | 35388653 | 2.89
10338 | Washington | THURSTON, PIERCE | SEATTLE-TACOMA, WA | 03,09 | 0053949 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 11/23/2009 |  |  | 9329697 | 21.94
10339 | Washington | PIERCE | TACOMA | 6 | 0053951 | This project reconstructs the eastbound interchange at I-5 and SR 16. This includes replacing the bridges over Nalley Valley, constructing freeway connections, reconstructing all of the ramp roadways | Other | 06/09/2009 | 06/09/2009 | 07/05/2011 | 6227940 | 1
10340 | Washington | SNOHOMISH |  | 2 | 0054272 | Install fiber, cameras and data stations in the corridor. Compliments conduit installation as part of the median barrier project. | Safety/Traffic Management | 07/07/2009 | 07/27/2009 | 12/03/2010 | 2500000 | 10.58
10341 | Washington | SKAGIT, SNOHOMISH |  | 2 | 0054277 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 06/18/2009 | 07/20/2009 | 05/14/2010 | 6225239.12 | 6.1
10342 | Washington | OKANOGAN |  | 05 | 0097137 | Construct curb; gutter; sidewalk; lighting; and stormwater drainage on US 97, 16th Ave, and Juniper St. | Transportation Enhancements | 09/08/2009 |  |  | 491383 | 1.58
10343 | Washington | KLICKITAT |  | 4 | 0097140 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 06/16/2009 | 07/20/2009 | 09/30/2009 | 3199516 | 23.32
10344 | Washington | DOUGLAS |  | 4 | 0097148 | Overlay roadway pavement with a chip seal | Pavement Improvement | 04/19/2010 |  |  | 1885373 | 0
10345 | Washington | KING | SEATTLE-TACOMA, WA | 07 | 0099078 | Construct a bridge to separate railroad and vehicle traffic on Duwamish Avenue South. | New Construction | 11/30/2009 |  |  | 2875171 | 0.2
10346 | Washington | GRAYS HARBOR |  | 06 | 0101318 | Remove and replace existing deteriorated curbs and sidewalks, along Heron Street from K Street to F Street. | Transportation Enhancements | 06/18/2009 |  | 08/25/2009 | 614448 | 0.4
10347 | Washington | MASON |  | 06 | 0101328 | Widen State Route 101; and provide intersection lighting, a pedestrian actuated signal, asphalt overlay of existing pavement, landscaping, road signs, and striping. | Pavement Widening | 05/24/2010 |  |  | 541220 | 0
10348 | Washington | GRAYS HARBOR |  | 06 | 0108006 | Construct new sidewalk on the north side of Simpson Avenue, from 5th Street to 10th Street; and reconstruct existing sidewalk on the south side of Simpson Avenue from 6th Street to 10th Street. | Transportation Enhancements | 03/01/2010 |  |  | 234309 | 0.32
10349 | Washington | KING | SEATTLE-TACOMA, WA | 01 | 0110008 | Construct a missing trail link between NE 195th Street and North Creek Parkway, construct pedestrian signals at two locations, and construct a 100-foot pedestrian bridge. | Transportation Enhancements | 01/19/2010 |  |  | 500000 | 0.75
10350 | Washington | KING | SEATTLE-TACOMA, WA | 01 | 0110009 | Construct a pedestrian bridge over North Creek north of 228th Street SE, and construct approximately 0.75 miles of an asphalt paved path. | Transportation Enhancements | 01/19/2010 |  |  | 600000 | 0.61
10351 | Washington | PIERCE |  | 08 | 0162017 | Reconstruction of State Route 162 between Calistoga and Bridge Streets. Includes signalization, addition of left turn lanes, installation of street lighting, and landscaping. | Pavement Improvement | 09/08/2009 |  |  | 420000 | 0.26
10352 | Washington | KING | SEATTLE-TACOMA, WA | 09 | 0167044 | Provide a bypass for surface water draining into the Rainier Ave South pump station. | Other | 09/21/2009 |  |  | 1948674 | 0.22
10353 | Washington | WHITMAN |  | 5 | 0195045 | Hot mix asphalt paving with basic safety restoration | Pavement Improvement | 05/06/2010 |  | 11/01/2010 | 2150000 | 0
10354 | Washington | WHITMAN |  | 5 | 0195046 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 07/17/2009 | 10/05/2009 | 05/12/2010 | 118868 | 17.75
10355 | Washington | SPOKANE | SPOKANE | 5 | 0195047 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project also includes some h | Pavement Improvement | 11/10/2009 |  |  | 2534112 | 4.56
10356 | Washington | STEVENS |  | 05 | 0205002 | Replace existing timber bridge with new concrete bridge. | Pavement Improvement | 09/02/2009 |  |  | 350000 | 0.01
10357 | Washington | SPOKANE |  | 5 | 0206003 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 06/17/2009 | 07/31/2009 | 09/01/2009 | 672508.59 | 2.44
10358 | Washington | OKANOGAN |  | 05 | 0215006 | Construct sidewalk along Okoma Drive from Jasmine St. to W. 4th Avenue. Also includes installation of sidewalk ramps at intersections; crosswalks; and new curbs. | Transportation Enhancements | 08/10/2009 |  |  | 166002 | 0.91
10359 | Washington | SPOKANE | SPOKANE | 05 | 0278001 | Remove and replace sidewalk on west side of First Street and both sides of Emma Street. Includes curbs, driveway approaches, curb ramps, and crosswalk striping where necessary. | Transportation Enhancements | 04/26/2010 |  |  | 319569 | 0.2
10360 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 0365007 | Pavement repairs and resurfacing of Dayton St. (5th Ave S to Admiral Way), 212th St SW (72nd Ave W to 84th Ave W), 220th St SW (SR 99 to 84th Ave W), and Olympic View Dr (76th Ave to Puget Dr). | Pavement Improvement | 09/21/2009 |  |  | 999985 | 2
10361 | Washington | STEVENS |  | 05 | 0395081 | Construct sidewalks and drainage improvements along US 395 from Juniper Street to Kettle Falls City limits. | Transportation Enhancements | 09/08/2009 |  |  | 43174 | 0.44
10362 | Washington | STEVENS |  | 5 | 0395088 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 06/22/2009 | 07/27/2009 | 09/08/2009 | 1965828.76 | 6.69
10363 | Washington | STEVENS |  | 5 | 0395089 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 06/30/2009 | 07/22/2009 | 11/02/2009 | 6200426.3 | 22.27
10364 | Washington | SPOKANE |  | 5 | 0395090 | High tension cable median barrier will be installed to reduce the frequency and severity of crossover collisions. | Safety/Traffic Management | 05/03/2010 |  | 10/22/2010 | 532271 | 0
10365 | Washington | BENTON |  | 04 | 03EI001 | Construct new sidewalks on 7th Street from Ellen Avenue to the North City Limits. | Transportation Enhancements | 09/21/2009 |  |  | 207000 | 0.436
10366 | Washington | WAHKIAKUM |  | 03 | 0409001 | Replace the existing Puget Island ferry ramp. | Bridge Replacement | 08/18/2009 |  |  | 590000 | 0.02
10367 | Washington | COWLITZ | LONGVIEW (OR) | 3 | 0433010 | Clean and paint the remaining steel elements on SR 433/Lewis and Clark Bridge. | Bridge Improvement | 04/30/2009 | 04/30/2009 | 10/26/2013 | 12500000 | 0.54
10368 | Washington | COWLITZ |  | 3 | 0503023 | Grind, Inlay and overlay pavement with hot-mix asphalt | Pavement Improvement | 05/04/2010 |  |  | 2281229 | 0
10369 | Washington | THURSTON |  | 03 | 0507024 | Pedestrian and street lighting improvements on Sussex Avenue from Ritter Street to Ragless Street. | Transportation Enhancements | 09/28/2009 |  |  | 554000 | 0.4
10370 | Washington | KING | SEATTLE-TACOMA, WA | 09 | 0509020 | Reconstruct 1st Ave SW between SW 192nd and SW 200th Streets to include three vehicle lanes, bike lanes, street lights, landscaping, and sidewalk. | Pavement Improvement | 08/03/2009 |  |  | 3834000 | 0.5
10371 | Washington | KING | SEATTLE-TACOMA, WA | 08 | 0520042 | Construct a new bridge over State Route 520. Bridge includes two vehicle lanes, bike lanes, sidewalks, street lighting. | New Bridge Construction | 05/12/2009 |  |  | 4594075 | 0.5
10372 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 0529017 | Widen sidewalk along West Marine View Drive to improve pedestrian/bicycle safety. | Transportation Enhancements | 09/28/2009 |  |  | 1288073 | 0.53
10373 | Washington | GRAYS HARBOR |  | 6 | 0560006 | New sidewalk and sidewalk ramps on State Route 101 and 7th St, Simpson, 8th St, L St, K St, 6th St, J St, 5th St, H St, Emerson, Jefferson, Grant, Cleveland, 4th St, Riverside, Sumner, 24th St. | Transportation Enhancements | 10/13/2009 | 10/13/2009 | 03/01/2010 | 195000 | 0
10374 | Washington | PACIFIC |  | 03 | 0575004 | Construct beach/ocean scenic overlook at Beards Hollow on State Route 100. | Transportation Enhancements | 10/09/2009 |  |  | 100000 | 0
10375 | Washington | THURSTON | OLYMPIA | 09 | 0643005 | Construct missing segments of the Woodland Trail from the Chehalis-Western Regional Trail to the Woodland Creek Community Park through the City of Lacey. | Transportation Enhancements | 06/26/2009 |  |  | 1000000 | 2.4
10376 | Washington | YAKIMA | YAKIMA | 4 | 0822128 | This project will rearrange the interchange to increase safety, relieve congestion and improve traffic flow movements. | Bridge Replacement | 03/10/2010 | 04/01/2010 | 10/15/2011 | 18768218 | 1.8
10377 | Washington | YAKIMA |  | 4 | 0822131 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 06/10/2009 | 07/07/2009 | 10/28/2009 | 5952408 | 14.73
10378 | Washington | YAKIMA |  | 4 | 0822132 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 03/19/2010 |  |  | 4584688 | 0
10379 | Washington | KITTITAS, KING |  | 04,08 | 0901476 | Replace the existing traveler information cameras in the Snoqualmie Pass vicinity with low light cameras to provide improved visibility of roadway conditions at night. | Safety/Traffic Management | 05/19/2009 | 08/10/2009 | 11/24/2009 | 60000 | 91.71
10380 | Washington | KING | SEATTLE-TACOMA, WA | 7 | 0901478 | Replacing broken concrete panels, grinding the existing concrete roadway surface and installing dowel bars to extend the service life of the pavement. | Pavement Improvement | 01/08/2010 |  | 05/13/2010 | 7456270 | 0
10381 | Washington | KITTITAS |  | 4 | 0902259 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 04/15/2009 | 04/27/2009 | 07/09/2009 | 2403340.87 | 3.73
10382 | Washington | KITTITAS |  | 4 | 0902260 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 04/15/2009 | 05/06/2009 | 08/03/2009 | 2729838.46 | 4.68
10383 | Washington | KITTITAS |  | 4 | 0902283 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 06/17/2009 | 07/07/2009 | 10/26/2009 | 3440325.89 | 3.21
10384 | Washington | KITTITAS |  | 4 | 0902302 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 06/15/2009 | 07/07/2009 | 07/30/2010 | 15337698.47 | 9.5
10385 | Washington | KITTITAS |  | 4 | 0902315 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 04/30/2009 | 04/30/2009 | 10/28/2011 | 16304322 | 5.5
10386 | Washington | SPOKANE |  | 5 | 0902319 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 07/17/2009 | 10/05/2009 | 05/12/2010 | 32751 | 11.84
10387 | Washington | GRANT |  | 4 | 0904118 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 08/04/2009 | 08/24/2009 | 10/28/2009 | 3754574.74 | 6.17
10388 | Washington | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 09WA004 | Reconstruct North Parkway Avenue from North Onsdorff Boulevard to N 5th Street. The road will include three traffic lanes, curb & gutter, sidewalks, landscaping, and street lighting. | Pavement Widening | 10/02/2009 |  |  | 43788 | 0.45
10389 | Washington | KING | SEATTLE-TACOMA, WA | 09 | 1073004 | Construct new curb, gutter, and sidewalk along East Valley Highway between S. 212th St. and State Route 167; add a third vehicle lane; and traffic signal improvements. | Pavement Widening | 07/27/2009 |  |  | 2000000 | 0.85
10390 | Washington | SPOKANE | SPOKANE | 05 | 1220021 | Construct a 4.4 mile long trail to connect to an existing trail. Includes the rehabilitation of 5 bridges and trailhead facility. | Transportation Enhancements | 07/07/2009 |  |  | 778317 | 4.4
10391 | Washington | KING | SEATTLE-TACOMA, WA | 09 | 1301003 | Construction of sidewalk, bicycle lane, and street lights on the east side of 4th Avenue SW between SW 153rd Street and SW 156th Street. | Transportation Enhancements | 08/17/2009 |  |  | 536293 | 0.22
10392 | Washington | YAKIMA | YAKIMA | 04 | 1335009 | Construct an approximately 0.6 mile long pedestrian pathway. | Transportation Enhancements | 08/24/2009 |  | 09/11/2009 | 121201 | 0.576
10393 | Washington | PIERCE | SEATTLE-TACOMA, WA | 06 | 1343002 | Transit facility improvements for public parking that include structural improvements, electrical, painting, ventilation, fire protection, and signage. | Other | 05/03/2010 |  |  | 798029 | 0
10394 | Washington | CHELAN | WENATCHEE | 04 | 1405006 | Cleaning and painting of an historic bridge. | Transportation Enhancements | 09/28/2009 |  |  | 1527749 | 0.208
10395 | Washington | KING | SEATTLE-TACOMA, WA | 07 | 1482010 | Construct a bridge parallel and connected to the existing Spokane Street Viaduct. Includes the construction of new on and off ramps. | Pavement Widening | 12/09/2009 |  |  | 15443000 | 0.75
10396 | Washington | KING | SEATTLE-TACOMA, WA | 08 | 1915008 | Reconstruct roadway to include a center turn lane; two traffic lanes; bike lanes; curb and gutter; sidewalk; and street lighting at intersections. | Pavement Improvement | 04/12/2010 |  |  | 3500000 | 0.12
10397 | Washington | CLALLAM |  | 06 | 2005075 | Construct a multi-use trail along railroad right of way on the north side of Lake Crescent. | Transportation Enhancements | 07/06/2009 |  |  | 335000 | 6.4
10398 | Washington | CLALLAM |  | 06 | 2005076 | Construct an approximately 0.7 mile long mult-use trail along railroad right of way. | Transportation Enhancements | 07/14/2009 |  | 09/16/2009 | 111000 | 0.682
10399 | Washington | FRANKLIN | SPOKANE | 04 | 2011027 | Improve rail access into and out of the Port of Pasco's 'Big Pasco Industrial Center'. | Other | 03/23/2010 |  |  | 220000 | 0
10400 | Washington | GARFIELD |  | 05 | 2012017 | Pavement resurfacing on the following roadways: Gould City-Mayview Rd, Iron Springs Rd, Mountain Rd, and Peola Rd. | Pavement Improvement | 05/01/2009 |  | 07/27/2009 | 230915 | 14.99
10401 | Washington | ISLAND |  | 02 | 2015076 | Pavement resurfacing of the following roadways in Island County: Front Street; Alexander Street; Maxwelton Road; 3rd Street; and NE Regatta Drive. | Pavement Improvement | 08/27/2009 |  |  | 325167 | 2.97
10402 | Washington | KING | SEATTLE-TACOMA, WA | 07 | 2017090 | Construct a pedestrian walkway along SW 98th St. corridor between 12th Avenue SW and 11th Avenue SW. | Transportation Enhancements | 06/25/2009 |  |  | 1270557 | 0.05
10403 | Washington | KITTITAS |  | 04 | 2019024 | Improve a visitor center located south of Ellensburg on the Yakima River Canyon Scenic Byway by adding gravel to the parking area, and replacing fencing and restroom facilities. | Transportation Enhancements | 10/19/2009 |  |  | 42798 | 0
10404 | Washington | KITTITAS |  | 04 | 2019025 | Installation of guardrail and related safety improvements on roadways within Kittitas County. | Safety/Traffic Management | 09/14/2009 |  |  | 390012.61 | 2.2
10405 | Washington | SKAGIT |  | 02 | 2029046 | Construct new ferry terminal main building on Anacortes. | Other | 02/24/2010 |  |  | 750000 | 0
10406 | Washington | SKAMANIA |  | 03 | 2030005 | Rehabilitation and resurfacing of an asphalt pathway section along Cascade Drive from Hot Springs to Greenleaf in the City of North Bonneville. | Transportation Enhancements | 07/30/2009 |  | 08/06/2009 | 13719 | 0.253
10407 | Washington | WHATCOM |  | 02 | 2037096 | Construct approximately 1.7 miles of shared bicycle-pedestrian trail adjacent to Haxton Way between Kwina Road and Slater Road. | Transportation Enhancements | 03/29/2010 |  |  | 250000 | 1.799
10408 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2506003 | Reconstruction of the roadway to include asphalt pavement resurfacing, new curb ramps, storm drainage repairs, and new bicycle lanes. | Pavement Improvement | 07/07/2009 |  |  | 856977 | 0.5
10409 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2523001 | Modify the existing Interstate 5/196th Street SW interchange to provide a pedestrian route across Interstate 5 and along 196th Street SW. | Transportation Enhancements | 07/17/2009 |  |  | 1250000 | 0.3
10410 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2528001 | Reconstruct existing two lane asphalt street. Includes new curb, gutter, sidewalk, drainage facilities, and bike lanes. | Pavement Improvement | 04/01/2010 |  |  | 818156 | 0
10411 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2674004 | This safety project will replace an existing 4-way stop sign controlled intersection with a roundabout. | Pavement Improvement | 01/11/2010 |  |  | 453431 | 0.2
10412 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2699002 | Asphalt resurfacing of 67th Ave from Grove Street to State Route 528 and 8th Street from State Ave to Cedar Ave. Includes replacing sidewalk ramps. | Pavement Improvement | 08/17/2009 |  | 09/25/2009 | 428489.83 | 0.75
10413 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2701004 | Remove existing culvert, construct 600 feet of new stream channel, and install new culvert fully open to fish passage. | Pavement Improvement | 08/17/2009 |  |  | 1403223 | 0.114
10414 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2722001 | Reconstruction of approximately 0.5 miles of roadway serving major residential and industrial areas. | Pavement Improvement | 07/15/2009 |  |  | 888692 | 0.511
10415 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 01,02 | 2787001 | Improve Holly Drive with the construction of curbs, gutters, sidewalks, and bike lanes. | Transportation Enhancements | 09/14/2009 |  |  | 385447 | 0.2
10416 | Washington | SNOHOMISH |  | 02 | 31BH001 | Reconstruct roadway and construct curb, gutter and sidewalk on 68th Avenue NW between approximately 279th Street NW and at 280th Street NW. | Pavement Improvement | 08/13/2009 |  |  | 641439 | 0.2
10417 | Washington | PIERCE | SEATTLE-TACOMA, WA | 09 | 3217001 | Construct an extension of Shaw Road from Pioneer to E Main, including a new bridge over the Burlington Northern/Santa Fe railroad tracks. | New Construction | 08/04/2009 |  |  | 1201972 | 0.76
10418 | Washington | PIERCE | SEATTLE-TACOMA, WA | 09 | 3266006 | Construction of a new bridge that will eliminate four existing roadway/railroad crossings. | New Bridge Construction | 07/31/2009 |  |  | 15408000 | 0.4
10419 | Washington | SPOKANE |  | 05 | 32DE001 | Rehabilitate the Rutter Parkway bridge by repairing bridge supports, removing the existing bridge deck, installing a new concrete deck, and resurfacing the adjacent roadway with asphalt. | Bridge Improvement | 07/06/2009 |  | 08/19/2009 | 346837 | 0.044
10420 | Washington | BENTON | RICHLAND-KENNEWICK | 04 | 3412007 | Construct approximately 0.5 miles of concrete sidewalk. Includes landscaping of an existing median. | Transportation Enhancements | 06/22/2009 |  | 09/02/2009 | 121862 | 0
10421 | Washington | BENTON | RICHLAND-KENNEWICK | 04 | 3502002 | Reconstruct roadway and construct bike lanes, curb, gutter, and sidewalks. Install traffic signal at George Washington. Add sidewalks along George Washington and 1st Street. | Pavement Widening | 10/01/2009 |  |  | 1600000 | 0.5
10422 | Washington | WHATCOM |  | 02 | 37A1001 | Asphalt resurfacing of the existing pavement. | Pavement Improvement | 09/11/2009 |  | 09/28/2009 | 112304.45 | 0.72
10423 | Washington | SPOKANE | SPOKANE | 05 | 3840008 | Asphalt resurfacing of the existing roadway, upgrade curb ramps, and improve the stormwater drainage system. | Pavement Improvement | 07/20/2009 |  |  | 2606469 | 2
10424 | Washington | SPOKANE | SPOKANE | 05 | 3867001 | Construction of a new roadway between Lincoln Road and Ash Street. Includes new sidewalks, curbs, bike lanes, and landscaping. Also includes asphalt resurfacing from Austin Road to Ash Street. | Pavement Improvement | 05/08/2009 |  |  | 112720 | 1.3
10425 | Washington | SPOKANE | SPOKANE | 05 | 3867002 | Replace existing pavement with three inches of asphalt pavement. | Pavement Improvement | 07/06/2009 |  | 08/27/2009 | 859000 | 1.95
10426 | Washington | SPOKANE | SPOKANE | 05 | 3867003 | Reconstruct a portion of Five Mile Road between Berridae and Waikiki by replacing the existing pavement with a new asphalt pavement. The remaining portions of Five Mile Road will be resurfaced with o | Pavement Improvement | 09/08/2009 |  |  | 331000 | 1.43
10427 | Washington | KING | SEATTLE-TACOMA, WA | 8 | 4053858 | Construct on and off ramps to provide relief in a highly congested area of I-405 in the vicinity of downtown Bellevue and the I-405/SR 520 Interchange. | Pavement Improvement | 11/25/2009 |  | 12/31/2012 | 58937553.42 | 1.5
10428 | Washington | KING, SNOHOMISH | SEATTLE-TACOMA, WA | 1 | 4053859 | Northbound I-405 will be widened to add an auxiliary (add/drop) lane between NE 195th Street and SR 527. | Pavement Widening | 09/11/2009 |  | 06/18/2010 | 22991402 | 3
10429 | Washington | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 4242022 | Improve rail access into the Port of Vancouver by providing new rail infrastructure within existing facilities, and new track at Terminal 5. | Other | 11/09/2009 |  |  | 2500000 | 0
10430 | Washington | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 4410002 | Widen NE 99th Street to three vehicle lanes, bicycle lanes, and sidewalks between State Route 503 and NE 137th Ave. | Pavement Improvement | 10/19/2009 |  |  | 1831151 | 1.05
10431 | Washington | YAKIMA | YAKIMA | 04 | 4566009 | Reconstruct portions of the Nob Hill Boulevard pavement from 64th Avenue to 72nd Avenue. Includes improvements to the curb & gutter, sidewalk, stormwater drainage system, and street lighting. | Pavement Improvement | 09/01/2009 |  |  | 766683 | 0.5
10432 | Washington | YAKIMA |  | 04 | 4628006 | Asphalt resurfacing of the roadway, and upgrading of the curb ramps. | Pavement Improvement | 07/20/2009 |  | 09/07/2009 | 400000 | 0.99
10433 | Washington | YAKIMA | YAKIMA | 04 | 4645001 | Widen and reconstruct approximately 0.3 miles of Beaudry Road, including curb and gutter, sidewalks, stormwater drainage system, and street lighting. | Pavement Improvement | 07/20/2009 |  |  | 500000 | 0.284
10434 | Washington | YAKIMA | YAKIMA | 04 | 4708001 | Reconstruct approximately 0.7 miles of Speyers Road, from the west City limits to Fremont Avenue, including curb and gutter, sidewalk, stormwater drainage system, and street lighting. | Pavement Improvement | 08/17/2009 |  |  | 1598000 | 0.68
10435 | Washington | THURSTON | OLYMPIA | 03 | 5235012 | Construction of a dedicated five foot wide bicycle path on the east side of the roadway, and relocation of the existing sidewalk to accommodate the new bicycle path. | Transportation Enhancements | 07/29/2009 |  |  | 307144 | 0.66
10436 | Washington | THURSTON | OLYMPIA | 03 | 5235013 | Asphalt resurfacing of Capitol Blvd. from Dennis Street to Israel Road. | Pavement Improvement | 08/10/2009 |  | 09/16/2009 | 159034 | 0.25
10437 | Washington | THURSTON | OLYMPIA | 03 | 5346001 | Asphalt resurfacing of Union Avenue from Capitol Way to Plum Street. | Pavement Improvement | 07/28/2009 |  |  | 1098824 | 0.44
10438 | Washington | THURSTON |  | 09 | 5394003 | Construct sidewalks, street lighting, and intersection crossing improvements on Steilacoom Road, between Stonewood Drive and Duterrow Road. | Transportation Enhancements | 07/31/2009 |  | 09/02/2009 | 110244 | 0.17
10439 | Washington | LEWIS |  | 03 | 5667003 | Asphalt resurfacing of Jackson Highway. | Pavement Improvement | 07/09/2009 |  | 09/15/2009 | 775898 | 1.59
10440 | Washington | ASOTIN |  | 05 | 6005002 | Asphalt resurfacing of Scenic Way from 2nd Avenue to Fleshman Way. | Pavement Improvement | 08/16/2009 |  |  | 585994.82 | 0.98
10441 | Washington | GRANT |  | 04 | 6061001 | Asphalt resurfacing of the roadway, including improvements to curbs, sidewalks, bike path, and stormwater drainage system. | Pavement Improvement | 08/24/2009 |  |  | 1200000 | 1
10442 | Washington | GRANT |  | 04 | 6065004 | Construction an approximately 0.5 mile long eight foot wide pedestrian path. | Transportation Enhancements | 08/24/2009 |  |  | 28647 | 0.48
10443 | Washington | SKAGIT | SEATTLE-TACOMA, WA | 02 | 6240001 | Reconstruct existing street with new curb, gutter, storm system, and street pavement. | Pavement Improvement | 03/11/2010 |  |  | 478806 | 0
10444 | Washington | YAKIMA |  | 04 | 6340003 | Asphalt resurfacing of the intersection located at Yakima Valley Highway and Lincoln Avenue. | Pavement Improvement | 11/09/2009 |  |  | 150000 | 0.2
10445 | Washington | YAKIMA | YAKIMA | 04 | 6408004 | Asphalt resurfacing of existing road surface; and reconstruction of driveways, crosswalk accesses, and sidewalks. | Pavement Improvement | 09/14/2009 |  |  | 290839 | 0.21
10446 | Washington | KITSAP | BREMERTON | 01 | 6683004 | Project will improve safety and mobility on Viking Avenue by constructing a two-way left turn lane, bike lanes, stormwater drainage improvements, curb, sidewalk, and intersection channelization at Fin | Pavement Improvement | 06/23/2009 |  |  | 2573948 | 0.66
10447 | Washington | KITSAP | BREMERTON | 01 | 6683005 | Construct bike lanes, curbs, gutter and sidewalks along Viking Avenue from Bovela Lane to a point approximately 1,000 ft south of Bovela Lane. Construct approximately 740 ft. of a continuous left tur | Pavement Improvement | 04/19/2010 |  |  | 824925 | 0.19
10448 | Washington | KITSAP | BREMERTON | 01 | 6701001 | Widen roadway shoulders near Blakely Elementary School to improve pedestrian safety. | Transportation Enhancements | 08/03/2009 |  | 09/28/2009 | 150000 | 0.133
10449 | Washington | COWLITZ | LONGVIEW (OR) | 03 | 6739001 | Roadway reconstruction and widening, and improvements to the roadway and intersection alignments to increase safety. | Pavement Widening | 08/10/2009 |  |  | 1056593 | 1.23
10450 | Washington | COWLITZ | LONGVIEW (OR) | 03 | 6763001 | Asphalt resurfacing of approximately 1.0 miles of South 13th Avenue. | Pavement Improvement | 07/20/2009 |  |  | 235554 | 0.975
10451 | Washington | KITTITAS |  | 04 | 6949002 | Asphalt resurfacing and restriping of Canyon Road from Interstate 90 to Umptanum Road. | Pavement Improvement | 06/23/2009 |  | 08/13/2009 | 394865 | 0.5
10452 | Washington | CLARK |  | 03 | 7042001 | Construct a new three lane roadway, with sidewalks and bicycle lanes. | New Construction | 05/27/2010 |  |  | 569529 | 0.76
10453 | Washington | WALLA WALLA |  | 05 | 7166001 | Construct a multi-use pathway connecting major residential development, a local airport, schools, and the existing pedestrian system. | Transportation Enhancements | 09/21/2009 |  |  | 58000 | 0.27
10454 | Washington | WALLA WALLA |  | 05 | 7169001 | Reconstruct 13th Avenue from Rose St. to Abadie St. and from Cherry St. to Rees Ave. Includes sidewalks, bike facilities, stormwater drainage facilities, street lighting, and traffic signals. | Pavement Widening | 10/05/2009 |  |  | 1980000 | 0.714
10455 | Washington | SKAGIT | MOUNT VERNON | 02 | 7337006 | Construct an extension of Laventure Road extending south from Fowler St. to Blackburn Road. Roadway includes two traffic lanes, turn lane, bike lanes, and sidewalks. | New Construction | 07/27/2009 |  |  | 923769 | 0.25
10456 | Washington | SKAGIT |  | 02 | 7390001 | Reconstruct Fruitdale Road from State Route 20 to McGarigle Road. Includes construction of curbs, gutters, sidewalks, and street lighting. | Pavement Improvement | 06/01/2009 |  |  | 134867 | 1.34
10457 | Washington | WHITMAN |  | 05 | 7418002 | Asphalt resurfacing of approximately 0.46 miles of the following roadways: Whitman St from Kamiaken to Maple, Maiden Lane from Whitman to Opal, and Opal from Maiden Lane to Campus. | Pavement Improvement | 07/07/2009 |  | 08/04/2009 | 358819 | 0.462
10458 | Washington | CLALLAM |  | 06 | 7541001 | Reconstruct and widen Mount Pleasant Road. | Pavement Improvement | 08/31/2009 |  |  | 568000 | 0.4
10459 | Washington | SPOKANE |  | 05 | 7690002 | The construction of a turn lane, curb, sidewalk, street lighting and bicycle pathways on Cheney-Spangle Road from State Route 904 to Cheney City limits. | Transportation Enhancements | 09/08/2009 |  |  | 576416 | 0.4
10460 | Washington | SPOKANE | SPOKANE | 05 | 7690003 | Install concrete pads and sidewalks to accommodate pedestrian access over the rail lines. | Transportation Enhancements | 02/16/2010 |  |  | 106000 | 0.07
10461 | Washington | ISLAND |  | 02 | 7790002 | Widening of Ault Field Road between Oak Harbor Road and Goldie Road to provide an additional travel lane. | Pavement Improvement | 07/23/2009 |  |  | 1357704 | 0.24
10462 | Washington | WHATCOM |  | 02 | 8037001 | Reconstruction of existing road and construction a new road on 2nd Ave from Washington to Portal Way at the Interstate-5 southbound offramp. | New Construction | 09/01/2009 |  |  | 1541000 | 0.5
10463 | Washington | YAKIMA |  | 04 | 8051001 | Asphalt resurfacing of Euclid Road from Forsell Road to Stassen Way. | Pavement Improvement | 06/25/2009 |  | 08/21/2009 | 318327 | 0.767
10464 | Washington | YAKIMA |  | 04 | 8057001 | Replace the asphalt pavement, improve storm drainage, construct sidewalks, provide street and pedestrian lighting, and landscaping. | Transportation Enhancements | 03/16/2010 |  |  | 2030000 | 0
10465 | Washington | WHATCOM |  | 02 | 8158001 | Widening and asphalt resurfacing of roadway; and improvements to curb, gutter, and stormwater drainage. | Pavement Improvement | 06/09/2009 |  |  | 981169 | 0.6
10466 | Washington | CLALLAM |  | 06 | 9905005 | Asphalt resurfacing of existing street, striping, and curb ramp installation. | Pavement Improvement | 08/10/2009 |  |  | 393000 | 0.341
10467 | Washington | CLARK | STATEWIDE | 03 | 9906026 | Asphalt resurfacing of the following locations: NW 9th Ave, NW 119th St/7th Ave/NW 114th St, NE 72nd Ave, SE Gibson Rd, NW 199th St, NE 20 Ave/Union Rd, NE 78th St/76th St, NW 151st/139th Sts/Tenny R | Pavement Improvement | 04/22/2010 |  |  | 668849 | 10.53
10468 | Washington | CLARK | SPOKANE | 03 | 9906027 | Asphalt resurfacing of the following locations: N. Parkway Ave, NW 25th St, SW 20th Ave, SE Eaton Blvd, S. Parkway Ave, and NW 20th Ave. | Pavement Improvement | 05/18/2010 |  |  | 406212 | 0
10469 | Washington | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 9906028 | Pavement overlays on SE 34th St, NE 112th Ave, Andresen Rd, Columbia Way, Grand Blvd, Hearthwood Blvd, Stapleton Rd, and Mill Plain Blvd. | Pavement Improvement | 05/19/2010 |  |  | 2500000 | 0
10470 | Washington | PIERCE | SEATTLE-TACOMA, WA | 08 | 9927049 | Construction of pedestrian amenities to include sidewalks, curb ramps, street lighting, and landscaping. | Pavement Widening | 09/21/2009 |  |  | 632296 | 1
10471 | Washington | STEVENS |  | 05 | 9933001 | Asphalt resurfacing of Williams Lake and Cedonia-Addy Roads. | Pavement Improvement | 06/22/2009 |  | 07/15/2009 | 980276 | 33.37
10472 | Washington | WHATCOM | BELLINGHAM | 02 | 9937002 | Installation of enhanced pedestrian crossings on high volume streets to improve safety and connectivity. Improvements include flashing lights, illuminated signage, and concrete pedestrian refuge isla | Transportation Enhancements | 07/22/2009 |  |  | 308596 | 0.1
10473 | Washington | WHATCOM | STATEWIDE | 02 | 9937003 | Pavement preservation resurfacing of all-weather arterials. Arterials include East Bakerview Road (Landon Road to Hannegan Road) and Hannegan Road (East Bakerview Road to Sunset Drive). | Pavement Improvement | 05/17/2010 |  |  | 1600000 | 2.49
10474 | Washington | YAKIMA | YAKIMA | 04 | 9939018 | Asphalt resurfacing of Rudkin Road and the Main Street/Ahtanum Road Intersection. | Pavement Improvement | 09/08/2009 |  |  | 266906 | 0.504
10475 | Washington | PACIFIC |  | 3 | 9999546 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 04/23/2009 | 05/18/2009 | 07/31/2009 | 394691 | 3.97
10476 | Washington | GRANT |  | 4 | 9999547 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 05/14/2009 | 06/08/2009 | 11/10/2009 | 5471392.27 | 13.49
10477 | Washington | GRANT, OKANOGAN |  | 5 | 9999548 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 05/13/2009 | 05/28/2009 | 08/30/2009 | 3294919.43 | 68.5
10478 | Washington | STEVENS, ADAMS, FERRY |  | 5 | 9999549 | Replace portable Highway Advisory Radio (HAR) trailers deployed on SR 20 and US 395 for Sherman Pass with permanent HAR stations and install a new station in the vicinity of the Hatton Coulee Rest Are | Safety/Traffic Management | 07/01/2009 | 10/06/2009 | 11/17/2009 | 239999.93 | 0
10479 | Washington | STATEWIDE |  | 4 | 9999550 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Other | 04/29/2009 | 04/29/2009 | 11/19/2010 | 187498.16 | 0
10480 | Washington | STATEWIDE |  | 4 | 9999551 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Other | 04/29/2009 | 04/29/2009 | 11/19/2010 | 365573.7 | 0
10481 | Washington | GRANT, CHELAN, BENTON, DOUGLAS, LINCOLN, FRANKLIN, YAKIMA, SPOKANE |  | 4 | 9999554 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 08/17/2009 | 08/24/2009 | 09/22/2009 | 581025.58 | 235.74
10482 | Washington | PACIFIC, CLARK, KITSAP, LEWIS, MASON, JEFFERSON, THURSTON, GRAYS HARBOR, PIERCE, COWLITZ, CLALLAM |  | 08,09,01,06 | 9999555 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 03/17/2010 |  | 11/19/2010 | 708200 | 180.02
10483 | Washington | ISLAND, SKAGIT, KING, SNOHOMISH, WHATCOM |  | 01,02,08 | 9999556 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 08/11/2009 | 08/11/2009 | 11/12/2009 | 822601 | 147.79
10484 | Washington | KING, THURSTON, WHATCOM |  | 8 | 9999557 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 08/07/2009 | 08/17/2009 | 03/31/2010 | 946131 | 6.009
10485 | Washington | GRANT, KITTITAS |  | 4 | 9999558 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 08/17/2009 | 10/05/2009 | 11/09/2009 | 804861.74 | 10.62
10486 | Washington | MASON, KITSAP, THURSTON |  | 03,06 | 9999576 | Install high tension cable barrier in the median to prevent crossover collisions. | Safety/Traffic Management | 04/28/2010 |  |  | 330389 | 0
10487 | Washington | GRANT, OKANOGAN |  | 04,05 | 9999577 | Overlay pavement with a chip seal | Pavement Improvement | 04/07/2010 |  |  | 2632580 | 0
10488 | Washington | KITTITAS, KING, YAKIMA, SNOHOMISH |  | 4 | 9999578 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 04/12/2010 |  | 10/29/2010 | 1183326 | 0
10489 | Washington | BENTON |  | 04 | A032001 | Reconstruction of Sheridan Avenue from Third Street to Sixth Street including sidewalks, curb and gutter, drainage, and street lighting. | Pavement Improvement | 07/20/2009 |  |  | 474511 | 0.275
10490 | Washington | CHELAN |  | 04 | A045002 | Reconstruct asphalt pavement, increase the vertical clearance at a railroad trestle, and construct a shared-use path through the trestle. | Pavement Improvement | 06/08/2009 |  |  | 1021318 | 0.56
10491 | Washington | CLALLAM |  | 06 | A058001 | Asphalt resurfacing and minor roadway widening to add curb, gutter and sidewalk. | Pavement Improvement | 08/12/2009 |  |  | 160000 | 0.51
10492 | Washington | COWLITZ |  | 03 | A083002 | Asphalt pavement resurfacing, including improvements to the street lighting, sidewalks, crosswalks, and stormwater drainage. | Transportation Enhancements | 09/08/2009 |  |  | 416250 | 0.3
10493 | Washington | LINCOLN |  | 05 | A221003 | Asphalt resurfacing of approximately 4 miles of roadway. | Pavement Improvement | 07/20/2009 |  | 07/30/2009 | 654000 | 4.24
10494 | Washington | SKAMANIA |  | 03 | A301006 | Asphalt pavement resurfacing of approximately 1.0 mile of Wind River Road. | Pavement Improvement | 07/30/2009 |  | 08/06/2009 | 306711 | 0.92
10495 | Washington | THURSTON |  | 03 | A341004 | Widen existing two lane roadway to add a two way center left turn lane on Old Highway 99; and replace existing bridge with a new 5 traffic lane bridge, including bike lanes, sidewalks, and illuminatio | Bridge Replacement | 02/22/2010 |  |  | 1330000 | 0.8
10496 | Washington | WHITMAN |  | 05 | A381004 | Asphalt resurfacing and striping of approximately 5.5 miles of Wawawai Road. | Pavement Improvement | 08/11/2009 |  | 09/04/2009 | 896000 | 5.44
10497 | Washington | YAKIMA |  | 04 | A393001 | Asphalt resurfacing of Harrah Road from South Town Limits to North Town Limits. | Pavement Improvement | 09/14/2009 |  |  | 360000 | 0.625
10498 | Washington | ADAMS |  | 05 | B012002 | Resurface approximately 3.0 miles of roadway with two inches of asphalt. | Pavement Improvement | 07/08/2009 |  | 07/27/2009 | 762232 | 3.03
10499 | Washington | CLARK |  | 03 | B063002 | Asphalt resurfacing of Hillhurst Road between South 15th Circle and South 22nd Circle. | Pavement Improvement | 08/25/2009 |  | 09/18/2009 | 168054 | 0.56
10500 | Washington | COLUMBIA |  | 05 | B071002 | Resurface existing 24 ft wide road with asphalt. | Pavement Improvement | 06/01/2010 |  |  | 465000 | 0
10501 | Washington | COLUMBIA |  | 05 | B074001 | Asphalt resurfacing of East Dayton Avenue from Front Street to US 12. | Pavement Improvement | 08/24/2009 |  | 10/05/2009 | 225000 | 0.25
10502 | Washington | FRANKLIN |  | 04 | B111002 | Relocation of the south 1.1 miles of the R-170 Road outside of the existing roadside slide area. | Pavement Improvement | 09/08/2009 |  |  | 750000 | 1.1
10503 | Washington | PACIFIC |  | 03 | B256007 | Asphalt resurfacing of Sandridge Road from State Route 101 to 67th Place; and install a traffic signal at the intersection of Sandridge Road and Sid Snyder Drive. | Pavement Improvement | 08/03/2009 |  |  | 279396 | 1.62
10504 | Washington | YAKIMA |  | 04 | B391002 | Asphalt resurfacing of South Camas Street, from 3rd Street to 9th Street. | Pavement Improvement | 10/07/2009 |  |  | 312000 | 0.4
10505 | Washington | WAHKIAKUM |  | 3 | C350002 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 06/17/2009 | 06/29/2009 | 12/28/2009 | 200000 | 27.76
10506 | Washington | KITSAP |  | 06 | D185001 | Construction of approximately 1.5 miles of new roadway, intersection improvements, bicycle lanes, and a separated asphalt pedestrian path. | New Construction | 10/12/2009 |  |  | 2623386 | 1.5
10507 | Washington | PEND OREILLE |  | 05 | D261001 | Asphalt resurfacing of Deer Valley Road from Coyote Trail to Gray Road. | Pavement Improvement | 09/14/2009 |  |  | 471000 | 1.17
10508 | Washington | SAN JUAN |  | 02 | D281003 | Asphalt resurfacing of Fisherman Bay Road, and installation of safety fencing. | Pavement Improvement | 08/28/2009 |  | 09/24/2009 | 416620 | 1.76
10509 | Washington | SKAGIT |  | 02 | D291002 | Asphalt resurfacing of Maple Avenue from Morris Street to Caledonia Street, installation of curb ramps. | Pavement Improvement | 08/06/2009 |  | 08/29/2009 | 154800 | 0.502
10510 | Washington | OKANOGAN |  | 05 | F241005 | Asphalt resurfacing of approximately 0.5 miles of Main Street (from south city limits to Lake Street) & East Lake Street (from Main Street east to city limits). | Pavement Improvement | 06/15/2009 |  | 06/19/2009 | 119071.16 | 0.54
10511 | Washington | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | H310001 | Asphalt pavement resurfacing on 84th Street NE. | Pavement Improvement | 02/03/2010 |  |  | 481976 | 4.72
10512 | Washington | WHITMAN |  | 05 | I382004 | Asphalt resurfacing of South Main Street from State Route 195 to the Fairview Street and Meadow intersection. | Pavement Improvement | 09/08/2009 |  | 09/21/2009 | 141069 | 0.284
10513 | Washington | MASON |  | 06 | K232001 | Asphalt resurfacing of approximately 1.6 miles of McEwan Prairie Road. | Pavement Improvement | 08/26/2009 |  | 09/04/2009 | 288576.34 | 1.62
10514 | Washington | THURSTON |  | 09 | K340001 | Widen and provide an asphalt overlay of Minnesota Street, construct sidewalks and crosswalks, and update traffic signs. | Pavement Improvement | 08/25/2009 |  |  | 729437 | 0.3
10515 | Washington | FERRY |  | 05 | L102009 | Asphalt resurfacing of approximately 9 miles of Bridge Creek Road. | Pavement Improvement | 05/01/2010 |  |  | 339046 | 7.11
10516 | Washington | KLICKITAT |  | 04 | L201003 | Asphalt resurfacing of approximately 2.4 miles of South Columbus Street. | Pavement Improvement | 09/04/2009 |  |  | 469572.54 | 2.39
10517 | Washington | KLICKITAT |  | 04 | M201002 | Asphalt resurfacing of approximately 1.6 miles of Bickleton Highway. | Pavement Improvement | 09/04/2009 |  |  | 255000 | 1.58
10518 | Washington | GRANT |  | 04 | P130002 | Construction of a new concrete bridge. | Bridge Replacement | 11/16/2009 |  |  | 750000 | 0.12
10519 | Washington | GRANT |  | 04 | P137001 | Asphalt resurfacing of approximately 2.0 miles of L-NE Road from Kittleson to 3-NE Road. | Pavement Improvement | 07/06/2009 |  | 07/28/2009 | 487009 | 2.01
10520 | Washington | WHATCOM |  | 02 | P368001 | Constructs approximately 0.1 miles of new roadway to provide an improved roadway connector between State Route 543 and the commercial and industrial areas. | New Construction | 08/21/2009 |  |  | 348000 | 0.133
10521 | Washington | JEFFERSON |  | 06 | Q161007 | Asphalt resurfacing of approximately 2.0 miles of Center Road. | Pavement Improvement | 07/20/2009 |  | 08/07/2009 | 358000 | 2
10522 | Washington | WHATCOM |  | 02 | T371008 | Replace the existing bridge on Hannegan Road over Scott Ditch, south of Lynden, Washington. | Bridge Replacement | 08/03/2009 |  |  | 600000 | 0.05
10523 | Washington | COWLITZ |  | 03 | X085001 | Reconstruct roadway to include curb, gutter and sidewalk. Includes channelization improvements to the existing intersection with State Route 504. | Pavement Widening | 07/14/2009 |  |  | 330000 | 0.73
10524 | Washington | LEWIS |  | 03 | Y210001 | Reconstruction and asphalt resurfacing of approximately 2.3 miles of Davis Lake Road. | Pavement Improvement | 07/09/2009 |  | 09/15/2009 | 1027000 | 2.29
10525 | Washington | SPOKANE |  | 05 | Y329008 | Reconstruction of Crawford Avenue, including the installation of a roundabout, curb and gutter, sidewalk, and stormwater drainage system. | Pavement Improvement | 05/11/2009 |  | 09/15/2009 | 1674431 | 0.61
10526 | Washington | MASON |  | 06 | Z923001 | Install solar street lights at intersections within Mason County. | Safety/Traffic Management | 03/18/2010 |  |  | 150000 | 0
10527 | Washington | YAKIMA |  | 04 | Z939004 | Asphalt resurfacing of 2nd Street and 3rd Street. Includes replacement of substandard curb, gutter, and sidewalk along 2nd Street, 3rd Street, and Canal Street. | Pavement Improvement | 08/17/2009 |  | 09/24/2009 | 326000 | 0.227
10528 | West Virginia | PLEASANTS |  | 1 | 0002474 | This project will improve safety for motorists by resurfacing 2.72 miles of West Virginia 2 from the City of Waverly to Willow Island Road in Pleasants County. | Pavement Improvement | 04/21/2009 | 05/27/2009 | 10/30/2009 | 799200 | 2.72
10529 | West Virginia | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 0002479 | This project will improve safety for motorists by resurfacing 1.04 miles of West Virginia Route 2 from the Brooke County/Hancock County line to Penn Avenue Road | Pavement Improvement | 02/22/2010 | 04/13/2010 | 06/30/2010 | 614200 | 1.04
10530 | West Virginia | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 0002481 | This project will improve safety for motorists by resurfacing 1.5 miles of deteriorated pavement on West Virginia 2 from the City of Wellsburg to Cross Creek Road in Brooke County. | Pavement Improvement | 02/22/2010 | 05/21/2010 | 06/30/2010 | 586900 | 1.5
10531 | West Virginia | OHIO | WHEELING (OH) | 1 | 0002482 | This project will improve safety for motorists by resurfacing 0.37 miles of deteriorated pavement on West Virginia 2 at milepoint 0.00 and resurfacing 1.39 miles of West Virginia Route 88 from Peter's | Pavement Improvement | 04/01/2010 | 05/12/2010 | 06/30/2010 | 508900 | 0.37
10532 | West Virginia | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 0002483 | This project will improve safety for motorists by resurfacing 1.31 miles of deteriorated pavement on West Virginia Route 2 from the City of Weirton to Kings Creek Road in Hancock County. | Pavement Improvement | 12/01/2009 | 04/13/2010 | 06/30/2010 | 482830 | 1.31
10533 | West Virginia | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 0002484 | This project will improve safety for motorists by resurfacing 1.55 miles of deteriorated pavement on West Virginia Route 2 from the City of New Cumberland to Moscow Road in Hancock County. | Pavement Improvement | 12/01/2009 | 04/23/2010 | 06/30/2010 | 378193 | 1.55
10534 | West Virginia | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 0002487 | This project will extend the life of the historic Ohio River Market Street Bridge by repairing bridge components, replacing the lighting and light fixtures on the bridge, cleaning the structrue and re | Bridge Improvement | 12/10/2009 | 01/11/2010 | 11/30/2011 | 10594435 | 0.01
10535 | West Virginia | MONROE |  | 3 | 0003216 | This project will improve safety for motorists by resurfacing the deck of the Alderson Bridge with Latex Modified Concrete. The bridge is located on West Virginia Route 3 at approximately milepoint 0. | Bridge Improvement | 05/12/2009 | 08/31/2009 | 10/30/2009 | 558200 | 0.17
10536 | West Virginia | BOONE |  | 3 | 0003217 | This project will improve safety for motorists by resurfacing 1.67 miles of deteriorated pavement and replace the existing guardrails on West Virginia Route 3 from the Big Coal River Bridge to West Vi | Pavement Improvement | 04/28/2009 | 05/05/2009 | 10/30/2009 | 576100 | 1.67
10537 | West Virginia | MERCER |  | 3 | 0003218 | This project will extend the life of two bridges, the County Route 3 Turnpike Overpass Bridge and the Camp Creek Overpass Bridge #2, by cleaning the structures and then painting them. The bridges are | Bridge Improvement | 07/21/2009 | 07/25/2009 | 10/15/2009 | 380400 | 0.07
10538 | West Virginia | TAYLOR |  | 1 | 0003221 | This project will improve safety for motorists by replacing the Berry Run Bridge due to condition. The bridge is located on County Route 3 at approximately milepoint 0.16 in Taylor County. | Bridge Replacement | 01/11/2010 | 03/22/2010 | 07/30/2010 | 384120 | 0.01
10539 | West Virginia | RALEIGH |  | 3 | 0003222 | This project will improve safety for motorists by the installation of piling for embankment stabilization on West Virginia Route 3 (Metalton Road) at approximately milepoint 29.13 in Raleigh County. | Pavement Improvement | 04/20/2009 | 04/20/2009 | 10/30/2009 | 311600 | 0.01
10540 | West Virginia | HARRISON |  | 1 | 0005119 | This project will improve safety for motorists by replacing the Big Arch Bridge due to condition. The bridge is located on County Route 5 at approximately milepoint 2.46 in Harrison County. | Bridge Replacement | 11/13/2009 | 04/22/2010 | 06/30/2010 | 517530 | 0.01
10541 | West Virginia | TAYLOR |  | 1 | 0007219 | This project will improve safety for motorists by replacing the Irontown Girder Bridge due to condition. The bridge is located on County Route 7 at approximately milepoint 3.2 in Taylor County. | Bridge Replacement | 09/21/2009 | 11/11/2009 | 06/30/2010 | 828900 | 0.01
10542 | West Virginia | WIRT |  | 2 | 0007221 | This project will improve safety for motorists by resurfacing 4.36 miles of deteriorated pavement on County Route 7 (Garfield Road) beginning at milepoint 6.10 in Wirt County. | Pavement Improvement | 09/02/2009 | 09/19/2009 | 10/30/2009 | 760846 | 4.36
10543 | West Virginia | PENDLETON |  | 2 | 0009194 | This project will extend the life of the 4-U Bridge by cleaning and painting the structure. The bridge is located on County Route 9 at approximately milepoint 9.24 in Pendleton County. | Bridge Improvement | 06/08/2009 | 04/12/2010 | 10/15/2009 | 171500 | 0.01
10544 | West Virginia | JEFFERSON |  | 2 | 0009196 | This project will reduce traffic congestion and improve access to the area by the upgrade of the existing West Virginia Route 9 to four lanes and the construction of a new bridge. The project is loca | Pavement Widening | 09/22/2009 | 09/22/2009 | 05/31/2011 | 18743700 | 0.27
10545 | West Virginia | HARRISON |  | 1 | 0009197 | This project will improve safety for motorists by replacing the West Robey Arch Bridge due to condition. The bridge is located on County Route 9 at approximately milepoint 6.75 in Harrison County. | Bridge Replacement | 11/12/2009 | 11/17/2009 | 06/30/2010 | 557670 | 0.01
10546 | West Virginia | BARBOUR |  | 1 | 0011124 | This project will improve safety for motorists by resurfacing 4.46 miles of deteriorated pavement on County Route 11 (Audra Park Road) in Barbour County. | Pavement Improvement | 09/09/2009 | 09/09/2009 | 10/30/2009 | 468496 | 4.46
10547 | West Virginia | PENDLETON |  | 2 | 0012048 | This project will improve safety for motorists by replacing the Deer Run Park Bridge due to condition. The bridge is located on County Route 12 at approximately milepoint 4.15 in Pendleton County. | Bridge Replacement | 10/13/2009 | 04/06/2010 | 06/10/2010 | 416270 | 0.01
10548 | West Virginia | TYLER |  | 1 | 0013056 | This project will improve safety for motorists by replacing the Walnut Fork Bridge due to condition. The bridge is located on County Route 13 at approximately milepoint 6.06 in Tyler County. | Bridge Replacement | 08/05/2009 | 03/02/2010 | 07/30/2010 | 537310 | 0.01
10549 | West Virginia | KANAWHA |  | 2 | 0015078 | This project will improve safety for motorists by replacing the Middle Fork Bridges due to condition. The bridges are located on County Route 15 at approximately milepoint 13.71 in Kanawha County. | Bridge Replacement | 09/18/2009 | 03/02/2010 | 06/30/2010 | 760920 | 0.01
10550 | West Virginia | DODDRIDGE |  | 1 | 0015079 | This project will improve safety for motorists by replacing Long Run Bridge due to condition. The bridge is located on County Route 15 at approximately milepoint 2.18 in Doddridge County. | Bridge Replacement | 10/09/2009 | 11/02/2009 | 06/30/2010 | 720210 | 0.01
10551 | West Virginia | RITCHIE |  | 1 | 0016205 | This project will improve safety for motorists by resurfacing 3.26 miles of deteriorated pavement on West Virginia 16 from the City of Washburn to Harrisville Road in Ritchie County. | Pavement Improvement | 06/18/2009 | 07/11/2009 | 07/30/2009 | 718511 | 3.26
10552 | West Virginia | CALHOUN |  | 2 | 0016206 | This project will improve safety for motorists by resurfacing 1.31 miles of deteriorated pavement on West Virginia Route 16 from the City of Grantsville to Smithville Road in Calhoun County. | Pavement Improvement | 07/01/2009 | 07/01/2009 | 09/11/2009 | 401720 | 1.31
10553 | West Virginia | RALEIGH |  | 3 | 0016207 | This project will improve safety for motorists by resurfacing 0.47 miles of West Virginia Route 16 from South Oakwood Avenue to Bus Station Road in Beckley, Raleigh County. | Pavement Improvement | 07/10/2009 | 07/20/2009 | 10/30/2009 | 516059 | 0.47
10554 | West Virginia | WETZEL |  | 1 | 0017086 | This project will improve safety for motorists by replacing the McBee Bridge due to condition. The bridge is located on County Route 17 at approximately milepoint 3.68 in Wetzel County. | Bridge Replacement | 12/16/2009 | 12/16/2009 | 07/30/2010 | 453800 | 0.01
10555 | West Virginia | TYLER |  | 1 | 0018119 | This project will improve safety for motorists by the installation of piling for embankment stabilization at five locations beginning at milepoint 11.12 and extending 0.50 miles on West Virginia 18 in | Pavement Improvement | 12/01/2009 | 05/11/2010 | 07/30/2010 | 962820 | 0.5
10556 | West Virginia | FAYETTE |  | 3 | 0019337 | This project will improve safety for motorists by resurfacing the deck of the New River Gorge Bridge located in Fayette County on United States Route 19 at the approximate milepoint 15.37 with Latex M | Bridge Improvement | 04/01/2010 | 04/09/2010 | 06/30/2010 | 918300 | 0.01
10557 | West Virginia | NICHOLAS |  | 3 | 0019338 | This project will improve safety for motorists by resurfacing 1.94 miles of United States Route 19 from the City of Fockler Branch to Muddlety Road in Nicholas County. | Pavement Improvement | 07/07/2009 | 07/07/2009 | 10/30/2009 | 1301100 | 1.94
10558 | West Virginia | LEWIS |  | 2 | 0019339 | This project will improve safety for motorists by resurfacing 1.89 miles of deteriorated pavement on United States Route 19 in the City of Weston, Lewis County. | Pavement Improvement | 05/22/2009 | 06/29/2009 | 10/30/2009 | 305396 | 1.89
10559 | West Virginia | RALEIGH |  | 3 | 0019340 | This project will help eliminate congestion by the relocation and upgrade to four lanes of United States Route 19 beginning at approximately milepoint 15.52 and bridge improvements ending at the South | New Construction | 08/20/2009 | 09/18/2009 | 08/30/2011 | 22190000 | 0.89
10560 | West Virginia | RALEIGH |  | 3 | 0019343 | This project will improve safety for motorists by resurfacing 0.50 miles of deteriorated pavement on United States Route 19 from the City of Prosperity to the Crossroads Mall in Raleigh County. | Pavement Improvement | 09/04/2009 | 10/01/2009 | 10/30/2009 | 347814 | 0.5
10561 | West Virginia | NICHOLAS |  | 3 | 0020254 | This project will improve safety for motorists by replacing the existing and failing piling currently restricting slippage of the embankment on West Virginia Route 20 at approximately milepoint 26.75 | Pavement Improvement | 09/01/2009 | 09/01/2009 | 10/30/2009 | 204200 | 0.01
10562 | West Virginia | UPSHUR |  | 2 | 0020255 | This project will improve safety for motorists by resurfacing 2.02 miles of West Virginia 20 From the City of French Creek to Adrian Road in Upshur County. | Pavement Improvement | 07/06/2009 | 07/06/2009 | 10/30/2009 | 303578 | 2.02
10563 | West Virginia | GREENBRIER |  | 3 | 0020256 | This project will improve safety for motorists by the construction of a 1.23 mile long truck climbing lane on West Virginia Route 20 in Greenbrier County. | Pavement Widening | 11/25/2009 | 12/10/2009 | 06/30/2010 | 2201710 | 1.23
10564 | West Virginia | MASON |  | 2 | 0029022 | This project will improve safety for motorists by replacing the Arlee Slab Bridge due to condition. The bridge is located on County Route 29 at approximately milepoint 5.59 in Mason County. | Bridge Replacement | 07/31/2009 | 11/10/2009 | 10/15/2009 | 317380 | 0.01
10565 | West Virginia | PENDLETON |  | 2 | 0033320 | This project will improve safety for motorists by resurfacing the deck of the Judy Gap Bridge with Latex Modified Concrete. The bridge is located on United States Route 33 at approximately milepoint 1 | Bridge Improvement | 11/16/2009 | 05/03/2010 | 06/30/2010 | 322200 | 0.05
10566 | West Virginia | UPSHUR |  | 2 | 0033321 | This project will improve safety for motorists by resurfacing 4.53 miles of United States Route 33 from the City of Buckhannon to Elkins Road in Upshur County. | Pavement Improvement | 07/06/2009 | 07/06/2009 | 10/30/2009 | 1399266 | 4.53
10567 | West Virginia | JACKSON |  | 2 | 0033322 | This project will improve safety for motorists by resurfacing 4.16 miles of deteriorated pavement on United States Route 33 from the City of Ripley to Frozencamp Road in Jackson County. | Pavement Improvement | 07/01/2009 | 07/11/2009 | 09/01/2009 | 1278600 | 4.16
10568 | West Virginia | RANDOLPH |  | 2 | 0033323 | This project will improve safety for motorists by resurfacing 1.75 miles of deteriorated pavement, drainage improvements and the construcion of a truck climbing lane on United States Route 33 (Shavers | Pavement Widening | 05/07/2010 | 05/21/2010 | 09/30/2010 | 2753900 | 1.76
10569 | West Virginia | PENDLETON |  | 2 | 0033327 | This project will improve safety for motorists by replacing the Rough Run Bridge due to condition. The bridge is located on County Route 3/3 at approximately milepoint 0.73 in Pendleton County. | Bridge Replacement | 10/29/2009 | 02/04/2010 | 06/30/2010 | 502940 | 0.01
10570 | West Virginia | RALEIGH |  | 3 | 0034067 | This project will improve safety for motorists by replacing the Horse Creek Bridge #5 due to condition. The bridge is located on County Route 3/4 at approximately milepoint 2.12 in Raleigh County. | Bridge Replacement | 09/16/2009 | 09/17/2009 | 06/30/2010 | 459850 | 0.009
10571 | West Virginia | CLAY |  | 2 | 0036040 | This project will improve safety for motorists by resurfacing 5.24 miles of WV 36 from Wallback to Clay RD in Clay County. | Pavement Improvement | 05/03/2010 | 06/02/2010 | 10/15/2010 | 1160700 | 5.24
10572 | West Virginia | WAYNE | HUNTINGTON-ASHLAND (KY-OH) | 3 | 0037028 | This project will improve safety for motorists by the installation of piling for embankment stabilization on West Virginia Route 37 at milepoint 18.64 in Wayne County. | Pavement Improvement | 11/12/2009 | 12/01/2009 | 06/30/2010 | 209143 | 0.03
10573 | West Virginia | NICHOLAS |  | 3 | 0039406 | This project will improve safety for motorists by resurfacing 1.29 miles of deteriorated pavement on West Virginia 39 (Deer Creek Road) beginning at approximately milepoint 35.12 in Nicholas County. | Pavement Improvement | 05/29/2009 | 06/26/2009 | 10/30/2009 | 388600 | 1.29
10574 | West Virginia | NICHOLAS |  | 3 | 0041072 | This project will improve safety for motorists by resurfacing 2.10 miles of deteriorated pavement on West Virginia 41 from the City of Glade Creek to Nile Road in Nicholas County. | Pavement Improvement | 10/14/2009 | 10/30/2009 | 05/30/2010 | 570700 | 2.01
10575 | West Virginia | RITCHIE |  | 1 | 0050276 | This project will improve safety for motorists by resurfacing 2.18 miles of deteriorated pavement on United States Route 50 between Nutter Farm and Camp Run Road beginning at approximately milepoint 2 | Pavement Improvement | 04/21/2009 | 06/28/2009 | 09/22/2009 | 944561 | 2.18
10576 | West Virginia | RITCHIE |  | 1 | 0050277 | This project will improve safety for motorists by resurfacing 2.23 miles of deteriorated pavement on United States Route 50 between Camp run Road and Ellenboro Road beginning at approximately milepoin | Pavement Improvement | 04/21/2009 | 07/04/2009 | 09/08/2009 | 965687 | 2.23
10577 | West Virginia | HAMPSHIRE |  | 2 | 0050278 | This project will improve safety for motorists by resurfacing 0.86 miles and the construction of a center turning lane on United States Route 50 at approximately milepoint 8.50 in Hampshire County. | Pavement Improvement | 08/31/2009 | 09/10/2009 | 06/30/2010 | 3693560 | 1.58
10578 | West Virginia | TAYLOR |  | 1 | 0050279 | This project will improve safety for motorists by the construction of a 1.90 mile truck climbing lane and the realignment of a hazardous curve on United States Route 50 beginning at milepoint 3.46 in | Pavement Widening | 06/22/2009 | 08/10/2009 | 10/30/2009 | 2338680 | 1.9
10579 | West Virginia | HARRISON |  | 1 | 0050280 | This project will improve safety for motorists by resurfacing 2.68 miles of US 50 in Harrison County. | Pavement Improvement | 04/01/2010 | 06/07/2010 | 10/29/2010 | 2144700 | 2.68
10580 | West Virginia | WAYNE |  | 3 | 0052263 | This project will improve safety for motorists by resurfacing 2.29 miles of United States Route 52 from the City of Stonecoal to the Mingo County line in Wayne County. | Pavement Improvement | 07/01/2009 | 07/08/2009 | 10/30/2009 | 1411700 | 2.29
10581 | West Virginia | MERCER |  | 3 | 0052264 | This project will improve safety for motorists by resurfacing 1.50 miles of deteriorated pavement on United States Route 52 from the City of Pinnacle Rock to Lorton Lick Road in Mercer County. | Pavement Improvement | 05/20/2009 | 06/11/2009 | 10/30/2009 | 612479 | 1.5
10582 | West Virginia | WAYNE | HUNTINGTON-ASHLAND (KY-OH) | 3 | 0052265 | This project will improve safety for motorists by resurfacing 5.42 miles of United States Route 52 from West Virginia Route 75 to Whites Creek Road in Wayne County. | Pavement Improvement | 08/17/2009 | 08/24/2009 | 10/30/2009 | 790000 | 6.42
10583 | West Virginia | MERCER |  | 3 | 0052270 | This project will extend the life of the Tunnel Overpass Bridge by cleaning and repainting the structure. The bridge is located on United States Route 52 at approximately milepoint 18.67 in Mercer Cou | Bridge Improvement | 07/21/2009 | 08/24/2009 | 10/15/2009 | 286500 | 0.04
10584 | West Virginia | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 3 | 0052271 | This project will extend the life of the Madison Avenue Overpass Bridge by cleaning the structure and repainting it. The bridge is located at Milepoint 0.73 on West Virginia Route 52 in Cabell County. | Bridge Improvement | 09/16/2009 | 11/14/2009 | 10/15/2009 | 173200 | 0.01
10585 | West Virginia | FAYETTE |  | 3 | 0060252 | This project will improve safety for motorists by replacing the existing and failing piling currently restricting slippage of the embankment on United States Route 60 at milepoint 14.60 in Fayette Cou | Pavement Improvement | 07/23/2009 | 08/25/2009 | 10/30/2009 | 155100 | 0.01
10586 | West Virginia | FAYETTE |  | 3 | 0061065 | This project will improve safety for motorists by resurfacing 1.24 miles of deteriorated pavement on West Virginia Route 61 from the City of Kincaid to Page Road in Fayette County. | Pavement Improvement | 05/20/2009 | 07/07/2009 | 10/30/2009 | 365000 | 1.24
10587 | West Virginia | FAYETTE |  | 3 | 0061066 | This project will improve safety for motorists by resurfacing 0.95 miles of deteriorated pavement on West Virginia Route 61 (Ingram Branch Road) in Fayette County. | Pavement Improvement | 06/23/2009 | 07/10/2009 | 10/30/2009 | 314912 | 0.95
10588 | West Virginia | RANDOLPH |  | 2 | 0062832 | This project will improve safety for motorists by replacing the Lower Mingo Bridge due to condition. The bridge is located on County Route 62 at approximately milepoint 0.08 in Randolph County. | Bridge Replacement | 10/29/2009 | 05/06/2010 | 06/30/2010 | 524700 | 0.01
10589 | West Virginia | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 0067005 | This project will improve safety for motorists by resurfacing 4.07 miles of detiorated pavement on West Virginia Route 67 from the City of Wellsburg to Bethany Road in Brooke County. | Pavement Improvement | 02/22/2010 | 04/09/2010 | 06/30/2010 | 789300 | 4.07
10590 | West Virginia | PRESTON |  | 1 | 0068135 | This project will improve safety for motorists by resurfacing the deck of the Laurel Run Bridges (West bound & East bound) with Latex Modified Concrete. The bridge is located on Interstate 68 at appro | Bridge Improvement | 12/07/2009 | 04/05/2010 | 07/30/2010 | 660600 | 0.01
10591 | West Virginia | MONONGALIA |  | 1 | 0068137 | This project will improve safety for motorists by resurfacing 2.20 miles of deteriorated pavement on Interstate 68 from the City of Pierpont to the West end of the Cheat Lake Bridge in Monongalia Coun | Pavement Improvement | 07/21/2009 | 07/23/2009 | 10/30/2009 | 1196116 | 2.2
10592 | West Virginia | MONONGALIA |  | 1 | 0068139 | This project will extend the life of the Cheat Lake Bridge by cleaning and repainting the structure. The bridge is located on Interstate 68 at approximately milepoint 9.39 in Monongalia County. | Bridge Improvement | 07/06/2009 | 03/26/2010 | 10/15/2010 | 6155000 | 0.02
10593 | West Virginia | OHIO | WHEELING (OH) | 1 | 0070158 | This project will improve safety for motorists by replacement of the existing bridge approach slabs, concrete repairs and drainage improvements on Interstate 70 beginning at the West Virginia/Ohio sta | Pavement Improvement | 05/27/2009 | 05/27/2009 | 10/30/2009 | 3351655 | 0.05
10594 | West Virginia | MARSHALL | WHEELING (OH) | 1 | 0074051 | This project will improve safety for motorists by replacing the Shepherd Bridge due to condition. The bridge is located on County Route 74 at approximately milepoint 16.8 in Marshall County. | Bridge Replacement | 05/28/2009 | 05/28/2009 | 05/28/2010 | 1552180 | 0.05
10595 | West Virginia | MCDOWELL |  | 3 | 0080032 | This project will improve safety for motorists by resurfacing 2.00 miles of West Virginia Route 80 from the City of Beartown to Iaeger Road in McDowell County. | Pavement Improvement | 05/01/2009 | 05/15/2009 | 10/30/2009 | 599234 | 2
10596 | West Virginia | NICHOLAS |  | 3 | 0082013 | This project will improve safety for motorists by resurfacing 2.20 miles of WV 82 in Webster County between Birch River and Boggs Road. | Pavement Improvement | 03/30/2010 |  | 10/15/2010 | 379000 | 2.2
10597 | West Virginia | KANAWHA | CHARLESTON | 2 | 0094168 | This project will improve safety for motorists by resurfacing 5.52 miles of West Virginia Route 94 beginning at approximately milepoint 1.48 from the City of Hernshaw to the City of Marmet in Kanawha | Pavement Improvement | 05/01/2009 | 05/11/2009 | 10/30/2009 | 2051683 | 5.52
10598 | West Virginia | GREENBRIER |  | 3 | 0099099 | This project will improve safety for motorists by replacing the Sinking Creek Bridge due to condition. The bridge is located on County Route 9/9 in Greenbrier County. | Bridge Replacement | 09/30/2009 | 12/01/2009 | 06/30/2010 | 241630 | 0.01
10599 | West Virginia | MONONGALIA |  | 1 | 0109013 | This project will help eliminate congestion and help in the movement of motorists and commerce by the construction of 0.14 miles of four lane highway, an interstate ramp, a box culvert and constructio | New Construction | 07/21/2009 | 08/12/2009 | 10/29/2010 | 13378800 | 0.14
10600 | West Virginia | LINCOLN |  | 3 | 0119339 | This project will extend the life of the Little Coal River Bridges (North & South) by cleaning and repainting the structure. The bridges are located on United States Route 119 at approximately milepoi | Bridge Improvement | 09/16/2009 | 09/12/2009 | 10/15/2009 | 725200 | 0.039
10601 | West Virginia | MINGO |  | 3 | 0119341 | This project will improve safety for motorists by resurfacing 4.26 miles of US 119 between Miller Creek and Belo in Mingo County. | Pavement Improvement | 04/13/2010 |  | 10/15/2010 | 2693100 | 4.26
10602 | West Virginia | KANAWHA | CHARLESTON | 2 | 0119342 | This project will improve safety for motorists by resurfacing 2.54 miles of deteriorated pavement on United States Route 119 beginning approximately at milepoint 39.13 in Kanawha County. | Pavement Improvement | 09/30/2009 | 05/03/2010 | 05/28/2010 | 617620 | 2.54
10603 | West Virginia | MINGO |  | 3 | 0119344 | This project will improve safety for motorists by resurfacing the deck of the West Belo Bridge with Latex Modified Concrete. The bridge is located on United States Route 119 at approximately milepoint | Bridge Improvement | 07/15/2009 | 08/11/2009 | 10/30/2009 | 401400 | 0.05
10604 | West Virginia | GREENBRIER |  | 3 | 0206002 | This project will improve safety for motorists by replacing the Greenbrier Avenue Bridge due to condition. The bridge is located on County Route 20/6 in Rainelle, Greenbrier County. | Bridge Replacement | 07/09/2009 | 07/20/2009 | 11/06/2009 | 480894 | 0.04
10605 | West Virginia | RANDOLPH |  | 2 | 0219299 | This project will improve safety for motorists by replacing the Jones Run Bridge due to condition. The bridge is located on United States Route 219 at approximately milepoint 28.50 in Randolph County. | Bridge Replacement | 07/15/2009 | 08/19/2009 | 09/10/2010 | 882830 | 0.01
10606 | West Virginia | MONROE |  | 3 | 0219300 | This project will improve safety for motorists by resurfacing 2.34 miles of deteriorated pavement on United States Route 219 beginning at approximately milepoint 0.50 in Peterstown, Monroe County. | Pavement Improvement | 05/15/2009 | 05/15/2009 | 10/30/2009 | 729612 | 2.34
10607 | West Virginia | TUCKER |  | 1 | 0219302 | This project will improve safety for motorists by resurfacing 1.20 miles of deteriorated pavement on United States Route 219 from the City of Parsons to Mackeyville Road in Tucker County. | Pavement Improvement | 09/21/2009 | 09/21/2009 | 05/28/2010 | 785610 | 1.2
10608 | West Virginia | RANDOLPH |  | 2 | 0219303 | This project will improve safety for motorists by resurfacing 1.20 miles of deteriorated pavement on United States Route 219, construction of turning lanes and the improvement of drainage from the Cit | Pavement Widening | 07/14/2009 | 07/30/2009 | 10/30/2009 | 1616480 | 1.2
10609 | West Virginia | PENDLETON |  | 2 | 0220182 | This project will improve safety for motorists by the installation of piling on United States Route 220 at approximately milepoint 13.30 between Smith Creek and Franklin Road for embankment stabilizat | Pavement Improvement | 04/13/2009 | 05/21/2009 | 10/30/2009 | 972000 | 0.18
10610 | West Virginia | MINERAL |  | 1 | 0220183 | This project will improve safety for motorists by resurfacing 0.87 miles of deteriorated pavement on United States Route 220 beginning at approximately milepoint 13.96 in Mineral County. | Pavement Improvement | 07/29/2009 | 08/18/2009 | 10/30/2009 | 1007870 | 0.97
10611 | West Virginia | MONROE |  | 3 | 0238046 | This project will improve safety for motorists by replacing the Indian Creek Bridge due to condition. The bridge is located at approximately milepoint 1.93 on County Route 23/8 in Monroe County. | Bridge Replacement | 11/06/2009 | 11/16/2009 | 06/30/2010 | 677160 | 0.01
10612 | West Virginia | MARSHALL | WHEELING (OH) | 1 | 0250183 | This project will improve safety for motorists by resurfacing the deck of the Bellaire Interchange Bridge with Latex Modified Concrete. The bridge is located on United States Route 250 at approximatel | Bridge Improvement | 07/27/2009 | 10/06/2009 | 06/30/2010 | 556820 | 0.01
10613 | West Virginia | MARSHALL | WHEELING (OH) | 1 | 0250184 | This project will improve safety for motorists by resurfacing 5.44 miles of deteriorated pavement on United States Route 250 in the City of McMechen, Marshall County. | Pavement Improvement | 05/06/2009 | 05/06/2009 | 10/30/2009 | 4459333 | 5.44
10614 | West Virginia | KANAWHA | CHARLESTON | 2 | 0271001 | This project will improve safety for motorists by replacing the Eden's Fork Pony Truss Bridge due to condition. The bridge is located on County Route 27/1 at approximately milepoint 1.1 in Kanawha Cou | Bridge Replacement | 08/14/2009 | 09/18/2009 | 04/06/2010 | 997319 | 0.03
10615 | West Virginia | MERCER |  | 3 | 0385005 | This project will improve safety for motorists by replacing the Jug Neck Bridge due to condition. The bridge is located on County Route 38/5 at approximately milepoint 0.85 in Mercer County. | Bridge Replacement | 07/24/2009 | 08/04/2009 | 11/06/2009 | 435090 | 0.01
10616 | West Virginia | MERCER |  | 3 | 0385006 | This project will improve safety for motorists by replacing the Blake Bridge due to condition. The bridge is located on County Route 38/5 at approximately milepoint 4.00 in Mercer County. | Bridge Replacement | 08/07/2009 | 08/07/2009 | 11/06/2009 | 449370 | 0.01
10617 | West Virginia | WAYNE |  | 3 | 0411002 | This project will improve safety for motorists by replacing the Turkey Creek Pony Truss Bridge downstream due to condition. The bridge is located on County Route 41/1 at approximately milepoint 0.01 i | Bridge Replacement | 12/11/2009 | 12/07/2009 | 08/31/2010 | 916170 | 0.01
10618 | West Virginia | MERCER |  | 3 | 0460038 | This project will improve safety for motorists by resurfacing the deck of both the East bound and West bound Oakvale Bridges with Latex Modified Concrete. The bridges are located on United States Rou | Bridge Improvement | 06/04/2009 | 06/18/2009 | 10/30/2009 | 890900 | 0.1
10619 | West Virginia | MERCER |  | 3 | 0460039 | This project will improve safety for motorists by resurfacing 1.67 miles of deteriorated pavement on United States Route 460 beginning at approximately milepoint 4.29 in Bluefield, Mercer County. | Pavement Improvement | 04/13/2009 | 04/20/2009 | 07/27/2009 | 1407164 | 1.67
10620 | West Virginia | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 1 | 0641332 | This project will improve safety for motorists by resurfacing the deck of three Cabell County bridges, Cedar Crest Bridge and both County Route 26 overpass bridges (East & West), with Latex Modified C | Bridge Improvement | 07/15/2009 | 03/29/2010 | 05/28/2010 | 766900 | 5.14
10621 | West Virginia | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 3 | 0641334 | This project will improve safety for motorists by resurfacing 1.59 miles of deteriorated pavement on Interstate 64 from the City of Milton to County Route 60/19 in Cabell County. | Pavement Improvement | 06/16/2009 | 06/24/2009 | 10/30/2009 | 997100 | 1.56
10622 | West Virginia | PUTNAM | HUNTINGTON-ASHLAND (KY-OH) | 2 | 0641335 | This project will improve safety for motorists by resurfacing 4.67 miles of deteriorated pavement on Interstate 64 from the Hurricane Interchange to the Winfield Interchange in Putnam County. | Pavement Improvement | 10/02/2009 | 10/12/2009 | 06/15/2010 | 8292800 | 4.67
10623 | West Virginia | GREENBRIER |  | 3 | 0644170 | This project will extend the life of the Mountain Avenue Bridges (North & South) by cleaning the structure and repainting it. The bridges are located at approximately milepoint 179.36 of Interstate 64 | Bridge Improvement | 08/26/2009 | 09/16/2009 | 10/30/2009 | 603606 | 0.179
10624 | West Virginia | GREENBRIER |  | 3 | 0644171 | This project will improve safety for motorists by resurfacing 1.50 miles of deteriorated pavement on Interstate 64 at approximately milepoint 174.61 in Greenbrier County. | Pavement Improvement | 05/15/2009 | 04/05/2010 | 10/30/2009 | 2629450 | 1.5
10625 | West Virginia | GREENBRIER |  | 3 | 0644172 | This project will improve safety for motorists by resurfacing 1.00 miles of deteriorated pavement on Interstate 64 at approximately milepoint 160.00 in Greenbrier County. | Pavement Improvement | 05/15/2009 | 05/27/2009 | 10/30/2009 | 1425900 | 1
10626 | West Virginia | MONONGALIA |  | 1 | 0705011 | This project will improve safety for motorists by resurfacing 1.00 miles of deteriorated pavement on West Virginia Route 705 beginning approximately at milepoint 2.55 in Morgantown, Monongalia County. | Pavement Improvement | 09/09/2009 | 09/14/2009 | 05/28/2010 | 1759900 | 1
10627 | West Virginia | FAYETTE |  | 03 | 0772083 | This project will improve safety for motorists by the installation of movable barriers at various locations on the West Virginia Turnpike to allow for the opening of lanes, movement of traffic, etc. d | Safety/Traffic Management | 01/29/2010 |  | 05/14/2010 | 911500 | 6
10628 | West Virginia | WOOD | PARKERSBURG (OH) | 1 | 0773399 | This project will improve safety for motorists by resurfacing the decks of four bridges, the County Route 25 Overpass Bridges (North and South), Wolf Run Overpass and the Buck Run Overpass, with Latex | Bridge Improvement | 07/27/2009 | 07/27/2009 | 05/28/2010 | 1168400 | 0.01
10629 | West Virginia | WOOD | PARKERSBURG (OH) | 1 | 0773402 | This project will improve safety for motorists by resurfacing the decks of five bridges, the Interstate 77/United States Route 50 Interchange Bridge, Worthington Creek Bridge, West Virginia Route 31 O | Bridge Improvement | 07/27/2009 | 07/27/2009 | 06/18/2010 | 1232000 | 9.45
10630 | West Virginia | LEWIS |  | 2 | 0792156 | This project will improve safety for motorists by resurfacing two bridges, Stone Coal Creek Bridge and the County Route 14 Overpass Bridge, on Interstate 79 in Lewis County. | Bridge Improvement | 08/05/2009 | 03/04/2010 | 10/30/2009 | 1179299 | 0.109
10631 | West Virginia | BRAXTON |  | 2 | 0792158 | This project will improve safety for motorists by resurfacing the deck of three bridges, the Little Kanawha River Bridge and the Oil Creek Bridges (North & South) on Interstate 79 in Braxton County wi | Bridge Improvement | 08/05/2009 | 03/09/2010 | 01/28/2010 | 2206800 | 0.439
10632 | West Virginia | ROANE |  | 2 | 0792160 | This project will improve safety for motorists by resurfacing the deck of the Wallback Interchange Bridge with Latex Modified Concrete. The bridge is located on Interstate 79 at approximately milepoin | Bridge Improvement | 03/10/2010 | 04/28/2010 | 06/30/2010 | 581900 | 0.059
10633 | West Virginia | BRAXTON |  | 2 | 0792161 | This project will extend the life of the Kenton Meadows Senior Bridges (North & South) by cleaning the structures and repainting them. The bridges are located on Interstate 79 at approximately milepoi | Bridge Improvement | 04/15/2010 | 04/22/2010 | 07/30/2010 | 1270000 | 0.28
10634 | West Virginia | ROANE |  | 2 | 0792162 | This project will extend the life of the Amma/Big Sandy Bridges (North & South) by cleaning and painting the structures. The bridges are located on Interstate 79 at approximately milepoint 25.79 in Ro | Bridge Improvement | 06/29/2009 | 07/22/2009 | 09/18/2009 | 906542 | 0.18
10635 | West Virginia | BRAXTON |  | 2 | 0792164 | This project will improve safety for motorists by resurfacing 6.99 iles of detiorated pavement, installation of raised pavement markers, guardrail repair/replacement and shoulder pavement/reconstuctio | Pavement Improvement | 07/13/2009 | 07/27/2009 | 10/30/2009 | 2940001 | 6.99
10636 | West Virginia | BRAXTON |  | 2 | 0792167 | This project will extend the life of the Saltlick Creek Bridges (North & South) by cleaning the structures and repainting them. The bridges are located on Interstate 79 at approximately milepoint 78.1 | Bridge Improvement | 09/16/2009 | 09/18/2009 | 10/15/2010 | 638466 | 0.119
10637 | West Virginia | ROANE |  | 2 | 0792168 | This project will improve Safety for motorists by resurfacing 4.49 miles of deteriorated pavement on Interstate 79 between the City of Amma and Wallback Road in Roane County. | Pavement Improvement | 05/11/2009 | 06/08/2009 | 10/30/2009 | 3069900 | 4.49
10638 | West Virginia | MONONGALIA |  | 1 | 0793222 | This project will improve safety for motorists by resurfacing the deck of the Westover Bridge with Latex Modified Concrete. The bridge is located on Interstate 79 at approximately milepoint 152.53 in | Bridge Improvement | 10/13/2009 | 04/05/2010 | 06/30/2010 | 992400 | 0.48
10639 | West Virginia | MARION |  | 1 | 0793223 | This project will improve safety for motorists by resurfacing 2.19 miles of deteriorated pavement on Interstate 79 beginning at approximately milepoint 136.68 in Fairmont, Marion County. | Pavement Improvement | 04/16/2009 | 04/17/2009 | 10/30/2009 | 1245675 | 2.19
10640 | West Virginia | BERKELEY | HAGERSTOWN | 2 | 0811104 | This project will improve safety for motorists by resurfacing 4.65 miles of deteriorated pavement on Interstate 81 from Falling Waters to the Maryland/West Virginia State line in Berkeley County. | Pavement Improvement | 07/01/2009 | 07/12/2009 | 10/30/2009 | 2167300 | 4.65
10641 | West Virginia | BERKELEY | HAGERSTOWN | 2 | 0811105 | This project will improve safety for motorists by resurfacing 4.27 miles of deteriorated pavement on Interstate 81 from the Virginia/West Virginia State Line to Inwood Road, in Berkely County. | Pavement Improvement | 07/01/2009 | 08/11/2009 | 10/30/2009 | 1748260 | 4.27
10642 | West Virginia | LEWIS |  | 2 | 1191007 | This project will improve safety for motorists by replacing the Sleeths Run Truss Bridge due to condition. The bridge is located on US Route 119 at approximately milepoint 0.09 in Lewis County. | Bridge Replacement | 07/17/2009 | 07/30/2009 | 08/30/2010 | 1279500 | 0.02
10643 | West Virginia | FAYETTE |  | 3 | 1601001 | This project will improve safety for motorists by replacing the Michigan Avenue Bridge due to condition. The bridge is located at approximately milepoint 0.01 of County Route 160/17 in Fayette County. | Bridge Replacement | 08/21/2009 | 08/21/2009 | 04/06/2010 | 660010 | 0.01
10644 | West Virginia | MCDOWELL |  | 3 | 1659001 | This project will improve safety for motorists by replacing the South Roselawn Street Bridge on County Route 16/59 at approximately milepoint 0.01 in McDowell County. | Bridge Replacement | 11/02/2009 | 03/01/2010 | 05/28/2010 | 443120 | 0.001
10645 | West Virginia | NICHOLAS |  | 3 | 1919002 | This project will improve safety for motorists by replacing the Peters Creek Bridge due to condition. The bridge is located on County Route 19/19 at approximately milepoint 0.03 in Nicholas County. | Bridge Replacement | 08/27/2009 | 03/15/2010 | 11/30/2010 | 457040 | 0.001
10646 | West Virginia | MONONGALIA |  | 1 | 2009170 | Construction/reconstruction of sidewalks, curbs and gutters along Main Street (West Virginia Route 100) from Dent's Run Bridge to Everly Street in Granville, Monongalia County. Project elements inclu | Transportation Enhancements | 06/02/2010 |  | 09/30/2010 | 617900 | 0
10647 | West Virginia | PLEASANTS |  | 1 | 2009172 | Reconstruction of sidewalks and curbing, installation of lighting , and minor drainage along Washington Street from WV 2 to Second Street in St. Marys, Pleasants County. | Transportation Enhancements | 06/22/2010 |  | 09/30/2010 | 152900 | 0
10648 | West Virginia | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 1 | 2009174 | Sidewalk construction, installation of decorative and historic brick pavers and curbing at various intersections along Charles Street, 22nd and 23rd Streets at their intersections with Pleasant Avenue | Transportation Enhancements | 06/17/2010 |  | 09/30/2010 | 135300 | 0
10649 | West Virginia | ROANE |  | 2 | 2009182 | Construction of sidewalks, crosswalks, curbing, lighting and minor drainage along Main Street from the intersection of US 33/US 119 to Court Street; Market Street from Court Street and along US 33 wes | Transportation Enhancements | 06/22/2010 |  | 09/30/2010 | 84200 | 0
10650 | West Virginia | WEBSTER |  | 3 | 2009192 | Construction of ADA compliant walking trail and minor drainage improvements to connect the facilities on the island to the facilities at Bakers Island in Webster Springs, Webster County. | Transportation Enhancements | 06/03/2010 |  | 09/30/2010 | 71307 | 0
10651 | West Virginia | OHIO | WHEELING (OH) | 1 | 2009232 | This project will improve safety for motorists by the installation or replacement of guardrail in various locations throughout WVDOH District 6 area. | Safety/Traffic Management | 06/01/2010 |  | 11/15/2010 | 126500 | 0
10652 | Wisconsin | PORTAGE |  | 7 | 2009242 | This is a bridge replacement project in Portage County on a town road, County Highwy P - Cemetary Road. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 565000 | 0.076
10653 | Wisconsin | WOOD |  | 7 | 2009244 | This is a bridge replacement project in Wood County on County Highway K, Branch of Mill Creek Crossing. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 285000 | 0.057
10654 | Wisconsin | PRICE |  | 7 | 2009245 | This is a bridge replacement project in Price County on a town road, Holmes Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 321338.95 | 0.086
10655 | Wisconsin | PRICE |  | 7 | 2009246 | This is a bridge replacement project in Price County on a town road, Douglas Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 193456.06 | 0.062
10656 | Wisconsin | TAYLOR |  | 7 | 2009254 | This is a bridge replacement project in Taylor County on County Highway D, Mondeaux River Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 512500 | 0
10657 | Wisconsin | JEFFERSON |  | 5 | 2009366 | This is a reconstruction project in Jefferson County on State Highway 59, Village of Palmyra, Maple Street. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 1343575.52 | 0.85
10658 | Wisconsin | JEFFERSON |  | 2,5 | 2009367 | This is a restoration and rehabilitation project in Jefferson County on State Highway 59, Whitewater - Palmyra Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 2202046.04 | 67.05
10659 | Wisconsin | DANE | MADISON | 2 | 2009368 | This is a bridge rehabilitation project in Dane County on US Highway 151, Sun Prairie Bypass. | Bridge Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 524210.55 | 0.02
10660 | Wisconsin | ROCK |  | 2 | 2009369 | This is a reconstruction project in Rock County on State Highway 11, Footville - Janesville Bypass. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 3132000 | 22.4
10661 | Wisconsin | VERNON |  | 3 | 2009370 | This is a restoration and rehabilitation project in Vernon County on State Highway 82, LaFarge and Otter Creek Briges. | Pavement Improvement | 05/15/2009 | 05/15/2009 | 10/01/2009 | 832000 | 0.231
10662 | Wisconsin | SAUK |  | 2 | 2009371 | This is a bridge rehabilitation project in Sauk County on US Highway 12, Lake Delton, Dell Creek Bridge and approaches. | Bridge Improvement | 05/15/2009 | 05/15/2009 | 06/01/2010 | 3038220.19 | 0.133
10663 | Wisconsin | RACINE |  | 1 | 2009372 | This is a reconstruction project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 08/01/2010 | 4626581.72 | 0.61
10664 | Wisconsin | RACINE |  | 1 | 2009373 | This is a reconstruction project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 08/01/2010 | 6124945.95 | 0.61
10665 | Wisconsin | RACINE |  | 1 | 2009374 | This is a reconstruction with additional lanes project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Widening | 03/30/2009 | 03/30/2009 | 08/01/2010 | 10839551.47 | 0.61
10666 | Wisconsin | RACINE |  | 1 | 2009375 | This is a fencing project in Racine County on Interstate 94. | Other | 03/30/2009 | 03/30/2009 | 08/01/2010 | 95401.9 | 0.61
10667 | Wisconsin | KENOSHA |  | 1 | 2009376 | This is a reconstruction with additional lanes project in Kenosha County on Interstate 94, North-South Freeway, County Highway C Interchange, mainline and ramps. | Pavement Widening | 03/30/2009 | 03/30/2009 | 12/01/2010 | 27023140.6 | 1.08
10668 | Wisconsin | KENOSHA |  | 1 | 2009377 | This is a reconstruction with additional lanes project in Kenosha County on Interstatet 94, North - South Freeway, Illinois State Line to County Highway C, mainline. | Pavement Widening | 03/30/2009 | 03/30/2009 | 12/01/2010 | 34193016.87 | 16.5
10669 | Wisconsin | KENOSHA |  | 1 | 2009378 | This is a bridge replacement with added lanes project in Kenosha County on Interstate 94, North South Freeway, County Highway C to State Highway 50, mainline. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 12/01/2010 | 5007480.82 | 0.66
10670 | Wisconsin | WAUPACA |  | 8 | 2009379 | This is a project in Waupaca County on State Highway 49, City of Waupaca. | Safety/Traffic Management | 03/30/2009 | 03/30/2009 | 09/01/2009 | 164374.87 | 0.095
10671 | Wisconsin | LINCOLN |  | 7 | 2009380 | This is a bridge rehabilitation project in Lincoln County on US Highway 51, Merrill - Tomahawk. | Bridge Improvement | 03/30/2009 | 03/30/2009 | 11/01/2009 | 1182735.39 | 0.8
10672 | Wisconsin | WOOD |  | 7 | 2009381 | This is a resurfacing project in Wood County on State Highway 13, Pittsville - Marshfield. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 12/30/2009 | 818600.13 | 7.614
10673 | Wisconsin | MARATHON |  | 7 | 2009382 | This is a resurfacing project in Marathon County on State Highway 153, Mosinee, Crooked Lake Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 06/01/2009 | 776804.13 | 43.596
10674 | Wisconsin | LANGLADE |  | 8 | 2009383 | This is a restoration and rehabilitation project in Langlade County on State Highway 52, Lily, Forest County Line. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 966000 | 22.16
10675 | Wisconsin | ST CROIX |  | 3 | 2009384 | This is a resurfacing project in St. Croix County on State Highway 64, New Richmond, Connorsville Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 3907157.55 | 50.47
10676 | Wisconsin | ST CROIX |  | 3 | 2009385 | This is a project in St. Croix County on State Highway 64, New Richmond, Connorsville Road. | Safety/Traffic Management | 03/30/2009 | 03/30/2009 | 10/01/2009 | 505495.91 | 0.18
10677 | Wisconsin | POLK |  | 7 | 2009386 | This is a resurfacing project in Polk County on US Highway 8, St. Croix Falls - Turtle Lake. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 3225447.52 | 74.16
10678 | Wisconsin | BURNETT |  | 7 | 2009387 | This is a resurfacing project in Burnett County on State Highway 70, Siren - Spooner. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 3196143.72 | 132.55
10679 | Wisconsin | DUNN |  | 3 | 2009388 | This is a restoration and rehabilitation project in Dunn County on State Highway 25, Menomonie - Wheeler Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 2165000 | 28.9
10680 | Wisconsin | DUNN |  | 3 | 2009389 | This is a resurfacing project in Dunn County on State Highway 64, New Richmond - Bloomer. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 1718368.73 | 38.88
10681 | Wisconsin | DANE |  | 2 | 2009390 | This is a reconstruction project in Dane County on County Highway B, Village of Rockdale. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 05/01/2010 | 972530.98 | 0.8
10682 | Wisconsin | LAFAYETTE |  | 3 | 2009391 | This is a bridge replacement project in Lafayette County on County Highway H, Fever River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 643416.39 | 0.145
10683 | Wisconsin | CRAWFORD |  | 3 | 2009392 | This is a reconstruction project in Crawford County on a town road, Rush Creek Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 436610.67 | 0.1
10684 | Wisconsin | SAUK |  | 3 | 2009393 | This is a bridge replacement project in Sauk County on County Highway G, Baraboo River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 870000 | 0.28
10685 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009394 | This is a bridge rehabilitation with added lanes project in Waukesha County on local streets, Valentine Road, Bridge over Oconomowoc River. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 228238.14 | 0
10686 | Wisconsin | WASHINGTON |  | 5 | 2009395 | This is a bridge replacement project in Washington County on County Highway W, Bridge over Rock River. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 462426.06 | 0
10687 | Wisconsin | MANITOWOC |  | 6 | 2009396 | This is a reconstruction project in Manitowoc County on a town road, Newton Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 272330.66 | 0.66
10688 | Wisconsin | MANITOWOC |  | 6 | 2009397 | This is a reconstruction project in Manitowoc County on a town road, Valley Drive Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 199108.49 | 0
10689 | Wisconsin | MANITOWOC |  | 6 | 2009398 | This is a reconstruction project in Manitowoc County on a town road, South Cleveland Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 221783.43 | 0
10690 | Wisconsin | MANITOWOC |  | 6 | 2009399 | This is a reconstruction project in Manitowoc County on a town road, County line Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 195139.2 | 0
10691 | Wisconsin | FOND DU LAC |  | 6 | 2009400 | This is a bridge replacement project in Fond du Lac County on a town road, Youth Camp Road Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 410865.84 | 0
10692 | Wisconsin | IRON |  | 7 | 2009401 | This is a bridge replacement project in Iron County on local streets, Montreal River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 666325.92 | 0.043
10693 | Wisconsin | TREMPEALEAU |  | 3 | 2009402 | This is a bridge replacement project in Trempealeau County on County Highway D, Bruce Valley Creek Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 07/01/2009 | 429733.64 | 0.071
10694 | Wisconsin | BARRON |  | 7 | 2009403 | This is a bridge replacement project in Barron County on a town road, Yellow River Bridge. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 504690.05 | 0.28
10695 | Wisconsin | DOUGLAS |  | 7 | 2009404 | This is a bridge replacement project in Douglas County on local streets, Town of Cloverland, McNeil's Landing Road, Brule River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 387000.5 | 0
10696 | Wisconsin | DOUGLAS |  | 7 | 2009405 | This is a bridge replacement project in Douglas County on a town road, Town of Oakland, Rice Farm Road, Little Amnicon River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 360847.17 | 0
10697 | Wisconsin | TAYLOR |  | 7 | 2009406 | This is a bridge replacement project in Taylor County on local streets, City of Medford, Black River Bridge and approaches. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 08/01/2009 | 657757.63 | 0
10698 | Wisconsin | MONROE |  | 3 | 2009407 | This is a reconstruction project in Monroe County on a town road, Kettle Road, Town of Wilton. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 07/01/2009 | 183311.19 | 0.038
10699 | Wisconsin | LINCOLN |  | 7 | 2009408 | This is a bridge replacement project in Lincoln County on County Highway H, Little Pine Creek Bridge. | Bridge Replacement | 03/30/2009 | 03/30/2009 | 10/01/2009 | 249000 | 0.081
10700 | Wisconsin | TAYLOR |  | 7 | 2009409 | This is a resurfacing project in Taylor County on State Highway 64, Medford - Goodrich. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 2030000 | 200.102
10701 | Wisconsin | WAUPACA |  | 8 | 2009411 | This is a resurfacing project in Waupaca County on US Highway 45, Winchester - New London. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 09/01/2009 | 585582.05 | 3.515
10702 | Wisconsin | EAU CLAIRE |  | 3 | 2009412 | This is a resurfacing project in Eau Claire County on US Highway 12, Augusta - Fairchild Road. | Pavement Improvement | 03/30/2009 | 03/30/2009 | 07/01/2009 | 1027265.12 | 92.6
10703 | Wisconsin | DANE |  | 2 | 2009486 | This is a bridge rehabilitation project in Dane County on Interstate 90, Madison - Janesville Road, Drotning Road bridges. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 192000 | 0.03
10704 | Wisconsin | DANE |  | 2 | 2009487 | This is a bridge rehabilitation project in Dane County on Interstate 39, Madsion to Janesville Road, County Highway W bridges. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 182316.4 | 0.03
10705 | Wisconsin | DANE |  | 2 | 2009488 | This is a bridge rehabilitation project in Dane County on Interstate 39, Madison - Janesville Road, County Highway B bridges. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 175866.4 | 0.03
10706 | Wisconsin | ROCK |  | 1 | 2009489 | This is a bridge rehabilitation project in Rock County on County Highway A, Blackhawk Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 166702.97 | 0.057
10707 | Wisconsin | DANE | MADISON | 2 | 2009490 | This is a bridge rehabilitation project in Dane County on County Highway N, Edgerton - Stoughton, Yahara River Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 738953.16 | 0.1
10708 | Wisconsin | RICHLAND |  | 3 | 2009491 | This is a bridge replacement project in Richland County on County Highway I, Gault Hollow Creek Bridge. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 11/01/2009 | 446955.73 | 0.15
10709 | Wisconsin | SAUK |  | 3 | 2009492 | This is a bridge rehabilitation project in Sauk County on County Highway PF, Seeley Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 510000 | 0.07
10710 | Wisconsin | IOWA |  | 3 | 2009493 | This is a bridge rehabilitation project in Iowa County on a town road, River Road Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 452491.06 | 0.11
10711 | Wisconsin | GRANT |  | 3 | 2009494 | This is a reconstruction project in Grant County on County Highway C, US Highway 18 - Millville Road, Warner Creek Brige and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 515000 | 0.09
10712 | Wisconsin | LA CROSSE | LA CROSSE (MN) | 3 | 2009495 | This is a reconstruction project in La Crosse County on local streets, Oak Avenue, Onalaska and LaCrosse. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 1119781.66 | 2.64
10713 | Wisconsin | DANE | MADISON | 2 | 2009496 | This is a pedestrian and bicycle path project in Dane County, Starkweather Creek Bike and Pedestrian Path. | Transportation Enhancements | 04/17/2009 | 04/17/2009 | 05/01/2010 | 2300581.88 | 0
10714 | Wisconsin | DODGE |  | 6 | 2009497 | This is a reconstruction project in Dodge County on County Highway G, Beaver Dam - Randolph. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 08/01/2009 | 950000 | 14.959
10715 | Wisconsin | LA CROSSE | LA CROSSE (MN) | 3 | 2009498 | This is a resurfacing project in La Crosse County on State Highway 16, La Crosse, West Salem and Monegan O'Head. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 690153.14 | 0.08
10716 | Wisconsin | WALWORTH |  | 1 | 2009499 | This is a restoration and rehabilitation project in Walworth County on US Highway 12, State Highway 67 to State Highway 50. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 11/01/2009 | 3185000 | 75.67
10717 | Wisconsin | WALWORTH |  | 1 | 2009500 | This is a bridge rehabilitation project in Walworth County on Interstate 43, Rock Freeway. | Pavement Improvement | 04/20/2009 | 04/20/2009 | 11/01/2009 | 3305066 | 26.9
10718 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2009501 | This is a reconstruction project in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2010 | 9469411.63 | 79.5
10719 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2009502 | This is a new roadway construction project of 15.9 milesin Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 04/17/2009 | 04/17/2009 | 07/01/2010 | 4600000 | 15.9
10720 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2009503 | This is a new roadway construction project of 2.07 miles in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 04/17/2009 | 04/17/2009 | 08/01/2010 | 3582652.15 | 4.14
10721 | Wisconsin | MANITOWOC |  | 6 | 2009504 | This is a resurfacing project in Manitowoc County on State Highway 147, Two Rivers - Mishicot. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 1334233.69 | 32.22
10722 | Wisconsin | MANITOWOC |  | 6 | 2009505 | This is a resurfacing project in Manitowoc County on State Highway 147, Mishicot, and Interstate 43. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 1394027.81 | 57.28
10723 | Wisconsin | DOOR |  | 8 | 2009506 | This is a reconstruction project in Door County on local streets, Michigan Street. | Pavement Improvement | 04/17/2009 | 08/13/2009 | 10/01/2009 | 852000 | 1.15
10724 | Wisconsin | FOND DU LAC |  | 6 | 2009507 | This is a reconstruction project in Fond du Lac County on a town road, Lake Maria Road Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 219529.54 | 0.03
10725 | Wisconsin | FOND DU LAC |  | 6 | 2009508 | This is a bridge replacement project in Fond du Lac County on a town road, Oak Grove Road Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 280635.24 | 0
10726 | Wisconsin | MARATHON |  | 7 | 2009509 | This is a reconstruction project in Marathon County on Interstate 39, Stevens Point - Wausau. | Pavement Improvement | 04/20/2009 | 04/20/2009 | 07/01/2010 | 8694548.76 | 28.4
10727 | Wisconsin | MARATHON | WAUSAU | 7 | 2009510 | This is a reconstruction project in Marathon County on Interstate 39, Stevens Point - Wausau. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 07/01/2010 | 3190260.9 | 6.88
10728 | Wisconsin | WOOD |  | 7 | 2009511 | This is a resurfacing project in Wood County on State Highway 73, Pittsville - Neilsville. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 08/01/2009 | 1414972.87 | 61.146
10729 | Wisconsin | VILAS |  | 8 | 2009512 | This is a resurfacing project in Vilas County on US Highway 45, Eagle River - Land-o-Lakes. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 2118628.08 | 47.18
10730 | Wisconsin | MARATHON |  | 7 | 2009513 | This is a bridge replacement project in Marathon County on County Highway F, Stoney Creek Crossing. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 08/01/2009 | 417406.51 | 0.1
10731 | Wisconsin | ASHLAND |  | 7 | 2009514 | This is a restoration and rehabilitation project in Ashland County on US Highway 2, Odanah - Saxon, Government Road. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 08/01/2009 | 3170000 | 34.88
10732 | Wisconsin | POLK |  | 7 | 2009515 | This is a bridge rehabilitation project in Polk County on US Highway 8, St. Croix Falls - Turtle Lake. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 105650.36 | 0.01
10733 | Wisconsin | TREMPEALEAU |  | 3 | 2009516 | This is a bridge rehabilitation project in Trempealeau County on County Highway G, Pine Creek Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 11/01/2009 | 350000 | 0.076
10734 | Wisconsin | JACKSON |  | 3 | 2009517 | This is a reconstruction project in Jackson County on County Highway A, Hixton - Black River Falls. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 1825000 | 10.15
10735 | Wisconsin | SAWYER |  | 7 | 2009518 | This is a resurfacing project in Sawyer County on State Highway 77, Ghost Lake - Clam Lake. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 2815000 | 79.36
10736 | Wisconsin | TAYLOR |  | 7 | 2009519 | This is a bridge replacement project in Taylor County on County Highway M, Branch River Bridge and approaches. | Bridge Replacement | 04/17/2009 | 04/17/2009 | 11/01/2009 | 257871.04 | 0
10737 | Wisconsin | WALWORTH |  | 1 | 2009520 | This is a reconstruction project in Walworth County on County Highway C, Stateline Road - Pleasant Street. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 10/01/2009 | 992903.18 | 0.49
10738 | Wisconsin | VILAS |  | 8 | 2009521 | This is a resurfacing project in Vilas County on US Highway 45, Eagle River - Land-o-Lakes. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 09/01/2009 | 3157710.31 | 58.24
10739 | Wisconsin | KENOSHA |  | 1 | 2009523 | This is a reconstruction with additional lanes project in Kenosha County on Interstate 94, North-South Freeway, County Highway C Interchange fencing. | Pavement Widening | 05/14/2009 | 05/14/2009 | 12/01/2010 | 155588.13 | 29.15
10740 | Wisconsin | SHEBOYGAN |  | 6 | 2009524 | This is a bridge rehabilitation project in Sheboygan County on Interstate 43, Milwaukee, Green Bay Road. | Bridge Improvement | 04/17/2009 | 04/17/2009 | 07/01/2010 | 2329511.86 | 194.26
10741 | Wisconsin | SHEBOYGAN | SHEBOYGAN | 6 | 2009525 | This is a resurfacing project in Sheboygan County on Interstate 43, Port Washington - Manitowoc. | Pavement Improvement | 04/17/2009 | 04/17/2009 | 07/01/2010 | 14319091.08 | 83.12
10742 | Wisconsin | DANE | MADISON | 2 | 2009530 | This is a bridge replacement project in Dane County on Interstate 94, Madison - Milwaukee Road. | Pavement Widening | 05/14/2009 | 05/14/2009 | 12/01/2011 | 46925107.6 | 15.6
10743 | Wisconsin | WASHINGTON |  | 5 | 2009531 | This is a resurfacing project in Washington County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 670965.87 | 1.996
10744 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2009532 | This is a reconstruction with additional lanes project in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 05/14/2009 | 05/14/2009 | 10/01/2010 | 17122027.12 | 1.61
10745 | Wisconsin | BROWN |  | 8 | 2009533 | This is a bridge replacement project in Brown County on US Highway 41, Green Bay - Suamico. | Bridge Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 343409.42 | 0.04
10746 | Wisconsin | OCONTO |  | 8 | 2009534 | This is a bridge rehabilitation project in Oconto County on US Highway 41, Suamico - Abrams. | Bridge Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 142873.75 | 0.02
10747 | Wisconsin | MANITOWOC |  | 6 | 2009535 | This is a restoration and rehabilitation project in Manitowoc County on Interstate 43, Denmark, Manitowoc River, CN Railroad. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 07/01/2010 | 8410801 | 51.42
10748 | Wisconsin | BROWN |  | 6, 8 | 2009536 | This is a resurfacing project in Brown County on Interstate 43, US Highway 12 - County Highway M. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 07/01/2010 | 8146435.56 | 46.5
10749 | Wisconsin | FOND DU LAC |  | 6 | 2009537 | This is a resurfacing project in Fond du Lac County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 2181230.34 | 95.76
10750 | Wisconsin | FOND DU LAC |  | 6 | 2009538 | This is a resurfacing project in Fond du Lac County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 2036702.25 | 64.48
10751 | Wisconsin | GREEN LAKE |  | 6 | 2009539 | This is a bridge rehabilitation project in Green Lake County on County Highway A, Grand River Crossing. | Bridge Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 383750.73 | 0.057
10752 | Wisconsin | MARATHON | WAUSAU | 7 | 2009540 | This is a reconstruction project in Marathon County on County Highway NN, Creek Road - Thornapple Road. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/01/2009 | 1730000 | 61.93
10753 | Wisconsin | FOREST |  | 8 | 2009541 | This is a restoration and rehabilitation project in Forest County on County Highway W, County Highway Q - US Highway 8. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 09/01/2009 | 990000 | 43.56
10754 | Wisconsin | MENOMINEE |  | 8 | 2009542 | This is a resurfacing project in Mennominee County on County Highway M, Strawberry Lane. | Pavement Improvement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 3905000 | 35.14
10755 | Wisconsin | CLARK |  | 3 | 2009543 | This is a bridge replacement project in Clark County on a town road, Town of Sherwood Ballard Road, Hay Creek Bridge and approaches. | Bridge Replacement | 05/14/2009 | 05/14/2009 | 10/01/2009 | 207542.32 | 0
10756 | Wisconsin | WASHINGTON | MILWAUKEE | 5 | 2009592 | This is a reconstruction with additional lanes project in Washington County on County Highway Q, County Line Road, Pilgrim Road. | Pavement Widening | 05/18/2009 | 05/18/2009 | 10/01/2009 | 3754459.37 | 10.53
10757 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009594 | This is a bridge rehabilitation project in Milwaukee County on local streets, River Road. | Bridge Improvement | 05/18/2009 | 05/18/2009 | 07/01/2010 | 317315 | 0
10758 | Wisconsin | OUTAGAMIE |  | 8 | 2009609 | This is a bridge replacement project in Outagamie County on a town road, Weyers Road Bridge and approaches. | Bridge Replacement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 677761 | 0
10759 | Wisconsin | GREEN LAKE |  | 6 | 2009610 | This is a resurfacing project in Green Lake County on County Highway A, Markesan - Green Lake. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 09/01/2009 | 1150000 | 15.6
10760 | Wisconsin | MARATHON |  | 7 | 2009611 | This is a bridge replacement project in Marathon County on a town road, Huckleberry Road, Fenwood Creek Crossing. | Bridge Replacement | 05/18/2009 | 05/18/2009 | 11/01/2009 | 228000 | 0.038
10761 | Wisconsin | PORTAGE |  | 7 | 2009612 | This is a resurfacing project in Portage County on County Highway W, Kellner - Bankroft Road. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 2245000 | 153.4
10762 | Wisconsin | WOOD |  | 7 | 2009613 | This is a resurfacing project in Wood County on County Highway A, Pittsville - Marshfield. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 09/01/2009 | 3120000 | 211.14
10763 | Wisconsin | WOOD |  | 7 | 2009614 | This is a reconstruction project in Wood County on a town road, Lincoln Avenue, City of Marshfield. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 06/01/2010 | 1725690 | 1.992
10764 | Wisconsin | LINCOLN |  | 7 | 2009615 | This is a resurfacing project in Lincoln County on County Highway CC, Nick Road to Tannery Road. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 1150000 | 61.27
10765 | Wisconsin | MARATHON |  | 7 | 2009622 | This is a bridge replacement project in Marathon County on a town road, Badger Road Bridge. | Bridge Replacement | 05/18/2009 | 05/18/2009 | 01/01/2010 | 732896 | 0.095
10766 | Wisconsin | CLARK |  | 3 | 2009623 | This is a bridge replacement project in Clark County on County Highway OO, Black River Bridge. | Bridge Replacement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 1476000 | 0
10767 | Wisconsin | ROCK |  | 2 | 2009624 | This is a bridge replacement project in Rock County on County Highway H, Raccoon Creek Bridge. | Pavement Improvement | 05/18/2009 | 05/18/2009 | 10/01/2009 | 488309.99 | 0.19
10768 | Wisconsin | ADAMS |  | 6 | 2009680 | This is a reconstruction project in Adams County on County Highway Z, Town of Strongs Prairie and Monroe. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 01/01/2010 | 5424989 | 89.7
10769 | Wisconsin | MARATHON | WAUSAU | 7 | 2009681 | This is a reconstruction project in Marathon County on local streets, Village of Weston, Ross Avenue. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 12/01/2009 | 2867007 | 61.64
10770 | Wisconsin | MARATHON | WAUSAU | 7 | 2009682 | This is a resurfacing project in Marathon County on local streets, Stewart Avenue - Elm Street. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 10/01/2009 | 445000 | 0.58
10771 | Wisconsin | PORTAGE |  | 7 | 2009683 | This is a resurfacing project in Portage County on County Highway D, Almond. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 11/01/2009 | 1230000 | 92.8
10772 | Wisconsin | FLORENCE |  | 8 | 2009684 | This is a restoration and rehabilitation project in Florence County on County Highway U, Marinette County Line - County Highway N. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 11/01/2009 | 3000000 | 54.9
10773 | Wisconsin | WAUPACA |  | 8 | 2009685 | This is a resurfacing project in Waupaca County on local streets, City of Clintonville, North 12th Street. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 375150 | 5.6
10774 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009686 | This is a reconstruction project in Milwaukee County on local streets, West State Street. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 07/01/2010 | 1638019 | 9.52
10775 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009687 | This is a reconstruction project in Milwaukee County on local streets, West Oklahoma Avenue. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 08/01/2010 | 2200000 | 12.96
10776 | Wisconsin | MONROE |  | 3 | 2009688 | This is a resurfacing project in Monroe County on County Highway O, Warrens. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 990000 | 19.11
10777 | Wisconsin | ROCK | JANESVILLE | 1 | 2009689 | This is a resurfacing project in Rock County on local streets, City of Janesville, various streets. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 1575630 | 127.76
10778 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009690 | This is a reconstruction project in Milwaukee County on local streets, West Lisbon Avenue. | Pavement Improvement | 06/25/2009 | 06/25/2009 | 06/01/2010 | 2793868 | 15.3
10779 | Wisconsin | BARRON |  | 7 | 2009691 | This is a bridge replacement project in Barron County on a town road, Pokegama Creek Bridge. | Bridge Replacement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 295200 | 0
10780 | Wisconsin | FOND DU LAC |  | 6 | 2009692 | This is a bridge replacement project in Fond du Lac County on local streets, Kiel Road Bridge and approaches. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 10/01/2009 | 342000 | 0
10781 | Wisconsin | WAUPACA |  | 8 | 2009693 | This is a bridge replacement project in Waupaca County on County Highway Q, Waupaca River Crossing. | Bridge Replacement | 06/24/2009 | 06/24/2009 | 11/01/2009 | 1357354 | 0.38
10782 | Wisconsin | TAYLOR |  | 7 | 2009694 | This is a bridge rehabilitation project in Taylor County on County Highway A, Pine Creek Bridge. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 12/30/2009 | 159900 | 0
10783 | Wisconsin | MARINETTE |  | 8 | 2009695 | This is a new roadway construction project of 1.15 miles in Marinette County on County Highway T, Roosevelt Road, City of Marinette. | New Construction | 06/25/2009 | 06/25/2009 | 06/01/2010 | 3382500 | 11.5
10784 | Wisconsin | FOREST |  | 8 | 2009696 | This is a pedestrian and bicycle path project in Forest County, Mole Lake Multi-Use Trail. | Transportation Enhancements | 06/24/2009 | 06/24/2009 | 11/01/2009 | 738000 | 0
10785 | Wisconsin | VILAS |  | 8 | 2009697 | This is a bicycle path project in Vilas County, Trout Lake Bicycle Trail. | Transportation Enhancements | 06/24/2009 | 06/24/2009 | 10/01/2009 | 279379 | 0
10786 | Wisconsin | DANE | MADISON | 2 | 2009866 | This is the design engineering effort for a construction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 62040 | 0
10787 | Wisconsin | MILWAUKEE | MILWAUKEE | 1 | 2009867 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 51st Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 5300 | 0
10788 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009868 | This is the design engineering effort for a construction project in Milwaukee County on local streets, West Vliet Street Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 25000 | 0
10789 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009869 | This is the design engineering effort for a construction project in Milwaukee County on local streets, North Sherman Blvd. Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 10600 | 0
10790 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009870 | This is the design engineering effort for a construction project in Milwaukee County on local streets, North Sherman Blvd. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 9100 | 0
10791 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2009871 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 76th Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 12260 | 0
10792 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009872 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 6th Street Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 19025 | 0
10793 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009873 | This is the design engineering effort for a construction project in Waukesha County on County Highway ES, Calhoun Road to County Highway O. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8200 | 0
10794 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009874 | This is the design engineering effort for a construction project in Milwaukee County on local streets, West National Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4800 | 0
10795 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2009875 | This is the design engineering effort for a construction project in Milwaukee County on local streets, Hampton Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 80000 | 0
10796 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009876 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South Cesar Chavez Drive. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 75000 | 0
10797 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009877 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 6th Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4580 | 0
10798 | Wisconsin | MILWAUKEE | MILWAUKEE | 5 | 2009878 | This is the design engineering effort for a construction project in Milwaukee County on local streets, 70th Street Brige. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 15800 | 0
10799 | Wisconsin | OZAUKEE | MILWAUKEE | 5 | 2009879 | This is the design engineering effort for a construction project in Ozaukee County on County Highway O, North Green Bay Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 15600 | 0
10800 | Wisconsin | OZAUKEE | MILWAUKEE | 5 | 2009880 | This is the design engineering effort for a construction project in Ozaukee County on local streets, West Donges Bay Road. | Other | 07/30/2009 | 07/30/2009 | 12/15/2009 | 5000 | 0
10801 | Wisconsin | RACINE | RACINE | 1 | 2009881 | This is the design engineering effort for a construction project in Racine County on local streets, North Main Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 31000 | 0
10802 | Wisconsin | RACINE | RACINE | 1 | 2009882 | This is the design engineering effort for a construction project in Racine County on County Highway C, Spring Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 6122 | 0
10803 | Wisconsin | KENOSHA | KENOSHA | 1 | 2009883 | This is the design engineering effort for a construction project in Kenosha County on local streets, 38th Street Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 16180 | 0
10804 | Wisconsin | RACINE | RACINE | 1 | 2009884 | This is the design engineering effort for a construction project in Racine County on local streets, Lathrop Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 7073 | 0
10805 | Wisconsin | RACINE | RACINE | 1 | 2009885 | This is the design engineering effort for a construction project in Racine County on local streets, Taylor Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 3122 | 0
10806 | Wisconsin | WASHINGTON |  | 5 | 2009886 | This is the design engineering effort for a construction project in Washington County on local streets, Decorah Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 12284 | 0
10807 | Wisconsin | WASHINGTON |  | 5 | 2009887 | This is the design engineering effort for a construction project in Washington County on local streets, 7th Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 1956 | 0
10808 | Wisconsin | WASHINGTON |  | 5 | 2009888 | This is the design engineering effort for a construction project in Washington County on local streets, Indiana Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8316 | 0
10809 | Wisconsin | WASHINGTON |  | 5 | 2009889 | This is the design engineering effort for a construction project in Washington County on local streets, Vine Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 1976 | 0
10810 | Wisconsin | WASHINGTON |  | 5 | 2009890 | This is the design engineering effort for a construction project in Washington County on local streets, Park Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 1730 | 0
10811 | Wisconsin | WASHINGTON |  | 5 | 2009891 | This is the design engineering effort for a construction project in Washington County on local streets, Jefferson Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4096 | 0
10812 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009892 | This is the design engineering effort for a construction project in Waukesha County on local streets, Wisconsin Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 18300 | 0
10813 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009893 | This is the design engineering effort for a construction project in Waukesha County on County Highway O, South Moorland Blvd. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 23250 | 0
10814 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009894 | This is the design engineering effort for a construction project in Waukesha County on County Highway K, North 132nd Street to North 124th Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 17393 | 0
10815 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009895 | This is the design engineering effort for a construction project in Waukesha County on County Highway T, Grandview Blvd.. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4400 | 0
10816 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009896 | This is the design engineering effort for a construction project in Waukesha County on County Highway V, Townline Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 16050 | 0
10817 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009897 | This is the design engineering effort for a construction project in Waukesha County on County Highway Y, Baker Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 20000 | 0
10818 | Wisconsin | MILWAUKEE | MILWAUKEE | 1 | 2009898 | This is the design engineering effort for a construction project in Milwaukee County on County Highway ZZ, West Loomis Road to South 51st Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 18150 | 0
10819 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2009899 | This is the design engineering effort for a construction project in Milwaukee County on local streets, Eastbrook Park Drive. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 16200 | 0
10820 | Wisconsin | WALWORTH |  | 1 | 2009900 | This is the design engineering effort for a construction project in Walworth County on local streets, Wrigley Drive. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 12000 | 0
10821 | Wisconsin | WALWORTH |  | 1 | 2009901 | This is the design engineering effort for a construction project in Walworth County on local streets, Mohawk Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 3560 | 0
10822 | Wisconsin | GRANT |  | 3 | 2009902 | This is the design engineering effort for a construction project in Grant County on County Highway D, City of Platteville, Chestnut Street. | Other | 07/30/2009 | 07/30/2009 | 12/15/2009 | 40500 | 0
10823 | Wisconsin | SHAWANO |  | 8 | 2009903 | This is the design engineering effort for a construction project in Shawano County on County Highway D, North Branch Embarrass River Crossing. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 9900 | 0
10824 | Wisconsin | TREMPEALEAU |  | 3 | 2009904 | This is the design engineering effort for a construction project in Trempealeau County, Whitehall Historic Railroad Depot. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 7820 | 0
10825 | Wisconsin | PIERCE |  | 3 | 2009905 | This is the design engineering effort for a construction project in Pierce County on County Highway P, May Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 6959.42 | 0
10826 | Wisconsin | POLK |  | 7 | 2009906 | This is the design engineering effort for a construction project in Polk County, Amery to Dresser Trail. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 13300 | 0
10827 | Wisconsin | WASHBURN |  | 7 | 2009907 | This is the design engineering effort for a construction project in Washburn County, Spooner Bicycle and Pedestrian Facility. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 6260 | 0
10828 | Wisconsin | BAYFIELD |  | 7 | 2009908 | This is the design engineering effort for a construction project in Bayfield County on State Highway 13, Red Cliff streetscape improvement. | Other | 07/30/2009 | 07/30/2009 | 01/05/2010 | 15300 | 0
10829 | Wisconsin | WASHBURN |  | 7 | 2009909 | This is the design engineering effort for a construction project in Washburn County on County Highway E, Namekagon River Bridge. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4000 | 0
10830 | Wisconsin | CHIPPEWA | EAU CLAIRE | 7 | 2009910 | This is the design engineering effort for a construction project in Chippewa County on local streets, First Avenue. | Other | 08/26/2009 | 08/26/2009 | 12/15/2009 | 8800 | 0
10831 | Wisconsin | CHIPPEWA | EAU CLAIRE | 7 | 2009911 | This is the design engineering effort for a construction project in Chippewa County on County Highway X, 57th Avenue West to 184th Street. | Other | 08/26/2009 | 08/26/2009 | 12/01/2009 | 7400 | 0
10832 | Wisconsin | DOUGLAS | DULUTH-SUPERIOR (MN) | 7 | 2009912 | This is the design engineering effort for a construction project in Douglas County on local streets, East 5th Street, 6th Avenue East to 20th Avenue East. | Other | 08/26/2009 | 08/26/2009 | 12/15/2009 | 7500 | 0
10833 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009914 | This is the design engineering effort for a construction project in Milwaukee County on County Highway S, North 84th Street to North 56th Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 211427 | 0
10834 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009915 | This is the design engineering effort for a construction project in Milwaukee County, South Cesar Chavez Drive, West National Avenue to Greenfield Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8000 | 0
10835 | Wisconsin | RACINE | RACINE | 1 | 2009916 | This is the design engineering effort for a construction project in Racine County, North Shore Multi-Use Path. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8880 | 0
10836 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2009917 | This is the design engineering effort for a construction project in Waukesha County, Lake Country Trail. | Other | 07/30/2009 | 07/30/2009 | 12/15/2009 | 17511 | 0
10837 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2009918 | This is the design engineering effort for a construction project in Milwaukee County on , Kinnickinnic River Bike Trail. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 7000 | 0
10838 | Wisconsin | KENOSHA | KENOSHA | 1 | 2009919 | This is the design engineering effort for a construction project in Kenosha County on local streets, 30th Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 16290 | 0
10839 | Wisconsin | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 1 | 2009920 | This is the design engineering effort for a construction project in Kenosha County on County Highway Z, Main Street East. | Other | 07/30/2009 | 07/30/2009 | 12/22/2009 | 9520 | 0
10840 | Wisconsin | KENOSHA |  | 1 | 2009921 | This is the design engineering effort for a construction project in Kenosha County on local streets, Cooper Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 5000 | 0
10841 | Wisconsin | RACINE |  | 1 | 2009922 | This is the design engineering effort for a construction project in Racine County on local streets, Kane Street. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 7120 | 0
10842 | Wisconsin | KEWAUNEE |  | 8 | 2009924 | This is the design engineering effort for a construction project in Kewaunee County on County Highway A, Town of Luxemburg. | Other | 07/30/2009 | 07/30/2009 | 12/15/2009 | 8325 | 0
10843 | Wisconsin | BROWN | GREEN BAY | 8 | 2009925 | This is the design engineering effort for a construction project in Brown County on County Highway I, Town of Scott. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 6706 | 0
10844 | Wisconsin | BROWN | GREEN BAY | 8 | 2009926 | This is the design engineering effort for a construction project in Brown County on local streets, City of DePere, Jordan Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 3560 | 0
10845 | Wisconsin | BROWN | GREEN BAY | 8 | 2009927 | This is the design engineering effort for a construction project in Brown County, Fox River Recreation Trail. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 4140 | 0
10846 | Wisconsin | BROWN | GREEN BAY | 8 | 2009928 | This is the design engineering effort for a construction project in Brown County on local streets, City of Green Bay, Manitowoc Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 13178 | 0
10847 | Wisconsin | BROWN | GREEN BAY | 8 | 2009929 | This is the design engineering effort for a construction project in Brown County, Verlin Road Bike and Pedestrian Facilities. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 7447 | 0
10848 | Wisconsin | JUNEAU |  | 3 | 2009930 | This is the design engineering effort for a construction project in Juneau County on County Highway A, New Lisbon, Krypton Road. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 10500 | 0
10849 | Wisconsin | ROCK | JANESVILLE | 1 | 2009931 | This is the design engineering effort for a construction project in Rock County, Rotamer Road Bike Trail Connector. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8700 | 0
10850 | Wisconsin | LA CROSSE | LA CROSSE (MN) | 3 | 2009932 | This is the design engineering effort for a construction project in La Crosse County on State Highway 35, Mormon Coulee Road Bike Path improvement. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 8620 | 0
10851 | Wisconsin | WINNEBAGO |  | 6 | 2009933 | This is the design engineering effort for a construction project in Winnebago County on County Highway D, Town of Winneconnie and Town of Poygan. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 23550 | 0
10852 | Wisconsin | PORTAGE |  | 7 | 2009934 | This is the design engineering effort for a construction project in Portage County on local streets, City of Stevens Point, Minnesota Avenue. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 53000 | 0
10853 | Wisconsin | BROWN | GREEN BAY | 8 | 2009935 | This is the design engineering effort for a construction project in Brown County on County Highway EB, Village of Howard. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 11120 | 0
10854 | Wisconsin | FOREST |  | 8 | 2009941 | This is the design engineering effort for a construction project in Forest County, the rebuild and rehabilitation of Laona Northern Railroad Track. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 10240 | 0
10855 | Wisconsin | OUTAGAMIE | APPLETON | 6 8 | 2009942 | This is the design engineering effort for a construction project in Outagamie County, Fox River Navigation, Lock Keeper Houses. | Other | 07/30/2009 | 07/30/2009 | 12/01/2009 | 15391 | 0
10856 | Wisconsin | DOUGLAS |  | 7 | 2009947 | This is the design engineering effort for a construction project in Douglas County on County Highway C, State Highway 35 to Kronberg Road. | Other | 10/20/2009 | 10/20/2009 | 12/01/2009 | 20000 | 0
10857 | Wisconsin | JEFFERSON |  | 5 6 | 2009953 | This is the design engineering effort for a construction project in Jefferson County on County Highway F, Sullivan, I-94. | Other | 08/04/2009 | 08/04/2009 | 12/01/2009 | 18900 | 0
10858 | Wisconsin | GRANT |  | 3 | 2009954 | This is the design engineering effort for a construction project in Grant County on local streets, Village of Bloomington, Mill Street. | Other | 08/04/2009 | 08/04/2009 | 12/15/2009 | 12120 | 0
10859 | Wisconsin | IOWA |  | 3 | 2009955 | This is the design engineering effort for a construction project in Iowa County on County Highway X, Village of Linden, Babcock Avenue. | Other | 08/04/2009 | 08/04/2009 | 12/15/2009 | 3860 | 0
10860 | Wisconsin | ROCK |  | 2 | 2009956 | This is the design engineering effort for a construction project in Rock County on County Highway C, North 4th Street and West Main Street. | Other | 08/04/2009 | 08/04/2009 | 12/01/2009 | 9600 | 0
10861 | Wisconsin | DANE | MADISON | 2 | 2009957 | This is the design engineering effort for a construction project in Dane County on local streets, City of Verona, North Nine Mound Road. | Other | 08/06/2009 | 08/06/2009 | 12/01/2009 | 15200 | 0
10862 | Wisconsin | ROCK | BELOIT (IL) | 2 | 2009958 | This is the design engineering effort for a construction project in Rock County on Town Road, Town of Beloit, Inman Parkway. | Other | 10/20/2009 | 10/20/2009 | 03/31/2010 | 1122.07 | 0
10863 | Wisconsin | DANE | MADISON | 2 | 2009959 | This is the design engineering effort for a construction project in Dane County on County Highway Q, City of Middleton, Allen Blvd.. | Other | 08/06/2009 | 08/06/2009 | 12/01/2009 | 7860 | 0
10864 | Wisconsin | DANE | MADISON | 2 | 2009960 | This is the design engineering effort for a construction project in Dane County on County Highway MS, City of Madison, University Avenue. | Other | 08/06/2009 | 08/06/2009 | 12/01/2009 | 41400 | 0
10865 | Wisconsin | DANE |  | 2 | 2009965 | This is the design engineering effort for a construction project in Dane County on County Highway K, US Highway 12 and County Highway M. | Other | 08/13/2009 | 08/13/2009 | 12/01/2009 | 9600 | 0
10866 | Wisconsin | SHEBOYGAN | SHEBOYGAN | 6 | 2010051 | This is the design engineering effort for a construction project in Sheboygan County on local streets, Taylor Drive, Superior Avenue, and Saemann Avenue. | Other | 09/29/2009 | 09/29/2009 | 12/01/2009 | 13266 | 0
10867 | Wisconsin | BARRON |  | 7 | 2010059 | This is a reconstruction project in Barron County on US Highway 53, New Auburn - Spooner. | Pavement Improvement | 12/16/2009 | 12/16/2009 | 11/01/2010 | 9710598.99 | 74.28
10868 | Wisconsin | BARRON |  | 7 | 2010060 | This is a reconstruction project in Barron County on US Highway 53, New Aubrurn - Spooner. | Pavement Improvement | 12/16/2009 | 12/16/2009 | 11/01/2010 | 8561385.4 | 74.28
10869 | Wisconsin | CRAWFORD |  | 3 | 2010061 | This is a bridge rehabilitation project in Crawford County on US Highway 61, Boscobel - Readstownn, Wisconsin River Structure. | Bridge Improvement | 05/13/2010 | 05/13/2010 |  | 331552 | 0.22
10870 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010062 | This is a bridge rehabilitation project in Milwaukee County on local streets, West Vliet Street Bridge. | Bridge Improvement | 12/04/2009 | 12/04/2009 | 09/01/2010 | 145843.22 | 0
10871 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010063 | This is a bridge rehabilitation project in Milwaukee County on local streets, North Sherman Blvd. Bridge. | Bridge Improvement | 12/04/2009 | 12/04/2009 | 09/01/2010 | 582424.83 | 0
10872 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010064 | This is a resurfacing project in Milwaukee County on local streets, North Sherman Blvd. | Pavement Improvement | 12/04/2009 | 12/04/2009 | 09/01/2010 | 417555.48 | 0
10873 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2010065 | This is a resurfacing project in Milwaukee County on local streets, South 76th Street. | Pavement Improvement | 12/04/2009 | 12/04/2009 | 07/01/2010 | 753990 | 0
10874 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010066 | This is a resurfacing project in Milwaukee County on local streets, West National Avenue. | Pavement Improvement | 12/02/2009 | 12/02/2009 | 07/01/2010 | 295200 | 0
10875 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010067 | This is a resurfacing project in Milwaukee County on local streets, South Cesar Chavez Drive. | Pavement Improvement | 12/04/2009 | 12/04/2009 | 07/01/2010 | 707250 | 0
10876 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010068 | This is a landscaping and other scenic beautification project in Milwaukee County, South Cesar Chavez Drive. | Transportation Enhancements | 12/04/2009 | 12/04/2009 | 07/01/2010 | 492000 | 0
10877 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010069 | This is a resurfacing project in Milwaukee County on local streets, South 68th Street. | Pavement Improvement | 12/04/2009 | 12/04/2009 | 07/01/2010 | 281670 | 0
10878 | Wisconsin | RACINE | RACINE | 1 | 2010070 | This is a pedestrian and bicycle path project in Racine County, North Shore Multi-use Path. | Transportation Enhancements | 12/04/2009 | 12/04/2009 | 06/01/2010 | 436120 | 0
10879 | Wisconsin | RACINE | RACINE | 1 | 2010071 | This is a resurfacing project in Racine County on local streets, Lathrop Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 435001 | 1.57
10880 | Wisconsin | RACINE | RACINE | 1 | 2010072 | This is a resurfacing project in Racine County on local streets, Taylor Avenue. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 192001 | 0.24
10881 | Wisconsin | RACINE |  | 1 | 2010073 | This is a restoration and rehabilitation project in Racine County on County Highway G, Union Church Drive. | Pavement Improvement | 12/04/2009 | 12/04/2009 | 06/01/2010 | 1438350 | 0
10882 | Wisconsin | RACINE |  | 1 | 2010074 | This is a restoration and rehabilitation project in Racine County on County Highway K, East Wink Lake Rd - Overson Road. | Pavement Improvement | 12/04/2009 | 12/04/2009 | 06/01/2010 | 962780 | 0
10883 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010075 | This is a bridge rehabilitation project in Milwaukee County on local streets, Jackson Park Drive. | Bridge Improvement | 12/04/2009 | 12/04/2009 | 07/01/2010 | 505000 | 0
10884 | Wisconsin | MANITOWOC |  | 6 | 2010076 | This is a bridge replacement project in Manitowoc County on local streets, Pioneer Road. | Bridge Replacement | 12/07/2009 | 12/07/2009 | 04/01/2010 | 341663 | 0
10885 | Wisconsin | WINNEBAGO | APPLETON | 6 | 2010077 | This is a bridge replacement project in Winnebago County on local streets, City of Neenah, Adams Street. | Bridge Replacement | 12/10/2009 | 12/10/2009 | 04/01/2010 | 504300 | 0
10886 | Wisconsin | CRAWFORD |  | 3 | 2010078 | This is a bridge rehabilitation project in Crawford County on State Highway 60, Bridgeport - Blue River. | Bridge Improvement | 05/13/2010 | 05/13/2010 |  | 325000 | 0.01
10887 | Wisconsin | MONROE |  | 3 | 2010079 | This is a bridge replacement project in Monroe County on County Highway M, County Higway A - State Highway 16. | Other | 12/04/2009 | 12/04/2009 | 09/01/2010 | 383760 | 0.1
10888 | Wisconsin | MONROE |  | 3 | 2010080 | This is a bridge replacement project in Monroe County on County Highway M, County Higway A - State Highway 16. | Other | 12/04/2009 | 12/04/2009 | 09/01/2010 | 471090 | 0.1
10889 | Wisconsin | VERNON |  | 3 | 2010081 | This is a bridge replacement project in Vernon County on County Highway UU, Victory Creek Bridge and approaches. | Bridge Replacement | 12/04/2009 | 12/04/2009 | 09/01/2010 | 348090 | 0.06
10890 | Wisconsin | CRAWFORD |  | 3 | 2010082 | This is a bridge replacement project in Crawford County on a town road, Town of Freeman, Buck Creek Bridge. | Bridge Replacement | 12/04/2009 | 12/04/2009 | 07/01/2010 | 258300 | 0.06
10891 | Wisconsin | DANE |  | 2 | 2010083 | This is a reconstruction project in Dane County on County Highway K, US Highway 12 - County Highway M. | Pavement Improvement | 12/04/2009 | 12/04/2009 | 08/01/2010 | 590400 | 11.9
10892 | Wisconsin | WAUSHARA |  | 6,8 | 2010084 | This is a resurfacing project in Waushara County on State Highway 49, Poysippi - Fremont. | Pavement Improvement | 05/13/2010 | 05/13/2010 | 10/01/2010 | 1883107.34 | 115.92
10893 | Wisconsin | OUTAGAMIE |  | 8 | 2010085 | This is a bridge replacement project in Outagamie County on a town road, Greiner Road Bridge and approaches. | Other | 12/10/2009 | 12/10/2009 | 10/01/2009 | 248200 | 0.025
10894 | Wisconsin | OUTAGAMIE |  | 8 | 2010086 | This is a bridge replacement project in Outagamie County on a town road, Central Valley Road Bridge and approaches. | Bridge Replacement | 12/07/2009 | 12/07/2009 | 07/01/2010 | 305900 | 0.04
10895 | Wisconsin | WAUSHARA |  | 6 | 2010087 | This is a reconstruction project in Waushara County on County Highway I, Alder Creek Crossing. | New Bridge Construction | 12/16/2009 | 12/16/2009 | 07/01/2010 | 175000 | 0
10896 | Wisconsin | PORTAGE |  | 7 | 2010088 | This is a resurfacing project in Portage County on local streets, City of Stevens Point, Minnesota Avenue. | Pavement Improvement | 12/16/2009 | 12/16/2009 | 09/01/2010 | 430500 | 3.2
10897 | Wisconsin | BAYFIELD |  | 7 | 2010089 | This is a bridge rehabilitation project in Bayfield County on County Highway D, Namekagon River Bridge. | Bridge Improvement | 12/16/2009 | 12/16/2009 | 07/01/2010 | 246000 | 0
10898 | Wisconsin | MENOMINEE |  | 8 | 2010090 | This is a resurfacing project in Menominee County on State Highway 55, Shawano - Langlade. | Pavement Improvement | 05/13/2010 | 05/13/2010 | 12/01/2010 | 2600000 | 129.92
10899 | Wisconsin | FOREST |  | 8 | 2010091 | This is an historic preservation project in Forest County, to rebuild and rehabilitate the Laona Northern Railroad Track. | Transportation Enhancements | 12/16/2009 | 12/16/2009 | 06/01/2010 | 629760 | 0
10900 | Wisconsin | PRICE |  | 7 | 2010092 | This is a bridge replacement project in Price County on a town road, Sailor Creek Bridge and approaches. | Bridge Replacement | 12/16/2009 | 12/16/2009 | 09/01/2010 | 420660 | 0.01
10901 | Wisconsin | JEFFERSON |  | 5 6 | 2010093 | This is a reconstruction project in Jefferson County on County Highway F, Sullivan - Interstate 94. | Pavement Improvement | 12/04/2009 | 12/04/2009 | 06/01/2010 | 1549800 | 15.6
10902 | Wisconsin | GRANT |  | 3 | 2010171 | This is a bridge rehabilitation project in Grant County on US Highway 18, Prairie du Chien - Fennimore, Wisconsin River Bridge. | Bridge Improvement | 06/28/2010 | 05/13/2010 |  | 678278.39 | 0.13
10903 | Wisconsin | ROCK | BELOIT (IL) | 1 | 2010172 | This is a reconstruction project in Rock County on a town road, Town of Turtle. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 08/01/2010 | 196800 | 6
10904 | Wisconsin | DODGE |  | 6 | 2010173 | This is a reconstruction project in Dodge County on County Highway DJ, Village of Juneau, East Oak Grove Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 07/01/2010 | 372690 | 0
10905 | Wisconsin | RICHLAND |  | 3 | 2010174 | This is a reconstruction project in Richland County on County Highway C, Vernon County Line, Rolt Lane. | Pavement Improvement | 01/12/2010 | 01/12/2010 | 09/01/2010 | 1482150 | 0
10906 | Wisconsin | RICHLAND |  | 3 | 2010175 | This is a reconstruction project in Richland County on County Highway D, Rockbrook Bridge. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 1166040 | 0
10907 | Wisconsin | JUNEAU |  | 3 | 2010176 | This is a reconstruction project in Juneau County on County Highway A, Monroe County Line - New Lisbon. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 08/01/2010 | 3062700 | 52
10908 | Wisconsin | ROCK |  | 2 | 2010177 | This is a reconstruction project in Rock County on County Highway C, North 4th Street and West Main Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 07/01/2010 | 590400 | 4
10909 | Wisconsin | ROCK | BELOIT (IL) | 2 | 2010178 | This is a reconstruction project in Rock County on a town road, Town of Beloit, Inman Parkway. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 08/01/2010 | 670350 | 16.8
10910 | Wisconsin | ROCK | BELOIT (IL) | 2 | 2010179 | This is a reconstruction project in Rock County on local streets, Town of Beloit, Cranston Road. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 08/01/2010 | 129150 | 0
10911 | Wisconsin | LA CROSSE | LA CROSSE (MN) | 3 | 2010180 | This is a bicycle path project in La Crosse County on State Highway 35, Mormon Coulee Road Bike Path Improvement. | Transportation Enhancements | 12/31/2009 | 12/31/2009 | 09/01/2010 | 530130 | 2.8
10912 | Wisconsin | DANE | MADISON | 2 | 2010181 | This is a reconstruction project in Dane County on County Highway MS, City of Madison, University Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 06/01/2010 | 3394800 | 7.2
10913 | Wisconsin | DODGE |  | 6 | 2010182 | This is a reconstruction project in Dodge County on various highways, Madison Street and University Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 956940 | 0
10914 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010183 | This is a roundabut project in Milwaukee County on local streets, West Winnebago Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 1164213 | 0
10915 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010184 | This is a reconstruction project in Milwaukee County on local streets, East and West Keefe Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 11/01/2010 | 3210617.01 | 0
10916 | Wisconsin | MILWAUKEE | MILWAUKEE | 1 | 2010185 | This is a resurfacing project in Milwaukee County on local streets, West Grange Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 688800 | 0
10917 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010186 | This is a reconstruction project in Milwaukee County on local streets, East and West North Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 2413949 | 0
10918 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2010187 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Hampton Avenue. | Pavement Improvement | 01/12/2010 | 01/12/2010 | 11/01/2010 | 773241 | 0
10919 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010188 | This is a restoration and rehabilitation project in Milwaukee County on local streets, 15th Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 799500 | 0
10920 | Wisconsin | OZAUKEE | MILWAUKEE | 5 | 2010189 | This is a restoration and rehabilitation project in Ozaukee County on County Highway O, North Green Bay Road. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 959400 | 0
10921 | Wisconsin | KENOSHA | KENOSHA | 1 | 2010190 | This is a bridge rehabilitation project in Kenosha County on local streets, 38th Street Bridge. | Bridge Replacement | 01/13/2010 | 01/13/2010 | 12/01/2010 | 995000 | 0
10922 | Wisconsin | WASHINGTON |  | 5 | 2010191 | This is a resurfacing project in Washington County on local streets, Decorah Road. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 10/01/2010 | 455466 | 0
10923 | Wisconsin | WASHINGTON |  | 5 | 2010192 | This is a resurfacing project in Washington County on local streets, 7th Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 10/01/2010 | 120294 | 0
10924 | Wisconsin | WASHINGTON |  | 5 | 2010193 | This is a resurfacing project in Washington County on local streets, Indiana Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 10/01/2010 | 311434 | 0
10925 | Wisconsin | WASHINGTON |  | 5 | 2010194 | This is a resurfacing project in Washington County on local streets, Vine Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 10/01/2010 | 121524 | 0
10926 | Wisconsin | WASHINGTON |  | 5 | 2010195 | This is a resurfacing project in Washington County on local streets, Park Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 10/01/2010 | 106395 | 0
10927 | Wisconsin | WASHINGTON |  | 5 | 2010196 | This is a resurfacing project in Washington County on local streets, Jefferson Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 10/01/2010 | 251904 | 0
10928 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 5 | 2010197 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Eastbrook Park Drive. | Pavement Widening | 01/12/2010 | 01/12/2010 | 11/01/2010 | 835580 | 0
10929 | Wisconsin | KENOSHA | KENOSHA | 1 | 2010198 | This is a resurfacing project in Kenosha County on local streets, 30th Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 1035780 | 0
10930 | Wisconsin | KENOSHA |  | 1 | 2010199 | This is a pedestrian access and safety project in Kenosha County. | Transportation Enhancements | 01/13/2010 | 01/13/2010 |  | 215182 | 0
10931 | Wisconsin | KENOSHA |  | 1 | 2010200 | This is a resurfacing project in Kenosha County on local streets, Cooper Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 307500 | 0
10932 | Wisconsin | KENOSHA | KENOSHA | 1 | 2010201 | This is a resurfacing project in Kenosha County on local streets, 80th Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 553500 | 0
10933 | Wisconsin | RACINE |  | 1 | 2010202 | This is a resurfacing project in Racine County on local streets, Kane Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 437880 | 0
10934 | Wisconsin | RACINE |  | 1 | 2010203 | This is a restoration and rehabilitation project in Racine County on various highways, Market Street, Pine Street - Dodge Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 433575 | 0
10935 | Wisconsin | RACINE |  | 1 | 2010204 | This is a resurfacing project in Racine County on various highways, Grove Street, Oak Street - Briody Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 551110 | 0
10936 | Wisconsin | OUTAGAMIE | APPLETON | 6 8 | 2010205 | This is an historic preservation project in Outagamie County, the rehabilitation of the Fox River Navigation System Lock Keeper houses. | Transportation Enhancements | 01/13/2010 | 01/13/2010 | 10/01/2010 | 946576 | 0
10937 | Wisconsin | OUTAGAMIE | APPLETON | 8 | 2010206 | This is a reconstruction project in Outagamie County on local streets, Village of Little Chute, Washington Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 |  | 360390 | 0.3
10938 | Wisconsin | BROWN | GREEN BAY | 8 | 2010207 | This is a pedestrian and bicycle path project in Brown County, Fox River Recreation Trail. | Transportation Enhancements | 01/13/2010 | 01/13/2010 | 07/01/2010 | 254610 | 0
10939 | Wisconsin | BROWN | GREEN BAY | 8 | 2010208 | This is a pedestrian and bicycle path project in Brown County, Verlin Road Bike Pedestrian Facilities. | Transportation Enhancements | 01/13/2010 | 01/13/2010 | 10/01/2010 | 457978 | 0
10940 | Wisconsin | WINNEBAGO | APPLETON | 6 | 2010209 | This is a restoration and rehabilitation project in Winnebago County on local streets, City of Mehasha, Tayco Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 473550 | 9.8
10941 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 2010210 | This is a resurfacing project in Winnebago County on local streets, City of Oshkosh, Snell Road. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 717090 | 16
10942 | Wisconsin | WINNEBAGO | APPLETON | 6 | 2010211 | This is a restoration and rehabilitation project in Winnebago County on local streets, City of Neenah, Wisconsin Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 07/01/2010 | 492000 | 0.42
10943 | Wisconsin | SHEBOYGAN | SHEBOYGAN | 6 | 2010212 | This is a reconstruction project in Sheboygan County on local streets, Taylor Drive, Superior Avenue, and Saemann Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 09/01/2010 | 815870 | 6.84
10944 | Wisconsin | OCONTO |  | 8 | 2010213 | This is a bridge rehabilitation project in Oconto County on County Highway S, Pensaukee River Bridge. | Bridge Improvement | 01/13/2010 | 01/13/2010 |  | 430500 | 0
10945 | Wisconsin | OCONTO |  | 8 | 2010214 | This is a bridge rehabilitation project in Oconto County on County Highway S, Pensaukee River Bridge. | Bridge Improvement | 01/13/2010 | 01/13/2010 |  | 344400 | 0
10946 | Wisconsin | MARINETTE |  | 8 | 2010215 | This is a reconstruction project in Marinette County on local streets, Cleveland Avenue. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 08/01/2010 | 638370 | 0
10947 | Wisconsin | MARINETTE |  | 8 | 2010216 | This is a reconstruction project in Marinette County on local streets, Hattie Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 08/01/2010 | 129150 | 0
10948 | Wisconsin | MARINETTE |  | 8 | 2010217 | This is a reconstruction project in Marinette County on local streets, Hosmer Street. | Pavement Improvement | 01/13/2010 | 01/13/2010 | 08/01/2010 | 116850 | 0
10949 | Wisconsin | MARINETTE |  | 8 | 2010218 | This is a reconstruction project in Marinette County on local streets, Marinette Mid City Bike and Pedestrian Path. | Transportation Enhancements | 01/13/2010 | 01/13/2010 | 06/01/2010 | 125826 | 0
10950 | Wisconsin | IRON |  | 7 | 2010219 | This is a new roadway construction project of 3.96 miles in Iron County on US Highway 51, County Highway C - Hurley. | Pavement Improvement | 05/13/2010 | 05/13/2010 |  | 1500000 | 19.8
10951 | Wisconsin | DUNN |  | 3 | 2010220 | This is a reconstruction project in Dunn County on County Highway P, Spring Valley - Menomonie. | Pavement Improvement | 01/14/2010 | 01/14/2010 | 06/01/2010 | 1184490 | 0
10952 | Wisconsin | PIERCE |  | 3 | 2010221 | This is a reconstruction project in Pierce County on County Highway P, May Avenue. | Pavement Improvement | 01/14/2010 | 01/14/2010 | 09/01/2010 | 693040.58 | 0
10953 | Wisconsin | DUNN |  | 3 | 2010222 | This is a resurfacing project in Dunn County on local streets, City of Menomonie, 3M Drive and 9th Street. | Pavement Improvement | 01/14/2010 | 01/14/2010 | 09/01/2010 | 1629750 | 0
10954 | Wisconsin | SAWYER |  | 7 | 2010223 | This is a resurfacing project in Sawyer County on State Highway 27, Ojibwa - Stone Lake. | Pavement Improvement | 03/11/2010 | 03/11/2010 |  | 954042.66 | 37.35
10955 | Wisconsin | SAWYER |  | 7 | 2010224 | This is a resurfacing project in Sawyer County on State Highway 27, Ojibwa - Stone Lake. | Pavement Improvement | 03/11/2010 | 03/11/2010 |  | 1411182.26 | 121.92
10956 | Wisconsin | DOUGLAS |  | 7 | 2010225 | This is a bridge replacement project in Douglas County on a town road, Town of Wascott, Cheever Road, Ounce River Bridge. | Bridge Replacement | 01/14/2010 | 01/14/2010 | 07/01/2010 | 238620 | 0
10957 | Wisconsin | DOUGLAS |  | 7 | 2010226 | This is a bridge replacement project in Douglas County on a town road, Town of Wascott, East Coppermine Road, Ounce River Bridge. | Bridge Replacement | 01/14/2010 | 01/14/2010 | 07/01/2010 | 252150 | 0
10958 | Wisconsin | RUSK |  | 7 | 2010227 | This is a restoration and rehabilitation project in Rusk County on County Highway F, Bear Lake, Potato Lake Road. | Pavement Improvement | 01/14/2010 | 01/14/2010 | 07/01/2010 | 541200 | 0
10959 | Wisconsin | WASHBURN |  | 7 | 2010228 | This is a bridge rehabilitation project in Washburn County on County Highway E, Namekagon River Bridge. | Bridge Improvement | 01/14/2010 | 01/14/2010 | 05/01/2010 | 246000 | 0
10960 | Wisconsin | CHIPPEWA | EAU CLAIRE | 7 | 2010229 | This is a restoration and rehabilitation project in Chippewa County on local streets, City of Chippewa Falls Bridge Street. | Pavement Improvement | 01/14/2010 | 01/14/2010 | 06/01/2010 | 221400 | 0
10961 | Wisconsin | DOUGLAS | DULUTH-SUPERIOR (MN) | 7 | 2010230 | This is a resurfacing project in Douglas County on local streets, City of Superior, Hill Avenue and Broadway Street. | Pavement Improvement | 01/14/2010 | 01/14/2010 | 08/01/2010 | 528900 | 0
10962 | Wisconsin | RICHLAND |  | 3 | 2010269 | This is a bridge replacement project in Richland County on town road, Cortland Lane, Town of Akan. | Bridge Replacement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 302580 | 0.55
10963 | Wisconsin | CRAWFORD |  | 3 | 2010270 | This is a reconstruction project in Crawford County on County Highway B, County Highway B, State Highway 35 - State Highway 27 Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 10/01/2010 | 3874500 | 2
10964 | Wisconsin | GRANT |  | 3 | 2010271 | This is a reconstruction project in Grant County on local streets, Village of Bloomington Mill Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 745380 | 0.28
10965 | Wisconsin | ROCK | JANESVILLE | 2 | 2010272 | This is a reconstruction project in Rock County on a town road, West Happy Hollow Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 544890 | 2.489
10966 | Wisconsin | DANE | MADISON | 2 | 2010273 | This is a reconstruction project in Dane County on local streets, City of Verona, North Nine Mound Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 934800 | 0.44
10967 | Wisconsin | ROCK | JANESVILLE | 1 | 2010274 | This is a bicycle path project in Rock County, Rotamer Road Bike Trail connector. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 10/01/2010 | 445000 | 0.975
10968 | Wisconsin | ROCK | JANESVILLE | 1 | 2010276 | This is a reconstruction project in Rock County on local streets, Ruger Avenue Bridge and approaches, City of Janesville. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 10/01/2010 | 619920 | 0.04
10969 | Wisconsin | ROCK | JANESVILLE | 1 | 2010277 | This is a reconstruction project in Rock County on local streets, City of Janesville Tyler - South Randall. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 415740 | 0.48
10970 | Wisconsin | ROCK | JANESVILLE | 1 | 2010278 | This is a reconstruction project in Rock County on local streets, City of Milton, East High Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 584250 | 1.19
10971 | Wisconsin | GRANT |  | 3 | 2010279 | This is a bridge replacement project in Grant County on County Highway D, City of Platteville, Chestnut Street, Rountree Branch Bridge. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 11/01/2010 | 3321000 | 0.09
10972 | Wisconsin | MILWAUKEE | MILWAUKEE | 1 | 2010280 | This is a reconstruction project in Milwaukee County on local streets, South 51st Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 10/01/2010 | 325950 | 0.39
10973 | Wisconsin | MILWAUKEE | MILWAUKEE | 1 | 2010281 | This is a resurfacing project in Milwaukee County on local streets, South 51st Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 1500600 | 1.02
10974 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010282 | This is a reconstruction project in Milwaukee County on local streets, South 1st Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 10/01/2010 | 1959841.35 | 0.69
10975 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010283 | This is a bridge replacement project in Milwaukee County on local streets, South 6th Street Bridge. | Bridge Replacement | 02/10/2010 | 02/10/2010 | 01/01/2011 | 2532695.48 | 0.14
10976 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010284 | This is a restoration and rehabilitation project in Milwaukee County on County Highway NN, South 76th Street to South 72nd Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 496960 | 0.3
10977 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010285 | This is a reconstruction project in Milwaukee County on local streets, South 13th Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 10/01/2010 | 1619230 | 0.62
10978 | Wisconsin | MILWAUKEE | MILWAUKEE | 5 | 2010286 | This is a resurfacing project in Milwaukee County on local streets, Burleigh Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 984700 | 0.47
10979 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010287 | This is a restoration and rehabilitation project in Milwaukee County on County Highway S, . | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 2606294 | 1.7
10980 | Wisconsin | MILWAUKEE | MILWAUKEE | 5 | 2010288 | This is a bridge replacement project in Milwaukee County on local streets, 70th Street Bridge. | Bridge Replacement | 02/10/2010 | 02/10/2010 |  | 971700 | 0.07
10981 | Wisconsin | OZAUKEE | MILWAUKEE | 5 | 2010289 | This is a restoration and rehabilitation project in Ozaukee County on local streets, West Donges Bay Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 07/01/2010 | 307500 | 0.69
10982 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2010290 | This is a pedestrian and bicycle path project in Waukesha County, Lake County Trail. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 08/01/2010 | 1435885 | 5.437
10983 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2010291 | This is a resurfacing project in Waukesha County on local streets, Wisconsin Avenue. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 10/01/2010 | 1134970 | 0.5
10984 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2010292 | This is a reconstruction project in Waukesha County on County Highway O, South Moorland Blvd. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 1906500 | 0.54
10985 | Wisconsin | MILWAUKEE | MILWAUKEE | 5 | 2010293 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Fairy Chasm Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 190650 | 0.1
10986 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010294 | This is a bicycle path project in Milwaukee County, Kinnickinnic River Bike Trail. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 07/01/2010 | 395500 | 0.639
10987 | Wisconsin | MILWAUKEE | MILWAUKEE | 1 | 2010295 | This is a restoration and rehabilitation project in Milwaukee County on County Highway ZZ, . | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 1449208 | 0.76
10988 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010296 | This is a bridge rehabilitation project in Milwaukee County on local streets, Root River Parkway. | Bridge Replacement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 1033738 | 0.7
10989 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010297 | This is a pedestrian and bicycle path project in Milwaukee County, Hank Aaron State Trail. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 10/01/2010 | 1520234 | 0.353
10990 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010298 | This is a streetscape project in Milwaukee County, St. Francis. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 11/01/2010 | 952881 | 0.83
10991 | Wisconsin | BROWN | GREEN BAY | 8 | 2010299 | This is a resurfacing project in Brown County on local streets, City of Depere, Jordan Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 218940 | 0.9
10992 | Wisconsin | BROWN | GREEN BAY | 8 | 2010300 | This is a restoration and rehabilitation project in Brown County on local streets, City of Green Bay, Manitowoc Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 07/01/2010 | 810447 | 0.89
10993 | Wisconsin | CALUMET | APPLETON | 6 | 2010301 | This is a bicycle path project in Calumet County, Town of Harrison, Noe Road Bike and Pedestrian Path. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 09/01/2010 | 347635 | 1.58
10994 | Wisconsin | WINNEBAGO | APPLETON | 6 | 2010302 | This is a restoration and rehabilitation project in Winnebago County on local streets, City and Town of Menasha, Manitowoc Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 07/01/2010 | 569019 | 1.18
10995 | Wisconsin | OUTAGAMIE | APPLETON | 8 | 2010303 | This is a pedestrian and bicycle path project in Outagamie County, Greenville Pedestrian Trail. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 10/01/2010 | 667894 | 0.75
10996 | Wisconsin | MARINETTE |  | 8 | 2010304 | This is a reconstruction project in Marinette County, Walk-way connection. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 08/01/2010 | 723988 | 0.268
10997 | Wisconsin | MARQUETTE |  | 6 | 2010305 | This is a resurfacing project in Marquette County on County Highway CX, Village of Endeavor. | Pavement Improvement | 02/09/2010 | 02/09/2010 | 09/01/2010 | 1260750 | 1.47
10998 | Wisconsin | WAUSHARA |  | 6 | 2010306 | This is a pedestrian and bicycle path project in Waushara County, Wild Rose Roberts Park Trail. | Transportation Enhancements | 02/09/2010 | 02/09/2010 | 08/01/2010 | 246700 | 0.23
10999 | Wisconsin | BUFFALO |  | 3 | 2010307 | This is a bridge replacement project in Buffalo County on a town road, Town of Montana, Buells Valley Road. | Bridge Replacement | 02/09/2010 | 02/09/2010 | 08/01/2010 | 223860 | 0.4
11000 | Wisconsin | TREMPEALEAU |  | 3 | 2010308 | This is a bridge replacement project in Trempealeau County on town road, Town of Chimney Rock, Borst Valley Creek Bridge. | Bridge Replacement | 02/09/2010 | 02/09/2010 | 07/01/2010 | 196800 | 0.45
11001 | Wisconsin | POLK |  | 7 | 2010309 | This is a construction project in Polk County, Amery to Dresser Trail. | Transportation Enhancements | 02/09/2010 | 02/09/2010 | 07/01/2010 | 707950 | 10.385
11002 | Wisconsin | POLK |  | 7 | 2010310 | This is a reconstruction project in Polk County on County Highway Y, County Higway M - County Highway F. | Pavement Improvement | 02/09/2010 | 02/09/2010 | 08/01/2010 | 2460000 | 2.36
11003 | Wisconsin | SAWYER |  | 7 | 2010311 | This is a resurfacing project in Sawyer County on County Highway EE, Draper - Oxbo. | Pavement Improvement | 02/09/2010 | 02/09/2010 | 07/01/2010 | 1261980 | 0.39
11004 | Wisconsin | WASHBURN |  | 7 | 2010312 | This is a pedestrian and bicycle path project in Washburn County, Spooner Bicycle and Pedestrian Facility. | Transportation Enhancements | 02/09/2010 | 02/09/2010 | 08/01/2010 | 384990 | 0.735
11005 | Wisconsin | DOUGLAS |  | 7 | 2010314 | This is a reconstruction project in Douglas County on County Highway C, State Highway 35 to Kronberg Road. | Pavement Improvement | 02/09/2010 | 02/09/2010 | 09/01/2010 | 1230000 | 3.65
11006 | Wisconsin | TAYLOR |  | 7 | 2010315 | This is a resurfacing project in Taylor County on County Highway O, Lublin - Medford. | Pavement Improvement | 02/09/2010 | 02/09/2010 | 06/01/2010 | 615000 | 3.09
11007 | Wisconsin | ASHLAND |  | 7 | 2010316 | This is a resurfacing project in Ashland County on local streets, City of Ashland - 11th Street W. | Pavement Improvement | 02/09/2010 | 02/09/2010 | 08/01/2010 | 307500 | 0.84
11008 | Wisconsin | DOUGLAS | DULUTH-SUPERIOR (MN) | 7 | 2010317 | This is a resurfacing project in Douglas County on local streets, East 5th Street. | Pavement Improvement | 02/09/2010 | 02/09/2010 | 07/01/2010 | 461250 | 0.69
11009 | Wisconsin | ASHLAND |  | 7 | 2010318 | This is a resurfacing project in Ashland County on County Highway F, Butternut -County Line Road. | Pavement Improvement | 02/09/2010 | 02/09/2010 | 07/01/2010 | 916350 | 5.06
11010 | Wisconsin | IOWA |  | 3 | 2010326 | This is a bridge replacement project in Iowa County on County Highway C, Sneed Creek Bridge and approaches. | Bridge Replacement | 02/10/2010 | 02/10/2010 |  | 575640 | 0.64
11011 | Wisconsin | IOWA |  | 3 | 2010327 | This is a reconstruction project in Iowa County on County Highway X, Village of Linden, Babcock Avenue. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 237390 | 0.12
11012 | Wisconsin | DANE | MADISON | 2 | 2010328 | This is a reconstruction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Pavement Widening | 02/11/2010 | 02/11/2010 | 10/01/2011 | 2012280 | 1.08
11013 | Wisconsin | DANE | MADISON | 2 | 2010329 | This is a reconstruction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Pavement Widening | 02/10/2010 | 02/10/2010 | 10/01/2011 | 3075000 | 1.09
11014 | Wisconsin | DANE | MADISON | 2 | 2010331 | This is a reconstruction project in Dane County on County Highway Q, City of Middleton, Allen Boulevard. | Pavement Improvement | 02/10/2010 | 02/10/2010 |  | 277140 | 0.1
11015 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010332 | This is a decorative street lighting project in Milwaukee County, South 2nd Street. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 11/01/2010 | 553500 | 0.661
11016 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2010333 | This is a resurfacing project in Waukesha County on County Highway ES, Calhoun Road to County Highway O. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 504300 | 1.32
11017 | Wisconsin | RACINE | RACINE | 1 | 2010334 | This is a resurfacing project in Racine County on local streets, South Memorial Drive. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 11/01/2010 | 667890 | 0.34
11018 | Wisconsin | RACINE | RACINE | 1 | 2010335 | This is a resurfacing project in Racine County on local streets, North Main Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 11/01/2010 | 569490 | 0.459
11019 | Wisconsin | RACINE | RACINE | 1 | 2010336 | This is a resurfacing project in Racine County on County Highway C, Spring Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 376510 | 0.38
11020 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2010337 | This is a resurfacing project in Waukesha County on County Highway K, North 132nd Street to North 124th Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 1069657 | 0.52
11021 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2010338 | This is a resurfacing project in Waukesha County on County Highway T, Grandview Blvd. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 270600 | 0.21
11022 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2010339 | This is a resurfacing project in Waukesha County on County Highway V, Townline Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 1316100 | 3.137
11023 | Wisconsin | WAUKESHA | MILWAUKEE | 5 | 2010340 | This is a new roadway construction project in Waukesha County on County Highway Y, Intersection with County Highway M. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 1230000 | 1
11024 | Wisconsin | MILWAUKEE | MILWAUKEE | 4 | 2010341 | This is a resurfacing project in Milwaukee County on various highways, City of Milwaukee. | Pavement Improvement | 05/13/2010 | 05/13/2010 |  | 1217932.55 | 0
11025 | Wisconsin | MILWAUKEE | MILWAUKEE | 1,4 | 2010342 | This is a resurfacing project in Milwaukee County on various highways, City of Milwaukee. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 2320859.08 | 2.262
11026 | Wisconsin | KENOSHA |  | 1 | 2010343 | This is a streetscape project in Kenosha County on , East Main Street, County Highway Z. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 11/01/2010 | 410820 | 0.14
11027 | Wisconsin | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 1 | 2010344 | This is a reconstruction project in Kenosha County on County Highway KD, County Highway F to 70th Place. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 671359 | 3.88
11028 | Wisconsin | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 1 | 2010345 | This is a reconstruction project in Kenosha County on County Highway Z, Main Street East. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 11/01/2010 | 585500 | 0.14
11029 | Wisconsin | KENOSHA | KENOSHA | 1 | 2010346 | This is a restoration and rehabilitation project in Kenosha County on local streets, Sheridan Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 898400 | 0.49
11030 | Wisconsin | WALWORTH |  | 1 | 2010347 | This is a bridge rehabilitation project in Walworth County on local streets, Wrigley Drive. | Bridge Replacement | 02/10/2010 | 02/10/2010 | 06/01/2011 | 738000 | 0.13
11031 | Wisconsin | WALWORTH |  | 1 | 2010348 | This is a bridge rehabilitation project in Walworth County on local streets, Mohawk Road. | Bridge Replacement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 218940 | 0.057
11032 | Wisconsin | MANITOWOC |  | 6 | 2010349 | This is a bridge replacement project in Manitowoc County on a town road, SCL Road. | Bridge Replacement | 02/10/2010 | 02/10/2010 | 10/01/2010 | 378225 | 1.47
11033 | Wisconsin | MANITOWOC |  | 6 | 2010350 | This is a bridge replacement project in Manitowoc County on a town road, South Cleveland Road. | Bridge Replacement | 02/10/2010 | 02/10/2010 |  | 267279 | 1.66
11034 | Wisconsin | KEWAUNEE |  | 8 | 2010351 | This is a restoration and rehabilitation project in Kewaunee County on County Highway A, Town of Luxemburg. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 07/01/2010 | 512005 | 2
11035 | Wisconsin | BROWN | GREEN BAY | 8 | 2010352 | This is a restoration and rehabilitation project in Brown County on County Highway I, Town of Scott. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 412418 | 1.17
11036 | Wisconsin | WINNEBAGO |  | 6 | 2010353 | This is a restoration and rehabilitation project in Winnebago County on County Highway C, Town of Winneconnie - Town of Paygan. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 1931100 | 7.85
11037 | Wisconsin | MARINETTE |  | 8 | 2010354 | This is a reconstruction project in Marinette County on County T, Roosevelt Road - Gallagher Road. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 1353000 | 0.31
11038 | Wisconsin | BROWN | GREEN BAY | 8 | 2010355 | This is a restoration and rehabilitation project in Brown County on County Highway EB, Village of Howard. | Pavement Improvement | 02/10/2010 | 02/10/2010 |  | 683855 | 2.24
11039 | Wisconsin | MARINETTE |  | 8 | 2010356 | This is a reconstruction project in Marinette County on local streets, Shore Drive. | Pavement Improvement | 02/10/2010 | 02/10/2010 |  | 837630 | 0.53
11040 | Wisconsin | SHAWANO |  | 8 | 2010357 | This is a bridge replacement project in Shawano County on County Highway D, North Branch Embarrass River Crossing. | Bridge Replacement | 02/10/2010 | 02/10/2010 | 11/01/2010 | 608850 | 0.09
11041 | Wisconsin | ONEIDA |  | 7 | 2010358 | This is a reconstruction project in Oneida County on local streets, Phillip Street, City of Rhinelander. | Pavement Improvement | 02/10/2010 | 02/10/2010 |  | 682650 | 0.21
11042 | Wisconsin | TREMPEALEAU |  | 3 | 2010359 | This is an historic preservation project in Trempealeau County, Whitehall Historic Railroad Depot. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 10/01/2010 | 480930 | 0.14
11043 | Wisconsin | SAWYER |  | 7 | 2010361 | This is a pedestrian and bicycle path project in Sawyer County, City of Hayward, various locations. | Transportation Enhancements | 02/10/2010 | 02/10/2010 |  | 474780 | 0.809
11044 | Wisconsin | BAYFIELD |  | 7 | 2010362 | This is a streetscape project in Bayfield County on State Highway 13, Red Cliff - State Highway 13, Streetscape Improvement. | Transportation Enhancements | 02/10/2010 | 02/10/2010 | 10/01/2010 | 940950 | 0.23
11045 | Wisconsin | CHIPPEWA | EAU CLAIRE | 7 | 2010363 | This is a reconstruction project in Chippewa County on local streets, First Avenue. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 10/01/2010 | 541200 | 0.94
11046 | Wisconsin | CHIPPEWA | EAU CLAIRE | 7 | 2010364 | This is a reconstruction project in Chippewa County on County Highway X, 57th Avenue West to 184th Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 455100 | 0.5
11047 | Wisconsin | BARRON |  | 7 | 2010365 | This is a reconstruction project in Barron County on local streets, City of Rice Lake, Main Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 09/01/2010 | 2460000 | 3.25
11048 | Wisconsin | BARRON |  | 7 | 2010366 | This is a reconstruction project in Barron County on local streets, City of Rice Lake, Pioneer Avenue. | Pavement Improvement | 02/10/2010 | 02/10/2010 | 08/01/2010 | 738000.01 | 1.06
11049 | Wisconsin | BARRON |  | 7 | 2010367 | This is a resurfacing project in Barron County on local streets, City of Rice Lake, Haugen Street. | Pavement Improvement | 02/10/2010 | 02/10/2010 |  | 399750 | 0.83
11050 | Wisconsin | STATEWIDE |  | 8 | 2010406 | This is an on the job training project included in the Wisconsin Department of Transportation TrANS Program. This project trains individuals for entry into the highway construction industry by placin | Other | 03/24/2010 | 03/24/2010 | 09/01/2010 | 200000 | 0
11051 | Wisconsin | STATEWIDE |  | 8 | 2010407 | This is an on the job training project included in the Wisconsin Department of Transportation TrANS Program. This project trains individuals for entry into the highway construction industry by placin | Other | 03/24/2010 | 03/24/2010 | 09/01/2010 | 195148 | 0
11052 | Wisconsin | GRANT |  | 3 | 2010503 | This is the design engineering effort for a ferry boat project in Grant County, the Cassville Ferry. | Other | 03/11/2010 | 03/11/2010 | 06/01/2010 | 25000 | 0
11053 | Wisconsin | KENOSHA | KENOSHA | 1 | 2010848 | This is a reconstruction project in Kenosha County on 14th Ave., City of Kenosha, 25th Street to 31st Street. | Pavement Improvement | 07/28/2010 | 07/28/2010 |  | 810630 | 0.365
11054 | Wisconsin | OUTAGAMIE | APPLETON | 8 | 3009018 | This is the design engineering effort for a construction project in Outagamie County, Greenville Pedestrian Trail. | Other | 09/10/2009 | 09/10/2009 | 12/15/2009 | 10860 | 0
11055 | Wisconsin | WINNEBAGO | APPLETON | 6 | 3009019 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Neenah, Adams Street. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 8200 | 0
11056 | Wisconsin | CALUMET | APPLETON | 6 | 3009020 | This is the design engineering effort for a construction project in Calumet County, Town of Harrison, Noe Road, Bike and Pedestrian Facilities. | Transportation Enhancements | 09/10/2009 | 09/10/2009 | 12/01/2009 | 5653 | 0
11057 | Wisconsin | WINNEBAGO | OSHKOSH | 6 | 3009021 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Oshkosh, Snell Road. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 11660 | 0
11058 | Wisconsin | WINNEBAGO | APPLETON | 6 | 3009022 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Neenah, Wisconsin Avenue. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 8000 | 0
11059 | Wisconsin | OUTAGAMIE | APPLETON | 8 | 3009023 | This is the design engineering effort for a construction project in Outagamie County on local streets, Village of Little Chute, Washington Street. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 5860 | 0
11060 | Wisconsin | WINNEBAGO | APPLETON | 6 | 3009024 | This is the design engineering effort for a construction project in Winnebago County on local streets, City and Town of Menasha, Manitowoc Road. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 9252 | 0
11061 | Wisconsin | WINNEBAGO | APPLETON | 6 | 3009025 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Menasha, Tayco Street. | Other | 09/10/2009 | 09/10/2009 | 12/01/2009 | 7700 | 0
11062 | Wisconsin | ROCK | BELOIT (IL) | 1 | 3009145 | This is the design engineering effort for a construction project in Rock County on Town Road, Town of Turtle Townline. | Other | 09/21/2009 | 09/21/2009 | 12/01/2009 | 3200 | 0
11063 | Wyoming | LINCOLN |  | 00 | 0007035 | Construction of retaining walls on US 189 in Diamondville in Lincoln County. | Transportation Enhancements | 05/20/2009 | 05/20/2009 | 07/31/2010 | 204160 | 0
11064 | Wyoming | BIG HORN |  | 00 | 0200028 | Pavement overlay on approximately 14 miles of WYO 30 between Basin and Burlington in Big Horn County. | Pavement Improvement | 05/06/2009 |  | 06/30/2010 | 1528810 | 13.79
11065 | Wyoming | CAMPBELL |  | 00 | 0300044 | Pavement overlay of 12 miles of WYO 50 between Gillette and Pine Tree Junction in Campbell County. | Pavement Improvement | 08/21/2009 |  | 10/31/2010 | 2334918 | 6.79
11066 | Wyoming | CAMPBELL |  | 00 | 0300045 | Pavement overlay of 12 miles of WYO 50 between Gillette and Pine Tree Junction in Campbell County. | Pavement Improvement | 08/21/2009 |  | 10/31/2010 | 1520716 | 5.3
11067 | Wyoming | GOSHEN |  | 00 | 0800010 | Pipe, curb and gutter, and sidewalk replacement on 0.38 miles of WYO 151 in the Town of Lagrange in Goshen County, Wyoming. | Other | 05/19/2009 |  | 09/30/2009 | 97770 | 0.53
11068 | Wyoming | CROOK |  | 00 | 0904121 | Pavement overlay of 7 miles of I-90 between Sundance and the South Dakota State Line in Crook County. | Pavement Improvement | 05/08/2009 |  | 07/31/2010 | 6158739 | 7
11069 | Wyoming | NATRONA |  | 00 | 1301018 | Drainage repairs of pipe locations on WYO 251 (Casper Mountain Road) in Natrona County. | Other | 05/11/2009 |  | 10/31/2009 | 346426 | 0
11070 | Wyoming | PARK |  | 00 | 1501007 | Pavement overlay on approximately 7 miles of WYO 291 between Cody and South Fork in Park County. | Pavement Improvement | 07/14/2009 | 07/14/2009 | 09/15/2010 | 3148344 | 6.66
11071 | Wyoming | SHERIDAN |  | 00 | 1701013 | Replace right-of-way fence on 2.24 miles of WYO 331 between Sheridan and Beckton in Sheridan County. | Other | 05/11/2009 |  | 10/31/2010 | 82343 | 2.2
11072 | Wyoming | WESTON |  | 00 | 2302011 | Pavement overlay and bridge rehabilitation on WYO 116 north of WYO 450 in Weston County. | Pavement Improvement | 05/06/2009 |  | 10/31/2010 | 7679866 | 7.29
11073 | Wyoming | UINTA |  | 00 | 6598005 | Sidewalk and curb and guter replacement on Harrison Drive in Evanston, Wyoming. | Transportation Enhancements | 08/18/2009 |  | 08/31/2010 | 341402 | 0.31
11074 | Wyoming | STATEWIDE |  | 00 | B045012 | Bridge preventive maintenance at various locations in Wyoming Transportation District 5. | Bridge Improvement | 05/11/2009 | 05/11/2009 | 09/30/2009 | 95057 | 0
11075 | Wyoming | STATEWIDE |  | 00 | B082008 | Preventive maintenance (contract patching) and miscellaneous work at various locations in Wyoming Transportation District 2. | Pavement Improvement | 06/24/2009 |  | 09/30/2010 | 3291202 | 35
11076 | Wyoming | BIG HORN |  | 00 | B085011 | Fence replacement on approximately 11 miles of US 14 east and west of Greybull in Big Horn and Park Counties. | Other | 05/13/2009 |  | 09/30/2009 | 460590 | 0
11077 | Wyoming | STATEWIDE |  | 00 | B091005 | Preventive Maintenance, Crack sealing on 85.15 miles of various highways in District 1. | Pavement Improvement | 05/19/2009 |  | 04/30/2010 | 569576 | 0
11078 | Wyoming | STATEWIDE |  | 00 | B091008 | Preventive Maintenance, Bituminous Pavement Patches at various locations in District 1. | Pavement Improvement | 05/19/2009 |  | 09/30/2009 | 715110 | 0
11079 | Wyoming | BIG HORN |  | 00 | B095014 | Preventive maintenance (crack seal) on 125 miles of various roads in Wyoming Transportation District 5. | Pavement Improvement | 05/11/2009 |  | 03/31/2010 | 897140 | 0
11080 | Wyoming | STATEWIDE |  | 00 | B151002 | Preventive Maintenance, Chip Seals on various roadways in District 1. | Pavement Improvement | 05/20/2009 |  | 08/31/2010 | 3701395 | 0
11081 | Wyoming | STATEWIDE |  | 00 | B152005 | Preventive maintenance (chip seal) and miscellaneous work on approzimately 84 miles of highway in Wyoming Transportation District Two. | Pavement Improvement | 05/11/2009 |  | 08/31/2010 | 2529630 | 0
11082 | Wyoming | STATEWIDE |  | 00 | B152006 | Preventive maintenance (crack seal) and miscellaneous work on approximately 367 miles of highway in Wyoming Transporatation District 2. | Pavement Improvement | 08/04/2009 |  | 05/31/2010 | 3630973 | 0
11083 | Wyoming | STATEWIDE |  | 00 | B152009 | Bridge preventive maintenance and miscellaneous work at various locations in Wyoming Transportation District 2. | Bridge Improvement | 12/03/2009 |  | 10/31/2010 | 1267475 | 0
11084 | Wyoming | LARAMIE |  | 00 | I180017 | Install a new pedestrian railing and upgrade the lighting system on I-180 in Cheyenne. | Transportation Enhancements | 05/08/2009 |  | 11/30/2009 | 953556 | 0
11085 | Wyoming | PLATTE |  | 00 | I252157 | Landscaping and miscellaneous work at the Dwyer Junction Rest at the intersection of US 26 and I-25 in Platte County. | Transportation Enhancements | 10/12/2009 |  | 07/31/2010 | 146735 | 0
11086 | Wyoming | UINTA |  | 0 | I801175 | Bridge maintenance and rehabilitation at various location on I-80 in Uinta County. | Bridge Improvement | 08/18/2009 |  | 08/31/2010 | 621915 | 0
11087 | Wyoming | UINTA |  | 00 | I801176 | Preventive pavement maintenance and miscellaneous work on 23.20 miles of I-80 between Carter and LaBarge in Sweetwater and Uinta Counties. | Pavement Improvement | 06/10/2009 |  | 09/30/2010 | 2764193 | 0
11088 | Wyoming | UINTA |  | 00 | I801177 | Preventive pavement maintenance and rehabilitation of 28.10 miles of I-80 beginning at the Utah State Line in Uinta County. | Pavement Improvement | 05/27/2009 |  | 09/30/2010 | 10368301 | 28.1
11089 | Wyoming | SWEETWATER |  | 00 | I802192 | Concrete Pavement Rehabilitation on 15.34 miles of I-80 between Green River and Rock Springs in Sweetwater County. | Pavement Improvement | 06/24/2009 |  | 09/30/2010 | 7264004 | 15.37
11090 | Wyoming | SWEETWATER |  | 00 | I803140 | Preventive pavement maintenance and miscellaneous work on 33.50 miles of I-80 east of Rock Springs in Sweetwater County. | Pavement Improvement | 05/27/2009 | 05/27/2009 | 09/30/2010 | 3868970 | 34
11091 | Wyoming | CARBON |  | 00 | I804245 | Pavement resurfacing of 6.39 miles of I-80 east of Sinclair in Carbon County. | Pavement Improvement | 06/24/2009 | 06/24/2009 | 08/31/2010 | 5016287 | 6.229
11092 | Wyoming | ALBANY |  | 0 | I804250 | Preventive Maintenance, Replace Snow Fence along 23.35 miles of I-80 in Albany and Carbon Counties. | Other | 06/11/2009 |  | 09/15/2010 | 5190172 | 23.25
11093 | Wyoming | CARBON |  | 00 | I804251 | Pavement resurfacing and bridge repair along 13.04 miles of I-80 near Elk Mountain. | Pavement Improvement | 10/01/2009 |  | 10/31/2010 | 2525237 | 5.06
11094 | Wyoming | ALBANY |  | 00 | I805165 | Preventive Maintenance, Installation of a friction course on I-80 in Telephone Canyon east of Laramie. | Pavement Improvement | 06/24/2009 |  | 09/30/2010 | 2039663 | 5.17
11095 | Wyoming | JOHNSON |  | 00 | I902118 | Pavement overlay and surface treatment on 6.2 miles of I-90 between Buffalo and Gillette in Johnson County. | Pavement Improvement | 05/20/2009 | 05/20/2009 | 07/15/2010 | 3541525 | 6.2
11096 | Wyoming | JOHNSON |  | 00 | I902119 | Pavement overlay and surface treatment on 6.2 miles of I-90 between Buffalo and Gillette in Johnson County. | Pavement Improvement | 05/20/2009 | 05/20/2009 | 07/15/2010 | 4709826 | 8
11097 | Wyoming | CROOK |  | 00 | I904130 | Pavement preventive maintenance on 12.7 miles of I-90 between Moorcroft and Sundance in Crook County. | Pavement Improvement | 06/10/2009 | 06/10/2009 | 06/30/2010 | 2640282 | 12.71
11098 | Wyoming | TETON |  | 00 | N104084 | Bike path construction along US 26/189/191 north of Jackson, Wyoming. | Transportation Enhancements | 09/28/2009 | 09/28/2009 | 10/30/2011 | 1000000 | 1.14
11099 | Wyoming | FREMONT |  | 00 | N202062 | Rest Area rehabilitation of the Sweetwater Station Rest Area between Muddy Gap and Lander. | Other | 06/10/2009 |  | 08/27/2010 | 466839 | 0
11100 | Wyoming | FREMONT |  | 00 | N203063 | Pavement overlay of approximately 4 miles of US 26 between Riverton and Shoshoni in Fremont County. | Pavement Improvement | 05/20/2009 | 05/20/2009 | 09/30/2010 | 1614019 | 4.91
11101 | Wyoming | PARK |  | 00 | N291036 | Pavement reconstruction and widening of 3.85 miles of US 14A between Cody and Powell in Park County. | Pavement Widening | 06/24/2009 |  | 10/15/2010 | 10945393 | 3.62
11102 | Wyoming | FREMONT |  | 00 | N303049 | Rest Area rehabilitation of the Diversion Dam Rest Area between Diversion Dam Junction and Dubois. | Other | 06/10/2009 |  | 08/27/2010 | 523873 | 0
11103 | Wyoming | BIG HORN |  | 00 | N312013 | Safety improvements including slope flattening and guardrail upgrades on 1.48 miles of US 14/16 between Cody and Greybull. | Safety/Traffic Management | 06/10/2009 |  | 10/15/2009 | 391600 | 1.48
11104 | Wyoming | HOT SPRINGS |  | 00 | N331025 | Rest Area rehabilitation of the Gooseberry Creek Rest Area between Thermopolis and Meeteetse. | Other | 06/10/2009 |  | 08/27/2010 | 388249 | 0
11105 | Wyoming | NATRONA |  | 00 | N341105 | Rest Area rehabilitation of the Waltman Rest Area between Casper and Shoshoni. | Other | 06/10/2009 |  | 08/27/2010 | 248366 | 0
11106 | Wyoming | FREMONT |  | 00 | N342042 | Pavement overlay on 11 miles of US 26 between Casper and Shoshoni in Fremont County. | Pavement Improvement | 08/18/2009 |  | 09/30/2010 | 3323603 | 11
11107 | Wyoming | BIG HORN |  | 00 | N345080 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Safety/Traffic Management | 06/11/2009 |  | 10/31/2010 | 874253 | 5.099
11108 | Wyoming | BIG HORN |  | 00 | N345089 | Rest Area rehabilitation of the Greybull Rest Area northwest of Greybull. | Other | 06/10/2009 |  | 08/27/2010 | 365613 | 0
11109 | Wyoming | BIG HORN |  | 00 | N345095 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Pavement Improvement | 06/11/2009 |  | 10/31/2010 | 1718433 | 4.99
11110 | Wyoming | BIG HORN |  | 00 | N345096 | Pavement overlay on approximately 6 miles of US 16.20 between Manderson and Basin in Big Horn County. | Pavement Improvement | 08/18/2009 |  | 09/30/2010 | 1346404 | 6.049
11111 | Wyoming | BIG HORN |  | 00 | N345101 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Safety/Traffic Management | 06/11/2009 |  | 10/31/2010 | 145171 | 7
11112 | Wyoming | NIOBRARA |  | 00 | N402016 | Pavement widening and overlay on 9.90 miles of US 18/20 between Lusk and Manville in Niobrara County. | Pavement Improvement | 05/27/2009 |  | 10/31/2010 | 12017032 | 10
11113 | Wyoming | WESTON |  | 00 | N442066 | Enhancements to US 16 (Upton Main Street) including landscaping, sidewalk, curb and gutter, in Weston County. | Transportation Enhancements | 08/17/2009 |  | 10/31/2010 | 150000 | 1.25
11114 | Wyoming | GOSHEN |  | 00 | N853084 | Pavement overlay and miscellaneous work on 9.51 miles of US 85 north of Lagrange in Goshen County. | Pavement Improvement | 05/20/2009 |  | 08/31/2010 | 3343449 | 9.75
11115 | Wyoming | NIOBRARA |  | 00 | N854071 | Pavement overlay and bridge repair of 5 miles of US 85 between Newcastle and Mule Creek Junction in Niobrara County. | Pavement Improvement | 08/04/2009 |  | 10/31/2010 | 2033742 | 6.65
11116 | Wyoming | LINCOLN |  | 00 | P112021 | Construction of retaining walls on US 189 in Diamondville in Lincoln County. | Transportation Enhancements | 05/20/2009 | 05/20/2009 | 07/31/2010 | 250000 | 0
11117 | Wyoming | FREMONT |  | 00 | P142041 | Rest Area rehabilitation of the South Pass Rest Area between Farson and Lander. | Other | 06/10/2009 |  | 08/27/2010 | 450785 | 0
11118 | Wyoming | CARBON |  | 00 | P182029 | Pavement rehabilitation and installation of a wildlife underpass on WYO 789 south of Creston Junction. | Pavement Improvement | 06/11/2009 | 06/11/2009 | 10/31/2010 | 1071737 | 4
11119 | Wyoming | UINTA |  | 00 | P341108 | Pavement rehabilitation, sidewalk replacement and curb and gutter replacement, and bridge repair on Casper Streets in Natrona County. | Pavement Improvement | 05/20/2009 |  | 10/31/2010 | 2508438 | 1.09
11120 | Wyoming | UINTA |  | 00 | P501001 | Pavement overlay and miscellaneous work on 10.45 miles of WYO 89 north of Evanston in Uinta County. | Pavement Improvement | 06/11/2009 |  | 09/30/2010 | 3216146 | 10.48
11121 | Wyoming | UINTA |  | 00 | P511018 | Sidewalk and curb and guter replacement on Harrison Drive in Evanston, Wyoming. | Transportation Enhancements | 08/18/2009 |  | 08/31/2010 | 169715 | 0.31
11122 | Wyoming | LARAMIE |  | 00 | P561028 | Reconstruct West Lincolnway (US-30) in Cheyenne. | Pavement Improvement | 07/20/2009 |  | 10/15/2010 | 9289380 | 1.289
11123 | Wyoming | CONVERSE |  | 00 | P581025 | Landscaping and miscellaneous work on US 20/26/87 in the City of Douglas. | Transportation Enhancements | 10/12/2009 |  | 07/31/2010 | 81558 | 0.759
11124 | Northern Mariana | STATEWIDE |  | 98 | 0031014 | Reconstruction and widening of Route 31, Phase II-A. This project involves reconstructing existing roadway to upgrade the pavement structure. The project includes excavation and backfilling, construct | Other | 11/13/2009 | 11/13/2009 |  | 4500000 | 1.5
11125 | Puerto Rico |  | AGUDILLA | 00 | 0002040 | This project consists of the replacement of BRIDGE NO. 763 ON PR-2 KM 127.4, over HIGHWAY PR-2R, in the municipality of Aguadilla, PR. | Pavement Improvement | 08/14/2009 | 08/14/2009 | 12/06/2010 | 6716258.75 | 0.49
11126 | Puerto Rico |  | PONCE | 00 | 0002051 | This project consists of the construction of a new interchange as part of the conversion of PR-2 to expressway. The project is located in the Punto Oro area, Ponce, PR. | Pavement Widening | 02/22/2010 | 02/22/2010 | 08/09/2012 | 18131172.55 | 0.618
11127 | Puerto Rico |  | SAN JUAN | 00 | 0020007 | This project consists of replacing damaged bearing pads under the bridge on PR-20, to raise it to its original grade and elevation. It also includes repairs to the bridge deck. It is located in Guay | Bridge Improvement | 10/30/2009 | 10/30/2009 | 03/18/2010 | 571297 | 0.073
11128 | Puerto Rico |  | MAYAGUEZ | 00 | 0102012 | This project consists of reconstructing and widening to four lanes of road PR-64 from PR-2 to PR-102 in "El Mani" sector of the municipality of Mayaguez. | Pavement Widening | 03/26/2010 | 03/26/2010 | 03/14/2012 | 10988520.71 | 1.92
11129 | Puerto Rico |  |  | 00 | 0173008 | This project consists of the realignment of highway PR-173 at KM 3.0 in the municipality of Cidra. This road was affected by a landslide. | Pavement Improvement | 11/05/2009 | 11/05/2009 | 04/03/2010 | 414374.9 | 0.152
11130 | Puerto Rico |  |  | 00 | 9999087 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's North Region Unit I, in | Pavement Improvement | 05/17/2010 | 05/17/2010 | 05/11/2011 | 3296542.58 | 9.625
11131 | Puerto Rico |  |  | 00 | 9999088 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region, Unit I in | Bridge Improvement | 08/10/2009 | 08/10/2009 | 08/04/2010 | 2480000 | 3.181
11132 | Puerto Rico |  |  | 00 | 9999089 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit I, in t | Pavement Improvement | 03/15/2010 | 03/15/2010 | 03/09/2011 | 3171302.67 | 13.82
11133 | Puerto Rico |  |  | 00 | 9999090 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's West Region Unit I, in t | Pavement Improvement | 04/16/2010 | 04/16/2010 | 04/11/2011 | 1890118.15 | 1.758
11134 | Puerto Rico |  |  | 00 | 9999091 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's Metro Region Unit I in | Pavement Improvement | 03/15/2010 | 03/15/2010 | 01/08/2011 | 2433604.7 | 3.9
11135 | Puerto Rico |  |  | 00 | 9999092 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region Unit II in | Pavement Improvement | 07/31/2009 | 07/31/2009 | 07/25/2010 | 3758034.4 | 18.026
11136 | Puerto Rico |  |  | 00 | 9999093 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region Unit III in | Pavement Improvement | 07/13/2009 | 07/13/2009 | 07/07/2010 | 3455054.83 | 12.505
11137 | Puerto Rico |  |  | 00 | 9999094 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's North Region Unit II in | Pavement Improvement | 05/10/2010 | 05/10/2010 | 05/04/2011 | 3097326.22 | 4.009
11138 | Puerto Rico |  |  | 00 | 9999095 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's North Region Unit III in | Pavement Improvement | 05/10/2010 | 05/10/2010 | 05/04/2011 | 4411210.82 | 7.75
11139 | Puerto Rico |  |  | 00 | 9999096 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit II, in | Pavement Improvement | 03/15/2010 | 03/15/2010 | 03/09/2011 | 2856249.25 | 3.622
11140 | Puerto Rico |  |  | 00 | 9999097 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit III in | Pavement Improvement | 02/22/2010 | 02/22/2010 | 10/19/2010 | 2321390 | 7.75
11141 | Puerto Rico |  |  | 00 | 9999098 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit IV in t | Pavement Improvement | 03/15/2010 | 03/15/2010 | 11/09/2010 | 1377963.35 | 5.5
11142 | Puerto Rico |  |  | 00 | 9999099 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's West Region Unit II in t | Pavement Improvement | 04/16/2010 | 04/16/2010 | 04/10/2011 | 1872894.6 | 1.388
11143 | Puerto Rico |  |  | 00 | 9999100 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's West Region Unit III in | Pavement Improvement | 04/16/2010 | 04/16/2010 | 08/08/2011 | 4798316.35 | 4.4
11144 | Puerto Rico |  |  | 00 | 9999101 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's Metro Region Unit II in | Pavement Improvement | 03/25/2010 | 03/25/2010 | 01/18/2011 | 2283739 | 10.5
11145 | Puerto Rico |  |  | 00 | 9999102 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's Metro Region Unit III in | Pavement Improvement | 03/25/2010 | 03/25/2010 | 03/19/2011 | 3096950 | 9.756
11146 | Virgin Islands | VIRGIN ISLANDS |  | VI00 | 0032008 | This project proposes to improve pedestrian mobility by constructing sidewalks, installing new crosswalks, new pedestrian crossing signs and installing new roadway striping from the Red Hook Marine Te | Other | 01/11/2010 | 01/11/2010 | 05/21/2010 | 1050359.96 | 0.35
11147 | Virgin Islands | VIRGIN ISLANDS |  | VI00 | 0070011 | This project proposes to repave 2 miles of asphalt roadway along the eastern section of Queen Mary Highway. The project will also make improvements to prevent flooding on the roadway. | New Construction | 10/16/2009 | 10/29/2009 | 10/28/2010 | 4859669.4 | 2.05
11148 | Virgin Islands | VIRGIN ISLANDS |  | VI00 | 0104003 | This project proposes to repave over 2 miles of asphalt roadway. The project will also replace culverts and pipes along the roadway to prevent flooding of the road. The project will install pedestrian | New Construction | 10/05/2009 | 10/05/2009 | 07/02/2010 | 4782469 | 2.83
11149 | (HQFL) IRR | MATANUSKA-SUSITNA, AK |  | 1 | 0108102 | Engineering design and estimates for new gravel road construction to include egress and ingress to tribally-owned housing area. Employ and train tribal citizens in the use of heavy equipment for futu | New Construction Roadway | 11/19/2009 | 04/01/2010 | 09/30/2011 | 524520 | 0.5
11150 | (HQFL) IRR | BRYAN, OK |  | 2 | 3808 | 3.0 miles of reconstruction | 4R Reconstruction, No Added Capacity | 04/26/2010 | 04/26/2010 | 01/21/2011 | 3292083.9 | 2.969
11151 | (HQFL) IRR | DEL NORTE, CA |  | 1 | 52564304 | Develop Planning, Survey and Engineering | 0ther | 02/22/2010 | 02/22/2010 | 02/22/2011 | 155339 | 1.2
11152 | (HQFL) IRR | EL PASO, TX |  | 16 | 6810E00132 01 | Traffic Signal Installation | Traffic Management Engineering - HOV | 06/01/2010 | 06/15/2010 | 09/01/2010 | 208525 | 0
11153 | (HQFL) IRR |  |  | 1 | E0114804 | Route # 0004 3.8 miles of new construction into our Hartney Bay Subdivision | New Construction Roadway | 12/24/2009 | 02/01/2010 | 05/21/2011 | 1267760 | 1.25
11154 | (HQFL) IRR |  |  | 1 | E0180001 | Construct 2763 feet of roadway. This involves three different roads, which will be built in a residential subdivision. Construction includes drainage system, material to subgrade, lighting, curb&gut | New Construction Roadway | 06/17/2009 | 08/24/2009 | 10/31/2012 | 1194726 | 0.52
11155 | (HQFL) IRR |  |  |  | E0224101 | Boardwalk Maintenance | 4R Restoration and Rehabilitation | 12/24/2009 | 04/01/2010 | 09/30/2010 | 8292 | 0
11156 | (HQFL) IRR |  |  | 0 | E0224102 | equipment purchase | 0ther | 12/24/2009 |  | 09/30/2010 | 24879 | 0
11157 | (HQFL) IRR |  |  |  | E0249701 | Purchase a vehicle | 0ther | 12/24/2009 |  | 09/30/2010 | 37293 | 0
11158 | (HQFL) IRR |  |  | 0 | E0302201 | Preliminary Engineering | New Construction Roadway | 01/08/2010 |  | 12/31/2010 | 13813 | 2.1
11159 | (HQFL) IRR |  |  | 0 | E0316201 | New Roads in new housing sub-division | New Construction Roadway | 10/15/2009 | 10/15/2009 |  | 1121741 | 2.9
11160 | (HQFL) IRR | SOUTHEAST FAIRBANKS, AK |  | 1 | E0348301 | Routine Maintenance on official routes | 0ther | 12/31/2009 | 02/15/2010 | 06/30/2010 | 25000 | 0
11161 | (HQFL) IRR | SOUTHEAST FAIRBANKS, AK |  | 1 | E0348302 | Rehab portion of Rt 1004 | New Construction Roadway | 12/31/2009 | 01/19/2010 | 09/30/2010 | 1090000 | 0
11162 | (HQFL) IRR | SOUTHEAST FAIRBANKS, AK |  | 1 | E0348303 | safety / purchase and install warning and speed limit signs for route 1004 | Safety | 12/31/2009 | 01/19/2010 | 09/30/2010 | 113494 | 0
11163 | (HQFL) IRR |  |  | 0 | E0363401 | Dust/Erosion Control using new technology surface materials | 0ther | 01/08/2010 |  | 09/30/2010 | 150136 | 0
11164 | (HQFL) IRR | PRINCE OF WALES-OUTER KETCHIKAN, AK |  | 1 | FY09 IRR 002 | Property Development and building construction | 0ther | 01/04/2010 |  | 06/01/2010 | 965657 | 0
11165 | (HQFL) IRR | PINAL, AZ |  | 07 | GRIR 103 | Grade, drain, construct curb, place aggregate base course, hot asphalt concrete, pavement markings, and maintenance | New Construction Roadway | 03/24/2010 | 03/01/2010 | 07/30/2010 | 1362231 | 0
11166 | (HQFL) IRR | UMATILLA, OR |  | 3 | ON 1009 | Road re-construction and widening | 4R Reconstruction, No Added Capacity | 04/12/2010 | 05/05/2010 | 10/15/2011 | 4137864 | 0
11167 | (HQFL) IRR | SNOHOMISH, WA |  | 2 | P10145R1 | Transit Capital Purchase | Transit | 02/23/2010 | 03/15/2010 |  | 220000 | 0
11168 | (HQFL) IRR |  |  | 2 | P10146R1 | Truck Purchase | 0ther | 02/23/2010 | 03/15/2010 |  | 45000 | 0
11169 | (HQFL) IRR |  |  | 1 | PIA10020 | SIDEWALK RECONSTRUCTION | 4R Reconstruction, No Added Capacity | 04/20/2010 | 04/20/2010 | 05/10/2010 | 42000 | 0.4
11170 | (HQFL) IRR | CIBOLA, NM |  | 2 | RN 125 | Milling and Paving Rehabilitation | 4R Reconstruction, No Added Capacity | 05/26/2009 |  | 08/31/2009 | 644000 | 9
11171 | (HQFL) IRR |  |  | 1 | TH 01 | Amalga Street - Remove existing asphalt pavement and repave approximately 775 ft of roadway Cinema Drive - Remove existing asphalt pavement and repave approximately 1,050 ft of roadway Crest Street | 4R Resurfacing | 05/15/2010 | 07/15/2010 | 09/30/2010 | 616718 | 1
11172 | (HQFL) IRR |  |  | 2 | Z331 2 2&4 | RE-CONSTRUCTION | 4R Reconstruction, No Added Capacity | 04/12/2010 | 04/12/2010 | 10/30/2010 | 856925 | 0.7
11173 | (HQFL) FS |  |  | 3 | AG4419C090059 | Resurfacing of approximately 4 miles of bituminous surface treated road with hot asphalt concrete in Polk County, Tennessee | 4R Resurfacing | 11/02/2009 | 11/02/2009 | 12/23/2009 | 312731 | 3.22
11174 | (BIA) IRR | POLK, TX |  | 08 | B00R8301 | roadway design | Preliminary Engineering | 05/17/2010 |  | 12/31/2011 | 65321 | 1.2
11175 | (BIA) IRR | JACKSON, KS |  | 02 | B04R8621 | Grade, Drain, and Surface | 4R Reconstruction, No Added Capacity | 06/18/2010 |  | 12/31/2011 | 64296 | 0.125
11176 | (BIA) IRR | JACKSON, KS |  | 02 | B04R8622 | Grade, Drain and Surface | 4R Reconstruction, No Added Capacity | 06/17/2010 |  | 12/31/2011 | 169642 | 0.083
11177 | (BIA) IRR | CADDO, OK |  | 03 | B06R8041 | Resurface 4.0 miles of roadway. | 4R Resurfacing | 05/17/2010 |  | 09/30/2010 | 508857 | 4
11178 | (BIA) IRR | CADDO, OK |  | 03 | B06R8061 | Resurfacing 6.0 miles of roadway in Western Caddo Co., OK | 4R Resurfacing | 05/25/2010 |  | 09/30/2010 | 996390 | 5.7
11179 | (BIA) IRR | COMANCHE, OK |  | 04 | B06R8081 | Bridge Replacement Project | Bridge Replacement, No Added Capacity | 06/30/2010 | 06/30/2010 | 12/27/2010 | 745021 | 0.273
11180 | (BIA) IRR | CADDO, OK |  | 03 | B06R8091 | Roadway surfacing/chip & seal project; 12.0 miles | 4R Resurfacing | 05/17/2010 |  | 09/30/2010 | 286009 | 12
11181 | (BIA) IRR | KAY, OK |  | 03 | B07R8101 | asphalt overlay/resurfacing | 4R Resurfacing | 05/03/2010 |  | 09/30/2010 | 798728 | 3
11182 | (BIA) IRR | KAY, OK |  | 03 | B07R8131 | Grade, Drain, and Surface | 4R Reconstruction, No Added Capacity | 05/27/2010 |  | 09/30/2010 | 632756 | 1.5
11183 | (BIA) IRR | KAY, OK |  | 03 | B07R8141 | asphalt overlay/resurfacing | 4R Resurfacing | 05/25/2010 |  | 09/30/2010 | 465376 | 1.75
11184 | (BIA) IRR | LINCOLN, OK |  | 03 | B08R8223 | Overlay/Surfacing Project | 4R Resurfacing | 05/27/2010 |  | 09/30/2010 | 283567 | 2
11185 | (BIA) IRR | POTTAWATOMIE, OK |  | 05 | B08R8232 | asphalt overlay/resurfacing | 4R Resurfacing | 05/27/2010 |  | 09/30/2010 | 577392 | 5
11186 | (BIA) IRR | LINCOLN, OK |  | 03 | B08R8241 | Construciton of Chapel Parking Lot; Grade, Drain and Surfacing | 4R Reconstruction, No Added Capacity | 05/03/2010 | 05/09/2010 | 10/30/2010 | 212126 | 0.143
11187 | (BIA) IRR | LINCOLN, OK |  | 03 | B08R8242 | Reconstruciton of Cemetery Road; Grade, Drain and Surfacing | 4R Reconstruction, No Added Capacity | 05/03/2010 | 05/09/2010 | 10/30/2010 | 522999 | 1.096
11188 | (BIA) IRR | LINCOLN, OK |  | 03 | B08R8243 | asphalt overlay/resurfacing | 4R Resurfacing | 05/27/2010 |  | 09/30/2010 | 823806 | 7.79
11189 | (BIA) IRR | GLACIER, MT |  | 01 | C51ER006 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 12028 | 0
11190 | (BIA) IRR | GLACIER, MT |  | 01 | C51ER008 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 916068 | 0
11191 | (BIA) IRR | GLACIER, MT |  | 01 | C51ER010 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 141633 | 0
11192 | (BIA) IRR | GLACIER, MT |  | 01 | C51ER017 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 298897 | 0
11193 | (BIA) IRR | GLACIER, MT |  | 01 | C51ER035 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 41167 | 0
11194 | (BIA) IRR | GLACIER, MT |  | 01 | C51ER041 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 46064 | 0
11195 | (BIA) IRR | GLACIER, MT |  | 01 | C51ER043 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 96832 | 0
11196 | (BIA) IRR | GLACIER, MT |  | 01 | C51ER070 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 83053 | 0
11197 | (BIA) IRR | BIG HORN, MT |  | 01 | C52ER014 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 171411 | 0
11198 | (BIA) IRR | BIG HORN, MT |  | 01 | C52ER055 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 52120 | 0
11199 | (BIA) IRR | BIG HORN, MT |  | 01 | C52ER088 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 347769 | 0
11200 | (BIA) IRR | BIG HORN, MT |  | 01 | C52ER091 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 3007005 | 0
11201 | (BIA) IRR | BIG HORN, MT |  | 01 | C52ER125 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 74586 | 0
11202 | (BIA) IRR | BIG HORN, MT |  | 01 | C52ER201 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 55211 | 0
11203 | (BIA) IRR | BIG HORN, MT |  | 01 | C52ER777 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 144496 | 0
11204 | (BIA) IRR | BLAINE, MT |  | 01 | C55ER004 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 286564 | 0
11205 | (BIA) IRR | BLAINE, MT |  | 01 | C55ER006 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 135913 | 0
11206 | (BIA) IRR | BLAINE, MT |  | 01 | C55ER011 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 48169 | 0
11207 | (BIA) IRR | BLAINE, MT |  | 01 | C55ER021 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 5641 | 0
11208 | (BIA) IRR | BLAINE, MT |  | 01 | C55ER112 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/03/2009 | 09/04/2009 |  | 7442 | 0
11209 | (BIA) IRR | ROSEBUD, MT |  | 01 | C57ER005 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/07/2009 | 09/07/2009 |  | 84814 | 0
11210 | (BIA) IRR | ROSEBUD, MT |  | 01 | C57ER011 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/07/2009 | 09/07/2009 |  | 958004 | 0
11211 | (BIA) IRR | ROSEBUD, MT |  | 01 | C57ER022 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/07/2009 | 09/07/2009 |  | 25666 | 0
11212 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER005 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 51194 | 0
11213 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER015 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 123468 | 0
11214 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER016 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 233781 | 0
11215 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER027 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 179818 | 0
11216 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER028 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 243359 | 0
11217 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER049 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 113936 | 0
11218 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER075 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 150161 | 0
11219 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER077 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 40153 | 0
11220 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER101 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 1574338 | 0
11221 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER116 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 187307 | 0
11222 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER211 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 393484 | 0
11223 | (BIA) IRR | FREMONT, WY |  | 01 | C58ER805 | CHIP SEAL AND CORRIDOR SAFETY IMPROVEMENT | 4R Resurfacing | 09/21/2009 | 09/21/2009 |  | 133725 | 0
11224 | (BIA) IRR | HILL, MT |  | 1 | C59ER001 | Chip Seal | 4R Resurfacing | 08/14/2009 | 08/14/2009 |  | 115120 | 2.9
11225 | (BIA) IRR | HILL, MT |  | 1 | C59ER002 | Chip Seal | 4R Resurfacing | 08/14/2009 | 08/14/2009 |  | 575976 | 9.7
11226 | (BIA) IRR | HILL, MT |  | 1 | C59ER101 | Chip Seal | 4R Resurfacing | 08/14/2009 | 08/14/2009 |  | 73466 | 1.1
11227 | (BIA) IRR | HILL, MT |  | 1 | C59ER114 | Chip Seal | 4R Resurfacing | 08/14/2009 | 08/14/2009 |  | 453391 | 5.6
11228 | (BIA) IRR | KODIAK ISLAND, AK |  | 01 | E01002A1 | Design for rehabilitation of Boat landing dock that begins access to trail #1009 | Preliminary Engineering | 04/01/2010 | 04/27/2010 | 12/31/2010 | 61532 | 0
11229 | (BIA) IRR | KODIAK ISLAND, AK |  | 01 | E01237A1 | Design of Landfill Road (Route 1014) | Preliminary Engineering | 04/01/2010 |  | 12/31/2010 | 180457 | 0
11230 | (BIA) IRR | DILLINGHAM, AK |  | 01 | E01259A3 | Preliminary design for 0.5 miles of an existing gravel road | Preliminary Engineering | 04/09/2010 |  | 12/31/2010 | 71418 | 0
11231 | (BIA) IRR | KENAI PENINSULA, AK |  | 01 | E01396A1 | Phase 1 design project to develop environmental docments for Windy Bay Road Project | Preliminary Engineering | 04/02/2010 |  | 09/06/2010 | 44626 | 0
11232 | (BIA) IRR | KENAI PENINSULA, AK |  | 01 | E01505A2 | Roadway realignment/ construction including drainage improvements | 4R Relocation | 04/09/2010 | 04/09/2010 | 05/30/2010 | 90055 | 0
11233 | (BIA) IRR | BETHEL, AK |  | 01 | E02005A1 | PS&E development for Design of Gweek Road | Preliminary Engineering | 04/02/2010 |  | 12/31/2010 | 152255 | 0
11234 | (BIA) IRR | BETHEL, AK |  | 01 | E02006A1 | PS&E Activities for the Reconstruction & Rehabilitation of AKIK2 | Preliminary Engineering | 04/09/2010 |  | 04/19/2010 | 47485 | 0
11235 | (BIA) IRR | BETHEL, AK |  | 01 | E02275A1 | Preliminary Design for Boardwalk Reconstruction | Preliminary Engineering | 04/01/2010 |  | 12/31/2010 | 54249 | 0
11236 | (BIA) IRR | BETHEL, AK |  | 01 | E02841A1 | Phase II of Loop Road construction, for the purchase of aggregate surface course, grading E-1 | 4R Reconstruction, No Added Capacity | 06/04/2010 |  | 12/31/2010 | 52098 | 0
11237 | (BIA) IRR | YUKON-KOYUKUK, AK |  | 01 | E03205A1 | Design project for the reconstruction of an existing gravel road | Preliminary Engineering | 04/01/2010 | 04/01/2010 | 12/31/2010 | 66425 | 0
11238 | (BIA) IRR | BELTRAMI, MN |  | 07 | F52409SI | For the reconstruction of the following projects identified in the Bid/Control Schedule: .040 Miles of Indian Service route 17, Jerome Cut Off, Project No. F52409SI located on the Red Lake Indian Rese | 4R Resurfacing | 09/14/2009 | 09/14/2009 | 09/30/2012 | 87000 | 0.04
11239 | (BIA) IRR | BELTRAMI, MN |  | 07 | F52409SJ | For the reconstruction of the following projects identified in the Bid/Control Schedule: 14.42 Miles of paved surface of Indian Service route 18, Ponemah Road, Project No. F52409SJ located on the Red | 4R Restoration and Rehabilitation | 09/14/2009 | 09/14/2009 | 09/30/2012 | 2626283 | 14.42
11240 | (BIA) IRR | CASS, MN |  | 08 | F53407SA | Centerline culverts, bituminous pavement reclamation & bituminous surfacing. | 4R Reconstruction, Added Capacity | 10/15/2009 | 10/15/2009 | 09/30/2012 | 2712170 | 15.7
11241 | (BIA) IRR | ITASCA, MN |  | 08 | F53407SC | Bituminous reclamation, bituminous pavement. | 4R Reconstruction, Added Capacity | 04/27/2010 | 04/28/2010 | 09/30/2012 | 241789 | 1.09
11242 | (BIA) IRR | ITASCA, MN |  | 08 | F53407SD | Bituminous reclamation, bituminous pavement. | 4R Reconstruction, Added Capacity | 04/27/2010 | 04/28/2010 | 09/30/2012 | 139444 | 0.48
11243 | (BIA) IRR | BELTRAMI, MN |  | 08 | F53407SG | Bituminous reclamation, bituminous pavement. | 4R Reconstruction, Added Capacity | 04/27/2010 | 04/28/2010 | 09/30/2012 | 468357 | 1.88
11244 | (BIA) IRR | CASS, MN |  | 08 | F53407SI | Grading, Drainage, aggregate base, bituminous pavement. | 4R Reconstruction, Added Capacity | 04/19/2010 | 04/19/2010 | 09/30/2012 | 133713 | 0.177
11245 | (BIA) IRR | CASS, MN |  | 08 | F53407SJ | Grading, Drainage, aggregate base, bituminous pavement. | 4R Reconstruction, Added Capacity | 04/19/2010 | 04/28/2010 | 09/30/2012 | 577960 | 0.55
11246 | (BIA) IRR | CASS, MN |  | 08 | F53407SK | Grading, Drainage, aggregate base, bituminous pavement. | 4R Reconstruction, Added Capacity | 04/27/2010 | 04/28/2010 | 09/30/2012 | 240911 | 0.45
11247 | (BIA) IRR | CASS, MN |  | 08 | F53407SM | Grading, Drainage, aggregate base, bituminous pavement. | 4R Reconstruction, Added Capacity | 04/29/2010 | 05/18/2010 | 09/30/2012 | 876042 | 4.84
11248 | (BIA) IRR | ITASCA, MN |  | 08 | F53407SN | Grading, Drainage, aggregate base, bituminous pavement. | 4R Reconstruction, Added Capacity | 04/27/2010 | 04/28/2010 | 09/30/2012 | 248975 | 0.39
11249 | (BIA) IRR | BAYFIELD, WI |  | 07 | F55435SB | Survey Design Project. Archeology and Administration added as part of Modification #1 (3/31/2010). Construction of Blueberry Road added as part of Modification #3 (6/22/2010). | Preliminary Engineering | 02/24/2010 | 03/01/2010 | 04/30/2010 | 90000 | 6
11250 | (BIA) IRR | BURNETT, WI |  | 7 | F55436SA | Road rehabilitation | 4R Reconstruction, No Added Capacity | 06/09/2010 | 06/16/2010 | 09/30/2010 | 290628 | 0.84
11251 | (BIA) IRR | SHAWANO, WI |  | 08 | F55438SD | Resurfacing of existing roadway | 4R Resurfacing | 05/24/2010 | 06/01/2010 | 09/30/2012 | 738842 | 5.07
11252 | (BIA) IRR | REDWOOD, MN |  | 07 | F57402SD | IRR Maintenance Activities. | 4R Restoration and Rehabilitation | 06/30/2010 |  |  | 326500 | 162.5
11253 | (BIA) IRR | GOODHUE, MN |  | 02 | F57403SD | IRR Road Maint. Activities | 4R Restoration and Rehabilitation | 07/15/2010 | 07/15/2010 | 09/30/2012 | 281667 | 9.8
11254 | (BIA) IRR | SCOTT, MN |  | 02 | F57411SA | Construction of road. | New Construction Roadway | 03/01/2010 | 04/05/2010 | 09/30/2012 | 1104742 | 1.982
11255 | (BIA) IRR | MENOMINEE, WI |  | 8 | F58440SC | Re-Construction and resurfacing of the existing roadway | 4R Reconstruction, Added Capacity | 06/24/2010 | 06/01/2010 | 09/30/2012 | 833752 | 1.9
11256 | (BIA) IRR | ISABELLA, MI |  | 4 | F60472SB | Rehabilitation | 4R Resurfacing | 09/21/2009 | 08/16/2009 | 12/31/2010 | 540000 | 0.3
11257 | (BIA) IRR | ISABELLA, MI |  | 4 | F60472SC | Rehabilitation | 4R Resurfacing | 09/21/2009 | 08/16/2009 | 12/31/2010 | 270000 | 8.47
11258 | (BIA) IRR | GOGEBIC, MI |  | 01 | F6047307 | Cooperative Agreement: Construction & CE utilizing funds originally planned for F604735A & F60473SC. | 4R Resurfacing | 09/14/2009 | 09/01/2009 | 10/31/2009 | 379305 | 2.02
11259 | (BIA) IRR | EMMET, MI |  | 1 | F60483SA | HMA milling and resurface. | 4R Restoration and Rehabilitation | 12/15/2009 | 05/24/2010 |  | 598660 | 3.03
11260 | (BIA) IRR | EMMET, MI |  | 1 | F60483SB | HMA milling and resurface. | 4R Restoration and Rehabilitation | 12/15/2009 | 05/17/2010 |  | 525502 | 0
11261 | (BIA) IRR | EMMET, MI |  | 1 | F60483SD | HMA Crush and Shapine, HMA Paving, Intersection Improvements, shoulders, restoration work and pavement markings. | Preliminary Engineering | 12/15/2009 | 05/17/2010 |  | 55000 | 1.65
11262 | (BIA) IRR | OTTAWA, OK |  | 02 | G04FER07 | S680 Road - Preparation of of plans, specifications, and estimates (PS&E), traffic, and related studies including field inspections, surveys, material testing, and borings. | 0ther | 12/11/2009 | 12/11/2009 |  | 533443 | 4.7
11263 | (BIA) IRR | OTTAWA, OK |  | 02 | G04FER14 | Wyandotte Road - Reconstruction of 0.25 miles of 2" thick or more bituminous material from Highway 60 north to Tribal Boundary. | 4R Reconstruction, No Added Capacity | 02/18/2010 | 03/31/2010 | 12/31/2010 | 222990 | 0.25
11264 | (BIA) IRR | OTTAWA, OK |  | 2 | G04FER24 | Bridge Design - The pre-engineering portion includes surveying, right-of-way, acquisition, roadway and bridge design. | Preliminary Engineering | 05/17/2010 |  |  | 206632 | 0
11265 | (BIA) IRR | OTTAWA, OK |  | 02 | G04FER37 | BIA Route 120 - Preparation of of plans, specifications, and estimates (PS&E), traffic, and related studies including field inspections, surveys, material testing, and borings. | Preliminary Engineering | 05/24/2010 |  |  | 103911 | 0
11266 | (BIA) IRR | OKMULGEE, OK |  | 02 | G07FER19 | Gun Club West - Resurfacing beginning at intersection of old highway 75 and Gun Club Road, runs 1 mile east to Highway 75. 2" or more bituminous material with last 3,000 feet of curb and gutter | 4R Resurfacing | 04/01/2010 |  |  | 497730 | 1
11267 | (BIA) IRR | MUSKOGEE, OK |  | 02 | G07FER20 | Old Highway 69 South - McIntosh - Overlay. Starting at the Muskogee/McIntosh County line approximately 5 miles north of Checotah, then 10.59 miles to entrance of New Highway 69 and old 69. | 4R Resurfacing | 05/17/2010 |  |  | 2967233 | 10.6
11268 | (BIA) IRR | MCINTOSH, OK |  | 02 | G07FER21 | Old Highway 69 - S. of Checotah - Overlay. Starting at the intersection of E1140 Road and Old 69 Highway then north 6.55 miles till insects with I-40 bridge S of Checotah. | 4R Resurfacing | 04/01/2010 | 04/26/2010 |  | 1916597 | 0
11269 | (BIA) IRR | SEMINOLE, OK |  | 05 | G10FER10 | Signing Project - Installing Road Signs throughout the Seminole Nation. | Safety | 03/05/2010 |  |  | 222358 | 0
11270 | (BIA) IRR |  |  | 07 | H51A040 | Grade, drain, aggregate base, hot asphalt conrete pavement, and pavement markings | New Construction Roadway | 08/02/2010 |  |  | 720000 | 0.7
11271 | (BIA) IRR |  |  | 01 | H52A0100 | Grade, drain, remove and dispose of existing bituminous pavement, construct pcc sidewalk, curb & gutter, place aggregate base, asphalt concrete pavement and pavement markings on 0.989 miles | New Construction Roadway | 05/24/2010 | 06/05/2010 | 09/21/2010 | 667829 | 1
11272 | (BIA) IRR |  |  | 07 | H54A0100 | Grade, drain, place aggregate base, double chip seal coat, construct dip sections, final fog seal and pavement markings on 2.846 miles | New Construction Roadway | 06/11/2010 | 06/06/2010 | 10/07/2010 | 1414457 | 2.8
11273 | (BIA) IRR |  |  | 01 | H65A0100 | Mill existing asphalt pavement, grade subgrade, place aggregate base leveling course, asphalt concrete pavement, asphalt rubber chip seal,... | 4R Reconstruction, No Added Capacity | 04/12/2010 | 06/05/2010 | 08/10/2010 | 1074788 | 0.9
11274 | (BIA) IRR | THURSTON, WA |  | 3 | P06013R1 | Joint project where tribe will provide the ARRA funds to the primary sponsor of the project (Thurston County) for specific asphalt items. | 4R Reconstruction, No Added Capacity | 02/22/2010 |  |  | 212395 | 0
11275 | (BIA) IRR |  |  | 06 | P06028R1 | Rehabilitation of Roadway and Drainage Improvements | 4R Resurfacing | 07/15/2010 | 07/19/2010 |  | 190755 | 0.44
11276 | (BIA) IRR |  |  | 06 | P06040R1 | Installation of guardrail | Safety | 01/14/2010 | 04/29/2010 |  | 92172 | 0.22
11277 | (BIA) IRR |  |  | 06 | P06801R1 | Installation of precast concrete culvert | 4R Reconstruction, No Added Capacity | 05/21/2010 |  |  | 141713 | 0.2
11278 | (BIA) IRR |  |  | 06 | P06911R1 | Final Design and environmental permitting for access improvements from SR 101 to the Lower Elwha Health Clinic | Preliminary Engineering | 02/08/2010 | 02/08/2010 |  | 107294 | 0.32
11279 | (BIA) IRR | UMATILLA, OR |  | 2 | P07700R | Construct 0.63 miles of new, double lane paved access road to the new Tribal governance center and associated parking lots. | New Construction Roadway | 09/29/2009 | 10/05/2009 |  | 800250 | 0
11280 | (BIA) IRR |  |  | 23 | S5030728 | Design of Iroquois Dr. Work to include new granular sub base, asphalt pavement, ditch regrading, and drainage improvement. | 4R Reconstruction, No Added Capacity | 03/26/2010 | 03/26/2010 | 06/30/2010 | 66000 | 0.25
11281 | (BIA) IRR |  |  | 02 | S5031907 | Design of Maliseet Dr overlayment. | 4R Resurfacing | 10/26/2009 | 11/04/2009 | 09/30/2010 | 54083 | 0.4
11282 | (BIA) IRR |  |  | 03 | S5039708 | Construction of Magnolia Drive, Market Lane, and Raintree Parking "A" (MMR) | 4R Reconstruction, No Added Capacity | 03/26/2010 |  |  | 966304 | 0.6
11283 | (BIA) IRR |  |  | 02 | S5051803 | Rehabilitation Drainage improvement, and safe passage | 0ther | 12/16/2009 |  | 09/30/2010 | 428766 | 5.86
11284 | (BIA) IRR |  |  | 010 | S5053003 | Provide engineering services required for the development of construction plans specifications and engineers estimate (PS&E) to facilitate new construction of 0.15 miles of BIA Route 2505-10 & 0.12 mi | New Construction Roadway | 04/27/2010 | 04/27/2010 | 12/31/2010 | 142185 | 0.27
11285 | (BIA) IRR |  |  | 5 | S5053207 | Design of Rivercrest Rd - Phase 3. Work includes the design of a bridge, approaches and sevral hundred feet of roadway to connect to Phase 1. | New Construction Roadway | 04/13/2010 | 04/13/2010 | 08/13/2011 | 125594 | 0.96
11286 | (BIA) IRR |  |  | 05 | S5053611 | Design | New Construction Roadway | 12/11/2009 | 12/11/2009 | 09/30/2010 | 35000 | 0.2
11287 | (BIA) IRR |  |  | 02 | S50ARA13 | Design of Summit Drive | New Construction Roadway | 03/25/2010 | 03/25/2010 |  | 30000 | 0.2
11288 | (BIA) IRR |  |  | 1 | S50FER01 | Design of Reconstruction and Overlay | 4R Reconstruction, No Added Capacity | 01/28/2010 | 02/24/2010 | 04/30/2010 | 75000 | 0.2
11289 | Federal Lands Eastern Division | JOHNSON, AR |  | 3 | 1515050653007 | Reconstruct 1.4 miles of Arkansas Route 215 in the Ozark National Forest, Johnson County, Arkansas. Work includes grading, aggregate base, asphalt paving, drainage, curb and gutter, retaining walls, | 4R Reconstruction, No Added Capacity | 02/08/2010 | 02/08/2010 |  | 807252 | 0
11290 | Federal Lands Eastern Division | DISTRICT OF COLUMBIA, DC |  | 98 | 1515113400014 | Rehabilitate Ohio Drive and Old Constitution Avenue. | 4R Restoration and Rehabilitation | 04/12/2010 | 04/12/2010 |  | 2305695.5 | 0
11291 | Federal Lands Eastern Division | WINSTON, MS |  | 3 | 1515280301002 | The Tombigbee National Forest is located in Choctaw County in Mississippi. This project consists of the full depth reconstruction and widening of Forest Highway 30 between Choctaw Lake and Forest Hig | 4R Restoration and Rehabilitation | 03/10/2010 | 03/10/2010 |  | 430771 | 0
11292 | Federal Lands Eastern Division | HYDE, NC |  | 3 | 1515370MTK001 | Located in Hyde County, NC, the project will repair of two canal bridges, and resurface Lake Landing Road. The refuge had 90,000 visitors last year. | Bridge Replacement, No Added Capacity | 02/15/2010 | 02/15/2010 | 12/01/2010 | 856788.2 | 0
11293 | Federal Lands Eastern Division | ANSON, NC |  | 0 | 1515370PED001 | The project consists of the rehabilitation of Wildlife Drive (Route 010), Sullivan Pond Road (Route 011), Ross Road (Route 101), and three parking areas within the Pee Dee National Wildlife Refuge. T | 4R Restoration and Rehabilitation | 03/01/2010 | 03/01/2010 |  | 767773.85 | 0
11294 | Federal Lands Eastern Division | PIKE, PA |  | 10 | 1515424320017 | The primary purpose of this project is to replacement Toms Creek Bridge along US Route 209. The work will include rehabilitation of US Route 209 from MP 4.3 to 5.3 including milling off the asphalt pa | Bridge Replacement, No Added Capacity | 03/01/2010 | 10/01/2009 | 10/01/2010 | 2042863.84 | 0
11295 | Federal Lands Eastern Division | CLARENDON, SC |  | 6 | 1515450SNT001 | Located in Clarendon County, SC, the project will rehabilitate Center Road and Wildlife Drive, key access points serving thousands of motorists annually. The refuge is home to endangered species like | 4R Restoration and Rehabilitation | 06/30/2009 | 06/30/2009 | 05/01/2010 | 1304442.75 | 0
11296 | Federal Lands Eastern Division | STEWART, TN |  | 8 | 1515470CRK001 | Located 75 miles NW of Nashville, TN, the project will upgrade Routes 12, 102, 104, and 105. The refuge, which receives 45,000 visitors annually, is a feeding and resting area for migratory birds and | 4R Restoration and Rehabilitation | 03/16/2010 | 03/16/2010 | 12/01/2010 | 871975 | 0
11297 | Federal Lands Eastern Division | BLOUNT, TN |  | 2 | 1515471220011 | The purpose of this project is to continue construction of "Missing Link" in the Foothills Parkway. The work will include the construction of one bridge (~800 feet ) and the construction of the roadwa | Bridge, New Construction | 05/21/2009 | 05/21/2009 | 12/01/2011 | 25301043.58 | 0
11298 | Federal Lands Eastern Division | FAIRFAX, VA |  | 8 | 1515513300049 | The primary purpose of this project is to generally rehabilitate three paved parking lots and the park access road at Daingerfield Island. The areas served include an active sailing marina and boat st | 4R Restoration and Rehabilitation | 06/01/2010 | 06/01/2010 |  | 452477 | 0
11299 | Federal Lands Eastern Division | YORK, VA |  | 0 | 1515514290011 | The purpose of this projects is to rehabilitate five bridges within Colonial National Historical Park - Beaverdam Creek Bridge, Yorktown Creek Bridget, Powhatan Creek Bridget, and College Creek Bridge | Bridge Rehabilitation, No Added Capacity | 06/30/2009 | 06/30/2009 |  | 165524 | 0
11300 | Federal Lands Eastern Division | FAIRFAX, VA |  | 11 | 151551FFXPK05 | Phase IV of the Fairfax County Parkway Project consists of the construction of the Boudinot Drive Interchange. This new interchange will provide full access to the Parkway from the Fullerton Industri | New Construction Roadway | 06/29/2009 | 06/29/2009 | 12/01/2011 | 22800000 | 0
11301 | Federal Lands Eastern Division | FAIRFAX, VA |  | 11 | 151551FFXPK06 | Phase III of the Fairfax County Parkway Project is the final segment required to complete the mainline Parkway. The project consists of constructing approximately 0.5 miles of 4-lane divided limited | New Construction Roadway | 01/25/2010 | 01/25/2010 | 01/26/2010 | 22960459 | 0
11302 | Federal Lands Eastern Division | PENDLETON, WV |  | 2 | 1515540972001 | The Monongahela National Forest is located in Grant and Pendleton Counties in West Virginia. This project consists of paving a portion of Smoke Hole Road. The total construction length is 0.8 miles. | 4R Resurfacing | 04/01/2010 | 04/01/2010 |  | 354775.79 | 0
11303 | Federal Lands Eastern Division | RÍO GRANDE, PR |  | 0 | 1515720003001 | Repair slide on Route 9966 in the El Yunque National Forest | 4R Resurfacing | 01/25/2010 | 01/25/2010 |  | 32883 | 0
11304 | Federal Lands Eastern Division | ST. JOHN, VI |  | 0 | 1515785360004 | The primary purpose of this project is to resurface the entire 7.5 miles of North Shore Road along with areas of shoulder reconditioning, drainage improvements, stone masonry edging at selected pull-o | 4R Reconstruction, Added Capacity | 09/28/2009 | 09/28/2009 | 12/01/2010 | 1397391.4 | 0
11305 | Federal Lands Eastern Division | ST. THOMAS, VI |  | 0 | 151578LONGBAY | Reconstruct and widen 0.28 miles of Long Bay Road from Veteran's Drive to Centerline Road on St. Thomas, USVI. | 4R Reconstruction, Added Capacity | 11/16/2009 | 11/16/2009 |  | 5537155 | 0
11306 | Federal Lands Eastern Division | NOXUBEE, MS |  | 3 | 15B5280NXB001 | This project consists of the rehabilitation of 18.2 miles of Bluff Lake Road, Brooksville-Louisville Road, and Section Line Road in Noxubee and Winston Counties, Mississippi. Bluff Lake Road and Broo | 4R Resurfacing | 06/19/2009 | 06/19/2009 | 08/01/2011 | 1438282.16 | 0
11307 | Federal Lands Central Division | APACHE, AZ |  | 01 | 1516040431003 | Near Eagar Arizona, install pavement over a previously constructed gravel road surface on Forest Highway 43 from the West Baldy Parking Area (8.5 miles south of State Highway 260) to the intersection | 4R Resurfacing | 07/06/2009 | 07/06/2009 | 11/01/2009 | 3386212.19 | 16.2
11308 | Federal Lands Central Division | APACHE, AZ |  | 01 | 1516040431004 | {Project Description} | 4R Resurfacing | 01/10/2010 |  | 10/29/2010 | 941739.89 | 0
11309 | Federal Lands Central Division | COCONINO, AZ |  | 01 | 1516043050003 | Design (provide completed plans, drawings and specifications for) the Depot Tour Bus Parking Area at the South Rim Grand Canyon National Park, Arizona (the plans are currently 10% complete). | Transit | 09/16/2009 |  |  | 74376.53 | 0
11310 | Federal Lands Central Division | NEVADA, CA |  | 04 | 1516061231001 | Remove existing pavement and repave approximately 5 miles of Washington Road from the intersection of SR 20 to a point just south of the town of Washington. | 4R Restoration and Rehabilitation | 05/28/2009 | 06/29/2009 | 11/01/2009 | 4651073.51 | 10.58
11311 | Federal Lands Central Division | EL DORADO, CA |  | 04 | 1516061371004 | On Wentworth Springs Road (in El Dorado County, California) remove the existing pavement and repave approximately 5 miles of roadway from mile post 1.30 to mile post 6. | 4R Restoration and Rehabilitation | 08/07/2009 | 08/10/2009 | 12/01/2009 | 2498849.27 | 10.76
11312 | Federal Lands Central Division | MONO, CA |  | 25 | 1516061381001 | The project is to rehabilitate, restore, and resurface the existing roadway pavement. The project work includes minor grading, drainage, pulverization, aggregate base and HACP. Road construction is | 4R Resurfacing | 06/14/2010 |  | 11/15/2010 | 4922880 | 0
11313 | Federal Lands Central Division | MARIPOSA, CA |  | 19 | 1516063401501 | Remove existing pavement and repave approximately 5.05 miles of roadway, and 2.17 lane miles of paved parking, in Yosemite National Park. The project includes the roadway from Chinquapin intersection | 4R Restoration and Rehabilitation | 06/02/2009 | 06/03/2009 | 11/30/2009 | 8998109.73 | 5.5
11314 | Federal Lands Central Division | MARIPOSA, CA |  | 19 | 1516063414004 | The Wawona Road project consists of pulverizing and overlaying 24.4 miles of Wawona Road (Highway 41) through Yosemite National Park. The scope of work includes pulverizing 8" of existing road and ov | 4R Resurfacing | 05/03/2010 |  | 11/08/2009 | 6528563.25 | 0
11315 | Federal Lands Central Division | INYO, CA |  | 25 | 1516063901102 | Pulverize roadway and overlay with asphalt pavement, and install drainage culverts on approximately 33.3 mile of the Bonnie Claire Road from mile post 7.4 at the junction of Ubehebe Crater Road to mil | 4R Restoration and Rehabilitation | 07/30/2009 | 08/17/2009 | 05/30/2010 | 12405855.53 | 33.3
11316 | Federal Lands Central Division | DEL NORTE, CA |  | 01 | 1516064710201 | Pulverize existing pavement and overlay with new pavement, and install new draininage ay pavement and drainage structures on approximately 2.18 miles of two-lane roadway between Costal Drive and Klama | 4R Restoration and Rehabilitation | 05/13/2009 | 05/18/2009 | 10/30/2009 | 3214936.96 | 2.1
11317 | Federal Lands Central Division | MONTEZUMA, CO |  | 03 | 1516080301009 | At Mesa Verde National apark in Colorado, remove existing pavement and repave the main entrance road from the Park entrance at Highway 160 to the Park Point Overlook. The project also includes adding | 4R Restoration and Rehabilitation | 06/15/2009 | 06/24/2009 | 08/30/2010 | 11956819.51 | 19.6
11318 | Federal Lands Central Division | CLEAR CREEK, CO |  | 02 | 1516088012023 | Recondition, regrade and pave approximately seven (7) miles of existing aggregate and chip seal surface on Guanella Pass, near Georgetown, Colorado. This work is near the boundary of Clear Creek and | 4R Reconstruction, Added Capacity | 07/07/2008 | 08/06/2009 | 10/01/2010 | 4590608.76 | 26.429
11319 | Federal Lands Central Division | RIO GRANDE, CO |  | 03 | 1516088501002 | Recondition and resurface the existing one-way loop road with aggregate (gravel) surfacing. Construct better defined boundaries for existing pullouts, create additional small pullouts where there is | 4R Resurfacing | 08/10/2009 | 08/10/2009 | 09/01/2009 | 292277.38 | 2.5
11320 | Federal Lands Central Division | SIOUX, NE |  | 06 | 1516310071004 | Design a box culvert drain structure and resurface approximately 1 mile of roadway. | Preliminary Engineering | 09/11/2009 | 09/11/2009 |  | 79132 | 0.3
11321 | Federal Lands Central Division | WASHOE, NV |  | 02 | 1516320002001 | Construct a left turn lane and acceleration/deceleration lanes for the Galena Recreation Facilities at approximately mile post 18 on State Highway 28. | 4R Reconstruction, Added Capacity | 05/05/2010 |  | 07/01/2010 | 834635.96 | 1.06
11322 | Federal Lands Central Division | CLARK, NV |  | 03 | 1516322800109 | Rehabilitate roadway pavement and drainage structures on approximately 17.5 miles of the Northshore Road from the Redstone Parking Area to the North Park Boundary. | 4R Restoration and Rehabilitation | 11/02/2009 |  | 08/29/2010 | 7113052.99 | 17.5
11323 | Federal Lands Central Division | DENVER, CO |  | 01 | 1516350057101 | Develop design drawings and specifications, including environmental studies and clearances, for the replacement of six small bridges in Cibola National Forest in New Mexico state. | Preliminary Engineering | 05/13/2009 | 05/13/2009 | 03/01/2010 | 539949.02 | 0
11324 | Federal Lands Central Division | SANDOVAL, NM |  | 03 | 1516350121006 | Contract modification to existing project between Cuba and LaCueva, NM, to add roadway drainage improvements to protect the roadway and to enhance stream water quality. | Environmental Only | 06/29/2009 | 06/29/2009 | 07/18/2009 | 700000 | 0
11325 | Federal Lands Central Division | DENVER, CO |  | 01 | 1516350121009 | Design services for the development of 100% plan set on project NM 12-1(9) and 70% set plan development on NM PFH12-1(10) for the reconstruction and paving of an existing | Preliminary Engineering | 06/29/2009 | 06/30/2009 | 09/01/2011 | 1138149.98 | 0
11326 | Federal Lands Central Division | MCKENZIE, ND |  | 01 | 1516381701003 | This project involves the removal of the existing asphalt pavement and replacement with new asphalt pavement on 13.8 miles of roadway within the North Unit of Theodore Roosevelt National Park. | 4R Restoration and Rehabilitation | 06/04/2009 | 06/07/2009 | 10/30/2009 | 7811767.13 | 13.8
11327 | Federal Lands Central Division | WARD, ND |  | 01 | 1516383040111 | Recondition and resurface Route 11, Lower Lake Road (at Des Lacs National Wildlife Refuge, in North Dakota) to a uniform width of 22 feet and regravel. Additionally, Lower Lake Parking 1 will be regr | 4R Resurfacing | 07/06/2009 | 07/28/2009 | 08/01/2009 | 772728.16 | 1.03
11328 | Federal Lands Central Division | MCHENRY, ND |  | 01 | 1516383111201 | Reconstruction of two bridges (Willow Creek and Johnson bridges). One bridge location will include a small parking area adjacent to it for canoe access to the river. | Bridge Replacement, No Added Capacity | 09/30/2009 |  | 06/30/2010 | 478239.6 | 0.26
11329 | Federal Lands Central Division | MURRAY, OK |  | 04 | 1516405721502 | Pave 0.87 miles of trails adjacent to Route 215. | 0ther | 07/14/2010 |  | 10/27/2010 | 14010.14 | 0
11330 | Federal Lands Central Division | PENNINGTON, SD |  | 01 | 1516460171006 | The project constructs pedestrian and bicycle overpasses and associated approaches at two locations on this route between Hill City and Lead. | Facilities for Pedestrians and Bicycles | 04/19/2010 |  | 08/16/2010 | 595110 | 1.6
11331 | Federal Lands Central Division | SEVIER, UT |  | 03 | 1516490391003 | Construct asphalt pavement surfacing on a previously constructed gravel surface on Forest Highway 39 from 5.1 miles south of I-70 (the end of the existing pavement) to the Gooseberry Administrative Si | 4R Resurfacing | 06/24/2009 | 07/07/2009 | 09/01/2009 | 1961852 | 10.2
11332 | Federal Lands Central Division | FREMONT, WY |  | 01 | 1516560231003 | Recondition the existing aggregate surfacing and roadbed by scarifying and reshaping to provide for consistent cross slopes and width. The roadway will then be resurfaced with a new aggregate surface | 4R Resurfacing | 09/09/2009 | 08/19/2009 | 10/31/2009 | 959408.75 | 19
11333 | Federal Lands Central Division | CARBON, WY |  | 01 | 1516560261901 | Construction of two (2) small drainiage structures (box culverts) on Wyoming State Route 71, including grading, draining, and paving along the existing alignment to facilitate installation of 2 draina | 4R Reconstruction, No Added Capacity | 06/30/2009 |  | 10/01/2009 | 1057995.01 | 1
11334 | (CFL) NPS | APACHE, AZ |  | 01 | 1516045501002 | Rehabilitate drainage and pavement on the South Rim Drive (route 10) (also known as N7, Navajo route 7) and spur roads off of Route 10 to White House, Spider Rock, Tunnel, and Tsegi overlooks. Spurs | 4R Resurfacing | 06/10/2010 |  | 12/03/2010 | 427.97 | 0
11335 | (CFL) NPS | INYO, CA |  | 25, 41, 45 | 1516062008001 | Construct chip seals on routes within Death Valley National Park, Joshua Tree National Park, and Lake Mead National Recreation Area. | 4R Resurfacing | 12/03/2009 | 02/01/2010 | 06/22/2010 | 7700781.23 | 14.55
11336 | (CFL) NPS | SHASTA, CA |  | 02 | 1516063201003 | Pulverize the existing pavement and repave approxmately 35 kilometers of roadway on Lassen Park Road in Lassen Volcanic National Park, Shasta County, California. | 4R Restoration and Rehabilitation | 08/26/2009 |  | 11/15/2010 | 19019.11 | 22
11337 | (CFL) NPS | INYO, CA |  | 25 | 1516063910901 | Pulverize and overlay (repave) approximately 6 miles of roadway on Bonnie CLair Road in Death Valley. Reconstruct the Ubehebe Crater Overlook parking area, including new pavement, curb, gutter and si | 4R Restoration and Rehabilitation | 10/13/2009 |  | 03/19/2010 | 3656529.9 | 6.2
11338 | (CFL) NPS | GRAND, CO |  | 02 | 1516080601005 | Project involves pulverizing the existing pavement and repaving approximately 17 kilometers of roadway, and two campgrounds, on Trail Ridge Road in Rocky Mountain National Park, Grand County, Colorado | 4R Restoration and Rehabilitation | 04/23/2009 | 04/24/2009 | 09/18/2009 | 7546196.4 | 10.787
11339 | (CFL) NPS | CLARK, NV |  | 03 | 1516322800109 | Pulverize the existing pavement and repave approximately 17.5 miles of the Northshore Road, in Lake Mead National Recreation Area, between mile posts 27.3 and 47.6. | 4R Restoration and Rehabilitation | 11/02/2009 |  | 08/29/2010 | 7113052.99 | 23.7
11340 | (CFL) NPS | SANTA FE, NM |  | 03 | 1516351520001 | Rehabilitate various campgrounds, residential areas and maintenance areas in Bandelier National Monument, New Mexico. The project also improves drainage and provides for the construction of new sewer | 0ther | 06/10/2010 |  | 10/01/2010 | 136187.52 | 10.78
11341 | (CFL) NPS | PENNINGTON, SD |  | 01 | 1516460701005 | The project includes the removal of the existing asphalt pavement and replacement with new aspahlt pavement and the installation of new roadway drainage features for 14.5 miles of roadway within the B | 4R Restoration and Rehabilitation | 09/23/2009 |  | 11/15/2010 | 8290885.05 | 14.552
11342 | (CFL) NPS | KANE, UT |  | 02 | 15J6082008002 | Construct seal coats (chip seals and slurry seals) on most paved surfaces in Glen Canyon National Recreation Area. This recreation area lies in Northern Arizona and Southern Utah. The project has ne | 4R Resurfacing | 04/21/2010 |  | 10/01/2010 | 4326936.02 | 0
11343 | (CFL) NPS | COCONINO, AZ |  | 02 | 15K6082008002 | Construct seal coats (chip seals and slurry seals) on the paved surfaces within the North Rim Grand Canyon National Park. The project has approximately 430,000 square yards of chip seal and 70,000 sq | 4R Resurfacing | 05/13/2010 |  | 09/03/2010 | 1568407 | 0
11344 | (CFL) NPS | PIMA, AZ |  | 01,07,08 | 15L6082008002 | Construct chipseals on all routes within Canyon De Chelly, Chiricahua, Fort Bowie, Organ Pipe, Saguaro, Tonto, and Tumacacori National Monuments. | 4R Resurfacing | 09/24/2009 |  | 11/20/2009 | 4466075.56 | 0
11345 | (CFL) BLM | MOHAVE, AZ |  | 02 | 1516049300001 | Add a paved right turn lane to US Highway 93 at the driveway to the Monolith Gardens Trailhead | 4R Resurfacing | 02/23/2010 |  |  | 63962.33 | 0
11346 | (CFL) BLM | ALPINE, CA |  | 03 | 1516060660001 | Add a new layer of asphalt to the Indian Creek Access Road, Campground Loop and Boat Parking Lot. | 4R Resurfacing | 12/10/2009 | 12/10/2009 | 09/27/2010 | 52103.1 | 0
11347 | (CFL) BLM | FRESNO, CA |  | 20 | 1516061900601 | Add gravel to 8 miles of road in Panoche Management Area | 4R Resurfacing | 01/21/2010 |  | 08/20/2010 | 906476 | 0
11348 | (CFL) BLM | MONTEREY, CA |  | 17 | 1516061904101 | Add gravel to 5 miles of various roads and replace the bridge over El Toro Creek with a low water crossing within the Ft. Ord Management Area. | Bridge Replacement, No Added Capacity | 01/21/2010 |  | 08/20/2010 | 83204.5 | 5
11349 | (CFL) BLM | MONTEREY, CA |  | 17 | 1516061904301 | Replace 25 culverts in Ft. Ord Management Area | 4R Restoration and Rehabilitation | 01/21/2010 |  | 08/20/2010 | 30241.82 | 0
11350 | (CFL) BLM | LASSEN, CA |  | 04 | 1516062376001 | Replace the 90 foot portion of the Bizz Johnson Trail Bridge Number 9 that burned in the Devil's Incident Fire in 2000. | Bridge Rehabilitation, No Added Capacity | 01/21/2010 |  | 10/08/2010 | 1515824.14 | 0
11351 | (CFL) BLM | LAKE, CA |  | 01 | 1516065403001 | Add gravel and pave 2 miles of Mendo Lake Road. | 4R Resurfacing | 01/21/2010 |  | 08/20/2010 | 63206.77 | 2
11352 | (CFL) BLM | CHURCHILL, NV |  | 02 | 1516323133001 | Pave 1.4 miles of Sand Mountain Access Road. | 4R Resurfacing | 12/10/2009 | 12/10/2009 |  | 80797.55 | 1.4
11353 | (CFL) BLM | SANDOVAL, NM |  | 03 | 1516351011001 | Pave 4.69 miles of Tent Rocks Road | 4R Resurfacing | 02/23/2010 |  | 10/01/2010 | 117730.1 | 0
11354 | (CFL) BLM | FREMONT, WY |  | 01 | 1516562302001 | Construct gravel surfacing on Hudson Atlantic Road in Wyoming. | 4R Resurfacing | 09/30/2009 |  | 06/30/2010 | 1174414.74 | 16
11355 | (CFL) BLM | CARBON, WY |  | 01 | 1516563301001 | Construct gravel surfacing on Bridger Pass and Barrel Springs Roads in Wyoming. | 4R Resurfacing | 09/14/2009 | 09/15/2009 | 12/01/2009 | 1561589.19 | 17.3
11356 | (CFL) BLM | SWEETWATER, WY |  | 01 | 1516564115001 | Construct gravel surfacing on Sand Dunes Recreation Site and White Mountain Petroglphs Roads. | 4R Resurfacing | 02/08/2010 |  | 05/30/2010 | 292286.16 | 0
11357 | (CFL) BLM | SUBLETTE, WY |  | 01 | 1516565201001 | Construct gravel surfacing on Upper Green and Scab Creek Roads. | 4R Resurfacing | 05/28/2010 |  | 09/15/2010 | 1801.67 | 0
11358 | (CFL) BOR | LA PAZ, AZ |  | 07 | 1516040090001 | Replace the bridge deck on the Lower Cibola Bridge. The bridge spans across the Colorado River between Arizona and California and is located in the Cibola National Wildlife Refuge, approximately 24 m | Bridge Rehabilitation, No Added Capacity | 02/23/2010 |  |  | 199932.47 | 0
11359 | Federal Lands Western Division | ALEUTIANS EAST, AK |  | 00 | 1517020200501 | This project involves upgrading about 4.3 miles of the local street system in the City of King Cove, including a new bridge or fish passage culverts over Ram Creek. The upgrades consist of constructi | 4R Reconstruction, Added Capacity | 09/01/2009 | 09/01/2009 |  | 1500000 | 0
11360 | Federal Lands Western Division | PRINCE OF WALES-OUTER KETCHIKAN, AK |  | 00 | 1517020440008 | In an effort to protect Tongass National Forest's streams and wildlife from impacts from exposed natural occurring acid rock; this project will cleanup affected areas, replace culverts, and buffer the | 0ther | 07/01/2009 | 07/01/2009 | 05/31/2010 | 1766392.81 | 0.944
11361 | Federal Lands Western Division | PRINCE OF WALES-OUTER KETCHIKAN, AK |  | 00 | 1517020440009 | This second project along Alaska's Coffman Cove Road will pave the 4.3 mile section of road within Tongass National Forest after the Acid Rock cleanup project AK PFH 44(8) is complete. | 0ther | 07/01/2009 | 07/01/2009 |  | 2253006.19 | 3.244
11362 | Federal Lands Western Division | DENALI, AK |  | 00 | 1517020701027 | This project will reconstruct unsafe road sections along Denali's National Park tour route enhancing the safety of Alaska's national park visitors. | 4R Reconstruction, No Added Capacity | 07/01/2009 | 07/01/2009 | 10/01/2010 | 2520061.15 | 9
11363 | Federal Lands Western Division | VALDEZ-CORDOVA, AK |  | 00 | 1517022003003 | Development of a 12 mile road to the Shotgun Cove ending at Decision Point. Approximately the first 2.7 miles (sections 1 and 2) is a pioneer road. Currently, an environmental assessment is being co | 4R Resurfacing | 09/01/2009 | 09/01/2009 |  | 3500000 | 0
11364 | Federal Lands Western Division | RAVALLI, MT |  | 00 | 1517300780001 | Improving visitor safety to our national forest, this project will preserve the pavement on 14.5 miles of Montana's East Fork Bitterroot Road leading into the Bitterroot National Forest. | 4R Reconstruction, No Added Capacity | 07/01/2009 | 07/01/2009 |  | 4682444 | 0
11365 | Federal Lands Western Division | FLATHEAD, MT |  | 00 | 1517302601031 | Reconstruct portion of the Going to the Sun Road in Glacier National Park Phase. | 4R Reconstruction, No Added Capacity | 08/01/2009 | 08/01/2009 | 10/31/2011 | 16702343.1 | 0
11366 | Federal Lands Western Division | FLATHEAD, MT |  | 00 | 1517302610023 | The work being performed on this project will reconstruct a portion of the multphase historic Going to the Sun Road project, providing access to Glacier National Park's spectacular scenery and ultimat | 4R Reconstruction, No Added Capacity | 06/08/2009 | 06/08/2009 | 07/01/2011 | 19229200.32 | 2.8
11367 | Federal Lands Western Division | GRAYS HARBOR, WA |  | 06 | 1517532080002 | This project, continuation of phase 1, fully reconstructs the remaining 7 miles of road providing improved access the Olympic National Forest in Washington. | 4R Resurfacing | 07/01/2009 | 07/01/2009 | 11/01/2010 | 4446476 | 5
11368 | Federal Lands Western Division | TETON, WY |  | 00 | 1517561601104 | This project will reconstruct and pave 8 miles of Grand Teton National Park roads from Spalding Bay to Jackson Lake Junction, as well as pave Signal Mountain Marina Road providing access of boats to J | 4R Restoration and Rehabilitation | 07/01/2009 | 07/01/2009 | 08/20/2010 | 4063482.65 | 9
11369 | (WFL) FS | LEMHI, ID |  | 02 | 1517166030001 | In an effort to improve safe access for visitors to the Challis National Forest, this project will replace three deteriorating bridges on the upper Salmon River Road: Cove Creek, Pine Creek, and Littl | Bridge Replacement, Added Capacity | 07/01/2009 | 07/01/2009 | 12/06/2009 | 620897.81 | 0
11370 | (WFL) FS | COOS, OR |  | 04 | 1517410330004 | This project will reconstruct road and improve drainage at various sites along 30 miles of Oregon's Agness Road stabilizing the aging road system located in the Sisikiyou National Forest. | 4R Restoration and Rehabilitation | 07/01/2009 | 07/01/2009 | 08/20/2010 | 446337.26 | 21.57
11371 | (WFL) FS | COOS, OR |  | 04 | 1517411376001 | This project will repair the Upper Chetco River Bridge stabilizing the foundation and making structural repairs. These repairs will add years to the life of the bridge and improve safety of visitors | 4R Restoration and Rehabilitation | 07/01/2009 | 07/01/2009 |  | 335194.27 | 0.05
11372 | (WFL) FS |  |  | 03, 04 | 1517532009004 | Western Federal Lands Highway Division will provide design support on this project to replace 9 deficient bridges with fabricated modular structures within the Gifford Pinchot National Forest in Washi | Preliminary Engineering | 07/01/2009 | 07/01/2009 |  | 316884.29 | 0
11373 | (WFL) FS | LEWIS, WA |  | 04 | 1517532009005 | Western Federal Lands Highway Division will prepare a feasibility study to replace Gifford Pinchot National Forest's Jody Mullins Bridge along Forest Road 1270 . The bridge provides access to trailhe | Preliminary Engineering | 07/01/2009 | 07/01/2009 |  | 33573.95 | 0
11374 | (WFL) BLM |  |  | 04 | 1517412009002 | This project replaces eleven 40 year old failing culverts with fish passage compliant culverts. This will improve fish passage for federally listed endangered species to Siuslaw River watershed as we | 4R Reconstruction, No Added Capacity | 07/01/2009 | 07/01/2009 |  | 25000 | 0

## Summary Proceed
As Of August 06, 2010
State | # of Projects | Total ARRA Obligations
(BIA) IRR | 115 | 48058837
(CFL) BLM | 13 | 5943638.07
(CFL) BOR | 1 | 199932.47
(CFL) NPS | 11 | 44824498.75
(HQFL) FS | 1 | 312731
(HQFL) IRR | 24 | 18117996.9
(WFL) BLM | 1 | 25000
(WFL) FS | 5 | 1752887.58
Alabama | 287 | 489468960.49
Alaska | 25 | 166038198
Arizona | 182 | 468713992.14
Arkansas | 117 | 316013259
California | 576 | 1887045759.7
Colorado | 100 | 373201790
Connecticut | 87 | 247335175.1
Delaware | 32 | 112338370.33
District of Columbia | 12 | 85153074.41
Federal Lands Central Division | 27 | 88518333.25
Federal Lands Eastern Division | 18 | 89827553.07
Federal Lands Western Division | 10 | 60663406.22
Florida | 527 | 1103617816
Georgia | 324 | 785601667.85
Hawaii | 17 | 83675973.67
Idaho | 78 | 177066457
Illinois | 734 | 896866968.38
Indiana | 1084 | 645710812.68
Iowa | 233 | 355180297.17
Kansas | 127 | 323230550.32
Kentucky | 101 | 411339904.6
Louisiana | 104 | 401411478.66
Maine | 74 | 132403441
Maryland | 129 | 356800177
Massachusetts | 62 | 256916358.13
Michigan | 719 | 840284719.95
Minnesota | 202 | 490418156.05
Mississippi | 165 | 350072405
Missouri | 314 | 613480693.28
Montana | 81 | 204592481.27
Nebraska | 120 | 226223725
Nevada | 59 | 178831377
New Hampshire | 34 | 129440556
New Jersey | 98 | 541344393
New Mexico | 79 | 229170720.55
New York | 402 | 895356868.53
North Carolina | 371 | 686491899
North Dakota | 160 | 162907352.25
Northern Mariana | 1 | 4500000
Ohio | 377 | 755635037.48
Oklahoma | 266 | 453744903.9
Oregon | 302 | 238652879.35
Pennsylvania | 302 | 992457558.93
Puerto Rico | 21 | 83422320.83
Rhode Island | 64 | 136044519.75
South Carolina | 170 | 429635747.09
South Dakota | 52 | 186302728.65
Tennessee | 311 | 559309681.18
Texas | 424 | 1999059114.99
Utah | 115 | 202818355.28
Vermont | 68 | 120006104.68
Virgin Islands | 3 | 10692498.36
Virginia | 53 | 262411818
Washington | 207 | 455167612.83
West Virginia | 124 | 190386512
Wisconsin | 411 | 521780490.7
Wyoming | 61 | 150186106
Total | 11374 | 23734204632.82