## Introduction
EVCI STRATEGIC GOALS AND TACTICAL ADVANCE TOOL (EVCI-STAT): A TOOL TO EVALUATE THE APPROPRIATENESS OF A PERFORMANCE-BASED PUBLIC-PRIVATE PARTNERSHIP APPROACH TO DELIVER ELECTRIC VEHICLE CHARGING INFRASTRUCTURE
The purpose of the EVCI-STAT tool is to help public agencies develop an effective acquisition process for EV charging infrastructure projects using a public-private partnership (P3). The user should begin the process by completing the separate tool called EVCI-SCREEN to see if an EVCI P3 could be effective for the user's agency. If the EVCI-SCREEN tool indicates that the a P3 could be an appropriate procurement model, the user can complete this EVCI-STAT tool. This tool asks the user to consider whether various strategic goals, tactical approaches, and implementation techniques should be considered or incorporated into the user's EVCI P3 procurement. The tool contains three worksheets or tabs in addition to this introduction: Instructions: Step-by-step instructions for using this tool. Strategic Goals: The main worksheet on which the user responds whether a given strategic goals, tactical approach, or implementation technique is relevant to the user's EVCI P3 procurement. Glossary: A table defining the acronyms and abbreviations used in the tool. Please refer to the Instructions worksheet in this tool and to the accompanying user guide for more complete information to understand this tool.

## Instructions
User Instructions
Step 1: Read the User Guide.
Step 2: Review the acronyms and terms defined on the Glossary worksheet.
Step 3: Proceed to the "Strategic Goals" worksheet. This worksheet guides the user through three different levels of consideration for the user’s agency to use: — Strategic Goals: These represent the main goals for the agency to consider. — Tactical Approaches: These are the approaches the agency could consider to achieve the relevant strategic goal. — Implementation Techniques: These are methods for implementing a given tactical approach.
Step 4: Carefully read each description and select a response (Yes or No) using the dropdown menu as to whether a particular item should be considered during the EVCI procurement process.
Step 5: You can print the results from this worksheet by pressing "Ctrl+P" or using the Print option in Excel's File menu. You may wish to filter out the rows for which you responded "No." Please refer to the user guide for details on how to filter out the rows with "No" responses.
Step 6: Consider using the EVCI Financial Analysis Spreadsheet Tool (EVCI-FAST) to further assist your decision-making process.

## Strategic Goals
ID Number | Goal | Group | Description | To be Considered for the Project? (Select response from drop-down menu.) | Comments or Notes (to be added by user)
1 | Minimize Budgetary Impact | Strategic Goals | Minimize the impact on the public agency budget of EVCI projects - reduce constraints imposed on the public agency’s investment in EV charging infrastructure projects by insufficient funding and limits on the public sector’s debt capacity (i.e., borrowing limit). | Response Option | Enter Text. | Response Option
2 | Minimize Budgetary Impact | Tactical Approaches | Ensure your P3 partners in the private sector clearly understand your agency’s budgetary constraints. | Response Option | Enter Text. | Yes
3 | Minimize Budgetary Impact | Tactical Approaches | Use market forces to establish a competitive bidding environment in which developers propose their most attractive schedule of project costs over the EV charging infrastructure project lifecycle (spread over design and construction [D&C] and O&M phases). | Response Option | Enter Text. | No
4 | Minimize Budgetary Impact | Implementation Techniques | Take advantage of deferred payment mechanisms to enhance the financial position of the public agency in the P3 deal. | Response Option | Enter Text.
5 | Minimize Budgetary Impact | Implementation Techniques | Ensure the proposed schedule of payments to the P3 developer meets the agency’s caps on capital payment, service commencement payment, and availability payments over the O&M phase. (See EVCI-FAST model discussed in the User Guide Section 4). | Response Option | Enter Text.
6 | Expedite Project Delivery | Strategic Goals | Expedite project delivery - Deliver EV charging station projects that would otherwise be delayed due to lack of funding. | Response Option | Enter Text.
7 | Expedite Project Delivery | Tactical Approaches | Incentivize the private sector P3 partners to provide an expedited deployment schedule for EV charging infrastructure P3 projects while holding them accountable for all critical delivery milestones (e.g., apply appropriate performance penalties for not meeting the required deadlines) | Response Option | Enter Text.
8 | Expedite Project Delivery | Implementation Techniques | Evaluate the P3 developer’s proposed schedule for the project and timeline for completion, including the following major milestones: | Response Option | Enter Text.
9 | Expedite Project Delivery | Implementation Techniques | a) Anticipated deadline for execution of the Project Agreement | Response Option | Enter Text.
10 | Expedite Project Delivery | Implementation Techniques | b) Assumed notice to proceed (NTP) for Design and Materials | Response Option | Enter Text.
11 | Expedite Project Delivery | Implementation Techniques | c) Design and Permitting Completion | Response Option | Enter Text.
12 | Expedite Project Delivery | Implementation Techniques | d) Power Utility Service Connection | Response Option | Enter Text.
13 | Expedite Project Delivery | Implementation Techniques | e) Communication/Data Utility Service Connection | Response Option | Enter Text.
14 | Expedite Project Delivery | Implementation Techniques | f) Project site Preparation | Response Option | Enter Text.
15 | Expedite Project Delivery | Implementation Techniques | g) Electric vehicle supply equipment (EVSE) and Associated Hardware Delivery | Response Option | Enter Text.
16 | Expedite Project Delivery | Implementation Techniques | h) EVSE Installation | Response Option | Enter Text.
17 | Expedite Project Delivery | Implementation Techniques | i) Planned Services Commencement Date | Response Option | Enter Text.
18 | Expedite Project Delivery | Implementation Techniques | j) Services Commencement Long Stop Date | Response Option | Enter Text.
19 | Support the Development of EVCI | Strategic Goals | Strategically support the development of convenient, accessible, reliable, and equitable access to publicly available EV charging infrastructure. | Response Option | Enter Text.
20 | Support the Development of EVCI | Tactical Approaches | Incentivize the private-sector P3 partners to bridge the identified gaps in alternative fuel corridors, especially in disadvantaged and rural communities, with the most cost-effective approach for the public. | Response Option | Enter Text.
21 | Support the Development of EVCI | Implementation Techniques | Provide incentives for the P3 partners to select project sites benefiting a disadvantaged community. | Response Option | Enter Text.
22 | Build and Grow the EVCI Industry | Strategic Goals | Build and grow the EV charging industry by establishing P3 partnerships. | Response Option | Enter Text.
23 | Build and Grow the EVCI Industry | Tactical Approaches | Utilize the advantages of the P3 model to provide the first stepping stone to building EV charging stations that should eventually be able to function without subsidies. | Response Option | Enter Text.
24 | Build and Grow the EVCI Industry | Tactical Approaches | Catalyze further investment in EV charging stations across the state where utilization is anticipated, but the private sector may not otherwise be economically motivated to install and operate EV charging stations. | Response Option | Enter Text.
25 | Build and Grow the EVCI Industry | Implementation Techniques | Allocate government funding subsidies as catalysts for developing a sustainable business model that can stand on its own beyond the period of government-subsidized funding. | Response Option | Enter Text.
26 | Connect Effectively with EV Charging Industry | Strategic Goals | Connect effectively with a new and evolving EV charging station industry. | Response Option | Enter Text.
27 | Connect Effectively with EV Charging Industry | Tactical Approaches | Utilize the EVCI Performance-Based P3 model as a platform for the public agency to engage with new or existing industry partners with whom the agency has not interacted for the same services. | Response Option | Enter Text.
28 | Connect Effectively with EV Charging Industry | Implementation Techniques | Use the EVCI Performance-based P3 model as an opportunity for new industry members to get to know the public agency and its requirements for executing projects and for the public agency to be informed about the latest technology trends and emerging practices in the EV infrastructure market. | Response Option | Enter Text.
29 | Shape Environment for Competitive Bidding | Strategic Goals | Shape an attractive environment for competitive bidding in the EV charging infrastructure market. | Response Option | Enter Text.
30 | Shape Environment for Competitive Bidding | Tactical Approaches | Generate competition – A competitive bidding environment would help the public agency accelerate the EV infrastructure deployment program. | Response Option | Enter Text.
31 | Shape Environment for Competitive Bidding | Implementation Techniques | Effectively use industry forums, requests for information, one-on-one meetings with interested stakeholders, partnering sessions, and other communication and collaboration mechanisms to remove barriers to participation and reduce the cost of pursuit for potential private-sector partners. | Response Option | Enter Text.
32 | Consider Economies of Scale | Strategic Goals | Consider the potential advantages of Economies of Scale in delivering EV charging infrastructure projects. | Response Option | Enter Text.
33 | Consider Economies of Scale | Tactical Approaches | Leverage opportunities for bundling projects that otherwise would be delivered in multiple segments over a much more extended period. | Response Option | Enter Text.
34 | Consider Economies of Scale | Tactical Approaches | Leverage existing resources and deliver additional EV charging infrastructure projects. | Response Option | Enter Text.
35 | Consider Economies of Scale | Implementation Techniques | Reduce costs related to upfront analysis, procurement, construction startup, and closeout for a portfolio of ECV charging infrastructure projects using a P3 bundling approach. | Response Option | Enter Text.
36 | Create Single Point of Responsibility | Strategic Goals | Benefit from a single point of responsibility in project delivery. | Response Option | Enter Text.
37 | Create Single Point of Responsibility | Tactical Approaches | Explicitly hold one entity accountable for all the required services throughout the lifecycle of the EV charging infrastructure project. | Response Option | Enter Text.
38 | Create Single Point of Responsibility | Implementation Techniques | Structure the P3 procurement and contracting to hold a single P3 agreement vs. multiple contracts for design, construction, financing, and O&M services. | Response Option | Enter Text.
39 | Facilitate Long-Term Contracting | Strategic Goals | Facilitate long-term, performance-based contracting. | Response Option | Enter Text.
40 | Facilitate Long-Term Contracting | Tactical Approaches | Refrain from defining prescriptive solutions (i.e., identifying all the inputs, plans, and specifications common in traditional delivery). | Response Option | Enter Text.
41 | Facilitate Long-Term Contracting | Tactical Approaches | Hold the private-sector developers accountable for the long-term performance of the constructed system. | Response Option | Enter Text.
42 | Facilitate Long-Term Contracting | Implementation Techniques | Transfer all the design liability risk to the P3 development team and hold the P3 developer accountable for meeting all the design criteria and performance requirements. | Response Option | Enter Text.
43 | Facilitate Long-Term Contracting | Implementation Techniques | Define specific performance measures to focus on actual outputs during the operations & maintenance phase of the project (i.e., identifying specific performance related to the desired level of service [LOS], for example, a minimum of 97% uptime for each charging port). | Response Option | Enter Text.
44 | Minimize Lifecycle Costs | Strategic Goals | Minimize the project lifecycle costs (i.e., Enhance lifecycle cost efficiencies) | Response Option | Enter Text.
45 | Minimize Lifecycle Costs | Tactical Approaches | Utilize the inherent strengths of the P3 model to achieve a minimum life cycle cost (Since the same investors are responsible for design, construction, and O&M, they are inherently incentivized to design and construct the facility). | Response Option | Enter Text.
46 | Minimize Lifecycle Costs | Implementation Techniques | Provide incentives to P3 developers to propose technical solutions going beyond the minimum design performance and construction quality requirements. | Response Option | Enter Text.
47 | Minimize Lifecycle Costs | Implementation Techniques | Encourage the P3 developer to partner with competent O&M subcontractors and equipment manufacturers to achieve optimal life cycle cost and enhanced level of service. | Response Option | Enter Text.
48 | Consider Non-Price Factors | Strategic Goals | Consider other important factors besides the price in selecting partners and evaluating their proposed ideas. | Response Option | Enter Text.
49 | Consider Non-Price Factors | Tactical Approaches | Develop an effective project acquisition strategy going beyond the traditional hard-bid procurement through utilizing qualifications-based selection (QBS) and best-value selection (BVS) procurement methods in a single-phase or two-phase procurement. (The first phase is the request for qualifications [RFQ] phase and the second phase is the request for proposal [RFP] phase). | Response Option | Enter Text.
50 | Consider Non-Price Factors | Tactical Approaches | Consider team qualifications and experience of key personnel (e.g., project manager, construction manager, electrician, operations and maintenance manager) as an integral component of the procurement of the EV charging infrastructure project. | Response Option | Enter Text.
51 | Consider Non-Price Factors | Implementation Techniques | Shortlist the most highly qualified partners (typically three teams) to move to the second phase to develop competitive technical and price proposals. | Response Option | Enter Text.
52 | Consider Non-Price Factors | Implementation Techniques | That depending on the project’s needs, the agency’s requirements, and the procurement duration constraints, the P3 procurement can be structured in a single phase where the P3 team’s qualifications, and proposed technical solutions and price are all evaluated in a single-phase RFP (sometimes noted as Request for Qualifications and Proposal [RFQ/P]). | Response Option | Enter Text.
53 | Consider Non-Price Factors | Implementation Techniques | Request detailed information about a prior recent experience of the key team members if available in completing the installation or operation of EV charging stations and use the past experience as a main criterion in selecting the most highly qualified P3 partner. | Response Option | Enter Text.
54 | Consider Non-Price Factors | Implementation Techniques | Require the adequate availability of key personnel to fulfill their responsibilities once the P3 contract is executed. | Response Option | Enter Text.
55 | Consider Non-Price Factors | Implementation Techniques | Require Electric Vehicle Infrastructure Training Program (EVITP) for electricians in the team. | Response Option | Enter Text.
56 | Consider Non-Price Factors | Implementation Techniques | Use experience and expertise in construction safety, environmental compliance, proactive utility coordination, and public involvement as examples of the main criteria for evaluating the qualifications of the key personnel in the proposed P3 team. | Response Option | Enter Text.
57 | Consider Non-Price Factors | Implementation Techniques | Incentivize the prospective P3 partners to provide their best solutions for addressing a wide range of project issues (e.g., construction safety, excellence in operations and maintenance, including safety, warranty, and routine maintenance, security, equitability, and accessibility to the site, and traffic patterns and ingress/egress considerations) | Response Option | Enter Text.
58 | Avoid Technology Risk | Strategic Goals | Do not accept any risk of new, rapidly evolving EV charging technology to the private-sector partners. | Response Option | Enter Text.
59 | Avoid Technology Risk | Tactical Approaches | Transfer the risk of technology deployment through an output and performance-based approach without accepting any risk for detailed design and technology deployment. | Response Option | Enter Text.
60 | Avoid Technology Risk | Implementation Techniques | Utilize the P3 contracting vehicle to use the private-sector expertise in the areas that the agency does not have internal expertise in design, construction, operations, and maintenance of the EV charging infrastructure. | Response Option | Enter Text.
61 | Optimize Allocation of Risks to Maximize Public Value | Strategic Goals | Do not accept project risks that compromise obtaining the best value for the public. | Response Option | Enter Text.
62 | Optimize Allocation of Risks to Maximize Public Value | Tactical Approaches | Utilize the P3 model to transfer project risks throughout the lifecycle of EV charging infrastructure projects (i.e., transfer risks related to design, construction, equipment procurement, installation, financing, availability, performance, O&M, and commercialization/revenue). | Response Option | Enter Text.
63 | Optimize Allocation of Risks to Maximize Public Value | Implementation Techniques | Encourage P3 developers to save money in design, construction, installation, operations and maintenance of project sites through implementing a more effective and integrated risk management system. | Response Option | Enter Text.
64 | Flexibility for Site Selection | Strategic Goals | Provide flexibility for site selection to benefit from the private sector’s real estate assets (i.e., open site selection). | Response Option | Enter Text.
65 | Flexibility for Site Selection | Tactical Approaches | Give the P3 developer as much freedom as possible to approach each installation site. | Response Option | Enter Text.
66 | Flexibility for Site Selection | Tactical Approaches | Provide the right incentives for the Performance Based P3 developer to encourage using a smart approach for site selection and preparation. | Response Option | Enter Text.
67 | Flexibility for Site Selection | Implementation Techniques | Ensure the selected Performance Based P3 developer confirms meeting all the project site minimum requirements: | Response Option | Enter Text.
68 | Flexibility for Site Selection | Implementation Techniques | Evaluate the P3 developer’s proposed plan for any applicable site development needs, including plans for site lease, site construction, or other site preparation other than electric power-related preparation. | Response Option | Enter Text.
69 | Flexibility for Site Selection | Implementation Techniques | Evaluate the P3 developer’s proposed plan for any permits (e.g., air/land electrical, structural, zoning, local agency, and environmental) or other approvals that are required to complete this Project and the status of each permit and anticipated timeline to obtain approval. | Response Option | Enter Text.
70 | Flexibility for Site Selection | Implementation Techniques | Evaluate the P3 developer’s proposed plan for providing communications networking capabilities at the proposed project site. | Response Option | Enter Text.
71 | Flexibility for Site Selection | Implementation Techniques | Evaluate the P3 developer’s identification of major project risks and its proposed risk mitigation strategies in several areas, related to existing or planned roads, buildings, or other infrastructure. | Response Option | Enter Text.
72 | Flexibility for Site Selection | Implementation Techniques | Evaluate the P3 developer’s proposed project site location through the assessment of the following information items from the proposed project site layout: | Response Option | Enter Text.
73 | Flexibility for Site Selection | Implementation Techniques | a) All existing buildings, structures, and amenities | Response Option | Enter Text.
74 | Flexibility for Site Selection | Implementation Techniques | b) Existing and proposed designated charging parking spaces | Response Option | Enter Text.
75 | Flexibility for Site Selection | Implementation Techniques | c) Electric vehicle supply equipment (EVSE) | Response Option | Enter Text.
76 | Flexibility for Site Selection | Implementation Techniques | d) Electric service distribution lines and utility connection build-out to the project site | Response Option | Enter Text.
77 | Flexibility for Site Selection | Implementation Techniques | e) Utility connection equipment (e.g., power meter, transformer, and switch gear) | Response Option | Enter Text.
78 | Flexibility for Site Selection | Implementation Techniques | f) Signage, marking, and striping | Response Option | Enter Text.
79 | Flexibility for Site Selection | Implementation Techniques | g) Vehicle and pedestrian points of access | Response Option | Enter Text.
80 | Flexibility for Site Selection | Implementation Techniques | h) Space (if any) available for future use | Response Option | Enter Text.
81 | Flexibility for Site Selection | Implementation Techniques | i) Americans with Disabilities Act (ADA) access | Response Option | Enter Text.
82 | Flexibility for Site Selection | Implementation Techniques | j) Lighting and security features | Response Option | Enter Text.
83 | Flexibility for Site Selection | Implementation Techniques | k) All other planned and proposed amenities | Response Option | Enter Text.
84 | Flexibility for Site Selection | Implementation Techniques | Evaluate the appearance of the P3 developer’s proposed project site, including height, width, color, and other visual features of the following items: | Response Option | Enter Text.
85 | Flexibility for Site Selection | Implementation Techniques | a) Existing and proposed designated charging parking spaces | Response Option | Enter Text.
86 | Flexibility for Site Selection | Implementation Techniques | b) Electric Vehicle Supply Equipment (EVSE) | Response Option | Enter Text.
87 | Flexibility for Site Selection | Implementation Techniques | c) Signage, marking, and striping | Response Option | Enter Text.
88 | Flexibility for Site Selection | Implementation Techniques | d) Lighting and security features | Response Option | Enter Text.
89 | Flexibility for Site Selection | Implementation Techniques | e) All other planned and/or proposed amenities | Response Option | Enter Text.
90 | Flexibility for Site Selection | Implementation Techniques | Evaluate the P3 developer’s proposed means and methods of EVSE installation for the project site including the anticipated depth and width of trenching for the following items: | Response Option | Enter Text.
91 | Flexibility for Site Selection | Implementation Techniques | a) EVSE footing and foundations | Response Option | Enter Text.
92 | Flexibility for Site Selection | Implementation Techniques | b) Power meter, transformer, switchgear footing, and foundations | Response Option | Enter Text.
93 | Flexibility for Site Selection | Implementation Techniques | c) Power utility, power lines, and cables connecting EVSE to the electrical grid | Response Option | Enter Text.
94 | Promote Sustainability | Strategic Goals | Promote sustainability in the development of EV charging infrastructure. | Response Option | Enter Text.
95 | Promote Sustainability | Tactical Approaches | Encourage the P3 developer to consider innovative sustainability features in their proposed project site. | Response Option | Enter Text.
96 | Promote Sustainability | Implementation Techniques | Provide incentives to the P3 developer during the procurement and contracting phases to consider using distributed energy resources like solar arrays and stationary batteries (e.g., onsite battery storage). | Response Option | Enter Text.
97 | Supply Chain Distributions | Strategic Goals | Minimize supply chain disruptions and get ahead of workforce shortages. | Response Option | Enter Text.
98 | Supply Chain Distributions | Implementation Techniques | Partners for EV charging infrastructure projects. | Response Option | Enter Text.
99 | Supply Chain Distributions | Implementation Techniques | Utilize the private partners’ resources and knowledge to better schedule the program delivery and expedite early procurement packages, considering substantial uncertainties in the availability of skilled labor and key equipment in the evolving EV charging station market. | Response Option | Enter Text.
100 | Facilitate Contingency Contracting | Strategic Goals | Facilitate contingency contracting. | Response Option | Enter Text.
101 | Facilitate Contingency Contracting | Tactical Approaches | Utilize a flexible contracting approach to award contingency Availability-based P3 contracts to the winning bidders and then enter into formal P3 agreements. | Response Option | Enter Text.
102 | Facilitate Contingency Contracting | Implementation Techniques | Formally contract with the winning bidders once the public agency has conducted and received environmental and real estate clearance on the proposed sites. | Response Option | Enter Text.
103 | Address Cybersecurity | Strategic Goals | Effectively address cybersecurity and safe data storing/sharing issues. | Response Option | Enter Text.
104 | Address Cybersecurity | Tactical Approaches | Take advantage of the private-sector expertise in collecting, harvesting, and analyzing data to track performance measures related to deploying EV charging infrastructure projects. | Response Option | Enter Text.
105 | Address Cybersecurity | Implementation Techniques | Use the P3 model to collect, store, and analyze the required data for tracking performance to ensure compliance with standards of access, sharing, reliability, convenience, and cybersecurity requirements. | Response Option | Enter Text.
106 | Address Cybersecurity | Implementation Techniques | Evaluate the P3 developer’s proposed approach on how to keep the collected data safe while being obtained, transferred, and stored following all federal and state cybersecurity requirements. | Response Option | Enter Text.
107 | Minimize Environmental Impacts | Strategic Goals | Minimize impacts to the surrounding environment. | Response Option | Enter Text.
108 | Minimize Environmental Impacts | Tactical Approaches | Hold the private partners accountable for upholding all federal and state environmental regulations in their site selection, site planning, and construction and operations management (i.e., transfer any potential environmental risks to the P3 developer). | Response Option | Enter Text.
109 | Minimize Environmental Impacts | Implementation Techniques | Conduct an initial environmental screening for the proposed project site to assess the overall environmental risk of the proposed project site and (possibly) the construction footprint for minor utility upgrades. | Response Option | Enter Text.
110 | Minimize Environmental Impacts | Implementation Techniques | Ensure that the developer clearly understands that any cost and schedule impacts associated with all environmental permitting and mitigation activities will be transferred to the P3 developer. | Response Option | Enter Text.
111 | Minimize Environmental Impacts | Implementation Techniques | Provide incentives in the P3 procurement and contracting process for the private-sector partners to innovate to minimize the environmental footprints (i.e., impacts) of the EV charging infrastructure project. | Response Option | Enter Text.
112 | Promote Local Development | Strategic Goals | Promote local economic development through investments in EV charging infrastructure sites. | Response Option | Enter Text.
113 | Promote Local Development | Tactical Approaches | Optimize economic development opportunities with suitable site placement. | Response Option | Enter Text.
114 | Promote Local Development | Implementation Techniques | Incentivize prospective P3 partners to place EV charging infrastructure sites in areas that support local businesses and generate additional economic growth and job opportunities. | Response Option | Enter Text.
115 | Ensure Opportunities for Local Firms | Strategic Goals | Ensure that EV charging infrastructure projects provide equitable opportunities to local, small firms. | Response Option | Enter Text.
116 | Ensure Opportunities for Local Firms | Tactical Approaches | Allow small and minority businesses from local communities to play a role in the EV charging infrastructure projects. | Response Option | Enter Text.
117 | Ensure Opportunities for Local Firms | Implementation Techniques | Encourage private developers to provide opportunities for disadvantaged business enterprises (DBEs) to participate in various phases of EV infrastructure projects from site development, design, construction, installation, operations, and maintenance. | Response Option | Enter Text.
118 | Enhance Public Involvement | Strategic Goals | Enhance public involvement and community engagement. | Response Option | Enter Text.
119 | Enhance Public Involvement | Tactical Approaches | Promote community awareness by facilitating collaborative project engagement and proactive stakeholder communications. | Response Option | Enter Text.
120 | Enhance Public Involvement | Implementation Techniques | Capitalize on the private-sector P3 partners’ expertise for public involvement and community engagement to build a supporting coalition in the community that is essential for the successful implementation of the EV charging infrastructure project. | Response Option | Enter Text.
121 | Address Demand Uncertainty | Strategic Goals | Effectively deal with commercialization issues and demand uncertainty. | Response Option | Enter Text.
122 | Address Demand Uncertainty | Tactical Approaches | Take advantage of the private sector’s business acumen and marketing experience to seek creative solutions to respond better to important issues related to understanding customer demand and its evolution, range anxiety, and willingness to pay. | Response Option | Enter Text.
123 | Address Demand Uncertainty | Implementation Techniques | Transfer the risk of meeting customer demands to the most qualified private sector partners capable of managing the revenue risk. | Response Option | Enter Text.
124 | Address Demand Uncertainty | Implementation Techniques | Whenever appropriate, provide minimum revenue guarantee (MRG) mechanisms in the P3 agreement to reduce the demand risk and attract more developers to participate in EV charging infrastructure development by establishing demand risk-sharing methods. | Response Option | Enter Text.
125 | Address Demand Uncertainty | Implementation Techniques | Whenever appropriate, identify revenue-sharing mechanisms to avoid cashflow rainfalls (i.e., windfall profits) and protect the public interest in the P3 agreement. | Response Option | Enter Text.
126 | Support Commercialization | Strategic Goals | Enhance the commercialization of EV infrastructure projects to make public investments more successful. | Response Option | Enter Text.
127 | Support Commercialization | Tactical Approaches | Take advantage of commercialization risk borne by the private-sector EVCI Performance-Based P3 partners. | Response Option | Enter Text.
128 | Support Commercialization | Tactical Approaches | Use the private sector’s expertise to build and grow the customer base and enhance customer satisfaction. | Response Option | Enter Text.
129 | Support Commercialization | Implementation Techniques | Provide incentives in the P3 procurement and contracting process to motivate private-sector P3 partners to select sites near existing amenities (e.g., shopping centers and eating establishments) and/or create additional amenities for customers. | Response Option | Enter Text.
130 | Support Commercialization | Implementation Techniques | Specify what enhancements and amenities are of high value for the public agency at the project site. | Response Option | Enter Text.
131 | Support Commercialization | Implementation Techniques | Ensure that the P3 developer recognizes that all associated costs related to project site enhancements and amenities are ineligible costs. | Response Option | Enter Text.
132 | Provide Secure Site | Strategic Goals | Provide a safe and secure EV charging station site. | Response Option | Enter Text.
133 | Provide Secure Site | Tactical Approaches | Transfer the risk of safe and secure construction and operations of the EV charging station project to the private-sector P3 partners. | Response Option | Enter Text.
134 | Provide Secure Site | Implementation Techniques | Evaluate the P3 developer’s plan regarding how the electric vehicle supply equipment (EVSE) equipment and supporting infrastructure will be hardened against damage or loss of service due to weather, transient surge voltages, traffic incidents, vandalism, or other environmental factors. | Response Option | Enter Text.
135 | Provide Secure Site | Implementation Techniques | Encourage the use of advanced technologies for monitoring and controlling the project site, its customers, and its equipment. | Response Option | Enter Text.
136 | Provide Secure Site | Implementation Techniques | Evaluate the P3 developer’s project site safety features for users and infrastructure safety equipment (e.g., site lighting, fire extinguisher, Automated External Defibrillator (AED), automatic safety shutoff, video cameras covering the site, and anti-vandalism equipment) | Response Option | Enter Text.
137 | Provide Secure Site | Implementation Techniques | Evaluate the P3 developer’s proposed plan for handling potential incidents during the construction and operations and management of the EV charging station site. | Response Option | Enter Text.
138 | Provide Secure Site | Implementation Techniques | Evaluate the P3 developer’s proposed plan for EV charging station access during times of emergency, such as evacuation during natural disasters. | Response Option | Enter Text.
139 | Provide Secure Site | Implementation Techniques | Evaluate the P3 developer’s safety plan for workforce training and the training approach for emergency service providers and host site owners. | Response Option | Enter Text.
140 | Require Private Equity Stake | Strategic Goals | Require the private partner to have an equity stake in the undertaking and therefore a vested interest in the success of the EV charging infrastructure project. | Response Option | Enter Text.
141 | Require Private Equity Stake | Tactical Approaches | Create a competitive procurement environment that encourages P3 developers to have skin in the game for the successful deployment and seamless operations of the EV charging infrastructure projects. | Response Option | Enter Text.
142 | Require Private Equity Stake | Tactical Approaches | Ensure the private partner in the P3 agreement clearly understands the distinction between Eligible and Ineligible Costs for Federally-funded projects. | Response Option | Enter Text.
143 | Require Private Equity Stake | Implementation Techniques | Explicitly spell out in the P3 procurement and contracting documents that the private developer only gets compensated up to a maximum of 80% of eligible costs and does not get compensated for the remaining 20% of demonstrated Eligible Costs, as well as any Ineligible Costs necessary to complete work. | Response Option | Enter Text.
144 | Address Utility Issues | Strategic Goals | Be proactive in addressing utility issues for the project site. | Response Option | Enter Text.
145 | Address Utility Issues | Tactical Approaches | Recommend that the P3 developer coordinate with Utility Owners for sufficient power and data communication availability for the proposed project site. | Response Option | Enter Text.
146 | Address Utility Issues | Tactical Approaches | Take advantage of all the risks for utility coordination, power connection, and data communication network availability to be borne by the Performance Based P3 developer at the proposed project site. | Response Option | Enter Text.
147 | Address Utility Issues | Implementation Techniques | Use proactive utility coordination experience and expertise as one of the main criteria for the evaluation of the qualifications of the key personnel in the team. | Response Option | Enter Text.
148 | Address Utility Issues | Implementation Techniques | Evaluate the electrical distribution service needs of the P3 developer’s proposed project site. | Response Option | Enter Text.
149 | Address Utility Issues | Implementation Techniques | Evaluate the P3 developer’s non-binding cost and schedule estimates for utility make-ready and interconnection work needed. | Response Option | Enter Text.
150 | Ensure Fair and Secure User Payments | Strategic Goals | Ensure fairness and security in user charge payments. | Response Option | Enter Text.
151 | Ensure Fair and Secure User Payments | Tactical Approaches | Hold the P3 partner accountable for the responsibility of providing secure, equitable, and accessible payment options. | Response Option | Enter Text.
152 | Ensure Fair and Secure User Payments | Implementation Techniques | Evaluate the reasonableness of the proposed rate structure for charging and methodology for assessing user fees (e.g., cost plus an appropriate profit rate, any additional cost at peak times, and any discounts to use the EV charging site). | Response Option | Enter Text.
153 | Ensure Fair and Secure User Payments | Implementation Techniques | For Federally-funded projects, ensure that the selected P3 partner confirms their proposed billing approach is consistent with billing practices outlined in the Federal Rule as per 23 CFR 680.106(m). | Response Option | Enter Text.
154 | Promote Long-Term Stewardship | Strategic Goals | Promote commitment to long-term stewardship. | Response Option | Enter Text.
155 | Promote Long-Term Stewardship | Tactical Approaches | Use the P3 business model as a first stepping stone for developing an EV charging site that will continue to serve the community beyond the duration of the P3 agreement. | Response Option | Enter Text.
156 | Promote Long-Term Stewardship | Implementation Techniques | Evaluate the proposed approach of the P3 developer to operate and maintain the facility longer than the minimum operating period required in the original P3 agreement. | Response Option | Enter Text.
157 | Facilitate Engagement with Site Owners | Strategic Goals | Facilitate engagement with prospective site owners. | Response Option | Enter Text.
158 | Facilitate Engagement with Site Owners | Tactical Approaches | Recommend that prospective Performance Based P3 developers discuss and negotiate with Host Site Owners regarding appropriate rights. | Response Option | Enter Text.
159 | Facilitate Engagement with Site Owners | Implementation Techniques | Request the P3 developer to submit the property owner’s affidavit for the proposed project site. | Response Option | Enter Text.
160 | Facilitate Engagement with Site Owners | Implementation Techniques | Ensure that the P3 developer understands that any arrangements with Host Site Owners must be on a non-exclusive basis and must not prevent other Proposers from agreeing to arrangements with other Host Site Owners. | Response Option | Enter Text.

## Glossary
Glossary
Acronym | Definition
DOT | Department of Transportation
EV | Electric Vehicle
EVCI | Electric Vehicle Charging Infrastructure
EVSE | Electric Vehicle Supply Equipment
FAST | Financial Analysis Tool for Electric Vehicle Charging Infrastructure using P3s
FHWA | Federal Highway Administration
NEVI | National Electric Vehicle Infrastructure
O&M | Operations & Maintenance
P3 | Public-Private Partnership
RFP | Request for Proposal
RFQ | Request for Qualification
STAT | EVCI Strategic Goals and Tactical Advance Tool
NTP | Notice to Proceed (NTP)