## Slide 1
Prof. J.J Lew, P.E.
Principal Investigator – Purdue Univ.
James H. Anspach, P.G.
Technical Advisor – So-Deep, Inc.
C. Paul Scott, P.E.
FHWA Advisor
Kevin Slack, P.E.
Highway Design Advisor – CH2M Hill

## Slide 2: The Federal Highway Administration (FHWA) commissioned Purdue University to study the effectiveness of subsurface utility engineering (SUE) as a means of reducing costs and delays on highway projects.
Previous studies and statements of cost savings were performed by various state DOTs, providers of SUE services, and the FHWA.
Commissioning Purdue University to conduct this study allowed for an independent and impartial review and study of costs savings.

## Slide 3: Four States were selected to participate
Virginia
North Carolina
Ohio
Texas

## Slide 4: Virginia DOT
Advantage
  Oldest program – started in 1986
  Most comprehensive use of SUE mapping in the country – every state DOT project gets QL B and QL A mapping
Disadvantage
  No recent database of claims / change orders due to not using QLB / QLA mapping

## Slide 5: North Carolina DOT
Advantage
  Program in development – used for approx 6 years
  Many projects to choose from
  Some system in place to track utility change orders / claims during construction
Disadvantage
  At that time, did not use QL A mapping, only QL B
  Mostly used on urban / suburban projects; few rural ones
  Designers typically got data late in their design process, so not used as effectively as possible

## Slide 6: OHIO DOT
Advantage
  Program in development – used for approx 4 years
  Aggressive program administrator kept track of past and present utility change orders / claims during construction
  Used both QL B and QL A mapping
Disadvantage
  Only used in several Districts – suburban in nature

## Slide 7: TEXAS DOT
Advantage
  New Program – used for only 2 years
  Recent history of past and present utility change orders / claims during construction
  Used both QL B and QL A mapping
  All types of projects
Disadvantage
  Most projects not yet in construction

## Slide 8: General Investigative Procedure
Pick projects as randomly as possible
Interview DOT personnel, SUE consultants, utility owners, contractors, and designers
Review state-wide utility claims histories
Review project plans / utility records in detail

## Slide 9: General Investigative Problems
Utility / DOT / Contractor personnel missing in action, retired, or unable to remember specifics
State DOT’s records of claims / change order history poor – usually worked out in “barter” by construction engineers or “hidden” in unrelated cost categories

## Slide 10: Developed checklist of 21 areas for potential project savings
Did not differentiate between savings to utility owner versus DOT

## Slide 11: Areas for Savings
Reduction in unforeseen utility conflicts and relocations;
Reduction in project delays due to utility relocates;
Reduction in claims and change orders
Reduction in delays due to utility cuts;
Reduction in project contingency fees;
Lower project bids;
Reduction in costs caused by conflict redesign;
Reduction in the cost of project design;
Reduction in travel delays during construction to the motoring public;
Improvement in contractor productivity and quality;
Reduction in utility companies’ cost to repair damaged facilities;

## Slide 12: Areas for Savings
Minimization of utility customers’ loss of service;
Minimization of damage to existing pavements;
Minimization of traffic disruption, increasing DOT public credibility;
Improvement in working relationships between DOT and utilities;
Increased efficiency of surveying activities by elimination of duplicate surveys;
Facilitation of electronic mapping accuracy;
Minimization of the chance of environmental damage;
Inducement of savings in risk management and insurance;
Introduction of the concept of a comprehensive SUE process;
Reduction in Right-of-Way acquisition costs.

## Slide 13: Many of these areas could not be quantified in the study

## Slide 14: The reductions in risk for projects utilizing SUE have been difficult to quantify. There are many variables and scenarios that may occur. Historical data is difficult to come by. Some savings are easily quantified; others may be qualitative or speculative in nature.
This study categorizes savings accordingly. These types of costs are:

## Slide 15: Exact costs that can be quantified in a precise manner.
Examples are costs much like the costs for test holes, the cost to eliminate construction and utility conflicts, or any other cost for which exact figures can be obtained.

## Slide 16: Estimated costs that are difficult to quantify, but can be calculated with a high degree of certainty.
These costs were estimated by studying projects in detail, interviewing the personnel involved in the project, and applying historical cost data.

## Slide 17: Costs that cannot be estimated with any degree of certainty due to a lack of data.
These are true qualitative costs and may in fact be significant to the real cost savings. These qualitative costs are not quantified in the evaluation study.
It is believed that the majority of savings fall into this category

## Slide 18: Therefore, the cost savings reflected from this study are a MINIMUM QUANTIFIABLE SAVINGS
True project savings are likely to be significantly higher than this study can prove.

## Slide 19: Study Results - Virginia
Studied 9 projects – total construction value of $42M
Costs savings of QL B / QL A mapping over QL D /QL C mapping was a minimum of 412%
project delivery time savings of 12 percent-15 percent
Quality level B mapping identifies an average of 10 percent - 50 percent more utilities than traditional mapping (QL D and QL C).

## Slide 20: Study Results – North Carolina
Studied 21 projects – total construction value of $205M
Costs savings of QL B mapping over QL D /QL C mapping was a minimum of 663%
SUE budget is approximately 2 % of the total state DOT budget for eng/ construction/
The majority of projects utilizing SUE showed no delays due to utility conflicts, an improvement over past data.

## Slide 21: Study Results – Ohio
Studied 14 projects – total construction value of $284M
Costs savings of QL B / QL A mapping over QL D /QL C mapping was a minimum of 521%
SUE was initially used to solve field utility conflict questions / Could be more effective if used earlier in design

## Slide 22: Study Results – Texas
Studied 28 projects – total construction value of $606M
Costs savings of QL B / QL A mapping over QL D /QL C mapping was a minimum of 427%
Projects only used on Interstate projects. Urban municipal projects not evaluated, but savings on these types of projects should be even more.

## Slide 23: From a study of 71 projects with a combined construction value in excess of $1 billion, the results indicated the effectiveness of the study was a total of $4.62 in savings for every $1.00 spent on SUE. The costs of obtaining QL B and QL A (except NCDOT) data on these 71 projects were 0.5 percent of the total construction costs, resulting in a construction savings of 1.9 percent by using SUE.
Qualitative savings were non-measurable, but it is clear that those savings are also significant and may be many times more valuable than the quantifiable savings.

## Slide 24: Only three of 71 projects had a negative return on investment
One individual project had a $206.00 to $1.00 return on investment (NCDOT).

## Slide 25: This leads to the conclusion that SUE should be used in a systemic manner, i.e. on virtually every project
Using the data from this study and given a national expenditure in 1998 of $51 billion for highway construction, the use of SUE in a systemic manner should result in a minimum national savings of approximately $1 billion per year.

## Slide 26: QL B / QL A mapping budgets should be approximately 1% of state DOT Eng/Constr Budget
This study shows a potential minimum stretching of project dollars by 4.62% if comprehensive QL B / QL A mapping is performed correctly.

## Slide 27: State DOTs and their consultants should integrate this SUE mapping with the pending ASCE / ANSI Standard
Standard Guidelines for the Collection and Depiction of Existing Subsurface Utility Data
Antic. Publish date - 2002